## Sheet1
| Report Date | Rig Name | Well No | Date and Time | Time in Hrs | Cummulative Hrs | LT ID | Parent LT ID | LT Type | Cause | Object | Company Name | Depth | LT Summary
0 | 06/21/2022 | ADC-43L | UTMN-3118 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
1 | 06/21/2022 | ADC-43L | UTMN-3118 | 19 Jun 0245 - 1700 | 12 | 38.25 | 898513 |  | WCNT | WCC8 | NA | TK3 | 10535 | OBSERVED INCREASE IN MPD RETURN FLOW. WELL FLOWING. SHUT-IN WELL ON RCD W/ 5 RPM. RECORD INITIAL SIDPP-1100 PSI, SICP - 1400 PSI, & PIT GAIN - 25 BBL.
2 | 06/21/2022 | ADC-55L | UTMN-3171 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
3 | 06/21/2022 | ADC-55L | UTMN-3171 | 21 Jun 1415 - 0500 | 14.25 | 14.25 | 898634 |  | WCNT | WC11 | NA | TK3 | 6243 | OBSERVED INCREASE IN FLOW OUT
4 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | DTU | DRFT | NSL | 16580 | 16580 |  |  | 3267 | R/U SLICK LINE & DRIFT. DRIFT WITH 2.347" TO 49 FT & DRIFT WITH 2.867" TO 35 FT AND TAG X/O.
5 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | SET | PLUGT | INW | 16580 | 16580 | 10 | 10 | 3267 | SLICK LINE SET INTERWELL PUMP DOWN THRU PLUG. CONFIRM PLUG SETTING BY SOFT S/O. POOH AND L/D SETTING TOOL. R/D SLICK LINE.
6 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | RPCS | SPCOM | TSC | 16580 | 16580 | 542 | 662 | 3267 | RIH ESP COMPLETION TO 662 FT ON 3-1/2" 9.3# J-55 EUE TUBING
7 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | OTH | PDHMS | HCO | 16580 | 16580 |  |  | 3267 | HANG CABLE SHEAVES ON MONKEY BOARD, PERFORMING DOWN HOLE ELECTRICAL INTEGRITY. P-P BALANCED: 6.9OHM, P-GROUND: 5 MIN READING 1.56G OHM & 10 MIN READING 2.17 G OHM
8 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | RPCS | SPCOM | TSC | 16580 | 16580 | 662 | 1562 | 3267 | RIH ESP COMPLETION TO 1,562 FT ON 3-1/2" 9.3# J-55 EUE TUBING
9 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | DTU | DRFT | NSL | 16580 | 16580 |  |  | 3267 | R/U SLICK LINE & DRIFT WITH 2.867" TO 1030 FT DEPTH AS PLANNED. R/D SLICKLINE EQUIPMENT. -MEANWHILE BAKER ERFORM DOWN HOLE ELECTRICAL INTEGRITY. P-P BALANCED: 7.0 HM, P-GROUND: 5 MIN READING 1.12G OHM & 10 MIN READING 2.0 G OHM.
10 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | RPCS | SPCOM | TSC | 16580 | 16580 | 1562 | 2789 | 3267 | RIH BAKER ESP COMPLETION TO 2,789 FT ON 3-1/2" 9.3# J-55 EUE TUBING.
11 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | RPCS | SPCOM | TSC | 16580 | 16580 | 2789 | 2800 | 3267 | P/U AND MAKE UP 4 FT 3-1/2" 9.3# J-55 EUE PUP JOINT+ X/O ( 4-1/2" 13.5# TENARIS TN-95HS 3SB X 3-1/2" 9.3# J-55 EUE) AND RIH TO 2800 FT
12 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | DTU | DRFT | NSL | 16580 | 16580 |  |  | 3267 | R/U SLICK LINE & DRIFT WITH 2.867" TO 1,300 FT DEPTH AS PLANNED. R/D SLICKLINE EQUIPMENT. - MEANWHILEBAKER PERFORM DOWN HOLE ELECTRICAL INTEGRITY. P-P BALANCED: 6.9 OHM, P-GROUND: 5 MIN READING 1.62 G OHM & 10 MIN READING 2.25 G OHM.
13 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | RPCS | SPCOM | TSC | 16580 | 16580 | 2800 | 3861 | 3267 | RIH BAKER ESP COMPLETION TO 3,861FT ON 4-1/2" 13.5# 3SB TUBING
14 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | DTU | DRFT | NSL | 16580 | 16580 |  |  | 3267 | R/U SLICK LINE & DRIFT WITH 3.795" TO 1,066 FT DEPTH AS PLANNED. R/D SLICKLINE EQUIPMENT. - MEANWHILE BAKER PERFORM DOWN HOLE ELECTRICAL INTEGRITY. P-P BALANCED: 7.0 OHM, P-GROUND: 5 MIN READING 1.42 G OHM & 10 MIN READING 2.04 G OHM
15 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | RPCS | SPCOM | TSC | 16580 | 16580 | 3861 | 4828 | 3267 | RIH BAKER ESP COMPLETION TO 4,828 FT ON 4-1/2" 13.5# 3SB TUBING
16 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | DTU | DRFT | NSL | 16580 | 16580 |  |  | 3267 | R/U SLICK LINE & DRIFT WITH 3.795" TO 1,008 FT DEPTH AS PLANNED. R/D SLICKLINE EQUIPMENT. - MEANWHILE BAKER PERFORM DOWN HOLE ELECTRICAL INTEGRITY. P-P BALANCED: 7.0 OHM, P-GROUND: 5 MIN READING 1.62 G OHM & 10 MIN READING 2.25 G OHM
17 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | RPCS | SPCOM | TSC | 16580 | 16580 | 4828 | 5802 | 3267 | RIH BAKER ESP COMPLETION TO 5,802 FT ON 4-1/2" 13.5# 3SB TUBING
18 | 06/21/2022 | ADC-57L | FDHL-158 | C | COMP | DTU | DRFT | NSL | 16580 | 16580 |  |  | 3267 | R/U SLICK LINE & DRIFT WITH 3.795" TO 1,015 FT DEPTH AS PLANNED. ON GOING AT RT. - CONTINUOUSLY PUMP 70 PCF BRINE INTO ANNULUS AT 2 BPM FROM TRIP TANK DURING ALL PAST OPERATION, WELL IN TOTAL LOSSES.
19 | 06/21/2022 | ADC-57L | FDHL-158 | DOOS ID | Type | Category | Out of Scope Summary | 19 Jun 0030 | 24 | 60 | 3267 | OOS | SMCM | RUN PDHMS & ESP COMPLETION.
20
21
22 | 06/21/2022 | ADC-62L | ANDR-745 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
23 | 06/21/2022 | ADC-62L | ANDR-745 | 18 Jun 0100 - 0500 | 24 | 76 | 898471 |  | STUK | STDP | DP | RIG | 9094 | DRILL STRING STUCK.
24 | 06/21/2022 | ADC-67L | SDGM-1265 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
25 | 06/21/2022 | ADC-67L | SDGM-1265 | 20 Jun 1600 - 0430 | 23.5 | 36.5 | 898518 |  | BHA | FOT | RSS | SDM | 12443 | RSS NOT RESPOND, PERFORMED TROUBLE SHOOTING. NO SUCCESS.
26 | 06/21/2022 | ADES-14 | HWYH-530 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
27 | 06/21/2022 | ADES-14 | HWYH-530 | 21 Jun 1830 - 2000 | 1.5 | 1.5 | 898521 |  | TF | XTTE | CRT | GOC | 10635 | EXCESS TIME DUE TO POOR HANDLING EQUIPMENT
28 | 06/21/2022 | ADES-158 | ABQQ-736 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
29 | 06/21/2022 | ADES-158 | ABQQ-736 | 20 Jun 1730 - 0500 | 16.5 | 26.5 | 898654 | 897478 | JF | HERR | STRG | RIG | 5206 | HAD OBSTRUCTION @ 5206' WHILE RIH WITH BAKER DIR BHA.
30 | 06/21/2022 | ADM-337 | MRJN-900 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
31 | 06/21/2022 | ADM-337 | MRJN-900 | 18 Jun 0100 - 0500 | 24 | 68.5 | 898514 |  | TF | ISEQ | SB | SLL | 11365 | UNABLE TO PASS TOL WITH SCHLUMBERGER W/LINE TOOLS CBL & USIT
32 | 06/21/2022 | ADM-656 | SFNY-396 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
33 | 06/21/2022 | ADM-656 | SFNY-396 | 19 Jun 0945 - 2145 | 16.75 | 60 | 898490 |  | TF | FOT | ESPL | SBA | 2368 | OBSERVED UNBALANCED PHASE TO PHASE READINGS ON ESP ELECTRICAL CABLE AT 2,368 FT. DECISION MADE TO POH AND CHANGE OUT ESP CABLE.
34 | 06/21/2022 | AOD-111 | MRJN-724 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
35 | 06/21/2022 | AOD-111 | MRJN-724 | 20 Jun 2100 - 1715 | 11 | 18 | 898595 |  | LCIR | UVLC | NA | ARM | 16052 | OBSERVED LOSSES IN RATAWI RESRV 150 BPH
36 | 06/21/2022 | ARO-4001 | MRJN-538 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
37 | 06/21/2022 | ARO-4001 | MRJN-538 | 21 Jun 2015 - 2315 | 3 | 3 | 898522 |  | RR | FOT | TDS | RIG | 16171 | REPAIRED LEAKING WATER COOLING HOSE IN TDS MOTOR.
38 | 06/21/2022 | CG-1 | ZULF-1201 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
39 | 06/21/2022 | CG-1 | ZULF-1201 | 09 Jun 2300 - 0500 | 24 | 293.5 | 897833 |  | STUK | STCT | SCRN | ARM | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
40 | 06/21/2022 | NA-207S | SHYB-132 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
41 | 06/21/2022 | NA-207S | SHYB-132 | 21 Jun 1330 - 1530 | 2 | 2 | 898519 |  | RR | FOT | ACDC | RIG | 4327 | OBSERVE FAULTY ENGINE CONTROL MODULE (AC MODULE).
42 | 06/21/2022 | NBR-16S | HMYM-433114 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
43 | 06/21/2022 | NBR-16S | HMYM-433114 | 21 Jun 0845 - 1245 | 4 | 4 | 898658 |  | JF | XTRI | NA | RIG | 0 | EXCESSIVE TIME TO MAKE UP BHA, TROUBESHHOTING AND REPLACING MANUAL TONGS & JAWS, IRON ROUGHNECK NOT WORKING)
44 | 06/21/2022 | NBR-263S | QTIF-736 | 20 Jun 0500 - 1430 | 9.5 | 26 | 898597 |  | LCIR | UVLC | NA | ARM | 8307 | WHILE DRLG START FROM 8200' TO 8307' (ARAB B), OBSERVE LOSSES 30 TO 40 BPH. DECREASE FLOW RATE FROM 550 GPM TO 250 GPM OBSERVE NO LOSSES.
45 | 06/21/2022 | NBR-263S | QTIF-736 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
46 | 06/21/2022 | NBR-263S | QTIF-736 | 21 Jun 1830 - 0500 | 10.5 | 10.5 | 898523 |  | WCNT | WC20 | NA | ARM | 8541 | WHILE WASH & REAM PRIOR CONNECTION OBSERVE INCREASE IN ACTIVE MUD TANKS. STOP PUMP & FLOW CHECK OBSERVE WELL FLOWING, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=160 PSI, PUMP OUT FLOAT VALVE AND OBSERVE SIDPP=70 PSI. - LINE UP TO TRIP TANK AND BLEED OFF PRESS 50 PSI, CLOSE CHOKE OBSERVE PRESS BUILD UP. - KILL WELL WITH DRILLER METHOD.
47 | 06/21/2022 | NBR-263S | QTIF-736 | 20 Jun 0500 - 1430 | 9.5 | 26 | 898597 |  | LCIR | UVLC | NA | ARM | 8307 | WHILE DRLG START FROM 8200' TO 8307' (ARAB B), OBSERVE LOSSES 30 TO 40 BPH. DECREASE FLOW RATE FROM 550 GPM TO 250 GPM OBSERVE NO LOSSES.
48 | 06/21/2022 | NBR-783S | NJYN-93 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
49 | 06/21/2022 | NBR-783S | NJYN-93 | 17 Jun 1400 - 0500 | 6.25 | 54.75 | 898442 |  | UPRA | GRF | TDS | RIG | 395 | LOST TDS COMMUNICATION, BLOWER MOTOR FAILED.
50 | 06/21/2022 | PA-70S | MDRK-64 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
51 | 06/21/2022 | PA-70S | MDRK-64 | 30 May 1800 - 0500 | 24 | 527.5 | 897183 |  | TF | FOT | LLAP | WLH | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
52 | 06/21/2022 | RM-74A | HSBH-68 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
53 | 06/21/2022 | RM-74A | HSBH-68 | 14 Jun 1300 - 1700 | 12 | 170 | 898171 |  | UPRA | GRF | RWCS | RIG | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
54 | 06/21/2022 | SA5898 | MDRK-57 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
55 | 06/21/2022 | SA5898 | MDRK-57 | 20 Jun 0000 - 0300 | 22 | 27 | 898574 |  | TF | FOT | SLIPS | RIG | 15500 | DROP IN HOLE 2 DIES OF 4-3/4" DC SLIPS.
56 | 06/21/2022 | SCTD-2 | HRDH-2307 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
57 | 06/21/2022 | SCTD-2 | HRDH-2307 | 21 Jun 1730 - 1830 | 1 | 1 | 898520 |  | MUD | HPMR | NA | RIG | 14992 | FAILURE IN THE ELECTRIC PUMP, REPLACE SUCTION PUMP & CLEAN SAME.
58 | 06/21/2022 | SINO-12L | HRDH-400 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
59 | 06/21/2022 | SINO-12L | HRDH-400 | 19 Jun 2230 - 0800 | 3 | 33.5 | 898505 |  | TF | FOT | LINR | TK1 | 7170 | UNABLE TO SET OFF-BTM LINER DUE STRING LEAK.
60 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | RPCS | UPCOM | ITS | 11380 | 11380 | 2300 | 2824 |  | RIH 4-1/2" UPPER COMPLETION WHILE P/U 4-1/2" 11.6# J-55 N.VAM TBG F/ 2300 FT T/ 2824 FT (66 /129 JTS).
61 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | DTU | DRFT | HSL | 11380 | 11380 |  |  |  | HPJSM, R/U HSL PCE , P/T PCE TO 1500 PSI-OK , RIH W/ 3.875" DRIFT TILL TAG UPPER "X" NIPPLE @ 2589 FT.
62 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | TI | TBG | RIG | 11380 | 11380 | 2824 | 5414 |  | RIH W/ 7" HCO 'VHR' PKR & TAIL PIPE ASSY ON 4-1/2" 11.6# J-55 NVAM TBG TO 5417 FT (129/129 JTS ).
63 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | HT | PKR | HCO | 11380 | 11380 |  |  |  | CONFIRMED TAG BOTTOM OF TBR, OK. P/U STRING AND SPACE OUT.- TUBING END 7 FT INSIDE TBR @ 5414 FT, PACKER ON SETTING DEPTH @ 5254 FT.
64 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | SET | PLUGN | HSL | 11380 | 11380 | 5424 | 5424 |  | R/U S/L BOP & LUBRICATOR, P/T SAME TO 1500 PSI.- S-LINE RIH WITH 3.875'' DRIFT, RIH T/ 3070 FT. & POOH.- S-LINE RIH WITH 3.5" GC T/ 6500 FT. POOH.- S-LINE RIH AND SET PXN PLUG IN XN NIPPLE BELOW THE PACKER @ 5363 FT (3 RUNS)- PRESS TEST TUBING TO 300 PSI- S-LINE RIH AND SET JUNK TRAPPER ABOVE PXN NIPPLE- POOH, AND R/D S-LINE LUBRICATOR
65 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | OTH | SFLN | RIG | 11380 | 11380 |  |  |  | P/T SURFACE LINES TO 4,000 PSI, OK. M/U XO & 4" PUP JT, CONNECT TDS.
66 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | PTST | SEAL | RIG | 11380 | 11380 |  |  |  | SPACE OUT STRING IN PACKER IN FINAL SETTING POSITION. SET HES 7" VHR PACKER @ 5254 FT BY PRESSURE UP TBG TO 2200 PSI, HOLD 10MIN; S/O 40 KLB (CONFIRM PKR SET) AND PRESS UP TO 3500 BY 10 MIN, HOLD OK. BLEED OFF PRESS AND P/U STRING W/10 KLB O/P, OK.CLOSE ANNULAR BOP, KEEP TBG SIDE OPEN, P/T TCA TO 1,000 PSI, FOR 10 MIN. OK.PRESSURE UP STRING TO 2200 PSI, SHEAR SEAL ASSEMBLY W/ 40 K.LB O/P; BLEED OFF PRESSUREP/U STRING 4 FT, FREE, SLACK OFF AND LAND LOCATOR SUB ON TOP OF PKR. P/U 4 FT TO LANDING POSITION.CLOSE ANNULAR BOP, KEEP TBG SIDE OPEN, P/T TCA TO 1,000 PSI, FOR 10 MIN, HOLD OK, P/T TBG SIDE TO 1000 PSI -OK.
67 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | OTH | SEAL | HCO | 11380 | 11380 |  |  |  | SPACE OUT & L/D 6 JTS X 4.5'' N.VAM TBG + 2 TBG PUP JTS
68 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | HT | SSSV | BC | 11380 | 11380 |  |  | 3305 | P/U & M/U 4.5'' BHI TR-SSSV, CONNECT CONTROL LINE & P/T SAME TO 6500 PSI FOR 30 MIN, OK.
69 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | OTH | SEAL | HCO | 11380 | 11380 |  |  |  | CONT. RIH W/ 4.5'' TBG JTS AS PER TALLEY, M/U 4-1/2" X 11'' N.VAM TBG HANGER.
70 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | DTU | DRFT | HSL | 11380 | 11380 |  |  |  | R/U S/L, P/T LUBRICATOR AND BOP TO 1,500 PSI, OK, S/L RIH 3.875" TO 200 FT, R/D S/L.
71 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | CIRC | MPMP | RIG | 11380 | 11380 |  |  |  | HPJSM , M/U FOSV W/ LANDING JT , DISPLACE TBG & TCA WITH 300 BBL 1% COAT-415 INHIBITED DIESEL IN STAGES & FLOW CHECKS ( MAX 1060 PRESS PSI @ 3 BPM ) VIA CHOKE.
72 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | CIRC | MPMP | RIG | 11380 | 11380 |  |  | 3305 | TERMINATE TR-SSSV C/L THROUGH TBG HGR & P/T C/L INTEGRITY, OK
73 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | CIRC | MPMP | RIG | 11380 | 11380 |  |  |  | CLOSED ANNULUAR, DISPLACE TBG & TCA WITH 300 BBL 1% COAT-415 INHIBITED DIESEL IN STAGES & FLOW CHECKS ( MAX 1060 PRESS PSI @ 3 BPM ) VIA CHOKE.
74 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | CIRC | MPMP | RIG | 11380 | 11380 |  |  |  | FLOW CHECK FOR 30 MIN, WELL STATIC
75 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | HT | SEAL | HCO | 11380 | 11380 |  |  |  | STING SEAL ASSEMBLY INTO PBR & LAND TBG HANGER, TIGHTEN LDS.EOT @ 5414 FT, "XN" NIPPLE @ 5366 FT , LOWER "X" NIPPLE @ 5312 FT , '7" VHR PKR @ 5254 FT, UPPER "X" NIPPLE @ 5169 FT.
76 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | PTST | SEAL | RIG | 11380 | 11380 |  |  |  | P/T TCA W/ DIESEL TO 1500 PSI-OK, P/T TBG W/ DIESEL TO 1500 PSI- OK.
77 | 06/21/2022 | SINO-15L | ANDR-482 | C | COMP | SET | PLUGT | HSL | 11380 | 11380 | 225 | 225 |  | HPJSM, R/U S/L PCE, PT TO 2500 PSI, OK. RIH & SET 4-1/2" MONOLOCK @ 225' ,P/T MONOLOCK TO 2500 PSI-OK, R/D HES S/L.
78 | 06/21/2022 | SINO-15L | ANDR-482 | C | BOP | BOP | BOP | RIG | 11380 | 11380 |  |  |  | N/D BELL NIPPLE & FLOW LINE, N/D CLASS "A" 13-5/8" 5M BOPE & RELATED EQUIPMENT .... ON GOING @ RPT
79 | 06/21/2022 | SINO-15L | ANDR-482 | DOOS ID | Type | Category | Out of Scope Summary | 21 Jun 1930 | 1.5 | 1.5 | 3305 | OOS | OTHR | M/U TRSSSV.
80
81
82 | 06/21/2022 | SINO-19L | UTMN-232 | N | DRLG | LDP | BHA | RIG | 6880 | 6880 | 70 | 0 |  | HPJSM, L/D 6-1/8" MTR/MWD/LWD BHA.
83 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | OTH | NA | HWP | 6880 | 6880 |  |  | 3245 | (OOS) HPJSM. P/U & M/U HES W/ TLC TRIPLE COMBO/DIELECTRIC/MSFL LOGGING TOOL STRING + X-O FOR 4"DP.>> FUNCTION TEST TOOLS, OK.
84 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | ST | STDP | RIG | 6880 | 6880 | 106 | 5255 | 3245 | (OOS) RIH W/ TLC TRIPLE COMBO/DIELECTRIC/MSFL LOGGING TOOLS @ CONTROLLED SPEED ON 4" DP/HWDP TO 5255'.>>KEEP MONITOR WELL ON TRIP TANK - STATIC>>DRIFTED 4" DP/HWDP WITH 2.25" SIZE WHILE RIH. >>FILLED STRING EVERY 10 STANDS W/ 86 PCF MUD USING W/L CIRC SUB & SCREEN.
85 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | OTH | NA | HWP | 6880 | 6880 |  |  | 3245 | (OOS) R/U HALL W/L SHEAVES, CIRC, M/U HES WL SIDE ENTRY SUB & CIRC SUB WITH MUD SCREEN. >>RIH WITH W/L CABLE 300 FT ABOVE TOOL-HEAD. >>LATCHED ON WET CONNECTOR. CHECKED SIGNAL, OK.
86 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | OTH | NA | HWP | 6880 | 6880 |  |  | 3245 | (OOS) INSTALLED CABLE CLAMP & PERFORMED PULL TEST, OK.
87 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | ST | STDP | RIG | 6880 | 6880 | 5255 | 6860 | 3245 | (OOS) CONT RIH W/ HES TRIPLE COMBO/DIELECTRIC/MSFL LOGGING TOOLS ON DRIFTED 4" DPS F/ 5255 FT TO 6860' (20' OFF BOTTOM).>> FILL STRING EVERY 15 STANDS.
88 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | LOG | WLT | HWP | 6880 | 6880 | 6860 | 6660 | 3245 | (OOS) HES ACTIVATED TOOLS & LOGGED UP REPEAT PASS WITH TRIPLE COMBO/DIELECTRIC/MSFL OH LOGGING TOOLS ON 4" DP F/ 6860' T/ 6660' AS PER RDD.
89 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | LOG | WLT | HWP | 6880 | 6880 | 6860 | 5860 | 3245 | (OOS) HES RIH BACK TO 6860' & ACTIVATED TOOLS & LOGGED UP MAIN PASS WITH TRIPLE COMBO/DIELECTRIC/MSFL OH LOGGING TOOLS ON 4" DP F/ 6860' T/ 5860'.
90 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | ST | STDP | RIG | 6880 | 6880 | 5860 | 5255 | 3245 | (OOS) POOH W/TLC TRIPLE COMBO/DIELECTRIC/MSFL LOGGING TOOLS ON 4" DP STD'S F/ 5860' T/ 5255'.>>KEEP MONITOR WELL ON TRIP TANK - STATIC.>>PROCCESSED LOGS & SENT DATA TO RDD
91 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | OTH | NA | HWP | 6880 | 6880 |  |  | 3245 | (OOS) HES WL UNLATCHED FROM WET CONNECTOR.>> POOH WITH W/L CABLE TO SURFACE.>> RIG DOWN HES WL SHEAVES & SPLIT BUSHING.
92 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | TO | STDP | RIG | 6880 | 6880 | 5255 | 106 | 3245 | (OOS) POOH HES MSFL / DIELECTRIC LOGGING TOOLS ON 4" DP STD'S TO SURFACE. >>KEEP MONITOR WELL ON TRIP TANK - STATIC
93 | 06/21/2022 | SINO-19L | UTMN-232 | E | LOG | OTH | NA | HWP | 6880 | 6880 |  |  | 3245 | (OOS) L/D HES WIRELINE LOOGING TOOLS.
94 | 06/21/2022 | SINO-19L | UTMN-232 | N | CT | HT | BHA | RIG | 6880 | 6880 |  |  |  | HPJSM, P/U & M/U 6-1/8" STIFF REAMING BHA AS FOLLOWS:>> 6-1/8" WELDED TRI-CONE BIT + 6-1/8" NEAR BIT REAMER WITH FLOAT VALVE + 1 JT X 4-3/4" D/C + 6-1/8" STRING REAMER + 1 JT 4-3/4" D/C + 6-1/8" STRING REAMER +1 JTS 4-3/4" D/C + XO + 3 JTS 4" HWDP + 4-3/4" JAR + 2 JTS 4'' HWDP
95 | 06/21/2022 | SINO-19L | UTMN-232 | N | CT | TI | STDP | RIG | 6880 | 6880 | 275 | 2300 |  | RIH W/ 6-1/8" STIFF REAMING ASSY. ON 4" HWDP/DP T/ 5488' (TOW)...... INC @ RPT>>KEEP MONITOR WELL ON TRIP TANK - STATIC
96 | 06/21/2022 | SINO-19L | UTMN-232 | DOOS ID | Type | Category | Out of Scope Summary | 15 Jun 0300 | 21 | 22.5 | 3245 | OOS | LOG | PERFORM TRIPLE COMBO/MSFL/DIELECTRIC LOG.
97
98
99 | 06/21/2022 | SINO-36L | SDGM-458 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
100 | 06/21/2022 | SINO-36L | SDGM-458 | 17 Jun 1130 - 0500 | 24 | 113.5 | 898452 |  | STUK | IPDF | DP | TK1 | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
101 | 06/21/2022 | SND-2001 | UTMN-2329 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
102 | 06/21/2022 | SND-2001 | UTMN-2329 | 19 Jun 1930 - 0500 | 23 | 44.5 | 898492 |  | BHA | FOT | RSS | SDM | 15637 | RSS UNABLE TO BUILD UP REQUIRED INCLINATION.
103 | 06/21/2022 | SND-2002 | WAQR-23 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
104 | 06/21/2022 | SND-2002 | WAQR-23 | 16 Jun 2330 - 0500 | 24 | 125.5 | 898293 |  | LCIR | UVLC | NA | ARM | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
105 | 06/21/2022 | SND-2005 | MHKK-2 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
106 | 06/21/2022 | SND-2005 | MHKK-2 | 20 Jun 0230 - 0730 | 2.5 | 5 | 898655 |  | TF | FOT | WLT | SWL | 13195 | SCHLUMBERGER ASSURED EXPLORATION THE CBL/IBC/USIT WOULD WORK WITH THE 126 PCF, HOWEVER, WHEN USED, INADEQUATE SIGNAL.
107 | 06/21/2022 | SND-3002 | DMMM-601 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
108 | 06/21/2022 | SND-3002 | DMMM-601 | 20 Jun 1900 - 2300 | 16 | 26 | 898516 |  | BHA | FOT | RSS | SDM | 12127 | SDM RSS/MWD UNABLE TO HOLD INC ANGLE.
109 | 06/21/2022 | SP-110 | BRRI-562 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
110 | 06/21/2022 | SP-110 | BRRI-562 | 21 Jun 1215 - 1315 | 1 | 1 | 898657 |  | STUK | STBH | BHA | ARM | 16745 | WHEN WASHING UP AT KELLY DOWN STRING GOT STUCK, RELEASE STUCK PIPE WITH WORK STRING UP & DOWN
111 | 06/21/2022 | SSA-101 | QTIF-785 | 21 Jun 0530 - 0700 | 1.5 | 1.5 | 898633 |  | BHA | FOT | MWD | SDM | 16910 | NO SDM MWD SIGNAL, SDM TROUBLE SHOOTING TO GET MWD SIGNAL WITHOUT SUCCESS, RIH TO BOTTOM AND DISPLACE HOLE TO 78 PCF WBM.
112 | 06/21/2022 | SSA-101 | QTIF-785 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
113 | 06/21/2022 | SSA-101 | QTIF-785 | 19 Jun 1330 - 0900 | 2.5 | 42 | 898508 |  | BHA | FOT | RSS | SPS | 9795 | SPS RSS GIVING WRONG VALUES AT MID WAY TOOL CHECK WHILE RIH,SPS TROUBLE SHOOT BY PUMPING HI VIS PILL AND JERKING STRING, NO PROGRESS(2ND SPS TOOL FAILURE IN 6 1/8" L-0 HOLE) - DECISION TO CHANGE DIRECTIONAL COMPANY FROM SPS TO SDM.
114 | 06/21/2022 | SSA-101 | QTIF-785 | 21 Jun 0530 - 0700 | 1.5 | 1.5 | 898633 |  | BHA | FOT | MWD | SDM | 16910 | NO SDM MWD SIGNAL, SDM TROUBLE SHOOTING TO GET MWD SIGNAL WITHOUT SUCCESS, RIH TO BOTTOM AND DISPLACE HOLE TO 78 PCF WBM.
115 | 06/21/2022 | WCL-83 | MRJN-834 | From - To | Hrs | Cum. Hrs | LT ID | Parent LT ID | Type | Cause | Object | Resp Co | Depth | LT Summary
116 | 06/21/2022 | WCL-83 | MRJN-834 | 21 Jun 0530 - 0500 | 23.5 | 23.5 | 898656 |  | STUK | STCT | SCRN | RIG | 11680 | WORK ON STUCK COMPLETION STRING BY DIFFERENT PARAMETERS