## ORIGINAL
SEQ | Cause | Company Name | Cummulative Hrs | Date and Time | Depth | LT ID | LT Summary | LT Type | Object | Parent LT ID | Report Date | Rig Name | Time in Hrs | Well No
0 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | 095TE | Hrs | MNIF-126
1 | FRFM | ARM | 65 | 28 Aug 1030 - 0500 | 6100 | 901348 | CURE LOSSES AT SFNY FORMATION WITH LCM PILL AND CMT PLUG. | LCIR | NA |  | 08/30/2022 | 095TE | 23.5 | MNIF-126
2 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-17 | Hrs | ZULF-1385
3 | FPMP | RIG | .5 | 30 Aug 0245 - 0315 | 1470 | 901503 | PRESSURE DROP DUE TO FAILURE OF PISTON FOR MUD PUMP #1. | RR | MPMP |  | 08/30/2022 | ADC-17 | .5 | ZULF-1385
4 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-35 | Hrs | MAQL-5
5 | FOT | HCB | 28.5 | 29 Aug 0030 - 0500 | 5915 | 901459 | AFTER PLT LOGGING ANALYSIS, FOUND COMMUNCATION BETWEEN TOP AND BTTM OF BRIDGE PLUG. | TF | BP |  | 08/30/2022 | ADC-35 | 24 | MAQL-5
6 | ORDS | TK3 | 15 | 30 Aug 1400 - 0500 | 10968 | 901520 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK | WO | NA |  | 08/30/2022 | ADC-55L | 15 | UTMN-3171
7 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-55L | Hrs | UTMN-3171
8 | FOT | RIG | 156 | 23 Aug 0200 - 1400 | 10968 | 901375 | WHILE PT BOP OBSERVED LEAK BETWEEN DSA & LOWER DBL GATE | BOP | RAMS |  | 08/30/2022 | ADC-55L | 9 | UTMN-3171
9 | ORDS | TK3 | 15 | 30 Aug 1400 - 0500 | 10968 | 901520 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK | WO | NA |  | 08/30/2022 | ADC-55L | 15 | UTMN-3171
10 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-56L | Hrs | UTMN-3069
11 | FOT | RIG | 1.5 | 30 Aug 0530 - 0700 | 12333 | 901493 | WHILE WASHING DOWN OBSERVED LEAK IN SAVER SUB CONNECTION TO DP XT -54 CONNECTION | RR | CSYS |  | 08/30/2022 | ADC-56L | 1.5 | UTMN-3069
12 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-62L | Hrs | ANDR-589
13 | FPMP | RIG | 3.25 | 30 Aug 2200 - 0500 | 7520 | 901517 | REPAIR MUD PUMPS - CHANGED PISTON & GASKET OF MP#1& 3. | RR | MPMP |  | 08/30/2022 | ADC-62L | 3.25 | ANDR-589
14 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADES-173 | Hrs | UTMN-1952
15 | FOT | RIG | 3 | 30 Aug 1800 - 2100 | 10404 | 901494 | TOP DRIVE SAVER SUB LEAKING. | RR | TDS |  | 08/30/2022 | ADES-173 | 3 | UTMN-1952
16 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADES-174 | Hrs | GHZL-72
17 | SFHS | BFW | 200.25 | 22 Aug 0530 - 2130 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/30/2022 | ADES-174 | 16.5 | GHZL-72
18 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADES-889 | Hrs | HRDH-2122
19 | FOT | BHI | 48.75 | 28 Aug 0245 - 0500 | 11160 | 901383 | HAD NO COMMUNICATION WITH BAKER RSS TOOL | BHA | RSS |  | 08/30/2022 | ADES-889 | 24 | HRDH-2122
20 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADM-262 | Hrs | MRJN-446
21 | XTRI | RIG | 2 | 30 Aug 1200 - 1400 | 450 | 901492 | ADES UNABLE TO RUN POWER TONG EFFICIENTLY, UNABLE TO CONFIGURE TOOL TO BREAK OUT X-OVERS AND COMPLETION COMPONENTS. | JF | CTRQ |  | 08/30/2022 | ADM-262 | 2 | MRJN-446
22 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADM-655 | Hrs | SFNY-183
23 | OTH | RIG | 48 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 08/30/2022 | ADM-655 | 24 | SFNY-183
24 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ENS-108 | Hrs | ZULF-2015
25 | GRF | RIG | 192 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/30/2022 | ENS-108 | 24 | ZULF-2015
26 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ENS-141 | Hrs | MRJN-3027
27 | FOT | RIG | 1.5 | 30 Aug 0745 - 0915 | 2055 | 901495 | TDS HPU OVER HEATED, UNABLE TO BREAK OUT STAND, CIRCULATE HOLE AND RECIPROCATE PIPE WHILE TROUBLESHOOTING AND COOLING DOWN SAME . | RR | TDS |  | 08/30/2022 | ENS-141 | 1.5 | MRJN-3027
28 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | HI-5 | Hrs | MHRH-57
29 | FOT | RIG | 3 | 30 Aug 1500 - 1800 | 8627 | 901499 | CHANGE IBOP AND FUNCTION TEST. | RR | TDS |  | 08/30/2022 | HI-5 | 3 | MHRH-57
30 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | HWU-1 | Hrs | HMYM-431414
31 | FOT | RIG | 34 | 29 Aug 1615 - 0215 | 0 | 901393 | UNABLE TO SCOPE UP GIN POLE | RR | CBLK |  | 08/30/2022 | HWU-1 | 21.25 | HMYM-431414
32 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | NA-18S | Hrs | SDGM-444
33 | FPMP | RIG | 1 | 30 Aug 1715 - 1815 | 11165 | 901506 | WORK ON MUD PUMP. | RR | MPMP |  | 08/30/2022 | NA-18S | 1 | SDGM-444
34 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | NBR-115S | Hrs | SDGM-1221
35 | FOT | SDM | 38 | 29 Aug 1045 - 0145 | 6554 | 901456 | NOTICED DRILL STRING PRESSURE DROP AND MWD TURBINE SPEED SLOWING. | BHA | MWD |  | 08/30/2022 | NBR-115S | 19.75 | SDGM-1221
36 | FOT | NRC | 3.25 | 30 Aug 0145 - 0500 | 740 | 901518 | OBSERVE NAPESCO CRT HYD HOSES LEAKING, FIX SAME. | TF | CRT |  | 08/30/2022 | NBR-263S | 3.25 | QTIF-736
37 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | NBR-263S | Hrs | QTIF-736
38 | STBH | ARM | 412.5 | 29 Jul 0230 - 1300 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/30/2022 | NBR-263S | 8 | QTIF-736
39 | FOT | NRC | 3.25 | 30 Aug 0145 - 0500 | 740 | 901518 | OBSERVE NAPESCO CRT HYD HOSES LEAKING, FIX SAME. | TF | CRT |  | 08/30/2022 | NBR-263S | 3.25 | QTIF-736
40 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | NBR-633S | Hrs | HRDH-1911
41 | FOT | SPS | 1.5 | 30 Aug 0200 - 0330 | 140 | 901500 | WHILE TESTING MWD TOOL (DGWD), HAD NO COMMUNICATION WITH TOOL. | BHA | MWD |  | 08/30/2022 | NBR-633S | 1.5 | HRDH-1911
42 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | PA-218S | Hrs | HRDH-1976
43 | FOT | RIG | .5 | 30 Aug 2030 - 2100 | 510 | 901523 | TRIP TANK PUMP FAILURE, REPAIR SAME & FIXED LEAKS IN FILL UP LINE. | RR | HSYS |  | 08/30/2022 | PA-218S | .5 | HRDH-1976
44 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SDA | Hrs | MRJN-653
45 | FOT | SCD | 7.25 | 30 Aug 2145 - 0500 | 314 | 901524 | UNABLE TO SURVEY AT SHOE DUE TO BAD DECODING. CYCLE PUMPS AND TROUBLESHOOTING SCIENTIFIC GYRO TOOL, CHANGE PRESSURE SENSOR, CHANGE MWD SURFACE BOX. APPLY DIFFERENT GPM AND FREQUENCY BANDS. ATTEMP TO CHANGE TOOL FREQUENCY - NO SUCCESS. POOH TO CHECK AND CHANGE GWD TOOLS. | SURV | GYRO |  | 08/30/2022 | SDA | 7.25 | MRJN-653
46 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SINO-33L | Hrs | HRDH-1542
47 | FOT | RIG | 203.5 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/30/2022 | SINO-33L | 24 | HRDH-1542

## Sheet1
seq | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | Type | Object | Parent LT ID | 08/30/2022 | 095TE | Hrs | MNIF-126 | LT Summary
1 | FRFM | ARM | 65 | 28 Aug 1030 - 0500 | 6100 | 901348 | LCIR | NA |  | 08/30/2022 | 095TE | 23.5 | MNIF-126 | CURE LOSSES AT SFNY FORMATION WITH LCM PILL AND CMT PLUG.
3 | FPMP | RIG | .5 | 30 Aug 0245 - 0315 | 1470 | 901503 | RR | MPMP |  | 08/30/2022 | ADC-17 | .5 | ZULF-1385 | PRESSURE DROP DUE TO FAILURE OF PISTON FOR MUD PUMP #1.
5 | FOT | HCB | 28.5 | 29 Aug 0030 - 0500 | 5915 | 901459 | TF | BP |  | 08/30/2022 | ADC-35 | 24 | MAQL-5 | AFTER PLT LOGGING ANALYSIS, FOUND COMMUNCATION BETWEEN TOP AND BTTM OF BRIDGE PLUG.
6 | ORDS | TK3 | 15 | 30 Aug 1400 - 0500 | 10968 | 901520 | WO | NA |  | 08/30/2022 | ADC-55L | 15 | UTMN-3171 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK
8 | FOT | RIG | 156 | 23 Aug 0200 - 1400 | 10968 | 901375 | BOP | RAMS |  | 08/30/2022 | ADC-55L | 9 | UTMN-3171 | WHILE PT BOP OBSERVED LEAK BETWEEN DSA & LOWER DBL GATE
9 | ORDS | TK3 | 15 | 30 Aug 1400 - 0500 | 10968 | 901520 | WO | NA |  | 08/30/2022 | ADC-55L | 15 | UTMN-3171 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK
11 | FOT | RIG | 1.5 | 30 Aug 0530 - 0700 | 12333 | 901493 | RR | CSYS |  | 08/30/2022 | ADC-56L | 1.5 | UTMN-3069 | WHILE WASHING DOWN OBSERVED LEAK IN SAVER SUB CONNECTION TO DP XT -54 CONNECTION
13 | FPMP | RIG | 3.25 | 30 Aug 2200 - 0500 | 7520 | 901517 | RR | MPMP |  | 08/30/2022 | ADC-62L | 3.25 | ANDR-589 | REPAIR MUD PUMPS - CHANGED PISTON & GASKET OF MP#1& 3.
15 | FOT | RIG | 3 | 30 Aug 1800 - 2100 | 10404 | 901494 | RR | TDS |  | 08/30/2022 | ADES-173 | 3 | UTMN-1952 | TOP DRIVE SAVER SUB LEAKING.
17 | SFHS | BFW | 200.25 | 22 Aug 0530 - 2130 | 11165 | 901031 | STUK | FISHT |  | 08/30/2022 | ADES-174 | 16.5 | GHZL-72 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED.
19 | FOT | BHI | 48.75 | 28 Aug 0245 - 0500 | 11160 | 901383 | BHA | RSS |  | 08/30/2022 | ADES-889 | 24 | HRDH-2122 | HAD NO COMMUNICATION WITH BAKER RSS TOOL
21 | XTRI | RIG | 2 | 30 Aug 1200 - 1400 | 450 | 901492 | JF | CTRQ |  | 08/30/2022 | ADM-262 | 2 | MRJN-446 | ADES UNABLE TO RUN POWER TONG EFFICIENTLY, UNABLE TO CONFIGURE TOOL TO BREAK OUT X-OVERS AND COMPLETION COMPONENTS.
23 | OTH | RIG | 48 | 29 Aug 0500 - 0500 | 0 | 901309 | UPRA | NA |  | 08/30/2022 | ADM-655 | 24 | SFNY-183 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING.
25 | GRF | RIG | 192 | 23 Aug 0500 - 0500 | 7186 | 901163 | UPRA | PSYS |  | 08/30/2022 | ENS-108 | 24 | ZULF-2015 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER.
27 | FOT | RIG | 1.5 | 30 Aug 0745 - 0915 | 2055 | 901495 | RR | TDS |  | 08/30/2022 | ENS-141 | 1.5 | MRJN-3027 | TDS HPU OVER HEATED, UNABLE TO BREAK OUT STAND, CIRCULATE HOLE AND RECIPROCATE PIPE WHILE TROUBLESHOOTING AND COOLING DOWN SAME .
29 | FOT | RIG | 3 | 30 Aug 1500 - 1800 | 8627 | 901499 | RR | TDS |  | 08/30/2022 | HI-5 | 3 | MHRH-57 | CHANGE IBOP AND FUNCTION TEST.
31 | FOT | RIG | 34 | 29 Aug 1615 - 0215 | 0 | 901393 | RR | CBLK |  | 08/30/2022 | HWU-1 | 21.25 | HMYM-431414 | UNABLE TO SCOPE UP GIN POLE
33 | FPMP | RIG | 1 | 30 Aug 1715 - 1815 | 11165 | 901506 | RR | MPMP |  | 08/30/2022 | NA-18S | 1 | SDGM-444 | WORK ON MUD PUMP.
35 | FOT | SDM | 38 | 29 Aug 1045 - 0145 | 6554 | 901456 | BHA | MWD |  | 08/30/2022 | NBR-115S | 19.75 | SDGM-1221 | NOTICED DRILL STRING PRESSURE DROP AND MWD TURBINE SPEED SLOWING.
36 | FOT | NRC | 3.25 | 30 Aug 0145 - 0500 | 740 | 901518 | TF | CRT |  | 08/30/2022 | NBR-263S | 3.25 | QTIF-736 | OBSERVE NAPESCO CRT HYD HOSES LEAKING, FIX SAME.
38 | STBH | ARM | 412.5 | 29 Jul 0230 - 1300 | 13970 | 900313 | STUK | BHA |  | 08/30/2022 | NBR-263S | 8 | QTIF-736 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST.
39 | FOT | NRC | 3.25 | 30 Aug 0145 - 0500 | 740 | 901518 | TF | CRT |  | 08/30/2022 | NBR-263S | 3.25 | QTIF-736 | OBSERVE NAPESCO CRT HYD HOSES LEAKING, FIX SAME.
41 | FOT | SPS | 1.5 | 30 Aug 0200 - 0330 | 140 | 901500 | BHA | MWD |  | 08/30/2022 | NBR-633S | 1.5 | HRDH-1911 | WHILE TESTING MWD TOOL (DGWD), HAD NO COMMUNICATION WITH TOOL.
43 | FOT | RIG | .5 | 30 Aug 2030 - 2100 | 510 | 901523 | RR | HSYS |  | 08/30/2022 | PA-218S | .5 | HRDH-1976 | TRIP TANK PUMP FAILURE, REPAIR SAME & FIXED LEAKS IN FILL UP LINE.
45 | FOT | SCD | 7.25 | 30 Aug 2145 - 0500 | 314 | 901524 | SURV | GYRO |  | 08/30/2022 | SDA | 7.25 | MRJN-653 | UNABLE TO SURVEY AT SHOE DUE TO BAD DECODING. CYCLE PUMPS AND TROUBLESHOOTING SCIENTIFIC GYRO TOOL, CHANGE PRESSURE SENSOR, CHANGE MWD SURFACE BOX. APPLY DIFFERENT GPM AND FREQUENCY BANDS. ATTEMP TO CHANGE TOOL FREQUENCY - NO SUCCESS. POOH TO CHECK AND CHANGE GWD TOOLS.
47 | FOT | RIG | 203.5 | 22 Aug 1300 - 0500 | 1396 | 901172 | RR | TDS |  | 08/30/2022 | SINO-33L | 24 | HRDH-1542 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION