## Sheet1
seq | Report Date | Date and Time | Well No | Rig Name | Company Name | Cause | Time in Hrs | Cummulative Hrs | LT ID | Parent LT ID | LT Type | Depth | Object | LT Summary
1 | 10/01/2022 | 30 Sep 2315 - 0500 | QTIF-519 | 088TE | RIG | FOT | 24 | 29.75 | 902992 |  | TF | 14011 | SLIPS | WHILE P/U SPS 8-1/2" RSS DIR. ASSY. SLIPS DIES DROPPED IN HOLE.
2 | 10/01/2022 | 01 Oct 1900 - 2100 | DMMM-136 | 910TE | SDM | FOT | 2 | 2 | 903039 |  | BHA | 16881 | MWD | OBSERVE SLB SOFTWARE CRASHING & NOT TRANSMITTING DATA; TROUBLE SHOOT; OK.
4 | 10/01/2022 | 01 Oct 2100 - 0500 | DMMM-136 | 910TE | SDM | FOT | 7.5 | 7.5 | 903038 |  | BHA | 16881 | MWD | LOST COMMUNICATION WITH MWD TOOL; TROUBLE SHOOT ANTI-JAMMING PROCEDURE; NO SUCCESS. POOH & CHECK/CHANGE BHA.
5 | 10/01/2022 | 01 Oct 1900 - 2100 | DMMM-136 | 910TE | SDM | FOT | 2 | 2 | 903039 |  | BHA | 16881 | MWD | OBSERVE SLB SOFTWARE CRASHING & NOT TRANSMITTING DATA; TROUBLE SHOOT; OK.
7 | 10/01/2022 | 30 Sep 1930 - 2100 | MAQL-6 | ADC-35 | RIG | FOT | 16 | 25.5 | 902986 |  | RR | 248 | TDS | RIG REPAIR - BAD DECODING BETWEEN TDS AND VFD ( TDS MOTOR ENCODER PROBLEM & SIGNAL INTERFERENCE).
9 | 10/01/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 243 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
11 | 10/01/2022 | 30 Sep 0000 - 0500 | ABHD-183 | ADC-58L | RIG | FOT | 24 | 29 | 902996 |  | BOP | 0 | BOP | ATTEMPT TO TEST BOP ANNULAR TO 3500 PSI OFFLINE OBSERVED VISUAL LEAK FROM OFF-DRILLER SIDE SHEAR/SINGLE RAM BONNETS
13 | 10/01/2022 | 22 Sep 0030 - 1500 | HWYH-1324 | ADC-59L | TK3 | FOT | 10 | 183.75 | 902684 |  | TF | 19319 | LINR | CONT. WIPER TRIP. RIH W/ WBCU ASSAY FROM 16412 FT TO 19,319 FT ON ELEVATOR. NOTE: RUN LOGS TO INVESTIGATE
25 | 10/01/2022 | 01 Oct 1730 - 0500 | UTMN-2299 | ADC-66L | TK3 | HELD | 11.5 | 11.5 | 903042 |  | JF | 720 | CSG | WORK ON CASING TO PASS THROUGH TIGHT SPOT AT 560 FT.
34 | 10/01/2022 | 01 Oct 0500 - 1000 | HRDH-1095 | ADES-157 | OCS | FOT | 5 | 5 | 902885 |  | TF | 3700 | TTRQ | FAILURE OF MANUAL SLIPS / POWER TONG DIES - FAILED TO GRIP TBG.
36 | 10/01/2022 | 15 Sep 0100 - 0500 | HRDH-2122 | ADES-889 | ARM | PCPF | 23.5 | 372 | 902524 |  | BHS | 10881 | NA | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL.
38 | 10/01/2022 | 30 Sep 1745 - 0215 | MRJN-900 | ADM-337 | BCT | FOT | 19.75 | 25.5 | 902988 |  | TF | 13019 | CTPMP | ATTEMPT TO PRESSURE TEST BAKER CT PUMPS, NOT HOLDING PRESSURE THEN PUMP #3 UNABLE TO PUMP
40 | 10/01/2022 | 29 Sep 1130 - 0500 | SFNY-4260 | AOD-1 | RIG | UNKN | 24 | 65.5 | 902939 |  | HSEI | 0 | NA | INVESTIGATE UNREPORTED INCIDENT ON SEPT 26.
42 | 10/01/2022 | 30 Sep 0030 - 0615 | MRJN-814 | ARO-3002 | RIG | FOT | 1.25 | 5.75 | 902985 |  | RR | 14186 | CSYS | LEAK ON STAND PIPE LINE.
43 | 10/01/2022 | 01 Oct 0000 - 0500 | HRDH-351 | DQ-50L | RIG | FOT | 5 | 5 | 903043 |  | RR | 3060 | DWKS | UN PLANNED SLIP & CUT DRILL LINE DUE TO WIRE ROPE OF DRAW-WORKS DRUM DEAD LAYER SQUEEZED & OUT OF ORIGINAL POSITION.
45 | 10/01/2022 | 01 Oct 1030 - 1700 | HRDH-351 | DQ-50L | TK2 | NARW | 6.5 | 6.5 | 902883 |  | TH | 2450 | NA | HAD DIFFICULTIES (TRQ & DRAG) WHILE WASH & REAM LAST DRLD STD @ 2,450', DECIDED TO POOH & CHANGE BHA DESIGN.
46 | 10/01/2022 | 01 Oct 0000 - 0500 | HRDH-351 | DQ-50L | RIG | FOT | 5 | 5 | 903043 |  | RR | 3060 | DWKS | UN PLANNED SLIP & CUT DRILL LINE DUE TO WIRE ROPE OF DRAW-WORKS DRUM DEAD LAYER SQUEEZED & OUT OF ORIGINAL POSITION.
48 | 10/01/2022 | 30 Sep 2045 - 1815 | ZULF-2041 | EXL-IVA | RIG | FOT | 6.25 | 7.75 | 902982 |  | RR | 6848 | TDS | LUBE OIL FAULT ON TOP DRIVE, WAS UNABLE TO REASSIGN AFTER STOPPING ROTATION.
50 | 10/01/2022 | 01 Oct 1930 - 2100 | BRRI-436 | HI-2 | BAW | FOT | 1.5 | 1.5 | 903041 |  | TF | 10262 | WLT | TROUBLESHOOT MALFUNCTION IN LOGGING TOOLS RESPONSE - FOUND ONE ELECTRCIAL PIN BENT, REPLACED SAME.
51 | 10/01/2022 | 30 Sep 1845 - 0900 | HRDH-1976 | PA-218S | RIG | FOT | 4 | 14.25 | 902989 |  | RR | 5000 | DWKS | DRAWWORK EATON BREAK SERVO VALVE MALFUNCTION.
53 | 10/01/2022 | 16 Sep 2000 - 0500 | HRDH-1976 | PA-218S | ARM | UVLC | 20 | 326.75 | 902417 |  | LCIR | 7387 | NA | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR).
54 | 10/01/2022 | 30 Sep 1845 - 0900 | HRDH-1976 | PA-218S | RIG | FOT | 4 | 14.25 | 902989 |  | RR | 5000 | DWKS | DRAWWORK EATON BREAK SERVO VALVE MALFUNCTION.
56 | 10/01/2022 | 30 Sep 0230 - 0315 | MRJN-673 | PN-9 | BHI | FOT | 5.5 | 6.5 | 902994 |  | BHA | 15677 | LWD | BAKER HUGHES TOOK EXCESSIVE TIME TO PERFORM DOWNLINK.
58 | 10/01/2022 | 29 Sep 1600 - 0500 | UTMN-3189 | SCTD-1 | RIG | FOT | 24 | 61 | 902935 |  | RR | 0 | EDR | FAILURE OF E-LINE INSULATION.
60 | 10/01/2022 | 01 Oct 2230 - 0130 | SHYB-245 | SINO-28L | TK2 | IBHA | 3 | 3 | 903002 |  | BHA | 39 | BHA | CANNOT PASS MOTOR BENT HOUSING THRU WELL HEAD
62 | 10/01/2022 | 01 Oct 1200 - 0500 | SHYB-124 | SINO-32L | BWH | FOT | 17 | 17 | 903001 |  | TF | 12668 | WPSTK | ATTEMPT TO CATCH L-1 BAKER WPSTK SEVERAL TIMES WITH HOOK WITHOUT SUCCESS.
64 | 10/01/2022 | 22 Sep 0500 - 0500 | BRRI-1148 | SND-2004 | HSL | FOT | 24 | 205.5 | 902598 |  | TF | 8196 | PLUGN | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL.
66 | 10/01/2022 | 25 Sep 1400 - 0500 | AWTD-104001 | SND-2007 | NPC | TOWC | 24 | 156.5 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
68 | 10/01/2022 | 27 Sep 0630 - 0500 | HRDH-1291 | SND-2008 | ARM | UVLC | 24 | 118.5 | 902798 |  | LCIR | 12135 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
70 | 10/01/2022 | 01 Oct 0030 - 0500 | MNIF-868 | SND-2010 | HTS | XTRI | 4.5 | 4.5 | 903003 |  | JF | 7039 | TESTT | DOWN TIME ON HALL WELLTEST COMPANY DUE TO DELAY IN OPERATIN WHILE R/U HALL WELLTEST UPSTREAM HP LINES.
72 | 10/01/2022 | 01 Oct 1545 - 1945 | MRJN-903 | SNF036 | GEP | FOT | 4 | 4 | 903000 |  | WH | 2628 | WH | MANY TRIALS TO CONNECT BAKER VETCO MLC TO 18-5/8" CSG WITH NO SUCCESS.
74 | 10/01/2022 | 01 Oct 0030 - 0200 | KRSN-128 | SP-103 | RIG | FOT | 1.5 | 1.5 | 902886 |  | RR | 5223 | SLIPS | REPAIR ON POWER TONG
76 | 10/01/2022 | 01 Oct 1400 - 0500 | JLDI-862 | SP-229 | KSC | FOT | 15 | 15 | 903036 |  | TF | 799 | ESPL | CHECK ESP CABLE INTEGRITY WHILE RIH AND FOUND CABLE GROUNDED.
77 | 10/01/2022 | 01 Oct 1830 - 0430 | QTIF-526 | SSA-101 | ARM | CWEL | 10 | 10 | 903004 |  | BHS | 1680 | NA | RE-RUN 13 3/8" CSG W/ CRT DUE TO OPEN HOLE UNSTABALITY. (WITH PREVIOUS RUN CONVENTIONAL CSG GOT HELD UP AT 1684').
79 | 10/01/2022 | 30 Sep 1415 - 1830 | QTIF-526 | SSA-101 | ARM | CWEL | 13.5 | 28.25 | 902882 |  | BHS | 1684 | NA | CONDITION TRIP DUE TO 17" OPEN HOLE UNSTABALITY.
80 | 10/01/2022 | 01 Oct 1830 - 0430 | QTIF-526 | SSA-101 | ARM | CWEL | 10 | 10 | 903004 |  | BHS | 1680 | NA | RE-RUN 13 3/8" CSG W/ CRT DUE TO OPEN HOLE UNSTABALITY. (WITH PREVIOUS RUN CONVENTIONAL CSG GOT HELD UP AT 1684').
82 | 10/01/2022 | 30 Sep 0345 - 0615 | HWYH-1217 | SSA-5859 | RIG | FOT | 1.25 | 2.5 | 902990 |  | RR | 6755 | DWKS | HAD PROBLEM IN HIGH SPEED CLUTCH FOR DRAW WORKS
84 | 10/01/2022 | 30 Sep 2200 - 1430 | HRDH-2364 | SSA-5868 | RIG | FOT | 9.5 | 16.5 | 902991 |  | RR | 9900 | TDS | > WHILE DRILLING 12" HOLE WITH ROTARY MWD-GR ASSY., HAD LEAKAGE IN IBOP UPPER CONNECTION (QUAIL SHAFT WASH OUT).
86 | 10/01/2022 | 01 Oct 0600 - 1030 | WDYH-80 | SSA-5914 | RIG | FOT | 4.5 | 4.5 | 902881 |  | BOP | 0 | RAMS | 4-1/2" UPPER CASING RAMS P/T FAILLED DUE TO CRACKED RAM DOOR SEAL,
87 | 10/01/2022 | 01 Oct 2030 - 0500 | RGHB-704 | SSA-5915 | RIG | FOT | 8.5 | 8.5 | 903037 |  | RR | 439 | TDS | TDS COULD NOT BREAK OUT OF HWDP. GRABBER DIES DAMAGED. AFTER BREAKOUT FOUND SAVERSUB THREAD DAMAGED. POOH INSIDE 18 5/8'' SHOE. WHILE CHANGING SAVER SUB, TDS GRABBER WOULD NOT STAY CLOSED WHILE ROTATING.
89 | 10/01/2022 | 01 Oct 1400 - 1600 | RGHB-704 | SSA-5915 | RIG | FOT | 2 | 2 | 902884 |  | RR | 245 | MPMP | MUD PUMPS DOWN, COOLING SYSTEM WAS DISCONNECTED SINCE LAST PUMP SERVICE.
90 | 10/01/2022 | 30 Sep 0330 - 0900 | RGHB-704 | SSA-5915 | RIG | FOT | 4 | 5.5 | 902993 |  | RR | 92 | SLIPS | WHILE PICKING UP BHA BV-100 TONGS WOULD NOT UNPIN TO ADJUST FOR DIFFERENT TUBULARS
91 | 10/01/2022 | 01 Oct 2030 - 0500 | RGHB-704 | SSA-5915 | RIG | FOT | 8.5 | 8.5 | 903037 |  | RR | 439 | TDS | TDS COULD NOT BREAK OUT OF HWDP. GRABBER DIES DAMAGED. AFTER BREAKOUT FOUND SAVERSUB THREAD DAMAGED. POOH INSIDE 18 5/8'' SHOE. WHILE CHANGING SAVER SUB, TDS GRABBER WOULD NOT STAY CLOSED WHILE ROTATING.
93 | 10/01/2022 | 19 Sep 0430 - 0500 | UTMN-3148 | SSA-5969 | ARM | WC20 | 24 | 250 | 902485 |  | WCNT | 10092 | NA | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF.
95 | 10/01/2022 | 28 Sep 1700 - 1030 | HWYH-1215 | SSA-5971 | BLH | FOT | 5.5 | 59.5 | 902853 |  | TF | 14560 | HGRL | RIH 4 1/2'' CONTROL SET ROT FL-V LINER HANGER TO 13434 FT TRIED TO CIRCULATE @ 6 BPM PRESSURE INCREASED AND MANY TRIALS TO GO DOWN WITHOUT PROGRESS.
97 | 10/02/2022 | 30 Sep 2315 - 0500 | QTIF-519 | 088TE | RIG | FOT | 24 | 53.75 | 902992 |  | TF | 14011 | SLIPS | WHILE P/U SPS 8-1/2" RSS DIR. ASSY. SLIPS DIE DROPPED IN HOLE, RIH FISHING ASSY. TO FISH IT.
99 | 10/02/2022 | 01 Oct 2100 - 0500 | DMMM-136 | 910TE | SDM | FOT | 23.5 | 31 | 903038 |  | BHA | 16881 | MWD | LOST COMMUNICATION WITH MWD TOOL; TROUBLE SHOOT ANTI-JAMMING PROCEDURE; NO SUCCESS. POOH & CHECK/CHANGE BHA.
101 | 10/02/2022 | 02 Oct 1130 - 1630 | HRDH-1864 | ADC-14 | RIG | FOT | 5 | 5 | 902887 |  | RR | 13050 | TDS | ROTARY HOSE LEAKING WHILE DRILLING.
103 | 10/02/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 267 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
105 | 10/02/2022 | 30 Sep 0000 - 0500 | ABHD-183 | ADC-58L | RIG | FOT | 24 | 53 | 902996 |  | BOP | 0 | BOP | ATTEMPT TO TEST BOP ANNULAR TO 3500 PSI OFFLINE OBSERVED VISUAL LEAK FROM OFF-DRILLER SIDE SHEAR/SINGLE RAM BONNETS
119 | 10/02/2022 | 01 Oct 1730 - 0500 | UTMN-2299 | ADC-66L | TK3 | HELD | 24 | 35.5 | 903042 |  | JF | 720 | CSG | WORK ON CASING TO PASS THROUGH TIGHT SPOT AT 560 FT.
135 | 10/02/2022 | 02 Oct 0800 - 1300 | HWYH-27 | ADES-14 | SDM | FOT | 5 | 5 | 902888 |  | BHA | 8755 | MWD | ACCUMALATIVE TIME FOR MWD LOST SIGNAL & TROUBLE SHOOT THE SAME & LOW ROP
137 | 10/02/2022 | 15 Sep 0100 - 0500 | HRDH-2122 | ADES-889 | ARM | PCPF | 23.5 | 395.5 | 902524 |  | BHS | 10881 | NA | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL.
139 | 10/02/2022 | 01 Oct 0500 - 0500 | SFNY-263 | ADM-266 | ARN | SRVC | 24 | 48 | 903044 |  | WO | 0 | NA | WAITING ON BARGE ARABIYAH-6 MOVE OUT FROM PF SFNY-258/263 LOCATION, TO ALLOW DIVERS TO REMOVE DEBRIS NEAR PF THEN THE RIG TO MOVE IN.
141 | 10/02/2022 | 02 Oct 2345 - 0145 | MRJN-900 | ADM-337 | BCT | FOT | 2 | 2 | 903007 |  | TF | 13019 | CTBG | TROUBLESHOOT LEAKING LTQ VALVE DURING PRESSURE TEST. CHANGE OUT AND REPLACE SAME
143 | 10/02/2022 | 29 Sep 1130 - 0500 | SFNY-4260 | AOD-1 | RIG | UNKN | 24 | 89.5 | 902939 |  | HSEI | 0 | NA | INVESTIGATE UNREPORTED INCIDENT ON SEPT 26.
145 | 10/02/2022 | 02 Oct 0500 - 1700 | SDGM-1221 | NBR-115S | RIG | FOT | 12 | 12 | 903006 |  | BOP | 12845 | BOP | BOP LEAKING AT TOP OF DSA.
147 | 10/02/2022 | 02 Oct 1130 - 1430 | HRDH-2313 | NBR-591S | RIG | FOT | 3 | 3 | 903046 |  | RR | 670 | TDS | LOST COMMUNICATION TO TDS & CHANGED OUT DAMAGED CABLE.
149 | 10/02/2022 | 16 Sep 2000 - 0400 | HRDH-1976 | PA-218S | ARM | UVLC | 23 | 349.75 | 902417 |  | LCIR | 7387 | NA | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR).
150 | 10/02/2022 | 02 Oct 1145 - 1245 | MRJN-673 | PN-9 | RIG | FOT | 1 | 1 | 903048 |  | RR | 16800 | MPMP | HAD MALFUNCTION IN MUD PUMP #1 "VFD OVERHEATED"
152 | 10/02/2022 | 30 Sep 0230 - 0845 | MRJN-673 | PN-9 | BHI | FOT | 1.25 | 5.25 | 902994 |  | BHA | 16712 | LWD | BAKER HUGHES TOOK EXCESSIVE TIME TO PERFORM DOWNLINK.
153 | 10/02/2022 | 02 Oct 1145 - 1245 | MRJN-673 | PN-9 | RIG | FOT | 1 | 1 | 903048 |  | RR | 16800 | MPMP | HAD MALFUNCTION IN MUD PUMP #1 "VFD OVERHEATED"
154 | 10/02/2022 | 29 Sep 1600 - 2100 | UTMN-3189 | SCTD-1 | RIG | FOT | 16 | 77 | 902935 |  | RR | 0 | EDR | FAILURE OF E-LINE INSULATION.
156 | 10/02/2022 | 02 Oct 0230 - 0500 | UTMN-3189 | SCTD-1 | RIG | FOT | 2.5 | 2.5 | 902889 |  | BHA | 10620 | MMOT | D&M LOST TELEMETRY WITH DOWNHOLE TOOLS.
157 | 10/02/2022 | 29 Sep 1600 - 2100 | UTMN-3189 | SCTD-1 | RIG | FOT | 16 | 77 | 902935 |  | RR | 0 | EDR | FAILURE OF E-LINE INSULATION.
172 | 10/02/2022 | 02 Oct 0200 - 0500 | BRRI-1144 | SINO-22 | SDM | FOT | 3 | 3 | 903052 |  | BHA | 11062 | RSS | RSS FAILURE. TRIP OUT TO CHANGE THE TOOL.
174 | 10/02/2022 | 01 Oct 1200 - 2115 | SHYB-124 | SINO-32L | BWH | FOT | 16.25 | 33.25 | 903001 |  | TF | 12668 | WPSTK | ATTEMPT TO CATCH L-1 BAKER WPSTK SEVERAL TIMES WITH HOOK WITHOUT SUCCESS.
176 | 10/02/2022 | 02 Oct 0730 - 1530 | ANDR-378 | SINO-36L | HWP | FOT | 8 | 8 | 903050 |  | TF | 11538 | PLT | SURFACE DEPTH CONTROL UNIT PANEL FAILURE, TROUBLESHOOTING, NO SUCCESSFUL.
198 | 10/02/2022 | 22 Sep 0500 - 0430 | BRRI-1148 | SND-2004 | HSL | FOT | 23.5 | 229 | 902598 |  | TF | 8196 | PLUGN | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL.
200 | 10/02/2022 | 02 Oct 0600 - 1930 | UTMN-3095 | SND-2006 | RIG | FOT | 13 | 13 | 903053 |  | DSF | 2500 | DP | PRESSURE SPIKE WHILE ATTEMPTING TO FILL THE STRING, WORK ON STRING TO CLEAR STRING RESTRICTION SEVERAL TIMES BY RECIPROCATION, WITH HIGH PRESSURE. NO SUCCESS.
202 | 10/02/2022 | 25 Sep 1400 - 0700 | AWTD-104001 | SND-2007 | NPC | TOWC | 2 | 158.5 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
203 | 10/02/2022 | 02 Oct 0830 - 0500 | HRDH-1291 | SND-2008 | SCD | FOT | 20.5 | 20.5 | 903005 |  | SURV | 10966 | GYRO | LOST COMMUNICATION WITH GYRO TOOL DOWN HOLE BEFORE SURVEYING
205 | 10/02/2022 | 27 Sep 0630 - 0830 | HRDH-1291 | SND-2008 | ARM | UVLC | 3.5 | 122 | 902798 |  | LCIR | 12135 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
206 | 10/02/2022 | 02 Oct 0830 - 0500 | HRDH-1291 | SND-2008 | SCD | FOT | 20.5 | 20.5 | 903005 |  | SURV | 10966 | GYRO | LOST COMMUNICATION WITH GYRO TOOL DOWN HOLE BEFORE SURVEYING
208 | 10/02/2022 | 01 Oct 0030 - 0630 | MNIF-868 | SND-2010 | HTS | XTRI | 1.5 | 6 | 903003 |  | JF | 7039 | TESTT | DOWN TIME ON HALL WELLTEST COMPANY DUE TO DELAY IN OPERATIN WHILE R/U HALL WELLTEST UPSTREAM HP LINES.
210 | 10/02/2022 | 01 Oct 1400 - 1430 | JLDI-862 | SP-229 | KSC | FOT | 9.5 | 24.5 | 903036 |  | TF | 799 | ESPL | CHECK ESP CABLE INTEGRITY WHILE RIH AND FOUND CABLE GROUNDED.
212 | 10/02/2022 | 01 Oct 1830 - 0745 | QTIF-526 | SSA-101 | ARM | CWEL | 2.75 | 12.75 | 903004 |  | BHS | 1680 | NA | RE-RUN 13 3/8" CSG W/ CRT DUE TO OPEN HOLE UNSTABALITY. (WITH PREVIOUS RUN 13 3/8" CONVENTIONAL CSG GOT HELD UP AT 1684').
214 | 10/02/2022 | 01 Oct 1915 - 0500 | HRDH-1989 | SSA-303 | ARM | NARW | 23.5 | 33.25 | 903047 |  | TH | 475 | NA | NOT ABLE TO PASS OBSTRUCTION @ 475' WITH 24" CSG.
216 | 10/02/2022 | 02 Oct 0600 - 0800 | WDYH-80 | SSA-5914 | SPR | FOT | 2 | 2 | 903045 |  | TF | 3900 | CRT | CRT PACKERS DAMMAGED DURING RUNNING
218 | 10/02/2022 | 01 Oct 2030 - 0215 | RGHB-704 | SSA-5915 | RIG | FOT | 21.25 | 29.75 | 903037 |  | RR | 439 | TDS | TDS COULD NOT BREAK OUT OF HWDP. GRABBER DIES DAMAGED. AFTER BREAKOUT FOUND SAVERSUB THREAD DAMAGED. POOH INSIDE 18 5/8'' SHOE. WHILE CHANGING SAVER SUB, TDS GRABBER WOULD NOT STAY CLOSED WHILE ROTATING.
220 | 10/02/2022 | 19 Sep 0430 - 0130 | UTMN-3148 | SSA-5969 | ARM | WC20 | 20.5 | 270.5 | 902485 |  | WCNT | 10092 | NA | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF.
222 | 10/02/2022 | 02 Oct 1600 - 0000 | ANDR-1207 | T216 | RIG | FOT | 8 | 8 | 903049 |  | RR | 0 | MPMP | VFD SYSTEM TRIPPED DOWN, PUMP OFF, TROUBLESHOOTING SAME.
224 | 10/02/2022 | 02 Oct 1700 - 2300 | SFNY-200 | ZPEC-3 | INW | FOT | 6 | 6 | 902891 |  | TF | 1026 | BP | PREMATURE PARTIALLY SET OF THE 5" RBP ABOVE T.O.LINER
225 | 10/03/2022 | 30 Sep 2315 - 1300 | QTIF-519 | 088TE | RIG | FOT | 8 | 61.75 | 902992 |  | TF | 14011 | SLIPS | WHILE P/U SPS 8-1/2" RSS DIR. ASSY. SLIPS DIE DROPPED IN HOLE, RIH FISHING ASSY. TO FISH IT.
227 | 10/03/2022 | 29 Sep 2130 - 0230 | QTIF-519 | 088TE | SPS | FOT | 11.5 | 37.25 | 902927 |  | BHA | 14011 | MWD | HALL. SPS MWD TOOLS FAILURE, NO SIGNAL, TROUBLESHOOT, NO SUCCESS. POOH TO CHANGE TOOLS.
228 | 10/03/2022 | 30 Sep 2315 - 1300 | QTIF-519 | 088TE | RIG | FOT | 8 | 61.75 | 902992 |  | TF | 14011 | SLIPS | WHILE P/U SPS 8-1/2" RSS DIR. ASSY. SLIPS DIE DROPPED IN HOLE, RIH FISHING ASSY. TO FISH IT.
230 | 10/03/2022 | 01 Oct 2100 - 0615 | DMMM-136 | 910TE | SDM | FOT | 1.25 | 32.25 | 903038 |  | BHA | 16881 | MWD | LOST COMMUNICATION WITH MWD TOOL; TROUBLE SHOOT ANTI-JAMMING PROCEDURE; NO SUCCESS. POOH & CHECK/CHANGE BHA.
232 | 10/03/2022 | 03 Oct 0500 - 1730 | HRDH-1864 | ADC-14 | RIG | FOT | 12.5 | 12.5 | 902892 |  | RR | 13253 | MPMP | PUMP PUP OFF VALVE FAILED WHILE DRILLING.
234 | 10/03/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 291 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
236 | 10/03/2022 | 30 Sep 0000 - 0500 | ABHD-183 | ADC-58L | RIG | FOT | 24 | 77 | 902996 |  | BOP | 0 | BOP | ATTEMPT TO TEST BOP ANNULAR TO 3500 PSI OFFLINE OBSERVED VISUAL LEAK FROM DRILLER SIDE SHEAR/SINGLE RAM BONNETS
253 | 10/03/2022 | 01 Oct 1730 - 0630 | UTMN-2299 | ADC-66L | TK3 | HELD | 1.5 | 37 | 903042 |  | JF | 720 | CSG | WORK ON CASING TO PASS THROUGH TIGHT SPOT AT 560 FT.
273 | 10/03/2022 | 01 Oct 0000 - 0500 | GHZL-72 | ADES-174 | HWP | FOT | 24 | 53 | 903056 |  | TF | 13760 | WLT | HALL LOGGING COULD NOT ACQUIRE SAMPLE, ELECTRICAL FAILURE IN SAMPLE TOOLS (LOSS OF COMMUNICATION OF ONE MODULE OF SAMPLE CHAMBER SECTION),
275 | 10/03/2022 | 15 Sep 0100 - 0500 | HRDH-2122 | ADES-889 | ARM | PCPF | 24 | 419.5 | 902524 |  | BHS | 10881 | NA | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL.
277 | 10/03/2022 | 03 Oct 0345 - 0500 | MRJN-57 | ADM-262 | RIG | FOT | 1.25 | 1.25 | 903136 |  | RR | 5521 | DWKS | DRILLERS SIDE ELMAGO BEARING FAILED.
278 | 10/03/2022 | 03 Oct 1500 - 0500 | SFNY-263 | ADM-266 | MRN | SRVC | 14 | 14 | 903117 |  | WO | 0 | NA | WAITING ON DIVING TO REMOVE DEBRIS NEAR PF SFNY-258/263 THEN THE RIG TO MOVE IN.
280 | 10/03/2022 | 01 Oct 0500 - 1500 | SFNY-263 | ADM-266 | ARN | SRVC | 10 | 58 | 903044 |  | WO | 0 | NA | WAITING ON BARGE ARABIYAH-6 MOVE OUT FROM PF SFNY-258/263 LOCATION, TO ALLOW DIVERS TO REMOVE DEBRIS NEAR PF THEN THE RIG TO MOVE IN.
281 | 10/03/2022 | 03 Oct 1500 - 0500 | SFNY-263 | ADM-266 | MRN | SRVC | 14 | 14 | 903117 |  | WO | 0 | NA | WAITING ON DIVING TO REMOVE DEBRIS NEAR PF SFNY-258/263 THEN THE RIG TO MOVE IN.
283 | 10/03/2022 | 03 Oct 1400 - 0500 | MRJN-537 | ARO-4001 | RIG | OTH | 15 | 15 | 903119 |  | UPRA | 10308 | NA | RIG MISTAKE, AFTER POOH WITH 8 1/2" REAMING/DLR ASSY ON 5 1/2" HWDP, FOUND THE RIG CREW RUN 6 STANDS OF 5 1/2" HWDP ONLY, NOT 12 STANDS, RIH BACK WITH REST OF 5 1/2" HWDP TO BTM.
285 | 10/03/2022 | 03 Oct 0000 - 0500 | ZULF-2054 | BB-84A | RIG | PPMP | 5 | 5 | 903014 |  | UPRA | 149 | NA | RIG UNABLE TO JACK UP DUE TO DEFLECTED D1 BULL GEAR
287 | 10/03/2022 | 03 Oct 1900 - 0500 | HRDH-2421 | BCTD-4 | BHI | FOT | 10 | 10 | 903156 |  | BHA | 11909 | MWD | LOST COMMUNICTION WITH THE TOOL, POH TO CHANGE BHA.
289 | 10/03/2022 | 02 Oct 0130 - 0815 | MRJN-741 | CG-1 | BHI | FOT | 3.25 | 6.75 | 902890 |  | BHA | 376 | MWD | TROUBLESHOOTING ON BHI MWD TOOLS.
291 | 10/03/2022 | 03 Oct 1415 - 0500 | HMYM-450404 | HWU-1 | RIG | FOT | 14.75 | 14.75 | 903097 |  | RR | 0 | HSYS | BLEED OFF ON STRIPPINF STACK MALFUNTIONING AND NOT OPENING,
292 | 10/03/2022 | 03 Oct 1900 - 0500 | BRRI-310 | MP-1 | ARM | DAY | 10 | 10 | 903010 |  | WON | 0 | NA | WAIT ON DAYLIGHT TO CONTINUE WORKING LEGS TO MINIMIZE RPD READING.
294 | 10/03/2022 | 03 Oct 0630 - 1300 | BRRI-310 | MP-1 | ARM | WTHR | 6.5 | 6.5 | 903009 |  | WON | 0 | NA | WEATHER IS UNFAVORABLE FOR WORKING LEGS TO MINIMIZE RPD READING. WOW.
295 | 10/03/2022 | 03 Oct 1900 - 0500 | BRRI-310 | MP-1 | ARM | DAY | 10 | 10 | 903010 |  | WON | 0 | NA | WAIT ON DAYLIGHT TO CONTINUE WORKING LEGS TO MINIMIZE RPD READING.
297 | 10/03/2022 | 03 Oct 0945 - 1030 | BRRI-562 | NADRU-1 | SWT | FOT | .75 | .75 | 903098 |  | TF | 0 | WTSE | OBSERVED SLIGHT OIL BUBBLE CAME OUT OF BLAYLOCK PRESSURE VALVE INSTALLED AT THE TOP OF FRAC TANK#4.
299 | 10/03/2022 | 03 Oct 1645 - 0045 | SDGM-1221 | NBR-115S | RIG | FOT | 8 | 8 | 903121 |  | RR | 10845 | TDS | HIGH ERRATIC TORQUE AND LOST OF COMMUNICATION TO TDS SYSTEM.
301 | 10/03/2022 | 02 Oct 0500 - 0500 | QTIF-503 | NBR-263S | RIG | OTH | 24 | 48 | 903118 |  | UPRA | 0 | NA | RIG UNDER UNPLANNED MAINTENANCE, AS THE ALLOCATED RIG MAINTENANCE DAYS OF THE YEAR 2022 IS ZERO DAYS.
303 | 10/03/2022 | 03 Oct 1930 - 0500 | ANDR-1018 | NBR-654S | RIG | FOT | 9 | 9 | 903015 |  | DSF | 3835 | STRG | OBSERVED PRESSURE DROP FROM +/-2000 PSI / 960 GPM, IN TWO STANDS PRESSURE DROP +/- 350 PSI. NO VISUAL LEAK ON SURFACE, NO DOWNHOLE LOSSES OBSERVED. CIRCULATE OFF BOTTOM WITH CONSTANT PRESSURE +/- 1450 PSI. ROTARY DRILL 22" HOLE SECTION WITH 67 PCF HBM, 100% RETURN. OBSERVE PRESSURE DECREASING +/- 100 PSI.POOH
305 | 10/03/2022 | 03 Oct 1545 - 0500 | MRJN-673 | PN-9 | BHI | FOT | 13.25 | 13.25 | 903008 |  | BHA | 17199 | MMOT | OBSERVED HIGH PUMP PRESSURE AND HIGHER TORQUE VALUE WITH LOW WEIGHT ON BIT, THEN FOUND MUD MOTOR RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD.
307 | 10/03/2022 | 03 Oct 0815 - 0100 | HSBH-25 | RBP-50A | BC | HERR | 16.75 | 16.75 | 903012 |  | JF | 645 | TBG | BAKER FAILED TO SET FLOT INTO TRSSSV.
309 | 10/03/2022 | 02 Oct 0230 - 1700 | UTMN-3189 | SCTD-1 | RIG | FOT | 12 | 14.5 | 902889 |  | BHA | 10620 | MMOT | D&M LOST TELEMETRY WITH DOWNHOLE TOOLS.
310 | 10/03/2022 | 03 Oct 1645 - 0430 | BRRI-1144 | SINO-22 | RIG | FOT | 11.75 | 11.75 | 903059 |  | RR | 1367 | TDS | CHANGE HYDRAULIC CYLINDERS ON TDS LINK TILT ASSEMBLY WITH NEW ONES & REPLACED FAULTY COUNTER BALANCE CONTROL VALVE WITH A NEW ONE.
312 | 10/03/2022 | 02 Oct 0200 - 0500 | BRRI-1144 | SINO-22 | SDM | FOT | 10 | 13 | 903052 |  | BHA | 11062 | RSS | RSS FAILURE. TRIP OUT TO CHANGE THE TOOL.
313 | 10/03/2022 | 03 Oct 1645 - 0430 | BRRI-1144 | SINO-22 | RIG | FOT | 11.75 | 11.75 | 903059 |  | RR | 1367 | TDS | CHANGE HYDRAULIC CYLINDERS ON TDS LINK TILT ASSEMBLY WITH NEW ONES & REPLACED FAULTY COUNTER BALANCE CONTROL VALVE WITH A NEW ONE.
315 | 10/03/2022 | 30 Sep 0530 - 0100 | UTMN-1245 | SINO-26 | ARM | WC20 | 20 | 91.5 | 903120 |  | WCNT | 6300 | NA | WATER INJECTOR WELL REQUIRES INCREASING MW TO CONTROL THE WELL.
333 | 10/03/2022 | 22 Sep 0500 - 0500 | BRRI-1148 | SND-2004 | HSL | FOT | 23 | 252.5 | 902598 |  | TF | 8196 | PLUGN | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL.
335 | 10/03/2022 | 25 Sep 1400 - 0500 | AWTD-104001 | SND-2007 | NPC | TOWC | 24 | 188 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
336 | 10/03/2022 | 02 Oct 0830 - 0700 | HRDH-1291 | SND-2008 | SCD | FOT | 2 | 22.5 | 903005 |  | SURV | 10966 | GYRO | LOST COMMUNICATION WITH GYRO TOOL DOWN HOLE BEFORE SURVEYING
338 | 10/03/2022 | 27 Sep 0630 - 0500 | HRDH-1291 | SND-2008 | ARM | UVLC | 22 | 144 | 902798 |  | LCIR | 0 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
339 | 10/03/2022 | 02 Oct 0830 - 0700 | HRDH-1291 | SND-2008 | SCD | FOT | 2 | 22.5 | 903005 |  | SURV | 10966 | GYRO | LOST COMMUNICATION WITH GYRO TOOL DOWN HOLE BEFORE SURVEYING
341 | 10/03/2022 | 03 Oct 1415 - 0100 | MNIF-142 | SP-110 | ARM | FRFM | 10.75 | 10.75 | 903060 |  | LCIR | 5892 | NA | CURE LOSSES WITH LCM PILL
343 | 10/03/2022 | 03 Oct 1630 - 2230 | LIDM-2 | SP-258 | HWP | FOT | 6 | 6 | 903011 |  | TF | 7367 | WLT | WIRE LINE TOOLS LOST COMUNICATION ,TROUBLE SHOOTING AND FOUND ALAT COMBO TOOLS NOT WORKING.
345 | 10/03/2022 | 02 Oct 1030 - 1200 | HRDH-2353 | SSA-302 | ARM | FNFS | 7 | 22 | 903057 |  | LROP | 5062 | BIT | OBSERVED HIGH ERRATIC TRQ. WHILE DRLG. @ 5062' AND VERY SLOW ROP USING 16" PDC BIT INTO BIYADH FORM. CHC AND POOH TO SURFACE AND CHECK THE BIT. BIT DULL GRADING: 7-6-JD-A-X-2-CT-BHA (FOUND METAL PIECES AT INNER ROW). M/U & RIH 16" CLEAN OUT BHA ON NEW 16" SECURITY TCM BIT, RIH TO BTM, CHC, DRLG. TO 5,110' & CHC & POOH.
347 | 10/03/2022 | 01 Oct 1915 - 0500 | HRDH-1989 | SSA-303 | ARM | NARW | 24 | 57.25 | 903047 |  | TH | 475 | NA | NOT ABLE TO PASS OBSTRUCTION @ 475' WITH 24" CSG.
349 | 10/03/2022 | 03 Oct 1600 - 0500 | RGHB-704 | SSA-5915 | RIG | FOT | 13 | 13 | 903013 |  | RR | 1029 | TDS | TDS GRABBER BLOCK PINS FAILED WHILE ATTEMPTING TO BREAK OUT SAVER SUB FROM HWDP.
350 | 10/04/2022 | 04 Oct 1215 - 1315 | HRDH-1864 | ADC-14 | RIG | FOT | 1 | 1 | 903158 |  | RR | 13529 | TDS | TORQUE CLAMP HYDRAULIC HOSE LEAKING.
352 | 10/04/2022 | 04 Oct 0615 - 0830 | HRDH-1864 | ADC-14 | RIG | FOT | 2.25 | 2.25 | 903100 |  | RR | 13455 | MPMP | STAND PIPE AND MUD CAP LEAKING HAD TO REPLACE SEAL.
353 | 10/04/2022 | 04 Oct 1215 - 1315 | HRDH-1864 | ADC-14 | RIG | FOT | 1 | 1 | 903158 |  | RR | 13529 | TDS | TORQUE CLAMP HYDRAULIC HOSE LEAKING.
355 | 10/04/2022 | 04 Oct 0000 - 0430 | UTMN-2309 | ADC-34 | SPS | FOT | 4.5 | 4.5 | 903176 |  | BHA | 10527 | MWD | MWD WOULD NOT GIVE SIGNAL.
357 | 10/04/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 315 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
359 | 10/04/2022 | 30 Sep 0000 - 0000 | ABHD-183 | ADC-58L | RIG | FOT | 19 | 96 | 902996 |  | BOP | 0 | BOP | ATTEMPT TO TEST BOP ANNULAR TO 3500 PSI OFFLINE OBSERVED VISUAL LEAK FROM DRILLER SIDE SHEAR/SINGLE RAM BONNETS
371 | 10/04/2022 | 04 Oct 1800 - 0500 | HWYH-27 | ADES-14 | OES | HSCM | 11 | 11 | 903180 |  | LCIR | 6540 | NA | STRING PLUGGED.
373 | 10/04/2022 | 01 Oct 0000 - 1715 | GHZL-72 | ADES-174 | HWP | FOT | 12.25 | 65.25 | 903056 |  | TF | 13760 | WLT | HALL LOGGING COULD NOT ACQUIRE SAMPLE, ELECTRICAL FAILURE IN SAMPLE TOOLS (LOSS OF COMMUNICATION OF ONE MODULE OF SAMPLE CHAMBER SECTION),
375 | 10/04/2022 | 03 Oct 0345 - 0500 | MRJN-57 | ADM-262 | RIG | FOT | 24 | 25.25 | 903136 |  | RR | 5521 | DWKS | DRILLERS SIDE ELMAGO BEARING FAILED.
376 | 10/04/2022 | 03 Oct 1500 - 1030 | SFNY-263 | ADM-266 | MRN | SRVC | 5.5 | 19.5 | 903117 |  | WO | 0 | NA | WAITING ON DIVING TO REMOVE DEBRIS NEAR PF SFNY-258/263 THEN THE RIG TO MOVE IN.
378 | 10/04/2022 | 04 Oct 1030 - 0500 | SFNY-263 | ADM-266 | ARM | WTHR | 18.5 | 18.5 | 903105 |  | WON | 0 | NA | AWAIT HIGH WATER SLACK & SUITABLE WEATHER CONDITION.
379 | 10/04/2022 | 03 Oct 1500 - 1030 | SFNY-263 | ADM-266 | MRN | SRVC | 5.5 | 19.5 | 903117 |  | WO | 0 | NA | WAITING ON DIVING TO REMOVE DEBRIS NEAR PF SFNY-258/263 THEN THE RIG TO MOVE IN.
381 | 10/04/2022 | 04 Oct 0500 - 1230 | MRJN-900 | ADM-337 | ARM | WTHR | 7.5 | 7.5 | 903143 |  | WON | 6905 | NA | UNABLE TO FLOW BACK WELL DUE TO WIND SPEED BELOW 5 KNTS
383 | 10/04/2022 | 04 Oct 1215 - 0500 | MRJN-3013 | ADM-339 | RIG | GRF | 16.75 | 16.75 | 903165 |  | UPRA | 5979 | PSYS | GEN#3 - TURBOCHARGER FAILURE WHICH TRIGER FIRE ALARM.
385 | 10/04/2022 | 03 Oct 1400 - 1330 | MRJN-537 | ARO-4001 | RIG | OTH | 8.5 | 23.5 | 903119 |  | UPRA | 10308 | NA | RIG MISTAKE, AFTER POOH WITH 8 1/2" REAMING/DLR ASSY ON 5 1/2" HWDP, FOUND THE RIG CREW RUN 6 STANDS OF 5 1/2" HWDP ONLY, NOT 12 STANDS, RIH BACK WITH REST OF 5 1/2" HWDP TO BTM.
387 | 10/04/2022 | 04 Oct 1300 - 1700 | MRJN-741 | CG-1 | BCM | FOT | 4 | 4 | 903166 |  | TF | 9182 | PUMP | TROUBLESHOOTING ON BAKER CEMENT UNIT.
389 | 10/04/2022 | 04 Oct 0730 - 1500 | ZULF-2015 | ENS-108 | ARN | ORDS | 7.5 | 7.5 | 903099 |  | WO | 9830 | NA | GOC ASKED TO CHANGE WELL TRAJECTORY WHICH IS DIFFERENT FROM APPROVED DIRECTIONAL PLAN, DECISION WAS TO POOH TO 9-5/8" CASING SHOE UNTILL RECEIVE NEW DIRECTIONAL PLAN (LOST TIME ON PETROLEUM ENGINEERING).
391 | 10/04/2022 | 03 Oct 1400 - 1230 | HRDH-2313 | NBR-591S | ARM | SMMF | 5.75 | 20.75 | 903144 |  | STUK | 4063 | STZRM | GOT STUCK WHILE CLEANOUT/PUSHING DOWN PLUGS DEBRIS W/CLEANOUT/STRING MILL.
393 | 10/04/2022 | 03 Oct 1930 - 0245 | ANDR-1018 | NBR-654S | NPJ | FOT | 21.75 | 30.75 | 903015 |  | BHA | 3835 | SKSUB | OBSERVED PRESSURE DROP +/- 350 PSI.POOH.REPLACE SHOCK SUB.
395 | 10/04/2022 | 03 Oct 1545 - 0500 | MRJN-673 | PN-9 | BHI | FOT | 24 | 37.25 | 903122 |  | BHA | 17199 | MMOT | WHILE DRILLING OBSERVED 200-300 PSI INCREASE IN PRESSSURE & HIGH TORQUE WITH LOW WOB. STOP DRILLING & CIRCULATE, THEN FOUND MUD MOTOR RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD.
397 | 10/04/2022 | 04 Oct 1100 - 1400 | ZULF-1336 | QMS-MARYAH | ARM | WTHR | 3 | 3 | 903164 |  | WON | 0 | NA | UNFAVORABLE WEATHER FOR FLARING OPERATIONS (WIND SPEED 2-3 KNTS)
399 | 10/04/2022 | 04 Oct 0030 - 0500 | MRJN-651 | SDA | RIG | GRF | 4.5 | 4.5 | 903174 |  | UPRA | 4036 | TDS | POOH TO CHANGE OUT DAMAGED TDS SAVER SUBE.
401 | 10/04/2022 | 02 Oct 0200 - 1715 | BRRI-1144 | SINO-22 | SDM | FOT | 12.25 | 27.5 | 903052 |  | BHA | 11062 | RSS | RSS FAILURE. TRIP OUT TO CHANGE THE TOOL.
412 | 10/04/2022 | 22 Sep 0500 - 0500 | BRRI-1148 | SND-2004 | HSL | FOT | 24 | 276.5 | 902598 |  | TF | 8196 | PLUGN | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL.
414 | 10/04/2022 | 25 Sep 1400 - 0500 | AWTD-104001 | SND-2007 | NPC | TOWC | 24 | 212 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
416 | 10/04/2022 | 27 Sep 0630 - 0500 | HRDH-1291 | SND-2008 | ARM | UVLC | 24 | 168 | 902798 |  | LCIR | 0 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
418 | 10/04/2022 | 04 Oct 1215 - 1715 | MNIF-868 | SND-2010 | NCT | FOT | 5 | 5 | 903159 |  | TF | 7064 | CTBG | DOWNTIME ON NESR CT: HAVE COUPLING BROKEN FOR N2 COOLING SYSTEM.
420 | 10/04/2022 | 04 Oct 1900 - 0400 | HRDH-457 | SP-154 | SDM | ETRQ | 9 | 9 | 903179 |  | LROP | 6330 | BHA | LOW ROP LESS THAN 35 FT/HRS.
422 | 10/04/2022 | 04 Oct 0500 - 0500 | DYBN-1 | SP-160 | GD2 | FOT | 24 | 24 | 903163 |  | TF | 0 | CTBG | WHILE FLUSHING COILED TUBING WITH RIG PUMP, PUMPED 29 BBLS AT 1.5 BPM, OBSERVE PRESSURE INCREASE TO 4000 PSI.BLEED OFF PRESSURE & ATTEMPTED AGAIN WITH SAME RESULT.OBSERVE COILED TUBING PLUGGED.
423 | 10/04/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | FOT | 9.25 | 9.25 | 903173 |  | RR | 1121 | TDS | WHILE MAKING CONNECTION TO DRILL AHEAD. TOPDRIVE WAS EXTREMELY DIFFICULT TO BREAK OUT OF HWDP.
425 | 10/04/2022 | 03 Oct 1600 - 1800 | RGHB-704 | SSA-5915 | RIG | FOT | 13 | 26 | 903013 |  | RR | 1029 | TDS | TDS GRABBER BLOCK PINS FAILED WHILE ATTEMPTING TO BREAK OUT SAVER SUB FROM HWDP.
426 | 10/04/2022 | 04 Oct 1845 - 1915 | RGHB-704 | SSA-5915 | RIG | FOT | .5 | .5 | 903172 |  | RR | 1032 | TDS | WHILE DRILLING LOST FUNCTION OF MUD PUMPS AND TOPDRIVE
427 | 10/04/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | FOT | 9.25 | 9.25 | 903173 |  | RR | 1121 | TDS | WHILE MAKING CONNECTION TO DRILL AHEAD. TOPDRIVE WAS EXTREMELY DIFFICULT TO BREAK OUT OF HWDP.
429 | 10/04/2022 | 04 Oct 0530 - 0900 | UTMN-2015 | SSA-5964 | WCR | FOT | 3.5 | 3.5 | 903160 |  | TF | 0 | CTRQ | CUMULATIVE LOST TIME ON WFRD TRS. CHANGING POWER TONG, DIES, SLIPS AND REPLACING JAM UNIT.
431 | 10/04/2022 | 04 Oct 1230 - 0500 | UTMN-3148 | SSA-5969 | WUD | FOT | 16.5 | 16.5 | 903162 |  | BHA | 10372 | FV | WFD MPD FLOAT VALVES FAILED.
433 | 10/05/2022 | 05 Oct 1300 - 1400 | QTIF-519 | 088TE | RIG | FOT | 1 | 1 | 903189 |  | RR | 14924 | MPMP | RIG REPAIR MUD PUMPS#2 & 3
434 | 10/05/2022 | 05 Oct 1445 - 0115 | HRDH-1864 | ADC-14 | RIG | FOT | 10.5 | 10.5 | 903182 |  | RR | 13834 | MPMP | MODULE FOR MUD PUMP # 2 LEAKING.
436 | 10/05/2022 | 05 Oct 0800 - 1300 | HRDH-1864 | ADC-14 | RIG | FOT | 5 | 5 | 903107 |  | RR | 13813 | MPMP | FAILURE OF PUMP #2 DUE TO LEAK OF JUMPER HOSE .
437 | 10/05/2022 | 05 Oct 1445 - 0115 | HRDH-1864 | ADC-14 | RIG | FOT | 10.5 | 10.5 | 903182 |  | RR | 13834 | MPMP | MODULE FOR MUD PUMP # 2 LEAKING.
439 | 10/05/2022 | 05 Oct 1445 - 0500 | HRDH-2249 | ADC-15 | HWP | HINW | 14.25 | 14.25 | 903187 |  | STUK | 14482 | WLT | HALLIBURTON LOGGING TOOLS (RUN#2) GOT STUCK.
441 | 10/05/2022 | 04 Oct 0000 - 0500 | UTMN-2309 | ADC-34 | SPS | FOT | 23.5 | 28.5 | 903176 |  | BHA | 10527 | MWD | MWD WOULD NOT GIVE SIGNAL.
443 | 10/05/2022 | 05 Oct 0100 - 0500 | UTMN-2360 | ADC-43L | TK1 | HELD | 4 | 4 | 903197 |  | JF | 775 | CSG | WORK ON CASING TO PASS THROUGH TIGHT SPOT AT 650 FT.
445 | 10/05/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 339 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
447 | 10/05/2022 | 05 Oct 2245 - 0315 | ABHD-631 | ADC-57L | TK3 | WTHR | 4.5 | 4.5 | 903198 |  | WON | 5790 | NA | OBSERVED HEAVY FOG & VERY POOR VISIBILITY, STOPPED OPERATION & WAIT ON WEATHER.
449 | 10/05/2022 | 05 Oct 0230 - 0430 | ABHD-183 | ADC-58L | RIG | FOT | 2 | 2 | 903203 |  | RR | 4258 | TDS | COULDN'T ABLE TO POOH TEST ASSY. DUE TO ELECTRICAL FAULT OF TDS SYSTEM.
451 | 10/05/2022 | 05 Oct 1500 - 2000 | SDGM-1259 | ADC-67L | SGR | FOT | 5 | 5 | 903199 |  | TF | 15640 | MLOG | SLB GEOLOG REAL TIME TRANSMISSION FAILURE. GEO SERVICE TROUBLE SHOOT REAL TIME LAG DATA-OK
467 | 10/05/2022 | 05 Oct 0845 - 0330 | UTMN-1952 | ADES-173 | RIG | FOT | 18.75 | 18.75 | 903123 |  | RR | 10865 | DWKS | DRAW WORK TRACTION MOTORS A & B WENT OUT.
469 | 10/05/2022 | 03 Oct 0345 - 0330 | MRJN-57 | ADM-262 | RIG | FOT | 22.5 | 47.75 | 903136 |  | RR | 5521 | DWKS | DRILLERS SIDE ELMAGCO BEARING FAILED.
471 | 10/05/2022 | 04 Oct 1030 - 0500 | SFNY-263 | ADM-266 | ARM | WTHR | 24 | 42.5 | 903105 |  | WON | 0 | NA | AWAIT HIGH WATER SLACK & SUITABLE WEATHER CONDITION.
473 | 10/05/2022 | 05 Oct 0500 - 1600 | MRJN-900 | ADM-337 | ARM | WTHR | 11 | 11 | 903192 |  | WON | 13019 | NA | UNABLE TO FLOW BACK WELL DUE TO WIND SPEED BELOW 5 KNTS
474 | 10/05/2022 | 05 Oct 1800 - 0500 | MRJN-3013 | ADM-339 | RIG | GRF | 11 | 11 | 903202 |  | UPRA | 6260 | PSYS | LOST RIG POWER WHILE REAMING AND WASHING WITH STAND #62 PRIOR TO MAKE CONNECTION TO DRILL AHEAD
476 | 10/05/2022 | 04 Oct 1430 - 0800 | MRJN-3013 | ADM-339 | RIG | GRF | 3 | 17.5 | 903165 |  | UPRA | 5979 | PSYS | GEN#3 - TURBOCHARGER FAILURE WHICH TRIGER FIRE ALARM.
477 | 10/05/2022 | 05 Oct 1800 - 0500 | MRJN-3013 | ADM-339 | RIG | GRF | 11 | 11 | 903202 |  | UPRA | 6260 | PSYS | LOST RIG POWER WHILE REAMING AND WASHING WITH STAND #62 PRIOR TO MAKE CONNECTION TO DRILL AHEAD
479 | 10/05/2022 | 05 Oct 1045 - 0500 | MRJN-537 | ARO-4001 | WLH | FOT | 18.25 | 18.25 | 903191 |  | TF | 10308 | HGRL | TRY TO SET 7" WFD LINER HGR, NO SUCCESS, TROUBLESHOOTING SAME, NO SUCCESS, POOH TO CHANGE 7" LINER HGR ASSY.
481 | 10/05/2022 | 02 Oct 0900 - 0500 | ZULF-2066 | ED-85A | ARM | PCPF | 24 | 91 | 903055 |  | TH | 6125 | NA | WHILE RUNNING 9-5/8" CSG HAD OBSTRUCTION AT 6215 FT , WASH DOWN AND WORK ON IT CAN NOT PASS.
482 | 10/05/2022 | 05 Oct 1730 - 1930 | ZULF-2015 | ENS-108 | SDM | FOT | 2 | 2 | 903188 |  | BHA | 10922 | LWD | SLB TROUBLESHOOT TOOLS DUE TO HIGH NOISE & NO CLEAR SIGNAL.
484 | 10/05/2022 | 05 Oct 0830 - 1430 | ZULF-2015 | ENS-108 | RIG | FOT | 6 | 6 | 903146 |  | RR | 10779 | TDS | OBSERVED WASH PIPE LEAKS, POOH TO SHOE TO CHANGE IT.
485 | 10/05/2022 | 05 Oct 1730 - 1930 | ZULF-2015 | ENS-108 | SDM | FOT | 2 | 2 | 903188 |  | BHA | 10922 | LWD | SLB TROUBLESHOOT TOOLS DUE TO HIGH NOISE & NO CLEAR SIGNAL.
487 | 10/05/2022 | 05 Oct 1230 - 2130 | BRRI-310 | MP-1 | RIG | FOT | 9 | 9 | 903185 |  | RR | 0 | WATER | EXCESSIVE TIME DURING PRELOAD OPERATION DUE TO GROUNDED 1 EA RAW WATER PUMP.
489 | 10/05/2022 | 05 Oct 2345 - 0100 | GHZL-106 | NA-128S | SWL | FOT | 1.25 | 1.25 | 903204 |  | TF | 13700 | WLU | AFTER REACHING 2ND PRESSURE POINT, SLB UNIT SUDDENLY GOT SHUT DOWN DUE TO GENERATOR PROBLEM.
491 | 10/05/2022 | 05 Oct 0030 - 0500 | SHYB-134 | NA-207S | RIG | FOT | 4.5 | 4.5 | 903193 |  | TF | 5847 | SFLN | WHILE DRILLING KELLY HOSE STARTED TO LEAK.
493 | 10/05/2022 | 05 Oct 1930 - 0500 | QTIF-503 | NBR-263S | RIG | OTH | 9.5 | 9.5 | 903190 |  | UPRA | 0 | NA | INCIDENT INVESTIGATION
494 | 10/05/2022 | 05 Oct 1730 - 0030 | MRJN-673 | PN-9 | RIG | FOT | 7 | 7 | 903186 |  | RR | 17353 | TDS | OBSERVED LEAKING IN TOP DRIVE WASH PIPE.
496 | 10/05/2022 | 03 Oct 1545 - 1445 | MRJN-673 | PN-9 | BHI | FOT | 9.75 | 47 | 903122 |  | BHA | 17199 | MMOT | WHILE DRILLING OBSERVED 200-300 PSI INCREASE IN PRESSSURE & HIGH TORQUE WITH LOW WOB. STOP DRILLING & CIRCULATE, THEN FOUND MUD MOTOR RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD.
497 | 10/05/2022 | 05 Oct 1730 - 0030 | MRJN-673 | PN-9 | RIG | FOT | 7 | 7 | 903186 |  | RR | 17353 | TDS | OBSERVED LEAKING IN TOP DRIVE WASH PIPE.
499 | 10/05/2022 | 04 Oct 0030 - 0900 | MRJN-651 | SDA | RIG | GRF | 4 | 8.5 | 903174 |  | UPRA | 4036 | TDS | POOH TO CHANGE OUT DAMAGED TDS SAVER SUBE.
501 | 10/05/2022 | 05 Oct 0000 - 0430 | SFNY-2005 | SINO-29N | RIG | XTRI | 4.5 | 4.5 | 903196 |  | JF | 8671 | BOP | EXCESSIVE TIME TO PERFORM NORMAL OPERATION
521 | 10/05/2022 | 05 Oct 0130 - 0330 | BRRI-1148 | SND-2004 | ARM | WTHR | 2 | 2 | 903201 |  | WON | 8134 | NA | HEAVY FOG, NO VISIBILITY TO POOH & L/DN TBG ON PIPE RACK
523 | 10/05/2022 | 22 Sep 0500 - 0500 | BRRI-1148 | SND-2004 | HSL | FOT | 22 | 298.5 | 902598 |  | TF | 8196 | PLUGN | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL.
524 | 10/05/2022 | 05 Oct 0130 - 0330 | BRRI-1148 | SND-2004 | ARM | WTHR | 2 | 2 | 903201 |  | WON | 8134 | NA | HEAVY FOG, NO VISIBILITY TO POOH & L/DN TBG ON PIPE RACK
526 | 10/05/2022 | 25 Sep 1400 - 0500 | AWTD-104001 | SND-2007 | NPC | TOWC | 24 | 236 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
528 | 10/05/2022 | 27 Sep 0630 - 0500 | HRDH-1291 | SND-2008 | ARM | UVLC | 24 | 192 | 902798 |  | LCIR | 0 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
530 | 10/05/2022 | 05 Oct 2230 - 0130 | MNIF-868 | SND-2010 | ARM | WTHR | 3 | 3 | 903194 |  | WON | 7064 | NA | SUSPENDED OPERATION DUE BAD WEATHER CONDITIONS (FOG AND HUMIDITY) -NO VISIBILITY.
532 | 10/05/2022 | 05 Oct 1430 - 0100 | QTIF-752 | SSA-102 | ARM | STBH | 8.75 | 8.75 | 903195 |  | STUK | 1625 | BHA | OBSERVED HIGH TORQUE & STRING GOT STUCK WORK ON STRING, UNTIL STRING GOT FREE.
534 | 10/05/2022 | 05 Oct 0500 - 0600 | HRDH-2353 | SSA-302 | SPS | SDIR | 1 | 1 | 903147 |  | STUK | 5425 | MMOT | GOT STUCK WHILE SLIDING. WORK STUCK PIPE, WORK STUCK STRG. TILL GOT FREE.
535 | 10/05/2022 | 05 Oct 0730 - 0900 | HRDH-1989 | SSA-303 | RIG | FOT | 1.5 | 1.5 | 903206 |  | RR | 520 | TDS | WORK ON TDS LINK TILT.
537 | 10/05/2022 | 05 Oct 2200 - 0000 | HRDH-1989 | SSA-303 | RIG | XTRI | 2 | 2 | 903205 |  | JF | 800 | NA | EXTRA TIME SPENT TO P/U REMAINING BHA DUE TO CREW COMPETENCY.
538 | 10/05/2022 | 05 Oct 0730 - 0900 | HRDH-1989 | SSA-303 | RIG | FOT | 1.5 | 1.5 | 903206 |  | RR | 520 | TDS | WORK ON TDS LINK TILT.
540 | 10/05/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 33.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON. EVAULATE POWER SYSTEM AND TDS MOTOR RPM'S.
542 | 10/05/2022 | 04 Oct 1230 - 0500 | UTMN-3148 | SSA-5969 | WUD | FOT | 24 | 40.5 | 903162 |  | BHA | 10372 | FV | WFD MPD FLOAT VALVES FAILED.
544 | 10/06/2022 | 06 Oct 1000 - 1230 | MNIF-126 | 095TE | RIG | HERR | 2.5 | 2.5 | 903207 |  | JF | 8510 | WH | HAD LEAK FROM ONE OF LOCK DOWN SCREW BOLTS WHILE PRESSURE TEST PKR, DUE TO IT WAS NOT TIGHTEN PROPERLY, RE- TIGHTEN OK.
545 | 10/06/2022 | 06 Oct 1945 - 2015 | HRDH-1864 | ADC-14 | RIG | FOT | .5 | .5 | 903215 |  | RR | 14021 | PSYS | UNABLE TO DRILL AHEAD DUE TO POWER FAILURE IN PCR#1 SYSTEM, MEANWHILE CIRCULATE AND ROTAT STRING.
547 | 10/06/2022 | 06 Oct 1630 - 1730 | HRDH-1864 | ADC-14 | RIG | FOT | 1 | 1 | 903214 |  | RR | 14000 | CSYS | STAND PIPE LEAKING HAD TO REPLACE SEAL.
548 | 10/06/2022 | 06 Oct 1945 - 2015 | HRDH-1864 | ADC-14 | RIG | FOT | .5 | .5 | 903215 |  | RR | 14021 | PSYS | UNABLE TO DRILL AHEAD DUE TO POWER FAILURE IN PCR#1 SYSTEM, MEANWHILE CIRCULATE AND ROTAT STRING.
550 | 10/06/2022 | 05 Oct 1445 - 2315 | HRDH-2249 | ADC-15 | HWP | HINW | 18.25 | 32.5 | 903187 |  | STUK | 14482 | WLT | HALLIBURTON LOGGING TOOLS (RUN#2) GOT STUCK.
552 | 10/06/2022 | 06 Oct 0315 - 0500 | UTMN-2309 | ADC-34 | RIG | FOT | 1.75 | 1.75 | 903241 |  | RR | 14021 | CSYS | STANDPIPE HOSE LEAKING.
554 | 10/06/2022 | 05 Oct 0100 - 0500 | UTMN-2360 | ADC-43L | TK1 | HELD | 24 | 28 | 903197 |  | JF | 775 | CSG | WORK ON CASING TO PASS THROUGH TIGHT SPOT AT 650 FT.
556 | 10/06/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 363 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
558 | 10/06/2022 | 06 Oct 0530 - 2300 | HWYH-1300 | ADC-65L | PM1 | FOT | 17.5 | 17.5 | 903212 |  | TF | 3242 | CRT | WHILE RUNNING 18 5/8" CASING USING CRT, PACKER CUP ASSEMBLY GOT DETACHED AND DROPPED FROM A HEIGHT
574 | 10/06/2022 | 05 Oct 1800 - 0500 | MRJN-3013 | ADM-339 | RIG | GRF | 24 | 35 | 903202 |  | UPRA | 6260 | PSYS | LOST RIG POWER WHILE REAMING AND WASHING WITH STAND #62 PRIOR TO MAKE CONNECTION TO DRILL AHEAD.
575 | 10/06/2022 | 06 Oct 1200 - 2200 | MRJN-537 | ARO-4001 | RIG | FOT | 10 | 10 | 903240 | 903191 | RR | 10308 | DWKS | OBSERVED VFD FAULT & UNABLE TO FUNCTION DRAW WORK, TROUBLESHOOTING SAME, CLEANED CHOPPERS, RE-ASSIGN VFD, WORKING OK.
577 | 10/06/2022 | 05 Oct 1045 - 0500 | MRJN-537 | ARO-4001 | RIG | OTH | 13 | 42.25 | 903191 |  | UPRA | 10308 | NA | UNABLE TO SET 7" WFD LINER HGR DUE TO SETTING BALLS JAMMED WITH PLASTIC PART OF DP MAT INSIDE DP, POOH TO CLEAN & DRIFT DP.
578 | 10/06/2022 | 06 Oct 0600 - 0700 | MRJN-537 | ARO-4001 | ITS | FOT | 1 | 1 | 903239 | 903191 | TF | 10308 | CTRQ | ITS POWER TONG UNABLE TO BREAK OUT 7" CSG JT, TROUBLESHOOTING SAME, NO SUCCESS, RD FAILED POWER TONG AND RU BACK UP POWER TONG.
579 | 10/06/2022 | 06 Oct 1200 - 2200 | MRJN-537 | ARO-4001 | RIG | FOT | 10 | 10 | 903240 | 903191 | RR | 10308 | DWKS | OBSERVED VFD FAULT & UNABLE TO FUNCTION DRAW WORK, TROUBLESHOOTING SAME, CLEANED CHOPPERS, RE-ASSIGN VFD, WORKING OK.
581 | 10/06/2022 | 02 Oct 0900 - 2045 | ZULF-2066 | ED-85A | ARM | PCPF | 15.75 | 106.75 | 903055 |  | TH | 6125 | NA | WHILE RUNNING 9-5/8" CSG HAD OBSTRUCTION AT 6215 FT , WASH DOWN AND WORK ON IT CAN NOT PASS.
583 | 10/06/2022 | 06 Oct 1830 - 2215 | JNAB-815 | JACK-203 | RIG | OTH | 2.25 | 2.25 | 903238 |  | UPRA | 44 | NA | CELLAR PUMP FAILURE
585 | 10/06/2022 | 05 Oct 2345 - 2200 | GHZL-106 | NA-128S | SWL | FOT | 15.5 | 16.75 | 903204 |  | TF | 13700 | WLU | SLB UNIT SUDDENLY GOT POWER SHUT DOWN DUE TO GENERATOR BREAKDOWN.
587 | 10/06/2022 | 06 Oct 0815 - 0500 | SDGM-444 | NA-18S | HCO | FOT | 20.75 | 20.75 | 903257 |  | TF | 10693 | RTTS | UNABLE TO SET RTTS PKR @ DIFFERENT POSITIONS.
589 | 10/06/2022 | 05 Oct 0030 - 0645 | SHYB-134 | NA-207S | RIG | FOT | 1.75 | 6.25 | 903193 |  | TF | 5847 | SFLN | WHILE DRILLING, KELLY HOSE STARTED TO LEAK.
591 | 10/06/2022 | 06 Oct 1030 - 1400 | BRRI-562 | NADRU-1 | SWT | FOT | 3.5 | 3.5 | 903210 |  | TF | 0 | WTSE | TROUBLESHOOT BLACK SMOKE WHILE FLARING OPERATIONS, CLEAN ALL LINES & RESUME OPERATIONS
593 | 10/06/2022 | 05 Oct 1930 - 1500 | QTIF-503 | NBR-263S | RIG | OTH | 10 | 19.5 | 903190 |  | UPRA | 0 | NA | INCIDENT INVESTIGATION
595 | 10/06/2022 | 16 Sep 2000 - 0500 | HRDH-1976 | PA-218S | ARM | UVLC | 12 | 384.25 | 902417 |  | LCIR | 7387 | NA | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR).
597 | 10/06/2022 | 04 Oct 2130 - 0500 | QTIF-269 | PA-785S | NTT | FOT | 24 | 55.5 | 903106 |  | TF | 0 | PCPD | LOST IN HOLE MOTOR DRIVE SHAFT AND 3-7/8" ECONO MILL
599 | 10/06/2022 | 06 Oct 1900 - 0500 | SFNY-2005 | SINO-29N | ARM | HELD | 10 | 10 | 903277 |  | JF | 5351 | RBHA | WIRE LINE GAMMA RAY/CCL TOOL CANT ACCESS TO TARGET DEPTH DUE TO CERAMIC DISC DEBRIS IN HOLE
601 | 10/06/2022 | 06 Oct 1830 - 1930 | HWYH-355 | SINO-42L | SPS | FOT | 1 | 1 | 903218 |  | BHA | 7575 | LWD | ABG SENSOR READINGS NOT MATCHING WITH LWD GAMA READINGS .
612 | 10/06/2022 | 22 Sep 0500 - 0500 | BRRI-1148 | SND-2004 | HSL | FOT | 24 | 322.5 | 902598 |  | TF | 8196 | PLUGN | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL.
614 | 10/06/2022 | 06 Oct 0700 - 1130 | UTMN-3095 | SND-2006 | NCS | FOT | 4.5 | 4.5 | 903211 |  | TF | 0 | PUMP | PU MU NPS CMT HEAD, UPON P/T SAME HAD LEAK AT NPS X.OVER BELOW THE CMT HEAD, WAIT ON NPS TO REPLACE SAME, REPLACED PRESSURE TESTED O.K.
616 | 10/06/2022 | 25 Sep 1400 - 0500 | AWTD-104001 | SND-2007 | NPC | TOWC | 24 | 260 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
618 | 10/06/2022 | 27 Sep 0630 - 0500 | HRDH-1291 | SND-2008 | ARM | UVLC | 24 | 216 | 902798 |  | LCIR | 0 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
620 | 10/06/2022 | 06 Oct 0700 - 0500 | HWYH-74 | SP-167 | SDM | ABFM | 20.5 | 20.5 | 903219 |  | TF | 7985 | RSS | SLB LWD NB/GR TOOL FAILURE. STOP SENDING DATA. ATTEMPT TO GET THE TOOL TO WORK BY CONTROL DRILL.
622 | 10/06/2022 | 06 Oct 1315 - 0030 | LIDM-2 | SP-258 | CAM | FOT | 11.25 | 11.25 | 903258 |  | TF | 7367 | FMH | UNABLE TO RELEASE RUNNING TOOL FROM HANGER WITH NORMAL PROCEDURE.
624 | 10/06/2022 | 05 Oct 1700 - 0415 | QTIF-423 | SSA-29 | WBP | FOT | 23.25 | 35.25 | 903216 |  | TF | 7900 | RBP | OBSERVED RETURN FROM FLOWLINE (WFD 7" DLT PKR LEAKING).
626 | 10/06/2022 | 06 Oct 0530 - 1500 | HWYH-1217 | SSA-5859 | OCS | FOT | 4 | 4 | 903208 |  | TF | 13786 | CTRQ | ODFJELL PICK UP MACHINE AND POWER TONG FAILED
628 | 10/06/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 57.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON. EVAULATE POWER SYSTEM AND TDS MOTOR RPM'S.
630 | 10/06/2022 | 06 Oct 0700 - 1700 | UTMN-2015 | SSA-5964 | EX1 | FOT | 10 | 10 | 903209 |  | TF | 12290 | PLUGN | EXPRO S/L 4.5" PR PLUG SET AT LOWER R-NIPPLE FAILED TO HOLD PRESS, RETRIEVED PR-PLUG, REPLACED WITH BACK-UP PR-PLUG, SET AT SAME LOWER R-NIPPLE, TESTED OK.
632 | 10/06/2022 | 04 Oct 1230 - 0500 | UTMN-3148 | SSA-5969 | WUD | FOT | 11 | 49 | 903162 |  | BHA | 10372 | FV | WFD MPD FLOAT VALVES FAILED.
634 | 10/06/2022 | 06 Oct 1930 - 0500 | ZULF-653 | V140A | RIG | FOT | 9.5 | 9.5 | 903276 |  | DSF | 2570 | STRG | WHILE ATTEMPTING TO PERFORM SHALLOW TEST FOR 12-1/4" DRLG BHA FOUND STRING PLUGGED, CHECKED SURFACE LINE UP AND TRIED TO TROUBLESHOOTING WITHOUT SUCCESS. POH & L/D BHA FOUND CEMENT CUTTINGS AND DEBRIS PLUGGING PBL SUB, FILTER SUB & BIT NOZZLES.
636 | 10/06/2022 | 06 Oct 0045 - 0145 | MRJN-3026 | V141A | RIG | FOT | 1 | 1 | 903278 |  | RR | 2995 | TDS | TDS INADVERTENTLY GIVEN THE COMMAND TO RETRACT CAUSING ALIGNMENT CYLINDER CLEVIS TO FAIL
637 | 10/07/2022 | 07 Oct 0100 - 0500 | MHWZ-991100 | ADC-21 | RIG | FPMP | 4 | 4 | 903288 |  | RR | 11061 | MPMP | AFTER MAKING A CONNECTION @ 11,057' AND DRILLING TO 11,061' THE DRILLER OBSEVERED A LEAK ON #2 STAND PIPE CONNECTION AT THE TOP KELLY HOSE CONNECTION. PULL 2 STANDS, & ATTEMPTED TO TIGHTEN THE HAMMER UNION. WITH NO SUCCESS. DECIDED TO PULL OUT TO 9-5/8" CASING SHOE. INSTALL CIRCULATING SWEDGE AND CHICKSANS. ESTABLISH CIRCULATION AT REDUCED RATE. PJSM. BREAK KELLY HOSE CONNECTION AND REPLACE O-RING SEAL ON STAND PIPE 1 & STAND PIPE 2
639 | 10/07/2022 | 07 Oct 1745 - 2000 | MHWZ-991100 | ADC-21 | RIG | FPMP | 2.25 | 2.25 | 903284 |  | RR | 10962 | MPMP | HAMMER UNION CONNECTION LEAKING ON #1 STAND PIPE. SWAP STAND PIPE AND KELLEY HOSE.
640 | 10/07/2022 | 07 Oct 2000 - 2145 | MHWZ-991100 | ADC-21 | RIG | FPMP | 1.75 | 1.75 | 903286 |  | RR | 10962 | MPMP | ATTEMPTED RETURN TO DRILLING USING MUD PUMPS #2 & 3. OBSEVERED LOW PUMP PRESSURE. FOUND BAD VALVE & SEAT ON MUD PUMP #3. SWAPPED TO PUMPS #2 & 1, MUD PUMP #1 2" BLEEDOFF LEAKING ON #1 PUMP. ISSOLATE PUMPS #1 & 3. UNABLE ACHIVE ADEQUATE GPM TO DRILL. CIRCULATE WITH PUMP #2 WHILE REPAIRING PUMPS #1 & 3.
641 | 10/07/2022 | 07 Oct 0100 - 0500 | MHWZ-991100 | ADC-21 | RIG | FPMP | 4 | 4 | 903288 |  | RR | 11061 | MPMP | AFTER MAKING A CONNECTION @ 11,057' AND DRILLING TO 11,061' THE DRILLER OBSEVERED A LEAK ON #2 STAND PIPE CONNECTION AT THE TOP KELLY HOSE CONNECTION. PULL 2 STANDS, & ATTEMPTED TO TIGHTEN THE HAMMER UNION. WITH NO SUCCESS. DECIDED TO PULL OUT TO 9-5/8" CASING SHOE. INSTALL CIRCULATING SWEDGE AND CHICKSANS. ESTABLISH CIRCULATION AT REDUCED RATE. PJSM. BREAK KELLY HOSE CONNECTION AND REPLACE O-RING SEAL ON STAND PIPE 1 & STAND PIPE 2
643 | 10/07/2022 | 06 Oct 0315 - 0545 | UTMN-2309 | ADC-34 | RIG | FOT | .75 | 2.5 | 903241 |  | RR | 14021 | CSYS | STANDPIPE HOSE LEAKING.
645 | 10/07/2022 | 07 Oct 2330 - 0300 | SDGM-1194 | ADC-36 | WUD | FOT | 3.5 | 3.5 | 903259 |  | TF | 12395 | MPD | HAD LEAKAGE FROM WFD RCD CLAMP, CHANGE BOWL SEAL, FUNCTION TEST, OK.
647 | 10/07/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 387 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
663 | 10/07/2022 | 07 Oct 2130 - 0500 | MRJN-2018 | ADM-261 | SWL | FOT | 7.5 | 7.5 | 903260 |  | TF | 17200 | WLT | WIRE-LINE SHEAVES FAILURE.
665 | 10/07/2022 | 05 Oct 1800 - 0500 | MRJN-3013 | ADM-339 | RIG | GRF | 24 | 59 | 903202 |  | UPRA | 6260 | PSYS | LOST RIG POWER WHILE REAMING AND WASHING WITH STAND #62 PRIOR TO MAKE CONNECTION TO DRILL AHEAD.
667 | 10/07/2022 | 07 Oct 0615 - 1145 | MRJN-3007 | ARO-3001 | BCR | XTRI | 5.5 | 5.5 | 903285 |  | JF | 203 | CTRQ | EXCESSIVE TIME TO MAKE UP SHOE TRACK.
669 | 10/07/2022 | 05 Oct 1045 - 0500 | MRJN-537 | ARO-4001 | RIG | OTH | 24 | 66.25 | 903191 |  | UPRA | 10308 | NA | UNABLE TO SET 7" WFD LINER HGR DUE TO SETTING BALLS JAMMED WITH PLASTIC PART OF DP MAT INSIDE DP, POOH TO CLEAN & DRIFT DP.
671 | 10/07/2022 | 07 Oct 1100 - 0500 | BRRI-436 | HI-2 | BAW | FOT | 8 | 8 | 903283 |  | TF | 7456 | WLT | BAKER WLLOGGING TOOL FAILURE
673 | 10/07/2022 | 05 Oct 2345 - 0045 | GHZL-106 | NA-128S | SWL | FOT | 19.75 | 43.5 | 903204 |  | TF | 13700 | WLU | SLB UNIT SUDDENLY GOT POWER SHUT DOWN DUE TO GENERATOR BREAKDOWN.
675 | 10/07/2022 | 06 Oct 0815 - 0745 | SDGM-444 | NA-18S | HCO | FOT | 2.75 | 23.5 | 903257 |  | TF | 10693 | RTTS | UNABLE TO SET RTTS PKR @ DIFFERENT POSITIONS.
677 | 10/07/2022 | 07 Oct 1130 - 1200 | SDGM-1223 | NBR-196S | BHI | FOT | .5 | .5 | 903242 |  | BHA | 11088 | MWD | BAKER LOSS TOOL SIGNAL WHILE CONDUCTING MWD SURVEY, TROUBLE SHOOT, SEND DOWNLINK & RE-GAINED SIGNAL. OK.
679 | 10/07/2022 | 16 Sep 2000 - 0500 | HRDH-1976 | PA-218S | ARM | UVLC | 24 | 408.25 | 902417 |  | LCIR | 7387 | NA | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR).
681 | 10/07/2022 | 07 Oct 0945 - 0500 | HRDH-2414 | PA-604S | SPS | FOT | 19.25 | 19.25 | 903296 |  | BHA | 15019 | MWD | MWD/GR GIVES BAD RESPONSES. SPERRY CREW UNABLE TO TROUBLESHOOTING.
683 | 10/07/2022 | 04 Oct 2130 - 0500 | QTIF-269 | PA-785S | NTT | FOT | 24 | 79.5 | 903106 |  | TF | 0 | PCPD | LOST IN HOLE MOTOR DRIVE SHAFT AND 3-7/8" ECONO MILL
685 | 10/07/2022 | 07 Oct 0100 - 0400 | HWYH-638 | SINO-19L | SPS | FOT | 3 | 3 | 903290 |  | BHA | 300 | RSS | PERFORMED SHALLOW TEST ICRUISE/LWD PULSE, NO RESPONSE FROM ICRUISE, ATTEMPTED TO TROUBLESHOOT - NO SUCCESS..
687 | 10/07/2022 | 07 Oct 1700 - 0400 | KHRS-75 | SINO-1L | TK1 | FOT | 11 | 11 | 903287 |  | TF | 0 | LINR | ATTEMPT TO OPEN 4-1/2" WFD OFF-BOTTOM LINER CEMENT VALVE, PRESSURE UP TO 4500 PSI, NO SUCCES
689 | 10/07/2022 | 07 Oct 2100 - 0500 | HWYH-355 | SINO-42L | SPS | FOT | 4 | 4 | 903291 |  | BHA | 9290 | LWD | LWD DOWNLINK RECEIVER NOT REPOND .
701 | 10/07/2022 | 22 Sep 0500 - 1200 | BRRI-1148 | SND-2004 | HSL | FOT | 7 | 329.5 | 902598 |  | TF | 8196 | PLUGN | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL.
703 | 10/07/2022 | 07 Oct 1130 - 1730 | UTMN-3095 | SND-2006 | RIG | FOT | 6 | 6 | 903282 |  | BOP | 0 | BOP | WHILE TESTING THE BOP HAD LEAK UPPER KILL LINE MANUAL & HCR VAVLES, REPLACED SAME AND TESTED TILL HAD GOOD TEST.
705 | 10/07/2022 | 25 Sep 1400 - 0500 | AWTD-104001 | SND-2007 | NPC | TOWC | 24 | 284 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
707 | 10/07/2022 | 27 Sep 0630 - 0500 | HRDH-1291 | SND-2008 | ARM | UVLC | 24 | 240 | 902798 |  | LCIR | 0 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
708 | 10/07/2022 | 07 Oct 1800 - 0200 | MRJN-903 | SNF036 | ARM | LCRW | 3.5 | 3.5 | 903297 |  | STUK | 5251 | STRG | PIPE STUCK DUE TO TOTAL LOST CIRCULATION.
710 | 10/07/2022 | 07 Oct 1130 - 1215 | MRJN-903 | SNF036 | ARN | CFFM | .75 | .75 | 903289 |  | LCIR | 5086 | MDCAP | HAD TOTAL LOST CIRCULATION WHILE DRLG AT 5086 FT.
711 | 10/07/2022 | 07 Oct 1800 - 0200 | MRJN-903 | SNF036 | ARM | LCRW | 3.5 | 3.5 | 903297 |  | STUK | 5251 | STRG | PIPE STUCK DUE TO TOTAL LOST CIRCULATION.
713 | 10/07/2022 | 07 Oct 0900 - 0500 | SFNY-517 | SNT-025 | APF | SRVC | 20 | 20 | 903279 |  | WO | 0 | NA | WAITING ON PERMISSION FROM SFNY PRODUCTION TO FLOW BACK SFNY-517 FOR CLEAN UP.
714 | 10/07/2022 | 07 Oct 1500 - 2245 | FDHL-146 | SP-165 | HCM | CEDE | 6.25 | 6.25 | 903281 |  | JF | 12180 | NA | DRILL OUT EXCESS CMT DUE TO NOT BUMP LINER WIPER PLUG
716 | 10/07/2022 | 07 Oct 1030 - 1345 | FDHL-146 | SP-165 | BLH | FOT | 3.25 | 3.25 | 903280 |  | TF | 11500 | HGRL | REAM DOWN INSIDE 7" LINER SHALLOWER THAN EXPECTED, DUE TO PRESENCE OF CMT RINGS.
717 | 10/07/2022 | 07 Oct 1500 - 2245 | FDHL-146 | SP-165 | HCM | CEDE | 6.25 | 6.25 | 903281 |  | JF | 12180 | NA | DRILL OUT EXCESS CMT DUE TO NOT BUMP LINER WIPER PLUG
719 | 10/07/2022 | 06 Oct 0700 - 1700 | HWYH-74 | SP-167 | SDM | ABFM | 12 | 30 | 903219 |  | TF | 7985 | RSS | SLB LWD NB/GR TOOL FAILURE. STOP SENDING DATA. ATTEMPT TO GET THE TOOL TO WORK BY CONTROL DRILL. NO SUCCESS.
721 | 10/07/2022 | 07 Oct 2300 - 0330 | MNIF-198 | SP-306 | RIG | FOT | 4.5 | 4.5 | 903292 |  | RR | 272 | TDS | FAILURE OF TDS BACK UP TONG
723 | 10/07/2022 | 05 Oct 1030 - 1800 | QTIF-423 | SSA-29 | WCS | FOT | 12.5 | 55 | 903216 |  | TF | 7900 | CHAMP | OBSERVED RETURN FROM FLOWLINE (WFD 7" DLT PKR LEAKING).
725 | 10/07/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 81.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON. EVAULATE POWER SYSTEM AND TDS MOTOR RPM'S.
727 | 10/07/2022 | 04 Oct 1230 - 0500 | UTMN-3148 | SSA-5969 | WUD | FOT | 23.5 | 72.5 | 903162 |  | BHA | 10372 | FV | WFD MPD FLOAT VALVES FAILED.
729 | 10/07/2022 | 06 Oct 1930 - 1300 | ZULF-653 | V140A | RIG | FOT | 8 | 17.5 | 903276 |  | DSF | 2570 | STRG | WHILE ATTEMPTING TO PERFORM SHALLOW TEST FOR 12-1/4" DRLG BHA FOUND STRING PLUGGED, CHECKED SURFACE LINE UP AND TRIED TO TROUBLESHOOTING WITHOUT SUCCESS. POH & L/D BHA FOUND CEMENT CUTTINGS AND DEBRIS PLUGGING PBL SUB, FILTER SUB & BIT NOZZLES.
731 | 10/08/2022 | 08 Oct 0730 - 0500 | SDGM-1244 | ADC-41L | TK3 | FOT | 21.5 | 21.5 | 903268 |  | TF | 10393 | CSG | TROUBLESHOOT LINER TIE BACK SEAL SETTING. WHILE TRYING TO STING INTO 9-5/8" LINER TBR, PRESSURE NOT HOLD AS AN INDICATION OF NO SEAL INTEGRITY.
733 | 10/08/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 411 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
735 | 10/08/2022 | 08 Oct 0900 - 0500 | HWYH-27 | ADES-14 | SWL | FOT | 20 | 20 | 903322 |  | TF | 10150 | WLT | SLB UNABLE TO PROCESS THE IMAGE LOG DATA.
737 | 10/08/2022 | 08 Oct 2045 - 2315 | ABQQ-590 | ADES-158 | HLH | FOT | 2.5 | 2.5 | 903321 |  | TF | 1537 | HGRL | FAILURE IN RUNNING TOOL: R.TOOL IS MOVING OUT OF 7" LINER.
739 | 10/08/2022 | 07 Oct 2130 - 1530 | MRJN-2018 | ADM-261 | SWL | FOT | 10.5 | 18 | 903260 |  | TF | 17200 | WLT | WIRE-LINE SHEAVES FAILURE.
741 | 10/08/2022 | 04 Oct 1030 - 0500 | SFNY-263 | ADM-266 | ARM | WTHR | 20 | 82 | 903105 |  | WON | 0 | NA | WAIT HIGH WATER SLACK & SUITABLE WEATHER CONDITION.
743 | 10/08/2022 | 05 Oct 1800 - 0500 | MRJN-3013 | ADM-339 | RIG | GRF | 24 | 83 | 903202 |  | UPRA | 6260 | PSYS | LOST RIG POWER WHILE REAMING AND WASHING WITH STAND #62 PRIOR TO MAKE CONNECTION TO DRILL AHEAD.
745 | 10/08/2022 | 05 Oct 1045 - 1515 | MRJN-537 | ARO-4001 | RIG | FOT | 10.25 | 76.5 | 903191 |  | DSF | 10308 | DP | UNABLE TO SET 7" WFD LINER HGR DUE TO SETTING BALLS JAMMED WITH PLASTIC PART OF DP MAT INSIDE DP, POOH TO CLEAN & DRIFT DP.
747 | 10/08/2022 | 08 Oct 1200 - 0445 | HRDH-351 | DQ-50L | TK2 | IBSL | 16.75 | 16.75 | 903263 |  | LROP | 6315 | BIT | LOW ROP, POOH & CHANGED BIT.
749 | 10/08/2022 | 08 Oct 1830 - 2015 | ZULF-2066 | ED-85A | RIG | FOT | 1.75 | 1.75 | 903343 |  | RR | 8524 | PSYS | MALFUNCTION ON BOP WINCH
751 | 10/08/2022 | 07 Oct 1100 - 0130 | BRRI-436 | HI-2 | BAW | FOT | 20.5 | 28.5 | 903283 |  | TF | 7456 | WLT | BAKER WLLOGGING TOOL FAILURE
752 | 10/08/2022 | 08 Oct 1715 - 2145 | HWYH-974 | NA-393S | RIG | FOT | 4.5 | 4.5 | 903319 |  | RR | 10644 | DWKS | DRAW WORKS MAIN DRIVE CHAIN FOR HIGH CLUTCH HAD PARTIALY BROKEN SUDDENLY WHILE POOH.
754 | 10/08/2022 | 08 Oct 1300 - 0500 | HWYH-974 | NA-393S | WI1 | UITE | 10.5 | 10.5 | 903262 |  | JF | 10644 | MILL | COULDN'T DRILLING RAT HOLE WITH 8-3/8" WIS TRI MILL ASSY.
755 | 10/08/2022 | 08 Oct 1715 - 2145 | HWYH-974 | NA-393S | RIG | FOT | 4.5 | 4.5 | 903319 |  | RR | 10644 | DWKS | DRAW WORKS MAIN DRIVE CHAIN FOR HIGH CLUTCH HAD PARTIALY BROKEN SUDDENLY WHILE POOH.
757 | 10/08/2022 | 08 Oct 1930 - 2345 | JLMN-200 | NBR-987S | RIG | GRF | 4.25 | 4.25 | 903340 |  | UPRA | 327 | TDS | FAILURE OF ACTUATOR VALVE
759 | 10/08/2022 | 16 Sep 2000 - 0600 | HRDH-1976 | PA-218S | ARM | UVLC | 1 | 409.25 | 902417 |  | LCIR | 7387 | NA | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR).
761 | 10/08/2022 | 07 Oct 0945 - 1615 | HRDH-2414 | PA-604S | SPS | FOT | 11.25 | 30.5 | 903296 |  | BHA | 15019 | MWD | MWD/GR GIVES BAD RESPONSES. SPERRY CREW UNABLE TO TROUBLESHOOTING.
763 | 10/08/2022 | 04 Oct 2130 - 0500 | QTIF-269 | PA-785S | NTT | FOT | 24 | 103.5 | 903106 |  | TF | 0 | PCPD | LOST IN HOLE MOTOR DRIVE SHAFT AND 3-7/8" ECONO MILL
765 | 10/08/2022 | 08 Oct 1845 - 0500 | USKR-6 | PA-866S | RIG | FPMP | 10.25 | 10.25 | 903267 |  | RR | 3411 | MPMP | OBSERVED DROP IN STANDPIPE PRESSURE. TROUBLESHOOT MUD PUMPS AND LINES, FOUND 12" MAIN SUCTION LINE PARTIALLY PLUGGED
767 | 10/08/2022 | 08 Oct 1600 - 0500 | HWYH-638 | SINO-19L | SPS | FOT | 13 | 13 | 903339 |  | BHA | 7208 | MWD | WHILE DRILLING OBSERVED NO MWD SIGNAL, TROUBLESHOOT NO SUCCESS.
769 | 10/08/2022 | 08 Oct 1730 - 0500 | KHRS-75 | SINO-1L | WLH | DSFT | 11.5 | 11.5 | 903336 |  | JF | 0 | PAC | ATTEMPT TO OPEN 4-1/2" WFD OFF-BOTTOM LINER CEMENT VALVE, PRESSURE UP TO 4500 PSI, NO SUCCES
771 | 10/08/2022 | 08 Oct 1130 - 0500 | MNIF-204 | SINO-25 | WI3 | FOT | 17.5 | 17.5 | 903320 |  | TF | 7504 | WPSTK | UNABLE TO PASS 9-5/8" CSG WINDOW WITH SPS DIRC ASSY, HAD OBSTRUCTION AT WHIPSTOCK RAMP AT 7508' & 7512'.
773 | 10/08/2022 | 07 Oct 2100 - 0500 | HWYH-355 | SINO-42L | SPS | FOT | 24 | 28 | 903291 |  | BHA | 9290 | LWD | LWD DOWNLINK RECEIVER NOT REPOND .
783 | 10/08/2022 | 08 Oct 1330 - 1445 | SFNY-1730 | SL-7 | RIG | FOT | 1.25 | 1.25 | 903266 |  | TF | 1373 | PEL | MALFUNCTION IN BX ELEVATOR , TROUBLESHOOTING NO SUCCESS
785 | 10/08/2022 | 08 Oct 0530 - 0645 | SFNY-1730 | SL-7 | ITS | FOT | 1.25 | 1.25 | 903265 |  | TF | 0 | CTRQ | ATTEMPTED TO MAKE UP 9 5/8'' FLOAT SHOE TO FIRST JOINT BUT UNABLE TO REACH THE REQUIRED TORQUE,
786 | 10/08/2022 | 08 Oct 1330 - 1445 | SFNY-1730 | SL-7 | RIG | FOT | 1.25 | 1.25 | 903266 |  | TF | 1373 | PEL | MALFUNCTION IN BX ELEVATOR , TROUBLESHOOTING NO SUCCESS
788 | 10/08/2022 | 08 Oct 0300 - 0500 | BRRI-1148 | SND-2004 | OZT | FOT | 2 | 2 | 903269 |  | TF | 8248 | CTBG | ATTEMPT SERVERAL TIMES TO BROKE CERAMIC DISK @ 8,248' - NO SUCCESS. POOH TO CHANGE BHA.
790 | 10/08/2022 | 25 Sep 1400 - 0500 | AWTD-104001 | SND-2007 | NPC | TOWC | 24 | 308 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
792 | 10/08/2022 | 07 Oct 1800 - 0200 | MRJN-903 | SNF036 | ARM | LCRW | 1 | 4.5 | 903297 |  | STUK | 5345 | STRG | PIPE STUCK DUE TO TOTAL LOST CIRCULATION.
794 | 10/08/2022 | 07 Oct 0900 - 0500 | SFNY-517 | SNT-025 | APF | SRVC | 24 | 44 | 903279 |  | WO | 0 | NA | WAITING ON PERMISSION FROM SFNY PRODUCTION TO FLOW BACK SFNY-517 FOR CLEAN UP.
796 | 10/08/2022 | 08 Oct 2045 - 2215 | MNHZ-1 | SSA-201 | SWL | FOT | 1.5 | 1.5 | 903264 |  | TF | 100 | WLT | AFTER MADE UP SLB (MDT/GR) LOGGING TOOLS, PERFORM SURFACE TEST, FOUND ONE OF THE SEAL VALVE ON THE SAMPLE CAPTURE TOOL IS NOT READING CORRECTLY, CLEAN THE VALVE AND CHECK THE READING AGAIN. IT DOESN'T SOLVE THE ISSUE. REPLACE THE TOOL
798 | 10/08/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 105.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON. EVAULATE POWER SYSTEM AND TDS MOTOR RPM'S.
799 | 10/08/2022 | 08 Oct 0400 - 0500 | UTMN-3148 | SSA-5969 | SDM | FOT | 1 | 1 | 903271 |  | BHA | 10540 | MWD | LOST SIGNAL FROM MWD -OK.
801 | 10/08/2022 | 04 Oct 1230 - 0930 | UTMN-3148 | SSA-5969 | WUD | FOT | 4.5 | 77 | 903162 |  | BHA | 10372 | FV | WFD MPD FLOAT VALVES FAILED.
802 | 10/08/2022 | 08 Oct 0400 - 0500 | UTMN-3148 | SSA-5969 | SDM | FOT | 1 | 1 | 903271 |  | BHA | 10540 | MWD | LOST SIGNAL FROM MWD -OK.
804 | 10/08/2022 | 08 Oct 2000 - 0500 | ZULF-2089 | STY-038 | SCP | HERR | 9 | 9 | 903337 |  | JF | 60 | TBG | SLB PROVIDED WRONG COMPLETION TALLY (PUP JOINT BELOW HANGER NOT AS PER SPECIFICATIONS).
806 | 10/08/2022 | 08 Oct 1800 - 2000 | ABSD-1 | T907 | SPS | XTTE | 2 | 2 | 903338 |  | TF | 0 | MWD | RSS NOT RECIEVING COMMANDS.
808 | 10/09/2022 | 09 Oct 0830 - 0300 | ABQQ-110 | ADC-12 | HCO | HERR | 18.5 | 18.5 | 903357 |  | JF | 0 | TBG | SHORT WRSSSV CONTROL LINE.
809 | 10/09/2022 | 09 Oct 1700 - 1730 | HRDH-1864 | ADC-14 | RIG | FOT | .5 | .5 | 903346 |  | RR | 14383 | PSYS | UNABLE TO DRILL AHEAD DUE TO POWER FAILURE IN PCR#4, WORK TO FIX ISSUE MEANWHILE CIRCULATE AND ROTAT STRING.
811 | 10/09/2022 | 09 Oct 0730 - 0830 | HRDH-1864 | ADC-14 | RIG | FOT | 1 | 1 | 903272 |  | RR | 14238 | MPMP | FAILURE OF RIG MUD PUMP#1 EXTENSION RUBBER LEAKING.
812 | 10/09/2022 | 09 Oct 1700 - 1730 | HRDH-1864 | ADC-14 | RIG | FOT | .5 | .5 | 903346 |  | RR | 14383 | PSYS | UNABLE TO DRILL AHEAD DUE TO POWER FAILURE IN PCR#4, WORK TO FIX ISSUE MEANWHILE CIRCULATE AND ROTAT STRING.
814 | 10/09/2022 | 09 Oct 1600 - 1700 | ANDR-1006 | ADC-31 | SPS | FOT | 1 | 1 | 903274 |  | BHA | 8380 | PWD | WHILE DRILLING 16" SECTION OBSERVED HALLIBURTOM PDW TOOL NOT WORKING PROPERTLY
816 | 10/09/2022 | 08 Oct 0730 - 0500 | SDGM-1244 | ADC-41L | HLH | FOT | 23 | 44.5 | 903268 |  | TF | 10393 | LLAP | TROUBLESHOOT LINER TIE BACK SEAL SETTING. WHILE TRYING TO STING INTO 9-5/8" LINER TBR, PRESSURE NOT HOLD AS AN INDICATION OF NO SEAL INTEGRITY.
818 | 10/09/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 435 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
836 | 10/09/2022 | 08 Oct 0900 - 0500 | HWYH-27 | ADES-14 | SWL | FOT | 24 | 44 | 903322 |  | TF | 10150 | WLT | SLB UNABLE TO PROCESS THE IMAGE LOG DATA.
837 | 10/09/2022 | 09 Oct 0130 - 0315 | HRDH-2354 | ADES-798 | RIG | FOT | 1.75 | 1.75 | 903363 |  | RR | 9696 | TDS | SAVER SUB FAILURE TO BREAK FROM TDS - CHANGE OUT SAME.
839 | 10/09/2022 | 09 Oct 2015 - 2215 | HRDH-2354 | ADES-798 | RIG | FOT | 2 | 2 | 903362 |  | RR | 9660 | MPMP | TROUBLE SHOOTING RIG PUMPS.
840 | 10/09/2022 | 09 Oct 0130 - 0315 | HRDH-2354 | ADES-798 | RIG | FOT | 1.75 | 1.75 | 903363 |  | RR | 9696 | TDS | SAVER SUB FAILURE TO BREAK FROM TDS - CHANGE OUT SAME.
842 | 10/09/2022 | 07 Oct 2130 - 1730 | MRJN-2018 | ADM-261 | SWL | FOT | 12.5 | 44 | 903260 |  | TF | 17200 | WLT | WIRE-LINE SHEAVES FAILURE.
844 | 10/09/2022 | 04 Oct 1030 - 0700 | SFNY-263 | ADM-266 | ARM | WTHR | 2 | 84 | 903105 |  | WON | 0 | NA | WAIT HIGH WATER SLACK & SUITABLE WEATHER CONDITION.
846 | 10/09/2022 | 08 Oct 0430 - 0830 | MRJN-3013 | ADM-339 | RIG | GRF | 3.5 | 4 | 903344 |  | UPRA | 6260 | MPMP | OBSERVE GASKET ON MUD PUMP#1 LEAKING AND BELT SLIPPING ON MUD PUMP#3. REPAIR THE SAME.
848 | 10/09/2022 | 09 Oct 0045 - 0500 | MRJN-537 | ARO-4001 | BHI | FOT | 4.25 | 4.25 | 903360 |  | BHA | 10308 | LWD | WHILE PERFORMING SHALLOW TESTING FOR 6 1/8" BHI RSS/MWD/LWD ASSY, FOUND NO COMMUNICATIONS WITH LWD TOOLS, POOH TO CHANGE OUT LWD TOOLS WITH BACK UP TOOLS.
850 | 10/09/2022 | 09 Oct 1700 - 1900 | ZULF-2066 | ED-85A | RIG | LHFL | 2 | 2 | 903376 |  | RR | 0 | HSYS | OBSERVED LEAK FROM OVER SHOT,N/D KFDJ DIVERTER
852 | 10/09/2022 | 08 Oct 1300 - 1030 | HWYH-974 | NA-393S | WI1 | UITE | 5.5 | 16 | 903262 |  | JF | 10644 | MILL | COULDN'T DRILLING RAT HOLE WITH 8-3/8" WIS TRI MILL ASSY.
854 | 10/09/2022 | 09 Oct 1145 - 1315 | ANDR-1018 | NBR-654S | RIG | FOT | 1.5 | 1.5 | 903356 |  | RR | 4496 | HSYS | UNABLE TO OPERATE IRON ROUGHNECK
856 | 10/09/2022 | 09 Oct 0245 - 0500 | JLMN-200 | NBR-987S | RIG | FOT | 2.25 | 2.25 | 903359 |  | RR | 669 | TDS | SEVERE HYDRAULIC LEAK ON TOP DRIVE
858 | 10/09/2022 | 04 Oct 2130 - 2130 | QTIF-269 | PA-785S | NTT | FOT | 16.5 | 120 | 903106 |  | TF | 0 | PCPD | LOST IN HOLE MOTOR DRIVE SHAFT AND 3-7/8" ECONO MILL
860 | 10/09/2022 | 08 Oct 1845 - 0615 | USKR-6 | PA-866S | RIG | FPMP | 1.25 | 11.5 | 903267 |  | RR | 3411 | MPMP | OBSERVED DROP IN STANDPIPE PRESSURE. TROUBLESHOOT MUD PUMPS AND LINES, FOUND 12" MAIN SUCTION LINE PARTIALLY PLUGGED
862 | 10/09/2022 | 09 Oct 1000 - 2300 | HRDH-2220 | SCTD-2 | SDM | FOT | 13 | 13 | 903273 |  | BHA | 12494 | MWD | LOST COMMUNICATION & POWER TO THE TOOL
884 | 10/09/2022 | 08 Oct 1600 - 2000 | HWYH-638 | SINO-19L | SPS | FOT | 15 | 28 | 903339 |  | BHA | 7208 | MWD | WHILE DRILLING OBSERVED NO MWD SIGNAL, TROUBLESHOOT NO SUCCESS.
886 | 10/09/2022 | 08 Oct 1730 - 0500 | KHRS-75 | SINO-1L | WLH | DSFT | 24 | 35.5 | 903336 |  | JF | 0 | PAC | ATTEMPT TO OPEN 4-1/2" WFD OFF-BOTTOM LINER CEMENT VALVE, PRESSURE UP TO 4500 PSI, NO SUCCES
888 | 10/09/2022 | 08 Oct 1130 - 2100 | MNIF-204 | SINO-25 | WI3 | FOT | 16 | 33.5 | 903320 |  | TF | 7504 | WPSTK | UNABLE TO PASS 9-5/8" CSG WINDOW WITH SPS DIRC ASSY, HAD OBSTRUCTION AT WHIPSTOCK RAMP AT 7508' & 7512'.
889 | 10/09/2022 | 09 Oct 0600 - 0500 | HWYH-355 | SINO-42L | SPS | FOT | 23 | 23 | 903361 |  | BHA | 9568 | RSS | I-CRUISE NOT RESPOND .
891 | 10/09/2022 | 07 Oct 2100 - 0600 | HWYH-355 | SINO-42L | SPS | FOT | 1 | 29 | 903291 |  | BHA | 9290 | LWD | LWD DOWNLINK RECEIVER NOT REPOND .
892 | 10/09/2022 | 09 Oct 0600 - 0500 | HWYH-355 | SINO-42L | SPS | FOT | 23 | 23 | 903361 |  | BHA | 9568 | RSS | I-CRUISE NOT RESPOND .
905 | 10/09/2022 | 08 Oct 0300 - 0000 | BRRI-1148 | SND-2004 | OZT | HERR | 19 | 21 | 903269 |  | JF | 8248 | CTAC | ATTEMPTED SEVERAL TIMES TO BROKE CERAMIC DISK WITH OILSERV CT & BHA JETTING TOOL- NO SUCCESS. POOH TO RUN CT WITH WIS MOTOR/MILLING ASSEMBLY.
907 | 10/09/2022 | 25 Sep 1400 - 0730 | AWTD-104001 | SND-2007 | NPC | TOWC | 2.5 | 310.5 | 902688 |  | TF | 15230 | JARS | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF.
909 | 10/09/2022 | 07 Oct 0900 - 1200 | SFNY-517 | SNT-025 | APF | SRVC | 7 | 51 | 903279 |  | WO | 0 | NA | WAITING ON PERMISSION FROM SFNY PRODUCTION TO FLOW BACK SFNY-517 FOR CLEAN UP.
911 | 10/09/2022 | 09 Oct 1130 - 0400 | HWYH-74 | SP-167 | ARM | STBH | 16.5 | 16.5 | 903364 |  | STUK | 10050 | BHA | WHILE M/U TDS TO STRING OBSERVED STRING STUCK. UNABLE TO GO UP OR COME DOWN. WORK ON STRING SEVERAL TIMES.
912 | 10/09/2022 | 09 Oct 0015 - 0145 | HRDH-1989 | SSA-303 | RIG | XTRI | 1.5 | 1.5 | 903358 |  | JF | 0 | NA | EXCESSIVE TIME WHILE P/U 5-1/2" DP FROM PIPE RACK.
914 | 10/09/2022 | 09 Oct 1400 - 1700 | HRDH-1989 | SSA-303 | RIG | FOT | 3 | 3 | 903345 |  | RR | 0 | TDS | HAVING TO ADJUST LINK TILT SYSTEM CLAMP NOT HOLDING
915 | 10/09/2022 | 09 Oct 0015 - 0145 | HRDH-1989 | SSA-303 | RIG | XTRI | 1.5 | 1.5 | 903358 |  | JF | 0 | NA | EXCESSIVE TIME WHILE P/U 5-1/2" DP FROM PIPE RACK.
917 | 10/09/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 129.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON, EVALUATE POWER SYSTEM AND TDS MOTOR RPM'S. WHILE ATTEMPTING TO DRILL AHEAD WITH 90 RPM'S, TDS GETTING ERRATIC RPM'S. MUD PUMPS LOSING AND GAINING POWER WHILE CIRCULATING OR DRILLING.
919 | 10/09/2022 | 08 Oct 2000 - 0500 | ZULF-2089 | STY-038 | SCP | HERR | 24 | 33 | 903337 |  | JF | 60 | TBG | SLB PROVIDED WRONG COMPLETION TALLY (PUP JOINT BELOW HANGER NOT AS PER SPECIFICATIONS).
920 | 10/10/2022 | 10 Oct 1515 - 1615 | HRDH-1864 | ADC-14 | SDM | FOT | 1 | 1 | 903367 |  | BHA | 14925 | MWD | SLB DEPTH SENSOR FAILED HAD TO REPLACE IT.
922 | 10/10/2022 | 10 Oct 1700 - 2045 | HRDH-1864 | ADC-14 | RIG | FOT | 3.75 | 3.75 | 903352 |  | RR | 14914 | MPMP | FAILURE OF RIG MUD PUMP#2 SUCTION LINE PLUGGED >> CLEAN MUD PUMP STRAINER & REPLACE THE EXTENSION RUBBER WHILE RECIPROCATE THE STRING.
923 | 10/10/2022 | 10 Oct 1515 - 1615 | HRDH-1864 | ADC-14 | SDM | FOT | 1 | 1 | 903367 |  | BHA | 14925 | MWD | SLB DEPTH SENSOR FAILED HAD TO REPLACE IT.
925 | 10/10/2022 | 08 Oct 0730 - 0500 | SDGM-1244 | ADC-41L | HLH | FOT | 24 | 68.5 | 903268 |  | TF | 10393 | LLAP | TROUBLESHOOT LINER TIE BACK SEAL SETTING. WHILE TRYING TO STING INTO 9-5/8" LINER TBR, PRESSURE NOT HOLD AS AN INDICATION OF NO SEAL INTEGRITY.
927 | 10/10/2022 | 08 Oct 0045 - 0845 | HRDH-529 | ADC-54L | TK2 | FRFM | 3.75 | 27.75 | 903377 |  | CMT | 6760 | NA | HAD LOSSES DURING 7" LINER CEMENT JOB.
929 | 10/10/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 459 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
931 | 10/10/2022 | 06 Oct 0115 - 0500 | SDGM-1259 | ADC-67L | ARM | UVLC | 24 | 86.5 | 903348 |  | LCIR | 15994 | NA | ENCOUNTERED LOSSES AT 15,994 FT. PUMPED 2 X 150 BBL OF 40 PPB LCM PILL AND LOSSES NOT CURED.
948 | 10/10/2022 | 10 Oct 2030 - 2330 | UTMN-1952 | ADES-173 | SPS | FOT | 3 | 3 | 903438 |  | SURV | 11307 | GYRO | TROUBLE SHOOT MWD TOOL NO SIGNAL
950 | 10/10/2022 | 09 Oct 2015 - 0645 | HRDH-2354 | ADES-798 | RIG | FOT | 1.75 | 3.75 | 903362 |  | RR | 9660 | MPMP | TROUBLE SHOOTING MUD PUMPS.
952 | 10/10/2022 | 10 Oct 1300 - 0500 | SFNY-1134 | ADM-655 | ARM | DAY | 16 | 16 | 903419 |  | WON | 0 | NA | WAIT ON DAYLIGHT TO COMPLETE RIG MOVE.
954 | 10/10/2022 | 09 Oct 0045 - 0845 | MRJN-537 | ARO-4001 | BHI | FOT | 3.75 | 8 | 903360 |  | BHA | 10308 | LWD | WHILE PERFORMING SHALLOW TESTING FOR 6 1/8" BHI RSS/MWD/LWD ASSY, FOUND NO COMMUNICATIONS WITH LWD TOOLS, POOH TO CHANGE OUT LWD TOOLS WITH BACK UP TOOLS.
956 | 10/10/2022 | 10 Oct 1100 - 1300 | UTMN-3019 | DPS-43 | RIG | FOT | 2 | 2 | 903294 |  | RR | 2302 | TDS | UNABLE TO BREAK OUT STD FROM SAVER SUB/TDS.
958 | 10/10/2022 | 10 Oct 0500 - 1800 | ABSF-165 | ENSCO-54 | KSC | FOT | 13 | 13 | 903381 |  | TF | 4542 | ESPL | ABSF-165 VSD MALFUNCTION - TROUBLE SHOOT & FIXED SAME
960 | 10/10/2022 | 10 Oct 1700 - 1800 | ABSF-128 | EXL-IA | RIG | FPMP | 1 | 1 | 903418 |  | RR | 5140 | MPMP | HAD PRESS. DROP ON MP.
962 | 10/10/2022 | 10 Oct 2230 - 0500 | JAHM-5 | NBR-210S | RIG | FOT | 6.5 | 6.5 | 903355 |  | RR | 0 | DWKS | DRILLER CONSULE FAILED TO OPERATE, TROUBLE SHOOT.. NO SUCCESS.WAIT ON TECHNICIAN FROM TOWN.
964 | 10/10/2022 | 10 Oct 2230 - 0300 | UTMN-3180 | NBR-304S | RIG | HERR | 4.5 | 4.5 | 903420 |  | BOP | 9640 | BOP | EXCESS TIME TO P/T TEST 9-5/8" CASING RAMS AND ANNULAR AGAINST 9-5/8" CSG DUE TO TEST UNIT MALFUNCTION AND LEAK FROM TEST PLUG SEAL
966 | 10/10/2022 | 10 Oct 1500 - 1545 | ANDR-1018 | NBR-654S | RIG | FOT | .75 | .75 | 903353 |  | RR | 4496 | EDR | THE ELECTRONIC DRILL PIPE PRESSURE SENSOR ON EPOCH SYSTEM NOT CALIBRATED.
968 | 10/10/2022 | 10 Oct 0400 - 0500 | TINT-91 | NBR-783S | MSD | FOT | 1 | 1 | 903400 |  | TF | 6575 | CTRQ | CRT TOOL LEAKING WHILE CIRCULATE.
970 | 10/10/2022 | 10 Oct 1730 - 1930 | UTMN-3012 | NBR-797S | GOC | XTRI | 2 | 2 | 903373 |  | JF | 4102 | CTRQ | EXCESS TIME DUE TO ALGAITH CREW POOR EXPERIENCE LEADING TO MULTIPLE CASING CROSS THREADS.
971 | 10/10/2022 | 10 Oct 1430 - 0430 | JLMN-200 | NBR-987S | RIG | FOT | 14 | 14 | 903380 |  | RR | 822 | TDS | BLOWER FAN ON TDS AND ACTUATOR VALVE DAMAGE
973 | 10/10/2022 | 09 Oct 0245 - 0900 | JLMN-200 | NBR-987S | RIG | FOT | 4 | 6.25 | 903359 |  | RR | 669 | TDS | SEVERE HYDRAULIC LEAK ON TOP DRIVE
974 | 10/10/2022 | 10 Oct 1430 - 0430 | JLMN-200 | NBR-987S | RIG | FOT | 14 | 14 | 903380 |  | RR | 822 | TDS | BLOWER FAN ON TDS AND ACTUATOR VALVE DAMAGE
976 | 10/10/2022 | 08 Oct 1845 - 2200 | USKR-6 | PA-866S | RIG | FPMP | 6.5 | 18 | 903267 |  | RR | 3411 | MPMP | OBSERVED DROP IN STANDPIPE PRESSURE. TROUBLESHOOT MUD PUMPS AND LINES, FOUND 12" MAIN SUCTION LINE PARTIALLY PLUGGED
978 | 10/10/2022 | 10 Oct 1300 - 0500 | ABJF-155 | SINO-11 | RTR | SRVC | 16 | 16 | 903371 |  | WO | 0 | NA | WAIT ON ABJF-155 LOCATION PREPARATION TO SPOT THE RIG
980 | 10/10/2022 | 10 Oct 1130 - 0500 | ANDR-139 | SINO-15L | TK1 | STBH | 17.5 | 17.5 | 903372 |  | STUK | 7243 | BHA | STRING GOT STUCK WHILE DRILLING.
982 | 10/10/2022 | 08 Oct 1730 - 0500 | KHRS-75 | SINO-1L | WLH | DSFT | 24 | 59.5 | 903336 |  | JF | 0 | PAC | ATTEMPT TO OPEN 4-1/2" WFD OFF-BOTTOM LINER CEMENT VALVE, PRESSURE UP TO 4500 PSI, NO SUCCESS.
984 | 10/10/2022 | 10 Oct 1800 - 0500 | HRDH-1542 | SINO-33L | BAW | FOT | 11 | 11 | 903436 |  | TF | 14618 | CORRL | LOGGING TOOL QUALITY OF READING
1001 | 10/10/2022 | 09 Oct 0600 - 0700 | HWYH-355 | SINO-42L | SPS | FOT | 2 | 25 | 903361 |  | BHA | 9568 | RSS | I-CRUISE NOT RESPOND .
1022 | 10/10/2022 | 10 Oct 1630 - 0130 | MRJN-903 | SNF036 | ARM | LCRW | 9 | 9 | 903437 |  | STUK | 5629 | STRG | PIPE STUCK WHILE CONNECTION
1024 | 10/10/2022 | 10 Oct 2100 - 0500 | BRRI-522 | SP-121 | WWB | FOT | 8 | 8 | 903399 |  | BHA | 11594 | WBCL | COULDN'T PASS WITH 9-5/8'' WBCO THRU 9-5/8'' DV. WORK ON THIS INTERVAL, NO SUCCESS, TRIP OUT TO CHECK THE BHA.
1026 | 10/10/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 3.25 | 3.25 | 903398 |  | BHS | 5835 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1028 | 10/10/2022 | 10 Oct 1030 - 0500 | HRDH-1989 | SSA-303 | RIG | LHFL | 18.5 | 18.5 | 903397 |  | BOP | 1981 | RWCS | ACCUMALATOR BOTTLES WERE CLOSED BECAUSE OF LACK OF OIL IN THE RESIVIOR AND ALSO WORKING ON ELECTRICAL CONTROL PANEL, PULL TO SHOE AND PERFORM AN INVESTIGATION AND REPAIR THE PROBLEMS.
1030 | 10/10/2022 | 10 Oct 0130 - 0230 | HWYH-1217 | SSA-5859 | RIG | FOT | 1 | 1 | 903354 |  | RR | 13751 | RSYS | CUMULATIVE TIME FOR TROUBLESHOOTING IRON ROUGHNECK.
1032 | 10/10/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 153.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNTIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON, EVALUATE POWER SYSTEM AND TDS MOTOR RPM'S. WHILE ATTEMPTING TO DRILL AHEAD WITH 90 RPM'S, TDS GETTING ERRATIC RPM'S. MUD PUMPS LOSING AND GAINING POWER WHILE CIRCULATING OR DRILLING. TDS & PUMPS ARE POWERING ON AND OFF WITH NO CHANGE IN COMMAND WHILE UNDER LOAD. FOUND GENERATORS ARE NOT SHARING THE ELECTRICAL LOAD PROPERLY.
1034 | 10/10/2022 | 08 Oct 2000 - 0100 | ZULF-2089 | STY-038 | SCP | HERR | 20 | 53 | 903337 |  | JF | 60 | TBG | SLB PROVIDED WRONG COMPLETION TALLY (PUP JOINT BELOW HANGER NOT AS PER SPECIFICATIONS).
1036 | 10/11/2022 | 11 Oct 0015 - 0045 | HRDH-1864 | ADC-14 | RIG | FOT | .5 | .5 | 903407 |  | RR | 15418 | MPMP | FAILURE OF RIG MUD PUMP#1, PUP OFF VALVE OPEN AT 3900 PSI. (SET AT 4500 PSI) >> REPLACED IT BY A NEW VALVE WHILE RECIPROCATE THE STRING.
1038 | 10/11/2022 | 08 Oct 0730 - 0500 | SDGM-1244 | ADC-41L | HLH | FOT | 24 | 92.5 | 903268 |  | TF | 10393 | LLAP | TROUBLESHOOT LINER TIE BACK SEAL SETTING. WHILE TRYING TO STING INTO 9-5/8" LINER TBR, PRESSURE NOT HOLD AS AN INDICATION OF NO SEAL INTEGRITY.
1039 | 10/11/2022 | 11 Oct 1830 - 1930 | UTMN-3045 | ADC-52 | GOC | FOT | 1 | 1 | 903413 |  | TF | 0 | CRT | AL-GAITH SUPPLIED WRONG LENGTH OF X/O & UNABLE TO TORQUE W/ TDS.
1041 | 10/11/2022 | 11 Oct 0100 - 0500 | UTMN-3045 | ADC-52 | GOC | XTTE | 4 | 4 | 903411 |  | TF | 116 | CTRQ | EXCESS TIME TO RUN 18-5/8" CASING DUE TO AL-GAITH CRT TOOL WITHOUT CORRECT LINKS. USE RIG TDS LINKS WITH DIFFICULTIES TO LINE UP CASING JOINT WITH CRT. CHANGE SPIDER SLIPS
1042 | 10/11/2022 | 11 Oct 1830 - 1930 | UTMN-3045 | ADC-52 | GOC | FOT | 1 | 1 | 903413 |  | TF | 0 | CRT | AL-GAITH SUPPLIED WRONG LENGTH OF X/O & UNABLE TO TORQUE W/ TDS.
1044 | 10/11/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 483 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1046 | 10/11/2022 | 06 Oct 0115 - 1130 | SDGM-1259 | ADC-67L | ARM | UXDF | 6.5 | 104.25 | 903348 |  | LCIR | 15994 | NA | ENCOUNTERED LOSSES AT 15,994 FT. PUMPED 2 X 150 BBL OF 40 PPB LCM PILL AND LOSSES NOT CURED.
1048 | 10/11/2022 | 11 Oct 1515 - 1615 | MRJN-3013 | ADM-339 | RIG | FOT | 1 | 1 | 903384 |  | RR | 4223 | HSYS | OBSERVED HYDRAULIC LEAK ON GRIPPER OF THE XY-RACKER. RIG NOT ABLE TO RACK DP STANDS. MAINT. TEAM - FAULT FIND AND REPAIR XY-RACKER.
1050 | 10/11/2022 | 11 Oct 0515 - 0130 | ABSF-223 | ADM-510 | SDM | FOT | 19.25 | 19.25 | 903425 |  | BHA | 8063 | LWD | LOST COMUNICATION WITH LWD TOOLS.TROUBLESHOOT WITHOUT SUCCESS. ROUND TRIP FOR TOOLS CHANGE OUT
1052 | 10/11/2022 | 11 Oct 1630 - 1730 | MRJN-814 | ARO-3002 | RIG | LHFL | 1 | 1 | 903410 |  | RR | 5205 | HSYS | IRON ROUGHNECK HYDRAULIC HOSE LEAKING.
1054 | 10/11/2022 | 11 Oct 0345 - 0500 | MRJN-537 | ARO-4001 | RIG | FOT | 1.25 | 1.25 | 903412 |  | RR | 11115 | TDS | OBSERVED HIGH TEMPERATURE ALARM ON TDS MOTOR B WHILE DRILLING 6 1/8" HOLE, STOP DRILLING, POOH TO 7" LINER SHOE, TROUBLESHOOTING TDS MOTOR B, OK.
1056 | 10/11/2022 | 11 Oct 1630 - 1900 | QTIF-99 | HI-5 | ARM | STBH | 2.5 | 2.5 | 903405 |  | STUK | 12142 | BHA | WHILE DRILLING 6" HORIZONTAL HOLE AT 12142 FT, THE STRING GOT STUCK.
1058 | 10/11/2022 | 11 Oct 1600 - 0500 | BRRI-17 | HI-9 | SDM | AINC | 13 | 13 | 903408 |  | DD | 6929 | BHA | SCHLUMBERGER RSS UNABLE TO BUILD THE DESIRED INCLINATION.
1060 | 10/11/2022 | 10 Oct 2045 - 1130 | HMYM-450414 | HWU-1 | RIG | IHFL | 6.5 | 14.75 | 903401 |  | RR | 0 | HSYS | INADEQUATE HYDRAULIC SUPPLY
1062 | 10/11/2022 | 10 Oct 2230 - 1600 | JAHM-5 | NBR-210S | RIG | FOT | 11 | 17.5 | 903355 |  | RR | 0 | PSYS | DRILLER CONSULE FAILED TO OPERATE, TROUBLE SHOOT.. NO SUCCESS.WAIT ON TECHNICIAN FROM TOWN.
1063 | 10/11/2022 | 11 Oct 0800 - 1145 | JLMN-200 | NBR-987S | RIG | FOT | 3.75 | 3.75 | 903423 |  | RR | 842 | TDS | TDS SHUT DOWN
1065 | 10/11/2022 | 11 Oct 0530 - 0700 | JLMN-200 | NBR-987S | RIG | FOT | 1.5 | 1.5 | 903422 |  | RR | 830 | TDS | TDS SHUT DOWN
1066 | 10/11/2022 | 11 Oct 0800 - 1145 | JLMN-200 | NBR-987S | RIG | FOT | 3.75 | 3.75 | 903423 |  | RR | 842 | TDS | TDS SHUT DOWN
1068 | 10/11/2022 | 11 Oct 1000 - 1230 | HSBH-68 | RM-74A | RIG | FOT | 2.5 | 2.5 | 903404 |  | RR | 9797 | SWVL | SWIVAL PACKING SEAL LEAKING WHILE P/TEST
1070 | 10/11/2022 | 11 Oct 1400 - 2200 | HWYH-352 | SINO-12L | RMD | SRVC | 8 | 8 | 903406 |  | WO | 5364 | NA | WAITING FOR RMD TO UPDATE DIRECTIONAL HWYH-352 L-0-1-3 PLAN#5.
1072 | 10/11/2022 | 10 Oct 1130 - 0500 | ANDR-139 | SINO-15L | TK1 | STBH | 24 | 41.5 | 903372 |  | STUK | 7243 | BHA | STRING GOT STUCK WHILE DRILLING.
1074 | 10/11/2022 | 10 Oct 1800 - 0230 | HRDH-1542 | SINO-33L | BAW | FOT | 21.5 | 32.5 | 903436 |  | TF | 14618 | CORRL | POOR QUALITY OF READING FOR LOGGING TOOL.
1076 | 10/11/2022 | 11 Oct 2245 - 0230 | HRDH-422 | SND-1502 | SAM | FOT | 3.75 | 3.75 | 903409 |  | BHA | 7018 | WBCL | ATTEMPT TO ACTIVATE PBL SUB WITH NO SUCCESS.
1078 | 10/11/2022 | 11 Oct 1715 - 1815 | MHKK-2 | SND-2005 | RIG | FOT | 1 | 1 | 903414 |  | TF | 13000 | PEL | SEALS BLEW OUT ON HYDRALIC CYLNDER TO RAISE AND LOWER PRAGMA
1080 | 10/11/2022 | 27 Sep 0630 - 0500 | HRDH-1291 | SND-2008 | ARM | UVLC | 24 | 336 | 902798 |  | LCIR | 0 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
1082 | 10/11/2022 | 10 Oct 2100 - 1330 | BRRI-522 | SP-121 | WWB | FOT | 7.5 | 15.5 | 903399 |  | BHA | 11594 | WBCL | COULDN'T PASS WITH 9-5/8'' WBCO THRU 9-5/8'' DV. WORK ON THIS INTERVAL, NO SUCCESS, TRIP OUT TO CHECK THE BHA.
1083 | 10/11/2022 | 11 Oct 1600 - 1700 | MZLJ-153202 | SP-261 | RIG | FOT | 1 | 1 | 903403 |  | RR | 4463 | TDS | REPLACE BRAND NEW WASH PIPE THAT WAS FOUND LEAKING
1085 | 10/11/2022 | 11 Oct 0530 - 0915 | MZLJ-153202 | SP-261 | RIG | XTRI | 3.75 | 3.75 | 903402 |  | JF | 4463 | BOP | EXCESSIVE TIME SPENT N/U BOP. NUMEROUS LEAKING FLANGES DURING PRESSURE TEST.
1086 | 10/11/2022 | 11 Oct 1600 - 1700 | MZLJ-153202 | SP-261 | RIG | FOT | 1 | 1 | 903403 |  | RR | 4463 | TDS | REPLACE BRAND NEW WASH PIPE THAT WAS FOUND LEAKING
1088 | 10/11/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 21.75 | 25 | 903398 |  | BHS | 5835 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1090 | 10/11/2022 | 10 Oct 1030 - 0500 | HRDH-1989 | SSA-303 | RIG | LHFL | 24 | 42.5 | 903397 |  | BOP | 1981 | RWCS | ACCUMALATOR BOTTLES WERE CLOSED BECAUSE OF LACK OF OIL IN THE RESIVIOR AND ALSO WORKING ON ELECTRICAL CONTROL PANEL, PULL TO SHOE AND PERFORM AN INVESTIGATION AND REPAIR THE PROBLEMS.
1092 | 10/11/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 177.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNTIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON, EVALUATE POWER SYSTEM AND TDS MOTOR RPM'S. WHILE ATTEMPTING TO DRILL AHEAD WITH 90 RPM'S, TDS GETTING ERRATIC RPM'S. MUD PUMPS LOSING AND GAINING POWER WHILE CIRCULATING OR DRILLING. TDS & PUMPS ARE POWERING ON AND OFF WITH NO CHANGE IN COMMAND WHILE UNDER LOAD. FOUND GENERATORS ARE NOT SHARING THE ELECTRICAL LOAD PROPERLY. M/U & RIH 16'' ROTARY BHA TO SHOE TO CREATE PRESSURE FOR PUMPS TO TEST LOAD SHARING
1094 | 10/12/2022 | 12 Oct 2330 - 0000 | QTIF-519 | 088TE | RIG | FOT | .5 | .5 | 903461 |  | TF | 15306 | TTRQ | WHILE USING IRON ROUGHNECK TO BREAKOUT 5" DP CONNECTION, ONE BOLT HEAD AND WASHER BROKE OFF FROM THE MOUNT BOLT ON THE UPPER WRENCH CLAMP CYLINDER. USE RIG MANUAL TONGS MEANWHILE FIXING THE IRON ROUGHNECK.
1096 | 10/12/2022 | 12 Oct 2015 - 2045 | HRDH-1864 | ADC-14 | RIG | FOT | .5 | .5 | 903457 |  | RR | 15610 | MPMP | FAILURE OF RIG MUD PUMP#1, CHANGED TWO VALVES AND TWO SEATS >> MEANWHILE RECIPROCATE AND ROTATE THE STRING.
1098 | 10/12/2022 | 08 Oct 0730 - 0500 | SDGM-1244 | ADC-41L | HLH | FOT | 23.5 | 116 | 903268 |  | TF | 9010 | LLAP | TROUBLESHOOT LINER TIE BACK SEAL SETTING. WHILE TRYING TO STING INTO 9-5/8" LINER TBR, PRESSURE NOT HOLD AS AN INDICATION OF NO SEAL INTEGRITY.
1100 | 10/12/2022 | 11 Oct 0100 - 0700 | UTMN-3045 | ADC-52 | GOC | XTTE | 2 | 6 | 903411 |  | TF | 116 | CTRQ | EXCESS TIME TO RUN 18-5/8" CASING DUE TO AL-GAITH CRT TOOL WITHOUT CORRECT LINKS. USE RIG TDS LINKS WITH DIFFICULTIES TO LINE UP CASING JOINT WITH CRT. CHANGE SPIDER SLIPS
1122 | 10/12/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | .75 | 477.25 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1138 | 10/12/2022 | 12 Oct 1200 - 0230 | MRJN-2018 | ADM-261 | SWL | FOT | 14.5 | 14.5 | 903465 |  | TF | 11200 | WLT | W/L UNIT UNABLE TO ACTIVATE TRACTOR TO CONTINUE PROCEEDING IN HOLE.
1140 | 10/12/2022 | 12 Oct 0430 - 0500 | MRJN-814 | ARO-3002 | BHI | HERR | .5 | .5 | 903473 |  | SURV | 11748 | MS | EXCESSIVE TIME TO TAKE SURVEY.
1142 | 10/12/2022 | 11 Oct 0345 - 1700 | MRJN-537 | ARO-4001 | RIG | FOT | 12 | 13.25 | 903412 |  | RR | 11115 | TDS | OBSERVED HIGH TEMPERATURE ALARM ON TDS MOTOR B WHILE DRILLING 6 1/8" HOLE, STOP DRILLING, PLAN TO POOH TO 7" LINER SHOE, TROUBLESHOOTING TDS MOTOR B.
1143 | 10/12/2022 | 12 Oct 0315 - 0500 | KHRS-335 | DQ-48 | BHI | IDPR | 1.75 | 1.75 | 903478 |  | DD | 2924 | MMOT | REPAIR ON DD CABINE- ELECTRICAL PROBLEM (ALL PC STATIONS SHUT DOWN), CHANGE UPS ELECTRICAL CABLES.
1145 | 10/12/2022 | 12 Oct 0115 - 0215 | KHRS-335 | DQ-48 | RIG | FOT | 1 | 1 | 903477 |  | RR | 2880 | MPMP | RIG REPAIR ON MUD PUMP N# 2 & 3 (CHANGE LINER & PISTON, LEAK BETWEEN PUMP & MUD TANKS).
1146 | 10/12/2022 | 12 Oct 0315 - 0500 | KHRS-335 | DQ-48 | BHI | IDPR | 1.75 | 1.75 | 903478 |  | DD | 2924 | MMOT | REPAIR ON DD CABINE- ELECTRICAL PROBLEM (ALL PC STATIONS SHUT DOWN), CHANGE UPS ELECTRICAL CABLES.
1148 | 10/12/2022 | 11 Oct 1600 - 0900 | BRRI-17 | HI-9 | SDM | AINC | 4 | 17 | 903408 |  | DD | 6929 | BHA | SCHLUMBERGER RSS UNABLE TO BUILD THE DESIRED INCLINATION.
1150 | 10/12/2022 | 12 Oct 1745 - 0430 | SHYB-134 | NA-207S | RIG | FOT | 10.75 | 10.75 | 903474 |  | DSF | 8506 | DP | OBSERVED GRADUAL PRESSURE DROP FROM 2,000 PSI TO 1,600 PSI WHILE DRILING 6 1/8" HOLE.
1151 | 10/12/2022 | 12 Oct 0130 - 0300 | UTMN-3012 | NBR-797S | RIG | FOT | 1.5 | 1.5 | 903462 |  | RR | 2440 | HSYS | HYDRAULIC SUPPLY LINE TO TM-120 FITTING AT A CONNECTION IN THE LINE FAILED CAUSING TM-120 HYRAULIC TANK TO EMPTY, REPLACED FITTING, REFILL HYDRAULIC OIL TANK. WHILE REPLACING FITTING RIG UP AIR PIPE SPINNERS.
1153 | 10/12/2022 | 12 Oct 0500 - 0800 | UTMN-3012 | NBR-797S | RIG | XTRI | 3 | 3 | 903456 |  | JF | 4102 | BOP | EXCESSIVE TIME N/U BOP, BELL NIPPLE & FLOW LINE
1154 | 10/12/2022 | 12 Oct 0130 - 0300 | UTMN-3012 | NBR-797S | RIG | FOT | 1.5 | 1.5 | 903462 |  | RR | 2440 | HSYS | HYDRAULIC SUPPLY LINE TO TM-120 FITTING AT A CONNECTION IN THE LINE FAILED CAUSING TM-120 HYRAULIC TANK TO EMPTY, REPLACED FITTING, REFILL HYDRAULIC OIL TANK. WHILE REPLACING FITTING RIG UP AIR PIPE SPINNERS.
1156 | 10/12/2022 | 10 Oct 1130 - 1930 | ANDR-139 | SINO-15L | TK1 | STBH | 14.5 | 56 | 903372 |  | STUK | 7243 | BHA | STRING GOT STUCK WHILE DRILLING.
1158 | 10/12/2022 | 11 Oct 0130 - 0500 | UTMN-3095 | SND-2006 | ARM | UXGE | 23.5 | 27 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
1160 | 10/12/2022 | 27 Sep 0630 - 0500 | HRDH-1291 | SND-2008 | ARM | UVLC | 24 | 360 | 902798 |  | LCIR | 0 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
1162 | 10/12/2022 | 12 Oct 0230 - 0500 | MNIF-142 | SP-110 | RIG | FOT | 2.5 | 2.5 | 903472 |  | RR | 10030 | TDS | REPAIR TDS HYDRAULIC LEAKAGE
1164 | 10/12/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 23.25 | 48.25 | 903398 |  | BHS | 5835 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1166 | 10/12/2022 | 10 Oct 1030 - 1730 | HRDH-1989 | SSA-303 | RIG | OTH | 12.5 | 55 | 903397 |  | UPRA | 1981 | NA | ACCUMALATOR BOTTLES WERE CLOSED BECAUSE OF LACK OF OIL IN THE RESIVIOR AND ALSO WORKING ON ELECTRICAL CONTROL PANEL, PULL TO SHOE AND PERFORM AN INVESTIGATION AND REPAIR THE PROBLEMS.
1168 | 10/12/2022 | 12 Oct 0645 - 0915 | NJYN-16 | SSA-5891 | RIG | FOT | 2.5 | 2.5 | 903427 |  | BHA | 1686 | HTMTR | PLUG DRILL STRING FROM 4" HWDP SCALE .
1170 | 10/12/2022 | 11 Oct 0245 - 0500 | HRDH-2406 | SSA-5917 | ARM | WC20 | 24 | 26.25 | 903460 |  | WCNT | 12199 | NA | AFTER EXTENDED FLOW CHECK AT TOP BHA ,SUSPECT JILH SLIGHTLY FLOW IN THE RANGE OF 1.5 BPH RIH BACK TO 9 5/8 SHOE & KILL WELL WITH 118 PCF
1172 | 10/13/2022 | 13 Oct 1530 - 1600 | HRDH-1864 | ADC-14 | RIG | FOT | .5 | .5 | 903479 |  | RR | 15788 | MPMP | FAILURE OF RIG MUD PUMP#2, CHANGED PISTON >> MEANWHILE RECIPROCATE AND ROTATE THE STRING.
1174 | 10/13/2022 | 13 Oct 1600 - 0500 | UTMN-2309 | ADC-34 | SPS | FOT | 13 | 13 | 903487 |  | BHA | 16069 | RSS | RSS ICRUISE STOPPED COMMUNICATING
1176 | 10/13/2022 | 13 Oct 0000 - 0300 | SDGM-1143 | ADC-51 | SPS | FOT | 3 | 3 | 903488 |  | BHA | 200 | RSS | WHILE SHALLOW TEST SPS TOOLS, NOTICED RSS NOT WORKING, REPLACED WITH NEW ONE/OK.
1193 | 10/13/2022 | 21 Sep 0200 - 1030 | UTMN-3171 | ADC-55L | TK3 | LCRW | 5.5 | 482.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1195 | 10/13/2022 | 13 Oct 2100 - 0500 | ABHD-183 | ADC-58L | RIG | FOT | 8 | 8 | 903482 |  | RR | 6828 | CRN | BOP WINCH ODS MALFUNCTION WHERE IT CAN'T MOVE ANY MORE FRONT OR BACKWARD (UNSAFE CONDITION TO WORK ON WELL HEAD).
1223 | 10/13/2022 | 13 Oct 1600 - 0000 | MRJN-2018 | ADM-261 | SWL | FOT | 8 | 8 | 903483 |  | TF | 0 | WLT | W/L ACTUATOR TOOL FAIL SURFACE TEST PRIOR TO PLUG RETRIEVAL. B/U ONBOARD ALSO NOT FUNCTIONING CORRECTLY.
1225 | 10/13/2022 | 13 Oct 1545 - 1615 | ABSF-128 | EXL-IA | RIG | FOT | .5 | .5 | 903486 |  | RR | 5328 | ACDC | RIG BLACK OUT AND POWER OUTAGE AFTER FAULT INDICATION ON HIFOG PUMP UNIT IN PORT P-TANK ROOM.
1227 | 10/13/2022 | 11 Oct 1600 - 1930 | BRRI-17 | HI-9 | SDM | AINC | 14.5 | 51.5 | 903408 |  | DD | 6929 | BHA | SCHLUMBERGER RSS UNABLE TO BUILD THE DESIRED INCLINATION.
1229 | 10/13/2022 | 13 Oct 2045 - 0500 | SHHM-571002 | NBR-16S | RIG | FOT | 6.75 | 6.75 | 903481 |  | RR | 10514 | DWKS | DRAWWORKS WOULD NOT START UP (ELECTRICAL PROBLEM)
1230 | 10/13/2022 | 13 Oct 1100 - 1900 | JLMN-200 | NBR-987S | RIG | GRF | 8 | 8 | 903517 |  | UPRA | 1004 | DWKS | EATON BRAKE LOCKED UP
1232 | 10/13/2022 | 13 Oct 2300 - 0015 | JLMN-200 | NBR-987S | RIG | GRF | 1.25 | 1.25 | 903489 |  | UPRA | 1004 | TDS | FOUND TORQUE BOOST MOTOR LEAKING OIL
1233 | 10/13/2022 | 13 Oct 1100 - 1900 | JLMN-200 | NBR-987S | RIG | GRF | 8 | 8 | 903517 |  | UPRA | 1004 | DWKS | EATON BRAKE LOCKED UP
1235 | 10/13/2022 | 13 Oct 1800 - 2100 | HWYH-352 | SINO-12L | RIG | FOT | 3 | 3 | 903490 |  | RR | 7019 | TDS | TDS COMMEND SYSTEM FAILURE.
1237 | 10/13/2022 | 13 Oct 0630 - 0500 | ABHD-108 | SINO-16 | BC | FOT | 22.5 | 22.5 | 903536 |  | TF | 5843 | PKR | BAKER 9-5/8" ELECPAC PACKER FAILED TO HOLD TCA PRESSURE AND OBSERVED THERE WAS NO ANY INDICATION OF SHEARING PINS SHEARED WHILE SETTING BAKER PKR.
1239 | 10/13/2022 | 13 Oct 1100 - 1230 | MNIF-204 | SINO-25 | RIG | FPMP | 1.5 | 1.5 | 903480 |  | RR | 9342 | MPMP | HAD LEAK IN MUD PUMP#2 PRV.
1241 | 10/13/2022 | 11 Oct 0130 - 0500 | UTMN-3095 | SND-2006 | ARM | UXGE | 22.75 | 49.75 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
1243 | 10/13/2022 | 27 Sep 0630 - 0030 | HRDH-1291 | SND-2008 | ARM | UVLC | 19.5 | 379.5 | 902798 |  | LCIR | 12135 | NA | UNEXPECTED LOSSES IN KHUF-B FORMATION
1245 | 10/13/2022 | 12 Oct 0230 - 0800 | MNIF-142 | SP-110 | RIG | FOT | 3 | 5.5 | 903472 |  | RR | 10030 | TDS | REPAIR TDS HYDRAULIC LEAKAGE
1247 | 10/13/2022 | 12 Oct 0300 - 0500 | HWYH-74 | SP-167 | WWL | FOT | 24 | 25.5 | 903516 |  | TF | 5857 | WLT | WFD CALIPER LOGGING COULDN'T PASS WINDOW, WORK ON SAME WITHIN LIMITS THEN POOH FOUND W'STOCK ENGAGED TO MULE SHOE
1248 | 10/13/2022 | 13 Oct 2030 - 0500 | QTIF-172 | SSA-202 | NCS | CPNF | 8.5 | 8.5 | 903485 |  | CMT | 3550 | NA | GREEN CONTAMINATED CEMENT ON SHAKER WHILE WASHING DOWN WITH 12-1/4" C/O ASSY & TOP OF CMT PLUG DEEPER THAN PREDICTED.
1250 | 10/13/2022 | 10 Oct 0145 - 2030 | QTIF-172 | SSA-202 | ARM | CWEL | 15 | 63.25 | 903398 |  | BHS | 5835 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1251 | 10/13/2022 | 13 Oct 2030 - 0500 | QTIF-172 | SSA-202 | NCS | CPNF | 8.5 | 8.5 | 903485 |  | CMT | 3550 | NA | GREEN CONTAMINATED CEMENT ON SHAKER WHILE WASHING DOWN WITH 12-1/4" C/O ASSY & TOP OF CMT PLUG DEEPER THAN PREDICTED.
1253 | 10/13/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 225.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNTIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON, EVALUATE POWER SYSTEM AND TDS MOTOR RPM'S. WHILE ATTEMPTING TO DRILL AHEAD WITH 90 RPM'S, TDS GETTING ERRATIC RPM'S. MUD PUMPS LOSING AND GAINING POWER WHILE CIRCULATING OR DRILLING. TDS & PUMPS ARE POWERING ON AND OFF WITH NO CHANGE IN COMMAND WHILE UNDER LOAD. FOUND GENERATORS ARE NOT SHARING THE ELECTRICAL LOAD PROPERLY. M/U & RIH 7'' SCRAPPER ASSY TO 185', IN ORDER TO CREATE MORE PRESSURE FOR MUD PUMPS TO LOAD TEST GENERATORS POWER SHARING
1255 | 10/14/2022 | 14 Oct 0515 - 0915 | HRDH-1864 | ADC-14 | RIG | FOT | 4 | 4 | 903491 |  | RR | 15839 | MPMP | FAILURE OF RIG MUD PUMP#1, CHANGED TWO VALVES AND SEATS >> MEANWHILE RECIPROCATE AND ROTATE THE STRING.
1257 | 10/14/2022 | 13 Oct 1600 - 0500 | UTMN-2309 | ADC-34 | SPS | FOT | 23.5 | 36.5 | 903487 |  | BHA | 16069 | RSS | RSS ICRUISE STOPPED COMMUNICATING
1259 | 10/14/2022 | 08 Oct 0730 - 0500 | SDGM-1244 | ADC-41L | HLH | FOT | 24 | 164 | 903268 |  | TF | 9010 | LLAP | TROUBLESHOOT LINER TIE BACK SEAL SETTING. WHILE TRYING TO STING INTO 9-5/8" LINER TBR, PRESSURE NOT HOLD AS AN INDICATION OF NO SEAL INTEGRITY.
1277 | 10/14/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 21 | 503.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1279 | 10/14/2022 | 13 Oct 2100 - 1700 | ABHD-183 | ADC-58L | RIG | FOT | 7 | 15 | 903482 |  | RR | 6828 | CRN | BOP WINCH ODS MALFUNCTION WHERE IT CAN'T MOVE ANY MORE FRONT OR BACKWARD (UNSAFE CONDITION TO WORK ON WELL HEAD).
1291 | 10/14/2022 | 14 Oct 1300 - 1730 | ABQQ-590 | ADES-158 | RIG | HERR | 4.5 | 4.5 | 903494 |  | JF | 6540 | DP | FOUND DRILL PIPE TALLY ERROR, GOC ASKED TO RELOG AGAIN FROM 6410 FT TO 6500 FT.
1293 | 10/14/2022 | 14 Oct 0900 - 1315 | MRJN-3013 | ADM-339 | FMC | FOT | 4.25 | 4.25 | 903493 |  | TF | 8060 | CTRQ | FRANKS INSPECTED EQUIPMENT BEFORE JOB AND THEN WE OBSERVE CRT RUBBER DAMAGED.
1295 | 10/14/2022 | 14 Oct 0445 - 0500 | MRJN-723 | AOD-111 | BHI | FOT | .25 | .25 | 903592 |  | BHA | 13358 | MWD | LOST BHI MWD SIGNAL, TROUBLE SHOOTING FAILED TOOL.
1297 | 10/14/2022 | 14 Oct 1830 - 0500 | MRJN-121 | ARO-2001 | HCM | CEDE | 10.5 | 10.5 | 903593 |  | JF | 11700 | NA | CEMENT PLUG FAILURE, CEMENT STILL SOFT 44 HRS AFTER SET THE PLUG.
1299 | 10/14/2022 | 14 Oct 0300 - 0445 | MRJN-537 | ARO-4001 | RIG | FOT | 1.75 | 1.75 | 903589 |  | RR | 14142 | PSYS | WHILE CIRCULATING HOLE CLEAN, HAD ALL RIG FLOOR EQUIPMENT SHUT DOWN, UNABLE TO CIRCULATE, ROTATE OR RECIPROCATE, TROUBLESHOOTING, WORKING OK.
1301 | 10/14/2022 | 14 Oct 0515 - 0500 | HRDH-1541 | DQ-49L | BWH | FOT | 22.5 | 22.5 | 903557 |  | TF | 9398 | WPSTK | AFTER FINISH DRLG 18' RATE HOLE T/ 9,403' OBSERVED 140 BPH / 300 GPM DYNAMIC LOSSES W/ 70% RETURN.
1303 | 10/14/2022 | 14 Oct 0100 - 0500 | ZULF-2066 | ED-85A | SDM | FOT | 4 | 4 | 903586 |  | BHA | 12181 | LWD | WHILE DRILLING 8-1/2" X 9-1/2" HOLE, SLB LWD TOOL STOP LOGGING, SLB ATTEMPT TO TROUBLESHOOTING NO SUCCESS. DECISION TO POH AND REPLACE SLB LWD.
1305 | 10/14/2022 | 14 Oct 0700 - 1900 | BRRI-17 | HI-9 | HCM | HERR | 12 | 12 | 903591 |  | CMT | 7049 | NA | HALLIBURTON LAB TEST REPORT NOT AVAILABLE ON TIME TO PERFORM L3 P & A.
1307 | 10/14/2022 | 13 Oct 2045 - 2100 | SHHM-571002 | NBR-16S | RIG | FOT | 7 | 13.75 | 903481 |  | RR | 10514 | DWKS | DRAWWORKS WOULD NOT START UP (ELECTRICAL PROBLEM)
1309 | 10/14/2022 | 14 Oct 1600 - 1830 | HSBH-68 | RM-74A | RIG | FOT | 2.5 | 2.5 | 903577 |  | RR | 9797 | HSYS | LEAK IN DERRICK BRIDGE RACKER, ARO TROUBLESHOOT & REPAIR SAME.
1311 | 10/14/2022 | 13 Oct 0630 - 0500 | ABHD-108 | SINO-16 | BAL | FOT | 24 | 46.5 | 903536 |  | TF | 5843 | PKR | BAKER 9-5/8" ELECPAC PACKER FAILED TO HOLD TCA PRESSURE. WHILE POOH FOUND ONE OF THE ESP BANDING FALL OFF THE ESP CABLE AND STUCK AROUND THE RUBBER ELEMENT OF THE PACKER, WHICH NOT ALLOWED THE PACKER TO BE FULLY SEAL.
1313 | 10/14/2022 | 14 Oct 0300 - 0500 | MNIF-204 | SINO-25 | SPS | FOT | 2 | 2 | 903595 |  | BHA | 10563 | RSS | HALL RSS LOST ELECTRIC COMMUNICATION WHILE DRILLING AT 10563'.
1315 | 10/14/2022 | 14 Oct 1630 - 2130 | UTMN-1245 | SINO-26 | WDS | FOT | 5 | 5 | 903582 |  | BHA | 0 | MWD | MWD FAILURE.
1317 | 10/14/2022 | 14 Oct 0630 - 0500 | KHRS-463 | SINO-27N | INW | FOT | 22.5 | 22.5 | 903576 |  | TF | 6979 | PLUGT | INTERWELL ME-PLUG JUMPED WHILE JARRING
1319 | 10/14/2022 | 14 Oct 0600 - 0830 | HWYH-355 | SINO-42L | ITS | FOT | 2.5 | 2.5 | 903590 |  | TF | 0 | TTRQ | MALFUNCTOIN OF ITS POWER UNIT .
1321 | 10/14/2022 | 11 Oct 0130 - 0500 | UTMN-3095 | SND-2006 | ARM | UXGE | 20.5 | 70.25 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
1323 | 10/14/2022 | 14 Oct 1200 - 2000 | AWTD-104001 | SND-2007 | SDM | MATL | 8 | 8 | 903588 |  | WO | 0 | NA | WHILE MU SLB 5-7/8" MUD MOTOR WITH BIT, FOUND MOTOR DRIVER SHAFT CONNECTION LOOSE WITH BIT BOX SUB.
1325 | 10/14/2022 | 12 Oct 0300 - 0500 | HWYH-74 | SP-167 | WWL | FOT | 24 | 49.5 | 903516 |  | TF | 5857 | WLT | WFD CALIPER LOGGING COULDN'T PASS WINDOW, WORK ON SAME WITHIN LIMITS THEN POOH FOUND W'STOCK ENGAGED TO MULE SHOE
1327 | 10/14/2022 | 13 Oct 2030 - 0500 | QTIF-172 | SSA-202 | NCS | CPNF | 24 | 32.5 | 903485 |  | CMT | 3550 | NA | GREEN CONTAMINATED CEMENT ON SHAKER WHILE WASHING DOWN WITH 12-1/4" C/O ASSY & TOP OF CMT PLUG DEEPER THAN PREDICTED.
1329 | 10/14/2022 | 14 Oct 1215 - 1500 | MSBA-1 | SSA-5820 | RIG | FOT | 2.75 | 2.75 | 903579 |  | RR | 9230 | MPMP | REPAIR ON MUD PUMP#1 & 3.
1331 | 10/14/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 249.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNTIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON, EVALUATE POWER SYSTEM AND TDS MOTOR RPM'S. WHILE ATTEMPTING TO DRILL AHEAD WITH 90 RPM'S, TDS GETTING ERRATIC RPM'S. MUD PUMPS LOSING AND GAINING POWER WHILE CIRCULATING OR DRILLING. TDS & PUMPS ARE POWERING ON AND OFF WITH NO CHANGE IN COMMAND WHILE UNDER LOAD. FOUND GENERATORS ARE NOT SHARING THE ELECTRICAL LOAD PROPERLY. M/U & RIH 7'' SCRAPPER ASSY TO 185', IN ORDER TO CREATE MORE PRESSURE FOR MUD PUMPS TO LOAD TEST GENERATORS POWER SHARING
1333 | 10/14/2022 | 14 Oct 0815 - 1145 | HRDH-2406 | SSA-5917 | APR | SRVC | 3.5 | 3.5 | 903556 |  | WO | 12199 | NA | WAIT ON CMT LAB TEST CONFIRMATION TO PERFOM 7 LINER CMT JOB
1335 | 10/14/2022 | 14 Oct 2300 - 0500 | UTMN-3193 | SSA-5970 | RIG | FOT | 6 | 6 | 903587 |  | RR | 913 | TDS | LOST CUMMUNICATION WITH TDS, SAIPEM TDS TECHNICIAN TROUBLE SHOOTING THE PROBLEM.
1337 | 10/14/2022 | 14 Oct 2300 - 0500 | DYBN-21 | SSA-5972 | WDV | FOT | 6 | 6 | 903583 |  | TF | 3885 | DV | DV PACEKER FAILED TO SET AND RESULTING LOST MUD RETURNS.
1339 | 10/14/2022 | 14 Oct 1515 - 1630 | HRDH-1979 | SSA-5974 | ARM | CWEL | 1.25 | 1.25 | 903594 |  | BHS | 8400 | NA | ENCOUNTERED TIGHT SPOT AT 8,400'. STRING TORQUED UP AND STRING STUCK, HAD CIRCULATION WITH NO ROTATION,
1341 | 10/14/2022 | 14 Oct 0600 - 1015 | ZULF-653 | V140A | DEP | FOT | 4.25 | 4.25 | 903498 |  | TF | 20 | RESH | DURING FUNCTION TESTING REAMER SHOE , OBSERVED REAMER SHOE NOT ROTATING.
1343 | 10/15/2022 | 13 Oct 1600 - 0700 | UTMN-2309 | ADC-34 | SPS | FOT | 2 | 38.5 | 903487 |  | BHA | 16069 | RSS | RSS ICRUISE STOPPED COMMUNICATING
1345 | 10/15/2022 | 08 Oct 0730 - 0200 | SDGM-1244 | ADC-41L | HLH | FOT | 21 | 185 | 903268 |  | TF | 9010 | LLAP | TROUBLESHOOT LINER TIE BACK SEAL SETTING. WHILE TRYING TO STING INTO 9-5/8" LINER TBR, PRESSURE NOT HOLD AS AN INDICATION OF NO SEAL INTEGRITY.
1347 | 10/15/2022 | 15 Oct 2115 - 2315 | UTMN-3045 | ADC-52 | RIG | FOT | 2 | 2 | 903619 |  | RR | 4600 | MPMP | REPAIR ON MUD PUMPS. MUD PUMP#2 ELECTRICAL DIVERTER SYSTEM NOT WORKING SWITCH TO BACK UP ONE STILL PROBLEM PERSIST. PUMP OUT OF SERVICE. CHANGE SEATS AND VALVE SEATS ON MUD PUMP#1,3
1349 | 10/15/2022 | 15 Oct 0500 - 0500 | HRDH-1530 | ADC-53L | BC | STCT | 24 | 24 | 903561 |  | STUK | 4818 | PDHMS | GOT STUCK WHILE RUNNING BACKER UPER COMPLETION
1369 | 10/15/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 527.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1370 | 10/15/2022 | 15 Oct 2015 - 0115 | HWYH-1287 | ADC-59L | RIG | PPMP | 5 | 5 | 903598 |  | UPRA | 372 | NA | TDS AND CRT WAS NOT ON CENTER OF THE CASING.
1372 | 10/15/2022 | 15 Oct 1630 - 2015 | HWYH-1287 | ADC-59L | ITS | FOT | 3.75 | 3.75 | 903543 |  | TF | 372 | CRT | OBSERVED ITS CRT RUBBER CONE STUCK & LEFT INSIDE JOINT # 10 (136 PPF).
1373 | 10/15/2022 | 15 Oct 1300 - 1530 | HWYH-1287 | ADC-59L | ITS | FOT | 2.5 | 2.5 | 903565 |  | TF | 127 | CRT | CRT SERVICE LOOP LINES WERE NOT FULLY PROTECTED WITH WRAP.
1374 | 10/15/2022 | 15 Oct 2015 - 0115 | HWYH-1287 | ADC-59L | RIG | PPMP | 5 | 5 | 903598 |  | UPRA | 372 | NA | TDS AND CRT WAS NOT ON CENTER OF THE CASING.
1376 | 10/15/2022 | 14 Oct 1830 - 0430 | MRJN-560 | ADC-60 | BAW | XTRI | 23.5 | 34 | 903596 |  | JF | 7255 | WLT | IFX (IN-SITU FLUID EXPLORER) IS NOT READING CORRECT OD VALUES (OPTICAL DENSITY).
1391 | 10/15/2022 | 15 Oct 2130 - 2330 | UTMN-1952 | ADES-173 | RIG | FOT | 2 | 2 | 903599 |  | RR | 12284 | SWVL | SAVER SUB WORN OUT.
1393 | 10/15/2022 | 15 Oct 0500 - 2100 | MRJN-723 | AOD-111 | BHI | FOT | 15 | 15 | 903616 |  | BHA | 13358 | MWD | LOST BHI MWD SIGNAL, ATTEMPT TO TROUBLESHOOT SAME WITHOUT SUCCESS.
1395 | 10/15/2022 | 14 Oct 1830 - 0500 | MRJN-121 | ARO-2001 | HCM | CEDE | 24 | 34.5 | 903593 |  | JF | 11700 | NA | CEMENT PLUG FAILURE, CEMENT STILL SOFT 44 HRS AFTER SET THE PLUG.
1397 | 10/15/2022 | 15 Oct 1915 - 0230 | MRJN-814 | ARO-3002 | RIG | FOT | 7.25 | 7.25 | 903597 |  | RR | 13913 | TDS | OBSERVED SWIVEL PAKING LEAKING ON TOP DRIVE
1399 | 10/15/2022 | 15 Oct 1130 - 1215 | NJYN-94 | DPS-4 | RIG | FOT | .75 | .75 | 903542 |  | RR | 13810 | TDS | WHILE SLIDE DRILLING 8-3/8'' HOLE, DRILLER ATEMPT TO HOLD TOOLFACE AZIMUTH BY TDS MOTOR BRAKE BUT BRAKE FUNCTION DIDN'T RESPOND. RIG ELECTRICIAN TROUBLESHOOT THE FAILURE. HE FOUND THAT TDS MOTOR WAS NOT RECEIVING ELECTRICAL SIGNAL.
1401 | 10/15/2022 | 15 Oct 1900 - 2000 | NJYN-18 | DPS-74 | RIG | FOT | 1 | 1 | 903541 |  | RR | 8735 | DWKS | HAVE A FAILURE IN RIG DRAWWORKS ENCODER; REPLACE A NEW ENCODER, AND PERFORM A FUNCTIONAL TEST.
1403 | 10/15/2022 | 14 Oct 0515 - 0500 | HRDH-1541 | DQ-49L | BWH | FOT | 24 | 46.5 | 903557 |  | TF | 9398 | WPSTK | AFTER FINISH DRLG 18' RATE HOLE T/ 9,403' OBSERVED 140 BPH / 300 GPM DYNAMIC LOSSES W/ 70% RETURN.
1405 | 10/15/2022 | 14 Oct 0100 - 0500 | ZULF-2066 | ED-85A | SDM | FOT | 23 | 27 | 903586 |  | BHA | 12181 | LWD | WHILE DRILLING 8-1/2" X 9-1/2" HOLE, SLB LWD TOOL STOP LOGGING, SLB ATTEMPT TO TROUBLESHOOTING NO SUCCESS. DECISION TO POH AND REPLACE SLB LWD.
1407 | 10/15/2022 | 15 Oct 0500 - 0600 | TINT-91 | NBR-783S | RIG | DRIG | 1 | 1 | 903562 |  | RR | 0 | HSYS | MAST LEVEL NOT STRAIGHT.
1409 | 10/15/2022 | 15 Oct 0500 - 1700 | HRDH-1944 | PA-70S | RIG | FOT | 12 | 12 | 903617 |  | RR | 1440 | TDS | TDS BLOWER MOTOR IS NOT WORKING, TROUBLE SHOOTING NOT WORKING.
1411 | 10/15/2022 | 15 Oct 0545 - 0745 | HSBH-68 | RM-74A | FMC | SRVC | 2 | 2 | 903559 |  | WO | 9797 | NA | FRANKS TORQUE SENSOR MALFUNCTION.
1413 | 10/15/2022 | 15 Oct 2100 - 0500 | ABJF-155 | SINO-11 | WWL | FOP | 8 | 8 | 903563 |  | JF | 4407 | CUT | RUN & FIRED WFD WL RCT, POOH & R/D WL EQT, ATTEMPT TO PULL COMPLETION STRING WITH 50 KLB OVERPULL , OBSERVE NO STRING MOVEMENT.
1415 | 10/15/2022 | 13 Oct 0630 - 0500 | ABHD-108 | SINO-16 | BAL | FOT | 24 | 70.5 | 903536 |  | TF | 5843 | PKR | BAKER 9-5/8" ELECPAC PACKER FAILED TO HOLD TCA PRESSURE. WHILE POOH FOUND ONE OF THE ESP BANDING FALL OFF THE ESP CABLE AND STUCK AROUND THE RUBBER ELEMENT OF THE PACKER, WHICH NOT ALLOWED THE PACKER TO BE FULLY SEAL.
1417 | 10/15/2022 | 14 Oct 0300 - 0500 | MNIF-204 | SINO-25 | SPS | FOT | 24 | 26 | 903595 |  | BHA | 10563 | RSS | SPS RSS LOST ELECTRIC COMMUNICATION WHILE DRILLING AT 10563'.
1419 | 10/15/2022 | 14 Oct 0630 - 0500 | KHRS-463 | SINO-27N | INW | FOT | 24 | 46.5 | 903576 |  | TF | 6979 | BP | INTERWELL ME-PLUG JUMPED UP & DROPPED WHILE JARRING TO RETRIEVE IT.
1421 | 10/15/2022 | 11 Oct 0130 - 0500 | UTMN-3095 | SND-2006 | ARM | UXGE | 15 | 85.25 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
1423 | 10/15/2022 | 15 Oct 1030 - 1415 | FDHL-148 | SP-124 | BHI | FOT | 3.75 | 3.75 | 903540 |  | BHA | 10623 | MWD | TROUBLESHOOT MWD SIGNAL LOSS
1425 | 10/15/2022 | 12 Oct 0300 - 0500 | HWYH-74 | SP-167 | WWL | FOT | 24 | 73.5 | 903516 |  | TF | 5857 | WLT | WFD CALIPER LOGGING COULDN'T PASS WINDOW, WORK ON SAME WITHIN LIMITS THEN POOH FOUND W'STOCK ENGAGED TO MULE SHOE
1427 | 10/15/2022 | 14 Oct 0400 - 1700 | HRDH-795 | SP-58 | TK1 | FOT | 12 | 13 | 903564 |  | TF | 17565 | LINR | CAN'T CIRCULATE THRU HES CMT HEAD, BY PASS PLUGGED, REPLACE WITH NEW ONE.
1428 | 10/15/2022 | 13 Oct 2030 - 1645 | QTIF-172 | SSA-202 | NCS | CPNF | 11.25 | 43.75 | 903485 |  | CMT | 3550 | NA | GREEN CONTAMINATED CEMENT ON SHAKER WHILE WASHING DOWN WITH 12-1/4" C/O ASSY & TOP OF CMT PLUG DEEPER THAN PREDICTED.
1430 | 10/15/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 12.25 | 75.5 | 903398 |  | BHS | 5835 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1431 | 10/15/2022 | 13 Oct 2030 - 1645 | QTIF-172 | SSA-202 | NCS | CPNF | 11.25 | 43.75 | 903485 |  | CMT | 3550 | NA | GREEN CONTAMINATED CEMENT ON SHAKER WHILE WASHING DOWN WITH 12-1/4" C/O ASSY & TOP OF CMT PLUG DEEPER THAN PREDICTED.
1433 | 10/15/2022 | 15 Oct 1145 - 1430 | MSBA-1 | SSA-5820 | RIG | FOT | 2.75 | 2.75 | 903558 |  | RR | 10291 | TDS | OBSERVED LEAK FROM TDS'S UPPER IBOP & FOUND CRACK ON IBOP BODY. - REPLACED & TEST SAME.
1435 | 10/15/2022 | 15 Oct 2300 - 0400 | HWYH-1217 | SSA-5859 | WWL | FOT | 5 | 5 | 903618 |  | TF | 14300 | CORRL | TROUBLESHOOTING ON LOGGING TOOLS COMMUNICATION FAILURE. >> LOST COMMUNICATION WITH TOOLS AT 14300' WHILE LOGGING UP THE CORRELATION PASS.
1437 | 10/15/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 273.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNTIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON, EVALUATE POWER SYSTEM AND TDS MOTOR RPM'S. WHILE ATTEMPTING TO DRILL AHEAD WITH 90 RPM'S, TDS GETTING ERRATIC RPM'S. MUD PUMPS LOSING AND GAINING POWER WHILE CIRCULATING OR DRILLING. TDS & PUMPS ARE POWERING ON AND OFF WITH NO CHANGE IN COMMAND WHILE UNDER LOAD. FOUND GENERATORS ARE NOT SHARING THE ELECTRICAL LOAD PROPERLY. M/U & RIH 7'' SCRAPPER ASSY TO 185', IN ORDER TO CREATE MORE PRESSURE FOR MUD PUMPS TO LOAD TEST GENERATORS POWER SHARING
1439 | 10/15/2022 | 14 Oct 2300 - 2230 | DYBN-21 | SSA-5972 | WDV | FOT | 12.5 | 18.5 | 903583 |  | TF | 3885 | DV | DV PACEKER FAILED TO SET AND RESULTING LOST MUD RETURNS.
1441 | 10/16/2022 | 16 Oct 1515 - 1615 | HRDH-1864 | ADC-14 | RIG | FOT | 1 | 1 | 903551 |  | RR | 12800 | MPMP | FAILURE IN MUD PUMP# 1 & 2, CHECK MUD PUMPS ELECTRICAL PROBLEM. >> WORK TO FIX ISSUE
1443 | 10/16/2022 | 15 Oct 0630 - 0500 | MZLJ-60 | ADC-47 | RIG | HERR | 24 | 46.5 | 903545 |  | FISH | 5040 | STRG | WHILE DRILLING LOST ROP AND UNABLE TO DRILL PULLED OUT AND BIT WAS DAMNAGED DUE TO JUNK IN THE HOLE
1445 | 10/16/2022 | 16 Oct 0800 - 0930 | SFNY-1172 | ADC-50 | SDM | FOT | 1.5 | 1.5 | 903600 |  | BHA | 420 | GMWD | TAKE EXCESSIVE TIME TO TAKE SURVEY BY SLB
1447 | 10/16/2022 | 15 Oct 0500 - 0500 | HRDH-1530 | ADC-53L | BC | STCT | 24 | 47.5 | 903561 |  | STUK | 4818 | PDHMS | GOT STUCK WHILE RUNNING BACKER UPER COMPLETION
1468 | 10/16/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 551.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1470 | 10/16/2022 | 16 Oct 1530 - 0100 | HWYH-1287 | ADC-59L | TK3 | SHHF | 9.5 | 9.5 | 903602 |  | BHS | 3050 | NA | R/U CEMENT HEAD AND WHILE PUMPING FRESH WATER OBSERVED PACK OFF TENDENCY (PRESSURE SHOOT UP TO 800 AND 200 KLBS OVER PULL).
1472 | 10/16/2022 | 14 Oct 1830 - 1915 | MRJN-560 | ADC-60 | BAW | XTRI | 14.25 | 48.75 | 903596 |  | JF | 7255 | WLT | IFX (IN-SITU FLUID EXPLORER) IS NOT READING CORRECT OD VALUES (OPTICAL DENSITY).
1487 | 10/16/2022 | 16 Oct 2130 - 0500 | ANDR-589 | ADC-62L | BC | FOT | 7.5 | 7.5 | 903638 |  | TF | 12348 | TBACC | UNABLE TO CIRCULATE DUE TO UNINTENTIONALLY CLOSING BAKER 4-1/2" WBIV (WILL BE CONFIRMED AFTER POOH & CHECKING WBIV).
1493 | 10/16/2022 | 16 Oct 2330 - 0015 | MRJN-2018 | ADM-261 | ARM | FOT | .75 | .75 | 903603 |  | TF | 11850 | CSG | WHEN POH W/ OLD UPPER COMPLETION, CENTRALIZER LEFT IN HOLE. STOP COLLARS WERE STILL IN PLACE ON CASING JT.
1495 | 10/16/2022 | 16 Oct 1000 - 1530 | MRJN-900 | ADM-337 | ARM | WTHR | 5.5 | 5.5 | 903625 |  | WON | 7080 | NA | UNABLE TO CONT. FLOW BACK OPERATION DUE TO WIND SPEED BELOW 5 KNOTS
1497 | 10/16/2022 | 14 Oct 1830 - 0500 | MRJN-121 | ARO-2001 | HCM | CEDE | 24 | 58.5 | 903593 |  | JF | 11700 | NA | CEMENT PLUG FAILURE, CEMENT STILL SOFT 44 HRS AFTER SET THE PLUG.
1499 | 10/16/2022 | 16 Oct 0630 - 0930 | MRJN-3003 | ARO-3001 | SCD | FOT | 3 | 3 | 903567 |  | SURV | 0 | GYRO | SURFACE TEST GRYO MWD, NO SIGNAL
1501 | 10/16/2022 | 16 Oct 0000 - 0500 | MRJN-537 | ARO-4001 | RIG | UNKN | 5 | 5 | 903622 |  | HSEI | 14142 | NA | WHILE POOH WITH 7" SCRAPER ASSY ON THE SECOND LAST 4" DP STAND, THE AD CATCH 4" DP STAND WITH PRS, BUT DRILLER DID NOT OPEN BX ELEVATOR, AD ROTATE PRS TO RACK BACK STAND AND DRILLER START LOWERING TDS WHICH CAUSING BEND TO THE STAND, SHUT DOWN OPERATION, SECURE WELL AND BARRICADE THE AREA, PREPARE PLAN TO LD THE BENDING STAND.
1503 | 10/16/2022 | 14 Oct 0500 - 0600 | HRDH-1541 | DQ-49L | BWH | FOT | 1 | 47.75 | 903557 |  | TF | 9398 | WPSTK | AFTER FINISH DRLG 18' RATE HOLE T/ 9,403' OBSERVED 140 BPH / 300 GPM DYNAMIC LOSSES W/ 70% RETURN.
1505 | 10/16/2022 | 14 Oct 0100 - 0830 | ZULF-2066 | ED-85A | SDM | FOT | 3.5 | 30.5 | 903586 |  | BHA | 12181 | LWD | WHILE DRILLING 8-1/2" X 9-1/2" HOLE, SLB LWD TOOL STOP LOGGING, SLB ATTEMPT TO TROUBLESHOOTING NO SUCCESS. DECISION TO POH AND REPLACE SLB LWD.
1507 | 10/16/2022 | 16 Oct 2145 - 0015 | ZULF-2041 | EXL-IVA | RIG | GRF | 2.5 | 2.5 | 903636 |  | UPRA | 11268 | TDS | TOP DRIVE SWIVEL PACKING FAILURE.
1509 | 10/16/2022 | 15 Oct 2230 - 0500 | QTIF-99 | HI-5 | NRT | FOT | 24 | 30.5 | 903620 |  | BHA | 9387 | UNDR | OBSERVED SUDDEN DROP IN PUMP PRESSURE, POH TO SURFACE & FOUND NOV BULL NOSE BACKED OFF FROM ANDER REAMER TOOL AND LOST IN HOLE.
1511 | 10/16/2022 | 16 Oct 0400 - 0430 | SDGM-1223 | NBR-196S | RIG | FPMP | .5 | .5 | 903626 |  | RR | 12414 | MPMP | MUD PUMPS LOSS PRESSURE & LOSS MWD SIGNAL.
1513 | 10/16/2022 | 16 Oct 1800 - 2030 | JAHM-5 | NBR-210S | WI3 | WOTO | 2.5 | 2.5 | 903637 |  | WO | 0 | NA | WAIT FOR WINDO MILL TOOL FROM WIS CO.
1515 | 10/16/2022 | 16 Oct 1800 - 0500 | UTMN-3185 | SCTD-1 | SDM | FOT | 11 | 11 | 903624 |  | BHA | 13766 | MWD | FAULTY READINGS OF APRS, DELTA PRESSUR AND WOB.
1517 | 10/16/2022 | 13 Oct 0630 - 1930 | ABHD-108 | SINO-16 | BAL | FOT | 14.5 | 85 | 903536 |  | TF | 5843 | PKR | BAKER 9-5/8" ELECPAC PACKER FAILED TO HOLD TCA PRESSURE. WHILE POOH FOUND ONE OF THE ESP BANDING FALL OFF THE ESP CABLE AND STUCK AROUND THE RUBBER ELEMENT OF THE PACKER, WHICH NOT ALLOWED THE PACKER TO BE FULLY SEAL.
1519 | 10/16/2022 | 14 Oct 0300 - 1400 | MNIF-204 | SINO-25 | SPS | FOT | 9 | 35 | 903595 |  | BHA | 10563 | RSS | SPS RSS LOST ELECTRIC COMMUNICATION WHILE DRILLING AT 10563'.
1521 | 10/16/2022 | 14 Oct 0630 - 0200 | KHRS-463 | SINO-27N | INW | FOT | 21 | 67.5 | 903576 |  | TF | 6979 | BP | INTERWELL ME-PLUG JUMPED UP & DROPPED WHILE JARRING TO RETRIEVE IT.
1522 | 10/16/2022 | 16 Oct 1500 - 2030 | SFNY-1730 | SL-7 | RIG | FOT | 5.5 | 5.5 | 903550 |  | RR | 4966 | DRRK | OBSERVED A SMALL LOOSE NUT DROP DOWN FROM PRS
1524 | 10/16/2022 | 16 Oct 0715 - 0845 | SFNY-1730 | SL-7 | RIG | FOT | 1.5 | 1.5 | 903549 |  | RR | 7792 | EDR | HAD ELECTRONIC COMMUNICATION FAULT ON RIG AMPHION SYSTEM
1525 | 10/16/2022 | 16 Oct 1500 - 2030 | SFNY-1730 | SL-7 | RIG | FOT | 5.5 | 5.5 | 903550 |  | RR | 4966 | DRRK | OBSERVED A SMALL LOOSE NUT DROP DOWN FROM PRS
1527 | 10/16/2022 | 16 Oct 0430 - 0500 | GZLN-1 | SND-2003 | HWP | FOT | .5 | .5 | 903552 |  | TF | 13888 | WLT | SIDE WALL CORE SAMPLE STUCK INSIDE SWC CORE HEAD.
1529 | 10/16/2022 | 11 Oct 0130 - 0500 | UTMN-3095 | SND-2006 | ARM | UXGE | 24 | 109.25 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
1531 | 10/16/2022 | 16 Oct 1530 - 2100 | ABQQ-531 | SP-101 | HCO | FOT | 5.5 | 5.5 | 903548 |  | TF | 987 | PDHMS | HALB PDHMS GAUGE LOST SIGNAL.
1533 | 10/16/2022 | 16 Oct 0900 - 0500 | FDHL-148 | SP-124 | BHI | FOT | 6 | 6 | 903544 | 903540 | BHA | 10623 | MWD | P/U BHI MWD/LWD TOOLS & RELOG MISSED HOLE SECTION DUE TO MWD FAILURE
1535 | 10/16/2022 | 12 Oct 0300 - 0500 | HWYH-74 | SP-167 | WWL | FOT | 24 | 97.5 | 903516 |  | TF | 5857 | WLT | WFD CALIPER LOGGING COULDN'T PASS WINDOW, WORK ON SAME WITHIN LIMITS THEN POOH FOUND W'STOCK ENGAGED TO MULE SHOE
1537 | 10/16/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 23 | 98.5 | 903398 |  | BHS | 5835 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1539 | 10/16/2022 | 16 Oct 0100 - 0500 | QTIF-423 | SSA-29 | HWP | FOT | 4 | 4 | 903553 |  | TF | 0 | WLU | HALLIBURTON E-LINE TENSION PANEL IS NOT ABLE TO READ THE CORRECT TENSION ON E-LINE CABLE. REPLACED WITH DIFFERENT PANEL. TROUBLE SHOOTING AND TRY TO STABILIZE TENSION READING ON CABLE.
1541 | 10/16/2022 | 04 Oct 1945 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 297.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNTIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON, EVALUATE POWER SYSTEM AND TDS MOTOR RPM'S. WHILE ATTEMPTING TO DRILL AHEAD WITH 90 RPM'S, TDS GETTING ERRATIC RPM'S. MUD PUMPS LOSING AND GAINING POWER WHILE CIRCULATING OR DRILLING. TDS & PUMPS ARE POWERING ON AND OFF WITH NO CHANGE IN COMMAND WHILE UNDER LOAD. FOUND GENERATORS ARE NOT SHARING THE ELECTRICAL LOAD PROPERLY. M/U & RIH 7'' SCRAPPER ASSY TO 185', IN ORDER TO CREATE MORE PRESSURE FOR MUD PUMPS TO LOAD TEST GENERATORS POWER SHARING
1543 | 10/16/2022 | 16 Oct 0900 - 0500 | HRDH-1979 | SSA-5974 | ARM | STBH | 20 | 20 | 903623 |  | STUK | 9179 | BHA | DRILLED OFF AT THE STAND END AND P/U 4 FT STRING TAKE WEIGHT AND TORQUED UP (STUCK). HAD CIRCULATION WITH NO ROTATION, SPEND TIME WORK STRING DOWN, WITH NO PROGRESS (JAR IS NOT WORKING). WORK PIPE SLACKING OFF WITH TRAPPED TORQUE WITH NO PROGRESS. TRIED TO WORK STRING UP WITH MAX OVERPULL (JAR IS WORKING OK UP). MOVE 3' PROGRESSED AND NO MORE. CONTINUE WORK STRING WITH NO PROGRESS.
1545 | 10/17/2022 | 17 Oct 0815 - 1045 | HRDH-1864 | ADC-14 | RIG | FOT | 2.5 | 2.5 | 903554 |  | RR | 15799 | MPMP | FAILURE IN MUD PUMP# 2, WORK TO CHANGE JUMPER HOSE LEAKING.
1547 | 10/17/2022 | 15 Oct 0630 - 0630 | MZLJ-60 | ADC-47 | ARM | FNFS | 1.5 | 48 | 903545 |  | LROP | 5040 | BIT | WHILE DRILLING, LOST ROP AND UNABLE TO DRILL, PULLED OUT AND BIT WAS DAMAGED
1548 | 10/17/2022 | 17 Oct 0830 - 1600 | HRDH-1530 | ADC-53L | BC | FOT | 7.5 | 7.5 | 903640 |  | TF | 3074 | PDHMS | PDHMS NOT READING
1550 | 10/17/2022 | 15 Oct 0500 - 2300 | HRDH-1530 | ADC-53L | BC | STCT | 10.5 | 58 | 903561 |  | STUK | 4818 | PDHMS | GOT STUCK WHILE RUNNING BACKER UPER COMPLETION
1551 | 10/17/2022 | 17 Oct 0830 - 1600 | HRDH-1530 | ADC-53L | BC | FOT | 7.5 | 7.5 | 903640 |  | TF | 3074 | PDHMS | PDHMS NOT READING
1576 | 10/17/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 575.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1592 | 10/17/2022 | 16 Oct 2130 - 1530 | ANDR-589 | ADC-62L | BC | FOT | 10.5 | 18 | 903638 |  | TF | 12348 | TBACC | UNABLE TO CIRCULATE, WBIV BALL SEAT GOT PLUGGED WITH A PIECE OF WOOD FROM SET-BACK AREA LEADING TO UNINTENTIONALLY CLOSING BAKER 4-1/2" WBIV (LOST TIME RESPONSIBILITY WILL BE FINALIZED AND SHARED AT THE END OF LOST TIME). ** DP'S & HWDP'S WERE DRIFTED WHILE POOH WITH REAMING BHA.
1597 | 10/17/2022 | 16 Oct 1130 - 0500 | MRJN-2018 | ADM-261 | INW | FOT | 23 | 27.25 | 903603 |  | TF | 11850 | PLUGT | PUMP THROUGH PLUG NOT RECOVERED WHEN POH W/ UPPER COMPLETION.
1599 | 10/17/2022 | 17 Oct 0845 - 1430 | MRJN-900 | ADM-337 | ARM | WTHR | 5.75 | 5.75 | 903661 |  | WON | 7080 | NA | UNABLE TO CONT. FLOW BACK OPERATION DUE TO WIND SPEED BELOW 5 KNOTS
1601 | 10/17/2022 | 14 Oct 1830 - 0500 | MRJN-121 | ARO-2001 | HCM | CEDE | 24 | 82.5 | 903593 |  | JF | 11700 | NA | CEMENT PLUG FAILURE, CEMENT STILL SOFT 44 HRS AFTER SET THE PLUG.
1603 | 10/17/2022 | 16 Oct 0000 - 1600 | MRJN-537 | ARO-4001 | RIG | UNKN | 11 | 16 | 903622 |  | HSEI | 14142 | NA | WHILE POOH WITH 7" SCRAPER ASSY ON THE SECOND LAST 4" DP STAND, THE AD CATCH 4" DP STAND WITH PRS, BUT DRILLER DID NOT OPEN BX ELEVATOR, AD ROTATE PRS TO RACK BACK STAND AND DRILLER START LOWERING TDS WHICH CAUSING BEND TO THE STAND, SHUT DOWN OPERATION, SECURE WELL AND BARRICADE THE AREA, LD BENDING STAND, INSPECT RIG FLOOR EQUIPMENT.
1605 | 10/17/2022 | 16 Oct 1530 - 0800 | BRRI-436 | HI-2 | ARM | IBSL | 1.75 | 14 | 903606 |  | LROP | 7905 | BIT | LOW ROP IN JUBAIL FORMATION.
1607 | 10/17/2022 | 15 Oct 2230 - 1100 | QTIF-99 | HI-5 | NRT | FOT | 6 | 36.5 | 903620 |  | BHA | 9387 | UNDR | OBSERVED SUDDEN DROP IN PUMP PRESSURE, POH TO SURFACE & FOUND NOV BULL NOSE BACKED OFF FROM ANDER REAMER TOOL AND LOST IN HOLE.
1609 | 10/17/2022 | 11 Oct 1600 - 0500 | BRRI-17 | HI-9 | SDM | AINC | 24 | 92 | 903408 |  | DD | 6764 | BHA | SCHLUMBERGER RSS UNABLE TO BUILD THE DESIRED INCLINATION.
1611 | 10/17/2022 | 17 Oct 1100 - 1400 | SHYB-134 | NA-207S | SDM | FOT | 3 | 3 | 903658 |  | BHA | 0 | MWD | PICK UP 4 3/4" NMDC. MAKE SEVERAL ATTEMPTS TO INSTALL MWD PROBE INSIDE COLLAR BUT UNABLE TO SEAT IT. TOOL HEAD WAS WRONG SIZE WHICH DOESNT FIT IN COLLAR SLEEVE
1613 | 10/17/2022 | 17 Oct 1900 - 2115 | ANDR-1018 | NBR-654S | RIG | LHFL | 2.25 | 2.25 | 903660 |  | RR | 9627 | HSYS | LEAK ON TDS LOWER HYDRAULIC VALVE PISTON.
1615 | 10/17/2022 | 17 Oct 2100 - 0500 | MRJN-673 | PN-9 | BHI | FOT | 7.5 | 7.5 | 903677 |  | BHA | 14913 | MMOT | WHILE DRILLING OBSERVED MUD MOTOR STALL AND 250 PSI INCREASE IN PRESSSURE. FOUND MUD MOTOR RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD. STOPPED DRILLING.
1617 | 10/17/2022 | 17 Oct 0330 - 0500 | HSBH-25 | RBP-50A | RIG | FOT | 1.5 | 1.5 | 903662 |  | BOP | 0 | BOP | FILL BOP W/ WATER - OBSERVE HYDROSTATIC WATER LEAK AT BSR BONNET SEAL. TROUBLESHOOT BSR BONNET SEAL LEAK AT BOP.
1619 | 10/17/2022 | 16 Oct 1400 - 0500 | KHRS-75 | SINO-1L | TK1 | HELD | 24 | 39 | 903676 |  | JF | 3989 | LINR | FAILURE TO PASS W/ CBL-VDL TOOL FROM TOL @ 3898',TRIED WITH DIFF. SPEEDS NO SUCCESS, POH & RD LOGGING TOOL ,MU & RIH W/3 7/8'' C/O STRG WITH MAGNETS.
1641 | 10/17/2022 | 17 Oct 1730 - 1830 | SFNY-1730 | SL-7 | ARN | FOT | 1 | 1 | 903659 |  | TF | 7915 | VSAT | HAD V-SAT ISSUE UNABLE TO TRANSMIT REAL TIME DATA TO GOC,
1643 | 10/17/2022 | 17 Oct 1015 - 0500 | HRML-815 | SND-1501 | KSC | FOT | 18.75 | 18.75 | 903680 |  | TF | 0 | ESP | AL-KHORYEF ESP EQUIPMENT FAILED AFTER M/U INCLUDING BACK UP
1645 | 10/17/2022 | 16 Oct 0430 - 0730 | GZLN-1 | SND-2003 | HWP | FOT | 2.5 | 3 | 903552 |  | TF | 13888 | WLT | SIDE WALL CORE SAMPLE STUCK INSIDE SWC CORE HEAD.
1647 | 10/17/2022 | 17 Oct 1200 - 0500 | MHKK-2 | SND-2005 | RIG | FOT | 17 | 17 | 903607 |  | BOP | 12736 | BOP | 13-5/8" 10M ANNULAR LEAKING DURING BOP TEST. TROUBLE SHOOT SAME WITHOUT SUCCESS.
1649 | 10/17/2022 | 11 Oct 0130 - 2000 | UTMN-3095 | SND-2006 | ARM | UXGE | 15 | 124.25 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
1651 | 10/17/2022 | 16 Oct 0900 - 0600 | FDHL-148 | SP-124 | BHI | FOT | 1 | 7 | 903544 | 903540 | BHA | 10623 | MWD | P/U BHI MWD/LWD TOOLS & RELOG MISSED HOLE SECTION DUE TO MWD FAILURE
1653 | 10/17/2022 | 17 Oct 1700 - 1745 | FDHL-146 | SP-165 | RIG | FOT | .75 | .75 | 903657 |  | RR | 0 | SLIPS | TROUBLESHOOTING AND REPAIR ON DRILL PIPE POWER TONG.
1655 | 10/17/2022 | 12 Oct 0300 - 0500 | HWYH-74 | SP-167 | WWL | FOT | 24 | 121.5 | 903516 |  | TF | 5857 | WLT | WFD CALIPER LOGGING COULDN'T PASS WINDOW, WORK ON SAME WITHIN LIMITS THEN POOH FOUND W'STOCK ENGAGED TO MULE SHOE
1657 | 10/17/2022 | 17 Oct 1715 - 1845 | THRY-822604 | SP-259 | RIG | STDP | 1.5 | 1.5 | 903641 |  | STUK | 11561 | DP | GOT STUCK WHILE POOH THROUGH LATERAL HOLE SECTION
1659 | 10/17/2022 | 17 Oct 1515 - 0230 | QTIF-526 | SSA-101 | ARM | WC20 | 11.25 | 11.25 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
1661 | 10/17/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 15 | 113.5 | 903398 |  | BHS | 0 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1663 | 10/17/2022 | 16 Oct 0100 - 0730 | QTIF-423 | SSA-29 | RIG | FOT | 2.5 | 6.5 | 903553 |  | TF | 0 | TESTT | HALLIBURTON E-LINE TENSION PANEL IS NOT ABLE TO READ THE CORRECT TENSION ON E-LINE CABLE. REPLACED WITH DIFFERENT PANEL. TROUBLE SHOOTING AND TRY TO STABILIZE TENSION READING ON CABLE. CHECK & FIND OUT THE NOISE COMING FROM RIG FLOOR (7 VOLTAGE DC) & DISTURPES TENSION PANEL READING AT WL UNIT.
1665 | 10/17/2022 | 04 Oct 1945 - 1800 | RGHB-704 | SSA-5915 | RIG | GRF | 13 | 310.25 | 903173 |  | UPRA | 1121 | TDS | WHILE MAKING CONNECTION RIG WAS UNABLE TO BREAK OUT SAVER SUB FROM HWDP, WORK ON SAVER SUB UNTIL BROKE OUT. CHC & POOH TO 18 5/8'' SHOE. RIG WAITING ON TOP DRIVE TECHNICIAN TO TROUBLESHOOT ELECTRICAL ISSUES. SAIPEM ELECTRICIAN MANAGER & TECHNICIAN ARRIVED ON LOCATION AT 10/4/22 15:00. TROUBLESHOOT TDS SOFTWARE SYSTEM WITH OEM LETOURNEAU/CAMERON, EVALUATE POWER SYSTEM AND TDS MOTOR RPM'S. WHILE ATTEMPTING TO DRILL AHEAD WITH 90 RPM'S, TDS GETTING ERRATIC RPM'S. MUD PUMPS LOSING AND GAINING POWER WHILE CIRCULATING OR DRILLING. TDS & PUMPS ARE POWERING ON AND OFF WITH NO CHANGE IN COMMAND WHILE UNDER LOAD. FOUND GENERATORS ARE NOT SHARING THE ELECTRICAL LOAD PROPERLY. M/U & RIH 7'' SCRAPPER ASSY TO 185', IN ORDER TO CREATE MORE PRESSURE FOR MUD PUMPS TO LOAD TEST GENERATORS POWER SHARING
1667 | 10/17/2022 | 16 Oct 0900 - 0500 | HRDH-1979 | SSA-5974 | ARM | STBH | 24 | 44 | 903623 |  | STUK | 0 | BHA | DRILLED OFF AT THE STAND END AND P/U 4 FT STRING TAKE WEIGHT AND TORQUED UP (STUCK). HAD CIRCULATION WITH NO ROTATION, SPEND TIME WORK STRING DOWN, WITH NO PROGRESS (JAR IS NOT WORKING). WORK PIPE SLACKING OFF WITH TRAPPED TORQUE WITH NO PROGRESS. TRIED TO WORK STRING UP WITH MAX OVERPULL (JAR IS WORKING OK UP). MOVE 3' PROGRESSED AND NO MORE. CONTINUE WORK STRING WITH NO PROGRESS.
1669 | 10/18/2022 | 18 Oct 1800 - 2230 | ABJF-3009 | ADC-16 | RIG | FOT | 4.5 | 4.5 | 903701 |  | RR | 1744 | TDS | TDS MAIN SHAFT CONNECTION WORKED LOOSE. UNABLE TO BREAK SAVER SUB FROM DP.
1694 | 10/18/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 599.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1705 | 10/18/2022 | 16 Oct 2130 - 0500 | ANDR-589 | ADC-62L | BC | FOT | 24 | 42 | 903638 |  | TF | 12348 | TBACC | UNABLE TO CIRCULATE, WBIV BALL SEAT GOT PLUGGED WITH A PIECE OF WOOD FROM SET-BACK AREA LEADING TO UNINTENTIONALLY CLOSING BAKER 4-1/2" WBIV (LOST TIME RESPONSIBILITY WILL BE FINALIZED AND SHARED AT THE END OF LOST TIME). ** DP'S & HWDP'S WERE DRIFTED WHILE POOH WITH REAMING BHA.
1710 | 10/18/2022 | 18 Oct 2000 - 0500 | HWYH-1300 | ADC-65L | SDM | FOT | 9 | 9 | 903719 |  | BHA | 8197 | MWD | GAMMA RAY READINGS HAS HIGHER VALUES AND UNBALE TO CORRELATE WITH OFFSET DATA
1712 | 10/18/2022 | 18 Oct 0500 - 0500 | UTMN-3134 | ADES-144 | RIG | OTH | 24 | 24 | 903663 |  | UPRA | 0 | NA | WHILE PINNING UP THE MAST ON THE RIG UP, HIGH HORSE STAND DAMAGED WHILE RESTING MAST CROWN SECTION ON IT.
1714 | 10/18/2022 | 16 Oct 1130 - 0500 | MRJN-2018 | ADM-261 | INW | FOT | 23 | 50.25 | 903603 |  | TF | 11850 | PLUGT | PUMP THROUGH PLUG NOT RECOVERED WHEN POH W/ UPPER COMPLETION.
1716 | 10/18/2022 | 14 Oct 1830 - 0500 | MRJN-121 | ARO-2001 | HCM | CEDE | 24 | 106.5 | 903593 |  | JF | 11700 | NA | CEMENT PLUG FAILURE, CEMENT STILL SOFT 44 HRS AFTER SET THE PLUG.
1717 | 10/18/2022 | 18 Oct 1215 - 1515 | MRJN-814 | ARO-3002 | RIG | FOT | 3 | 3 | 903716 |  | RR | 0 | CSYS | STANDPIPE VALVES; TOP STAND PIPE VALVE #1 AND SPLITTER VALVE WOULD NOT TEST.
1719 | 10/18/2022 | 18 Oct 0300 - 0430 | MRJN-814 | ARO-3002 | RIG | FOT | 1.5 | 1.5 | 903715 |  | RR | 0 | TDS | TOP DRIVE BACKOUT DIES SLIPPING
1720 | 10/18/2022 | 18 Oct 1215 - 1515 | MRJN-814 | ARO-3002 | RIG | FOT | 3 | 3 | 903716 |  | RR | 0 | CSYS | STANDPIPE VALVES; TOP STAND PIPE VALVE #1 AND SPLITTER VALVE WOULD NOT TEST.
1722 | 10/18/2022 | 18 Oct 1130 - 1330 | SFNY-1157 | ARO-3003 | RIG | FOT | 2 | 2 | 903702 |  | RR | 0 | WATER | RIG 4" WATER SUPPLY VALVE TO CEMENT UNIT FAILED.
1724 | 10/18/2022 | 18 Oct 1415 - 0130 | MRJN-537 | ARO-4001 | RIG | FOT | 11.25 | 11.25 | 903705 |  | RR | 14142 | PSYS | DURING WEEKLY EMERGENCY GENERATOR TEST, THE SR. ELECTRICIAN INADVERTENTLY ACTIVATED THE INCORRECT FUNCTION (SWITCH), THIS RESULTED IN ALL ENGINES TRIGGERING THE EMERGENCY STOP CONDITION, TROUBLESHOOTING SAME TO GET RIG FLOOR EQUIPMENT BACK TO WORK, WORKING OK.
1726 | 10/18/2022 | 18 Oct 0830 - 0500 | HRDH-1383 | BCTD-3 | RIG | FOT | 20.5 | 20.5 | 903683 |  | RR | 14840 | TRVL | POOH TO INSPECT INJECTOR- INJECTOR CHAINS ARE NOT ALIGNED.
1728 | 10/18/2022 | 18 Oct 1430 - 0500 | MRJN-741 | CG-1 | HWP | FOT | 14.5 | 14.5 | 903714 |  | TF | 9370 | CORRL | HALLIBURTON LOGGING TOOLS FAILURE, LEAK ON HYDRAULIC SYSTEM
1729 | 10/18/2022 | 17 Oct 2000 - 0500 | SDGM-1111 | DPS-46 | CRT | FOT | 17.75 | 26.75 | 903696 |  | BHA | 12626 | WBCL | CORETRAX WBC TOOLS HANGING UP INSIDE CASING, STIFF WBC BHA.
1731 | 10/18/2022 | 18 Oct 0800 - 1300 | SDGM-1111 | DPS-46 | RIG | FOT | 5 | 5 | 903644 |  | RR | 0 | DWKS | REPLACE BROKEN HIGH DRUM CLUTCH CHAIN.
1732 | 10/18/2022 | 17 Oct 2000 - 0500 | SDGM-1111 | DPS-46 | CRT | FOT | 17.75 | 26.75 | 903696 |  | BHA | 12626 | WBCL | CORETRAX WBC TOOLS HANGING UP INSIDE CASING, STIFF WBC BHA.
1734 | 10/18/2022 | 11 Oct 1600 - 1230 | BRRI-17 | HI-9 | SDM | AINC | 7.5 | 99.5 | 903408 |  | DD | 6764 | BHA | SCHLUMBERGER RSS UNABLE TO BUILD THE DESIRED INCLINATION.
1736 | 10/18/2022 | 18 Oct 1130 - 1215 | SDGM-1221 | NBR-115S | WCR | FOT | .75 | .75 | 903643 |  | TF | 741 | CTRQ | WFD TUBING TONGS NOT GRIPPING PIPE CORRECTLY.
1738 | 10/18/2022 | 18 Oct 1715 - 1815 | TINT-91 | NBR-783S | RIG | FOT | 1 | 1 | 903707 |  | RR | 9258 | MPMP | MUD PUMPS FAILED
1740 | 10/18/2022 | 18 Oct 0100 - 0200 | HRDH-1976 | PA-218S | RIG | FOT | 1 | 1 | 903706 |  | BOP | 9380 | RAMS | ATTEMPTED TO P/T 9-5/8" CSG RAMS T/ 7000 PSI, HAD VISUAL LEAK FROM BONNET SEAL.
1741 | 10/18/2022 | 18 Oct 2200 - 0200 | MRJN-673 | PN-9 | RIG | OTH | 3.5 | 3.5 | 903712 |  | UPRA | 14913 | NA | IRON ROUGHNECK OUT OF SERVICE FOR REPAIR TO DRAG CHAIN AND PIPE SPINNER.
1743 | 10/18/2022 | 17 Oct 2100 - 0500 | MRJN-673 | PN-9 | BHI | FOT | 19.25 | 26.75 | 903677 |  | BHA | 14913 | MMOT | WHILE DRILLING OBSERVED MOTORIZED RSS STALL AND 250 PSI INCREASE IN PRESSSURE. FOUND MOTORIZED RSS RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD. STOPPED DRILLING.
1744 | 10/18/2022 | 18 Oct 2200 - 0200 | MRJN-673 | PN-9 | RIG | OTH | 3.5 | 3.5 | 903712 |  | UPRA | 14913 | NA | IRON ROUGHNECK OUT OF SERVICE FOR REPAIR TO DRAG CHAIN AND PIPE SPINNER.
1746 | 10/18/2022 | 17 Oct 0330 - 0500 | HSBH-25 | RBP-50A | RIG | GRF | 24 | 25.5 | 903662 |  | UPRA | 9973 | RWCS | FILL BOP W/ WATER - OBSERVE HYDROSTATIC WATER LEAK AT BSR BONNET SEAL. TROUBLESHOOT BSR BONNET SEAL LEAK AT BOP. (CAMERON-TL BOP, BSR CAVITY WITH TANDEM BOOSTERS).
1748 | 10/18/2022 | 18 Oct 0030 - 0415 | BRRI-1144 | SINO-22 | SWL | FOT | 3.75 | 3.75 | 903710 |  | TF | 8789 | WLT | DIFFICULTIES TO UNLATCH WL CABLE FROM PWCH. UNLATCHED CABLE WITH OVERPULL.
1749 | 10/18/2022 | 18 Oct 1015 - 0500 | UTMN-1245 | SINO-26 | HUD | FOT | 18.75 | 18.75 | 903718 |  | TF | 9624 | MPD | HALL MPD FLOATS FAILED.
1751 | 10/18/2022 | 17 Oct 0100 - 1015 | UTMN-1245 | SINO-26 | HUD | FOT | 5.25 | 9.25 | 903717 |  | TF | 9624 | MPD | HALL MPD BEARING LEAK.
1752 | 10/18/2022 | 18 Oct 1015 - 0500 | UTMN-1245 | SINO-26 | HUD | FOT | 18.75 | 18.75 | 903718 |  | TF | 9624 | MPD | HALL MPD FLOATS FAILED.
1754 | 10/18/2022 | 18 Oct 0300 - 0500 | SDGM-269 | SINO-36L | ITS | MATL | 2 | 2 | 903711 |  | WO | 2970 | NA | HAD LEAKAGE FROM ITS OPERATIONG POWER UNIT, ATTEMPT TO FIX, NO SUCCESS.
1756 | 10/18/2022 | 18 Oct 0045 - 0500 | ABQQ-454 | SINO21 | WI1 | FOT | 4.25 | 4.25 | 903708 |  | BHA | 7228 | MILL | WIS MILLING ASSY STUCK CROSS WINDOW.
1758 | 10/18/2022 | 17 Oct 1015 - 1200 | HRML-815 | SND-1501 | KSC | FOT | 7 | 25.75 | 903680 |  | TF | 0 | ESP | ALKHORAYEF ESP TOOLS FAILURE
1760 | 10/18/2022 | 18 Oct 1700 - 2300 | HRDH-2415 | SND-2002 | RIG | FOT | 6 | 6 | 903704 |  | RR | 630 | TDS | TROUBLESHOOTING ON TDS TORQ.
1762 | 10/18/2022 | 17 Oct 1200 - 1130 | MHKK-2 | SND-2005 | RIG | FOT | 6.5 | 23.5 | 903607 |  | BOP | 12736 | BOP | 13-5/8" 10M ANNULAR LEAKING DURING BOP TEST. TROUBLE SHOOT SAME WITHOUT SUCCESS.
1764 | 10/18/2022 | 11 Oct 0130 - 0500 | UTMN-3095 | SND-2006 | ARM | UXGE | 16.5 | 142.5 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
1766 | 10/18/2022 | 18 Oct 0600 - 0800 | MNIF-867 | SND-2010 | ARM | WTHR | 2 | 2 | 903682 |  | WON | 1032 | NA | SUSPEND OPERATION DUE TO FOGGY WEATHER AND NO VISIBILITY
1768 | 10/18/2022 | 16 Oct 0900 - 1330 | FDHL-148 | SP-124 | BHI | FOT | 2.5 | 9.5 | 903544 | 903540 | BHA | 10623 | MWD | P/U BHI MWD/LWD TOOLS & RELOG MISSED HOLE SECTION DUE TO MWD FAILURE
1770 | 10/18/2022 | 12 Oct 0300 - 0500 | HWYH-74 | SP-167 | WWL | FOT | 24 | 145.5 | 903516 |  | TF | 5857 | WLT | WFD CALIPER LOGGING COULDN'T PASS WINDOW, WORK ON SAME WITHIN LIMITS THEN POOH FOUND W'STOCK ENGAGED TO MULE SHOE
1771 | 10/18/2022 | 18 Oct 0300 - 0400 | THRY-822604 | SP-259 | ITS | FOT | 1 | 1 | 903709 |  | TF | 6780 | CRT | REPAIRE ON FMS.
1773 | 10/18/2022 | 18 Oct 1330 - 1500 | THRY-822604 | SP-259 | ITS | FOT | 1.5 | 1.5 | 903703 |  | TF | 0 | TTRQ | JAM UNIT ELECTRICAL CABLES FAILLURE.
1774 | 10/18/2022 | 18 Oct 0300 - 0400 | THRY-822604 | SP-259 | ITS | FOT | 1 | 1 | 903709 |  | TF | 6780 | CRT | REPAIRE ON FMS.
1776 | 10/18/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 17.75 | 131.25 | 903398 |  | BHS | 0 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1778 | 10/18/2022 | 18 Oct 0900 - 0500 | RGHB-704 | SSA-5915 | RIG | FOT | 20 | 20 | 903700 |  | RR | 2177 | TDS | WHILE MAKING DP CONNECTION OBSERVED DAMAGE ON TDS STAND JUMP & 2 BOLTS MISSING & DROPPED.
1780 | 10/18/2022 | 16 Oct 0900 - 0700 | HRDH-1979 | SSA-5974 | ARM | STBH | 2 | 46 | 903623 |  | STUK | 0 | BHA | DRILLED OFF AT THE STAND END AND P/U 4 FT STRING TAKE WEIGHT AND TORQUED UP (STUCK). HAD CIRCULATION WITH NO ROTATION, SPEND TIME WORK STRING DOWN, WITH NO PROGRESS (JAR IS NOT WORKING). WORK PIPE SLACKING OFF WITH TRAPPED TORQUE WITH NO PROGRESS. TRIED TO WORK STRING UP WITH MAX OVERPULL (JAR IS WORKING OK UP). MOVE 3' PROGRESSED AND NO MORE. CONTINUE WORK STRING WITH NO PROGRESS.
1782 | 10/19/2022 | 19 Oct 2300 - 0500 | SDGM-1244 | ADC-41L | TK3 | WC11 | 6 | 6 | 903733 |  | WCNT | 13658 | NA | WHILE DRILLING @ 13658 FT, OBSERVED SUDDEN INCREASE IN FLOWOUT AND 5 BBLS GAIN IN ACTIVE.
1784 | 10/19/2022 | 17 Oct 0200 - 0500 | UTMN-2321 | ADC-46L | TK3 | UVLC | 24 | 50.5 | 903664 |  | LCIR | 9062 | NA | COMPLETE LOSS OF CIRCULATION @ 9,062' (LFDR)
1809 | 10/19/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 623.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1823 | 10/19/2022 | 16 Oct 2130 - 2230 | ANDR-589 | ADC-62L | RIG | FOT | 17.5 | 59.5 | 903638 |  | TF | 12348 | SLIPS | UNABLE TO CIRCULATE, WBIV BALL SEAT GOT PLUGGED WITH A PIECE OF WOOD FROM SET-BACK AREA LEADING TO UNINTENTIONALLY CLOSING BAKER 4-1/2" WBIV.
1828 | 10/19/2022 | 18 Oct 2000 - 1130 | HWYH-1300 | ADC-65L | SDM | FOT | 6.5 | 15.5 | 903719 |  | BHA | 8197 | MWD | GAMMA RAY READINGS HAS HIGHER VALUES AND UNBALE TO CORRELATE WITH OFFSET DATA
1830 | 10/19/2022 | 18 Oct 0500 - 1900 | UTMN-3134 | ADES-144 | RIG | OTH | 14 | 38 | 903663 |  | UPRA | 0 | NA | WHILE PINNING UP THE MAST ON THE RIG UP, HIGH HORSE STAND DAMAGED WHILE RESTING MAST CROWN SECTION ON IT.
1832 | 10/19/2022 | 19 Oct 0900 - 1030 | HRDH-1095 | ADES-157 | RIG | FPMP | 1.5 | 1.5 | 903726 |  | RR | 12280 | MPMP | HAD MP#1 PRESSURE RELIEF VALVE LEAKING & MP#3 PUMPER HOSE FAILURE.
1834 | 10/19/2022 | 19 Oct 2030 - 0345 | KHRS-556 | ADES-799 | INW | FOT | 7.25 | 7.25 | 903666 |  | TF | 6966 | PLUGT | RIH WITH 2.24" GS PULLING TOOLS TO TOP OF INTERWELL HEX PLUG ASSY ON 2" CT. SEVERAL ATTEMPTS TO ENGAGE INTO 2.3" HEX PLUG WITH NO SUCCESS.
1836 | 10/19/2022 | 16 Oct 1130 - 0500 | MRJN-2018 | ADM-261 | INW | FOT | 23 | 73.25 | 903603 |  | TF | 11850 | PLUGT | PUMP THROUGH PLUG NOT RECOVERED WHEN POH W/ UPPER COMPLETION.
1838 | 10/19/2022 | 19 Oct 1200 - 1315 | MRJN-799 | ADM-511 | HTS | FOT | 1.25 | 1.25 | 903736 |  | TF | 13899 | FLR | WELL TESTING CREW REPAIR IGNITION SYSTEM ON STRB FLARE BOOM
1840 | 10/19/2022 | 14 Oct 1830 - 2130 | MRJN-121 | ARO-2001 | HCM | CEDE | 16.5 | 123 | 903593 |  | JF | 11700 | NA | CEMENT PLUG FAILURE, CEMENT STILL SOFT 44 HRS AFTER SET THE PLUG.
1841 | 10/19/2022 | 19 Oct 1830 - 2130 | MRJN-814 | ARO-3002 | RIG | FOT | 3 | 3 | 903757 |  | RR | 0 | DWKS | DURING INSPECTION, EMERGENCY BRAKE ON DRILLERS SIDE FOUND TO BE OUT OF SPECIFICATION
1843 | 10/19/2022 | 19 Oct 1330 - 1745 | MRJN-814 | ARO-3002 | RIG | FOT | 4.25 | 4.25 | 903756 |  | RR | 0 | CSYS | STANDPIPE SPLITTER VALVE LEAKING.
1844 | 10/19/2022 | 19 Oct 1830 - 2130 | MRJN-814 | ARO-3002 | RIG | FOT | 3 | 3 | 903757 |  | RR | 0 | DWKS | DURING INSPECTION, EMERGENCY BRAKE ON DRILLERS SIDE FOUND TO BE OUT OF SPECIFICATION
1845 | 10/19/2022 | 19 Oct 2030 - 0500 | MRJN-537 | ARO-4001 | RIG | FOT | 8.5 | 8.5 | 903732 |  | RR | 14142 | DWKS | WHILE REAMING DOWN WITH 6 1/8" REAMING/DLR ASSY HAD DRAW WORK STOP WORKING, UNABLE TO MOVE UP OR DOWN, TROUBLESHOOTING SAME TILL GET IT MOVING UP & DOWN, BUT STILL HAD LEAKING IN THE AIR SYSTEM FEEDING THE DRAW WORK, POOH TO 7" LINER SHOE TO CONT. TROUBLESHOOTING.
1847 | 10/19/2022 | 19 Oct 0500 - 0645 | MRJN-537 | ARO-4001 | RIG | FOT | 1.75 | 1.75 | 903665 |  | RR | 14142 | EDR | HAD TEST UNIT CHECK VALVE LEAKING, CHANGE OUT SAME, OK.
1848 | 10/19/2022 | 19 Oct 2030 - 0500 | MRJN-537 | ARO-4001 | RIG | FOT | 8.5 | 8.5 | 903732 |  | RR | 14142 | DWKS | WHILE REAMING DOWN WITH 6 1/8" REAMING/DLR ASSY HAD DRAW WORK STOP WORKING, UNABLE TO MOVE UP OR DOWN, TROUBLESHOOTING SAME TILL GET IT MOVING UP & DOWN, BUT STILL HAD LEAKING IN THE AIR SYSTEM FEEDING THE DRAW WORK, POOH TO 7" LINER SHOE TO CONT. TROUBLESHOOTING.
1850 | 10/19/2022 | 18 Oct 0830 - 0500 | HRDH-1383 | BCTD-3 | RIG | FOT | 24 | 44.5 | 903683 |  | RR | 14840 | TRVL | POOH TO INSPECT INJECTOR- INJECTOR CHAINS ARE NOT ALIGNED.
1852 | 10/19/2022 | 18 Oct 1430 - 0500 | MRJN-741 | CG-1 | HWP | FOT | 9.5 | 24 | 903714 |  | TF | 9370 | CORRL | HALLIBURTON LOGGING TOOLS FAILURE, LEAK ON HYDRAULIC SYSTEM
1854 | 10/19/2022 | 17 Oct 2000 - 0500 | SDGM-1111 | DPS-46 | CRW | FOT | 24 | 50.75 | 903696 |  | BHA | 12626 | WBCL | SUSPECT CORETRAX WBC TOOLS HANGING UP INSIDE 9-5/8" CASING.
1856 | 10/19/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 10 | 10 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
1858 | 10/19/2022 | 19 Oct 1845 - 1945 | SDGM-1223 | NBR-196S | ITS | FOT | 1 | 1 | 903729 |  | TF | 12633 | CTRQ | REPAIR TUBING TONGS.
1860 | 10/19/2022 | 18 Oct 0530 - 0500 | QTIF-503 | NBR-263S | RIG | GRF | 24 | 47.5 | 903645 |  | UPRA | 0 | PSYS | - TROUBLESHOOT COMMUNICATION NOISE BETWEEN VFD AND TDS, DRAWORK, MUD PUMPS & OTHER EQUIP'S.
1862 | 10/19/2022 | 19 Oct 1200 - 2215 | HRDH-1944 | PA-70S | RIG | FOT | 10.25 | 10.25 | 903722 |  | RR | 2750 | EDR | RIG WATCH OUT OF SERVICE,
1864 | 10/19/2022 | 17 Oct 2100 - 2245 | MRJN-673 | PN-9 | BHI | FOT | 16.75 | 43.5 | 903677 |  | BHA | 14913 | MMOT | WHILE DRILLING OBSERVED MOTORIZED RSS STALL AND 250 PSI INCREASE IN PRESSSURE. FOUND MOTORIZED RSS RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD. STOPPED DRILLING.
1866 | 10/19/2022 | 17 Oct 0330 - 0500 | HSBH-25 | RBP-50A | RIG | GRF | 24 | 49.5 | 903662 |  | UPRA | 9973 | RWCS | FILL BOP W/ WATER - OBSERVE HYDROSTATIC WATER LEAK AT BSR BONNET SEAL. TROUBLESHOOT BSR BONNET SEAL LEAK AT BOP. (CAMERON-TL BOP, BSR CAVITY WITH TANDEM BOOSTERS).
1868 | 10/19/2022 | 19 Oct 1215 - 1245 | MRJN-657 | SDA | NCS | FOT | .5 | .5 | 903648 |  | TF | 5584 | PUMP | OBSERVE LEAK ON CEMENT HEAD. CHANGE GASKET, RESUME JOB.
1870 | 10/19/2022 | 18 Oct 1015 - 0430 | UTMN-1245 | SINO-26 | HUD | FOT | 23.5 | 42.25 | 903718 |  | TF | 9624 | MPD | HALL MPD FLOATS FAILED.
1872 | 10/19/2022 | 18 Oct 0300 - 0830 | SDGM-269 | SINO-36L | ITS | MATL | 3.5 | 5.5 | 903711 |  | WO | 2970 | NA | HAD LEAKAGE FROM ITS OPERATIONG POWER UNIT, ATTEMPT TO FIX, NO SUCCESS.
1874 | 10/19/2022 | 18 Oct 0045 - 0500 | ABQQ-454 | SINO21 | WI1 | FOT | 24 | 28.25 | 903708 |  | BHA | 7228 | MILL | WIS MILLING ASSY STUCK CROSS WINDOW.
1876 | 10/19/2022 | 19 Oct 0300 - 0500 | BRRI-1148 | SND-2004 | SWT | FOT | 2 | 2 | 903650 |  | TF | 0 | SEPR | WHILE OFFLOADING AND EMPTY SLB FRAC TANK BY VACUUM TANKER, THE FRAC TANK GOT DAMAGED. HOLD STAND-DOWN MEETING AND SHUT DOWN THE OPERATION FIR INVESTIGATION.
1878 | 10/19/2022 | 19 Oct 0200 - 0500 | MHKK-2 | SND-2005 | ARM | MATL | 3 | 3 | 903737 |  | WO | 12736 | NA | WAIT ON REMAINING ITEMS DUE TO SHORT NOTICE TO RUN 2ND 4-1/2" SCAB LINER (4-1/2" CENTRALIZERS/STOP RINGS, 7" CENTRALIZERS/STOP RINGS, "APPROVED" SUPPLEMENT & CMT PROGRAM).
1880 | 10/19/2022 | 11 Oct 0130 - 0500 | UTMN-3095 | SND-2006 | ARM | UXGE | 24 | 166.5 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
1882 | 10/19/2022 | 19 Oct 2215 - 0415 | KRSN-51 | SP-103 | SLL | FOT | 6 | 6 | 903759 |  | TF | 0 | PLUGT | LATCHED SLB SIM PLUG PRONG , MULTIPLE JARRING TO ATTEMPT TO RETRIEVE WITHOUT SUCCESS
1884 | 10/19/2022 | 19 Oct 0915 - 1345 | BRRI-522 | SP-121 | GOC | HERR | 4 | 4 | 903731 |  | JF | 7646 | CTRQ | COULDN'T PASS WITH SLB SLICK LINE TO DRIFT COMPLETION ASSY. L/D TUBING FROM THAT INTERVAL, FOUND MAXTUBE RING SLIGHTLY DEFORMED. RUN BACK TUBING & DRIFT COMPLETION ASSEMBLY, OK.
1886 | 10/19/2022 | 12 Oct 0300 - 1200 | HWYH-74 | SP-167 | WWL | FOT | 7 | 152.5 | 903516 |  | TF | 5857 | WLT | WFD CALIPER LOGGING COULDN'T PASS WINDOW, WORK ON SAME WITHIN LIMITS THEN POOH FOUND W'STOCK ENGAGED TO MULE SHOE
1888 | 10/19/2022 | 19 Oct 1330 - 1430 | THRY-822604 | SP-259 | ITS | FOT | 1 | 1 | 903728 |  | TF | 12000 | CRT | EXCESS TIME, POWER UNIT FAILLURE, FIXED AFTER TROUBLESHOOTING
1890 | 10/19/2022 | 19 Oct 1430 - 0500 | DNAN-554002 | SP-262 | SPS | IDPR | 14.5 | 14.5 | 903667 |  | DD | 9000 | RSS | HIGH VIBRATION ON HALLIBURTON ICRUISE RSS, POH, CHANGE BIT & ICRUISE.
1892 | 10/19/2022 | 17 Oct 1515 - 0500 | QTIF-526 | SSA-101 | ARM | WC20 | 23.25 | 58 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
1893 | 10/19/2022 | 19 Oct 1845 - 2300 | QTIF-172 | SSA-202 | ARM | UVLC | 4.25 | 4.25 | 903730 |  | LCIR | 5145 | NA | WHILE DRLG HAD PARTIAL LOSSES AT 5145'. CURE WITH LCM PILL
1895 | 10/19/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 19.25 | 150.5 | 903398 |  | BHS | 0 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
1896 | 10/19/2022 | 19 Oct 1845 - 2300 | QTIF-172 | SSA-202 | ARM | UVLC | 4.25 | 4.25 | 903730 |  | LCIR | 5145 | NA | WHILE DRLG HAD PARTIAL LOSSES AT 5145'. CURE WITH LCM PILL
1898 | 10/19/2022 | 19 Oct 1800 - 0500 | NJYN-16 | SSA-5891 | RIG | HERR | 11 | 11 | 903724 |  | JF | 14176 | DP | WRONG NUMBER OF 4" DP STANDS IN BHA TALLY.
1900 | 10/19/2022 | 19 Oct 1600 - 2330 | AWTD-141400 | SSA-5892 | SWL | FOT | 7.5 | 7.5 | 903646 |  | TF | 16750 | WLT | POOR SONIC DATA QUALITY
1902 | 10/19/2022 | 18 Oct 0900 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 44 | 903700 |  | UPRA | 2177 | TDS | WHILE MAKING DP CONNECTION OBSERVED DAMAGE ON TDS STAND JUMP & 2 BOLTS MISSING & DROPPED.
1904 | 10/19/2022 | 19 Oct 0330 - 0500 | SFNY-202 | ZPEC-3 | HSL | FOT | 1.5 | 1.5 | 903649 |  | TF | 0 | SLICK | WHILE RIH 3.62" HALLIBURTON GS PULLING TOOL TO RETRIEVE WRSSSV AT 312', SL WIRE CUT FROM ROPE SOCKET WHEN STARTED POH.
1906 | 10/20/2022 | 20 Oct 0630 - 2130 | ANDR-1006 | ADC-31 | GOC | XTTE | 4 | 4 | 903785 |  | TF | 7175 | CTRQ | DAMAGE PU/LD MACHIN WINCH CABLE. SPIDER SLIPS FAILURE.
1908 | 10/20/2022 | 19 Oct 2300 - 1000 | SDGM-1244 | ADC-41L | ARM | WC20 | 5 | 11 | 903733 |  | WCNT | 13658 | NA | WHILE DRILLING @ 13658 FT, OBSERVED SUDDEN INCREASE IN FLOWOUT AND 5 BBLS GAIN IN ACTIVE.
1910 | 10/20/2022 | 17 Oct 0200 - 0500 | UTMN-2321 | ADC-46L | TK3 | UVLC | 23.5 | 74 | 903664 |  | LCIR | 9062 | NA | COMPLETE LOSS OF CIRCULATION @ 9,062' (LFDR)
1932 | 10/20/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 647.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
1934 | 10/20/2022 | 20 Oct 1000 - 0500 | ABHD-183 | ADC-58L | SDM | XTTE | 18.5 | 18.5 | 903745 |  | TF | 8476 | RSS | RSS TOOLS IS NOT RESPONDING PROPERLY AND IS NOT ACCEPTING PROPER COMMAND
1955 | 10/20/2022 | 20 Oct 1630 - 1730 | HRDH-1095 | ADES-157 | RIG | FPMP | 1 | 1 | 903752 |  | RR | 12810 | MPMP | HAD LEAK IN MUD PUMP SURFACE LINE.
1957 | 10/20/2022 | 17 Oct 0830 - 0500 | MRJN-2018 | ADM-261 | RIG | HERR | 24 | 70.75 | 903777 |  | JF | 11890 | DP | HAD ERROR IN RIG PIPE TALLY RECORD.
1959 | 10/20/2022 | 20 Oct 1600 - 1945 | MRJN-57 | ADM-262 | BR1 | SRVC | 3.75 | 3.75 | 903786 |  | WO | 9995 | NA | LOST BROADBAND COMMUNICATION. SWITCH TO VSAT SYSTEM. DUE TO WELLLINK HIGH DATA BANDWIDTH USE, ALL IT AND COMMS SYSTEMS NON FUNCTIONAL (GOC COMMS, TELEPHONE, GENERAL OFFICE IT SYSTEMS).
1961 | 10/20/2022 | 20 Oct 0800 - 2030 | SFNY-263 | ADM-266 | AP2 | WOPF | 12.5 | 12.5 | 903755 |  | WO | 0 | NA | WAIT ON PRODUCTION PERMISSION TO FLOW BACK WELL SFNY-263.
1963 | 10/20/2022 | 20 Oct 1300 - 0100 | MRJN-3017 | ADM-339 | RIG | GRF | 12 | 12 | 903668 |  | UPRA | 3982 | TDS | OBSERVED DROPPED OBJECT ON RIG FLOOR (SMALL BEARING ROLLER). STOP TRIPPING OPERATIONS & SECURE WELL. INVESTIGATE SAME, CARRY OUT FULL DROPS INSPECTION OF AREA & FULL DROPS INSPECTION OF DERRICK.
1965 | 10/20/2022 | 20 Oct 0800 - 0500 | ABSF-223 | ADM-510 | SDM | AINC | 20.25 | 20.25 | 903746 |  | DD | 12658 | BHA | SDM UNABLE TO MAINTAIN TRAJECTORY, DECISION TAKEN TO POH FOR BHA CHANGE
1967 | 10/20/2022 | 19 Oct 2030 - 1930 | MRJN-537 | ARO-4001 | RIG | FOT | 14.5 | 23 | 903732 |  | RR | 14142 | DWKS | WHILE REAMING DOWN WITH 6 1/8" REAMING/DLR ASSY HAD DRAW WORK STOP WORKING, UNABLE TO MOVE UP OR DOWN, TROUBLESHOOTING SAME TILL GET IT MOVING UP & DOWN, BUT STILL HAD LEAKING IN THE AIR SYSTEM FEEDING THE DRAW WORK, POOH TO 7" LINER SHOE TO CONT. TROUBLESHOOTING, WORKING OK.
1969 | 10/20/2022 | 18 Oct 0830 - 0500 | HRDH-1383 | BCTD-3 | RIG | FOT | 24 | 68.5 | 903683 |  | RR | 14840 | TRVL | POOH TO INSPECT INJECTOR- INJECTOR CHAINS ARE NOT ALIGNED.
1971 | 10/20/2022 | 18 Oct 1430 - 1515 | MRJN-741 | CG-1 | HWP | FOT | 10.25 | 34.25 | 903714 |  | TF | 9370 | CORRL | HALLIBURTON LOGGING TOOLS FAILURE, LEAK ON HYDRAULIC SYSTEM
1973 | 10/20/2022 | 17 Oct 2000 - 0600 | SDGM-1111 | DPS-46 | CRW | FOT | 1 | 51.75 | 903696 |  | BHA | 12626 | WBCL | SUSPECT CORETRAX WBC TOOLS HANGING UP INSIDE 9-5/8" CASING.
1975 | 10/20/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 24 | 34 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
1977 | 10/20/2022 | 20 Oct 1300 - 0500 | HMYM-450412 | HWU-1 | RIG | FOT | 16 | 16 | 903743 |  | RR | 0 | SLIPS | SLIPS GETTING COCK-LOCKED ON TUBING
1979 | 10/20/2022 | 20 Oct 1800 - 0500 | BRRI-310 | MP-1 | RIG | FOT | 11 | 11 | 903753 |  | RR | 8168 | CRN | ASSISTANT CRANE OPERATOR OBSERVED & REPORTED DEFORMED BOW CRANE BOOM. RIG SHUT DOWN PENDING INVESTIGATIONS INTO DEFORMED BOW CRANE BOOM.
1981 | 10/20/2022 | 18 Oct 0530 - 0500 | QTIF-503 | NBR-263S | RIG | GRF | 24 | 71.5 | 903645 |  | UPRA | 0 | PSYS | - TROUBLESHOOT COMMUNICATION NOISE BETWEEN VFD AND TDS, DRAWORK, MUD PUMPS & OTHER EQUIP'S.
1983 | 10/20/2022 | 20 Oct 1130 - 1730 | MRJN-673 | PN-9 | RIG | FOT | 6 | 6 | 903790 |  | RR | 15401 | TDS | OBSERVE LEAK AT TDS WASH PIPE.
1985 | 10/20/2022 | 17 Oct 0330 - 0500 | HSBH-25 | RBP-50A | RIG | GRF | 24 | 73.5 | 903662 |  | UPRA | 9973 | RWCS | FILL BOP W/ WATER - OBSERVE HYDROSTATIC WATER LEAK AT BSR BONNET SEAL. TROUBLESHOOT BSR BONNET SEAL LEAK AT BOP. (CAMERON-TL BOP, BSR CAVITY WITH TANDEM BOOSTERS).
1986 | 10/20/2022 | 18 Oct 1015 - 0630 | UTMN-1245 | SINO-26 | HUD | FOT | 1.5 | 43.75 | 903718 |  | TF | 9624 | MPD | HALL MPD FLOATS FAILED.
1988 | 10/20/2022 | 17 Oct 0100 - 1800 | UTMN-1245 | SINO-26 | HUD | FOT | 11.5 | 20.75 | 903717 |  | TF | 9624 | MPD | HALL MPD BEARING LEAK.
1989 | 10/20/2022 | 18 Oct 1015 - 0630 | UTMN-1245 | SINO-26 | HUD | FOT | 1.5 | 43.75 | 903718 |  | TF | 9624 | MPD | HALL MPD FLOATS FAILED.
1991 | 10/20/2022 | 18 Oct 0045 - 0500 | ABQQ-454 | SINO21 | WI1 | FOT | 24 | 52.25 | 903708 |  | BHA | 7228 | MILL | WIS MILLING ASSY STUCK CROSS WINDOW.
1993 | 10/20/2022 | 20 Oct 2245 - 0500 | SFNY-1730 | SL-7 | BLH | FOT | 6.25 | 6.25 | 903788 |  | TF | 5148 | HGRL | ENCOUNTERED DRAG WHILE RIH, UNABLE TO PASS OBSTRUCTION WITHOUT CIRCULATION.
1994 | 10/20/2022 | 20 Oct 1100 - 1500 | BRRI-1148 | SND-2004 | ARM | FOT | 4 | 4 | 903742 |  | TF | 0 | SEPR | WHILE OFFLOADING AND EMPTY SLB FRAC TANK BY VACUUM TANKER, THE FRAC TANK COLLAPSED. HOLD STAND-DOWN MEETING AND SHUT DOWN THE OPERATION FOR INVESTIGATION.
1996 | 10/20/2022 | 19 Oct 0300 - 0700 | BRRI-1148 | SND-2004 | SWT | FOT | 2 | 4 | 903650 |  | TF | 0 | SEPR | WHILE OFFLOADING AND EMPTY SLB FRAC TANK BY VACUUM TANKER, THE FRAC TANK COLLAPSED. HOLD STAND-DOWN MEETING AND SHUT DOWN THE OPERATION FOR INVESTIGATION.
1997 | 10/20/2022 | 20 Oct 0700 - 1100 | BRRI-1148 | SND-2004 | RIG | FOT | 4 | 4 | 903741 |  | TF | 0 | SEPR | WHILE OFFLOADING AND EMPTY SLB FRAC TANK BY VACUUM TANKER, THE FRAC TANK COLLAPSED. HOLD STAND-DOWN MEETING AND SHUT DOWN THE OPERATION FOR INVESTIGATION.
1998 | 10/20/2022 | 20 Oct 1100 - 1500 | BRRI-1148 | SND-2004 | ARM | FOT | 4 | 4 | 903742 |  | TF | 0 | SEPR | WHILE OFFLOADING AND EMPTY SLB FRAC TANK BY VACUUM TANKER, THE FRAC TANK COLLAPSED. HOLD STAND-DOWN MEETING AND SHUT DOWN THE OPERATION FOR INVESTIGATION.
2000 | 10/20/2022 | 19 Oct 0200 - 2030 | MHKK-2 | SND-2005 | OTH | WOTR | 15.5 | 18.5 | 903737 |  | WO | 12736 | NA | WAIT ON REMAINING ITEMS DUE TO CHANGE OF PLAN FROM EXPLORATION MANAGEMENT TO RUN ANOTHER SCAB LINER TO COVER CO2 TARGETS FOR RIG-LESS TESTING.
2002 | 10/20/2022 | 11 Oct 0130 - 0500 | UTMN-3095 | SND-2006 | ARM | UXGE | 24 | 190.5 | 903464 |  | LCIR | 11225 | NA | WHILE DRILLING AT 11,225 FT OBSERVED DYNAMIC LOSSES 120 BPH.
2004 | 10/20/2022 | 20 Oct 1330 - 1500 | LIDM-2 | SP-258 | RIG | FOT | 1.5 | 1.5 | 903751 |  | RR | 10461 | RSYS | AFTER BREAK OUT CONNECTION , IRON ROUGHNECK UNABLE TO MOVE BACKWORD TO IT'S POSITION, TROUBLE SHOOTING & FIXED THE ISSUE.
2006 | 10/20/2022 | 19 Oct 1430 - 0915 | DNAN-554002 | SP-262 | SPS | IDPR | 4.25 | 18.75 | 903667 |  | DD | 9000 | RSS | HIGH VIBRATION ON HALLIBURTON ICRUISE RSS, POH, CHANGE BIT & ICRUISE.
2008 | 10/20/2022 | 20 Oct 1100 - 1815 | MNIF-198 | SP-306 | RIG | FOT | 2 | 2 | 903750 |  | RR | 6254 | MPMP | REPAIR ON MUD PUMPS
2010 | 10/20/2022 | 17 Oct 1515 - 0500 | QTIF-526 | SSA-101 | ARM | WC20 | 23.5 | 81.5 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
2012 | 10/20/2022 | 10 Oct 0145 - 0500 | QTIF-172 | SSA-202 | ARM | CWEL | 23.5 | 174 | 903398 |  | BHS | 0 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
2014 | 10/20/2022 | 19 Oct 1800 - 0600 | NJYN-16 | SSA-5891 | RIG | HERR | 1 | 12 | 903724 |  | JF | 14176 | DP | WRONG NUMBER OF 4" DP STANDS IN BHA TALLY.
2016 | 10/20/2022 | 18 Oct 0900 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 68 | 903700 |  | UPRA | 2177 | TDS | WHILE MAKING DP CONNECTION OBSERVED DAMAGE ON TDS STAND JUMP & 2 BOLTS MISSING & DROPPED.
2018 | 10/20/2022 | 19 Oct 1500 - 0730 | HRDH-1983 | SSA-5962 | RTC | XBTR | 2.5 | 16 | 903761 |  | LROP | 3667 | BIT | UNABLE TO D/O WFD DV-TOOL WITH REED PDC BIT.
2020 | 10/20/2022 | 20 Oct 1400 - 1500 | UTMN-3193 | SSA-5970 | RIG | XTTE | 1 | 1 | 903780 |  | TF | 720 | BHA | EXCESSIVE TIME HANDLING BHA AND ADJUSTING TDS CLAMP.
2021 | 10/20/2022 | 20 Oct 2030 - 2215 | MRJN-3024 | V141A | RIG | XTRI | 1.75 | 1.75 | 903787 |  | JF | 5350 | CTRQ | EXCESSIVE TIME RUNNING 13-3/8" CSG, KPI IS 10 JTS/HR, RIG RUNNING +/- 8.5 JTS/HR
2023 | 10/20/2022 | 20 Oct 1530 - 1630 | MRJN-3024 | V141A | MSD | XTTE | 1 | 1 | 903744 |  | TF | 3000 | CRT | DRILLER HAVE ISSUSES WITH BACKING OUT CRT FROM CSG AFTER LANDING IN SLIPS.
2024 | 10/20/2022 | 20 Oct 2030 - 2215 | MRJN-3024 | V141A | RIG | XTRI | 1.75 | 1.75 | 903787 |  | JF | 5350 | CTRQ | EXCESSIVE TIME RUNNING 13-3/8" CSG, KPI IS 10 JTS/HR, RIG RUNNING +/- 8.5 JTS/HR
2026 | 10/20/2022 | 20 Oct 0500 - 1000 | SFNY-202 | ZPEC-3 | HSL | FOT | 5 | 5 | 903649 |  | TF | 0 | SLICK | WHILE RIH 3.62" HALLIBURTON GS PULLING TOOL TO RETRIEVE WRSSSV AT 312', SL WIRE CUT FROM ROPE SOCKET WHEN STARTED POH.
2028 | 10/21/2022 | 21 Oct 1545 - 1700 | HRDH-1864 | ADC-14 | RIG | FOT | 1.25 | 1.25 | 903792 |  | RR | 2300 | TDS | REPAIR HYDRAULIC HOSE LEAKING IN TDS.
2030 | 10/21/2022 | 17 Oct 0200 - 0500 | UTMN-2321 | ADC-46L | TK3 | UVLC | 23.5 | 97.5 | 903664 |  | LCIR | 9062 | NA | COMPLETE LOSS OF CIRCULATION @ 9,062' (LFDR)
2032 | 10/21/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 671.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
2034 | 10/21/2022 | 20 Oct 1000 - 1045 | ABHD-183 | ADC-58L | SDM | XTTE | 5.75 | 23.75 | 903745 |  | TF | 8476 | RSS | RSS TOOLS IS NOT RESPONDING PROPERLY AND IS NOT ACCEPTING PROPER COMMAND
2036 | 10/21/2022 | 21 Oct 0330 - 0500 | SDGM-1255 | ADC-64L | ITS | FOT | 1.5 | 1.5 | 903798 |  | TF | 12430 | CTRQ | CHANGE POWER TONG SENSOR
2038 | 10/21/2022 | 21 Oct 1800 - 1945 | HRDH-2354 | ADES-798 | BLH | FOT | 1.75 | 1.75 | 903796 |  | TF | 13152 | LLAP | LINER RUNNING TOOL STUCK INSIDE LINER HANGER. WORK ON SAME TILL RELEASED.
2040 | 10/21/2022 | 20 Oct 0800 - 1200 | ABSF-223 | ADM-510 | SDM | AINC | 5.75 | 26 | 903746 |  | DD | 12658 | BHA | SDM UNABLE TO MAINTAIN TRAJECTORY, DECISION TAKEN TO POH FOR BHA CHANGE
2042 | 10/21/2022 | 21 Oct 1900 - 0500 | MRJN-723 | AOD-111 | BHI | FOT | 9.5 | 9.5 | 903793 |  | BHA | 14482 | MWD | BHI TOOLS UNABLE TO RESPOND FOR DOWN LINK. TROUBLE SHOOTING SAME WITHOUT SUCCESS.
2044 | 10/21/2022 | 18 Oct 0830 - 1800 | HRDH-1383 | BCTD-3 | RIG | FOT | 13 | 81.5 | 903683 |  | RR | 14840 | TRVL | POOH TO INSPECT INJECTOR- INJECTOR CHAINS ARE NOT ALIGNED.
2046 | 10/21/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 22 | 56 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2060 | 10/21/2022 | 20 Oct 1300 - 1800 | HMYM-450412 | HWU-1 | RIG | FOT | 13 | 29 | 903743 |  | RR | 0 | SLIPS | SLIPS GETTING COCK-LOCKED ON TUBING
2062 | 10/21/2022 | 20 Oct 1800 - 0800 | BRRI-310 | MP-1 | RIG | FOT | 3 | 14 | 903753 |  | RR | 8168 | CRN | ASSISTANT CRANE OPERATOR OBSERVED & REPORTED DEFORMED BOW CRANE BOOM. RIG SHUT DOWN PENDING INVESTIGATIONS INTO DEFORMED BOW CRANE BOOM.
2064 | 10/21/2022 | 18 Oct 0530 - 0900 | QTIF-503 | NBR-263S | RIG | GRF | 4 | 75.5 | 903645 |  | UPRA | 0 | PSYS | - TROUBLESHOOT COMMUNICATION NOISE BETWEEN VFD AND TDS, DRAWORK, MUD PUMPS & OTHER EQUIP'S.
2066 | 10/21/2022 | 21 Oct 0200 - 0500 | MRJN-673 | PN-9 | BHI | FOT | 3 | 3 | 903797 |  | BHA | 16149 | MMOT | RECEIVE UNCLEAR DENSITY DATA FROM BAKER HUGES, CIRCULATE & TROUBLESHOOTING, FOUND MOTORIZED RSS RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD.
2068 | 10/21/2022 | 17 Oct 0330 - 0500 | HSBH-25 | RBP-50A | RIG | GRF | 24 | 97.5 | 903662 |  | UPRA | 9973 | RWCS | FILL BOP W/ WATER - OBSERVE HYDROSTATIC WATER LEAK AT BSR BONNET SEAL. TROUBLESHOOT BSR BONNET SEAL LEAK AT BOP. (CAMERON-TL BOP, BSR CAVITY WITH TANDEM BOOSTERS).
2070 | 10/21/2022 | 21 Oct 1945 - 0500 | UTMN-4066 | SINO-43L | BHI | FOT | 9.25 | 9.25 | 903795 |  | BHA | 7994 | RSS | LOST COMMUNICATION W/ BHI DOWNHOLE STEERING TOOL.
2072 | 10/21/2022 | 18 Oct 0045 - 0500 | ABQQ-454 | SINO21 | WI1 | FOT | 24 | 76.25 | 903708 |  | BHA | 7228 | MILL | WIS MILLING ASSY STUCK CROSS WINDOW.
2074 | 10/21/2022 | 21 Oct 1230 - 0500 | HRDH-457 | SP-154 | INW | XTTE | 16.5 | 16.5 | 903794 |  | TF | 2500 | SLICK | INTERWELL FAILED TO RETRIEVE THE 7'' ME PLUG.
2076 | 10/21/2022 | 17 Oct 1515 - 0500 | QTIF-526 | SSA-101 | ARM | WC20 | 23 | 104.5 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
2078 | 10/21/2022 | 10 Oct 0145 - 0915 | QTIF-172 | SSA-202 | ARM | CWEL | 4.25 | 178.25 | 903398 |  | BHS | 0 | NA | HOLE COLLAPSED ABOVE LOSS ZONE. WHILE RIH 9-5/8" CSG.
2080 | 10/21/2022 | 18 Oct 0900 - 0500 | RGHB-704 | SSA-5915 | RIG | GRF | 24 | 92 | 903700 |  | UPRA | 2177 | TDS | WHILE MAKING DP CONNECTION OBSERVED DAMAGE ON TDS STAND JUMP & 2 BOLTS MISSING & DROPPED.
2082 | 10/22/2022 | 22 Oct 1500 - 1830 | ANDR-1006 | ADC-31 | RIG | FOT | 3.5 | 3.5 | 903769 |  | RR | 10660 | TDS | IBOP YOKE DAMAGE.
2084 | 10/22/2022 | 22 Oct 2100 - 0130 | SDGM-1194 | ADC-36 | BHI | FOT | 4.5 | 4.5 | 903770 |  | BHA | 0 | RSS | ATTEMPTED TO SHALLOW TEST BHI RSS/MWD/GR; FAILED, L/D 5-7/8" BHI ONTRACK & BCPM, CHANGED WITH BACK-UP TOOLS.
2086 | 10/22/2022 | 17 Oct 0200 - 0500 | UTMN-2321 | ADC-46L | TK3 | UVLC | 23.5 | 121 | 903664 |  | LCIR | 9062 | NA | COMPLETE LOSS OF CIRCULATION @ 9,062' (LFDR)
2088 | 10/22/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 695.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
2109 | 10/22/2022 | 22 Oct 1430 - 0500 | SDGM-1259 | ADC-67L | PKP | FOT | 14.5 | 14.5 | 903670 |  | TF | 11836 | HGRL | ATTEMPT TO SHEAR SECOND BALL SEAT W/6500 PSI, NO SUCCESS.
2111 | 10/22/2022 | 22 Oct 0500 - 0500 | UTMN-1952 | ADES-173 | NFM | FOT | 23 | 23 | 903773 |  | BHA | 12473 | MMOT | MUD MOTOR FAILURE.
2113 | 10/22/2022 | 22 Oct 2300 - 0015 | MRJN-57 | ADM-262 | ARN | SRVC | 1.25 | 1.25 | 903774 |  | WO | 11850 | NA | LOST COMMUNICATIONS, UNABLE TO DRILL AHEAD. BROADBAND SIGNAL DROPPED OUT, VSAT NON-FUNCTIONING WHEN CONNECTED WITH WELLLINK.
2115 | 10/22/2022 | 22 Oct 0700 - 1015 | MRJN-3017 | ADM-339 | RIG | FOT | 3.25 | 3.25 | 903765 |  | RR | 5543 | DWKS | OBSERVED DRAW WORKS ALARM ON SYSTEM SHUT DOWN AND INVESTIGATE SAME.
2117 | 10/22/2022 | 21 Oct 1900 - 2045 | MRJN-723 | AOD-111 | BHI | FOT | 15.25 | 24.75 | 903793 |  | BHA | 14482 | MWD | BHI TOOLS UNABLE TO RESPOND FOR DOWN LINK. TROUBLE SHOOTING SAME WITHOUT SUCCESS.
2118 | 10/22/2022 | 22 Oct 1645 - 0330 | MRJN-121 | ARO-2001 | WCS | DSFT | 10.75 | 10.75 | 903768 | 903593 | JF | 10044 | PAK | RIH TO SET 4-1/2" WFD 4-1/2" PERMANENT BRIDGE PLUG. BRIDGE PLUG UNABLE TO SET IN 4-1/2" LINER
2120 | 10/22/2022 | 14 Oct 1830 - 1645 | MRJN-121 | ARO-2001 | HCM | CEDE | 11.75 | 190 | 903593 |  | JF | 11700 | NA | CEMENT PLUG FAILURE, CEMENT STILL SOFT 44 HRS AFTER SET THE PLUG.
2121 | 10/22/2022 | 22 Oct 1645 - 0330 | MRJN-121 | ARO-2001 | WCS | DSFT | 10.75 | 10.75 | 903768 | 903593 | JF | 10044 | PAK | RIH TO SET 4-1/2" WFD 4-1/2" PERMANENT BRIDGE PLUG. BRIDGE PLUG UNABLE TO SET IN 4-1/2" LINER
2123 | 10/22/2022 | 22 Oct 0100 - 0330 | UTMN-3019 | DPS-43 | FME | HERR | 2.5 | 2.5 | 903674 |  | WH | 4685 | WH | TRIED TO INSTALL 26-3/4" 3K X 18 3/4" 5K CASING SPOOL, ABSERVED PACKOFF SLIGHTLY OUT OF PLACE.
2125 | 10/22/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 24 | 80 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2127 | 10/22/2022 | 22 Oct 2245 - 0500 | HRDH-1541 | DQ-49L | TK2 | NARW | 6.25 | 6.25 | 903673 |  | TH | 9401 | NA | RIH W/ BKR 7" / 9 5/8" WBCU ASSY. RUN # 1 ON 4" DP TILL HAD OBSTRUCTION @ 9,401' (16' BELOW L-2 BOW) W/ 15 KLB S.O.WT AND WORK ON SAME MANY TIMES W/ DIFFERENT PARAMETERS, NO SUCCESS.
2129 | 10/22/2022 | 22 Oct 0000 - 0100 | ZULF-2066 | ED-85A | RIG | LHFL | 1 | 1 | 903841 |  | RR | 1545 | HSYS | HYDRAULIC LEAK ON IRON ROUGHNECK
2131 | 10/22/2022 | 22 Oct 1715 - 1745 | ZULF-2015 | ENS-108 | RIG | FOT | .5 | .5 | 903672 |  | RR | 5775 | TRVL | OBSERVED 5-1/2" DP ELEVATOR NOT OPENING COMPLETELY. REPLACED ELEVATORS.
2133 | 10/22/2022 | 20 Oct 1300 - 0500 | HMYM-450412 | HWU-1 | RIG | FOT | 12.5 | 41.5 | 903743 |  | RR | 0 | SLIPS | SLIPS GETTING COCK-LOCKED ON TUBING
2135 | 10/22/2022 | 22 Oct 0500 - 1500 | QTIF-503 | NBR-263S | RIG | GRF | 10 | 10 | 903844 |  | UPRA | 0 | RSYS | ROTARY TABLE NOT WORKING, TROUBLE SHOOT ROTARY TABLE ISSUE
2137 | 10/22/2022 | 22 Oct 1315 - 1715 | HRDH-1976 | PA-218S | RIG | FOT | 4 | 4 | 903766 |  | RR | 9060 | CSYS | ACTUATOR VALVE TOP CONNECTION SEAL LEAKING.
2138 | 10/22/2022 | 22 Oct 1615 - 1715 | MRJN-673 | PN-9 | RIG | UNKN | 1 | 1 | 903836 |  | HSEI | 6040 | NA | 4" DP STAND FELL ACCROSS DERRICK DUE TO PRS OPERATOR ACCIDENTAL OPENING 2 FINGERS IN FINGERBOARD WHEN RACKING STAND.
2140 | 10/22/2022 | 21 Oct 0200 - 0500 | MRJN-673 | PN-9 | BHI | FOT | 19.75 | 22.75 | 903797 |  | BHA | 16149 | MMOT | RECEIVE UNCLEAR DENSITY DATA FROM BAKER HUGHES, CIRCULATE & TROUBLESHOOTING, FOUND MOTORIZED RSS RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD.
2141 | 10/22/2022 | 22 Oct 1615 - 1715 | MRJN-673 | PN-9 | RIG | UNKN | 1 | 1 | 903836 |  | HSEI | 6040 | NA | 4" DP STAND FELL ACCROSS DERRICK DUE TO PRS OPERATOR ACCIDENTAL OPENING 2 FINGERS IN FINGERBOARD WHEN RACKING STAND.
2143 | 10/22/2022 | 17 Oct 0330 - 0500 | HSBH-25 | RBP-50A | RIG | GRF | 24 | 121.5 | 903662 |  | UPRA | 9973 | RWCS | FILL BOP W/ WATER - OBSERVE HYDROSTATIC WATER LEAK AT BSR BONNET SEAL. TROUBLESHOOT BSR BONNET SEAL LEAK AT BOP. (CAMERON-TL BOP, BSR CAVITY WITH TANDEM BOOSTERS).
2145 | 10/22/2022 | 22 Oct 1700 - 1845 | HSBH-68 | RM-74A | FMC | FOT | 1.75 | 1.75 | 903842 |  | TF | 9797 | CTRQ | FRANK'S TROUBLESHOOTING 500 TON SPIDER ELEVATOR AND HYDRAULIC POWER UNIT
2147 | 10/22/2022 | 21 Oct 1945 - 2015 | UTMN-4066 | SINO-43L | BHI | FOT | 15.25 | 24.5 | 903795 |  | BHA | 7994 | RSS | LOST COMMUNICATION W/ BHI DOWNHOLE STEERING TOOL.
2149 | 10/22/2022 | 18 Oct 0045 - 0500 | ABQQ-454 | SINO21 | WI1 | FOT | 24 | 100.25 | 903708 |  | BHA | 7228 | MILL | WIS MILLING ASSY STUCK CROSS WINDOW.
2151 | 10/22/2022 | 20 Oct 2245 - 0500 | SFNY-1730 | SL-7 | SAM | FOT | 24 | 54.25 | 903817 |  | BHA | 5148 | WBCL | 7" LINER UNABLE TO PASS OBSTRUCTION.
2153 | 10/22/2022 | 22 Oct 1930 - 2330 | DMMM-632 | SND-3002 | RIG | FOT | 4 | 4 | 903840 |  | RR | 183 | TDS | TDS ELECTRICAL FAILURE DUE TO LOSS COMMUNICAION ON ASB MODULE.
2155 | 10/22/2022 | 22 Oct 1630 - 0500 | DNAN-554002 | SP-262 | SPS | FOT | 12.5 | 12.5 | 903843 |  | BHA | 11834 | MWD | SPERRY LOST COMMUNICATION WITH THE RSS.
2157 | 10/22/2022 | 17 Oct 1515 - 0500 | QTIF-526 | SSA-101 | ARM | WC20 | 23.5 | 128 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
2159 | 10/22/2022 | 22 Oct 2130 - 0500 | AWTD-141400 | SSA-5892 | SWL | FOP | 7.5 | 7.5 | 903671 |  | JF | 16750 | PLT | SLB WIRELINE DATA COLLECTED ON RUN 1 WAS NOT ACCEPTED BY ARAMCO AND COMPANY SWITCHED TO HALLIBURTON WIRELINE
2161 | 10/22/2022 | 18 Oct 0900 - 0200 | RGHB-704 | SSA-5915 | RIG | GRF | 21 | 113 | 903700 |  | UPRA | 2177 | TDS | WHILE MAKING DP CONNECTION OBSERVED DAMAGE ON TDS STAND JUMP & 2 BOLTS MISSING & DROPPED.
2163 | 10/23/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 33.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2165 | 10/23/2022 | 17 Oct 0200 - 0500 | UTMN-2321 | ADC-46L | TK3 | UVLC | 23.5 | 144.5 | 903664 |  | LCIR | 9062 | NA | COMPLETE LOSS OF CIRCULATION @ 9,062' (LFDR)
2166 | 10/23/2022 | 23 Oct 2000 - 2230 | UTMN-3171 | ADC-55L | RIG | FOT | 2.5 | 2.5 | 903880 |  | TF | 11238 | SLIPS | WHILE POH WITH 5 7/8" BHA ON 5.5" DPS, OBSERVED DP MANUAL SLIPS NOT HOLDING THE STRING WT, CHECKED DIES, FOUND WORN OUT, NO BACK UP DIES ON RIG.
2168 | 10/23/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 21.5 | 717.25 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
2169 | 10/23/2022 | 23 Oct 2000 - 2230 | UTMN-3171 | ADC-55L | RIG | FOT | 2.5 | 2.5 | 903880 |  | TF | 11238 | SLIPS | WHILE POH WITH 5 7/8" BHA ON 5.5" DPS, OBSERVED DP MANUAL SLIPS NOT HOLDING THE STRING WT, CHECKED DIES, FOUND WORN OUT, NO BACK UP DIES ON RIG.
2185 | 10/23/2022 | 22 Oct 1430 - 1700 | SDGM-1259 | ADC-67L | PKP | FOT | 11.5 | 26 | 903670 |  | TF | 11836 | HGRL | ATTEMPT TO SHEAR SECOND BALL SEAT W/6500 PSI, NO SUCCESS.
2186 | 10/23/2022 | 23 Oct 0245 - 0345 | UTMN-1952 | ADES-173 | RIG | FOT | 1 | 1 | 903861 |  | RR | 12553 | HSYS | IRON ROUGHNECK HOSE BROKEN
2188 | 10/23/2022 | 22 Oct 0500 - 1530 | UTMN-1952 | ADES-173 | NFM | FOT | 8.5 | 31.5 | 903773 |  | BHA | 12473 | MMOT | MUD MOTOR FAILURE.
2189 | 10/23/2022 | 23 Oct 0245 - 0345 | UTMN-1952 | ADES-173 | RIG | FOT | 1 | 1 | 903861 |  | RR | 12553 | HSYS | IRON ROUGHNECK HOSE BROKEN
2191 | 10/23/2022 | 22 Oct 2030 - 1300 | HRDH-2354 | ADES-798 | BLH | HERR | 8 | 16.5 | 903846 |  | JF | 13152 | MILL | BIT NOZZELS PLUGGED DUE TO WRONG RECOMMENDATION FROM BAKER.
2193 | 10/23/2022 | 22 Oct 2300 - 1115 | MRJN-57 | ADM-262 | ARN | SRVC | .75 | 2 | 903774 |  | WO | 11850 | NA | LOST COMMUNICATIONS, UNABLE TO DRILL AHEAD. BROADBAND SIGNAL DROPPED OUT, VSAT NON-FUNCTIONING WHEN CONNECTED WITH WELLLINK.
2195 | 10/23/2022 | 23 Oct 1645 - 1745 | SFNY-4260 | AOD-1 | RIG | FOT | 1 | 1 | 903675 |  | RR | 4831 | EDR | WHILE DRILLING SEA DRILL RIGSENSE STOPPED DATA TRANSMISSION TO WELLLINK.
2196 | 10/23/2022 | 23 Oct 1600 - 0130 | NJYN-18 | DPS-74 | HWP | FOT | 9.5 | 9.5 | 903887 |  | TF | 15595 | WLT | FAILURE HALL WIRE LINE 3.25" MECHANICAL CUTTER TO CUT 5.5" DP.
2198 | 10/23/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 14.5 | 94.5 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2199 | 10/23/2022 | 23 Oct 1600 - 0130 | NJYN-18 | DPS-74 | HWP | FOT | 9.5 | 9.5 | 903887 |  | TF | 15595 | WLT | FAILURE HALL WIRE LINE 3.25" MECHANICAL CUTTER TO CUT 5.5" DP.
2201 | 10/23/2022 | 22 Oct 2245 - 1600 | HRDH-1541 | DQ-49L | TK2 | NARW | 11 | 17.25 | 903673 |  | TH | 9401 | NA | RIH W/ BKR 7" / 9 5/8" WBCU ASSY. RUN # 1 ON 4" DP TILL HAD OBSTRUCTION @ 9,401' (16' BELOW L-2 BOW) W/ 15 KLB S.O.WT AND WORK ON SAME MANY TIMES W/ DIFFERENT PARAMETERS, NO SUCCESS.
2203 | 10/23/2022 | 20 Oct 1300 - 1930 | HMYM-450412 | HWU-1 | RIG | FOT | 14.5 | 56 | 903743 |  | RR | 0 | SLIPS | SLIPS GETTING COCK-LOCKED ON TUBING
2205 | 10/23/2022 | 06 Oct 1030 - 0500 | BRRI-562 | NADRU-1 | SLL | FOT | 3 | 6.5 | 903210 |  | TF | 244 | SLICK | TRY TO SET GAUGES AT 4900', NO SUCCESS, POOH HANGER STUCK AT TRSSV. LEFT FISH MEMORY GAUES & HANGER.
2207 | 10/23/2022 | 22 Oct 0115 - 1330 | SHYB-65 | PA-529S | NTT | WOTO | 8.5 | 12.25 | 903845 |  | WO | 6668 | NA | NESR THRU TUBING NOT BRING ENOUGH MILL AS DRILLING PROGRAM PLANED.
2209 | 10/23/2022 | 21 Oct 0200 - 0100 | MRJN-673 | PN-9 | BHI | FOT | 19.5 | 42.25 | 903797 |  | BHA | 16149 | MMOT | RECEIVE UNCLEAR DENSITY DATA FROM BAKER HUGHES, CIRCULATE & TROUBLESHOOTING, FOUND MOTORIZED RSS RUBBER ON SHAKERS, CONFIRMED WITH BAKER DD.
2211 | 10/23/2022 | 17 Oct 0330 - 2130 | HSBH-25 | RBP-50A | RIG | GRF | 16.5 | 138 | 903662 |  | UPRA | 9973 | RWCS | FILL BOP W/ WATER - OBSERVE HYDROSTATIC WATER LEAK AT BSR BONNET SEAL. TROUBLESHOOT BSR BONNET SEAL LEAK AT BOP. (CAMERON-TL BOP, BSR CAVITY WITH TANDEM BOOSTERS).
2213 | 10/23/2022 | 23 Oct 1600 - 0500 | HSBH-68 | RM-74A | RIG | FOT | 13 | 13 | 903860 |  | RR | 9797 | CSYS | PIT WITH MIX WATER FOR LEAD CEMENT SLURRY LEAKING, DUMP MIX WATER AND FIX THE LEAKS.
2215 | 10/23/2022 | 23 Oct 2000 - 2100 | MRJN-659 | SDA | RIG | HERR | 1 | 1 | 903883 |  | JF | 5570 | WH | WHILE ASSEMBLING 13 3/8'' FMC AUTO SLIPS ON C-PLATE ABOVE 20 X-13-3/8" CSG POOL , SEAL ENERGIZING BOLT BROKEN. CHANGE SLIPS W/ NEW ONE.
2217 | 10/23/2022 | 23 Oct 0100 - 0500 | UTMN-1279 | SINO-45L | SPS | FOT | 4 | 4 | 903862 |  | BHA | 9665 | LWD | SPS LWD/DENSITY SENSOR FAILURE.
2238 | 10/23/2022 | 18 Oct 0045 - 0500 | ABQQ-454 | SINO21 | WI1 | FOT | 16.75 | 117 | 903708 |  | BHA | 7228 | MILL | WIS MILLING ASSY STUCK CROSS WINDOW.
2240 | 10/23/2022 | 22 Oct 0500 - 1200 | SFNY-1730 | SL-7 | BLH | FOT | 7 | 31 | 903885 |  | TF | 5148 | HGRL | 7" LINER UNABLE TO PASS OBSTRUCTION.
2242 | 10/23/2022 | 23 Oct 1830 - 2315 | AWTD-104001 | SND-2007 | RIG | FOT | 4.75 | 4.75 | 903851 |  | RR | 15792 | DWKS | WHILE PICK UP DRILL STRING FOUND DWKS LOW DRUM CLUTCH SLIPS.
2244 | 10/23/2022 | 23 Oct 0330 - 0500 | MNIF-867 | SND-2010 | RIG | FPMP | 1.5 | 1.5 | 903896 |  | RR | 3685 | MPMP | OBSERVED PRESSURE FLUCTUATION WHILE DRILLING.
2246 | 10/23/2022 | 23 Oct 1545 - 1645 | FDHL-146 | SP-165 | SPS | ISEQ | 1 | 1 | 903856 |  | BHA | 12774 | LWD | MWD DEPTH MALFUNCTION, TROOBLESHOOT AT MWD UNIT & FIXED SAME.
2248 | 10/23/2022 | 22 Oct 1630 - 1930 | DNAN-554002 | SP-262 | SPS | FOT | 14 | 26.5 | 903843 |  | BHA | 11834 | MWD | SPERRY LOST COMMUNICATION WITH THE RSS.
2250 | 10/23/2022 | 17 Oct 1515 - 0500 | QTIF-526 | SSA-101 | ARM | WC20 | 23 | 151 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
2252 | 10/23/2022 | 23 Oct 0000 - 0500 | HWYH-1217 | SSA-5859 | MSL | FOT | 5 | 5 | 903886 |  | TF | 14682 | SLICK | 3.795 DRIFT STICKING INSIDE LUBRICATOR, JAR FREE AND CHECK ROPE SOCKET, VISUAL INSPECT NOTHING OUTSTANDING
2254 | 10/23/2022 | 22 Oct 2130 - 2045 | AWTD-141400 | SSA-5892 | SWL | FOP | 15.75 | 23.25 | 903671 |  | JF | 16750 | PLT | SLB WIRELINE DATA COLLECTED ON RUN 1 WAS NOT ACCEPTED BY ARAMCO AND COMPANY SWITCHED TO HALLIBURTON WIRELINE
2255 | 10/23/2022 | 23 Oct 1430 - 1730 | UTMN-3193 | SSA-5970 | RIG | FOT | 3 | 3 | 903876 |  | RR | 1250 | TDS | FOUND DS MONORAIL LATCH PARTIALLY DISENGAGED
2257 | 10/23/2022 | 22 Oct 2300 - 1815 | UTMN-3193 | SSA-5970 | BHT | FOT | 9.75 | 15.25 | 903857 |  | TF | 4467 | BIT | OBSERVED 1300 PSI SUDDEN DROP IN PRESSURE, POH AND FOUND HUGHES BIT BALLED UP AND 1 X LOST NOZZLE.
2258 | 10/23/2022 | 23 Oct 1430 - 1730 | UTMN-3193 | SSA-5970 | RIG | FOT | 3 | 3 | 903876 |  | RR | 1250 | TDS | FOUND DS MONORAIL LATCH PARTIALLY DISENGAGED
2260 | 10/23/2022 | 23 Oct 2130 - 2330 | JAHQ-801 | ZPEC-2 | RIG | FOT | 2 | 2 | 903882 |  | RR | 526 | CRN | CRANE HOISTING SYSTEM NOT WORK
2262 | 10/24/2022 | 24 Oct 1200 - 1600 | QTIF-519 | 088TE | SPS | FOT | 3.5 | 3.5 | 903921 |  | BHA | 20420 | MWD | INTERMITTENT MWD SIGNAL, HALL. SPS TROUBLE SHOOTING TILL GET STEADY & STABLE MWD SIGNAL.
2264 | 10/24/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 57.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2266 | 10/24/2022 | 17 Oct 0200 - 0500 | UTMN-2321 | ADC-46L | ARM | UVLC | 18 | 149.5 | 903664 |  | LCIR | 9062 | NA | COMPLETE LOSS OF CIRCULATION @ 9,062' (LFDR)
2268 | 10/24/2022 | 21 Sep 0200 - 1600 | UTMN-3171 | ADC-55L | TK3 | LCRW | 11 | 728.25 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
2270 | 10/24/2022 | 24 Oct 1030 - 1200 | SDGM-1099 | ADC-56L | RIG | FOT | 1.5 | 1.5 | 903868 |  | RR | 3055 | MPMP | LINER WENT IN MUD PUMP #1 AND POP OFF VALVE IN MUD PUMP #3
2291 | 10/24/2022 | 24 Oct 1600 - 0300 | HRDH-2342 | DPS-5 | CAM | FOT | 6 | 6 | 903891 |  | WH | 1895 | WH | WHILE INSTALLING THE OF 24" SOW X 26-3/4" 3M CIW CSG HEAD, CIW REP OBSERVED A DEEP GROOVE INSIDE THE CSG HEAD LOCATED IN THE SEAL AREA WHERE THE CSG 18 5/8" CSG SLIP LAND. UPON INVESTIGATION, FOUND SHARP EDGE ON THE OUTER SURFACE OF THE TEST PLUG THAT CIW REP. FAILED TO NOTICE BEFORE PERFORM OFFLINE DRIFT. DECISION MADE AFTER CONTACTING THE OFFICE AND CIW BASE TO REPLACE DAMAGED CSG HEAD
2292 | 10/24/2022 | 23 Oct 1600 - 1300 | NJYN-18 | DPS-74 | HWP | FOT | 8 | 17.5 | 903887 |  | TF | 15595 | WLT | FAILURE HALL WIRE LINE 3.25" & 3" MECHANICAL CUTTER TO CUT 5.5" DP.
2294 | 10/24/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 15.5 | 110 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2295 | 10/24/2022 | 23 Oct 1600 - 1300 | NJYN-18 | DPS-74 | HWP | FOT | 8 | 17.5 | 903887 |  | TF | 15595 | WLT | FAILURE HALL WIRE LINE 3.25" & 3" MECHANICAL CUTTER TO CUT 5.5" DP.
2297 | 10/24/2022 | 23 Oct 1630 - 0500 | ZULF-2066 | ED-85A | RIG | UNKN | 7.25 | 8.5 | 903889 |  | HSEI | 13471 | NA | RIG SHUT DOWN DUE TO INCIDENT INVESTIGATION ON GOING.
2299 | 10/24/2022 | 24 Oct 1730 - 0500 | ZULF-2041 | EXL-IVA | BLH | FOT | 11.5 | 11.5 | 903900 |  | TF | 13160 | HGRL | DROPPED BALL TO SET LINER HANGER WITHOUT SUCCESS OR INDICATION. DROPPED 2ND BALL TO ACTIVATE HANGER WITHOUT SUCCESS. PRESSURE DIFFERENTIAL BETWEEN CIRCULATING AT SHOE AND BOTTOM 1,000 PSI LESS. POOH TO INVESTIGATE PRESSURE DROP.
2301 | 10/24/2022 | 24 Oct 1000 - 0200 | SDGM-1175 | NA-18S | HCB | FOT | 16 | 16 | 903898 |  | TF | 13365 | BP | COULDN'T PASS WITH HALLIBURTON 3.66" EZSV-BP.
2303 | 10/24/2022 | 06 Oct 1030 - 1700 | BRRI-562 | NADRU-1 | SLL | FOT | 11.5 | 18 | 903210 |  | TF | 244 | SLICK | TRY TO SET GAUGES AT 4900', NO SUCCESS, POOH HANGER STUCK AT TRSSV @ 244'. LEFT FISH MEMORY GAUES & HANGER,RECOVER FISH, RUN & SET DIGITAL HANGER.
2305 | 10/24/2022 | 24 Oct 1815 - 0500 | SHHM-571002 | NBR-16S | RIG | FOT | 10.75 | 10.75 | 903920 |  | RR | 11139 | DWKS | DRAWWORKS AND TOP DRIVE SYSTEM WOULD NOT FUNCTION PROPERLY AGAIN (KEEPS STALLING OUT)
2307 | 10/24/2022 | 24 Oct 0500 - 0200 | SDGM-1223 | NBR-196S | ITS | HERR | 21 | 21 | 903917 |  | JF | 4860 | CTRQ | ATTEMPT TO DRIFT TUBING WITH THE 3.795" DRIFT, DRIFT WOULD NOT PASS 3527' RKB ( JOINT # 33). POOH W/ SLICKLINE AND RIH W/ 3.70" DRIFT. DRIFTED DOWN TO X-OVER IN HALLIBURTON ASSEMBLY AT 151 FEET RKB. POOH W/ 3.70" DRIFT AND RIH 3.75" DRIFT TO 3.527' WHERE DRIFT HUNG UP. POOH W/ 3.75" DRIFT.
2309 | 10/24/2022 | 24 Oct 2145 - 0015 | QTIF-503 | NBR-263S | RIG | HERR | 2.5 | 2.5 | 903895 |  | BB | 128 | BIT | WHILE CLEANING CLAY OFF BIT FOUND 13 TON SHACKLE STUCK INSIDE THE CLAY ON THE BIT, INSPECTED BIT NO DAMAGE TO BIT, CLEANED BIT TRIP IN HOLE AND BACK TO DRILLING,
2311 | 10/24/2022 | 24 Oct 0500 - 0800 | HRDH-2313 | NBR-591S | ARM | PSSW | 3 | 3 | 903916 |  | STUK | 8984 | NA | STRING STUCK @ 8984' (3 ' OFF-BTM) WHILE BACKREAMING PRIOR TO MAKE CONNECTION.
2313 | 10/24/2022 | 24 Oct 1015 - 1530 | SHYB-65 | PA-529S | SJT | FOT | 5.25 | 5.25 | 903924 |  | BHA | 1000 | CTAC | TAQA/SANJEL COILED TUBING RIH WITH NESR 2.72 SHIFTING TOOL TO 1,000 FT, DURING FUNCTION AND BREAK CIRCULATION TEST WITH 0.3 PRESSURE UP TO 3,000 PSI HOLD. PULL OUT TO SURFACE FIND SOLT PLUGED BHA BETWEEN HALLIBURTON SHIFTING TOOL.
2315 | 10/24/2022 | 24 Oct 1730 - 1930 | UTMN-3700 | PA-622S | ITS | FOT | 2 | 2 | 903899 |  | TF | 3033 | CRT | BOTTOM PART OF CRT PACKER RUBBER LEFT STUCK INSIDE CSG JOINT.
2317 | 10/24/2022 | 23 Oct 1600 - 1600 | HSBH-68 | RM-74A | RIG | FOT | 11 | 24 | 903860 |  | RR | 9797 | CSYS | PIT WITH MIX WATER FOR LEAD CEMENT SLURRY LEAKING, DUMP MIX WATER AND FIX THE LEAKS.
2319 | 10/24/2022 | 24 Oct 0330 - 0500 | MZLJ-326 | SIN30L | ARM | STOP | 1.5 | 1.5 | 903923 |  | WO | 237 | NA | BREAKDOWN IN WATER PIT CORNER WHICH ALLOWED ALL WATER TO DRAIN OUTSIDE WATER PIT.
2321 | 10/24/2022 | 24 Oct 0500 - 2100 | ZUML-33 | SINO-18 | ARM | MATL | 16 | 16 | 903888 |  | WO | 0 | NA | MATERIALS HAVE NOT BEEN DELIVERED BY TRANSPORTATION FOR SPUDDING OPERATIONS AS REQUIRED AND DESIGNED BY THE DRILLING RIG SUPPLY SYSTEM. ALL MATERIAL WAS REQUESTED FOR DELIVERY TO SINO-18 ON OCTOBER 14TH.
2323 | 10/24/2022 | 24 Oct 0130 - 0500 | HWYH-318 | SINO-37L | ITS | FOT | 3.5 | 3.5 | 903894 |  | TF | 0 | TTRQ | HAD POWER UNIT FAILURE DUE TO CRACK AT TOP CONNECTION OF OIL TANK.
2325 | 10/24/2022 | 23 Oct 0100 - 0500 | UTMN-1279 | SINO-45L | SPS | FOT | 24 | 28 | 903862 |  | BHA | 9665 | LWD | SPS LWD/DENSITY SENSOR FAILURE.
2327 | 10/24/2022 | 24 Oct 1200 - 1500 | FDHL-122 | SINO-7N | SWT | SRVC | 3 | 3 | 903901 |  | WO | 0 | NA | LOST TIME ON SLB FLOWBACK, DUE TO EXCESS TIME TO COMPLETE R/U & PT THE TEST PACKAGE.
2329 | 10/24/2022 | 18 Oct 0045 - 0500 | ABQQ-454 | SINO21 | WI1 | FOT | 21 | 135.5 | 903708 |  | BHA | 7228 | MILL | WIS MILLING ASSY STUCK CROSS WINDOW.
2331 | 10/24/2022 | 24 Oct 0500 - 0500 | UTMN-3095 | SND-2006 | SPS | UDWL | 24 | 24 | 903922 |  | DD | 12044 | RSS | UNABLE TO BUILD AS PER DIRECTIONAL PLAN#4
2333 | 10/24/2022 | 23 Oct 0330 - 0800 | MNIF-867 | SND-2010 | RIG | FPMP | 3 | 4.5 | 903896 |  | RR | 3685 | MPMP | OBSERVED PRESSURE FLUCTUATION WHILE DRILLING.
2335 | 10/24/2022 | 24 Oct 2200 - 0500 | HZEM-162414 | SP-257 | CAM | FOT | 7 | 7 | 903870 |  | WH | 21706 | WH | FAIL TO SET PACK-OFF SEAL.
2337 | 10/24/2022 | 24 Oct 0100 - 0500 | DNAN-554002 | SP-262 | SPS | FOT | 4 | 4 | 903893 |  | BHA | 15023 | RSS | MWD FAILURE. NO COMMUNICATION.
2339 | 10/24/2022 | 24 Oct 0800 - 0900 | MNIF-198 | SP-306 | WCR | FOT | 1 | 1 | 903890 |  | TF | 8478 | CTRQ | REPLACE SPIDER SLIPS
2341 | 10/24/2022 | 17 Oct 1515 - 0500 | QTIF-526 | SSA-101 | ARM | WC20 | 23.25 | 174.25 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
2343 | 10/24/2022 | 23 Oct 0000 - 0930 | HWYH-1217 | SSA-5859 | MSL | FOT | 4.5 | 9.5 | 903886 |  | TF | 14682 | SLICK | 3.795 DRIFT STICKING INSIDE LUBRICATOR, JAR FREE AND CHECK ROPE SOCKET, VISUAL INSPECT NOTHING OUTSTANDING
2345 | 10/24/2022 | 24 Oct 0130 - 0330 | HRDH-1983 | SSA-5962 | RIG | FOT | 2 | 2 | 903892 |  | RR | 10541 | DWKS | REPAIR DRAWWORKS LOW CLATCH CHAIN.
2347 | 10/25/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 81.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2349 | 10/25/2022 | 17 Oct 0200 - 1745 | UTMN-2321 | ADC-46L | ARM | UVLC | 12.75 | 162.25 | 903664 |  | LCIR | 9062 | NA | COMPLETE LOSS OF CIRCULATION @ 9,062' (LFDR)
2351 | 10/25/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 21 | 749.25 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
2367 | 10/25/2022 | 24 Oct 1300 - 1815 | HRDH-2354 | ADES-798 | ARM | UXDF | 13.25 | 29.25 | 903904 |  | LCIR | 13387 | NA | SEVERE LOSSES IN UNZA FORMATION, CURE LOSSES WITH LCM.
2369 | 10/25/2022 | 25 Oct 0600 - 1800 | MRJN-900 | ADM-337 | ARM | WTHR | 12 | 12 | 903956 |  | WON | 7155 | NA | WOW; WAIT ON FAVOURABLE WIND SPEED FOR FLOW BACK OPS
2371 | 10/25/2022 | 25 Oct 0515 - 0715 | SFNY-1263 | ADM-657 | RIG | FOT | 2 | 2 | 903938 |  | RR | 1287 | TDS | TDS RPM DOWN, TROUBLESHOOTING, CHANGED POWER SUPPLY CARD AND POTENTIAL TRANSFORMER INSIDE VFD UNIT. TESTED RPM-OK.
2373 | 10/25/2022 | 25 Oct 1500 - 0500 | SFNY-4260 | AOD-1 | RIG | FOT | 13 | 13 | 903906 |  | RR | 5230 | DWKS | WHILE RAISING THE BLOCKS TO PICK UP A STAND, THE E-STOP ENGAGED ON DRAWWORKS CAUSING THE DRUM SUDDENLY STOP AND DRILL LINE ON THE DRUM TO GET SLACK IN IT.
2375 | 10/25/2022 | 22 Oct 1645 - 0500 | MRJN-121 | ARO-2001 | WCS | DSFT | 13.75 | 24.5 | 903768 | 903593 | JF | 10044 | PAK | RIH TO SET 4-1/2" WFD 4-1/2" PERMANENT BRIDGE PLUG. BRIDGE PLUG UNABLE TO SET IN 4-1/2" LINER
2376 | 10/25/2022 | 25 Oct 2115 - 2315 | SFNY-1157 | ARO-3003 | RIG | FOT | 2 | 2 | 903986 |  | RR | 0 | DWKS | TROUBLE SHOOT LOW CLUTCH NOT WORKING. FOUND RELAY VALVE NOT FUNCTIONING PROPERLY.
2378 | 10/25/2022 | 25 Oct 1130 - 1730 | SFNY-1157 | ARO-3003 | RIG | FOT | 6 | 6 | 903985 |  | RR | 0 | FL | DUMP VALVE CLOGGED ON SAND TRAP #1
2379 | 10/25/2022 | 25 Oct 2115 - 2315 | SFNY-1157 | ARO-3003 | RIG | FOT | 2 | 2 | 903986 |  | RR | 0 | DWKS | TROUBLE SHOOT LOW CLUTCH NOT WORKING. FOUND RELAY VALVE NOT FUNCTIONING PROPERLY.
2380 | 10/25/2022 | 25 Oct 2100 - 2300 | SDGM-1111 | DPS-46 | SLL | FOT | 2 | 2 | 903982 |  | TF | 11902 | SLICK | SLB SLICKLINE HYDRAULICS HOSES RUPTURED,
2382 | 10/25/2022 | 25 Oct 1700 - 0130 | SDGM-1111 | DPS-46 | SCM | FOT | 4.5 | 4.5 | 903981 |  | TF | 11808 | PUMP | UNABLE TO PRESS. TEST SLB PUMPER, LEAKING BACK THROUGH PUMP,
2383 | 10/25/2022 | 25 Oct 2100 - 2300 | SDGM-1111 | DPS-46 | SLL | FOT | 2 | 2 | 903982 |  | TF | 11902 | SLICK | SLB SLICKLINE HYDRAULICS HOSES RUPTURED,
2385 | 10/25/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 23.5 | 133.5 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2387 | 10/25/2022 | 23 Oct 1630 - 0500 | ZULF-2066 | ED-85A | RIG | UNKN | 24 | 29.5 | 903889 |  | HSEI | 13471 | NA | RIG SHUT DOWN DUE TO INCIDENT INVESTIGATION ON GOING.
2389 | 10/25/2022 | 25 Oct 1845 - 2245 | MRJN-2004 | ENSCO-76 | SCB | FOT | 4 | 4 | 903979 |  | TF | 0 | RBP | ATTEMPT TO SET 7" RBP ON SLICK LINE AT 500 FT, NO SUCCESS, POH TO SURFACE, REPLACED 7" RBP
2391 | 10/25/2022 | 25 Oct 1900 - 2015 | QTIF-503 | NBR-263S | RIG | FOT | 1.25 | 1.25 | 903977 |  | RR | 374 | TDS | OBSERVED HYDRAULIC LEAK FROM TDS GRABBER BOX, FIX SAME MEANWHILE CIRC
2393 | 10/25/2022 | 25 Oct 1800 - 0500 | HRDH-2313 | NBR-591S | RIG | FOT | 11 | 11 | 903905 |  | RR | 9298 | MPMP | OBSERVE MUD PUMP #1 CRANK-SHAFT BEARING FAILURE WHILE MUD PUMP #3 UNDER REPAIR DUE TO CROSS-HEAD BARING FAILURE.
2395 | 10/25/2022 | 25 Oct 0530 - 0600 | HSBH-68 | RM-74A | RIG | SRVC | .5 | .5 | 903902 |  | WO | 9797 | NA | SAFETY STAND DOWN, DISCUSS RECENT MINOT FIRST AID INCIDENT.
2397 | 10/25/2022 | 24 Oct 0330 - 1530 | MZLJ-326 | SIN30L | ARM | STOP | 10.5 | 12 | 903923 |  | WO | 237 | NA | BREAKDOWN IN WATER PIT CORNER WHICH ALLOWED ALL WATER TO DRAIN OUTSIDE WATER PIT.
2399 | 10/25/2022 | 25 Oct 0730 - 0500 | UTMN-1245 | SINO-26 | RIG | FOT | 21.5 | 21.5 | 903991 |  | TF | 6100 | SLIPS | HAD COMMUNICATION BETWEEN DP SIDE & BACK SIDE WITH PREESURE INCREASE IN DP.
2401 | 10/25/2022 | 25 Oct 0330 - 0500 | HRDH-1542 | SINO-33L | BCR | FOT | 1.5 | 1.5 | 903988 |  | TF | 1600 | PEL | DISCONNECTION ON THE SAFETY SUB JOINT
2403 | 10/25/2022 | 24 Oct 0130 - 0830 | HWYH-318 | SINO-37L | ITS | FOT | 3.5 | 7 | 903894 |  | TF | 0 | TTRQ | TROUBLESHOOTING ON ITS POWER UNIT.
2405 | 10/25/2022 | 23 Oct 0100 - 0630 | UTMN-1279 | SINO-45L | SPS | FOT | 1.5 | 29.5 | 903862 |  | BHA | 9665 | LWD | SPS LWD/DENSITY SENSOR FAILURE.
2407 | 10/25/2022 | 18 Oct 0045 - 1230 | ABQQ-454 | SINO21 | WI1 | FOT | 7.5 | 143 | 903708 |  | BHA | 7228 | MILL | WIS MILLING ASSY STUCK CROSS WINDOW.
2409 | 10/25/2022 | 24 Oct 0500 - 0500 | UTMN-3095 | SND-2006 | SPS | UDWL | 24 | 48 | 903922 |  | DD | 12044 | RSS | UNABLE TO BUILD AS PER DIRECTIONAL PLAN#4
2411 | 10/25/2022 | 25 Oct 1330 - 0200 | SAHB-101 | SND-2009 | RIG | FOT | 12.5 | 12.5 | 903990 |  | RR | 14682 | TDS | TDS HAS DRIVE FAULT. TROUBLESHOOTING TDS. > WHILE ROTATING TORQUE WAS SPIKE SUDDENLY AND ROTARY STOP. TRIED WITH DIFFERENT RPM, SAME ISSUE.
2413 | 10/25/2022 | 25 Oct 0500 - 0800 | MNIF-867 | SND-2010 | RIG | FPMP | 3 | 3 | 903903 |  | RR | 4762 | MPMP | REPAIR VALVES & SEATS IN MUD PUMP#2
2415 | 10/25/2022 | 24 Oct 2200 - 1430 | HZEM-162414 | SP-257 | CAM | FOT | 5 | 12 | 903870 |  | WH | 21706 | WH | FAIL TO SET PACK-OFF SEAL.
2417 | 10/25/2022 | 24 Oct 0100 - 0500 | DNAN-554002 | SP-262 | SPS | FOT | 20.75 | 24.75 | 903893 |  | BHA | 15023 | MWD | MWD FAILURE. NO COMMUNICATION.
2419 | 10/25/2022 | 17 Oct 1515 - 0500 | QTIF-526 | SSA-101 | ARM | WC20 | 23.75 | 198 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
2421 | 10/25/2022 | 25 Oct 0130 - 0500 | UTMN-3044 | SSA-5964 | HCO | DSFT | 3.5 | 3.5 | 903989 |  | JF | 10010 | RTTS | HALL. RTTS FAILED WHILE TESTING THE WELL BORE TO 5,200 PSI.
2423 | 10/25/2022 | 25 Oct 0645 - 0745 | UTMN-3193 | SSA-5970 | GOC | FOT | 1 | 1 | 903980 |  | TF | 2643 | CRT | AL-GHAITH SPIDER SLIPS UNABLE TO DISENGAGE FROM CSG JT.
2425 | 10/25/2022 | 25 Oct 0645 - 0300 | MRJN-3022 | V141A | ULT | IBSL | 20.25 | 20.25 | 903978 |  | LROP | 4648 | BIT | LOW PENETRATION RATE, DECISION MADE TO POOH AND CHECK BIT CONDITION, BIT CAME OUT DAMAGED (RING OUT)
2427 | 10/25/2022 | 25 Oct 0700 - 1900 | MRJN-1002 | WCL-83 | RIG | FOT | 12 | 12 | 903987 |  | RR | 6254 | MPMP | UNABLE TO DRILL DUE TO MUD PUMPS FAILURE
2429 | 10/26/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 105.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2431 | 10/26/2022 | 26 Oct 1730 - 2030 | ANDR-1006 | ADC-31 | RIG | FOT | 3 | 3 | 904021 |  | RR | 10957 | CSYS | POOH TO SHOE. CHANGE ROTARY HOSE & P/T SAME TO 4000 PSI OK
2433 | 10/26/2022 | 21 Sep 0200 - 0500 | UTMN-3171 | ADC-55L | TK3 | LCRW | 24 | 773.25 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
2435 | 10/26/2022 | 26 Oct 1445 - 0500 | ABHD-183 | ADC-58L | TK3 | SCSG | 14.25 | 14.25 | 903963 |  | STUK | 9560 | LINR | 7" LINER WHILE RIH ON DP GOT STUCK
2436 | 10/26/2022 | 26 Oct 0545 - 0500 | HWYH-1287 | ADC-59L | TK3 | ETRQ | 10 | 10 | 903944 |  | DD | 6017 | MMOT | OFF/ON BOTTOM PRESSURES INCREASED BY 1300 PSI.
2438 | 10/26/2022 | 26 Oct 1800 - 2100 | HWYH-1287 | ADC-59L | RIG | FOT | 3 | 3 | 903943 |  | RR | 6544 | MPMP | CUMULATIVE NPT ON ADC FOR MUD PUMPS REPAIR. REPAIR ON CROSS HEAD OF MP N#3.
2439 | 10/26/2022 | 26 Oct 0545 - 0500 | HWYH-1287 | ADC-59L | TK3 | ETRQ | 10 | 10 | 903944 |  | DD | 6017 | MMOT | OFF/ON BOTTOM PRESSURES INCREASED BY 1300 PSI.
2463 | 10/26/2022 | 25 Oct 0500 - 0500 | MRJN-3017 | ADM-339 | ARN | STBH | 24 | 48 | 903957 |  | STUK | 7668 | BHA | DRILL STRING BECAME STUCK DURING CONNECTION. ATTEMPT TO FREE THE SAME.
2465 | 10/26/2022 | 25 Oct 1500 - 0500 | SFNY-4260 | AOD-1 | RIG | FOT | 22.75 | 35.75 | 903906 |  | RR | 5230 | DWKS | WHILE THE DRILLER WAS COMING UP WITH THE BLOCKS TO PICK UP A STAND, THE E-STOP ENGAGED ON DRAWWORKS CAUSING THE DRUM TO SUDDENLY STOP AND DRILL LINE ON THE DRUM TO GET SLACK IN IT.
2467 | 10/26/2022 | 14 Oct 1830 - 1045 | MRJN-121 | ARO-2001 | HCM | CEDE | 5.75 | 209.5 | 903593 |  | JF | 11700 | NA | CEMENT PLUG FAILURE, CEMENT STILL SOFT 44 HRS AFTER SET THE PLUG.
2468 | 10/26/2022 | 25 Oct 2100 - 1000 | SDGM-1111 | DPS-46 | SLL | FOT | 4 | 6 | 903982 |  | TF | 11902 | SLICK | SLB SLICKLINE HYDRAULICS HOSES RUPTURED,
2470 | 10/26/2022 | 25 Oct 0700 - 1400 | SDGM-1111 | DPS-46 | SCM | FOT | 5 | 23.75 | 903981 |  | TF | 11808 | PUMP | UNABLE TO PRESS. TEST DUE TO SLB PUMPER, LEAKING BACK THROUGH PUMP & VALVES.
2471 | 10/26/2022 | 25 Oct 2100 - 1000 | SDGM-1111 | DPS-46 | SLL | FOT | 4 | 6 | 903982 |  | TF | 11902 | SLICK | SLB SLICKLINE HYDRAULICS HOSES RUPTURED,
2473 | 10/26/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 23.5 | 166.5 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2475 | 10/26/2022 | 23 Oct 1630 - 0500 | ZULF-2066 | ED-85A | RIG | UNKN | 24 | 53.5 | 903889 |  | HSEI | 13471 | NA | RIG SHUT DOWN DUE TO INCIDENT INVESTIGATION ON GOING.
2477 | 10/26/2022 | 26 Oct 1930 - 0215 | ABSF-128 | EXL-IA | BAW | FOT | 6.25 | 6.25 | 904022 |  | TF | 5700 | WLT | HIGH CURRENT IN BAKER MREX TOOL.
2479 | 10/26/2022 | 26 Oct 0500 - 1400 | SDGM-1223 | NBR-196S | EX1 | FOT | 9 | 9 | 904016 |  | TF | 12633 | PLUGN | ATTEMPTED SEVERAL TIMES TO SET PR PLUG IN LOWER R-NIPPLE AT 11843' WITHOUT SUCCESS. DECISION MADE TO POOH W/ PR PLUG TO CHECK TOOLS. WHILE PULLING OUT OF THE HOLE AT 5825 ' OBSERVED SUDDEN INCREASE IN STRING WEIGHT FROM 600 LBS TO 900 LBS FOLLOWED BY A DROP IN STRING TO 300 LBS. CONTINUE TO POOH TO SURFACE AND FOUND 25 FT. FISH LEFT IN HOLE CONSISTING OF SLICKLINE ROPE SOCKET, 13 FT. STEM BAR, MECHANICAL JARS, X/O, PR PLUG RUNNING TOOL AND PR PLUG.
2481 | 10/26/2022 | 26 Oct 0730 - 0930 | QTIF-503 | NBR-263S | RIG | HERR | 2 | 2 | 904017 |  | FISH | 0 | BHA | CREW DID NOT PAY ATTENTION ABOUT TOTCO BAR WHICH RESULTED IN TOTCO BAR DROPPED IN HOLE.
2483 | 10/26/2022 | 25 Oct 1800 - 0500 | HRDH-2313 | NBR-591S | RIG | FOT | 24 | 35 | 903905 |  | RR | 9298 | MPMP | OBSERVE MUD PUMP #1 CRANK-SHAFT BEARING FAILURE WHILE MUD PUMP #3 UNDER REPAIR DUE TO CROSS-HEAD BARING FAILURE.
2485 | 10/26/2022 | 26 Oct 1630 - 1730 | ANDR-1018 | NBR-654S | RIG | LHFL | 1 | 1 | 904019 |  | RR | 430 | HSYS | TDS COUNTERBALANCE HYDRAULIC SUPPLY HOSE LEAKING
2487 | 10/26/2022 | 25 Oct 2245 - 0500 | HRDH-1976 | PA-218S | ARM | WC20 | 24 | 30.25 | 904018 |  | WCNT | 11517 | NA | UN-AVOIDABLE WELL CONTROL FROM JILH HIGH PRESSURE FORMATION.
2489 | 10/26/2022 | 25 Oct 0730 - 1200 | UTMN-1245 | SINO-26 | RIG | FOT | 7 | 28.5 | 903991 |  | TF | 6100 | SLIPS | HAD COMMUNICATION BETWEEN DP SIDE & BACK SIDE WITH PREESURE INCREASE IN DP.
2491 | 10/26/2022 | 25 Oct 0330 - 1400 | HRDH-1542 | SINO-33L | BLH | FOT | 9 | 10.5 | 903988 |  | TF | 1600 | PBR | DISCONNECTION ON THE SAFETY SUB JOINT
2493 | 10/26/2022 | 26 Oct 1630 - 0500 | SHYB-449 | SINO-46L | BHI | FOT | 12.5 | 12.5 | 904023 |  | BHA | 7718 | RSS | ATTEMPTED TO OPEN RSS RIBS WITHOUT SUCCESS ,TROUBLESHOOTING NO SUCCESS.
2495 | 10/26/2022 | 26 Oct 1515 - 0500 | HWYH-1286 | SINO-47 | ULT | IBSL | 13.75 | 13.75 | 904020 |  | LROP | 7523 | BIT | POOH & CHANGE ULTERRA BIT FOR LOW ROP.
2497 | 10/26/2022 | 24 Oct 0500 - 0500 | UTMN-3095 | SND-2006 | SPS | UDWL | 24 | 72 | 903922 |  | DD | 12044 | RSS | UNABLE TO BUILD AS PER DIRECTIONAL PLAN#4
2499 | 10/26/2022 | 26 Oct 2130 - 2230 | HRDH-1291 | SND-2008 | RIG | LHFL | 1 | 1 | 903999 |  | RR | 13538 | HSYS | LEAK ON TDS HPU HOSE
2501 | 10/26/2022 | 24 Oct 0100 - 0930 | DNAN-554002 | SP-262 | SPS | FOT | 4 | 28.75 | 903893 |  | BHA | 15023 | MWD | MWD FAILURE. NO COMMUNICATION.
2503 | 10/26/2022 | 17 Oct 1515 - 1800 | QTIF-526 | SSA-101 | ARM | WC20 | 13 | 211 | 903681 |  | WCNT | 9249 | NA | BACKGROUND GASES INCREASED QUICKLY TO 70%, STOP PUMP FOR FLOW CHECK,OBSERVE WELL FLOWING W/ GAS BUBBLES ,CLOSE BOP,SECURE WELL,CASING SHUT IN PRESSUER 200 PSI .PUMP FLOAT,HAD DRILL PIPE PRESSURE;150 PSI.
2505 | 10/26/2022 | 25 Oct 0130 - 0500 | UTMN-3044 | SSA-5964 | HCO | DSFT | 24 | 27.5 | 903989 |  | JF | 10010 | CHAMP | HALL 9-5/8" RTTS PKR FAILED WHILE TESTING THE WELLBORE TO 5,200 PSI.
2507 | 10/26/2022 | 26 Oct 1815 - 2030 | MRJN-1002 | WCL-83 | BHI | FOT | 2.25 | 2.25 | 903964 |  | BHA | 7531 | LWD | LOST COMMUNICATION WITH MAGTRAK (NO REAL TIME DATA). TROUBLE SHOT BUT NO SUCCESS.
2509 | 10/27/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 129.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2510 | 10/27/2022 | 27 Oct 1930 - 0500 | UTMN-3171 | ADC-55L | SDM | FOT | 9.5 | 9.5 | 904028 |  | BHA | 12742 | RSS | LOST COMMUNICATION WITH RSS, DECISION TAKEN TO POH TO CHANGE RSS TOOL.
2512 | 10/27/2022 | 21 Sep 0200 - 1230 | UTMN-3171 | ADC-55L | TK3 | LCRW | 7.5 | 780.75 | 902553 |  | STUK | 12503 | STRG | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC
2513 | 10/27/2022 | 27 Oct 1930 - 0500 | UTMN-3171 | ADC-55L | SDM | FOT | 9.5 | 9.5 | 904028 |  | BHA | 12742 | RSS | LOST COMMUNICATION WITH RSS, DECISION TAKEN TO POH TO CHANGE RSS TOOL.
2515 | 10/27/2022 | 26 Oct 1445 - 0500 | ABHD-183 | ADC-58L | TK3 | SCSG | 23 | 37.25 | 903963 |  | STUK | 9560 | LINR | 7" LINER GOT STUCK AFTER CONNECTION.
2516 | 10/27/2022 | 26 Oct 0545 - 0115 | HWYH-1287 | ADC-59L | TK3 | ETRQ | 17.25 | 27.25 | 903944 |  | DD | 6017 | MMOT | OFF/ON BOTTOM PRESSURES INCREASED BY 1300 PSI.
2518 | 10/27/2022 | 26 Oct 1800 - 2130 | HWYH-1287 | ADC-59L | RIG | FOT | 3 | 6 | 903943 |  | RR | 6544 | MPMP | CUMULATIVE NPT ON ADC FOR MUD PUMPS REPAIR. REPAIR ON CROSS HEAD OF MP N#3.
2519 | 10/27/2022 | 26 Oct 0545 - 0115 | HWYH-1287 | ADC-59L | TK3 | ETRQ | 17.25 | 27.25 | 903944 |  | DD | 6017 | MMOT | OFF/ON BOTTOM PRESSURES INCREASED BY 1300 PSI.
2534 | 10/27/2022 | 27 Oct 1400 - 1830 | MRJN-57 | ADM-262 | RIG | FOT | 4.5 | 4.5 | 904039 |  | BOP | 0 | BOP | UNABLE TO PRESSURE TEST ANNULAR WITH 2-3/8" DP. PREMATURE FAILURE, EXCHANGE SAME.
2535 | 10/27/2022 | 27 Oct 1330 - 0500 | MRJN-3017 | ADM-339 | RIG | UNKN | 15.5 | 15.5 | 904056 |  | HSEI | 7524 | NA | AD WAS INSTRUCTED TO GREASE THE CHOKE MANIFOLD. WHILE PUMPING GREASE IT BECAME HARD TO PUT THE GREASE INTO THE VALVE. IP ATTEMPTED TO REMOVE THE GREASE FITTING WHEN THE GREASE FITTING EJECTED FROM THE VALVE BODY AND HIT HIM IN THE LEFT HAND CAUSING INJURY.
2537 | 10/27/2022 | 25 Oct 0500 - 1330 | MRJN-3017 | ADM-339 | ARN | STBH | 8.5 | 56.5 | 903957 |  | STUK | 7668 | BHA | DRILL STRING BECAME STUCK DURING CONNECTION. ATTEMPT TO FREE THE SAME.
2538 | 10/27/2022 | 27 Oct 1330 - 0500 | MRJN-3017 | ADM-339 | RIG | UNKN | 15.5 | 15.5 | 904056 |  | HSEI | 7524 | NA | AD WAS INSTRUCTED TO GREASE THE CHOKE MANIFOLD. WHILE PUMPING GREASE IT BECAME HARD TO PUT THE GREASE INTO THE VALVE. IP ATTEMPTED TO REMOVE THE GREASE FITTING WHEN THE GREASE FITTING EJECTED FROM THE VALVE BODY AND HIT HIM IN THE LEFT HAND CAUSING INJURY.
2540 | 10/27/2022 | 25 Oct 1500 - 1330 | SFNY-4260 | AOD-1 | RIG | FOT | 7.5 | 43.25 | 903906 |  | RR | 5230 | DWKS | WHILE THE DRILLER WAS COMING UP WITH THE BLOCKS TO PICK UP A STAND, THE E-STOP ENGAGED ON DRAWWORKS CAUSING THE DRUM TO SUDDENLY STOP AND DRILL LINE ON THE DRUM TO GET SLACK IN IT.
2542 | 10/27/2022 | 27 Oct 0500 - 0700 | MRJN-121 | ARO-2001 | RIG | HERR | 2 | 2 | 903946 |  | FISH | 0 | STRG | WHILE POOH THE RIG CREW WAS UTILIZING A 3' PIECE OF 1/2" RUBBER HOSE TO STRIP DP INSTEAD OF INSTALLING THE PROPER PIPE WIPER. FLOORHAND LOST HIS GRIP AND WIPER HOSE DROPPED INTO WELLBORE.
2544 | 10/27/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 12.75 | 179.25 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2546 | 10/27/2022 | 27 Oct 1945 - 2145 | ABSF-128 | EXL-IA | BAW | FOT | 2 | 2 | 904035 |  | TF | 6420 | WLT | MREX TOOL RECORDS ABNORMAL HIGH POROSITY READINGS.
2548 | 10/27/2022 | 24 Oct 1730 - 2200 | ZULF-2041 | EXL-IVA | BLH | FOT | 17 | 76.5 | 903900 |  | TF | 13160 | HGRL | DROPPED BALL TO SET LINER HANGER WITHOUT SUCCESS OR INDICATION. DROPPED 2ND BALL TO ACTIVATE HANGER WITHOUT SUCCESS. PRESSURE DIFFERENTIAL BETWEEN CIRCULATING AT SHOE AND BOTTOM 1,000 PSI LESS. POOH TO INVESTIGATE PRESSURE DROP.
2550 | 10/27/2022 | 27 Oct 2045 - 2145 | QTIF-503 | NBR-263S | RIG | UNKN | 1 | 1 | 904034 |  | HSEI | 400 | NA | WHILE M/U 5-1/2" HWDP WITH TDS & A BACK UP TONG, THE STRG ROTATE SUDDENLY CAUSING A SLIGHT BENT TO THE TOOL JT DUE TO SNUB LINE WAS NOT USED, NO PERSONNEL WAS IN THE LINE OF FIRE & NO INJURY. - STOP OPERATION, HELD SAFETY STAND DOWN MEETING WITH ALL PERSONNEL ON THE RIG FLOOR. - L/D DAMAGED JT & REPLACED WITH NEW ONE.
2551 | 10/27/2022 | 27 Oct 0500 - 1030 | HRDH-2313 | NBR-591S | RIG | FOT | 5.5 | 5.5 | 904027 |  | RR | 9298 | DWKS | EATON BRAKE JOYSTICK FAILURE.
2553 | 10/27/2022 | 25 Oct 1800 - 1400 | HRDH-2313 | NBR-591S | RIG | FOT | 3.5 | 38.5 | 903905 |  | RR | 9298 | MPMP | OBSERVE MUD PUMP #1 CRANK-SHAFT BEARING FAILURE WHILE MUD PUMP #3 UNDER REPAIR DUE TO CROSS-HEAD BARING FAILURE.
2554 | 10/27/2022 | 27 Oct 0500 - 1030 | HRDH-2313 | NBR-591S | RIG | FOT | 5.5 | 5.5 | 904027 |  | RR | 9298 | DWKS | EATON BRAKE JOYSTICK FAILURE.
2556 | 10/27/2022 | 27 Oct 2245 - 2345 | TINT-91 | NBR-783S | RIG | FOT | 1 | 1 | 904036 |  | RR | 11452 | MPMP | DISCHARGE LINE GATE VALVE FOR MP#2 WASHOUT, WASHOUT GASKET ON MP #1
2558 | 10/27/2022 | 27 Oct 1600 - 2000 | UTMN-3700 | PA-622S | RIG | ISEQ | 4 | 4 | 904057 |  | BOP | 3030 | BOP | PERFORMED ACCUMULATOR FUNCTIONAL TEST, OBSERVED THE 30" X 1K ANNULAR BOPE CLOSING TIME (70 SEC) EXCEEDING SAUDI ARAMCO REQUIREMENT (45 SEC) AS PER WELL CONTROL MANUAL. CORRECTIVE ACTION: CHANGE & TEST 30" X 1K ANNULAR BOPE.
2560 | 10/27/2022 | 27 Oct 0430 - 0500 | UTMN-1245 | SINO-26 | HUD | FOT | .5 | .5 | 904038 |  | TF | 9800 | MPD | HALL MPD POWER SHUT DOWN
2561 | 10/27/2022 | 27 Oct 0400 - 0500 | SHYB-449 | SINO-46L | BHI | FOT | 1 | 1 | 904037 |  | BHA | 9083 | RSS | LOST COMMUNICATION WITH AUTO-TRACK, AUTO-TRACK SHOWING 0 READING & NOT SENDING SIGNALS TO MWD.
2563 | 10/27/2022 | 26 Oct 1630 - 1215 | SHYB-449 | SINO-46L | BHI | FOT | 7.25 | 19.75 | 904023 |  | BHA | 7718 | RSS | ATTEMPTED TO OPEN RSS RIBS WITHOUT SUCCESS ,TROUBLESHOOTING NO SUCCESS.
2564 | 10/27/2022 | 27 Oct 0400 - 0500 | SHYB-449 | SINO-46L | BHI | FOT | 1 | 1 | 904037 |  | BHA | 9083 | RSS | LOST COMMUNICATION WITH AUTO-TRACK, AUTO-TRACK SHOWING 0 READING & NOT SENDING SIGNALS TO MWD.
2566 | 10/27/2022 | 26 Oct 1515 - 0600 | HWYH-1286 | SINO-47 | ULT | IBSL | 1 | 14.75 | 904020 |  | LROP | 7523 | BIT | POOH & CHANGE ULTERRA BIT FOR LOW ROP.
2568 | 10/27/2022 | 24 Oct 0500 - 0500 | UTMN-3095 | SND-2006 | SPS | UDWL | 24 | 96 | 903922 |  | DD | 12044 | RSS | UNABLE TO BUILD AS PER DIRECTIONAL PLAN#4
2570 | 10/27/2022 | 26 Oct 0415 - 0500 | HRDH-1291 | SND-2008 | SDM | FOT | 22.5 | 23.25 | 903966 |  | BHA | 13538 | RSS | RSS STEERING UNIT FAILURE, UNABLE TO STEER RSS ACCORDING TO THE WELL PLAN
2572 | 10/27/2022 | 27 Oct 1830 - 0500 | KRSN-51 | SP-103 | SSW | FOT | 10.5 | 10.5 | 904030 |  | BHA | 0 | WBCL | SINOPEC 7" STRING MAGNET FAILURE (TOOL PARTS BROKEN AND LEFT IN HOLE)
2574 | 10/27/2022 | 27 Oct 1345 - 1815 | LIDM-2 | SP-258 | HWP | FOT | 4.5 | 4.5 | 903967 |  | TF | 7300 | WLT | MEANWHILE RECORD VSP POINT , TOOL FAILURE ENCOUNTERED DUE TO A SHORT CIRCUIT
2576 | 10/27/2022 | 25 Oct 1800 - 0500 | MZLJ-153202 | SP-261 | FME | HERR | 24 | 59 | 904000 |  | WH | 9750 | WH | AFTER PRESSURE TESTING 13 5/8" 10M BOP, WHEN PERFORMING REMOVAL OF FMC TEST PLUG OPERATION ENCOUTERED OVERPULL - TEST PLUG WAS FOUND TO BE STUCK IN THE WELLHEAD.
2578 | 10/27/2022 | 26 Oct 1630 - 0500 | MSBA-1 | SSA-5820 | HDV | FOT | 24 | 36.5 | 904024 |  | TF | 11346 | DV | PRESSURE TEST CSG & HALLIBURTON OPEN HOLE DVT CSG START LEAK @ 3,700 PSI,
2580 | 10/27/2022 | 25 Oct 0130 - 0500 | UTMN-3044 | SSA-5964 | HCO | DSFT | 24 | 49 | 903989 |  | JF | 10010 | CHAMP | HALL 9-5/8" RTTS PKR FAILED WHILE TESTING THE WELLBORE TO 5,200 PSI.
2581 | 10/27/2022 | 27 Oct 2130 - 2200 | UTMN-3193 | SSA-5970 | RIG | FOT | .5 | .5 | 904032 |  | RR | 405 | TDS | TIGHTEN LOOSE BOLTS ON MONORAIL TURN BUCKLE.
2583 | 10/27/2022 | 27 Oct 1900 - 1930 | UTMN-3193 | SSA-5970 | RIG | FOT | .5 | .5 | 904031 |  | RR | 230 | MPMP | REPAIR ON ALL MUD PUMPS
2584 | 10/27/2022 | 27 Oct 2130 - 2200 | UTMN-3193 | SSA-5970 | RIG | FOT | .5 | .5 | 904032 |  | RR | 405 | TDS | TIGHTEN LOOSE BOLTS ON MONORAIL TURN BUCKLE.
2586 | 10/28/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 153.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2588 | 10/28/2022 | 28 Oct 0500 - 0700 | UTMN-2321 | ADC-46L | TK3 | WTHR | 2 | 2 | 904067 |  | WON | 0 | NA | OPERATION SUSPENDED DUE TO HEAVY FOG CREATING NO VISIBILITY FOR CRANE ACTIVITY.
2590 | 10/28/2022 | 27 Oct 1330 - 0500 | MZLJ-60 | ADC-47 | WCM | CCAT | 24 | 39.5 | 904076 |  | TF | 10127 | CSTR | 9-5/8" SHOE TRACK FLOATS NOT HOLDING - AFTER BUMPING DV PLUG.
2592 | 10/28/2022 | 27 Oct 1930 - 0500 | UTMN-3171 | ADC-55L | SDM | FOT | 24 | 33.5 | 904028 |  | BHA | 12742 | RSS | LOST COMMUNICATION WITH RSS, DECISION TAKEN TO POH TO CHANGE RSS TOOL.
2594 | 10/28/2022 | 28 Oct 1845 - 0500 | SDGM-1099 | ADC-56L | TK3 | WC20 | 10.25 | 10.25 | 904096 |  | WCNT | 3205 | NA | WHEN WASHING DOWN AT 3205 FT. OBSERVED INCREASE IN FLOW OUT %, P/U, SPACE OUT AT TOOL JOINT, FLOW CHECK WELL FLOWING.
2596 | 10/28/2022 | 26 Oct 1445 - 0500 | ABHD-183 | ADC-58L | TK3 | SCSG | 24 | 62.25 | 903963 |  | STUK | 9560 | LINR | 7" LINER GOT STUCK AFTER CONNECTION.
2610 | 10/28/2022 | 27 Oct 1330 - 0500 | MRJN-3017 | ADM-339 | RIG | UNKN | 24 | 39.5 | 904056 |  | HSEI | 7524 | NA | AD WAS INSTRUCTED TO GREASE THE CHOKE MANIFOLD. WHILE PUMPING GREASE IT BECAME HARD TO PUT THE GREASE INTO THE VALVE. IP ATTEMPTED TO REMOVE THE GREASE FITTING WHEN THE GREASE FITTING EJECTED FROM THE VALVE BODY AND HIT HIM IN THE LEFT HAND CAUSING INJURY. RIG ON SAFETY SHUT DOWN DUE TO OCCURED INCIDENT. CONDUCT INCIDENT INVESTIGATION.
2612 | 10/28/2022 | 28 Oct 0645 - 0800 | SFNY-1504 | AOD-11 | BCR | FOT | 1.25 | 1.25 | 904079 |  | TF | 1255 | CTRQ | BAKER FMS CLOSED ON CASING JTS, TROUBLESHOOTING THE SAME FMS CONTROL PANEL MALFUNCTION,
2614 | 10/28/2022 | 28 Oct 0130 - 0300 | UTMN-3019 | DPS-43 | WCR | FOT | 1.5 | 1.5 | 904066 |  | TF | 0 | CRT | WFD CONTROL UNIT FAILED TO OPEN/CLOSE FLUSH MOUNTED SLIPS.
2616 | 10/28/2022 | 28 Oct 1000 - 1200 | HWYH-1128 | DPS-44 | RIG | XTRI | 2 | 2 | 903971 |  | JF | 2110 | NA | EXCESSIVE TIME TO DISCONNECT & R/D CRT TOOL FROM TDS.
2618 | 10/28/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 23.5 | 202.75 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2620 | 10/28/2022 | 23 Oct 1630 - 0500 | ZULF-2066 | ED-85A | RIG | UNKN | 24 | 101.5 | 903889 |  | HSEI | 13471 | NA | RIG SHUT DOWN DUE TO INCIDENT INVESTIGATION ON GOING.
2622 | 10/28/2022 | 28 Oct 1100 - 1700 | MRJN-2004 | ENSCO-76 | RIG | MRWL | 6 | 6 | 904065 |  | BOP | 0 | BOP | MISALIGNMENT BETWEEN RIG & WELLHEAD, SKID IN CANTILEVER 3 INCHES.
2624 | 10/28/2022 | 27 Oct 1945 - 0500 | ABSF-128 | EXL-IA | BAW | HERR | 14.25 | 16.25 | 904035 |  | JF | 6420 | CORL | MREX TOOL RECORDS ABNORMAL HIGH POROSITY READINGS.
2626 | 10/28/2022 | 28 Oct 1215 - 0500 | BRRI-310 | MP-1 | SDM | FOT | 6 | 6 | 903969 |  | BHA | 12637 | RSS | SLB LOST COMMUNICATION BETWEEN RSS POWERDRIVE & MWD. UNABLE TO TRANSMIT NEAR BIT GAMMA RAY READINGS.
2628 | 10/28/2022 | 28 Oct 0500 - 0500 | ZMLH-18 | NBR-575S | SPS | FOT | 22 | 22 | 903972 |  | BHA | 8695 | MMOT | UNABLE TO ACHIEVE THE REQUIRED BUILD RATE AS PER DIRECTIONAL PLAN.
2630 | 10/28/2022 | 27 Oct 1600 - 2300 | UTMN-3700 | PA-622S | RIG | ISEQ | 11.75 | 15.75 | 904057 |  | BOP | 3030 | BOP | PERFORMED ACCUMULATOR FUNCTIONAL TEST, OBSERVED THE 30" X 1K ANNULAR BOPE CLOSING TIME (70 SEC) EXCEEDING SAUDI ARAMCO REQUIREMENT (45 SEC) AS PER WELL CONTROL MANUAL. CORRECTIVE ACTION: CHANGE & TEST 30" X 1K ANNULAR BOPE.
2632 | 10/28/2022 | 28 Oct 0630 - 0430 | ABJF-155 | SINO-11 | BC | DSFT | 22 | 22 | 904062 |  | JF | 4276 | CHAMP | SET AT 4276' WHILE RUNNING NEW BAKER ESP
2634 | 10/28/2022 | 27 Oct 0430 - 0730 | UTMN-1245 | SINO-26 | HUD | FOT | 2.5 | 3 | 904038 |  | TF | 9800 | MPD | HALL MPD POWER SHUT DOWN
2636 | 10/28/2022 | 27 Oct 0400 - 0500 | SHYB-449 | SINO-46L | BHI | FOT | 24 | 25 | 904037 |  | BHA | 9083 | RSS | LOST COMMUNICATION WITH AUTO-TRACK, AUTO-TRACK SHOWING 0 READING & NOT SENDING SIGNALS TO MWD.
2638 | 10/28/2022 | 28 Oct 1645 - 1815 | SFNY-1730 | SL-7 | RIG | FOT | 1.5 | 1.5 | 904098 |  | RR | 0 | DRRK | TROUBLESHOOT CTU. UNABLE TO PUT CONDUCTOR IN TENSION.
2640 | 10/28/2022 | 28 Oct 1215 - 1415 | HRDH-2415 | SND-2002 | GOC | XTRI | 2 | 2 | 904059 |  | JF | 2320 | CTRQ | POWER TONG & HIGH PRESSURE HYDRAULIC HOSE FAILURE.
2642 | 10/28/2022 | 24 Oct 0500 - 0500 | UTMN-3095 | SND-2006 | SPS | UDWL | 24 | 120 | 903922 |  | DD | 12044 | RSS | UNABLE TO BUILD AS PER DIRECTIONAL PLAN#4
2644 | 10/28/2022 | 28 Oct 1515 - 1815 | AWTD-104001 | SND-2007 | RIG | XTRI | 3 | 3 | 904064 |  | JF | 16300 | NA | EXCESSIVE TIME TO TRIP IN HOLE DUE TO FAILURE OF IRON ROUGHNECK( ST-80).
2645 | 10/28/2022 | 28 Oct 1215 - 1415 | HRDH-1291 | SND-2008 | RIG | FOT | 2 | 2 | 904041 |  | RR | 12750 | TRVL | HYDRAULIC OIL LEAK ON WEIGHT INDICATOR LOAD CELL SENSOR
2647 | 10/28/2022 | 26 Oct 0415 - 1730 | HRDH-1291 | SND-2008 | SDM | FOT | 10 | 33.25 | 903966 |  | BHA | 13538 | RSS | RSS STEERING UNIT FAILURE, UNABLE TO STEER RSS ACCORDING TO THE WELL PLAN
2648 | 10/28/2022 | 28 Oct 1215 - 1415 | HRDH-1291 | SND-2008 | RIG | FOT | 2 | 2 | 904041 |  | RR | 12750 | TRVL | HYDRAULIC OIL LEAK ON WEIGHT INDICATOR LOAD CELL SENSOR
2650 | 10/28/2022 | 25 Oct 1330 - 0500 | SAHB-101 | SND-2009 | RIG | FOT | 12 | 24.5 | 903990 |  | RR | 14682 | TDS | TDS HAS DRIVE FAULT. TROUBLESHOOTING TDS. > WHILE ROTATING TORQUE WAS SPIKE SUDDENLY AND ROTARY STOP. TRIED WITH DIFFERENT RPM, SAME ISSUE.
2652 | 10/28/2022 | 28 Oct 0900 - 1500 | HRDH-1965 | SND-3003 | WCR | SRVC | 6 | 6 | 904060 |  | WO | 510 | NA | WAIT ON WDF CREW AND EQPTS TO BE ON LOCATION AHEAD OF TIME PRIOR THE JOB, WDF WAS NOTIFIED ON 10/25/2022 AT 10:50 AM TO SEND CREW AND EQPTS FOR RUN 24" CSG AHEAD.
2654 | 10/28/2022 | 27 Oct 1830 - 0015 | KRSN-51 | SP-103 | SSW | FOT | 19.25 | 29.75 | 904030 |  | BHA | 0 | WBCL | SINOPEC 7" STRING MAGNET FAILURE (TOOL PARTS BROKEN AND LEFT IN HOLE)
2656 | 10/28/2022 | 28 Oct 1500 - 1630 | HRML-98 | SP-161 | HWP | FOT | 1.5 | 1.5 | 904042 |  | TF | 9713 | WLT | LOST TIME ON HALL. W/L DUE TO NOT FOLLOWING PLAN FROM RDD.
2658 | 10/28/2022 | 28 Oct 0315 - 0400 | LIDM-2 | SP-258 | HWP | FOT | .75 | .75 | 904068 |  | TF | 0 | WLT | R/U HALLIBURTON WL BOP IN WHICH ROD IS INSTALLED FOR PRESSURE TEST SAME -ENCOUNTER A SEVERE LEAKAGE AT LOW PRESSURE
2660 | 10/28/2022 | 25 Oct 1800 - 0500 | MZLJ-153202 | SP-261 | FME | HERR | 24 | 83 | 904000 |  | WH | 9750 | WH | AFTER PRESSURE TESTING 13 5/8" 10M BOP, WHEN PERFORMING REMOVAL OF FMC TEST PLUG OPERATION ENCOUTERED OVERPULL - TEST PLUG WAS FOUND TO BE STUCK IN THE WELLHEAD.
2662 | 10/28/2022 | 26 Oct 1630 - 0500 | MSBA-1 | SSA-5820 | HDV | FOT | 20.75 | 57.25 | 904024 |  | TF | 11346 | DV | PRESSURE TEST CSG & HALLIBURTON OPEN HOLE DVT CSG START LEAK @ 3,700 PSI,
2664 | 10/28/2022 | 28 Oct 0730 - 0500 | AWTD-141400 | SSA-5892 | HWP | FOT | 21.5 | 21.5 | 904097 |  | TF | 16270 | WLT | AFTER POOH HALLIBURTON LOGGING TOOLS THERE WERE 2 FINS MISSING OFF THE CENTRALIZER
2666 | 10/28/2022 | 28 Oct 1530 - 2230 | MNHZ-221200 | SSA-5914 | RIG | FOT | 7 | 7 | 904069 |  | RR | 120 | EDR | OBSERVED SENSOR READING PROBLEM ON NOV RIGSENSE. UNABLE TO READ HOOK LOAD & WOB READING. TRIED TO FIX BY ON LOCATION. NO SUCCESS.
2668 | 10/28/2022 | 25 Oct 0130 - 1100 | UTMN-3044 | SSA-5964 | HCO | DSFT | 6 | 55 | 903989 |  | JF | 10010 | CHAMP | HALL 9-5/8" RTTS PKR FAILED WHILE TESTING THE WELLBORE TO 5,200 PSI.
2670 | 10/28/2022 | 28 Oct 0945 - 1115 | MHWZ-901 | T902 | ITS | WOTO | 1.5 | 1.5 | 904043 |  | WO | 5105 | NA | WAIT ON ITS CSG RUNNING EQUIP. REQUESTED TO BE ON LOCATION 10/26/22 BEFORE DARK.
2672 | 10/29/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 177.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2674 | 10/29/2022 | 27 Oct 1330 - 0500 | MZLJ-60 | ADC-47 | WCM | CCAT | 24 | 63.5 | 904076 |  | TF | 10127 | CSTR | 9-5/8" SHOE TRACK FLOATS NOT HOLDING - AFTER BUMPING DV PLUG.
2676 | 10/29/2022 | 27 Oct 1930 - 0745 | UTMN-3171 | ADC-55L | SDM | FOT | 2.75 | 36.25 | 904028 |  | BHA | 12742 | RSS | LOST COMMUNICATION WITH RSS, DECISION TAKEN TO POH TO CHANGE RSS TOOL.
2678 | 10/29/2022 | 28 Oct 1845 - 1100 | SDGM-1099 | ADC-56L | TK3 | WC20 | 6 | 16.25 | 904096 |  | WCNT | 3205 | NA | WHEN WASHING DOWN AT 3205 FT. OBSERVED INCREASE IN FLOW OUT %, P/U, SPACE OUT AT TOOL JOINT, FLOW CHECK WELL FLOWING.
2680 | 10/29/2022 | 26 Oct 1445 - 0045 | ABHD-183 | ADC-58L | TK3 | SCSG | 19.75 | 82 | 903963 |  | STUK | 9560 | LINR | 7" LINER GOT STUCK AFTER CONNECTION.
2702 | 10/29/2022 | 29 Oct 0715 - 0400 | HWYH-1300 | ADC-65L | SDM | FOT | 20.75 | 20.75 | 904103 |  | BHA | 12100 | MWD | LOST MWD SIGNAL, TROUBLESHOOT, NO SUCCESS.
2704 | 10/29/2022 | 27 Oct 1330 - 0500 | MRJN-3017 | ADM-339 | RIG | UNKN | 24 | 63.5 | 904056 |  | HSEI | 7524 | NA | AD WAS INSTRUCTED TO GREASE THE CHOKE MANIFOLD. WHILE PUMPING GREASE IT BECAME HARD TO PUT THE GREASE INTO THE VALVE. IP ATTEMPTED TO REMOVE THE GREASE FITTING WHEN THE GREASE FITTING EJECTED FROM THE VALVE BODY AND HIT HIM IN THE LEFT HAND CAUSING INJURY. RIG ON SAFETY SHUT DOWN DUE TO OCCURED INCIDENT. CONDUCT INCIDENT INVESTIGATION.
2705 | 10/29/2022 | 29 Oct 1300 - 1500 | UTMN-3019 | DPS-43 | WCR | FOT | 2 | 2 | 904101 |  | TF | 4682 | CRT | CRT DIES TOOL COULD NOT BE RELEASED FROM CASING AFTER CIRCULATION AT CSG SHOE
2707 | 10/29/2022 | 29 Oct 2300 - 0030 | UTMN-3019 | DPS-43 | WCR | XTTE | 1.5 | 1.5 | 904045 |  | TF | 7330 | CTRQ | EXCESSIVE TIME BREAKING OUT CSG JT WITH POWER TONGUE
2708 | 10/29/2022 | 29 Oct 1300 - 1500 | UTMN-3019 | DPS-43 | WCR | FOT | 2 | 2 | 904101 |  | TF | 4682 | CRT | CRT DIES TOOL COULD NOT BE RELEASED FROM CASING AFTER CIRCULATION AT CSG SHOE
2710 | 10/29/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 24 | 226.75 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2712 | 10/29/2022 | 23 Oct 1630 - 0500 | ZULF-2066 | ED-85A | RIG | UNKN | 24 | 125.5 | 903889 |  | HSEI | 13471 | NA | RIG SHUT DOWN DUE TO INCIDENT INVESTIGATION ON GOING.
2714 | 10/29/2022 | 27 Oct 1945 - 1045 | ABSF-128 | EXL-IA | BAW | HERR | 5.75 | 22 | 904035 |  | JF | 6420 | CORL | MREX TOOL RECORDS ABNORMAL HIGH POROSITY READINGS.
2716 | 10/29/2022 | 29 Oct 0200 - 0500 | ZULF-2041 | EXL-IVA | MSD | HERR | 3 | 3 | 904116 |  | JF | 13207 | CTRQ | WAIT ON REPLACEMENT CASING CREW AND COMPANY AS PER ARAMCO.
2718 | 10/29/2022 | 28 Oct 1215 - 0500 | BRRI-310 | MP-1 | SDM | FOT | 24 | 30 | 903969 |  | BHA | 12637 | RSS | SLB LOST COMMUNICATION BETWEEN RSS POWERDRIVE & MWD. UNABLE TO TRANSMIT NEAR BIT GAMMA RAY READINGS.
2719 | 10/29/2022 | 29 Oct 0930 - 0500 | ZMLH-18 | NBR-575S | SPS | SDIR | 19.5 | 19.5 | 904105 |  | STUK | 8719 | MMOT | STRING GOT DIFFERENTIAL STUCK AFTER SLIDING.
2721 | 10/29/2022 | 28 Oct 0500 - 0745 | ZMLH-18 | NBR-575S | SPS | FOT | 2.75 | 24.75 | 903972 |  | BHA | 8695 | MMOT | UNABLE TO ACHIEVE THE REQUIRED BUILD RATE AS PER DIRECTIONAL PLAN.
2722 | 10/29/2022 | 29 Oct 0930 - 0500 | ZMLH-18 | NBR-575S | SPS | SDIR | 19.5 | 19.5 | 904105 |  | STUK | 8719 | MMOT | STRING GOT DIFFERENTIAL STUCK AFTER SLIDING.
2724 | 10/29/2022 | 28 Oct 0500 - 0500 | TINT-91 | NBR-783S | ARM | UVLC | 24 | 48 | 904099 |  | LCIR | 11529 | NA | SEVERE LOSS CIRCULATION IN JIHL DOLEMITE
2726 | 10/29/2022 | 29 Oct 0745 - 1045 | JLMN-200 | NBR-987S | RIG | FOT | 3 | 3 | 904071 |  | RR | 10147 | DWKS | OBSERVED LEAK IN DRAWWORK WATER SEALS.
2728 | 10/29/2022 | 29 Oct 0330 - 0500 | USKR-6 | PA-866S | SWL | XTRI | 1.5 | 1.5 | 904106 |  | JF | 5498 | WLT | EXCEESIVE TIME FOR TERMINATION FOR RUN #4
2730 | 10/29/2022 | 29 Oct 0815 - 1615 | HSBH-25 | RBP-50A | RIG | FOT | 8 | 8 | 903973 |  | RR | 9973 | DWKS | BLOCKAGE/LOSS OF AIR WHEN ENGAGE CLUTCH, DWKS UNABLE TO PULL STRING. ARO MAINTENANCE TEAM TROUBLESHOOT AND REPAIR SAME.
2732 | 10/29/2022 | 28 Oct 0630 - 0500 | ABJF-155 | SINO-11 | BAL | DSFT | 24 | 46 | 904062 |  | JF | 4276 | PKR | SET AT 4276' WHILE RUNNING NEW BAKER ESP
2734 | 10/29/2022 | 27 Oct 0400 - 0645 | SHYB-449 | SINO-46L | BHI | FOT | 1.75 | 26.75 | 904037 |  | BHA | 9083 | RSS | LOST COMMUNICATION WITH AUTO-TRACK, AUTO-TRACK SHOWING 0 READING & NOT SENDING SIGNALS TO MWD.
2736 | 10/29/2022 | 29 Oct 0700 - 0500 | ABQQ-454 | SINO21 | SDM | FOT | 22 | 22 | 903975 |  | BHA | 8634 | LWD | SLB LWD FAILURE.
2738 | 10/29/2022 | 24 Oct 0500 - 0430 | UTMN-3095 | SND-2006 | SPS | UDWL | 23 | 143 | 903922 |  | DD | 12044 | RSS | UNABLE TO BUILD AS PER DIRECTIONAL PLAN#4
2740 | 10/29/2022 | 25 Oct 1330 - 0500 | SAHB-101 | SND-2009 | RIG | FOT | 21.5 | 46 | 903990 |  | RR | 14682 | TDS | TDS HAS DRIVE FAULT. TROUBLESHOOTING TDS. > WHILE ROTATING TORQUE WAS SPIKE SUDDENLY AND ROTARY STOP. TRIED WITH DIFFERENT RPM, SAME ISSUE.
2741 | 10/29/2022 | 29 Oct 1400 - 1530 | MNIF-142 | SP-110 | WCR | FOT | 1.5 | 1.5 | 904072 |  | TF | 15124 | TTRQ | HAD A PROBLEM IN WFD POWER TONG DUMP VALVE.
2743 | 10/29/2022 | 29 Oct 0030 - 0300 | MNIF-142 | SP-110 | WCR | FOT | 2.5 | 2.5 | 904046 |  | TF | 15124 | TTRQ | HAD MULTIPLE PROBLEMS WITH WFD JAM UNIT AND POWER TONG DIE BLOCKS.
2744 | 10/29/2022 | 29 Oct 1400 - 1530 | MNIF-142 | SP-110 | WCR | FOT | 1.5 | 1.5 | 904072 |  | TF | 15124 | TTRQ | HAD A PROBLEM IN WFD POWER TONG DUMP VALVE.
2746 | 10/29/2022 | 28 Oct 2200 - 0430 | ABHD-877 | SP-229 | RIG | HERR | 23.5 | 30.5 | 904044 |  | WH | 0 | WH | RIG NIGHT TOOLPUSHER MISTAKELY ENERGIZED 2 EA LOCK DOWN SCREWS ON CIW 13" TEST PLUG AND APPLIED PRESSURE RESULTED ON DAMAGED OF LOCK DOWN SCREWS & STUCK TEST PLUG IN WELLHEAD.
2748 | 10/29/2022 | 25 Oct 1800 - 0500 | MZLJ-153202 | SP-261 | FME | HERR | 24 | 107 | 904000 |  | WH | 9750 | WH | AFTER PRESSURE TESTING 13 5/8" 10M BOP, WHEN PERFORMING REMOVAL OF FMC TEST PLUG OPERATION ENCOUTERED OVERPULL - TEST PLUG WAS FOUND TO BE STUCK IN THE WELLHEAD.
2750 | 10/29/2022 | 26 Oct 1630 - 0500 | MSBA-1 | SSA-5820 | HDV | FOT | 24 | 81.25 | 904024 |  | TF | 11346 | DV | PRESSURE TEST CSG & HALLIBURTON OPEN HOLE DVT CSG START LEAK @ 3,700 PSI,
2752 | 10/29/2022 | 28 Oct 0730 - 0500 | AWTD-141400 | SSA-5892 | HWP | FOT | 24 | 45.5 | 904097 |  | TF | 16270 | WLT | AFTER POOH HALLIBURTON LOGGING TOOLS THERE WERE 2 FINS MISSING OFF THE CENTRALIZER
2754 | 10/29/2022 | 29 Oct 1330 - 0500 | HRDH-222 | T218 | WDS | FOT | 15 | 15 | 903974 |  | BHA | 6995 | LWD | LWD TOOL FAILURE
2756 | 10/30/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 201.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2757 | 10/30/2022 | 30 Oct 2330 - 0330 | ANDR-1006 | ADC-31 | RIG | FPMP | 4 | 4 | 904110 |  | RR | 11976 | MPMP | OBSERVE MUD PUMP 1 NOT WORKING PROPERLY
2759 | 10/30/2022 | 30 Oct 1530 - 2330 | ANDR-1006 | ADC-31 | RIG | FPMP | 8 | 8 | 904109 |  | RR | 11976 | MPMP | CHANGE PUSATOR DUMPNER, AND ISOLATION VALVE PUMP 1, CANGE GROUND MANIFOLD VALVE
2760 | 10/30/2022 | 30 Oct 2330 - 0330 | ANDR-1006 | ADC-31 | RIG | FPMP | 4 | 4 | 904110 |  | RR | 11976 | MPMP | OBSERVE MUD PUMP 1 NOT WORKING PROPERLY
2762 | 10/30/2022 | 27 Oct 1330 - 1630 | MZLJ-60 | ADC-47 | WCM | CCAT | 11.5 | 75 | 904076 |  | TF | 10127 | CSTR | 9-5/8" SHOE TRACK FLOATS NOT HOLDING - AFTER BUMPING DV PLUG.
2764 | 10/30/2022 | 11 Oct 1830 - 2215 | UTMN-3045 | ADC-52 | GOC | FOT | 1 | 2 | 903413 |  | TF | 160 | CTRQ | NO COMMUNICATION BETWEEN CRT AND JAM UNIT. TROUBLE SHOOTING SAME. WIRELESS SYSTEM NOT WORKING . * CHANGE BATTERY AND TRY TO FIX THE PROBLEM WITHOUT SUCCESS. * DECIDED TO CONTINUE RUN CASING.
2766 | 10/30/2022 | 30 Oct 0745 - 0500 | SDGM-1099 | ADC-56L | TK3 | CFFM | 21.25 | 21.25 | 904158 |  | HC | 4322 | NA | CONT WASHING DOWN 18-5/8" CSG TO 4,322 FT UNABLE TO PASS OBSTRUCTION.
2768 | 10/30/2022 | 26 Oct 1445 - 0500 | ABHD-183 | ADC-58L | TK3 | SCSG | 24 | 106 | 903963 |  | STUK | 9560 | LINR | 7" LINER GOT STUCK AFTER CONNECTION.
2779 | 10/30/2022 | 30 Oct 0500 - 0500 | HWYH-360 | ADES-13 | BAW | FOP | 24 | 24 | 904157 |  | JF | 4836 | CORL | BAKER E-LINE TOOLS STUCK WHEN TAG EZSV-CR @ 4832 FT.
2781 | 10/30/2022 | 29 Oct 0430 - 2100 | SFNY-259 | ADM-266 | SBA | FOT | 16 | 16.5 | 904107 |  | TF | 632 | ESPL | SAWAFI/BORETS CHECKED ESP CABLE INTEGRITY, FOUND CABLE GROUNDED, POH FOUND ONE OF THE PACKER PENETRATOR DISENGAGED & PULLED OUT,
2782 | 10/30/2022 | 27 Oct 1330 - 0730 | MRJN-3017 | ADM-339 | RIG | UNKN | 2.5 | 66 | 904056 |  | HSEI | 7524 | NA | AD WAS INSTRUCTED TO GREASE THE CHOKE MANIFOLD. WHILE PUMPING GREASE IT BECAME HARD TO PUT THE GREASE INTO THE VALVE. IP ATTEMPTED TO REMOVE THE GREASE FITTING WHEN THE GREASE FITTING EJECTED FROM THE VALVE BODY AND HIT HIM IN THE LEFT HAND CAUSING INJURY. RIG ON SAFETY SHUT DOWN DUE TO OCCURED INCIDENT. CONDUCT INCIDENT INVESTIGATION.
2784 | 10/30/2022 | 25 Oct 0500 - 0500 | MRJN-3017 | ADM-339 | ARN | STBH | 21.5 | 78 | 903957 |  | STUK | 7668 | BHA | DRILL STRING BECAME STUCK DURING CONNECTION. ATTEMPT TO FREE THE SAME.
2785 | 10/30/2022 | 27 Oct 1330 - 0730 | MRJN-3017 | ADM-339 | RIG | UNKN | 2.5 | 66 | 904056 |  | HSEI | 7524 | NA | AD WAS INSTRUCTED TO GREASE THE CHOKE MANIFOLD. WHILE PUMPING GREASE IT BECAME HARD TO PUT THE GREASE INTO THE VALVE. IP ATTEMPTED TO REMOVE THE GREASE FITTING WHEN THE GREASE FITTING EJECTED FROM THE VALVE BODY AND HIT HIM IN THE LEFT HAND CAUSING INJURY. RIG ON SAFETY SHUT DOWN DUE TO OCCURED INCIDENT. CONDUCT INCIDENT INVESTIGATION.
2787 | 10/30/2022 | 30 Oct 2030 - 0115 | SFNY-1501 | AOD-11 | RIG | FOT | 4.75 | 4.75 | 904138 |  | RR | 2370 | CSYS | RETURN LINE FROM SHALESHAKER TANKS DOWN TO MUD PIT'S GOT CHOKED.
2789 | 10/30/2022 | 30 Oct 1245 - 1345 | MRJN-537 | ARO-4001 | RIG | LHFL | 1 | 1 | 904120 |  | RR | 13600 | HSYS | WHILE POOH HOSE ON PRS LEAKING, PRS NOT ABLE TO FUNCTION, REPLACE HOSE. MAKE UP TOP DRIVE ROTATE AND RECIPROCATE STRING.
2791 | 10/30/2022 | 30 Oct 1145 - 0000 | ZULF-2051 | BB-84A | BAW | HINW | 12.25 | 12.25 | 904136 |  | STUK | 5688 | WLT | WIRELINE TOOLS HUNG UP DURING CORROLATIONS PASS
2793 | 10/30/2022 | 19 Oct 1900 - 0300 | NJYN-18 | DPS-74 | ARM | STDP | 15 | 241.75 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2795 | 10/30/2022 | 23 Oct 1630 - 0500 | ZULF-2066 | ED-85A | RIG | UNKN | 24 | 149.5 | 903889 |  | HSEI | 13471 | NA | RIG SHUT DOWN DUE TO INCIDENT INVESTIGATION ON GOING.
2797 | 10/30/2022 | 29 Oct 0200 - 0500 | ZULF-2041 | EXL-IVA | MSD | HERR | 24 | 27 | 904116 |  | JF | 13207 | CTRQ | WAIT ON REPLACEMENT CASING CREW AND COMPANY AS PER ARAMCO.
2799 | 10/30/2022 | 28 Oct 1215 - 2300 | BRRI-310 | MP-1 | SDM | FOT | 14.5 | 36.75 | 903969 |  | BHA | 12637 | RSS | SLB LOST COMMUNICATION BETWEEN RSS POWERDRIVE & MWD. UNABLE TO TRANSMIT NEAR BIT GAMMA RAY READINGS.
2801 | 10/30/2022 | 29 Oct 0930 - 0500 | ZMLH-18 | NBR-575S | SPS | SDIR | 24 | 43.5 | 904105 |  | STUK | 8719 | MMOT | STRING GOT MECHANICAL STUCK AFTER SLIDING.
2803 | 10/30/2022 | 29 Oct 1430 - 0500 | ANDR-1018 | NBR-654S | ARM | WC11 | 24 | 38.5 | 904122 |  | WCNT | 10637 | NA | WHILE DRILLING AT 10,637 FT. HAVE LEL ALARM IN BELL NIPPLE SHOWING 70% , WITHOUT ANY GAIN OR CHANGE IN FLOW OUT RETURN,
2805 | 10/30/2022 | 28 Oct 0500 - 1130 | TINT-91 | NBR-783S | ARM | UVLC | 6.5 | 54.5 | 904099 |  | LCIR | 11529 | NA | SEVERE LOSS CIRCULATION IN JIHL DOLEMITE
2807 | 10/30/2022 | 30 Oct 1215 - 1715 | UTMN-3012 | NBR-797S | RIG | FOT | 5 | 5 | 904049 |  | RR | 10017 | DWKS | AIRLINE TO HIGH DRUM CLUTCH NOT SUPPLYING AIR.
2809 | 10/30/2022 | 30 Oct 1130 - 1430 | HRDH-1976 | PA-218S | BLH | FOT | 3 | 3 | 904121 |  | TF | 11517 | HGRL | FAILURE TO SET LINER HANGER DUE TO BALL SEAT EXTRUDED EARLIER @ 1400 PSI BEFORE REACHING LINER HGR SETTING PRESSURE VALUE (+/- 1900 PSI).
2811 | 10/30/2022 | 30 Oct 1630 - 1800 | MRJN-840 | SL-7 | RIG | FOT | 1.5 | 1.5 | 904108 |  | RR | 0 | PSYS | TROUBLESHOOT JACKING SYSTEM. UNABLE TO JACK DOWN.
2812 | 10/30/2022 | 30 Oct 0245 - 0315 | MHKK-2 | SND-2005 | SWL | FOT | .5 | .5 | 904140 |  | TF | 8900 | WLT | IBC TOOL SUB (ISOLATION SCAN TOOL) NOT ABLE TO ROTATE CLOCKWISE TO ALLOW CBL RECORDING.
2814 | 10/30/2022 | 30 Oct 2100 - 2200 | MHKK-2 | SND-2005 | SWL | FOT | 1 | 1 | 904139 |  | TF | 0 | WLT | FUNCTION TEST SLB TOOLS PRIOR CBL LOG, NO COMMUNICATION W/ TOOL.
2815 | 10/30/2022 | 30 Oct 0245 - 0315 | MHKK-2 | SND-2005 | SWL | FOT | .5 | .5 | 904140 |  | TF | 8900 | WLT | IBC TOOL SUB (ISOLATION SCAN TOOL) NOT ABLE TO ROTATE CLOCKWISE TO ALLOW CBL RECORDING.
2817 | 10/30/2022 | 30 Oct 0500 - 0500 | UTMN-3095 | SND-2006 | SPS | FOT | 24 | 24 | 904119 |  | BHA | 12052 | RSS | RIH WITH NEW SPS BHA, DRILLED 7 FT, OBSERVED SPS TOOLS WITHOUT RESPONSE.
2819 | 10/30/2022 | 27 Oct 1830 - 0615 | KRSN-51 | SP-103 | SSW | FOT | 1.25 | 43 | 904030 |  | BHA | 0 | WBCL | SINOPEC 7" STRING MAGNET FAILURE (TOOL PARTS BROKEN AND LEFT IN HOLE)
2821 | 10/30/2022 | 28 Oct 2200 - 0500 | ABHD-877 | SP-229 | RIG | HERR | 15.5 | 46 | 904044 |  | WH | 0 | WH | RIG NIGHT TOOLPUSHER MISTAKELY ENERGIZED 2 EA LOCK DOWN SCREWS ON CIW 13" TEST PLUG AND APPLIED PRESSURE RESULTED ON DAMAGED AND CHOPPED 1.5" OF LOCK DOWN SCREWS & STUCK TEST PLUG IN WELLHEAD.
2823 | 10/30/2022 | 25 Oct 1800 - 0500 | MZLJ-153202 | SP-261 | FME | HERR | 24 | 131 | 904000 |  | WH | 9750 | WH | AFTER PRESSURE TESTING 13 5/8" 10M BOP, WHEN PERFORMING REMOVAL OF FMC TEST PLUG OPERATION ENCOUTERED OVERPULL - TEST PLUG WAS FOUND TO BE STUCK IN THE WELLHEAD.
2825 | 10/30/2022 | 28 Oct 2130 - 0500 | QTIF-363 | SSA-29 | WFS | FOT | 24 | 47.5 | 904137 |  | BHA | 0 | FISHT | WEATHERFORD UNABLE TO RELEASE FISHING TOOLS.
2827 | 10/30/2022 | 26 Oct 1630 - 0500 | MSBA-1 | SSA-5820 | HDV | FOT | 22.5 | 103.75 | 904024 |  | TF | 11346 | DV | PRESSURE TEST CSG & HALLIBURTON OPEN HOLE DVT CSG START LEAK @ 3,700 PSI,
2829 | 10/30/2022 | 26 Oct 0645 - 1330 | UTMN-3193 | SSA-5970 | NCS | CFST | 6.75 | 77 | 904073 |  | CMT | 0 | NA | CMT FLUSH SET.
2831 | 10/30/2022 | 29 Oct 1330 - 1130 | HRDH-222 | T218 | WDS | FOT | 6.5 | 21.5 | 903974 |  | BHA | 6995 | LWD | LWD TOOL FAILURE
2833 | 10/30/2022 | 30 Oct 1545 - 0500 | ABSD-1 | T907 | RIG | SRVC | 11.25 | 11.25 | 904156 |  | WO | 14592 | NA | AS PER SCHEDULE G, KCA IS RESPONSIBLE TO SUPPLY POWER TONGS, AT TIME OF POOH, THEIR VENDOR BACKED OUT.
2835 | 10/30/2022 | 30 Oct 1430 - 2000 | JAHQ-801 | ZPEC-2 | RIG | SRVC | 5.5 | 5.5 | 904075 |  | WO | 1518 | NA | RIG SHUTDOWN WAITING ON ZPEC MANAGEMENT TO SOLVE CATERING ISSUE.
2837 | 10/31/2022 | 31 Oct 1145 - 0500 | QTIF-519 | 088TE | ENP | MAOS | 3 | 3 | 904178 |  | TF | 675 | TBG | ENPRO/MAXTUBE BUILT-IN GRE CBR (BLACK FLARE) BROKEN, REPLACE JOINT BY ANOTHER JOINT.
2839 | 10/31/2022 | 22 Oct 1945 - 0500 | ZULF-1386 | ADC-17 | MSD | UNKN | 24 | 225.25 | 903850 |  | HSEI | 2433 | NA | FILL-UP TOOL HOSE DISCONNECTED FROM FILL-UP TOOL, FALLING TO RIG FLOOR FROM ELEVATED POSITION, STRUCK IP'S FOREHEAD. STOP OPERATION AND ACTIVATE 911 REQUEST OF MEDI-VAC HELICOPTER, EVACUATE IP TO TANAJIB CLINIC.
2841 | 10/31/2022 | 30 Oct 0745 - 0130 | SDGM-1099 | ADC-56L | TK3 | CFFM | 20.5 | 41.75 | 904158 |  | HC | 4322 | NA | CONT WASHING DOWN 18-5/8" CSG TO 4,322 FT UNABLE TO PASS OBSTRUCTION.
2843 | 10/31/2022 | 26 Oct 1445 - 0500 | ABHD-183 | ADC-58L | TK3 | SCSG | 24 | 130 | 903963 |  | STUK | 9560 | LINR | 7" LINER GOT STUCK AFTER CONNECTION.
2845 | 10/31/2022 | 30 Oct 0500 - 0500 | HWYH-360 | ADES-13 | BAW | FOP | 24 | 48 | 904157 |  | JF | 4836 | CORL | BAKER E-LINE TOOLS STUCK WHEN TAG EZSV-CR @ 4832 FT.
2846 | 10/31/2022 | 31 Oct 0715 - 1145 | MRJN-3017 | ADM-339 | RIG | FOT | 4.5 | 4.5 | 904124 |  | RR | 7014 | DRRK | OBSERVE BOLT SHEAR ON XY-RACKER ROLLER GRIPPER HEAD (NO DROPPPED OBJECTS, ALL LOCKWIRE). ADES - REPAIR THE SAME.
2848 | 10/31/2022 | 25 Oct 0500 - 0500 | MRJN-3017 | ADM-339 | ARN | STBH | 19.5 | 97.5 | 903957 |  | STUK | 7668 | BHA | DRILL STRING BECAME STUCK DURING CONNECTION. ATTEMPT TO FREE THE SAME.
2849 | 10/31/2022 | 31 Oct 0715 - 1145 | MRJN-3017 | ADM-339 | RIG | FOT | 4.5 | 4.5 | 904124 |  | RR | 7014 | DRRK | OBSERVE BOLT SHEAR ON XY-RACKER ROLLER GRIPPER HEAD (NO DROPPPED OBJECTS, ALL LOCKWIRE). ADES - REPAIR THE SAME.
2851 | 10/31/2022 | 19 Oct 1900 - 0500 | NJYN-18 | DPS-74 | ARM | STDP | 24 | 265.75 | 903727 |  | STUK | 16400 | DP | WHILE MAKE CONNECTION @16,400' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
2853 | 10/31/2022 | 23 Oct 1630 - 0500 | ZULF-2066 | ED-85A | RIG | UNKN | 24 | 173.5 | 903889 |  | HSEI | 13471 | NA | RIG SHUT DOWN DUE TO INCIDENT INVESTIGATION ON GOING.
2855 | 10/31/2022 | 31 Oct 0515 - 0500 | ZULF-2015 | ENS-108 | RIG | FOT | 23.75 | 23.75 | 904125 |  | RR | 4878 | DWKS | RIGS AMPHION SYSTEM (ELECTRONIC SOFTWARE) CAUSED A LOSS OF POWER TO RIG FLOOR, TDS/ DRAW WORKS. STOPPED OPERATIONS. ATTEMPTED TO RESET/ REPLACE SOFTWARE CARDS, UNSUCCESSFUL. CONTINUED TROUBLE SHOOTING.
2857 | 10/31/2022 | 31 Oct 0215 - 0315 | BRRI-310 | MP-1 | SDM | FOT | 1 | 1 | 904128 |  | BHA | 15289 | MWD | SLB RECIEVED POOR SIGNAL FROM LWD TOOLS. SLB TROUBLESHOOT COMMUNICATION ISSUES.
2859 | 10/31/2022 | 29 Oct 0930 - 0500 | ZMLH-18 | NBR-575S | SPS | SDIR | 24 | 67.5 | 904105 |  | STUK | 8719 | MMOT | STRING GOT MECHANICAL STUCK AFTER SLIDING.
2861 | 10/31/2022 | 29 Oct 1430 - 0500 | ANDR-1018 | NBR-654S | ARM | WC11 | 24 | 62.5 | 904122 |  | WCNT | 10637 | NA | WHILE DRILLING AT 10,637 FT. HAVE LEL ALARM IN BELL NIPPLE SHOWING 70% , WITHOUT ANY GAIN OR CHANGE IN FLOW OUT RETURN, SHUT IN & START KILL OPEARTION.
2863 | 10/31/2022 | 31 Oct 0500 - 1530 | TINT-91 | NBR-783S | ARM | WC20 | 10.5 | 10.5 | 904177 |  | WCNT | 11580 | NA | WHILE CIRC. HAD NCREASE IN FLOW OUT & 10 BBL PIT GAIN, MW CUT F/ 120 TO 117 PCF, SHUT IN WELL, RECORD SIDPP & SICP, KILLED SAME W/ W&W METHOD USING 125 PCF KMW.
2865 | 10/31/2022 | 30 Oct 1130 - 0500 | HRDH-1976 | PA-218S | BLH | FOT | 24 | 27 | 904121 |  | TF | 11517 | HGRL | FAILURE TO SET LINER HANGER DUE TO BALL SEAT EXTRUDED EARLIER @ 1400 PSI BEFORE REACHING LINER HGR SETTING PRESSURE VALUE (+/- 1900 PSI).
2867 | 10/31/2022 | 31 Oct 2015 - 2200 | HRDH-2414 | PA-604S | SPS | HERR | 1.75 | 1.75 | 904198 |  | DD | 15043 | RSS | EXCESS TIME HANDLING MWD.
2869 | 10/31/2022 | 31 Oct 2030 - 0000 | UTMN-3700 | PA-622S | BHT | FOT | 3.5 | 3.5 | 904196 |  | BHA | 4226 | BIT | DROP IN PRESSURE FROM 2600 PSI TO 1500 PSI, POOH TO SURFACE TO CHECK BHA, BIT LOST ONE NOZZLE, ATTEMPT TO INSTALL NEW JET 12/32" NOT SUCCESS DUE TO WASHOUT SPRING GROOVE. CORRECTIVE ACTION: CHANGE BIT.
2871 | 10/31/2022 | 30 Oct 0230 - 1400 | KHRS-154 | SND-1201 | HCB | FOT | 9 | 11.5 | 904162 |  | TF | 5980 | BP | 9-5/8'' HALL RBP NOT COMPLETE SET AND NOT HOLDING PRESSURE WHILE P/T.
2873 | 10/31/2022 | 31 Oct 2300 - 0500 | HRML-808 | SND-1501 | KSC | FOT | 6 | 6 | 904180 |  | TF | 0 | ESP | ESP CABLE FAILURE
2875 | 10/31/2022 | 30 Oct 0500 - 2200 | UTMN-3095 | SND-2006 | SPS | FOT | 17 | 41 | 904119 |  | BHA | 12052 | RSS | RIH WITH NEW SPS BHA, DRILLED 7 FT, OBSERVED SPS TOOLS WITHOUT RESPONSE.
2877 | 10/31/2022 | 31 Oct 0600 - 0800 | MNIF-867 | SND-2010 | ND1 | ISEQ | 2 | 2 | 904112 |  | BHA | 4762 | MMOT | CHECK BEARING SLACK ON FIRST MMTR, HAVE EXCESS OF 7-MM - L/D & P/U BACK UP MMTR, BEARING SLACK 3-4MM OKAY
2879 | 10/31/2022 | 31 Oct 2200 - 0500 | ABQQ-546 | SP-101 | NCS | FOT | 7 | 7 | 904115 |  | JF | 4149 | SQZ | NPS CEMENT UNIT FAILED .
2881 | 10/31/2022 | 27 Oct 1200 - 0500 | FRUQ-805 | SP-106 | RIG | WOTR | 8 | 53 | 904114 |  | WO | 1755 | NA | WAIT ON WATER TRANSPORTATION TRUCKS DUE TO RIG EIGHT TANKERS ARE NOT WORKING 24 HRS
2883 | 10/31/2022 | 31 Oct 0830 - 0500 | FDHL-148 | SP-124 | BAW | FOT | 20.5 | 20.5 | 904176 |  | TF | 10250 | WLT | TOOL FAILURE DURING SAMPLING OPERATION
2885 | 10/31/2022 | 28 Oct 2200 - 0500 | ABHD-877 | SP-229 | RIG | HERR | 24 | 70 | 904044 |  | WH | 0 | WH | RIG NIGHT TOOLPUSHER MISTAKELY ENERGIZED 2 EA LOCK DOWN SCREWS ON CIW 13" TEST PLUG AND APPLIED PRESSURE RESULTED ON DAMAGED AND CHOPPED 1.5" OF LOCK DOWN SCREWS & STUCK TEST PLUG IN WELLHEAD.
2887 | 10/31/2022 | 25 Oct 1800 - 0500 | MZLJ-153202 | SP-261 | FME | HERR | 24 | 155 | 904000 |  | WH | 9750 | WH | AFTER PRESSURE TESTING 13 5/8" 10M BOP, WHEN PERFORMING REMOVAL OF FMC TEST PLUG OPERATION ENCOUTERED OVERPULL - TEST PLUG WAS FOUND TO BE STUCK IN THE WELLHEAD.
2889 | 10/31/2022 | 31 Oct 0200 - 0500 | QTIF-172 | SSA-202 | SPS | FOT | 3 | 3 | 904127 |  | BHA | 11800 | MWD | LOST MWD SIGNAL.
2891 | 10/31/2022 | 28 Oct 2130 - 0500 | QTIF-363 | SSA-29 | WFS | FOT | 24 | 71.5 | 904137 |  | BHA | 0 | FISHT | WEATHERFORD UNABLE TO RELEASE FISHING TOOLS.
2893 | 10/31/2022 | 26 Oct 1630 - 0430 | MSBA-1 | SSA-5820 | HDV | FOT | 23.5 | 127.25 | 904024 |  | TF | 11346 | DV | PRESSURE TEST CSG & HALLIBURTON OPEN HOLE DVT CSG START LEAK @ 3,700 PSI,
2894 | 10/31/2022 | 29 Oct 1530 - 0600 | AWTD-141400 | SSA-5892 | ARM | STBH | 1 | 33 | 904159 |  | STUK | 14397 | BHA | WHILE BACKREAMING OOH DRILLER WORKED HIS SLIP AREA. SET SLIPS. BROKE OUT STAND TO RACK BACK WITH THE ROTARY TABLE IS ROTATING. CAME DOWN WITH TDS. STOPPED THE ROTARY TABLE AND SCREWED INTO THE NEXT TOOL JOINT. UPON PICKING OUT OF THE SLIPS HAD CIRCULATION BUT NO ROTATION. STRING IS STUK
2896 | 10/31/2022 | 28 Oct 0730 - 0230 | AWTD-141400 | SSA-5892 | HWP | FOT | 20.5 | 58 | 904097 |  | TF | 16270 | WLT | AFTER POOH HALLIBURTON LOGGING TOOLS THERE WERE 2 FINS MISSING OFF THE CENTRALIZER
2897 | 10/31/2022 | 29 Oct 1530 - 0600 | AWTD-141400 | SSA-5892 | ARM | STBH | 1 | 33 | 904159 |  | STUK | 14397 | BHA | WHILE BACKREAMING OOH DRILLER WORKED HIS SLIP AREA. SET SLIPS. BROKE OUT STAND TO RACK BACK WITH THE ROTARY TABLE IS ROTATING. CAME DOWN WITH TDS. STOPPED THE ROTARY TABLE AND SCREWED INTO THE NEXT TOOL JOINT. UPON PICKING OUT OF THE SLIPS HAD CIRCULATION BUT NO ROTATION. STRING IS STUK
2898 | 10/31/2022 | 31 Oct 0100 - 0215 | MNHZ-221200 | SSA-5914 | RIG | FOT | 1.25 | 1.25 | 904197 |  | RR | 1160 | CSYS | EXCESSIVE TIME TO OPEN 24" CIRCULATION SWEDGE PROTECTOR DUE TO WRONG INSTALLATION.
2900 | 10/31/2022 | 31 Oct 1545 - 1630 | MNHZ-221200 | SSA-5914 | WCR | FOT | .75 | .75 | 904161 |  | TF | 1160 | CTRQ | DIESEL POWER UNIT FOR POWER TONG NOT WORKED.
2901 | 10/31/2022 | 31 Oct 0100 - 0215 | MNHZ-221200 | SSA-5914 | RIG | FOT | 1.25 | 1.25 | 904197 |  | RR | 1160 | CSYS | EXCESSIVE TIME TO OPEN 24" CIRCULATION SWEDGE PROTECTOR DUE TO WRONG INSTALLATION.
2903 | 10/31/2022 | 31 Oct 1700 - 1930 | UTMN-3044 | SSA-5964 | WCR | WOTO | 2.5 | 2.5 | 904179 |  | WO | 0 | NA | WAITING FOR WEATHERFORD JAM UNIT FOR RUNNING UPPER COMPLETION.
2905 | 10/31/2022 | 26 Oct 0645 - 0500 | UTMN-3193 | SSA-5970 | NCS | CFST | 19.5 | 96.5 | 904073 |  | CMT | 0 | NA | CMT FLUSH SET.
2907 | 10/31/2022 | 30 Oct 1545 - 1230 | ABSD-1 | T907 | RIG | SRVC | 7.5 | 18.75 | 904156 |  | WO | 14592 | NA | AS PER SCHEDULE G, KCA IS RESPONSIBLE TO SUPPLY POWER TONGS, AT TIME OF POOH, THEIR VENDOR BACKED OUT.