## Sheet1
SEQ | Report Date | Rig Name | Well No | Company Name | Date and Time | Time in Hrs | Cummulative Hrs | LT ID | Parent LT ID | LT Type | Cause | Object | Depth | LT Summary
1 | 02/01/2022 | ADC-17 | ZULF-1210 | RIG | 01 Feb 1915 - 2215 | 3 | 3 | 890606 |  | RR | FOT | CSYS | 6470 | ATTEMPT TO PT SURFACE LINES ON RIG. OBSERVE LOSS IN PRESSURE. TROUBLESHOOT AND LOOK FOR LEAK IN STANDPIPE MANIFOLD. GREASE AND WORK ALL VALVES ON RIG FLOOR.
3 | 02/01/2022 | ADC-42L | UTMN-2319 | TK3 | 24 Jan 1545 - 0500 | 22.5 | 197.25 | 889625 |  | DRG | WNCA | NA | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
5 | 02/01/2022 | ADC-65L | HRDH-1980 | SWL | 31 Jan 1415 - 1630 | 11.5 | 26.25 | 890488 |  | TF | FOT | WLT | 11760 | THE RESISTIVITY DATA SENT FOR THIS WELL WAS NOT ACCEPTED.
7 | 02/01/2022 | ADES-14 | HRDH-476 | BHI | 31 Jan 1600 - 1030 | 5.5 | 18.5 | 890546 |  | BHA | FOT | MWD | 5200 | MWD FAILURE (INTERMITTENT PULSER FAILURE).
9 | 02/01/2022 | AOD-111 | MRJN-726 | ARM | 22 Jan 1800 - 0500 | 24 | 249.75 | 889152 |  | TH | NARW | NA | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
11 | 02/01/2022 | ARO-3003 | SFNY-1150 | RIG | 29 Jan 1000 - 2100 | 16 | 83 | 890246 |  | UPRA | OTH | NA | 7314 | HSE INCIDENT SUSPEND OPERATIONS FOR INVESTIGATION.
13 | 02/01/2022 | BB-84A | MRJN-588 | MSD | 01 Feb 0130 - 0300 | 1.5 | 1.5 | 890493 |  | TF | XTTE | CRT | 4455 | CRT CASING SLIPS WOULD NOT GRAB TO LOWER CASING STRING INTO HOLE
15 | 02/01/2022 | ENS-141 | MRJN-758 | BHI | 01 Feb 1545 - 1615 | .5 | .5 | 890492 |  | TF | FOT | COMP | 8410 | DRILLING WAS STOPPED DUE TO LOSS OF COMMUNICATIONS WITH THE BAKER WELL LINK SYSTEM
17 | 02/01/2022 | EXL-IA | SFNY-4050 | RIG | 31 Jan 0230 - 0500 | 24 | 26.5 | 890526 |  | TF | FOT | PEL | 457 | WHILE PICK UP 30" CASING FROM V DOOR TDS LINK TILT ACCIDENTLY BROKE ELEVATOR EAR LATCH CAUSING THE ELEVATORS TO HANG IN ONLY ONE BAIL ARM.
18 | 02/01/2022 | NA-128S | ZMLH-5 | WTC | 01 Feb 0800 - 1030 | 2.5 | 2.5 | 890608 |  | TF | FOT | TBACC | 0 | TROUBLESHOOT & RECTIFY WELLTEC MPC TOOL ELECTRICAL MALFUNCTION WHILE CONFIGURATION.
20 | 02/01/2022 | NA-128S | ZMLH-5 | WTC | 30 Jan 0500 - 1930 | 12 | 60 | 890446 |  | TF | FOT | TBACC | 13011 | SLB RCT FAILED TO CUT 4.5'' TBG.
21 | 02/01/2022 | NA-128S | ZMLH-5 | WTC | 01 Feb 1930 - 0500 | 9.5 | 9.5 | 890607 |  | TF | FOT | TBACC | 12700 | WELLTEC MPC TOOL GOT SHORT CIRCUIT WHILE POWERING UP.
22 | 02/01/2022 | NA-128S | ZMLH-5 | WTC | 01 Feb 0800 - 1030 | 2.5 | 2.5 | 890608 |  | TF | FOT | TBACC | 0 | TROUBLESHOOT & RECTIFY WELLTEC MPC TOOL ELECTRICAL MALFUNCTION WHILE CONFIGURATION.
24 | 02/01/2022 | NBR-196S | SDGM-1174 | SWL | 27 Jan 0100 - 0500 | 24 | 113.5 | 890026 |  | STUK | HINW | WLT | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
26 | 02/01/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 444 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
28 | 02/01/2022 | NBR-987S | ABTL-2 | HWP | 31 Jan 1600 - 0900 | 4 | 17 | 890527 |  | TF | FOT | WLT | 10995 | UNABLE TO WORK FREE THE CSG AFTER CASING CUTTER RUN @ 10,995' POSSIBLY DUE TO PARTIAL CUTTING.
30 | 02/01/2022 | RBP-50A | HSBH-58 | RIG | 25 Jan 0100 - 0500 | 24 | 161 | 889765 |  | UPRA | OTH | NA | 13243 | WHILE JACKING RIG DOWN FOR WATER INTEGRITY TEST OBSERVED PORT LEG BOW GEAR BOX FAILURE, BULL GEAR DAMAGED AND 2 TEETH MISSING FROM CHORD/JACKING COLUMN.
32 | 02/01/2022 | SINO-12L | HRDH-447 | RIG | 01 Feb 1200 - 1430 | 2.5 | 2.5 | 890586 |  | TF | FOT | TESTT | 0 | BOP TEST UNIT FAILURE.
34 | 02/01/2022 | SNF036 | MRJN-901 | ARM | 01 Feb 0600 - 0730 | 1.5 | 1.5 | 890585 |  | BHA | ETRQ | BHA | 2802 | UNABLE TO BREAK 28" NBRR AND 28" STRING RR FROM 14" SHOCK SUB
36 | 02/01/2022 | SP-110 | HWYH-127 | WDS | 31 Jan 0030 - 0500 | 23.5 | 28 | 890486 |  | BHA | FOT | RSS | 8570 | WFD MAGNUS RSS TOOL UNABLE TO BUILD INCLINATION AS PER PLAN
37 | 02/01/2022 | SP-260 | HZEM-141612 | BHI | 01 Feb 2300 - 2330 | .5 | .5 | 890605 |  | BHA | FOT | MWD | 10949 | LOST MWD SIGNAL
39 | 02/01/2022 | SP-260 | HZEM-141612 | BHI | 24 Jan 0545 - 0915 | 4.25 | 171.5 | 889506 |  | BHA | FOT | RSS | 10369 | BAKER RSS BROKEN, LOST IN THE HOLE BIT BOX OF BAKER RSS AND BIT.
40 | 02/01/2022 | SP-260 | HZEM-141612 | BHI | 01 Feb 2300 - 2330 | .5 | .5 | 890605 |  | BHA | FOT | MWD | 10949 | LOST MWD SIGNAL
42 | 02/01/2022 | SP-306 | MNIF-865 | RIG | 25 Jan 0330 - 0500 | 24 | 169.5 | 889885 |  | BHA | FOT | DC | 4309 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
44 | 02/01/2022 | SSA-46 | JAHM-5 | ARM | 29 Jan 1845 - 0500 | 24 | 82.25 | 890215 |  | WO | STOP | NA | 3790 | RIG SHUT DOWN BY GOVT ENVIRONMENTAL GUARDS DUE TO OPERATION PERMISSION IN THE NATURE RESERVE NOT BEING ISSUED.
46 | 02/01/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 0500 | 23.5 | 386 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
48 | 02/01/2022 | STY-038 | ZULF-2083 | SRT | 31 Jan 0500 - 0500 | 23.5 | 47.5 | 890528 |  | BHA | FOT | STZRM | 6070 | WHILE TRYING TO FREE PIPE SMITH STABILIZER PARTED DUE TO A FATIGUE OF THE MATERIAL.
50 | 02/02/2022 | ADC-41L | UTMN-3105 | RIG | 02 Feb 1330 - 1430 | 1 | 1 | 890656 |  | RR | FPMP | MPMP | 6120 | RIGS PUMPS 1 AND 2 BEING REPAIRED - FAILED PUMP HEADS
52 | 02/02/2022 | ADC-42L | UTMN-2319 | TK3 | 24 Jan 1545 - 0500 | 24 | 221.25 | 889625 |  | DRG | WNCA | NA | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
53 | 02/02/2022 | ADC-68L | KRSN-705 | ARM | 02 Feb 1715 - 1830 | 1.25 | 1.25 | 890705 |  | LCIR | CFFM | MDCAP | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT
55 | 02/02/2022 | ADC-68L | KRSN-705 | ARM | 02 Feb 1845 - 0500 | 10.25 | 10.25 | 890654 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRED LOSSES @4192 FT , OPENED MORE LOSSES ZONE
56 | 02/02/2022 | ADC-68L | KRSN-705 | ARM | 02 Feb 1715 - 1830 | 1.25 | 1.25 | 890705 |  | LCIR | CFFM | MDCAP | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT
58 | 02/02/2022 | ADM-511 | MRJN-2011 | RIG | 02 Feb 0600 - 0715 | 1.25 | 1.25 | 890665 |  | RR | FOT | TDS | 8020 | CHANGE OUT HYDRAULIC HOSE ON BX ELEVATOR
60 | 02/02/2022 | ADM-656 | ABSF-134 | ARN | 02 Feb 0930 - 0500 | 19.5 | 19.5 | 890667 |  | WO | STOP | NA | 0 | RIG MOVE BOAT UNABLE TO COMPLETE RIG MOVE DUE TO PROBLEM WITH BOW THRUSTER.
62 | 02/02/2022 | AOD-111 | MRJN-726 | ARM | 22 Jan 1800 - 0500 | 24 | 273.75 | 889152 |  | TH | NARW | NA | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
64 | 02/02/2022 | DPS-43 | SDGM-1187 | SJC | 02 Feb 0730 - 0500 | 21.5 | 21.5 | 890686 |  | WO | SRVC | NA | 13260 | TAQA CMT SLURRY LAB TEST SHOWED A SHORT THICKENING TIME THAN REQUIRED. DUMPED MIXED FLUID. INVESTIGATE AND PREPARED A NEW ONE. WAIT ON TAQA CMT SLURRY LAB RESULTS & CONFIRMATION.
66 | 02/02/2022 | ENS-141 | MRJN-758 | BHI | 02 Feb 0600 - 0500 | 20.75 | 20.75 | 890649 |  | BHA | FOT | LWD | 9212 | BAKER LWD DENSITY TOOL FAILED. DESICION MADE TO POOH AND P/U NEW TOOLS
68 | 02/02/2022 | EXL-IA | SFNY-4050 | RIG | 31 Jan 0230 - 0500 | 23 | 49.5 | 890526 |  | TF | FOT | PEL | 457 | WHILE PICK UP 30" CASING FROM V DOOR TDS LINK TILT ACCIDENTLY BROKE ELEVATOR EAR LATCH CAUSING THE ELEVATORS TO HANG IN ONLY ONE BAIL ARM.
70 | 02/02/2022 | MP-1 | LWHH-28 | SMI | 02 Feb 0215 - 0245 | .5 | .5 | 890655 |  | MUD | IPDF | NA | 5885 | WHILE POOH WITH 8-1/2" RSS ASS'Y INSIDE 9-5/8" CSG. STRING STUCK INSIDE CASING @ 5885' DUE TO CUTTINGS ACCUMULATION.
71 | 02/02/2022 | NA-128S | ZMLH-5 | BAW | 02 Feb 1100 - 1345 | 2.75 | 2.75 | 890648 |  | STUK | HINW | WLT | 12695 | BAKER MPC TOOL GOT STUCK AFTER CUTTING TBG.
73 | 02/02/2022 | NA-128S | ZMLH-5 | SWL | 30 Jan 0500 - 1100 | 6 | 69 | 890446 |  | TF | FOT | CUT | 13011 | SLB RCT FAILED TO CUT 4.5'' TBG.
74 | 02/02/2022 | NA-128S | ZMLH-5 | BAW | 02 Feb 1100 - 1345 | 2.75 | 2.75 | 890648 |  | STUK | HINW | WLT | 12695 | BAKER MPC TOOL GOT STUCK AFTER CUTTING TBG.
76 | 02/02/2022 | NBR-196S | SDGM-1174 | SWL | 27 Jan 0100 - 0500 | 24 | 137.5 | 890026 |  | STUK | HINW | WLT | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
78 | 02/02/2022 | NBR-591S | HRDH-1933 | ARM | 02 Feb 0800 - 1500 | 7 | 7 | 890666 |  | WCNT | WC20 | NA | 8310 | WHILE RIH @ 8310', NOTICE GAIN. SPACE OUT & SHUT IN WELL W/ 12 BBL GAIN. RECORD SIDP=100 PSI & SICP=410 PSI.
80 | 02/02/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 23 | 466.75 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
82 | 02/02/2022 | PA-604S | HRDH-1392 | RIG | 02 Feb 1315 - 1615 | 3 | 3 | 890658 |  | RR | LHFL | HSYS | 4000 | HYDRAULIC HOSE ON TDS WAS LEAKING.
84 | 02/02/2022 | RBP-50A | HSBH-58 | RIG | 25 Jan 0100 - 0500 | 24 | 185 | 889765 |  | UPRA | OTH | NA | 13243 | WHILE JACKING RIG DOWN FOR WATER INTEGRITY TEST OBSERVED PORT LEG BOW GEAR BOX FAILURE, BULL GEAR DAMAGED AND 2 TEETH MISSING FROM CHORD/JACKING COLUMN.
86 | 02/02/2022 | SINO-18 | ADHN-10 | RIG | 02 Feb 1400 - 2200 | 8 | 8 | 890646 |  | RR | FOT | TDS | 2592 | OBSERVE MUD LEAKING FROM THE TDS. POOH TO THE SHOE TO CHANGE OUT THE TDS STD PIPE PACKING. OBSERVE A CRACK ON THE FACE OF THE STANDPIPE INSERT.
88 | 02/02/2022 | SINO-28L | SHYB-243 | BAW | 02 Feb 1945 - 0500 | 9.25 | 9.25 | 890652 |  | TF | FOT | WLT | 8987 | LOST COMMUNICATION WITH SDN DENSITY TOOL.
90 | 02/02/2022 | SP-110 | HWYH-127 | WDS | 31 Jan 0030 - 0500 | 24 | 52 | 890486 |  | BHA | FOT | RSS | 8570 | WFD MAGNUS RSS TOOL UNABLE TO BUILD INCLINATION AS PER PLAN
92 | 02/02/2022 | SP-258 | HZEM-160614 | ITS | 02 Feb 0945 - 1045 | 1 | 1 | 890657 |  | TF | FOT | CTRQ | 11922 | ITS PIPE RUNNER POWER UNIT WENT OUT OF ORDER.
94 | 02/02/2022 | SP-260 | HZEM-141612 | BHI | 01 Feb 2300 - 0500 | 21 | 21.5 | 890605 |  | BHA | FOT | MWD | 10949 | LOST MWD SIGNAL
96 | 02/02/2022 | SP-306 | MNIF-865 | RIG | 25 Jan 0330 - 0500 | 24 | 193.5 | 889885 |  | BHA | FOT | DC | 4309 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
98 | 02/02/2022 | SSA-102 | QTIF-699 | SLH | 02 Feb 1700 - 0000 | 7 | 7 | 890651 |  | TF | FOT | HGRL | 9590 | LOST TIME ON SLB LINER HANGER DUE TO 7" WIPER PLUG DID NOT FULLY WIPED CMT AHEAD OF IT & LEFT CMT SHEET ON THE LOW SIDE OF 7" CSG WHICH RESULTED TO TAG CMT SHEET SHALLOWER & REAM DOWN.
100 | 02/02/2022 | SSA-46 | JAHM-5 | ARM | 29 Jan 1845 - 0500 | 24 | 106.25 | 890215 |  | WO | STOP | NA | 3790 | RIG SHUT DOWN BY GOVT ENVIRONMENTAL GUARDS DUE TO OPERATION PERMISSION IN THE NATURE RESERVE NOT BEING ISSUED.
101 | 02/02/2022 | SSA-5859 | HWYH-1265 | SPS | 02 Feb 1200 - 1630 | 4.5 | 4.5 | 890653 |  | BHA | FOT | MMOT | 3180 | EXCESS TIME TO SET UP BENT HOUSING OF SPERRY MUD MOTOR FROM 2.12 DEG TO 1.85 DEG.
103 | 02/02/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 0500 | 19 | 405 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
104 | 02/02/2022 | SSA-5859 | HWYH-1265 | SPS | 02 Feb 1200 - 1630 | 4.5 | 4.5 | 890653 |  | BHA | FOT | MMOT | 3180 | EXCESS TIME TO SET UP BENT HOUSING OF SPERRY MUD MOTOR FROM 2.12 DEG TO 1.85 DEG.
106 | 02/02/2022 | SSA-5964 | SDGM-1158 | RIG | 02 Feb 0500 - 0500 | 24 | 24 | 890647 |  | RR | FOT | DWKS | 14516 | FAILURE ON BEARING IN DRAW WORKS GEAR BOX
108 | 02/02/2022 | SSA-5970 | HWYH-1257 | RIG | 02 Feb 1615 - 1730 | 1.25 | 1.25 | 890650 |  | DD | FPMP | MMOT | 12960 | MWD LOST SIGNAL,
110 | 02/02/2022 | STY-038 | ZULF-2083 | SRT | 31 Jan 0500 - 0500 | 24 | 71.5 | 890528 |  | BHA | FOT | STZRM | 6070 | SMITH STABILIZER PARTED DUE TO A FATIGUE OF THE MATERIAL.
112 | 02/03/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 15.25 | 15.25 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
114 | 02/03/2022 | ADC-42L | UTMN-2319 | TK3 | 24 Jan 1545 - 0730 | 2.5 | 223.75 | 889625 |  | DRG | WNCA | NA | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
116 | 02/03/2022 | ADC-56L | UTMN-3011 | RIG | 03 Feb 0200 - 0300 | 1 | 1 | 890807 |  | RR | FOT | MPMP | 12555 | SIMULTANEOUS PISTON FAILURE ON BOTH PUMPS
118 | 02/03/2022 | ADC-65L | HRDH-1980 | SLH | 03 Feb 1400 - 1945 | 5.75 | 5.75 | 890827 |  | TF | FOT | HGRL | 11760 | ATTEMPT TO SET PACKERPLUS PRIMESET LINER HANGER, FOUND PRESSURE BLEEDOFF AFTER SHEAR FIRST BALL SEAT AND BALL NOT LANDED IN 2ND BALL SEAT TO SET LINER HANGER.
119 | 02/03/2022 | ADC-68L | KRSN-705 | TK3 | 03 Feb 1200 - 0500 | 17 | 17 | 890830 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT,SPOT TWO LCM PILLS, POOH FOR SPOT CEMENT PLUG
121 | 02/03/2022 | ADC-68L | KRSN-705 | TK3 | 02 Feb 1845 - 1145 | 6.75 | 17 | 890654 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRED LOSSES @4192 FT , OPENED MORE LOSSES ZONE, SPOT LCM PILLS
122 | 02/03/2022 | ADC-68L | KRSN-705 | TK3 | 03 Feb 1200 - 0500 | 17 | 17 | 890830 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT,SPOT TWO LCM PILLS, POOH FOR SPOT CEMENT PLUG
124 | 02/03/2022 | ADES-174 | HRDH-2184 | CRW | 03 Feb 2145 - 0500 | 7.25 | 7.25 | 890831 |  | BHA | FOT | WBCL | 13955 | 9 5/8'' LTTT PACKER ELEMENTS FAILED DURING NEGATIVE TEST OPERATION WHILE DISPLACE AND BLEED OFF DIFFERENTIAL PRESSURE
125 | 02/03/2022 | ADM-511 | MRJN-2011 | ARM | 03 Feb 1430 - 1715 | 2.75 | 2.75 | 890806 |  | WON | WTHR | NA | 19175 | UNABLE TO OFFLOAD SUPPLY VESSEL DUE TO ADVERSE WEATHER CONDITIONS
127 | 02/03/2022 | ADM-511 | MRJN-2011 | RIG | 03 Feb 0615 - 0500 | 11 | 11 | 890785 |  | RR | FOT | SWVL | 19175 | TOP DRIVE MECHANICAL WASH PIPE SEALS LEAKING BRINE
128 | 02/03/2022 | ADM-511 | MRJN-2011 | ARM | 03 Feb 1430 - 1715 | 2.75 | 2.75 | 890806 |  | WON | WTHR | NA | 19175 | UNABLE TO OFFLOAD SUPPLY VESSEL DUE TO ADVERSE WEATHER CONDITIONS
130 | 02/03/2022 | ADM-655 | QTIF-98 | ARM | 03 Feb 1200 - 0500 | 17 | 17 | 890690 |  | WON | WTHR | NA | 0 | UNABLE TO DEPART AND MOVE RIG FROM BRRI-147/150 PF TO QTIF-96/101, 228 PF DUE TO WEATHER.
131 | 02/03/2022 | ADM-656 | ABSF-134 | ARM | 03 Feb 0830 - 0500 | 20.5 | 20.5 | 890745 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO MOVE RIG INTO FINAL POSITION.
133 | 02/03/2022 | ADM-656 | ABSF-134 | ARN | 02 Feb 0930 - 0830 | 3.5 | 23 | 890667 |  | WO | STOP | NA | 0 | RIG MOVE BOAT UNABLE TO COMPLETE RIG MOVE DUE TO PROBLEM WITH BOW THRUSTER.
134 | 02/03/2022 | ADM-656 | ABSF-134 | ARM | 03 Feb 0830 - 0500 | 20.5 | 20.5 | 890745 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO MOVE RIG INTO FINAL POSITION.
136 | 02/03/2022 | AOD-11 | SFNY-1502 | RWC | 02 Feb 0630 - 0945 | 3.75 | 14.25 | 890689 |  | WO | SRVC | NA | 0 | IMPROPER TANK HANDLING. TANK ON RIG GOT FULL & WAITING ON RAWABI WELL TESTING TANKS.
138 | 02/03/2022 | AOD-111 | MRJN-726 | ARM | 22 Jan 1800 - 0500 | 24 | 297.75 | 889152 |  | TH | NARW | NA | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
140 | 02/03/2022 | ARO-3003 | SFNY-1150 | RIG | 03 Feb 1000 - 2330 | 13.5 | 13.5 | 890765 |  | DSF | FOT | DP | 7314 | UNABLE TO TEST RAMS AGAINST JOINT 4" DRILL PIPE.
142 | 02/03/2022 | DPS-43 | SDGM-1187 | SJC | 02 Feb 0730 - 1100 | 6 | 27.5 | 890686 |  | WO | SRVC | NA | 13260 | TAQA CMT SLURRY LAB TEST SHOWED A SHORT THICKENING TIME THAN REQUIRED. DUMPED MIXED FLUID. INVESTIGATE AND PREPARED A NEW ONE. WAIT ON TAQA CMT SLURRY LAB RESULTS & CONFIRMATION.
144 | 02/03/2022 | ENS-141 | MRJN-758 | BHI | 02 Feb 0600 - 0930 | 4.5 | 25.25 | 890649 |  | BHA | FOT | LWD | 9212 | BAKER LWD DENSITY TOOL FAILED. DESICION MADE TO POOH AND P/U NEW TOOLS
146 | 02/03/2022 | EXL-IA | SFNY-4050 | RIG | 31 Jan 0230 - 0500 | 23 | 72.5 | 890526 |  | TF | FOT | PEL | 457 | WHILE PICK UP 30" CASING FROM V DOOR TDS LINK TILT ACCIDENTLY BROKE ELEVATOR EAR LATCH CAUSING THE ELEVATORS TO HANG IN ONLY ONE BAIL ARM.
148 | 02/03/2022 | NBR-196S | SDGM-1174 | SWL | 27 Jan 0100 - 0500 | 24 | 161.5 | 890026 |  | STUK | HINW | WLT | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
150 | 02/03/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 23.5 | 490.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
152 | 02/03/2022 | SINO-12L | HRDH-447 | BC | 03 Feb 0215 - 0500 | 2.75 | 2.75 | 890789 |  | STUK | STCT | EQLZR | 7452 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION
154 | 02/03/2022 | SINO-27N | HRDH-485 | BAW | 03 Feb 2200 - 0500 | 7 | 7 | 890828 |  | TF | FOT | WLT | 7911 | AS PER RDD REQUEST NEED TO RUN RTEX TO CONFIRM DATA FROM OH RUN#1 (HDIL LOG)
156 | 02/03/2022 | SINO-28L | SHYB-243 | BHI | 02 Feb 1945 - 1700 | 10 | 19.25 | 890652 |  | BHA | FOT | LWD | 8987 | LOST COMMUNICATION WITH SDN DENSITY/NEUTRON LWD TOOL.
158 | 02/03/2022 | SINO-43L | UTMN-4808 | BHT | 03 Feb 2115 - 0500 | 7.75 | 7.75 | 890788 |  | TF | FOT | BIT | 4821 | DROP ON ROP FROM 50 FR/HR TO 2 FT/HR, TRIED DIFFERENT DRILLING PARAMETERS, NO IMPROVEMENT.
159 | 02/03/2022 | SP-110 | HWYH-127 | RIG | 03 Feb 2330 - 0500 | 5.5 | 5.5 | 890825 |  | RR | FOT | TDS | 8841 | LEAK IN TOP DRIVE SYSTEM SAVER SUB. POOH TO INSIDE CSG AND CHANGE SAVER SUB.
161 | 02/03/2022 | SP-110 | HWYH-127 | WDS | 31 Jan 0030 - 1500 | 10 | 62 | 890486 |  | BHA | FOT | RSS | 8570 | WFD MAGNUS RSS TOOL UNABLE TO BUILD INCLINATION AS PER PLAN
162 | 02/03/2022 | SP-110 | HWYH-127 | RIG | 03 Feb 2330 - 0500 | 5.5 | 5.5 | 890825 |  | RR | FOT | TDS | 8841 | LEAK IN TOP DRIVE SYSTEM SAVER SUB. POOH TO INSIDE CSG AND CHANGE SAVER SUB.
164 | 02/03/2022 | SP-124 | ABHD-6 | BHI | 03 Feb 1700 - 0500 | 12 | 12 | 890786 |  | BHA | FOT | LWD | 9229 | HAD NO RESPONSE FROM BAKER NMR LOGGING TOOL (NMR MAGTRAK SENSOR, NUCLAR MAGNETIC RESONANCE), MANY TRIALS ATTEMPTING TO TROUBLE-SHOOT THE LOGGING TOOL, NO SUCCESS.
166 | 02/03/2022 | SP-258 | HZEM-160614 | RIG | 03 Feb 0245 - 0500 | 2.25 | 2.25 | 890829 |  | TF | XTTE | BOP | 0 | EXCESSIVE TIME TO N/D BOP.
168 | 02/03/2022 | SP-260 | HZEM-141612 | BHI | 01 Feb 2300 - 0730 | 2.5 | 24 | 890605 |  | BHA | FOT | MWD | 10949 | LOST MWD SIGNAL
170 | 02/03/2022 | SP-306 | MNIF-865 | RIG | 25 Jan 0330 - 0500 | 24 | 217.5 | 889885 |  | DSF | FOT | DP | 4309 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
172 | 02/03/2022 | SSA-102 | QTIF-699 | NCS | 03 Feb 0730 - 0830 | 1 | 1 | 890787 |  | CMT | WSHO | CSG | 11490 | LOST TIME ON NPS CEMENTING DUE TO SOFT CMT WHILE DRILL OUT SHOE TRACK.
174 | 02/03/2022 | SSA-46 | JAHM-5 | ARN | 29 Jan 1845 - 0430 | 23.5 | 129.75 | 890215 |  | WO | STOP | NA | 3790 | RIG SHUT DOWN BY GOVT ENVIRONMENTAL GUARDS DUE TO OPERATION PERMISSION IN THE NATURE RESERVE NOT BEING ISSUED.
176 | 02/03/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 0500 | 23.5 | 428.5 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
178 | 02/03/2022 | SSA-5962 | KHRS-1314 | SC1 | 03 Feb 0000 - 0500 | 5 | 5 | 890826 |  | TF | FOT | CTAC | 16634 | COMPLETION ENERGY 2-7/8" CT AGITATOR FAILURE.
180 | 02/03/2022 | SSA-5964 | SDGM-1158 | RIG | 02 Feb 0500 - 0130 | 20.5 | 44.5 | 890647 |  | RR | FOT | DWKS | 14516 | FAILURE ON BEARING IN DRAW WORKS GEAR BOX
182 | 02/03/2022 | SSA-5970 | HWYH-1257 | SDM | 03 Feb 2000 - 0500 | 9 | 9 | 890808 |  | DD | UDWL | RSS | 13285 | RSS COULDN'T REACH THE PLANNED BUR 3.5 TO 4 DEG/100 FT,
184 | 02/03/2022 | STY-038 | ZULF-2083 | SRT | 31 Jan 0500 - 1100 | 6 | 77.5 | 890528 |  | BHA | FOT | STZRM | 6070 | SMITH STABILIZER PARTED DUE TO A FATIGUE OF THE MATERIAL.
186 | 02/03/2022 | WCL-83 | MRJN-831 | MSL | 03 Feb 2345 - 0200 | 2.25 | 2.25 | 890805 |  | TF | FOT | SLICK | 5653 | ATTEMPTED TO PRESSURE TEST PX PLUG, OBSERVED LEAK FROM LUBRICATOR CONNECTION, CHANGED LUBRICATOR SEALS, ATTEMPTED TO PRESSURE TEST PX PLUG, OBSERVED RETRUNS FROM TCA, PX PLUG WAS NOT PROPERLY SET.
188 | 02/04/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 39.25 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
190 | 02/04/2022 | ADC-68L | KRSN-705 | TK3 | 03 Feb 1200 - 0500 | 24 | 41 | 890830 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT,SPOT TWO LCM PILLS, POOH FOR SPOT CEMENT PLUG
192 | 02/04/2022 | ADES-174 | HRDH-2184 | CRW | 03 Feb 2145 - 2000 | 15 | 22.25 | 890831 |  | BHA | FOT | WBCL | 13955 | 9 5/8'' LTTT PACKER ELEMENTS FAILED DURING NEGATIVE TEST OPERATION WHILE DISPLACE AND BLEED OFF DIFFERENTIAL PRESSURE
194 | 02/04/2022 | ADM-655 | QTIF-98 | ARM | 04 Feb 2030 - 0500 | 8.5 | 8.5 | 890887 |  | WON | DAY | NA | 0 | WAIT ON DAYLIGHT TO APPROACH & POSITION RIG ON QTIF-96/101 PF.
196 | 02/04/2022 | ADM-656 | ABSF-134 | ARM | 03 Feb 0830 - 0800 | 3 | 23.5 | 890745 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO MOVE RIG INTO FINAL POSITION.
198 | 02/04/2022 | AOD-111 | MRJN-726 | ARM | 22 Jan 1800 - 1530 | 10.5 | 308.25 | 889152 |  | TH | NARW | NA | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
200 | 02/04/2022 | ARO-3004 | KARN-46 | RIG | 04 Feb 1645 - 1715 | .5 | .5 | 890886 |  | RR | FOT | DWKS | 10110 | LEAK ON STEEL HYDRAULIC HOSE ON DRAW WORKS. REPAIR THE SAME
202 | 02/04/2022 | BB-84A | MRJN-586 | RIG | 04 Feb 2330 - 0500 | 5.5 | 5.5 | 890890 |  | BOP | LHFL | RWCS | 5278 | HYDRAULIC OIL LEAKING FROM ANNULAR WEAP HOLE
204 | 02/04/2022 | ENSCO-54 | ABSF-105 | ARM | 04 Feb 1600 - 0500 | 13 | 13 | 890833 |  | WON | DAY | NA | 0 | WAIT ON DAY LIGHT.
206 | 02/04/2022 | ENSCO-76 | MRJN-2004 | RIG | 04 Feb 2045 - 2300 | 2.25 | 2.25 | 890846 |  | RR | FOT | SWVL | 13540 | SWIVEL PACKING FAILED WHILE DRILLING 8-1/2" HOLE SECTION.
207 | 02/04/2022 | EXL-IA | SFNY-4050 | RIG | 04 Feb 1830 - 0145 | 5.5 | 5.5 | 890889 |  | JF | HERR | NA | 374 | CTU INSERT BUSHING CAME OUT AND FELL TO THE SEABED DUE TO RIG CREWS LEAVING THE AREA WHILE INSTRUCTED TO STAY AND WATCH. NOT FOLLOWING PROCEDURES.
209 | 02/04/2022 | EXL-IA | SFNY-4050 | RIG | 31 Jan 0230 - 0500 | 18 | 90.5 | 890526 |  | TF | FOT | PEL | 457 | WHILE PICK UP 30" CASING FROM V DOOR TDS LINK TILT ACCIDENTLY BROKE ELEVATOR EAR LATCH CAUSING THE ELEVATORS TO HANG IN ONLY ONE BAIL ARM.
210 | 02/04/2022 | EXL-IA | SFNY-4050 | RIG | 04 Feb 1830 - 0145 | 5.5 | 5.5 | 890889 |  | JF | HERR | NA | 374 | CTU INSERT BUSHING CAME OUT AND FELL TO THE SEABED DUE TO RIG CREWS LEAVING THE AREA WHILE INSTRUCTED TO STAY AND WATCH. NOT FOLLOWING PROCEDURES.
212 | 02/04/2022 | HI-5 | MHRH-60 | RIG | 04 Feb 0030 - 0430 | 4 | 4 | 890834 |  | RR | FOT | TDS | 8215 | OBSERVED THE IBOP IN TDS HAD OBSTRUCTION TO OPEN & CLOSED.
214 | 02/04/2022 | NBR-196S | SDGM-1174 | SWL | 27 Jan 0100 - 0500 | 24 | 185.5 | 890026 |  | STUK | HINW | WLT | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
216 | 02/04/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 23 | 513.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
218 | 02/04/2022 | PA-218S | QTIF-515 | HCM | 04 Feb 0730 - 2200 | 14.5 | 14.5 | 890865 |  | TF | FOT | PUMP | 2950 | MALFUNCTION OF HALL CEMENT UNIT MIXER, CHANGE CEMENT UNIT
220 | 02/04/2022 | PA-861S | HRDH-1332 | RIG | 04 Feb 2200 - 0500 | 7 | 7 | 890888 |  | RR | FOT | TDS | 0 | TOP DRIVE CERTIFICATION EXPIRE AT 2/7/2022
222 | 02/04/2022 | SCTD-2 | UTMN-1889 | SDM | 04 Feb 0600 - 1730 | 11.5 | 11.5 | 890850 |  | BHA | FOT | MWD | 10190 | LOST COMMUNICATIONS WITH DOWN HOLE TOOLS
223 | 02/04/2022 | SINO-10 | UMTW-1 | SAM | 04 Feb 2100 - 2245 | 1.75 | 1.75 | 890848 |  | BHA | FOT | WBCL | 3850 | FUNCTION TEST PBL SUB AT SURFACE - TOOL OPENED, BUT FAILED TO CLOSE
225 | 02/04/2022 | SINO-10 | UMTW-1 | ARM | 18 Jan 1215 - 0500 | 22.25 | 132 | 888745 |  | LCIR | UVLC | NA | 3794 | UN- CONTROLLABLE /UN-EXPECTED COMPLETE LOSSES ACROSS THE TARGET FORMATION , LEAD TO COLLAPSED HOLE AND STRING STUCK
226 | 02/04/2022 | SINO-10 | UMTW-1 | SAM | 04 Feb 2100 - 2245 | 1.75 | 1.75 | 890848 |  | BHA | FOT | WBCL | 3850 | FUNCTION TEST PBL SUB AT SURFACE - TOOL OPENED, BUT FAILED TO CLOSE
228 | 02/04/2022 | SINO-11 | UMJF-17 | MSD | 03 Feb 0300 - 1700 | 12 | 14 | 890790 |  | TF | FOT | CTRQ | 4850 | RIH WITH 2.876' DRIFT FOR 3-1/2 TBG AT 1398' COULDN'T PASS DUE TO TBG COLAPS BELOW COUPLING.
230 | 02/04/2022 | SINO-12L | HRDH-447 | TK1 | 03 Feb 0215 - 1200 | 7 | 9.75 | 890789 |  | STUK | STBG | TBG | 7452 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION
232 | 02/04/2022 | SINO-25 | MNIF-143 | APC | 04 Feb 0700 - 1500 | 8 | 8 | 890847 |  | WO | WOTO | NA | 303 | RMS WAITING ON CORRECT SIZE SPECIAL TOOL TO TORQUE PACKER CABLE PENITRATOR CONNECTION. WRONG SIZE SPECIAL WRENCH FOR TORQUEING THE PACKER CABLE PENITRATOR CONNECTION.
234 | 02/04/2022 | SINO-27N | HRDH-485 | BAW | 03 Feb 2200 - 2230 | 17.5 | 24.5 | 890828 |  | TF | FOT | WLT | 7911 | AS PER RDD REQUEST NEED TO RUN RTEX TO CONFIRM DATA FROM OH RUN#1 (HDIL LOG)
236 | 02/04/2022 | SINO-43L | UTMN-4808 | BHT | 03 Feb 2115 - 1530 | 10.5 | 18.25 | 890788 |  | TF | FOT | BIT | 4821 | DROP ON ROP FROM 50 FR/HR TO 2 FT/HR, TRIED DIFFERENT DRILLING PARAMETERS, NO IMPROVEMENT.
238 | 02/04/2022 | SINO-47 | HRDH-2206 | ARM | 04 Feb 1700 - 2130 | 4.5 | 4.5 | 890849 |  | STUK | STDP | DP | 18389 | DURING CIRCULATION & WHILE WORKING PIPE, STRING STALLED AND GOT STUCK. NO MOVEMENT OR ROTATION, UNRESTRICTED CIRCULATION.
240 | 02/04/2022 | SP-110 | HWYH-127 | RIG | 03 Feb 2330 - 1100 | 6 | 11.5 | 890825 |  | RR | FOT | TDS | 8841 | LEAK IN TOP DRIVE SYSTEM SAVER SUB. POOH TO INSIDE CSG AND CHANGE SAVER SUB.
242 | 02/04/2022 | SP-124 | ABHD-6 | BHI | 03 Feb 1700 - 2100 | 16 | 28 | 890786 |  | BHA | FOT | LWD | 9229 | HAD NO RESPONSE FROM BAKER NMR LOGGING TOOL (NMR MAGTRAK SENSOR, NUCLAR MAGNETIC RESONANCE), MANY TRIALS ATTEMPTING TO TROUBLE-SHOOT THE LOGGING TOOL, NO SUCCESS.
244 | 02/04/2022 | SP-257 | HZEM-141214 | RIG | 04 Feb 1630 - 2200 | 5.5 | 5.5 | 890851 |  | RR | FOT | DWKS | 3475 | DRAW WORKS CLUTCH SEAL FAILURE.
246 | 02/04/2022 | SP-258 | HZEM-160614 | RIG | 03 Feb 0245 - 0630 | 1.5 | 3.75 | 890829 |  | TF | XTTE | BOP | 0 | EXCESSIVE TIME TO N/D BOP.
248 | 02/04/2022 | SP-306 | MNIF-865 | RIG | 25 Jan 0330 - 0500 | 24 | 241.5 | 889885 |  | DSF | FOT | DP | 4309 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
250 | 02/04/2022 | SSA-51 | MNIF-254 | GOC | 04 Feb 0700 - 0815 | 1.25 | 1.25 | 890845 |  | TF | FOT | CTRQ | 284 | TROUBLE SHOOT JAM UNIT. GRAPH NOT INDICATING NVAM OPTIMUM SEALING. FOUND ELECTRIC CABLE CONNECTION BETWEEN JAM UNIT & POWER TONG FAILLURE. CHANGED SAME. TESTED OK.
251 | 02/04/2022 | SSA-5859 | HWYH-1265 | SPS | 04 Feb 1400 - 0500 | 14.5 | 14.5 | 890905 |  | DD | AINC | BHA | 2135 | UNABLE TO INITIATE 22" SIDE TRACK HOLE WITH SPERRY SUN ASSEMBLY, NO ANGLE BUILDUP.
253 | 02/04/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 1400 | 9 | 437.5 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
254 | 02/04/2022 | SSA-5859 | HWYH-1265 | SPS | 04 Feb 1400 - 0500 | 14.5 | 14.5 | 890905 |  | DD | AINC | BHA | 2135 | UNABLE TO INITIATE 22" SIDE TRACK HOLE WITH SPERRY SUN ASSEMBLY, NO ANGLE BUILDUP.
256 | 02/04/2022 | SSA-5962 | KHRS-1314 | SC1 | 03 Feb 0000 - 1300 | 8 | 13 | 890826 |  | TF | FOT | CTAC | 16634 | COMPLETION ENERGY 2-7/8" CT AGITATOR FAILURE.
257 | 02/04/2022 | SSA-5970 | HWYH-1257 | RIG | 04 Feb 0400 - 0500 | 1 | 1 | 890852 |  | RR | FOT | DWKS | 7943 | RIG REPAIR ON DRAWWORKS LOW CLOUTCH.
259 | 02/04/2022 | SSA-5970 | HWYH-1257 | SDM | 03 Feb 2000 - 0130 | 19.5 | 28.5 | 890808 |  | DD | UDWL | RSS | 13285 | RSS COULDN'T REACH THE PLANNED BUR 3.5 TO 4 DEG/100 FT,
260 | 02/04/2022 | SSA-5970 | HWYH-1257 | RIG | 04 Feb 0400 - 0500 | 1 | 1 | 890852 |  | RR | FOT | DWKS | 7943 | RIG REPAIR ON DRAWWORKS LOW CLOUTCH.
262 | 02/04/2022 | STY-038 | ZULF-2083 | SRT | 31 Jan 0500 - 0500 | 23.5 | 118.5 | 890528 |  | BHA | FOT | STZRM | 6070 | SMITH STABILIZER PARTED DUE TO A FATIGUE OF THE MATERIAL.
264 | 02/05/2022 | ADC-14 | HRDH-694 | OZT | 05 Feb 1100 - 1300 | 2 | 2 | 890907 |  | TF | FOT | CTPMP | 0 | OIL SERV N2 UNIT FAILURE TROUBLE SHOOT & REPAIR IT.
266 | 02/05/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 23.5 | 62.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
268 | 02/05/2022 | ADC-32 | SDGM-1139 | RIG | 04 Feb 0415 - 0300 | 22 | 22.75 | 890891 |  | JF | HERR | SFLN | 10570 | TAGGED ON TOC @ 10,570' [545' BELOW DV TOOL], APPROX. 1766' SHALLOWER THAN PLAN DUE TO MISS-ALIGNMENT ON SURFACE LINES DURING 9-5/8" 1ST STAGE CMT JOB
270 | 02/05/2022 | ADC-48 | HWYH-1258 | BHI | 05 Feb 0300 - 0500 | 2 | 2 | 890966 |  | TF | XTTE | RSS | 13713 | BHI RSS COMMUNICATION AND UNABLE TO STEER.
272 | 02/05/2022 | ADC-55L | UTMN-3076 | RIG | 05 Feb 1630 - 1800 | 1.5 | 1.5 | 890909 |  | RR | FOT | CHK | 12966 | OBSERVED KILL LINE NRV NOT HOLDING PRESSURE.
274 | 02/05/2022 | ADC-68L | KRSN-705 | TK3 | 03 Feb 1200 - 0500 | 24 | 65 | 890830 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT
276 | 02/05/2022 | ADES-889 | HRDH-1282 | PKP | 05 Feb 1800 - 2200 | 4 | 4 | 890840 |  | TF | FOT | HGRL | 13933 | FAILURE TO RELESE THE RUNNING TOOL
278 | 02/05/2022 | ADM-261 | MRJN-138 | RAC | 05 Feb 1400 - 0500 | 15 | 15 | 890985 |  | JF | UITE | MILL | 0 | FAILURE TO SUPPLY THE CORRECT SIZED HIGH SPEED REAMING TOOL AND MILL TO PERFORM THE 4-1/2" TUBING CLEANOUT OPERATION.
280 | 02/05/2022 | AOD-1 | ZULF-695 | ARM | 05 Feb 0130 - 0500 | 3.5 | 3.5 | 890844 |  | CMT | HERR | NA | 11436 | WHILE RIH TO DESIRED DEPTH FOR SPOTTING P&A PLUG #2, PIPE BECAME PLUGGED. MAKE SEVERAL ATTEMPTS TO CLEAR, UNSUCCESSFUL.
282 | 02/05/2022 | BB-84A | MRJN-586 | RIG | 04 Feb 2330 - 1600 | 11 | 16.5 | 890890 |  | BOP | LHFL | RWCS | 5278 | HYDRAULIC OIL LEAKING FROM ANNULAR WEAP HOLE
284 | 02/05/2022 | CR-36A | ZULF-2038 | SPR | 05 Feb 2100 - 0500 | 8 | 8 | 890842 |  | JF | HERR | CTRQ | 1681 | WITH LAST JOINT, STRING WEIGHT DROPED SUDDENLY F/ 310 KLBS TO 170 KLBS AND THE CASING PARTED FROM BOX OF JT 26.
286 | 02/05/2022 | ENSCO-54 | ABSF-105 | AP2 | 05 Feb 0900 - 1300 | 4 | 4 | 890945 |  | WO | WOPF | NA | 0 | WAIT ON FIELD SERCIVE TO DEPRESSURIZE PLATFORM
288 | 02/05/2022 | EXL-IA | SFNY-4050 | RIG | 31 Jan 0230 - 1300 | 7.5 | 98 | 890526 |  | TF | FOT | PEL | 457 | WHILE PICK UP 30" CASING FROM V DOOR TDS LINK TILT ACCIDENTLY BROKE ELEVATOR EAR LATCH CAUSING THE ELEVATORS TO HANG IN ONLY ONE BAIL ARM.
290 | 02/05/2022 | HI-5 | MHRH-60 | SDM | 05 Feb 0200 - 0500 | 3 | 3 | 890841 |  | BHA | FOT | MWD | 8215 | OBSERVED LOST COMMUNICATION WITH MWD TOOL, TRIED TO REGAIN THE SIGNAL WITH DIFFERENT PARAMETERS WITH NO PROGRESS
292 | 02/05/2022 | NBR-196S | SDGM-1174 | SWL | 27 Jan 0100 - 0600 | 1 | 186.5 | 890026 |  | STUK | HINW | WLT | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
294 | 02/05/2022 | NBR-591S | HRDH-1933 | BHI | 05 Feb 1230 - 0500 | 16.5 | 16.5 | 890925 |  | BHA | FOT | MWD | 18163 | LOST COMMUNICATION W/ BAKER RSS & MWD,
296 | 02/05/2022 | NBR-633S | TRYQ-5 | SWL | 05 Feb 1130 - 0500 | 17.5 | 17.5 | 890908 |  | STUK | HINW | WLT | 9547 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE LOGGING RUN#3 AT 9,547'
298 | 02/05/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 537.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
300 | 02/05/2022 | NBR-987S | ABTL-2 | RIG | 05 Feb 2000 - 0500 | 9 | 9 | 890839 |  | RR | FOT | DWKS | 4519 | DRILLING LINE BACK LASHES AND STUCK DRILLING LINE INTO DRAWWORK DRUM ROW.
302 | 02/05/2022 | PA-861S | HRDH-1332 | RIG | 04 Feb 2200 - 2100 | 16 | 23 | 890888 |  | UPRA | IRES | TDS | 0 | TOP DRIVE CAT IV CERTIFICATION EXPIRE AT 2/7/2022, INCOMPLIANCE OF RIG STANDARDS
304 | 02/05/2022 | SCTD-1 | UTMN-3070 | RIG | 05 Feb 1630 - 0500 | 12.5 | 12.5 | 890838 |  | DD | AINC | BHA | 13320 | D&M FAILED TO FOLLOW THE PLAN ,CREATED EXCESSIVE INCLINATION WITH HIGH DOG LEGS, ATTEMPT TO DROP INCLINATION WITH NO SUCCESS , DECISION MADE TO INITIATE NEW SIDE TRACK AND FOLLOW THE SAME PLAN.
306 | 02/05/2022 | SINO-10 | UMTW-1 | ARM | 18 Jan 1215 - 1330 | 8.5 | 140.5 | 888745 |  | LCIR | UVLC | NA | 3794 | UN- CONTROLLABLE /UN-EXPECTED COMPLETE LOSSES ACROSS THE TARGET FORMATION , LEAD TO COLLAPSED HOLE AND STRING STUCK
308 | 02/05/2022 | SNF036 | MRJN-901 | RIG | 05 Feb 1200 - 1215 | .25 | .25 | 890837 |  | JF | HERR | PSYS | 2802 | RIG POWER OUTAGE - 2 MAIN ENGINES ONLINE WHEN 1 ENGINE #3TRIPPED AND WENT OFFLINE - REMAINING ENGINE UNABLE TO SUPPORT LOAD. ISOLATED ENGINE #3 AND LINED UP TO ENGINE #4 TO RESTORE POWER. (NOTE: RIG HAS 5 EA ENGINES. CURRENT DRILLING OPERATIONS REQUIRES 3 EA ENGINES)
310 | 02/05/2022 | SP-306 | MNIF-865 | RIG | 25 Jan 0330 - 0500 | 24 | 265.5 | 889885 |  | DSF | FOT | DP | 4309 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
312 | 02/05/2022 | SSA-5859 | HWYH-1265 | SPS | 04 Feb 1400 - 0500 | 23.5 | 38 | 890905 |  | DD | AINC | BHA | 2135 | UNABLE TO INITIATE 22" SIDE TRACK HOLE WITH SPERRY SUN ASSEMBLY, NO ANGLE BUILDUP.
314 | 02/05/2022 | SSA-5970 | HWYH-1257 | RIG | 05 Feb 1100 - 1400 | 3 | 3 | 890946 |  | RR | FOT | DWKS | 11097 | OBSERVED LOW CLUTCH WAS NOT DISENGAGING, CHECKED AND FOUND THE 4-WAY VALVE CLOSED AND CANNOT RELEASE AIR. - CHANGED AIR PILOT VALVE IN DRILLER CABIN. - CHANGED 4 WAY VALVE.
316 | 02/05/2022 | STY-038 | ZULF-2083 | SRT | 31 Jan 0500 - 0500 | 24 | 142.5 | 890528 |  | BHA | FOT | STZRM | 6070 | SMITH STABILIZER PARTED DUE TO A FATIGUE OF THE MATERIAL.
318 | 02/05/2022 | T217 | UTMN-488 | RIG | 05 Feb 1600 - 0500 | 13 | 13 | 890965 |  | BOP | FOT | CTRL | 6052 | HYD LEAK ON SHEAR BLIND BOP RAMS
320 | 02/05/2022 | T218 | UTMN-471 | WBP | 04 Feb 0100 - 0500 | 22.5 | 26.5 | 890843 |  | TF | FOT | RBP | 6400 | WFD 4-1/2"RBP LEFT IN HOLE DURING SETTING
322 | 02/06/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 23.5 | 86.25 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
324 | 02/06/2022 | ADC-42L | UTMN-2319 | TK3 | 06 Feb 2230 - 0500 | 6.5 | 6.5 | 890912 |  | STUK | STBH | BHA | 6624 | AT 6,624 FT, STRING STALLED WHILE DRILLING. NO ROTATION. NO MOVEMENT UPWARD. STRING GET STUCK.
326 | 02/06/2022 | ADC-48 | HWYH-1258 | BHI | 05 Feb 0300 - 2100 | 16 | 18 | 890966 |  | TF | XTTE | RSS | 13713 | BHI RSS COMMUNICATION AND UNABLE TO STEER.
328 | 02/06/2022 | ADC-50 | SFNY-1179 | SCP | 06 Feb 1015 - 0500 | 18.75 | 18.75 | 891025 |  | TF | FOT | PKR | 6314 | UNABLE TO RELEASE SLB 9 5/8" X 3 1/2" MRP-ESP PACKER, ATTEMPT SEVERAL TIMES WITH MAX OVER PULL 75 KLB'S, NO SUCCESS.
330 | 02/06/2022 | ADC-62L | ANDR-764 | OTH | 06 Feb 1545 - 1645 | 1 | 1 | 890914 |  | WON | WTHR | NA | 13000 | LOST TIME DUE TO WAITING ON ENVIORNMENTAL CONDITIONS
332 | 02/06/2022 | ADC-68L | KRSN-705 | TK3 | 03 Feb 1200 - 0500 | 24 | 89 | 890830 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT
334 | 02/06/2022 | ADES-144 | UTMN-3041 | WCR | 06 Feb 0930 - 1230 | 3 | 3 | 891005 |  | TF | FOT | CRT | 4500 | CRT PACKER ELEMENT FAILED TO PROVIDE SEAL WHILE FILL UP OR CIRCULATE THROUGH CASING
336 | 02/06/2022 | ADM-261 | MRJN-138 | RAC | 05 Feb 1400 - 0500 | 24 | 39 | 890985 |  | JF | UITE | MILL | 0 | TOOLS SHIPPED TO LOCATION WERE NOT CONFIGURED TO OPERATE WITHIN NEEDED PARAMETERS. - CLEAN OUT OF 4-1/2" TUBING REQUIRED MOTORS W/MORE TORQUE THAN SUPPLIED AND LARGER OD MILLS.
338 | 02/06/2022 | AOD-1 | ZULF-695 | BCM | 05 Feb 0130 - 0600 | 1 | 4.5 | 890844 |  | CMT | FOP | SQZ | 11436 | WHILE RIH TO DESIRED DEPTH FOR SPOTTING P&A PLUG #2, PIPE BECAME PLUGGED. MAKE SEVERAL ATTEMPTS TO CLEAR, UNSUCCESSFUL.
340 | 02/06/2022 | ARO-3003 | SFNY-1150 | RIG | 06 Feb 0500 - 2300 | 18 | 18 | 890990 |  | RR | FOT | SLIPS | 0 | CORE HEAD DAMAGED DUE SLIP COLLAR DIE FALL INTO WELLBORE.
342 | 02/06/2022 | CR-36A | ZULF-2038 | SPR | 05 Feb 2100 - 0500 | 24 | 32 | 890842 |  | JF | HERR | CTRQ | 1681 | WITH LAST JOINT, STRING WEIGHT DROPED SUDDENLY F/ 310 KLBS TO 170 KLBS AND THE CASING PARTED FROM BOX OF JT 26.
344 | 02/06/2022 | DQ-47 | KHRS-369 | TK2 | 06 Feb 1600 - 2315 | 7.25 | 7.25 | 890995 |  | TH | PCPF | NA | 135 | TIGH HOLE WHILE RUNNING CASING.
346 | 02/06/2022 | HI-5 | MHRH-60 | SDM | 05 Feb 0200 - 2100 | 16 | 19 | 890841 |  | BHA | FOT | MWD | 8215 | OBSERVED LOST COMMUNICATION WITH MWD TOOL, TRIED TO REGAIN THE SIGNAL WITH DIFFERENT PARAMETERS WITH NO PROGRESS
348 | 02/06/2022 | NBR-591S | HRDH-1933 | BHI | 05 Feb 1230 - 0500 | 21.5 | 38 | 890925 |  | BHA | FOT | MWD | 18163 | LOST COMMUNICATION W/ BAKER RSS & MWD,
350 | 02/06/2022 | NBR-633S | TRYQ-5 | SWL | 05 Feb 1130 - 1600 | 11 | 28.5 | 890908 |  | STUK | HINW | WLT | 9547 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE LOGGING RUN#3 AT 9,547'
352 | 02/06/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 23 | 560.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
354 | 02/06/2022 | NBR-987S | ABTL-2 | RIG | 05 Feb 2000 - 1330 | 8.5 | 17.5 | 890839 |  | RR | FOT | DWKS | 4519 | DRILLING LINE BACK LASHES AND STUCK DRILLING LINE INTO DRAWWORK DRUM ROW.
356 | 02/06/2022 | PA-622S | ZHRA-1 | RIG | 06 Feb 1000 - 1545 | 5.75 | 5.75 | 890986 |  | RR | FOT | RWCS | 199 | ATTEMPTED ACCUM. & DIVERTER FUNCTIONAL TEST, AIR PUMPS ACTIVATED OVER PRESSURE CONTROL SYSTEM BEFORE REACHING ACCUM. WORKING PRESSURE, AIR PUMP #1 GOT STUCK, ELECTRONIC CONTROLER OF ELECTRICAL PUMP #3 OUT OF SERVICES. OBSERVED SEVERAL LEAKS ON BOTH DIVERTER LINES.
358 | 02/06/2022 | SCTD-1 | UTMN-3070 | RIG | 05 Feb 1630 - 2230 | 17.5 | 30 | 890838 |  | DD | AINC | BHA | 13320 | D&M FAILED TO FOLLOW THE PLAN ,CREATED EXCESSIVE INCLINATION WITH HIGH DOG LEGS, ATTEMPT TO DROP INCLINATION WITH NO SUCCESS , DECISION MADE TO INITIATE NEW SIDE TRACK AND FOLLOW THE SAME PLAN.
360 | 02/06/2022 | SDA | MRJN-732 | RIG | 06 Feb 2000 - 2330 | 3.5 | 3.5 | 890991 |  | RR | FOT | TDS | 0 | ATTEMPT TO RIH 48 STANDS OF 4" DP AND TO L/DOWN IN SINGLES FOR INSPECTION. NOT ABLE TO LATCH WITH 4" DP BX ELEVATOR AT TOP OF STAND ONCE 4" DRILL PIPE STAND IS PLACED IN POSITION WITH PRS FOR RIH.
362 | 02/06/2022 | SL-7 | ZULF-1335 | RIG | 06 Feb 1830 - 1915 | .75 | .75 | 890994 |  | RR | FOT | TDS | 4500 | TROUBLESHOOT IRON ROUGHNECK
364 | 02/06/2022 | SP-161 | HWYH-2551 | RIG | 06 Feb 0300 - 0500 | 2 | 2 | 890993 |  | RR | FOT | DWKS | 8525 | DRILLING LINE NOT SPOOLING PROPERLY.
366 | 02/06/2022 | SP-306 | MNIF-865 | RIG | 25 Jan 0330 - 0500 | 23.5 | 289 | 889885 |  | DSF | FOT | DP | 4309 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
367 | 02/06/2022 | SSA-101 | BRRI-1145 | ARM | 06 Feb 1000 - 1500 | 5 | 5 | 890989 |  | WON | WTHR | NA | 9280 | WAIT ON WEATHER DUE TO HIGH WIND SPEED (55 KM/HR)
369 | 02/06/2022 | SSA-101 | BRRI-1145 | GD1 | 06 Feb 1615 - 1745 | 1.5 | 1.5 | 890988 |  | WO | WOTR | NA | 9280 | GDMC SLICK LINE LUBRICATOR CONNECTION INCOMPATIBILITY ISSUE- USED ADAPTER TO FIX IT.
370 | 02/06/2022 | SSA-101 | BRRI-1145 | ARM | 06 Feb 1000 - 1500 | 5 | 5 | 890989 |  | WON | WTHR | NA | 9280 | WAIT ON WEATHER DUE TO HIGH WIND SPEED (55 KM/HR)
372 | 02/06/2022 | SSA-46 | JAHM-5 | RIG | 06 Feb 0100 - 0400 | 3 | 3 | 891027 |  | RR | FOT | TDS | 1050 | TDS MAIN HYD HOSE THAT SUPPLY HYD TO ROTATE HANDLER AND TILT LINK DAMAGE. REPLACE SAME.
374 | 02/06/2022 | SSA-5859 | HWYH-1265 | SPS | 04 Feb 1400 - 0500 | 23.5 | 61.5 | 890905 |  | DD | AINC | BHA | 2135 | UNABLE TO INITIATE 22" SIDE TRACK HOLE WITH SPERRY SUN ASSEMBLY, NO ANGLE BUILDUP.
376 | 02/06/2022 | SSA-5969 | UTMN-3195 | HCB | 05 Feb 0100 - 0500 | 24 | 28 | 891006 |  | TF | FOT | RETNR | 5422 | FAILURE OH HALL. FAS DRILL CMT RETAINER TO SHUT OFF THE SLIDING SLLEVE AFTER STING OUT WITH STINGER
377 | 02/06/2022 | SSA-5971 | UTMN-2302 | SPR | 06 Feb 0330 - 0500 | 1.5 | 1.5 | 891045 |  | TF | FOT | CRT | 8222 | SIDE DOOR ELEVATOR UNABLE TO LATCH ON 13-3/8" VAM TOP FBE CSG.
379 | 02/06/2022 | SSA-5971 | UTMN-2302 | ARM | 05 Feb 1500 - 0300 | 14 | 28 | 890910 |  | JF | HELD | CSG | 5258 | HAD OBSTRUCTION AT 5,258 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
380 | 02/06/2022 | SSA-5971 | UTMN-2302 | ARM | 06 Feb 0930 - 1730 | 8 | 8 | 890911 |  | WON | WTHR | NA | 8222 | DUST AND HIGH WIND SPEED (42-57 KM/HR) .
381 | 02/06/2022 | SSA-5971 | UTMN-2302 | SPR | 06 Feb 0330 - 0500 | 1.5 | 1.5 | 891045 |  | TF | FOT | CRT | 8222 | SIDE DOOR ELEVATOR UNABLE TO LATCH ON 13-3/8" VAM TOP FBE CSG.
383 | 02/06/2022 | STY-038 | ZULF-2083 | SRT | 31 Jan 0500 - 0500 | 24 | 166.5 | 890528 |  | BHA | FOT | STZRM | 6070 | SMITH STABILIZER PARTED DUE TO A FATIGUE OF THE MATERIAL.
384 | 02/06/2022 | T217 | UTMN-488 | RIG | 05 Feb 1600 - 0500 | 20 | 22 | 891026 |  | BOP | LHFL | RWCS | 6052 | OBSERVED HYD LEAK ON BOP.
386 | 02/06/2022 | T217 | UTMN-488 | ARM | 05 Feb 1800 - 0900 | 4 | 15 | 890992 |  | STUK | STBH | BHA | 5982 | GOT STUCK PIPE WHILE POH.
387 | 02/06/2022 | T217 | UTMN-488 | RIG | 05 Feb 1600 - 0500 | 20 | 22 | 891026 |  | BOP | LHFL | RWCS | 6052 | OBSERVED HYD LEAK ON BOP.
389 | 02/06/2022 | T218 | UTMN-471 | WBP | 04 Feb 0100 - 0415 | 23.25 | 49.75 | 890843 |  | TF | FOT | RBP | 6400 | WFD 4-1/2"RBP LEFT IN HOLE DURING SETTING
391 | 02/07/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 23.5 | 109.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
393 | 02/07/2022 | ADC-42L | UTMN-2319 | TK3 | 06 Feb 2230 - 0500 | 23.5 | 30 | 890912 |  | STUK | STBH | BHA | 6624 | AT 6,624 FT, STRING STALLED WHILE DRILLING. NO ROTATION. NO MOVEMENT UPWARD. STRING GET STUCK.
395 | 02/07/2022 | ADC-45 | KHRS-402 | GD1 | 07 Feb 1900 - 0100 | 6 | 6 | 891088 |  | TF | FOT | SLICK | 4400 | GDMC SLICKLINE PARTED WHILE ATTEMPT TO RETREIEVE PLUG.
397 | 02/07/2022 | ADC-50 | SFNY-1179 | SWA | 06 Feb 1015 - 0200 | 21 | 39.75 | 891025 |  | TF | FOT | PKR | 6314 | UNABLE TO RELEASE SLB 9 5/8" X 3 1/2" MRP-ESP PACKER, ATTEMPT SEVERAL TIMES WITH MAX OVER PULL 75 KLB'S, NO SUCCESS.
399 | 02/07/2022 | ADC-59L | HRDH-2232 | RIG | 07 Feb 1530 - 1630 | 1 | 1 | 891089 |  | RR | FOT | MPMP | 10525 | HAD DISCHARGE SCREEN FLANGE LEAKING ON MUD PUMP #2.
401 | 02/07/2022 | ADC-68L | KRSN-705 | TK3 | 03 Feb 1200 - 0500 | 21.5 | 110.5 | 890830 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT
403 | 02/07/2022 | ADES-798 | JFYN-13 | BLH | 07 Feb 2200 - 0500 | 7 | 7 | 891068 |  | JF | DSFT | HGRL | 16114 | EXCESSIVE TIME TO DRILL OUT BAKER 4-1/2" LANDING COLLAR.
405 | 02/07/2022 | BB-84A | MRJN-586 | RIG | 07 Feb 1200 - 0500 | 5.75 | 5.75 | 891105 |  | RR | FOT | MPMP | 5277 | LOSS OF PRIME - UNABLE TO OBTAIN CORRECT PUMP PRESSURE
407 | 02/07/2022 | CR-36A | ZULF-2038 | SPR | 05 Feb 2100 - 0500 | 24 | 56 | 890842 |  | JF | HERR | CTRQ | 1681 | WITH LAST JOINT, STRING WEIGHT DROPED SUDDENLY F/ 310 KLBS TO 170 KLBS AND THE CASING PARTED FROM BOX OF JT 26.
408 | 02/07/2022 | EXL-IA | SFNY-4050 | ARM | 05 Feb 2030 - 0500 | 17.25 | 47.75 | 890997 |  | CELR | UNSF | NA | 243 | ATTEMPT TO RUN 30" CASING INTO 34" CONDUCTOR HOLE.
410 | 02/07/2022 | EXL-IA | SFNY-4050 | RIG | 04 Feb 1830 - 1600 | 5.75 | 11.25 | 890889 |  | JF | HERR | NA | 374 | CTU INSERT BUSHING CAME OUT AND FELL TO THE SEABED DUE TO RIG CREWS LEAVING THE AREA WHILE INSTRUCTED TO STAY AND WATCH. NOT FOLLOWING PROCEDURES.
411 | 02/07/2022 | EXL-IA | SFNY-4050 | ARM | 05 Feb 2030 - 0500 | 17.25 | 47.75 | 890997 |  | CELR | UNSF | NA | 243 | ATTEMPT TO RUN 30" CASING INTO 34" CONDUCTOR HOLE.
413 | 02/07/2022 | NBR-591S | HRDH-1933 | BHI | 05 Feb 1230 - 1400 | 9 | 47 | 890925 |  | BHA | FOT | MWD | 18163 | LOST COMMUNICATION W/ BAKER RSS & MWD,
415 | 02/07/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 584.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
417 | 02/07/2022 | NBR-987S | ABTL-2 | RIG | 07 Feb 2030 - 0000 | 3.5 | 3.5 | 891091 |  | JF | XTRI | NA | 9300 | EXCESSIVE TIME IN PERFORMING REGULAR JOB
419 | 02/07/2022 | PA-218S | QTIF-515 | RIG | 07 Feb 1200 - 1330 | 1.5 | 1.5 | 891125 |  | RR | FOT | RWCS | 2950 | LEAKS BEFORE TO TEST BOP, FIX SAME BY RETIGHTENING CONNECTION.
421 | 02/07/2022 | SINO-10 | UMTW-1 | WCM | 07 Feb 1400 - 0500 | 15 | 15 | 890998 |  | TF | CCAT | CSTR | 3184 | WFD 13-3/8" DV.TOOL PACKER NOT HOLDING AFTER SET DV.TOOL, OPEN SAME, CIRC. WITH NO RETURNS
423 | 02/07/2022 | SINO-18 | ADHN-10 | ARM | 04 Feb 1930 - 1645 | 11.75 | 69.25 | 891066 |  | LCIR | UVLC | NA | 4652 | UNCONTROLABLE LOST CIRCULTATION ACROSS THE SHU'AIBA FORMATION
425 | 02/07/2022 | SINO-27N | HRDH-485 | ARN | 07 Feb 0700 - 1100 | 4 | 4 | 891090 |  | WO | ORDS | NA | 0 | WAIT ON RDD/RMD FOR FURTHER PLAN.
427 | 02/07/2022 | SND-2008 | HWYH-947 | HLH | 07 Feb 0030 - 0230 | 2 | 2 | 891067 |  | TF | FOT | HGRL | 11413 | AFTER POH HAL R/T, FOUND 1 FINGER OF R/T COLLET LEFT IN HOLE. RUN JUNK MILL TO C/OUT JUNK.
429 | 02/07/2022 | SP-103 | KRSN-48 | BLH | 07 Feb 0500 - 1400 | 9 | 9 | 891087 |  | TF | FOT | LLAP | 6085 | BAKER LINER ZXP PAKER PERMITURE FALIURE SET
431 | 02/07/2022 | SP-260 | HZEM-141612 | RIG | 07 Feb 0915 - 1015 | 1 | 1 | 891106 |  | JF | XTRI | NA | 18412 | IRON ROUGHNECK STOPPED WORKING.
433 | 02/07/2022 | SSA-5859 | HWYH-1265 | SPS | 04 Feb 1400 - 0500 | 23.5 | 85 | 890905 |  | DD | AINC | BHA | 2135 | UNABLE TO INITIATE 22" SIDE TRACK HOLE WITH SPERRY SUN ASSEMBLY, NO ANGLE BUILDUP.
435 | 02/07/2022 | SSA-5969 | UTMN-3195 | HCB | 05 Feb 0100 - 0600 | 1 | 29 | 891006 |  | TF | FOT | RETNR | 5422 | FAILURE OH HALL. FAS DRILL CMT RETAINER TO SHUT OFF THE SLIDING SLLEVE AFTER STING OUT WITH STINGER
437 | 02/07/2022 | SSA-5971 | UTMN-2302 | ARM | 05 Feb 1500 - 0330 | 22.5 | 50.5 | 890910 |  | JF | HELD | CSG | 5258 | HAD OBSTRUCTION AT 5,258 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
439 | 02/07/2022 | SSA-5972 | NJYN-102 | RIG | 07 Feb 1030 - 1200 | 1.5 | 1.5 | 891065 |  | RR | FOT | DWKS | 13452 | PARK BREAK ON DRAWWORKS NOT RELEASING
441 | 02/07/2022 | STY-038 | ZULF-2083 | SRT | 31 Jan 0500 - 0500 | 24 | 190.5 | 890528 |  | BHA | FOT | STZRM | 6070 | SMITH STABILIZER PARTED DUE TO A FATIGUE OF THE MATERIAL.
443 | 02/07/2022 | T216 | ANDR-486 | RIG | 07 Feb 1915 - 2045 | 1.5 | 1.5 | 891092 |  | RR | FOT | PSYS | 0 | LOST RIG POWER
445 | 02/07/2022 | T217 | UTMN-488 | RIG | 05 Feb 1600 - 0500 | 24 | 46 | 891026 |  | BOP | LHFL | RWCS | 6052 | OBSERVED HYD LEAK ON BOP.
447 | 02/08/2022 | ADC-23 | RMLH-15 | SWL | 08 Feb 1530 - 0500 | 13.5 | 13.5 | 891185 |  | TF | FOT | WLT | 8993 | WHEN ATTEMPTING TO TAKE SECOND FLUID SAMPLE SLB LOST COMMUNICATION WITH THE TLC TOOLS. TROUBLE SHOT PROBLEM, UNABLE TO REGAIN COMMUNICATION.
449 | 02/08/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 23.5 | 133.25 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
451 | 02/08/2022 | ADC-42L | UTMN-2319 | TK3 | 06 Feb 2230 - 0415 | 17.25 | 47.25 | 890912 |  | STUK | STBH | BHA | 6624 | AT 6,624 FT, STRING STALLED WHILE DRILLING. NO ROTATION. NO MOVEMENT UPWARD. STRING GET STUCK.
453 | 02/08/2022 | ADC-48 | HWYH-1258 | BHI | 05 Feb 0300 - 0500 | 17.5 | 35.5 | 890966 |  | TF | XTTE | RSS | 13713 | BHI RSS COMMUNICATION AND UNABLE TO STEER.
455 | 02/08/2022 | ADC-50 | SFNY-1179 | SWA | 06 Feb 1015 - 0500 | 14.5 | 54.25 | 891025 |  | TF | FOT | PKR | 6314 | UNABLE TO RELEASE SLB 9 5/8" X 3 1/2" MRP-ESP PACKER, ATTEMPT SEVERAL TIMES WITH MAX OVER PULL 75 KLB'S, NO SUCCESS.
457 | 02/08/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 16.5 | 16.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
459 | 02/08/2022 | ADC-53L | HRDH-1532 | SDM | 08 Feb 1130 - 0500 | 17.5 | 17.5 | 891215 |  | DD | UDWL | RSS | 7690 | TOOL NOT RESPONDING TO DOWN LINK AND CONTINUE TEND TO BUILD UP ANGLE.
461 | 02/08/2022 | ADC-56L | UTMN-3011 | RIG | 08 Feb 0630 - 0945 | 3.25 | 3.25 | 891166 |  | RR | FOT | RWCS | 12724 | TEST PUMP FAILED WHILE TESTING 13 5/8" BOP, DUE TO PRESSURE REGULATOR MALFUNCTION, NO BACK UP.
462 | 02/08/2022 | ADC-59L | HRDH-2232 | RIG | 08 Feb 1815 - 1845 | .5 | .5 | 891211 |  | RR | FOT | MPMP | 11036 | WORKED ON MP#2 - HAD DISCHARGE SCREEN FLANGE LEAKING.
464 | 02/08/2022 | ADC-59L | HRDH-2232 | RIG | 08 Feb 0630 - 0730 | 1 | 1 | 891210 |  | RR | FOT | CSYS | 10830 | WORK ON SHALE SHAKERS - SHAKERS UNABLE TO HANDLE FLOW.
465 | 02/08/2022 | ADC-59L | HRDH-2232 | RIG | 08 Feb 1815 - 1845 | .5 | .5 | 891211 |  | RR | FOT | MPMP | 11036 | WORKED ON MP#2 - HAD DISCHARGE SCREEN FLANGE LEAKING.
467 | 02/08/2022 | ADC-68L | KRSN-705 | TK3 | 03 Feb 1200 - 1215 | 6.75 | 117.25 | 890830 |  | LCIR | CFFM | LCM | 4192 | ENCOUNTRD COMPLETE LOSS @ 4192 FT
469 | 02/08/2022 | ADES-144 | UTMN-3041 | WDV | 08 Feb 1900 - 0130 | 6.5 | 6.5 | 891206 |  | TF | FOT | DV | 1886 | WHILE CLEANING CEMENT ABOVE DV AT 1875 FT, THE WOB SUDDENLY INCREASED AND THE STRING WEIGHT DROPPED FROM 170K TO 68K AND STRING JUMPED ABOUT 3-4 FEET. IMMEDIATELY, SHUT DOWN THE PUMP AND PICK UP STRING AND FOUND THE DP BENT ABOVE ROTARY TABLE.
471 | 02/08/2022 | ADM-261 | MRJN-138 | BCT | 08 Feb 1315 - 0500 | 15.75 | 15.75 | 891213 |  | BHA | ISEQ | CTAC | 0 | WHILST RIH W/ 3.625" MILL ASSEMBLY; ATTEMPT TO WORK PAST 37 FT AND LATER AT 39 FT. TOP RAM OF BOP IS 37 FT AND LOWER RAM IS 39 FT FROM RIG FLOOR.
472 | 02/08/2022 | AOD-1 | ZULF-695 | BCM | 08 Feb 2100 - 2330 | 2.5 | 2.5 | 891218 |  | TF | FOT | PUMP | 7536 | CEMENT UNIT NOT HOLDING PRESSURE. TOURBLESHOOT & FOUND LEAKING VALVES.
474 | 02/08/2022 | AOD-1 | ZULF-695 | BCM | 08 Feb 1930 - 0500 | 7 | 7 | 891217 |  | CMT | CPNF | NA | 7536 | CEMENT PLUG NOT HOLDING PRESSURE.
475 | 02/08/2022 | AOD-1 | ZULF-695 | BCM | 08 Feb 2100 - 2330 | 2.5 | 2.5 | 891218 |  | TF | FOT | PUMP | 7536 | CEMENT UNIT NOT HOLDING PRESSURE. TOURBLESHOOT & FOUND LEAKING VALVES.
477 | 02/08/2022 | BB-84A | MRJN-586 | RIG | 07 Feb 1200 - 1030 | 5.5 | 11.25 | 891105 |  | RR | FOT | MPMP | 5277 | LOSS OF PRIME - UNABLE TO OBTAIN CORRECT PUMP PRESSURE
479 | 02/08/2022 | CR-36A | ZULF-2038 | SPR | 05 Feb 2100 - 0500 | 24 | 80 | 890842 |  | JF | HERR | CTRQ | 1681 | WITH LAST JOINT, STRING WEIGHT DROPED SUDDENLY F/ 310 KLBS TO 170 KLBS AND THE CASING PARTED FROM BOX OF JT 26.
481 | 02/08/2022 | EXL-IA | SFNY-4050 | ARM | 05 Feb 2030 - 0500 | 22 | 69.75 | 890997 |  | CELR | UNSF | NA | 243 | ATTEMPT TO RUN 30" CASING INTO 34" CONDUCTOR HOLE.
483 | 02/08/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 608.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
485 | 02/08/2022 | RBP-50A | HSBH-58 | ARM | 06 Feb 1900 - 2130 | 16.5 | 50.5 | 891145 |  | WON | WTHR | NA | 0 | WOW, UNABLE TO WORK BOATS DUE ADVERSE WEATHER CONDITION
487 | 02/08/2022 | RM-74A | KARN-61 | RIG | 08 Feb 1400 - 1900 | 5 | 5 | 891186 |  | RR | FOT | HSYS | 14220 | ARO TROUBLESHOOTING COUPLING OF DRIEVSHAFT OF BRIDGE RACKER SYSTEM
489 | 02/08/2022 | SA5898 | HRDH-2101 | BC | 08 Feb 1145 - 2330 | 11.75 | 11.75 | 891187 |  | TF | FOT | SEAL | 12007 | BAKER SEAL ASSY SHEARED OUT FROM PBR
491 | 02/08/2022 | SCTD-1 | UTMN-3070 | RIG | 08 Feb 2230 - 0500 | 6.5 | 6.5 | 891207 |  | BHA | FOT | MMOT | 14350 | LOST CIMMUNICATION WITH BHA
493 | 02/08/2022 | SINO-10 | UMTW-1 | WCM | 07 Feb 1400 - 1430 | 9.5 | 24.5 | 890998 |  | TF | CCAT | CSTR | 3184 | WFD 13-3/8" DV.TOOL PACKER NOT HOLDING AFTER SET DV.TOOL, OPEN SAME, CIRC. WITH NO RETURNS
495 | 02/08/2022 | SINO-43L | UTMN-4808 | BHI | 08 Feb 0700 - 0930 | 2.5 | 2.5 | 891205 |  | DD | DFOR | RSS | 5770 | LOST TRANSMISSION ON SIGNAL FROM MWD TOOL TO SURFACE.
497 | 02/08/2022 | SND-2008 | HWYH-947 | HLH | 07 Feb 0030 - 0500 | 21 | 23 | 891067 |  | TF | FOT | HGRL | 11413 | AFTER POH HAL R/T, FOUND 1 FINGER OF R/T COLLET LEFT IN HOLE. RUN JUNK MILL TO C/OUT JUNK.
499 | 02/08/2022 | SND-3001 | MHWZ-167102 | CAM | 08 Feb 1900 - 2200 | 3 | 3 | 891168 |  | WH | FOT | WH | 6712 | UNABLE TO LAND FMH IN WELLHEAD DURING DUMMY RUN.
501 | 02/08/2022 | SP-103 | KRSN-48 | BLH | 07 Feb 0500 - 0500 | 9 | 18 | 891087 |  | TF | FOT | LLAP | 6085 | BAKER LINER ZXP PAKER PERMITURE FALIURE SET
503 | 02/08/2022 | SP-110 | HWYH-127 | WDS | 08 Feb 1700 - 1900 | 2 | 2 | 891165 |  | BHA | FOT | LWD | 11380 | SLOW ROP DUE TO INABILITY OF LWD TO GET GOOD DETECTION USING FULL DRILLING PARAMETERS
505 | 02/08/2022 | SSA-102 | QTIF-699 | SPS | 08 Feb 1800 - 0500 | 11 | 11 | 891208 |  | BHA | FOT | RSS | 13535 | LOST COMMUNICATION WITH RSS, TRIP OUT TO CHANGE TOOL.
507 | 02/08/2022 | SSA-302 | HRDH-1954 | RIG | 08 Feb 0230 - 0500 | 2.5 | 2.5 | 891209 |  | RR | FOT | FL | 1885 | EXCESSIVE TIME FROM RIG CREW TO ADJUST FLOWLINE WITH BELL NIPPLE AND FIX LEAK BETWEEN BOP AND BELL NIPPLE.
508 | 02/08/2022 | SSA-5859 | HWYH-1265 | SPS | 04 Feb 1400 - 1800 | 12.5 | 97.5 | 890905 |  | DD | AINC | BHA | 2135 | UNABLE TO INITIATE 22" SIDE TRACK HOLE WITH SPERRY SUN ASSEMBLY, NO ANGLE BUILDUP.
510 | 02/08/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 0500 | 11 | 448.5 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
511 | 02/08/2022 | SSA-5859 | HWYH-1265 | SPS | 04 Feb 1400 - 1800 | 12.5 | 97.5 | 890905 |  | DD | AINC | BHA | 2135 | UNABLE TO INITIATE 22" SIDE TRACK HOLE WITH SPERRY SUN ASSEMBLY, NO ANGLE BUILDUP.
513 | 02/08/2022 | SSA-5891 | HRDH-695 | HWP | 08 Feb 0130 - 0500 | 3.5 | 3.5 | 891225 |  | FISH | HERR | WLT | 2120 | HLB RUN CHECK SET TOOL AND WHEN AT SURFACE WITH TOOLS FOUND THAT THEY LOST LOWER PART OF CHECK SET TOOL LENGTH 1" AND 3.6" OD.
515 | 02/08/2022 | SSA-5971 | UTMN-2302 | ARM | 05 Feb 1500 - 0500 | 24 | 74.5 | 890910 |  | JF | HELD | CSG | 5258 | HAD OBSTRUCTION AT 5,258 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
517 | 02/08/2022 | STY-038 | ZULF-2083 | SRT | 31 Jan 0500 - 0145 | 20.75 | 211.25 | 890528 |  | BHA | FOT | STZRM | 6070 | SMITH STABILIZER PARTED DUE TO A FATIGUE OF THE MATERIAL.
519 | 02/08/2022 | ZPEC-1 | HRDH-3543 | ARM | 05 Feb 2200 - 0500 | 24 | 79 | 891212 |  | LCIR | UVLC | NA | 1860 | LOSS OF CIRCULATION ACROSS ARUM FORMATION
520 | 02/09/2022 | ADC-29 | ABMK-4 | WWL | 09 Feb 0015 - 0330 | 3.25 | 3.25 | 891247 |  | STUK | HINW | WLT | 11816 | WFD APC RCT WITH CCL, WELLTEC TRACTOR ON WELLTE WIRELINE STUCK AFTER CUTTING 5" DP.
522 | 02/09/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 20.75 | 154 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
523 | 02/09/2022 | ADC-29 | ABMK-4 | WWL | 09 Feb 0015 - 0330 | 3.25 | 3.25 | 891247 |  | STUK | HINW | WLT | 11816 | WFD APC RCT WITH CCL, WELLTEC TRACTOR ON WELLTE WIRELINE STUCK AFTER CUTTING 5" DP.
525 | 02/09/2022 | ADC-32 | SDGM-1139 | SPS | 09 Feb 2230 - 0500 | 6.5 | 6.5 | 891294 |  | DD | AINC | BHA | 13900 | RSS NOT RESPONDING TO BUILD UP INCLINATION TO CATCH THE PLAN
527 | 02/09/2022 | ADC-36 | SDGM-1186 | PKP | 09 Feb 1100 - 0500 | 18 | 18 | 891287 |  | TF | FOT | HGRL | 15057 | FAILED TO SET PACKER PLUS PRIMESET LINER HANGER AS SETTING BALL NOT LANDING IN LOWER BALL SEAT.
529 | 02/09/2022 | ADC-41L | UTMN-3105 | RIG | 09 Feb 0330 - 0415 | .75 | .75 | 891272 |  | RR | FPMP | MPMP | 6210 | PRESSURE SENSOR ON STAND PIPE FAILED AND WAS READING ZERO PRESSURE.
531 | 02/09/2022 | ADC-42L | UTMN-2319 | RIG | 09 Feb 0630 - 1015 | 3.75 | 3.75 | 891285 |  | RR | FPMP | MPMP | 6650 | OBSERVED LEAKAGE ON MUD PUMP #3 BLEED OFF VALVE & ISOLATION VALVES.
533 | 02/09/2022 | ADC-48 | HWYH-1258 | BHI | 05 Feb 0300 - 1145 | 6.75 | 42.25 | 890966 |  | TF | XTTE | RSS | 13713 | BHI RSS COMMUNICATION AND UNABLE TO STEER.
535 | 02/09/2022 | ADC-50 | SFNY-1179 | SWA | 06 Feb 1015 - 0500 | 21.25 | 75.5 | 891025 |  | TF | FOT | PKR | 6314 | UNABLE TO RELEASE SLB 9 5/8" X 3 1/2" MRP-ESP PACKER, ATTEMPT SEVERAL TIMES WITH MAX OVER PULL 75 KLB'S, NO SUCCESS.
537 | 02/09/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 40.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
538 | 02/09/2022 | ADC-53L | HRDH-1532 | RIG | 09 Feb 0300 - 0500 | 2 | 2 | 891296 |  | RR | FOT | CSYS | 7690 | LEAK ON ROTARY HOSE.
540 | 02/09/2022 | ADC-53L | HRDH-1532 | SDM | 08 Feb 1130 - 0300 | 22 | 39.5 | 891215 |  | DD | UDWL | RSS | 7690 | TOOL NOT RESPONDING TO DOWN LINK AND CONTINUE TEND TO BUILD UP ANGLE.
541 | 02/09/2022 | ADC-53L | HRDH-1532 | RIG | 09 Feb 0300 - 0500 | 2 | 2 | 891296 |  | RR | FOT | CSYS | 7690 | LEAK ON ROTARY HOSE.
543 | 02/09/2022 | ADC-56L | UTMN-3011 | TK3 | 09 Feb 1900 - 0500 | 10 | 10 | 891290 |  | DSF | FOT | STRG | 12724 | UNABLE TO ACHIEVE REDUCE IN FLOW WHEN PERFORMING NEG TEST. OBSERVED ANNULUS GOING DOWN. SUSPECTED PCKR LEAKING.
545 | 02/09/2022 | ADC-67L | UTMN-3102 | SBT | 09 Feb 1000 - 0400 | 18 | 18 | 891292 |  | BHA | FOT | BIT | 6617 | ABNORMALLY LOW ROP AFTER DRILLING OUT OF 13-3/8 CASING SHOE - AVG ROP AT 2 FT/HR - POH - FOUND BIT TO BE DAMAGED: 3-7-BT-A-X-1/16-LT-ROP
547 | 02/09/2022 | ADES-158 | ABQQ-737 | BHI | 09 Feb 2100 - 0500 | 8 | 8 | 891291 |  | BHA | FOT | LWD | 8046 | BHI DENSITY LWD TOOL NOT WORKING, POOH TO CHANGE IT.
549 | 02/09/2022 | ARO-3001 | ZULF-2054 | SPR | 09 Feb 1200 - 1630 | 2.5 | 2.5 | 891289 |  | JF | HERR | CTRQ | 1684 | CASING TORQUE OPERATOR WAS UNABLE TO DELIVER A GOOD SERVICE IN THE RESULT CASING CROSS THREAD
551 | 02/09/2022 | ARO-3002 | MRJN-813 | OTH | 09 Feb 1430 - 0500 | 14.5 | 14.5 | 891246 |  | WON | WTHR | NA | 15782 | WAITING ON WEATHER TO RECEIVE BRINE FROM HUB. HUB SUSPENDED OPERATIONS FOR THE PAST 3DAYS DUE TO WEATHER.
553 | 02/09/2022 | BB-84A | MRJN-586 | RIG | 07 Feb 1200 - 0930 | 1 | 12.25 | 891105 |  | RR | FOT | MPMP | 5277 | LOSS OF PRIME - UNABLE TO OBTAIN CORRECT PUMP PRESSURE
555 | 02/09/2022 | CR-36A | ZULF-2038 | SPR | 05 Feb 2100 - 0500 | 24 | 104 | 890842 |  | JF | HERR | CTRQ | 1681 | WITH LAST JOINT, STRING WEIGHT DROPED SUDDENLY F/ 310 KLBS TO 170 KLBS AND THE CASING PARTED FROM BOX OF JT 26.
557 | 02/09/2022 | DQ-50L | HRDH-1492 | RIG | 09 Feb 1700 - 0030 | 7.5 | 7.5 | 891270 |  | RR | FOT | DWKS | 3730 | OBSERVED TWO STRANDS OF WIRE ROPE NO. 6 (ON DRAWWORKS DRUM DEAD LAYER) SQUEEZED & OUT OF ORIGINAL BRAIDED CONSTRUCTION. CHC & POOH TO SHOE. SLIP & CUT DRILL LINE & RIH BACK TO BTM.
559 | 02/09/2022 | EXL-IA | SFNY-4050 | ARM | 05 Feb 2030 - 0500 | 21 | 90.75 | 890997 |  | CELR | UNSF | NA | 243 | ATTEMPT TO RUN 30" CASING INTO 34" CONDUCTOR HOLE.
560 | 02/09/2022 | NBR-797S | UTMN-3145 | WI3 | 09 Feb 0800 - 0500 | 19 | 19 | 891271 |  | TF | FOT | WPSTK | 14393 | DRESS 7" CASING WINDOW AS PER WIS - P/U OFF BOTTOM WHEM FINISH RATHOLE. OBSERVE 500PSI DROP IN PRESSURE - WORK UP / DOWN THROUGH WINDOW 2 TIMES NO RESTRICTION OBSERVED. PRESSURE STABLE, NO CHANGE IN TORQUE OR HOOKLOAD - 3RD PASS DOWN THROUGH WINDOW ENCOUNTER RESTRICTION AT MIDRAMP 14,381FT. - MULTIPLE ATTEMPTS TO PASS THROUGH WINDOW WITH NO SUCCESS. - POOH TO SURFACE AND OBSERVE TWIST OFF AT CONNECTION OF HYD RUNNING TOOL & 5-7/8" MILL
562 | 02/09/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0800 | 3 | 611.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
563 | 02/09/2022 | NBR-797S | UTMN-3145 | WI3 | 09 Feb 0800 - 0500 | 19 | 19 | 891271 |  | TF | FOT | WPSTK | 14393 | DRESS 7" CASING WINDOW AS PER WIS - P/U OFF BOTTOM WHEM FINISH RATHOLE. OBSERVE 500PSI DROP IN PRESSURE - WORK UP / DOWN THROUGH WINDOW 2 TIMES NO RESTRICTION OBSERVED. PRESSURE STABLE, NO CHANGE IN TORQUE OR HOOKLOAD - 3RD PASS DOWN THROUGH WINDOW ENCOUNTER RESTRICTION AT MIDRAMP 14,381FT. - MULTIPLE ATTEMPTS TO PASS THROUGH WINDOW WITH NO SUCCESS. - POOH TO SURFACE AND OBSERVE TWIST OFF AT CONNECTION OF HYD RUNNING TOOL & 5-7/8" MILL
565 | 02/09/2022 | PA-785S | QTIF-24 | HCO | 09 Feb 1530 - 0500 | 13.5 | 13.5 | 891268 |  | TF | FOT | PKR | 0 | HALLIBURTON PACKER ASSY FAILLED AND SEAL ASSY SHEARED OFF FROM PBR WHILE RUNNING AT SURFACE,
567 | 02/09/2022 | PA-861S | HRDH-1332 | RIG | 09 Feb 0300 - 0330 | .5 | .5 | 891293 |  | RR | FOT | RSYS | 0 | ROTARY CAT IV INSPECTION, CERTIFICATION WAS DUE, OCT 2021
569 | 02/09/2022 | PN-9 | MRJN-92 | HCB | 09 Feb 0800 - 1630 | 8.5 | 8.5 | 891295 |  | TF | FOT | BP | 4000 | UNABLE TO CIRC THRU HALL 4-1/2" EZSV-CR, PORTS CLOSED.
571 | 02/09/2022 | SA5898 | HRDH-2101 | GOC | 08 Feb 1145 - 0500 | 18.5 | 30.25 | 891187 |  | TF | FOT | CRT | 12007 | WHILE SLICK LINE RUNNING DRIFT AT 20 FT; SUDDENLY THE TUBING STRING SLIPPED THRU THE SLIPS AND SAFETY CLAMPS AND DROPPED DOWN 3-4 FT WHICH CAUSED THE PBR TO SHEAR, PBR HOUSING AND S-3 DROPPED IN THE WELL.
573 | 02/09/2022 | SCTD-1 | UTMN-3070 | RIG | 08 Feb 2230 - 1030 | 5.5 | 12 | 891207 |  | BHA | FOT | MMOT | 14350 | LOST CIMMUNICATION WITH BHA
575 | 02/09/2022 | SND-2008 | HWYH-947 | HLH | 07 Feb 0030 - 0500 | 23.5 | 46.5 | 891067 |  | TF | FOT | HGRL | 11413 | AFTER POH HAL R/T, FOUND 1 FINGER OF R/T COLLET LEFT IN HOLE. RUN JUNK MILL TO C/OUT JUNK.
577 | 02/09/2022 | SNF036 | MRJN-901 | RIG | 09 Feb 0000 - 0030 | .5 | .5 | 891288 |  | RR | FOT | MPMP | 4734 | MUD PUMP POP OFF VALVES LEAKING - UNABLE TO CONTINUE DRILLING - CIRCULATE WHILE CARRY OUT REPAIRS
579 | 02/09/2022 | SP-103 | KRSN-48 | BLH | 07 Feb 0500 - 0500 | 24 | 42 | 891087 |  | TF | FOT | LLAP | 6085 | BAKER LINER ZXP PAKER PERMITURE FALIURE SET
581 | 02/09/2022 | SP-110 | HWYH-127 | WDS | 09 Feb 1100 - 1300 | 2 | 2 | 891265 |  | BHA | FOT | LWD | 11607 | SLOW ROP DUE TO INABILITY OF LWD TO GET GOOD DETECTION USING FULL DRILLING PARAMETERS
583 | 02/09/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0500 | 24 | 27.75 | 891286 |  | STUK | SCSG | LINR | 17815 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
585 | 02/09/2022 | SP-257 | HZEM-141214 | RIG | 09 Feb 1330 - 1430 | 1 | 1 | 891269 |  | TF | XTTE | CTRQ | 7705 | EXCESSIVE TIME TO RUN 9-5/8" CSG DUE TO HYDRAULIC CATWALK FAILURE.
587 | 02/09/2022 | SSA-102 | QTIF-699 | SPS | 08 Feb 1800 - 0500 | 23.5 | 34.5 | 891208 |  | BHA | FOT | RSS | 13535 | LOST COMMUNICATION WITH RSS, TRIP OUT TO CHANGE TOOL.
589 | 02/09/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 0430 | 23.5 | 548 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
591 | 02/09/2022 | SSA-5891 | HRDH-695 | HSL | 08 Feb 0130 - 0500 | 24 | 27.5 | 891225 |  | TF | FOT | SLICK | 2120 | HLB RUN CHECK SET TOOL AND WHEN AT SURFACE WITH TOOLS FOUND THAT THEY LOST LOWER PART OF CHECK SET TOOL LENGTH 1' AND 3.6" OD.
593 | 02/09/2022 | SSA-5971 | UTMN-2302 | ARM | 05 Feb 1500 - 0500 | 24 | 98.5 | 890910 |  | JF | HELD | CSG | 5258 | HAD OBSTRUCTION AT 5,258 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
595 | 02/09/2022 | STY-038 | ZULF-2083 | DEP | 09 Feb 1000 - 1215 | 2.25 | 2.25 | 891245 |  | TF | FOT | RESH | 8915 | 9-5/8" TURBO-CASER NOT FUNCTIONING DURING SURFACE TEST
597 | 02/09/2022 | T217 | UTMN-488 | RIG | 05 Feb 1600 - 0500 | 1 | 59.5 | 891026 |  | BOP | LHFL | RWCS | 6052 | OBSERVED HYD LEAK ON BOP.
599 | 02/09/2022 | ZPEC-1 | HRDH-3543 | ARM | 05 Feb 2200 - 0500 | 24 | 103 | 891212 |  | LCIR | UVLC | NA | 1860 | LOSS OF CIRCULATION ACROSS ARUM FORMATION
601 | 02/10/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 178 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
603 | 02/10/2022 | ADC-32 | SDGM-1139 | SPS | 09 Feb 2230 - 0300 | 22 | 28.5 | 891294 |  | DD | AINC | BHA | 13900 | RSS NOT RESPONDING TO BUILD UP INCLINATION TO CATCH THE PLAN
605 | 02/10/2022 | ADC-36 | SDGM-1186 | PKP | 09 Feb 1100 - 0500 | 13.75 | 31.75 | 891287 |  | TF | FOT | HGRL | 15057 | FAILED TO SET PACKER PLUS PRIMESET LINER HANGER AS SETTING BALL NOT LANDING IN LOWER BALL SEAT TO INTIATE SETTING MECHANISM.
607 | 02/10/2022 | ADC-48 | HWYH-1258 | BHI | 05 Feb 0300 - 2130 | 1 | 43.25 | 890966 |  | TF | XTTE | RSS | 13713 | BHI RSS COMMUNICATION AND UNABLE TO STEER.
609 | 02/10/2022 | ADC-50 | SFNY-1179 | SWA | 06 Feb 1015 - 0000 | 19 | 95.5 | 891025 |  | TF | FOT | PKR | 6314 | UNABLE TO RELEASE SLB 9 5/8" X 3 1/2" MRP-ESP PACKER, ATTEMPT SEVERAL TIMES WITH MAX OVER PULL 75 KLB'S, NO SUCCESS.
611 | 02/10/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 64.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
613 | 02/10/2022 | ADC-56L | UTMN-3011 | TK3 | 09 Feb 1900 - 1830 | 13.5 | 23.5 | 891290 |  | DSF | FOT | STRG | 12724 | UNABLE TO ACHIEVE REDUCE IN FLOW WHEN PERFORMING NEG TEST. OBSERVED ANNULUS GOING DOWN. SUSPECTED PCKR LEAKING.
615 | 02/10/2022 | ADC-67L | UTMN-3102 | SDM | 10 Feb 1930 - 2300 | 3.5 | 3.5 | 891428 |  | BHA | IDPR | MWD | 6920 | MISSED LOGGING DATA AND SURVEYS
617 | 02/10/2022 | ADES-158 | ABQQ-737 | BHI | 09 Feb 2100 - 1700 | 12 | 20 | 891291 |  | BHA | FOT | LWD | 8046 | BHI DENSITY LWD TOOL NOT WORKING, POOH TO CHANGE IT.
619 | 02/10/2022 | AOD-1 | ZULF-695 | ARM | 08 Feb 1930 - 0500 | 24 | 55 | 891226 |  | CMT | CPNF | NA | 7536 | CEMENT PLUG NOT HOLDING PRESSURE.
621 | 02/10/2022 | AOD-111 | MRJN-728 | BHI | 10 Feb 1800 - 0500 | 11 | 11 | 891410 |  | BHA | FOT | MMOT | 5066 | WHILE DRILLING@5066' OBSERVED VERY LOW ROP AND NO DIFFERENTIAL PRESSURE AT THE MOTOR
623 | 02/10/2022 | ARO-3002 | MRJN-813 | OTH | 09 Feb 1430 - 0215 | 21.25 | 35.75 | 891246 |  | WON | WTHR | NA | 15782 | WAITING ON WEATHER TO BACKLOAD OBM & RECEIVE BRINE FROM HUB. HUB SUSPENDED OPERATIONS FOR THE PAST 3DAYS DUE TO WEATHER. UNABLE TO BACKLOAD OBM TO CREATE SPACE DUE TO WEATHER.
625 | 02/10/2022 | CR-36A | ZULF-2038 | SPR | 05 Feb 2100 - 0500 | 21.5 | 125.5 | 890842 |  | JF | HERR | CTRQ | 1681 | WITH LAST JOINT, STRING WEIGHT DROPED SUDDENLY F/ 310 KLBS TO 170 KLBS AND THE CASING PARTED FROM BOX OF JT 26.
627 | 02/10/2022 | DQ-57L | KHRS-505 | RIG | 10 Feb 2030 - 2200 | 1.5 | 1.5 | 891429 |  | TF | FOT | PEL | 6490 | CHANGE OUT PIPE HANDLER PISTON ON TDS.
629 | 02/10/2022 | EXL-IA | SFNY-4050 | ARM | 05 Feb 2030 - 1645 | 10.75 | 101.5 | 890997 |  | CELR | UNSF | NA | 243 | ATTEMPT TO RUN 30" CASING INTO 34" CONDUCTOR HOLE.
631 | 02/10/2022 | EXL-IVA | SFNY-1660 | RIG | 10 Feb 1645 - 0500 | 12.25 | 12.25 | 891386 |  | RR | FOT | CSYS | 0 | PRE-LOAD PUMP GROUND FAULT.
633 | 02/10/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 19.25 | 19.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
635 | 02/10/2022 | NBR-797S | UTMN-3145 | WI3 | 09 Feb 0800 - 0500 | 24 | 43 | 891271 |  | TF | FOT | WPSTK | 14393 | DRESS 7" CASING WINDOW AS PER WIS - P/U OFF BOTTOM AFTER DRILLING RATHOLE. OBSERVE 500PSI DROP IN PRESSURE - WORK UP / DOWN THROUGH WINDOW 2 TIMES NO RESTRICTION OBSERVED. PRESSURE STABLE, NO CHANGE IN TORQUE OR HOOKLOAD - 3RD PASS DOWN THROUGH WINDOW ENCOUNTER RESTRICTION AT MIDRAMP 14,381FT. - MULTIPLE ATTEMPTS TO PASS THROUGH WINDOW WITH NO SUCCESS. - POOH TO SURFACE AND OBSERVE TWIST OFF AT CONNECTION OF HYD RUNNING TOOL & 5-7/8" MILL
637 | 02/10/2022 | NBR-987S | ABTL-2 | RIG | 09 Feb 1700 - 0500 | 24 | 36 | 891305 |  | UPRA | OTH | NA | 2818 | TROUBLESHOOT EATON BRAKE SYSTEM. UNABLE TO RUN DRAW WORK EFFICIENTLY.
639 | 02/10/2022 | SA5898 | HRDH-2101 | GOC | 08 Feb 1145 - 0500 | 20 | 50.25 | 891187 |  | TF | FOT | CRT | 12007 | WHILE SLICK LINE RUNNING DRIFT AT 20 FT; SUDDENLY THE TUBING STRING SLIPPED THRU THE SLIPS AND SAFETY CLAMPS AND DROPPED DOWN 3-4 FT WHICH CAUSED THE PBR TO SHEAR, PBR HOUSING AND S-3 DROPPED IN THE WELL.
641 | 02/10/2022 | SCTD-2 | UTMN-1889 | ARM | 10 Feb 1900 - 2200 | 3 | 3 | 891411 |  | STUK | STBH | BHA | 13069 | WHILE MAKING NORMAL WT CHECK, OBSERVED HIGH ANNULAR SPIKE WITH OP (WELL PACKING OFF). BHA GOT STUCK.
643 | 02/10/2022 | SINO-36L | SDGM-452 | SPS | 10 Feb 0800 - 0500 | 21 | 21 | 891408 |  | BHA | FOT | MWD | 6726 | SPS TROUBLE SHOOTING MWD TOOL, NO SUCCESS.
645 | 02/10/2022 | SND-2004 | BRRI-528 | RIG | 10 Feb 1700 - 2100 | 4 | 4 | 891445 |  | BOP | FOT | BOP | 5267 | ATTEMPTED TO PRESSURE TEST 13 5/8 5K BOPS, FOUND PRESSURE DROPS TROUBLESHOOT, CLEANED PASSING CHECK VALVE, TIGHTEN SBR BONNET BOLTS
647 | 02/10/2022 | SND-2008 | HWYH-947 | HLH | 07 Feb 0030 - 0500 | 14.75 | 61.25 | 891067 |  | TF | FOT | HGRL | 11413 | AFTER POH HAL R/T, FOUND 1 FINGER OF R/T COLLET LEFT IN HOLE. RUN JUNK MILL TO C/OUT JUNK.
649 | 02/10/2022 | SNF036 | MRJN-901 | ARM | 10 Feb 1230 - 1245 | .25 | .25 | 891385 |  | LCIR | CFFM | MDCAP | 4892 | HAD TOTAL LOST CIRCULATRION AT 4892 FT.
651 | 02/10/2022 | SP-103 | KRSN-48 | BLH | 07 Feb 0500 - 0500 | 24 | 66 | 891087 |  | TF | FOT | LLAP | 6085 | BAKER LINER MECHANICAL FB PACKER PERMITURE FALIURE SET
653 | 02/10/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0500 | 24 | 51.75 | 891286 |  | STUK | SCSG | LINR | 17815 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
655 | 02/10/2022 | SP-258 | HZEM-160602 | RIG | 10 Feb 0615 - 0715 | 1 | 1 | 891427 |  | TF | FOT | SFLN | 1164 | FLOW LINE PLUGGED BY RUBBER
657 | 02/10/2022 | SP-259 | HZEM-160812 | RIG | 10 Feb 2200 - 0500 | 7 | 7 | 891430 |  | BOP | FOT | BOP | 5080 | EXESS TIME DURING P/T BOP, HCR CHOKE LINE DID NOT HOLDING DURING P/T
659 | 02/10/2022 | SP-261 | HZEM-162104 | SDM | 10 Feb 0245 - 0500 | 2.25 | 2.25 | 891407 |  | DD | UDWL | RSS | 10720 | NEO-STEER RSS UNABLE TO ACHIEVE DESIRED BUILD RATE - POH TO CHANGE NEO-STEER RSS TO ARCHER RSS.
660 | 02/10/2022 | SSA-102 | QTIF-699 | SPS | 10 Feb 1200 - 0500 | 17 | 17 | 891406 |  | BHA | FOT | LWD | 13668 | FAILURE OF SPERRY NMR TOOL, TRIP OUT TO CHANGE TOOL.
662 | 02/10/2022 | SSA-102 | QTIF-699 | SPS | 08 Feb 1800 - 0930 | 4.5 | 39 | 891208 |  | BHA | FOT | RSS | 13535 | LOST COMMUNICATION WITH RSS, TRIP OUT TO CHANGE TOOL.
663 | 02/10/2022 | SSA-102 | QTIF-699 | SPS | 10 Feb 1200 - 0500 | 17 | 17 | 891406 |  | BHA | FOT | LWD | 13668 | FAILURE OF SPERRY NMR TOOL, TRIP OUT TO CHANGE TOOL.
665 | 02/10/2022 | SSA-29 | QTIF-381 | RIG | 10 Feb 1730 - 0500 | 11.5 | 11.5 | 891409 |  | BOP | FOT | BOP | 0 | WHILE TESTING BOP ANNULAR, OBSERVED DROPPING IN PRESSURE. INVESTIGATED AND FOUND LEAK IN THE TOP OF ANNULAR ELEMENT.
667 | 02/10/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 0500 | 23.5 | 571.5 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
669 | 02/10/2022 | SSA-5891 | HRDH-695 | HSL | 08 Feb 0130 - 0500 | 24 | 51.5 | 891225 |  | TF | FOT | SLICK | 2120 | HLB RUN CHECK SET TOOL AND WHEN AT SURFACE WITH TOOLS FOUND THAT THEY LOST LOWER PART OF CHECK SET TOOL LENGTH 1' AND 3.6" OD.
671 | 02/10/2022 | SSA-5971 | UTMN-2302 | ARM | 05 Feb 1500 - 0500 | 23 | 121.5 | 890910 |  | JF | HELD | CSG | 5258 | HAD OBSTRUCTION AT 5,258 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
673 | 02/10/2022 | SSA-5974 | HRDH-1970 | ARM | 10 Feb 1030 - 1700 | 6.5 | 6.5 | 891405 |  | WCNT | WCC5 | NA | 7931 | WHILE DRILLING 12" HOLE AT 7,931', NOTICE WELL START GAIN AND MUD LOG GAS PERCENT INCREASE.
675 | 02/10/2022 | T217 | UTMN-488 | RIG | 05 Feb 1600 - 2000 | 15 | 74.5 | 891026 |  | BOP | LHFL | RWCS | 6052 | OBSERVED HYD LEAK ON BOP.
677 | 02/10/2022 | ZPEC-1 | HRDH-3543 | ARM | 05 Feb 2200 - 0500 | 24 | 127 | 891212 |  | LCIR | UVLC | NA | 1860 | LOSS OF CIRCULATION ACROSS ARUM FORMATION
679 | 02/11/2022 | ADC-12 | ABQQ-199 | RIG | 11 Feb 1400 - 0500 | 15 | 15 | 891466 |  | RR | FOT | RWCS | 5130 | REPAIR TDS
680 | 02/11/2022 | ADC-17 | ZULF-1210 | SCP | 11 Feb 0630 - 0500 | 22.5 | 22.5 | 891526 |  | TF | FOT | PKR | 6062 | PACKER #1 FAILING TO HOLD PRESSURE. CONFIRMED BY INCREASE IN PRESSURE ON DOWNHOLE GAUGE DURING PRESSURE TEST OF TCA ABOVE PACKER #1
682 | 02/11/2022 | ADC-17 | ZULF-1210 | MSL | 11 Feb 0500 - 0630 | 1.5 | 1.5 | 891525 |  | TF | FOT | SSD | 5100 | SLIDING SLEEVE FAILED TO CLOSE FULLY AND UNABLE TO HOLD PRESSURE.
683 | 02/11/2022 | ADC-17 | ZULF-1210 | SCP | 11 Feb 0630 - 0500 | 22.5 | 22.5 | 891526 |  | TF | FOT | PKR | 6062 | PACKER #1 FAILING TO HOLD PRESSURE. CONFIRMED BY INCREASE IN PRESSURE ON DOWNHOLE GAUGE DURING PRESSURE TEST OF TCA ABOVE PACKER #1
685 | 02/11/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 15 | 193.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
686 | 02/11/2022 | ADC-32 | SDGM-1139 | RIG | 11 Feb 1415 - 1615 | 2 | 2 | 891487 |  | RR | FOT | TDS | 14088 | OBSERVED HYDRAULIC OIL LEAK ON TDS
688 | 02/11/2022 | ADC-32 | SDGM-1139 | SPS | 09 Feb 2230 - 0700 | 2 | 30.5 | 891294 |  | DD | AINC | BHA | 13900 | RSS NOT RESPONDING TO BUILD UP INCLINATION TO CATCH THE PLAN
689 | 02/11/2022 | ADC-32 | SDGM-1139 | RIG | 11 Feb 1415 - 1615 | 2 | 2 | 891487 |  | RR | FOT | TDS | 14088 | OBSERVED HYDRAULIC OIL LEAK ON TDS
691 | 02/11/2022 | ADC-36 | SDGM-1186 | PKP | 09 Feb 1100 - 0500 | 22.5 | 54.25 | 891287 |  | TF | FOT | HGRL | 15057 | FAILED TO SET PACKER PLUS PRIMESET LINER HANGER AS SETTING BALL NOT LANDING IN LOWER BALL SEAT TO INTIATE SETTING MECHANISM.
693 | 02/11/2022 | ADC-48 | HWYH-1258 | BHI | 05 Feb 0300 - 0500 | 24 | 67.25 | 890966 |  | TF | XTTE | RSS | 13713 | BHI RSS COMMUNICATION AND UNABLE TO STEER.
695 | 02/11/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 88.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
697 | 02/11/2022 | ADC-55L | UTMN-3076 | RIG | 11 Feb 2000 - 2245 | 2.75 | 2.75 | 891511 |  | JF | HERR | BHA | 995 | OBSERVED THAT LAST 7 JOINT OF 4-3/4" DC OVER TORQUED, APPLIED M/U 22.5 KLB.FT INSTEAD OF 10.5 KLBS.FT. ( IRON-ROUGHNECK TORQUE ADJUSTED FOR XT-39 CONNECTION & FORGOT READJUST TORQUE PRIOR TO 4-3/4" DC CONNECTION).
699 | 02/11/2022 | ADC-56L | UTMN-3011 | SDM | 13 Dec 0930 - 0500 | 23.5 | 50 | 884688 |  | BHA | FOT | MMOT | 2457 | LOST 200 PSI WHILE DRILLING
701 | 02/11/2022 | ADES-144 | UTMN-3041 | RIG | 11 Feb 1400 - 1630 | 2.5 | 2.5 | 891508 |  | RR | FOT | CSYS | 5640 | STANDPIPE UNION LEAKING DUE TO FAILURE OF O-RING.
703 | 02/11/2022 | ADM-510 | ABSF-230 | RIG | 11 Feb 1545 - 1645 | 1 | 1 | 891469 |  | RR | FOT | CSYS | 3459 | ATTEMPT TO CIRCULATE CASING THROUGH CEMENT HEAD AND LINE PRESSURED UP. TROUBLESHOOT AND FOUND BLOCKAGE IN THE LINE FROM STANDPIPE MANIFOLD TO CEMENT MANIFOLD
705 | 02/11/2022 | AOD-1 | ZULF-695 | BCM | 08 Feb 1930 - 0500 | 24 | 79 | 891226 |  | CMT | CPNF | NA | 7536 | CEMENT PLUG NOT HOLDING PRESSURE.
707 | 02/11/2022 | AOD-111 | MRJN-728 | BHI | 10 Feb 1800 - 0730 | 2.5 | 13.5 | 891410 |  | BHA | FOT | MMOT | 5066 | WHILE DRILLING@5066' OBSERVED VERY LOW ROP AND NO DIFFERENTIAL PRESSURE AT THE MOTOR
708 | 02/11/2022 | ARO-3001 | ZULF-2054 | HCM | 11 Feb 0000 - 0500 | 5 | 5 | 891510 |  | WO | MATL | NA | 0 | WAITING ON HALLIBURTON'S CHEMICALS FOR SPACER.
710 | 02/11/2022 | ARO-3001 | ZULF-2054 | HCM | 11 Feb 1700 - 0000 | 7 | 7 | 891509 |  | TF | ISEQ | PUMP | 0 | AFTER PUMPING 130 BBLS LEAD CMT SLURRY, UNABLE TO CONTROL CMT DENSITY DUE TO MACROMOTION DID NOT FUNCTION & ALSO PUMP CAVITATION PROBLEM.
711 | 02/11/2022 | ARO-3001 | ZULF-2054 | HCM | 11 Feb 0000 - 0500 | 5 | 5 | 891510 |  | WO | MATL | NA | 0 | WAITING ON HALLIBURTON'S CHEMICALS FOR SPACER.
713 | 02/11/2022 | BCTD-3 | HRDH-101001 | BHI | 11 Feb 2200 - 0500 | 7 | 7 | 891467 |  | BHA | FOT | MWD | 13907 | BHI LOST COMMUNICATION WITH TOOL.
715 | 02/11/2022 | CR-36A | ZULF-2038 | SPR | 05 Feb 2100 - 0400 | 23 | 148.5 | 890842 |  | JF | HERR | CTRQ | 1681 | WITH LAST JOINT, STRING WEIGHT DROPED SUDDENLY F/ 310 KLBS TO 170 KLBS AND THE CASING PARTED FROM BOX OF JT 26.
717 | 02/11/2022 | EXL-IVA | SFNY-1660 | RIG | 10 Feb 1645 - 0600 | 1 | 13.25 | 891386 |  | RR | FOT | CSYS | 0 | PRE-LOAD PUMP GROUND FAULT.
719 | 02/11/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 9 | 28.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
721 | 02/11/2022 | NBR-304S | HRDH-2260 | SPS | 11 Feb 0800 - 1000 | 2 | 2 | 891465 |  | BHA | FOT | MWD | 15982 | SPPERY SUN GR SENSOR PCGK NOT WORKING
723 | 02/11/2022 | NBR-591S | HRDH-1933 | BHI | 11 Feb 1300 - 1400 | 1 | 1 | 891505 |  | BHA | FOT | MWD | 19067 | LOST COMMUNICATION W/ BAKER RSS & LWD-GR,
724 | 02/11/2022 | NBR-797S | UTMN-3145 | WI3 | 09 Feb 0800 - 1530 | 10.5 | 53.5 | 891271 |  | TF | FOT | WPSTK | 14393 | DRESS 7" CASING WINDOW AS PER WIS - P/U OFF BOTTOM AFTER DRILLING RATHOLE. OBSERVE 500PSI DROP IN PRESSURE - WORK UP / DOWN THROUGH WINDOW 2 TIMES NO RESTRICTION OBSERVED. PRESSURE STABLE, NO CHANGE IN TORQUE OR HOOKLOAD - 3RD PASS DOWN THROUGH WINDOW ENCOUNTER RESTRICTION AT MIDRAMP 14,381FT. - MULTIPLE ATTEMPTS TO PASS THROUGH WINDOW WITH NO SUCCESS. - POOH TO SURFACE AND OBSERVE TWIST OFF AT CONNECTION OF HYD RUNNING TOOL & 5-7/8" MILL
726 | 02/11/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 13.5 | 624.75 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
727 | 02/11/2022 | NBR-797S | UTMN-3145 | WI3 | 09 Feb 0800 - 1530 | 10.5 | 53.5 | 891271 |  | TF | FOT | WPSTK | 14393 | DRESS 7" CASING WINDOW AS PER WIS - P/U OFF BOTTOM AFTER DRILLING RATHOLE. OBSERVE 500PSI DROP IN PRESSURE - WORK UP / DOWN THROUGH WINDOW 2 TIMES NO RESTRICTION OBSERVED. PRESSURE STABLE, NO CHANGE IN TORQUE OR HOOKLOAD - 3RD PASS DOWN THROUGH WINDOW ENCOUNTER RESTRICTION AT MIDRAMP 14,381FT. - MULTIPLE ATTEMPTS TO PASS THROUGH WINDOW WITH NO SUCCESS. - POOH TO SURFACE AND OBSERVE TWIST OFF AT CONNECTION OF HYD RUNNING TOOL & 5-7/8" MILL
729 | 02/11/2022 | NBR-987S | ABTL-2 | RIG | 09 Feb 1700 - 0100 | 20 | 56 | 891305 |  | UPRA | OTH | NA | 2818 | TROUBLESHOOT EATON BRAKE SYSTEM. UNABLE TO RUN DRAW WORK EFFICIENTLY.
731 | 02/11/2022 | PA-785S | QTIF-24 | HCO | 09 Feb 1530 - 0500 | 24 | 61.5 | 891268 |  | TF | FOT | PKR | 0 | HALLIBURTON PACKER ASSY FAILLED AND SEAL ASSY SHEARED OFF FROM PBR WHILE RUNNING AT SURFACE,
733 | 02/11/2022 | SA5898 | HRDH-2101 | GOC | 08 Feb 1145 - 0500 | 24 | 74.25 | 891187 |  | TF | HERR | TTRQ | 12007 | WHILE SLICK LINE RUNNING DRIFT AT 20 FT; SUDDENLY THE TUBING STRING SLIPPED THRU THE SLIPS AND SAFETY CLAMPS AND DROPPED DOWN 3-4 FT WHICH CAUSED THE PBR TO SHEAR, PBR HOUSING AND S-3 DROPPED IN THE WELL.
735 | 02/11/2022 | SINO-36L | SDGM-452 | SPS | 10 Feb 0800 - 0700 | 2 | 23 | 891408 |  | BHA | FOT | MWD | 6726 | SPS TROUBLE SHOOTING MWD TOOL, NO SUCCESS.
737 | 02/11/2022 | SINO-45L | UTMN-99 | SPS | 11 Feb 0300 - 0500 | 2 | 2 | 891513 |  | BHA | FOT | MMOT | 5918 | AFTER MAKING CONNECTION. ATTEMPT TO RESUME SLIDE DRLG, NO SUCCESS; NO DIFFERENTIAL ON MTR. CONFIRM MTR FAILURE
738 | 02/11/2022 | SND-2008 | HWYH-947 | SAM | 11 Feb 2300 - 0500 | 6 | 6 | 891547 |  | BHA | FOT | WBCL | 9530 | SAMA 9-5/8" FSC PKR FAILED TO HOLD 5200 PSI DIFFERENTIAL PR.
740 | 02/11/2022 | SND-2008 | HWYH-947 | HLH | 07 Feb 0030 - 1000 | 5 | 66.25 | 891067 |  | TF | FOT | HGRL | 11413 | AFTER POH HAL R/T, FOUND 1 FINGER OF R/T COLLET LEFT IN HOLE. RUN JUNK MILL TO C/OUT JUNK.
741 | 02/11/2022 | SND-2008 | HWYH-947 | SAM | 11 Feb 2300 - 0500 | 6 | 6 | 891547 |  | BHA | FOT | WBCL | 9530 | SAMA 9-5/8" FSC PKR FAILED TO HOLD 5200 PSI DIFFERENTIAL PR.
743 | 02/11/2022 | SP-103 | KRSN-48 | ARM | 07 Feb 0500 - 0500 | 24 | 90 | 891087 |  | STUK | LCRW | STRG | 6085 | 4-1/2" BAKER OBL LINER STUCK AT 6085' (NO CIRCULATION)
745 | 02/11/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0500 | 24 | 75.75 | 891286 |  | STUK | SCSG | LINR | 17815 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
747 | 02/11/2022 | SP-259 | HZEM-160812 | RIG | 10 Feb 2200 - 2100 | 10 | 17 | 891430 |  | BOP | FOT | BOP | 5080 | EXESS TIME DURING P/T BOP, HCR CHOKE LINE DID NOT HOLDING DURING P/T
748 | 02/11/2022 | SP-261 | HZEM-162104 | RIG | 11 Feb 1900 - 2100 | 2 | 2 | 891546 |  | RR | FOT | TDS | 10720 | EXCESSIVE TIME SPENT REPLACING & REBUILDING WASHPIPE ON TDS
750 | 02/11/2022 | SP-261 | HZEM-162104 | SDM | 10 Feb 0245 - 0000 | 13.5 | 15.75 | 891407 |  | DD | UDWL | RSS | 10720 | NEO-STEER RSS UNABLE TO ACHIEVE DESIRED BUILD RATE - POH TO CHANGE NEO-STEER RSS TO ARCHER RSS.
751 | 02/11/2022 | SP-261 | HZEM-162104 | RIG | 11 Feb 1900 - 2100 | 2 | 2 | 891546 |  | RR | FOT | TDS | 10720 | EXCESSIVE TIME SPENT REPLACING & REBUILDING WASHPIPE ON TDS
753 | 02/11/2022 | SSA-102 | QTIF-699 | SPS | 10 Feb 1200 - 0500 | 24 | 41 | 891406 |  | BHA | FOT | LWD | 13668 | FAILURE OF SPERRY NMR TOOL, TRIP OUT, CHANGE DIRECTIONAL COMPANY, TRIP IN.
755 | 02/11/2022 | SSA-29 | QTIF-381 | RIG | 10 Feb 1930 - 0730 | 2.5 | 12 | 891409 |  | BOP | FOT | BOP | 0 | WHILE TESTING BOP ANNULAR, OBSERVED DROPPING IN PRESSURE. INVESTIGATED AND FOUND LEAK IN THE TOP OF ANNULAR ELEMENT.
757 | 02/11/2022 | SSA-5820 | SDGM-1215 | RIG | 11 Feb 2230 - 0230 | 4 | 4 | 891545 |  | RR | FOT | TDS | 895 | LEAK ON TDS, WASHPIPE FAILURE.
759 | 02/11/2022 | SSA-5891 | HRDH-695 | HSL | 08 Feb 0130 - 0500 | 24 | 75.5 | 891225 |  | TF | FOT | SLICK | 2120 | HLB RUN CHECK SET TOOL AND WHEN AT SURFACE WITH TOOLS FOUND THAT THEY LOST LOWER PART OF CHECK SET TOOL LENGTH 1' AND 3.6" OD.
761 | 02/11/2022 | SSA-5971 | UTMN-2302 | ARM | 05 Feb 1500 - 0500 | 24 | 145.5 | 890910 |  | JF | HELD | CSG | 5258 | HAD OBSTRUCTION AT 5,258 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
763 | 02/11/2022 | ZPEC-1 | HRDH-3543 | ARM | 05 Feb 2200 - 1630 | 11.5 | 138.5 | 891212 |  | LCIR | UVLC | NA | 1860 | LOSS OF CIRCULATION ACROSS ARUM FORMATION
765 | 02/12/2022 | ADC-12 | ABQQ-199 | RIG | 11 Feb 1400 - 0900 | 4 | 19 | 891466 |  | RR | FOT | RWCS | 5130 | REPAIR TDS
767 | 02/12/2022 | ADC-17 | ZULF-1210 | SCP | 11 Feb 0630 - 1100 | 6 | 28.5 | 891526 |  | TF | FOT | PKR | 6062 | PACKER #1 FAILING TO HOLD PRESSURE. CONFIRMED BY INCREASE IN PRESSURE ON DOWNHOLE GAUGE DURING PRESSURE TEST OF TCA ABOVE PACKER #1
769 | 02/12/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 217.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
771 | 02/12/2022 | ADC-48 | HWYH-1258 | BHI | 05 Feb 0300 - 0500 | 24 | 91.25 | 890966 |  | TF | XTTE | RSS | 13713 | BHI RSS COMMUNICATION AND UNABLE TO STEER.
773 | 02/12/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 112.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
775 | 02/12/2022 | ADM-339 | RBYN-53 | RIG | 12 Feb 0400 - 0500 | 1 | 1 | 891605 |  | JF | XTRI | NA | 3308 | EXCESSIVE TIME FOR RIH LOWER COMPLETION WITH 5-1/2" DP DUE TO WHILE DRIFT PIPE ON CAT WALK MACHINE, BOTTOM PROTECTOR BROKEN AND NOT RECOVER IMMEDIATELY DRIFT
777 | 02/12/2022 | AOD-1 | ZULF-695 | BCM | 08 Feb 1930 - 0445 | 23.75 | 102.75 | 891226 |  | CMT | CPNF | NA | 7536 | CEMENT PLUG NOT HOLDING PRESSURE.
778 | 02/12/2022 | ARO-3001 | ZULF-2054 | HCM | 11 Feb 0000 - 0445 | 15.75 | 20.75 | 891510 |  | WO | MATL | NA | 0 | WAITING ON HALLIBURTON'S CHEMICALS FOR SPACER.
780 | 02/12/2022 | ARO-3001 | ZULF-2054 | HCM | 11 Feb 1700 - 1600 | 8 | 15 | 891509 |  | TF | ISEQ | PUMP | 0 | AFTER PUMPING 130 BBLS LEAD CMT SLURRY, UNABLE TO CONTROL CMT DENSITY DUE TO MACROMOTION DID NOT FUNCTION & ALSO PUMP CAVITATION PROBLEM.
781 | 02/12/2022 | ARO-3001 | ZULF-2054 | HCM | 11 Feb 0000 - 0445 | 15.75 | 20.75 | 891510 |  | WO | MATL | NA | 0 | WAITING ON HALLIBURTON'S CHEMICALS FOR SPACER.
783 | 02/12/2022 | BCTD-3 | HRDH-101001 | BHI | 11 Feb 2200 - 1330 | 8.5 | 15.5 | 891467 |  | BHA | FOT | MWD | 13907 | BHI LOST COMMUNICATION WITH TOOL.
785 | 02/12/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 22 | 50.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
787 | 02/12/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 648.75 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
789 | 02/12/2022 | PA-218S | QTIF-515 | RIG | 12 Feb 1300 - 1445 | 1.75 | 1.75 | 891518 |  | RR | DRIG | PSYS | 2950 | OBSERVED 5.5" D/P NOT CENTER WITH ROTARY TABLE. RIG CREW ALLINGED THE MAST
791 | 02/12/2022 | PA-785S | QTIF-24 | HCO | 09 Feb 1530 - 0500 | 24 | 85.5 | 891268 |  | TF | FOT | PKR | 0 | HALLIBURTON PACKER ASSY FAILLED AND SEAL ASSY SHEARED OFF FROM PBR WHILE RUNNING AT SURFACE,
793 | 02/12/2022 | SA5898 | HRDH-2101 | GOC | 08 Feb 1145 - 0500 | 24 | 98.25 | 891187 |  | TF | HERR | TTRQ | 12007 | WHILE SLICK LINE RUNNING DRIFT AT 20 FT; SUDDENLY THE TUBING STRING SLIPPED THRU THE SLIPS AND SAFETY CLAMPS AND DROPPED DOWN 3-4 FT WHICH CAUSED THE PBR TO SHEAR, PBR HOUSING AND S-3 DROPPED IN THE WELL.
795 | 02/12/2022 | SINO-45L | UTMN-99 | SPS | 11 Feb 0300 - 2300 | 17.5 | 19.5 | 891513 |  | BHA | FOT | MMOT | 5918 | MOTOR FAILURE. NO DIFFERENTIAL ON MTR.
797 | 02/12/2022 | SND-2006 | UTMN-3135 | SPS | 12 Feb 2000 - 0500 | 9 | 9 | 891585 |  | BHA | FOT | RSS | 10492 | TROUBLE SHOOTING RSS. FAILED & FAILED TO POWER THE RSS WITH DIFFERENT FLOW RATE
799 | 02/12/2022 | SND-2008 | HWYH-947 | SAM | 11 Feb 2300 - 0130 | 18.5 | 24.5 | 891547 |  | BHA | FOT | WBCL | 9530 | SAMA 9-5/8" FSC PKR FAILED TO HOLD 5200 PSI DIFFERENTIAL PR.
801 | 02/12/2022 | SNF036 | MRJN-901 | ARM | 12 Feb 1500 - 0115 | 10.25 | 10.25 | 891565 |  | WON | WTHR | NA | 5145 | WAIT ON WEATHER TO MODERATE SUFFICIENTLY TO ALLOW VESSELS TO WORK. WAITING FOR BACK UP TOOLS - 9 1/2" DRILLING JAR - BHA PROBLEMS DUE TO UNEXPECTED FORMATION DIFFICULTIES AND HARSH DRILLING CONDITIONS.
803 | 02/12/2022 | SP-103 | KRSN-48 | ARM | 07 Feb 0500 - 0500 | 24 | 114 | 891087 |  | STUK | LCRW | STRG | 6085 | 4-1/2" BAKER OBL LINER STUCK AT 6085' (NO CIRCULATION)
804 | 02/12/2022 | SP-120 | MNIF-189 | HCM | 12 Feb 1500 - 0000 | 9 | 9 | 891515 |  | WO | SRVC | NA | 22213 | EXCESS WAITING TIME ON CEMENT MIX FLUIDS AND SPACERS CONFIRMATION TEST RESULTS.
806 | 02/12/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 1500 | 10 | 85.75 | 891286 |  | STUK | SCSG | LINR | 17815 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
807 | 02/12/2022 | SP-120 | MNIF-189 | HCM | 12 Feb 1500 - 0000 | 9 | 9 | 891515 |  | WO | SRVC | NA | 22213 | EXCESS WAITING TIME ON CEMENT MIX FLUIDS AND SPACERS CONFIRMATION TEST RESULTS.
808 | 02/12/2022 | SP-261 | HZEM-162104 | SDM | 12 Feb 0230 - 0500 | 2.5 | 2.5 | 891520 |  | BHA | FOT | MWD | 11240 | TROUBLE SHOOT MWD TOOLS - TOOLS NOT SHOWING PRE-PROGRAMMED VALUES
810 | 02/12/2022 | SP-261 | HZEM-162104 | SDM | 12 Feb 0100 - 0230 | 1.5 | 1.5 | 891519 |  | BHA | HERR | MWD | 11240 | EXCESSIVE TIME SPENT MAKING UP BHA.
811 | 02/12/2022 | SP-261 | HZEM-162104 | SDM | 12 Feb 0230 - 0500 | 2.5 | 2.5 | 891520 |  | BHA | FOT | MWD | 11240 | TROUBLE SHOOT MWD TOOLS - TOOLS NOT SHOWING PRE-PROGRAMMED VALUES
813 | 02/12/2022 | SSA-101 | BRRI-1145 | ARM | 12 Feb 0500 - 1700 | 12 | 12 | 891521 |  | WON | WTHR | NA | 9025 | WAIT ON WEATHER DUE TO WIND DIRECTION.
815 | 02/12/2022 | SSA-102 | QTIF-699 | SPS | 10 Feb 1200 - 0500 | 24 | 65 | 891406 |  | BHA | FOT | LWD | 13668 | FAILURE OF SPERRY NMR TOOL, TRIP OUT, CHANGE DIRECTIONAL COMPANY, TRIP IN.
817 | 02/12/2022 | SSA-5820 | SDGM-1215 | RIG | 12 Feb 1230 - 1430 | 2 | 2 | 891471 |  | RR | FOT | TDS | 995 | LOSS OF ROTARY FUNCTION ON TDS.
819 | 02/12/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 0500 | 24 | 619.5 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
821 | 02/12/2022 | SSA-5891 | HRDH-695 | HSL | 08 Feb 0130 - 1530 | 10.5 | 86 | 891225 |  | TF | FOT | SLICK | 2120 | HLB RUN CHECK SET TOOL AND WHEN AT SURFACE WITH TOOLS FOUND THAT THEY LOST LOWER PART OF CHECK SET TOOL LENGTH 1' AND 3.6" OD.
823 | 02/12/2022 | SSA-5971 | UTMN-2302 | ARM | 05 Feb 1500 - 0500 | 24 | 169.5 | 890910 |  | JF | HELD | CSG | 5258 | HAD OBSTRUCTION AT 5,258 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
825 | 02/13/2022 | ADC-17 | ZULF-1211 | RIG | 13 Feb 0045 - 0300 | 2.25 | 2.25 | 891667 |  | RR | FOT | HSYS | 0 | EZY TORQUE FAILED TO MAKE UP THE JOINTS LEAK ON CONNECTION FOUND REPAIR THE CONNECTION PART WITH NO SUCCESS. DECISION MADE TO USE CAT HEAD
827 | 02/13/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 241.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
829 | 02/13/2022 | ADC-48 | HWYH-1258 | BHI | 05 Feb 0300 - 1200 | 7 | 87.5 | 890966 |  | TF | XTTE | RSS | 13713 | BHI RSS COMMUNICATION AND UNABLE TO STEER.
831 | 02/13/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 136.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
833 | 02/13/2022 | ADM-337 | MRJN-900 | RIG | 13 Feb 2200 - 2330 | 1.5 | 1.5 | 891651 |  | TF | FOT | SFLN | 9325 | CHANGE OUT CHART RECORDER, RELIEF VALVE & AUTO CLAVE FITTINGS ON TEST PUMP, TEST PUMP OK
835 | 02/13/2022 | DQ-48 | KHRS-1411 | RIG | 13 Feb 0600 - 0730 | 1.5 | 1.5 | 891665 |  | JF | XTRI | CTRQ | 75 | EXCESS TIME TO N/U, WELD & SECURE 30" RISER.
837 | 02/13/2022 | ED-85A | SFNY-4060 | BCM | 13 Feb 2345 - 0130 | 1.75 | 1.75 | 891654 |  | CMT | HERR | NA | 8778 | BAKER CEMENTING TAKE EXTRA TO PREPARE MIX FLUID.
839 | 02/13/2022 | ENSCO-76 | MRJN-2004 | BHI | 12 Feb 0500 - 1345 | 8.75 | 32.75 | 891627 |  | BHA | FOT | LWD | 13795 | WHILE ATTEMPTING TO ACQUIRE SAMPLE, FASTRAK LOSING SEAL AND PLUGGING INTERMITTENTLY.
841 | 02/13/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 74.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
842 | 02/13/2022 | NBR-196S | SDGM-1174 | BC | 13 Feb 1630 - 0500 | 12.5 | 12.5 | 891626 |  | TF | FOT | SEAL | 3754 | WHILE RUN SAPESCO 3.75" DRIFT TO DRIFT 4.5" 15.1# VM-125HC TBG DRIFT BECAME STUCK.
844 | 02/13/2022 | NBR-196S | SDGM-1174 | ITS | 13 Feb 1415 - 1445 | .5 | .5 | 891522 |  | TF | FOT | CTRQ | 895 | WHILE MAKE UP 4.5" TBG ITS POWER TONG BACK UP JAW KEEP JUMPING GIVING FAULSE MAKE UP READING.
845 | 02/13/2022 | NBR-196S | SDGM-1174 | BC | 13 Feb 1630 - 0500 | 12.5 | 12.5 | 891626 |  | TF | FOT | SEAL | 3754 | WHILE RUN SAPESCO 3.75" DRIFT TO DRIFT 4.5" 15.1# VM-125HC TBG DRIFT BECAME STUCK.
847 | 02/13/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 672.75 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
849 | 02/13/2022 | PA-604S | HRDH-1392 | RIG | 13 Feb 2115 - 0030 | 3.25 | 3.25 | 891652 |  | RR | FOT | SWVL | 9189 | REPAIR / REPLACE TDS WASHPIPE.
851 | 02/13/2022 | PA-785S | QTIF-24 | HCO | 09 Feb 1530 - 0500 | 24 | 109.5 | 891268 |  | TF | FOT | PKR | 0 | HALLIBURTON PACKER ASSY FAILLED AND SEAL ASSY SHEARED OFF FROM PBR WHILE RUNNING AT SURFACE,
853 | 02/13/2022 | SA5898 | HRDH-2101 | GOC | 08 Feb 1145 - 0500 | 24 | 122.25 | 891187 |  | TF | HERR | TTRQ | 12007 | WHILE SLICK LINE RUNNING DRIFT AT 20 FT; SUDDENLY THE TUBING STRING SLIPPED THRU THE SLIPS AND SAFETY CLAMPS AND DROPPED DOWN 3-4 FT WHICH CAUSED THE PBR TO SHEAR, PBR HOUSING AND S-3 DROPPED IN THE WELL.
855 | 02/13/2022 | SINO21 | ABQQ-551 | RIG | 13 Feb 1100 - 0500 | 18 | 18 | 891648 |  | RR | FOT | TDS | 9835 | TDS FAILURE.
857 | 02/13/2022 | SND-1501 | HRDH-431 | WBP | 12 Feb 1830 - 0500 | 24 | 34.5 | 891653 |  | TF | FOT | BP | 5795 | WFD COULD'T EQULIZE AND RETRIEVE PUMP THRU PLUG AND GOT THE EQUILIZING BAR STUCK INSIDE PUMP THRU.
859 | 02/13/2022 | SND-2006 | UTMN-3135 | SPS | 12 Feb 2000 - 0330 | 22.5 | 31.5 | 891585 |  | BHA | FOT | RSS | 10492 | TROUBLE SHOOTING RSS. FAILED & FAILED TO POWER THE RSS WITH DIFFERENT FLOW RATE
861 | 02/13/2022 | SP-103 | KRSN-48 | ARM | 07 Feb 0500 - 1200 | 7 | 121 | 891087 |  | STUK | LCRW | STRG | 6085 | 4-1/2" BAKER OBL LINER STUCK AT 6085' (NO CIRCULATION)
863 | 02/13/2022 | SP-110 | HWYH-127 | WUD | 13 Feb 0345 - 0500 | 1.25 | 1.25 | 891666 |  | BOP | FOT | RCD | 13283 | WHILE DRILL 6 1/8" LATERAL SEC. @ 13283 FT FOUND LEAK IN WFD RCD BEARING.
865 | 02/13/2022 | SP-261 | HZEM-162104 | SDM | 12 Feb 0230 - 1230 | 7.5 | 10 | 891520 |  | BHA | FOT | MWD | 11240 | TROUBLE SHOOT MWD TOOLS - TOOLS NOT SHOWING PRE-PROGRAMMED VALUES
867 | 02/13/2022 | SSA-102 | QTIF-699 | SPS | 10 Feb 1200 - 1045 | 2.75 | 67.75 | 891406 |  | BHA | FOT | LWD | 13669 | FAILURE OF SPERRY NMR TOOL, TRIP OUT, CHANGE DIRECTIONAL COMPANY, TRIP IN.
869 | 02/13/2022 | SSA-202 | QTIF-674 | SPS | 13 Feb 1445 - 0500 | 14.25 | 14.25 | 891629 |  | BHA | FOT | MWD | 14077 | FAILURE OF SPS LWD TOOL.
871 | 02/13/2022 | SSA-5820 | SDGM-1215 | OTH | 13 Feb 1200 - 1400 | 2 | 2 | 891625 |  | WON | WTHR | NA | 1234 | SUSPEND CRANE OPERATIONS DUE TO HIGH WINDS AT 15 METERS PER SECOND. UNABLE TO LAY DOWN BHA.
873 | 02/13/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 0500 | 24 | 643.5 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
875 | 02/13/2022 | STY-038 | ZULF-2082 | RIG | 13 Feb 1430 - 1700 | 2.5 | 2.5 | 891649 |  | JF | HERR | WBSH | 0 | TEST PLUG GOT JAMMED IN RT INSERT BUSHING WHILE RUNNING WB
876 | 02/13/2022 | T217 | UTMN-488 | ARM | 13 Feb 0700 - 0030 | 15.5 | 15.5 | 891685 |  | STUK | PSSW | NA | 7102 | DRILLING STRING STUCK
878 | 02/13/2022 | T217 | UTMN-488 | OCT | 13 Feb 2100 - 2300 | 2 | 2 | 891668 |  | WO | SRVC | NA | 7102 | PUMP UNABLE TO PUMP ACID
879 | 02/13/2022 | T217 | UTMN-488 | ARM | 13 Feb 0700 - 0030 | 15.5 | 15.5 | 891685 |  | STUK | PSSW | NA | 7102 | DRILLING STRING STUCK
881 | 02/14/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 23.5 | 265.25 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
883 | 02/14/2022 | ADC-32 | SDGM-1139 | HWP | 14 Feb 1100 - 0500 | 18 | 18 | 891706 |  | TF | FOT | WLT | 13000 | WHILE LOG DOWN OBSERVED HALLIBURTON SONIC LOGGING TOOL NOT RESPONDING.
885 | 02/14/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 160.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
887 | 02/14/2022 | ADES-173 | HRDH-2256 | RIG | 14 Feb 0100 - 0200 | 1 | 1 | 891788 |  | RR | FOT | TDS | 430 | TOP DRIVE HPU FAILURE
888 | 02/14/2022 | ADM-337 | MRJN-900 | RIG | 14 Feb 2115 - 2145 | .5 | .5 | 891786 |  | TF | FOT | SFLN | 9325 | CHANGE OUT LEAKING LOW TORQUE VALVE ON BOP TESTING LINE
890 | 02/14/2022 | ADM-337 | MRJN-900 | RIG | 14 Feb 0330 - 0500 | 1.5 | 1.5 | 891748 |  | TF | FOT | SFLN | 9325 | TROUBLE SHOOT LEAKING BLLED OFF VALVE ON BOP TEST PUMP
891 | 02/14/2022 | ADM-337 | MRJN-900 | RIG | 14 Feb 2145 - 2300 | 1.25 | 1.25 | 891768 |  | TF | FOT | SFLN | 9325 | CHANGE OUT PRV & NEEDLE VALVES ON BOP TEST PUMP
892 | 02/14/2022 | ADM-337 | MRJN-900 | RIG | 14 Feb 2115 - 2145 | .5 | .5 | 891786 |  | TF | FOT | SFLN | 9325 | CHANGE OUT LEAKING LOW TORQUE VALVE ON BOP TESTING LINE
894 | 02/14/2022 | AOD-111 | MRJN-728 | ARM | 14 Feb 0945 - 0500 | 19.25 | 19.25 | 891769 |  | TH | NARW | NA | 4931 | HELD UP WITH 13-3/8" CASING AT 4931'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS.
896 | 02/14/2022 | DPS-43 | SDGM-1187 | SPS | 14 Feb 0000 - 0500 | 5 | 5 | 891787 |  | BHA | FOT | RSS | 16054 | LOSS OF COMMUNICATION BETWEEN MWD & RSS
898 | 02/14/2022 | EXL-IVA | SFNY-1660 | RIG | 14 Feb 1330 - 1600 | 2.5 | 2.5 | 891767 |  | RR | FOT | TDS | 248 | OBSERVED VIBRATION ON TDS BLOWER MOTOR DUE TO BROKEN BOLTS.
900 | 02/14/2022 | HI-4 | BRRI-780 | EMC | 14 Feb 0830 - 0500 | 20.5 | 20.5 | 891707 |  | MUD | IPDF | NA | 10453 | UNABLE TO CIRCULATE THICK MUD THROUGH SLB RSS/MWD BHA. POH & L/D RSS BHA AND RIH WITH 8.5" ROTARY BHA.
902 | 02/14/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 98.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
904 | 02/14/2022 | NBR-196S | SDGM-1174 | BC | 13 Feb 1630 - 1600 | 10 | 22.5 | 891626 |  | TF | FOT | SEAL | 3754 | WHILE RUN SAPESCO 3.75" DRIFT TO DRIFT 4.5" 15.1# VM-125HC TBG DRIFT BECAME STUCK.
906 | 02/14/2022 | NBR-210S | HRDH-1491 | WDS | 14 Feb 1000 - 1300 | 3 | 3 | 891747 |  | BHA | FOT | LWD | 0 | DURING SHALLOW TEST, THE NDT TOOL WAS NOT RESPONDING, CHANGED WITH BACK-UP TOOL
908 | 02/14/2022 | PA-326S | SAHB-32 | SPS | 14 Feb 2315 - 0500 | 5.75 | 5.75 | 891785 |  | BHA | FOT | MWD | 15314 | LOST SIGNAL WITH SPERRY SUN MWD.
910 | 02/14/2022 | PA-529S | SHYB-45 | TLH | 12 Feb 0030 - 0500 | 24 | 52.5 | 891705 |  | WO | MATL | NA | 0 | WAIT ON SUPPLY OF CACL2 BIG BAGS. SHORTAGE OF THIS CHEMICAL IN ARAMCO.
912 | 02/14/2022 | SA5898 | HRDH-2101 | GOC | 08 Feb 1145 - 0500 | 24 | 146.25 | 891187 |  | TF | HERR | TTRQ | 12007 | WHILE SLICK LINE RUNNING DRIFT AT 20 FT; SUDDENLY THE TUBING STRING SLIPPED THRU THE SLIPS AND SAFETY CLAMPS AND DROPPED DOWN 3-4 FT WHICH CAUSED THE PBR TO SHEAR, PBR HOUSING AND S-3 DROPPED IN THE WELL.
914 | 02/14/2022 | SND-1501 | HRDH-431 | WBP | 12 Feb 1830 - 0500 | 24 | 58.5 | 891653 |  | TF | FOT | BP | 5795 | WFD COULD'T EQULIZE AND RETRIEVE PUMP THRU PLUG AND GOT THE EQUILIZING BAR STUCK INSIDE PUMP THRU.
916 | 02/14/2022 | SND-2006 | UTMN-3135 | SPS | 12 Feb 2000 - 0630 | 1.5 | 33 | 891585 |  | BHA | FOT | RSS | 10492 | TROUBLE SHOOTING RSS. FAILED & FAILED TO POWER THE RSS WITH DIFFERENT FLOW RATE
918 | 02/14/2022 | SP-110 | HWYH-127 | WUD | 13 Feb 1300 - 1730 | 12.5 | 28.5 | 891666 |  | BOP | FOT | RCD | 13283 | WHILE DRILL 6 1/8" , FOUND LEAK IN WFD RCD BEARING. KILL THE WELL, TRIP OUT, CHANGE SAME, TRIP IN, DISPLACE THE WELL.
920 | 02/14/2022 | SP-261 | HZEM-162104 | SDM | 14 Feb 1400 - 0500 | 15 | 15 | 891765 |  | BHA | FOT | LWD | 13072 | LWD TOOLS NOT SENDING QUALITY LOG DATA. REQUIRED TO CHANGE OUT LWD TOOL.
922 | 02/14/2022 | SSA-202 | QTIF-674 | SPS | 13 Feb 1445 - 0100 | 18.25 | 32.5 | 891629 |  | BHA | FOT | MWD | 14077 | FAILURE OF SPS LWD TOOL.
924 | 02/14/2022 | SSA-5859 | HWYH-1265 | ARM | 15 Jan 0030 - 2230 | 17.5 | 661 | 888311 |  | STUK | STBH | BHA | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
926 | 02/14/2022 | STY-038 | ZULF-2082 | SRT | 14 Feb 1930 - 0500 | 9.5 | 9.5 | 891789 |  | BHA | FOT | UNDR | 9100 | SMITH RHINO REAMER FAILED TO OPEN
928 | 02/15/2022 | ADC-23 | RMLH-15 | GOC | 15 Feb 0015 - 0500 | 4.75 | 4.75 | 891865 |  | TF | FOT | CTRQ | 4527 | AL-GAITH FILL UP TOOL FAILED. 6' RUBBER PORTION SEPERATED AND FELL INSIDE OF CASING.
930 | 02/15/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 289.25 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
932 | 02/15/2022 | ADC-32 | SDGM-1139 | HWP | 14 Feb 1300 - 0330 | 22.5 | 38.5 | 891706 |  | TF | FOT | WLT | 13000 | WHILE LOG DOWN OBSERVED HALLIBURTON SONIC LOGGING TOOL NOT RESPONDING.
934 | 02/15/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 184.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
936 | 02/15/2022 | ADC-53L | HRDH-1532 | SDM | 14 Feb 0100 - 2345 | 18.75 | 22.75 | 891790 |  | BHA | FOT | LWD | 9093 | LWD TOOL NOT READING DATA.
938 | 02/15/2022 | ADC-58L | ABHD-172 | TK3 | 12 Feb 1600 - 0500 | 23.5 | 83.5 | 891656 |  | TH | PCPF | NA | 6811 | RIH WITH 9-5/8" CSG REAM DOWN WITH CRT, HAD OBS @ 4508 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
940 | 02/15/2022 | ADES-173 | HRDH-2256 | RIG | 15 Feb 1730 - 1830 | 1 | 1 | 891825 |  | RR | FOT | PSYS | 700 | RIG ENGINE KEEPS TRIPPING OFF.COMMULATIVE TIME TO RESTART RIG ENGINE.
942 | 02/15/2022 | ADM-337 | MRJN-900 | RIG | 14 Feb 0330 - 0700 | 2 | 3.5 | 891748 |  | TF | FOT | SFLN | 9325 | TROUBLE SHOOT LEAKING BLLED OFF VALVE ON BOP TEST PUMP
944 | 02/15/2022 | AOD-111 | MRJN-728 | ARM | 14 Feb 0945 - 0500 | 24 | 43.25 | 891769 |  | TH | NARW | NA | 4931 | HELD UP WITH 13-3/8" CASING AT 4931'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS.
946 | 02/15/2022 | DPS-43 | SDGM-1187 | SPS | 14 Feb 0000 - 0500 | 14 | 19 | 891787 |  | BHA | FOT | MWD | 16054 | LOSS OF COMMUNICATION BETWEEN MWD & RSS
948 | 02/15/2022 | HI-4 | BRRI-780 | EMC | 14 Feb 0830 - 2000 | 15 | 35.5 | 891707 |  | MUD | IPDF | NA | 10453 | UNABLE TO CIRCULATE THICK MUD THROUGH SLB RSS/MWD BHA. POH & L/D RSS BHA AND RIH WITH 8.5" ROTARY BHA.
950 | 02/15/2022 | MP-1 | LWHH-28 | BLH | 15 Feb 0345 - 0500 | 1.25 | 1.25 | 891849 |  | TF | FOT | LLAP | 10480 | ATTEMPTED TO TEST 4-1/2" X 7" LINER TOP PKR FAILED. LINER TOP PKR SUSPECTED LEAK.
952 | 02/15/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 22 | 120.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
954 | 02/15/2022 | NBR-591S | HRDH-1933 | RIG | 15 Feb 0100 - 0500 | 4 | 4 | 891847 |  | RR | FOT | DWKS | 14411 | HAD FAILURE IN DRAWWORKS WHILE RIH .
956 | 02/15/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 721 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
958 | 02/15/2022 | PA-326S | SAHB-32 | SPS | 14 Feb 2300 - 0500 | 24 | 30 | 891785 |  | BHA | FOT | MWD | 15314 | LOST SIGNAL WITH SPERRY SUN MWD.
960 | 02/15/2022 | PA-529S | SHYB-45 | OTH | 12 Feb 0030 - 0830 | 3.5 | 56 | 891705 |  | WO | SRVC | NA | 0 | WAIT ON SUPPLY OF CACL2 BIG BAGS. SHORTAGE OF THIS CHEMICAL IN ARAMCO.
962 | 02/15/2022 | SA5898 | HRDH-2101 | GOC | 08 Feb 1145 - 0500 | 24 | 170.25 | 891187 |  | TF | HERR | TTRQ | 12007 | WHILE SLICK LINE RUNNING DRIFT AT 20 FT; SUDDENLY THE TUBING STRING SLIPPED THRU THE SLIPS AND SAFETY CLAMPS AND DROPPED DOWN 3-4 FT WHICH CAUSED THE PBR TO SHEAR, PBR HOUSING AND S-3 DROPPED IN THE WELL.
964 | 02/15/2022 | SINO-1L | KHRS-548 | TK1 | 15 Feb 0900 - 0500 | 20 | 20 | 891848 |  | TF | FOT | TBG | 6706 | MALFUNCTION OF HES BATCH MIXERS AND UNABLE TO BATCH MIX CEMENT SLURRY.
966 | 02/15/2022 | SINO21 | ABQQ-551 | SDM | 15 Feb 0800 - 0430 | 20.5 | 20.5 | 891845 |  | BHA | FOT | MWD | 10942 | MWD TOOL FAILURE.
968 | 02/15/2022 | SND-1501 | HRDH-431 | ARM | 12 Feb 1830 - 0500 | 24 | 82.5 | 891653 |  | TF | HERR | TBG | 5795 | OBSERVED PTP WAS PLUGGED WITH SALT ACCUMULATED ABOVE IT DUE TO NOT CHECKING THE FLOAT WHILE RIH.
970 | 02/15/2022 | SND-2009 | NJYN-81 | ARM | 15 Feb 0930 - 0500 | 19.5 | 19.5 | 891846 |  | TH | PCPF | NA | 3395 | HAD OBSTRUCTION AT 3,395 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
972 | 02/15/2022 | SNT-025 | SFNY-520 | SPS | 15 Feb 0900 - 0115 | 16.25 | 16.25 | 891709 |  | DD | IDPR | MMOT | 0 | DUE TO FORMATION COMING SHALLOW, SPS COULDN'T ACHIEVE THE WELL TRAJECTORY.
973 | 02/15/2022 | SP-261 | HZEM-162104 | SDM | 14 Feb 1400 - 1945 | 13.5 | 28.5 | 891765 |  | BHA | FOT | LWD | 13072 | LWD TOOLS NOT SENDING QUALITY LOG DATA. REQUIRED TO CHANGE OUT LWD TOOL.
975 | 02/15/2022 | SP-261 | HZEM-162104 | SDM | 12 Feb 0100 - 0915 | 1.25 | 2.75 | 891519 |  | BHA | HERR | MWD | 11240 | EXCESSIVE TIME SPENT MAKING UP BHA.
976 | 02/15/2022 | SP-261 | HZEM-162104 | SDM | 14 Feb 1400 - 1945 | 13.5 | 28.5 | 891765 |  | BHA | FOT | LWD | 13072 | LWD TOOLS NOT SENDING QUALITY LOG DATA. REQUIRED TO CHANGE OUT LWD TOOL.
978 | 02/15/2022 | STY-038 | ZULF-2082 | SRT | 14 Feb 1930 - 1330 | 8 | 17.5 | 891789 |  | BHA | FOT | UNDR | 9100 | SMITH RHINO REAMER FAILED TO OPEN
980 | 02/16/2022 | ADC-23 | RMLH-15 | GOC | 15 Feb 0015 - 0500 | 24 | 28.75 | 891865 |  | TF | FOT | CTRQ | 4527 | AL-GAITH FILL UP TOOL FAILED. 11' RUBBER PORTION SEPERATED AND FELL INSIDE OF CASING.
982 | 02/16/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 313.25 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
984 | 02/16/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 208.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
986 | 02/16/2022 | ADC-58L | ABHD-172 | TK3 | 12 Feb 1600 - 1800 | 13 | 96.5 | 891656 |  | TH | PCPF | NA | 6811 | RIH WITH 9-5/8" CSG REAM DOWN WITH CRT, HAD OBS @ 4508 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
988 | 02/16/2022 | ADM-510 | ABSF-222 | RIG | 16 Feb 1530 - 1730 | 2 | 2 | 891827 |  | RR | FOT | RWCS | 0 | UNABLE TO UNLATCH BIG BORE DIVERTER
990 | 02/16/2022 | AOD-111 | MRJN-728 | ARM | 14 Feb 0945 - 0300 | 22 | 65.25 | 891769 |  | TH | NARW | NA | 4931 | HELD UP WITH 13-3/8" CASING AT 4931'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS.
992 | 02/16/2022 | ARO-3001 | ZULF-2058 | RIG | 16 Feb 1900 - 2115 | 2.25 | 2.25 | 891906 |  | RR | FOT | TDS | 5500 | TOP DRIVE ENCODER FAILURE.
994 | 02/16/2022 | DPS-43 | SDGM-1187 | SPS | 14 Feb 0000 - 0500 | 22.5 | 41.5 | 891787 |  | BHA | FOT | MWD | 16054 | LOSS OF COMMUNICATION BETWEEN MWD & RSS
996 | 02/16/2022 | ENSCO-54 | ABSF-102 | KSC | 16 Feb 1700 - 2030 | 3.5 | 3.5 | 891908 |  | WO | MATL | NA | 0 | WAIT ON ALKHORAYEF ESP PAKCER. ALKHORAYEF SENT TO RIG A WRONG ESP PACKER (HNBR PACKER INSTEAD OF AFLAS PACKER) WHICH IT DOESN'T MEET THE REQUIRED SPECIFICATION FOR CURRENT WELL.
998 | 02/16/2022 | MP-1 | LWHH-28 | BLH | 15 Feb 0345 - 0500 | 24 | 25.25 | 891849 |  | TF | FOT | LLAP | 10480 | ATTEMPTED TO TEST 4-1/2" X 7" LINER TOP PKR FAILED. LINER TOP PKR SUSPECTED LEAK.
1000 | 02/16/2022 | NA-128S | ZMLH-5 | SWL | 16 Feb 0230 - 0500 | 2.5 | 2.5 | 891907 |  | TF | FOT | WLU | 10678 | TROUBLE SHOOTING ON POWER OF SLB WIRELINE UNIT NO SUCCESS, WAITING ON BACK-UP UNIT.
1002 | 02/16/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 144.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1004 | 02/16/2022 | NBR-591S | HRDH-1933 | RIG | 15 Feb 0100 - 0500 | 24 | 28 | 891847 |  | RR | FOT | DWKS | 14411 | HAD FAILURE IN DRAWWORKS WHILE RIH .
1006 | 02/16/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 23.5 | 744.5 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1008 | 02/16/2022 | SA5898 | HRDH-2101 | GOC | 08 Feb 1145 - 1515 | 10.25 | 180.5 | 891187 |  | TF | HERR | TTRQ | 12007 | WHILE SLICK LINE RUNNING DRIFT AT 20 FT; SUDDENLY THE TUBING STRING SLIPPED THRU THE SLIPS AND SAFETY CLAMPS AND DROPPED DOWN 3-4 FT WHICH CAUSED THE PBR TO SHEAR, PBR HOUSING AND S-3 DROPPED IN THE WELL.
1010 | 02/16/2022 | SINO-19L | UTMN-633 | BAW | 16 Feb 0815 - 1145 | 3.5 | 3.5 | 891905 |  | TF | FOT | PGUN | 6592 | PERFORATION GUN#6 MISS FIRE DUE TO CABLE HEAD ADAPTER SUB.
1012 | 02/16/2022 | SINO-1L | KHRS-548 | TK1 | 15 Feb 0900 - 0800 | 3 | 23 | 891848 |  | TF | FOT | TBG | 6706 | MALFUNCTION OF HES BATCH MIXERS AND UNABLE TO BATCH MIX CEMENT SLURRY.
1014 | 02/16/2022 | SINO21 | ABQQ-551 | SDM | 15 Feb 0800 - 1530 | 10 | 30.5 | 891845 |  | BHA | FOT | MWD | 10942 | MWD TOOL FAILURE.
1016 | 02/16/2022 | SND-1501 | HRDH-431 | ARM | 12 Feb 1830 - 1630 | 11.5 | 94 | 891653 |  | TF | HERR | TBG | 5795 | OBSERVED PTP WAS PLUGGED WITH SALT ACCUMULATED ABOVE IT DUE TO NOT CHECKING THE FLOAT WHILE RIH.
1018 | 02/16/2022 | SND-2009 | NJYN-81 | ARM | 15 Feb 0930 - 0500 | 24 | 43.5 | 891846 |  | TH | PCPF | NA | 3395 | HAD OBSTRUCTION AT 3,395 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
1020 | 02/17/2022 | ADC-23 | RMLH-15 | GOC | 15 Feb 0015 - 0500 | 24 | 52.75 | 891865 |  | TF | FOT | CTRQ | 4527 | AL-GAITH FILL UP TOOL FAILED. 11' RUBBER PORTION SEPERATED AND FELL INSIDE OF CASING.
1021 | 02/17/2022 | ADC-29 | ABMK-4 | BHI | 17 Feb 0500 - 1430 | 9.5 | 9.5 | 891950 |  | DD | HERR | RSS | 7358 | RIH A NEW BIT INSTEAD OF RR IN GOOD CONDITIONS
1023 | 02/17/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 14.5 | 327.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
1024 | 02/17/2022 | ADC-29 | ABMK-4 | BHI | 17 Feb 0500 - 1430 | 9.5 | 9.5 | 891950 |  | DD | HERR | RSS | 7358 | RIH A NEW BIT INSTEAD OF RR IN GOOD CONDITIONS
1026 | 02/17/2022 | ADC-32 | SDGM-1139 | ARM | 17 Feb 0000 - 0500 | 5 | 5 | 891947 |  | CMT | TCPD | NA | 10570 | EXTRA REQUIREMENT DUE TO TAGGING CMT HIGHER.
1028 | 02/17/2022 | ADC-41L | UTMN-3105 | RIG | 17 Feb 1430 - 1530 | 1 | 1 | 891990 |  | RR | FOT | CSYS | 10265 | LEAKING WASH PIPE.
1030 | 02/17/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 24 | 232.5 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
1031 | 02/17/2022 | ADES-173 | HRDH-2256 | RIG | 17 Feb 0330 - 0400 | .5 | .5 | 891972 |  | RR | FOT | MPMP | 950 | JET CELLAR PUMP FAILURE
1033 | 02/17/2022 | ADES-173 | HRDH-2256 | RIG | 17 Feb 0115 - 0230 | 1.25 | 1.25 | 891948 |  | RR | FPMP | MPMP | 900 | REPAIR ON MUD PUMP#3, ELECTRICAL PROBLEM.
1034 | 02/17/2022 | ADES-173 | HRDH-2256 | RIG | 17 Feb 0330 - 0400 | .5 | .5 | 891972 |  | RR | FOT | MPMP | 950 | JET CELLAR PUMP FAILURE
1036 | 02/17/2022 | BCTD-4 | AWTD-11 | BHI | 17 Feb 0130 - 0500 | 3.5 | 3.5 | 892006 |  | BHA | FOT | MWD | 15405 | ED TOOL FAILURE. POH TO CHANGE TOOL.
1038 | 02/17/2022 | DQ-50L | HRDH-1492 | BHI | 17 Feb 1015 - 0500 | 18.75 | 18.75 | 891946 |  | BHA | FOT | MWD | 8504 | LOST MWD DECODING, TROUBLESHOOTING WITHOUT SUCCESS. DECIDED TO POOH & CHANGE TOOL.
1040 | 02/17/2022 | HI-4 | BRRI-780 | EMC | 14 Feb 0830 - 0500 | 24 | 65.75 | 891707 |  | MUD | IPDF | NA | 10453 | UNABLE TO CIRCULATE THICK MUD THROUGH SLB RSS/MWD BHA. POH & L/D RSS BHA AND RIH WITH 8.5" ROTARY BHA.
1041 | 02/17/2022 | MP-1 | LWHH-28 | RIG | 17 Feb 0700 - 1000 | 3 | 3 | 891945 |  | WO | MATL | NA | 0 | WAIT ON 7" SCRAPER TO ARRIVE FROM MP-4 (7" SCRAPER INCLUDS IN SCHEDULE "G" BUT CURRENTLY NOT ON BOARD).
1043 | 02/17/2022 | MP-1 | LWHH-28 | BLH | 15 Feb 0345 - 0500 | 21 | 23.25 | 891849 |  | TF | FOT | LLAP | 10480 | ATTEMPTED TO TEST 4-1/2" X 7" LINER TOP PKR FAILED. LINER TOP PKR SUSPECTED LEAK.
1044 | 02/17/2022 | MP-1 | LWHH-28 | RIG | 17 Feb 0700 - 1000 | 3 | 3 | 891945 |  | WO | MATL | NA | 0 | WAIT ON 7" SCRAPER TO ARRIVE FROM MP-4 (7" SCRAPER INCLUDS IN SCHEDULE "G" BUT CURRENTLY NOT ON BOARD).
1045 | 02/17/2022 | NBR-115S | HRDH-2140 | SJT | 17 Feb 1900 - 0300 | 8 | 8 | 891951 |  | TF | FOT | CTBG | 17371 | EXCESS TIME RU TOOLS/EQUIPMENT.
1047 | 02/17/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 16 | 160.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1048 | 02/17/2022 | NBR-115S | HRDH-2140 | SJT | 17 Feb 1900 - 0300 | 8 | 8 | 891951 |  | TF | FOT | CTBG | 17371 | EXCESS TIME RU TOOLS/EQUIPMENT.
1050 | 02/17/2022 | NBR-591S | HRDH-1933 | RIG | 15 Feb 0100 - 0500 | 24 | 52 | 891847 |  | RR | FOT | DWKS | 14411 | HAD FAILURE IN DRAWWORKS WHILE RIH .
1052 | 02/17/2022 | NBR-633S | TRYQ-5 | ARM | 13 Feb 1700 - 0500 | 24 | 106.5 | 891925 |  | TH | NARW | NA | 7750 | ATTEMPT TO RIH WASH DOWN 4-1/2" BOT LINER HANGER FROM 7,670' TO 7,750' WITH NO SUCCESS.
1054 | 02/17/2022 | NBR-783S | NJYN-89 | ARM | 17 Feb 1330 - 0500 | 15.5 | 15.5 | 891988 |  | TH | PCPF | NA | 3624 | HAD HOLE OBSTRUCTION, UNABLE TO RUN CSG
1056 | 02/17/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 768.5 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1058 | 02/17/2022 | PA-218S | QTIF-515 | RIG | 17 Feb 1200 - 1330 | 1.5 | 1.5 | 891966 |  | RR | FOT | DWKS | 1620 | WHILE P/U DRILL PIPE DRAWWORK STOPPED SUDDENLY AND DRILLING LINE BACKLASHED AND THE WRAPS BECOME UNSPOOL, SECURED THE BLOCK WITH HANG OFF LINE.
1060 | 02/17/2022 | SCTD-1 | UTMN-3070 | RIG | 17 Feb 0200 - 0500 | 3 | 3 | 891949 |  | TF | FOT | SFLN | 15050 | DOWNSTREAM PRV BYPASS TOWARD COLD FLARE
1062 | 02/17/2022 | SINO-10 | UMTW-1 | SWL | 17 Feb 1200 - 1430 | 2.5 | 2.5 | 891987 |  | TF | FOT | WLT | 200 | SURFACE CHECK AT 200 FT WITH W/L CONNECTOR, WEAK SIGNAL.
1064 | 02/17/2022 | SINO-32L | SHYB-535 | SCP | 17 Feb 2200 - 0100 | 3 | 3 | 891970 |  | TF | ISEQ | PDHMS | 7198 | COULD NOT PASS WITH SMART COMPLETION GAUGE MANDREL THRU 7" LINER TIE PACK PKR.
1065 | 02/17/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 9.5 | 9.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1067 | 02/17/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 0530 - 1930 | 14 | 14 | 891991 |  | WCNT | WC17 | NA | 9361 | WHILE MAKING CONNECTION NOTICED WELL FLOWING
1068 | 02/17/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 9.5 | 9.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1070 | 02/17/2022 | SND-2009 | NJYN-81 | ARM | 15 Feb 0930 - 2100 | 16 | 59.5 | 891846 |  | TH | PCPF | NA | 3395 | HAD OBSTRUCTION AT 3,395 FT AND UNABLE TO PASS. CIRCULATE HOLE AND ATTMEPT TO WASH DOWN THROUGH NO PROGRESS.
1072 | 02/17/2022 | SNF036 | MRJN-901 | ARN | 17 Feb 1845 - 2130 | 2.75 | 2.75 | 891989 |  | STUK | SCSG | CSG | 5517 | OBSERVED HOLE PACKED OFF AND 18-5/8'' CSG STRING STUCK.
1074 | 02/17/2022 | SP-122 | SDGM-726 | ITS | 17 Feb 2115 - 0145 | 4.5 | 4.5 | 891969 |  | TF | FOT | CTRQ | 3309 | ITS SLIPS NOT HOLDING 2-7/8" TBG.
1076 | 02/17/2022 | SP-261 | HZEM-162104 | SDM | 14 Feb 1400 - 0500 | 5 | 33.5 | 891765 |  | BHA | FOT | LWD | 13072 | LWD TOOLS NOT SENDING QUALITY LOG DATA. REQUIRED TO CHANGE OUT LWD TOOL.
1077 | 02/17/2022 | SP-306 | MNIF-865 | ARM | 17 Feb 0130 - 0500 | 3.5 | 3.5 | 891993 |  | LCIR | CFFM | SQZ | 6323 | ENCOUNTERED SEVERE LOSSES WHILE DRILLING AT 6323', CURE LOSSES.
1079 | 02/17/2022 | SP-306 | MNIF-865 | ARM | 17 Feb 1245 - 0130 | 12.75 | 12.75 | 891967 |  | LCIR | CFFM | LCM | 6323 | ENCOUNTERED SEVERE LOSSES WHILE DRILLING AT 6323', CURE LOSSES.
1080 | 02/17/2022 | SP-306 | MNIF-865 | ARM | 17 Feb 0130 - 0500 | 3.5 | 3.5 | 891993 |  | LCIR | CFFM | SQZ | 6323 | ENCOUNTERED SEVERE LOSSES WHILE DRILLING AT 6323', CURE LOSSES.
1082 | 02/17/2022 | SSA-5970 | HWYH-1257 | RIG | 17 Feb 2100 - 0500 | 8 | 8 | 892005 |  | RR | FOT | HSYS | 14551 | FAILURE IN SERVICE LOOP HYDRAULIC SUPPLY LINE.
1084 | 02/17/2022 | SSA-5974 | HRDH-1970 | GOC | 17 Feb 1700 - 2030 | 3.5 | 3.5 | 891994 |  | TF | XTTE | CTRQ | 5700 | AL-GAITH CRT TOOL NOT FUNCTIONING RIGHT- CHANGE OUT CRT TOOL.
1086 | 02/17/2022 | ZPEC-2 | HZEM-836 | ARM | 17 Feb 1200 - 0500 | 17 | 17 | 891971 |  | JF | HELD | CSG | 1105 | WHILE RIH 24" CSG GOT OBSTRCTION @850')HAD 15-20KLBS WEIGHT ON BTM.
1088 | 02/18/2022 | ADC-23 | RMLH-15 | GOC | 15 Feb 0015 - 0500 | 24 | 76.75 | 891865 |  | TF | FOT | CTRQ | 4527 | AL-GAITH FILL UP TOOL FAILED. 11' RUBBER PORTION SEPERATED AND FELL INSIDE OF CASING.
1090 | 02/18/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0430 | 23.5 | 256 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
1092 | 02/18/2022 | ADC-58L | ABHD-172 | RIG | 18 Feb 0200 - 0500 | 3 | 3 | 892105 |  | BOP | FOT | RAMS | 0 | ATTEMPT TO P/T BOP, OBSERVED BLIND SHEAR RAM NONNET SEAL LEAKING.
1094 | 02/18/2022 | ADC-65L | HWYH-1273 | RIG | 18 Feb 0315 - 0500 | 1.75 | 1.75 | 892070 |  | RR | FOT | TDS | 358 | ENCOUNTERED LEACK FROM THE TDS/IBOP DURING DRILLING TOP HOLE WITH HIGH VIBRATIONS.
1096 | 02/18/2022 | BCTD-4 | AWTD-11 | BHI | 17 Feb 0130 - 1400 | 9 | 12.5 | 892006 |  | BHA | FOT | MWD | 15405 | ED TOOL FAILURE. POH TO CHANGE TOOL.
1098 | 02/18/2022 | DPS-43 | SDGM-1187 | SPS | 18 Feb 1400 - 0500 | 15 | 15 | 892069 |  | BHA | FOT | MWD | 16440 | LOSS OF COMMUNICATION FROM TELEMETRY TOOLS MWD
1100 | 02/18/2022 | DQ-50L | HRDH-1492 | BHI | 17 Feb 1015 - 1300 | 8 | 26.75 | 891946 |  | BHA | FOT | MWD | 8504 | LOST MWD DECODING, TROUBLESHOOTING WITHOUT SUCCESS. DECIDED TO POOH & CHANGE TOOL.
1102 | 02/18/2022 | DQ-57L | KHRS-505 | TK1 | 18 Feb 0500 - 0500 | 24 | 24 | 892072 |  | DRG | WNCA | NA | 4850 | UNABLE TO PULL 7" WFD WHIPSTOCK.
1104 | 02/18/2022 | EXL-IA | SFNY-4050 | RIG | 18 Feb 0500 - 0800 | 2 | 2 | 892046 |  | RR | FOT | TDS | 1558 | TOP DRIVE BAILS KEPT ON GOING OFF CENTER CAUSING BAILS TO GO AGAINST THE ELVATORS SAFETY LATCH. THE BAILS CLAMPS SLIPPING ON ONE SIDE
1106 | 02/18/2022 | HI-4 | BRRI-780 | EMC | 14 Feb 0830 - 0300 | 22 | 87.75 | 891707 |  | MUD | IPDF | NA | 10453 | UNABLE TO CIRCULATE THICK MUD THROUGH SLB RSS/MWD BHA. POH & L/D RSS BHA AND RIH WITH 8.5" ROTARY BHA. MUD IS OUT OF SPEC DUE TO COMPETENCY ISSUE OF EMEC MUD ENGINEERS. PH METER IS NOT WORKING.
1107 | 02/18/2022 | MP-1 | LWHH-28 | BC | 18 Feb 1430 - 0500 | 5.75 | 5.75 | 892086 |  | TF | FOT | SCRN | 10480 | CONFIRMED THAT BAKER PRODUCTION SCREENS WAS OPENED WHICH LEAD TO CAUSING THE LEAK.
1109 | 02/18/2022 | MP-1 | LWHH-28 | BLH | 15 Feb 0345 - 1430 | 9.5 | 32.75 | 891849 |  | TF | FOT | LLAP | 10480 | ATTEMPTED TO TEST 4-1/2" X 7" LINER TOP PKR FAILED. LINER TOP PKR SUSPECTED LEAK.
1110 | 02/18/2022 | MP-1 | LWHH-28 | BC | 18 Feb 1430 - 0500 | 5.75 | 5.75 | 892086 |  | TF | FOT | SCRN | 10480 | CONFIRMED THAT BAKER PRODUCTION SCREENS WAS OPENED WHICH LEAD TO CAUSING THE LEAK.
1112 | 02/18/2022 | NBR-115S | HRDH-2140 | SJT | 17 Feb 1900 - 0500 | 24 | 32 | 891951 |  | TF | FOT | CTBG | 17371 | EXCESS TIME RU TOOLS/EQUIPMENT. COIL TUBING SHEARED WHILE TESTING LOWER SLIP/PIPE RAM.
1114 | 02/18/2022 | NBR-210S | HRDH-1491 | RIG | 17 Feb 2200 - 2300 | 18 | 25 | 892067 |  | DSF | FOT | DP | 8935 | WHILE DRILLING 8-1/2" W/ WFD RSS/LWD, OBSERVED PRESSURE GRADUALLY DROPPED BY 400 - 500 PSI, DECIDED TO POOH TO CHECK STRING & WFD TOOLS. FOUND WASH OUT IN DP BODY BELOW SLIPS AREA.
1116 | 02/18/2022 | NBR-591S | HRDH-1933 | RIG | 15 Feb 0100 - 0500 | 24 | 76 | 891847 |  | RR | FOT | DWKS | 14411 | HAD FAILURE IN DRAWWORKS WHILE RIH .
1118 | 02/18/2022 | NBR-633S | TRYQ-5 | ARM | 13 Feb 1700 - 0500 | 23.5 | 130 | 891925 |  | TH | NARW | NA | 7750 | ATTEMPT TO RIH WASH DOWN 4-1/2" BOT LINER HANGER FROM 7,670' TO 7,750' WITH NO SUCCESS.
1120 | 02/18/2022 | NBR-783S | NJYN-89 | ARM | 17 Feb 1330 - 0500 | 24 | 39.5 | 891988 |  | TH | PCPF | NA | 3624 | HAD HOLE OBSTRUCTION, UNABLE TO RUN CSG
1122 | 02/18/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 792.5 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1124 | 02/18/2022 | PA-529S | SHYB-45 | BHO | 18 Feb 0800 - 1030 | 2.5 | 2.5 | 892045 |  | WO | ORDS | NA | 100 | RECEIVED INSTRUCTIONS FROM ENGINEERING TO STOP RIH WHILE OFFICE TEAM WAS DISCUSSING WITH BAKER IF THE CORRECT TOOL WAS RIH ON COILED TUBING.
1126 | 02/18/2022 | SL-7 | ZULF-1335 | RIG | 18 Feb 0345 - 0500 | 1.25 | 1.25 | 892085 |  | RR | FOT | DWKS | 0 | DRAW WORKS BRAKE SHAFT SHIFTED OFF CENTER CAUSING BRAKE TO HANG UP.
1128 | 02/18/2022 | SND-2004 | BRRI-528 | RIG | 18 Feb 0000 - 0100 | 1 | 1 | 892071 |  | BOP | FOT | BOP | 6622 | WHEN BOP TEST BPR FAIL TO HOLD PRESSURE & TOOK LOG TIME FOR CLOSING , TROUBLESHHOT ONGOING
1130 | 02/18/2022 | SP-124 | ABHD-6 | BAW | 18 Feb 0500 - 0830 | 3.5 | 3.5 | 892107 |  | TF | FOT | WLT | 10671 | FALIED TO PERFORM VIT TEST AT 10671'
1131 | 02/18/2022 | SP-261 | HZEM-162104 | SDM | 14 Feb 1400 - 1030 | 5.5 | 39 | 891765 |  | BHA | FOT | LWD | 13072 | LWD TOOLS NOT SENDING QUALITY LOG DATA. REQUIRED TO CHANGE OUT LWD TOOL & RE-LOG OPEN HOLE
1133 | 02/18/2022 | SP-261 | HZEM-162104 | SDM | 12 Feb 0230 - 1200 | 1.5 | 11.5 | 891520 |  | BHA | FOT | MWD | 11240 | TROUBLE SHOOT MWD/LWD TOOLS.
1134 | 02/18/2022 | SP-261 | HZEM-162104 | SDM | 14 Feb 1400 - 1030 | 5.5 | 39 | 891765 |  | BHA | FOT | LWD | 13072 | LWD TOOLS NOT SENDING QUALITY LOG DATA. REQUIRED TO CHANGE OUT LWD TOOL & RE-LOG OPEN HOLE
1136 | 02/18/2022 | SP-306 | MNIF-865 | ARM | 17 Feb 0130 - 0500 | 24 | 27.5 | 891993 |  | LCIR | CFFM | SQZ | 6323 | ENCOUNTERED SEVERE LOSSES WHILE DRILLING AT 6323', CURE LOSSES.
1138 | 02/18/2022 | SSA-202 | QTIF-674 | SPS | 18 Feb 2215 - 2345 | 1.5 | 1.5 | 892066 |  | BHA | FOT | MWD | 17770 | SPERRY SUN TROUBLESHOOT DENSITY DATA QUALITY.
1140 | 02/18/2022 | SSA-5969 | UTMN-3195 | RIG | 18 Feb 0830 - 1000 | 1.5 | 1.5 | 892065 |  | RR | FOT | TDS | 11695 | EXCESS TIME FOR TRIPPING DUE TO IR PROBLEMS.
1142 | 02/18/2022 | ZPEC-2 | HZEM-836 | ARM | 17 Feb 1200 - 0500 | 24 | 41 | 891971 |  | JF | HELD | CSG | 1105 | WHILE RIH 24" CSG GOT OBSTRCTION @850')HAD 15-20KLBS WEIGHT ON BTM.
1144 | 02/19/2022 | ADC-23 | RMLH-15 | GOC | 15 Feb 0015 - 1130 | 6.5 | 83.25 | 891865 |  | TF | FOT | CTRQ | 4527 | AL-GAITH FILL UP TOOL FAILED. 11' RUBBER PORTION SEPERATED AND FELL INSIDE OF CASING.
1146 | 02/19/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 375.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
1148 | 02/19/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 8.75 | 264.75 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
1150 | 02/19/2022 | ADC-62L | ANDR-743 | TK3 | 18 Feb 2245 - 1200 | 7 | 13.25 | 892157 |  | LCIR | CFFM | LCM | 332 | ENCOUNTER TOTAL LOSSES AT 332 FT. ATTEMPT TO CURE WITH LCM AND CEMENT PLUG WITH NO SUCCESS
1152 | 02/19/2022 | ADC-65L | HWYH-1273 | RIG | 19 Feb 1045 - 1145 | 1 | 1 | 892155 |  | RR | FOT | TDS | 465 | OBSERVED BROKEN BOLTS ON TDS PIPE HANDLER JAWS
1154 | 02/19/2022 | ADM-337 | MRJN-900 | SWL | 19 Feb 0000 - 0100 | 1 | 1 | 892156 |  | TF | FOT | WLT | 8882 | SLB REPORT SHUT DOWN TOOL STRING LOST POWER DUE TO ELECTRIC SHORT INSIDE W/L UNIT. FOUND ONE LINE OF THE CABLE BURNED IN THE CONNECTION.
1156 | 02/19/2022 | ARO-2003 | MNIF-735 | ARM | 17 Feb 2015 - 0500 | 19 | 51.75 | 892146 |  | WO | SRVC | NA | 0 | WAITING THE ARRIVAL OF CAMERON WELLHEAD SPECIALIST AND PWS UT INSPECTION EQUIPMENT TO REPAIR DAMAGED HGR NECK.
1158 | 02/19/2022 | DPS-43 | SDGM-1187 | SPS | 18 Feb 1400 - 0330 | 22.5 | 37.5 | 892069 |  | BHA | FOT | MWD | 16440 | LOSS OF COMMUNICATION FROM TELEMETRY TOOLS MWD
1160 | 02/19/2022 | DQ-57L | KHRS-505 | TK1 | 18 Feb 0500 - 0500 | 17.5 | 41.5 | 892072 |  | DRG | WNCA | NA | 4850 | UNABLE TO PULL 7" WFD WHIPSTOCK.
1162 | 02/19/2022 | ENSCO-54 | ABSF-102 | INW | 19 Feb 0500 - 0830 | 3.5 | 3.5 | 892087 |  | TF | FOT | PLUGT | 0 | EXCESS TIME TO RETRIEVE 2-7/8" ME INTERWELL PLUG
1164 | 02/19/2022 | HI-5 | MHRH-58 | HSL | 19 Feb 1930 - 0000 | 4.5 | 4.5 | 892149 |  | JF | XTTE | SLICK | 6550 | ATTEMPTED TO PUNCH WITH HALLIBURTON DPU AT 6550 FT, NO INDICATION FOR PUNCH.
1166 | 02/19/2022 | MP-4 | LWHH-20 | NNN | 19 Feb 1530 - 0500 | 13.5 | 13.5 | 892150 |  | BHA | FOT | AST | 7552 | OBSERVED DROP IN PRESSURE, CHC, POH FOUND WAS OUT IN NAPESCO NEOTORK TOOL L/D SAME.
1168 | 02/19/2022 | NA-18S | SDGM-442 | BAW | 18 Feb 0630 - 0500 | 24 | 46.5 | 892165 |  | STUK | HINW | WLT | 507 | BAKER E-LINE TOOLS GOT STUCK WHILE RUNNING WITH EZSV-BP. WORK ON TOOLS STUCK.
1169 | 02/19/2022 | NBR-115S | HRDH-2140 | SJT | 17 Feb 1900 - 2030 | 15.5 | 47.5 | 891951 |  | TF | FOT | CTBG | 17371 | EXCESS TIME RU TOOLS/EQUIPMENT. COIL TUBING SHEARED WHILE TESTING LOWER SLIP/PIPE RAM.
1171 | 02/19/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 8.5 | 168.75 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1172 | 02/19/2022 | NBR-115S | HRDH-2140 | SJT | 17 Feb 1900 - 2030 | 15.5 | 47.5 | 891951 |  | TF | FOT | CTBG | 17371 | EXCESS TIME RU TOOLS/EQUIPMENT. COIL TUBING SHEARED WHILE TESTING LOWER SLIP/PIPE RAM.
1174 | 02/19/2022 | NBR-16S | HMYM-433304 | RIG | 19 Feb 1230 - 1830 | 6 | 6 | 892147 |  | RR | FOT | PSYS | 3063 | WHILE DRILLING LOST POWER TO TOP DRIVE, MUD PUMPS AND DRAW WORKS.
1176 | 02/19/2022 | NBR-591S | HRDH-1933 | RIG | 15 Feb 0100 - 0500 | 24 | 100 | 891847 |  | RR | FOT | DWKS | 14411 | HAD FAILURE IN DRAWWORKS WHILE RIH .
1178 | 02/19/2022 | NBR-633S | TRYQ-5 | ARM | 13 Feb 1700 - 0500 | 21.5 | 151.5 | 891925 |  | TH | NARW | NA | 7750 | ATTEMPT TO RIH WASH DOWN 4-1/2" BOT LINER HANGER FROM 7,670' TO 7,750' WITH NO SUCCESS.
1180 | 02/19/2022 | NBR-783S | NJYN-89 | ARM | 17 Feb 1330 - 0500 | 24 | 63.5 | 891988 |  | TH | PCPF | NA | 3624 | HAD HOLE OBSTRUCTION, UNABLE TO RUN CSG
1182 | 02/19/2022 | PA-622S | ZHRA-1 | BHT | 19 Feb 2100 - 0500 | 8 | 8 | 892154 |  | BHA | FOT | BIT | 4717 | POOH TO SURFACE 6-1/8" CORETRAX CLEAN-OUT ASSEMBLY, NOTICED 1 X CONE MISSING FROM 6-1/8" TRICONE BIT (HTC, MX-1, S/N Z616XT, IADC-117). 6-1/8" BIT DRILLED-OUT 7" LANDING COLLAR, 7" FLOAT COLLAR & 280' OF HARD CEMENT.
1184 | 02/19/2022 | SINO-43L | UTMN-4808 | TK2 | 18 Feb 0230 - 0500 | 24 | 26.5 | 892075 |  | STUK | STBH | BHA | 9361 | WHILE WORKING PIPE AND SPOT ACID PILLS LOST ABILITY TO CIRCULATE
1186 | 02/19/2022 | SL-7 | ZULF-1335 | RIG | 18 Feb 0345 - 0500 | 20 | 21.25 | 892085 |  | UPRA | GRF | DWKS | 0 | DRAW WORKS BRAKE SHAFT SHIFTED OFF CENTER CAUSING BRAKE TO HANG UP.
1188 | 02/19/2022 | SND-2001 | SDGM-1240 | CAM | 18 Feb 2030 - 1930 | 14.5 | 23 | 892126 |  | TF | ISEQ | WH | 0 | COULD NOT LAND CAMERON TBG HANGER (SN: 121659737-05) INSIDE CAMERON TBG SPOOL.
1190 | 02/19/2022 | SND-2004 | BRRI-528 | RIG | 18 Feb 0000 - 1600 | 5 | 6 | 892071 |  | BOP | FOT | BOP | 6622 | WHILE BOP TEST, MASTER RAM (BPR) FAIL TO HOLD PRESSURE - TROUBLESHOOT, CHANGE ACCUMULATOR 4 WAY VALVE & REARRANGE THE HYDRAULIC CONTROL LINES.
1192 | 02/19/2022 | SP-261 | HZEM-162104 | ITS | 19 Feb 0500 - 1230 | 7.5 | 7.5 | 892129 |  | WO | SRVC | NA | 17830 | I.T.S SENT TO LOCATION 2 X POWER TONGS IN DISREPAIR. BOTH TONGS FAILED AND NOT FIT FOR USE. WAIT ON REPLACEMENT TONGS FROM I.T.S YARD.
1194 | 02/19/2022 | SP-306 | MNIF-865 | ARM | 17 Feb 0130 - 0500 | 22.75 | 50.25 | 891993 |  | LCIR | CFFM | SQZ | 6323 | ENCOUNTERED SEVERE LOSSES WHILE DRILLING AT 6323', CURE LOSSES.
1196 | 02/19/2022 | SSA-202 | QTIF-674 | SPS | 19 Feb 0530 - 0500 | 23.5 | 23.5 | 892153 |  | BHA | FOT | MWD | 18025 | SPERRY SUN LOST COMMUNICATION WITH LWD TOOLS.
1198 | 02/19/2022 | SSA-302 | HRDH-1954 | ARM | 19 Feb 0930 - 1400 | 4.5 | 4.5 | 892127 |  | STUK | STBH | BHA | 6435 | PULLED INTO TIGHT HOLE, BHA BECAME STUCK, SPOT GREASE PILL & FREE STUCK.
1200 | 02/19/2022 | SSA-5868 | HRDH-1946 | RIG | 19 Feb 2215 - 2315 | 1 | 1 | 892145 |  | RR | FOT | TDS | 7103 | HAD MULFUNCTION IN TDS ENCODER.
1202 | 02/19/2022 | SSA-5969 | UTMN-3195 | SDM | 19 Feb 0830 - 0500 | 20.5 | 20.5 | 892128 |  | BHA | FOT | MWD | 11743 | LOST SLB MWD SIGNAL
1204 | 02/19/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 13.5 | 13.5 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1206 | 02/19/2022 | STY-038 | ZULF-2082 | DEP | 19 Feb 0800 - 0930 | 1.5 | 1.5 | 892125 |  | TF | FOT | RESH | 11795 | 7" TURBO-CASERS FAILED SURFACE TEST.
1208 | 02/19/2022 | ZPEC-2 | HZEM-836 | ARM | 17 Feb 1200 - 0600 | 1 | 42 | 891971 |  | JF | HELD | CSG | 1105 | WHILE RIH 24" CSG GOT OBSTRCTION @850')HAD 15-20KLBS WEIGHT ON BTM.
1210 | 02/20/2022 | ADC-49 | HRDH-1975 | ARM | 20 Feb 2000 - 0500 | 9 | 9 | 892213 |  | STUK | STBH | BHA | 1554 | AFTER CONNECTION PIPE STUCK.
1212 | 02/20/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 0500 | 23.5 | 288.25 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
1213 | 02/20/2022 | ADC-59L | HRDH-2232 | SDM | 20 Feb 1115 - 0500 | 17.75 | 17.75 | 892206 |  | BHA | FOT | MMOT | 12333 | OBSERVED RUBBER PIECES OF THE MUD MOTOR ON SHAKERS
1215 | 02/20/2022 | ADC-59L | HRDH-2232 | TK3 | 20 Feb 0630 - 1115 | 4.75 | 4.75 | 892205 |  | STUK | STBH | BIT | 12494 | BEFORE CONNECTION, BACK REAMED F/ 12,499 FT TO 12,494 FT ANG GOT STRING STALL W/ 19 KLB.FT & PRESSURE SHOOT UP F/ 3850 PSI TO 4550 PSI.
1216 | 02/20/2022 | ADC-59L | HRDH-2232 | SDM | 20 Feb 1115 - 0500 | 17.75 | 17.75 | 892206 |  | BHA | FOT | MMOT | 12333 | OBSERVED RUBBER PIECES OF THE MUD MOTOR ON SHAKERS
1218 | 02/20/2022 | ADC-68L | KRSN-705 | ARM | 20 Feb 0300 - 0400 | 1 | 1 | 892218 |  | WON | WTHR | NA | 8170 | WAIT ON WEATHER, WIND SPEED: 42-50 KM/HR.
1219 | 02/20/2022 | ADES-173 | HRDH-2256 | RIG | 20 Feb 0200 - 0315 | 1.25 | 1.25 | 892217 |  | RR | FOT | TDS | 86 | TOP DRIVE NOT CENTRELIZED.
1221 | 02/20/2022 | ADES-173 | HRDH-2256 | RIG | 20 Feb 2045 - 2145 | 1 | 1 | 892216 |  | RR | FOT | TDS | 0 | 1 CYLINDER OF TOP DRIVE LINK NOT WORKING.
1222 | 02/20/2022 | ADES-173 | HRDH-2256 | RIG | 20 Feb 0200 - 0315 | 1.25 | 1.25 | 892217 |  | RR | FOT | TDS | 86 | TOP DRIVE NOT CENTRELIZED.
1224 | 02/20/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 44 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1226 | 02/20/2022 | ARO-2003 | MNIF-735 | ARM | 17 Feb 2015 - 0500 | 18 | 69.75 | 892146 |  | WO | SRVC | NA | 0 | WAITING THE ARRIVAL OF CAMERON WELLHEAD SPECIALIST AND PWS UT INSPECTION EQUIPMENT TO REPAIR DAMAGED HGR NECK.
1228 | 02/20/2022 | BCTD-3 | HRDH-1924 | RIG | 20 Feb 0500 - 1900 | 14 | 14 | 892158 |  | DSF | FOT | STRG | 13909 | LOST COMMUNICATION WITH DHT. POH FOR BHA.
1230 | 02/20/2022 | DQ-57L | KHRS-505 | WWD | 18 Feb 0500 - 1530 | 10.5 | 52 | 892072 |  | TF | FOT | WPSTK | 4850 | UNABLE TO PULL 7" WFD WHIPSTOCK.
1232 | 02/20/2022 | NA-18S | SDGM-442 | BAW | 18 Feb 0630 - 0500 | 24 | 70.5 | 892165 |  | STUK | HINW | WLT | 507 | BAKER E-LINE TOOLS GOT STUCK WHILE RUNNING WITH EZSV-BP. WORK ON TOOLS STUCK.
1234 | 02/20/2022 | NBR-591S | HRDH-1933 | RIG | 15 Feb 0100 - 0445 | 23.75 | 123.75 | 891847 |  | RR | FOT | DWKS | 14411 | HAD FAILURE IN DRAWWORKS WHILE RIH .
1236 | 02/20/2022 | NBR-633S | TRYQ-5 | ARM | 13 Feb 1700 - 2130 | 16.5 | 168 | 891925 |  | TH | NARW | NA | 7750 | ATTEMPT TO RIH WASH DOWN 4-1/2" BOT LINER HANGER FROM 7,670' TO 7,750' WITH NO SUCCESS.
1237 | 02/20/2022 | NBR-783S | NJYN-89 | GOC | 20 Feb 1600 - 1730 | 1.5 | 1.5 | 892220 |  | JF | XTRI | CTRQ | 160 | CASING CREW UNABLE TO MAKE UP CASING IN A TIMELY MANNER. TOO MUCH TIME TAKEN
1239 | 02/20/2022 | NBR-783S | NJYN-89 | ARM | 17 Feb 1330 - 0200 | 19.5 | 83 | 891988 |  | TH | PCPF | NA | 3624 | HAD HOLE OBSTRUCTION, UNABLE TO RUN CSG
1240 | 02/20/2022 | NBR-783S | NJYN-89 | GOC | 20 Feb 1600 - 1730 | 1.5 | 1.5 | 892220 |  | JF | XTRI | CTRQ | 160 | CASING CREW UNABLE TO MAKE UP CASING IN A TIMELY MANNER. TOO MUCH TIME TAKEN
1242 | 02/20/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 22 | 838.5 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1244 | 02/20/2022 | PA-622S | ZHRA-1 | BHT | 19 Feb 2100 - 1145 | 6.75 | 14.75 | 892154 |  | BHA | FOT | BIT | 4717 | POOH TO SURFACE 6-1/8" CORETRAX CLEAN-OUT ASSEMBLY, NOTICED 1 X CONE MISSING FROM 6-1/8" TRICONE BIT (HTC, MX-1, S/N Z616XT, IADC-117). 6-1/8" BIT DRILLED-OUT 7" LANDING COLLAR, 7" FLOAT COLLAR & 280' OF HARD CEMENT.
1246 | 02/20/2022 | SCTD-1 | UTMN-3070 | RIG | 20 Feb 0500 - 0500 | 24 | 24 | 892185 |  | BHA | FOT | MMOT | 13794 | POOH DUE TO DOWNHOLE TOOL FAILURE.
1248 | 02/20/2022 | SCTD-2 | UTMN-1889 | SDM | 20 Feb 2030 - 0500 | 8.5 | 8.5 | 892207 |  | BHA | FOT | MWD | 12112 | LOST COMMUNICATIONS WITH DOWN HOLE TOOLS
1250 | 02/20/2022 | SINO-18 | ADHN-10 | CDS | 20 Feb 2045 - 0500 | 8.25 | 8.25 | 892208 |  | BHA | FOT | FV | 10980 | FLOAT VALVE NOT HOLDING -
1252 | 02/20/2022 | SINO-43L | UTMN-4808 | TK2 | 18 Feb 0230 - 0500 | 24 | 50.5 | 892075 |  | STUK | STBH | BHA | 9361 | WHILE WORKING PIPE AND SPOT ACID PILLS LOST ABILITY TO CIRCULATE
1254 | 02/20/2022 | SL-7 | ZULF-1335 | RIG | 18 Feb 0345 - 0500 | 24 | 45.25 | 892085 |  | UPRA | GRF | DWKS | 0 | DRAWWORKS BRAKE SHIFTED OFF CENTER CAUSING BRAKE TO HANG UP.
1256 | 02/20/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 73 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
1258 | 02/20/2022 | SP-258 | HZEM-160602 | RIG | 20 Feb 2045 - 0500 | 8.25 | 8.25 | 892219 |  | RR | FOT | TDS | 10253 | UNABLE TO FUNCTION TDS LINKS DUE TO LOCK PIN DISENGAGED.
1260 | 02/20/2022 | SP-306 | MNIF-865 | RIG | 20 Feb 1930 - 2030 | 1 | 1 | 892210 |  | RR | EDIS | CSYS | 6912 | OBSERVED LEAK FROM STAND PIPE- ROTARY HOSE CONNECTION. FIX SAME.
1261 | 02/20/2022 | SSA-101 | BRRI-1145 | SJC | 20 Feb 0730 - 1530 | 8 | 8 | 892222 |  | JF | CEDE | NA | 9280 | CEMENT DEBRIS FROM 4" DRILL PIPE USED FOR CEMENT PLUG ACCUMULATED AT FLOAT VALVE WHILE FILL UP CLEAN OUT ASSY.
1263 | 02/20/2022 | SSA-101 | BRRI-1145 | RIG | 20 Feb 2130 - 2300 | 1.5 | 1.5 | 892221 |  | RR | ITRP | RSSS | 9280 | AIR TAGGER CABLE MISALIGNMENT
1264 | 02/20/2022 | SSA-101 | BRRI-1145 | SJC | 20 Feb 0730 - 1530 | 8 | 8 | 892222 |  | JF | CEDE | NA | 9280 | CEMENT DEBRIS FROM 4" DRILL PIPE USED FOR CEMENT PLUG ACCUMULATED AT FLOAT VALVE WHILE FILL UP CLEAN OUT ASSY.
1266 | 02/20/2022 | SSA-202 | QTIF-674 | SPS | 19 Feb 0530 - 0500 | 21.75 | 45.25 | 892153 |  | BHA | FOT | MWD | 18025 | LOST COMMUNICATION WITH SPS LWD TOOLS.
1268 | 02/20/2022 | SSA-51 | MNIF-259 | ARM | 20 Feb 2045 - 2130 | .75 | .75 | 892214 |  | LCIR | FRFM | NA | 3935 | HAD TOTAL LOSS AT 3935FT, PICK UP OFF BOTTOM AND PUMP 100 BBLS 85 PCF MUD CAP.
1270 | 02/20/2022 | SSA-5969 | UTMN-3195 | SDM | 19 Feb 0830 - 0800 | 3 | 23.5 | 892128 |  | BHA | FOT | MWD | 11743 | LOST SLB MWD SIGNAL
1272 | 02/20/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 23.5 | 37 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1274 | 02/21/2022 | ADC-12 | ABQQ-199 | RIG | 11 Feb 1400 - 1000 | 1.75 | 20.75 | 891466 |  | RR | FOT | RWCS | 5130 | REPAIR TDS
1276 | 02/21/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 423.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
1278 | 02/21/2022 | ADC-49 | HRDH-1975 | ARM | 20 Feb 2000 - 2300 | 18 | 27 | 892213 |  | STUK | STBH | BHA | 1554 | AFTER CONNECTION PIPE STUCK.
1280 | 02/21/2022 | ADC-52 | HRDH-2312 | ARM | 08 Feb 1230 - 1130 | 6.5 | 294.75 | 891216 |  | LCIR | FRFM | NA | 11592 | TOOK TOTAL LOSSES AFTER PENETRATING KFBC FORMATION.
1282 | 02/21/2022 | ADC-59L | HRDH-2232 | TK3 | 20 Feb 1115 - 1800 | 13 | 30.75 | 892206 |  | DD | LTHI | MMOT | 12333 | OBSERVED RUBBER PIECES OF THE MUD MOTOR ON SHAKERS
1284 | 02/21/2022 | ADC-60 | ABSF-214 | SDM | 21 Feb 1015 - 0500 | 18.75 | 18.75 | 892289 |  | BHA | FOT | RSS | 11595 | DOWNLINK COMMANDS NOT ACCEPTED BY SLB RSS (POWERDRIVE) - ATTEMPT DOWNLINKS THROUGH MUD PUMPS & TOP DRIVE (23 DOWNLINKS ATTEMPTED: 4 ACCEPTED, 19 FAILED)
1286 | 02/21/2022 | ADES-14 | HRDH-476 | ARM | 20 Feb 0500 - 0500 | 24 | 48 | 892225 |  | BHS | FOHL | NA | 6660 | HAD OBSTRUCTION WHILE RUNNING OBL.
1288 | 02/21/2022 | ADES-173 | HRDH-2256 | RIG | 21 Feb 1600 - 2030 | 4.5 | 4.5 | 892306 |  | RR | DRIG | RSYS | 1000 | EXCESS TIME WHILE RIH 18'' 5/8 CASING.
1290 | 02/21/2022 | ADES-40 | SDGM-139 | RIG | 20 Feb 0430 - 1800 | 13 | 13.5 | 892226 |  | DSF | FOT | STRG | 0 | ATTEMPT TO CIRCULATE AT PLANNED DEPTH, OBSERVED STRING PLUGGED
1292 | 02/21/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 68 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1294 | 02/21/2022 | ARO-2003 | MNIF-735 | ARM | 17 Feb 2015 - 0000 | 19 | 88.75 | 892146 |  | WO | SRVC | NA | 0 | WAITING THE ARRIVAL OF CAMERON WELLHEAD SPECIALIST AND PWS UT INSPECTION EQUIPMENT TO REPAIR DAMAGED HGR NECK.
1296 | 02/21/2022 | HI-4 | BRRI-780 | SWL | 20 Feb 0100 - 0700 | 2 | 6 | 892223 |  | WO | SRVC | NA | 8562 | EXCESS TIME FOR SLB TO WORK ON DOWNLOADING & PROCESSING LOG DATA.
1298 | 02/21/2022 | HI-9 | MRJN-228 | TOT | 18 Feb 0000 - 0300 | 22 | 74 | 892285 |  | TF | FOT | HGRL | 12305 | TOT OH PACKER SETTING DART UNABLE TO SEAT IN DART COLLAR BELOW SETTING TOOL INFLATION CUP ASSY. UNABLE TO PRESSURE UP THE STRING TO SET TOT OH PACKER.
1299 | 02/21/2022 | NA-18S | SDGM-442 | WI1 | 21 Feb 1900 - 2300 | 4 | 4 | 892290 |  | WO | WOTO | NA | 0 | WAIT ON WIS X-OVER
1301 | 02/21/2022 | NA-18S | SDGM-442 | BAW | 18 Feb 0630 - 0500 | 20 | 90.5 | 892165 |  | STUK | HINW | WLT | 507 | BAKER E-LINE TOOLS GOT STUCK WHILE RUNNING WITH EZSV-BP. WORK ON TOOLS STUCK.
1302 | 02/21/2022 | NA-18S | SDGM-442 | WI1 | 21 Feb 1900 - 2300 | 4 | 4 | 892290 |  | WO | WOTO | NA | 0 | WAIT ON WIS X-OVER
1304 | 02/21/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 216.75 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1306 | 02/21/2022 | NBR-16S | HMYM-433304 | CAM | 21 Feb 1430 - 1530 | 1 | 1 | 892286 |  | WH | UITE | WBSH | 4877 | EXCESSIVE TIME TO USE RUN AND INSTALL CAMERON PACK-OFF
1307 | 02/21/2022 | NBR-783S | NJYN-89 | GOC | 21 Feb 0830 - 0500 | 20.5 | 20.5 | 892305 |  | JF | HERR | CTRQ | 2046 | WHILE RIH WITH 18 5/8" CASING HAD SUDDEN LOOSE OF STRING WEIGHT, FOUND THREAD CONNECTION NOT PROPERLY TORQUED (NOT TORQUED TO BASE OF TRIANGLE).
1309 | 02/21/2022 | NBR-783S | NJYN-89 | ARM | 17 Feb 1330 - 0830 | 3.5 | 86.5 | 891988 |  | TH | PCPF | NA | 3624 | HAD HOLE OBSTRUCTION, UNABLE TO RUN CSG
1310 | 02/21/2022 | NBR-783S | NJYN-89 | GOC | 21 Feb 0830 - 0500 | 20.5 | 20.5 | 892305 |  | JF | HERR | CTRQ | 2046 | WHILE RIH WITH 18 5/8" CASING HAD SUDDEN LOOSE OF STRING WEIGHT, FOUND THREAD CONNECTION NOT PROPERLY TORQUED (NOT TORQUED TO BASE OF TRIANGLE).
1312 | 02/21/2022 | SCTD-1 | UTMN-3070 | RIG | 20 Feb 0500 - 0530 | .5 | 24.5 | 892185 |  | BHA | FOT | MMOT | 13794 | POOH DUE TO DOWNHOLE TOOL FAILURE.
1313 | 02/21/2022 | SCTD-2 | UTMN-1889 | SDM | 21 Feb 0000 - 0500 | 5 | 5 | 892327 |  | BHA | FOT | MMOT | 12140 | WHILE RETURNING TO DRILL AHEAD SEEN 1500 PSI DIFFERENTIAL SPIKE, INTERNAL FACTORS ONLY
1315 | 02/21/2022 | SCTD-2 | UTMN-1889 | SDM | 20 Feb 2030 - 1430 | 9.5 | 18 | 892207 |  | BHA | FOT | MWD | 12112 | LOST COMMUNICATIONS WITH DOWN HOLE TOOLS
1316 | 02/21/2022 | SCTD-2 | UTMN-1889 | SDM | 21 Feb 0000 - 0500 | 5 | 5 | 892327 |  | BHA | FOT | MMOT | 12140 | WHILE RETURNING TO DRILL AHEAD SEEN 1500 PSI DIFFERENTIAL SPIKE, INTERNAL FACTORS ONLY
1318 | 02/21/2022 | SINO-10 | UMTW-1 | ZPC | 21 Feb 2130 - 0500 | 2 | 2 | 892328 |  | TF | FOT | CRT | 8270 | PICK UP & LAY DOWN MACHINE UNABLE TO HOLD IN UP POSITION - UNSAFE TO OPERATE
1320 | 02/21/2022 | SINO-18 | ADHN-10 | CDS | 20 Feb 2045 - 1700 | 12 | 20.25 | 892208 |  | BHA | FOT | FV | 10980 | FLOAT VALVE NOT HOLDING -
1322 | 02/21/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 84.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1324 | 02/21/2022 | SINO-46L | SHYB-203 | TK2 | 21 Feb 1145 - 1830 | 6.75 | 6.75 | 892326 |  | WO | SRVC | NA | 3658 | HAD LOW ROP, POOH TO CHECK BHA.
1326 | 02/21/2022 | SL-7 | ZULF-1335 | RIG | 18 Feb 0345 - 0500 | 24 | 69.25 | 892085 |  | UPRA | GRF | DWKS | 0 | DRAWWORKS BRAKE SHIFTED OFF CENTER CAUSING BRAKE TO HANG UP.
1328 | 02/21/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 97 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
1330 | 02/21/2022 | SP-258 | HZEM-160602 | RIG | 20 Feb 2045 - 1530 | 10.5 | 18.75 | 892219 |  | RR | FOT | TDS | 10253 | UNABLE TO FUNCTION TDS LINKS DUE TO LOCK PIN DISENGAGED.
1332 | 02/21/2022 | SSA-202 | QTIF-674 | SPS | 19 Feb 0530 - 0930 | 4.5 | 49.75 | 892153 |  | BHA | FOT | MWD | 18025 | LOST COMMUNICATION WITH SPS LWD TOOLS.
1334 | 02/21/2022 | SSA-5917 | HRDH-2344 | RIG | 21 Feb 2130 - 0000 | 2.5 | 2.5 | 892329 |  | JF | XTRI | BOP | 3078 | EXCESSIVE TIME FOR N/UP BOP STACK 26"3/4 3M
1336 | 02/21/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 23.5 | 60.5 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1338 | 02/22/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 447.75 | 890691 |  | STUK | STBH | BHA | 12174 | STRING STUCK AFTER CONNECTION.
1340 | 02/22/2022 | ADC-55L | UTMN-3076 | SWL | 22 Feb 0230 - 0500 | 2.5 | 2.5 | 892348 |  | TF | FOT | WLT | 15150 | RUN TLC LOG #3 (HLDS/QCNT/ECS/HNGS/GR) ON DP TO 15,150', ATTEMPTED TO OPEN TOOLS CALIPER FOR LOGGING UP, OBSERVED COMMUNACATION LOST, TROUBLE SHOOT- NO COMMUNICATION, POH.
1342 | 02/22/2022 | ADC-60 | ABSF-214 | SDM | 21 Feb 1015 - 1300 | 8 | 26.75 | 892289 |  | BHA | FOT | RSS | 11595 | DOWNLINK COMMANDS NOT ACCEPTED BY SLB RSS (POWERDRIVE) - ATTEMPT DOWNLINKS THROUGH MUD PUMPS & TOP DRIVE (23 DOWNLINKS ATTEMPTED: 4 ACCEPTED, 19 FAILED)
1344 | 02/22/2022 | ADC-62L | ANDR-743 | RIG | 22 Feb 2145 - 2230 | .75 | .75 | 892367 |  | RR | FOT | TDS | 870 | TDS LOST COMMUNICATION WITH VFD ROOM,
1346 | 02/22/2022 | ADES-14 | HRDH-476 | ARM | 20 Feb 0500 - 1100 | 6 | 54 | 892225 |  | BHS | FOHL | NA | 6660 | HAD OBSTRUCTION WHILE RUNNING OBL.
1348 | 02/22/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 92 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1350 | 02/22/2022 | NA-18S | SDGM-442 | BAW | 18 Feb 0630 - 0500 | 24 | 114.5 | 892165 |  | STUK | HINW | WLT | 507 | BAKER E-LINE TOOLS GOT STUCK WHILE RUNNING WITH EZSV-BP. WORK ON TOOLS STUCK.
1352 | 02/22/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 240.75 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1354 | 02/22/2022 | NBR-783S | NJYN-89 | GOC | 21 Feb 0830 - 0500 | 24 | 44.5 | 892305 |  | JF | HERR | CTRQ | 2046 | WHILE RIH WITH 18 5/8" CASING HAD SUDDEN LOOSE OF STRING WEIGHT, FOUND THREAD CONNECTION NOT PROPERLY TORQUED (NOT TORQUED TO BASE OF TRIANGLE).
1356 | 02/22/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 847.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1358 | 02/22/2022 | SCTD-2 | UTMN-1889 | RIG | 21 Feb 0000 - 1630 | 11.5 | 16.5 | 892327 |  | BHA | FOT | MMOT | 12140 | WHILE RETURNING TO DRILL AHEAD SEEN 1500 PSI DIFFERENTIAL SPIKE, INTERNAL FACTORS ONLY
1360 | 02/22/2022 | SINO-10 | UMTW-1 | ZPC | 21 Feb 2130 - 1645 | 1 | 3 | 892328 |  | TF | FOT | CRT | 8270 | PICK UP & LAY DOWN MACHINE UNABLE TO HOLD IN UP POSITION - UNSAFE TO OPERATE
1362 | 02/22/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 108.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1364 | 02/22/2022 | SL-7 | ZULF-1335 | RIG | 18 Feb 0345 - 0500 | 24 | 93.25 | 892085 |  | UPRA | GRF | DWKS | 0 | DRAWWORKS BRAKE SHIFTED OFF CENTER CAUSING BRAKE TO HANG UP.
1366 | 02/22/2022 | SND-2004 | BRRI-528 | WDS | 22 Feb 0700 - 0400 | 20 | 20 | 892346 |  | BHA | FOT | MWD | 6829 | LOST COMMUNICATION BETWEEN MWD & RSS , TRIP OUT TO CHANGE MWD
1367 | 02/22/2022 | SND-2007 | ADHN-370100 | RIG | 22 Feb 0915 - 1015 | 1 | 1 | 892349 |  | TF | XTTE | DP | 2359 | EXCESS TIME TRIPPING PIPE DUE TO IRON ROUGHNECK NOT WORKING.
1369 | 02/22/2022 | SND-2007 | ADHN-370100 | RIG | 22 Feb 1100 - 1230 | 1.5 | 1.5 | 892345 |  | RR | FOT | MPMP | 2359 | PUMP EFFIECIENCY TEST ON # 3 FAILED.
1370 | 02/22/2022 | SND-2007 | ADHN-370100 | RIG | 22 Feb 0915 - 1015 | 1 | 1 | 892349 |  | TF | XTTE | DP | 2359 | EXCESS TIME TRIPPING PIPE DUE TO IRON ROUGHNECK NOT WORKING.
1372 | 02/22/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 121 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
1374 | 02/22/2022 | SP-259 | HZEM-160812 | ITS | 22 Feb 0145 - 0345 | 2 | 2 | 892368 |  | TF | FOT | CRT | 0 | CRT SERVICE LUBE NOT COMPATIBLE WITH CRT.
1376 | 02/22/2022 | SSA-5891 | HRDH-1178 | RIG | 22 Feb 1430 - 0500 | 14.5 | 14.5 | 892350 |  | HSEI | UNKN | NA | 0 | FIRST AID INCIDENT W/THIRD PARTY COMPANY.
1378 | 02/22/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 23.5 | 84 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1380 | 02/22/2022 | WCL-83 | MRJN-835 | HML | 22 Feb 1200 - 0500 | 17 | 17 | 892365 |  | TF | FOT | WPSML | 6140 | HALLIBURTON MULTILATERAL WHIPSTOCK UNABLE TO LATCH WITH LATCH COLLAR.
1382 | 02/23/2022 | ADC-12 | ABQQ-199 | RIG | 23 Feb 1330 - 1730 | 4 | 4 | 892370 |  | RR | FOT | DWKS | 8200 | REPAIR DRAW WORKS.
1383 | 02/23/2022 | ADC-29 | ABMK-4 | BHI | 23 Feb 0615 - 0800 | 1.75 | 1.75 | 892353 |  | DD | HERR | RSS | 10885 | BHI TOOL PULSING TRANSMETING INTERMITTENT DATA.
1385 | 02/23/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 22.25 | 470 | 890691 |  | STUK | STBH | BHA | -12174 | STRING STUCK AFTER CONNECTION.
1386 | 02/23/2022 | ADC-29 | ABMK-4 | BHI | 23 Feb 0615 - 0800 | 1.75 | 1.75 | 892353 |  | DD | HERR | RSS | 10885 | BHI TOOL PULSING TRANSMETING INTERMITTENT DATA.
1388 | 02/23/2022 | ADC-32 | SDGM-1139 | RIG | 23 Feb 0230 - 0400 | 1.5 | 1.5 | 892357 |  | RR | FOT | RSYS | 14499 | EXCESS TIME DUE TO PIPE SPINNER NOT WORKING.
1390 | 02/23/2022 | ADC-60 | ABSF-214 | SDM | 23 Feb 0145 - 0445 | 1 | 1 | 892380 |  | TF | XTTE | MWD | 14445 | EXESSIVE TIME TO TAKE SURVEY
1392 | 02/23/2022 | ADES-173 | HRDH-2256 | RIG | 23 Feb 2100 - 2200 | 1 | 1 | 892354 |  | RR | FOT | TDS | 0 | TOP DRIVE HPU FAILURE.
1394 | 02/23/2022 | ADM-261 | MRJN-138 | BHI | 23 Feb 1730 - 0500 | 8.25 | 8.25 | 892378 |  | BHA | FOT | LWD | 8360 | LWD FAILURE AFTER FREQUENT MALFUNCTIONS.
1396 | 02/23/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 116 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1398 | 02/23/2022 | BB-84A | MRJN-588 | RIG | 23 Feb 0530 - 0630 | 1 | 1 | 892371 |  | BOP | HERR | SPOOL | 0 | OBSERVE LEAK BETWEEN DSA & T.H.S, REPLACED RING GASKET, TEST HOLD-OK.
1400 | 02/23/2022 | BCTD-3 | HRDH-1924 | RIG | 23 Feb 0630 - 0100 | 15 | 15 | 892355 |  | DSF | FOT | STRG | 15052 | DOWN HOLE "USMPR" TOOL FAILURE.
1402 | 02/23/2022 | MP-1 | LWHH-28 | OTH | 23 Feb 0500 - 2230 | 17.5 | 17.5 | 892356 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER, UNFAVOURABLE SEA CONDITIONS FOR PRODUCTION FIELD SERVICES TO BOARD PLATFORM AND CONFIRM ZERO-FLARE LINE-UP FOR FLOW BACK OPERATIONS TO GOSP.
1404 | 02/23/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 264.75 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1406 | 02/23/2022 | NBR-633S | TRYQ-5 | SPR | 23 Feb 0500 - 0700 | 2 | 2 | 892369 |  | TF | FOT | TTRQ | 3468 | EXCESS TIME TO RUN TUNBING DUE TO SAPESCO 2-7/8" TUBING SLIPS DIES WORN OUT AND NOT HOLDING TUBING GOOD.
1408 | 02/23/2022 | NBR-783S | NJYN-89 | GOC | 21 Feb 0830 - 0500 | 24 | 68.5 | 892305 |  | JF | HERR | CTRQ | 2046 | WHILE RIH WITH 18 5/8" CASING HAD SUDDEN LOOSE OF STRING WEIGHT, FOUND THREAD CONNECTION NOT PROPERLY TORQUED (NOT TORQUED TO BASE OF TRIANGLE).
1410 | 02/23/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 871.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1412 | 02/23/2022 | SINO-1L | KHRS-548 | TK1 | 23 Feb 1030 - 0500 | 18.5 | 18.5 | 892377 |  | DRG | WNCA | NA | 6345 | 7" WHIPSTOCK PREMATURE SET.
1414 | 02/23/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 132.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1416 | 02/23/2022 | SINO-5L | UTMN-307 | TK1 | 23 Feb 1830 - 0500 | 10.5 | 10.5 | 892376 |  | STUK | STBG | TBG | 8380 | HAD DIFFERENTIAL STUCK WHILE RIH W/ 4-1/2" LC.
1418 | 02/23/2022 | SL-7 | ZULF-1335 | RIG | 18 Feb 0345 - 0500 | 24 | 117.25 | 892085 |  | UPRA | GRF | DWKS | 0 | DRAWWORKS BRAKE SHIFTED OFF CENTER CAUSING BRAKE TO HANG UP.
1420 | 02/23/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 23.5 | 144.5 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
1422 | 02/23/2022 | SP-259 | HZEM-160812 | ITS | 22 Feb 0145 - 0730 | 2.5 | 4.5 | 892368 |  | TF | FOT | CRT | 0 | CRT SERVICE LUBE NOT COMPATIBLE WITH CRT.
1424 | 02/23/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0300 | 19.5 | 103.5 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1426 | 02/23/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 26 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1428 | 02/23/2022 | WCL-83 | MRJN-835 | HML | 22 Feb 1200 - 2200 | 17 | 34 | 892365 |  | TF | FOT | WPSML | 6140 | HALLIBURTON MULTILATERAL WHIPSTOCK UNABLE TO LATCH WITH LATCH COLLAR.
1430 | 02/24/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 493.25 | 890691 |  | STUK | STBH | BHA | -12174 | STRING STUCK AFTER CONNECTION.
1432 | 02/24/2022 | ADC-34 | UTMN-2317 | WDV | 20 Dec 0500 - 0500 | 9.5 | 31 | 885525 |  | TF | FOT | DV | 7107 | WFD DV TOOL FAILED, NOT ABLE TO SET PKR & OPEN DV PORTS.
1434 | 02/24/2022 | ADES-158 | ABQQ-737 | ARM | 23 Feb 0330 - 0400 | 23 | 24.5 | 892382 |  | STUK | HINW | WLT | 9546 | ATTEMPTED TO MOVE STRING AFTER RECORDING 1ST FLUID SAMPLE, STRING GOT STUCK.
1436 | 02/24/2022 | ADES-173 | HRDH-2256 | RIG | 24 Feb 0530 - 0915 | 3.75 | 3.75 | 892426 |  | RR | FOT | TDS | 1200 | TOP DRIVE IBOP FAILURE.
1438 | 02/24/2022 | ADM-261 | MRJN-138 | BHI | 23 Feb 1730 - 0430 | 22.5 | 30.75 | 892378 |  | BHA | FOT | LWD | 8360 | LWD FAILURE AFTER FREQUENT MALFUNCTIONS.
1440 | 02/24/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 140 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1442 | 02/24/2022 | ENS-108 | SFNY-1560 | RIG | 24 Feb 2130 - 0500 | 7.5 | 7.5 | 892428 |  | RR | FOT | TDS | 7888 | CHANGED OUT TDS ROTATING LINK ASSEMBLY.
1444 | 02/24/2022 | MP-1 | LWHH-28 | AP2 | 24 Feb 0500 - 0500 | 24 | 24 | 892429 |  | WO | WOPF | NA | 0 | WAITED ON TANAJIB OIL PRODUCTION PLANT APPROVAL/ AUTHORIZATION TO COMMENCE FLOWBACK OPERATIONS VIA GOSP TO TANAJIB. PLANT OVERLOADED WITH OTHER PLATFORMS ADDITIONAL FLOW.
1446 | 02/24/2022 | NA-18S | SDGM-442 | BAW | 18 Feb 0630 - 0500 | 24 | 162.5 | 892165 |  | STUK | HINW | WLT | 507 | BAKER E-LINE TOOLS GOT STUCK WHILE RUNNING WITH EZSV-BP. WORK ON TOOLS STUCK.
1448 | 02/24/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 288.75 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1450 | 02/24/2022 | NBR-16S | HMYM-433304 | WDV | 24 Feb 0730 - 0500 | 21.5 | 21.5 | 892431 |  | TF | FOT | DV | 4580 | FAILED TO INFLATE DV AND OPEN PORT.
1452 | 02/24/2022 | NBR-783S | NJYN-89 | GOC | 21 Feb 0830 - 0500 | 24 | 92.5 | 892305 |  | JF | HERR | CTRQ | 2046 | WHILE RIH WITH 18 5/8" CASING HAD SUDDEN LOOSE OF STRING WEIGHT, FOUND THREAD CONNECTION NOT PROPERLY TORQUED (NOT TORQUED TO BASE OF TRIANGLE).
1454 | 02/24/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 895.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1456 | 02/24/2022 | PA-529S | SHYB-45 | RIG | 24 Feb 0645 - 2300 | 16.25 | 16.25 | 892405 |  | TF | FOT | SLIPS | 1950 | OBSERVED STRING PLUGGED WHILE RIH.
1458 | 02/24/2022 | SINO-1L | KHRS-548 | TK1 | 23 Feb 1030 - 0500 | 24 | 42.5 | 892377 |  | DRG | CEDE | NA | 6345 | 7" WHIPSTOCK PREMATURE SET.
1460 | 02/24/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 156.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1462 | 02/24/2022 | SINO-5L | UTMN-307 | TK1 | 23 Feb 1830 - 0500 | 24 | 34.5 | 892376 |  | STUK | STBG | TBG | 8380 | HAD DIFFERENTIAL STUCK WHILE RIH W/ 4-1/2" LC.
1464 | 02/24/2022 | SL-7 | ZULF-1335 | RIG | 18 Feb 0345 - 1015 | 5.25 | 122.5 | 892085 |  | UPRA | GRF | DWKS | 0 | DRAWWORKS BRAKE SHIFTED OFF CENTER CAUSING BRAKE TO HANG UP.
1466 | 02/24/2022 | SP-262 | HZEM-141412 | SCD | 24 Feb 0400 - 0500 | 1 | 1 | 892430 |  | TF | XTTE | MWD | 1135 | FAULTY SCIENTIFIC GYRO DROP.
1468 | 02/24/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 23.5 | 127.5 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1470 | 02/24/2022 | STY-038 | ZULF-2084 | SRT | 24 Feb 0530 - 0500 | 10.75 | 10.75 | 892425 |  | BHA | FOT | UNDR | 9040 | XC-RHINO-REAMER NOT FUNCTIONING
1472 | 02/24/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 50 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1474 | 02/24/2022 | T914 | HWYH-512 | ARM | 24 Feb 1130 - 0500 | 17.5 | 17.5 | 892465 |  | STUK | STBH | BHA | 8690 | LOWER COMPLETION STUCK WHILE RIH
1476 | 02/24/2022 | WCL-83 | MRJN-835 | HML | 22 Feb 1200 - 1800 | 9.5 | 43.5 | 892365 |  | TF | FOT | WPSML | 6140 | HALLIBURTON MULTILATERAL WHIPSTOCK UNABLE TO LATCH WITH LATCH COLLAR.
1478 | 02/25/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 517.25 | 890691 |  | STUK | STBH | BHA | -12174 | STRING STUCK AFTER CONNECTION.
1480 | 02/25/2022 | ADC-32 | SDGM-1139 | RIG | 25 Feb 2100 - 2330 | 2.5 | 2.5 | 892532 |  | RR | FOT | DWKS | 14499 | OBSERVED DRAW WORKS NOT WORKING PROPERLY, PROBLEM IN WICHITA BREAK.
1482 | 02/25/2022 | ADC-34 | UTMN-2317 | WDV | 20 Dec 0500 - 0500 | 24 | 55 | 885525 |  | TF | FOT | DV | 7107 | WFD DV TOOL FAILED, NOT ABLE TO SET PKR & OPEN DV PORTS.
1484 | 02/25/2022 | ADES-14 | HRDH-476 | OES | 25 Feb 1230 - 1600 | 3.5 | 3.5 | 892525 |  | MUD | GAWH | SCS | 500 | PLUG STRING DUE TO SALT SETTLING (OES NPT).
1486 | 02/25/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 164 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1488 | 02/25/2022 | ADM-510 | ABSF-223 | WCR | 25 Feb 2200 - 2300 | 1 | 1 | 892529 |  | TF | FOT | CTRQ | 42 | FAILURE ON WEATHERFORD POWER UNIT
1490 | 02/25/2022 | AOD-1 | ZULF-693 | RIG | 25 Feb 1815 - 2015 | 2 | 2 | 892526 |  | JF | HERR | DRRK | 825 | DERRICK MANS PULL BACK WIRE CAUGHT UNDER FINGER, AND OPENED LATCH. RACKED STAND MOVED OUT FROM FINGER BOARD AND FELL ACROSS DERRICK.
1492 | 02/25/2022 | DPS-45 | UTMN-3175 | GOC | 25 Feb 2230 - 0300 | 4.5 | 4.5 | 892530 |  | TF | XTTE | CTRQ | 0 | EXCESS TIME DUE TO FAILURE OF POWER TONG TO REACH OPTIMUM TORQUE VALUES.
1494 | 02/25/2022 | ENS-108 | SFNY-1560 | RIG | 24 Feb 2130 - 0700 | 2 | 9.5 | 892428 |  | RR | FOT | TDS | 7888 | CHANGED OUT TDS ROTATING LINK ASSEMBLY.
1496 | 02/25/2022 | MP-1 | LWHH-28 | AP2 | 24 Feb 0500 - 1500 | 10 | 34 | 892429 |  | WO | WOPF | NA | 0 | WAITED ON TANAJIB OIL PRODUCTION PLANT APPROVAL/ AUTHORIZATION TO COMMENCE FLOWBACK OPERATIONS VIA GOSP TO TANAJIB. PLANT OVERLOADED WITH OTHER PLATFORMS ADDITIONAL FLOW.
1498 | 02/25/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0400 | 23 | 311.75 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1499 | 02/25/2022 | NBR-783S | NJYN-89 | GOC | 25 Feb 0900 - 1330 | 4.5 | 4.5 | 892505 |  | JF | XTRI | CTRQ | 455 | BROKEN CLAMP ON AL-GAITH BAILS.
1501 | 02/25/2022 | NBR-783S | NJYN-89 | ARM | 17 Feb 1330 - 0030 | 3.5 | 90 | 891988 |  | TH | PCPF | NA | 3624 | HAD HOLE OBSTRUCTION, UNABLE TO RUN CSG
1502 | 02/25/2022 | NBR-783S | NJYN-89 | GOC | 21 Feb 0830 - 2100 | 11.5 | 104 | 892305 |  | JF | HERR | CTRQ | 2046 | WHILE RIH WITH 18 5/8" CASING HAD SUDDEN LOOSE OF STRING WEIGHT, FOUND THREAD CONNECTION NOT PROPERLY TORQUED (NOT TORQUED TO BASE OF TRIANGLE).
1503 | 02/25/2022 | NBR-783S | NJYN-89 | GOC | 25 Feb 0900 - 1330 | 4.5 | 4.5 | 892505 |  | JF | XTRI | CTRQ | 455 | BROKEN CLAMP ON AL-GAITH BAILS.
1505 | 02/25/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 919.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1507 | 02/25/2022 | PA-529S | SHYB-45 | BAW | 24 Feb 0645 - 0500 | 3.5 | 19.75 | 892405 |  | TF | FOT | WLT | 7130 | UNSUCCESSFULL RCT TUBING CUT.
1509 | 02/25/2022 | RBP-50A | HSBH-58 | ARM | 25 Feb 0600 - 1800 | 12 | 12 | 892506 |  | WON | WTHR | NA | 13243 | WAIT ON WEATHER, UNABLE TO FLOW BACK WELL DUE TO UNFAVORABLE WIND CONDITION.
1511 | 02/25/2022 | SINO-18 | ADHN-10 | NCS | 24 Feb 0300 - 0600 | 1 | 3 | 892446 |  | CMT | HFFT | NA | 11440 | WHILE PERFORMING THE 9-5/8" CASING 1ST STAGE CEMENT JOB. AFTER PUMPING ALL THE CEMENT AND DURING THE CEMENT DISPLACEMENT. THE DISPLACEMENT PRESSURE WAS ON A GRADUAL CONTINOUS INCREASE AND THE DISPLACEMENT RATE WAS @ 12 BPM. WHEN THE PRESSURE REACHED 3,500 PSI THE CEMENT STOPPED MOVING. THE DISPLACEMENT WAS 13 BBLS SHORT AND THE DV TOOL OPENING PLUG HAD NOT LANDED IN THE DV TOOL. THEREFORE WE WERE NOT ABLE TO INFLATE THE DV TOOL PACKER AND SHIFT THE DV TOOL INTO THE OPEN POSITION.
1513 | 02/25/2022 | SINO-1L | KHRS-548 | TK1 | 23 Feb 1030 - 1100 | 6 | 48.5 | 892377 |  | DRG | CEDE | NA | 6345 | OBSTRUCTION WHILE RUNNING IN HOLE WITH 7" WFD WHIPSTOCK.
1515 | 02/25/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 180.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1517 | 02/25/2022 | SINO-46L | SHYB-203 | RIG | 25 Feb 2230 - 0130 | 3 | 3 | 892531 |  | RR | FOT | TDS | 4954 | WASH PIPE LEAKAGE .
1519 | 02/25/2022 | SINO-5L | UTMN-307 | TK1 | 23 Feb 1830 - 0500 | 24 | 58.5 | 892376 |  | STUK | STBG | TBG | 8380 | HAD DIFFERENTIAL STUCK WHILE RIH W/ 4-1/2" LC.
1521 | 02/25/2022 | SL-7 | ZULF-1335 | SPS | 25 Feb 0900 - 0500 | 20 | 20 | 892485 |  | TF | XTTE | MWD | 8094 | SPS LOST MWD SIGNAL.
1523 | 02/25/2022 | SND-2007 | ADHN-370100 | RIG | 25 Feb 1745 - 2215 | 4.5 | 4.5 | 892528 |  | RR | FOT | TDS | 1713 | FAILURE OF CONTROL SWITCH OF TOP DRIVE LINKS.
1525 | 02/25/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 192.5 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
1527 | 02/25/2022 | SP-262 | HZEM-141412 | SCD | 24 Feb 0400 - 0730 | 2.5 | 3.5 | 892430 |  | TF | XTTE | MWD | 1135 | FAULTY SCIENTIFIC GYRO DROP.
1529 | 02/25/2022 | SSA-5970 | HWYH-1257 | RIG | 25 Feb 1430 - 1700 | 2.5 | 2.5 | 892486 |  | RR | FOT | SLIPS | 16255 | FAILURE OF IRON ROUGHNECK & EASY TORQUE WHILE MAKE UP DRILLING BHA.
1531 | 02/25/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 23.5 | 151 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1533 | 02/25/2022 | STY-038 | ZULF-2084 | SRT | 24 Feb 0530 - 1200 | 4.25 | 15 | 892425 |  | BHA | FOT | UNDR | 9040 | XC-RHINO-REAMER NOT FUNCTIONING
1535 | 02/25/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 74 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1537 | 02/25/2022 | T914 | HWYH-512 | ARM | 24 Feb 1130 - 1100 | 6 | 23.5 | 892465 |  | STUK | STBH | BHA | 8690 | LOWER COMPLETION STUCK WHILE RIH
1539 | 02/26/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 0500 | 24 | 541.25 | 890691 |  | STUK | STBH | BHA | -12174 | STRING STUCK AFTER CONNECTION.
1541 | 02/26/2022 | ADC-32 | SDGM-1139 | RIG | 25 Feb 2100 - 1900 | 5.75 | 8.25 | 892532 |  | RR | FOT | DWKS | 14499 | OBSERVED DRAW WORKS NOT WORKING PROPERLY, PROBLEM IN WICHITA BREAK.
1543 | 02/26/2022 | ADC-34 | UTMN-2317 | WDV | 20 Dec 0500 - 0500 | 13.5 | 68.5 | 885525 |  | TF | FOT | DV | 7107 | WFD DV TOOL FAILED, NOT ABLE TO SET PKR & OPEN DV PORTS.
1545 | 02/26/2022 | ADC-56L | UTMN-3011 | TSC | 26 Feb 0015 - 0200 | 1.75 | 1.75 | 892537 |  | TF | FOT | PEL | 14868 | UNABLE TO OPERATE HCW DUE TO POWER FAILURE WITH REMOTE AND CABLE OPERATED CONTOL FOR HYDRAULIC CATWALK.
1547 | 02/26/2022 | ADES-173 | HRDH-2256 | RIG | 26 Feb 0245 - 0500 | 2.25 | 2.25 | 892538 |  | FISH | FWTS | BHA | 4986 | LOST PUMP PRESSURE & 75 KLB OF STRING WEIGHT.
1549 | 02/26/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 188 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1551 | 02/26/2022 | ENS-108 | SFNY-1560 | RIG | 26 Feb 0100 - 0230 | 1.5 | 1.5 | 892536 |  | JF | HERR | DRRK | 7800 | PIPE ELEVATORS INCORRECTLY POSITIONED TO PICK UP STAND, DERRICK MAN ATTEMPTED TO ENGAGE STAND TO ELEVATOR, HOWEVER MISSED AND LED TO FALLING STD ACROSS THE DERRICK.
1553 | 02/26/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 10.25 | 322 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1555 | 02/26/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 943.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1557 | 02/26/2022 | NBR-987S | ABTL-2 | RIG | 26 Feb 1930 - 2100 | 1.5 | 1.5 | 892535 |  | JF | XTRI | NA | 886 | EXCESIVE TIME TO PERFORM REGULAR MAINTENANCE
1559 | 02/26/2022 | PA-218S | QTIF-515 | RIG | 26 Feb 0245 - 0345 | 1 | 1 | 892540 |  | RR | LHFL | HSYS | 14226 | OBSERVED OIL LEAK FROM TDS GRABER BOX HYDRAULIC HOSE. REPLACE SAME.
1561 | 02/26/2022 | PA-529S | SHYB-45 | BAW | 24 Feb 0645 - 0500 | 24 | 43.75 | 892405 |  | TF | FOT | WLT | 7130 | UNSUCCESSFULL RCT TUBING CUT.
1563 | 02/26/2022 | RBP-50A | HSBH-58 | ARM | 25 Feb 0600 - 1115 | 3.25 | 15.25 | 892506 |  | WON | WTHR | NA | 13243 | WAIT ON WEATHER, UNABLE TO FLOW BACK WELL DUE TO UNFAVORABLE WIND CONDITION.
1565 | 02/26/2022 | SINO-18 | ADHN-10 | NCS | 24 Feb 0300 - 0500 | 9.75 | 12.75 | 892446 |  | CMT | HFFT | NA | 11440 | WHILE PERFORMING THE 9-5/8" CASING 1ST STAGE CEMENT JOB. AFTER PUMPING ALL THE CEMENT AND DURING THE CEMENT DISPLACEMENT. THE DISPLACEMENT PRESSURE WAS ON A GRADUAL CONTINOUS INCREASE AND THE DISPLACEMENT RATE WAS @ 12 BPM. WHEN THE PRESSURE REACHED 3,500 PSI THE CEMENT STOPPED MOVING. THE DISPLACEMENT WAS 13 BBLS SHORT AND THE DV TOOL OPENING PLUG HAD NOT LANDED IN THE DV TOOL. THEREFORE WE WERE NOT ABLE TO INFLATE THE DV TOOL PACKER AND SHIFT THE DV TOOL INTO THE OPEN POSITION.
1567 | 02/26/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 204.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1569 | 02/26/2022 | SINO-46L | SHYB-203 | RIG | 25 Feb 2230 - 1000 | 2 | 5 | 892531 |  | RR | FOT | TDS | 4954 | WASH PIPE LEAKAGE .
1571 | 02/26/2022 | SINO-5L | UTMN-307 | TK1 | 23 Feb 1830 - 0330 | 22.5 | 81 | 892376 |  | STUK | STBG | TBG | 8380 | HAD DIFFERENTIAL STUCK WHILE RIH W/ 4-1/2" LC.
1573 | 02/26/2022 | SL-7 | ZULF-1335 | SPS | 25 Feb 0900 - 0930 | 4.5 | 24.5 | 892485 |  | TF | XTTE | MWD | 8094 | SPS LOST MWD SIGNAL.
1575 | 02/26/2022 | SND-2006 | UTMN-3135 | FME | 26 Feb 2330 - 0430 | 5 | 5 | 892539 |  | WH | HERR | WH | 11973 | WAIT ON FMC TO SUPPLY THE PROPER BOTLS SIZE FOR TUBING HEAD SPOOL (1 7/8")
1577 | 02/26/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 216.5 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
1579 | 02/26/2022 | SSA-5969 | UTMN-3195 | ARM | 26 Feb 1200 - 0500 | 15 | 15 | 892541 |  | TH | NARW | NA | 10799 | GOT OBSTRUCTION WHILE RIH WITH SAMAA WBCO ASSY .
1581 | 02/26/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 23.5 | 174.5 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1582 | 02/26/2022 | T217 | UTMN-488 | WWL | 26 Feb 1100 - 0100 | 14 | 14 | 892534 |  | TF | FOT | FREE | 6050 | FPI TOOL IS NOT WORKING.
1584 | 02/26/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 10 | 84 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1585 | 02/26/2022 | T217 | UTMN-488 | WWL | 26 Feb 1100 - 0100 | 14 | 14 | 892534 |  | TF | FOT | FREE | 6050 | FPI TOOL IS NOT WORKING.
1587 | 02/26/2022 | WCL-83 | MRJN-835 | TK2 | 26 Feb 1245 - 0500 | 14.5 | 14.5 | 892542 |  | DD | ETRQ | RSS | 6193 | BHI RSS BHA UNABLE TO PASS WINDOW DUE TO BHA STIFF.
1589 | 02/27/2022 | ADC-29 | ABMK-4 | ARM | 03 Feb 1345 - 1200 | 7 | 548.25 | 890691 |  | STUK | STBH | BHA | -12174 | STRING STUCK AFTER CONNECTION.
1591 | 02/27/2022 | ADC-34 | UTMN-2317 | WDV | 20 Dec 0500 - 0500 | 24 | 92.5 | 885525 |  | TF | FOT | DV | 7107 | WFD DV TOOL FAILURE, UNABLE TO SET PKR & OPEN DV PORTS TO PERFORM 2ND STAGE CEMENT JOB.
1592 | 02/27/2022 | ADES-173 | HRDH-2256 | RIG | 27 Feb 0015 - 0500 | 4.75 | 4.75 | 892571 |  | RR | FOT | TDS | 4179 | TDS LINKS TILT SYSTEM MALFUNCTIONING, UNABLE TO POH. ELECTRICAL ISSUE.
1594 | 02/27/2022 | ADES-173 | HRDH-2256 | OJR | 26 Feb 0245 - 0015 | 18.75 | 21 | 892566 |  | BHA | FOT | JARS | 4986 | JAR PARTED
1595 | 02/27/2022 | ADES-173 | HRDH-2256 | RIG | 27 Feb 0015 - 0500 | 4.75 | 4.75 | 892571 |  | RR | FOT | TDS | 4179 | TDS LINKS TILT SYSTEM MALFUNCTIONING, UNABLE TO POH. ELECTRICAL ISSUE.
1597 | 02/27/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 212 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1598 | 02/27/2022 | ADM-511 | MRJN-2015 | ITS | 27 Feb 1830 - 1900 | .5 | .5 | 892576 |  | TF | FOT | CTRQ | 468 | OBSERVED OIL LEAKAGE FROM ITS POWER TONG HYDRAULIC HOSE
1600 | 02/27/2022 | ADM-511 | MRJN-2015 | ITS | 27 Feb 1600 - 1700 | 1 | 1 | 892574 |  | JF | HERR | CTRQ | 0 | ITS CRUSHED 7" PUP JOINT ON SEAL ASSY.
1601 | 02/27/2022 | ADM-511 | MRJN-2015 | ITS | 27 Feb 1700 - 1730 | .5 | .5 | 892575 |  | TF | FOT | CTRQ | 0 | MALUFUNCTION IN ITS POWER TONG, ROTATING HEAD STUCK ON 7" JOINT.
1602 | 02/27/2022 | ADM-511 | MRJN-2015 | ITS | 27 Feb 1830 - 1900 | .5 | .5 | 892576 |  | TF | FOT | CTRQ | 468 | OBSERVED OIL LEAKAGE FROM ITS POWER TONG HYDRAULIC HOSE
1604 | 02/27/2022 | AOD-1 | ZULF-693 | SBA | 27 Feb 2315 - 0500 | 5.75 | 5.75 | 892568 |  | TF | FOT | ESPL | 4545 | CHECK ESP CABLE, GROUND FAULT, PHASE TO GRND= 0 OHMS.
1606 | 02/27/2022 | DQ-50L | HRDH-1492 | BHI | 27 Feb 1900 - 0500 | 10 | 10 | 892565 |  | BHA | FOT | LWD | 11039 | LOST DEEP & MEDIUM RESISTIVITY DATA FROM LWD, TROUBLESHOOTING WITHOUT SUCCESS. DECIDED TO POOH & CHANGE TOOL.
1608 | 02/27/2022 | MP-4 | LWHH-20 | SPS | 26 Feb 1530 - 0500 | 18 | 31.5 | 892543 |  | DD | HERR | RSS | 9845 | SPS UNABLE TO GEOSTEER TO REQUIRED INCLINATION WITHIN DESIRED DLS.
1610 | 02/27/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 23.5 | 345.5 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1612 | 02/27/2022 | NBR-591S | HRDH-1933 | RIG | 27 Feb 2045 - 2215 | 1.5 | 1.5 | 892569 |  | RR | FOT | DWKS | 10855 | OBSERVED DRAWWORK OVERHEATED, TROUBLESHOOT & FIX SAME.
1614 | 02/27/2022 | NBR-633S | TRYQ-5 | ARN | 27 Feb 2000 - 0100 | 5 | 5 | 892567 |  | DRG | NARW | NA | 3822 | RUN FINAL DRIFT STRING WITH 3.625" HAD OBSTRUCTION AT 3,822'. TRY TO PASS WITHOUT SUCSSES.
1616 | 02/27/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 967.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1618 | 02/27/2022 | PA-529S | SHYB-45 | BC | 24 Feb 0645 - 0500 | 24 | 67.75 | 892405 |  | TF | FOT | PKR | 6014 | UNSUCCESSFULL RCT TUBING CUT.
1620 | 02/27/2022 | SINO-12L | HRDH-410 | RIG | 27 Feb 1130 - 1515 | 3.75 | 3.75 | 892573 |  | JF | HERR | FV | 1776 | FLOAT VALVE PLUGGED WITH HWDP DEBRIS.
1622 | 02/27/2022 | SINO-18 | ADHN-10 | NCS | 24 Feb 0300 - 0930 | 4.5 | 17.25 | 892446 |  | CMT | HFFT | NA | 11440 | WHILE PERFORMING THE 9-5/8" CASING 1ST STAGE CEMENT JOB. AFTER PUMPING ALL THE CEMENT AND DURING THE CEMENT DISPLACEMENT. THE DISPLACEMENT PRESSURE WAS ON A GRADUAL CONTINOUS INCREASE AND THE DISPLACEMENT RATE WAS @ 12 BPM. WHEN THE PRESSURE REACHED 3,500 PSI THE CEMENT STOPPED MOVING. THE DISPLACEMENT WAS 13 BBLS SHORT AND THE DV TOOL OPENING PLUG HAD NOT LANDED IN THE DV TOOL. THEREFORE WE WERE NOT ABLE TO INFLATE THE DV TOOL PACKER AND SHIFT THE DV TOOL INTO THE OPEN POSITION.
1624 | 02/27/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 228.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1626 | 02/27/2022 | SND-2002 | WAQR-9 | SDM | 27 Feb 1030 - 0500 | 18.5 | 18.5 | 892545 |  | BHA | FOT | MWD | 15180 | LOST SLB MWD SIGNAL
1628 | 02/27/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 148.5 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
1630 | 02/27/2022 | SP-261 | HZEM-162202 | RIG | 27 Feb 0300 - 0500 | 2 | 2 | 892570 |  | RR | FOT | TDS | 1362 | TOP DRIVE UN-ABLE TO BACK OUT OF DRILL STRING - EXCESSIVE TORQUE TO OPEN TDS. POH TO SHOE AND CHANGE OUT SAVER SUB.
1632 | 02/27/2022 | SSA-5969 | UTMN-3195 | ARM | 26 Feb 1400 - 0500 | 24 | 37 | 892541 |  | TH | NARW | NA | 10799 | GOT OBSTRUCTION WHILE RIH WITH SAMAA WBCO ASSY .
1634 | 02/27/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 1630 | 11.5 | 186 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1636 | 02/27/2022 | STY-038 | ZULF-2084 | SDM | 27 Feb 1430 - 0500 | 14 | 14 | 892544 |  | BHA | FOT | RSS | 11701 | RSS FAILURE, UNABLE TO BUILD INCLINATION
1637 | 02/27/2022 | T217 | UTMN-488 | WWL | 26 Feb 1100 - 1430 | 9.5 | 23.5 | 892534 |  | TF | FOT | FREE | 6050 | FPI TOOL IS NOT WORKING.
1639 | 02/27/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 14.5 | 98.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1640 | 02/27/2022 | T217 | UTMN-488 | WWL | 26 Feb 1100 - 1430 | 9.5 | 23.5 | 892534 |  | TF | FOT | FREE | 6050 | FPI TOOL IS NOT WORKING.
1642 | 02/27/2022 | WCL-83 | MRJN-835 | BHI | 26 Feb 1245 - 1445 | 9.75 | 24.25 | 892542 |  | DD | ETRQ | RSS | 6193 | BHI RSS BHA UNABLE TO PASS WINDOW DUE TO BHA STIFF.
1644 | 02/28/2022 | ADC-34 | UTMN-2317 | WDV | 20 Dec 0500 - 0500 | 24 | 116.5 | 885525 |  | TF | FOT | DV | 7107 | WFD DV TOOL FAILURE, UNABLE TO SET PKR & OPEN DV PORTS TO PERFORM 2ND STAGE CEMENT JOB.
1645 | 02/28/2022 | ADES-173 | HRDH-2256 | RIG | 28 Feb 1300 - 1530 | 2.5 | 2.5 | 892666 |  | RR | FOT | TDS | 4986 | WORK ON TDS (SERVICE LOOP PROBLEM)
1647 | 02/28/2022 | ADES-173 | HRDH-2256 | OJR | 26 Feb 0245 - 2300 | 15 | 36 | 892566 |  | BHA | FOT | JARS | 4986 | JAR PARTED
1648 | 02/28/2022 | ADES-173 | HRDH-2256 | RIG | 28 Feb 1300 - 1530 | 2.5 | 2.5 | 892666 |  | RR | FOT | TDS | 4986 | WORK ON TDS (SERVICE LOOP PROBLEM)
1650 | 02/28/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 236 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
1651 | 02/28/2022 | ADM-511 | MRJN-2015 | BLH | 28 Feb 0030 - 0345 | 3.25 | 3.25 | 892670 |  | JF | DSFT | SCBLR | 10063 | EXPERIENCE IN TROUBLE EXCESSIVE TIME TO STING IN WITH 7" TUBING INTO TBR,
1653 | 02/28/2022 | ADM-511 | MRJN-2015 | RIG | 28 Feb 0900 - 1600 | 7 | 7 | 892649 |  | HSEI | UNKN | NA | 7110 | DROPPED 7" TUBING JOINT FROM SIDE DOOR ELEVATOR AND SLIPT ACROSS THE RIG FLOOR THEN PASSED DOWN THROUGH THE V-DOOR AND STAYED ON THE PIPE DECK AREA.
1654 | 02/28/2022 | ADM-511 | MRJN-2015 | BLH | 28 Feb 0030 - 0345 | 3.25 | 3.25 | 892670 |  | JF | DSFT | SCBLR | 10063 | EXPERIENCE IN TROUBLE EXCESSIVE TIME TO STING IN WITH 7" TUBING INTO TBR,
1656 | 02/28/2022 | AOD-1 | ZULF-693 | SBA | 27 Feb 2315 - 0915 | 4.25 | 10 | 892568 |  | TF | FOT | ESPL | 4545 | CHECK ESP CABLE, GROUND FAULT, PHASE TO GRND= 0 OHMS.
1658 | 02/28/2022 | DQ-50L | HRDH-1492 | BHI | 27 Feb 1900 - 2330 | 18.5 | 28.5 | 892565 |  | BHA | FOT | LWD | 11039 | LOST DEEP & MEDIUM RESISTIVITY DATA FROM LWD, TROUBLESHOOTING WITHOUT SUCCESS. DECIDED TO POOH & CHANGE TOOL.
1660 | 02/28/2022 | ENS-141 | MRJN-758 | MSD | 28 Feb 2200 - 0500 | 6 | 6 | 892668 |  | JF | HERR | CTRQ | 1129 | SLICKLINE 3.875" DRIFT HUNG UP AT 1,129 FT DUE TO OVER TORQUED CONNECTION.
1662 | 02/28/2022 | HI-4 | BRRI-780 | SWL | 28 Feb 2315 - 0500 | 5.75 | 5.75 | 892648 |  | TF | FOT | WLT | 10223 | ATTEMPT TO POSITING WIRELINE DOWN, NO SUCCESS, WIRELINE WILL NOT GO DOWN, SUSPECT WIRELINE CABLE CLAMP SLIP
1664 | 02/28/2022 | JACK-203 | MHWZ-823 | ARM | 28 Feb 1400 - 1530 | 1.5 | 1.5 | 892669 |  | WON | WTHR | NA | 158 | SUSPEND OPERATION DUE TO HIGH WIND SPEED MORE THAN 32KM/H.
1666 | 02/28/2022 | MP-1 | LWHH-28 | SJT | 28 Feb 0800 - 1000 | 2 | 2 | 892688 |  | WO | WOTO | NA | 0 | WAITED ON ARRIVAL OF COIL TUBING EQUIPMENT RISER CROSSOVER. VESSEL DELIVERED ITEM, CONTINUED OPERATION WITH NO ISSUES.
1668 | 02/28/2022 | NA-393S | HWYH-1087 | ARM | 28 Feb 1800 - 0500 | 11 | 11 | 892685 |  | STUK | STDP | DP | 14950 | WHILE DRLG AT 14,950', HAD ERRATIC TQ, TRIED TO DRILL OFF TO GET SMOOTH TQ, HAD STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, HAD STRING STUCK.
1670 | 02/28/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 20.75 | 366.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1672 | 02/28/2022 | NBR-633S | TRYQ-5 | ARN | 27 Feb 2000 - 0500 | 24 | 29 | 892567 |  | JF | HELD | RBHA | 3822 | RUN FINAL DRIFT STRING WITH 3.625" HAD OBSTRUCTION AT 3,822'. TRY TO PASS WITHOUT SUCSSES.
1673 | 02/28/2022 | NBR-783S | NJYN-89 | RIG | 28 Feb 1930 - 0000 | 4.5 | 4.5 | 892667 |  | RR | FOT | TDS | 4115 | BACK UP WRENCH BOLTS BROKEN WHILE BREAK OUT SAVER SUB.
1675 | 02/28/2022 | NBR-783S | NJYN-89 | RIG | 27 Feb 0230 - 1430 | 7.5 | 10 | 892585 |  | RR | FOT | RWCS | 4115 | EXCESS TIME FOR NORMAL JOB TO M/U ACTUATOR ON TDS & FIX LEAKS ON BOP'S.
1676 | 02/28/2022 | NBR-783S | NJYN-89 | RIG | 28 Feb 1930 - 0000 | 4.5 | 4.5 | 892667 |  | RR | FOT | TDS | 4115 | BACK UP WRENCH BOLTS BROKEN WHILE BREAK OUT SAVER SUB.
1678 | 02/28/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 991.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1680 | 02/28/2022 | PA-529S | SHYB-45 | BC | 25 Feb 0130 - 0500 | 24 | 74.75 | 892607 |  | TF | FOT | PKR | 6014 | PACKER SLEEVE FAILED TO SHIFT
1682 | 02/28/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 252.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
1684 | 02/28/2022 | SND-2002 | WAQR-9 | SDM | 28 Feb 1030 - 1615 | 5.75 | 5.75 | 892626 |  | BHA | FOT | MWD | 15180 | HAD SLB MWD SIGNAL LOST FROM 15180' TO 15655' WHILE DRLG 5-7/8" HOLE.
1686 | 02/28/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 172.5 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
1688 | 02/28/2022 | SP-261 | HZEM-162202 | RIG | 27 Feb 0300 - 0745 | 2.75 | 4.75 | 892570 |  | RR | FOT | TDS | 1362 | TOP DRIVE UN-ABLE TO BACK OUT OF DRILL STRING - EXCESSIVE TORQUE TO OPEN TDS. POH TO SHOE AND CHANGE OUT SAVER SUB.
1690 | 02/28/2022 | SSA-5969 | UTMN-3195 | ARM | 26 Feb 1400 - 1430 | 9.5 | 46.5 | 892541 |  | TH | NARW | NA | 10799 | GOT OBSTRUCTION WHILE RIH WITH SAMAA WBCO ASSY .
1691 | 02/28/2022 | SSA-5971 | UTMN-2302 | CRT | 28 Feb 2100 - 0500 | 8 | 8 | 892687 |  | BHA | FOT | WBCL | 9050 | DROP PBL OPENING DART AND PUMP DOWN. PRESSURE INCREASED TO 3600 PSI WITHOUT OPENING PORTS. UNABLE TO CIRCULATE - STRING PLUGGED
1693 | 02/28/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 2100 | 2 | 188 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
1694 | 02/28/2022 | SSA-5971 | UTMN-2302 | CRT | 28 Feb 2100 - 0500 | 8 | 8 | 892687 |  | BHA | FOT | WBCL | 9050 | DROP PBL OPENING DART AND PUMP DOWN. PRESSURE INCREASED TO 3600 PSI WITHOUT OPENING PORTS. UNABLE TO CIRCULATE - STRING PLUGGED
1696 | 02/28/2022 | STY-038 | ZULF-2084 | SDM | 27 Feb 1430 - 1115 | 6.25 | 20.25 | 892544 |  | BHA | FOT | RSS | 11701 | RSS FAILURE, UNABLE TO BUILD INCLINATION
1697 | 02/28/2022 | T217 | UTMN-488 | HWP | 27 Feb 1430 - 1000 | 5 | 19.5 | 892606 |  | STUK | HINW | WLT | 6710 | FPI LOGGIGNG TOOL GOT STUCK @ PAC VALVE DEPTH.
1699 | 02/28/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 19 | 112.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1700 | 02/28/2022 | T217 | UTMN-488 | HWP | 27 Feb 1430 - 1000 | 5 | 19.5 | 892606 |  | STUK | HINW | WLT | 6710 | FPI LOGGIGNG TOOL GOT STUCK @ PAC VALVE DEPTH.
1702 | 02/28/2022 | ZPEC-1 | HRDH-3543 | RIG | 28 Feb 1600 - 0100 | 9 | 9 | 892645 |  | WO | MATL | NA | 4075 | OBSERVED LEAKING IN 8" DISCHARGE LINE, WAIT ON ZPEC TO PROVIDE 8" INVASION LINE.