## Sheet1
| Cause | Company Name | Cummulative Hrs | Date and Time | Depth | LT ID | LT Summary | LT Type | Object | Parent LT ID | Report Date | Rig Name | Time in Hrs | Well No
0 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ADC-21 | Hrs | MHWZ-991100
1 | UNKN | RIG | 17.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | A ROUSTABOUT JUMPED IN THE WATER PIT ON HIS OWN WHILE OTHER RIG CREW TRIED TO STOP HIM FROM JUMPING INTO THE WATER PIT. HE DROWNED AND COULD NOT GET OUT FROM THE WATER PIT. TWO LIFE RINGS WERE THROWN AT HIM BUT HE DID NOT CATCH ANY. CREW MEMBERS RESCUED HIM BUT HE WAS UNCONSCIOUS. CPR & AED WERE PERFOMED ON HIM BUT THERE WAS NO RESPONSE AND HE WAS IMMEDIATELY EVACUATED TO THE NEAREST HOSPITAL. KING KHALED HOSPITAL, IN AL KHARJ, HAS DECLARED THE IP AS DECEASED. | HSEI | NA |  | 09/01/2022 | ADC-21 | 17.25 | MHWZ-991100
2 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ADC-35 | Hrs | MAQL-5
3 | FOT | HCB | 76.5 | 29 Aug 0030 - 0500 | 5915 | 901459 | AFTER PLT LOGGING ANALYSIS, FOUND COMMUNCATION THRU HALLIBURTON BRIDGE PLUG SET ABOVE PREVIOUS PERFORATION. | TF | BP |  | 09/01/2022 | ADC-35 | 24 | MAQL-5
4 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ADC-42L | Hrs | SDGM-1258
5 | FOT | PKP | 10 | 01 Sep 1900 - 0500 | 15570 | 901600 | ATTEMPT TO SET LINER HANGER WITH NO SUCCESS | TF | HGRL |  | 09/01/2022 | ADC-42L | 10 | SDGM-1258
6 | ORDS | TK3 | 50 | 30 Aug 1400 - 1600 | 10968 | 901520 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK | WO | NA |  | 09/01/2022 | ADC-55L | 11 | UTMN-3171
7 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ADC-55L | Hrs | UTMN-3171
8 | STBH | TK3 | 584 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/01/2022 | ADC-55L | 13 | UTMN-3171
9 | ORDS | TK3 | 50 | 30 Aug 1400 - 1600 | 10968 | 901520 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK | WO | NA |  | 09/01/2022 | ADC-55L | 11 | UTMN-3171
10 | 13523 |  | OTH | C | 4485 | NA | HPJSM, CLOSED ICV # 2 FOR L1 AND CONTINUE FLOWING THE WELL VIA ICV#1 FOR L0.- @ 11:00 AM CONFIRMED OIL PERCENTAGE IS 98 %, WHP STABILIZED FOR LAST 5 HRS, TOTAL OIL PUMPED TO GOSP 1800 BBLS SINCE STARTED FLOW BACK, ACHIEVED MORE THAN 3 WELLBORE VOLUMES. | 13523 |  | BAL | 09/01/2022 | ADC-58L | LIFT | ABHD-169
11 | 13523 |  | SDR1 | C | 4485 | NA | CONDUCTED H2S DRILL, SIMULATED H2S RELEASE WHILE FLOWING BACK THE WELL, HENCE BAKER SIMULATED TO STOP THE ESP AND HALL SIMULATED TO CLOSE SSV VIA ESD REMOTLY. MEANWHILE ALL POB MASTERED ON SBA.- ALL POB WORKING WITH 15 MIN SCABA. | 13523 |  | RIG | 09/01/2022 | ADC-58L | LIFT | ABHD-169
12 | 13523 |  | OTH | C | 4485 | NA | HPJSM, HPJSM, OPENED ICV # 2 FOR L1 AND CLOSED ICV#1 FOR L0, MEANWHILE ESP WORKING W/ FREQ. 55 HZ & 32/64 CHOKE.- HALL WTS FLUSHED SAND FILTER & NO SOLIDS WERE RECOVERED. | 13523 |  | SCP | 09/01/2022 | ADC-58L | LIFT | ABHD-169
13 | 13523 |  | OTH | C | 4485 | NA | CONT FLOWING THE WELL VIA ICV#2 FOR L1. MEANWHILE ESP WORKING W/ FREQ. 55 HZ & 48/64 CHOKE.- STARTED WITH 99% OIL, AFTER 680 BBLS OF CUMMULATIVE VOLUME WATER % STARTED TO INCREASE GRADULALLY AND REACHED 95% AT RT.- CONT FLOWING TILL MEET MULTI LATERAL FLOW BACK CRITERIA. TOTAL FLUIDS FLOWED TO GOSP FROM L1 2255 BBLS (1053 BBLS OF OIL & 1202 BBLS OF WATER) | 13523 |  | BAL | 09/01/2022 | ADC-58L | LIFT | ABHD-169
14 | 48 | OOSS | Category | DOOS ID | WTST | Out of Scope Summary | WELL TESTING OPERATION. | 24 | 4485 | 30 Aug 1500 | 09/01/2022 | ADC-58L | Type | ABHD-169
15
16
17 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ADES-13 | Hrs | HWYH-163
18 | FRFM | ARM | 88.5 | 28 Aug 1300 - 1930 | 7809 | 901462 | SEVERE LOSSES WHILE CEMENT 4-1/2" OBL. | LCIR | NA |  | 09/01/2022 | ADES-13 | 14 | HWYH-163
19 | IDPR | BHI | 1.5 | 01 Sep 1530 - 1700 | 6564 | 901607 | GOT BHI UNIT SYSTEM PC FROZEN, TROUBLESHOOT SAME & FIX. | DD | RSS |  | 09/01/2022 | ADES-158 | 1.5 | ABQQ-590
20 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ADES-158 | Hrs | ABQQ-590
21 | FOT | BHI | 4.5 | 01 Sep 0030 - 0500 | 6838 | 901602 | RSS RIBS LOST RESPONSE WHILE DRILLING, TROUBLSHOOTING, NO SUCCESS. | BHA | RSS |  | 09/01/2022 | ADES-158 | 4.5 | ABQQ-590
22 | IDPR | BHI | 1.5 | 01 Sep 1530 - 1700 | 6564 | 901607 | GOT BHI UNIT SYSTEM PC FROZEN, TROUBLESHOOT SAME & FIX. | DD | RSS |  | 09/01/2022 | ADES-158 | 1.5 | ABQQ-590
23 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ADM-510 | Hrs | ABSF-225
24 | ISEQ | HML | 18 | 31 Aug 2300 - 1700 | 7180 | 901573 | DRAG WHILE POOH. INSUFFIENT AMOUNT OF METAL RECOVERED FROM MILLING OPERATION | TF | WPSML |  | 09/01/2022 | ADM-510 | 12 | ABSF-225
25 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ADM-655 | Hrs | SFNY-183
26 | OTH | RIG | 96 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/01/2022 | ADM-655 | 24 | SFNY-183
27 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ARO-3003 | Hrs | SFNY-1159
28 | FOT | RIG | 3.75 | 31 Aug 0400 - 0745 | 1733 | 901572 | UNABLE TO BREAKING OUT TIGHT CONNECTION WITH TDS, UPPER IBOP BROKE OUT FROM QUILL SHAFT. | RR | TDS |  | 09/01/2022 | ARO-3003 | 2.75 | SFNY-1159
29 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | ENS-108 | Hrs | ZULF-2015
30 | GRF | RIG | 240 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/01/2022 | ENS-108 | 24 | ZULF-2015
31 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | EXL-IA | Hrs | SFNY-1790
32 | FOT | RIG | 1 | 01 Sep 1115 - 1215 | 7480 | 901593 | CEMENT MANIFOLD ON RIG FLOOR LEAKING DURING PRESSURE TEST BEFORE CMT JOB | RR | CSYS |  | 09/01/2022 | EXL-IA | 1 | SFNY-1790
33 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | MP-1 | Hrs | MRJN-78
34 | FOT | NRT | 749.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 09/01/2022 | MP-1 | 24 | MRJN-78
35 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | NBR-797S | Hrs | UTMN-3119
36 | FOT | RIG | 2.5 | 01 Sep 1130 - 1400 | 10260 | 901592 | RIG POWER SYSTEM BACKOUT. | RR | PSYS |  | 09/01/2022 | NBR-797S | 2.5 | UTMN-3119
37 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | PA-218S | Hrs | HRDH-1976
38 | FOT | RIG | 5.5 | 01 Sep 1800 - 2330 | 700 | 901594 | MUD PUMP# 1 & 3 POP OFF VALVES LEAKING. | RR | MPMP |  | 09/01/2022 | PA-218S | 5.5 | HRDH-1976
39 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | RM-74A | Hrs | HSBH-68
40 | DSFT | TIL | 4.25 | 01 Sep 1615 - 2030 | 6459 | 901606 | TIW 18-5/8" LINER HANGER SETTING TOOL UNABLE TO RELEASE WITH PRIMARY METHORD AND 2 ATTEMPTS WITH CONTIGENCY RELEASE | JF | HGRL |  | 09/01/2022 | RM-74A | 4.25 | HSBH-68
41 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | SINO-33L | Hrs | HRDH-1542
42 | FOT | RIG | 169.25 | 24 Aug 1130 - 1715 | 1318 | 901575 | RIG TAKE LONG TIME TROUBLESHOOTING TDS ISSUES, KEEPING THE HOLE OPEN WITH NO CONDITION TRIP. CAUSING UN-STABLE SHALE AND HOLE PACKING OFF IN SEVERAL SPOTS, DECIDED TO SIDETRACK | RR | TDS |  | 09/01/2022 | SINO-33L | 12.25 | HRDH-1542
43 | 0 |  | OTH | N | 4406 | NA | CT CONTINUE POOH WITH 3.5" WFD CLEAN OUT ASSY. TO SURFACE. SECURE WELL, DISCONNECT RISER WITH CT INJECTOR HEAD, LD 3.5" WFD CLEAN OUT ASSY. | 0 |  | GDM | 09/01/2022 | SINO-37L | DCOM | HWYH-114
44 | 0 |  | OTH | N | 4406 | NA | M/U 3.625" WFD OVERSHOT WITH 3.125" GRAPPLE CONNECT SAME TO 2" GDMC CTU. CONNECTOR.- BHA LENGTH: 21.75 FT, MAX OD = 3.625".- FUNCTION TEST BHA ASSY WITH 0.5 / 1.0 / 1.5 / 2.0 BPM @ 500 / 1100/ 2100 / 3400 PSI RESPECTIVELY.- CONNECT INJECTOR HEAD TO RISER AND PT TO 2500 PSI.- FUNCTION TEST WFD BHA FLAPPER VALVE . | 0 |  | GDM | 09/01/2022 | SINO-37L | DCOM | HWYH-114
45 | 0 |  | OTH | N | 4406 | NA | RIH WITH 3.625" WFD OVERSHOT WITH 3.125" GRAPPLE TILL TAG AT 2,028' ODF (2048' CT DEPTH) WITH 82 PCF BRINE.- WASH DOWN TO CLEAN SAME TILL TAG TOF @ 2055' ODF ( 2075' CT DEPTH) MEANWHILE SWEEP HOLE WITH HI. VIS. PILL AND CIRCULATE OUT TO CLEAN TOF.- WASH DOWN TO LATCH TOF, HAD PRESSURE INCREASE BY 300 PSI, STOP PUMP. CONFIRM LATCH BY OVERPULL WITH 9.0 KLB.- POOH TO SURFACE - NO FISH RECOVERED - LD 3.625" WFD OVERSHOT.- RUNNING SPEED: 30 FT/MIN.- PUMPING RATE: 0.5 - 2 BPM @ 1250/4,300 PSI.- PULL TEST EVERY 1000 FT.- TAKE RETURNS THRU RAWABI DESANDER & CHOCK. | 0 |  | GDM | 09/01/2022 | SINO-37L | DCOM | HWYH-114
46 | 0 |  | OTH | N | 4406 | NA | M/U 3.25" WFD OVERSHOT WITH 2.313" GRAPPLE CONNECT ASSY. TO CT CONNECTOR.- BHA LENGTH: 21.75 FT, MAX OD = 3.25".- FUNCTION TEST BHA ASSY WITH 1.0 / 1.5 BPM @ 1600/ 2850 PSI RESPECTIVELY.- CONNECT INJECTOR HEAD TO RISER AND PT TO 2500 PSI.- FUNCTION TEST WFD BHA FLAPPER VALVE . | 0 |  | GDM | 09/01/2022 | SINO-37L | DCOM | HWYH-114
47 | 0 |  | OTH | N | 4406 | NA | RIH 3.25" WFD OVERSHOT WITH 2.313" GRAPPLE TO 2,045' ODF (2065' CT DEPTH), WASH DOWN TILL TAG TOF @ 2055' ODF (2075' CT DEPTH). ENGAGE FISH, HAD PRESSURE INCREASE BY 300 PSI, STOP PUMP, CONFIRM ENGAGEMNET WITH 12 KLB OVERPULL. POOH CT TO SURFACE.- NO FISH HAS BEEN RECOVERED.- NO JUNK MARKES FROM INSIDE ON 2.313" GRAPPLE.- RUNNING SPEED: 30 FT/MIN.- BREAK CIRC. WITH 0.5 BPM AND PERFORM PULL TEST EACH 1000 FT.- PUMPING RATE: 0.5 - 1.5 BPM @ 1250/4,300 PSI.- TAKE RETURNS THRU RAWABI DESANDER & CHOCK.- RECOVERED BY DESANDER: 1 KG SAND/SCALES. | 0 |  | GDM | 09/01/2022 | SINO-37L | DCOM | HWYH-114
48 | 0 |  | OTH | N | 4406 | NA | L/D 3.25" WFD OVERSHOT WITH 2.313" GRAPPLE, CHECK OVERSHOT CONDITION, M/U 3.25" WFD OVERSHOT WITH 2.313" GRAPPLE CONNECT ASSY. TO CT CONNECTOR.- BHA LENGTH: 20.25 FT, MAX OD = 3.25".- FUNCTION TEST BHA ASSY WITH 1.0 / 1.5 BPM @ 1600/ 2850 PSI RESPECTIVELY.- CONNECT INJECTOR HEAD TO RISER AND PT TO 2500 PSI.- FUNCTION TEST WFD BHA FLAPPER VALVE. | 0 |  | GDM | 09/01/2022 | SINO-37L | DCOM | HWYH-114
49 | 0 |  | OTH | N | 4406 | NA | CT RIH WITH 3.25" WFD FLOW RELEASE OVERSHOT DRESSED WITH 2.313" GRAPPLE TO 2,045' ODF (2065' CT DEPTH), WASH DOWN TAG @ 2050' (2070" CT DEPTH), CONT WASH DOWN TILL TAG TOF @ 2055' ODF (2075' CT DEPTH). ENGAGE FISH, HAD PRESSURE INCREASE BY 600 PSI , STOP PUMP, CONFIRM ENGAGEMENT WITH 7 KLB OVERPULL. START POOH CT TO SURFACE IN PROGRESS.- RUNNING SPEED: 30 FT/MIN.- BREAK CIRC. WITH 0.5 BPM AND PERFORM- PULL TEST EACH 1000 FT.- TAKE RETURNS THRU RAWABI DESANDER & CHOCK.- WHP = 800 PSI. | 0 |  | GDM | 09/01/2022 | SINO-37L | DCOM | HWYH-114
50 | 162 | OOS | Category | DOOS ID | DCOM | Out of Scope Summary | RETRIEVE PX PLUG STUCK IN X-NIPPLE, INSTALLED BY PRODUCTION TO SECURE THE WELL DURING CELLAR INSTALLATION. | 24 | 4406 | 26 Aug 1100 | 09/01/2022 | SINO-37L | Type | HWYH-114
51
52
53 | 5163 |  | NU | E |  | SNIP | HPJSM. N/D BELL NIPPLE & N/U 13-5/8" X 9-5/8" SHOOTING NIPPLE. * MONITOR WELL ON TRIP TANK. | 5163 |  | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
54 | 5163 |  | OTH | E |  | NA | HPJSM. R/U BAKER ATLAS WL LOGGING SHEAVES; CABLES AND BOP.* MONITOR WELL ON TRIP TANK. | 5163 |  | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
55 | 5163 |  | PTST | E |  | LUB | HPJSM. PT SHOOTING NIPPLE AND WL BOP TO 1500 PSI- OK.* MONITOR WELL ON TRIP TANK. | 5163 |  | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
56 | 5163 |  | OTH | E | 4545 | NA | HPJSM. P/U & M/U BAKER ATLAS W/L RUN#1 LOGGING TOOLS (XMAC-GR-WGI ).- HPJSM & DISCUSS JSA W/ ALL PARTIES INVOLVED PRIOR TO PERFORM W/L LOGGING OPERATIONS.- SURFACE CHECK & TEST LOGGING TOOLS -OK.- MONITOR ON TRIP TANK-STATIC.- TOOL LENGHT 102.69' & MAX OD 4.12". | 5163 |  | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
57 | 5163 | 5163 | LOG | E | 4545 | WLT | RIH BAKER W/L TOOLS (RUN#1) TO 9-5/8'' CS.* RECORD DOWN TO BOTTOM FROM CS TO 5163'. | 5163 | 0 | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
58 | 5163 | 4441 | LOG | E | 4545 | WLT | BHI W/L LOG UP 8-1/2" SECTION WITH LOGGING TOOLS (GR-XMAC-WGI) F/ 5163 FT TO 4441 FT (200' ABOVE 9-5/8" CS).* MONITOR THE WELL ON TT.* TOTAL HRS SINCE LAST CIRCULATION : 16 HRS. | 5163 | 5163 | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
59 | 5163 | 0 | LOG | E | 4545 | WLT | POOH W/L RUN#1 FROM 4441 FT TO SURFACE. | 5163 | 4441 | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
60 | 5163 |  | OTH | E | 4545 | NA | HPJSM, L/D LOGGING TOOLS (XMAC-GR-WGI). | 5163 |  | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
61 | 5163 |  | OTH | E |  | NA | HPJSM. P/U & M/U BAKER ATLAS W/L RUN#2 LOGGING TOOLS (HDIL-WGI-GR ).- SURFACE CHECK & TEST LOGGING TOOLS -OK.- MONITOR ON TRIP TANK-STATIC.- TOOL LENGHT 87.17' & MAX OD 4.12". | 5163 |  | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
62 | 5163 | 5163 | LOG | E |  | WLT | RIH BAKER W/L TOOLS (RUN#2) TO 9-5/8'' CS.* RECORD DOWN TO BOTTOM FROM CS TO 5163'.* MONITOR ON TRIP TANK-STATIC | 5163 | 0 | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
63 | 5163 | 4441 | LOG | E |  | WLT | BHI W/L LOG UP 8-1/2" SECTION WITH LOGGING TOOLS (HDIL-WGI-GR) F/ 5163 FT TO 4441 FT (200' ABOVE 9-5/8" CS).* MONITOR THE WELL ON TT.* TOTAL HRS SINCE LAST CIRCULATION : 21 HRS. | 5163 | 5163 | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
64 | 5163 | 0 | LOG | E |  | WLT | POOH W/L RUN#2 FROM 4441 FT TO SURFACE. | 5163 | 4441 | NWL | 09/01/2022 | SINO-46L | LOG | SHYB-270
65 | 5163 |  | OTH | E |  | NA | HPJSM, L/D LOGGING TOOLS (HDIL-WGI-GR). | 5163 |  | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
66 | 5163 |  | OTH | E |  | NA | HPJSM. P/U & M/U BAKER ATLAS W/L RUN#3 LOGGING TOOLS (DZDL-CN-GR ).- SURFACE CHECK & TEST LOGGING TOOLS -OK.- MONITOR ON TT -STATIC.- TOOL LENGHT 87.17' & MAX OD 4.12". | 5163 |  | BAW | 09/01/2022 | SINO-46L | LOG | SHYB-270
67 | 5163 | 5163 | LOG | E |  | WLT | RIH BAKER W/L TOOLS (RUN#3) TO 9-5/8''.* RECORD DOWN TO BOTTOM FROM CS TO 5163'.* MONITOR ON TT-STATIC | 5163 | 0 | NWL | 09/01/2022 | SINO-46L | LOG | SHYB-270
68 | 9 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ). | 9 | 4545 | 01 Sep 0800 | 09/01/2022 | SINO-46L | Type | SHYB-270
69
70
71 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | SINO-5L | Hrs | UTMN-639
72 | XBTR | TK1 | 4 | 01 Sep 0100 - 0500 | 7170 | 901605 | SLOW ROP. | LROP | BIT |  | 09/01/2022 | SINO-5L | 4 | UTMN-639
73 | FOT | RIG | 8.5 | 01 Sep 2030 - 0500 | 7100 | 901597 | REPAIR MUD PUMP #2 | RR | MPMP |  | 09/01/2022 | SND-1501 | 8.5 | HWYH-89
74 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | SND-1501 | Hrs | HWYH-89
75 | FOT | RIG | 12 | 31 Aug 2330 - 1130 | 6813 | 901552 | STAND PIPE ISOLATION VALVE LEAK | RR | CSYS |  | 09/01/2022 | SND-1501 | 6.5 | HWYH-89
76 | FOT | RIG | 8.5 | 01 Sep 2030 - 0500 | 7100 | 901597 | REPAIR MUD PUMP #2 | RR | MPMP |  | 09/01/2022 | SND-1501 | 8.5 | HWYH-89
77 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | SP-165 | Hrs | FDHL-146
78 | DFLI | EMC | 1 | 01 Sep 1145 - 1815 | 10585 | 901596 | OBSERVED CUT OF MUD WEIGHT OUT WHILE CIRCULATING | MUD | NA |  | 09/01/2022 | SP-165 | 1 | FDHL-146
79 | 6769 | 6452 | LOG | E | 4405 | WLT | CONTD STATION#9 , PUMP OUT POINT @ 6452' (2B08).- ACTIVATE DXL PROBE & PUMP OUT STATION #9 @ 6452'.- PUMP OUT 9 LITRES OF FIILTRATED FLUID, 166 LITRES OF FORMATION WATER, 139 LITERS OIL.TAKE 1 BOTTLE OF 500CC FLUID SAMPLE- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 2.95 BBLS (WATER: 1.67 BBLS - OIL: 1.28 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6452 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
80 | 6769 | 6445 | LOG | E | 4405 | WLT | POSITION STRING AT STATION#10, SIMPLE POINT @ 6445' & PERFORM STICKY TENDENCY TEST @ 15& 60 MIN - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6452 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
81 | 6769 | 6445 | LOG | E | 4405 | WLT | STATION#10 , SAMPLE POINT @ 6445' (AD2B).- ACTIVATE STANDARD PROBE & PUMP OUT STATION #10 @ 6445'.- PUMP OUT 9 LITRES OF FIILTRATED FLUID, 170 LITRES OF FORMATION WATER,TAKE 1 BOTTLE OF 500CC FLUID SAMPLE- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 4.08 BBLS (WATER: 2.80 BBLS - OIL: 1.28 BBLS).- DEACTIVATE STANDARD PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6445 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
82 | 6769 | 6440 | LOG | E | 4405 | WLT | CORRELATE & POSITION STRING AT STATION#11, PUMP OUT POINT @ 6440'.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6445 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
83 | 6769 | 6440 | LOG | E | 4405 | WLT | STATION#11 , PUMP OUT POINT @ 6440' (AD2B).- ACTIVATE DXL PROBE & PUMP OUT STATION #11 @ 6440'.- PUMP OUT 8 LITRES OF FIILTRATED FLUID, 26 LITRES OF FORMATION WATER, 139 LITERS OIL.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 5.16 BBLS (WATER: 3.01 BBLS - OIL: 2.15 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6440 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
84 | 6769 | 6434 | LOG | E | 4405 | WLT | POSITION STRING AT STATION#12, SAMPLE POINT @ 6434' & PERFORM STICKY TENDENCY TEST @ 15& 30,60 MIN - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6440 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
85 | 6769 | 6434 | LOG | E | 4405 | WLT | STATION#12 , SAMPLE POINT @ 6434' (2A06).- ACTIVATE DXL PROBE & PUMP OUT STATION #12 @ 6434'.- PUMP OUT 7 LITRES OF FIILTRATED FLUID, 7.5 LITRES OF FORMATION WATER, 131.5 LITERS OIL.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 6.07 BBLS (WATER: 3.10 BBLS - OIL: 2.97 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6434 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
86 | 6769 | 6429 | LOG | E | 4405 | WLT | CORRELATE& POSITION STRING AT STATION#13, PUMP OUT POINT @ 6429' .- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6435 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
87 | 6769 | 6429 | LOG | E | 4405 | WLT | STATION#13 , PUMP OUT POINT @ 6429' (2A06),CYCLE#1 : - ACTIVATE DXL PROBE & PUMP OUT STATION #13 @ 6429'.- PUMP OUT 15 LITRES OF FIILTRATED FLUID, 65.5 LITRES OF FORMATION WATER,65.5 LITERS OIL.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 6.98 BBLS (WATER: 3.60 BBLS - OIL: 3.38 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, MOVED STRING NO OVERPULL OBSERVED.- 41.25 HRS SINCE LAST CIRCULATION AT BTM. | 6769 | 6430 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
88 | 6769 | 6416 | LOG | E | 4405 | WLT | STATION#13 , PUMP OUT POINT @ 6429' (2A06),CYCLE#2 ...........ON GOING - ACTIVATE DXL PROBE & PUMP OUT STATION #13 @ 6429'.- 42.25 HRS SINCE LAST CIRCULATION AT BTM. | 6769 | 6429 | BAW | 09/01/2022 | SP-53L | LOG | HRDH-528
89 | 122.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RECORDING (ADEX-MREX-MLL) LOG & RUN #2:(GR-RCX-IFX-WGI) LOG AS PER PLAN | 24 | 4405 | 27 Aug 1015 | 09/01/2022 | SP-53L | Type | HRDH-528
90
91
92 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | SSA-201 | Hrs | MNHZ-1
93 | FOT | RIG | 4.25 | 01 Sep 0045 - 0500 | 5864 | 901601 | TOP DRIVE FUNCTION FAILURE. SUSPECT LOSS OF COMMUNICATION BETWEEM TDS AND PCR. | RR | TDS |  | 09/01/2022 | SSA-201 | 4.25 | MNHZ-1
94 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | SSA-5892 | Hrs | AWTD-141400
95 | FOT | RIG | 168.5 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 09/01/2022 | SSA-5892 | 24 | AWTD-141400
96 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/01/2022 | SSA-5914 | Hrs | WDYH-80
97 | FOT | RIG | .5 | 01 Sep 0230 - 0300 | 20137 | 901604 | OBSERVED TDS PIPE HANDLER MALFUNCTION. | RR | TDS |  | 09/01/2022 | SSA-5914 | .5 | WDYH-80
98 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADC-12 | Hrs | ABQQ-110
99 | XTRI | WWL | 6 | 02 Sep 1100 - 1700 | 5820 | 901638 | UNABLE TO SET EZSV | JF | WLT |  | 09/02/2022 | ADC-12 | 6 | ABQQ-110
100 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADC-21 | Hrs | MHWZ-991100
101 | UNKN | RIG | 41.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | A ROUSTABOUT JUMPED IN THE WATER PIT ON HIS OWN WHILE OTHER RIG CREW TRIED TO STOP HIM FROM JUMPING INTO THE WATER PIT. HE DROWNED AND COULD NOT GET OUT FROM THE WATER PIT. TWO LIFE RINGS WERE THROWN AT HIM BUT HE DID NOT CATCH ANY. CREW MEMBERS RESCUED HIM BUT HE WAS UNCONSCIOUS. CPR & AED WERE PERFOMED ON HIM BUT THERE WAS NO RESPONSE AND HE WAS IMMEDIATELY EVACUATED TO THE NEAREST HOSPITAL. KING KHALED HOSPITAL, IN AL KHARJ, HAS DECLARED THE IP AS DECEASED. | HSEI | NA |  | 09/02/2022 | ADC-21 | 24 | MHWZ-991100
102 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADC-35 | Hrs | MAQL-5
103 | FOT | HCB | 100.5 | 29 Aug 0030 - 0500 | 5915 | 901459 | AFTER PLT LOGGING ANALYSIS, FOUND COMMUNCATION THRU HALLIBURTON BRIDGE PLUG SET ABOVE PREVIOUS PERFORATION. | TF | BP |  | 09/02/2022 | ADC-35 | 24 | MAQL-5
104 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADC-41L | Hrs | SDGM-1244
105 | FOT | PM1 | 1 | 02 Sep 1230 - 1330 | 4069 | 901649 | CRT WAS HAVING TROUBLE FULLY ENGAGING INSIDE CASG. JOINT | TF | CTRQ |  | 09/02/2022 | ADC-41L | 1 | SDGM-1244
106 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADC-42L | Hrs | SDGM-1258
107 | FOT | PKP | 34 | 01 Sep 1900 - 0500 | 15570 | 901600 | ATTEMPT TO SET LINER HANGER WITH NO SUCCESS | TF | HGRL |  | 09/02/2022 | ADC-42L | 24 | SDGM-1258
108 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADC-55L | Hrs | UTMN-3171
109 | STBH | TK3 | 608 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/02/2022 | ADC-55L | 24 | UTMN-3171
110 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADC-56L | Hrs | UTMN-3069
111 | FOT | TSC | 1 | 02 Sep 0400 - 0500 | 1150 | 901652 | OBSERVED PROBLEM WITH TESCO POWER TONG. BACKUP GRABBER NOT ENGAGING. SUSPECTED BLOCKAGE IN HYDRAULIC HOSE FROM POWER UNIT. | TF | CTRQ |  | 09/02/2022 | ADC-56L | 1 | UTMN-3069
112 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADC-68L | Hrs | FDHL-174
113 | IBSL | TK3 | 13.75 | 02 Sep 0615 - 0500 | 6208 | 901647 | SLOW PROGRESS WHILE DRILLING OUT 9-5/8" SHUT-OFF PLUG & BAFFLE F/ 6,191 FT TO 6,208 FT, USING RSS BHA WITH 8-1/2" PDC BIT. | LROP | BIT |  | 09/02/2022 | ADC-68L | 13.75 | FDHL-174
114 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADES-158 | Hrs | ABQQ-590
115 | FOT | BHI | 28 | 01 Sep 0030 - 0430 | 6838 | 901602 | RSS RIBS LOST RESPONSE WHILE DRILLING, TROUBLESHOOTING, NO SUCCESS. | BHA | RSS |  | 09/02/2022 | ADES-158 | 23.5 | ABQQ-590
116 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADM-337 | Hrs | MRJN-900
117 | FOT | SWL | 4.75 | 02 Sep 0015 - 0500 | 0 | 901645 | TROUBLESSHOOT SCHLUMBERGER UNIT. COMMUINCATION POWER SUPPLY ON THE WAFE SYSTEM. | TF | WLU |  | 09/02/2022 | ADM-337 | 4.75 | MRJN-900
118 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ADM-655 | Hrs | SFNY-183
119 | OTH | RIG | 120 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/02/2022 | ADM-655 | 24 | SFNY-183
120 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | AOD-1 | Hrs | ZULF-694
121 | XTRI | RIG | 1.5 | 02 Sep 2230 - 0000 | 5153 | 901644 | TRIED TO FUNCTION THE BOP WINCHES, INADAQUATE AIR SUPPLY TO WINCHES. | JF | BOP |  | 09/02/2022 | AOD-1 | 1.5 | ZULF-694
122 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ARO-3002 | Hrs | MRJN-813
123 | WTHR | ARM | 41.5 | 22 Aug 0745 - 0500 | 8852 | 901136 | WIND SPEED TO LOW TO COMMENCE FLKOW BACK OPERATION. | WON | NA |  | 09/02/2022 | ARO-3002 | 16.25 | MRJN-813
124 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | DQ-57L | Hrs | KHRS-345
125 | UITE | WFS | 10.5 | 02 Sep 1830 - 0500 | 2852 | 901650 | ATTEMPTS TO PASS DVT W/WHIPSTOCK ASSEMBLY , NO SUCESSES | JF | MILL |  | 09/02/2022 | DQ-57L | 10.5 | KHRS-345
126 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ENS-108 | Hrs | ZULF-2015
127 | GRF | RIG | 264 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/02/2022 | ENS-108 | 24 | ZULF-2015
128 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | ENS-141 | Hrs | MRJN-3303
129 | FOT | RIG | 2 | 02 Sep 1415 - 1615 | 0 | 901613 | REPAIRED LEAKING N25 SUPPLY VALVE IN ACCUMULATOR UNIT. REPLACED O-RING WITH NEW ONE. | RR | RWCS |  | 09/02/2022 | ENS-141 | 2 | MRJN-3303
130 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | EXL-IA | Hrs | SFNY-1790
131 | FOT | RIG | 5.25 | 02 Sep 2015 - 0130 | 1200 | 901643 | RIG BULK CEMENT SUPPLY LINE PLUGGED WHEN SUPPLYING CEMENT TO CEMENT UNIT. | RR | ACDC |  | 09/02/2022 | EXL-IA | 5.25 | SFNY-1790
132 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | EXL-IVA | Hrs | ZULF-2041
133 | FOT | RIG | .75 | 02 Sep 1745 - 1830 | 1714 | 901648 | UNABLE TO DRILL AHEAD DUE TO SHAKERS OVERLOADING. SOME OF THE SHAKERS ARE DOWN WAITING ON PARTS. THE OTHER SHAKERS ARE NOT EFFICEINT, LOSING MUD AND UNABLE TO TRACK BBL IN AND BBL OUT WHILE DRILLING. USE OF FIREHOSE TO CLEAN SHAKERS EFFECTING THE ACTIVE MUD WEIGHT. | RR | CSYS |  | 09/02/2022 | EXL-IVA | .75 | ZULF-2041
134 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | MP-1 | Hrs | MRJN-78
135 | FOT | NRT | 773.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 09/02/2022 | MP-1 | 24 | MRJN-78
136 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | NBR-210S | Hrs | DILM-100
137 | MATL | MSL | 16.5 | 02 Sep 0500 - 2130 | 11945 | 901632 | ALMANSOORI LUBRICATOR CONNECTION ACME & X/O NOT FOR FIT FOR 4-1/16" X-TREE, WAITING FOR ALMANSOORI X/O. | WO | NA |  | 09/02/2022 | NBR-210S | 16.5 | DILM-100
138 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | NBR-987S | Hrs | JLMN-35
139 | FOT | RIG | 10.75 | 02 Sep 1815 - 0500 | 4400 | 901641 | UNABLE TO USE PRAGMA DUE TO HYDRAULIC LEAK. | RR | CATW |  | 09/02/2022 | NBR-987S | 10.75 | JLMN-35
140 | 9502 | 4675 | TI | N | 4585 | STDP | (OOS) RIH W/ 7" EZSV-STINGER ON 4" DP STD'S TO 4675' (20' ABOVE EZSV). | 9502 | 2500 | RIG | 09/02/2022 | SINO-19L | PA | HWYH-565
141 | 9502 |  | CIRC | N |  | MPMP | CIRC OUT HI VIS ABOVE EZSV. STING IN, CHECK INJECTIVITY W/75 PCF VISC BRINE - 2.5 BPM @ 1300 PSI. | 9502 |  | RIG | 09/02/2022 | SINO-19L | PA | HWYH-565
142 | 9502 |  | OTH | N |  | NA | HPJSM, R/U CEMENT HARD LINES CEMENT SQUEEZE P&A JOB. FLUSH & P/T CEMENT LINES TO 3000 PSI,OK. | 9502 |  | HCM | 09/02/2022 | SINO-19L | PA | HWYH-565
143 | 9502 | 9502 | CMP | N |  | RETNR | HPJSM, PERFORMED CEMENT/ACID SQUEEZE JOB,IN STING OUT, STINGER @ 4675' PUMP :>> 20 BBL 80 PCF TUNED SPACER, 5 BBL WATER, 30 BBL VDA ACID, FOLLOWED BY 5 BBL WATERSTING IN & PUMP>> FLY MIX & PUMP 98 BBL CMT SLURRY 118 PCF , PUMP 10 BBL 80 PCF TUNED SPACER BEHIND, DISPLACED W/14 BBL OF 75 PCF VISC BRINE (20 BBL UNDERDISPLACEMENT).>> TOTAL CMT PUMPED BELOW EZSV: 78 BBL. | 9502 | 4695 | HCM | 09/02/2022 | SINO-19L | PA | HWYH-565
144 | 9502 |  | CIRC | N |  | MPMP | STING OUT, REV CIRC 3 X STRG CAP W/ 75 PCF VISCOUS BRINE -RECOVERED 20 BBL PURE CMT @ SURFACE . | 9502 |  | RIG | 09/02/2022 | SINO-19L | PA | HWYH-565
145 | 9502 |  | OTH | N |  | NA | R/D CEMENT SURFACE LINES. | 9502 |  | HCM | 09/02/2022 | SINO-19L | PA | HWYH-565
146 | 9502 |  | CIRC | N |  | MPMP | SWEEP & CIRC HOLE CLEAN, FLOW CHECK - WELL STATIC. | 9502 |  | RIG | 09/02/2022 | SINO-19L | PA | HWYH-565
147 | 9502 | 10 | TO | N |  | STDP | POOH W/ EZSV STINGER ON 4" DP TO SURFACE.>> MONITOR WELL ON TRIP TANK. WELL STATIC. | 9502 | 4695 | RIG | 09/02/2022 | SINO-19L | PA | HWYH-565
148 | 9502 |  | HT | N |  | BHA | L/D EZSV-CR MST TOOLS | 9502 |  | RIG | 09/02/2022 | SINO-19L | PA | HWYH-565
149 | 9502 |  | NU | N |  | SNIP | N/D BELL NIPPLE, N/U 9-5/8" SHOOTING NIPPLE. | 9502 |  | RIG | 09/02/2022 | SINO-19L | BOP | HWYH-565
150 | 9502 |  | OTH | E |  | NA | HPJSM , R/U HES E-LINE SHEAVES , M/U MPET - GR - CCL - TEMP LOGGING TOOLS , FUNCTION TEST- OK . | 9502 |  | HWP | 09/02/2022 | SINO-19L | LOG | HWYH-565
151 | 9502 |  | OTH | E |  | NA | RIH W/ MPET- GR -CCL -TEMP LOGGING TOOLS TO 4680'(15' ABOVE EZSV-CR), CORRELATE DEPTH , PERFORM LOG UP MAIN PASS F/ 4680' TO SURFACE. | 9502 |  | HWP | 09/02/2022 | SINO-19L | LOG | HWYH-565
152 | 21 | OOS | Category | DOOS ID | LCL | Out of Scope Summary | LOCATE 7" CSG LEAK. | 1.5 | 4585 | 01 Sep 0130 | 09/02/2022 | SINO-19L | Type | HWYH-565
153
154
155 | FOT | RIG | 2 | 02 Sep 2315 - 0115 | 696 | 901640 | RIG ELECTRICIAN AND SINO BASE ELECTRICIAN FIX PUMP #2 ELECTRIC FAILURE IN SCR ROOM. | RR | MPMP |  | 09/02/2022 | SINO-22 | 2 | BRRI-1144
156 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SINO-22 | Hrs | BRRI-1144
157 | HERR | RIG | 2 | 02 Sep 2045 - 2245 | 696 | 901639 | RIG WELDER FIX THE LEAK AT 30" X 24" WELDED NECK FLANGE. | BOP | DVRT |  | 09/02/2022 | SINO-22 | 2 | BRRI-1144
158 | FOT | RIG | 2 | 02 Sep 2315 - 0115 | 696 | 901640 | RIG ELECTRICIAN AND SINO BASE ELECTRICIAN FIX PUMP #2 ELECTRIC FAILURE IN SCR ROOM. | RR | MPMP |  | 09/02/2022 | SINO-22 | 2 | BRRI-1144
159 | 0 |  | OTH | N | 4406 | NA | CT POOH WITH 3.25" WFD FLOW RELEASE OVERSHOT DRESSED WITH 2.313" GRAPPLE TO SURFACE, PRONG NOT RETREIVED. | 0 |  | GDM | 09/02/2022 | SINO-37L | DCOM | HWYH-114
160 | 0 |  | OTH | N | 4406 | NA | L/D 3.25" WFD FLOW RELEASE OVERSHOT, CHECK CONDITION OF OVERSHOT. NO MARKS AT BTM OF 2.313" GRAPPLE. PREPARE AND ARM 3.625" WFD OVERSHOT WITH 3.125" GRAPPLE. | 0 |  | GDM | 09/02/2022 | SINO-37L | DCOM | HWYH-114
161 | 0 |  | OTH | N | 4406 | NA | MU 3.625" WFD OVERSHOT WITH 3.125" GRAPPLE CONNECT SAME TO 2" GDMC CTU. CONNECTOR.- BHA LENGTH: 21.75 FT, MAX OD = 3.625".- FUNCTION TEST BHA ASSY WITH 0.5 BPM @ 700 PSI.- CONNECT INJECTOR HEAD TO RISER AND PT TO 2500 PSI.- FUNCTION TEST WFD BHA FLAPPER VALVE . | 0 |  | GDM | 09/02/2022 | SINO-37L | DCOM | HWYH-114
162 | 0 |  | OTH | N | 4406 | NA | RIH WITH 3.625" WFD OVERSHOT DRESSED WITH 3.125" GRAPPLE TO 2,045' ODF (2065' CT DEPTH), WASH DOWN TILL TAG TOF @ 2055' ODF (2075' CT DEPTH) MEANWHILE SWEEP HOLE WITH HI. VIS. PILL TO CLEAN TOF.- ENGAGE FISH, PRESSURE, INCREASE WITH 200 PSI, STOP PUMP. CONFIRM ENGAGEMENT WITH 9 KLB OVERPULL.- RUNNING SPEED: 30 FT/MIN.- BREAK CIRC. WITH 0.5 BPM AND PERFORM PULL TEST EACH 1000 FT.- POOH TO SURFACE. 3.125" ARAMCO PRONG RECOVERED SUCCESSFULLY AT SURFACE.- LD 3.625" WFD OVERSHOT.- TAKE RETURNS THRU RAWABI DESANDER & CHOCK, SAND/SCALES RECOVERED BY DESANDER: 0.25 KG.- WHP = 800 PSI. | 0 |  | GDM | 09/02/2022 | SINO-37L | DCOM | HWYH-114
163 | 0 |  | OTH | N | 4406 | NA | MU 4" WFD GS PULLING TOOL ASSY. AND CONNECT TO 2" CONNECTOR.- BHA LENGTH: 21.5 FT, MAX OD = 3.625".- FUNCTION TEST BHA ASSY WITH 0.5 BPM @ 700 PSI.- CONNECT INJECTOR HEAD TO RISER AND PT TO 2500 PSI.- FUNCTION TEST WFD BHA FLAPPER VALVE. | 0 |  | GDM | 09/02/2022 | SINO-37L | DCOM | HWYH-114
164 | 0 |  | OTH | N | 4406 | NA | RIH WITH 4" WFD GS PULLING TOOL ASSY. TO 2,045' ODF (2065' CT DEPTH), WASH DOWN TILL TAG TOP OF PX PLUG @ 2058' ODF ( 2078' CT DEPTH)- ENGAGE PLUG, PRESSURE INCREASE BY 200 PSI, STOP PUMP. CONFIRM ENGAGEMENT WITH 7 KLB OVERPULL.- POOH TO SURFACE.- RUNNING SPEED: 30 FT/MIN.- BREAK CIRC. WITH 0.5 BPM AND PERFORM PULL TEST EACH 1000 FT.- 100 % ARAMCO PX PLUG HAS BEEN RECOVERED.- LD 4" WFD 4" WFD GS PULLING TOOL ASSY. NOTES- TAKE RETURNS THRU RAWABI DESANDER & CHOCK, SAND/SCALES RECOVERED BY DESANDER: 0.25 KG.- WHP = 800 PSI. | 0 |  | GDM | 09/02/2022 | SINO-37L | DCOM | HWYH-114
165 | 186 | OOS | Category | DOOS ID | DCOM | Out of Scope Summary | RETRIEVE PX PLUG STUCK IN X-NIPPLE, INSTALLED BY PRODUCTION TO SECURE THE WELL DURING CELLAR INSTALLATION. | 24 | 4406 | 26 Aug 1100 | 09/02/2022 | SINO-37L | Type | HWYH-114
166
167
168 | 5163 | 0 | LOG | E |  | WLT | BHI W/L LOG UP WITH LOGGING TOOLS (DZDL-CN-GR ) F/ 5163' TO SURFACE.* MONITOR THE WELL ON TT.* TOTAL HRS SINCE LAST CIRCULATION : 32 HRS | 5163 | 5163 | BAW | 09/02/2022 | SINO-46L | LOG | SHYB-270
169 | 5163 |  | OTH | E |  | NA | HPJSM, R/D LOGGING TOOLS (GR- CN-ZDL). | 5163 |  | BAW | 09/02/2022 | SINO-46L | LOG | SHYB-270
170 | 5163 |  | NU | E |  | SNIP | HPJSM, ND SHOOTING NIPPLE, NU BELL NIPPLE & CONNECT FLOW LINE. | 5163 |  | BAW | 09/02/2022 | SINO-46L | LOG | SHYB-270
171 | 5163 |  | HT | E | 4545 | BHA | HPJSM , P/U & M/U 8-1/2" CONDITION TRIP ASSY . | 5163 |  | RIG | 09/02/2022 | SINO-46L | CT | SHYB-270
172 | 5163 | 5163 | TI | E | 4545 | STDP | RIH W/8-1/2" CONDITION TRIP ASSY ON 5" STDS DP TO BTM @ 5163',** PASS DV TOOL FREELY.** WASH DOWN LAST STAND. | 5163 | 0 | RIG | 09/02/2022 | SINO-46L | CT | SHYB-270
173 | 5163 |  | CIRC | E | 4545 | MPMP | HPJSM, SWEEP THE HOLE W/ 50 BBLS HI-VIS PILL, CHC, 100% CIRC. F/C- WELL STATIC | 5163 |  | RIG | 09/02/2022 | SINO-46L | MILL | SHYB-270
174 | 5163 | 4641 | TO | E | 4545 | STDP | POOH FREELY ON ELEVATOR W/8-1/2" CONDITION TRIP ASSY TO 9-5/8" CSG SHOE @ 4641'.** F/C- WELL STATIC.* MONITOR THE WELL ON TT & T/SHHET. | 5163 | 5163 | RIG | 09/02/2022 | SINO-46L | CT | SHYB-270
175 | 5163 | 0 | TO | E | 4545 | STDP | CONT POOH W/8-1/2" CONDITION TRIP ASSY TO SURFACE.* F/C WELL STATIC.* MONITOR THE WELL ON TRIP TANK. | 5163 | 4641 | RIG | 09/02/2022 | SINO-46L | CT | SHYB-270
176 | 5163 |  | HT | E | 4545 | BHA | HPJSM, LD 8-1/2" CONDITION TRIP ASSY.* MONITOR THE WELL ON TRIP TANK. | 5163 |  | RIG | 09/02/2022 | SINO-46L | CT | SHYB-270
177 | 5163 |  | NU | E | 4545 | SNIP | HPJSM. N/D BELL NIPPLE & N/U 13-5/8" X 9-5/8" SHOOTING NIPPLE. ** MONITOR WELL ON TRIP TANK.** DE DECISION MADE TO RUN WL FTEX PRIOR TO RUN RCX ON TCP. | 5163 |  | BAW | 09/02/2022 | SINO-46L | LOG | SHYB-270
178 | 5163 |  | OTH | E | 4545 | NA | HPJSM. R/U BAKER ATLAS WL LOGGING SHEAVES; CABLES AND BOP.* MONITOR WELL ON TRIP TANK. | 5163 |  | BAW | 09/02/2022 | SINO-46L | LOG | SHYB-270
179 | 5163 |  | PTST | E | 4545 | LUB | HPJSM. PT SHOOTING NIPPLE AND WL BOP TO 1500 PSI- OK.* MONITOR WELL ON TRIP TANK. | 5163 |  | BAW | 09/02/2022 | SINO-46L | LOG | SHYB-270
180 | 5163 |  | OTH | E | 4545 | NA | HPJSM. P/U & M/U BAKER ATLAS W/L RUN#4 LOGGING TOOLS (FTEX-GR ).- HPJSM & DISCUSS JSA W/ ALL PARTIES INVOLVED PRIOR TO PERFORM W/L LOGGING OPERATIONS.- SURFACE CHECK & TEST LOGGING TOOLS -OK.- MONITOR ON TRIP TANK-STATIC.- TOOL LENGHT 69.47' & MAX OD 4.12". | 5163 |  | BAW | 09/02/2022 | SINO-46L | LOG | SHYB-270
181 | 5163 | 4641 | LOG | E | 4545 | WLT | RIH BAKER W/L TOOLS (RUN#4) TO 9-5/8'' CS. | 5163 | 0 | BAW | 09/02/2022 | SINO-46L | LOG | SHYB-270
182 | 25.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #2 (FTEX -GR) | 16.5 | 4545 | 01 Sep 0800 | 09/02/2022 | SINO-46L | Type | SHYB-270
183
184
185 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SINO-5L | Hrs | UTMN-639
186 | XBTR | TK1 | 15.5 | 01 Sep 0100 - 1730 | 7170 | 901605 | SLOW ROP. | LROP | BIT |  | 09/02/2022 | SINO-5L | 11.5 | UTMN-639
187 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SND-1501 | Hrs | HWYH-89
188 | FOT | RIG | 16 | 01 Sep 2030 - 1230 | 7100 | 901597 | REPAIR MUD PUMP #2 | RR | MPMP |  | 09/02/2022 | SND-1501 | 7.5 | HWYH-89
189 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SND-2007 | Hrs | AWTD-104001
190 | FOT | NC1 | 59.75 | 31 Aug 1600 - 0345 | 17900 | 901608 | NOV TOOL FAILED TO ACTIVATE OPENING OF THE REAMER FROM 5.875"TO 7". | TF | HVLV |  | 09/02/2022 | SND-2007 | 22.75 | AWTD-104001
191 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SP-121 | Hrs | BRRI-522
192 | UNKN | RIG | 2 | 02 Sep 1600 - 1800 | 14529 | 901642 | HELD STAND DOWN MEETING WITH CREW AND DISCUSSED THE FINGER PINCHED INCIDENT - INVESTIGATION WILL FOLLOW. | HSEI | NA |  | 09/02/2022 | SP-121 | 2 | BRRI-522
193 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SP-124 | Hrs | FDHL-106
194 | FOT | BAL | 5 | 02 Sep 2000 - 0100 | 2850 | 901646 | ESP CABLE COME BETWEEN TBG AND HOLE COVER CAUSING DAMAGE TO THE ESP CABLE. | TF | ESPL |  | 09/02/2022 | SP-124 | 5 | FDHL-106
195 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SP-165 | Hrs | FDHL-146
196 | DFLI | EMC | 2 | 01 Sep 1145 - 2100 | 10585 | 901596 | OBSERVED CUT OF MUD WEIGHT OUT WHILE CIRCULATING | MUD | NA |  | 09/02/2022 | SP-165 | 1 | FDHL-146
197 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SP-257 | Hrs | HZEM-162412
198 | FOT | ITS | 1 | 02 Sep 1400 - 1500 | 587 | 901612 | POWER TONGS FAILED | TF | CTRQ |  | 09/02/2022 | SP-257 | 1 | HZEM-162412
199 | 6769 | 6429 | LOG | E | 4405 | WLT | CONTD STATION#13 , PUMP OUT POINT @ 6429' (2A06),CYCLE#2 : - ACTIVATE DXL PROBE & PUMP OUT STATION #13 @ 6429'.- PUMP OUT 6 LITRES OF FIILTRATED FLUID, 39 LITRES OF FORMATION WATER, 84 LITERS OIL,TAKE 1 BOTTLE OF 500CC FLUID SAMPLE.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 7.79 BBLS (WATER: 3.88 BBLS - OIL: 3.9 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 45.75 HRS SINCE LAST CIRCULATION AT BTM. | 6769 | 6429 | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
200 | 6769 |  | OTH | E | 4405 | NA | RIH WITH LOGGING TOOL STRING TO BOTTOM @ 6727'.- MONITOR WELL THRU TRIP TANK, STATIC.-OPEN HOLE IN GOOD CONDITION. | 6769 |  | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
201 | 6769 |  | CIRC | E | 4405 | MPMP | CIRCULATE 25 BBL UNTIL GET FORMATION FLUID INSIDE 7" CSG SHOE. | 6769 |  | RIG | 09/02/2022 | SP-53L | LOG | HRDH-528
202 | 6769 |  | OTH | E | 4405 | NA | POOH W/ BHI PCL LOGGING RUN#2: (GR-RCX-IFX-WGI ) TO SES DEPTH @6114'.- MONITOR WELL THROUGH TRIP TANK& TRIP SHEET. | 6769 |  | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
203 | 6769 |  | OTH | E | 4405 | NA | SPACE OUT AND CLOSED BOPE, LINE UP TO CHOKE MANIFOLD. | 6769 |  | RIG | 09/02/2022 | SP-53L | LOG | HRDH-528
204 | 6769 |  | CIRC | E | 4405 | MPMP | CIRCULATED OUT FORMATION FLUID AND CONTINUED CIRCULATION & CONDITION MUD THROUGH CHOKE MWT IN/OUT 70 PCF. | 6769 |  | RIG | 09/02/2022 | SP-53L | LOG | HRDH-528
205 | 6769 |  | OTH | E | 4405 | NA | EXTENDED FLOW CHECKED, WELL STATIC. | 6769 |  | RIG | 09/02/2022 | SP-53L | LOG | HRDH-528
206 | 6769 |  | OTH | E | 4405 | NA | RIH BHI PCL LOGGING RUN#2: (GR-RCX-IFX-WGI ) TO 6416'.- MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 6769 |  | RIG | 09/02/2022 | SP-53L | LOG | HRDH-528
207 | 6769 | 2416 | LOG | E | 4405 | WLT | POSITION STRING AT STATION#14,PUMP OUT POINT @ 6416' & PERFORM STICKY TENDENCY TEST @ 15& 60 MIN - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 2416 | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
208 | 6769 | 2416 | LOG | E | 4405 | WLT | STATION#14 , PUMP OUT POINT @ 6416' (2A05-BPOR),CYCLE#1 : - ACTIVATE STRADDLE PACKER & PUMP OUT STATION #14 @ 6416'.- PUMP OUT 12 LITRES OF FIILTRATED FLUID, 55 LITRES OF FORMATION WATER, 55 LITERS OIL.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 0.76 BBLS (WATER: 0.42 BBLS - OIL: 0.349 BBLS).- DEACTIVATE STRADDLE PACKER, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 2416 | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
209 | 6769 | 2416 | LOG | E | 4405 | WLT | STATION#14 , PUMP OUT POINT @ 6416' (2A05-BPOR),CYCLE#2 : - ACTIVATE DXL PROBE & PUMP OUT STATION #14 @ 6416'.- PUMP OUT 12 LITRES OF FIILTRATED FLUID, 5 LITRES OF FORMATION WATER, 100 LITERS OIL.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 1.49 BBLS (WATER: 0.52 BBLS - OIL: 0.97 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 2416 | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
210 | 6769 | 2407 | LOG | E | 4405 | WLT | SCANNING & POSITION STRING AT STATION#15, SAMPLE POINT @ 6407' .- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 2416 | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
211 | 6769 | 2407 | LOG | E | 4405 | WLT | STATION#15 , PUMP OUT POINT @ 6407' (2A05).- ACTIVATE DXL PROBE & PUMP OUT STATION #15 @ 6407'.- PUMP OUT 14 LITRES OF FIILTRATED FLUID, 07 LITRES OF FORMATION WATER, 121 LITERS OIL.- TOTAL CUMULATIVE VOLUME PUMPED TO WELL BORE - 2.25 BBLS (WATER: 0.62 BBLS - OIL: 1.73 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 15.75 HRS SINCE LAST CIRCULATION AT BTM. | 6769 | 2407 | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
212 | 6769 |  | OTH | E | 4405 | NA | RIH WITH LOGGING TOOL STRING TO BOTTOM @6727'.- MONITOR WELL THRU TRIP TANK, STATIC.- OPEN HOLE IN GOOD CONDITION. | 6769 |  | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
213 | 6769 |  | CIRC | E | 4405 | MPMP | CIRCULATE 30 BBL UNTIL GET FORMATION FLUID INSIDE 7" CSG SHOE. | 6769 |  | RIG | 09/02/2022 | SP-53L | LOG | HRDH-528
214 | 6769 |  | OTH | E | 4405 | NA | POOH W/ BHI PCL LOGGING RUN#2: (GR-RCX-IFX-WGI ) TO SES DEPTH @6114'- MONITOR WELL THROUGH TRIP TANK& TRIP SHEET. - OPEN HOLE IN GOOD CONDITION. | 6769 |  | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
215 | 6769 |  | OTH | E | 4405 | NA | HPJSM, BAKER WIRELINE UNLATCHED CABLE HEAD & POOH W/ WIRELINE CONNECTOR HEAD TO SURFACE, L/D SES & R/D WL SHEAVES......ON GOING - MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 6769 |  | BAW | 09/02/2022 | SP-53L | LOG | HRDH-528
216 | 146.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RECORDING (ADEX-MREX-MLL) LOG & RUN #2:(GR-RCX-IFX-WGI) LOG AS PER PLAN | 24 | 4405 | 27 Aug 1015 | 09/02/2022 | SP-53L | Type | HRDH-528
217
218
219 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SSA-201 | Hrs | MNHZ-1
220 | FOT | RIG | 11.5 | 01 Sep 0045 - 1215 | 5864 | 901601 | TOP DRIVE FUNCTION FAILURE. SUSPECT LOSS OF COMMUNICATION BETWEEM TDS AND PCR. | RR | TDS |  | 09/02/2022 | SSA-201 | 7.25 | MNHZ-1
221 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SSA-303 | Hrs | HRDH-2411
222 | FOT | BLH | 73 | 30 Aug 1630 - 0500 | 14125 | 901436 | MECHANICAL FAILURE OF SLIPS 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY, POOH & CHANGE OUT 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY | TF | HGRL |  | 09/02/2022 | SSA-303 | 24 | HRDH-2411
223 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | SSA-5892 | Hrs | AWTD-141400
224 | FOT | RIG | 192 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 09/02/2022 | SSA-5892 | 23.5 | AWTD-141400
225 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | T218 | Hrs | HRDH-1511
226 | FOT | RIG | 3.5 | 02 Sep 2330 - 0300 | 0 | 901651 | DRAW WORKS MALFUNCTION. | RR | DWKS |  | 09/02/2022 | T218 | 3.5 | HRDH-1511
227 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/02/2022 | WCL-83 | Hrs | MRJN-831
228 | WTHR | ARM | 2.75 | 02 Sep 1445 - 1730 | 6000 | 901634 | SUSPEND FLARING DUE TO LOW WIND SPEED. | WON | NA |  | 09/02/2022 | WCL-83 | 2.75 | MRJN-831
229 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ADC-21 | Hrs | MHWZ-991100
230 | UNKN | RIG | 65.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/03/2022 | ADC-21 | 24 | MHWZ-991100
231 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ADC-35 | Hrs | MAQL-5
232 | FOT | HCB | 124.5 | 29 Aug 0030 - 0500 | 5915 | 901459 | AFTER PLT LOGGING ANALYSIS, FOUND COMMUNCATION THRU HALLIBURTON BRIDGE PLUG SET ABOVE PREVIOUS PERFORATION. | TF | BP |  | 09/03/2022 | ADC-35 | 24 | MAQL-5
233 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ADC-42L | Hrs | SDGM-1258
234 | FOT | PKP | 54.75 | 01 Sep 1900 - 0145 | 15570 | 901600 | ATTEMPT TO SET LINER HANGER WITH NO SUCCESS | TF | HGRL |  | 09/03/2022 | ADC-42L | 20.75 | SDGM-1258
235 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ADC-55L | Hrs | UTMN-3171
236 | STBH | TK3 | 632 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/03/2022 | ADC-55L | 24 | UTMN-3171
237 | 13523 |  | OTH | C | 4485 | NA | CONT FLOWING THE WELL VIA ICV#2 FOR L1. MEANWHILE ESP WORKING W/ FREQ. 55 HZ & 48/64 CHOKE.- BS&W% @ REPORT TIME: 80 %. FOR MORE DETAILS REFER TO PRODUCTION DAILY REPORT.- WHP: 653, TCAP: 421 PSI, CCAP: 629 PSI- CONT. FLOWING THE WELL TILL MEET MULTI LATERAL FLOW BACK CRITERIA, TOTAL FLUIDS FLOWED TO GOSP FROM L1 7559 BBLS (1903 BBLS OF OIL & 5656 BBLS OF WATER) SINCE OPENED SAME ON 31ST SEPT. 2022 @ 12:30.- HALL SSV CLOSED DUE TO MALFUNCTION OF SSV HYD. HOSE, ESP AUTOMATICALLY SHUT DOWN, CLOSED LMV OF X-TREE, TILL FIX SAME.** ALL FLOWING BACK OPERATION WENT BACK TO NORMAL WITHIN 1 HR. | 13523 |  | BAL | 09/03/2022 | ADC-58L | LIFT | ABHD-169
238 | 96 | OOSS | Category | DOOS ID | WTST | Out of Scope Summary | WELL TESTING OPERATION. | 24 | 4485 | 30 Aug 1500 | 09/03/2022 | ADC-58L | Type | ABHD-169
239
240
241 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ADC-62L | Hrs | ANDR-589
242 | LHFL | RIG | 23.5 | 03 Sep 0530 - 0500 | 8384 | 901696 | LEAK FROM 4" X 75 FT ROTARY DRILLING HOSE | RR | HSYS |  | 09/03/2022 | ADC-62L | 23.5 | ANDR-589
243 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ADM-337 | Hrs | MRJN-900
244 | FOT | SWL | 19.75 | 02 Sep 0015 - 2000 | 0 | 901645 | TROUBLE-SHOOT SCHLUMBERGER UNIT. COMMUINCATION POWER SUPPLY ON THE WAFE SYSTEM. | TF | WLU |  | 09/03/2022 | ADM-337 | 15 | MRJN-900
245 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ADM-655 | Hrs | SFNY-183
246 | OTH | RIG | 144 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/03/2022 | ADM-655 | 24 | SFNY-183
247 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ARO-3002 | Hrs | MRJN-813
248 | WTHR | ARM | 39.5 | 22 Aug 0745 - 1800 | 8852 | 901136 | WIND SPEED TO LOW TO COMMENCE FLKOW BACK OPERATION. | WON | NA |  | 09/03/2022 | ARO-3002 | 9 | MRJN-813
249 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | DPS-46 | Hrs | UTMN-102001
250 | SRVC | GOC | 4.5 | 03 Sep 2230 - 0300 | 12419 | 901693 | AL GHAITH POWER TONG REJECT JOB DUE TO NO EQUIPTMENT, | WO | NA |  | 09/03/2022 | DPS-46 | 4.5 | UTMN-102001
251 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ENS-108 | Hrs | ZULF-2015
252 | GRF | RIG | 288 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/03/2022 | ENS-108 | 24 | ZULF-2015
253 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | ENS-141 | Hrs | MRJN-3303
254 | OTH | RIG | 11 | 03 Sep 1800 - 0500 | 805 | 901675 | FAILURE IN FIRE DETECTORS CONTROL LOOP. | UPRA | NA |  | 09/03/2022 | ENS-141 | 11 | MRJN-3303
255 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | MP-1 | Hrs | MRJN-78
256 | FOT | NRT | 797.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 09/03/2022 | MP-1 | 24 | MRJN-78
257 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | NA-393S | Hrs | SDGM-1134
258 | XWSW | SAM | 4 | 03 Sep 0100 - 0500 | 13227 | 901678 | SAMMA PACKER RUBBER ELEMENT LOST IN HOLE. | TF | WBCL |  | 09/03/2022 | NA-393S | 4 | SDGM-1134
259 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | NBR-20S | Hrs | HMYM-433512
260 | HERR | RIG | 6 | 03 Sep 0800 - 1400 | 3139 | 901674 | EXCESSIVE TIME TO HANDLE BHA. | JF | BHA |  | 09/03/2022 | NBR-20S | 6 | HMYM-433512
261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | NBR-575S | Hrs | HRDH-1990
262 | FOT | RIG | 11.25 | 03 Sep 1130 - 0500 | 9560 | 901676 | EATON BRAKE NOT WORKING PROPERLY; FOUND MAIN CYLINDER SEAL TORN OUT. | RR | DWKS |  | 09/03/2022 | NBR-575S | 11.25 | HRDH-1990
263 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | PN-9 | Hrs | MRJN-673
264 | FOT | BHI | 6.75 | 03 Sep 2130 - 0415 | 13460 | 901712 | AFTER POH WITH 8-1/2" BHI MOTORIZED RSS BHA, FOUND ONE FLANGE THAT COVERS THE HYDRAULIC UNIT AND STEERING PAD ON THE RSS IS MISSING ALONG WITH SOME OF THE SCREWS THAT HOLDS THIS PIECE IN PLACE | BHA | RSS |  | 09/03/2022 | PN-9 | 6.75 | MRJN-673
265 | FOT | GEP | 2 | 03 Sep 0715 - 0915 | 12846 | 901673 | OBSERVED LEAK ON BAKER GE QUICK CONNECTION MANIFOLD WITH NEEDLE VALVE ON BAKER GE LUBRICATOR DURING TESTING WITH N2. BLEED OFF PER PROCEDURE. BAKER GE CHANGE OUT QUICK CONNECTION MANIFOLD WITH NEEDLE VALVE. | TF | BPV |  | 09/03/2022 | RBP-50A | 2 | HSBH-55
266 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | RBP-50A | Hrs | HSBH-55
267 | FOT | GEP | 2.25 | 03 Sep 0500 - 0715 | 12846 | 901672 | OBSERVED LEAK ON BAKER GE LUBRICATOR PISTON DURING HIGH PRESSURE WITH N2. BLEED OFF N2 PER PROCEDURE. GREASE PISTON AND TIGHTEN GLAND NUT ON BAKER GE PISTON PER BAKER GE PROCEDURE. | TF | BPV |  | 09/03/2022 | RBP-50A | 2.25 | HSBH-55
268 | FOT | GEP | 2 | 03 Sep 0715 - 0915 | 12846 | 901673 | OBSERVED LEAK ON BAKER GE QUICK CONNECTION MANIFOLD WITH NEEDLE VALVE ON BAKER GE LUBRICATOR DURING TESTING WITH N2. BLEED OFF PER PROCEDURE. BAKER GE CHANGE OUT QUICK CONNECTION MANIFOLD WITH NEEDLE VALVE. | TF | BPV |  | 09/03/2022 | RBP-50A | 2 | HSBH-55
269 | HERR | FMC | 3.75 | 03 Sep 0115 - 0500 | 328 | 901700 | RU SPIDER SLIPS, FOUND SLIPS AND ELEVATORS NOT COMPATIBLE WITH CSG SIZE, CHANGED OUT SPIDER ELEVATOR AND SLIPS. | JF | CTRQ |  | 09/03/2022 | SDA | 3.75 | MRJN-653
270 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SDA | Hrs | MRJN-653
271 | FOT | FMC | 1.25 | 03 Sep 0000 - 0115 | 328 | 901699 | FRANKS CSG POWER TONMG LEAKS. REPLACED HYDRAULIC HOSE. | TF | CTRQ |  | 09/03/2022 | SDA | 1.25 | MRJN-653
272 | HERR | FMC | 3.75 | 03 Sep 0115 - 0500 | 328 | 901700 | RU SPIDER SLIPS, FOUND SLIPS AND ELEVATORS NOT COMPATIBLE WITH CSG SIZE, CHANGED OUT SPIDER ELEVATOR AND SLIPS. | JF | CTRQ |  | 09/03/2022 | SDA | 3.75 | MRJN-653
273 | 7630 |  | OTH | E |  | NA | R/D WL TOOLS, PCE & SHEAVES. | 7630 |  | HWP | 09/03/2022 | SINO-15L | LOG | ANDR-311
274 | 7630 |  | ND | E |  | SNIP | N/D SHOOTING BPL & N/U BELL NPL. | 7630 |  | HWP | 09/03/2022 | SINO-15L | LOG | ANDR-311
275 | 7630 |  | OTH | N |  | NA | M/U & RIH 18 STDS 4" HWDP, M/U HALLIBURTON 9-5/8" RTTS PACKER & STORM VALVE AND RIH ON 2 STDS X 4" DP TO 200 FT. | 7630 |  | IWS | 09/03/2022 | SINO-15L | WH | ANDR-311
276 | 7630 | 200 | SET | N |  | RBP | SET 9-5/8" RTTS @ 200 FT & P/T TO 1000 PSI, OK, RELEASE RTTS RUNNING TOOL, POH & RACK BACK 2 STDS 4" DP, L/D SETTING TOOL.- P/T 7" RTTS & STORM VALVE TO 1000 PSI, HOLD. | 7630 | 200 | HCB | 09/03/2022 | SINO-15L | WH | ANDR-311
277 | 7630 |  | ND | N |  | BOP | HPJSM. HANG FLOW LINE, N/D BELL NIPPLE, REMOVE MOUSE HOLE, DISCONNECT EM. K.LINE & HANG BOP. | 7630 |  | RIG | 09/03/2022 | SINO-15L | BOP | ANDR-311
278 | 7630 |  | OTH | N |  | NA | HPJSM, DIG OUT CELLAR 6 FT BELOW LANDING BASE.- ISSUE REQUIRED PTW & DISCUSSED JSA .CHECK 9" X 13" CCA IS ZERO PRESSURE - PT 9-5/8" X 13-3/8" CCA TO 500 PSI WITH INHIBITED WATER, PRESSURE DROP TO 200 PSI & HOLD (NO INJECTIVITY).- PT 9-5/8" CSG SLIPS TO 1000 PSI, OK- MANSOORI PERFORM INSPECTION FOR LANDING BASE ( GOOD CONDITION ) & UT FOR 18-5/8" CSG (SEAL WELDED TO DONUT PLATE). | 7630 |  | IWS | 09/03/2022 | SINO-15L | WH | ANDR-311
279 | 7630 |  | OTH | N | 4605 | NA | HPJSM, HOT-HED WELD 1-1/2" NIPPLE ON 18-5/8" CSG, MANSOORI PERFORM MPI FOR WELDING, WILD WELL PERFORM HOT TAPPING ON 18-5/8" CSG, NO PRESSURE OR GAS ON 18-5/8" X 13-3/8" CCA. | 7630 |  | IWS | 09/03/2022 | SINO-15L | WH | ANDR-311
280 | 7630 |  | OTH | N |  | NA | HOTHED CUT WINDOW ON 18-5/8" CSG, REMOVE CMT, ALMANSOORI PERFORM UT INSPECTION ON 13-3/8" CSG , GOOD CONDITION, FILL BACK 18-5/8" X 13-3/8" CCA WITH CMT, HOT-HEAD WELD BACK WINDOW, ALMANSOORI PERFORM MPI FOR WELDING AREA-OK, FILL BAK CELLAR WITH SWEET SAND | 7630 |  | IWS | 09/03/2022 | SINO-15L | WH | ANDR-311
281 | 7630 |  | ND | N |  | WH | HPJSM, N/D OLD 13-5/8" X 11" GRAY THS, HOT-HED CUT 9-5/8" CSG & RESTUB SAME. N/U NEW 13-5/8" X 11" CIW THS WITH 9-5/8" INTERFERENCE SEAL.- P/T 9-5/8" CSG SLIP & SEAL TO 1500 PSI, OK. | 7630 |  | RIG | 09/03/2022 | SINO-15L | WH | ANDR-311
282 | 7630 |  | NU | N |  | BOP | HPJSM , N/U CLASS "A" 13-5/8" 5M BOPE & RELATED EQUIPMENT . | 7630 |  | RIG | 09/03/2022 | SINO-15L | BOP | ANDR-311
283 | 7630 |  | BOPT | N |  | BOP | HPJSM, F/T BOPE, M/U TSET ASSY, P/T THS GATE VALVES, BOP CONNECTIONS, E-KILL LINE TO 300/ 2550 PSI-OK , L/D TEST ASSY . | 7630 |  | RIG | 09/03/2022 | SINO-15L | BOP | ANDR-311
284 | 7630 |  | OTH | N |  | NA | HPJSM, RIH, UNSET, POH & L/D 9-5/8" RTTS . | 7630 |  | IWS | 09/03/2022 | SINO-15L | WH | ANDR-311
285 | 7630 | 0 | TO | N |  | STDP | POH 18 STDS 4" HWDP & RACK BACK SAME TO DERRICK.- MONITOR WELL ON TRIP TANK, STATIC. | 7630 | 1710 | RIG | 09/03/2022 | SINO-15L | PA | ANDR-311
286 | 7630 |  | HT | N |  | BHA | HPJSM - M/U 7'' WFD WHIPSTOCK/MWD ASSY. ALIGNED WHIPSTOCK FACE WITH ORIENT SUB (MWD) BHA : 5 1/2'' QC RHN WHIPSTOCK. 6-1/8'' LEAD MILL (WF). 6-1/8'' FLEX MILL (WF). 1 JOINT 3 1/2'' HWDP (WF). F/S (SPERRY) + MWD (SPERRY) + X/O. | 7630 |  | RIG | 09/03/2022 | SINO-15L | TINL | ANDR-311
287 | 7630 |  | OTH | N |  | NA | RIH WITH 7'' WHIPSTOCK ASSY ON 4" HW/DP TO 2200 FT ... INC @ RPT.- CONTROLLED RIH SPEED 3 MIN/STAND SLIPS TO SLIPS.- PASSED VERY CAREFULLY FROM BOP STACK & WELLHEAD.- CIRC. STRG VOLUME EVERY 20 STAND | 7630 |  | WWD | 09/03/2022 | SINO-15L | TINL | ANDR-311
288 | 1 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | HOT TAPING 18-5/8" CSG. | 1 | 4605 | 03 Sep 1230 | 09/03/2022 | SINO-15L | Type | ANDR-311
289
290
291 | 9502 | 4675 | LOG | E |  | WLT | RIH W/ MPET- GR -CCL -TEMP LOGGING TOOLS TO 4675' PERFORMED REPEAT SECTION F/4675' T/4350', POOH TO SURFACE. | 9502 | 4350 | HWP | 09/03/2022 | SINO-19L | LOG | HWYH-565
292 | 9502 |  | OTH | E |  | NA | HPJSM, R/D HALLIBURTON W/L MULTI CASING CORROSION LOGGING TOOLS, SHEAVES & BOP. | 9502 |  | HWP | 09/03/2022 | SINO-19L | LOG | HWYH-565
293 | 9502 |  | NU | N |  | BNIP | N/D SHOOTING NIPPLE, N/U BEL NIPPLE. | 9502 |  | RIG | 09/03/2022 | SINO-19L | BOP | HWYH-565
294 | 9502 | 1030 | LDP | N | 4585 | STRG | (OOS) RIH 2-3/8" OPEN END DP CMT STINGER TO 1030' FOR BALANCE CMT PLUG.>> P/U 33 JTS 2-3/8" DP WHILE RIH.>> CIRC STRING VOLUME EVERY 20 JOINTS WHILE RIH. | 9502 | 0 | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
295 | 9502 |  | HT | N | 4585 | STRG | (OOS) R/D 2-3/8" DP HANDLING TOOLS, R/U 4" DP HANDLING TOOLS. | 9502 |  | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
296 | 9502 | 4685 | TI | N | 4585 | STDP | (OOS) CONT.RIH W/2-3/8" OPEN END DP CMT STINGER ON 4" DP STD'S FROM 1030' TO 4685' (10' ABOVE EZSV).<< BREAK CIRC EVERY 10 STD W/ 75 PCF VISC BRINE WHILE RIH | 9502 | 1030 | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
297 | 9502 |  | CIRC | N | 4585 | MPMP | (OOS) CHC & SPOT 35 BBL 110 PCF HI VIS PILL, DISPLACE W/35 BBL 75 PCF VISC BRINE. | 9502 |  | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
298 | 9502 | 3900 | TO | N | 4585 | STDP | (OOS) POOH W/2-3/8" OPEN END DP CMT STINGER ON 4" DP STD'S FROM 4685' TO 3900'. | 9502 | 4685 | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
299 | 9502 |  | PTST | N | 4585 | MPMP | (OOS) HPJSM, R/U CEMENT HARD LINES, FLUSH & P/T CEMENT LINES TO 3000 PSI,OK.>> CIRC MEANWHILE BATCH MIX 23 BBL OF 118 PCF CEMENT. | 9502 |  | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
300 | 9502 | 3900 | CMP | N | 4585 | OEDP | (OOS) HPJSM, PERFORMED BALANCED CEMENT PLUG FROM 3900'- 3300', PUMP FROM CMT UNIT AS FOLLOWING :>> 30 BBL 80 PCF TUNED SPACER AHEAD.>> 23 BBL 118 PCF CMT SLURRY.>> DISPLACE W/9 BBL 80 PCF TUNED SPACER BEHIND.>> 24 BBL 75 PCF BRINE (3 BBL UNDER DISPLACEMENT)>> NO LOSSES WHILE SPOTTING CMT PLUG>> BREAK OUT CMT LINES - NO BACK FLOW>> CMT IN PLACE @ 16:00 HRS. | 9502 | 3300 | HCM | 09/03/2022 | SINO-19L | PA | HWYH-565
301 | 9502 | 2800 | TO | N | 4585 | STHDP | (OOS) POOH W/2-3/8" OPEN END DP CMT STINGER ON 4" DP STD'S FROM 3900' TO 2800' | 9502 | 3900 | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
302 | 9502 |  | CIRC | N | 4585 | MPMP | (OOS) REV CIRC TWICE STRING CAP W/ 75 PCF VISCOUS BRINE -RECOVERED 20 BBL SPACER @ SURFACE | 9502 |  | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
303 | 9502 | 3800 | CMP | N | 4585 | SQZ | (OOS) CLOSED BOP, SQUEEZED CEMENT INTO LEAK INTERVAL W/75 PCF BRINE FROM CEMENT PUMP: >> TOTAL CEMENT VOLUME SQUEEZED: 2 BBL MAX PRESSURE: 1500 PSI & HOLD. | 9502 | 3700 | HCM | 09/03/2022 | SINO-19L | PA | HWYH-565
304 | 9502 |  | WOC | N | 4585 | CSG | (OOS) WAIT ON CEMENT MAIN WHILE HOLD 1500 PSI IN DRILLSTRING. | 9502 |  | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
305 | 9502 |  | OTH | N | 4585 | NA | (OOS) BLEED OFF PRESSURE GRADUALLY TO ZERO PSI,>> TOTAL VOLUME RETURNED BACK: 0.7 BBL.>> CEMENT VOLUME SQUEEZED BEHIND CSG: 1.3 BBL. | 9502 |  | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
306 | 9502 | 1030 | TO | N | 4585 | STHDP | (OOS) POOH W/2-3/8" OPEN END DP CMT STINGER ON 4" DP STD'S FROM 2800' TO 1030'. | 9502 | 2800 | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
307 | 9502 |  | HT | N | 4585 | STRG | (OOS) R/U 2-3/8" DP HANDLING TOOLS, R/D 4" DP HANDLING TOOLS. | 9502 |  | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
308 | 9502 | 0 | LDP | N | 4585 | STRG | (OOS) POOH W/2-3/8" OPEN END DP CMT STINGER FROM 1030' TO SURFACE.>>L/D 33 JTS 2-3/8" DP WHILE RIH. | 9502 | 1030 | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
309 | 9502 |  | HT | N | 4585 | BHA | (OOS) R/D 2-3/8" DP HANDLING TOOLS, R/U 4" DP HANDLING TOOLS. | 9502 |  | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
310 | 9502 |  | HT | N | 4585 | BHA | (OOS) HPJSM, P/U, M/U & RIH W/6 1/8" CLEAN OUT BHA TO 190'.>> BHA : 6-1/8"RR PDC ARAMCO (S/N : JP8220) + FS + 3 JTS 4" HWDP + 4-3/4" JAR + 2 JTS 4" HWDP. | 9502 |  | RIG | 09/03/2022 | SINO-19L | CT | HWYH-565
311 | 9502 | 2900 | TI | N | 4585 | STDP | (OOS) RIH WITH 6 1/8" CLEAN OUT BHA ON 4" DP STD'S TO 2900'. | 9502 | 190 | RIG | 09/03/2022 | SINO-19L | PA | HWYH-565
312 | 9502 | 3238 | RW | N | 4585 | BIT | (OOS) WASH DOWN FROM 2900' & TAG CEMENT @ 3238'. | 9502 | 2900 | RIG | 09/03/2022 | SINO-19L | CT | HWYH-565
313 | 9502 | 3290 | RW | N | 4585 | BIT | (OOS) DRILL OUT MEDIUM-HARD CMT FROM 3238' TO 3290'.>> PARAMETERS: 5 WOB KLB, 250 GPM, 500 - 600 PSI, 60 RPM, 500-600 FT.LB. | 9502 | 3238 | RIG | 09/03/2022 | SINO-19L | CT | HWYH-565
314 | 40.5 | OOS | Category | DOOS ID | LCL | Out of Scope Summary | LOCATE 7" CSG LEAK. | 19.5 | 4585 | 01 Sep 0130 | 09/03/2022 | SINO-19L | Type | HWYH-565
315
316
317 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SINO-1L | Hrs | ABJF-260
318 | FOT | BAL | 3 | 03 Sep 0200 - 0500 | 4718 | 901697 | BAKER VSD SYSTEM NOT PROVIDING ACCURATE VALUES WHEN ESP IS STARTED IN BOTH DIRECTIONS. | TF | ESP |  | 09/03/2022 | SINO-1L | 3 | ABJF-260
319 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SINO-26 | Hrs | UTMN-1312
320 | FOT | HWP | 1 | 03 Sep 1300 - 1400 | 0 | 901713 | WHILE TEST SAMPLING LOGGING TOOLS AT SURFACE, ONE OF THE TOOLS DID NOT RESPOND | TF | WLT |  | 09/03/2022 | SINO-26 | 1 | UTMN-1312
321 | 5163 | 5145 | LOG | E | 4545 | WLT | CONT. RIH WL RUN#4 LOGGING TOOLS (FTEX-GR) WHILE RECORDED 31 PRESSURE PTS F/ 4650' T/ 5145'.** 30 PTS AS PER RDD PROGRAM & RDD ADDED ADDITIONAL ONE @ 4780'.** PRESS PTS @: 4650', 4662', 4690', 4700', 471', 4724', 4735', 4764', 4780', 4795', 4812', 4825', 4840', 4862', 4872', 4880', 4890', 4910', 4925', 4940', 4965', 4982', 5005', 5022', 5038', 5050', 5060', 5110', 5118', 5130', 5145'.** MINIMUM OVER BALANCE 283 PSI @ 5118'.** MONITOR HOLE ON TRIP TANK, HOLE STATIC.** OPEN HOLE IN GOOD CONDITION. | 5163 | 0 | BAW | 09/03/2022 | SINO-46L | LOG | SHYB-270
322 | 5163 | 0 | LOG | E | 4545 | WLT | POOH W/L RUN#4 FROM 5145 FT TO SURFACE.** MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 5163 | 5145 | BAW | 09/03/2022 | SINO-46L | LOG | SHYB-270
323 | 5163 |  | OTH | E | 4545 | NA | HPJSM, R/D LOGGING TOOLS (FTEX-GR). ** MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 5163 |  | BAW | 09/03/2022 | SINO-46L | LOG | SHYB-270
324 | 5163 |  | ND | E | 4545 | SNIP | HPJSM, ND SHOOTING NIPPLE, NU BELL NIPPLE & CONNECT FLOW LINE.** MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 5163 |  | BAW | 09/03/2022 | SINO-46L | LOG | SHYB-270
325 | 5163 |  | PJSM | E | 4545 | NA | HPJSM WITH RIG & BAKER WIRELINE CREW PRIOR TO RU RCX LOGGING TOOLS, DISCUSSED JSA & PROCEDURES, SAFETY ISSUES, KEEP GOOD COMMUNICATION BETWEEN DRILLER, WL ENGINEER AND WINCH MAN IN THE WL UNIT.** FUNCTION TESTED MECHANICAL AND HYDRAULIC WL CABLE CUTTERS, OK. | 5163 |  | RIG | 09/03/2022 | SINO-46L | LOG | SHYB-270
326 | 5163 |  | OTH | E | 4545 | NA | P/U & M/U BHI W/L LOGGING TOOLS RUN #5: RCX-GR (FORMATION SAMPLING).** 2 X PROBE (STANDARD & XL)-SAMPLE VIEW, FLUID ANALYZER, 3 X PUMPS, 2 CARRIERS (10 TANK, 2 FILTER), STRADDLE PKR'S (02 EA)-GAMMA RAY AND CALIPER LOG.** PERFORM SURFACE FUNCTION CHECKS AND TOOL CALIBRATION ON SURFACE BEFORE RIH, OK.** TOTAL LOGGING TOOL LENGTH: 188.06', WT: 5,280 LB & MAX OD: 7.8".** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 5163 |  | BAW | 09/03/2022 | SINO-46L | LOG | SHYB-270
327 | 5163 |  | OTH | E | 4545 | NA | HPJSM, RIH WL RUN#5 LOGGING TOOLS (RCX-GR) ON 5" DRIFTED DP STDS WITH CONTROL SPEED TO 188'........ON-GOING @ RPT. ** FILL STRING EVERY 10 STDS & BREAK CIRC.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC.** TOTAL HRS SINCE LAST CIRCULATION: 34 HRS | 5163 |  | RIG | 09/03/2022 | SINO-46L | LOG | SHYB-270
328 | 49.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #4 (FTEX -GR), RUN #5 (RCX -GR-WGI). | 24 | 4545 | 01 Sep 0800 | 09/03/2022 | SINO-46L | Type | SHYB-270
329
330
331 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SINO-47 | Hrs | HWYH-1341
332 | XTTE | FMC | 1 | 03 Sep 0130 - 0230 | 408 | 901680 | EXCESSIVE TIME IN HANDLING TOOLS & EQUIPMENT. | TF | CTRQ |  | 09/03/2022 | SINO-47 | 1 | HWYH-1341
333 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SND-1501 | Hrs | HWYH-89
334 | FPMP | RIG | 8.5 | 03 Sep 0930 - 1800 | 7574 | 901694 | REPAIR ON MUD PUMP-2 | RR | MPMP |  | 09/03/2022 | SND-1501 | 8.5 | HWYH-89
335 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SND-2001 | Hrs | HWYH-1229
336 | SRVC | GOC | 2.75 | 03 Sep 0200 - 0445 | 4675 | 901695 | EXCESS TIME BY ALGAITH TO MAKE UP 2 PUP JNTS + FULL JNT | WO | NA |  | 09/03/2022 | SND-2001 | 2.75 | HWYH-1229
337 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SP-121 | Hrs | BRRI-522
338 | UNKN | RIG | 19 | 02 Sep 1600 - 0500 | 14529 | 901642 | HELD STAND DOWN MEETING WITH CREW AND DISCUSSED THE FINGER PINCHED INCIDENT - SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION BY DOE&CD. | HSEI | NA |  | 09/03/2022 | SP-121 | 17 | BRRI-522
339 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SP-165 | Hrs | FDHL-146
340 | DFLI | EMC | 2.5 | 01 Sep 1145 - 0045 | 10585 | 901596 | OBSERVED CUT OF MUD WEIGHT OUT WHILE CIRCULATING | MUD | NA |  | 09/03/2022 | SP-165 | .5 | FDHL-146
341 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SP-261 | Hrs | MHWZ-903
342 | HERR | RIG | 2.5 | 03 Sep 0900 - 1130 | 4579 | 901679 | WHILE MAKING UP TDS TO FILL PIPE DURING RIH OPERATION, SAVER SUB WAS DAMAGED DUE TO MISALLIGNMENT. | JF | TDS |  | 09/03/2022 | SP-261 | 2.5 | MHWZ-903
343 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SP-306 | Hrs | MNIF-192
344 | FOT | OGS | 5 | 02 Sep 1900 - 1400 | 8236 | 901653 | DROPPED GYRO DID NOT RECORDED ANY DATA. REPEATED THE JOB ON WIRELINE THROUGH DIR BHA. | SURV | MS |  | 09/03/2022 | SP-306 | 4 | MNIF-192
345 | 6769 |  | OTH | E | 4405 | NA | BAKER WIRELINE UNLATCHED CABLE HEAD & POOH W/ WIRELINE CONNECTOR HEAD TO SURFACE, L/D SES & R/D WL SHEAVES.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 6769 |  | BAW | 09/03/2022 | SP-53L | LOG | HRDH-528
346 | 6769 |  | OTH | E | 4405 | NA | SPACE OUT & CLOSE ANNULAR BOP, LINE UP TO CHOKE MANIFOLD. | 6769 |  | RIG | 09/03/2022 | SP-53L | LOG | HRDH-528
347 | 6769 |  | CIRC | E | 4405 | MPMP | CIRCULATED OUT FORMATION FLUID AND CONTINUED CIRCULATION & CONDITION MUD THROUGH CHOKE MWT IN/OUT 70 PCF. | 6769 |  | RIG | 09/03/2022 | SP-53L | LOG | HRDH-528
348 | 6769 |  | OTH | E | 4405 | NA | EXTENDED FLOW CHECKED, WELL STATIC. | 6769 |  | RIG | 09/03/2022 | SP-53L | LOG | HRDH-528
349 | 6769 | 180 | TO | E | 4405 | STDP | POOH W/ BHI PCL LOGGING RUN#2: (GR-RCX-IFX-WGI ) TO TOP OF BHA@181'.- MONITOR WELL THROUGH TRIP TANK& TRIP SHEET. - FLOW CHECK@ TOL,WELL STATIC . | 6769 | 6114 | RIG | 09/03/2022 | SP-53L | LOG | HRDH-528
350 | 6769 |  | OTH | E | 4405 | NA | HPJSM, L/D BHI LOGGING TOOLS,RUN#2: (GR-RCX-IFX-WGI).- MONITOR WELL THRU TRIP TANK, STATIC. | 6769 |  | BAW | 09/03/2022 | SP-53L | LOG | HRDH-528
351 | 6769 |  | RTRV | C |  | WBSH | RETRIEVE 11'' WEAR BUSHING. | 6769 |  | RIG | 09/03/2022 | SP-53L | WH | HRDH-528
352 | 6769 |  | BOP | C |  | BOP | P/U, M/U BOP JETTING TOOLS, JET BOP & WELL HEAD AND L/D SAME. | 6769 |  | RIG | 09/03/2022 | SP-53L | WH | HRDH-528
353 | 6769 |  | SET | C |  | WBSH | INSTALL 11" WEAR BUSHING. | 6769 |  | RIG | 09/03/2022 | SP-53L | WH | HRDH-528
354 | 6769 |  | HT | N |  | BHA | PU/MU 6" 1/8 CLEAN OUT ASSY TO 427'.- 6-1/8" WELDED MT BIT+ BIT SUB (WITH FLOAT VALVE) +11 X 4-3/4" DC'S + 4 3/4" D- JAR+2 X 4 3/4" DC+XO+6 STD X 4" DP+7" SCRAPER +7" BRUSH+ 2 STRING MAGNET+ FILTER+ 2 STRING MAGNET.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 6769 |  | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
355 | 6769 | 6374 | TI | N |  | STDP | RIH W/ 6-1/8'' CLEAN OUT ASSY TO 6374'.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 6769 | 427 | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
356 | 6769 | 6769 | TI | N |  | BHA | CONT RIH W/ 6-1/8'' CLEAN OUT ASSY AT CONTROLLED SPEED IN OPEN HOLE F/ 6374' TO 6769'.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- HOLE IN GOOD CONDITION.- SCRAPE & BRUSH COMPLETION PACKER SETTING INTERVAL F/ 6502' TO/ 6769' BIT DEPTH. | 6769 | 6374 | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
357 | 6769 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH W/30 BBL HI VIS & CIRCULATE HOLE CLEAN . | 6769 |  | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
358 | 6769 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH W/30 BBL HI VIS SPACER AHEAD , CIRC. AND DISPLACE HOLE TO 72 PCF BRINE , 100% RETURN. | 6769 |  | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
359 | 6769 |  | WCNT | N |  | NA | EXTENDED FLOW CHECK, WELL STATIC. | 6769 |  | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
360 | 6769 |  | CIRC | N |  | MPMP | SPOT MUDZYME AS FOLLOW:- PUMP 25 BBL HV BRINE SPACER 72 PCF.- PUMP 15 BBL MUDZYME 72 PCF.- CHASE WITH 72 PCF COMPLETION FLUID. | 6769 |  | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
361 | 6769 |  | WCNT | N |  | NA | FLOW CHECK, WELL STATIC. | 6769 |  | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
362 | 6769 | 6374 | TO | N |  | STDP | POOH W/ 6-1/8'' CLEAN OUT ASSY AT CONTROLLED SPEED ON OH TO 07 CSG SHOE @6374'.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- HOLE IN GOOD CONDITION. | 6769 | 6769 | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
363 | 6769 |  | WCNT | N |  | NA | FLOW CHECK, WELL STATIC OK. | 6769 |  | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
364 | 6769 | 3600 | LDP | N |  | STRG | POOH 6-1/8'' CLEAN OUT ASSY WITH L/D 5'' AND 4'' DP JTS( TO 3600' ---------.ON GOING - MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 6769 | 6374 | RIG | 09/03/2022 | SP-53L | CT | HRDH-528
365 | 154.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RECORDING (ADEX-MREX-MLL) LOG & RUN #2:(GR-RCX-IFX-WGI) LOG AS PER PLAN | 8 | 4405 | 27 Aug 1015 | 09/03/2022 | SP-53L | Type | HRDH-528
366
367
368 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SSA-303 | Hrs | HRDH-2411
369 | FOT | BLH | 88 | 30 Aug 1630 - 2000 | 14125 | 901436 | MECHANICAL FAILURE OF SLIPS 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY, POOH & CHANGE OUT 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY | TF | HGRL |  | 09/03/2022 | SSA-303 | 15 | HRDH-2411
370 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SSA-51 | Hrs | MNIF-257
371 | FOT | HSL | 1 | 03 Sep 0200 - 0300 | 5620 | 901655 | HALL 4 1/2" MONOLOCK TUBING PLUG STUCK AT 5,620' (200' ABOVE SETTING DEPTH). | TF | PLUGT |  | 09/03/2022 | SSA-51 | 1 | MNIF-257
372 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SSA-5859 | Hrs | HWYH-1217
373 | FOT | NRC | 1.5 | 03 Sep 0300 - 0430 | 155 | 901698 | DIFFICULTIES TO SCREW THE JOINT N#5 W/ CRT, | TF | CTRQ |  | 09/03/2022 | SSA-5859 | 1.5 | HWYH-1217
374 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | SSA-5892 | Hrs | AWTD-141400
375 | FOT | RIG | 215.25 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 09/03/2022 | SSA-5892 | 23.25 | AWTD-141400
376 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/03/2022 | WCL-83 | Hrs | MRJN-831
377 | WTHR | ARM | 7.75 | 03 Sep 0945 - 1730 | 13192 | 901677 | SUSPEND FLARING DUE TO LOW WIND SPEED. | WON | NA |  | 09/03/2022 | WCL-83 | 7.75 | MRJN-831
378 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | 095TE | Hrs | MNIF-126
379 | HERR | MSD | 7 | 04 Sep 2200 - 0500 | 9063 | 901659 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | TF | TTRQ |  | 09/04/2022 | 095TE | 7 | MNIF-126
380 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADC-21 | Hrs | MHWZ-991100
381 | UNKN | RIG | 89.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/04/2022 | ADC-21 | 24 | MHWZ-991100
382 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADC-29 | Hrs | NYYM-100
383 | WOTO | BC | 9 | 04 Sep 0500 - 1400 | 0 | 901701 | RECIEVED BAKER TOOLS WITHOUT CERAMIC DISK. | WO | NA |  | 09/04/2022 | ADC-29 | 9 | NYYM-100
384 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADC-35 | Hrs | MAQL-5
385 | FOT | HCB | 135 | 29 Aug 0030 - 1530 | 5915 | 901459 | AFTER PLT LOGGING ANALYSIS, FOUND COMMUNCATION THRU HALLIBURTON BRIDGE PLUG SET ABOVE PREVIOUS PERFORATION. | TF | BP |  | 09/04/2022 | ADC-35 | 10.5 | MAQL-5
386 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADC-55L | Hrs | UTMN-3171
387 | STBH | TK3 | 656 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/04/2022 | ADC-55L | 24 | UTMN-3171
388 | 13523 |  | OTH | C | 4485 | NA | CONT FLOWING THE WELL VIA ICV#2 FOR L1. MEANWHILE ESP WORKING W/ FREQ. 55 HZ & 48/64 CHOKE.- BS&W% : 78 %. FOR MORE DETAILS REFER TO PRODUCTION DAILY REPORT.- WHP: 618, TCAP: 437 PSI, CCAP: 705 PSI- @ 12:39 MET MULTI LATERAL FLOW BACK CRITERIA (72 HRS FLOWING), TOTAL FLUIDS FLOWED TO GOSP FROM L1 8471 BBLS (2093 BBLS OF OIL & 6378 BBLS OF WATER) SINCE OPENED SAME ON 31ST SEPT. 2022 @ 12:30. | 13523 |  | BFS | 09/04/2022 | ADC-58L | LIFT | ABHD-169
389 | 13523 |  | OTH | C | 4485 | NA | SLB CYCLED ICV@1 FOR L0 IN OPEN POSITION, SO WELL WILL PRODUCE FROM BOTH LATERALS COMMINGLY FOR NEXT 2 HRS. AS PER RMD RQUEST. | 13523 |  | SCP | 09/04/2022 | ADC-58L | LIFT | ABHD-169
390 | 13523 |  | OTH | C | 4485 | NA | BOTH ICV'S 1&2 ARE OPENED, FLOW BACK THE WELL VIA ICV#2 FOR L1 & ICV#2 FOR L1. MEANWHILE ESP WORKING W/ FREQ. 55 HZ & 36/64 CHOKE.- BS&W% : 0 %. FOR MORE DETAILS REFER TO PRODUCTION DAILY REPORT.- WHP: 931, TCAP: 353 PSI, CCAP: 728 PSI, BLED OF TCAP TO 300-600 PSI INTERVAL AND CCAP TO 700 PSI.- TOTAL FLUIDS FLOWED TO GOSP FROM L1 & L2 "574 BBLS (570 BBLS OF OIL & 4 BBLS OF WATER)" SINCE OPENED BOTH L1&2 ON 3RD SEPT. 2022 @ 13:15. FOR 2 HRS DURATION. | 13523 |  | BAL | 09/04/2022 | ADC-58L | LIFT | ABHD-169
391 | 13523 |  | OTH | C | 4485 | NA | SHUT IN WELL VIA HALL CHOKE VALVE AND IDLE ESP AGAINST THE CLOSED VALVE FOR 5 MIN AS PER BHGE. WHP: 1672 PSI, TCA 148 PSI, CCA_ 655 PSI_- SHUT OFF ESP AND CONTINUE TO MONITOR PRESSURES, WHP: 555 PSI, TCA: 0 PSI, CCA: 530 PSI | 13523 |  | BAL | 09/04/2022 | ADC-58L | LIFT | ABHD-169
392 | 13523 |  | OTH | C | 4485 | NA | CLOSED LMV, FLUSHED SURFACE & PRODUCTION LINES UTILIZED 200 BBLS INHIBITED WATER. | 13523 |  | RIG | 09/04/2022 | ADC-58L | LIFT | ABHD-169
393 | 13523 |  | OTH | C | 4485 | NA | HPJSM, HALL WT R/D SURFACE LINE EQPT & CLEARED CELLAR AREA SAFELY. | 13523 |  | HTS | 09/04/2022 | ADC-58L | LIFT | ABHD-169
394 | 13523 |  | HT | C |  | SFLN | HPJSM, CONNECTED RIG SURFACE LINES TO X-MASS TREE, FLUSHED & P/T SURFACE LINES TO 1500 PSI FOR 10 MINS, OK. | 13523 |  | RIG | 09/04/2022 | ADC-58L | COMP | ABHD-169
395 | 13523 |  | OTH | C |  | SFLN | BULLHEAD 220 BBLS INHIBITED DIESEL THROUGH ESP TO THE END OF TUBING, FR: 2 BPM, SPP: 800- 1150 PSI- SET MAX PRESSURE @ 1200 PSI. MAINTAINED TCA PRESSURE 800 PSI, CCAP: 0 PSI ALL TIME FOR BULLHEADING. | 13523 |  | RIG | 09/04/2022 | ADC-58L | COMP | ABHD-169
396 | 13523 |  | HT | C |  | ESP | CLOSED TRSSSV, BLED OFF PRESSURE ABOVE TRSSSV.- SLB CYCLED TRFC#2 (UPPER) TO POSITION #0 (FULLY CLOSED) & KEPT TRFC#1 (LOWER) IN POSITION #10 (FULLY OPENED)- SECURED WELL, INSTALLED BPV, CLOSED X-MASS TREE LMV & WING VALVE.- BHGE CHECKED AND RECORDED FINAL READING: PH-PH BALANCED: 5.4 OHM, PH-G 5 MIN: 690 M OHM & 10 MIN: 884 M OHM. | 13523 |  | BAL | 09/04/2022 | ADC-58L | COMP | ABHD-169
397 | 13523 |  | PTST | C |  | TREE | R/D SURFACE LINES, INSTALLED BLIND FLANGE ON WING VALVE & P/T SAME TO 2500 PSI AGAINST WING VALVE, HOLD OK, BLED OFF PRESSURE.* CLOSED X-MAS TREE CROWN VALVE AFTER P/T. | 13523 |  | RIG | 09/04/2022 | ADC-58L | WH | ABHD-169
398 | 13523 |  | NU | C |  | WH | INSTALLED VR PLUG IN THS EAST GATE VLV, P/T VR PLUG TO 1000 PSI, OK, REMOVED SOV, INSTALLED BLIND FLANGE ON THS & P/T SAME TO 2500 PSI, OK.- WHP: 0 PSI, CCAP: 0 PSI, KEPT 350 PSI IN TCA. | 13523 |  | RIG | 09/04/2022 | ADC-58L | WH | ABHD-169
399 | 13523 |  | OTH | C |  | TBG | L/D 2 STD X 5" DP FROM DERRICK. | 13523 |  | RIG | 09/04/2022 | ADC-58L | COMP | ABHD-169
400 | 13523 |  | OTH | C |  | NA | CLEANED CELLAR AREA, SECURED WELL HEAD SURFACE CONTROL CABLES, CLEANED MUD TANKS. | 13523 |  | RIG | 09/04/2022 | ADC-58L | LIFT | ABHD-169
401 | 13523 |  | RELS | S |  | NA | RELEASED RIG FROM LOCATION ABHD-169-158 TO ABHD-183 AT 05:00 HRS ON 4TH SEPT. 2022.- WELL SECURED W/TRSSV & PRODUCTION PACKER, ALL VALES CLOSED ON X-MASS TREE.- TCA PRESSURE 350 PSI.- BPV TO BE RETRIEVED AFTER CLEAR CELLAR AREA FROM RIG EQPT. | 13523 |  | RIG | 09/04/2022 | ADC-58L | OT | ABHD-169
402 | 109.5 | OOSS | Category | DOOS ID | WTST | Out of Scope Summary | WELL TESTING OPERATION. | 13.5 | 4485 | 30 Aug 1500 | 09/04/2022 | ADC-58L | Type | ABHD-169
403
404
405 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADC-62L | Hrs | ANDR-589
406 | FOT | RIG | 42 | 03 Sep 0530 - 2330 | 8384 | 901696 | LEAK FROM ROTARY HOSE. | RR | CSYS |  | 09/04/2022 | ADC-62L | 18.5 | ANDR-589
407 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADES-144 | Hrs | UTMN-3018
408 | IBSL | ULT | 13.5 | 03 Sep 0230 - 1630 | 6932 | 901681 | ROP DROPPED TO 15 PFH, ATTEMPTED TO ADJUST DRILLING PARAMETER AND DIFFERENT TROUBLE SHOOTING APPROACH WITHOUT SUCCESS. CHC AND POH TO CHECK BHA. INNER BIT CUTTERS HAVE EXCESSIVE DAMAGE WITH DULL GRADING 5-1-BC-C-X-1-NO-PR | LROP | BIT |  | 09/04/2022 | ADES-144 | 11 | UTMN-3018
409 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADM-261 | Hrs | MRJN-24
410 | HERR | RIG | 14 | 03 Sep 0230 - 1630 | 0 | 901714 | WHILE POOH, FOUND BHA WAS MISSING ONE STAND 4" HWDP BELOW JARS. CLEAN-OUT RUN TOC TAG IS 92 FT SHALLOW, NEED ADDITIONAL CEMENT CLEAN-OUT RUN FOR WHIPSTOCK PLACEMENT. | JF | BHA |  | 09/04/2022 | ADM-261 | 11.5 | MRJN-24
411 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADM-262 | Hrs | MRJN-446
412 | XTTE | BC | 1.5 | 04 Sep 1430 - 1600 | 5023 | 901702 | BAKER REDUCED PACKER SETTING PRESSURE FROM THE NORMAL 3,500 PSI TO 3,000 PSI AS WELL WAS ON LOSSES. UNABLE TO OBTAIN TCA TEST, PACKER PARTIALLY SET. | TF | PKR |  | 09/04/2022 | ADM-262 | 1.5 | MRJN-446
413 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ADM-655 | Hrs | SFNY-183
414 | OTH | RIG | 168 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/04/2022 | ADM-655 | 24 | SFNY-183
415 | FOT | BHI | 7 | 04 Sep 0600 - 1300 | 8820 | 901703 | LOST COMMUNICATION W/ RSS & NEAR BIT GAMMA WHILE PERFORMING SHALLOW TEST FOR 8-1/2" BHI RSS/MWD/LWD BHA. | BHA | RSS |  | 09/04/2022 | AOD-111 | 7 | MRJN-729
416 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | AOD-111 | Hrs | MRJN-729
417 | FOT | BHI | 1 | 04 Sep 0300 - 0400 | 9158 | 901660 | AT DEPTH 9,158 FT, AFTER DOWNLINK OBSERVED 500 PSI PRESSURE INCREASE & LOST MWD/LWD SIGNAL. | BHA | MWD |  | 09/04/2022 | AOD-111 | 1 | MRJN-729
418 | FOT | BHI | 7 | 04 Sep 0600 - 1300 | 8820 | 901703 | LOST COMMUNICATION W/ RSS & NEAR BIT GAMMA WHILE PERFORMING SHALLOW TEST FOR 8-1/2" BHI RSS/MWD/LWD BHA. | BHA | RSS |  | 09/04/2022 | AOD-111 | 7 | MRJN-729
419 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ARO-3002 | Hrs | MRJN-813
420 | WTHR | ARM | 48.25 | 22 Aug 0745 - 1500 | 8852 | 901136 | WIND SPEED TO LOW TO COMMENCE FLKOW BACK OPERATION. | WON | NA |  | 09/04/2022 | ARO-3002 | 8.75 | MRJN-813
421 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | DPS-4 | Hrs | MDRK-63
422 | FOT | RIG | 1.5 | 04 Sep 0300 - 0430 | 11145 | 901661 | REPAIR ON DRAWWORK. CHANED EXTENTION SHAFT COUPLING FOR DRAWWORKS DC MOTOR DRILLER SIDE. | RR | DWKS |  | 09/04/2022 | DPS-4 | 1.5 | MDRK-63
423 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | DPS-43 | Hrs | SDGM-1218
424 | DSFT | HLH | 24 | 04 Sep 0500 - 0500 | 13264 | 901707 | WHILE RUNNING 7" LINER ON 5-1/2" DP IN CASED HOLE AT DEPTH 10,000' ; THE 7" HALL XTREMEGRIP LINER HGR TAGGED ON 9-5/8" DVT & UNABLE TO PASS THROUGH IT. ATTEMPTED TO PASS THROUGH DVT WITH CIRCULATION AND ROTATION AS PRACTICALLY AS POSSIBLE - NO SUCCESS. | JF | HGRL |  | 09/04/2022 | DPS-43 | 24 | SDGM-1218
425 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ENS-108 | Hrs | ZULF-2015
426 | GRF | RIG | 312 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/04/2022 | ENS-108 | 24 | ZULF-2015
427 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ENS-141 | Hrs | MRJN-3303
428 | OTH | RIG | 24 | 03 Sep 1800 - 1800 | 805 | 901675 | FAILURE IN FIRE DETECTORS CONTROL LOOP. | UPRA | NA |  | 09/04/2022 | ENS-141 | 13 | MRJN-3303
429 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ENSCO-76 | Hrs | MRJN-2004
430 | HERR | SCM | .25 | 04 Sep 2045 - 2100 | 13400 | 901708 | ATTEMPT TO P/T SLB CEMENT UNIT & LINES, OBSERVE PRESSURE DROP (180 PSI / MIN). | CMT | NA |  | 09/04/2022 | ENSCO-76 | .25 | MRJN-2004
431 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | EXL-IA | Hrs | SFNY-1790
432 | FOT | GEP | 1 | 04 Sep 1245 - 1345 | 215 | 901711 | CASING SLIPS JAMMED IN WELL HEAD BACKING OUT 13 3/8" CASING & 18 5/8" CASING SAME TIME | TF | MLS |  | 09/04/2022 | EXL-IA | 1 | SFNY-1790
433 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | EXL-IVA | Hrs | ZULF-2041
434 | FOT | RIG | 12.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE | RR | TDS |  | 09/04/2022 | EXL-IVA | 12.25 | ZULF-2041
435 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | HI-2 | Hrs | BRRI-435
436 | FOT | RIG | 1 | 04 Sep 0945 - 1045 | 8069 | 901721 | UNABLE TO DISCONNECT TDS DUE TO OVERTORQUD CONNECTION. | RR | TDS |  | 09/04/2022 | HI-2 | 1 | BRRI-435
437 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | MP-1 | Hrs | MRJN-78
438 | FOT | NRT | 821.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 09/04/2022 | MP-1 | 24 | MRJN-78
439 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | NA-128S | Hrs | GHZL-106
440 | FPMP | RIG | 3 | 04 Sep 0845 - 1145 | 1308 | 901656 | OBSERVED SUDN SPP PRESSURE DROP, AFTER TROUBLESHOOT FOUND THE GROUND MANIFOLD VALVE IS PLUGGED AND THE POP OFF VALVE ACTIVATED. | RR | MPMP |  | 09/04/2022 | NA-128S | 3 | GHZL-106
441 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | NA-393S | Hrs | SDGM-1134
442 | XWSW | SAM | 51 | 02 Sep 0130 - 0500 | 13227 | 901678 | SAMMA PACKER RUBBER ELEMENT LOST IN HOLE. | TF | WBCL |  | 09/04/2022 | NA-393S | 24 | SDGM-1134
443 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | NBR-575S | Hrs | HRDH-1990
444 | FOT | RIG | 14.75 | 03 Sep 1115 - 0830 | 9560 | 901676 | EATON BRAKE NOT WORKING PROPERLY; FOUND MAIN CYLINDER SEAL TORN OUT. | RR | DWKS |  | 09/04/2022 | NBR-575S | 3.5 | HRDH-1990
445 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | PA-785S | Hrs | QTIF-269
446 | FOT | RIG | 2 | 04 Sep 0630 - 0830 | 17473 | 901715 | RIG PUMP#2 FAILURE, RIG PUMP#1 NOISY DATA FOR MWD, RIG REPAIRED PUMP#2 TO RESUME DRILLING. | RR | MPMP |  | 09/04/2022 | PA-785S | 2 | QTIF-269
447 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | PN-9 | Hrs | MRJN-673
448 | FOT | BHI | 26.5 | 03 Sep 2130 - 0415 | 13460 | 901712 | AFTER POH WITH 8-1/2" BHI MOTORIZED RSS BHA, FOUND ONE FLANGE THAT COVERS THE HYDRAULIC UNIT AND STEERING PAD ON THE RSS IS MISSING ALONG WITH SOME OF THE SCREWS THAT HOLDS THIS PIECE IN PLACE | BHA | RSS |  | 09/04/2022 | PN-9 | 19.75 | MRJN-673
449 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SDA | Hrs | MRJN-653
450 | XTRI | FMC | 5 | 04 Sep 1400 - 1900 | 2589 | 901722 | EXCESSIVE TIME TAKEN TO RUN CASING DUE TO PROBLEM TO OPERATE CASING HANDLING EQUIPMENT. | JF | CTRQ |  | 09/04/2022 | SDA | 5 | MRJN-653
451 | 9502 | 3830 | RW | N | 4585 | BIT | (OOS) DRILL OUT MEDIUM-HARD CMT FROM 3200' TO 3830'( 30' BELOW LEAK INTERVAL)>> PARAMETERS: 5-8 WOB KLB, 250 GPM, 500 PSI, 60 RPM, 500-1000 FT.LB | 9502 | 3200 | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
452 | 9502 |  | CIRC | N | 4585 | MPMP | (OOS) SWEEP HOLE W/30 BBLS HVP TWICE & CHC W/CLEAN BRINE. | 9502 |  | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
453 | 9502 |  | CIRC | N | 4585 | MPMP | (OOS) P/T 7" CSG W/75 PCF BRINE IN STAGES TO 1000 PSI FOR 15 MINS - OK. | 9502 |  | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
454 | 9502 | 3900 | RW | N | 4585 | BIT | (OOS) DRILLED OUT HARD CMT FROM 3830' TO 3900'.>>PARAMETERS: 8-10 KLBS WOB, 250 GPM,500-600 PSI, 60 RPM, 800-1000 FT.LB | 9502 | 3830 | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
455 | 9502 | 4685 | RW | N | 4585 | BIT | (OOS) WASHED DOWN TO 4020'. RIH W/6-1/8" CLEAN OUT BHA TO 4685' (10' ABOVE EZSV). | 9502 | 3900 | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
456 | 9502 |  | CIRC | N | 4585 | MPMP | (OOS) SWEEP HOLE W/30 BBLS HVP TWICE & CHC , FLOW CHECK, STATIC. | 9502 |  | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
457 | 9502 | 10 | TO | N | 4585 | STDP | (OOS) POOH W/6 1/8" CLEAN OUT BHA FROM 4685' TO SURFACE. | 9502 | 4685 | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
458 | 9502 |  | HT | N | 4585 | BHA | (OOS) L/D 6-1/8" CLEAN OUT BHA. | 9502 |  | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
459 | 9502 |  | HT | N | 4585 | BHA | (OOS) P/U & M/U 7" SCRAPER CLEAN OUT BHA.>> BHA: 6-1/8" WELDED BIT, FLOAT SUB, 7" SCRAPER, XO. | 9502 |  | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
460 | 9502 | 4685 | TI | N | 4585 | STDP | (OOS) RIH W/7" SCRAPER CLEAN OUT BHA TO 4685' (10' ABOVE EZSV).>> PASS CAREFULLY 7" TOL @ 1616'.>> WORK 7" SCRAPER FROM 3455' TO 3645' & FROM 4400' TO 4680'>> FILL STRING EVERY 15 STD W/ 75 PCF VISC BRINE. | 9502 | 10 | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
461 | 9502 |  | CIRC | N | 4585 | MPMP | (OOS) SWEEP HOLE W/30 BBLS HVP TWICE & CHC, SPOT 40 BBL 75 PCF INHIBITED BRINE ON TOP OF 7" EZSV-CR. FLOW CHECK, STATIC. | 9502 |  | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
462 | 9502 | 1465 | TO | N | 4585 | STDP | (OOS) POOH W/ 7" SCRAPER CLEAN OUT BHA FROM 4685' TO 1465'. | 9502 | 4685 | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
463 | 9502 |  | HT | N |  | BHA | HPJSM, M/U 9 5/8" RTTS WITH STORM VALVE. RIH & SET RTTS PACKER@220', P/T ANNULUS TO 1000 PSI, L/D RTTS SETTING TOOL, CLOSED SBR, P/T RTTS & STORM VALVE TO 1000 PSI - HOLD FOR 10 MIN,OK. | 9502 |  | RIG | 09/04/2022 | SINO-19L | CT | HWYH-565
464 | 63 | OOS | Category | DOOS ID | LCL | Out of Scope Summary | LOCATE 7" CSG LEAK. | 22.5 | 4585 | 01 Sep 0130 | 09/04/2022 | SINO-19L | Type | HWYH-565
465
466
467 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SINO-1L | Hrs | ABJF-260
468 | FOT | BAL | 27 | 03 Sep 0200 - 0500 | 4718 | 901697 | BAKER VSD SYSTEM NOT PROVIDING ACCURATE VALUES WHEN ESP IS STARTED IN BOTH DIRECTIONS. START UP PUMP W/ NEW VSD UNIT, SAME RESULTS. DECISION WAS MADE TO POOH ESP COMPLETION & RUN NEW ONE. | TF | ESP |  | 09/04/2022 | SINO-1L | 24 | ABJF-260
469 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SINO-27N | Hrs | KHRS-299
470 | HERR | BAL | 3 | 04 Sep 0200 - 0500 | 9972 | 901719 | DUE TO BAKER ESP DROP BANDS IN HOLE. | JF | ESP |  | 09/04/2022 | SINO-27N | 3 | KHRS-299
471 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SINO-33L | Hrs | HRDH-1542
472 | GRF | RIG | 50 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/04/2022 | SINO-33L | 24 | HRDH-1542
473 |  |  | BML | OTH | 4545 | 5163 | HPJSM, RIH WL RUN#5 LOGGING TOOLS (RCX-GR) ON 5" DRIFTED DP STDS WITH CONTROL SPEED TO 4528'. ** FILL STRING EVERY 10 STDS & BREAK CIRC.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. |  |  | 5163 | 09/04/2022 | SINO-46L | NA | SHYB-270
474 |  |  | RIG | CIRC | 4545 | 5163 | HPJSM, CIRCULATE 2 X STRG VOLUME 245 GPM, 160 PSI, 100% CIRC. |  |  | 5163 | 09/04/2022 | SINO-46L | MPMP | SHYB-270
475 |  |  | BAW | OTH | 4545 | 5163 | HPJSM, PU & MU WL SIDE ENTRY SUB (SES).* MONITOR WELL ON TRIP TANK. |  |  | 5163 | 09/04/2022 | SINO-46L | NA | SHYB-270
476 |  | 901716 | BAW | OTH | 4545 | 5163 | HPJSM, RIH W/ PUMP DOWN HEAD ON W/L CABLE ATTEMPTED TO LATCH PWCH INTO THE DOCKING HEAD WITOUT SUCCESS.** TRY TO LATCH SEVERAL ATTEMPTS WITHOUT SUCCESS (GOT PARTIAL LATCH) WITH INCREASE OF FLOW RATE TO 500 GPM AND CIRC BTM/UP.** L/D SES AND CHECK PWCH -GOOD-.** AS PER BHI LOGGING RECOMMENDATION PULL OUT 4 STAND, MU SES AND PERFORM ANOTHER ATTEMPTS WITHOUT SUCCESS (PARTIAL LATCH).** AS PER BHI LOGGING RECOMENDATIONS PULL OUT TO CHECK DOCKING HEAD.** MONITOR WELL ON TRIP TANK. |  | TF | 5163 | 09/04/2022 | SINO-46L | NA | SHYB-270
477 |  | 901716 | RIG | OTH | 4545 | 5163 | POOH W/ WIRELINE CONNECTOR HEAD TO SURFACE, L/D SES & R/D WL SHEAVES.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. |  | TF | 5163 | 09/04/2022 | SINO-46L | NA | SHYB-270
478 |  | 901716 | BAW | OTH | 4545 | 5163 | POOH W/ BHI PCL LOGGING RUN#5: (GR-RCX) TO TOP OF LOGGING TOOLS@188'.** LATCH AT SURFACE -OK-** PERFORM SURFACE FUNCTION CHECKS AND TOOL CALIBRATION ON SURFACE, OK.** MONITOR WELL THROUGH TRIP TANK. |  | TF | 5163 | 09/04/2022 | SINO-46L | NA | SHYB-270
479 |  | 901716 | BAW | OTH | 4545 | 5163 | L/D PWCH AND DOCKING AND CHANGED WITH NEW BACK-UP ONES.** MONITOR WELL THROUGH TRIP TANK. ** LAST CIRCULATION 12H. |  | TF | 5163 | 09/04/2022 | SINO-46L | NA | SHYB-270
480 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SINO-46L | Hrs | SHYB-270
481 | FOT | BAW | 16 | 04 Sep 1300 - 0500 | 4528 | 901716 | RIH W/ PUMP DOWN HEAD ON W/L CABLE ATTEMPTED TO LATCH PWCH INTO THE DOCKING HEAD WITOUT SUCCESS. | TF | WLT |  | 09/04/2022 | SINO-46L | 16 | SHYB-270
482 | 73.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #4 (FTEX -GR), RUN #5 (RCX -GR-WGI). | 24 | 4545 | 01 Sep 0800 | 09/04/2022 | SINO-46L | Type | SHYB-270
483
484
485 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SINO21 | Hrs | ABQQ-575
486 | FOT | SDM | 17.25 | 04 Sep 0500 - 2245 | 5372 | 901658 | MOTOR FAILURE | BHA | MMOT |  | 09/04/2022 | SINO21 | 17.25 | ABQQ-575
487 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SP-121 | Hrs | BRRI-522
488 | OTH | RIG | 43 | 02 Sep 1600 - 0500 | 14529 | 901642 | HELD STAND DOWN MEETING WITH CREW AND DISCUSSED THE FINGER PINCHED INCIDENT - SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION BY DOE&CD. | UPRA | NA |  | 09/04/2022 | SP-121 | 24 | BRRI-522
489 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SP-124 | Hrs | FDHL-106
490 | FOT | SLL | 2.5 | 04 Sep 1830 - 2100 | 0 | 901718 | SLB UNABLE TO SET 4-1/2" SIMPLUS PLUG AT 200 FT. POOH & RIH W/ NEW 4-1/2" SIMPLUS PLUG. | TF | SLICK |  | 09/04/2022 | SP-124 | 2.5 | FDHL-106
491 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SP-257 | Hrs | HZEM-162412
492 | FOT | CAM | 4.5 | 04 Sep 1430 - 1900 | 0 | 901685 | PACKOFF NOT HOLDING PRESSURE. | WH | WH |  | 09/04/2022 | SP-257 | 4.5 | HZEM-162412
493 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SSA-5859 | Hrs | HWYH-1217
494 | DRIG | RIG | 2 | 04 Sep 0530 - 0730 | 200 | 901683 | DERRICK / TDS ALIGNMENT. | RR | RSYS |  | 09/04/2022 | SSA-5859 | 2 | HWYH-1217
495 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | SSA-5892 | Hrs | AWTD-141400
496 | FOT | RIG | 237.25 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 09/04/2022 | SSA-5892 | 22 | AWTD-141400
497 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | T901 | Hrs | JLMN-60
498 | FOT | RIG | 18.75 | 04 Sep 1015 - 0500 | 0 | 901710 | WHILE BREAKING OUT CRT FROM SAVER SUB, THE TDS GRAPPLES WERE NOT HOLDING THE CRT, WHICH LEAD THE CRT TO ROTATE, MEANWHILE THE CRT GRAPPLE DIES BEING UNDERNEATH ROTARY TABLE WERE CAUGHT BY THE EDGE OF INTERNAL FACE OF MASTER BUSHING. RESULTED IN 1 PIECE OF GRAPPLE DIES BROKE AND FELL DOWN. | TF | CRT |  | 09/04/2022 | T901 | 18.75 | JLMN-60
499 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | WCL-83 | Hrs | MRJN-831
500 | WTHR | ARM | 6.75 | 04 Sep 0745 - 1730 | 13192 | 901682 | SUSPEND FLARING DUE TO LOW WIND SPEED. | WON | NA |  | 09/04/2022 | WCL-83 | 6.75 | MRJN-831
501 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/04/2022 | ZPEC-2 | Hrs | QMRN-806
502 | FOT | RIG | 3 | 04 Sep 1200 - 1500 | 56 | 901709 | BIT DEPTH SENSORS NOT WORKING. | TF | COMP |  | 09/04/2022 | ZPEC-2 | 3 | QMRN-806
503 | HERR | RIG | 11 | 05 Sep 1000 - 2100 | 9063 | 901754 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | FISH | STRG |  | 09/05/2022 | 095TE | 11 | MNIF-126
504 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | 095TE | Hrs | MNIF-126
505 | HERR | MSD | 12 | 04 Sep 2200 - 1000 | 9063 | 901659 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | TF | TTRQ |  | 09/05/2022 | 095TE | 5 | MNIF-126
506 | HERR | RIG | 11 | 05 Sep 1000 - 2100 | 9063 | 901754 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | FISH | STRG |  | 09/05/2022 | 095TE | 11 | MNIF-126
507 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ADC-21 | Hrs | MHWZ-991100
508 | UNKN | RIG | 113.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/05/2022 | ADC-21 | 24 | MHWZ-991100
509 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ADC-43L | Hrs | UTMN-3118
510 | FOT | BLH | 8.5 | 05 Sep 0500 - 1330 | 14276 | 901767 | LINER HANGER FAQILED TO SET AFTER DROPPING 1.25" SETTING BALL AND CHASE W/3BPM. | TF | HGRL |  | 09/05/2022 | ADC-43L | 8.5 | UTMN-3118
511 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ADC-55L | Hrs | UTMN-3171
512 | STBH | TK3 | 680 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/05/2022 | ADC-55L | 24 | UTMN-3171
513 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ADM-339 | Hrs | MRJN-3013
514 | FOT | RIG | 6 | 05 Sep 1400 - 2000 | 5692 | 901752 | TDS ISSUES CAUSING EXCESSIVE TIME BACKREAMING. | RR | TDS |  | 09/05/2022 | ADM-339 | 6 | MRJN-3013
515 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ADM-655 | Hrs | SFNY-183
516 | OTH | RIG | 192 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/05/2022 | ADM-655 | 24 | SFNY-183
517 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | DPS-43 | Hrs | SDGM-1218
518 | DSFT | HLH | 45.5 | 04 Sep 0500 - 0500 | 13264 | 901707 | WHILE RUNNING 7" LINER ON 5-1/2" DP IN CASED HOLE AT DEPTH 10,000' ; THE 7" HALL XTREMEGRIP LINER HGR TAGGED ON 9-5/8" DVT & UNABLE TO PASS THROUGH IT. ATTEMPTED TO PASS THROUGH DVT WITH CIRCULATION AND ROTATION AS PRACTICALLY AS POSSIBLE - NO SUCCESS. | JF | HGRL |  | 09/05/2022 | DPS-43 | 21.5 | SDGM-1218
519 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | DQ-57L | Hrs | KHRS-345
520 | FOT | SPS | 11 | 05 Sep 1800 - 0500 | 4747 | 901763 | SUDDEN INCREASE IN PRESSURE TO 4200 PSI, THEN PRESSURE DROPED TO NROAML. FOUND RUBBER IN SHAKERS. ATTEMPT TO RESUME DRILLING, NO PROGRESS IN BOTH MODE SLIDING/ROTARY. | BHA | MMOT |  | 09/05/2022 | DQ-57L | 11 | KHRS-345
521 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ED-85A | Hrs | ZULF-2066
522 | FOT | RIG | 26.5 | 04 Sep 0230 - 0500 | 0 | 901686 | IBOP IS LEAKING. | RR | RSYS |  | 09/05/2022 | ED-85A | 24 | ZULF-2066
523 | GRF | RIG | 4.5 | 05 Sep 0030 - 0500 | 2734 | 901761 | DURING COMMISSIONING TESTS ON RIG POWER SYSTEM, OBSERVED THE BLOCKS DRIFTING PASSED SET LOWER BLOCK LIMITS. PERFORMED TESTS, OBSERVED LEAKING BRAKE SEAL ON SERVICE BRAKE #2. SUSPENDED OPERATIONS, PROCEED TO FIX LEAKING SEAL. | UPRA | DWKS | 901163 | 09/05/2022 | ENS-108 | 4.5 | ZULF-2015
524 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ENS-108 | Hrs | ZULF-2015
525 | GRF | RIG | 336 | 23 Aug 0500 - 0030 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/05/2022 | ENS-108 | 19.5 | ZULF-2015
526 | GRF | RIG | 4.5 | 05 Sep 0030 - 0500 | 2734 | 901761 | DURING COMMISSIONING TESTS ON RIG POWER SYSTEM, OBSERVED THE BLOCKS DRIFTING PASSED SET LOWER BLOCK LIMITS. PERFORMED TESTS, OBSERVED LEAKING BRAKE SEAL ON SERVICE BRAKE #2. SUSPENDED OPERATIONS, PROCEED TO FIX LEAKING SEAL. | UPRA | DWKS | 901163 | 09/05/2022 | ENS-108 | 4.5 | ZULF-2015
527 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ENSCO-76 | Hrs | MRJN-2004
528 | HERR | SCM | 12.25 | 04 Sep 2045 - 1645 | 13400 | 901708 | ATTEMPT TO P/T SLB CEMENT UNIT & LINES, OBSERVE PRESSURE DROP (180 PSI / MIN), TROUBLSHOOTING SAME. | CMT | NA |  | 09/05/2022 | ENSCO-76 | 9.25 | MRJN-2004
529 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | EXL-IVA | Hrs | ZULF-2041
530 | GRF | RIG | 36.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/05/2022 | EXL-IVA | 24 | ZULF-2041
531 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | HI-4 | Hrs | BRRI-1001
532 | FOT | SDM | 7.5 | 05 Sep 2130 - 0500 | 9173 | 901762 | UNABLE TO ESTABLISH CORRECT TOOL FACE. CONSULT WITH SHOREBASE AND ATTEMPT TO ESTABLISH VIA TROUBLE SHOOTING PROCEEDURES. NO SUCCESS. (TOOL PICKING UP SIGNAL BUT WITH INCORRECT DIRECTIONS) POOH CHANGE TOOLS | BHA | MWD |  | 09/05/2022 | HI-4 | 7.5 | BRRI-1001
533 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | JACK-203 | Hrs | HZEM-849
534 | FOT | WWL | 5.5 | 05 Sep 1200 - 1730 | 5785 | 901732 | TOOL FAILURE ( DCOR CURVE ON THE DENSITY TOOL: IT WAS READING SLIGHTLY NEGATIVE THROUGHOUT THE LOG (BETWEEN 0 AND -.05)) | TF | WLT |  | 09/05/2022 | JACK-203 | 5.5 | HZEM-849
535 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | MP-1 | Hrs | MRJN-78
536 | FOT | NRT | 825 | 31 Jul 0245 - 0830 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 09/05/2022 | MP-1 | 3.5 | MRJN-78
537 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | NA-393S | Hrs | SDGM-1134
538 | XWSW | SAM | 75 | 02 Sep 0130 - 0500 | 13227 | 901678 | SAMMA PACKER RUBBER ELEMENT LOST IN HOLE. | TF | WBCL |  | 09/05/2022 | NA-393S | 24 | SDGM-1134
539 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | NBR-575S | Hrs | HRDH-1990
540 | XBTR | ULT | 17 | 05 Sep 1200 - 0500 | 10538 | 901760 | OBSERVED VERY LOW ROP PAST 10505'. | LROP | BIT |  | 09/05/2022 | NBR-575S | 17 | HRDH-1990
541 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | PA-529S | Hrs | SHYB-523
542 | FOT | BC | 37.25 | 04 Sep 1545 - 0500 | 4029 | 901687 | RIH WITH BAKER ESP COMPLETION WITH PDHMS HAD OBSTRUCTION @ 4029'. (BAKER 7" OCTOPUS PACKER DETH @ 3828', SAME DEPTH AS 7" TOL) ATTEMPT TO PASS SAME WITH 5 KLB S/O WT IN PRESENCE OF BAKER PACKER ENGINEER, NO SUCCESS. | JF | GP |  | 09/05/2022 | PA-529S | 24 | SHYB-523
543 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | PN-9 | Hrs | MRJN-673
544 | FOT | BHI | 50.5 | 03 Sep 2130 - 0500 | 13460 | 901712 | AFTER POH WITH 8-1/2" BHI MOTORIZED RSS BHA, FOUND ONE FLANGE THAT COVERS THE HYDRAULIC UNIT AND STEERING PAD ON THE RSS IS MISSING ALONG WITH SOME OF THE SCREWS THAT HOLDS THIS PIECE IN PLACE | BHA | RSS |  | 09/05/2022 | PN-9 | 24 | MRJN-673
545 | FOT | HTS | 1.75 | 05 Sep 0500 - 0645 | 12846 | 901766 | HWT TROUBLESHOOT STBD FLARE-BOOM, REPAIR SAME: CHANGE OUT ELECTRIC CABLE, FUNCTION TEST: (OK). | TF | WTSE |  | 09/05/2022 | RBP-50A | 1.75 | HSBH-55
546 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | RBP-50A | Hrs | HSBH-55
547 | FOT | HSL | 2.5 | 05 Sep 1800 - 2030 | 12846 | 901764 | DURING HIGH TEST OBSERVED VISUAL LEAK BETWEEN HSL RISER CONNECTION | TF | SLICK |  | 09/05/2022 | RBP-50A | 2.5 | HSBH-55
548 | FOT | HTS | 1.5 | 05 Sep 0330 - 0500 | 12846 | 901765 | DURING EQUALIZING PRESSURE TO WELL BORE PRESSURE NOTICED GREASE FITTING ON SSV1 VALVE LEAKING. BLEED OFF PRESSURE TO ZERO CHANGE GREASE FITTING SAME. | TF | WTSE |  | 09/05/2022 | RBP-50A | 1.5 | HSBH-55
549 | FOT | HTS | 1.75 | 05 Sep 0500 - 0645 | 12846 | 901766 | HWT TROUBLESHOOT STBD FLARE-BOOM, REPAIR SAME: CHANGE OUT ELECTRIC CABLE, FUNCTION TEST: (OK). | TF | WTSE |  | 09/05/2022 | RBP-50A | 1.75 | HSBH-55
550 | 6750 | 0 | LOG | E |  | WLT | CONT HES W/L RECORDING MULTI-CASING CORROSION LOG (MPET) F/ 2380 FT TO SURFACE- LOGGING SPEED 8 FPM (LAST 1000 FT 5 FPM).- PERFORMED REPEAT PASS F/ 5250 FT T/ 4950 FT & F/ 400 FT T/200 FT.- POOH TO SURFACE.- RD LOGGING TOOLS & EQPT. | 6750 | 2380 | HWP | 09/05/2022 | SINO-12L | LOG | HWYH-518
551 | 6750 |  | ND | N |  | SNIP | N/D SHOOTING NIPPLE. N/U BELL NIPPLE & FLOW LINE. | 6750 |  | RIG | 09/05/2022 | SINO-12L | BOP | HWYH-518
552 | 6750 | 215 | SET | N |  | RTTS | RIH WITH 16 STD'S 4" HWDP, M/U 9-5/8" RTTS & STORM VALVE, SET 7" RTTS PKR @ 220 FT. P/T BACK SIDE TO 1000 PSI. RELEASE SETTING TOOL AND POOH. P/T STORM VALVE & RTTS PKR TO 1000 PSI / 10 MINS, HOLD. L/D SETTING TOOL. | 6750 | 215 | HCO | 09/05/2022 | SINO-12L | PA | HWYH-518
553 | 6750 |  | OTH | N |  | NA | HPJSM, ISSUE REQUIRED PTW & DISCUSSED JSA , CHECK WH & CSG INTEGRITY.- CHECK 9 5/8" X 13 3/8" CCA IS ZERO PRESSURE.- P/T 9 5/8" X13-3/8" CCA WITH 1% B-1400 INHIBITED WATER. TO 500 PSI HOLD, NO INJECTIVITY.- P/T 9 -5/8" " SEAL AND SLIPS TO 1,500 PSI, HOLD.- DIG CELLAR 6 FT BELOW LANDING BASE.- MANSOORI PERFORM UT INSPECTION FOR LANDING BASE & 18-5/8" CONDUCTOR FOUND ALL IN GOOD CONDITION. | 6750 |  | IWS | 09/05/2022 | SINO-12L | WH | HWYH-518
554 | 6750 |  | OTH | N | 4625 | NA | OUT OF SCOPE:- HOT-HED WELD 1" NIPPLE ON 18 5/8" CONDUCTOR CSG, AL-MANSOORI MPI INSPECTED WELDING AREA-OK. - HOT-HEAD INSTALLED BALL VALVE, P/T TO 1000 PSI HOLD.- HOT TAP HOLE, MONITOR 18-5/8" X 13 3/8" CCA NO GAS READINGS. | 6750 |  | IWS | 09/05/2022 | SINO-12L | WH | HWYH-518
555 | 6750 |  | OTH | N |  | NA | HPJSM:- HOT-HEAD OPNED WINDOW ON 18-5/8".- AL MANSOURI UT INSPECTED 13 3/8" CSG, FOUND IN GOOD CONDITION.- FILLED UP 18-5/8" X 13 3/8" CCA WITH CEMENT 118 PCF.- HOT-HEAD WELDED BACK 18-5/8" WINDOW. AL MANSOURI PERFORMED MPI ON 18-5/8" WINDOW WELDING - OK.- FILLED CELLAR WITH SWEET SAND. | 6750 |  | IWS | 09/05/2022 | SINO-12L | WH | HWYH-518
556 | 6750 |  | OTH | N |  | NA | REMOVE 2" BLIND FLANGE, VR PLUG & INSTALL 2ND NEW 2-1/16" GATE VALVE ON THS. M/U & RIH W/ 9-5/8" CUP TESTER, PT GATE VALVE & CONNECTION TO 300/2550 PSI - HOLD.- POOH & L/D 9-5/8" CUP TESTER. | 6750 |  | IWS | 09/05/2022 | SINO-12L | WH | HWYH-518
557 | 6750 | 0 | OTH | N |  | NA | RIH W/ 7" RTTS RETRIEVING TOOL TO 220 FT. UNSET 9-5/8" RTTS, POOH & L/D SAME. | 6750 | 215 | HCO | 09/05/2022 | SINO-12L | PA | HWYH-518
558 | 6750 | 0 | TO | N |  | STHDP | POOH RACK BACK16 STDS OF 4" HWDP | 6750 | 1704 | RIG | 09/05/2022 | SINO-12L | PA | HWYH-518
559 | 6750 |  | SET | N |  | WBSH | INSTALL 11" CIW WEAR BUSHING. | 6750 |  | RIG | 09/05/2022 | SINO-12L | WH | HWYH-518
560 | 6750 |  | HT | N |  | BHA | HPJSM, M/U WFD WHIPSTOCK W/ 6-1/8" MILL ASSY WITH UBHO AS FOLLOWS: 5-1/2 QC RHN WHIPSTOCK, 6" QC LEAD MILL, 6-1/8" QC FLEX MILL, 1 JOINT 3-1/2" HWDP, FLOAT SUB WITH FLOAT VALVE, UBHO SUB.- ORIENTED WHIPSTOCK FACE WITH UBHO HIGH SIDE. | 6750 |  | RIG | 09/05/2022 | SINO-12L | TINL | HWYH-518
561 | 6750 | 1700 | TI | N |  | STHDP | RIH WITH 7" WFD WHIPSTOCK ON 4" HWDP / DP'S STANDS AT CONTROLLED SPEED TO 1700 FT... ONGOING @ RT.- FILL UP & PUMP STRING VOL EVERY 10 STDS.- KEPT MONITORING WELL ON TRIP TANK W/ 74 PCF VISCOUS BRINE, WELL STATIC. | 6750 | 62 | RIG | 09/05/2022 | SINO-12L | TINL | HWYH-518
562 | 1 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | HOT-HEAD HOT TAP HOLE IN 18-5/8" CSG | 1 | 4625 | 05 Sep 1930 | 09/05/2022 | SINO-12L | Type | HWYH-518
563
564
565 | 9502 |  | PJSM | N |  | NA | HPJSM, ISSUE PTW & REVIEW JSA, GAS TEST CELLAR; NO H2S/LEL, DIG OUT CELLAR 6 FT BELOW LANDING BASE.>> PRESSURE TEST 9-5/8" X 13 3/8" CCA TO 500 PSI WITH INHIBITED WATER, PRESSURE HOLD @ 300 PSI (NO INJECTIVITY).>> MANSOORI PERFORM UT INSPECTION FOR LANDING BASE ( GOOD CONDITION ) ,18-5/8" CSG , 87.5# ( SEAL WELDED TO DONUT PLATE).>> PRESSURE TEST 9-5/8" CSG SLIPS TO 1000 PSI, OK. | 9502 |  | RIG | 09/05/2022 | SINO-19L | WH | HWYH-565
566 | 9502 |  | PJSM | N | 4626 | NA | (OOS) HPJSM , WELDED 1-1/2" NIPPLE ON 18-5/8" CSG , MANSOORI PERFORM MPI FOR WELDINGS , HOT HEAD R/U & P/T MPHT FOR 1200 PSI- OK , HOT HEAD PERFORMED HOT TAPPING ON 18-5/8" CSG , NO PRESSURE OR GAS IN 18-5/8" X 13-3/8" CCA , R/D MPHT. | 9502 |  | RIG | 09/05/2022 | SINO-19L | WH | HWYH-565
567 | 9502 |  | OTH | N |  | NA | HOT-HED CUT WINDOW ON 18-5/8" CSG , ALMANSOORI PERFORMED UT INSPECTION ON 13-3/8" CSG ( GOOD CONDITION ), BACK FILL 18-5/8" X 13-3/8" CCA W/ CMT, HOT-HED WELD BACK WINDOW, MANSOORI PERFORM MPI FOR WELDING AREA, OK , BACK FILL CELLAR W/ SWEET SAND.> INSTALLED NEEDLE VALVE ON 18-5/8'' CSG FOR FUTURE WORKOVER OPERATIONS. | 9502 |  | IWS | 09/05/2022 | SINO-19L | WH | HWYH-565
568 | 9502 |  | PJSM | N |  | NA | HPJSM, M/U & RIH WITH HALLIBURTON RETRIEVING TOOL, LATCHED & RETRIVED 9-5/8" RTTS PKR, POOH TO SURFACE, L/D HALLIBURTON 9-5/8" RTTS. | 9502 |  | RIG | 09/05/2022 | SINO-19L | WH | HWYH-565
569 | 9502 |  | CIRC | N | 4585 | MPMP | (OOS) P/T 7" CSG W/75 PCF BRINE IN STAGES TO 1000 PSI FOR 15 MINS -OK. | 9502 |  | RIG | 09/05/2022 | SINO-19L | CT | HWYH-565
570 | 9502 | 10 | TO | N | 4585 | STDP | (OOS) CONT.POOH W/7" CLEAN OUIT SCRAPER ASSY TO SURFACE. | 9502 | 1465 | RIG | 09/05/2022 | SINO-19L | CT | HWYH-565
571 | 9502 |  | HT | N | 4585 | BHA | (OOS) L/D 7" CLEAN OUT SCRAPER BHA. | 9502 |  | RIG | 09/05/2022 | SINO-19L | CT | HWYH-565
572 | 9502 |  | HT | N |  | BHA | M/U & RIH W/ WFD 7'' WHIPSTOCK & MILLING BHA .>> 7" WHIPSTOCK BHA: 5-1/2" RHN WHIPSTOCK + 6-1/8" LEAD MILL + 6-1/8" FLEX MILL + 3-1/2" HWDP + FLOAT SUB+ UBHO+ 3 X 4-3/4"DC'S+X/O .>> ALIGN WHIPSTOCK FACE W/UBHO.>> GAUGE LEAD & FLEX MILLS-OK .>> ATTACH LEAD MILL TO WHIP FACE W/ 36 KLB SHEAR BOLT . | 9502 |  | RIG | 09/05/2022 | SINO-19L | TINL | HWYH-565
573 | 9502 | 4591 | TI | N |  | STHDP | RIH W/ 7'' WFD QC RHN HYD WHIPSTOCK ASSY. ON DRIFTED 4" HWDP/DP STD'S @ CONTROLLED SPEED TO 4591'(BTM OF W'STOCK).>> PASS CAREFULLY 7" TOL @ 1616'.>> CONTROL RIH SPEED.>> FILL STRG EVERY STD.>> KEEP MONITOR WELL ON TRIP TANK - STATIC. | 9502 | 150 | RIG | 09/05/2022 | SINO-19L | TINL | HWYH-565
574 | 9502 |  | SURV | N |  | GYRO | HPJSM, R/U GYRO SHEAVES & M/U GYRO TOOL,RIH, ORIENT WHIPSTOCK TO 307 AZIMUTH, POOH TO SURFACE. R/D GYRO TOOLS & SHEAVES.>CONFIRMED WHIPSTOCK ORIENTATION WITH THREE GYRO SHOTS. | 9502 |  | GCD | 09/05/2022 | SINO-19L | TINL | HWYH-565
575 | 9502 | 4591 | SET | N |  | WPSTK | HPJSM, SET 7" W'STOCK DEPTH @ 4591' (TOW @ 4575', BOW @ 4584'), APPLY 370 GPM @ 1800 PSI FOR 5 MIN, CONFIRM SET W/20 KLB S/O WEIGHT, SHEARED BOLT W/ 35 KLB S/O WEIGHT, P/U 5 FT & CONFIRM STRING FREE. | 9502 | 4591 | WWD | 09/05/2022 | SINO-19L | TINL | HWYH-565
576 | 9502 |  | CIRC | N |  | MPMP | DISPLACE HOLE TO 77 PCF POLYMER MUD, FLOW CHWECK, WELL STATIC | 9502 |  | RIG | 09/05/2022 | SINO-19L | CT | HWYH-565
577 | 9502 | 4584 | MILL | N |  | MILL | CUT 6-1/8" WINDOW ( 9 FT ) F/ 4575' (TOW) T/4584' (BOW) W/77 PCF POLYMER MUD & HVP, 100% RETURN.> MILLING PARAMETERS : WOB : 10-20 KLB , PR : 270 GPM 750 PSI , ROT: 100 RPM , TRQ : 2000-4000 LB-FT .> SWEEP HOLE W/ 15 BBL HVP EVERY 1 FT. | 9502 | 4575 | WFS | 09/05/2022 | SINO-19L | TINL | HWYH-565
578 | 4584 |  | TINL | S |  | NA | TIE-IN NEW LATERAL 0-2 @ 4584'. | 4584 |  | RIG | 09/05/2022 | SINO-19L | OT | HWYH-565
579 | 4592 | 4592 | D | N |  | TDS | DRILL 8' RAT HOLE F/ 4584' TO 4592' W/ 77 PCF POLYMER MUD & HVP, 100% RETURN.>> DRILLING PARAMETERS : WOB : 20-25 KLB , PR : 270 GPM 800 PSI , ROT: 100 RPM , TRQ : 1500-2000 LB-FT .>> SWEEP HOLE W/ 15 BBL HVP EVERY 1 FT . | 4584 | 4582 | RIG | 09/05/2022 | SINO-19L | DRLG | HWYH-565
580 | 4592 |  | CIRC | N |  | MPMP | DRESSED WINDOW, PASSED THRU WINDOW SMOOTH W/O CIRCULATION & ROTATION | 4592 |  | RIG | 09/05/2022 | SINO-19L | DRLG | HWYH-565
581 | 4592 |  | CIRC | N |  | MPMP | SWEPT HOLE TWICE W/50 BBLS HI-VIS PILL LOADED W/BAROLIFT & CHC..............INC @ RPT. | 4592 |  | RIG | 09/05/2022 | SINO-19L | DRLG | HWYH-565
582 | 1.5 | OOS | LCL | 4585 | WHWK | LOCATE & FIX 7" CSG LEAK. | HOT-HED PERFORM HOT TAPPING ON 18-5/8" CSG . | 1.5 | 4626 | 05 Sep 0630 | 09/05/2022 | SINO-19L | OOS | HWYH-565
583
584
585
586 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SINO-1L | Hrs | ABJF-260
587 | FOT | BAL | 51 | 03 Sep 0200 - 0500 | 4718 | 901697 | BAKER VSD SYSTEM NOT PROVIDING ACCURATE VALUES WHEN FUNCTION TESTING ESP START UP PUMP W/ NEW VSD UNIT, SAME RESULTS. DECISION WAS MADE TO POH W/ ESP COMPLETION & RIH WITH NEW PUMP. | TF | ESP |  | 09/05/2022 | SINO-1L | 24 | ABJF-260
588 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SINO-32L | Hrs | SHYB-124
589 | FOT | BHI | 4 | 05 Sep 1230 - 1630 | 1350 | 901755 | RIH 16" MTR/MWD BHA TO 1350 FT. SHALLOW TEST MWD - NO SIGNAL | BHA | MWD |  | 09/05/2022 | SINO-32L | 4 | SHYB-124
590 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SINO-33L | Hrs | HRDH-1542
591 | GRF | RIG | 74 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/05/2022 | SINO-33L | 24 | HRDH-1542
592 |  | 901716 | BAW | OTH | 4545 | 5163 | HPJSM, RIH WL RUN#5 LOGGING TOOLS (RCX-GR) ON 5" DRIFTED DP STDS WITH CONTROL SPEED TO 4528'. ** FILL STRING EVERY 10 STDS & BREAK CIRC.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. |  | TF | 5163 | 09/05/2022 | SINO-46L | NA | SHYB-270
593 |  | 901716 | RIG | CIRC | 4545 | 5163 | HPJSM, CIRCULATE 2 X STRG VOLUME WITH 245 GPM, 160 PSI, |  | TF | 5163 | 09/05/2022 | SINO-46L | MPMP | SHYB-270
594 |  | 901716 | BAW | OTH | 4545 | 5163 | HPJSM. R/U BHI W/L SHEAVES AND INSTALL SES.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC.. |  | TF | 5163 | 09/05/2022 | SINO-46L | NA | SHYB-270
595 |  | 901716 | BAW | OTH | 4545 | 5163 | HPJSM, RIH W/ PUMP DOWN HEAD ON W/L CABLE ATTEMPTED TO LATCH PWCH INTO THE DOCKING HEAD WITOUT SUCCESS (PARTIAL LATCH), ** INCREASE FLOW RATE SEVERAL TIMES & TRY TO LATCH SAME PARTIAL LATCH. ** PUMPED HVP, CHC, TRY TO LATCH SAME PARTIAL LATCH. .** L/D SES AND CHECK PWCH -GOOD-.** PULL OUT TO CHECK DOCKING HEAD.** MONITOR WELL ON TRIP TANK.** DICISON MADE TO REPLACE BHI BY HLB. |  | TF | 5163 | 09/05/2022 | SINO-46L | NA | SHYB-270
596 |  | 901716 | BAW | OTH | 4545 | 5163 | POOH W/ WIRELINE CONNECTOR HEAD TO SURFACE, R/D WL SHEAVES.** MONITOR HOLE ON TRIP TANK, HOLE STATIC. |  | TF | 5163 | 09/05/2022 | SINO-46L | NA | SHYB-270
597 |  | 901716 | BAW | OTH | 4545 | 5163 | POOH W/ BHI PCL LOGGING TOOLS RUN#5: (GR-RCX) TO TOP OF LOGGING TOOLS@188'.** HARDLY LATCH AT SURFACE AFTER 3 TRIALS-*** PERFORM SURFACE FUNCTION CHECKS AND TOOL CALIBRATION ON SURFACE, OK.*** MONITOR WELL THROUGH TRIP TANK. |  | TF | 5163 | 09/05/2022 | SINO-46L | NA | SHYB-270
598 |  | 901716 | BAW | OTH | 4545 | 5163 | HPJSM, POOH & L/D BHI RUN#5 LOGGING TOOLS (RCX/GR).* MONITOR THE WELL ON T/TANK: WELL STATIC. |  | TF | 5163 | 09/05/2022 | SINO-46L | NA | SHYB-270
599 |  | 901716 | RIG | HT |  | 5163 | HPJSM , P/U & M/U 8-1/2" CONDITION TRIP ASSY . |  | TF | 5163 | 09/05/2022 | SINO-46L | BHA | SHYB-270
600 | 5163 | 901716 | RIG | TI |  | 5163 | RIH W/8-1/2" CONDITION TRIP ASSY ON 5" STDS DP TO BTM @ 5163',** PASS DV TOOL FREELY.** WASH DOWN LAST STAND.** HOLE CONDITION TRIP PRIOR RUN HLB LOGGING TO COLLECT SAMPLES. | 0 | TF | 5163 | 09/05/2022 | SINO-46L | STDP | SHYB-270
601 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SINO-46L | Hrs | SHYB-270
602 | FOT | BAW | 40 | 04 Sep 1300 - 0500 | 4528 | 901716 | RIH W/ PUMP DOWN HEAD ON W/L CABLE ATTEMPTED TO LATCH PWCH INTO THE DOCKING HEAD WITOUT SUCCESS (PARTIAL LATCH). | TF | WLT |  | 09/05/2022 | SINO-46L | 24 | SHYB-270
603 | 93.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #4 (FTEX -GR), RUN #5 (RCX -GR-WGI). | 20 | 4545 | 01 Sep 0800 | 09/05/2022 | SINO-46L | Type | SHYB-270
604
605
606 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SINO-47 | Hrs | HWYH-1341
607 | FOT | WCM | 11 | 05 Sep 1800 - 0500 | 11139 | 901756 | WEATHERFORD DV FAILED. | TF | ACCSS |  | 09/05/2022 | SINO-47 | 11 | HWYH-1341
608 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SL-7 | Hrs | SFNY-1730
609 | FOT | RIG | 2 | 05 Sep 0830 - 1030 | 940 | 901759 | TROUBLESHOOT LOOSE DIES ON TOP DRIVE CLAMP. | RR | TDS |  | 09/05/2022 | SL-7 | 2 | SFNY-1730
610 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SP-121 | Hrs | BRRI-522
611 | OTH | RIG | 67 | 02 Sep 1600 - 0500 | 14529 | 901642 | HELD STAND DOWN MEETING WITH CREW AND DISCUSSED THE FINGER PINCHED INCIDENT - SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION BY DOE&CD. | UPRA | NA |  | 09/05/2022 | SP-121 | 24 | BRRI-522
612 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SP-161 | Hrs | HRML-98
613 | FOT | GOC | 3.5 | 05 Sep 0915 - 1245 | 5480 | 901758 | POWER TONG FAILURE | TF | CTRQ |  | 09/05/2022 | SP-161 | 3.5 | HRML-98
614 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SP-165 | Hrs | FDHL-146
615 | FOT | SWL | 6 | 05 Sep 2300 - 0500 | 7140 | 901753 | FAILURE ON SLB MDT SAMPLING TOOL, NO READING ON DENSITY & VISCOSITY SENSOR | TF | WLT |  | 09/05/2022 | SP-165 | 6 | FDHL-146
616 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | SSA-5892 | Hrs | AWTD-141400
617 | FOT | RIG | 261.25 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 09/05/2022 | SSA-5892 | 24 | AWTD-141400
618 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | T901 | Hrs | JLMN-60
619 | FOT | RIG | 42.75 | 04 Sep 1015 - 0500 | 0 | 901710 | WHILE BREAKING OUT CRT FROM SAVER SUB, THE TDS GRAPPLES WERE NOT HOLDING THE CRT, WHICH LEAD THE CRT TO ROTATE, MEANWHILE THE CRT GRAPPLE DIES BEING UNDERNEATH ROTARY TABLE WERE CAUGHT BY THE EDGE OF INTERNAL FACE OF MASTER BUSHING. RESULTED IN 1 PIECE OF GRAPPLE DIES BROKE AND FELL DOWN. | TF | CRT |  | 09/05/2022 | T901 | 24 | JLMN-60
620 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | WCL-83 | Hrs | MRJN-831
621 | WTHR | ARM | 8.5 | 04 Sep 0745 - 0845 | 13192 | 901682 | SUSPEND FLARING DUE TO LOW WIND SPEED. | WON | NA |  | 09/05/2022 | WCL-83 | 1.75 | MRJN-831
622 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/05/2022 | ZPEC-2 | Hrs | QMRN-806
623 | FOT | RIG | 1.5 | 05 Sep 1100 - 1230 | 125 | 901757 | AFTER PT CMT LINE. TRIED TO PUMP SPACER PRESSURE INCREASED TO 400 PSI. CHECKED RIG CMT LINES FOUND PLUGGED BY CMT. | TF | SFLN |  | 09/05/2022 | ZPEC-2 | 1.5 | QMRN-806
624 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ADC-21 | Hrs | MHWZ-991100
625 | UNKN | RIG | 137.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/06/2022 | ADC-21 | 24 | MHWZ-991100
626 | FOT | WUD | 41.5 | 05 Sep 0530 - 2300 | 11518 | 901856 | DRILL PIPE STUCK IN BEARING FOR RCD | TF | MPD |  | 09/06/2022 | ADC-55L | 18 | UTMN-3171
627 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ADC-55L | Hrs | UTMN-3171
628 | STBH | TK3 | 662.5 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/06/2022 | ADC-55L | 6 | UTMN-3171
629 | FOT | WUD | 41.5 | 05 Sep 0530 - 2300 | 11518 | 901856 | DRILL PIPE STUCK IN BEARING FOR RCD | TF | MPD |  | 09/06/2022 | ADC-55L | 18 | UTMN-3171
630 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ADC-62L | Hrs | ANDR-589
631 | FOT | RIG | 9.5 | 06 Sep 0700 - 1630 | 9016 | 901874 | HAD LEAK FROM 3" TDS WASH PIPE ASSEMBLY. | RR | TDS |  | 09/06/2022 | ADC-62L | 9.5 | ANDR-589
632 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ADES-157 | Hrs | HRDH-1840
633 | FOT | SWL | 3.75 | 06 Sep 1815 - 2200 | 9603 | 901852 | IBC SHOWING QUESTIONABLE DATA QUALITY. | TF | CBL |  | 09/06/2022 | ADES-157 | 3.75 | HRDH-1840
634 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ADM-261 | Hrs | MRJN-24
635 | SRVC | WWD | 9 | 05 Sep 0130 - 1030 | 5509 | 901792 | UNABLE TO COMPLETE WINDOW MILLING AND RATHOLE IN ONE RUN. | WO | NA |  | 09/06/2022 | ADM-261 | 5.5 | MRJN-24
636 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ADM-266 | Hrs | MRJN-309
637 | WOPF | AP2 | 14.5 | 05 Sep 0200 - 1630 | 0 | 901768 | WAIT ON PRODUCING FS PERMISSION TO FLOWBACK VIA GOSP LINE. | WO | NA |  | 09/06/2022 | ADM-266 | 11.5 | MRJN-309
638 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ADM-339 | Hrs | MRJN-3013
639 | FOT | RIG | 17 | 05 Sep 1400 - 1600 | 5692 | 901752 | TDS ISSUES CAUSING EXCESSIVE TIME BACKREAMING. | RR | TDS |  | 09/06/2022 | ADM-339 | 11 | MRJN-3013
640 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ADM-655 | Hrs | SFNY-183
641 | OTH | RIG | 216 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/06/2022 | ADM-655 | 24 | SFNY-183
642 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | DQ-57L | Hrs | KHRS-345
643 | FOT | SPS | 13.5 | 05 Sep 1800 - 0730 | 4747 | 901763 | SUDDEN INCREASE IN PRESSURE TO 4200 PSI, THEN PRESSURE DROPED TO NROAML. FOUND RUBBER IN SHAKERS. ATTEMPT TO RESUME DRILLING, NO PROGRESS IN BOTH MODE SLIDING/ROTARY. | BHA | MMOT |  | 09/06/2022 | DQ-57L | 2.5 | KHRS-345
644 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ED-85A | Hrs | ZULF-2066
645 | FOT | RIG | 32.5 | 04 Sep 0230 - 1100 | 0 | 901686 | IBOP IS LEAKING. | RR | RSYS |  | 09/06/2022 | ED-85A | 6 | ZULF-2066
646 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ENS-108 | Hrs | ZULF-2015
647 | GRF | RIG | 28.5 | 05 Sep 0030 - 0500 | 2734 | 901761 | DURING COMMISSIONING TESTS ON RIG POWER SYSTEM, OBSERVED THE BLOCKS DRIFTING PASSED SET LOWER BLOCK LIMITS. PERFORMED TESTS, OBSERVED LEAKING BRAKE SEAL ON SERVICE BRAKE #2. SUSPENDED OPERATIONS, PROCEED TO FIX LEAKING SEAL. | UPRA | DWKS | 901163 | 09/06/2022 | ENS-108 | 24 | ZULF-2015
648 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ENS-141 | Hrs | MRJN-3303
649 | FOT | RIG | 1.75 | 06 Sep 0500 - 0645 | 2151 | 901812 | CHANGED WASHED OUT LINER & PISTON IN MUD PUMP #2, CHANGED 2 SWAPS IN MUD PUMP#1. | RR | CSYS |  | 09/06/2022 | ENS-141 | 1.75 | MRJN-3303
650 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | ENSCO-76 | Hrs | MRJN-2004
651 | FOT | BHI | 2.5 | 06 Sep 2030 - 0430 | 14527 | 901853 | HAD BAD DECODING FROM BHI DIRECTION TOOLS, TROUBLESHOOTING SAME. | BHA | MWD |  | 09/06/2022 | ENSCO-76 | 2.5 | MRJN-2004
652 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | EXL-IA | Hrs | SFNY-1790
653 | FCLK | ARM | 24 | 06 Sep 0500 - 0500 | 7495 | 901855 | BUBBLES COMMING FROM CUT CONDUCTOR AT SEA BED FROM 30" X 18 5/8" CASING ANNULAS | TF | CSG |  | 09/06/2022 | EXL-IA | 24 | SFNY-1790
654 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | EXL-IVA | Hrs | ZULF-2041
655 | GRF | RIG | 60.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/06/2022 | EXL-IVA | 24 | ZULF-2041
656 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | HI-4 | Hrs | BRRI-1001
657 | FOT | SDM | 14 | 05 Sep 2130 - 1200 | 9173 | 901762 | UNABLE TO ESTABLISH CORRECT TOOL FACE. CONSULT WITH SHOREBASE AND ATTEMPT TO ESTABLISH VIA TROUBLE SHOOTING PROCEEDURES. NO SUCCESS. (TOOL PICKING UP SIGNAL BUT WITH INCORRECT DIRECTIONS) POOH CHANGE TOOLS | BHA | MWD |  | 09/06/2022 | HI-4 | 6.5 | BRRI-1001
658 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | NA-393S | Hrs | SDGM-1134
659 | XWSW | SAM | 84.75 | 02 Sep 0130 - 0500 | 13227 | 901678 | SAMMA PACKER RUBBER ELEMENT LOST IN HOLE. | TF | WBCL |  | 09/06/2022 | NA-393S | 15.75 | SDGM-1134
660 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | NBR-575S | Hrs | HRDH-1990
661 | XBTR | ULT | 19.75 | 05 Sep 1200 - 0745 | 10538 | 901760 | OBSERVED VERY LOW ROP PAST 10505'. | LROP | BIT |  | 09/06/2022 | NBR-575S | 2.75 | HRDH-1990
662 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | PA-218S | Hrs | HRDH-1976
663 | FOT | RIG | 4 | 06 Sep 2200 - 0200 | 2040 | 901835 | FLOW LINE PLUGGED WITH PIECES OF RUBBER AT VALVE LOCATED IN THE MIDDLE OF FLOWLINE. UNPLUG & CLEAN SAME. | RR | CSYS |  | 09/06/2022 | PA-218S | 4 | HRDH-1976
664 | WOTO | SLH | 8.5 | 06 Sep 2030 - 0500 | 0 | 901872 | WAIT ON SMITH 7" POLISH MILL TOOLS. | WO | NA |  | 09/06/2022 | PA-529S | 8.5 | SHYB-523
665 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | PA-529S | Hrs | SHYB-523
666 | FOT | BC | 52.75 | 04 Sep 1545 - 2030 | 4029 | 901687 | RIH WITH BAKER ESP COMPLETION WITH PDHMS HAD OBSTRUCTION @ 4029'. (BAKER 7" OCTOPUS PACKER DETH @ 3828', SAME DEPTH AS 7" TOL) ATTEMPT TO PASS SAME WITH 5 KLB S/O WT IN PRESENCE OF BAKER PACKER ENGINEER, NO SUCCESS. | JF | GP |  | 09/06/2022 | PA-529S | 15.5 | SHYB-523
667 | WOTO | SLH | 8.5 | 06 Sep 2030 - 0500 | 0 | 901872 | WAIT ON SMITH 7" POLISH MILL TOOLS. | WO | NA |  | 09/06/2022 | PA-529S | 8.5 | SHYB-523
668 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | PN-9 | Hrs | MRJN-673
669 | FOT | BHI | 72 | 03 Sep 2130 - 0500 | 13460 | 901712 | AFTER POH WITH 8-1/2" BHI MOTORIZED RSS BHA, FOUND ONE FLANGE THAT COVERS THE HYDRAULIC UNIT AND STEERING PAD ON THE RSS IS MISSING ALONG WITH SOME OF THE SCREWS THAT HOLDS THIS PIECE IN PLACE | BHA | RSS |  | 09/06/2022 | PN-9 | 23.5 | MRJN-673
670 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | RBP-50A | Hrs | HSBH-55
671 | FOT | HTS | 2.75 | 05 Sep 0330 - 0615 | 12846 | 901765 | DURING EQUALIZING PRESSURE TO WELL BORE PRESSURE NOTICED GREASE FITTING ON SSV1 VALVE LEAKING. BLEED OFF PRESSURE TO ZERO CHANGE GREASE FITTING SAME. | TF | WTSE |  | 09/06/2022 | RBP-50A | 1.25 | HSBH-55
672 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SINO-12L | Hrs | HWYH-518
673 | FOT | SPS | 1.5 | 06 Sep 1245 - 1415 | 5131 | 901833 | GYRO COMPUTER SYSTEM MALFUNCTION | BHA | GMWD |  | 09/06/2022 | SINO-12L | 1.5 | HWYH-518
674 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SINO-1L | Hrs | ABJF-260
675 | FOT | BAL | 75 | 03 Sep 0200 - 0500 | 4718 | 901697 | FAILURE OF BAKER ESP PUMP TO OPERATE AFTER INSTALLING IT, RETRIEVED COMPLETION ASSY. , FOUND WRONG SHAFT COUPLING INSTALLED INSIDE ESP MOTOR. | TF | ESP |  | 09/06/2022 | SINO-1L | 24 | ABJF-260
676 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SINO-33L | Hrs | HRDH-1542
677 | GRF | RIG | 98 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/06/2022 | SINO-33L | 24 | HRDH-1542
678 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SINO-46L | Hrs | SHYB-270
679 | FOT | BAW | 64 | 04 Sep 1300 - 0500 | 4528 | 901716 | RIH W/ PUMP DOWN HEAD ON W/L CABLE ATTEMPTED TO LATCH PWCH INTO THE DOCKING HEAD WITOUT SUCCESS (PARTIAL LATCH). | TF | WLT |  | 09/06/2022 | SINO-46L | 24 | SHYB-270
680 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SINO-47 | Hrs | HWYH-1341
681 | FOT | WDV | 24 | 05 Sep 1800 - 1800 | 11139 | 901756 | WEATHERFORD DV FAILED. | TF | DV |  | 09/06/2022 | SINO-47 | 13 | HWYH-1341
682 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SL-7 | Hrs | SFNY-1730
683 | FOT | SAM | 2 | 06 Sep 1515 - 1715 | 408 | 901854 | SAMAA PBL SUB DIDN'T FULLY CLOSE AFTER DEACTIVATION. | BHA | MACS |  | 09/06/2022 | SL-7 | 2 | SFNY-1730
684 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SND-2007 | Hrs | AWTD-104001
685 | STBH | ARM | 6.25 | 06 Sep 2245 - 0500 | 18825 | 901814 | DURING REAMING DOWN OH WITH 5-7/8"X7" REAMER ASSY, PRESSURE SHOOT UP IN STRING & TDS STALL. | STUK | UNDR |  | 09/06/2022 | SND-2007 | 6.25 | AWTD-104001
686 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SP-120 | Hrs | MNIF-187
687 | FOT | RIG | 2 | 06 Sep 2130 - 2330 | 20500 | 901815 | CHANGE DRAW WORKS BRAKES. | RR | DWKS |  | 09/06/2022 | SP-120 | 2 | MNIF-187
688 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SP-121 | Hrs | BRRI-522
689 | OTH | RIG | 91 | 02 Sep 1600 - 0500 | 14529 | 901642 | HELD STAND DOWN MEETING WITH CREW AND DISCUSSED THE FINGER PINCHED INCIDENT - SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION BY DOE&CD. | UPRA | NA |  | 09/06/2022 | SP-121 | 24 | BRRI-522
690 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SP-161 | Hrs | HRML-98
691 | FOT | GOC | 13 | 06 Sep 1500 - 0400 | 5480 | 901873 | CSG LEAKED OR PARTED, CSG SLIPS JUMPED & CAME OUT OF ITS POSITION WHILE CLOSING WFD DV PORTS AFTER 2ND STAGE CMT JOB. | TF | CTRQ |  | 09/06/2022 | SP-161 | 13 | HRML-98
692 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SP-165 | Hrs | FDHL-146
693 | FOT | SWL | 26.5 | 05 Sep 2300 - 0130 | 7140 | 901753 | FAILURE ON SLB MDT SAMPLING TOOL, NO READING ON DENSITY & VISCOSITY SENSOR | TF | WLT |  | 09/06/2022 | SP-165 | 20.5 | FDHL-146
694 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SSA-303 | Hrs | HRDH-2411
695 | HFFT | NCS | 9 | 06 Sep 1200 - 2100 | 14802 | 901813 | 4-1/2" LNR CMT DIDN'T DEVELOP REQUIRED UCA STRENGTH. | CMT | NA |  | 09/06/2022 | SSA-303 | 9 | HRDH-2411
696 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SSA-5859 | Hrs | HWYH-1217
697 | LHFL | RIG | 2.5 | 06 Sep 0530 - 0800 | 3036 | 901793 | EXCESS TIME TO CONNECT AND REPAIR LEAK ON KOOMEY HYD-COFLEX. | RR | HSYS |  | 09/06/2022 | SSA-5859 | 2.5 | HWYH-1217
698 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SSA-5892 | Hrs | AWTD-141400
699 | FOT | RIG | 285.25 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 09/06/2022 | SSA-5892 | 24 | AWTD-141400
700 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | SSA-5970 | Hrs | UTMN-2340
701 | XTTE | SAM | 5 | 06 Sep 0000 - 0500 | 13703 | 901834 | WHILE PERFORMING NEGATIVE TEST SAMAA PACKER FAILED. | TF | WBCL |  | 09/06/2022 | SSA-5970 | 5 | UTMN-2340
702 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/06/2022 | T901 | Hrs | JLMN-60
703 | FOT | RIG | 65.5 | 04 Sep 1015 - 0345 | 0 | 901710 | WHILE BREAKING OUT CRT FROM SAVER SUB, THE TDS GRAPPLES WERE NOT HOLDING THE CRT, WHICH LEAD THE CRT TO ROTATE, MEANWHILE THE CRT GRAPPLE DIES BEING UNDERNEATH ROTARY TABLE WERE CAUGHT BY THE EDGE OF INTERNAL FACE OF MASTER BUSHING. RESULTED IN 1 PIECE OF GRAPPLE DIES BROKE AND FELL DOWN. | TF | CRT |  | 09/06/2022 | T901 | 22.75 | JLMN-60
704 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADC-21 | Hrs | MHWZ-991100
705 | UNKN | RIG | 161.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/07/2022 | ADC-21 | 24 | MHWZ-991100
706 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADC-41L | Hrs | SDGM-1244
707 | XBTR | TK3 | 10 | 07 Sep 1530 - 0130 | 10713 | 901825 | 12" RSS BHA WITH PDC BIT RIH TO DRILL OUT DVT, SHOE TRACK AND AHEAD NEW FORMATION COULD NOT DRILL OUT DVT, POOH AND CHANGED BHA TO ROTARY WITH MILL TOOTH TRI CONE, RIH AND DV WAS DRILLED OUT NO ISSUES. | LROP | BIT |  | 09/07/2022 | ADC-41L | 10 | SDGM-1244
708 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADC-50 | Hrs | SFNY-1176
709 | UVLC | ARM | 17 | 06 Sep 1730 - 1030 | 4365 | 901816 | ENCOUNTER LOSSES 230 BPH DYNAMIC/ 60 BPH STATIC LOSSES AT 4365' | LCIR | NA |  | 09/07/2022 | ADC-50 | 5.5 | SFNY-1176
710 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADC-55L | Hrs | UTMN-3171
711 | STBH | TK3 | 686.5 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/07/2022 | ADC-55L | 24 | UTMN-3171
712 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADC-56L | Hrs | UTMN-3069
713 | FOT | RIG | 1 | 07 Sep 1930 - 2030 | 1853 | 901824 | OBSERVED HYDRAULIC CATWALK MALFUNCTION DURING OPERATION. | RR | CATW |  | 09/07/2022 | ADC-56L | 1 | UTMN-3069
714 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADES-173 | Hrs | UTMN-1952
715 | WHOL | RIG | 16 | 07 Sep 0830 - 0030 | 10697 | 901820 | DRILL PIPE WASHED OUT. | DSF | DP |  | 09/07/2022 | ADES-173 | 16 | UTMN-1952
716 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADM-339 | Hrs | MRJN-3013
717 | FOT | RIG | 24.5 | 05 Sep 1400 - 1300 | 5692 | 901752 | TOP DRIVE SPEED GOES TO 0 RPM AT APPROXIMATELY 70' - 90' ELEVATOR POSITION. THE DRILLER HAS TO RE-ASSIGN THE SPEED TO TOP DRIVE AND IT BEGINS TO ROTATE. THIS IS OCCURRING WHILE TRYING TO BACK REAM OUT OF THE HOLE IN TIGHT HOLE. SOMETIMES IT CUTS OUT NUMEROUS TIMES AND SOMETIMES IT MAY GO A FEW STANDS AND NOT CUT OFF. | RR | TDS |  | 09/07/2022 | ADM-339 | 7.5 | MRJN-3013
718 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADM-655 | Hrs | SFNY-183
719 | OTH | RIG | 240 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/07/2022 | ADM-655 | 24 | SFNY-183
720 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ADM-657 | Hrs | SFNY-1228
721 | HERR | SCP | 7.5 | 07 Sep 1700 - 0030 | 4540 | 901818 | LBFV FAILED TO BREAK ON FIRST ATTEMPT. SLB ENGINEER FAILED TO IDENTIFY. | JF | TBG |  | 09/07/2022 | ADM-657 | 7.5 | SFNY-1228
722 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ED-85A | Hrs | ZULF-2066
723 | XTTE | FMC | 2.25 | 07 Sep 0030 - 0245 | 2128 | 901821 | HAD EXCESSIVE TIME WHILE DISENGAGE CRT FROM CASING JOINTS DUE TO INTERNAL MECHANICAL ISSUE INSIDE FRANKS CRT TOOL. | TF | CTRQ |  | 09/07/2022 | ED-85A | 2.25 | ZULF-2066
724 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | ENS-108 | Hrs | ZULF-2015
725 | GRF | RIG | 52.5 | 05 Sep 0030 - 0500 | 7186 | 901761 | DURING COMMISSIONING TESTS ON RIG POWER SYSTEM, OBSERVED THE BLOCKS DRIFTING PASSED SET LOWER BLOCK LIMITS. PERFORMED TESTS, OBSERVED LEAKING BRAKE SEAL ON SERVICE BRAKE #2. SUSPENDED OPERATIONS, PROCEED TO FIX LEAKING SEAL. | UPRA | DWKS | 901163 | 09/07/2022 | ENS-108 | 24 | ZULF-2015
726 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | EXL-IA | Hrs | SFNY-1790
727 | FCLK | ARM | 48 | 06 Sep 0500 - 0500 | 7495 | 901855 | OBSERVED BUBBLES COMMING FROM 30" CONDUCTOR AFTER FINAL CUT AND MEASUREMENT BUY DIVERS. MONITOR WELL @ CASING CUT OFF ABOVE SEABED | TF | CSG |  | 09/07/2022 | EXL-IA | 24 | SFNY-1790
728 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | EXL-IVA | Hrs | ZULF-2041
729 | GRF | RIG | 84.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/07/2022 | EXL-IVA | 24 | ZULF-2041
730 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | HI-5 | Hrs | MHRH-57
731 | FOT | NNN | 18.5 | 07 Sep 1030 - 0500 | 10512 | 901822 | WHILE DRILLING, HAD SUDDEN DROP IN ROP. ATTEMPT TO CHANGE DRILLING PARAMETERS. NO PROGRESS. SWEEP HOLE. CHC. POH. FOUND NEO-TORK FAILURE. | BHA | AST |  | 09/07/2022 | HI-5 | 18.5 | MHRH-57
732 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | JACK-203 | Hrs | HZEM-849
733 | FPMP | RIG | 4.5 | 07 Sep 0030 - 0500 | 5785 | 901826 | ROTARY HOSE LEAK. | RR | MPMP |  | 09/07/2022 | JACK-203 | 4.5 | HZEM-849
734 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | NA-393S | Hrs | SDGM-1134
735 | XWSW | SAM | 88.75 | 02 Sep 0130 - 0900 | 13227 | 901678 | SAMMA PACKER RUBBER ELEMENT LOST IN HOLE. | TF | WBCL |  | 09/07/2022 | NA-393S | 4 | SDGM-1134
736 | XTRI | RIG | 2 | 07 Sep 2315 - 0115 | 4822 | 901892 | EXCESSIVE TIME TO PICK UP BHA, | JF | NA |  | 09/07/2022 | NBR-20S | 2 | HMYM-433512
737 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | NBR-20S | Hrs | HMYM-433512
738 | HERR | RIG | 2.75 | 07 Sep 0615 - 0900 | 4822 | 901817 | EXCESSIVE TIME TO NIPPLE UP BOPE. | JF | RWCS |  | 09/07/2022 | NBR-20S | 2.75 | HMYM-433512
739 | XTRI | RIG | 2 | 07 Sep 2315 - 0115 | 4822 | 901892 | EXCESSIVE TIME TO PICK UP BHA, | JF | NA |  | 09/07/2022 | NBR-20S | 2 | HMYM-433512
740 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | PA-529S | Hrs | SHYB-523
741 | FOT | ARM | 85.25 | 04 Sep 1545 - 0500 | 4029 | 901687 | RIH WITH BAKER ESP COMPLETION WITH PDHMS HAD OBSTRUCTION @ 4029'. (BAKER 7" OCTOPUS PACKER DETH @ 3828', SAME DEPTH AS 7" TOL) ATTEMPT TO PASS SAME WITH 5 KLB S/O WT IN PRESENCE OF BAKER PACKER ENGINEER, NO SUCCESS. | JF | GP |  | 09/07/2022 | PA-529S | 24 | SHYB-523
742 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | PN-9 | Hrs | MRJN-673
743 | FOT | BHI | 94.25 | 03 Sep 2130 - 0500 | 13460 | 901712 | AFTER POH WITH 8-1/2" BHI MOTORIZED RSS BHA, FOUND ONE FLANGE THAT COVERS THE HYDRAULIC UNIT AND STEERING PAD ON THE RSS IS MISSING ALONG WITH SOME OF THE SCREWS THAT HOLDS THIS PIECE IN PLACE | BHA | RSS |  | 09/07/2022 | PN-9 | 22.25 | MRJN-673
744 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SINO-1L | Hrs | ABJF-260
745 | FOT | BAL | 99 | 03 Sep 0200 - 0500 | 4718 | 901697 | FAILURE OF BAKER ESP PUMP TO OPERATE AFTER INSTALLING IT, RETRIEVED COMPLETION ASSY. , FOUND WRONG SHAFT COUPLING INSTALLED INSIDE ESP MOTOR. | TF | ESP |  | 09/07/2022 | SINO-1L | 24 | ABJF-260
746 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SINO-22 | Hrs | BRRI-1144
747 | UNKN | RIG | 1 | 07 Sep 2100 - 2200 | 3198 | 901819 | HOLD STAND DOWN MEETING AND DISCUSS INCIDENT HAPPEND WITH ONE CREW MEMBER WHILE PREPARING RIG FLOOR FOR CEMENTING OPERATION. | HSEI | NA |  | 09/07/2022 | SINO-22 | 1 | BRRI-1144
748 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SINO-26 | Hrs | UTMN-1312
749 | FOT | HWP | 1.5 | 07 Sep 0530 - 0700 | 6900 | 901827 | TROUBLSHOOTING ON LOGGING UNIT. | TF | WLU |  | 09/07/2022 | SINO-26 | 1.5 | UTMN-1312
750 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SINO-33L | Hrs | HRDH-1542
751 | GRF | RIG | 122 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/07/2022 | SINO-33L | 24 | HRDH-1542
752 |  | 901716 | HWP | OTH |  | 5163 | P/U & M/U HLB W/L LOGGING TOOLS RUN #5: RDT-GR (FORMATION SAMPLING).** 01 PROBE -SAMPLE VIEW, FLUID IDENTIFIER, 2XPUMPS, 4 CARRIERS (10 TANK, 2 FILTER), STRADDLE PKR'S (02 EA)-GR.** PERFORM SURFACE FUNCTION CHECKS AND TOOL CALIBRATION ON SURFACE BEFORE RIH, OK.** TOTAL LOGGING TOOL LENGTH: 144.69', WT: 4.900 LB & MAX OD: 7".** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. |  | TF | 5163 | 09/07/2022 | SINO-46L | NA | SHYB-270
753 |  | 901716 | HWP | OTH |  | 5163 | HPJSM, RIH WL RUN#5 LOGGING TOOLS (RDT-GR) ON 5" DRIFTED DP STDS WITH CONTROL SPEED TO 4512'. ** FILL STRING EVERY 10 STDS & BREAK CIRC.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. |  | TF | 5163 | 09/07/2022 | SINO-46L | NA | SHYB-270
754 |  | 901716 | HWP | OTH |  | 5163 | HPJSM, PU & MU WL SIDE ENTRY SUB (SES).** MONITOR WELL ON TRIP TANK. |  | TF | 5163 | 09/07/2022 | SINO-46L | NA | SHYB-270
755 |  |  | HWP | OTH | 4545 | 5163 | RIH W/ PUMP DOWN HEAD ON W/L CABLE TILL LATCH PWCH INTO THE DOCKING HEAD @ 4368'.** MONITOR WELL ON TRIP TANK.** BOTTOM OF STRING @ 4512 FT.** PUMP DOWN STRING GRADUALLY TO 500 GPM, 1000 PSI.** LATCH PWCH INTO DOCKING HEAD & CONFIRM SAME WITH GOOD SIGNAL.** INSTALL CABLE CLAMP AND PERFORM PULL TEST (5 KLBS / 5 MIN), OK.** FUNCTION TEST ON W/L TOOLS, OK. |  |  | 5163 | 09/07/2022 | SINO-46L | NA | SHYB-270
756 |  |  | HWP | OTH | 4545 | 5163 | HPJSM, RIH RDT LOG TOOLS TO 5156', CORRELATION PATH F/ 4528' TO 5118'.** MONITORING WELL ON TRIP TANK .** OPEN HOLE IN GOOD CONDITION.** RUNNING SPEED = 5 MIN/ STDS. |  |  | 5163 | 09/07/2022 | SINO-46L | NA | SHYB-270
757 |  |  | HWP | OTH | 4545 | 5163 | POSITION STRING @ 1ST SAMPLE POINT @ 5118',(STATION#1 SAMPLING POINT), PERFORM STICKY TENDENCY TEST FOR 15 MNS, 30 MNS AND 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. |  |  | 5163 | 09/07/2022 | SINO-46L | NA | SHYB-270
758 | 5050 |  | HWP | LOG | 4545 | 5163 | STATION#1 @ 1ST SAMPLE POINT@ 5118' (BAYADHA).** TRIED WITH PROBE , LOW MOBILITY.** ACTIVATED STRADDLE PKR'S & PUMP OUT STATION#1 @ 5118'.** PUMP OUT 420 LITRES OF FORMATION WATER, TAKE 1 BOTTLE OF 921 CC FLUID SAMPLE WATER. ** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 2.64 BBLS (WATER: 2.64 BBLS - OIL: 0 BBLS).** DEACTIVATE STRADDLE PKR'S , MOVED UP, OBSERVED 20 KLB OVERPULL THEN FREE. | 5050 |  | 5163 | 09/07/2022 | SINO-46L | WLT | SHYB-270
759 |  |  | HWP | OTH | 4545 | 5163 | POOH W/ LOG TOOLS & POSITION STRING @ 5078' (STATION#2 SAMPLING POINT),PERFORM STICKY TENDENCY TEST FOR 15 MIN, 30 MIN 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. |  |  | 5163 | 09/07/2022 | SINO-46L | NA | SHYB-270
760 | 5118 |  | HWP | LOG | 4545 | 5163 | STATION#2 @ 2ND SAMPLE POINT@ 5078' (BAYADHA)---ONGOING.** 15.5 HRS SINCE LAST CIRCUATION @ LATCH DEPTH.** 39 HRS SINCE LAST CIRCULATION W/ REAMING BHA AT BTM.** 0.75 HR SINCE LAST STICKY TEST. | 5118 |  | 5163 | 09/07/2022 | SINO-46L | WLT | SHYB-270
761 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SINO-46L | Hrs | SHYB-270
762 | FOT | BAW | 74.5 | 04 Sep 1300 - 1530 | 4528 | 901716 | RIH W/ PUMP DOWN HEAD ON W/L CABLE ATTEMPTED TO LATCH PWCH INTO THE DOCKING HEAD WITOUT SUCCESS (PARTIAL LATCH). | TF | WLT |  | 09/07/2022 | SINO-46L | 10.5 | SHYB-270
763 | 71 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #4 (FTEX -GR), RUN #5 (RDT -GR). | 13.5 | 4545 | 01 Sep 0800 | 09/07/2022 | SINO-46L | Type | SHYB-270
764
765
766 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SINO-47 | Hrs | HWYH-1341
767 | FOT | WDV | 35 | 05 Sep 1800 - 0500 | 11139 | 901756 | WEATHERFORD DV FAILED. | TF | DV |  | 09/07/2022 | SINO-47 | 11 | HWYH-1341
768 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SND-2001 | Hrs | HWYH-1229
769 | FOT | RIG | 13.25 | 07 Sep 1130 - 0045 | 5175 | 901859 | HANDLER LOCK ON TDS WILL NOT ENGAGE. THIS COULD CAUSE UNWANTED ROTATION OF TOP DRIVE. | RR | TDS |  | 09/07/2022 | SND-2001 | 13.25 | HWYH-1229
770 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SP-106 | Hrs | THRY-831
771 | HERR | RIG | 7.75 | 07 Sep 0515 - 1300 | 2564 | 901858 | AFTER P/U KELLY AND START CIRCULATION, THE PRESSURE INCREASED AND CONTINUE INCREASING, STOP THE PUMP AND POOH TO CHECK THE BIT NOZZLES. ** FOUND TOTCO SEAT PLUGGED BY FIBER (LCM). | BB | BIT |  | 09/07/2022 | SP-106 | 7.75 | THRY-831
772 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SP-121 | Hrs | BRRI-522
773 | OTH | RIG | 115 | 02 Sep 1600 - 0500 | 14529 | 901642 | HELD STAND DOWN MEETING WITH CREW AND DISCUSSED THE FINGER PINCHED INCIDENT - SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION BY DOE&CD. | UPRA | NA |  | 09/07/2022 | SP-121 | 24 | BRRI-522
774 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SSA-5892 | Hrs | AWTD-141400
775 | FOT | RIG | 305.25 | 25 Aug 1330 - 0100 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 09/07/2022 | SSA-5892 | 20 | AWTD-141400
776 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | SSA-5970 | Hrs | UTMN-2340
777 | XTTE | SAM | 29 | 06 Sep 0000 - 0500 | 13703 | 901834 | WHILE PERFORMING NEGATIVE TEST SAMAA PACKER FAILED. | TF | WBCL |  | 09/07/2022 | SSA-5970 | 24 | UTMN-2340
778 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/07/2022 | T901 | Hrs | JLMN-60
779 | FOT | RIG | 83.5 | 04 Sep 1015 - 0500 | 0 | 901710 | WHILE BREAKING OUT CRT FROM SAVER SUB, THE TDS GRAPPLES WERE NOT HOLDING THE CRT, WHICH LEAD THE CRT TO ROTATE, MEANWHILE THE CRT GRAPPLE DIES BEING UNDERNEATH ROTARY TABLE WERE CAUGHT BY THE EDGE OF INTERNAL FACE OF MASTER BUSHING. RESULTED IN 1 PIECE OF GRAPPLE DIES BROKE AND FELL DOWN. | TF | CRT |  | 09/07/2022 | T901 | 18 | JLMN-60
780 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | 088TE | Hrs | QTIF-519
781 | OTH | RIG | 16 | 08 Sep 1300 - 0500 | 5117 | 901934 | ROUSTABOUT PUSHER LEFT HAND FINGER PINCHED BETWEEN CATWALK AND THE DRILL PIPE. HELD SAFETY STAND DOWN MEETING, SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION. | UPRA | NA |  | 09/08/2022 | 088TE | 16 | QTIF-519
782 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADC-21 | Hrs | MHWZ-991100
783 | UNKN | RIG | 185.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/08/2022 | ADC-21 | 24 | MHWZ-991100
784 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADC-42L | Hrs | SDGM-1258
785 | FOT | RIG | 1.5 | 08 Sep 0015 - 0145 | 15570 | 901941 | WHILE PERFORMING BOP P/T, HIGH PRESSURE WATER SUPPLY HOSE FROM TEST UNIT START LEAKING | TF | TESTT |  | 09/08/2022 | ADC-42L | 1.5 | SDGM-1258
786 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADC-50 | Hrs | SFNY-1176
787 | FOT | SDM | .75 | 08 Sep 0415 - 0500 | 6309 | 901953 | WHILE DRILLING 8 3/8" SECTION WITH SLB RSS BHA ASSY, LOST GR SIGNAL AT 6309'. | SURV | MS |  | 09/08/2022 | ADC-50 | .75 | SFNY-1176
788 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADC-55L | Hrs | UTMN-3171
789 | STBH | TK3 | 710.5 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/08/2022 | ADC-55L | 24 | UTMN-3171
790 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADC-65L | Hrs | HWYH-1299
791 | FOT | RIG | 23 | 08 Sep 0500 - 0500 | 14079 | 901937 | NOTICED LEAK ON CONNECTION B/T DSA 11'' 10K X 13 5/8'' 10K TO LOWER DOUBLE RAM BOP WHILE TESTING 4" RAM | BOP | BOP |  | 09/08/2022 | ADC-65L | 23 | HWYH-1299
792 | 10376 |  | CIRC | N |  | MPMP | FLOW CHECK, WELL STATIC. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
793 | 10376 |  | HT | N |  | STRG | POOH IN OPEN HOLE W/ 8-1/2" DIR BHA FOR WIPER TRIP F/ 10,376 FT TO 6,487 FT. OBSERVED TIGHT SPOT AT THIS DEPTH. - MONITOR THE WELL WITH TRIP TANK. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
794 | 10376 | 6358 | BR | N |  | STRG | ATTEMPTED TO PASS WITH RECIPROCATION AND WASHING UP WITHOUT SUCCESS. SOFT BACKREAMED INTERVAL FROM 6,487 FT TO 9 5/8" SHOE AT 6358 FT. CONFIRMED FREE PASS ON ELEVATOR. | 10376 | 6487 | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
795 | 10376 |  | CIRC | N |  | MPMP | CIRCULATED 1 BOTTOM UP AT SHOE. FLOW CHECK, WELL STATIC. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
796 | 10376 |  | HT | N |  | STRG | RIH W/ 8-1/2" DIR BHA IN OPEN HOLE ON ELEVATORS F/ 6,300 FT TO BOTTOM AT 10,376 FT.- HOLE IN GOOD CONDITION.- PRECAUTIONARY WASH/REAM DOWN LAST 2 STANDS TO BTM.- MONITOR THE WELL WITH TRIP TANK. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
797 | 10376 |  | CIRC | N |  | MPMP | CIRCULATE HOLE CLEAN W/ 2 X FULL CYCLES.- PUMP 30 BBLS HI-VIS EVERY CYCLE- REAM UP/DOWN FULL STAND.- SPOT 300 BBL OF LOW CHLORIDE PILL ON BOTTOM.- MW IN & OUT: 75 PCF, NO DOWNHOLE LOSSES.- RECORDED SCR'S. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
798 | 10376 |  | CIRC | N |  | MPMP | FLOW CHECK, WELL STATIC. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
799 | 10376 |  | HT | N |  | STRG | POOH IN OPEN HOLE W/ 8-1/2" DIR BHA F/ 10,376 FT TO 6,300 FT (INSIDE 9-5/8" CSG SHOE).- FLOW CHECK AFTER 5 STDS, WELL STATIC.- POOH FREE ON ELEVATORS, HOLE IN GOOD CONDITIONS.- MONITOR THE WELL WITH TRIP TANK. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
800 | 10376 |  | CIRC | N |  | MPMP | FLOW CHECK, WELL STATIC. PUMP SLUG & DROP DRIFT. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
801 | 10376 | 1300 | TO | N |  | STDP | CONTINUE POOH WITH 8 1/2" RSS BHA TO 1,300 FT- MONITOR WELL ON TRIP TANK, FILL UP TRIP SHEET. | 10376 | 6300 | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
802 | 10376 |  | CIRC | N |  | MPMP | FLOW CHECK, WELL STATIC | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
803 | 10376 |  | HT | N |  | BHA | POOH & L/D 8 1/2" RSS BHA. | 10376 |  | RIG | 09/08/2022 | ADC-68L | DRLG | FDHL-174
804 | 10376 |  | PJSM | E | 4627 | NA | HELD PRE-JOB SAFETY MEETING BEFORE RUNNING WIRELINE ON TLC.- DISCUSSED ABOUT WL OPERATION, MECHANICAL LIFTING, PINCH POINTS AND LINE OF FIRE.- ENSURE PROPER WARNING SIGNS AND BARRICADE AROUND RIG FLOOR AND CAT WALK AREA. | 10376 |  | RIG | 09/08/2022 | ADC-68L | LOG | FDHL-174
805 | 10376 |  | OTH | E | 4627 | NA | R/U WL ALL SURFACE RUNNING EQUIPMENT & P/U LOGGING TOOL RUN #1 ( AIT - MSIP - TLD - CNL- HNGS - CAL - GR) ON TLC. FUNCTION TESTED LOGGING TOOLS, OK.- TOOL LENGTH: 185.8 FT- MONITOR WELL THROUGH TT, WELL STATIC. | 10376 |  | SWL | 09/08/2022 | ADC-68L | LOG | FDHL-174
806 | 2 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1: QUAD COMBO ON TLC ( RESISTIVITY/ MSFL/ DENSITY/ NEUTRON/ GR). RUN#2: NMR LOG ON TLC. RUN#3: FORMATION PRESSURE AND SAMPLES ( RMD) ON TLC. | 2 | 4627 | 08 Sep 0300 | 09/08/2022 | ADC-68L | Type | FDHL-174
807
808
809 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADES-174 | Hrs | GHZL-72
810 | FOT | BFW | 10.75 | 08 Sep 1815 - 0500 | 11664 | 901936 | POH WITH BAKER 5-1/4'' PILOT MILL ASSY TO SURFACE. FOUND TAPER MILL LEFT IN HOLE. >LOST IN HOLE 1 X 3.7'' TAPER MILL 2.71' LENGHT. | BHA | MILL |  | 09/08/2022 | ADES-174 | 10.75 | GHZL-72
811 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADES-798 | Hrs | HRDH-2354
812 | FOT | RIG | 3.25 | 08 Sep 0145 - 0500 | 1269 | 901954 | TDS MALFUNCTION, TROUBLESHOOT ISSUE, FOUND BLOWER MOTOR CONTACTOR & WIRES FEEDER DAMAGED. | RR | TDS |  | 09/08/2022 | ADES-798 | 3.25 | HRDH-2354
813 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADM-339 | Hrs | MRJN-3013
814 | FOT | RIG | .5 | 08 Sep 0300 - 0330 | 5692 | 901948 | OBSERVED HYRAULIC LEAK IN THE TDS. | RR | TDS |  | 09/08/2022 | ADM-339 | .5 | MRJN-3013
815 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ADM-655 | Hrs | SFNY-183
816 | OTH | RIG | 264 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/08/2022 | ADM-655 | 24 | SFNY-183
817 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | DQ-49L | Hrs | HRDH-1541
818 | LHFL | RIG | 4.25 | 08 Sep 0600 - 1015 | 1184 | 901946 | OBSERVED HYDRAULIC OIL LEAK FROM TDS WHILE DRILLING 17" HOLE @ 1184 FT. | RR | HSYS |  | 09/08/2022 | DQ-49L | 4.25 | HRDH-1541
819 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | ENS-108 | Hrs | ZULF-2015
820 | GRF | RIG | 76.5 | 05 Sep 0030 - 0500 | 7186 | 901761 | DURING COMMISSIONING TESTS ON RIG POWER SYSTEM, OBSERVED THE BLOCKS DRIFTING PASSED SET LOWER BLOCK LIMITS. PERFORMED TESTS, OBSERVED LEAKING BRAKE SEAL ON SERVICE BRAKE #2. SUSPENDED OPERATIONS, PROCEED TO FIX LEAKING SEAL. | UPRA | DWKS | 901163 | 09/08/2022 | ENS-108 | 24 | ZULF-2015
821 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | EXL-IA | Hrs | SFNY-1790
822 | FCLK | ARM | 58.5 | 06 Sep 0500 - 1530 | 7495 | 901855 | OBSERVED BUBBLES COMMING FROM 30" CONDUCTOR AFTER FINAL CUT AND MEASUREMENT BUY DIVERS. MONITOR WELL @ CASING CUT OFF ABOVE SEABED | TF | CSG |  | 09/08/2022 | EXL-IA | 10.5 | SFNY-1790
823 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | EXL-IVA | Hrs | ZULF-2041
824 | GRF | RIG | 108.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/08/2022 | EXL-IVA | 24 | ZULF-2041
825 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | HI-4 | Hrs | BRRI-1001
826 | FOT | SDM | 2 | 08 Sep 0300 - 0500 | 14207 | 901939 | RSS POWER-DRIVE LOST SIGNAL. ATTEMPT TO RE-ESTABLISH AS PER SHORE BASE TECH SUPPORT WITH NO SUCCESS. ALL AGREED TO CONTINUE DRILLING 1/2 STAND WHILE STILL TROUBLE SHOOTING AT REDUCED PARAMETERS. NO SUCCESS. CHC, & POOH TO SWAP TOOLS. | BHA | RSS |  | 09/08/2022 | HI-4 | 2 | BRRI-1001
827 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | HI-5 | Hrs | MHRH-57
828 | FOT | NNN | 35 | 07 Sep 1030 - 2130 | 10512 | 901822 | WHILE DRILLING, HAD SUDDEN DROP IN ROP. ATTEMPT TO CHANGE DRILLING PARAMETERS. NO PROGRESS. SWEEP HOLE. CHC. POH. FOUND NEO-TORK FAILURE. | BHA | AST |  | 09/08/2022 | HI-5 | 16.5 | MHRH-57
829 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | JACK-203 | Hrs | HZEM-849
830 | FPMP | RIG | 12.5 | 07 Sep 0030 - 1300 | 5785 | 901826 | ROTARY HOSE LEAK. | RR | MPMP |  | 09/08/2022 | JACK-203 | 8 | HZEM-849
831 | FOT | SDM | 20.5 | 08 Sep 0700 - 0500 | 10699 | 901947 | SLB RSS DOES NOT RESPOND FOR DROPPING OR BUILDING. | BHA | RSS |  | 09/08/2022 | NBR-115S | 20.5 | SDGM-1221
832 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | NBR-115S | Hrs | SDGM-1221
833 | FOT | SAM | 1 | 08 Sep 2130 - 2230 | 10699 | 901945 | TEST PBL SUB WITHOUT SUCCESS (FAILED TO DEACTIVATE/CLOSE THE PORT). | TF | SCS |  | 09/08/2022 | NBR-115S | 1 | SDGM-1221
834 | FOT | SDM | 20.5 | 08 Sep 0700 - 0500 | 10699 | 901947 | SLB RSS DOES NOT RESPOND FOR DROPPING OR BUILDING. | BHA | RSS |  | 09/08/2022 | NBR-115S | 20.5 | SDGM-1221
835 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | NBR-20S | Hrs | HMYM-433512
836 | FOT | RIG | 1.25 | 08 Sep 0615 - 0730 | 4822 | 901829 | PRESSURE GAUGES ON REMOTE CHOKE PANEL NOT WORKING. | RR | CHK |  | 09/08/2022 | NBR-20S | 1.25 | HMYM-433512
837 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | PA-622S | Hrs | UTMN-3600
838 | UITE | SWL | 7 | 08 Sep 1315 - 2015 | 12803 | 901949 | CAN NOT PASS 4-1/2" TOL WITH LOGGING TOOLS HELD AT 12803' | JF | CBL |  | 09/08/2022 | PA-622S | 7 | UTMN-3600
839 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | PA-785S | Hrs | QTIF-269
840 | FOT | RIG | 2 | 08 Sep 2000 - 2200 | 17900 | 901935 | HYDRAULIC LEAK ON TDS ACTUATOR VALVE. | RR | TDS |  | 09/08/2022 | PA-785S | 2 | QTIF-269
841 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | PN-9 | Hrs | MRJN-673
842 | FOT | BHI | 115 | 03 Sep 2130 - 0130 | 13460 | 901712 | AFTER POH WITH 8-1/2" BHI MOTORIZED RSS BHA, FOUND ONE FLANGE THAT COVERS THE HYDRAULIC UNIT AND STEERING PAD ON THE RSS IS MISSING ALONG WITH SOME OF THE SCREWS THAT HOLDS THIS PIECE IN PLACE | BHA | RSS |  | 09/08/2022 | PN-9 | 20.5 | MRJN-673
843 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SINO-1L | Hrs | ABJF-260
844 | FOT | BAL | 123 | 03 Sep 0200 - 0500 | 4718 | 901697 | FAILURE OF BAKER ESP PUMP TO OPERATE AFTER INSTALLING IT, RETRIEVED COMPLETION ASSY. , FOUND WRONG SHAFT COUPLING INSTALLED INSIDE ESP MOTOR BY BAKER. | TF | ESP |  | 09/08/2022 | SINO-1L | 24 | ABJF-260
845 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SINO-33L | Hrs | HRDH-1542
846 | GRF | RIG | 146 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/08/2022 | SINO-33L | 24 | HRDH-1542
847 | 5163 | 5078 | LOG | E | 4545 | WLT | STATION#2 @ 2ND SAMPLE POINT@ 5078' (BAYADHA).** TRIED WITH PROBE , LOW MOBILITY.** ACTIVATED STRADDLE PKR'S & PUMP OUT STATION#2 @ 5078'.** COULDN'T PUMP OUT. ** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 2.64 BBLS (WATER: 2.64 BBLS - OIL: 0 BBLS).** DEACTIVATE STRADDLE PKR'S , MOVED UP, OBSERVED 9 KLB OVERPULL THEN FREE. | 5163 | 5078 | HWP | 09/08/2022 | SINO-46L | LOG | SHYB-270
848 | 5163 |  | OTH | E | 4545 | NA | POOH W/ LOG TOOLS & POSITION STRING @ 5066' (STATION#3 SAMPLING POINT),PERFORM STICKY TENDENCY TEST FOR 15 MIN, 30 MIN 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 5163 |  | HWP | 09/08/2022 | SINO-46L | LOG | SHYB-270
849 | 5163 | 5066 | LOG | E | 4545 | WLT | STATION#3 @ 3RD SAMPLE POINT@ 5066' (BAYADHA).** TRIED WITH PROBE , LOW MOBILITY.** ACTIVATED STRADDLE PKR'S & PUMP OUT STATION#3 @ 5066'.** PUMP OUT 50 LITRES OF FORMATION OIL. ** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 2.95 BBLS (WATER: 2.64 BBLS - OIL: 0.31 BBLS).** DEACTIVATE STRADDLE PKR'S, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 5066 | HWP | 09/08/2022 | SINO-46L | LOG | SHYB-270
850 | 5163 | 5066 | LOG | E | 4545 | WLT | STATION#3 @ 3RD SAMPLE POINT@ 5066' (BAYADHA).** ACTIVATED STRADDLE PKR'S & PUMP OUT STATION#3 @ 5066'.** CONT. PUMP STATION#3, PUMP OUT 55 LITRES OF FORMATION OIL, TAKE 1 BOTTLE OF 597 CC FLUID SAMPLE WATER. ** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 3.30 BBLS (WATER: 2.64 BBLS - OIL: 0.66 BBLS).** DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 5066 | HWP | 09/08/2022 | SINO-46L | LOG | SHYB-270
851 | 5163 |  | OTH | E | 4545 | NA | POOH W/ LOG TOOLS & POSITION STRING @ 5050' (STATION#4 SAMPLING POINT),** PERFORM STICKY TENDENCY TEST FOR 15 MIN, 30 MIN OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.** TRIED 3 TIMES WITH PROBE AT 3 POINTS, LOW MOBILITY.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 5163 |  | HWP | 09/08/2022 | SINO-46L | LOG | SHYB-270
852 | 5163 | 5050 | LOG | E | 4545 | WLT | STATION#4 (PUMP OUT/SAMPLE)@ 5050' (SHU'AIBA), CYCLE#1: ** ACTIVATED STRADEL PACKER & PUMP OUT STATION #4 @ 5050'.** PUMP OUT 169 LITRES (1.06 BBL) OF FORMATION MIX OF OIL AND WATER (MAINLY OIL), TAKE 1 BOTTLE OF 587 CC FLUID SAMPLE OIL. ** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE 4.39 BBLS (WATER: 2.46 BBLS - OIL: 1.72 BBLS)** DEACTIVATE STRADEL PACKER, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 5050 | HWP | 09/08/2022 | SINO-46L | LOG | SHYB-270
853 | 5163 | 5050 | LOG | E | 4545 | WLT | STATION#4 (PUMP OUT/SAMPLE)@ 5050' (SHU'AIBA), CYCLE#2: ** INFLATE STRADEL PACKER & PUMP OUT STATION #4 @ 5050'.** PUMP OUT 98 LITRES OF FORMATION MIX OF OIL AND WATER (MAINLY OIL). ** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE 4.98 BBLS (WATER: 2.46 BBLS - OIL: 2.52 BBLS)** DEACTIVATE STRADEL PACKER, MOVED FREELY, NO OVERPULL OBSERVED. ** 39.5 HRS SINCE LAST CIRCULATION @ LATCH DEPTH.** 63 HRS SINCE LAST CIRCULATION CONDITION TRIP BHA AT BTM. | 5163 | 5050 | HWP | 09/08/2022 | SINO-46L | LOG | SHYB-270
854 | 95 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #4 (FTEX -GR), RUN #5 (RDT -GR). | 24 | 4545 | 01 Sep 0800 | 09/08/2022 | SINO-46L | Type | SHYB-270
855
856
857 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SND-2001 | Hrs | HWYH-1229
858 | FOT | SDM | .5 | 08 Sep 0700 - 0730 | 5365 | 901912 | RELOG MISSED INTERVAL BY SLB MWD. | BHA | MWD |  | 09/08/2022 | SND-2001 | .5 | HWYH-1229
859 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SND-2007 | Hrs | AWTD-104001
860 | STBH | ARM | 32.75 | 06 Sep 2245 - 0500 | 18825 | 901814 | DURING REAMING DOWN OH WITH 5-7/8"X7" REAMER ASSY, PRESSURE SHOOT UP IN STRING & TDS STALL. WORK ON STRING WHILE TRANSMITTING TORQUE TO STRING. STRING 4" DP PIN THREAD SHEARED OFF. FISH LEFT IN HOLE. | STUK | UNDR |  | 09/08/2022 | SND-2007 | 10.5 | AWTD-104001
861 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SND-3001 | Hrs | SMNH-10
862 | FOT | RIG | 1.75 | 08 Sep 1230 - 1415 | 10579 | 901828 | TDS OBSERVED LEAKING HYDRAULIC OIL, INSPECT AND DISCOVER ISSUE WITH ACTUATOR, DECIDE TO REPLACE ACTUATOR | RR | TDS |  | 09/08/2022 | SND-3001 | 1.75 | SMNH-10
863 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SP-121 | Hrs | BRRI-522
864 | OTH | RIG | 139 | 02 Sep 1600 - 0500 | 14529 | 901642 | HELD STAND DOWN MEETING WITH CREW AND DISCUSSED THE FINGER PINCHED INCIDENT - SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION BY DOE&CD. | UPRA | NA |  | 09/08/2022 | SP-121 | 24 | BRRI-522
865 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SP-161 | Hrs | HRML-98
866 | FOT | GOC | 32.5 | 06 Sep 1500 - 0500 | 5480 | 901873 | CSG SLIPS JUMPED & CAME OUT OF ITS POSITION WHILE CLOSING WFD DV PORTS AFTER 2ND STAGE CMT JOB. | TF | CTRQ |  | 09/08/2022 | SP-161 | 19.5 | HRML-98
867 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SSA-201 | Hrs | MNHZ-1
868 | FOT | RIG | 1 | 08 Sep 1415 - 1515 | 9960 | 901942 | WHILE POOH WIH MILLIG BHA, THE DP SPINNER USED IN BREAKING OUT DRILL PIPE MALFUNTIONED AND THIS LED TO SLOW POOH AS THE RIG WORKED TO FIX IT. | RR | RSYS |  | 09/08/2022 | SSA-201 | 1 | MNHZ-1
869 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SSA-5962 | Hrs | HRDH-2513
870 | FOT | GOC | 4.25 | 08 Sep 0500 - 0915 | 8700 | 901932 | WHILE DRIFTING BY 3.795'' DRIFT NOT PASSING THROUGH COUPLING OF JOINT #200 & #201 (JOINT #201 OVER TORQUED) | TF | TTRQ |  | 09/08/2022 | SSA-5962 | 4.25 | HRDH-2513
871 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | SSA-5970 | Hrs | UTMN-2340
872 | XTTE | SAM | 33.5 | 06 Sep 0000 - 0930 | 13703 | 901834 | WHILE PERFORMING NEGATIVE TEST SAMAA PACKER FAILED. | TF | WBCL |  | 09/08/2022 | SSA-5970 | 4.5 | UTMN-2340
873 | FOT | RIG | 13.5 | 08 Sep 0800 - 2130 | 0 | 901940 | TOP OF ANNULAR ELEMENT DAMAGED. | BOP | BOP |  | 09/08/2022 | T901 | 13.5 | JLMN-60
874 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | T901 | Hrs | JLMN-60
875 | FOT | RIG | 86.5 | 04 Sep 1015 - 0800 | 0 | 901710 | WHILE BREAKING OUT CRT FROM SAVER SUB, THE TDS GRAPPLES WERE NOT HOLDING THE CRT, WHICH LEAD THE CRT TO ROTATE, MEANWHILE THE CRT GRAPPLE DIES BEING UNDERNEATH ROTARY TABLE WERE CAUGHT BY THE EDGE OF INTERNAL FACE OF MASTER BUSHING. RESULTED IN 1 PIECE OF GRAPPLE DIES BROKE AND FELL DOWN. | TF | CRT |  | 09/08/2022 | T901 | 3 | JLMN-60
876 | FOT | RIG | 13.5 | 08 Sep 0800 - 2130 | 0 | 901940 | TOP OF ANNULAR ELEMENT DAMAGED. | BOP | BOP |  | 09/08/2022 | T901 | 13.5 | JLMN-60
877 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | T914 | Hrs | UTMN-415
878 | FOT | HUD | 44 | 07 Sep 0900 - 0500 | 9000 | 901893 | HALLIBURTON MPD FLOAT VALVES IN THE DRILL STRING FAILED. | TF | MPD |  | 09/08/2022 | T914 | 24 | UTMN-415
879 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/08/2022 | V140A | Hrs | ZULF-654
880 | LHFL | RIG | 1.5 | 08 Sep 0130 - 0300 | 2100 | 901952 | OBSERVED LEAKING FITTING AT THE DIVERTER CONTROL SYSTEM. | BOP | RWCS |  | 09/08/2022 | V140A | 1.5 | ZULF-654
881 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | 088TE | Hrs | QTIF-519
882 | OTH | RIG | 19.5 | 08 Sep 1300 - 0830 | 5117 | 901934 | ROUSTABOUT PUSHER LEFT HAND FINGER PINCHED BETWEEN CATWALK AND THE DRILL PIPE. HELD SAFETY STAND DOWN MEETING, SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION. | UPRA | NA |  | 09/09/2022 | 088TE | 3.5 | QTIF-519
883 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | 095TE | Hrs | MNIF-126
884 | HERR | RIG | 13.5 | 05 Sep 1000 - 0500 | 9063 | 901754 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | FISH | STRG |  | 09/09/2022 | 095TE | 2.5 | MNIF-126
885 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADC-17 | Hrs | ZULF-1388
886 | FOT | RIG | 1.25 | 09 Sep 2330 - 0045 | 171 | 902003 | TOP DRIVE GRABBER BREAKDOWN, | RR | TDS |  | 09/09/2022 | ADC-17 | 1.25 | ZULF-1388
887 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADC-21 | Hrs | MHWZ-991100
888 | UNKN | RIG | 209.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/09/2022 | ADC-21 | 24 | MHWZ-991100
889 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADC-41L | Hrs | SDGM-1244
890 | LHFL | RIG | 3.75 | 09 Sep 1915 - 2300 | 10723 | 901958 | - REPLACE OIL PUMP AND OIL MOTOR IN TDS. - RE-FILL OIL AND FUNCTION TEST. | RR | HSYS |  | 09/09/2022 | ADC-41L | 3.75 | SDGM-1244
891 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADC-50 | Hrs | SFNY-1176
892 | FPMP | RIG | 3.5 | 09 Sep 1515 - 1845 | 6835 | 901981 | THE BLEED OFF VALVE OF MUD PUMP#2 FOUND WASHED OUT, ATTEMPTED TO ISOLATE MUD PUMP#2 AND OPERATE OTHER MUD PUMPS, FAILED TO OPERATE THE ISOLATION VALVE TO FULLY CLOSED POSITION CAUSING LEAK THROUGH MUD PUMP#2 BLEED OFF VALVE. | RR | MPMP |  | 09/09/2022 | ADC-50 | 3.5 | SFNY-1176
893 | FOT | WUD | 1 | 09 Sep 1930 - 2030 | 12155 | 901984 | WEATHERFORD MPD UNIT HAD MALFUNCTION OF HPU UNIT. | TF | MPD |  | 09/09/2022 | ADC-55L | 1 | UTMN-3171
894 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADC-55L | Hrs | UTMN-3171
895 | STBH | TK3 | 733.5 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/09/2022 | ADC-55L | 23 | UTMN-3171
896 | FOT | WUD | 1 | 09 Sep 1930 - 2030 | 12155 | 901984 | WEATHERFORD MPD UNIT HAD MALFUNCTION OF HPU UNIT. | TF | MPD |  | 09/09/2022 | ADC-55L | 1 | UTMN-3171
897 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADC-65L | Hrs | HWYH-1299
898 | FOT | RIG | 47 | 08 Sep 0500 - 0500 | 14079 | 901937 | NOTICED LEAK ON CONNECTION B/T DSA 11'' 10K X 13 5/8'' 10K TO LOWER DOUBLE RAM BOP WHILE TESTING 4" RAM | BOP | BOP |  | 09/09/2022 | ADC-65L | 24 | HWYH-1299
899 | 10376 |  | OTH | E | 4627 | NA | RIH TLC LOGGING TOOLS ON 5 STANDS OF 5" HWDP & 5" DP FROM 152 FT TO 6065 FT- RIH CONTROLLED SPEED, RIH SPEED: 3 MIN/STD.- FILL UP STRING EVERY 10 STANDS.- DRIFTED ALL STANDS RIH WITH 2.5" DRIFT. | 10376 |  | SWL | 09/09/2022 | ADC-68L | LOG | FDHL-174
900 | 10376 |  | CIRC | E | 4627 | MPMP | CIRCULATE 1.5 STRING VOLUME & SPOT 50 BBLS OF LOW CHLORIDE PILL ON TOP OF TLC LOGGING TOOLS.- MEANWHILE R/U WL SHEAVES & SECURE SAME.- HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW. | 10376 |  | RIG | 09/09/2022 | ADC-68L | LOG | FDHL-174
901 | 10376 |  | OTH | E | 4627 | NA | LATCH WIRELINE CABLE PWCH INTO DWCH @ 5925 FT AS PER WIRELINE ENGINEER INSTRUCTION.- FUNCTION TEST SLB TOOLS- PERFORM PULL TEST TO 3,200 LBS.- MONITORE WELL THROUGH TRIP TANK, WELL STATIC. | 10376 |  | SWL | 09/09/2022 | ADC-68L | LOG | FDHL-174
902 | 10376 |  | OTH | E | 4627 | NA | RIH TLC LOGGING TOOLS ON 5" DP FROM 5925 FT TO 10339 FT.- RIH SPEED: 3 MIN/STD.- MONITOR WELL ON TRIP TANK. | 10376 |  | SWL | 09/09/2022 | ADC-68L | LOG | FDHL-174
903 | 10376 | 6187 | LOG | E | 4627 | WLT | LOGGING UP TLC LOGGING RUN #1 ON 5" DP IN OPEN HOLE FROM 10337 FT TO 6187 FT.- MONITOR WELL ON TRIP TANK.- POOH SPEED: 3 MIN/STD | 10376 | 10337 | SWL | 09/09/2022 | ADC-68L | LOG | FDHL-174
904 | 10376 |  | OTH | E | 4627 | NA | WL ENGINEER PROCESSED DATA AND SENT TO TOWN FOR QC AND CONFIRMATION. - FLOW CHECK, WELL STATIC.- MONITOR WELL ON TRIP TANK. | 10376 |  | SWL | 09/09/2022 | ADC-68L | LOG | FDHL-174
905 | 26 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS | 24 | 4627 | 08 Sep 0300 | 09/09/2022 | ADC-68L | Type | FDHL-174
906
907
908 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADES-157 | Hrs | HRDH-1840
909 | FOT | ODJ | 2 | 09 Sep 0100 - 0300 | 105 | 901982 | POWER TONG NOT WORKING PROPERLY. | TF | CRT |  | 09/09/2022 | ADES-157 | 2 | HRDH-1840
910 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADES-174 | Hrs | GHZL-72
911 | FOT | BFW | 22.75 | 08 Sep 1815 - 1700 | 11664 | 901936 | POH WITH BAKER 5-1/4'' PILOT MILL ASSY TO SURFACE. FOUND TAPER MILL LEFT IN HOLE. >LOST IN HOLE 1 X 3.7'' TAPER MILL 2.71' LENGHT. | BHA | MILL |  | 09/09/2022 | ADES-174 | 12 | GHZL-72
912 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ADM-655 | Hrs | SFNY-183
913 | OTH | RIG | 288 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 09/09/2022 | ADM-655 | 24 | SFNY-183
914 | GRF | RIG | 91.5 | 05 Sep 0030 - 2000 | 7186 | 901761 | DURING COMMISSIONING TESTS ON RIG POWER SYSTEM, OBSERVED THE BLOCKS DRIFTING PASSED SET LOWER BLOCK LIMITS. PERFORMED TESTS, OBSERVED LEAKING BRAKE SEAL ON SERVICE BRAKE #2. SUSPENDED OPERATIONS, PROCEED TO FIX LEAKING SEAL. | UPRA | DWKS | 901163 | 09/09/2022 | ENS-108 | 15 | ZULF-2015
915 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ENS-108 | Hrs | ZULF-2015
916 | GRF | RIG | 432 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/09/2022 | ENS-108 | 9 | ZULF-2015
917 | GRF | RIG | 91.5 | 05 Sep 0030 - 2000 | 7186 | 901761 | DURING COMMISSIONING TESTS ON RIG POWER SYSTEM, OBSERVED THE BLOCKS DRIFTING PASSED SET LOWER BLOCK LIMITS. PERFORMED TESTS, OBSERVED LEAKING BRAKE SEAL ON SERVICE BRAKE #2. SUSPENDED OPERATIONS, PROCEED TO FIX LEAKING SEAL. | UPRA | DWKS | 901163 | 09/09/2022 | ENS-108 | 15 | ZULF-2015
918 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | ENSCO-76 | Hrs | MRJN-2004
919 | OTH | RIG | 2 | 09 Sep 0500 - 0700 | 17460 | 902019 | OBSERVED LEAKAGE IN WASHPIPE OF TOP DRIVE SYSTEM, CHANGED SAME | UPRA | NA |  | 09/09/2022 | ENSCO-76 | 2 | MRJN-2004
920 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | EXL-IVA | Hrs | ZULF-2041
921 | GRF | RIG | 132.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/09/2022 | EXL-IVA | 24 | ZULF-2041
922 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | HI-4 | Hrs | BRRI-1001
923 | FOT | SDM | 23.25 | 08 Sep 0300 - 0430 | 14207 | 901939 | RSS POWER-DRIVE LOST SIGNAL. ATTEMPT TO RE-ESTABLISH AS PER SHORE BASE TECH SUPPORT WITH NO SUCCESS. ALL AGREED TO CONTINUE DRILLING 1/2 STAND WHILE STILL TROUBLE SHOOTING AT REDUCED PARAMETERS. NO SUCCESS. CHC, & POOH TO SWAP TOOLS. | BHA | RSS |  | 09/09/2022 | HI-4 | 21.25 | BRRI-1001
924 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SINO-15L | Hrs | ANDR-311
925 | IDPR | SPS | 31.5 | 08 Sep 1700 - 0030 | 9385 | 901895 | UNABLE TO BUILD INCLINATION AS PER GOC INSTRUCTION & BHA TENDS TO DROP ANGLE | DD | RSS |  | 09/09/2022 | SINO-15L | 19.5 | ANDR-311
926 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SINO-25 | Hrs | MNIF-160
927 | FOT | GD1 | 13 | 09 Sep 1600 - 0500 | 6744 | 901978 | GDMC SL RIH & ATTEMPTED TO RTRV ME PLUG, SLICKLINE BROKE WITH NO OVERPULL WHILE P/U TO CHECK GS RTRV TOOL. LOST 500 FT OF SLICKLINE, SL TOOL STRING & GS TOOL ON TOP OF THE SET ME PLUG. | TF | SLICK |  | 09/09/2022 | SINO-25 | 13 | MNIF-160
928 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SINO-33L | Hrs | HRDH-1542
929 | GRF | RIG | 170 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/09/2022 | SINO-33L | 24 | HRDH-1542
930 | 5163 | 5155 | LOG | E | 4545 | WLT | RIH WITH LOGGING TOOL STRING TO 5155' (8' OFF BTM)** MONITOR WELL THRU TRIP TANK, STATIC. | 5163 | 5050 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
931 | 5163 |  | CIRC | E | 4545 | MPMP | CIRCULATE 50 BBL UNTIL GET FORMATION FLUID 4.98 BBL INSIDE 9-5/8" CSG SHOE. | 5163 |  | RIG | 09/09/2022 | SINO-46L | LOG | SHYB-270
932 | 5163 | 4512 | LOG | E | 4545 | WLT | POOH W/ HLB PCL LOGGING RUN#1: RDT-GR TO SES DEPTH @ 4512'. ** MONITOR WELL THRU TRIP TANK, STATIC. | 5163 | 5155 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
933 | 5163 |  | CIRC | E | 4545 | MPMP | CLOSED ANNULAR BOP & CIRCULATE THRU. CHOKE & MGS TO CONDITION MUD 1X CYCLE (INTERNAL+ANNULUS), +/-3.5 BPM, 190 PSI, MW IN/OUT=77 PCF (NORMAL MUD), OK. SICP & SIDPP = 0 PSI. ** MONITOR WELL THROUGH CHOKE WELL STATIC. | 5163 |  | RIG | 09/09/2022 | SINO-46L | LOG | SHYB-270
934 | 5163 | 5038 | LOG | E | 4545 | WLT | RIH PCL RUN#5 LOGGING TOOLS (RDT-GR) ON 5" DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED 2 MIN/STD SLIPS TO SLIPS TO 5038'.** MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC.** OPEN HOLE IN GOOD CONDITION. | 5163 | 4512 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
935 | 5163 | 5038 | LOG | E | 4545 | WLT | SCANNING AROUND THE STATION#5 (SAMPLE) @ 5038' (SHU'AIBA) FOR GOOD MOBILITY: ** CHECK MOBILITY WITH PROBE AT 5038', 5037' AND 5039' MEANWHILE PERFORM STCKY TEST NO STICKING TENDENCY NOR OVERPULL OBSERVED. | 5163 | 5038 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
936 | 5163 | 5039 | LOG | E | 4545 | WLT | POSITION STRING @ 5039', ACTIVATED STRADDEL PKR'S & PUMP OUT/SAMPLE STATION #5.** PUMP OUT 222 LITERS OF OIL (1.40 BBL), TAKE 1 BOTTLE OF 596 CC FLUID.** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 1.40 BBLS.** DEACTIVATE STRADDLE PKR'S, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 5039 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
937 | 5163 | 4965 | LOG | E | 4545 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 4965' (STATION#6: PUMPING OUT POINT).** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 5163 | 5039 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
938 | 5163 | 4965 | LOG | E | 4545 | WLT | SCANNING AROUND THE STATION#6 (SAMPLE) @ 4965' (SHU'AIBA) FOR GOOD MOBILITY: ** CHECK MOBILITY WITH PROBE AT 4965' AND PERFORM PRESSURE POINT MEANWHILE PERFORM STCKY TEST NO STICKING TENDENCY NOR OVERPULL OBSERVED. | 5163 | 4965 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
939 | 5163 | 4965 | LOG | E | 4545 | WLT | POSITION STRING @ 4965', ACTIVATED STRADDEL PKR'S & PUMP OUT/SAMPLE STATION #6.** PUMP OUT 183 LITERS OF OIL (1.15 BBL), TAKE 1 BOTTLE OF 423 CC FLUID.** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 2.45 BBLS.** DEACTIVATE STRADDLE PKR'S, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 4965 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
940 | 5163 | 4910 | LOG | E | 4545 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 4910' (STATION#7 SAMPLING POINT)** PERFORM STICKY TENDENCY TEST AS PER DE GUIDELINES (24 HRS AFTER LAST ONE) FOR 15 MIN, 30 MIN 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.** MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 5163 | 4965 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
941 | 5163 | 4910 | LOG | E | 4545 | WLT | POSITION STRING @ 4910', ACTIVATED STRADDEL PKR'S & PUMP OUT/SAMPLE STATION #7.** PUMP OUT 101 LITERS OF OIL (0.63 BBL), TAKE 1 BOTTLE OF 600 CC FLUID.** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 3.18 BBLS.** DEACTIVATE STRADDLE PKR'S, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 4910 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
942 | 5163 | 4865 | LOG | E | 4545 | WLT | SCANNING AROUND THE STATION#8 (SAMPLE) @ 4865' (SHU'AIBA) FOR GOOD MOBILITY: ............ONGOING** CHECK MOBILITY WITH PROBE AT 4865' AND PERFORM PRESSURE POINT MEANWHILE PERFORM STCKY TEST NO STICKING TENDENCY NOR OVERPULL OBSERVED.** 19 HRS SINCE LAST CIRCULATION. | 5163 | 4865 | HWP | 09/09/2022 | SINO-46L | LOG | SHYB-270
943 | 119 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #4 (FTEX -GR), RUN #5 (RDT -GR). | 24 | 4545 | 01 Sep 0800 | 09/09/2022 | SINO-46L | Type | SHYB-270
944
945
946 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SND-1501 | Hrs | HWYH-89
947 | FOT | SDM | 8.5 | 09 Sep 2030 - 0500 | 9411 | 902002 | SLB LWD FAILURE. | BHA | LWD |  | 09/09/2022 | SND-1501 | 8.5 | HWYH-89
948 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SND-3002 | Hrs | DMMM-828
949 | FOT | RIG | 3 | 09 Sep 0200 - 0500 | 3003 | 902001 | REPETITIVE TDS SHUTDOWN WHILE DRILL OUT CEMENT. | RR | TDS |  | 09/09/2022 | SND-3002 | 3 | DMMM-828
950 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SP-110 | Hrs | MNIF-142
951 | OTH | RIG | 192 | 02 Sep 0500 - 0500 | 0 | 902000 | EXCESS TIME TO CLOSE OUT OPEN ITEMS | UPRA | NA |  | 09/09/2022 | SP-110 | 24 | MNIF-142
952 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SP-120 | Hrs | MNIF-187
953 | FOT | BHI | 11 | 09 Sep 1800 - 0500 | 12645 | 901980 | RSS UNABLE TO STEER AND NO RESPONSE FROM RSS RIBS, TROUBLESHOOT WITHOUT SUCCESS. POOH TO CHANGE RSS TOOL. | BHA | RSS |  | 09/09/2022 | SP-120 | 11 | MNIF-187
954 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SP-121 | Hrs | BRRI-522
955 | OTH | RIG | 158.5 | 02 Sep 1600 - 0030 | 14529 | 901642 | HELD STAND DOWN MEETING WITH CREW AND DISCUSSED THE FINGER PINCHED INCIDENT - SHUT DOWN THE OPERATION AND CONDUCT INCIDENT INVESTIGATION BY DOE&CD. | UPRA | NA |  | 09/09/2022 | SP-121 | 19.5 | BRRI-522
956 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SP-161 | Hrs | HRML-98
957 | FOT | GOC | 56.5 | 06 Sep 1500 - 0500 | 5480 | 901873 | CSG SLIPS JUMPED & CAME OUT OF ITS POSITION WHILE CLOSING WFD DV PORTS AFTER 2ND STAGE CMT JOB. | TF | CTRQ |  | 09/09/2022 | SP-161 | 24 | HRML-98
958 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SSA-102 | Hrs | QTIF-693
959 | XTTE | NCT | 24 | 09 Sep 0500 - 0500 | 10300 | 901955 | EXCESS TIME FOR NESR MLT TO MAP L-1 | TF | CTBG |  | 09/09/2022 | SSA-102 | 24 | QTIF-693
960 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SSA-302 | Hrs | HRDH-2353
961 | FOT | RIG | 4 | 09 Sep 2100 - 0100 | 356 | 902004 | FOUND CRACKED BLOWER MOTOR FRAME. PIPE HANDLER CYLINDER SAFETY PIN WAS BROKEN. ACS ANTI8COLLISION SENSOR NOT WORKING. | RR | TDS |  | 09/09/2022 | SSA-302 | 4 | HRDH-2353
962 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/09/2022 | SSA-303 | Hrs | HRDH-2411
963 | FOT | RIG | 2 | 09 Sep 0915 - 1115 | 14802 | 901956 | OBSERVE LEAK ON MAIN RETURN HYDRAULIC HOSE ON TOP DRIVE TOP DRIVE DUE TO DAMAGED FITTING END. ALL HYDRAULIC FUNCTIONS LOST DUE TO LEAK. | RR | TDS |  | 09/09/2022 | SSA-303 | 2 | HRDH-2411
964 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | 088TE | Hrs | QTIF-519
965 | FOT | SDM | 10 | 10 Sep 1900 - 0500 | 5127 | 902021 | SDM MOTOR STALLED MANY TIMES, AFTER SEVERAL ATTEMPTS TO CIRCULATE AND ROTATE STRING WITHOUT SUCCESS TO GO DOWN. | BHA | MMOT |  | 09/10/2022 | 088TE | 10 | QTIF-519
966 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | 095TE | Hrs | MNIF-126
967 | HERR | RIG | 37 | 05 Sep 1000 - 0500 | 9063 | 901754 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | FISH | STRG |  | 09/10/2022 | 095TE | 23.5 | MNIF-126
968 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | ADC-21 | Hrs | MHWZ-991100
969 | UNKN | RIG | 233.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/10/2022 | ADC-21 | 24 | MHWZ-991100
970 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | ADC-34 | Hrs | UTMN-2309
971 | FOT | SPS | 14.5 | 10 Sep 1430 - 0500 | 10430 | 901959 | NO SIGNAL | BHA | MWD |  | 09/10/2022 | ADC-34 | 14.5 | UTMN-2309
972 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | ADC-36 | Hrs | SDGM-1194
973 | WC20 | ARM | 13.25 | 10 Sep 1015 - 2330 | 11167 | 901988 | WHILE DRILLING @ 11167, OBSERVED LEL LIGHT ACTIVATED @ 25%, SHUT-IN THE WELL & MOINTOR FOR PRESSURES STABLIZATION. | WCNT | NA |  | 09/10/2022 | ADC-36 | 13.25 | SDGM-1194
974 | FOT | WUD | 13.5 | 10 Sep 1530 - 0500 | 12269 | 902020 | LEAK ON RCD BEARING. | TF | MPD |  | 09/10/2022 | ADC-55L | 13.5 | UTMN-3171
975 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | ADC-55L | Hrs | UTMN-3171
976 | STBH | TK3 | 744 | 30 Jul 0830 - 1530 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/10/2022 | ADC-55L | 10.5 | UTMN-3171
977 | FOT | WUD | 13.5 | 10 Sep 1530 - 0500 | 12269 | 902020 | LEAK ON RCD BEARING. | TF | MPD |  | 09/10/2022 | ADC-55L | 13.5 | UTMN-3171
978 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | ADC-65L | Hrs | HWYH-1299
979 | FOT | RIG | 68 | 08 Sep 0500 - 0500 | 14079 | 901937 | NOTICED LEAK ON CONNECTION B/T DSA 11'' 10K X 13 5/8'' 10K TO LOWER DOUBLE RAM BOP WHILE TESTING 4" RAM | BOP | BOP |  | 09/10/2022 | ADC-65L | 21 | HWYH-1299
980 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | ENS-108 | Hrs | ZULF-2015
981 | GRF | RIG | 455 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/10/2022 | ENS-108 | 24 | ZULF-2015
982 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | EXL-IVA | Hrs | ZULF-2041
983 | GRF | RIG | 156.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/10/2022 | EXL-IVA | 24 | ZULF-2041
984 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | NBR-797S | Hrs | UTMN-3119
985 | FOT | SAM | 8 | 10 Sep 2100 - 0500 | 11834 | 902007 | SET FCS PACKER AS PER SAMAA ENGINEER. BLEED OFF PRESSURE THROUGH CHOKE @ 500PSI INCREMENTS, UNABLE TO BLEED OFF PRESSURE W/ PACKER SET, MUD LEVEL DROPPING IN THE BACKSIDE. SAMMA PACKER FAILED | BHA | WBCL |  | 09/10/2022 | NBR-797S | 8 | UTMN-3119
986 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | PA-218S | Hrs | HRDH-1976
987 | WOTO | RIG | 2 | 10 Sep 2300 - 0100 | 0 | 902022 | EXCESS TIME TO RIG UP SURFACE LINE | WO | NA |  | 09/10/2022 | PA-218S | 2 | HRDH-1976
988 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | PA-529S | Hrs | SHYB-523
989 | FOT | ARM | 157.25 | 04 Sep 1545 - 0500 | 4029 | 901687 | RIH WITH BAKER ESP COMPLETION WITH PDHMS HAD OBSTRUCTION @ 4029'. (BAKER 7" OCTOPUS PACKER DETH @ 3828', SAME DEPTH AS 7" TOL) ATTEMPT TO PASS SAME WITH 5 KLB S/O WT IN PRESENCE OF BAKER PACKER ENGINEER, NO SUCCESS. | JF | GP |  | 09/10/2022 | PA-529S | 24 | SHYB-523
990 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SINO-12L | Hrs | HWYH-518
991 | HERR | RIG | 23.5 | 10 Sep 0530 - 0500 | 250 | 901960 | DROPPED SHACKLE IN THE HOLE WHILE M/U 6-1/8" MM/MWD/LWD DIR DRILL ASSY. | FISH | STRG |  | 09/10/2022 | SINO-12L | 23.5 | HWYH-518
992 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SINO-1L | Hrs | ABJF-260
993 | FOT | BAL | 147.5 | 03 Sep 0200 - 0530 | 4718 | 901697 | FAILURE OF BAKER ESP PUMP TO OPERATE AFTER INSTALLING IT, RETRIEVED COMPLETION ASSY. , FOUND WRONG SHAFT COUPLING INSTALLED INSIDE ESP MOTOR BY BAKER. | TF | ESP |  | 09/10/2022 | SINO-1L | .5 | ABJF-260
994 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SINO-25 | Hrs | MNIF-160
995 | FOT | GD1 | 13 | 09 Sep 1700 - 0600 | 6744 | 901978 | GDMC SL RIH & ATTEMPTED TO RTRV ME PLUG, SLICKLINE BROKE WITH NO OVERPULL WHILE P/U TO CHECK GS RTRV TOOL. LOST 500 FT OF SLICKLINE, SL TOOL STRING & GS TOOL ON TOP OF THE SET ME PLUG. | TF | SLICK |  | 09/10/2022 | SINO-25 | 1 | MNIF-160
996 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SINO-33L | Hrs | HRDH-1542
997 | GRF | RIG | 194 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/10/2022 | SINO-33L | 24 | HRDH-1542
998 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SINO-37L | Hrs | HWYH-114
999 | DSFT | HCM | 2.5 | 10 Sep 2230 - 0100 | 5960 | 902009 | EZSV-CR CEMENT RETAINER PLUG MOVED DOWNWARD FOR 15 FT. | JF | CHAMP |  | 09/10/2022 | SINO-37L | 2.5 | HWYH-114
1000 | 5163 | 4865 | LOG | E | 4545 | WLT | CONT. POSITION STRING @ 4865', ACTIVATED STRADDLE PKR'S & PUMP OUT (1ST CYCLE)/SAMPLE STATION #8.** PUMP OUT 62 LITERS OF OIL & GAS (0.39 BBL), TAKE 1 BACK UP BOTTLE OF 1000 CC FLUID.** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 3.57 BBLS.** DEACTIVATE STRADDLE PKR'S, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 4865 | HWP | 09/10/2022 | SINO-46L | LOG | SHYB-270
1001 | 5163 | 4865 | LOG | E | 4545 | WLT | POSITION STRING @ 4865', ACTIVATED STRADDLE PKR'S & PUMP OUT (2ND CYCLE)/SAMPLE STATION #8.** PUMP OUT 74 LITERS OF OIL & GAS (0.46 BBL), TAKE 1 BOTTLE OF 1000 CC FLUID.** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 4.04 BBLS.** DEACTIVATE STRADDLE PKR'S, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 4865 | HWP | 09/10/2022 | SINO-46L | LOG | SHYB-270
1002 | 5163 | 4808 | LOG | E | 4545 | WLT | SCANNING AROUND THE STATION#9 (SAMPLE) @ 4808' (SHU'AIBA) FOR GOOD MOBILITY: ** CORRELATION MEANWHILE DUMPING BACK UP SAMPLE OF PREVIOUS POINT.** CHECK MOBILITY WITH PROBE AT 4808'. | 5163 | 4808 | HWP | 09/10/2022 | SINO-46L | LOG | SHYB-270
1003 | 5163 | 4808 | LOG | E | 4545 | WLT | POSITION STRING @ 4808', ACTIVATED STRADDLE PKR'S & PUMP OUT (1ST CYCLE)/SAMPLE STATION #9.** PUMP OUT 67 LITERS OF OIL & GAS (0.42 BBL).** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 4.46 BBLS.** DEACTIVATE STRADDLE PKR'S, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 4808 | HWP | 09/10/2022 | SINO-46L | LOG | SHYB-270
1004 | 5163 | 4808 | LOG | E | 4545 | WLT | POSITION STRING @ 4808', ACTIVATED STRADDLE PKR'S & PUMP OUT (2ND CYCLE)/SAMPLE STATION #9.** PUMP OUT 195 LITERS OF GAS (1.23 BBL), TAKE 1 BOTTLE OF 1000 CC GAS.** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 5.69 BBLS.** DEACTIVATE STRADDLE PKR'S, MOVED FREELY, NO OVERPULL OBSERVED. | 5163 | 4808 | HWP | 09/10/2022 | SINO-46L | LOG | SHYB-270
1005 | 5163 |  | CIRC | E | 4545 | MPMP | HPJSM, RIH WITH LOGGING TOOL STRING TO 5155' (8' OFF BTM)** MONITOR WELL THRU TRIP TANK, STATIC. | 5163 |  | RIG | 09/10/2022 | SINO-46L | LOG | SHYB-270
1006 | 5163 |  | CIRC | E | 4545 | MPMP | CIRCULATE 50 BBL UNTIL GET FORMATION FLUID 5.69 BBL INSIDE 9-5/8" CSG SHOE.** IGNITE FLARE BEFORE START CIRCULATION. | 5163 |  | RIG | 09/10/2022 | SINO-46L | LOG | SHYB-270
1007 | 5163 |  | CIRC | E | 4545 | MPMP | HPJSM, POOH W/ HLB PCL LOGGING RUN#1: RDT-GR TO SES DEPTH @ 4512'. ** MONITOR WELL THRU TRIP TANK, STATIC. | 5163 |  | RIG | 09/10/2022 | SINO-46L | LOG | SHYB-270
1008 | 5163 |  | CIRC | E | 4545 | MPMP | HPJSM, CLOSED ANNULAR BOP & CIRCULATE THRU. CHOKE & MGS TO CONDITION MUD 1X CYCLE (INTERNAL+ANNULUS), +/-3 BPM, 200 PSI, MW IN/OUT=77 PCF (NORMAL MUD), OK. SICP & SIDPP = 0 PSI. ** GAS BURNED AT FLARE.** FLOW CHECK THROUGH CHOKE WELL STATIC.** OPEN ANNULAR AND PERFORM FLOW CHECK -STEADY LEVEL- | 5163 |  | RIG | 09/10/2022 | SINO-46L | LOG | SHYB-270
1009 | 5163 | 4650 | LOG | E | 4545 | WLT | RIH PCL RUN#5 LOGGING TOOLS (RDT-GR) ON 5" DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED 2 MIN/STD SLIPS TO SLIPS TO 4875'.** MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC.** OPEN HOLE IN GOOD CONDITION. | 5163 | 4512 | HWP | 09/10/2022 | SINO-46L | LOG | SHYB-270
1010 | 143 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #4 (FTEX -GR), RUN #5 (RDT -GR). | 24 | 4545 | 01 Sep 0800 | 09/10/2022 | SINO-46L | Type | SHYB-270
1011
1012
1013 | FOT | RIG | 1.5 | 10 Sep 0030 - 0200 | 6470 | 902008 | REPAIR MUD PUMP #1 | RR | MPMP |  | 09/10/2022 | SND-1501 | 1.5 | HWYH-89
1014 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SND-1501 | Hrs | HWYH-89
1015 | FOT | SDM | 31 | 09 Sep 2030 - 0500 | 9411 | 902002 | SLB LWD FAILURE. | BHA | LWD |  | 09/10/2022 | SND-1501 | 22.5 | HWYH-89
1016 | FOT | RIG | 1.5 | 10 Sep 0030 - 0200 | 6470 | 902008 | REPAIR MUD PUMP #1 | RR | MPMP |  | 09/10/2022 | SND-1501 | 1.5 | HWYH-89
1017 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SND-2008 | Hrs | HRDH-1291
1018 | SRVC | GEP | 2.5 | 10 Sep 0730 - 1000 | 0 | 901987 | WAIT ON GEP ENGINEER TO ARRIVE ON LOCATION TO PERFORM BONNET INETGRITY TEST | WO | NA |  | 09/10/2022 | SND-2008 | 2.5 | HRDH-1291
1019 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SND-3002 | Hrs | DMMM-828
1020 | FOT | RIG | 19 | 09 Sep 0200 - 2100 | 3003 | 902001 | REPETITIVE TDS SHUTDOWN WHILE DRILL OUT CEMENT. | RR | TDS |  | 09/10/2022 | SND-3002 | 16 | DMMM-828
1021 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SP-120 | Hrs | MNIF-187
1022 | FOT | BHI | 23 | 09 Sep 1800 - 1700 | 12645 | 901980 | RSS UNABLE TO STEER AND NO RESPONSE FROM RSS RIBS, TROUBLESHOOT WITHOUT SUCCESS. POOH TO CHANGE RSS TOOL. | BHA | RSS |  | 09/10/2022 | SP-120 | 12 | MNIF-187
1023 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SP-161 | Hrs | HRML-98
1024 | FOT | GOC | 80.5 | 06 Sep 1500 - 0500 | 5480 | 901873 | CSG SLIPS JUMPED & CAME OUT OF ITS POSITION WHILE CLOSING WFD DV PORTS AFTER 2ND STAGE CMT JOB. | TF | CTRQ |  | 09/10/2022 | SP-161 | 24 | HRML-98
1025 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SSA-102 | Hrs | QTIF-693
1026 | XTTE | NCT | 48 | 09 Sep 0500 - 0500 | 10300 | 901955 | EXCESS TIME FOR NESR MLT TO MAP L-1 | TF | CTBG |  | 09/10/2022 | SSA-102 | 24 | QTIF-693
1027 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | SSA-302 | Hrs | HRDH-2353
1028 | FOT | WCR | 3 | 10 Sep 0200 - 0500 | 0 | 901989 | WHILE RIG UP WFD CASING RUNNING EQUIPMENT, FOUND POWER TONG HYDRAULIC DOOR IS STUCK AND NOT FUNCTIONING. | TF | CTRQ |  | 09/10/2022 | SSA-302 | 3 | HRDH-2353
1029 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/10/2022 | V141A | Hrs | MRJN-3025
1030 | FOT | SCD | 2.5 | 10 Sep 1730 - 2000 | 1611 | 901961 | SCINETIFIC-GYRO LOSS SIGNAL | TF | GYRO |  | 09/10/2022 | V141A | 2.5 | MRJN-3025
1031 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | 088TE | Hrs | QTIF-519
1032 | FOT | SDM | 32.75 | 10 Sep 1900 - 0445 | 5127 | 902021 | SDM MOTOR STALLED MANY TIMES, AFTER SEVERAL ATTEMPTS TO CIRCULATE AND ROTATE STRING WITHOUT SUCCESS TO GO DOWN. | BHA | MMOT |  | 09/11/2022 | 088TE | 22.75 | QTIF-519
1033 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | 095TE | Hrs | MNIF-126
1034 | HERR | RIG | 60.5 | 05 Sep 1000 - 0500 | 9063 | 901754 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | FISH | STRG |  | 09/11/2022 | 095TE | 23.5 | MNIF-126
1035 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | ADC-21 | Hrs | MHWZ-991100
1036 | UNKN | RIG | 257.25 | 01 Sep 1145 - 0500 | 2077 | 901595 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | HSEI | NA |  | 09/11/2022 | ADC-21 | 24 | MHWZ-991100
1037 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | ADC-34 | Hrs | UTMN-2309
1038 | FOT | SPS | 27.5 | 10 Sep 1430 - 1800 | 10430 | 901959 | NO SIGNAL | BHA | MWD |  | 09/11/2022 | ADC-34 | 13 | UTMN-2309
1039 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | ADC-36 | Hrs | SDGM-1194
1040 | WC20 | ARM | 17.5 | 11 Sep 0530 - 2300 | 11212 | 902028 | WHILE DRILLING AT 11,212' OBSERVED INCREASED FLOW ON FLOW-OUT SENSOR & GOT 46 % LEL ALARM, SHUT-IN WELL, INITIAL SICP=740 PSI; MONITORED THE PRESSURE TILL STABILIZED AT 900 PSI, RECORDED SIDPP=550 PSI. KILLED WELL WITH 142 PCF OBM. | WCNT | NA |  | 09/11/2022 | ADC-36 | 17.5 | SDGM-1194
1041 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | ADC-49 | Hrs | HRDH-1934
1042 | HERR | RIG | 3 | 11 Sep 0900 - 1200 | 3297 | 902025 | CREW FAILED TO CORRECTLY LINE UP TO MUD PUMPS, ACTIVE TANK LEVEL DROPPED AND S.P.P DROPPED, UNABLE TO DRILL, TRIED TO TRANSFER MUD TO ACTIVE WITHOUT SUCCESS. POOH INSIDE CASING SHOE. | JF | CSYS |  | 09/11/2022 | ADC-49 | 3 | HRDH-1934
1043 | FOT | WUD | 22.5 | 10 Sep 1530 - 1500 | 12269 | 902020 | LEAK ON RCD BEARING. | TF | MPD |  | 09/11/2022 | ADC-55L | 9 | UTMN-3171
1044 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | ADC-55L | Hrs | UTMN-3171
1045 | STBH | TK3 | 759 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/11/2022 | ADC-55L | 15 | UTMN-3171
1046 | FOT | WUD | 22.5 | 10 Sep 1530 - 1500 | 12269 | 902020 | LEAK ON RCD BEARING. | TF | MPD |  | 09/11/2022 | ADC-55L | 9 | UTMN-3171
1047 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | ADM-657 | Hrs | SFNY-1228
1048 | FOT | KSC | 5 | 10 Sep 0430 - 0930 | 10193 | 901965 | ALKHORAYEF CHECK CABLE WITH MEGGER, READING BELOW LIMIT 330 MOHMS, AFTER INVESTIGATING KSC MEGGER FAULTY. CONTACTED ARAMCO FIELD SERVICES AND HAD THEM STOP BY PLATFORM TO PERFORM CHECK WITH THEIR MEGGER, GOOD READING 3.03 GOHMS. | TF | ESP |  | 09/11/2022 | ADM-657 | 4.5 | SFNY-1228
1049 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | ENS-108 | Hrs | ZULF-2015
1050 | GRF | RIG | 479 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/11/2022 | ENS-108 | 24 | ZULF-2015
1051 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | EXL-IVA | Hrs | ZULF-2041
1052 | GRF | RIG | 180.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/11/2022 | EXL-IVA | 24 | ZULF-2041
1053 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | NBR-797S | Hrs | UTMN-3119
1054 | FOT | SAM | 29 | 10 Sep 2100 - 0200 | 11834 | 902007 | SET FSC PACKER AS PER SAMAA ENGINEER. BLEED OFF PRESSURE THROUGH CHOKE @ 500PSI INCREMENTS, UNABLE TO BLEED OFF PRESSURE W/ PACKER SET, MUD LEVEL DROPPING IN THE BACKSIDE. SAMMA PACKER FAILED | BHA | WBCL |  | 09/11/2022 | NBR-797S | 21 | UTMN-3119
1055 | XTTE | BAL | 3 | 11 Sep 2030 - 2330 | 0 | 901969 | HAD SLACK IN ESP FLAT CABLE BELOW PKR WITH 4.2" OD AFTER SPLICE, BAKER ADJUST BANDING BELOW PKR AND REMOVE MOST OF THE SLACK IN ESP CABLE BELOW PKR | TF | PKR |  | 09/11/2022 | PA-529S | 3 | SHYB-523
1056 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | PA-529S | Hrs | SHYB-523
1057 | FOT | ARM | 178.25 | 04 Sep 1545 - 0500 | 4029 | 901687 | RIH WITH BAKER ESP COMPLETION WITH PDHMS HAD OBSTRUCTION @ 4029'. (BAKER 7" OCTOPUS PACKER DETH @ 3828', SAME DEPTH AS 7" TOL) ATTEMPT TO PASS SAME WITH 5 KLB S/O WT IN PRESENCE OF BAKER PACKER ENGINEER, NO SUCCESS. | JF | GP |  | 09/11/2022 | PA-529S | 21 | SHYB-523
1058 | XTTE | BAL | 3 | 11 Sep 2030 - 2330 | 0 | 901969 | HAD SLACK IN ESP FLAT CABLE BELOW PKR WITH 4.2" OD AFTER SPLICE, BAKER ADJUST BANDING BELOW PKR AND REMOVE MOST OF THE SLACK IN ESP CABLE BELOW PKR | TF | PKR |  | 09/11/2022 | PA-529S | 3 | SHYB-523
1059 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | PA-604S | Hrs | HRDH-2414
1060 | FOT | RIG | 13.75 | 11 Sep 1015 - 0000 | 5725 | 902031 | FLT VALVE FAILURE | BHA | FV |  | 09/11/2022 | PA-604S | 13.75 | HRDH-2414
1061 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | PA-622S | Hrs | UTMN-3600
1062 | UITE | HWP | 8 | 11 Sep 2100 - 0500 | 12803 | 902026 | ATTEMPTED 4 TIMES TO PASS THRU 4 1/2" LINER HGR (DIFFERENT SPEED, INCREASE SLACK-OFF) WITHOUT SUCCESS. | JF | CBL |  | 09/11/2022 | PA-622S | 8 | UTMN-3600
1063 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | PA-785S | Hrs | QTIF-269
1064 | UDWL | WDS | 44.5 | 09 Sep 1600 - 1230 | 13513 | 901968 | WFD FAILED TO INITIATE SIDE TRACK. | DD | RSS |  | 09/11/2022 | PA-785S | 7.5 | QTIF-269
1065 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SINO-12L | Hrs | HWYH-518
1066 | HERR | RIG | 47.5 | 10 Sep 0530 - 0500 | 250 | 901960 | DROPPED SHACKLE IN THE HOLE WHILE M/U 6-1/8" MM/MWD/LWD DIR DRILL ASSY. | FISH | STRG |  | 09/11/2022 | SINO-12L | 24 | HWYH-518
1067 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SINO-22 | Hrs | BRRI-1144
1068 | FOT | RIG | 4 | 11 Sep 0845 - 1245 | 3198 | 901966 | ZERO DISCHARGE SYSTEM MALFUNCTION DUE TO DIESEL PUMP SUCTION/DISCHARGE ISSUE, ATTEMPT TO FIX SAME WITHOUT SUCCESS, MEANWHILE REQUESTED NEW CELLAR JETTING PUMP FROM SINO YARD. INSTALLED NEW PUMP AND FUNCTION TEST, OK. | RR | CSYS |  | 09/11/2022 | SINO-22 | 4 | BRRI-1144
1069 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SINO-29N | Hrs | SFNY-2005
1070 | FOT | SWL | 6 | 11 Sep 2300 - 0500 | 7010 | 902059 | MANY TRIALS ATTEMED TO TROUBLE-SHOOT THE HIGH CURRENT FOR MDT LOGGING TOOL, NO SUCCESS. | TF | WLT |  | 09/11/2022 | SINO-29N | 6 | SFNY-2005
1071 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SINO-33L | Hrs | HRDH-1542
1072 | GRF | RIG | 218 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/11/2022 | SINO-33L | 24 | HRDH-1542
1073 | FOT | RIG | 1 | 11 Sep 1245 - 1345 | 8380 | 902060 | MUD PUMP# 2 FAILED DUE TO ELECTRICAL ISSUE. | RR | MPMP |  | 09/11/2022 | SND-1501 | 1 | HWYH-89
1074 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SND-1501 | Hrs | HWYH-89
1075 | FOT | SDM | 42.75 | 09 Sep 2030 - 2000 | 9411 | 902002 | SLB LWD FAILURE. | BHA | LWD |  | 09/11/2022 | SND-1501 | 11.75 | HWYH-89
1076 | FOT | RIG | 1 | 11 Sep 1245 - 1345 | 8380 | 902060 | MUD PUMP# 2 FAILED DUE TO ELECTRICAL ISSUE. | RR | MPMP |  | 09/11/2022 | SND-1501 | 1 | HWYH-89
1077 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SND-2004 | Hrs | BRRI-1148
1078 | FOT | RIG | 2 | 11 Sep 1830 - 2030 | 6150 | 902027 | TDS LUBRICATING PUMP FAILED. REPLACE IT WITH NEW ONE. | RR | TDS |  | 09/11/2022 | SND-2004 | 2 | BRRI-1148
1079 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SP-161 | Hrs | HRML-98
1080 | FOT | GOC | 89.5 | 06 Sep 1500 - 1400 | 5480 | 901873 | CSG SLIPS JUMPED & CAME OUT OF ITS POSITION WHILE CLOSING WFD DV PORTS AFTER 2ND STAGE CMT JOB. | TF | CTRQ |  | 09/11/2022 | SP-161 | 9 | HRML-98
1081 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SP-261 | Hrs | MHWZ-903
1082 | SRVC | GEP | 8.5 | 11 Sep 1715 - 0145 | 12605 | 901967 | WAIT ON BAKER WELL HEAD ENGINEER TO ARRIVE THE RIG SITE FOR RETRIEVING THE WEAR BUSHING AND M/U , INSTALL 5.5" TUBING HANGER ASSY. | WO | NA |  | 09/11/2022 | SP-261 | 8.5 | MHWZ-903
1083 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SSA-102 | Hrs | QTIF-693
1084 | XTTE | NCT | 72 | 09 Sep 0500 - 0500 | 10300 | 901955 | EXCESS TIME FOR NESR MLT TO MAP L-1 | TF | CTBG |  | 09/11/2022 | SSA-102 | 24 | QTIF-693
1085 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SSA-201 | Hrs | MNHZ-1
1086 | IDPR | SDM | 18.25 | 11 Sep 1045 - 0500 | 13448 | 902015 | SCHLUMBERGER MWD/RSS TOOL UNABLE TO SEND AND HOLD TELEMETERY COMMUNICATION. EXTENSIVE TROUBLE SHOOT CARRIED OUT WITH SUPPORT FROM BASE AND TOOL COMMUNICATION WAS SPORADIC AT BEST. | BHA | RSS | 901942 | 09/11/2022 | SSA-201 | 18.25 | MNHZ-1
1087 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SSA-29 | Hrs | QTIF-423
1088 | IDPR | WDS | 31 | 07 Sep 2230 - 1200 | 13020 | 902013 | EXCESSIVE TIME TO DRILL 6-1/8" L0-1. OFFSET WELLS AVERAGE ROP = 55 FT/HR | LROP | BHA |  | 09/11/2022 | SSA-29 | 4 | QTIF-423
1089 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SSA-302 | Hrs | HRDH-2353
1090 | FOT | RIG | 2 | 11 Sep 1230 - 1430 | 656 | 902014 | TOP DRIVE GRABBER NOT WORKING | RR | TDS |  | 09/11/2022 | SSA-302 | 2 | HRDH-2353
1091 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SSA-303 | Hrs | HRDH-2411
1092 | FOT | RIG | 2 | 11 Sep 0130 - 0330 | 14802 | 902029 | TDS LINK TILT STOP WORKING, TROUBLESHOOTING PROBLEM. | RR | TDS |  | 09/11/2022 | SSA-303 | 2 | HRDH-2411
1093 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SSA-51 | Hrs | BRRI-2050
1094 | OTH | RIG | 24 | 11 Sep 0500 - 0500 | 0 | 901963 | WORK ON RIG MOVE PERMISSIONS APPROVAL TO ABU ALI ISLAND. | UPRA | NA |  | 09/11/2022 | SSA-51 | 24 | BRRI-2050
1095 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SSA-5892 | Hrs | AWTD-141400
1096 | STDP | ARM | 12.5 | 11 Sep 1630 - 0500 | 14635 | 902030 | MOTOR DRILLING 8-3/8" SIDETRACK SECTION AND AFTER WORKING THE STRING. PICK UP 5FT OFF BOTTOM AND TAKE SURVEY. TURN ON PUMPS AND HAVE CIRCULATION BUT TURN ON ROTATION AND STRING IS STUCK | STUK | DP |  | 09/11/2022 | SSA-5892 | 12.5 | AWTD-141400
1097 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | SSA-5917 | Hrs | HRDH-2406
1098 | UXDF | ARM | .75 | 11 Sep 0415 - 0500 | 470 | 902032 | ATTEMPT TO REGAIN CIRCULATION WITH 1X LCM PILLS @100 PPB EACH. SPOT 1ST LCM PILL ON-BOTTOM. POOH TO THE SHOE, ALLOW SOAKING FOR 2 HOURS. | LCIR | NA |  | 09/11/2022 | SSA-5917 | .75 | HRDH-2406
1099 | PSSW | ARM | 2.75 | 11 Sep 2345 - 0500 | 6948 | 902061 | STUCK PIPE AFTER CONNECTION | STUK | NA |  | 09/11/2022 | T218 | 2.75 | HRDH-1511
1100 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | T218 | Hrs | HRDH-1511
1101 | FOT | RIG | 2.5 | 11 Sep 0200 - 0430 | 7045 | 901970 | STAND PIPE CONNECTION LEAKING | RR | CSYS |  | 09/11/2022 | T218 | 2.5 | HRDH-1511
1102 | PSSW | ARM | 2.75 | 11 Sep 2345 - 0500 | 6948 | 902061 | STUCK PIPE AFTER CONNECTION | STUK | NA |  | 09/11/2022 | T218 | 2.75 | HRDH-1511
1103 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/11/2022 | V140A | Hrs | ZULF-654
1104 | FOT | RIG | 2 | 11 Sep 1630 - 1830 | 4238 | 902056 | WHILE DOING CONNECTION USING PS-21 AUTO SLIPS, MALFUNCTIONED, UNABLE TO OPEN SAME. | TF | SLIPS |  | 09/11/2022 | V140A | 2 | ZULF-654
1105 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | 088TE | Hrs | QTIF-519
1106 | FOT | SDM | 40.5 | 10 Sep 1900 - 1245 | 5127 | 902021 | SDM MOTOR STALLED MANY TIMES, AFTER SEVERAL ATTEMPTS TO CIRCULATE AND ROTATE STRING WITHOUT SUCCESS TO GO DOWN. | BHA | MMOT |  | 09/12/2022 | 088TE | 7.75 | QTIF-519
1107 | HERR | RIG | 37.25 | 05 Sep 1000 - 1100 | 9063 | 901754 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | JF | CTRQ |  | 09/12/2022 | 095TE | 5 | MNIF-126
1108 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | 095TE | Hrs | MNIF-126
1109 | HERR | MSD | 41.25 | 04 Sep 2200 - 0700 | 9063 | 901659 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | TF | TTRQ |  | 09/12/2022 | 095TE | 1 | MNIF-126
1110 | HERR | RIG | 37.25 | 05 Sep 1000 - 1100 | 9063 | 901754 | WHILE R/U OF AL MASOOD CASING FILL UP TOOL A THREADED 1" X 12" BOLT WAS DROPPED IN THE HOLE. | JF | CTRQ |  | 09/12/2022 | 095TE | 5 | MNIF-126
1111 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ADC-21 | Hrs | MHWZ-991100
1112 | OTH | RIG | 24 | 12 Sep 0500 - 0500 | 2077 | 901973 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | UPRA | NA |  | 09/12/2022 | ADC-21 | 24 | MHWZ-991100
1113 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ADC-36 | Hrs | SDGM-1194
1114 | WC20 | ARM | 10 | 12 Sep 1900 - 0500 | 11474 | 902084 | STOP PUMP TO EVALUATE STATIC LOSSES @ 11474' WHILE DRILLING WITH 144 PCF OBM, OBSERVED WELL FLOW, SHUT IN THE WELL WITH 390 PSI SICP, CIRC OUT INFLUX WITH 144 PCF OBM. | WCNT | NA |  | 09/12/2022 | ADC-36 | 10 | SDGM-1194
1115 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ADC-53L | Hrs | HRDH-1530
1116 | OTH | RIG | 24 | 12 Sep 0500 - 0500 | 0 | 902098 | EXCEEDING PLANNED TIME FOR CAT IV & OVERHAULING MAINTENANCE. | UPRA | NA |  | 09/12/2022 | ADC-53L | 24 | HRDH-1530
1117 | FOT | WUD | 4.5 | 12 Sep 1100 - 1530 | 12486 | 902080 | FAILURE WITH WFD CORIOLIS FLOW METER. | TF | MPD |  | 09/12/2022 | ADC-55L | 4.5 | UTMN-3171
1118 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ADC-55L | Hrs | UTMN-3171
1119 | STBH | TK3 | 774.25 | 30 Jul 0830 - 0045 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 09/12/2022 | ADC-55L | 15.25 | UTMN-3171
1120 | FOT | WUD | 4.5 | 12 Sep 1100 - 1530 | 12486 | 902080 | FAILURE WITH WFD CORIOLIS FLOW METER. | TF | MPD |  | 09/12/2022 | ADC-55L | 4.5 | UTMN-3171
1121 | 10376 |  | OTH | E | 4627 | NA | POOH TLC LOGGING TOOLS FROM 1300 FT TO 58 FT,- POOH SPEED 2 MIN/STD SLIP TO SLIP.- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET. | 10376 |  | SWL | 09/12/2022 | ADC-68L | LOG | FDHL-174
1122 | 10376 |  | OTH | E | 4627 | NA | HELD PJSM, L/D SLB WL TLC RUN #2 TOOL STRING.- MONITOR THE WELL WITH TRIP TANK. | 10376 |  | SWL | 09/12/2022 | ADC-68L | LOG | FDHL-174
1123 | 10376 |  | PJSM | N | 4627 | NA | HELD PJSM PRIOR TO M/U 8-1/2" CONDITIONING BHA. | 10376 |  | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1124 | 10376 |  | HT | N | 4627 | BHA | P/U AND M/U 8-1/2" CONDITIONING BHA (SMITH MS616-C SN: SM2084 W/ 6X13 NOZZLES, BIT SUB WITH FV, 30 JOINTS 5HWDP, 6-1/2JAR, 6 JOINTS 5HWDP) AND RIH TO1,135 FT | 10376 |  | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1125 | 10376 | 6355 | TI | N | 4627 | STDP | RIH W/ 8-1/2" CONDITIONING BHA ON 5"DP FROM 1148 FT TO 6355 FT (9-5/8" CSG SHOE).- FILL THE STRING EVERY 20 STDS- MONITOR THE WELL WITH TRIP TANK | 10376 | 1148 | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1126 | 10376 |  | HT | N | 4627 | STRG | RIH W/ 8-1/2" CONDITIONING BHA ON 5"DP FROM 6355 FT TO 10,376 FT (BTM).- FILL THE STRING EVERY 20 STDS- WASH DOWN LAST 2 STD.- MONITOR THE WELL WITH TRIP TANK | 10376 |  | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1127 | 10376 |  | CIRC | N | 4627 | MPMP | SWEEP HOLE WITH 30 BBLS HI-VIS AND CIRC. TILL SHAKERS CLEAN.- NO DYNAMIC LOSSES.** CONDUCT MEETING TO REVIEW ARANGEMENT OF MUD TANKS. VERIFY LINE UP CORRECTLY. | 10376 |  | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1128 | 10376 |  | CIRC | N | 4627 | DSBT | DISPLACE WELLBORE FLUID TO 75 PCF OBM AND CIRCULATE TO CONDITION MUD.- NO DYNAMIC LOSSES. | 10376 |  | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1129 | 10376 |  | CIRC | N | 4627 | MPMP | CIRC TO CONDITION MUD, MWT-IN= MWT-OUT= 75 PCF,- NO LOSSES.- RECORD SCR AT THE END OF CIRC. | 10376 |  | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1130 | 10376 |  | CIRC | N | 4627 | MPMP | FLOW CHECK. - WELL STATIC. | 10376 |  | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1131 | 10376 |  | HT | N | 4627 | STRG | HELD PJSM, POOH ON ELEVATOR W/8-1/2" CONDITIONING BHA FROM 10,376 FT TO 6,262 FT (CSG SHOE).- PERFORM FLOW CHECK AFTER 5 STD, WELL STATIC.- HOLE IN GOOD CONDITION.- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET | 10376 |  | RIG | 09/12/2022 | ADC-68L | DRLG | FDHL-174
1132 | 98 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 24 | 4627 | 08 Sep 0300 | 09/12/2022 | ADC-68L | Type | FDHL-174
1133
1134
1135 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ADM-261 | Hrs | MRJN-24
1136 | FOT | NPC | 26.5 | 11 Sep 0230 - 0500 | 7893 | 901971 | LOST DRILLING TORQUE SUDDENLY WHILE DRILLING ONBOTTOM, UNABLE TO DRILL WITH MAX WOB. POH FOUND NEOTORQ TOOL FAILED. | BHA | SKSUB |  | 09/12/2022 | ADM-261 | 24 | MRJN-24
1137 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ADM-657 | Hrs | SFNY-1228
1138 | HERR | ARM | 29.5 | 11 Sep 2330 - 0500 | 4233 | 902063 | TIH W/ GS RETRIEVAL TOOL TO RETRIEVE SCHLUMBERGER M/E TUBING PLUG, UNABLE TO PASS 4220', M/U 2.5" / 3" SAND BAILERS & TIH W/SAME, UNABLE TO PASS 4227', M/E JUNK TRAPPER TOP @ 4233' | TF | TBG |  | 09/12/2022 | ADM-657 | 24 | SFNY-1228
1139 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | AOD-1 | Hrs | ZULF-690
1140 | FOT | SWL | 2.5 | 12 Sep 1130 - 1400 | 5590 | 902097 | ATTEMPTED TO PERFORATE MDDD FORMATION (INTERVAL#4) PER PROGRAM, GUNS DID NOT FIRE. | TF | PGUN |  | 09/12/2022 | AOD-1 | 2.5 | ZULF-690
1141 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ARO-4001 | Hrs | MRJN-532
1142 | FOT | RIG | 1.5 | 12 Sep 0930 - 1100 | 4820 | 902078 | BROKEN MAIN DRIVE CHAIN OF CAT WALK MACHINE. | RR | CATW |  | 09/12/2022 | ARO-4001 | 1.5 | MRJN-532
1143 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | BCTD-4 | Hrs | HRDH-2421
1144 | CWEL | ARM | 1.5 | 11 Sep 0400 - 0530 | 13227 | 902064 | OBSERVED DIFFERENTIAL & BHP SPIKES DUE TO WELLBORE INSTABILITY. WORK CT UNTIL FREE. | BHS | NA |  | 09/12/2022 | BCTD-4 | .5 | HRDH-2421
1145 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | DQ-47 | Hrs | KHRS-1739
1146 | FOT | RIG | 3 | 12 Sep 1500 - 1800 | 999 | 902083 | IBOP FAILURE, STUCK IN CLOSED POSITION WHILE CONNECTION. | RR | RWCS |  | 09/12/2022 | DQ-47 | 3 | KHRS-1739
1147 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ENS-108 | Hrs | ZULF-2015
1148 | GRF | RIG | 503 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/12/2022 | ENS-108 | 24 | ZULF-2015
1149 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | ENSCO-54 | Hrs | ABSF-134
1150 | FOT | KSC | 3 | 12 Sep 1200 - 1500 | 0 | 902038 | WHILE FUNCTION TEST & FLOW BACK THE WELL , ESP WAS SHUT DOWN DUE TO PROBLEM IN TRANSFORMER & VSD. | TF | ESP |  | 09/12/2022 | ENSCO-54 | 3 | ABSF-134
1151 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | EXL-IVA | Hrs | ZULF-2041
1152 | GRF | RIG | 204.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/12/2022 | EXL-IVA | 24 | ZULF-2041
1153 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | JACK-202 | Hrs | THRY-829
1154 | HERR | RIG | 22.75 | 12 Sep 0615 - 0500 | 5270 | 902123 | DRILL OUT FLOAT SHOE BY MISTAKE. | JF | NA |  | 09/12/2022 | JACK-202 | 22.75 | THRY-829
1155 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | NBR-263S | Hrs | QTIF-736
1156 | FOT | RIG | 5 | 12 Sep 2130 - 0230 | 11500 | 902081 | BIT NOZZLE PLUG DUE TO RELIEF VALVE OF MUD PUMP#2 POP-OFF@ 3500 PSI WHILE DRLG (PRE-SET VALUE 5500 PSI), PUMP CAUSTIC SODA & UNPLUG NOZZLE. | RR | MPMP |  | 09/12/2022 | NBR-263S | 5 | QTIF-736
1157 | FOT | RIG | .5 | 12 Sep 2030 - 2100 | 0 | 902101 | EZ TORQUE FAILURE NOT APPLE TO BREAK OUT 9-1/2" DC'S CONNECTION. | RR | RSYS |  | 09/12/2022 | PA-218S | .5 | HRDH-1976
1158 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | PA-218S | Hrs | HRDH-1976
1159 | HERR | RIG | 1.5 | 12 Sep 0830 - 1000 | 0 | 902037 | LEAKS ON CONNECTION FLANGE OF SPACER & BLOCKS ON KILL LINE WHILE ATTEMPTED TO TEST BOP'S | BOP | BOP |  | 09/12/2022 | PA-218S | 1.5 | HRDH-1976
1160 | FOT | RIG | .5 | 12 Sep 2030 - 2100 | 0 | 902101 | EZ TORQUE FAILURE NOT APPLE TO BREAK OUT 9-1/2" DC'S CONNECTION. | RR | RSYS |  | 09/12/2022 | PA-218S | .5 | HRDH-1976
1161 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | PA-529S | Hrs | SHYB-523
1162 | FOT | ARM | 188.25 | 04 Sep 1545 - 1500 | 4029 | 901687 | RIH WITH BAKER ESP COMPLETION WITH PDHMS HAD OBSTRUCTION @ 4029'. (BAKER 7" OCTOPUS PACKER DETH @ 3828', SAME DEPTH AS 7" TOL) ATTEMPT TO PASS SAME WITH 5 KLB S/O WT IN PRESENCE OF BAKER PACKER ENGINEER, NO SUCCESS. | JF | GP |  | 09/12/2022 | PA-529S | 10 | SHYB-523
1163 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | PA-622S | Hrs | UTMN-3600
1164 | FOT | CRT | 27 | 11 Sep 2100 - 0500 | 12803 | 902026 | ATTEMPTED 4 TIMES TO PASS THRU 4 1/2" LINER HGR (DIFFERENT SPEED, INCREASE SLACK-OFF) WITHOUT SUCCESS. ADDITIONAL CLEAN OUT TRIP IS NEED IT. | TF | SCRP |  | 09/12/2022 | PA-622S | 19 | UTMN-3600
1165 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | PA-785S | Hrs | QTIF-269
1166 | UDWL | WDS | 85 | 09 Sep 1600 - 0500 | 13513 | 901968 | WFD FAILED TO INITIATE SIDE TRACK L-0-2-1-1. | DD | RSS |  | 09/12/2022 | PA-785S | 24 | QTIF-269
1167 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | PA-861S | Hrs | HRDH-1973
1168 | FOT | SCP | 45 | 11 Sep 0730 - 0500 | 16845 | 902099 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/12/2022 | PA-861S | 23.5 | HRDH-1973
1169 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SINO-12L | Hrs | HWYH-518
1170 | IBHA | TK1 | 25 | 11 Sep 0400 - 0500 | 6533 | 902100 | DROPPED SHACKLE IN THE HOLE WHILE M/U 6-1/8" MM/MWD/LWD DIR DRILL ASSY. | JF | BHA |  | 09/12/2022 | SINO-12L | 24 | HWYH-518
1171 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SINO-19L | Hrs | HWYH-565
1172 | FOT | RIG | 7 | 12 Sep 2200 - 0500 | 9631 | 902082 | STOP DRILLING. OBSERVED SEVERE LEAK IN WASHPIPE. | RR | TDS |  | 09/12/2022 | SINO-19L | 7 | HWYH-565
1173 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SINO-22 | Hrs | BRRI-1144
1174 | FOT | SDM | 1.25 | 12 Sep 1830 - 1945 | 3338 | 902117 | LOST MWD SIGNAL, TROUBLESHOOT UNTIL REGAIN SIGNAL. | BHA | MWD |  | 09/12/2022 | SINO-22 | 1.25 | BRRI-1144
1175 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SINO-29N | Hrs | SFNY-2005
1176 | FOT | SWL | 30 | 11 Sep 2300 - 0500 | 7010 | 902059 | MANY TRIALS ATTEMED TO TROUBLE-SHOOT THE HIGH CURRENT FOR MDT LOGGING TOOL, NO SUCCESS. | TF | WLT |  | 09/12/2022 | SINO-29N | 24 | SFNY-2005
1177 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SINO-33L | Hrs | HRDH-1542
1178 | GRF | RIG | 242 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/12/2022 | SINO-33L | 24 | HRDH-1542
1179 | 5163 | 4700 | LOG | E | 4545 | WLT | CONT. POSITION STRING @ 4700', ACTIVATED STRADDLE PKR'S & PUMP OUT (2ND CYCLE)/SAMPLE STATION #11** PUMP OUT 181 LITERS OF GAS (1.14 BBL). TAKE A SAMPLE OF 1000 CC.** TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 2.64 BBLS. | 5163 | 4700 | HWP | 09/12/2022 | SINO-46L | LOG | SHYB-270
1180 | 5163 | 5155 | LOG | E | 4545 | WLT | HPJSM, RIH WITH LOGGING TOOL STRING TO 5155' (8' OFF BTM)** MONITOR WELL THRU TRIP TANK, STATIC. | 5163 | 4700 | HWP | 09/12/2022 | SINO-46L | LOG | SHYB-270
1181 | 5163 | 5155 | LOG | E | 4545 | WLT | CIRCULATE 50 BBL UNTIL GET FORMATION FLUID 2.64 BBL INSIDE 9-5/8" CSG SHOE.** IGNITE FLARE BEFORE START CIRCULATION. | 5163 | 5155 | HWP | 09/12/2022 | SINO-46L | LOG | SHYB-270
1182 | 5163 | 4512 | LOG | E | 4545 | WLT | HPJSM, POOH W/ HLB PCL LOGGING RUN#5: RDT-GR TO SES DEPTH @ 4512'. ** MONITOR WELL THRU TRIP TANK, STATIC. | 5163 | 5155 | HWP | 09/12/2022 | SINO-46L | LOG | SHYB-270
1183 | 5163 | 4512 | LOG | E | 4545 | WLT | HPJSM, CLOSED PIPE RAM BOP & CIRCULATE THRU. CHOKE & MGS TO CONDITION MUD 1X CYCLE (INTERNAL+ANNULUS), +/-3 BPM, 200 PSI, MW IN/OUT=77 PCF (NORMAL MUD), OK. SICP & SIDPP = 0 PSI. ** GAS BURNED AT FLARE.** CIRCULATE BOTTOM'S UP AFTER END OF GAS.** FLOW CHECK THROUGH CHOKE WELL STATIC.** OPEN PIPE RAMS AND PERFORM FLOW CHECK -STEADY LEVEL- | 5163 | 4512 | HWP | 09/12/2022 | SINO-46L | LOG | SHYB-270
1184 | 5163 | 4512 | LOG | E | 4545 | WLT | HPJSM, HLB WIRELINE UNLATCHED CABLE HEAD & POOH W/ WIRELINE CONNECTOR HEAD TO SURFACE, L/D SES & R/D WL SHEAVES.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 5163 | 4512 | HWP | 09/12/2022 | SINO-46L | LOG | SHYB-270
1185 | 5163 |  | OTH | E | 4545 | NA | POOH W/ HLB PCL LOGGING RUN#5: RDT-GR ON 5" DP STDS TO LAST STD ABOVE LOG TOOLS @ 144'. - MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC. | 5163 |  | RIG | 09/12/2022 | SINO-46L | LOG | SHYB-270
1186 | 5163 |  | OTH | E | 4545 | NA | FLOW CHECK, WELL STATIC. | 5163 |  | RIG | 09/12/2022 | SINO-46L | LOG | SHYB-270
1187 | 5163 |  | OTH | E | 4545 | NA | CONT'D POOH WITH L/D LOGGING TOOL TO SURFACE. | 5163 |  | HWP | 09/12/2022 | SINO-46L | LOG | SHYB-270
1188 | 5163 | 561 | HT | N |  | BHA | HPJSM , P/U & M/U 8-1/2" CONDITION TRIP ASSY . | 5163 | 0 | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1189 | 5163 | 4641 | TI | N |  | STDP | RIH W/8-1/2" CONDITION TRIP ASSY ON 5" STDS DP TO 9-5/8'' CS @ 4641',** PASS DV TOOL FREELY. | 5163 | 561 | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1190 | 5163 | 5163 | TI | N |  | STDP | RIH W/8-1/2" CONDITION TRIP ASSY ON 5" STDS DP F/ 9-5/8'' CS TO TD @ 5163',** WASH DOWN LAST STAND. | 5163 | 4641 | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1191 | 5163 |  | CIRC | N |  | MPMP | SWEPT THE HOLE WITH HVP & CIRCULATE 1 CYCLE.** FLOW CHECK - WELL STATIC- | 5163 |  | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1192 | 5163 | 4641 | TO | N |  | STDP | POOH FREELY ON ELEVATOR W/8-1/2" CONDITION TRIP ASSY TO 9-5/8" CSG SHOE @ 4641'.** F/C- WELL STATIC.* MONITOR THE WELL ON TRIP TANK. | 5163 | 5163 | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1193 | 5163 | 5163 | TI | N |  | STDP | RIH FREELY ON ELEVATOR W/8-1/2" CONDITION TRIP ASSY TO TD @ 5163'.** MONITOR THE WELL ON TRIP TANK. | 5163 | 4641 | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1194 | 5163 |  | CIRC | N |  | MPMP | SWEPT THE HOLE WITH HVP & CIRCULATE 1 CYCLE .** SPOT 50 BBL HIV AT BOTTOM.** F/C- WELL STATIC | 5163 |  | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1195 | 5163 | 4641 | TO | N |  | STDP | POOH FREELY ON ELEVATOR W/8-1/2" CONDITION TRIP ASSY TO 9-5/8" CSG SHOE @ 4641'.** MONITOR THE WELL ON TRIP TANK. ** F/C- WELL STATIC. | 5163 | 5163 | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1196 | 5163 | 4013 | TO | C |  | STDP | CONT. POOH W/8-1/2" CONDITION TRIP ASSY F 4641' TO 4013'.** MONITOR THE WELL ON TRIP TANK.** F/C WELL STATIC. | 5163 | 4641 | RIG | 09/12/2022 | SINO-46L | CT | SHYB-270
1197 | 158 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN#1 LOGGING TOOLS (XMAC-GR-WGI ), CONDITION TRIP, RUN #4 (FTEX -GR), RUN #5 (RDT -GR). | 15 | 4545 | 01 Sep 0800 | 09/12/2022 | SINO-46L | Type | SHYB-270
1198
1199
1200 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SND-1501 | Hrs | HWYH-89
1201 | FOT | RIG | 11.25 | 12 Sep 0500 - 1615 | 9700 | 902119 | REPAIR MUD PUMP | RR | MPMP |  | 09/12/2022 | SND-1501 | 11.25 | HWYH-89
1202 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SND-2007 | Hrs | AWTD-104001
1203 | FOT | RIG | 1.5 | 12 Sep 1945 - 2115 | 1100 | 902122 | DRILL LINE CLAMP. ON DRWKS NOT TIGHTEN PROPERLY. | RR | DWKS |  | 09/12/2022 | SND-2007 | 1.5 | AWTD-104001
1204 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SND-2008 | Hrs | HRDH-1291
1205 | XTRI | RIG | 7 | 12 Sep 1400 - 2100 | 0 | 902039 | EXCESSIVE TIME TO R/U BOPE AND RELATED EQUIP. | JF | BOP |  | 09/12/2022 | SND-2008 | 7 | HRDH-1291
1206 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SND-2010 | Hrs | MNIF-868
1207 | FOT | ANT | 7 | 12 Sep 2200 - 0500 | 5151 | 902040 | FAILURE OF SINOPEC MWD TOOL (LOST SIGNAL) . | BHA | MWD |  | 09/12/2022 | SND-2010 | 7 | MNIF-868
1208 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SP-259 | Hrs | JNAB-271612
1209 | FOT | SDM | 19.75 | 12 Sep 0500 - 0500 | 10204 | 902116 | LOST MWD SIGNAL | BHA | MWD |  | 09/12/2022 | SP-259 | 19.75 | JNAB-271612
1210 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SSA-102 | Hrs | QTIF-693
1211 | XTTE | NCT | 96 | 09 Sep 0500 - 0500 | 10300 | 901955 | NESR CT MLT NOT ABLE TO MAP L-1 | TF | CTBG |  | 09/12/2022 | SSA-102 | 24 | QTIF-693
1212 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SSA-201 | Hrs | MNHZ-1
1213 | IDPR | SDM | 30.75 | 11 Sep 1045 - 0415 | 13448 | 902015 | SCHLUMBERGER MWD/RSS TOOL UNABLE TO SEND AND HOLD TELEMETERY COMMUNICATION. EXTENSIVE TROUBLE SHOOT CARRIED OUT WITH SUPPORT FROM BASE AND TOOL COMMUNICATION WAS SPORADIC AT BEST. | BHA | RSS | 901942 | 09/12/2022 | SSA-201 | 16.75 | MNHZ-1
1214 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SSA-29 | Hrs | QTIF-423
1215 | IDPR | WDS | 40.5 | 07 Sep 2230 - 1430 | 13020 | 902013 | EXCESSIVE TIME TO DRILL 6-1/8" L0-1. OFFSET WELLS AVERAGE ROP = 55 FT/HR | LROP | BHA |  | 09/12/2022 | SSA-29 | 9.5 | QTIF-423
1216 | FWTS | RIG | 3 | 12 Sep 0200 - 0500 | 1013 | 902121 | WHILE DRILLING AT 1013 FT, LOST 48 KLB OF STRING WT IN HOLEAND PRESSURE DROPPED FROM 650 PSI TO 150 PSI. | FISH | BHA |  | 09/12/2022 | SSA-302 | 3 | HRDH-2353
1217 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SSA-302 | Hrs | HRDH-2353
1218 | FOT | RIG | 8 | 11 Sep 1230 - 2000 | 889 | 902014 | TOP DRIVE WAS NOT ROTATING, NO COMMUNICATION. | RR | TDS |  | 09/12/2022 | SSA-302 | 6 | HRDH-2353
1219 | FWTS | RIG | 3 | 12 Sep 0200 - 0500 | 1013 | 902121 | WHILE DRILLING AT 1013 FT, LOST 48 KLB OF STRING WT IN HOLEAND PRESSURE DROPPED FROM 650 PSI TO 150 PSI. | FISH | BHA |  | 09/12/2022 | SSA-302 | 3 | HRDH-2353
1220 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SSA-5892 | Hrs | AWTD-141400
1221 | STDP | ARM | 35.25 | 11 Sep 1630 - 0500 | 14635 | 902030 | MOTOR DRILLING 8-3/8" SIDETRACK SECTION AND AFTER WORKING THE STRING. PICK UP 5FT OFF BOTTOM AND TAKE SURVEY. TURN ON PUMPS AND HAVE CIRCULATION BUT TURN ON ROTATION AND STRING IS STUCK | STUK | DP |  | 09/12/2022 | SSA-5892 | 22.75 | AWTD-141400
1222 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | SSA-5914 | Hrs | WDYH-80
1223 | FOT | RIG | 22.75 | 12 Sep 0500 - 0500 | 20711 | 902077 | OBSERVED LEAK WHILE PRESSURE TEST ANNULAR BOP WITH 4" PIPE. | BOP | BOP |  | 09/12/2022 | SSA-5914 | 22.75 | WDYH-80
1224 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | T218 | Hrs | HRDH-1511
1225 | PSSW | ARM | 5.75 | 11 Sep 2345 - 0800 | 6948 | 902061 | STUCK PIPE AFTER CONNECTION | STUK | NA |  | 09/12/2022 | T218 | 3 | HRDH-1511
1226 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | T907 | Hrs | SRYN-2
1227 | FOT | RIG | 1.5 | 12 Sep 2230 - 0000 | 7830 | 902120 | WHILE RIH W/ 3-1/2" TUBING IT WAS FOUND THAT THE TUBING WOULD NOT DRIFT | TF | PEL |  | 09/12/2022 | T907 | 1.5 | SRYN-2
1228 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/12/2022 | V141A | Hrs | MRJN-3025
1229 | FOT | RIG | .5 | 12 Sep 2330 - 0000 | 2426 | 902118 | EXCESSIVE TIME PUMPING TAIL CEMENT DUE TO POOR CEMENT DELIVERY FROM THE RIG, DROP IN COMPRESSOR PRESSURE. DELAY ON DELIVERING TAIL MIX WATER TO CEMENT UNIT. | RR | HSYS |  | 09/12/2022 | V141A | .5 | MRJN-3025
1230 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | 095TE | Hrs | MNIF-126
1231 | FOT | RIG | 1.5 | 13 Sep 1930 - 2100 | 9080 | 902093 | OBSERVED WASHOUT ON BLEED OFF VALVE ON STD PIPE, PULL BACK INSIDE CSG SHOE AND REPLACE THE WASH OUT VALVE. | RR | CSYS |  | 09/13/2022 | 095TE | 1.5 | MNIF-126
1232 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADC-21 | Hrs | MHWZ-991100
1233 | OTH | RIG | 305.25 | 01 Sep 1145 - 0500 | 2077 | 901973 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | UPRA | NA |  | 09/13/2022 | ADC-21 | 24 | MHWZ-991100
1234 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADC-36 | Hrs | SDGM-1194
1235 | WC20 | ARM | 27 | 12 Sep 1900 - 2200 | 11474 | 902084 | STOP PUMP TO EVALUATE STATIC LOSSES @ 11474' WHILE DRILLING WITH 144 PCF OBM, OBSERVED WELL FLOW, SHUT IN THE WELL WITH 390 PSI SICP, KILLED WELL WITH 150 PCF OBM. | WCNT | NA |  | 09/13/2022 | ADC-36 | 17 | SDGM-1194
1236 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADC-53L | Hrs | HRDH-1530
1237 | OTH | RIG | 27.5 | 12 Sep 0500 - 0830 | 0 | 902098 | EXCEEDING PLANNED TIME FOR CAT IV & OVERHAULING MAINTENANCE. | UPRA | NA |  | 09/13/2022 | ADC-53L | 3.5 | HRDH-1530
1238 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADC-55L | Hrs | UTMN-3171
1239 | FOT | WUD | 6.25 | 12 Sep 1100 - 1900 | 12486 | 902080 | FAILURE WITH WFD CORIOLIS FLOW METER. | TF | MPD |  | 09/13/2022 | ADC-55L | 1.75 | UTMN-3171
1240 | 10376 |  | RR | N | 4627 | DWKS | SLIP AND CUT DRILLING LINE. | 10376 |  | RIG | 09/13/2022 | ADC-68L | DRLG | FDHL-174
1241 | 10376 |  | HT | N | 4627 | STRG | POOH W/8-1/2" CONDITIONING BHA FROM 6262 FT TO1135 FT.- FLOW CHECK. - WELL STATIC.- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET | 10376 |  | RIG | 09/13/2022 | ADC-68L | DRLG | FDHL-174
1242 | 10376 |  | HT | N | 4627 | BHA | POOH W/ 8-1/2" CONDITIONING BHA FROM 1135 FT TO SURFACE.- SMITH MS616-C SN: SM2084 W/ 6X13 NOZZLES R/B 12 STD'S 5HWDP- L/D 6-1/2JAR. BIT DULL GRADING: 1-1-WT-A-X-I-NO-TD.FLOW CHECK. - WELL STATIC. | 10376 |  | RIG | 09/13/2022 | ADC-68L | DRLG | FDHL-174
1243 | 10376 |  | PJSM | E | 4627 | NA | PJSM, PRIOR TO PICKING SLB TLC LOGGING BHA, DISCUSS THE RISK AND HAZARD- REVIEW THE JSA | 10376 |  | TK3 | 09/13/2022 | ADC-68L | LOG | FDHL-174
1244 | 10376 | 164 | OTH | E | 4627 | NA | P/U AND M/U SLB WL TLC LOGGING STRING # 3 ( GRMDT) AND RIH TO 164 FT. CONNECT LATCHING HEAD TO TLCLOGGING TOOLS & CHECK TOOLS AT SURFACE.- TOOL LENGTH:164 FT, MAX TOOL OD: 7 INCHES- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET. | 10376 | 0 | SWL | 09/13/2022 | ADC-68L | LOG | FDHL-174
1245 | 10376 | 6060 | TI | E | 4627 | STDP | RIH TLC LOGGING TOOLS (MDT-GR) ON 5" HWDP X 5" DP FROM 168 FT TO 6068 FT WITH CONTROLLED SPEED.- RIH SPEED=3 MIN/STD SLIP TO SLIP- FILL UP STRING EVERY 10 STANDS.- DRIFTED ALL STANDS RIH WITH 2.5" DRIFT.- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET | 10376 | 168 | RIG | 09/13/2022 | ADC-68L | LOG | FDHL-174
1246 | 10376 |  | CIRC | E | 4627 | MPMP | CIRCULATE 1.5 STRING VOLUME W/OBM - FR= 250 GPM, SPP= 150 PSI. MEANWHILE R/U WL SHEAVES.- HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW. | 10376 |  | RIG | 09/13/2022 | ADC-68L | LOG | FDHL-174
1247 | 10376 |  | OTH | E | 4627 | NA | LATCH WIRELINE CABLE PWCH INTO DWCH @ 5943 FTAS PER WIRELINE ENGINEER INSTRUCTION.- M/U WL CSES WITH FED THRU WIRE LINE CABLE RIH SLB WL CABLE- PUMP DOWN @ 250 GPM, 390 PSI TO ASSIST TO LATCH.- FUNCTION TEST SLB TOOLS- PERFORM PULL TEST TO 3,200 LBS.- MONITOR WELL THROUGH TRIP TANK, WELL STATIC. | 10376 |  | SWL | 09/13/2022 | ADC-68L | LOG | FDHL-174
1248 | 10376 | 6400 | TI | E | 4627 | STDP | RIH TLC RUN #3 FROM 6060 FT TO 6400 FT.- RIH SPEED=3 MIN/STD SLIP TO SLIP, FILL UP STRING EVERY 10 STANDS | 10376 | 6085 | RIG | 09/13/2022 | ADC-68L | LOG | FDHL-174
1249 | 10376 | 9980 | LOG | E | 4627 | WLT | SLB WL START TAKING PRESSURE POINTS AS PERARAMCO RMD, PERFORM STICK TEST 3, 5, 8, 15 MIN BEFORE EVERY NEWFORMATION AND PERFORM 3, 8 MIN STICKING TEST BEFOREEACH PRESSURE POINT IN SAME FORMATION.- RECORD FORMATION PRESSURE | 10376 | 6400 | SWL | 09/13/2022 | ADC-68L | LOG | FDHL-174
1250 | 122 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 24 | 4627 | 08 Sep 0300 | 09/13/2022 | ADC-68L | Type | FDHL-174
1251
1252
1253 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADC-70 | Hrs | MRJN-767
1254 | UDWL | BHI | 2 | 13 Sep 1000 - 1200 | 545 | 902091 | PRECAUTIONALY, DD ASKED TO CHECK GYRO POSITION IN PLACE TO CONFIRM SURVEY QUALITY. | DD | MMOT |  | 09/13/2022 | ADC-70 | 2 | MRJN-767
1255 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADES-40 | Hrs | UTMN-1539
1256 | HERR | RIG | 12 | 13 Sep 0500 - 1700 | 2348 | 902090 | TBG COLLAPSED DUE TO POWER TONG, UNABLE TO PASS WITH DRIFT. | JF | CTRQ |  | 09/13/2022 | ADES-40 | 12 | UTMN-1539
1257 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADES-798 | Hrs | HRDH-2354
1258 | FOT | RIG | 1.5 | 13 Sep 0730 - 0900 | 200 | 902163 | EXCESS TIME WHILE M/U ISC DUE TO MALFUNCTION IRON ROUGHNECK. | RR | HSYS |  | 09/13/2022 | ADES-798 | 1.5 | HRDH-2354
1259 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADM-261 | Hrs | MRJN-24
1260 | FOT | NNN | 29 | 11 Sep 0230 - 0730 | 7893 | 901971 | LOST DRILLING TORQUE SUDDENLY WHILE DRILLING ONBOTTOM, UNABLE TO DRILL WITH MAX WOB. POH FOUND NEOTORQ TOOL FAILED. | BHA | AST |  | 09/13/2022 | ADM-261 | 2.5 | MRJN-24
1261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADM-262 | Hrs | MRJN-448
1262 | FOT | BAL | 2 | 13 Sep 0000 - 0200 | 328 | 902094 | LEAK IN CONNECTION OF ESP FLAT CABLE AND MOTOR, INTERNAL LEAK IN O-RING OF CONTROL LINE. | TF | ESP |  | 09/13/2022 | ADM-262 | 2 | MRJN-448
1263 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ADM-657 | Hrs | SFNY-1228
1264 | HERR | ARM | 53.5 | 11 Sep 2330 - 0500 | 4233 | 902063 | RIH W/ GS RETRIEVAL TOOL TO RETRIEVE SCHLUMBERGER M/E TUBING PLUG, UNABLE TO PASS 4220', M/U 2.5" & 3" SAND BAILERS REMOVING GREASE LIKE SLUDGE FROM TOP OF ME PLUG JUNK TRAPPER TOP @ 4233'. CONTINUE TO RUN SLICK LINE WITH VARIOUS CONFIGURATIONS & OPTIONS IN ATTEMPT TO RETRIEVE ME PLUG JUNK BASKET & PRONG. | TF | TBG |  | 09/13/2022 | ADM-657 | 24 | SFNY-1228
1265 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | ENS-108 | Hrs | ZULF-2015
1266 | GRF | RIG | 523.5 | 23 Aug 0500 - 0130 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 09/13/2022 | ENS-108 | 20.5 | ZULF-2015
1267 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | EXL-IVA | Hrs | ZULF-2041
1268 | GRF | RIG | 228.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/13/2022 | EXL-IVA | 24 | ZULF-2041
1269 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | HI-2 | Hrs | BRRI-436
1270 | XTTE | BCR | 1.5 | 13 Sep 1200 - 1330 | 3438 | 902162 | BKR POWER UNIT DOWN WHILE RUNNING CSG. | TF | CTRQ |  | 09/13/2022 | HI-2 | 1.5 | BRRI-436
1271 | XTRI | RIG | 1 | 13 Sep 1530 - 1630 | 7147 | 902086 | EXCESSIVE TIME TO PICK UP RSS BHA | JF | NA |  | 09/13/2022 | NBR-20S | 1 | HMYM-433512
1272 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | NBR-20S | Hrs | HMYM-433512
1273 | FOT | RIG | 2.5 | 13 Sep 0600 - 0830 | 7147 | 902085 | NEWLY INSTALLED WASHPIPE FAILED TO PRESSURE TEST. | RR | TDS |  | 09/13/2022 | NBR-20S | 2.5 | HMYM-433512
1274 | XTRI | RIG | 1 | 13 Sep 1530 - 1630 | 7147 | 902086 | EXCESSIVE TIME TO PICK UP RSS BHA | JF | NA |  | 09/13/2022 | NBR-20S | 1 | HMYM-433512
1275 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | PA-622S | Hrs | UTMN-3600
1276 | FOT | CRT | 51 | 11 Sep 2100 - 0500 | 12803 | 902026 | ATTEMPTED 4 TIMES TO PASS THRU 4 1/2" LINER HGR (DIFFERENT SPEED, INCREASE SLACK-OFF) WITHOUT SUCCESS. ADDITIONAL CLEAN OUT TRIP IS NEED IT. | TF | SCRP |  | 09/13/2022 | PA-622S | 24 | UTMN-3600
1277 | FOT | RIG | 1.5 | 13 Sep 0600 - 0730 | 0 | 902136 | TDS WASH PIPE LEAKAGE | RR | TDS |  | 09/13/2022 | PA-785S | 1.5 | QTIF-269
1278 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | PA-785S | Hrs | QTIF-269
1279 | UDWL | WDS | 103 | 09 Sep 1600 - 0030 | 13513 | 901968 | WFD FAILED TO INITIATE SIDE TRACK L-0-2-1-1. | DD | RSS |  | 09/13/2022 | PA-785S | 18 | QTIF-269
1280 | FOT | RIG | 1.5 | 13 Sep 0600 - 0730 | 0 | 902136 | TDS WASH PIPE LEAKAGE | RR | TDS |  | 09/13/2022 | PA-785S | 1.5 | QTIF-269
1281 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | PA-861S | Hrs | HRDH-1973
1282 | FOT | SCP | 69 | 11 Sep 0730 - 0500 | 16845 | 902099 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/13/2022 | PA-861S | 24 | HRDH-1973
1283 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SINO-12L | Hrs | HWYH-518
1284 | HERR | RIG | 76.5 | 10 Sep 0530 - 0500 | 250 | 901960 | DROPPED SHACKLE IN THE HOLE WHILE M/U 6-1/8" MM/MWD/LWD DIR DRILL ASSY. | FISH | STRG |  | 09/13/2022 | SINO-12L | 24 | HWYH-518
1285 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SINO-18 | Hrs | HDYF-4
1286 | WOTO | HTS | 4.5 | 13 Sep 2130 - 0200 | 10770 | 902160 | HAL SURFACE TEST TEFLON RING FOR ORIFICE PLATE FAIL, NO BACK UP ON LOCATION, WAIT ON RING FROM HAL YARD. | WO | NA |  | 09/13/2022 | SINO-18 | 4.5 | HDYF-4
1287 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SINO-29N | Hrs | SFNY-2005
1288 | FOT | SWL | 38.5 | 11 Sep 2300 - 1330 | 7010 | 902059 | MANY TRIALS ATTEMED TO TROUBLE-SHOOT THE HIGH CURRENT FOR MDT LOGGING TOOL, NO SUCCESS. | TF | WLT |  | 09/13/2022 | SINO-29N | 8.5 | SFNY-2005
1289 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SINO-33L | Hrs | HRDH-1542
1290 | GRF | RIG | 266 | 02 Sep 0300 - 0500 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/13/2022 | SINO-33L | 24 | HRDH-1542
1291 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SINO21 | Hrs | ABQQ-575
1292 | ISEQ | SDM | 38.75 | 12 Sep 1315 - 0500 | 9611 | 902092 | PRESSURE POINT TOOL MALFUNCTION | BHA | LWD |  | 09/13/2022 | SINO21 | 23 | ABQQ-575
1293 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SND-1501 | Hrs | HWYH-89
1294 | FOT | RIG | 7 | 13 Sep 2200 - 0500 | 11022 | 902158 | REPAIR MUD PUMP#2 | RR | MPMP |  | 09/13/2022 | SND-1501 | 7 | HWYH-89
1295 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SND-2007 | Hrs | AWTD-104001
1296 | XTRI | RIG | .5 | 13 Sep 0815 - 0845 | 0 | 902161 | EXCESS TIME CHANGE LOWER WELL CONTROL VALVE ON TOP DRIVE. | JF | NA |  | 09/13/2022 | SND-2007 | .5 | AWTD-104001
1297 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SND-2008 | Hrs | HRDH-1291
1298 | FOT | WCR | 3.5 | 13 Sep 0900 - 1230 | 11700 | 902088 | ATTEMPT TO OPEN WFD ELEVATOR WITHOUT SUCCESS, WFD ELEVATOR GOT STUCK ON LANDING JOINT | TF | PEL |  | 09/13/2022 | SND-2008 | 3.5 | HRDH-1291
1299 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SND-2010 | Hrs | MNIF-868
1300 | FOT | ANT | 19.5 | 12 Sep 2200 - 1730 | 5151 | 902040 | FAILURE OF SINOPEC MWD TOOL (LOST SIGNAL) . | BHA | MWD |  | 09/13/2022 | SND-2010 | 12.5 | MNIF-868
1301 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SP-259 | Hrs | JNAB-271612
1302 | FOT | SDM | 31.5 | 12 Sep 0500 - 1645 | 10204 | 902116 | LOST MWD SIGNAL | BHA | MWD |  | 09/13/2022 | SP-259 | 11.75 | JNAB-271612
1303 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SP-306 | Hrs | MNIF-192
1304 | KSFM | ARN | 2.75 | 13 Sep 0215 - 0500 | 17029 | 902157 | DRILL STRING STUCK IN 8-1/2" HOLE. | STUK | STRG |  | 09/13/2022 | SP-306 | 2.75 | MNIF-192
1305 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SSA-102 | Hrs | QTIF-693
1306 | XTTE | NCT | 120 | 09 Sep 0500 - 0500 | 10300 | 901955 | NESR CT MLT NOT ABLE TO MAP L-1 | TF | CTBG |  | 09/13/2022 | SSA-102 | 24 | QTIF-693
1307 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SSA-202 | Hrs | QTIF-191
1308 | FOT | SCP | 19 | 13 Sep 1000 - 0500 | 6490 | 902095 | SLB NOT ABLE TO EXPAND 7" CSG PATCH. | TF | PKR |  | 09/13/2022 | SSA-202 | 19 | QTIF-191
1309 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SSA-302 | Hrs | HRDH-2353
1310 | FWTS | RIG | 8.5 | 12 Sep 0200 - 1030 | 1013 | 902121 | WHILE DRILLING AT 1013 FT, LOST 48 KLB OF STRING WT IN HOLEAND PRESSURE DROPPED FROM 650 PSI TO 150 PSI. | FISH | BHA |  | 09/13/2022 | SSA-302 | 5.5 | HRDH-2353
1311 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SSA-5914 | Hrs | WDYH-80
1312 | FOT | RIG | 24.25 | 12 Sep 0500 - 0630 | 20711 | 902077 | OBSERVED LEAK WHILE PRESSURE TEST ANNULAR BOP WITH 4" PIPE. | BOP | BOP |  | 09/13/2022 | SSA-5914 | 1.5 | WDYH-80
1313 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/13/2022 | SSA-5917 | Hrs | HRDH-2406
1314 | LHFL | RIG | 1.5 | 13 Sep 1900 - 2030 | 650 | 902156 | RIG REPAIR, FIXED LEAK ON ROTARY HOSE AND LEAK OIL ON LUBRICATION PUMP ON TDS. | RR | HSYS |  | 09/13/2022 | SSA-5917 | 1.5 | HRDH-2406
1315 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | 088TE | Hrs | QTIF-519
1316 | FOT | RIG | 2 | 14 Sep 1700 - 1900 | 5780 | 902172 | RIG HYDRAULIC CATWALK MALFUNCTION. | RR | CATW |  | 09/14/2022 | 088TE | 2 | QTIF-519
1317 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | ADC-21 | Hrs | MHWZ-991100
1318 | OTH | RIG | 329.25 | 01 Sep 1145 - 0500 | 2077 | 901973 | SHUT DOWN OPERATIONS FOR INCIDENT INVESTIGATION. | UPRA | NA |  | 09/14/2022 | ADC-21 | 24 | MHWZ-991100
1319 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | ADC-34 | Hrs | UTMN-2309
1320 | FOT | WUD | 5.5 | 14 Sep 1500 - 2030 | 11295 | 902174 | RUBBER PACKER SEPERATED AND FOUND ON SHAKERS. | BOP | RCD |  | 09/14/2022 | ADC-34 | 5.5 | UTMN-2309
1321 | 10376 | 10215 | LOG | E | 4627 | WLT | CON'T SLB WL TAKING PRESSURE POINTS AS PER RMD REQUEST.- PERFORM STICK TEST 3, 5, 8, 15 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 3, 8 MIN FOR SUBSEQUENT POINTS. NO SIGNIFICANT INCREASE IN OVER PULL DURING STICK TEST.- (ABDR FM) 1 PT @ 8,950 FT, O.B 898.73 PSI. (HDRR FM) 1 PTS @ 9,980 FT DRY. (UFDR FM) 6 PT @ 10,174 FT, 10,181 FT, 10,188 FT, 10,193 FT, 10,205 FT, 10,215 FT DRY/ TIGHT.- TOTAL PTS 9 OUT OF 9 PTS.- MONITOR WELL ON TRIP TANK. | 10376 | 6982 | SWL | 09/14/2022 | ADC-68L | LOG | FDHL-174
1322 | 10376 | 10205 | LOG | E | 4627 | WLT | SLB WL START TAKING SAMPLING AS PER RMD REQUEST.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. CORRELATION PASSES TO SET THE TOOL DEPTH WHILE MOVING DOWN. NO SIGNIFICANT INCREASE DURING STICK TEST.- MAX STATIONARY TIME: 4 HRS.- SAMPLE #1 (UFDR FM) @ 10,215 FT. VOL PUMPED TO WELL BORE: 3.5 L.- SAMPLE #2 (UFDR FM) @ 10,205 FT. ON GOING AT RT.- MONITOR WELL ON TRIP TANK.** LAST CIRC ON 12 SEP 2022 AT 01:00 AM, 52 HRS. | 10376 | 10215 | SWL | 09/14/2022 | ADC-68L | LOG | FDHL-174
1323 | 146 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 24 | 4627 | 08 Sep 0300 | 09/14/2022 | ADC-68L | Type | FDHL-174
1324
1325
1326 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | ADM-657 | Hrs | SFNY-1228
1327 | HERR | ARM | 77.5 | 11 Sep 2330 - 0500 | 4233 | 902063 | RIH W/ GS RETRIEVAL TOOL TO RETRIEVE SCHLUMBERGER M/E TUBING PLUG, UNABLE TO PASS 4220', M/U 2.5" & 3" SAND BAILERS REMOVING GREASE LIKE SLUDGE FROM TOP OF ME PLUG JUNK TRAPPER TOP @ 4233'. CONTINUE TO RUN SLICK LINE WITH VARIOUS CONFIGURATIONS & OPTIONS IN ATTEMPT TO RETRIEVE ME PLUG JUNK BASKET & PRONG. | TF | TBG |  | 09/14/2022 | ADM-657 | 24 | SFNY-1228
1328 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | ARO-3004 | Hrs | MRJN-2060
1329 | FOT | SWL | 11 | 14 Sep 1545 - 0245 | 8050 | 902169 | SLB WIRELINE UNABLE TO COMMUNICATE WITH GR-CCL TOOL TO SET 9 5/8" BRIDGE PLUG. TROUBLESHOOT AND FIND BROKEN CONNECTION IN CABLE HEAD. CUT OFF BAD END OF WIRE. CRIMP WIRE TO CABLE HEAD - OKAY | TF | WLT |  | 09/14/2022 | ARO-3004 | 11 | MRJN-2060
1330 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | DQ-49L | Hrs | HRDH-1541
1331 | FOT | GCD | 5 | 14 Sep 1600 - 2100 | 4568 | 902197 | AFTER PERFORMING GYRO SURVEY, POOH TO SURFACE ON W/L- FOUND GYRO TOOL STRING LOST INSIDE DRILL STRING, | SURV | GYRO |  | 09/14/2022 | DQ-49L | 5 | HRDH-1541
1332 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | ENS-108 | Hrs | ZULF-2015
1333 | FPMP | RIG | 21 | 14 Sep 0800 - 0500 | 7381 | 902164 | MUD PUMP #1 PRESSURE DROPPED & MUD PUMP #2 WAS UNABLE TO MAINTAIN SUFFICIENT FLOW RATE DUE TO BELT SLIPPAGE. | RR | MPMP |  | 09/14/2022 | ENS-108 | 21 | ZULF-2015
1334 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | EXL-IVA | Hrs | ZULF-2041
1335 | GRF | RIG | 252.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/14/2022 | EXL-IVA | 24 | ZULF-2041
1336 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | PA-622S | Hrs | UTMN-3600
1337 | FOT | CRT | 72.5 | 11 Sep 2100 - 0500 | 12803 | 902026 | ATTEMPTED 4 TIMES TO PASS THRU 4 1/2" LINER HGR (DIFFERENT SPEED, INCREASE SLACK-OFF) WITHOUT SUCCESS. ADDITIONAL CLEAN OUT TRIP IS NEED IT. | TF | SCRP |  | 09/14/2022 | PA-622S | 21.5 | UTMN-3600
1338 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | PA-861S | Hrs | HRDH-1973
1339 | FOT | SCP | 93 | 11 Sep 0730 - 0500 | 16845 | 902099 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/14/2022 | PA-861S | 24 | HRDH-1973
1340 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | PN-9 | Hrs | MRJN-673
1341 | FOT | RIG | 2 | 14 Sep 0630 - 0830 | 15702 | 902176 | TRIP TANK PUMP NOT CIRCULATING WHILE SLIP & CUT DRILLING LINE. | TF | SFLN | 901862 | 09/14/2022 | PN-9 | 2 | MRJN-673
1342 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SINO-12L | Hrs | HWYH-518
1343 | HERR | RIG | 82.5 | 10 Sep 0530 - 1100 | 250 | 901960 | DROPPED SHACKLE IN THE HOLE WHILE M/U 6-1/8" MM/MWD/LWD DIR DRILL ASSY. | FISH | STRG |  | 09/14/2022 | SINO-12L | 6 | HWYH-518
1344 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SINO-33L | Hrs | HRDH-1542
1345 | GRF | RIG | 277 | 02 Sep 0300 - 1600 | 1819 | 901717 | AFTER INCIDENT OCCURRED FOR THE MONORAIL, AND SEQUENCED MULTIPLE TDS FAILURES REQUESTED SINO TO CONDUCT CAT-IV INSPECTION AGAIN FOR MONORAIL, ADJUSTABLE PLATE, TDS, TRAVELING AND CROWN BLOCKS AS PER OEM RECOMMENDATIONS. | UPRA | TDS |  | 09/14/2022 | SINO-33L | 11 | HRDH-1542
1346 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SINO-42L | Hrs | HWYH-480
1347 | FOT | RIG | 1 | 14 Sep 1530 - 1630 | 0 | 902167 | TEST UNIT CLOCK MULFUNCTIONED | RR | EDR |  | 09/14/2022 | SINO-42L | 1 | HWYH-480
1348 | FOT | HUD | 3.5 | 14 Sep 2200 - 0130 | 10511 | 902173 | RCD BEARING FAILURE | TF | MPD |  | 09/14/2022 | SINO21 | 3.5 | ABQQ-575
1349 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SINO21 | Hrs | ABQQ-575
1350 | ISEQ | SDM | 45.75 | 12 Sep 1315 - 1200 | 9611 | 902092 | PRESSURE POINT TOOL MALFUNCTION | BHA | LWD |  | 09/14/2022 | SINO21 | 7 | ABQQ-575
1351 | FOT | HUD | 3.5 | 14 Sep 2200 - 0130 | 10511 | 902173 | RCD BEARING FAILURE | TF | MPD |  | 09/14/2022 | SINO21 | 3.5 | ABQQ-575
1352 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SND-1501 | Hrs | HWYH-89
1353 | FOT | RIG | 31 | 13 Sep 2200 - 0500 | 11022 | 902158 | REPAIR MUD PUMP#2 | RR | MPMP |  | 09/14/2022 | SND-1501 | 24 | HWYH-89
1354 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SND-2010 | Hrs | MNIF-868
1355 | FOT | RIG | 12.5 | 14 Sep 1630 - 0500 | 6032 | 902165 | WHILE ATTEMPTING TO SLIDE HAVE MOTOR STALLING EVENTS W/ NIL ROP | BHA | MMOT |  | 09/14/2022 | SND-2010 | 12.5 | MNIF-868
1356 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SP-121 | Hrs | BRRI-522
1357 | FOT | RIG | 8.5 | 14 Sep 0930 - 0330 | 9662 | 902198 | RIG CREW CLEAN MUD SYSTEM CIRCUIT & SUCTION/DISCHARGE SCREENS DUE TO PRESENCE OF CEMENT AND CUTTINGS DEBRIS. | RR | CSYS |  | 09/14/2022 | SP-121 | 8.5 | BRRI-522
1358 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SP-306 | Hrs | MNIF-192
1359 | KSFM | ARN | 4.75 | 13 Sep 0215 - 0700 | 17029 | 902157 | 8 1/2" REAMING BHA GOT STUCK WHILE POOH THE 1ST STAND. PUMPED ACID PILL & GOT STRING FREE. | STUK | STRG |  | 09/14/2022 | SP-306 | 2 | MNIF-192
1360 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SSA-102 | Hrs | QTIF-693
1361 | XTTE | NCT | 124.75 | 09 Sep 0500 - 0945 | 10300 | 901955 | NESR CT MLT NOT ABLE TO MAP L-1 | TF | CTBG |  | 09/14/2022 | SSA-102 | 4.75 | QTIF-693
1362 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SSA-202 | Hrs | QTIF-191
1363 | FOT | SCP | 29.5 | 13 Sep 1000 - 1530 | 6490 | 902095 | SLB NOT ABLE TO EXPAND 7" CSG PATCH. | TF | PKR |  | 09/14/2022 | SSA-202 | 10.5 | QTIF-191
1364 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SSA-5859 | Hrs | HWYH-1217
1365 | FOT | SPS | 7.75 | 14 Sep 2115 - 0500 | 5584 | 902171 | SPERRY SUN RSS TOOL FAILURE. TROUBLESHOOTING (LOST COMMUNICATION) WITHOUT SUCCESS. | BHA | RSS |  | 09/14/2022 | SSA-5859 | 7.75 | HWYH-1217
1366 | FOT | BHI | 3.5 | 14 Sep 2130 - 0430 | 12837 | 902168 | LOST SIGNAL FROM MWD-GR | BHA | MWD |  | 09/14/2022 | SSA-5971 | 3.5 | HWYH-1215
1367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/14/2022 | SSA-5971 | Hrs | HWYH-1215
1368 | FOT | RIG | 2.5 | 14 Sep 0930 - 1230 | 12360 | 902166 | SAVER SUB WASHED OUT WHILE DRILLING 8"3/8 HOLE SECTION | DSF | STRG |  | 09/14/2022 | SSA-5971 | 2.5 | HWYH-1215
1369 | FOT | BHI | 3.5 | 14 Sep 2130 - 0430 | 12837 | 902168 | LOST SIGNAL FROM MWD-GR | BHA | MWD |  | 09/14/2022 | SSA-5971 | 3.5 | HWYH-1215
1370 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | ADC-12 | Hrs | ABQQ-110
1371 | FOT | GCD | 9 | 15 Sep 1400 - 2300 | 5792 | 902236 | GYRO TOOLS FAILURE | SURV | GYRO |  | 09/15/2022 | ADC-12 | 9 | ABQQ-110
1372 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | ADC-41L | Hrs | SDGM-1244
1373 | MATL | WUD | 2.5 | 15 Sep 0600 - 0830 | 11149 | 902210 | WHILE INSPECTING MPD EQUIPMENT BEFORE RCD PRESSURE TEST FOUND THAT MANUAL VALVE AND HCR VALVE WERE RIGGED UP WITH HCR INSTALLED ON INSIDE AND MANUAL VALVE INSTALLED ON OUT SIDE. DISCONNECTED VALVES AND REINSTALLED CORRECTLY. | WO | NA |  | 09/15/2022 | ADC-41L | 2.5 | SDGM-1244
1374 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | ADC-43L | Hrs | UTMN-3118
1375 | XTTE | SLL | 2.5 | 15 Sep 0230 - 0500 | 11321 | 902217 | DRIFT WITH 3.625" (GAUGE CUTTER) TO 11,321 FT - HELD UP & UNABLE TO PASS THRU SEAL ASSEMBLY MULE SHOE. CHANGE TO 3.5" DRIFT - NO SUCCESS, | JF | SLICK |  | 09/15/2022 | ADC-43L | 2.5 | UTMN-3118
1376 | 13097 | 8858 | TI | E | 4648 | STDP | RIH SLB WL MC LOGGING TOOL ON 4" DP TO 8858 FT.- CONTROL RUNNING SPEED @ 2 MINS SLIP-TO-SLIP.- RIH WITH DRIFTED 4" DP.- FILL & BREAK CIRC. EVERY 10 STANDS.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 5720 | RIG | 09/15/2022 | ADC-62L | LOG | ANDR-589
1377 | 13097 |  | CIRC | E | 4648 | MPMP | CIRCULATE FOR 2 STRING VOLUMES.- FR=200 GPM; SPP=780 PSI. | 13097 |  | RIG | 09/15/2022 | ADC-62L | LOG | ANDR-589
1378 | 13097 |  | PJSM | E | 4648 | NA | PJSM PRIOR TO R/U WL SHEAVES , CSES. | 13097 |  | TK3 | 09/15/2022 | ADC-62L | LOG | ANDR-589
1379 | 13097 |  | OTH | E | 4648 | NA | R/U WL SHEAVES- M/U CSES, OS, DLG LEG REAMER. | 13097 |  | SWL | 09/15/2022 | ADC-62L | LOG | ANDR-589
1380 | 13097 |  | OTH | E | 4648 | NA | LATCH AS PER SLB WL ENGINEER INSTRUCTION : CONFIRMED LATCH.- INSTALL CLAMP ON SES.- PULL TEST AT 3500LBS | 13097 |  | SWL | 09/15/2022 | ADC-62L | LOG | ANDR-589
1381 | 13097 | 13082 | TI | E | 4648 | STDP | RIH TCL MC LOGGING TOOL F/ 8,958 FT TO 13,082 FT.- RUNNING SPEED = 3 MIN/STAND SLIP TO SLIP.- MONITOR THE WELL WITH TRIP TANK.- FILL THE STRING AFTER 10 STDS. | 13097 | 8958 | RIG | 09/15/2022 | ADC-62L | LOG | ANDR-589
1382 | 13097 | 9097 | LOG | E | 4648 | WLT | LOG UP WL MULTI ARM CALIPER LOG AS PER SLB WL INSTRUCTION FROM 13,082 FT TO 9,097 FT.- LOGGING SPEED = 3 MINS SLIP-TO-SLIP.- OPEN HOLE IN GOOD CONDITION.- POOH STRING DRY | 13097 | 13082 | SWL | 09/15/2022 | ADC-62L | LOG | ANDR-589
1383 | 13097 |  | OTH | E | 4648 | NA | UNLATCH PWCH AS PER SLB WL ENG INSTRUCTION. POOH PWCH & CABLE ...IN PROGRESS AT RPT- REMOVE CLAMP.- MONITOR WELL ON TRIP TANK - WELL STATIC | 13097 |  | SWL | 09/15/2022 | ADC-62L | LOG | ANDR-589
1384 | 36.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RUN SLB CALLIPER LOG TOOL | 24 | 4648 | 14 Sep 1615 | 09/15/2022 | ADC-62L | Type | ANDR-589
1385
1386
1387 | 10376 | 10215 | LOG | E | 4627 | WLT | SLB WL TAKING SAMPLING AS PER RMD REQUEST.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. CORRELATION PASSES TO SET THE TOOL DEPTH WHILE MOVING DOWN. NO SIGNIFICANT INCREASE DURING STICK TEST.- MAX STATIONARY TIME: 4 HRS.- SAMPLE #2 (UFDR FM) @ 10,205 FT. (TOTAL 4 SESSIONS) VOL PUMPED TO WELL BORE: 201 L.- MONITOR WELL ON TRIP TANK. | 10376 | 10205 | SWL | 09/15/2022 | ADC-68L | LOG | FDHL-174
1388 | 10376 |  | CIRC | E | 4627 | MPMP | RIH F/ 10,205 FT TO 10,318 FT & CIRC W/ 150 GPM OH BOTTOM TO CSG SHOE. MW IN & OUT: 75 PCF.- FLOW CHECK. - WELL STATIC. | 10376 |  | RIG | 09/15/2022 | ADC-68L | LOG | FDHL-174
1389 | 10376 | 6085 | TO | E | 4627 | STDP | POOH TLC RUN #3 F/ 10,318 FT TO 6,085 FT @ CSG SHOE. WL SES ABOVE RT. POOH SPEED=3 MIN/STD SLIP TO SLIP.- FLOW CHECK AFTER 5 STDS, WELL STATIC.- MONITOR WELL ON TRIP TANK. | 10376 | 10318 | RIG | 09/15/2022 | ADC-68L | LOG | FDHL-174
1390 | 10376 |  | CIRC | E | 4627 | MPMP | CLOSE UPPER RAMS & CIRC W/ 150 GPM THRU THE CHOKE. MW IN & OUT 75 PCF. | 10376 |  | RIG | 09/15/2022 | ADC-68L | LOG | FDHL-174
1391 | 170 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 24 | 4627 | 08 Sep 0300 | 09/15/2022 | ADC-68L | Type | FDHL-174
1392
1393
1394 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | ADES-798 | Hrs | HRDH-2354
1395 | FOT | RIG | 1 | 15 Sep 0400 - 0500 | 3259 | 902218 | TDS MALFUNCTION, TROUBLESHOOT ISSUE. | RR | TDS |  | 09/15/2022 | ADES-798 | 1 | HRDH-2354
1396 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | ADM-657 | Hrs | SFNY-1228
1397 | HERR | ARM | 101.5 | 11 Sep 2330 - 0500 | 4233 | 902063 | RIH W/ GS RETRIEVAL TOOL TO RETRIEVE SCHLUMBERGER M/E TUBING PLUG, UNABLE TO PASS 4220', M/U 2.5" & 3" SAND BAILERS REMOVING GREASE LIKE SLUDGE FROM TOP OF ME PLUG JUNK TRAPPER TOP @ 4233'. CONTINUE TO RUN SLICK LINE WITH VARIOUS CONFIGURATIONS & OPTIONS IN ATTEMPT TO RETRIEVE ME PLUG JUNK BASKET & PRONG. | TF | TBG |  | 09/15/2022 | ADM-657 | 24 | SFNY-1228
1398 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | ARO-2001 | Hrs | BRRI-91
1399 | FOT | SJT | 9 | 15 Sep 2000 - 0500 | 0 | 902211 | TRIED TO START ACID PUMP FOR CT PICKLING BUT FOUND PUMP FAILURE | TF | CTPMP |  | 09/15/2022 | ARO-2001 | 9 | BRRI-91
1400 | OTH | RIG | 16 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/15/2022 | ENS-108 | 16 | ZULF-2015
1401 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | ENS-108 | Hrs | ZULF-2015
1402 | FPMP | RIG | 29 | 14 Sep 0800 - 1300 | 7381 | 902164 | MUD PUMP #1 PRESSURE DROPPED & MUD PUMP #2 WAS UNABLE TO MAINTAIN SUFFICIENT FLOW RATE DUE TO BELT SLIPPAGE. | RR | MPMP |  | 09/15/2022 | ENS-108 | 8 | ZULF-2015
1403 | OTH | RIG | 16 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/15/2022 | ENS-108 | 16 | ZULF-2015
1404 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | EXL-IVA | Hrs | ZULF-2041
1405 | GRF | RIG | 276.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/15/2022 | EXL-IVA | 24 | ZULF-2041
1406 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | NBR-591S | Hrs | HRDH-2313
1407 | FOT | RIG | 3 | 15 Sep 1100 - 1400 | 165 | 902209 | LOST COMMUNICATION WITH TDS, TROUBLESHOOT AND FIX SAME. | RR | TDS |  | 09/15/2022 | NBR-591S | 3 | HRDH-2313
1408 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | PA-326S | Hrs | SHDN-22
1409 | FOT | RIG | 4.5 | 15 Sep 1230 - 1700 | 825 | 902200 | HAD FAILURE IN PRAGMAA DURING RUN 7" LINER. | RR | CATW |  | 09/15/2022 | PA-326S | 4.5 | SHDN-22
1410 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | PA-622S | Hrs | UTMN-3600
1411 | FOT | CRT | 76.5 | 11 Sep 2100 - 0900 | 12803 | 902026 | ATTEMPTED 4 TIMES TO PASS THRU 4 1/2" LINER HGR (DIFFERENT SPEED, INCREASE SLACK-OFF) WITHOUT SUCCESS. ADDITIONAL CLEAN OUT TRIP IS NEED IT. | TF | SCRP |  | 09/15/2022 | PA-622S | 4 | UTMN-3600
1412 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | PA-785S | Hrs | QTIF-269
1413 | FOT | RIG | 11.5 | 15 Sep 0700 - 1830 | 13552 | 902177 | RIG TDS WASH PIPE LEAKS | RR | TDS |  | 09/15/2022 | PA-785S | 11.5 | QTIF-269
1414 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | PA-861S | Hrs | HRDH-1973
1415 | FOT | SCP | 117 | 11 Sep 0730 - 0500 | 16845 | 902099 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/15/2022 | PA-861S | 24 | HRDH-1973
1416 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | PN-9 | Hrs | MRJN-673
1417 | FOT | RIG | 12 | 15 Sep 1200 - 0000 | 15702 | 902208 | FRANKS CASING MAIN & BACK UP TONG FAIL WHEN RUNNINGF 7" CASING | TF | CTRQ |  | 09/15/2022 | PN-9 | 12 | MRJN-673
1418 | IPDF | ARN | .5 | 15 Sep 0430 - 0500 | 9750 | 902215 | BAD RESULT ON STIKY TEST IN OPEN HOLE | MUD | NA |  | 09/15/2022 | SINO-29N | .5 | SFNY-2005
1419 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SINO-29N | Hrs | SFNY-2005
1420 | IPDF | ARN | 1.75 | 15 Sep 1345 - 1530 | 8175 | 902204 | BAD RESULT ON STIKY TEST IN OPEN HOLE | MUD | NA |  | 09/15/2022 | SINO-29N | 1.75 | SFNY-2005
1421 | IPDF | ARN | 2.5 | 15 Sep 1630 - 1900 | 9700 | 902205 | BAD RESULT ON STIKY TEST IN OPEN HOLE | MUD | NA |  | 09/15/2022 | SINO-29N | 2.5 | SFNY-2005
1422 | IPDF | ARN | 7.5 | 15 Sep 2000 - 0330 | 10879 | 902206 | INADEQUATE PROPERTIES OF MUD , SHEAR MUD AT HIGH RATE AND CHC | MUD | NA |  | 09/15/2022 | SINO-29N | 7.5 | SFNY-2005
1423 | IPDF | ARN | .5 | 15 Sep 0430 - 0500 | 9750 | 902215 | BAD RESULT ON STIKY TEST IN OPEN HOLE | MUD | NA |  | 09/15/2022 | SINO-29N | .5 | SFNY-2005
1424 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SINO-33L | Hrs | HRDH-1542
1425 | FOT | RIG | 2.5 | 15 Sep 0230 - 0500 | 2281 | 902259 | WHILE DRILLING AT 2,281 FT TDS STOPPED ROTATION. NO COMMUNICATION BETWEEN TDS AND DRILLER CABIN. - TROUBLE SHOOTING ON TDS COMMUNICATION ISSUE, NO SUCCESS - FAULT IN TDS PANEL. | RR | TDS |  | 09/15/2022 | SINO-33L | 2.5 | HRDH-1542
1426 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SINO21 | Hrs | ABQQ-575
1427 | XTTE | SDM | 7 | 15 Sep 1900 - 0500 | 11743 | 902212 | MWD SIGNAL ISSUE | TF | LWD |  | 09/15/2022 | SINO21 | 7 | ABQQ-575
1428 | FOT | HUD | 2.25 | 15 Sep 0245 - 0500 | 11178 | 902213 | HALLIBURTON RCD BEARING FAILURE. | TF | UBDO |  | 09/15/2022 | SND-1501 | 2.25 | HWYH-89
1429 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SND-1501 | Hrs | HWYH-89
1430 | FOT | RIG | 48 | 13 Sep 2200 - 2200 | 11022 | 902158 | REPAIR MUD PUMP#2 | RR | MPMP |  | 09/15/2022 | SND-1501 | 17 | HWYH-89
1431 | FOT | HUD | 2.25 | 15 Sep 0245 - 0500 | 11178 | 902213 | HALLIBURTON RCD BEARING FAILURE. | TF | UBDO |  | 09/15/2022 | SND-1501 | 2.25 | HWYH-89
1432 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SND-2001 | Hrs | HWYH-1229
1433 | FOT | RIG | 3.5 | 15 Sep 0100 - 0430 | 10226 | 902258 | TDS WOULD NOT ROTATE DRILL STRING | RR | TDS |  | 09/15/2022 | SND-2001 | 3.5 | HWYH-1229
1434 | FOT | GOC | .5 | 15 Sep 0400 - 0430 | 8590 | 902261 | AL-GHAITH SPIDER SLIPS FAIL TO OPERATE. | TF | CTRQ |  | 09/15/2022 | SND-2009 | .5 | SAHB-101
1435 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SND-2009 | Hrs | SAHB-101
1436 | FOT | GOC | 1 | 15 Sep 1400 - 1500 | 2620 | 902199 | AL-GHAITH FIX LEAK ON CRT HYD HOSE. | TF | CTRQ |  | 09/15/2022 | SND-2009 | 1 | SAHB-101
1437 | FOT | GOC | .5 | 15 Sep 0400 - 0430 | 8590 | 902261 | AL-GHAITH SPIDER SLIPS FAIL TO OPERATE. | TF | CTRQ |  | 09/15/2022 | SND-2009 | .5 | SAHB-101
1438 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SND-2010 | Hrs | MNIF-868
1439 | FOT | SDD | 29 | 14 Sep 1630 - 2130 | 6032 | 902165 | WHILE ATTEMPTING TO SLIDE HAVE MOTOR STALLING EVENTS W/ NIL ROP | BHA | MMOT |  | 09/15/2022 | SND-2010 | 16.5 | MNIF-868
1440 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SP-121 | Hrs | BRRI-522
1441 | FOT | RIG | 2 | 15 Sep 1300 - 1500 | 9662 | 902207 | RIG TROUBLESHOOT TDS COOLING FAN MOTOR & FIX SAME. | RR | TDS |  | 09/15/2022 | SP-121 | 2 | BRRI-522
1442 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SSA-5859 | Hrs | HWYH-1217
1443 | FOT | SPS | 23.25 | 14 Sep 2115 - 2030 | 5584 | 902171 | SPERRY SUN RSS TOOL FAILURE. TROUBLESHOOTING (LOST COMMUNICATION) WITHOUT SUCCESS. | BHA | RSS |  | 09/15/2022 | SSA-5859 | 15.5 | HWYH-1217
1444 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | SSA-5969 | Hrs | UTMN-3148
1445 | HERR | CAM | 2 | 15 Sep 0900 - 1100 | 9700 | 902201 | EXCESS TIME TO SET SLIPS ON WELLHEAD | WH | WH |  | 09/15/2022 | SSA-5969 | 2 | UTMN-3148
1446 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/15/2022 | V141A | Hrs | MRJN-3024
1447 | FOT | SCD | 2 | 15 Sep 2030 - 2230 | 2432 | 902257 | EXCESSIVE TIME TO TAKE GWD SURVEYS DUE TO REPETITIVE FAILURE OF SCIENTIFIC GWD. | TF | GYRO |  | 09/15/2022 | V141A | 2 | MRJN-3024
1448 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ADC-32 | Hrs | ANDR-1010
1449 | FOT | RIG | 6 | 16 Sep 0500 - 1100 | 12645 | 902250 | HAD STAND PIPE MANIFOLD LEAK. | RR | CSYS |  | 09/16/2022 | ADC-32 | 6 | ANDR-1010
1450 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ADC-34 | Hrs | UTMN-2309
1451 | FOT | RIG | 2 | 16 Sep 1600 - 1930 | 12129 | 902246 | OBSERVED MUD LEAK AT HAMMER UNION CONNECTION ON STAND PIPE MANIFOLD JUMPER HOSE. | RR | CSYS |  | 09/16/2022 | ADC-34 | 2 | UTMN-2309
1452 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ADC-43L | Hrs | UTMN-3118
1453 | XTTE | SLL | 26.5 | 15 Sep 0230 - 0500 | 11321 | 902217 | DRIFT WITH 3.625" (GAUGE CUTTER) TO 11,321 FT - HELD UP & UNABLE TO PASS THRU SEAL ASSEMBLY MULE SHOE. CHANGE TO 3.5" DRIFT - NO SUCCESS, | JF | SLICK |  | 09/16/2022 | ADC-43L | 24 | UTMN-3118
1454 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ADC-56L | Hrs | UTMN-3069
1455 | FOT | SCP | 24 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY, WC LEAKED. | TF | CHAMP |  | 09/16/2022 | ADC-56L | 24 | UTMN-3069
1456 | 13097 |  | OTH | E | 4648 | NA | CONTINUE POOH PWCH & CABLE- R/D WL SHEAVES- R/D CSES.- R/D X/O'S, DLG LEG REAMER.- MONITOR WELL ON TRIP TANK. | 13097 |  | SWL | 09/16/2022 | ADC-62L | LOG | ANDR-589
1457 | 13097 |  | CIRC | E | 4648 | MPMP | CIRCULATE 1.5 ANNULUS VOL & CONDITION MUD- FR:260 .SPP: 1480 PSI. FLOW CHECK- WELL STATIC. | 13097 |  | RIG | 09/16/2022 | ADC-62L | LOG | ANDR-589
1458 | 13097 | 5486 | TO | E | 4648 | STDP | POOH TLC CAL LOGGING TOOLS ON 4" DP TO 5,486 FT.- CONTROL POOH SPEED @ 2 MINS SLIP-TO-SLIP.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 9030 | RIG | 09/16/2022 | ADC-62L | LOG | ANDR-589
1459 | 13097 |  | RR | E | 4648 | TDS | SERVICE TDS AND CHECK DROP OBJECT- GREASE MONORAIL. | 13097 |  | RIG | 09/16/2022 | ADC-62L | LOG | ANDR-589
1460 | 13097 | 75 | TO | E | 4648 | STDP | POOH TLC CAL LOGGING TOOLS TO 75 FT (BELOW BHA).- CONTROL POOH SPEED @ 2 MINS SLIP-TO-SLIP.- MONITOR WELL ON TRIP TANK - OK.FLOW CHECK- WELL STATIC. | 13097 | 5486 | RIG | 09/16/2022 | ADC-62L | LOG | ANDR-589
1461 | 13097 |  | OTH | E | 4648 | NA | POOH & L/D SLB WL LOGGING TOOL.- MONITOR THE WELL WITH TRIP TANK. | 13097 |  | SWL | 09/16/2022 | ADC-62L | LOG | ANDR-589
1462 | 13097 |  | PJSM | C | 4708 | STRG | PJSM PRIOR TO P/U AND M/U REAMING BHA. | 13097 |  | RIG | 09/16/2022 | ADC-62L | CT | ANDR-589
1463 | 13097 |  | HT | C | 4708 | BHA | P/U, M/U & RIH REAMING BHA TO 417 FT.- 6-1/8" SMITH RR PDC ( M613B;SN/RJ1265, +3 X13 )- 6 1/8" NBRR + 1 JT X 4 3/4" DC- 6 1/8" STRR + 1 JT X 4 3/4" DC- XO + 1 JT X 4" HWDP +6 1/8" DLR- 4 JTS X 3" HWDP (FROM PIPE RACK)- 6-1/8 DLG JAR- 6 JTS X 4" HWDP (FROM PIPE RACK)- MONITOR THE WELL WITH TRIP TANK | 13097 |  | RIG | 09/16/2022 | ADC-62L | CT | ANDR-589
1464 | 13097 | 3730 | TI | C | 4708 | STDP | RIH 6-1/8" REAMING TRIP BHA F/ 417 FT TO 3,730 FT.- RIH SPEED: 20.5 STDS/HR.- FILL UP STRING EVERY 20 STDS.- PRECAUTIONARY PASS 7" TOL @ 2,733' - OK.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 417 | RIG | 09/16/2022 | ADC-62L | CT | ANDR-589
1465 | 13097 |  | RR | C | 4708 | DWKS | SLIP & CUT DRILLING LINE- MONITOR WELL ON TRIP TANK, OK. | 13097 |  | RIG | 09/16/2022 | ADC-62L | CT | ANDR-589
1466 | 13097 | 6931 | TI | C | 4708 | STDP | RIH 6-1/8" REAMING BHA F/ 3,730 FT TO 6,931 FT.- RIH SPEED: 20 STDS/HR.- FILL UP STRING EVERY 20 STDS.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 3730 | RIG | 09/16/2022 | ADC-62L | CT | ANDR-589
1467 | 13097 | 8479 | LDP | C | 4708 | STRG | CONT RIH 6-1/8" REAMING BHA ON 4" HWDP SINGLE TO 8,479 FT.- P/U 41 JNTS OF 4" HWDP FROM PIPE RACK- P/U 3 STANDS OF 4" HWDP FROM MAST.- MONITOR WELL ON TRIP TANK, OK. | 13097 | 6931 | RIG | 09/16/2022 | ADC-62L | CT | ANDR-589
1468 | 13097 | 9097 | TI | C | 4708 | STDP | RIH 6-1/8" REAMING BHA F/ 8,479 FT FT TO 9,097 FT.- RIH SPEED: 24 STDS/HR.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 8479 | RIG | 09/16/2022 | ADC-62L | CT | ANDR-589
1469 | 13097 | 9907 | RW | C | 4708 | BIT | REAM 6-1/8" OPEN HOLE FROM 9,097' TO 9907'....IN PROGRESS AT RPT.- FR: 280 GPM, SPP: 2675 PSI.- RPM: 80, WOB: 1-2 KLBS, TQ: 2-3 KLB-FT.- NO LOSSES. | 13097 | 9097 | RIG | 09/16/2022 | ADC-62L | CT | ANDR-589
1470 | 14 | OOS | LOG | 4648 | COM | RUN SLB CALLIPER LOG TOOL | HOLE CONDITION TRIP W/REAMING BHA | 14 | 4708 | 16 Sep 0030 | 09/16/2022 | ADC-62L | OOS | ANDR-589
1471
1472
1473
1474 | 10376 |  | CIRC | E | 4627 | MPMP | CONT CIRC W/ 150 GPM THRU THE CHOKE. MW IN & OUT 75 PCF. - FLOW CHECK THRU CHOKE, STATIC, OPEN UPPER PIPE RAMS.- FLOW CHECK. - WELL STATIC. | 10376 |  | RIG | 09/16/2022 | ADC-68L | LOG | FDHL-174
1475 | 10376 | 6440 | TI | E | 4627 | STDP | RIH TLC RUN #3 FROM 6,100 FT TO 6,440 FT. RIH SPEED=3 MIN/STD SLIP TO SLIP.- MONITOR WELL ON TRIP TANK. | 10376 | 6100 | RIG | 09/16/2022 | ADC-68L | LOG | FDHL-174
1476 | 10376 | 6400 | LOG | E | 4627 | WLT | SLB WL TAKING SAMPLING AS PER RMD REQUEST.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. CORRELATION PASSES TO SET THE TOOL DEPTH WHILE MOVING DOWN. NO SIGNIFICANT INCREASE DURING STICK TEST.- MAX STATIONARY TIME: 4 HRS.- SAMPLE #3 (BUMB FM) @ 6,400 FT. (2 SESSIONS) VOL PUMPED TO WELL BORE: 486.94 L. - MONITOR WELL ON TRIP TANK. | 10376 | 6400 | SWL | 09/16/2022 | ADC-68L | LOG | FDHL-174
1477 | 10376 |  | CIRC | E | 4627 | MPMP | RIH BELOW DEEPEST SAMPLING POINT @ 6,550 FT & CIRC HOLE CLEAN W/ 150 GPM , 100% CIRC. MW IN/ OUT 75 PCF. - FLOW CHECK - WELL STATIC. | 10376 |  | RIG | 09/16/2022 | ADC-68L | LOG | FDHL-174
1478 | 10376 | 6100 | TO | E | 4627 | STDP | POOH TLC RUN #3 FROM 6,550 FT TO 6,100 FT. WL SES ABOVE RT. POOH SPEED=3 MIN/STD SLIP TO SLIP.- FLOW CHECK AFTER 5 STDS, WELL STATIC.- MONITOR WELL ON TRIP TANK. | 10376 | 6550 | RIG | 09/16/2022 | ADC-68L | LOG | FDHL-174
1479 | 10376 |  | OTH | E | 4627 | NA | UNLATCH THE CABLE F/ DWCH & RETRIEVE WIRELINE CABLE PWCH. L/D SAME.- SES ABOVE RT, B/O & L/D CSES. R/D WL SHEAVES- MONITOR WELL ON TRIP TANK. | 10376 |  | SWL | 09/16/2022 | ADC-68L | LOG | FDHL-174
1480 | 10376 |  | CIRC | E | 4627 | MPMP | CLOSE UPPER RAMS ON DRILL PIPE BODY & CIRC W/ 300 GPM THRU THE CHOKE. MW IN & OUT 75 PCF.- FLOW CHECK THRU CHOKE, STATIC, OPEN UPPER PIPE RAMS.- FLOW CHECK. - WELL STATIC. | 10376 |  | RIG | 09/16/2022 | ADC-68L | LOG | FDHL-174
1481 | 10376 | 626 | TO | E | 4627 | STDP | POOH TLC LOGGING TOOLS F/ 6,100 FT TO 626 FT. POOH SPEED 3 MIN/STD SLIP TO SLIP.- FLOW CHECK. - WELL STATIC.- MONITOR WELL ON TRIP TANK. | 10376 | 6100 | RIG | 09/16/2022 | ADC-68L | LOG | FDHL-174
1482 | 10376 |  | OTH | E | 4627 | NA | POOH & L/D SLB WL TLC RUN #3 TOOL STRING. ONGOING AT MRT.- MONITOR THE WELL WITH TRIP TANK. | 10376 |  | SWL | 09/16/2022 | ADC-68L | LOG | FDHL-174
1483 | 194 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 24 | 4627 | 08 Sep 0300 | 09/16/2022 | ADC-68L | Type | FDHL-174
1484
1485
1486 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ADES-144 | Hrs | UTMN-3018
1487 | FPMP | RIG | 4.5 | 15 Sep 0300 - 0730 | 11269 | 902276 | REPAIRS ON MUD PUMP 2 & 3. | RR | MPMP |  | 09/16/2022 | ADES-144 | 2.5 | UTMN-3018
1488 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ADM-657 | Hrs | SFNY-1228
1489 | HERR | ARM | 125.5 | 11 Sep 2330 - 0500 | 4233 | 902063 | RIH W/ GS RETRIEVAL TOOL TO RETRIEVE SCHLUMBERGER M/E TUBING PLUG, UNABLE TO PASS 4220', M/U 2.5" & 3" SAND BAILERS REMOVING GREASE LIKE SLUDGE FROM TOP OF ME PLUG JUNK TRAPPER TOP @ 4233'. CONTINUE TO RUN SLICK LINE WITH VARIOUS CONFIGURATIONS & OPTIONS IN ATTEMPT TO RETRIEVE ME PLUG JUNK BASKET & PRONG. | TF | TBG |  | 09/16/2022 | ADM-657 | 24 | SFNY-1228
1490 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ARO-2001 | Hrs | BRRI-91
1491 | FOT | SJT | 31 | 15 Sep 2200 - 0500 | 0 | 902211 | TRIED TO START ACID PUMP FOR CT PICKLING BUT FOUND PUMP FAILURE | TF | CTPMP |  | 09/16/2022 | ARO-2001 | 24 | BRRI-91
1492 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ARO-3002 | Hrs | MRJN-814
1493 | FOT | BHI | 1 | 16 Sep 2300 - 0000 | 9330 | 902270 | BHI LOST MWD SIGNAL | SURV | MS |  | 09/16/2022 | ARO-3002 | 1 | MRJN-814
1494 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ARO-3004 | Hrs | MRJN-2060
1495 | FOT | SWL | .25 | 16 Sep 0915 - 0930 | 6955 | 902249 | RESSURE TEST SLB WIRELINE PCE TO 300/ 2000 PSI - OBSERVE LEAK 9 5/8" X 7" X/OVER FROM SHOOTING NIPPLE TO WIRELINE PCE. CLEAN X/OVER AND M/U SAME | TF | LUB |  | 09/16/2022 | ARO-3004 | .25 | MRJN-2060
1496 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ARO-4001 | Hrs | MRJN-537
1497 | CFFM | ARM | 31.5 | 15 Sep 2130 - 0500 | 7057 | 902242 | HAD TOTAL LOSSES WHILE DRILLING 12-1/4" HOLE. CURE LOSSES WITH CMT PLUG, SET EZSV @ 5902-FT. RE-DRILL 12-1/4" HOLE. | LCIR | SQZ |  | 09/16/2022 | ARO-4001 | 24 | MRJN-537
1498 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | BB-84A | Hrs | MRJN-581
1499 | FOT | RIG | 1 | 16 Sep 1515 - 1615 | 13800 | 902265 | ENCODER FAILURE ON DRAWWORKS "B" MOTOR | RR | DWKS |  | 09/16/2022 | BB-84A | 1 | MRJN-581
1500 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | CG-1 | Hrs | MRJN-741
1501 | FOT | HWP | 13.5 | 16 Sep 1530 - 0500 | 5500 | 902248 | DRILL PIPE CONVEYED LOGGING. BAD ELECTRICAL CONNECTION BETWEEN WIRELING LATCH AND DRILL PIPE CONVEYED LOGGING TOOLS. | TF | WLT |  | 09/16/2022 | CG-1 | 13.5 | MRJN-741
1502 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | DQ-47 | Hrs | KHRS-1739
1503 | LCRW | TK2 | 20 | 15 Sep 2330 - 0000 | 2988 | 902245 | WHILE POOH 12 1/4" ROTARY DRILL BHA F/ 3520' TO 2988', HAD TIGHT SPOT & OVERPULL 25 KLBS. AT 2988' (6TH STAND OFF BTM). RIH FREELY, ATTEMPTED TO POOH, HAD OVERPULL 31 KLBS. AT SAME DEPTH. TRIED TO RIH, DP STUCK. JAR NOT FIRING. | STUK | STRG |  | 09/16/2022 | DQ-47 | 14.5 | KHRS-1739
1504 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | ENS-108 | Hrs | ZULF-2015
1505 | OTH | RIG | 40 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/16/2022 | ENS-108 | 24 | ZULF-2015
1506 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | EXL-IVA | Hrs | ZULF-2041
1507 | GRF | RIG | 300.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/16/2022 | EXL-IVA | 24 | ZULF-2041
1508 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | NA-18S | Hrs | SDGM-444
1509 | HERR | SDM | 12 | 16 Sep 1230 - 0500 | 14201 | 902266 | MISSING MWD SIGNAL, UNABLE TO READ MWD/GR/RSS SIGNALS. | DD | RSS |  | 09/16/2022 | NA-18S | 12 | SDGM-444
1510 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | NBR-797S | Hrs | UTMN-3119
1511 | FOT | SLL | 11.5 | 16 Sep 0500 - 1630 | 11572 | 902247 | RUN W/ 3.688" PR PLUG BODY AS PER SLB S/L. ATTEMPT TO SET SAME IN LOWER R-NIPPLE, OBSERVE OBSTRUCTION, NO SUCCESS, CAN NOT SET THE PR PLUG IN LOWER R-NIPPLE. ATTEMPT TO PULL THE PLUG UP, NO SUCCESS, PLUG IS STUCK. | TF | PLUGN |  | 09/16/2022 | NBR-797S | 11.5 | UTMN-3119
1512 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | PA-218S | Hrs | HRDH-1976
1513 | UXDF | ARN | 9 | 16 Sep 2000 - 0500 | 7387 | 902252 | GOT TOTAL LOSS WHILE DRILLING 12" HOLE @ 7387' (HADRIYA FM). | LCIR | NA |  | 09/16/2022 | PA-218S | 9 | HRDH-1976
1514 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | PA-861S | Hrs | HRDH-1973
1515 | FOT | SCP | 59 | 14 Sep 1800 - 0500 | 16845 | 902241 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/16/2022 | PA-861S | 24 | HRDH-1973
1516 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | PN-9 | Hrs | MRJN-673
1517 | FOT | RIG | 1 | 16 Sep 1415 - 1515 | 7236 | 902243 | HAD MALFUNCTION IN FRANKS CASING POWER UNIT. * TROUBLESHOOT SAME W/ NO PROGRESS, REPLACED SAME WITH B/UP ONE. | TF | CTRQ |  | 09/16/2022 | PN-9 | 1 | MRJN-673
1518 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SCTD-1 | Hrs | UTMN-3189
1519 | FOT | SDM | 10 | 16 Sep 1900 - 0500 | 12746 | 902267 | MWD FAILURE | BHA | MWD |  | 09/16/2022 | SCTD-1 | 10 | UTMN-3189
1520 | 7001 | 5025 | TI | E | 4688 | STHDP | RIH W/ HES W/L TRIPLE COMBO W/ DIELECTRIC OH LOGGING TOOL STRING ON 4" DRIFTED DP/HWDP'S W/ CONTROLLED SPEED ( 1.5 MIN/STD) F/3750 FT TO 5025 FT.- DRIFT 4" DP/HWDP WHILE RIH.- FILL STRING EVERY 10 STANDS USING HES CIRCULATION SUB WITH MUD SCREEN WITH 77 PCF POLYMER MUD.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 3750 | RIG | 09/16/2022 | SINO-12L | LOG | HWYH-518
1521 | 7001 |  | OTH | E | 4688 | NA | HPJSM, R/U HES W/L SHEAVES WHILE CIRCULATE W/4 BPM @ 490 PSI . | 7001 |  | HWP | 09/16/2022 | SINO-12L | LOG | HWYH-518
1522 | 7001 |  | OTH | E | 4688 | NA | CONNECT SES & LINE GUIDE, RIH W/ WET CONNECTOR TO ABOVE CALIPER TOOLS, LATCH WET CONNECTOR TO LATCHING HEAD, CONFIRMED SIGNAL, OK.>> INSTALL CABLE CLAMP, PERFORM TENSION TEST, OK. | 7001 |  | HWP | 09/16/2022 | SINO-12L | LOG | HWYH-518
1523 | 7001 | 6992 | TI | E | 4688 | STHDP | CONT RIH W/ HES W/L TRIPLE COMBO W/ DIELECTRIC OH LOGGING TOOL STRING ON 4" DRIFTED DP/HWDP'S WITH CONTROLLED SPEED F/ 5025 FT TO 6992 FT (9 FT ABOVE TD @ 7001 FT).- CAREFULLY PASS 7" WINDOW.- DRIFT 4" DP/HWDP WHILE RIH.- FILL STRING EVERY 10 STANDS USING HES CIRCULATION SUB WITH MUD SCREEN WITH 77 PCF POLYMER MUD.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 5025 | RIG | 09/16/2022 | SINO-12L | LOG | HWYH-518
1524 | 7001 | 5934 | LOG | E | 4688 | WLT | HES LOG UP WITH TRIPLE COMBO / DIELECTRIC LOGGING TOOLS ON 4" DP/HWDP F/ 6992 T/ 5934 FT ( 810 FT BELOW BOW @ 5124 FT).- RIH TO 6700 FT, RECORD REPEAT PASS FROM 6700 FT TO 6500 FT.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 6991 | HWP | 09/16/2022 | SINO-12L | LOG | HWYH-518
1525 | 7001 |  | OTH | E | 4688 | NA | POOH W/ HES W/L TRIPLE COMBO W/ DIELECTRIC OH LOGGING TOOL STRING W/ CONTROLLED SPEED F/ 6500 TO SES DEPTH @ 5025 FT.- PROCCESS LOGS AND SEND THEM TO RDD.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 |  | HWP | 09/16/2022 | SINO-12L | LOG | HWYH-518
1526 | 7001 |  | OTH | E | 4688 | NA | UNLATCH CABLE HEAD. POOH W/L CABLE TO SIDE ENTRY SUB, DISCONNECT CABLE, R/D SES SUB W/L SPLIT BUSHING.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 |  | HWP | 09/16/2022 | SINO-12L | LOG | HWYH-518
1527 | 7001 | 500 | TO | E | 4688 | STHDP | CONT POOH W/ HES W/L TRIPLE COMBO W/ DIELECTRIC OH LOGGING TOOL STRING ON 4" DP/HWDP'S W/ CONTROLLED SPEED F/ 5025 FT TO 500 FT.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 5025 | RIG | 09/16/2022 | SINO-12L | LOG | HWYH-518
1528 | 7001 |  | WCNT | E | 4688 | NA | FLOW CHECK, WELL STATIC | 7001 |  | RIG | 09/16/2022 | SINO-12L | LOG | HWYH-518
1529 | 7001 |  | OTH | E | 4688 | NA | CONT POOH W/ HES W/L TRIPLE COMBO W/ DIELECTRIC OH LOGGING TOOL STRING ON 4" DP/HWDP'S W/ CONTROLLED SPEED F/ 500 FT TO SURFACE.- L/D HES W/L TRIPLE COMBO W/ DIELECTRIC LOGGING TOOL.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 |  | HWP | 09/16/2022 | SINO-12L | LOG | HWYH-518
1530 | 7001 |  | OTH | E |  | NA | HPJSM, P/U & M/U HES W/L MNR OPEN HOLE LOGGING TOOL STRING, CHECKED SAME- OK.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 |  | HWP | 09/16/2022 | SINO-12L | LOG | HWYH-518
1531 | 7001 | 1600 | TI | E |  | SPHDP | RIH W/ HES W/L NMR OPEN HOLE LOGGING TOOLS TRING ON 4" DRIFTED DP/HWDP'S W/ CONTROLLED SPEED TO 1600 FT.- DRIFT 4" DP/HWDP WHILE RIH.- FILL STRING EVERY 10 STANDS USING HES CIRCULATION SUB WITH MUD SCREEN WITH 77 PCF POLYMER MUD.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 0 | RIG | 09/16/2022 | SINO-12L | DRLG | HWYH-518
1532 | 27 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED HES W/L TRIPLE COMBO & DIELECTRIC OPEN HOLE LOGGING JOB (RECORD UP LOGS FROM 6992 FT TO 5934 FT). | 21 | 4688 | 15 Sep 0100 | 09/16/2022 | SINO-12L | Type | HWYH-518
1533
1534
1535 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SINO-29N | Hrs | SFNY-2005
1536 | IPDF | ARN | 83 | 08 Sep 0500 - 1400 | 10879 | 902076 | BAD RESULT ON STIKY TEST IN OPEN HOLE | MUD | NA |  | 09/16/2022 | SINO-29N | 7.25 | SFNY-2005
1537 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SINO-33L | Hrs | HRDH-1542
1538 | FOT | RIG | 8.5 | 15 Sep 0230 - 1100 | 2281 | 902259 | WHILE DRILLING AT 2,281 FT TDS STOPPED ROTATION. NO COMMUNICATION BETWEEN TDS AND DRILLER CABIN. - TROUBLE SHOOTING ON TDS COMMUNICATION ISSUE, NO SUCCESS - FAULT IN TDS PANEL. | RR | TDS |  | 09/16/2022 | SINO-33L | 6 | HRDH-1542
1539 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SINO21 | Hrs | ABQQ-575
1540 | XTTE | SDM | 17.25 | 15 Sep 1900 - 0500 | 11743 | 902212 | MWD SIGNAL ISSUE | TF | LWD |  | 09/16/2022 | SINO21 | 10.25 | ABQQ-575
1541 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SND-1501 | Hrs | HWYH-89
1542 | FOT | HUD | 26.25 | 15 Sep 0245 - 0500 | 11178 | 902213 | HALLIBURTON RCD BEARING FAILURE. | TF | UBDO |  | 09/16/2022 | SND-1501 | 24 | HWYH-89
1543 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SND-2004 | Hrs | BRRI-1148
1544 | FOT | RIG | 1 | 16 Sep 2015 - 2115 | 1100 | 902269 | REPLACE THE LEAKING HYDRAULIC HOSE ON IRON ROUGHNECK. | RR | HSYS |  | 09/16/2022 | SND-2004 | 1 | BRRI-1148
1545 | FPMP | RIG | 1 | 16 Sep 1230 - 1330 | 6225 | 902263 | REPAIR WASHED HEAD (SWAB) ON #1 PUMP | RR | MPMP |  | 09/16/2022 | SND-2010 | 1 | MNIF-868
1546 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SND-2010 | Hrs | MNIF-868
1547 | FOT | RIG | 6 | 16 Sep 0600 - 1200 | 6209 | 902262 | TROUBLESHOOT DRAWORKS AND TOP-DRIVE I-BOP COMMUNICATIONS | RR | RSYS |  | 09/16/2022 | SND-2010 | 6 | MNIF-868
1548 | FPMP | RIG | 1 | 16 Sep 1230 - 1330 | 6225 | 902263 | REPAIR WASHED HEAD (SWAB) ON #1 PUMP | RR | MPMP |  | 09/16/2022 | SND-2010 | 1 | MNIF-868
1549 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SSA-101 | Hrs | QTIF-526
1550 | WSHO | ARM | 6 | 16 Sep 2300 - 0500 | 125 | 902268 | FILL UP & HYDRO TEST 30" CSG W/ 66 PCF SPUD MUD, OBSERVED MUD LEVEL SLOWLY DROP INSIDE 30" CSG AND SAW SLIGHT RETURN INSIDE CELLAR BESIDE 30" CSG. | CMT | CSG |  | 09/16/2022 | SSA-101 | 6 | QTIF-526
1551 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SSA-5865 | Hrs | FRHH-3
1552 | XTRI | GOC | 2 | 16 Sep 0145 - 0345 | 3348 | 902251 | EXCESS TIME RUNNING CASING DUE TO CASILS BAILS TOO LONG AND WRONG PACKER WEIGHT FOR CRT. | JF | CTRQ |  | 09/16/2022 | SSA-5865 | 2 | FRHH-3
1553 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | SSA-5868 | Hrs | HRDH-2364
1554 | FOT | RIG | 1 | 16 Sep 0600 - 0700 | 6400 | 902240 | HAD TOP DRIVE WASH PIPE LEAK. | RR | TDS |  | 09/16/2022 | SSA-5868 | 1 | HRDH-2364
1555 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/16/2022 | T218 | Hrs | HRDH-1511
1556 | FOT | RIG | 5 | 11 Sep 0200 - 0000 | 7045 | 901970 | STAND PIPE CONNECTION LEAKING | RR | CSYS |  | 09/16/2022 | T218 | 2.5 | HRDH-1511
1557 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADC-15 | Hrs | HRDH-2249
1558 | IDPR | ARM | 27 | 16 Sep 2130 - 0030 | 11126 | 902275 | HIGH TORQUE AND PRESSURE FLUCTUATIONS, TROUBLESHOOT, NEGATIVE. | LROP | BIT |  | 09/17/2022 | ADC-15 | 19.5 | HRDH-2249
1559 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADC-43L | Hrs | UTMN-3118
1560 | HELD | TK3 | 50.5 | 15 Sep 0230 - 0500 | 11321 | 902217 | DRIFT WITH 3.625" (GAUGE CUTTER) TO 11,321 FT - HELD UP & UNABLE TO PASS THRU SEAL ASSEMBLY MULE SHOE & BTM OF LNR TBR. CHANGE TO 3.5" DRIFT - NO SUCCESS. | JF | LINR |  | 09/17/2022 | ADC-43L | 24 | UTMN-3118
1561 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADC-49 | Hrs | HRDH-1934
1562 | FOT | RIG | 2 | 17 Sep 2015 - 2215 | 7215 | 902274 | WHILE DRILLING AT 7,215', HAD SPP DROP & VISUAL LEAK IN TDS S-PIPE HAMMER UNION CONNETION. | RR | TDS |  | 09/17/2022 | ADC-49 | 2 | HRDH-1934
1563 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADC-56L | Hrs | UTMN-3069
1564 | FOT | TK3 | 48 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/17/2022 | ADC-56L | 24 | UTMN-3069
1565 | 13097 | 13097 | RW | C | 4708 | BIT | REAM 6-1/8" OPEN HOLE FROM 9,907' TO 13097' BTM.- FR: 280 GPM, SPP: 2675- 2750 PSI.- RPM: 80, WOB: 1-2 KLBS, TQ: 2-3 KLB-FT.- NO LOSSES. | 13097 | 9907 | RIG | 09/17/2022 | ADC-62L | CT | ANDR-589
1566 | 13097 |  | CIRC | C | 4708 | MPMP | CIRC. HOLE CLEAN.- FR: 280 GPM, SPP: 3400 PSI.- RPM: 100, TQ: 5 -7 KLB-FT.- CIRC 2 X BTM UP.- NO LOSSES.CONDUCT MEETING TO REVIEW MANAGEMNET OF MUD TANKS. VERIFY LINE UP CORRECTLY. | 13097 |  | RIG | 09/17/2022 | ADC-62L | CT | ANDR-589
1567 | 13097 |  | CIRC | C | 4708 | MPMP | DISPLACE WELL TO 85 PCF OBM.- FR: 250 GPM, SPP: 3300-3400 PSI.- RPM: 100, TQ: 5-7 KLB-FT.- NO LOSSES. | 13097 |  | RIG | 09/17/2022 | ADC-62L | CT | ANDR-589
1568 | 13097 |  | CIRC | C | 4708 | MPMP | CIRC TO CONDITION OBM MUD- FR: 280 GPM; SPP: 3300 PSI.- RPM: 100, TQ: 4.5 KLB-FT.- NO LOSSES- RECORD SCR AT THE END OF CIRCFLOW CHECK - WELL STATIC.- ROTATED SRING AT 20 RPM | 13097 |  | RIG | 09/17/2022 | ADC-62L | CT | ANDR-589
1569 | 13097 | 12197 | TO | C | 4708 | BHA | POOH 6-1/8" REAMING BHA F/13,097' TO 12,197'.- POOH AT CONTROLLED SPEED IN OH ON ELEVATORS- OPEN HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK - OKFLOW CHECK - WELL STATIC.- ROTATED SRING AT 20 RPM. | 13097 | 13097 | RIG | 09/17/2022 | ADC-62L | CT | ANDR-589
1570 | 13097 | 9009 | TO | C | 4708 | BHA | POOH 6-1/8" REAMING BHA F/12,197' TO 9,009' (INSIDE 7" SHOE)- POOH AT CONTROLLED SPEED IN OH ON ELEVATORS- OPEN HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK - OK.FLOW CHECK - WELL STATIC. | 13097 | 12197 | RIG | 09/17/2022 | ADC-62L | CT | ANDR-589
1571 | 13097 | 10342 | TI | C | 4708 | BHA | RIH 6-1/8" REAMING TRIP F/ 9,009' TO 10342'....IN PROGRESS AT RPT- RIH AT CONTROLLED SPEED IN OH ON ELEVATORES- OPEN HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK - OK.- RIH WITNESSED BY BAKER COMPLETION ENG. | 13097 | 9009 | RIG | 09/17/2022 | ADC-62L | CT | ANDR-589
1572 | 38 | OOS | Category | DOOS ID | COM | Out of Scope Summary | HOLE CONDITION TRIP W/REAMING BHA | 24 | 4708 | 16 Sep 0030 | 09/17/2022 | ADC-62L | Type | ANDR-589
1573
1574
1575 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADC-67L | Hrs | SDGM-1259
1576 | FOT | RIG | 10.5 | 17 Sep 0900 - 1930 | 11905 | 902316 | OBSERVED LEAK IN ROTARY MUD HOSE | RR | TDS |  | 09/17/2022 | ADC-67L | 10.5 | SDGM-1259
1577 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADES-798 | Hrs | HRDH-2354
1578 | FOT | RIG | 15 | 17 Sep 0600 - 2100 | 3862 | 902300 | TDS MALFUNCTION. STOPPED ROTATION, TROUBLESHOOT ISSUE. NEED TO CHANGE TDS ENCODER. | RR | TDS |  | 09/17/2022 | ADES-798 | 15 | HRDH-2354
1579 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADM-262 | Hrs | MRJN-448
1580 | XTTE | RWC | 3 | 17 Sep 1330 - 1630 | 0 | 902308 | POOR PERFORMANCE FROM WELL TEST EQUIPMENT & CREW LEADS TO EXTRA TIME TO RIG UP & PRESSURE TEST THE FLOW BACK EQUIPMENT. | TF | TESTT |  | 09/17/2022 | ADM-262 | 3 | MRJN-448
1581 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADM-510 | Hrs | ABSF-225
1582 | WTHR | ARM | 4.75 | 17 Sep 1600 - 2045 | 9910 | 902273 | WAIT ON WEATHER TO TAKE ON 76 PCF NACL/NABR BRINE REQUIRED FOR DISPLACEMENT | WON | NA |  | 09/17/2022 | ADM-510 | 4.75 | ABSF-225
1583 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ADM-657 | Hrs | SFNY-1228
1584 | HERR | ARM | 149.5 | 11 Sep 2330 - 0500 | 4233 | 902063 | RIH W/ GS RETRIEVAL TOOL TO RETRIEVE SCHLUMBERGER M/E TUBING PLUG, UNABLE TO PASS 4220', M/U 2.5" & 3" SAND BAILERS REMOVING GREASE LIKE SLUDGE FROM TOP OF ME PLUG JUNK TRAPPER TOP @ 4233'. CONTINUE TO RUN SLICK LINE WITH VARIOUS CONFIGURATIONS & OPTIONS IN ATTEMPT TO RETRIEVE ME PLUG JUNK BASKET & PRONG. | TF | TBG |  | 09/17/2022 | ADM-657 | 24 | SFNY-1228
1585 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ARO-2001 | Hrs | BRRI-91
1586 | FOT | SJT | 32 | 15 Sep 2200 - 0600 | 0 | 902211 | TRIED TO START ACID PUMP FOR CT PICKLING BUT FOUND PUMP FAILURE | TF | CTPMP |  | 09/17/2022 | ARO-2001 | 1 | BRRI-91
1587 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ARO-3001 | Hrs | MRJN-3001
1588 | WTHR | ARM | 29.5 | 16 Sep 2330 - 0500 | 0 | 902302 | WAITING ON WEATHER | WON | NA |  | 09/17/2022 | ARO-3001 | 24 | MRJN-3001
1589 | FOT | CTC | 3.5 | 17 Sep 1500 - 1830 | 215 | 902318 | OBSERVED OIL LEAKING ON 6-3/4" DRILLING JAR. | BHA | JARS |  | 09/17/2022 | ARO-4001 | 3.5 | MRJN-537
1590 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ARO-4001 | Hrs | MRJN-537
1591 | CFFM | ARM | 52 | 15 Sep 2130 - 0500 | 6122 | 902242 | HAD TOTAL LOSSES WHILE DRILLING 12-1/4" HOLE. CURE LOSSES WITH CMT PLUG, SET EZSV @ 5902-FT. RE-DRILL 12-1/4" HOLE. | LCIR | SQZ |  | 09/17/2022 | ARO-4001 | 20.5 | MRJN-537
1592 | FOT | CTC | 3.5 | 17 Sep 1500 - 1830 | 215 | 902318 | OBSERVED OIL LEAKING ON 6-3/4" DRILLING JAR. | BHA | JARS |  | 09/17/2022 | ARO-4001 | 3.5 | MRJN-537
1593 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | BCTD-4 | Hrs | HRDH-2421
1594 | CWEL | ARM | 5.5 | 17 Sep 2300 - 0430 | 11124 | 902307 | OBSERVED 15KLBS. UP-DRAG FROM BOTTOM, FREE TO RIH UNTIL 11,124 FT. (CT STUCK) WORK STUCK CT UNTIL FREE. | BHS | NA |  | 09/17/2022 | BCTD-4 | 5.5 | HRDH-2421
1595 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | CG-1 | Hrs | MRJN-741
1596 | FOT | HWP | 28 | 16 Sep 1530 - 1930 | 5500 | 902248 | DRILL PIPE CONVEYED LOGGING. BAD ELECTRICAL CONNECTION BETWEEN WIRELING LATCH AND DRILL PIPE CONVEYED LOGGING TOOLS. | TF | WLT |  | 09/17/2022 | CG-1 | 14.5 | MRJN-741
1597 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | ENS-108 | Hrs | ZULF-2015
1598 | OTH | RIG | 64 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/17/2022 | ENS-108 | 24 | ZULF-2015
1599 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | EXL-IVA | Hrs | ZULF-2041
1600 | GRF | RIG | 324.25 | 04 Sep 1645 - 0500 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/17/2022 | EXL-IVA | 24 | ZULF-2041
1601 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | JACK-202 | Hrs | THRY-829
1602 | FOT | RIG | 4 | 17 Sep 1730 - 2130 | 5780 | 902306 | WAIT TO REPAIR GEAR SHIF ON CARRIER FOR DRAWWORKS. | RR | DWKS |  | 09/17/2022 | JACK-202 | 4 | THRY-829
1603 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | NA-18S | Hrs | SDGM-444
1604 | HERR | SDM | 25.5 | 16 Sep 1230 - 0500 | 14201 | 902266 | MISSING MWD SIGNAL, UNABLE TO READ MWD/GR/RSS SIGNALS. | DD | RSS |  | 09/17/2022 | NA-18S | 13.5 | SDGM-444
1605 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | NBR-20S | Hrs | HMYM-433512
1606 | FPMP | RIG | 7 | 16 Sep 2115 - 1330 | 10530 | 902301 | EXCESSIVE PUMP FAILURES. | RR | MPMP |  | 09/17/2022 | NBR-20S | 5 | HMYM-433512
1607 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | PA-861S | Hrs | HRDH-1973
1608 | FOT | SCP | 83 | 14 Sep 1800 - 0500 | 16845 | 902241 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/17/2022 | PA-861S | 24 | HRDH-1973
1609 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | SCTD-1 | Hrs | UTMN-3189
1610 | FOT | SDM | 14.5 | 16 Sep 1900 - 0930 | 12746 | 902267 | MWD FAILURE | BHA | MWD |  | 09/17/2022 | SCTD-1 | 4.5 | UTMN-3189
1611 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | SINO-29N | Hrs | SFNY-2005
1612 | PCPF | ARM | 13 | 17 Sep 1600 - 0500 | 10879 | 902272 | REAPEATED OPERATION (SECOND OPERATION NOT COVERED IN PROGRAM & SHOULD HAVE BEEN DONE TOGETHER WITH PRESSURE POINT LOGS IN SAME RUN) | TH | NA |  | 09/17/2022 | SINO-29N | 13 | SFNY-2005
1613 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | SINO21 | Hrs | ABQQ-575
1614 | XTTE | SDM | 41.25 | 15 Sep 1900 - 0500 | 11743 | 902212 | MWD SIGNAL ISSUE | TF | LWD |  | 09/17/2022 | SINO21 | 24 | ABQQ-575
1615 | FOT | RIG | 2.75 | 17 Sep 2215 - 0100 | 11707 | 902305 | STAND PIPE HOSE FAILURE. | TF | SFLN |  | 09/17/2022 | SND-1501 | 2.75 | HWYH-89
1616 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | SND-1501 | Hrs | HWYH-89
1617 | FOT | HUD | 29.75 | 15 Sep 0245 - 0830 | 11178 | 902213 | HALLIBURTON RCD BEARING FAILURE. | TF | UBDO |  | 09/17/2022 | SND-1501 | 3.5 | HWYH-89
1618 | FOT | RIG | 2.75 | 17 Sep 2215 - 0100 | 11707 | 902305 | STAND PIPE HOSE FAILURE. | TF | SFLN |  | 09/17/2022 | SND-1501 | 2.75 | HWYH-89
1619 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | SNT-025 | Hrs | SFNY-517
1620 | WTHR | ARM | 18 | 17 Sep 1100 - 0500 | 0 | 902299 | WAIT ON HIGH TIDE AND WEATHER FOR BOAT TO CROSS PIPE LINE. | WON | NA |  | 09/17/2022 | SNT-025 | 18 | SFNY-517
1621 | FOT | RIG | 7 | 17 Sep 2200 - 0500 | 123 | 902304 | RIG TDS UNABLE TO ROTATE, RIG ELECTRICIAN TROUBLE SHOOT AND REPLACED TDS CONTROL UNIT INVERTERS. | RR | TDS |  | 09/17/2022 | SSA-101 | 7 | QTIF-526
1622 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | SSA-101 | Hrs | QTIF-526
1623 | CCAT | WCM | 18 | 16 Sep 2300 - 1700 | 125 | 902268 | WEATHERFORD DP DART PLUG FAIL, STING OUT ISC, DP DART PLUG UNABLE TO HOLD MUD LEVEL. WHILE HYDRO TEST 30" CSG W/ 66 PCF SPUD MUD, OBSERVED MUD LEVEL SLOWLY DROP INSIDE 30" CSG AND SAW SLIGHT RETURN INSIDE CELLAR BESIDE 30" CSG. . | TF | CSTR |  | 09/17/2022 | SSA-101 | 12 | QTIF-526
1624 | FOT | RIG | 7 | 17 Sep 2200 - 0500 | 123 | 902304 | RIG TDS UNABLE TO ROTATE, RIG ELECTRICIAN TROUBLE SHOOT AND REPLACED TDS CONTROL UNIT INVERTERS. | RR | TDS |  | 09/17/2022 | SSA-101 | 7 | QTIF-526
1625 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | SSA-5865 | Hrs | FRHH-3
1626 | FOT | GOC | 3 | 17 Sep 1630 - 1930 | 10200 | 902271 | CRT REQUIRING EXCESSIVE WEIGHT TO ENGAGE AND DISENGAGE FULLY. CRT REQUIRES FRICTION TO HOLD THE BODY STATIONARY WHILE MADREL ROTATES TO ENGAGE THE DIES. FIRST 7000' OF THE RUN THE CRT WORKED CORRECTLY MAXIMUM REQUIRED SLACK OFF WAS 3K BUT FURTHER ON THE CRT REQUIRED MORE AND MORE SLACK OFF WEIGHT TO DISENGAGE FULLY. BUT THIS DESTROYED THE PLASTIC PROTECTORS THAT ALGHAITH USES FOR PACKER PROTECTORS SO WE HAVE TO PICK UP ENOUGH TO INSERT ANOTHER PIECE TO CREATE FRICTION THEN SET DOWN SO WE CAN DISENGAGE THE CRT. | TF | CTRQ |  | 09/17/2022 | SSA-5865 | 3 | FRHH-3
1627 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/17/2022 | WCL-83 | Hrs | MRJN-836
1628 | FOT | BC | 24 | 17 Sep 0500 - 0500 | 268 | 902303 | OBSERVED BAKERHUGHES TRSSSV ON MRJN-836 NOT ABLE TO HOLD PRESSURE BELOW THE TRSSSV FLAPPER PIROR HANDOVER PLATFORM TO PRODUCTION. | TF | SSSV |  | 09/17/2022 | WCL-83 | 24 | MRJN-836
1629 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | ADC-43L | Hrs | UTMN-3118
1630 | HELD | TK3 | 74.5 | 15 Sep 0230 - 0500 | 11321 | 902217 | DRIFT WITH 3.625" (GAUGE CUTTER) TO 11,321 FT - HELD UP & UNABLE TO PASS THRU SEAL ASSEMBLY MULE SHOE & BTM OF LNR TBR. CHANGE TO 3.5" DRIFT - NO SUCCESS. | JF | LINR |  | 09/18/2022 | ADC-43L | 24 | UTMN-3118
1631 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | ADC-56L | Hrs | UTMN-3069
1632 | FOT | TK3 | 72 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/18/2022 | ADC-56L | 24 | UTMN-3069
1633 | 13097 | 13097 | TI | C | 4708 | STDP | RIH 6-1/8" REAMING TRIP F/ 10,342' TO 13097'.- RIH AT CONTROLLED SPEED IN OH ON ELEVATORES- OPEN HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK - OK.- RIH WITNESSED BY BAKER COMPLETION ENG. | 13097 | 10342 | RIG | 09/18/2022 | ADC-62L | CT | ANDR-589
1634 | 13097 |  | CIRC | C | 4708 | MPMP | CIRC. & CONDITION OBM AS PER ARAMCO- FR: 250 GPM; SPP: 2,800 PSI; RPM: 100; TQ: 3-4KLB.FT- PERFORM CHEMICAL TREATMENT TO OBM AS PER ARAMCO.PERFORM FLOW CHECK, STATIC- ROTATE STRING 15 RPM- MONITOR WELL THRU TT, OK- TAKE SCR | 13097 |  | RIG | 09/18/2022 | ADC-62L | CT | ANDR-589
1635 | 13097 | 12197 | TO | C | 4708 | BHA | POOH 6-1/8" REAMING BHA F/13,097' TO 12,197'.- POOH AT CONTROLLED SPEED IN OH ON ELEVATORS- OPEN HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK - OK.FLOW CHECK - WELL STATIC.- ROTATED SRING AT 20 RPM | 13097 | 13097 | RIG | 09/18/2022 | ADC-62L | CT | ANDR-589
1636 | 13097 | 9009 | TO | C | 4708 | BHA | POOH 6-1/8" REAMING BHA F/12,197' TO 9,009' (INSIDE 7"SHOE)- POOH AT CONTROLLED SPEED IN OH ON ELEVATORS- OPEN HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 12197 | RIG | 09/18/2022 | ADC-62L | CT | ANDR-589
1637 | 13097 |  | RR | C | 4708 | TDS | SERVICE TDS AND CHEKC FOR DROP SURVEYFLOW CHECK- WELL STATIC- PUMP SLUG- DROP 2.25" HOLLOW DRIFT | 13097 |  | RIG | 09/18/2022 | ADC-62L | CT | ANDR-589
1638 | 13097 | 478 | TO | C | 4708 | STDP | POOH 6-1/8" REAMING BHA F/ 9,009' TO 478'.- TRIPPING SPEED: SPH- MONITOR WELL ON TRIP TANK - OK.FLOW CHECK- WELL STATIC | 13097 | 9009 | RIG | 09/18/2022 | ADC-62L | CT | ANDR-589
1639 | 13097 |  | HT | C | 4708 | BHA | POOH & L/D 6-1/8" REAMING BHA- R/B 4" HWDP STANDS.- L/D 4-3/4" DC, 6-1/8" DLR, 6-1/8" STRR, 6-1/8" NBRR, & PDC BIT.- RECOVER 2.25" HOLLOW DRIFT FROM BHA.- BIT DULL GRADE: 1-1-WT-A-X-NO- BHA.- MONITOR WELL ON TRIP TANK - OK.HOUSEKEEPING AND CLEAR RIG FLOOR. | 13097 |  | RIG | 09/18/2022 | ADC-62L | CT | ANDR-589
1640 | 13097 |  | HT | C | 4752 | PEL | R/U TESCO 4-1/2" TBG RUNNING EQUIPMENT.- R/U POWER TONG WITH JAM UNIT & FUNCTION TEST SAME. | 13097 |  | TSC | 09/18/2022 | ADC-62L | COMP | ANDR-589
1641 | 13097 |  | PJSM | C | 4752 | PKR | HPJSM PRIOR TO RUN BAKER LOWER COMPLETION STRING.- BRIEF JOB PROCEDURES & RELATED HAZARDS.- ASSIGN TASKS & RESPONSIBILITIES | 13097 |  | BC | 09/18/2022 | ADC-62L | COMP | ANDR-589
1642 | 13097 |  | HT | C | 4752 | PKR | M/U & RIH 4-1/2" L0 LOWER COMPLETION ASSY TO 1,764'....IN PROGRESS AT RPT- ASSY 1: 4.5" GPV SHOE + 1 X 4.5" PJ 11.6# J-55 NVAM- ASSY 2: 1 X 4.5" PJ + 4.5" WBIV 12.6# NVAM + 1 X 4.5" PJ- 2 X 4.5" TBG JNT 11.6" J-55 NVAM- MTV 1: EQ SCREEN MTV 12.6# L-80 NVAM- 2 X 4.5" TBG JNT 11.6" J-55 NVAM- MPAS 1: 4.5" MPAS PACKER 12.6# L-80 NVAM + 1 X 4.5" PJ- 12 X 4.5" TBG JNT 11.6" J-55 NVAM- MTV 2: EQ SCREEN MTV 12.6# L-80 NVAM- 13 X 4.5" TBG JNT 11.6" J-55 NVAM- MPAS 2: 4.5" MPAS PACKER 12.6# L-80 NVAM + 1 X 4.5" PJ- 8 X 4.5" TBG JNT 11.6" J-55 NVAM- MTV 3: EQ SELECT CF PLUS 12.6# L-80 NVAM- 3 X 4.5" TBG JNT 11.6" J-55 NVAM- RIH ON 4-1/2" 11.6# J-55 AM-TS TBG AS PER TALLY- APPLY OPT. M/U TQ @ 3,470 FT-LBS WITH JAM UNIT.- FILL UP STRING EVERY 5 JTS.- RIH TOTAL 46/90 X 4-1/2" TBG JTS.- MONITOR WELL ON TRIP TANK - OK. | 13097 |  | BC | 09/18/2022 | ADC-62L | COMP | ANDR-589
1643 | 6.25 | OOS | COM | 4708 | CORE | HOLE CONDITION TRIP W/REAMING BHA | RUN BAKER LOWER COMPLETIONIN L-0 | 6.25 | 4752 | 18 Sep 0000 | 09/18/2022 | ADC-62L | OOS | ANDR-589
1644
1645
1646
1647 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | ADES-157 | Hrs | HRDH-1840
1648 | XTTE | ODJ | 2 | 18 Sep 1415 - 1615 | 11934 | 902321 | ACCUMULATIVE EXCESS TIME TO RUN COMPLETION DUE TO POOR CREW ORGANIZATION AND IMPROPER USE OF POWER TONG( L/D & CHANGE 6 JTS DAMAGED BY RUNNING CREW, ) | TF | CTRQ |  | 09/18/2022 | ADES-157 | 2 | HRDH-1840
1649 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | ADM-262 | Hrs | MRJN-446
1650 | FOT | BAL | 13 | 18 Sep 1600 - 0500 | 5200 | 902223 | ESP IS NOT WORKING PROPERLY DURING FUNCTION TEST | TF | ESP |  | 09/18/2022 | ADM-262 | 13 | MRJN-446
1651 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | ADM-657 | Hrs | SFNY-1228
1652 | HERR | ARM | 173.5 | 11 Sep 2330 - 0500 | 4233 | 902063 | RIH W/ GS RETRIEVAL TOOL TO RETRIEVE SCHLUMBERGER M/E TUBING PLUG, UNABLE TO PASS 4220', M/U 2.5" & 3" SAND BAILERS REMOVING GREASE LIKE SLUDGE FROM TOP OF ME PLUG JUNK TRAPPER TOP @ 4233'. CONTINUE TO RUN SLICK LINE WITH VARIOUS CONFIGURATIONS & OPTIONS IN ATTEMPT TO RETRIEVE ME PLUG JUNK BASKET & PRONG. | TF | TBG |  | 09/18/2022 | ADM-657 | 24 | SFNY-1228
1653 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | ARO-3001 | Hrs | MRJN-3001
1654 | WTHR | ARM | 53.5 | 16 Sep 2330 - 0500 | 0 | 902302 | WAITING ON WEATHER | WON | NA |  | 09/18/2022 | ARO-3001 | 24 | MRJN-3001
1655 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | ARO-4001 | Hrs | MRJN-537
1656 | CFFM | ARM | 76 | 15 Sep 2130 - 0500 | 6122 | 902242 | HAD TOTAL LOSSES WHILE DRILLING 12-1/4" HOLE. CURE LOSSES WITH CMT PLUG, SET EZSV @ 5902-FT. RE-DRILL 12-1/4" HOLE. | LCIR | SQZ |  | 09/18/2022 | ARO-4001 | 24 | MRJN-537
1657 | XTRI | BCR | 1 | 18 Sep 0400 - 0500 | 950 | 902380 | EXCESSIVE TIME WHILE M/UP 24" CSG USING BAKER POWER TONG & RUNNING TOOL. | JF | CTRQ |  | 09/18/2022 | DPS-4 | 1 | NJYN-94
1658 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | DPS-4 | Hrs | NJYN-94
1659 | XTRI | BCR | 2 | 18 Sep 2300 - 0100 | 0 | 902379 | EXCESSIVE TIME WHILE R/U BAKER POWER TONG & 24" CSG RUNNING TOOLS. | JF | CTRQ |  | 09/18/2022 | DPS-4 | 2 | NJYN-94
1660 | XTRI | BCR | 1 | 18 Sep 0400 - 0500 | 950 | 902380 | EXCESSIVE TIME WHILE M/UP 24" CSG USING BAKER POWER TONG & RUNNING TOOL. | JF | CTRQ |  | 09/18/2022 | DPS-4 | 1 | NJYN-94
1661 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | DPS-43 | Hrs | SDGM-1218
1662 | FOT | HCO | 46 | 17 Sep 0700 - 0500 | 11639 | 902336 | HALLIBURTON UPPER COMPLETION SEAL ASSY FAIL PRESSURE TEST | TF | SEAL |  | 09/18/2022 | DPS-43 | 24 | SDGM-1218
1663 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | ENS-108 | Hrs | ZULF-2015
1664 | OTH | RIG | 88 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/18/2022 | ENS-108 | 24 | ZULF-2015
1665 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | EXL-IVA | Hrs | ZULF-2041
1666 | GRF | RIG | 326.25 | 04 Sep 1645 - 0700 | 3676 | 901657 | WHILE DRILLING AT 3,767' OBSERVE TDS RPM DROP TO 0 RPM. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/18/2022 | EXL-IVA | 2 | ZULF-2041
1667 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | JACK-202 | Hrs | THRY-829
1668 | FOT | RIG | 2 | 18 Sep 2330 - 0130 | 5780 | 902222 | WAIT TO CHANGE LOW TORQUE VALVE ON TOP 5" DP. | TF | SFLN |  | 09/18/2022 | JACK-202 | 2 | THRY-829
1669 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | NA-18S | Hrs | SDGM-444
1670 | HERR | SDM | 29.5 | 16 Sep 1230 - 0900 | 14201 | 902266 | MISSING MWD SIGNAL, UNABLE TO READ MWD/GR/RSS SIGNALS. | DD | RSS |  | 09/18/2022 | NA-18S | 4 | SDGM-444
1671 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | NBR-20S | Hrs | HMYM-433512
1672 | FPMP | RIG | 8.25 | 16 Sep 2115 - 0745 | 10530 | 902301 | EXCESSIVE PUMP FAILURES. | RR | MPMP |  | 09/18/2022 | NBR-20S | 1.25 | HMYM-433512
1673 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | NBR-575S | Hrs | HRDH-1990
1674 | HFFT | NCS | 5.5 | 18 Sep 0730 - 1300 | 12518 | 902320 | EXCESSIVE TIME TO ACHIEVE 500 PSI COMPRESSIVE STRENGTH (36HRS). | CMT | NA |  | 09/18/2022 | NBR-575S | 5.5 | HRDH-1990
1675 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | PA-218S | Hrs | HRDH-1976
1676 | FOT | RIG | 1.5 | 18 Sep 0830 - 1000 | 3000 | 902310 | HAD EATON BRAKE ON DRAWWORK MALFUNCTION. | RR | DWKS |  | 09/18/2022 | PA-218S | 1.5 | HRDH-1976
1677 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | PA-861S | Hrs | HRDH-1973
1678 | FOT | SCP | 72 | 16 Sep 0500 - 0500 | 16845 | 902241 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/18/2022 | PA-861S | 24 | HRDH-1973
1679 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SCTD-1 | Hrs | UTMN-3189
1680 | FOT | RIG | 2 | 18 Sep 1330 - 1530 | 13026 | 902356 | LOST COMMUNICATION BETWEEN COIL CAB AND D&M CABINE. | RR | EDR |  | 09/18/2022 | SCTD-1 | 2 | UTMN-3189
1681 | 17912 | 8200 | RW | N |  | BIT | POOH 6-1/8" MRSS DRLG ASSY F/ 15,000' T/ 8,200'.- HOLE IN GOOD CONDITION.- HAD 6 BPH STATOC LOSSES. | 17912 | 15000 | BHT | 09/18/2022 | SIN30L | DRLG | KHRS-1716
1682 | 17912 |  | OTH | N |  | NA | FLOW CHECK, 8 BPH STATIC LOSSES. | 17912 |  | RIG | 09/18/2022 | SIN30L | DRLG | KHRS-1716
1683 | 17912 | 8090 | LOG | N |  | LWD | RELOG INTERVAL FROM 8,200' TO 8,090' | 17912 | 8200 | BHI | 09/18/2022 | SIN30L | DRLG | KHRS-1716
1684 | 17912 | 412 | TO | N |  | STDP | POOH 6-1/8" MRSS DRLG ASSY F/ 8,090' T/412'.- HAD 8 BPH STATIC LOSSES. | 17912 | 8090 | RIG | 09/18/2022 | SIN30L | DRLG | KHRS-1716
1685 | 17912 |  | OTH | N |  | NA | FLOW CHECK, 8 BPH STATIC LOSSES. | 17912 |  | RIG | 09/18/2022 | SIN30L | DRLG | KHRS-1716
1686 | 17912 |  | HT | N |  | BHA | CONT. POOH W/ 6-1/8" MRSS DRLG BHA TO SURFACE, L/D SAME.- RETREIVE RA SOURCE AND DUMP TOOLS MEMORRY DATA.- MONITOR WELL THRO TRIP TANK, HAD 8 BPH STATIC LOSSES.- BIT DULL: 1-1-WT-A-X-I-NO-TD | 17912 |  | RIG | 09/18/2022 | SIN30L | DRLG | KHRS-1716
1687 | 17912 |  | RTRV | N |  | WBSH | RETRIEVE WEAR BUSHING. | 17912 |  | RIG | 09/18/2022 | SIN30L | WH | KHRS-1716
1688 | 17912 |  | BOPT | N |  | BOP | PERFORM FULL BOP TEST AS PER ARAMCO STANDARDS.- PERFORM ACCUMULATOR DRILL. | 17912 |  | RIG | 09/18/2022 | SIN30L | BOP | KHRS-1716
1689 | 17912 |  | SET | N |  | WBSH | SET WEAR BUSHING. | 17912 |  | RIG | 09/18/2022 | SIN30L | WH | KHRS-1716
1690 | 17912 |  | HT | C | 4751 | BHA | (OOS) P/U 6-1/8" SLICK BHA W/ WELDED CONE BIT OPEN JETS T/ 284 FT.- MONITOR WELL THRO TRIP TANK. | 17912 |  | RIG | 09/18/2022 | SIN30L | STIM | KHRS-1716
1691 | 17912 | 1900 | TI | C | 4751 | STDP | (OOS) RIH W / 6-1/8" SLICK BHA W/ WELDED CONE BIT OPEN JETS ON 4" DP T/ 1,900'- FILL UP STRING WHILE RIH EACH 20 STDS.- MONITOR WELL THRO TRIP TANK. | 17912 | 284 | RIG | 09/18/2022 | SIN30L | STIM | KHRS-1716
1692 | 1.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | ACID WASH JOB FOR L-1 & L-0 | 1.25 | 4751 | 18 Sep 0345 | 09/18/2022 | SIN30L | Type | KHRS-1716
1693
1694
1695 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SINO21 | Hrs | ABQQ-575
1696 | XTTE | SDM | 60.75 | 15 Sep 1900 - 0200 | 11743 | 902212 | MWD SIGNAL ISSUE | TF | LWD |  | 09/18/2022 | SINO21 | 19.5 | ABQQ-575
1697 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SND-2002 | Hrs | WAQR-23
1698 | FOT | MSD | 1 | 18 Sep 1330 - 1430 | 2696 | 902359 | JAM UNIT CABLE FAILURE. | TF | CTRQ |  | 09/18/2022 | SND-2002 | 1 | WAQR-23
1699 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SND-2005 | Hrs | MHKK-2
1700 | FOT | SWL | 10.25 | 18 Sep 1845 - 0500 | 15200 | 902337 | SLB W/L LOST COMMUNICATION WITH TOOLS. | TF | WLT |  | 09/18/2022 | SND-2005 | 10.25 | MHKK-2
1701 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SNT-025 | Hrs | SFNY-517
1702 | WTHR | ARM | 34 | 17 Sep 1100 - 2100 | 0 | 902299 | WAIT ON HIGH TIDE AND WEATHER FOR BOAT TO CROSS PIPE LINE. | WON | NA |  | 09/18/2022 | SNT-025 | 16 | SFNY-517
1703 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SP-120 | Hrs | MNIF-187
1704 | FOT | RIG | 1.5 | 18 Sep 1230 - 1400 | 18300 | 902319 | TDS IBOP FUNCTION FAILURE, CHANGE IBOP. | RR | TDS |  | 09/18/2022 | SP-120 | 1.5 | MNIF-187
1705 | IDPR | SPS | 27 | 17 Sep 0030 - 0445 | 7400 | 902358 | ACCESS ISSUE TO ENTER ALL RSS BHA THRU NEWLY SIDETRACKED LATERAL. TRIP OUT & RUN MOTOR ASSY TO CHECK THE LATERAL ACCESS. | DD | RSS |  | 09/18/2022 | SP-165 | 22.5 | FDHL-146
1706 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SP-165 | Hrs | FDHL-146
1707 | FOT | RIG | .75 | 18 Sep 2045 - 2130 | 7425 | 902357 | REPLACED TDS HYDRAULIC HOSE BY NEW ONE. | RR | TDS |  | 09/18/2022 | SP-165 | .75 | FDHL-146
1708 | IDPR | SPS | 27 | 17 Sep 0030 - 0445 | 7400 | 902358 | ACCESS ISSUE TO ENTER ALL RSS BHA THRU NEWLY SIDETRACKED LATERAL. TRIP OUT & RUN MOTOR ASSY TO CHECK THE LATERAL ACCESS. | DD | RSS |  | 09/18/2022 | SP-165 | 22.5 | FDHL-146
1709 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SSA-302 | Hrs | HRDH-2353
1710 | FOT | RIG | 4 | 18 Sep 0100 - 0500 | 2616 | 902378 | TRIED TO CIRC, FOUND IBOP STUCK CLOSED. TROUBLESHOOTING TO FIX IT | RR | TDS |  | 09/18/2022 | SSA-302 | 4 | HRDH-2353
1711 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | SSA-5971 | Hrs | HWYH-1215
1712 | FOT | RIG | 1 | 18 Sep 1530 - 1630 | 13519 | 902377 | TWO BONNET BOLTS WERE UNABLE TO BE SCREWED INTO THE BOP BODY BONNET THREADS. | BOP | BOP |  | 09/18/2022 | SSA-5971 | 1 | HWYH-1215
1713 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | V141A | Hrs | MRJN-3026
1714 | UXGE | ARM | 20.5 | 18 Sep 0830 - 0500 | 444 | 902221 | WHILE DRILLING AHEAD IN 22" HOLE SECTION, TOTAL LOSE OF RETURNS. STATIC LOSESS AT 612 BPH | LCIR | NA |  | 09/18/2022 | V141A | 20.5 | MRJN-3026
1715 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/18/2022 | WCL-83 | Hrs | MRJN-836
1716 | FOT | BC | 39 | 17 Sep 0500 - 2000 | 268 | 902303 | OBSERVED BAKERHUGHES TRSSSV ON MRJN-836 NOT ABLE TO HOLD PRESSURE BELOW THE TRSSSV FLAPPER PIROR HANDOVER PLATFORM TO PRODUCTION. | TF | SSSV |  | 09/18/2022 | WCL-83 | 15 | MRJN-836
1717 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ADC-17 | Hrs | ZULF-1385
1718 | FOT | SPS | 1.5 | 19 Sep 2030 - 0400 | 4201 | 902389 | BAD GAMMA RAY DETECTION WHILE DRILLING, RIG HAVING TO RELOG EVERY INTERVAL AFTER DRILLING | BHA | LWD |  | 09/19/2022 | ADC-17 | 1.5 | ZULF-1385
1719 | FOT | RIG | 1 | 19 Sep 0300 - 0400 | 2623 | 902390 | LEAK ON BLIND RAM BONNET | BOP | RAMS |  | 09/19/2022 | ADC-21 | 1 | MHWZ-991100
1720 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ADC-21 | Hrs | MHWZ-991100
1721 | HERR | RIG | 1.25 | 19 Sep 2130 - 2245 | 2623 | 902388 | EXCESSIVE TIME N/U BOPE | BOP | BOP |  | 09/19/2022 | ADC-21 | 1.25 | MHWZ-991100
1722 | FOT | RIG | 1 | 19 Sep 0300 - 0400 | 2623 | 902390 | LEAK ON BLIND RAM BONNET | BOP | RAMS |  | 09/19/2022 | ADC-21 | 1 | MHWZ-991100
1723 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ADC-43L | Hrs | UTMN-3118
1724 | HELD | TK3 | 98.5 | 15 Sep 0230 - 0500 | 11321 | 902217 | DRIFT WITH 3.625" (GAUGE CUTTER) TO 11,321 FT - HELD UP & UNABLE TO PASS THRU SEAL ASSEMBLY MULE SHOE & BTM OF LNR TBR. CHANGE TO 3.5" DRIFT - NO SUCCESS. | JF | LINR |  | 09/19/2022 | ADC-43L | 24 | UTMN-3118
1725 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ADC-56L | Hrs | UTMN-3069
1726 | FOT | TK3 | 91.5 | 16 Sep 0500 - 0030 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/19/2022 | ADC-56L | 19.5 | UTMN-3069
1727 | 13097 | 3952 | HT | C | 4752 | EQLZR | RIH IN L-0 BAKER 4-1/2" LOWER COMPLETION ASSY F/ 1,764' TO 3,952'- 8 X 4.5" TBG JNT 11.6" J-55 NVAM- MPAS 3: 4.5" MPAS PACKER 12.6# L-80 NVAM + 1 X 4.5" PJ- 5 X 4.5" TBG JNT 11.6" J-55 NVAM- MTV 4: EQ SCREEN MTV 12.6# L-80 NVAM- 6 X 4.5" TBG JNT 11.6" J-55 NVAM + 1 X 4.5" PJ- MPAS 4: 4.5" MPAS PACKER 12.6# L-80 NVAM + 1 X 4.5" PJ- 9 X 4.5" TBG JNT 11.6" J-55 NVAM- MTV 5: EQ SCREEN MTV 12.6# L-80 NVAM- 9 X 4.5" TBG JNT 11.6" J-55 NVAM- MPAS 5: 4.5" MPAS PACKER 12.6# L-80 NVAM + 1 X 4.5" PJ- 4 X 4.5" TBG JNT 11.6" J-55 NVAM- MTV 6: EQ SCREEN MTV 12.6# L-80 NVAM- 12 X 4.5" TBG JNT 11.6" J-55 NVAM +1 X 4.5" PJ- RIH ON 4-1/2" 11.6# J-55 AM-TS TBG AS PER TALLY- APPLY OPT. M/U TQ @ 3,470 FT-LBS WITH JAM UNIT.- FILL UP STRING EVERY 5 JTS.- RIH TOTAL 90/90 X 4-1/2" TBG JTS.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 1764 | BC | 09/19/2022 | ADC-62L | COMP | ANDR-589
1728 | 13097 |  | PJSM | C | 4752 | PKR | HPJSM PRIOR TO P/U LNR HANGER & RIH 4-1/2" LOWER COMPLETION STRING ON DP | 13097 |  | BC | 09/19/2022 | ADC-62L | COMP | ANDR-589
1729 | 13097 |  | HT | C | 4752 | PKR | M/U 4-1/2" BAKER LINER HANGER ASSY TO 3,996'- CHANGE ELEVATOR FROM 4-1/2" TO 4" SIZE.- CHECK STRING INTEGRITY.- MONITOR WELL ON TRIP TANK - OK | 13097 |  | BC | 09/19/2022 | ADC-62L | COMP | ANDR-589
1730 | 13097 |  | CIRC | C | 4752 | MPMP | CIRCULATE FOR 1.5 X LINER VOL.- FR: 167 GPM, SPP: 525 PSI.- MW IN = MW OUT = 85 PCF.- RECORD P/U / S/O WT: 112/108 / KLBS (PUMPS OFF).**MEANWHILE- R/D TESCO RUNNING EQUIPMENT. | 13097 |  | RIG | 09/19/2022 | ADC-62L | COMP | ANDR-589
1731 | 13097 | 9065 | RPCS | C | 4752 | LWSCO | RIH BAKER 4-1/2" LOWER COMPLETION ASSY ON 4" DP & 4" HWDP STDS F/3,999' TO 9,065'' (7" LINER SHOE).- CONTROL TRIPPING SPEED TO 2 MINS SLIP-TO-SLIP.- RIH ON DRIFTED 4" TUBULARS.- FILL UP STRING EVERY 10 STDS.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 3999 | RIG | 09/19/2022 | ADC-62L | COMP | ANDR-589
1732 | 13097 |  | CIRC | C | 4752 | MPMP | CIRCULATE FOR 1 X BTM UP.- FR: 150 GPM, SPP: 1050 PSI.- RECORD P/U / S/O WT: 190/177 KLBS (PUMPS OFF).- MUD WT: IN/OUT = 85 PCF.**MEANWHILE- HOLD PJSM WITH CREWS PRIOR TO RUN 4-1/2" LOWER COMPLETION STRING IN OPEN HOLE. | 13097 |  | RIG | 09/19/2022 | ADC-62L | COMP | ANDR-589
1733 | 13097 | 12939 | RPCS | C | 4752 | LWSCO | RIH BAKER 4-1/2" LOWER COMPLETION ASSY F/ 9,065' TO 12,939'.- CONTROL TRIPPING SPEED TO 2 MINS SLIP-TO-SLIP.- FILL UP STRING ON FLY EVERY STD.- OPEN HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK - OK. | 13097 | 9065 | RIG | 09/19/2022 | ADC-62L | COMP | ANDR-589
1734 | 13097 |  | CIRC | C | 4752 | MPMP | CIRC 2 X STRING VOLUME.- FR=120 GPM; SPP=1020 PSI.- STRING WEIGHT: 195 UP / 155 DOWN- NO LOSSES. | 13097 |  | RIG | 09/19/2022 | ADC-62L | COMP | ANDR-589
1735 | 13097 |  | CIRC | C | 4752 | MPMP | DISPLACE WELL TO 86 PCF BRINE CIRC. & CONDITION BRINE WT IN/OUT = 86 PCF.- PUMP 25 BBL, 86 PCF MICRO-PRIME PUSH SPACER- PUMP 25 BBL, 86 PCF MICRO-PRIME CLEANING SPACER- MENAWHILE PREPARE & MIX BAKER MICRO WASH PILL. | 13097 |  | RIG | 09/19/2022 | ADC-62L | COMP | ANDR-589
1736 | 13097 | 8918 | SET | C | 4752 | PKR | HELD PJSM & SET 4-1/2" X 7" HMC (HGR), MPAS PKR'S & ACTIVATE EQ CF PLUS (ICD'S) AS FOLLOWS:- PUMP 80 BBLS OF 82 PCF BAKER MICRO WASH PILL.- PUMP 10 BBL ,86 PCF HI-VIS BRINE.- DROP 1-1/2" LOW DENSITY SETTING BALL- PUMP 10 BBL ,86 PCF HI-VIS BRINE.- CHASE BALL WITH 86 PCF BRINE....IN PROGRESS AT RPT. | 13097 | 8918 | BC | 09/19/2022 | ADC-62L | COMP | ANDR-589
1737 | 30.25 | OOS | Category | DOOS ID | COM | Out of Scope Summary | RUN BAKER LOWER COMPLETIONIN L-0 | 24 | 4752 | 18 Sep 0000 | 09/19/2022 | ADC-62L | Type | ANDR-589
1738
1739
1740 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ADM-262 | Hrs | MRJN-446
1741 | FOT | BAL | 17.5 | 18 Sep 1600 - 0930 | 5200 | 902223 | ESP IS NOT WORKING PROPERLY DURING FUNCTION TEST | TF | ESP |  | 09/19/2022 | ADM-262 | 4.5 | MRJN-446
1742 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ADM-657 | Hrs | SFNY-1228
1743 | FOT | RIG | 11.5 | 18 Sep 0245 - 1415 | 10193 | 902381 | PORT CRANE IS CURRENTLY SHUT DOWN, WAITING ON ALMANSOORI MECHANIC AND NOV (OEM) INSPECTOR TO COMPLETE FULL INSPECTION AND FIX ONGOING ISSUES. UNABLE TO CONTINUE HALLIBURTON FLOW BACK RIG UP UNTIL PORT CRANE IS OPERATIONAL. | RR | CRN |  | 09/19/2022 | ADM-657 | 9.25 | SFNY-1228
1744 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ARO-3001 | Hrs | MRJN-3001
1745 | WTHR | ARM | 60.75 | 16 Sep 2330 - 1215 | 0 | 902302 | WAITING ON WEATHER | WON | NA |  | 09/19/2022 | ARO-3001 | 7.25 | MRJN-3001
1746 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ARO-3003 | Hrs | SFNY-1157
1747 | FOT | SCD | 4.5 | 19 Sep 1430 - 1900 | 725 | 902398 | SCIENTIFIC DRILLING GWD TOOL FAILED DURING SURFACE TEST. | TF | GYRO |  | 09/19/2022 | ARO-3003 | 4.5 | SFNY-1157
1748 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ARO-4001 | Hrs | MRJN-537
1749 | CFFM | ARM | 87.5 | 15 Sep 2130 - 1630 | 6122 | 902242 | HAD TOTAL LOSSES WHILE DRILLING 12-1/4" HOLE. CURE LOSSES WITH CMT PLUG, SET EZSV @ 5902-FT. RE-DRILL 12-1/4" HOLE. | LCIR | SQZ |  | 09/19/2022 | ARO-4001 | 11.5 | MRJN-537
1750 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | DPS-43 | Hrs | SDGM-1218
1751 | FOT | HCO | 69 | 17 Sep 0700 - 0500 | 11639 | 902336 | HALLIBURTON UPPER COMPLETION SEAL ASSY FAIL PRESSURE TEST | TF | SEAL |  | 09/19/2022 | DPS-43 | 23 | SDGM-1218
1752 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | DQ-49L | Hrs | HRDH-1541
1753 | IBHA | BHI | 14.5 | 19 Sep 1430 - 0500 | 4585 | 902418 | RIH W/ 8 1/2" MRSS/LWD ASSY, HAD OBST. 18 FT BELOW 9 5/8" CSG SHOE, MANY TRIALS TO PASS W/O SUCCESS, POOH FOR BHA CHECK, FOUND SCRATCH MARKD ON MODULAR MTR & MEASURED MTR OD FOUND 8.56". | BHA | MMOT |  | 09/19/2022 | DQ-49L | 14.5 | HRDH-1541
1754 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | ENS-108 | Hrs | ZULF-2015
1755 | OTH | RIG | 112 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/19/2022 | ENS-108 | 24 | ZULF-2015
1756 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | PA-218S | Hrs | HRDH-1976
1757 | UXDF | ARN | 79.5 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/19/2022 | PA-218S | 24 | HRDH-1976
1758 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | PA-861S | Hrs | HRDH-1973
1759 | FOT | SCP | 96 | 16 Sep 0500 - 0500 | 16845 | 902241 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/19/2022 | PA-861S | 24 | HRDH-1973
1760 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | PN-9 | Hrs | MRJN-673
1761 | CFST | HCM | 241.25 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 09/19/2022 | PN-9 | 17.5 | MRJN-673
1762 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SA5898 | Hrs | MDRK-66
1763 | FOT | BAW | 18 | 19 Sep 1100 - 0500 | 15908 | 902384 | BAKER HUGHES LOGGING HAD MALFUNCTION IN PRESSURE POINT TOOL & TRY TO FIX SAME WITHOUT PROGRESS. | TF | WLT |  | 09/19/2022 | SA5898 | 18 | MDRK-66
1764 | 17912 | 8240 | TI | C | 4751 | STDP | (OOS) RIH W / 6-1/8" SLICK BHA W/ WELDED CONE BIT OPEN JETS ON 4" DP FROM 1900' TO 8240'- MONITOR WELL THRO TRIP TANK. - HAD 8 BPH STATIC LOSSES.- FILL UP STRING WHILE RIH EACH 20 STDS. | 17912 | 1900 | RIG | 09/19/2022 | SIN30L | STIM | KHRS-1716
1765 | 17912 |  | OTH | C | 4751 | NA | (OOS) HPJSM, P/U & M/U 4" X 1502 CIRCULATING SUB WITH SWIVEL + 4" SAFETY VALVE., CONNECTED SURFACE LINE TO ACID PUMPING UNIT, FLUSHED & P/T LINE TO 500/5000 PSI-OK.- HAD 8 BPH STATIC LOSSES. | 17912 |  | BCT | 09/19/2022 | SIN30L | STIM | KHRS-1716
1766 | 17912 |  | OTH | C | 4751 | NA | (OOS) BAKER PUMP 60 BBL ACID PICKLING FLUIDS (10% FORMIC ACID) 66 PCF FOLLOWED WITH 40 BBLS 66 PCF BRINE, SWITCHED TO RIG, CLOSED BOP, CIRC. THROUGH CHOKE & CONTINUE TO DISPLACE WITH 66 PCF BRINE TILL HAD CLEAN BRINE ON SURFACE. | 17912 |  | BCT | 09/19/2022 | SIN30L | STIM | KHRS-1716
1767 | 17912 |  | OTH | C | 4751 | NA | (OOS) OPEN BOP, FLOW CHECK, HAD 8 BPH STATIC LOSSES.- R/D SURFACE LINES. | 17912 |  | RIG | 09/19/2022 | SIN30L | STIM | KHRS-1716
1768 | 17912 | 17912 | ST | C | 4751 | STDP | (OOS) CONT. RIH W/6-1/8" (L -1) ACID WASH SLICK BHA FROM 8240' TO 17912'- OPEN HOLE IN GOOD CONDITION.- FILL UP STRING WHILE RIH EACH 20 STDS.- HAD 8 BPH STATIC LOSSES. | 17912 | 8240 | RIG | 09/19/2022 | SIN30L | STIM | KHRS-1716
1769 | 17912 |  | OTH | C | 4751 | NA | (OOS) HPJSM, P/U & M/U 4" X 1502 CIRCULATING SUB WITH SWIVEL + 4" SAFETY VALVE., CONNECTED SURFACE LINE TO ACID PUMPING UNIT, FLUSHED & P/T LINE TO 400/5000 PSI-OK. | 17912 |  | BCT | 09/19/2022 | SIN30L | STIM | KHRS-1716
1770 | 17912 |  | OTH | C | 4751 | NA | (OOS) SPOT ACID WASH IN OPEN HOLE (L -1) AS FOLLOW:- PUMPED 410 BBL OF PRE-FLUSH 66 PCF, PUMPED 82 BBL OF ACID WASH TREATMENT (10% FORMIC ACID) 66 PCF, STOP PUMPING, CLOSE BOP - RETURN THROUGH FULL OPEN CHOKE MANIFOLD.- CONT. PUMP 328 BBL ACID WASH TREATMENT (10% FORMIC ACID) 66 PCF.- PUMPED 200 BBL POST FLUSH @ 66 PCF TO SPOT ACID IN OPEN HOLE. | 17912 |  | BCT | 09/19/2022 | SIN30L | STIM | KHRS-1716
1771 | 17912 |  | OTH | C | 4751 | NA | (OOS) FLOWCHECK THRU CHOKE, 27 BPH LOSSES, OPEN BOP. | 17912 |  | RIG | 09/19/2022 | SIN30L | STIM | KHRS-1716
1772 | 17912 | 11500 | ST | C | 4751 | STDP | (OOS) POOH W/ 6-1/8" (L-1) ACID WASH SLICK BHA TO 11,500'.- HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK.- HAD 22 BPH STATIC LOSSES. | 17912 | 17912 | RIG | 09/19/2022 | SIN30L | STIM | KHRS-1716
1773 | 25.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | ACID WASH JOB FOR L-1 & L-0 | 24 | 4751 | 18 Sep 0345 | 09/19/2022 | SIN30L | Type | KHRS-1716
1774
1775
1776 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SINO-29N | Hrs | SFNY-2005
1777 | FOT | RIG | 4.5 | 19 Sep 1500 - 1930 | 10879 | 902437 | RIG TRIPPING WET WITH OBM, MUD CAN LEAKING | RR | FL |  | 09/19/2022 | SINO-29N | 4.5 | SFNY-2005
1778 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SND-2004 | Hrs | BRRI-1148
1779 | FOT | SCM | 4.5 | 19 Sep 2130 - 0200 | 8353 | 902438 | TROUBLE SHOOTING CMT UNIT, SCREEN SHUT DOWN & UNIT CAN NOT PUMP, NO SUCCESS. MEANWHILE WAITING FOR OTHER SLB CMT UNIT. RU NEW UNIT. | TF | PUMP |  | 09/19/2022 | SND-2004 | 4.5 | BRRI-1148
1780 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SND-2005 | Hrs | MHKK-2
1781 | FOT | SWL | 21 | 18 Sep 1845 - 1545 | 15200 | 902337 | SLB W/L LOST COMMUNICATION WITH TOOLS. | TF | WLT |  | 09/19/2022 | SND-2005 | 10.75 | MHKK-2
1782 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SND-2009 | Hrs | SAHB-101
1783 | STBH | ARM | 20 | 19 Sep 0900 - 0500 | 10580 | 902387 | AFTER DRILLOUT F/S @ 10,575 FT, PU STRING FREE, ADJUST PARAMETERS, RIH BACK, CLEANOUT RAT HOLE, WHEN BIT REACH BTM @ 10,580 FT (NBRR @ 9 5/8" FLOAT SHOE AT 10,575 FT). STRING STALLED AND GET STUCK. UNABLE TO CIRC. | STUK | BHA |  | 09/19/2022 | SND-2009 | 20 | SAHB-101
1784 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SP-165 | Hrs | FDHL-146
1785 | IDPR | SPS | 51.25 | 17 Sep 0030 - 0500 | 7400 | 902358 | ACCESS ISSUE TO ENTER ALL RSS BHA THRU NEWLY SIDETRACKED LATERAL. TRIP OUT & RUN MOTOR ASSY TO CHECK THE LATERAL ACCESS. | DD | RSS |  | 09/19/2022 | SP-165 | 24 | FDHL-146
1786 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SP-257 | Hrs | HZEM-162402
1787 | FOT | RIG | 15.75 | 19 Sep 0500 - 2045 | 7638 | 902382 | MANUAL IBOP ON THE TOP DRIVE WASHED OUT CAUSING INTERNAL FAILURE OF VALVE. | RR | TDS |  | 09/19/2022 | SP-257 | 15.75 | HZEM-162402
1788 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SP-306 | Hrs | MNIF-192
1789 | FOT | RIG | 1.25 | 19 Sep 0100 - 0215 | 17106 | 902400 | CHANGE TDS WASH PIPE | RR | TDS |  | 09/19/2022 | SP-306 | 1.25 | MNIF-192
1790 | FWTS | RIG | 1 | 19 Sep 0400 - 0500 | 3545 | 902399 | WHILE DRILLING AT 3545' W/900 GPM @1600 PSI, SUDDENLY LOST 700 PSI & +/-12KLB FROM STRING WT. SWEPT HOLE W/150 BBL HVP - CHC. | FISH | BHA |  | 09/19/2022 | SSA-302 | 1 | HRDH-2353
1791 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SSA-302 | Hrs | HRDH-2353
1792 | FOT | RIG | 7.5 | 18 Sep 0100 - 0830 | 2616 | 902378 | TRIED TO CIRC, FOUND IBOP STUCK CLOSED. TROUBLESHOOTING TO REPAIR COMUNICATION TO IBOP ON TOP DRIVE | RR | TDS |  | 09/19/2022 | SSA-302 | 3.5 | HRDH-2353
1793 | FWTS | RIG | 1 | 19 Sep 0400 - 0500 | 3545 | 902399 | WHILE DRILLING AT 3545' W/900 GPM @1600 PSI, SUDDENLY LOST 700 PSI & +/-12KLB FROM STRING WT. SWEPT HOLE W/150 BBL HVP - CHC. | FISH | BHA |  | 09/19/2022 | SSA-302 | 1 | HRDH-2353
1794 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/19/2022 | SSA-5914 | Hrs | WDYH-80
1795 | FOT | RIG | 1.75 | 19 Sep 2330 - 0115 | 21000 | 902392 | OBSERVED SEVERAL LEAKS ON TEST ASSEMBLY HIGH PRESSURE HOSE. LEAKS ON SEVERAL VALVES DUE TO LACK OF GREASING PRIOR TO PRESSURE TEST. | BOP | BOP |  | 09/19/2022 | SSA-5914 | 1.75 | WDYH-80
1796 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | ADC-21 | Hrs | MHWZ-991100
1797 | HERR | RIG | 5.5 | 20 Sep 0900 - 1430 | 2630 | 902420 | WHEN REMOVING BOLTS PRIOR INSTALLATION OF THE BELL NIPPLE , ONE BOLT FELT DOWN HOLE | BOP | BOP |  | 09/20/2022 | ADC-21 | 5.5 | MHWZ-991100
1798 | FOT | BCT | 10 | 20 Sep 1600 - 0200 | 11300 | 902491 | DUAL CHECK VALVE FAILED PRESSURE TEST. | TF | CTAC |  | 09/20/2022 | ADC-43L | 10 | UTMN-3118
1799 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | ADC-43L | Hrs | UTMN-3118
1800 | HELD | TK3 | 99.5 | 15 Sep 0230 - 0500 | 11321 | 902217 | DRIFT WITH 3.625" (GAUGE CUTTER) TO 11,321 FT - HELD UP & UNABLE TO PASS THRU SEAL ASSEMBLY MULE SHOE & BTM OF LNR TBR. CHANGE TO 3.5" DRIFT - NO SUCCESS. | JF | LINR |  | 09/20/2022 | ADC-43L | 3 | UTMN-3118
1801 | HERR | BCT | 13 | 19 Sep 0300 - 1600 | 11300 | 902419 | EXCESS TIME OVER 24 HRS TO RIG UP & TEST CTD UNTI & ACCESSORIES | JF | CTAC |  | 09/20/2022 | ADC-43L | 11 | UTMN-3118
1802 | FOT | BCT | 10 | 20 Sep 1600 - 0200 | 11300 | 902491 | DUAL CHECK VALVE FAILED PRESSURE TEST. | TF | CTAC |  | 09/20/2022 | ADC-43L | 10 | UTMN-3118
1803 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | ADC-48 | Hrs | HRDH-2316
1804 | SDIR | ARM | 16.75 | 20 Sep 1215 - 0500 | 18441 | 902493 | AFTER 1 X BU, RACK BACK 1 STD, MADE UP TOP DRIVE, ESTABLISH CIRC, OBSERVED STRING TAKING TORQUE/ ROTARY STALLED, IMMEDIATELY PICK UP THE STD AND ATTEMPED TO GO DOWN WITH CIRC, NO SUCCESS, FOUND STRING STUCK AT 18,358'(83' OFF BOTTOM). RACK BACK THE STD AND ADD ONE SINGLE, IMMEDIATELY CONTINUE TO ACTIVATE DOWN JAR WITH TORQ AND UPWARD JAR- NO SUCCESS. | STUK | RSS |  | 09/20/2022 | ADC-48 | 16.75 | HRDH-2316
1805 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | ADC-56L | Hrs | UTMN-3069
1806 | FOT | TK3 | 99.75 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/20/2022 | ADC-56L | 8.25 | UTMN-3069
1807 | 13097 |  | CIRC | C | 4752 | MPMP | CHASE SETTING BALL WITH 140 BBL OF 86 PCF BRINE. | 13097 |  | RIG | 09/20/2022 | ADC-62L | COMP | ANDR-589
1808 | 13097 | 8900 | SET | C | 4752 | PKR | SET 4-1/2" LINER HANGER AS PER BAKER ENG.- PRESSURE TO 2200 PSI & HOLD FOR 10 MIN AFTER BALL LANDING.- S/O 80 KLBS AND CONFIRM HANGER SET- INCREASE PRESSURE TO 3500 PSI W/ 30 KLS S/O & HOLD FOR 10 MIN TO SET MPAS & ACTIVATE MTVS. | 13097 | 8900 | BC | 09/20/2022 | ADC-62L | COMP | ANDR-589
1809 | 13097 | 8900 | SET | C | 4752 | PKR | RELEASE RUNNING TOOL.- BLEED OFF TO 500 PSI.- P/U 10 FT, S/O 60 KLB AND ROTATE 15 RPM FOR 5 MIN.- P/U STRING & OBSERVE PRESSURE DROP.- CONFIRM RUNNING TOOL RELEASED.- P/U TO NEUTRAL POINT. | 13097 | 8900 | BC | 09/20/2022 | ADC-62L | COMP | ANDR-589
1810 | 13097 |  | CIRC | C | 4752 | MPMP | CIRCULATE WELL W/ 86 PCF BRINE AND CONDITION MUD IN/OUT 86 PCF.-POOH 1 STANDS & CHC.- NO DYNAMIC LOSSES.- RECORD SCR. | 13097 |  | RIG | 09/20/2022 | ADC-62L | COMP | ANDR-589
1811 | 13097 |  | WCNT | C | 4752 | MPMP | FLOW CHECK - WELL STATIC. | 13097 |  | RIG | 09/20/2022 | ADC-62L | COMP | ANDR-589
1812 | 13097 | 0 | TO | C | 4752 | STDP | POOH BAKER RUNNING TOOL F/ 8900' TO SURFACE.- MONITOR WELL ON TRIP TANK- WELL STATIC. | 13097 | 8900 | RIG | 09/20/2022 | ADC-62L | COMP | ANDR-589
1813 | 13097 |  | OTH | C | 4752 | PKR | L/D BAKER RUNNING TOOL @ SURFACE.- CONFIRM RUNNING TOOL IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK- WELL STATIC. | 13097 |  | BC | 09/20/2022 | ADC-62L | COMP | ANDR-589
1814 | 13097 |  | RR | N |  | TDS | SERVICES TOP DRIVE.- HOUSEKEEPING AND CLEAR RIG FLOOR.- MONITOR WELL ON TRIP TANK- WELL STATIC. | 13097 |  | RIG | 09/20/2022 | ADC-62L | TINL | ANDR-589
1815 | 13097 |  | OTH | N |  | NA | PERFORM MWD SHALLOW TEST OK.- M/U 6-1/8 BIT + BIT SUB W/FV+ MWD AND RIH TO 500'- FR: 252-290 GPM, SPP: 900 - 1200 PSI- POOH & RACK BACK 4" DP, L/D BIT & BIT SUB.- TEST GOOD | 13097 |  | SDM | 09/20/2022 | ADC-62L | TINL | ANDR-589
1816 | 13097 |  | PJSM | N |  | NA | HPJSM WITH CREW BEFORE M/U COMBINED WHIPSTOCK-MILL ASSY.- DISCUSSED JSA TO P/U AND RIH WITH WHIPSTOCK ASSY.- DISCUSSED ALL RELATED HAZARDS FOR USING CRANE TO- P/U TOOLS AND ALL STEPS TO M/U THE ASSY.- MONITOR WELL ON TRIP TANK- WELL STATIC. | 13097 |  | TK3 | 09/20/2022 | ADC-62L | TINL | ANDR-589
1817 | 13097 |  | HT | N |  | BHA | P/U & M/U SMITH TM WHIPSTOCK- M/U 6-1/8" SMITH TRI-MILL + HYD RUNNING TOOL + X/O- M/U 1 X 4" HWDP + X/O + MCBPV + MWD SLIMPULSE.- CHECKED TRI MILL IN GAUGE (6 1/8" GAUGE).- SERVICE WS & CONNECT CONTROL LINE HOSE- B/O RUNNING TOOL & FILL OIL INTO HYD SUB- CONNECT MILL ASSY. TO WS- SCRIBE W/S HIGHSIDE TO MWD (TF CORRECTION 121.5 DEG)- MONITOR WELL ON TRIP TANK- WELL STATIC. | 13097 |  | RIG | 09/20/2022 | ADC-62L | TINL | ANDR-589
1818 | 13097 |  | HT | N |  | BHA | M/U & RIH WITH COMBINED WS - CO ASSY. TO 250'- P/U AND M/U 1 STD X 4" HWDP + 3 X 7" MAGNOSTAR.- MONITOR WELL ON TRIP TANK- WELL STATIC. | 13097 |  | RIG | 09/20/2022 | ADC-62L | TINL | ANDR-589
1819 | 13097 | 7600 | TI | N |  | BHA | RIH W/ COMBINED 7" WHIPSTOCK-MIL ASSY. F/250' T/ 7600'- CONTROLLED RIH SPEED.- MONITOR WELL ON TRIP TANK- WELL STATIC. | 13097 | 250 | RIG | 09/20/2022 | ADC-62L | TINL | ANDR-589
1820 | 40 | OOS | Category | DOOS ID | COM | Out of Scope Summary | RUN BAKER LOWER COMPLETIONIN L-0 | 9.75 | 4752 | 18 Sep 0000 | 09/20/2022 | ADC-62L | Type | ANDR-589
1821
1822
1823 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | ADM-337 | Hrs | MRJN-900
1824 | WTHR | ARM | 5.75 | 20 Sep 0530 - 1115 | 13019 | 902487 | UNFAVORABLE WEATHER FOR FLOW BACK OPERATION, WIND SPEED BELOW 5 KNOTS | WON | NA |  | 09/20/2022 | ADM-337 | 5.75 | MRJN-900
1825 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | ARO-4001 | Hrs | MRJN-537
1826 | CFFM | ARM | 104 | 15 Sep 2130 - 0500 | 6122 | 902242 | HAD TOTAL LOSSES WHILE DRILLING 12-1/4" HOLE. CURE LOSSES WITH CMT PLUG, SET EZSV @ 5902-FT. RE-DRILL 12-1/4" HOLE. | LCIR | SQZ |  | 09/20/2022 | ARO-4001 | 16.5 | MRJN-537
1827 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | DPS-4 | Hrs | NJYN-94
1828 | UVLC | ARM | 4 | 20 Sep 0800 - 1200 | 1170 | 902477 | LOST FULL RETURN WHILE DRILLING 22" HOLE SECTION IN RUS FORMATION, ATTEMPT TO CURE LOSSES WITH LCM PILLS. | LCIR | NA |  | 09/20/2022 | DPS-4 | 4 | NJYN-94
1829 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | DPS-43 | Hrs | SDGM-1218
1830 | FOT | HCO | 93 | 17 Sep 0700 - 0500 | 11639 | 902336 | HALLIBURTON UPPER COMPLETION SEAL ASSY FAIL PRESSURE TEST | TF | SEAL |  | 09/20/2022 | DPS-43 | 24 | SDGM-1218
1831 | FOT | SDM | 1 | 20 Sep 1715 - 1815 | 5340 | 902478 | MWD FAILURE. | BHA | MWD |  | 09/20/2022 | ENS-108 | 1 | ZULF-2015
1832 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | ENS-108 | Hrs | ZULF-2015
1833 | OTH | RIG | 135 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/20/2022 | ENS-108 | 23 | ZULF-2015
1834 | FOT | SDM | 1 | 20 Sep 1715 - 1815 | 5340 | 902478 | MWD FAILURE. | BHA | MWD |  | 09/20/2022 | ENS-108 | 1 | ZULF-2015
1835 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | EXL-IA | Hrs | ABSF-128
1836 | OTH | RIG | 1.25 | 20 Sep 0530 - 0645 | 0 | 902393 | REPLACEMENT OF JACKING CORD SECTION K ON PORT LEG FINAL INSPECTION OF WELDS & FUNCTION WITNESSED BY ABS INSPECTOR | UPRA | NA |  | 09/20/2022 | EXL-IA | 1.25 | ABSF-128
1837 | FOT | ARM | 6.75 | 20 Sep 2215 - 0500 | 5185 | 902480 | CANNOT RUN 7" SCREENS TAG AT 5185' AT LANDING COLLAR. | TF | CSG |  | 09/20/2022 | JACK-202 | 6.75 | THRY-829
1838 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | JACK-202 | Hrs | THRY-829
1839 | FOT | RIG | 1 | 20 Sep 2000 - 2100 | 4892 | 902479 | REPAIR PASSON FOR DEPTH AND WEIGHT. | TF | COMP |  | 09/20/2022 | JACK-202 | 1 | THRY-829
1840 | FOT | ARM | 6.75 | 20 Sep 2215 - 0500 | 5185 | 902480 | CANNOT RUN 7" SCREENS TAG AT 5185' AT LANDING COLLAR. | TF | CSG |  | 09/20/2022 | JACK-202 | 6.75 | THRY-829
1841 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | NA-18S | Hrs | SDGM-444
1842 | FPMP | RIG | 18.5 | 20 Sep 1030 - 0500 | 14795 | 902476 | LOST POWER TO DRAWWORK & MUD PUMPS WHILE DRILLING CAUSING BIT NOZZLE PLUGGED. | RR | MPMP |  | 09/20/2022 | NA-18S | 18.5 | SDGM-444
1843 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | NBR-304S | Hrs | UTMN-3180
1844 | FOT | FMC | 2 | 20 Sep 0030 - 0230 | 2130 | 902488 | FRANK SPIDER SLIP NOT HOLDING 18-5/8" CSG. | TF | CRT |  | 09/20/2022 | NBR-304S | 2 | UTMN-3180
1845 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | NBR-654S | Hrs | ANDR-1018
1846 | FOT | RIG | 1 | 20 Sep 1700 - 1800 | 397 | 902481 | STOPPER GUIDE ON BACK UP WRENCH DISCONNECTED | RR | TDS |  | 09/20/2022 | NBR-654S | 1 | ANDR-1018
1847 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | PA-218S | Hrs | HRDH-1976
1848 | UXDF | ARN | 103.5 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/20/2022 | PA-218S | 24 | HRDH-1976
1849 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | PA-326S | Hrs | SHDN-22
1850 | FOT | RIG | 20 | 20 Sep 0900 - 0500 | 10290 | 902483 | DURING RIH WITH 5-7/8" ROT.DRLG ASSY AT 10290 FT, OBSERVED WATER LEAK FROM EDS COOLING SYSTEM, CHECK SAME AND FOUND WORN OUT IN THE HUB TEETH AND EDS SPROKET (EATON BRAKE). | RR | DWKS |  | 09/20/2022 | PA-326S | 20 | SHDN-22
1851 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | PA-861S | Hrs | HRDH-1973
1852 | FOT | SCP | 113 | 16 Sep 1200 - 0500 | 16845 | 902241 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/20/2022 | PA-861S | 24 | HRDH-1973
1853 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | PN-9 | Hrs | MRJN-673
1854 | CFST | HCM | 265.25 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 09/20/2022 | PN-9 | 24 | MRJN-673
1855 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | SA5898 | Hrs | MDRK-66
1856 | FOT | BAW | 20 | 19 Sep 1100 - 0700 | 15908 | 902384 | BAKER HUGHES LOGGING HAD MALFUNCTION IN PRESSURE POINT TOOL & TRY TO FIX SAME WITHOUT PROGRESS. | TF | WLT |  | 09/20/2022 | SA5898 | 2 | MDRK-66
1857 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | SCTD-1 | Hrs | UTMN-3189
1858 | FOT | RIG | 1.5 | 20 Sep 1930 - 2100 | 14095 | 902490 | N2 PUMPING FAILED. | RR | MPMP |  | 09/20/2022 | SCTD-1 | 1.5 | UTMN-3189
1859 | 17912 | 8310 | RW | C | 4751 | BIT | ( OOS ) CONT POOH W/ 6-1/8" (L-1) ACID WASH SLICK BHA FROM 11,500' TO TOW @ 8,310'.- HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK. | 17912 | 11500 | BHT | 09/20/2022 | SIN30L | STIM | KHRS-1716
1860 | 17912 |  | CIRC | C | 4751 | MPMP | ( OOS ) CLOSE BOP, DISPLACE HOLE WITH 66 PCF BRINE AND GET RETURN THRU CHOKE TILL CELAN BRINE TO SURFACE. | 17912 |  | RIG | 09/20/2022 | SIN30L | STIM | KHRS-1716
1861 | 17912 |  | OTH | C | 4751 | NA | ( OOS ) FLOW CHECK, STATIC LOSS 14 BPH . | 17912 |  | RIG | 09/20/2022 | SIN30L | STIM | KHRS-1716
1862 | 17912 | 281 | TO | C | 4751 | STDP | ( OOS ) POOH 6-1/8" ACID WASH BHA F/8,310' T/ TOP OF BHA @ 281'. | 17912 | 8310 | RIG | 09/20/2022 | SIN30L | STIM | KHRS-1716
1863 | 17912 |  | OTH | C | 4751 | NA | ( OOS ) FLOW CHECK, STATIC LOSS 13 BPH . | 17912 |  | RIG | 09/20/2022 | SIN30L | STIM | KHRS-1716
1864 | 17912 |  | HT | C | 4751 | BHA | ( OOS ) L/D 6-1/8" ACID WASH BHA.- MONITOR WELL ON TRIP TANK, STATIC LOSS 13 BPH . | 17912 |  | RIG | 09/20/2022 | SIN30L | STIM | KHRS-1716
1865 | 17912 |  | HT | N |  | BHA | HPJSM, P/U & M/U WIS WHIPSTOCK RETRIEVAL BHA:-- ALIGN BAKER RETRIEVING HOOK NOZZLE WITH MWD.- BHA: RETRIEVING HOOK + X-O, 1 JT X 4" DP + X-O + FLOAT SUB + MWD + FILTER SUB + X-O + 3 JT X 4" HWDP + 4 X 7 " MAGNETS, PJ, 4-3/4" DJ, 2 JT X 4" HWDP TO 332 FT.- MWD TEST: 550 GPM & 260 PSI.- MONITOR WELL ON TRIP TANK, STATIC LOSS 12 BPH . | 17912 |  | RIG | 09/20/2022 | SIN30L | FISH | KHRS-1716
1866 | 17912 | 8310 | TI | N |  | STDP | RIH W/ WIS WHIPSTOCK RETRIEVAL BHA F/ 332 FT T/ 8,310 FT.- FILL EVERY 20 STRG.- MONITOR WELL ON TRIP TANK, STATIC LOSS 12 BPH . | 17912 | 332 | RIG | 09/20/2022 | SIN30L | FISH | KHRS-1716
1867 | 17912 |  | CIRC | N |  | MPMP | FILL UP STRING EVERY 20 STD. | 17912 |  | RIG | 09/20/2022 | SIN30L | FISH | KHRS-1716
1868 | 17912 | 8314 | RTRV | N |  | WPSTK | ORIENTATE NOZZEL TO 221 DEGREE RIGHT. WASH WS SLOT. ORIENTATE WS HOOK TO 41 DEGREE LEFT OF HIGH SIDE. LATCH WS SLOT AT 8314 FT, CONFIRM ENGAGMENT WITH 10K O.P AND APPLEIED TORQUE TEST, RELEASE SAME WITH 82 KLB OVERPULL. | 17912 | 8314 | WI3 | 09/20/2022 | SIN30L | FISH | KHRS-1716
1869 | 17912 |  | OTH | N |  | NA | FLOW CHECK & WAIT FOR WHIPSTOCK PACKER RUBBER TO RETRACT, 24 BPH STATIC LOSSES. | 17912 |  | RIG | 09/20/2022 | SIN30L | FISH | KHRS-1716
1870 | 17912 | 3800 | TO | N |  | BHA | POOH W/ WIS 7" WHIPSTOCK AT CONTROLLED SPEED FROM 8314 FT TO 3,800'.- PUMP OUT FRIST 5 STD.- MONITOR WELL ON TRIP TANK, 16 BPH STATIC LOSSES. | 17912 | 8314 | RIG | 09/20/2022 | SIN30L | FISH | KHRS-1716
1871 | 34.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | ACID WASH JOB FOR L-1 & L-0 | 9 | 4751 | 18 Sep 0345 | 09/20/2022 | SIN30L | Type | KHRS-1716
1872
1873
1874 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | SND-2001 | Hrs | HWYH-1229
1875 | XTRI | GOC | 6.5 | 20 Sep 1730 - 0000 | 1920 | 902486 | EXCESS TIME TO RUN CSG DUE TO LINKS MISALIGNMENT. | JF | CTRQ |  | 09/20/2022 | SND-2001 | 6.5 | HWYH-1229
1876 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | SND-2009 | Hrs | SAHB-101
1877 | STBH | ARM | 44 | 19 Sep 0900 - 0500 | 10580 | 902387 | AFTER DRILLOUT F/S @ 10,575 FT, PU STRING FREE, ADJUST PARAMETERS, RIH BACK, CLEANOUT RAT HOLE, WHEN BIT REACH BTM @ 10,580 FT (NBRR @ 9 5/8" FLOAT SHOE AT 10,575 FT). STRING STALLED AND GET STUCK. UNABLE TO CIRC. | STUK | BHA |  | 09/20/2022 | SND-2009 | 24 | SAHB-101
1878 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | SND-2010 | Hrs | MNIF-868
1879 | HERR | RIG | 11.5 | 20 Sep 0830 - 2000 | 7064 | 902394 | THREADS ON DSA STUDS DAMAGED WHEN SETTING DOWN BOP ON WELL-HEAD LIFT BOP AND CHANGE STUDS IN DSA | BOP | BOP |  | 09/20/2022 | SND-2010 | 11.5 | MNIF-868
1880 | FOT | RIG | 1.25 | 20 Sep 0645 - 0800 | 1256 | 902492 | REPLACED TDS SAVER SUB | RR | TDS |  | 09/20/2022 | SP-165 | 1.25 | FDHL-146
1881 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | SP-165 | Hrs | FDHL-146
1882 | IDPR | SPS | 66 | 17 Sep 0030 - 2230 | 7400 | 902358 | ACCESS ISSUE TO ENTER ALL RSS BHA THRU NEWLY SIDETRACKED LATERAL. TRIP OUT & RUN MOTOR ASSY TO CHECK THE LATERAL ACCESS. | DD | RSS |  | 09/20/2022 | SP-165 | 14.75 | FDHL-146
1883 | FOT | RIG | 1.25 | 20 Sep 0645 - 0800 | 1256 | 902492 | REPLACED TDS SAVER SUB | RR | TDS |  | 09/20/2022 | SP-165 | 1.25 | FDHL-146
1884 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | SSA-302 | Hrs | HRDH-2353
1885 | FWTS | RIG | 21.5 | 19 Sep 0400 - 0200 | 3545 | 902399 | WHILE DRILLING AT 3545' W/900 GPM @1600 PSI, SUDDENLY LOST 700 PSI & +/-12KLB FROM STRING WT. SWEPT HOLE W/150 BBL HVP - CHC. | FISH | BHA |  | 09/20/2022 | SSA-302 | 20.5 | HRDH-2353
1886 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | SSA-5969 | Hrs | UTMN-3148
1887 | WC20 | ARM | 24.5 | 19 Sep 0430 - 0500 | 10092 | 902485 | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF. | WCNT | NA |  | 09/20/2022 | SSA-5969 | 24 | UTMN-3148
1888 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | T901 | Hrs | JLMN-60
1889 | HERR | RIG | 3.5 | 20 Sep 1715 - 2045 | 10514 | 902489 | ATTEMPTED TO PT ANNULAR AND OBSERVED LEAK ON SPACER SPOOL. | BOP | SPOOL |  | 09/20/2022 | T901 | 3.5 | JLMN-60
1890 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/20/2022 | T902 | Hrs | MHWZ-907
1891 | FOT | FMC | 5 | 20 Sep 1630 - 2330 | 1060 | 902482 | CRT DAMAGED DUE TO POOR MAINTENANCE. | TF | CTRQ |  | 09/20/2022 | T902 | 5 | MHWZ-907
1892 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-29 | Hrs | NYYM-3
1893 | FOT | HCO | 8 | 21 Sep 2100 - 0500 | 0 | 902543 | 7" HAL MFR PKR AT 7235' RETRIEVED WITH HAL RETRIEVING TOOL AND METALIC SLIPS LOST IN HOLE. | TF | PKR |  | 09/21/2022 | ADC-29 | 8 | NYYM-3
1894 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-42L | Hrs | SDGM-1266
1895 | FOT | RIG | 6.5 | 21 Sep 2230 - 0500 | 626 | 902544 | AT KELLY DOWN DURING PERFORMING DROP OBJECT HAZARD SURVEY, FOUND THE 4 BOLTES OF S-PIPE CLAMP OF TDS BROKEN DUE TO MEDIUM TO HIGH VIBRATIONS WHILE DRILLING. | RR | TDS |  | 09/21/2022 | ADC-42L | 6.5 | SDGM-1266
1896 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-43L | Hrs | UTMN-3118
1897 | HELD | TK3 | 123.5 | 15 Sep 0230 - 0500 | 11321 | 902217 | DRIFT WITH 3.625" (GAUGE CUTTER) TO 11,321 FT - HELD UP & UNABLE TO PASS THRU SEAL ASSEMBLY MULE SHOE & BTM OF LNR TBR. CHANGE TO 3.5" DRIFT - NO SUCCESS. | JF | LINR |  | 09/21/2022 | ADC-43L | 24 | UTMN-3118
1898 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-48 | Hrs | HRDH-2316
1899 | SDIR | ARM | 25.25 | 20 Sep 1215 - 1330 | 18441 | 902493 | AFTER 1 X BU, RACK BACK 1 STD, MADE UP TOP DRIVE, ESTABLISH CIRC, OBSERVED STRING TAKING TORQUE/ ROTARY STALLED, IMMEDIATELY PICK UP THE STD AND ATTEMPED TO GO DOWN WITH CIRC, NO SUCCESS, FOUND STRING STUCK AT 18,358'(83' OFF BOTTOM). RACK BACK THE STD AND ADD ONE SINGLE, IMMEDIATELY CONTINUE TO ACTIVATE DOWN JAR WITH TORQ AND UPWARD JAR- NO SUCCESS. | STUK | RSS |  | 09/21/2022 | ADC-48 | 8.5 | HRDH-2316
1900 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-49 | Hrs | HRDH-1934
1901 | FOT | RIG | 3 | 21 Sep 2100 - 0000 | 10996 | 902537 | WHILE DRILLING AT 10,996', HAD SPP DROP & VISUAL LEAK IN TDS S-PIPE HAMMER UNION CONNETION. | RR | TDS |  | 09/21/2022 | ADC-49 | 3 | HRDH-1934
1902 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-50 | Hrs | SFNY-1176
1903 | FOT | ARM | 11.25 | 21 Sep 1530 - 0245 | 7090 | 902542 | LOST V-SAT CONNECTION AT 7090' | TF | COMP |  | 09/21/2022 | ADC-50 | 11.25 | SFNY-1176
1904 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-51 | Hrs | SDGM-1143
1905 | WC11 | ARM | 6 | 20 Sep 0400 - 1000 | 6916 | 902516 | DURING DRILLING 12" HOLE IN ARABS FORMATION OBSERVED WELL FLOW. | WCNT | NA |  | 09/21/2022 | ADC-51 | 5 | SDGM-1143
1906 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-55L | Hrs | UTMN-3171
1907 | LCRW | TK3 | 3 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/21/2022 | ADC-55L | 3 | UTMN-3171
1908 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-56L | Hrs | UTMN-3069
1909 | FOT | TK3 | 123.75 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/21/2022 | ADC-56L | 24 | UTMN-3069
1910 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADC-57L | Hrs | ABHD-631
1911 | OTH | RIG | 12 | 21 Sep 1330 - 0130 | 2120 | 902550 | OPERATION SHUT DOWN FOR LAST FIRST AID INCIDENT INVESTIGATION. WAITING ON IDS & ADC INVESTIGATION REPORT | UPRA | NA |  | 09/21/2022 | ADC-57L | 12 | ABHD-631
1912 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADES-889 | Hrs | HRDH-2122
1913 | PCPF | ARM | 137 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/21/2022 | ADES-889 | 23.5 | HRDH-2122
1914 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADM-337 | Hrs | MRJN-900
1915 | WTHR | ARM | 3 | 21 Sep 1500 - 1800 | 13019 | 902520 | UNFAVORABLE WEATHER FOR FLOW BACK OPERATION, WIND SPEED BELOW 5 KNOTS | WON | NA |  | 09/21/2022 | ADM-337 | 3 | MRJN-900
1916 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ADM-510 | Hrs | ABSF-225
1917 | FOP | HCB | 9.75 | 21 Sep 1915 - 0500 | 7400 | 902546 | ADDITIONAL CLEAN OUT RUN REQUESTED BY HALLIBURTON BEFORE RETREIVING RBP | JF | RBP |  | 09/21/2022 | ADM-510 | 9.75 | ABSF-225
1918 | FOT | RIG | 2 | 21 Sep 1300 - 1500 | 6696 | 902519 | CHANGE OUT TOP DRIVE GRAPPLE DIES. | RR | TDS |  | 09/21/2022 | ARO-4001 | 2 | MRJN-537
1919 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ARO-4001 | Hrs | MRJN-537
1920 | FOT | FMC | 19.5 | 21 Sep 0500 - 0500 | 6696 | 902518 | FRANKS CRT LEAKING | TF | CRT |  | 09/21/2022 | ARO-4001 | 19.5 | MRJN-537
1921 | FOT | RIG | 2 | 21 Sep 1300 - 1500 | 6696 | 902519 | CHANGE OUT TOP DRIVE GRAPPLE DIES. | RR | TDS |  | 09/21/2022 | ARO-4001 | 2 | MRJN-537
1922 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | CG-1 | Hrs | MRJN-741
1923 | FOT | HWP | 1.5 | 21 Sep 0330 - 0500 | 100 | 902547 | PROBLEM FOUND DURING SURFACE TEST. PROBLEM WITH ELECTRICAL CONNECTION BETWEEN TOOLS. | TF | WLT |  | 09/21/2022 | CG-1 | 1.5 | MRJN-741
1924 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | DPS-43 | Hrs | SDGM-1218
1925 | FOT | HCO | 117 | 17 Sep 0700 - 0500 | 11639 | 902336 | HALLIBURTON UPPER COMPLETION SEAL ASSY FAIL PRESSURE TEST | TF | SEAL |  | 09/21/2022 | DPS-43 | 24 | SDGM-1218
1926 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | DPS-5 | Hrs | HRDH-1917
1927 | FOT | WDS | 21 | 21 Sep 0700 - 0500 | 9900 | 902521 | LOST SIGNAL OF WFD MWD/GR TOOL WHILE DRILLING. | BHA | MWD |  | 09/21/2022 | DPS-5 | 21 | HRDH-1917
1928 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ENS-108 | Hrs | ZULF-2015
1929 | OTH | RIG | 159 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/21/2022 | ENS-108 | 24 | ZULF-2015
1930 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | ENSCO-76 | Hrs | MRJN-2004
1931 | FOT | BCR | 1 | 21 Sep 1900 - 2000 | 2681 | 902522 | BAKER HUGHES CASING JAM UNIT FAILED | TF | CTRQ |  | 09/21/2022 | ENSCO-76 | 1 | MRJN-2004
1932 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | HI-4 | Hrs | BRRI-1001
1933 | HERR | RIG | 2.5 | 21 Sep 0230 - 0500 | 5600 | 902535 | DURING PREPARING FOR APPLYING PRESSURE OVER RBP TO STABILIZE PRESS ABOVE RBP, ASSISTANT DRILLAR CLOSED X-TREE CROWN VALVE INSTEAD OF WING VALVE AND EXPRO SLICKLINE CUT AND DROPPED IN THE STRING. | FISH | STRG |  | 09/21/2022 | HI-4 | 2.5 | BRRI-1001
1934 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | JACK-202 | Hrs | THRY-829
1935 | FOT | ARM | 30.75 | 20 Sep 2215 - 0500 | 5185 | 902480 | CANNOT RUN 7" SCREENS TAG AT 5185' AT LANDING COLLAR. | TF | CSG |  | 09/21/2022 | JACK-202 | 24 | THRY-829
1936 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | NA-18S | Hrs | SDGM-444
1937 | FOT | RIG | 32.75 | 20 Sep 1030 - 1915 | 14795 | 902476 | LOST POWER TO DRAWWORK & MUD PUMPS WHILE DRILLING CAUSING BIT NOZZLE PLUGGED. | RR | PSYS |  | 09/21/2022 | NA-18S | 14.25 | SDGM-444
1938 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | NBR-654S | Hrs | ANDR-1018
1939 | FOT | WCR | .75 | 21 Sep 0415 - 0500 | 577 | 902552 | REPAIR ON WFD POWER TONG UNIT. | TF | CTRQ |  | 09/21/2022 | NBR-654S | .75 | ANDR-1018
1940 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | PA-218S | Hrs | HRDH-1976
1941 | UXDF | ARN | 127.5 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/21/2022 | PA-218S | 24 | HRDH-1976
1942 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | PA-326S | Hrs | SHDN-22
1943 | FOT | RIG | 44 | 20 Sep 0900 - 0500 | 10290 | 902483 | DURING RIH WITH 5-7/8" ROT.DRLG ASSY AT 10290 FT, OBSERVED WATER LEAK FROM EDS COOLING SYSTEM, CHECK SAME AND FOUND WORN OUT IN THE HUB TEETH AND EDS SPROKET (EATON BRAKE). | RR | DWKS |  | 09/21/2022 | PA-326S | 24 | SHDN-22
1944 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | PA-785S | Hrs | QTIF-269
1945 | FOT | RIG | 1 | 21 Sep 1100 - 1200 | 16869 | 902498 | TROUBLESHOOTING RIG PUMPS DUE TO NOISY DATA FOR MWD. | RR | MPMP |  | 09/21/2022 | PA-785S | 1 | QTIF-269
1946 | FOT | INW | 3.5 | 21 Sep 2030 - 0000 | 12180 | 902526 | TRIED TO SET 4-1/2" INTERWELL RBP WITH SLB SLICK LINE, INTERWELL SEATING TOOL WASN'T ACTIVATED AND PLUG WASN'T SET. | TF | BP |  | 09/21/2022 | PA-861S | 3.5 | HRDH-1973
1947 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | PA-861S | Hrs | HRDH-1973
1948 | FOT | SCP | 127.25 | 16 Sep 0500 - 0200 | 16845 | 902241 | LEAK SUSPECTED FROM SLB MSF KICK START VALVE. | TF | HVLV |  | 09/21/2022 | PA-861S | 17.5 | HRDH-1973
1949 | FOT | INW | 3.5 | 21 Sep 2030 - 0000 | 12180 | 902526 | TRIED TO SET 4-1/2" INTERWELL RBP WITH SLB SLICK LINE, INTERWELL SEATING TOOL WASN'T ACTIVATED AND PLUG WASN'T SET. | TF | BP |  | 09/21/2022 | PA-861S | 3.5 | HRDH-1973
1950 | FOT | RIG | 2.5 | 21 Sep 2130 - 0000 | 15702 | 902534 | EXCESS TIME TO CHANGE PIPE RAM DUE TO BONNET BOLT THREAD. | RR | RWCS |  | 09/21/2022 | PN-9 | 2.5 | MRJN-673
1951 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | PN-9 | Hrs | MRJN-673
1952 | CFST | HCM | 279 | 14 Aug 2045 - 1845 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 09/21/2022 | PN-9 | 13.75 | MRJN-673
1953 | FOT | RIG | 2.5 | 21 Sep 2130 - 0000 | 15702 | 902534 | EXCESS TIME TO CHANGE PIPE RAM DUE TO BONNET BOLT THREAD. | RR | RWCS |  | 09/21/2022 | PN-9 | 2.5 | MRJN-673
1954 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SA5898 | Hrs | MDRK-66
1955 | FOT | BAW | 25.5 | 19 Sep 1100 - 2315 | 15908 | 902384 | BAKER PRESSURE POINT LOGGING TOOL (RUN#3) HAD MALFUNCTIONED. | TF | WLT |  | 09/21/2022 | SA5898 | 5.5 | MDRK-66
1956 | 17912 | 425 | TO | N |  | BHA | POOH W/ L-1WPS RETRIVAL BHA @ CONTROLLED SPEED F/3,741' T/ TOP OF BHA @ 425'.- HAD 16 BPH STATIC LOSSES. | 17912 | 3800 | RIG | 09/21/2022 | SIN30L | FISH | KHRS-1716
1957 | 17912 |  | OTH | N |  | NA | FLOW CHECK, STATIC LOSS @ 16 BPH. | 17912 |  | RIG | 09/21/2022 | SIN30L | FISH | KHRS-1716
1958 | 17912 |  | HT | N |  | BHA | CONT POOH TO SURFACE, L/D WIS WPS L-1 (100% RECOVERY), 7" MAGNETS, RETRIEVAL HOOK & MWD. - COLLECTED 7.5 KG FINE DEBRIS FROM 7'' STRING MAGNETS. - STATIC LOSSES RATE @ 16 BPH. | 17912 |  | RIG | 09/21/2022 | SIN30L | FISH | KHRS-1716
1959 | 17912 |  | HT | C | 4751 | BHA | (OOS) P/U & M/U 6 1/8" SLICK BHA.- 6.125" WELDED TRIC(OPEN NOZZLES)+BIT SUB+X-O+4"HWDP*6JNTS+4-3/4" D.J+4"HWDP*2JNTS.- MONITOR FROM TRIP TANK, STATIC LOSS RATE @ 16 BPH. | 17912 |  | RIG | 09/21/2022 | SIN30L | STIM | KHRS-1716
1960 | 17912 | 8716 | TI | C | 4751 | STDP | (OOS) RIH 6 1/8" SLICK BHA F/ 281' T/ LINER SHOE @ 8716'.- MONITOR FROM TRIP TANK, STATIC LOSS RATE @ 16 BPH. | 17912 | 281 | RIG | 09/21/2022 | SIN30L | STIM | KHRS-1716
1961 | 17912 |  | CIRC | C | 4751 | MPMP | (OOS) FILL UP STRING EVERY 20 STD. | 17912 |  | RIG | 09/21/2022 | SIN30L | STIM | KHRS-1716
1962 | 17912 | 17912 | RW | C | 4751 | BIT | (OOS) CONT. RIH W/ 6-1/8" SLICK BHA F/ LINER SHOE @ 8716' T/ 18129'-FILL UP STRING EVERY 20 STDS-HOLE IN GOOD CONDITION | 17912 | 8716 | RIG | 09/21/2022 | SIN30L | STIM | KHRS-1716
1963 | 17912 |  | OTH | C | 4751 | NA | (OOS) HPJSM, M/U 10FT 4" PUP JOINT, TIW & SIDE ENTRY SIDE SUB MEANWHILE R/U SURFACE LINES, FLUSH THE LINE & P/T SAME T/300 /5000 PSI, OK.- MONITOR FROM TRIP TANK, STATIC LOSS RATE @ 16 BPH. | 17912 |  | BCT | 09/21/2022 | SIN30L | STIM | KHRS-1716
1964 | 17912 |  | OTH | C | 4751 | NA | (OOS) SPOT ACID WASH IN OPEN HOLE (L -0) AS FOLLOW:- PUMPED 398 BBL OF PRE-FLUSH 66 PCF, PUMPED 197 BBL OF ACID WASH TREATMENT (10% FORMIC ACID) 66 PCF, STOP PUMPING, CLOSE BOP - RETURN THROUGH FULL OPEN CHOKE MANIFOLD.- CONT. PUMP 201 BBL ACID WASH TREATMENT (10% FORMIC ACID) 66 PCF.- PUMPED 200 BBL POST FLUSH @ 66 PCF TO SPOT ACID IN OPEN HOLE. | 17912 |  | BCT | 09/21/2022 | SIN30L | STIM | KHRS-1716
1965 | 17912 |  | OTH | C | 4751 | NA | (OOS) FLOWCHECK THRU CHOKE, 45 BPH LOSSES, OPEN BOP. | 17912 |  | RIG | 09/21/2022 | SIN30L | STIM | KHRS-1716
1966 | 17912 | 16900 | RW | C | 4751 | BIT | (OOS) POOH W/ 6-1/8" (L-0) ACID WASH SLICK BHA TO 16,900'.- HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK.- HAD 45 BPH STATIC LOSSES. | 17912 | 17912 | RIG | 09/21/2022 | SIN30L | STIM | KHRS-1716
1967 | 52.5 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | ACID WASH JOB FOR L-1 & L-0 | 18.25 | 4751 | 18 Sep 0345 | 09/21/2022 | SIN30L | Type | KHRS-1716
1968
1969
1970 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SINO-22 | Hrs | BRRI-1144
1971 | FOT | RIG | 17 | 21 Sep 1200 - 0500 | 6365 | 902525 | REPLACED TDS ROTARY HOSE DUE TO SMALL LEAK, AFTER TRIP OUT TO SHOE. PT SAME, RUN BACK TO BOTTOM. | RR | CSYS |  | 09/21/2022 | SINO-22 | 17 | BRRI-1144
1972 | 7588 |  | ND | E |  | SNIP | HPJSM, N/D SHOOTING BPL & N/U BELL NPL. | 7588 |  | RIG | 09/21/2022 | SINO-36L | LOG | ANDR-378
1973 | 7588 |  | OTH | N |  | NA | M/U & RIH 18 STDS 4" HWDP, M/U HALLIBURTON 9-5/8" RTTS PACKER WITH STORM VALVE AND RIH ON 2 STDS X 4" DP TO 200 FT. | 7588 |  | IWS | 09/21/2022 | SINO-36L | WH | ANDR-378
1974 | 7588 | 200 | SET | N |  | RBP | SET 9-5/8" RTTS @ 200 FT & P/T TO 1000 PSI, OK, RELEASE RTTS RUNNING TOOL, POH & RACK BACK 2 STDS 4" DP, L/D SETTING TOOL.- P/T 9-5/8 " RTTS & STORM VALVE TO 1000 PSI, HOLD. | 7588 | 200 | HCB | 09/21/2022 | SINO-36L | WH | ANDR-378
1975 | 7588 |  | ND | N |  | BOP | HPJSM. HANG FLOW LINE, N/D BELL NIPPLE, REMOVE MOUSE HOLE, DISCONNECT EM. K.LINE & HANG BOP. | 7588 |  | RIG | 09/21/2022 | SINO-36L | BOP | ANDR-378
1976 | 7588 |  | OTH | N |  | NA | HPJSM, DIG OUT CELLAR 6 FT BELOW LANDING BASE.- ISSUE REQUIRED PTW & DISCUSSED JSA .CHECK 9" X 13" CCA IS ZERO PRESSURE - PT 9-5/8" X 13-3/8" CCA TO 500 PSI WITH INHIBITED WATER, PRESSURE DROP TO 300 PSI & HOLD (NO INJECTIVITY).- PT 9-5/8" CSG SLIPS TO 1000 PSI, OK- MANSOORI PERFORM INSPECTION FOR LANDING BASE ( GOOD CONDITION ) & UT FOR 18-5/8" CSG (SEAL WELDED TO DONUT PLATE). | 7588 |  | IWS | 09/21/2022 | SINO-36L | WH | ANDR-378
1977 | 7588 |  | OTH | N | 4788 | NA | HPJSM, HOT-HED WELD 1-1/2" NIPPLE ON 18-5/8" CSG, MANSOORI PERFORM MPI FOR WELDING, WILD WELL PERFORM HOT TAPPING ON 18-5/8" CSG, NO PRESSURE OR GAS ON 18-5/8" X 13-3/8" CCA. | 7588 |  | IWS | 09/21/2022 | SINO-36L | WH | ANDR-378
1978 | 7588 |  | OTH | N |  | NA | HOTHED CUT WINDOW ON 18-5/8" CSG, REMOVE CMT, ALMANSOORI PERFORM UT INSPECTION ON 13-3/8" CSG , GOOD CONDITION, FILL BACK 18-5/8" X 13-3/8" CCA WITH CMT, HOT-HEAD WELD BACK WINDOW, ALMANSOORI PERFORM MPI FOR WELDING AREA-OK, FILL BAK CELLAR WITH SWEET SAND | 7588 |  | IWS | 09/21/2022 | SINO-36L | WH | ANDR-378
1979 | 7588 |  | ND | N |  | WH | HPJSM, N/D OLD 13-5/8" X 11" MCEVOY THS, HOT-HED CUT 9-5/8" CSG & DRESS SAME. N/U NEW 13-5/8" X 11" CIW THS WITH 9-5/8" INTERFERENCE SEAL.- P/T 9-5/8" CSG SLIP & SEAL TO 1500 PSI, OK. | 7588 |  | RIG | 09/21/2022 | SINO-36L | WH | ANDR-378
1980 | 7588 |  | NU | N |  | BOP | HPJSM , N/U CLASS "A" 13-5/8" 5M BOPE & RELATED EQUIPMENT . | 7588 |  | RIG | 09/21/2022 | SINO-36L | BOP | ANDR-378
1981 | 7588 |  | BOPT | N |  | BOP | HPJSM, F/T BOPE, M/U TSET ASSY, FULL BOPE TEST AS PER SA STANDARD, L/D TEST ASSY. | 7588 |  | RIG | 09/21/2022 | SINO-36L | BOP | ANDR-378
1982 | 7588 |  | OTH | N |  | NA | HPJSM, RIH, UNSET, POH & L/D 9-5/8" RTTS . | 7588 |  | IWS | 09/21/2022 | SINO-36L | WH | ANDR-378
1983 | 7588 | 0 | TO | N |  | STDP | POH 18 STDS 4" HWDP & RACK BACK SAME TO DERRICK.- MONITOR WELL ON TRIP TANK, STATIC. | 7588 | 1800 | RIG | 09/21/2022 | SINO-36L | PA | ANDR-378
1984 | 7588 |  | HT | N |  | BHA | HPJSM - M/U 7'' WFD WHIPSTOCK/MWD ASSY. ALIGNED WHIPSTOCK FACE WITH ORIENT SUB (MWD), MWD SHALLOW TEST, OK. BHA : 5 1/2'' QC RHN WHIPSTOCK. 6-1/8'' LEAD MILL (WF). 6-1/8'' FLEX MILL (WF). 1 JOINT 3 1/2'' HWDP (WF). F/S (SPERRY) + MWD (SPERRY) + X/O. | 7588 |  | RIG | 09/21/2022 | SINO-36L | TINL | ANDR-378
1985 | 7588 |  | OTH | N |  | NA | RIH WITH 7'' WHIPSTOCK ASSY ON 4" HW/DP TO 2300 FT ... INC @ RPT.- CONTROLLED RIH SPEED 3 MIN/STAND SLIPS TO SLIPS.- PASSED VERY CAREFULLY FROM BOP STACK & WELLHEAD.- CIRC. STRG VOLUME EVERY 20 STAND | 7588 |  | WWD | 09/21/2022 | SINO-36L | TINL | ANDR-378
1986 | 1.5 | OOSS | Category | DOOS ID | HTAP | Out of Scope Summary | HOT TAPING 18-5/8" CSG. | 1.5 | 4788 | 21 Sep 1130 | 09/21/2022 | SINO-36L | Type | ANDR-378
1987
1988
1989 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SND-2009 | Hrs | SAHB-101
1990 | STBH | ARM | 66 | 19 Sep 0900 - 0500 | 10580 | 902387 | AFTER DRILLOUT F/S @ 10,575 FT, PU STRING FREE, ADJUST PARAMETERS, RIH BACK, CLEANOUT RAT HOLE, WHEN BIT REACH BTM @ 10,580 FT (NBRR @ 9 5/8" FLOAT SHOE AT 10,575 FT). STRING STALLED AND GET STUCK. UNABLE TO CIRC. | STUK | BHA |  | 09/21/2022 | SND-2009 | 22 | SAHB-101
1991 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SNT-025 | Hrs | SFNY-517
1992 | FOT | NCT | 8 | 21 Sep 2100 - 0500 | 5150 | 902548 | WEATHERFORD CABLE HEAD LOST SIGNAL TO LOGGING TOOLS | TF | CTAC |  | 09/21/2022 | SNT-025 | 8 | SFNY-517
1993 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SP-165 | Hrs | FDHL-146
1994 | FPMP | RIG | .5 | 21 Sep 0430 - 0500 | 8709 | 902549 | CHANGE TWO PISTON AND ONE VALVE OF MP# 2 | RR | MPMP |  | 09/21/2022 | SP-165 | .5 | FDHL-146
1995 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SP-257 | Hrs | HZEM-162402
1996 | FOT | SPS | 13.5 | 21 Sep 1530 - 0500 | 10129 | 902541 | UNABLE TO ACHIEVE DESIRED BUR | BHA | RSS |  | 09/21/2022 | SP-257 | 13.5 | HZEM-162402
1997 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SSA-201 | Hrs | MNHZ-1
1998 | WHOL | RIG | 2.25 | 21 Sep 0245 - 0500 | 15561 | 902551 | DRILLING AT 15.561', PUMP PRESSURE DROPPED BY 1000 PSI. TROUBLE SHOT BY CHANGING MUD PUMPS AND VERIFYING ALL SURFACE EQUIPMENT ARE OK. - CONFIRMED THERE IS A DOWN HOLE WASHOUT. | DSF | DP |  | 09/21/2022 | SSA-201 | 2.25 | MNHZ-1
1999 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SSA-302 | Hrs | HRDH-2353
2000 | FWTS | RIG | 20 | 21 Sep 0830 - 0500 | 3767 | 902517 | LOSS 900 PSI PUMP PRESSURE, AND NO TQ., POOH FOUND BACKOFF BETWEEN SHOCK SUB AND NEAR BIT REAMER | FISH | BHA |  | 09/21/2022 | SSA-302 | 20 | HRDH-2353
2001 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SSA-5868 | Hrs | HRDH-2364
2002 | IBSL | VAR | 11.5 | 16 Sep 0600 - 0500 | 8915 | 902240 | POOR ROP | TF | BIT |  | 09/21/2022 | SSA-5868 | 10.5 | HRDH-2364
2003 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SSA-5914 | Hrs | WDYH-80
2004 | HERR | RIG | 1.5 | 21 Sep 1700 - 1830 | 21000 | 902523 | OBSERVED WIRELINE CABLE IS IN CONTACT WITH STABBING BOARD AFTER APPLIED TENSION DUE TO WRONG INSTALLATION OF UPPER SHEAVE BY RIG CREW. | JF | WLT |  | 09/21/2022 | SSA-5914 | 1.5 | WDYH-80
2005 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SSA-5969 | Hrs | UTMN-3148
2006 | WC20 | ARM | 38 | 19 Sep 0430 - 0330 | 10092 | 902485 | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF. | WCNT | NA |  | 09/21/2022 | SSA-5969 | 22.5 | UTMN-3148
2007 | FOT | RIG | .5 | 21 Sep 0300 - 0330 | 3850 | 902545 | ONE HOSE IN THE IRONROGHNECK GOT PARTED AND NEEDED TO REPLACED. | RR | HSYS |  | 09/21/2022 | SSA-5971 | .5 | HWYH-1215
2008 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/21/2022 | SSA-5971 | Hrs | HWYH-1215
2009 | FOT | RIG | 1 | 21 Sep 0630 - 0730 | 9000 | 902532 | TDS MAIN HYDROLIC HOSE WAS PARTED AND NEEDED TO BE CHANGED. | RR | TDS |  | 09/21/2022 | SSA-5971 | 1 | HWYH-1215
2010 | FOT | RIG | 1 | 21 Sep 1030 - 1130 | 3500 | 902533 | HPU FILTER HAD BEEN PLUGGED AND THE UNIT COULD NOT OPERATED, IRON ROUGHNECK AND POWER TOUNG COULD NOT BE OPERATED TOO. | RR | HSYS |  | 09/21/2022 | SSA-5971 | 1 | HWYH-1215
2011 | FOT | RIG | .5 | 21 Sep 0300 - 0330 | 3850 | 902545 | ONE HOSE IN THE IRONROGHNECK GOT PARTED AND NEEDED TO REPLACED. | RR | HSYS |  | 09/21/2022 | SSA-5971 | .5 | HWYH-1215
2012 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | 088TE | Hrs | QTIF-519
2013 | FOT | RIG | .5 | 22 Sep 1100 - 1130 | 11435 | 902605 | GENERATORS GEN#5 TRIP DOWN DUE TO HIGH TEMPERATURE, LED TO OTHER TWO GENERATORS #2 & #3 OVERLOADED & TRIPP DOWN. FIX SAME & RESUME OPERATION. | RR | PSYS |  | 09/22/2022 | 088TE | .5 | QTIF-519
2014 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | ADC-51 | Hrs | SDGM-1143
2015 | FOT | RIG | 5 | 22 Sep 0630 - 1130 | 8452 | 902599 | WHILE DRILLING 12" HOLE SECTION, RIG HAD COMPLETE BLACK OUT. | RR | PSYS |  | 09/22/2022 | ADC-51 | 5 | SDGM-1143
2016 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | ADC-55L | Hrs | UTMN-3171
2017 | LCRW | TK3 | 27 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/22/2022 | ADC-55L | 24 | UTMN-3171
2018 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | ADC-56L | Hrs | UTMN-3069
2019 | FOT | TK3 | 147.75 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/22/2022 | ADC-56L | 24 | UTMN-3069
2020 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | ADC-58L | Hrs | ABHD-183
2021 | FOT | RIG | 6.5 | 22 Sep 1500 - 2130 | 655 | 902643 | ATTEMPTED TO P/T DVRT TO 200 PSI, OBSERVED LEAKS ON WELDED NECK FLANGE & 1502 NIPPLE. (WELDING AREA). | RR | FLR |  | 09/22/2022 | ADC-58L | 6.5 | ABHD-183
2022 | FOT | BHI | 19 | 22 Sep 0930 - 0500 | 10980 | 902596 | BAKER RSS DIDN'T BUILD ENOUGH INCLINATION. DECISION MADE TO POOH AND CHANGE TOOLS. | BHA | RSS | 902524 | 09/22/2022 | ADES-889 | 19 | HRDH-2122
2023 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | ADES-889 | Hrs | HRDH-2122
2024 | PCPF | ARM | 160.5 | 15 Sep 0100 - 0930 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/22/2022 | ADES-889 | 4.5 | HRDH-2122
2025 | FOT | BHI | 19 | 22 Sep 0930 - 0500 | 10980 | 902596 | BAKER RSS DIDN'T BUILD ENOUGH INCLINATION. DECISION MADE TO POOH AND CHANGE TOOLS. | BHA | RSS | 902524 | 09/22/2022 | ADES-889 | 19 | HRDH-2122
2026 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | ADM-337 | Hrs | MRJN-900
2027 | WTHR | ARM | 4 | 21 Sep 1500 - 0600 | 13019 | 902520 | UNFAVORABLE WEATHER FOR FLOW BACK OPERATION, WIND SPEED BELOW 5 KNOTS | WON | NA |  | 09/22/2022 | ADM-337 | 1 | MRJN-900
2028 | FOT | RIG | 2 | 22 Sep 0245 - 0445 | 6809 | 902638 | AFTER MAKING CONNECTION OBSERVED WASH PIPE ON TDS LEAKING. | RR | TDS |  | 09/22/2022 | ARO-4001 | 2 | MRJN-537
2029 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | ARO-4001 | Hrs | MRJN-537
2030 | CFFM | ARM | 118.25 | 15 Sep 2130 - 0500 | 6122 | 902242 | HAD TOTAL LOSSES WHILE DRILLING 12-1/4" HOLE. CURE LOSSES WITH CMT PLUG, SET EZSV @ 5902-FT. RE-DRILL 12-1/4" HOLE. | LCIR | SQZ |  | 09/22/2022 | ARO-4001 | 14.25 | MRJN-537
2031 | FOT | FMC | 27.25 | 21 Sep 0500 - 1245 | 6696 | 902518 | FRANKS CRT LEAKING | TF | CRT |  | 09/22/2022 | ARO-4001 | 7.75 | MRJN-537
2032 | FOT | RIG | 2 | 22 Sep 0245 - 0445 | 6809 | 902638 | AFTER MAKING CONNECTION OBSERVED WASH PIPE ON TDS LEAKING. | RR | TDS |  | 09/22/2022 | ARO-4001 | 2 | MRJN-537
2033 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | CG-1 | Hrs | MRJN-741
2034 | FOT | HWP | 4.5 | 21 Sep 0330 - 0800 | 100 | 902547 | PROBLEM FOUND DURING SURFACE TEST. PROBLEM WITH ELECTRICAL CONNECTION BETWEEN TOOLS. | TF | WLT |  | 09/22/2022 | CG-1 | 3 | MRJN-741
2035 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | DPS-43 | Hrs | SDGM-1218
2036 | FOT | HCO | 133 | 17 Sep 0700 - 2100 | 11639 | 902336 | HALLIBURTON UPPER COMPLETION SEAL ASSY FAIL PRESSURE TEST | TF | SEAL |  | 09/22/2022 | DPS-43 | 16 | SDGM-1218
2037 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | DPS-5 | Hrs | HRDH-1917
2038 | FOT | WDS | 23 | 21 Sep 0700 - 0700 | 9900 | 902521 | LOST SIGNAL OF WFD MWD/GR TOOL WHILE DRILLING. | BHA | MWD |  | 09/22/2022 | DPS-5 | 2 | HRDH-1917
2039 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | ENS-108 | Hrs | ZULF-2015
2040 | OTH | RIG | 183 | 15 Sep 1300 - 0500 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/22/2022 | ENS-108 | 24 | ZULF-2015
2041 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | HI-4 | Hrs | BRRI-1001
2042 | HERR | RIG | 26.5 | 21 Sep 0230 - 0500 | 5600 | 902535 | DURING PREPARING FOR APPLYING PRESSURE OVER RBP TO STABILIZE PRESS ABOVE RBP, ASSISTANT DRILLAR CLOSED X-TREE CROWN VALVE INSTEAD OF WING VALVE AND EXPRO SLICKLINE CUT AND DROPPED IN THE STRING. | FISH | STRG |  | 09/22/2022 | HI-4 | 24 | BRRI-1001
2043 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | JACK-202 | Hrs | THRY-829
2044 | IBHA | RIG | 54.75 | 20 Sep 2215 - 0500 | 5185 | 902480 | CANNOT RUN 7" SCREENS TAG AT 5185' AT LANDING COLLAR. DUE TO UNDER GAUGE OF 8 1/2" NBRM & 8 1/2" STRM. | BHA | RM |  | 09/22/2022 | JACK-202 | 24 | THRY-829
2045 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | NBR-196S | Hrs | SDGM-1223
2046 | FOT | ITS | 1.5 | 22 Sep 0915 - 1045 | 5303 | 902576 | 13-3/8" FMS CSG SLIPS FAILED TO OPERATE DUE TO HYDRAULIC ISSUES. | TF | CTRQ |  | 09/22/2022 | NBR-196S | 1.5 | SDGM-1223
2047 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | NBR-654S | Hrs | ANDR-1018
2048 | FOT | WCR | 1.25 | 21 Sep 0415 - 0530 | 577 | 902552 | REPAIR ON WFD POWER TONG UNIT. | TF | CTRQ |  | 09/22/2022 | NBR-654S | .5 | ANDR-1018
2049 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | PA-218S | Hrs | HRDH-1976
2050 | UXDF | ARN | 151.5 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/22/2022 | PA-218S | 24 | HRDH-1976
2051 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | PA-326S | Hrs | SHDN-22
2052 | FOT | RIG | 63 | 20 Sep 0900 - 0000 | 10290 | 902483 | DURING RIH WITH 5-7/8" ROT.DRLG ASSY AT 10290 FT, OBSERVED WATER LEAK FROM EDS COOLING SYSTEM, CHECK SAME AND FOUND WORN OUT IN THE HUB TEETH AND EDS SPROKET (EATON BRAKE). | RR | DWKS |  | 09/22/2022 | PA-326S | 19 | SHDN-22
2053 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SCTD-2 | Hrs | JFYN-11
2054 | FOT | RIG | 6 | 22 Sep 1730 - 2330 | 0 | 902601 | STRIPPERS SEALS WAS NOT INSTALLED PROPERLY, INSPECTED AND RE-INSTAL SAME. | RR | HSYS |  | 09/22/2022 | SCTD-2 | 6 | JFYN-11
2055 | 18129 | 8716 | RW | C | 4751 | BIT | ( OOS ) POOH 6 1/8" ACID WASH BHA F/16900' T/ LINER SHOE @ 8716'.-HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK, STATIC LOSS 40 BPH . | 18129 | 16900 | RIG | 09/22/2022 | SIN30L | STIM | KHRS-1716
2056 | 18129 |  | CIRC | C | 4751 | MPMP | (OOS) CLOSE BOP, CIRC. & CONDITION 66 PCF BRINE IN/OUT THROUGH CHOKE MANIFOLD.- CIRCULATE 450 BBL OF 66 PCF INHIBITED BRINE TILL HAD CLEAN RETURN ON SURFACE & OPENED BOP. | 18129 |  | RIG | 09/22/2022 | SIN30L | STIM | KHRS-1716
2057 | 18129 |  | OTH | C | 4751 | NA | (OOS) FLOW CHECK, STATIC LOSS RATE @ 16 BPH. | 18129 |  | RIG | 09/22/2022 | SIN30L | STIM | KHRS-1716
2058 | 18129 | 5750 | LDP | C | 4751 | STRG | CONT POOH W/ 6-1/8" ACID WASH BHA F/ LINER SHOE @ 8716' T/ 5750' MEANWHILE L/D 4" DP (93 JNTS) .- MONITOR WELL ON TRIP TANK, STATIC LOSS 24 BPH . | 18129 | 8716 | RIG | 09/22/2022 | SIN30L | STIM | KHRS-1716
2059 | 18129 | 281 | LDP | C |  | STRG | CONT POOH W/ 6-1/8" ACID WASH BHA F/ LINER SHOE @ 5750' T/ TOP OF BHA @ 281' MEANWHILE L/D 4" DP ( 171 JNTS) .- MONITOR WELL ON TRIP TANK, STATIC LOSS 24 BPH . | 18129 | 5750 | RIG | 09/22/2022 | SIN30L | STIM | KHRS-1716
2060 | 18129 |  | OTH | C | 4751 | NA | ( OOS ) FLOW CHECK, STATIC LOSS 24 BPH . | 18129 |  | RIG | 09/22/2022 | SIN30L | STIM | KHRS-1716
2061 | 18129 |  | HT | C | 4751 | BHA | ( OOS ) L/D 6-1/8"( L-0) ACID WASH BHA.- MONITOR WELL ON TRIP TANK, STATIC LOSS 24 BPH . | 18129 |  | RIG | 09/22/2022 | SIN30L | STIM | KHRS-1716
2062 | 18129 |  | HT | C |  | STRG | L/D EXCESS 4" DP FROM DERRICK (78 JNTS) .- MONITOR WELL ON TRIP TANK, STATIC LOSS 24 BPH . | 18129 |  | RIG | 09/22/2022 | SIN30L | STIM | KHRS-1716
2063 | 66 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | ACID WASH JOB FOR L-1 & L-0 | 13.5 | 4751 | 18 Sep 0345 | 09/22/2022 | SIN30L | Type | KHRS-1716
2064
2065
2066 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SINO-22 | Hrs | BRRI-1144
2067 | FOT | RIG | 20.5 | 21 Sep 1200 - 0900 | 6365 | 902525 | REPLACED TDS ROTARY HOSE DUE TO SMALL LEAK, AFTER TRIP OUT TO SHOE. PT SAME, RUN BACK TO BOTTOM. | RR | CSYS |  | 09/22/2022 | SINO-22 | 3.5 | BRRI-1144
2068 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SINO-33L | Hrs | HRDH-1542
2069 | IBSL | TK2 | 1 | 22 Sep 0800 - 0900 | 5492 | 902602 | WHILE DRILLING 8.5" HOLE WITH MOTORIZED RSS BHA,ROP FOUND TO BE LOWER THAN USUAL, DESCION MADE TO POOH AND TROUBLESHOOT MOTOR CLEARENCE AND BIT. FOUND NO ISSUE WITH MOTOR CLEARENCE, BIT WAS NOT IN GOOD CONDITION. | LROP | BIT |  | 09/22/2022 | SINO-33L | 1 | HRDH-1542
2070 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SINO-47 | Hrs | HWYH-1341
2071 | FOT | BAW | 5 | 22 Sep 1100 - 1600 | 14080 | 902636 | RE-TEST LOGGING TOOLS PRIOR TO START RUN IN OPEN HOLE, LOST COMMUNICATION WITH LOGGING TOOLS, TROUBLESHOOT, NO SUCCESS. POOH WITH AND REPLACED LATCH CONNECTOR, RIH AND LATCHED ON LOGGING TOOLS. CONFIRMED GOOD SIGNAL. | TF | WLT |  | 09/22/2022 | SINO-47 | 5 | HWYH-1341
2072 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SND-2004 | Hrs | BRRI-1148
2073 | FOT | HCB | 3.5 | 22 Sep 0500 - 0830 | 8179 | 902598 | UNABLE TO RETRIEVE HALLIBURTON MONOLOCK PLUG USING NESR SLICKLINE. DECISION MADE TO USE OILSERV COIL TUBING RETRIEVAL TOOL. THE RIG UP OF CT PLANNED FOR FLOWBACK OPERATION. | TF | RBP |  | 09/22/2022 | SND-2004 | 3.5 | BRRI-1148
2074 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SND-2007 | Hrs | AWTD-104001
2075 | FOT | RIG | 3.5 | 22 Sep 2030 - 0000 | 8539 | 902637 | WATER FLOW FOR COOLING SYSTEM ON DRAW WORKS IS MALFUNCTION. | RR | DWKS |  | 09/22/2022 | SND-2007 | 3.5 | AWTD-104001
2076 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SND-2009 | Hrs | SAHB-101
2077 | STBH | ARM | 89 | 19 Sep 0900 - 0500 | 10580 | 902387 | AFTER DRILLOUT F/S @ 10,575 FT, PU STRING FREE, ADJUST PARAMETERS, RIH BACK, CLEANOUT RAT HOLE, WHEN BIT REACH BTM @ 10,580 FT (NBRR @ 9 5/8" FLOAT SHOE AT 10,575 FT). STRING STALLED AND GET STUCK. UNABLE TO CIRC. | STUK | BHA |  | 09/22/2022 | SND-2009 | 23 | SAHB-101
2078 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SND-3003 | Hrs | HRDH-1981
2079 | FOT | MSD | .75 | 22 Sep 1115 - 1200 | 0 | 902642 | EXCESSIVE TIME TO CONNECT AND CALIBRATED THE JAM UNIT | TF | CTRQ |  | 09/22/2022 | SND-3003 | .75 | HRDH-1981
2080 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SNT-025 | Hrs | SFNY-517
2081 | FOT | NCT | 18 | 21 Sep 2100 - 1500 | 5150 | 902548 | WEATHERFORD CABLE HEAD LOST SIGNAL TO LOGGING TOOLS | TF | CTAC |  | 09/22/2022 | SNT-025 | 10 | SFNY-517
2082 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SP-165 | Hrs | FDHL-146
2083 | FPMP | RIG | 3 | 21 Sep 0430 - 1330 | 9020 | 902549 | RIG REPAIR ON MUD PUMPS ALTERNATELY, MEANWHILE CIRCULATE WITH ONE PUMP AND RECIPROCATE PIPE. | RR | MPMP |  | 09/22/2022 | SP-165 | 2.5 | FDHL-146
2084 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SSA-102 | Hrs | QTIF-752
2085 | OTH | RIG | 12 | 22 Sep 1700 - 0500 | 0 | 902604 | INCIDENT INVESTIGATION | UPRA | NA |  | 09/22/2022 | SSA-102 | 12 | QTIF-752
2086 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SSA-201 | Hrs | MNHZ-1
2087 | WHOL | RIG | 26.25 | 21 Sep 0245 - 0500 | 15561 | 902551 | DRILLING AT 15.561', PUMP PRESSURE DROPPED BY 1000 PSI. TROUBLE SHOT BY CHANGING MUD PUMPS AND VERIFYING ALL SURFACE EQUIPMENT ARE OK. - CONFIRMED THERE IS A DOWN HOLE WASHOUT. | DSF | DP |  | 09/22/2022 | SSA-201 | 24 | MNHZ-1
2088 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SSA-29 | Hrs | QTIF-423
2089 | DSFT | TIL | 18 | 22 Sep 1100 - 0500 | 12430 | 902603 | TIW FAILED TO PROVIDE ADEQUATE DESIGN AND 4.5" OBL SIMULATION RUN | JF | HGRL |  | 09/22/2022 | SSA-29 | 18 | QTIF-423
2090 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SSA-302 | Hrs | HRDH-2353
2091 | FWTS | RIG | 25 | 21 Sep 0830 - 1000 | 3767 | 902517 | LOSS 900 PSI PUMP PRESSURE, AND NO TQ., POOH FOUND BACKOFF BETWEEN SHOCK SUB AND NEAR BIT REAMER | FISH | BHA |  | 09/22/2022 | SSA-302 | 5 | HRDH-2353
2092 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SSA-5868 | Hrs | HRDH-2364
2093 | IBSL | VAR | 22 | 16 Sep 0600 - 1530 | 8915 | 902240 | POOR ROP | TF | BIT |  | 09/22/2022 | SSA-5868 | 10.5 | HRDH-2364
2094 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SSA-5892 | Hrs | AWTD-141400
2095 | FOT | BHI | 20.5 | 22 Sep 0830 - 0500 | 14800 | 902600 | WHILE DRILLING WITH RSS NOTICED MWD FAILURE | BHA | MWD |  | 09/22/2022 | SSA-5892 | 20.5 | AWTD-141400
2096 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | SSA-5969 | Hrs | UTMN-3148
2097 | WC20 | ARM | 63.5 | 19 Sep 0430 - 0500 | 10092 | 902485 | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF. | WCNT | NA |  | 09/22/2022 | SSA-5969 | 24 | UTMN-3148
2098 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/22/2022 | WCL-83 | Hrs | MRJN-1002
2099 | FOT | RIG | 8 | 22 Sep 2100 - 0500 | 0 | 902639 | ROV LOST COMMUNICATION SIGNAL AND TROUBLESHOOTING. | RR | RSSS |  | 09/22/2022 | WCL-83 | 8 | MRJN-1002
2100 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | ADC-12 | Hrs | ABQQ-110
2101 | FOT | RIG | 1 | 23 Sep 1715 - 1815 | 10601 | 902619 | TROUBLE SHOOTING GENERATORS MALFUNCTION | RR | ACDC |  | 09/23/2022 | ADC-12 | 1 | ABQQ-110
2102 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | ADC-48 | Hrs | HRDH-2316
2103 | FOT | WCR | .5 | 23 Sep 0330 - 0400 | 18441 | 902656 | WFD 4-1/2" SLIP TYPE ELEVATOR NOT WORKING | TF | CTRQ |  | 09/23/2022 | ADC-48 | .5 | HRDH-2316
2104 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | ADC-55L | Hrs | UTMN-3171
2105 | LCRW | TK3 | 51 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/23/2022 | ADC-55L | 24 | UTMN-3171
2106 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | ADC-56L | Hrs | UTMN-3069
2107 | FOT | TK3 | 171.75 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/23/2022 | ADC-56L | 24 | UTMN-3069
2108 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | ADES-144 | Hrs | UTMN-3018
2109 | FOT | RIG | 12.25 | 23 Sep 0930 - 2215 | 4330 | 902618 | RIH 5-7/8" SPS RSS/MWD BHA TO 4330'. ATTEMPTED TO FILL STRING AND TEST TOOL. PRESSURE WENT UP TP 4000 PSI RIGHT AFTER FILLING STRING. TRHOUBLE SHOOTING ON SURFACE WITHOUT SUCCESS. DECIDED TO POH AND CHECK BHA. | DSF | DP |  | 09/23/2022 | ADES-144 | 12.25 | UTMN-3018
2110 | FOT | BHI | 21 | 22 Sep 0930 - 0700 | 10980 | 902596 | BAKER RSS DIDN'T BUILD ENOUGH INCLINATION. DECISION MADE TO POOH AND CHANGE TOOLS. | BHA | RSS | 902524 | 09/23/2022 | ADES-889 | 2 | HRDH-2122
2111 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | ADES-889 | Hrs | HRDH-2122
2112 | PCPF | ARM | 184 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/23/2022 | ADES-889 | 21.5 | HRDH-2122
2113 | FOT | BHI | 21 | 22 Sep 0930 - 0700 | 10980 | 902596 | BAKER RSS DIDN'T BUILD ENOUGH INCLINATION. DECISION MADE TO POOH AND CHANGE TOOLS. | BHA | RSS | 902524 | 09/23/2022 | ADES-889 | 2 | HRDH-2122
2114 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | ADM-337 | Hrs | MRJN-900
2115 | WTHR | ARM | 13 | 23 Sep 0500 - 1800 | 13019 | 902627 | UNFAVOURABLE WEATHER FOR FLOWBACK, WIND SPEAD BELOW 5 KNOTS | WON | NA |  | 09/23/2022 | ADM-337 | 13 | MRJN-900
2116 | OTH | RIG | 4 | 23 Sep 1245 - 1645 | 6980 | 902645 | CIRCULATED AND MOVED THE STRING WHILE REPLACING MUD PUMPS FLUID END VALVE AND SEAT. | UPRA | NA |  | 09/23/2022 | ENS-108 | 4 | ZULF-2015
2117 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | ENS-108 | Hrs | ZULF-2015
2118 | OTH | RIG | 197 | 15 Sep 1300 - 2300 | 7381 | 902202 | PLUGBACK AND SIDETRACK MB DUE TO WELLBORE INSTABILITY AS A RESULT OF EXTENSIVE PERIOD OF RIG REPAIR. | UPRA | NA |  | 09/23/2022 | ENS-108 | 14 | ZULF-2015
2119 | OTH | RIG | 4 | 23 Sep 1245 - 1645 | 6980 | 902645 | CIRCULATED AND MOVED THE STRING WHILE REPLACING MUD PUMPS FLUID END VALVE AND SEAT. | UPRA | NA |  | 09/23/2022 | ENS-108 | 4 | ZULF-2015
2120 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | HI-4 | Hrs | BRRI-1001
2121 | HERR | RIG | 50.5 | 21 Sep 0230 - 0500 | 5600 | 902535 | DURING PREPARING FOR APPLYING PRESSURE OVER RBP TO STABILIZE PRESS ABOVE RBP, ASSISTANT DRILLAR CLOSED X-TREE CROWN VALVE INSTEAD OF WING VALVE AND EXPRO SLICKLINE CUT AND DROPPED IN THE STRING. | FISH | STRG |  | 09/23/2022 | HI-4 | 24 | BRRI-1001
2122 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | JACK-202 | Hrs | THRY-829
2123 | IBHA | RIG | 78.75 | 20 Sep 2215 - 0500 | 5185 | 902480 | CANNOT RUN 7" SCREENS TAG AT 5185' AT LANDING COLLAR. DUE TO UNDER GAUGE OF 8 1/2" NBRM & 8 1/2" STRM. | BHA | RM |  | 09/23/2022 | JACK-202 | 24 | THRY-829
2124 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | NBR-115S | Hrs | SDGM-1221
2125 | FOT | WCR | 2 | 23 Sep 1400 - 1600 | 12845 | 902658 | CONTROL PANEL OIL LEAK. | TF | CTRQ |  | 09/23/2022 | NBR-115S | 2 | SDGM-1221
2126 | FOT | RIG | 7.75 | 23 Sep 2115 - 0500 | 7130 | 902633 | UNABLE TO STOP ROTARY TABLE | RR | RSYS |  | 09/23/2022 | NBR-20S | 7.75 | HMYM-433512
2127 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | NBR-20S | Hrs | HMYM-433512
2128 | FOT | BCR | 1.5 | 23 Sep 1945 - 2115 | 7130 | 902632 | CRT NOT ENGAGE | TF | CTRQ |  | 09/23/2022 | NBR-20S | 1.5 | HMYM-433512
2129 | FOT | RIG | 7.75 | 23 Sep 2115 - 0500 | 7130 | 902633 | UNABLE TO STOP ROTARY TABLE | RR | RSYS |  | 09/23/2022 | NBR-20S | 7.75 | HMYM-433512
2130 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | NBR-304S | Hrs | UTMN-3180
2131 | HERR | RIG | 9.5 | 23 Sep 1330 - 2300 | 2130 | 902634 | EXCESS TIME TO NU BOPE | BOP | BOP |  | 09/23/2022 | NBR-304S | 9.5 | UTMN-3180
2132 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | NBR-575S | Hrs | HRDH-1990
2133 | XTTE | EX1 | 8.5 | 23 Sep 0700 - 1530 | 11287 | 902620 | EXPRO PR PLUG NOT HOLDING PRESSURE. | JF | SLICK |  | 09/23/2022 | NBR-575S | 8.5 | HRDH-1990
2134 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | NBR-591S | Hrs | HRDH-2313
2135 | FOT | RIG | 8.5 | 23 Sep 2030 - 0500 | 2051 | 902657 | RIG REPAIR - DRAWWORKS LUBRICATOR PUMP FAILURE. | RR | DWKS |  | 09/23/2022 | NBR-591S | 8.5 | HRDH-2313
2136 | FPMP | RIG | 2.75 | 23 Sep 0215 - 0500 | 7150 | 902630 | WHILE PUMPING LCM RIG PUMP#3 & PUMP#2 MULFUNCTION. | RR | MPMP |  | 09/23/2022 | PA-218S | 2.75 | HRDH-1976
2137 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | PA-218S | Hrs | HRDH-1976
2138 | UXDF | ARN | 171.75 | 16 Sep 2000 - 0215 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/23/2022 | PA-218S | 20.25 | HRDH-1976
2139 | FOT | RIG | 1 | 23 Sep 2115 - 2215 | 4300 | 902624 | EXCESS TIME TO MIX MUD DUE TO HOPPER PLUGGING MANY TIMES. > RIG CAN'T ADJUST TRIP TANK RATE TO PUMP 2 BPM WHICH LEAD TO LOSE MUD & USE KILL LINE FROM TIME TO TIME. | RR | CSYS |  | 09/23/2022 | PA-218S | 1 | HRDH-1976
2140 | FPMP | RIG | 2.75 | 23 Sep 0215 - 0500 | 7150 | 902630 | WHILE PUMPING LCM RIG PUMP#3 & PUMP#2 MULFUNCTION. | RR | MPMP |  | 09/23/2022 | PA-218S | 2.75 | HRDH-1976
2141 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | PA-861S | Hrs | HRDH-1973
2142 | FOT | BFL | 6 | 23 Sep 1500 - 2100 | 12180 | 902622 | WHILE CIRC. CSG PICKLING, HALLIBURTON FILTRATION UNIT WASN'T CAPABLE TO FILTER THE RETURNED BRINE ON FLY AND PLUGGED MANY TIMES, TRIED TO FIX SAME AND FILTER BRINE, BUT EVERY TIME PLUGGED AFTER +/- 60 BBL. | TF | FILT |  | 09/23/2022 | PA-861S | 6 | HRDH-1973
2143 | FOT | SDM | 13.5 | 23 Sep 1200 - 0130 | 16426 | 902646 | LOST COMMUNICATION W/ ORIENTER. POH TO CHANGE BHA | BHA | MWD |  | 09/23/2022 | SCTD-2 | 13.5 | JFYN-11
2144 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SCTD-2 | Hrs | JFYN-11
2145 | LHFL | RIG | 3.5 | 23 Sep 0130 - 0500 | 0 | 902628 | PRESSURE IS NOT HOLDING AT LUBRICATOR. STUFFING BOX IS LEAKING. | RR | HSYS |  | 09/23/2022 | SCTD-2 | 3.5 | JFYN-11
2146 | FOT | SDM | 13.5 | 23 Sep 1200 - 0130 | 16426 | 902646 | LOST COMMUNICATION W/ ORIENTER. POH TO CHANGE BHA | BHA | MWD |  | 09/23/2022 | SCTD-2 | 13.5 | JFYN-11
2147 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SINO-29N | Hrs | SFNY-2005
2148 | PSSW | ARN | 8.25 | 23 Sep 2045 - 0500 | 7202 | 902625 | 4 - 1/2" LINER DIFF STUCK DUE TO HI OVERBALANCE (1000 PSI) | STUK | NA |  | 09/23/2022 | SINO-29N | 8.25 | SFNY-2005
2149 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SND-1501 | Hrs | HWYH-89
2150 | SCSG | ARM | 3 | 23 Sep 1700 - 2000 | 7817 | 902631 | WORK ON STUCK 4-1/2" OBL . | STUK | LINR |  | 09/23/2022 | SND-1501 | 3 | HWYH-89
2151 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SND-2004 | Hrs | BRRI-1148
2152 | FOT | HCO | 16.5 | 22 Sep 0500 - 0500 | 8196 | 902598 | UNABLE TO RETRIEVE HALLIBURTON MONOLOCK PLUG USING NESR SLICKLINE. DECISION MADE TO USE OILSERV COIL TUBING RETRIEVAL TOOL. THE RIG UP OF CT PLANNED FOR FLOWBACK OPERATION. | TF | PLUGN |  | 09/23/2022 | SND-2004 | 13 | BRRI-1148
2153 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SND-2006 | Hrs | UTMN-3095
2154 | IBSL | SEC | 21.25 | 22 Sep 0430 - 0315 | 10012 | 902623 | VERY LOW PENETRATION RATE, PULL OUT TO CHECK THE BIT FOUND BIT NOSE CORED OUT | LROP | BIT |  | 09/23/2022 | SND-2006 | 20.75 | UTMN-3095
2155 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SND-2007 | Hrs | AWTD-104001
2156 | FOT | RIG | 13 | 22 Sep 2030 - 0500 | 8539 | 902637 | WATER FLOW FOR COOLING SYSTEM ON DRAW WORKS IS MALFUNCTION. | RR | DWKS |  | 09/23/2022 | SND-2007 | 9.5 | AWTD-104001
2157 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SND-2009 | Hrs | SAHB-101
2158 | STBH | ARM | 109.5 | 19 Sep 0900 - 0200 | 10580 | 902387 | AFTER DRILLOUT F/S @ 10,575 FT, PU STRING FREE, ADJUST PARAMETERS, RIH BACK, CLEANOUT RAT HOLE, WHEN BIT REACH BTM @ 10,580 FT (NBRR @ 9 5/8" FLOAT SHOE AT 10,575 FT). STRING STALLED AND GET STUCK. UNABLE TO CIRC. | STUK | BHA |  | 09/23/2022 | SND-2009 | 20.5 | SAHB-101
2159 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SP-121 | Hrs | BRRI-522
2160 | HERR | RIG | 1 | 23 Sep 2200 - 2300 | 15660 | 902647 | WHILE PU 7" FROM AL-GHAITH PU MACHINE, THE JOINT GET IN CONTACT WITH PU MACHINE'S SAFETY GUIDE STAND PULLAR'. DRESS THE SLIGHT BEND AND HELD STAND DOWN SAFETY MEETING. | JF | CTRQ |  | 09/23/2022 | SP-121 | 1 | BRRI-522
2161 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SSA-102 | Hrs | QTIF-752
2162 | OTH | RIG | 25 | 22 Sep 1700 - 1800 | 0 | 902604 | INCIDENT INVESTIGATION | UPRA | NA |  | 09/23/2022 | SSA-102 | 13 | QTIF-752
2163 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SSA-201 | Hrs | MNHZ-1
2164 | WHOL | RIG | 50.25 | 21 Sep 0245 - 0500 | 15561 | 902551 | DRILLING AT 15.561', PUMP PRESSURE DROPPED BY 1000 PSI. TROUBLE SHOT BY CHANGING MUD PUMPS AND VERIFYING ALL SURFACE EQUIPMENT ARE OK. - CONFIRMED THERE IS A DOWN HOLE WASHOUT. | DSF | DP |  | 09/23/2022 | SSA-201 | 24 | MNHZ-1
2165 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SSA-29 | Hrs | QTIF-423
2166 | DSFT | TIL | 35 | 22 Sep 1100 - 0500 | 12430 | 902603 | TIW FAILED TO PROVIDE ADEQUATE DESIGN AND 4.5" OBL SIMULATION RUN | JF | HGRL |  | 09/23/2022 | SSA-29 | 17 | QTIF-423
2167 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SSA-51 | Hrs | MNIF-255
2168 | FOT | ARM | 1.5 | 23 Sep 0515 - 0645 | 0 | 902621 | WHEN RELEASING THE SETTING TOOL TWCV RUNNING TOOL WAS DISCONNECTED FROM BAR SWIVEL | TF | SB |  | 09/23/2022 | SSA-51 | 1.5 | MNIF-255
2169 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | SSA-5892 | Hrs | AWTD-141400
2170 | FOT | BHI | 40.5 | 22 Sep 0830 - 0100 | 14800 | 902600 | WHILE DRILLING WITH RSS NOTICED MWD FAILURE | BHA | MWD |  | 09/23/2022 | SSA-5892 | 20 | AWTD-141400
2171 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/23/2022 | V140A | Hrs | ZULF-653
2172 | FOT | SDM | 4.5 | 23 Sep 0030 - 0500 | 3337 | 902626 | LOST MWD SIGNAL WHILE DRILLING. | BHA | MWD |  | 09/23/2022 | V140A | 4.5 | ZULF-653
2173 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | ADC-31 | Hrs | ANDR-1006
2174 | FRFM | ARM | 35 | 23 Sep 1800 - 0500 | 2725 | 902676 | HAD TOTAL LOSSES IN RATE HOLE AT 2702' (21 FT BELOW THE SHOE). | LCIR | NA |  | 09/24/2022 | ADC-31 | 24 | ANDR-1006
2175 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | ADC-50 | Hrs | SFNY-1176
2176 | FOT | RIG | 12 | 24 Sep 0615 - 1815 | 9135 | 902716 | WHILE MAKING CONNECTION OBSERVED DAMGE ON KELLY HOSE | RR | TDS |  | 09/24/2022 | ADC-50 | 12 | SFNY-1176
2177 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | ADC-55L | Hrs | UTMN-3171
2178 | LCRW | TK3 | 75 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/24/2022 | ADC-55L | 24 | UTMN-3171
2179 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | ADC-56L | Hrs | UTMN-3069
2180 | FOT | TK3 | 195.75 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/24/2022 | ADC-56L | 24 | UTMN-3069
2181 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | ADC-58L | Hrs | ABHD-183
2182 | FOT | RIG | 4 | 24 Sep 0700 - 1130 | 1208 | 902704 | AT CONNECTION, OBSERVED TDS IBOP MALFUNCTIONED DUE TO IBOP ACTUATOR CRANK BEARING ROLLER FAILURE. | RR | CSYS |  | 09/24/2022 | ADC-58L | 4 | ABHD-183
2183 | 10794 | 10171 | OTH | E | 4627 | NA | RIH TLC LOGGING TOOLS FROM 5,600 FT TO 10,171 FT WITH CONTROLLED SPEED.- RIH SPEED: 3 MIN/STD.- FILL UP STRING EVERY 10 STANDS.- DRIFT ALL STANDS WHILE RIH WITH 2.5" DRIFT.- MONITOR WELL THROUGH TRIP TANK. | 10794 | 5600 | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2184 | 10794 |  | PJSM | E | 4627 | NA | CIRCULATE 1.5 STRING VOLUME- MEANWHILE R/U WL SHEAVES & SECURE SAME.- HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW. | 10794 |  | RIG | 09/24/2022 | ADC-68L | LOG | FDHL-174
2185 | 10794 |  | OTH | E | 4627 | NA | LATCH WIRELINE CABLE PWCH INTO DWCH @ 10,105 FT AS PER WIRELINE ENGINEER INSTRUCTION..- RIH SLB WL CABLE- PUMP DOWN @ 200 GPM, 575 PSI TO ASSIST LATCHING.- FUNCTION TEST SLB TOOLS, OK.- PERFORM PULL TEST TO 3,200 LBS.- MONITOR WELL THROUGH TRIP TANK, WELL STATIC. | 10794 |  | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2186 | 10794 |  | OTH | E | 4627 | NA | RIH TLC LOGGING TOOLS FROM 10,171 FT TO 10,760 FT WITH CONTROLLED SPEED.- RIH SPEED: 5 MIN/STD.- CORRELATION WITH CMR TOOL AT DEPTH 10,488 FT.- DRIFT ALL STANDS WHILE RIH WITH 2.5" DRIFT.- MONITOR WELL THROUGH TRIP TANK | 10794 |  | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2187 | 10794 | 10400 | LOG | E | 4627 | WLT | UP LOG MAIN PASS FROM 10,760 FT TO 10,400 FT.- CONTROLLED SPEED AS PER WL REQUESTED 250 FT/HR- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET. | 10794 | 10760 | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2188 | 10794 |  | OTH | E | 4627 | NA | RIH TLC LOGGING TOOLS FROM 10,400 FT TO 10,600 FT WITH CONTROLLED SPEED.- RIH SPEED: 5 MIN/STD.- MONITOR WELL THROUGH TRIP TANK. | 10794 |  | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2189 | 10794 | 10400 | LOG | E | 4627 | WLT | UP LOG REPEAT PASS FROM 10,600 FT TO 10,400 FT.- CONTROLLED SPEED AS PER WL REQUESTED 250 FT/HR- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET. | 10794 | 10600 | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2190 | 10794 |  | OTH | E | 4627 | NA | RIH TLC LOGGING TOOLS FROM 10,400 FT TO 10,550 FT WITH CONTROLLED SPEED.- RIH SPEED: 5 MIN/STD.- MONITOR WELL THROUGH TRIP TANK | 10794 |  | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2191 | 10794 | 10400 | LOG | E | 4627 | WLT | UP LOG 2ND REPEAT PASS FROM 10,550 FT TO 10,400 FT.- CONTROLLED SPEED AS PER WL REQUESTED 250 FT/HR- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET | 10794 | 10550 | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2192 | 10794 |  | CIRC | E | 4627 | MPMP | FLOW CHECK, WELL STATIC. | 10794 |  | RIG | 09/24/2022 | ADC-68L | LOG | FDHL-174
2193 | 10794 |  | PJSM | E | 4627 | NA | PJSM PRIOR TO L/D CSES AND R/D WL SHEAVES,- DISCUSS THE RISK AND HAZARD & - REVIEW THE JSA.- MONITOR THE WELL WITH TRIP TANK. | 10794 |  | RIG | 09/24/2022 | ADC-68L | LOG | FDHL-174
2194 | 10794 |  | OTH | E | 4627 | NA | UNLATCH THE CABLE FROM DWCH AND RETRIEVE WIRELINE CABLE PWCH. L/D SAME.- SES ABOVE RT, B/O & L/D CSES AND - R/D WL SHEAVES- MONITOR WELL ON TRIP TANK. | 10794 |  | SWL | 09/24/2022 | ADC-68L | LOG | FDHL-174
2195 | 10794 |  | OTH | E | 4627 | NA | POOH TLC LOGGING TOOLS FROM 10,171 FT TO 9300 FT WITH CONTROLLED SPEED- POOH SPEED: 2 MIN/STD.- MONITOR WELL ON TRIP TANK & PREPARED TRIP SHEET. | 10794 |  | RIG | 09/24/2022 | ADC-68L | LOG | FDHL-174
2196 | 235.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 24 | 4627 | 08 Sep 0300 | 09/24/2022 | ADC-68L | Type | FDHL-174
2197
2198
2199 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | ADES-889 | Hrs | HRDH-2122
2200 | PCPF | ARM | 207.5 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/24/2022 | ADES-889 | 23.5 | HRDH-2122
2201 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | ADM-262 | Hrs | MRJN-57
2202 | WOPF | AP2 | 24 | 24 Sep 0500 - 0500 | 0 | 902680 | WAIT FOR VAHANA ARYAN BARGE TO COMPLETE INSTALLING SECURING ME PLUGS ON MRJN-52/57 FOR SAFE RIG APPROACH. | WO | NA |  | 09/24/2022 | ADM-262 | 24 | MRJN-57
2203 | WTHR | ARM | 2 | 24 Sep 1530 - 1730 | 13019 | 902702 | UNFAVOURABLE WEATHER FOR FLOWBACK, WIND SPEAD BELOW 5 KNOTS | WON | NA |  | 09/24/2022 | ADM-337 | 2 | MRJN-900
2204 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | ADM-337 | Hrs | MRJN-900
2205 | WTHR | ARM | 2.75 | 24 Sep 0815 - 1100 | 13019 | 902701 | UNFAVOURABLE WEATHER FOR FLOWBACK, WIND SPEAD BELOW 5 KNOTS | WON | NA |  | 09/24/2022 | ADM-337 | 2.75 | MRJN-900
2206 | WTHR | ARM | 2 | 24 Sep 1530 - 1730 | 13019 | 902702 | UNFAVOURABLE WEATHER FOR FLOWBACK, WIND SPEAD BELOW 5 KNOTS | WON | NA |  | 09/24/2022 | ADM-337 | 2 | MRJN-900
2207 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | HI-4 | Hrs | BRRI-1001
2208 | HERR | RIG | 74.5 | 21 Sep 0230 - 0500 | 5600 | 902535 | DURING PREPARING FOR APPLYING PRESSURE OVER RBP TO STABILIZE PRESS ABOVE RBP, ASSISTANT DRILLAR CLOSED X-TREE CROWN VALVE INSTEAD OF WING VALVE AND EXPRO SLICKLINE CUT AND DROPPED IN THE STRING. | FISH | STRG |  | 09/24/2022 | HI-4 | 24 | BRRI-1001
2209 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | JACK-202 | Hrs | THRY-829
2210 | FOT | ARM | 102.75 | 20 Sep 2215 - 0500 | 5185 | 902480 | CANNOT RUN 7" SCREENS TAG AT 5185' AT LANDING COLLAR. | TF | CSG |  | 09/24/2022 | JACK-202 | 24 | THRY-829
2211 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | NBR-20S | Hrs | HMYM-433512
2212 | FOT | RIG | 6 | 24 Sep 0500 - 1100 | 7130 | 902703 | RIG WATCH NOT FUNCTIONING | RR | EDR |  | 09/24/2022 | NBR-20S | 6 | HMYM-433512
2213 | FOT | RIG | 6 | 24 Sep 2100 - 0300 | 2051 | 902705 | TOP DRIVE ACTUATOR VALVE BODY BEGAN TO LEAK. | RR | TDS |  | 09/24/2022 | NBR-591S | 6 | HRDH-2313
2214 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | NBR-591S | Hrs | HRDH-2313
2215 | FOT | RIG | 13.5 | 23 Sep 2030 - 1000 | 2051 | 902657 | RIG REPAIR - DRAWWORKS LUBRICATOR PUMP FAILURE. | RR | DWKS |  | 09/24/2022 | NBR-591S | 5 | HRDH-2313
2216 | FOT | RIG | 6 | 24 Sep 2100 - 0300 | 2051 | 902705 | TOP DRIVE ACTUATOR VALVE BODY BEGAN TO LEAK. | RR | TDS |  | 09/24/2022 | NBR-591S | 6 | HRDH-2313
2217 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | PA-218S | Hrs | HRDH-1976
2218 | UXDF | ARN | 195.75 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/24/2022 | PA-218S | 24 | HRDH-1976
2219 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | PA-604S | Hrs | HRDH-2414
2220 | FOT | WDV | 5.25 | 24 Sep 1945 - 0100 | 11216 | 902677 | UNABLE TO INFLATE DV PACKER DESPITE REPEATED ATTEMPTS & VARIED PARAMETERS. | TF | DV |  | 09/24/2022 | PA-604S | 5.25 | HRDH-2414
2221 | FOT | SDM | 22 | 23 Sep 1200 - 2330 | 16426 | 902646 | LOST COMMUNICATION W/ ORIENTER. POH TO CHANGE BHA | BHA | MWD |  | 09/24/2022 | SCTD-2 | 8.5 | JFYN-11
2222 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | SCTD-2 | Hrs | JFYN-11
2223 | LHFL | RIG | 10.5 | 23 Sep 0130 - 1200 | 0 | 902628 | PRESSURE IS NOT HOLDING AT LUBRICATOR. STUFFING BOX IS LEAKING. | RR | HSYS |  | 09/24/2022 | SCTD-2 | 7 | JFYN-11
2224 | FOT | SDM | 22 | 23 Sep 1200 - 2330 | 16426 | 902646 | LOST COMMUNICATION W/ ORIENTER. POH TO CHANGE BHA | BHA | MWD |  | 09/24/2022 | SCTD-2 | 8.5 | JFYN-11
2225 | FOT | SPS | 2 | 24 Sep 1300 - 1400 | 0 | 902700 | EXCESSIVE TIME TO TAKE SURVEY& AND TROUBLESHOOTING DUE TO MWD DOWNHOLE VIBRATION. | BHA | GMWD |  | 09/24/2022 | SINO-1L | 1 | KHRS-75
2226 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | SINO-1L | Hrs | KHRS-75
2227 | FOT | SPS | 1 | 24 Sep 1700 - 1800 | 0 | 902678 | EXCESSIVE TIME TO TAKE SURVEY& AND TROUBLESHOOTING DUE TO MWD DOWNHOLE VIBRATION. | BHA | GMWD | 902700 | 09/24/2022 | SINO-1L | 1 | KHRS-75
2228 | FOT | SPS | 1 | 24 Sep 0930 - 1030 | 0 | 902699 | EXCESSIVE TIME TO TAKE SURVEY& AND TROUBLESHOOTING DUE TO MWD DOWNHOLE VIBRATION. | BHA | GMWD |  | 09/24/2022 | SINO-1L | 1 | KHRS-75
2229 | FOT | SPS | 2 | 24 Sep 1300 - 1400 | 0 | 902700 | EXCESSIVE TIME TO TAKE SURVEY& AND TROUBLESHOOTING DUE TO MWD DOWNHOLE VIBRATION. | BHA | GMWD |  | 09/24/2022 | SINO-1L | 1 | KHRS-75
2230 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | SINO-29N | Hrs | SFNY-2005
2231 | PSSW | ARN | 32.25 | 23 Sep 2045 - 0500 | 7202 | 902625 | 4 - 1/2" LINER DIFFERENTIALY STICKING AT CONNECTIONS IN OH | STUK | NA |  | 09/24/2022 | SINO-29N | 24 | SFNY-2005
2232 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | SND-2004 | Hrs | BRRI-1148
2233 | FOT | HSL | 40.5 | 22 Sep 0500 - 0500 | 8196 | 902598 | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG USING NESR SLICKLINE, OILSERV COIL TUBING, THEN HALL SLICK LINE, RUN IMPRESSION BLOCK TO EVALUATE TOP OF MONOLOCK. | TF | PLUGN |  | 09/24/2022 | SND-2004 | 24 | BRRI-1148
2234 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | SND-2009 | Hrs | SAHB-101
2235 | STBH | ARM | 136 | 19 Sep 0900 - 0500 | 10580 | 902387 | AFTER DRILLOUT F/S @ 10,575 FT, PU STRING FREE, ADJUST PARAMETERS, RIH BACK, CLEANOUT RAT HOLE, WHEN BIT REACH BTM @ 10,580 FT (NBRR @ 9 5/8" FLOAT SHOE AT 10,575 FT). STRING STALLED AND GET STUCK. UNABLE TO CIRC. | STUK | BHA |  | 09/24/2022 | SND-2009 | 23.5 | SAHB-101
2236 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | SND-2010 | Hrs | MNIF-868
2237 | EXPL | BAW | 7.5 | 24 Sep 1800 - 0130 | 0 | 902697 | W.O. BAKER TCP EXPLOSIVES TO ARRIVE | WO | NA |  | 09/24/2022 | SND-2010 | 7.5 | MNIF-868
2238 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | SSA-29 | Hrs | QTIF-423
2239 | DSFT | TIL | 59 | 22 Sep 1100 - 0500 | 12430 | 902603 | TIW FAILED TO PROVIDE ADEQUATE DESIGN AND 4.5" OBL SIMULATION RUN | JF | HGRL |  | 09/24/2022 | SSA-29 | 24 | QTIF-423
2240 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | SSA-51 | Hrs | MNIF-255
2241 | FOT | GOC | 2 | 24 Sep 0500 - 0700 | 4517 | 902698 | AL-GHAITH POWER TONG GOT STUCK ON THE PIPE & COULD NOT BE RELEASED, DISMANTEL JAWS , LAY DOWN POWER TONG & CHANGE WITH NEW ONE. | TF | TTRQ |  | 09/24/2022 | SSA-51 | 2 | MNIF-255
2242 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/24/2022 | V140A | Hrs | ZULF-653
2243 | FOT | SDM | 17.5 | 23 Sep 0030 - 1830 | 3337 | 902626 | LOST MWD SIGNAL WHILE DRILLING. | BHA | MWD |  | 09/24/2022 | V140A | 13 | ZULF-653
2244 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | ADC-31 | Hrs | ANDR-1006
2245 | FRFM | ARM | 36 | 23 Sep 1800 - 0600 | 2725 | 902676 | HAD TOTAL LOSSES IN RATE HOLE AT 2702' (21 FT BELOW THE SHOE). | LCIR | NA |  | 09/25/2022 | ADC-31 | 1 | ANDR-1006
2246 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | ADC-55L | Hrs | UTMN-3171
2247 | LCRW | TK3 | 99 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/25/2022 | ADC-55L | 24 | UTMN-3171
2248 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | ADC-56L | Hrs | UTMN-3069
2249 | FOT | TK3 | 219.75 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/25/2022 | ADC-56L | 24 | UTMN-3069
2250 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | ADC-59L | Hrs | HWYH-1324
2251 | CEDE | TK3 | 64 | 22 Sep 0030 - 0500 | 19319 | 902684 | CONT. WIPER TRIP. RIH W/ WBCU ASSAY FROM 16412 FT TO 19,319 FT ON ELEVATOR. | DRG | NA |  | 09/25/2022 | ADC-59L | 12.5 | HWYH-1324
2252 | 10794 |  | OTH | E | 4627 | NA | POOH TLC LOGGING TOOLS FROM 9,300 FT TO 66 FT WITH CONTROLLED SPEED- POOH SPEED: 2 MIN/STD.- AT 5,080 FT CHANGED HANDLING GEARS TO 4"DP- MONITOR WELL ON TRIP TANK & FILL TRIP SHEET. | 10794 |  | SWL | 09/25/2022 | ADC-68L | LOG | FDHL-174
2253 | 10794 |  | OTH | E | 4627 | NA | L/D SLB WL TLC CMR-GR RUN #2 TOOL STRING.- MONITOR THE WELL WITH TRIP TANK. | 10794 |  | SWL | 09/25/2022 | ADC-68L | LOG | FDHL-174
2254 | 10794 |  | PJSM | N | 4627 | STRG | HELD PJSM PRIOR TO M/U 6-1/8" CONDITION TRIP BHA | 10794 |  | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2255 | 10794 |  | HT | E | 4627 | BHA | P/U AND M/U 6-1/8" CONDITION TRIP BHA AND RIH TO 936 FT.- 6-1/8" PDC BIT, TYPE TA606, S/N: 7913402 W/ 3X13 NOZZLES- BIT SUB WITH FV- 10 STD X 4"HWDP | 10794 |  | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2256 | 10794 | 5667 | TI | E | 4627 | STDP | RIH W/ 6-1/8" CONDITION TRIP BHA ON 4"DP FROM 936 FT TO 5,667 FT.- MONITOR WELL ON TRIP TANK & FILL TRIP SHEET. | 10794 | 963 | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2257 | 10794 |  | HT | E | 4627 | BHA | CHANGE HANDLING EQUIPMENT FROM 4" TO 5" SIZE. | 10794 |  | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2258 | 10794 | 10370 | TI | E | 4627 | STDP | RIH W/ 6-1/8" CONDITION TRIP BHA ON 5"DP FROM 5,667 FT TO LINER SHOE @10,370 FT.- MONITOR WELL ON TRIP TANK & FILL TRIP SHEET. | 10794 | 5667 | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2259 | 10794 |  | RR | E |  | DWKS | HPJSM, SLIP AND CUT DRILLING LINE. | 10794 |  | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2260 | 10794 |  | HT | E | 4627 | STRG | RIH W/ 6-1/8" CONDITION TRIP BHA ON 5"DP FROM 10,370 FT TO BTM @10,794 FT.- WASH DOWN LAST 2 STD.- HOLE GOOD- MONITOR WELL ON TRIP TANK & FILL TRIP SHEET. | 10794 |  | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2261 | 10794 |  | CIRC | E | 4627 | MPMP | SWEEP HOLE WITH 30 BBLS HI-VIS AND CIRCULATE.- NO DYNAMIC LOSSES.** MEANWHILE CONDUCT MEETING TO REVIEW ARANGEMENT OF MUD TANKS. VERIFY LINE UP CORRECTLY. | 10794 |  | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2262 | 10794 |  | CIRC | E | 4627 | MPMP | DISPLACE WELLBORE FLUID TO 77 PCF OBM- NO DYNAMIC LOSSES | 10794 |  | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2263 | 10794 |  | CIRC | E |  | MPMP | CIRC TO CONDITION OBM, ONGOING.- NO LOSSES. | 10794 |  | RIG | 09/25/2022 | ADC-68L | CT | FDHL-174
2264 | 255.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 20 | 4627 | 08 Sep 0300 | 09/25/2022 | ADC-68L | Type | FDHL-174
2265
2266
2267 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | ADES-889 | Hrs | HRDH-2122
2268 | PCPF | ARM | 231 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/25/2022 | ADES-889 | 23.5 | HRDH-2122
2269 | WTHR | ARM | 16 | 25 Sep 1300 - 0500 | 0 | 902711 | WAIT ON WEATHER TO TRANSFER FOREMAN TO CHECK PF DEPRESSURIZATION & VAHANA ARYAN BARGE TO MOVE OUT FROM LOCATION. | WON | NA |  | 09/25/2022 | ADM-262 | 16 | MRJN-57
2270 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | ADM-262 | Hrs | MRJN-57
2271 | WOPF | AP2 | 32 | 24 Sep 0500 - 1300 | 0 | 902680 | WAIT FOR VAHANA ARYAN BARGE TO COMPLETE INSTALLING SECURING ME PLUGS ON MRJN-52/57 FOR SAFE RIG APPROACH. | WO | NA |  | 09/25/2022 | ADM-262 | 8 | MRJN-57
2272 | WTHR | ARM | 16 | 25 Sep 1300 - 0500 | 0 | 902711 | WAIT ON WEATHER TO TRANSFER FOREMAN TO CHECK PF DEPRESSURIZATION & VAHANA ARYAN BARGE TO MOVE OUT FROM LOCATION. | WON | NA |  | 09/25/2022 | ADM-262 | 16 | MRJN-57
2273 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | ARO-2001 | Hrs | MRJN-121
2274 | WTHR | ARM | 36 | 24 Sep 1700 - 0500 | 0 | 902713 | WAIT ON WEATHER TO RIG MOVE TO MRJN 121/126 PF | WON | NA |  | 09/25/2022 | ARO-2001 | 24 | MRJN-121
2275 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | HI-4 | Hrs | BRRI-1001
2276 | HERR | RIG | 76.5 | 21 Sep 0230 - 0700 | 5600 | 902535 | DURING PREPARING FOR APPLYING PRESSURE OVER RBP TO STABILIZE PRESS ABOVE RBP, DRILLER INSTRUCTED ASSISTANT DRILLAR TO CLOSE X-TREE WING VALVE WITHOUT INFORMING TOOLPUSHER OR ARAMCO FOREMAN. AD CLOSED CROWN VALVE INSTEAD OF WING VALVE BY MISTAKE AND EXPRO SLICKLINE WAS CUT AND DROPPED IN THE STRING. | FISH | STRG |  | 09/25/2022 | HI-4 | 2 | BRRI-1001
2277 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | JACK-202 | Hrs | THRY-829
2278 | FOT | ARM | 89.75 | 20 Sep 2215 - 1200 | 5577 | 902709 | CANNOT RUN 7" SCREENS TAG AT 5185' AT LANDING COLLAR | TF | LC |  | 09/25/2022 | JACK-202 | 7 | THRY-829
2279 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | MP-1 | Hrs | BRRI-310
2280 | WTHR | ARM | 6 | 25 Sep 2300 - 0500 | 0 | 902660 | UNABLE TO BACKLOAD CTU & WELL TESTING EQ DUE TO UNFAVORABLE WEATHER CONDITION. | WON | NA |  | 09/25/2022 | MP-1 | 6 | BRRI-310
2281 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | NBR-263S | Hrs | QTIF-736
2282 | WTHR | ARM | 6.5 | 25 Sep 0900 - 1530 | 14100 | 902661 | STOPPED CT INJECTOR LIFTING OPERATION DUE TO HIGH WIND SPEED (45-37 KM/HR) . STC, TAQA RIGGER-I: TRACKED WIND SPEED EVERY 10 MINTS BY BOTH RIG ANAMOMETER & CRAN SENSOR TILL REACH SAFE LIMIT:<32 KM/HR. | WON | NA |  | 09/25/2022 | NBR-263S | 6.5 | QTIF-736
2283 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | NBR-654S | Hrs | ANDR-1018
2284 | XTRI | RIG | 1 | 25 Sep 1700 - 1800 | 865 | 902723 | EXCESS TIME TO M/U AND RIH BHA DUE TO MISALIGNMENT BETWEEN ROTARY TABLE & BELL NIPPLE, TROUBLESHOOTING ON TONG SENSOR. | JF | NA |  | 09/25/2022 | NBR-654S | 1 | ANDR-1018
2285 | FOT | RIG | 1 | 25 Sep 1215 - 1315 | 1043 | 902685 | EXCESS TRIPPING TIME, 14 STDS/HRS, DUE TO IRON ROUGHNECK MALFUNCTION. | RR | SLIPS |  | 09/25/2022 | PA-218S | 1 | HRDH-1976
2286 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | PA-218S | Hrs | HRDH-1976
2287 | UXDF | ARN | 207.5 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/25/2022 | PA-218S | 11.75 | HRDH-1976
2288 | FOT | RIG | 1 | 25 Sep 1215 - 1315 | 1043 | 902685 | EXCESS TRIPPING TIME, 14 STDS/HRS, DUE TO IRON ROUGHNECK MALFUNCTION. | RR | SLIPS |  | 09/25/2022 | PA-218S | 1 | HRDH-1976
2289 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | PA-622S | Hrs | UTMN-3600
2290 | FOT | NCT | 3 | 25 Sep 1445 - 1745 | 14342 | 902712 | WHILE POOH COIL TUBING AND LIFTING N2 @ 12,400 FEET, OBSERVED LEAKAGE AT THE REEL SWIVEL. ATTEMPTED TO REPAIR WITHOUT SUCCESS. CONTINUED TO POOH TO A SAFE DEPTH WITHOUT PUMPING. | TF | CTBG |  | 09/25/2022 | PA-622S | 3 | UTMN-3600
2291 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | PN-9 | Hrs | MRJN-673
2292 | FOT | RIG | 1 | 25 Sep 0300 - 0400 | 15675 | 902726 | HAD FAILURE IN MUD PUMP #1 & PUMP #2. | RR | MPMP |  | 09/25/2022 | PN-9 | 1 | MRJN-673
2293 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | RM-74A | Hrs | HSBH-68
2294 | FOT | RIG | .5 | 25 Sep 0930 - 1000 | 6459 | 902686 | RIG LOSS MAIN POWER, DUE TO ONE ENGINE SHUT DOWN, ARO TROUBLESHOOT SAME AND REGAIN FULL POWER. | RR | PSYS |  | 09/25/2022 | RM-74A | .5 | HSBH-68
2295 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SA5898 | Hrs | MDRK-66
2296 | FOT | RIG | 6 | 25 Sep 1015 - 1615 | 12537 | 902710 | LEAKAGE IN BODY OF VIBRATOR HOSE. | RR | CSYS |  | 09/25/2022 | SA5898 | 6 | MDRK-66
2297 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SINO-1L | Hrs | KHRS-75
2298 | FOT | SPS | 2 | 25 Sep 1000 - 1200 | 0 | 902724 | EXCESSIVE TIME TO TAKE SURVEY & TROUBLESHOOTING DUE TO MWD DOWNHOLE VIBRATION. | BHA | GMWD | 902678 | 09/25/2022 | SINO-1L | 2 | KHRS-75
2299 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SINO-29N | Hrs | SFNY-2005
2300 | PSSW | ARN | 55.25 | 23 Sep 2045 - 0400 | 7202 | 902625 | 4 - 1/2" LINER DIFFERENTIALY STICKING AT CONNECTIONS IN OH | STUK | NA |  | 09/25/2022 | SINO-29N | 23 | SFNY-2005
2301 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SND-2004 | Hrs | BRRI-1148
2302 | FOT | HSL | 64.5 | 22 Sep 0500 - 0500 | 8196 | 902598 | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL. | TF | PLUGN |  | 09/25/2022 | SND-2004 | 24 | BRRI-1148
2303 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SND-2005 | Hrs | MHKK-2
2304 | HINW | SWL | 49 | 23 Sep 1415 - 1515 | 15025 | 902687 | AFTER TAKING SAMPLE, UNABLE TO UN SEAT PACKER. | STUK | WLT |  | 09/25/2022 | SND-2005 | 10.25 | MHKK-2
2305 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SND-2007 | Hrs | AWTD-104001
2306 | TOWC | NPC | 15 | 25 Sep 1400 - 0500 | 15230 | 902688 | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP. | TF | JARS |  | 09/25/2022 | SND-2007 | 15 | AWTD-104001
2307 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SND-2009 | Hrs | SAHB-101
2308 | STBH | ARM | 152.5 | 19 Sep 0900 - 2130 | 10580 | 902387 | AFTER DRILLOUT F/S @ 10,575 FT, PU STRING FREE, ADJUST PARAMETERS, RIH BACK, CLEANOUT RAT HOLE, WHEN BIT REACH BTM @ 10,580 FT (NBRR @ 9 5/8" FLOAT SHOE AT 10,575 FT). STRING STALLED AND GET STUCK. UNABLE TO CIRC. | STUK | BHA |  | 09/25/2022 | SND-2009 | 16.5 | SAHB-101
2309 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SND-3003 | Hrs | HRDH-1981
2310 | WOTO | SPS | 1 | 25 Sep 0900 - 1000 | 0 | 902721 | FAILED TO GET MWD TOOL READY FOR PICK UP DUE SUDDEN CHANGE IN BHA DESIGN BY SPERRY SUN | WO | NA |  | 09/25/2022 | SND-3003 | 1 | HRDH-1981
2311 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SP-110 | Hrs | MNIF-142
2312 | HERR | ITS | 122 | 03 Aug 0730 - 0500 | 4583 | 900424 | EXCESSIVE TIME TO RUN CSG. ITS EQT FAILLURE. NON COMPETENT ITS CREW. | JF | CTRQ |  | 09/25/2022 | SP-110 | 1.5 | MNIF-142
2313 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SSA-101 | Hrs | QTIF-526
2314 | CWEL | ARM | 2.25 | 25 Sep 1430 - 1645 | 1881 | 902722 | AFTER M/UP DP CONNECTION, OBSERVED HIGH TORQUE & STRING GOT STUCK AT 1,881' (30 FT OFF BOTTOM), WORK ON STRING, MEANWHILE PREPARE AND SPOT 70 BBLS OF CITRIC ACID PILL AROUND BHA, WORK ON STRING & GOT STRING FREE. | BHS | NA |  | 09/25/2022 | SSA-101 | 2.25 | QTIF-526
2315 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SSA-5917 | Hrs | HRDH-2406
2316 | FPMP | RIG | 1.5 | 25 Sep 0330 - 0500 | 6300 | 902689 | DROP PRESSURE , CHECK PUMP ,RIG REPAIR ON MUD PUMP N*1 | RR | MPMP |  | 09/25/2022 | SSA-5917 | 1.5 | HRDH-2406
2317 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/25/2022 | SSA-5964 | Hrs | UTMN-2015
2318 | FOT | WWL | 13 | 25 Sep 1600 - 0500 | 0 | 902725 | LOST TIME ON WFRD WL LOGGING DUE TO PREVIOUS LOGGING RUN DATA BAD QUALITY AS PER ARAMCO RDD. | TF | WLT |  | 09/25/2022 | SSA-5964 | 13 | UTMN-2015
2319 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ADC-55L | Hrs | UTMN-3171
2320 | LCRW | TK3 | 123 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/26/2022 | ADC-55L | 24 | UTMN-3171
2321 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ADC-56L | Hrs | UTMN-3069
2322 | FOT | TK3 | 243.75 | 16 Sep 0500 - 0500 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/26/2022 | ADC-56L | 24 | UTMN-3069
2323 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ADC-59L | Hrs | HWYH-1324
2324 | CEDE | TK3 | 78.25 | 22 Sep 0030 - 2215 | 19319 | 902684 | CONT. WIPER TRIP. RIH W/ WBCU ASSAY FROM 16412 FT TO 19,319 FT ON ELEVATOR. | DRG | NA |  | 09/26/2022 | ADC-59L | 14.25 | HWYH-1324
2325 | 10794 |  | CIRC | E |  | MPMP | CONTINUE CIRC TO CONDITION OBM, TILL MUD PARAMETER MATCHED WITH ARAMCO PROGRAM , FR= 300 GPM; SPP=1,950 PSI, RPM: 70, TQ: 3.0-3.5 KLB*FT, MW IN = MW OUT = 77 PCF- NO LOSSES, RECORD SCR AT THE END OF CIRC,FLOW CHECK. - WELL STATIC.-SENT SAMPLE FOR AGING TEST | 10794 |  | RIG | 09/26/2022 | ADC-68L | CT | FDHL-174
2326 | 10794 | 10374 | TO | E | 4627 | STDP | POOH ON ELEVATOR W/6-1/8" CONDITION TRIP BHA,FROM 10,794 FT TO LINER SHOE @ 10,374 FT.- HOLE IN GOOD CONDITION, MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET, FLOW CHECK. - WELL STATIC | 10794 | 10794 | RIG | 09/26/2022 | ADC-68L | CT | FDHL-174
2327 | 10794 | 5667 | TO | E | 4627 | STDP | POOH W/6-1/8" CONDITION TRIP BHA ON 5"DP FROM10,374 FT TO 5,667 FT.- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET | 10794 | 10374 | RIG | 09/26/2022 | ADC-68L | CT | FDHL-174
2328 | 10794 |  | HT | E | 4627 | STRG | CHANGE HANDLING EQUIPMENT FROM 5" TO 4" SIZE, B/O XT-39 P X 4-1/2" IF B X/O SUB. | 10794 |  | RIG | 09/26/2022 | ADC-68L | CT | FDHL-174
2329 | 10794 | 936 | TO | E | 4627 | STDP | POOH W/6-1/8" CONDITION TRIP BHA ON 4"DP FROM 5,667 FT TO 936 FT TOP BHA , FLOW CHECK. WELL STATIC.- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET | 10794 | 5667 | RIG | 09/26/2022 | ADC-68L | CT | FDHL-174
2330 | 10794 |  | HT | E | 4627 | BHA | POOH W/6-1/8" CONDITION TRIP BHA FROM 936 FT TO SURFACE.- R/B 10 X 4" HWDP STD, B/O BIT AND BIT SUB, BIT DULL: 1-1-WT-A-X-I-NO-BHA- MONITOR THE WELL WITH TRIP TANK AND FILL TRIP SHEET | 10794 |  | RIG | 09/26/2022 | ADC-68L | CT | FDHL-174
2331 | 10794 |  | PJSM | E | 4627 | NA | CLEAR AND CLEAN RIG FLOOR BEFORE WL JOB.HELD PRE-JOB SAFETY MEETING BEFORE RUNNING WIRELINE ON TLC.- DISCUSSED ABOUT WL TLC OPERATION, MECHANICAL LIFTING, PINCH POINTS AND LINE OF FIRE, ENSURE PROPER WARNING SIGNS AND BARRICADEAROUND RIG FLOOR AND CATWALK AREA, EXPLAIN THE WELL CONTROL IN CASE WIRE LINE PASS THROUGH BOP. | 10794 |  | RIG | 09/26/2022 | ADC-68L | LOG | FDHL-174
2332 | 10794 |  | OTH | E | 4627 | NA | P/U & M/U TLC RUN #2 SLB TLC LOGGING TOOLS (MDTGR) & RIH TO 178.82 FT.- CHECK WL TLC TOOLS ON SURFACE. OK, - MAX TOOL OD: 5.284 INCH MONITOR WELL ON TRIP TANK. | 10794 |  | SWL | 09/26/2022 | ADC-68L | LOG | FDHL-174
2333 | 10794 | 5291 | LOG | E | 4627 | WLT | RIH TLC LOGGING TOOLS TO 5,291 FT WITH CONTROLLED SPEED.- RUN 3 STD X 4"HWDP + 50 STD X 4"DP + 1 STD X 5" DP,- CHANGE HANDLING EQUIPMENT FROM 4" TO 5" SIZE, M/U XT-39 P X 4-1/2" IF B X/O SUB- RIH SPEED: 3 MIN/STD, FILL UP STRING EVERY 10 STANDS DRIFT ALL STANDS WHILE RIH WITH 2.5" DRIFT.- MONITOR WELL THROUGH TRIP TANK. | 10794 | 0 | SWL | 09/26/2022 | ADC-68L | LOG | FDHL-174
2334 | 274.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 18.75 | 4627 | 08 Sep 0300 | 09/26/2022 | ADC-68L | Type | FDHL-174
2335
2336
2337 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ADES-889 | Hrs | HRDH-2122
2338 | PCPF | ARM | 254.5 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/26/2022 | ADES-889 | 23.5 | HRDH-2122
2339 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ADM-262 | Hrs | MRJN-57
2340 | WTHR | ARM | 40 | 25 Sep 1300 - 0500 | 0 | 902711 | WAIT ON WEATHER TO TRANSFER FOREMAN TO CHECK PF DEPRESSURIZATION & VAHANA ARYAN BARGE TO MOVE OUT FROM LOCATION. | WON | NA |  | 09/26/2022 | ADM-262 | 24 | MRJN-57
2341 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ADM-511 | Hrs | MRJN-799
2342 | WTHR | ARM | 5 | 26 Sep 0000 - 0500 | 12899 | 902738 | CANNOT BACKLOAD OFFLOAD HALLIBURTON, BAKER, AND SLB EQUIPMENT FROM BOAT DUE TO HIGH WINDS AND SEAS | WON | NA |  | 09/26/2022 | ADM-511 | 5 | MRJN-799
2343 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ADM-657 | Hrs | SFNY-1263
2344 | WTHR | ARM | 18 | 26 Sep 1100 - 0500 | 0 | 902733 | UNABLE TO RIG MOVE DUE TO WEATHER | WON | NA |  | 09/26/2022 | ADM-657 | 18 | SFNY-1263
2345 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ARO-2001 | Hrs | MRJN-121
2346 | WTHR | ARM | 60 | 24 Sep 1700 - 0500 | 0 | 902713 | WAIT ON WEATHER TO RIG MOVE TO MRJN 121/126 PF | WON | NA |  | 09/26/2022 | ARO-2001 | 24 | MRJN-121
2347 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ARO-3001 | Hrs | MRJN-3001
2348 | LHFL | RIG | .75 | 26 Sep 2215 - 2300 | 625 | 902776 | DRAWWORK HYDRULIC HOSE BROKED. | RR | HSYS |  | 09/26/2022 | ARO-3001 | .75 | MRJN-3001
2349 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | DQ-47 | Hrs | KHRS-1739
2350 | FPMP | RIG | 4 | 26 Sep 2130 - 0130 | 8665 | 902739 | ATTEMPT TO P/T 7" LINER CSG, HAD PRESS. DROP 15 PSI/MIN, P/T SURF. LINES HAD SAME PRESS. DROP & DETECT THE LEAK IN STAND PIPE MNFLD BLEED OFF VLV. | RR | MPMP |  | 09/26/2022 | DQ-47 | 4 | KHRS-1739
2351 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | ED-85A | Hrs | ZULF-2066
2352 | FOT | RIG | 1.5 | 26 Sep 0930 - 1100 | 5950 | 902735 | MUD PUMP FAILURE | RR | CSYS |  | 09/26/2022 | ED-85A | 1.5 | ZULF-2066
2353 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | JACK-202 | Hrs | THRY-829
2354 | WOTO | RIG | 1 | 26 Sep 0200 - 0300 | 5550 | 902737 | WAIT TO FIX CONNEXION LEAK ON VENT LINE FOR FLOW TEST. | WO | NA |  | 09/26/2022 | JACK-202 | 1 | THRY-829
2355 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | MP-1 | Hrs | BRRI-310
2356 | WTHR | ARM | 24 | 25 Sep 2300 - 0500 | 0 | 902660 | UNABLE TO BACKLOAD CTU & WELL TESTING EQ DUE TO UNFAVORABLE WEATHER CONDITION. | WON | NA |  | 09/26/2022 | MP-1 | 18 | BRRI-310
2357 | FOT | RIG | 2 | 26 Sep 0500 - 0700 | 4309 | 902692 | MP#1 POOP OFF VALVE LEAKING & DUMP LINE BUTTER FLAY VALVE LEAKING CHANGE SAME. | RR | CSYS |  | 09/26/2022 | PA-218S | 2 | HRDH-1976
2358 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | PA-218S | Hrs | HRDH-1976
2359 | UXDF | ARN | 229.5 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/26/2022 | PA-218S | 22 | HRDH-1976
2360 | FOT | RIG | 2 | 26 Sep 0500 - 0700 | 4309 | 902692 | MP#1 POOP OFF VALVE LEAKING & DUMP LINE BUTTER FLAY VALVE LEAKING CHANGE SAME. | RR | CSYS |  | 09/26/2022 | PA-218S | 2 | HRDH-1976
2361 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | PA-604S | Hrs | HRDH-2414
2362 | FOT | RIG | 8 | 26 Sep 0500 - 1300 | 11216 | 902664 | ATTEMPT PT ANN BOP WITH 4" TEST JNT, NOT HOLDING. VISIBLE LEAKS OBSERVED, FAILED PACKING ELEMENT (IN-SERVICE APPRX 60 DAYS). REPLACE ANNULAR BOP WITH NEW AND RE-TEST OK. | RR | RWCS |  | 09/26/2022 | PA-604S | 8 | HRDH-2414
2363 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | PA-785S | Hrs | QTIF-269
2364 | FOT | ODJ | 1.5 | 26 Sep 1400 - 1530 | 0 | 902669 | ODFJELL POWER TONG JAM UNIT FAILURE | TF | TTRQ |  | 09/26/2022 | PA-785S | 1.5 | QTIF-269
2365 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | RM-74A | Hrs | HSBH-68
2366 | WTHR | OTH | 2.75 | 26 Sep 2330 - 0215 | 6459 | 902756 | UNABLE TO OPERATE CRANES DUE TO HIGH WINDSPEED (38-40KNTS). | WON | NA |  | 09/26/2022 | RM-74A | 2.75 | HSBH-68
2367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SDA | Hrs | MRJN-654
2368 | FOT | SCD | 8 | 26 Sep 2100 - 0500 | 2235 | 902731 | WHILE DRILLING, LOST GWD SIGNAL. | BHA | GMWD |  | 09/26/2022 | SDA | 8 | MRJN-654
2369 | 7001 |  | HT | N | 4828 | PEL | HPJSM, R/D 2-3/8" DP HANDLING TOOLS & R/U 4" DP HANDING EQUIPMENT. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2370 | 7001 | 6500 | TI | N | 4828 | STDP | CONT. RIH W/ 3-7/8" CO ASSY. ON 4" DP FROM 2060' TO 6500'.- WASH DOWN & PASSED SMOOTHLY 4-1/2" TOL @ 4998'.- FILL & BREAK CIRC EVERY 10 STANDS W/ 77 PCF OBM | 7001 | 2060 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2371 | 7001 | 6730 | ST | N | 4828 | SPDP | CONT. RIH & WASH DOWN W/ 3-7/8" CO ASSY. ON 4" DP FROM 6500' TILL TAG ON T.O.C @ 6730'. | 7001 | 6500 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2372 | 7001 |  | CIRC | N | 4828 | MPMP | DISPLACE WELL TO 77 PCF SOLIDS FREE VISCOUS BRINE. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2373 | 7001 | 6859 | RW | N | 4828 | BIT | CLEAN OUT SOFT/HARD CMT FROM 6730' TO 6859' (10' ABOVE LANDING COLLAR). | 7001 | 6730 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2374 | 7001 |  | CIRC | N | 4828 | MPMP | CHC W/ 77 PCF SOLIDS FREE VISCOUS BRINE & P/T 4 1/2" LINER TO 1350 PSI W/ 77 PCF SOLIDS FREE VISCOUS BRINE- HOLD FOR 10 MIN - OK. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2375 | 7001 |  | WCNT | N | 4828 | NA | FLOW CHECK- WELL STATIC. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2376 | 7001 | 2060 | TO | N | 4828 | STDP | POOH W/ 3-7/8" C/O ASSY F/ 6859 FT T/ 2060 FT WHILE RACK BACK 4" DP / HWDP STANDS TO DERRICK. | 7001 | 6859 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2377 | 7001 |  | HT | N | 4828 | PEL | R/D 4" DP HANDLING TOOLS. R/U 2 3/8" DP HANDLING TOOLS. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2378 | 7001 | 0 | TO | N | 4828 | STHDP | POOH W/ 3-7/8" C/O ASSY F/ 2060 FT T/ SURFACE WHILE RACK BACK 2 3/8" DP STANDS IN DERRICK.- L/D (8) JT'S X 2-3/8" DP | 7001 | 2060 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2379 | 7001 |  | HT | N | 4828 | BHA | HPJSM, M/U 4" SCRAPER ASSY. AS FOLLOWING:- BHA : 3-7/8" PDC BIT, BIT SUB W/ FV,1 JT 2-3/8'' DP, XO, 4'' SCRAPER, XO, 1 JT 2-3/8'' DP, XO, 3-1/2'' STRG MAGNET, XO. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2380 | 7001 | 1829 | LDP | N | 4828 | STRG | RIH W/ 4" SCRAPER ASSY. ON 2 3/8" DP T/ 1829 FT- FILL STRING AND BREAK CIRCULATION EVERY 10 STANDS W/ 77 PCF VISCOUS BRINE. | 7001 | 85 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2381 | 7001 |  | HT | N | 4828 | STRG | R/D 2 3/8" DP HANDLING TOOLS. R/U 4"DP HANDLING TOOLS. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2382 | 7001 |  | HT | N | 4828 | BHA | P/U, M/U 5-1/4'' WFD POLISH MILL, XO, 1EA 4-3/4'' DC, 5-1/2" STRG MAGNET , XO, 5-7/8" JUNK SUB, 1EA 4-3/4'' DC,7'' SCRAPER,1EA 4-3/4'' DC, XO, 3JT X 4" HWDP, 4-3/4" HYD JAR , 2 JT X 4" HWDP. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2383 | 7001 | 6680 | TI | N | 4828 | STDP | CONT. RIH W/ 4" X 7" TANDEM SCRAPER & 5-1/4" POLISH MILL ON 4"DP/HWDP F/ 1829 FT TO 6680 FT- FILL AND BREAK CIRC EVERY 10 STANDS W/ 77 PCF OBM | 7001 | 1829 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2384 | 7001 | 4914 | RW | N | 4828 | BIT | WORK SCRAPER ACROSS 7" PRODUCTION PKR PLAN SETTING DEPTH FROM 4756' TO 4914' & POLISH 4-1/2" PBR.- BIT DEPTH : 6838' ( 31' ABOVE L.C.) | 7001 | 4756 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2385 | 7001 |  | CIRC | N | 4828 | MPMP | DISPLACED WELL TO 72 PCF SOLIDS FREE VISCOUS BRINE. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2386 | 7001 |  | WCNT | N | 4828 | NA | FLOW CHECK, WELL STATIC. | 7001 |  | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2387 | 7001 | 6000 | TO | N | 4828 | STDP | POOH W/ 4" X 7" TANDEM SCRAPER & 5-1/4" POLISH MILL ON 4"DP/HWDP F/ 6838 FT TO 6000 FT | 7001 | 6838 | RIG | 09/26/2022 | SINO-12L | CT | HWYH-518
2388 | 24 | OOS | Category | DOOS ID | WCLN | Out of Scope Summary | PERFORM C/O CMT FOR 4-1/2" LINER. | 24 | 4828 | 26 Sep 0100 | 09/26/2022 | SINO-12L | Type | HWYH-518
2389
2390
2391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SINO-22 | Hrs | BRRI-1144
2392 | HERR | MSD | 1.25 | 26 Sep 0045 - 0200 | 3852 | 902757 | ALMASAOOD CROSSED PJ BELOW HALLIBURTON DVT, L/D SAME & MAKE UP DVT, OK. | JF | CTRQ |  | 09/26/2022 | SINO-22 | 1.25 | BRRI-1144
2393 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SINO-26 | Hrs | UTMN-1245
2394 | SRVC | NSL | 17 | 25 Sep 1800 - 1100 | 0 | 902740 | NESR SLICK LINE FAILED TO PUNCH 4-1/2" TBG WITH MECHANICAL PUNCHER | WO | NA |  | 09/26/2022 | SINO-26 | 6 | UTMN-1245
2395 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SND-2004 | Hrs | BRRI-1148
2396 | FOT | HSL | 88.5 | 22 Sep 0500 - 0500 | 8196 | 902598 | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL. | TF | PLUGN |  | 09/26/2022 | SND-2004 | 24 | BRRI-1148
2397 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SND-2007 | Hrs | AWTD-104001
2398 | TOWC | NPC | 36.5 | 25 Sep 1400 - 0430 | 15230 | 902688 | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP. | TF | JARS |  | 09/26/2022 | SND-2007 | 21.5 | AWTD-104001
2399 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SND-2010 | Hrs | MNIF-868
2400 | FOT | BC | 13 | 26 Sep 1600 - 0500 | 7039 | 902665 | 7.0" SLZXP PACKER DID NOT SHOW ANY INDICATION OF SETTING POOH - BAKER 7" X 9-5/8" SLZXP PKR ASSY LEFT IN THE HOLE | TF | PKR |  | 09/26/2022 | SND-2010 | 13 | MNIF-868
2401 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SP-110 | Hrs | MNIF-142
2402 | HERR | ITS | 25.5 | 25 Sep 0330 - 0500 | 4583 | 902728 | EXCESSIVE TIME TO RUN CSG. ITS EQT FAILLURE. INCOMPETENT ITS CREW. | JF | CTRQ |  | 09/26/2022 | SP-110 | 24 | MNIF-142
2403 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SSA-51 | Hrs | MNIF-255
2404 | WTHR | ARM | .75 | 26 Sep 2300 - 2345 | 2297 | 902668 | SUSPENDED OPERATION DUE TO HIGH WIND SPEED OVER 40 KM/HR | WON | NA |  | 09/26/2022 | SSA-51 | .75 | MNIF-255
2405 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SSA-5915 | Hrs | RGHB-704
2406 | FOT | RIG | 5.5 | 26 Sep 2330 - 0500 | 106 | 902730 | WHILE DRILLING 22'' SECTION, DRILLER CONSOLE LOST COMMUNICATION WITH VFD POWER SYSTEM | RR | PSYS |  | 09/26/2022 | SSA-5915 | 5.5 | RGHB-704
2407 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | SSA-5964 | Hrs | UTMN-2015
2408 | FOT | WWL | 37 | 25 Sep 1600 - 0500 | 0 | 902725 | LOST TIME ON WFRD WL LOGGING DUE TO PREVIOUS LOGGING RUN DATA BAD QUALITY AS PER ARAMCO RDD. | TF | WLT |  | 09/26/2022 | SSA-5964 | 24 | UTMN-2015
2409 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/26/2022 | V140A | Hrs | ZULF-653
2410 | UNKN | ARM | 1 | 26 Sep 0300 - 0400 | 4917 | 902734 | WHILE PU 13-3/8'' CASING. H2S ALARM AT FLOW LINE ACTIVATED. SHOWING 20 PPM @ CONTROL ROOM FLOW LINE SENSOR | HSEI | NA |  | 09/26/2022 | V140A | 1 | ZULF-653
2411 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | 088TE | Hrs | QTIF-519
2412 | FOT | SDM | 19 | 27 Sep 0830 - 0500 | 14011 | 902819 | FAILURE OF LWD STETHOSCOPE TOOL, TROUBLSHOOT SAME, NO SUCCESS, POOH TO CHANGE TOOL. | BHA | LWD |  | 09/27/2022 | 088TE | 19 | QTIF-519
2413 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADC-55L | Hrs | UTMN-3171
2414 | LCRW | TK3 | 147 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/27/2022 | ADC-55L | 24 | UTMN-3171
2415 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADC-56L | Hrs | UTMN-3069
2416 | FOT | TK3 | 267.25 | 16 Sep 0500 - 0430 | 14035 | 902244 | PERFORMED NEGATIVE TEST FOR 7" & 4-1/2" , OBSERVED ANNULUS LEVEL DROP SLOWLY | DSF | STRG |  | 09/27/2022 | ADC-56L | 23.5 | UTMN-3069
2417 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADC-59L | Hrs | HWYH-1324
2418 | CEDE | TK3 | 101.75 | 22 Sep 0030 - 0500 | 19319 | 902684 | CONT. WIPER TRIP. RIH W/ WBCU ASSAY FROM 16412 FT TO 19,319 FT ON ELEVATOR. | DRG | NA |  | 09/27/2022 | ADC-59L | 23.5 | HWYH-1324
2419 | 10794 |  | OTH | E | 4627 | NA | RIH TLC LOGGING TOOLS FROM 5,291 FT TO 10,189 FTWITH CONTROLLED SPEED.- PASS CAREFULLY THRU TOL @ 6,024 FT.- RUN ON 5" DP STANDS- RIH SPEED: 3 MIN/STD.- FILL UP STRING EVERY 10 STANDS.- DRIFT ALL STANDS WHILE RIH WITH 2.5" DRIFT.- MONITOR WELL THROUGH TRIP TANK. | 10794 |  | SWL | 09/27/2022 | ADC-68L | LOG | FDHL-174
2420 | 10794 |  | CIRC | E | 4627 | MPMP | CIRCULATE 1.5 STRING VOLUME W/OBM,- FR= 170 GPM, SPP= 350 PSI, MEANWHILE R/U WL SHEAVES.- HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW. | 10794 |  | RIG | 09/27/2022 | ADC-68L | LOG | FDHL-174
2421 | 10794 |  | OTH | E | 4627 | NA | LATCH WIRELINE CABLE PWCH INTO DWCH @ 10,189 FT AS PER WL ENG INSTRUCTION.- M/U WL CSES WITH FED THRU WIRE LINE CABLE, RIH SLB WL CABLE PUMP DOWN @ 200 GPM, 700 PSI TO ASSIST LATCHING.- FUNCTION TEST SLB TOOLS, OK, PERFORM PULL TEST TO 3,200 LBS, MONITOR WELL THROUGH TRIP TANK, WELL STATIC | 10794 |  | SWL | 09/27/2022 | ADC-68L | LOG | FDHL-174
2422 | 10794 | 10385 | TI | E | 4627 | STDP | RIH TLC LOGGING TOOLS FROM 10,189 FT TO 10,385 FT,WITH CONTROLLED SPEED- RUN WITH 5" DP STDS RIH SPEED: 5 MIN/STD, MONITOR WELL THROUGH TRIP TANK | 10794 | 10189 | RIG | 09/27/2022 | ADC-68L | LOG | FDHL-174
2423 | 10794 |  | OTH | E | 4627 | NA | PERFORMED STICK TEST AT 10,385 FT FOR 3, 5, 8,15MIN,BEFORE TAKING FORMATION PRESSURE.- WL TOOL MEASURE 4,700 LBF; 4,750 LBF; 4,800 LBF; 4,900 LBF,ACCORDINGLY. NO SIGNIFICANT INCREASE DURING STICK TEST.- MONITOR WELL THROUGH TRIP TANK, WELL STATIC. | 10794 |  | SWL | 09/27/2022 | ADC-68L | LOG | FDHL-174
2424 | 10794 | 10520 | LOG | E | 4627 | WLT | SLB WL TAKE PRESSURE POINTS AS PER ARAMCO RMD.- FORMATION: LFDR. TAKE PRESSURE POINTS AT ( 10,385; 10,390'; 10,395'; 10,410';10,420'; 10,430'; 10,435'; 10,440'; 10,450'; 10,460'; 10,470'; 10,475';10,485'; 10,495'; 10,505' AND 10,520').- PERFORM 3, 8 MIN STICKING TEST BEFORE EACHPRESSURE POINT IN LFDR FORMATION. NO SIGNIFICANTINCREASE DURING STICK TEST IN THE MAJORITY OF THEPOINTS.** AT 10,460' OBSERVE 3,000, LBS AFTER 3 MIN 5,000 LBS O/P AFTER 8 MIN STICK TEST, DECIDED TO SKIP THIS POINT)- MONITOR WELL THROUGH TRIP TANK, WELL STATIC. | 10794 | 10385 | SWL | 09/27/2022 | ADC-68L | LOG | FDHL-174
2425 | 298.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 24 | 4627 | 08 Sep 0300 | 09/27/2022 | ADC-68L | Type | FDHL-174
2426
2427
2428 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADC-70 | Hrs | MRJN-761
2429 | UDWL | BHI | 18 | 27 Sep 1100 - 0500 | 455 | 902817 | RECORDED DIR SURVEY, FOUND WELL PATH OPPOSITE TO DIR PLAN. POH, FOUND BHI-MM ALIGNMENT SHIFTED 120 DEG. DECISION MADE TO PERFORM P&A CMT PLUG AND SIDE TRACK 22" OPEN HOLE. | DD | MMOT |  | 09/27/2022 | ADC-70 | 18 | MRJN-761
2430 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADES-173 | Hrs | UTMN-1952
2431 | WHOL | RIG | 13.75 | 27 Sep 0815 - 2200 | 11556 | 902828 | DRILL PIPE WASHED OUT. | DSF | DP |  | 09/27/2022 | ADES-173 | 13.75 | UTMN-1952
2432 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADES-889 | Hrs | HRDH-2122
2433 | PCPF | ARM | 278 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/27/2022 | ADES-889 | 23.5 | HRDH-2122
2434 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADM-262 | Hrs | MRJN-57
2435 | WTHR | ARM | 64 | 25 Sep 1300 - 0500 | 0 | 902711 | WAIT ON WEATHER TO TRANSFER FOREMAN TO CHECK PF DEPRESSURIZATION & VAHANA ARYAN BARGE TO MOVE OUT FROM LOCATION. | WON | NA |  | 09/27/2022 | ADM-262 | 24 | MRJN-57
2436 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADM-266 | Hrs | SFNY-263
2437 | WTHR | ARM | 6 | 27 Sep 1900 - 0100 | 0 | 902840 | AIT ON WEATHER TO BACKLOAD CARGOS & 3RD PARTY EQUIPMENT PRIOR TO SKID IN. | WON | NA |  | 09/27/2022 | ADM-266 | 6 | SFNY-263
2438 | WOTO | BCT | 5 | 27 Sep 0000 - 0500 | 13899 | 902835 | POWER PACK FOR CT REEL FAILED. WAITING ON REPLACEMENT TO BE SENT TO RIG | WO | NA |  | 09/27/2022 | ADM-511 | 5 | MRJN-799
2439 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADM-511 | Hrs | MRJN-799
2440 | WTHR | ARM | 24 | 26 Sep 0000 - 0000 | 12899 | 902738 | CANNOT BACKLOAD OFFLOAD HALLIBURTON, BAKER, AND SLB EQUIPMENT FROM BOAT DUE TO HIGH WINDS AND SEAS | WON | NA |  | 09/27/2022 | ADM-511 | 19 | MRJN-799
2441 | WOTO | BCT | 5 | 27 Sep 0000 - 0500 | 13899 | 902835 | POWER PACK FOR CT REEL FAILED. WAITING ON REPLACEMENT TO BE SENT TO RIG | WO | NA |  | 09/27/2022 | ADM-511 | 5 | MRJN-799
2442 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ADM-657 | Hrs | SFNY-1263
2443 | WTHR | ARM | 42 | 26 Sep 1100 - 0500 | 0 | 902733 | UNABLE TO RIG MOVE DUE TO WEATHER | WON | NA |  | 09/27/2022 | ADM-657 | 24 | SFNY-1263
2444 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ARO-2001 | Hrs | MRJN-121
2445 | WTHR | ARM | 82.25 | 24 Sep 1845 - 0500 | 0 | 902713 | WAIT ON WEATHER TO RIG MOVE TO MRJN 121/126 PF | WON | NA |  | 09/27/2022 | ARO-2001 | 24 | MRJN-121
2446 | FOT | RIG | 1.5 | 27 Sep 0030 - 0200 | 1308 | 902834 | DURING BOP PRESSURE TEST OBSERVE BONNET LEAKING ON LOWER MASTER PIPE RAM | RR | RWCS |  | 09/27/2022 | ARO-3003 | 1.5 | SFNY-1157
2447 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ARO-3003 | Hrs | SFNY-1157
2448 | FOT | RIG | 1.5 | 27 Sep 2200 - 2330 | 1308 | 902833 | WHILE PRESSURE TESTING 26 3/4" 3M BOP OBSERVED LEAKING BONNET SEAL ON THE BLIND RAM. | RR | RWCS |  | 09/27/2022 | ARO-3003 | 1.5 | SFNY-1157
2449 | FOT | RIG | 1.5 | 27 Sep 0030 - 0200 | 1308 | 902834 | DURING BOP PRESSURE TEST OBSERVE BONNET LEAKING ON LOWER MASTER PIPE RAM | RR | RWCS |  | 09/27/2022 | ARO-3003 | 1.5 | SFNY-1157
2450 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ARO-3004 | Hrs | MRJN-2060
2451 | WTHR | ARM | 13 | 27 Sep 1400 - 0300 | 9578 | 902832 | WAIT ON WEATHER TO RECEIVE EXPLOSIVES FOR SETTING 9 5/8'' EZSV/BP | WON | NA |  | 09/27/2022 | ARO-3004 | 13 | MRJN-2060
2452 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ENS-108 | Hrs | ZULF-2015
2453 | FOT | BCR | .75 | 27 Sep 0330 - 0415 | 8220 | 902839 | OBSERVED BKR CSG POWER TONG FALIED AND LEAK IN FMS AIR HOSE. | TF | CTRQ |  | 09/27/2022 | ENS-108 | .75 | ZULF-2015
2454 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | ENSCO-54 | Hrs | ABSF-146
2455 | WTHR | ARM | 2.5 | 27 Sep 0230 - 0500 | 4050 | 902830 | BOAT HADI-41 UNABLE TO APPROACH DUE TO ADVERSE WEATHER CONDITIONS - CARGO ON HADI-41 NEEDED FOR THE NEXT RUN- ESP COMPLETION. | WON | NA |  | 09/27/2022 | ENSCO-54 | 2.5 | ABSF-146
2456 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | EXL-IA | Hrs | ABSF-128
2457 | FOT | GEP | 1.5 | 27 Sep 0330 - 0500 | 217 | 902838 | WHILE ATTEMPTING TO PRESSURE TEST MLS, WOULD NOT MAKE UP AND PRESSRE TEST | WH | WH |  | 09/27/2022 | EXL-IA | 1.5 | ABSF-128
2458 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | HWU-1 | Hrs | HMYM-450212
2459 | FOT | RIG | 5.25 | 27 Sep 1015 - 1530 | 1 | 902796 | TCC DATA CABLE NOT READING PRESSURE. REPLACEMENT CABLE DID NOT REACH WELLHEAD | RR | MPMP |  | 09/27/2022 | HWU-1 | 5.25 | HMYM-450212
2460 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | MP-1 | Hrs | BRRI-310
2461 | WTHR | ARM | 44 | 25 Sep 2300 - 0100 | 0 | 902660 | UNABLE TO BACKLOAD CTU & WELL TESTING EQ DUE TO UNFAVORABLE WEATHER CONDITION. | WON | NA |  | 09/27/2022 | MP-1 | 20 | BRRI-310
2462 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | MP-4 | Hrs | RBYN-65
2463 | WTHR | ARM | 18 | 27 Sep 1100 - 0500 | 1470 | 902836 | UNABLE TO OFFLOAD 18-5/8" CSG FROM BOAT DUE TO UNFAVORABLE WEATHER CONDITION. | WON | NA |  | 09/27/2022 | MP-4 | 18 | RBYN-65
2464 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | NBR-263S | Hrs | QTIF-736
2465 | WOTO | SJT | 2 | 27 Sep 0900 - 1100 | 14100 | 902674 | DELAY WHILE PURGING CT W/ N2 AS PUMP WAS NOT AVAILABLE, SPOT, LINE UP & START PUGING. | WO | NA |  | 09/27/2022 | NBR-263S | 2 | QTIF-736
2466 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | PA-218S | Hrs | HRDH-1976
2467 | UXDF | ARN | 253.5 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/27/2022 | PA-218S | 24 | HRDH-1976
2468 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | PA-622S | Hrs | UTMN-3600
2469 | FOT | NWT | .75 | 27 Sep 0700 - 0745 | 14342 | 902778 | ATTEMPTED TO SHUT IN THE WELL WITH AUTOMATIC CHOKE BUT NO RESPONSE, CLOSE THE WELL MANUALLY. RE-OPEN THE WELL TO SHUT IN PROPERLY. | TF | CHK |  | 09/27/2022 | PA-622S | .75 | UTMN-3600
2470 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | RM-74A | Hrs | HSBH-68
2471 | FOT | RIG | 2.5 | 27 Sep 1030 - 1300 | 6459 | 902672 | DRIVE COUPLING ON BRIDGE RACKER MAIN SHAFT FOUND TO BE WORKING LOOSE. ARO REPAIRED SAME. | RR | HSYS |  | 09/27/2022 | RM-74A | 2.5 | HSBH-68
2472 | 7001 | 5020 | TO | N | 4828 | STDP | POOH W/ 4" X 7" TANDEM SCRAPER & 5-1/4" POLISH MILL ON 4"DP/HWDP T/ 5020' ( 22 FT BELOW 4-1/2" T.O.L). | 7001 | 6000 | RIG | 09/27/2022 | SINO-12L | CT | HWYH-518
2473 | 7001 |  | CIRC | N | 4828 | MPMP | SWEEP & CIRCULATE HOLE CLEAN W/ 72 PCF VISCOUS BRINE. | 7001 |  | RIG | 09/27/2022 | SINO-12L | CT | HWYH-518
2474 | 7001 | 1829 | TO | N | 4828 | STDP | CONT. POOH W/ 4" X 7" TANDEM SCRAPER & 5-1/4" POLISH MILL ON 4"DP/HWDP T/ 1829' ( 27 FT BELOW 7" T.O.L). | 7001 | 5020 | RIG | 09/27/2022 | SINO-12L | CT | HWYH-518
2475 | 7001 |  | CIRC | N | 4828 | MPMP | SWEEP & CIRCULATE HOLE CLEAN W/ 72 PCF VISCOUS BRINE. | 7001 |  | RIG | 09/27/2022 | SINO-12L | CT | HWYH-518
2476 | 7001 |  | HT | N | 4828 | BHA | L/D 4 3/4" DC'S, 5 7/8" JUNK SUB, 5 1/4" MAGNET & 5 1/4" POLISH MILL. | 7001 |  | RIG | 09/27/2022 | SINO-12L | CT | HWYH-518
2477 | 7001 |  | HT | N | 4828 | PEL | R/D 4" DP HANDLING TOOLS. R/U 2 3/8"DP HANDLING TOOLS. | 7001 |  | RIG | 09/27/2022 | SINO-12L | CT | HWYH-518
2478 | 7001 | 0 | TO | N | 4828 | STHDP | HPJSM. POOH W/ 4-1/2" SCRAPER F/ 1829 FT T/ SURFACE WHILE RACK BACK 2 3/8" DP STANDS ON DERRICK. | 7001 | 1829 | RIG | 09/27/2022 | SINO-12L | CT | HWYH-518
2479 | 7001 |  | HT | N | 4828 | BHA | L/D 3-7/8" PDC BIT, 4-1/2" ROTATING SCRAPER, RECOVED 100 G FINE METAL JUNK FROM 3-1/2" STRING MAGNET. | 7001 |  | RIG | 09/27/2022 | SINO-12L | CT | HWYH-518
2480 | 7001 |  | NU | N | 4889 | SNIP | HPJSM, N/D BELL NIPPLE. N/U 9-5/8" SHOOTING NIPPLE. | 7001 |  | RIG | 09/27/2022 | SINO-12L | LOG | HWYH-518
2481 | 7001 |  | OTH | E | 4889 | NA | HELD PJSM. R/U HES WL PCE. P/T SAME TO 1000 PSI - OK- R/U WIRELINE SHEAVE. P/U & M/U WIRELINE CAST-CBL-GR TOOLSTRING. | 7001 |  | HWP | 09/27/2022 | SINO-12L | LOG | HWYH-518
2482 | 7001 | 6000 | LOG | E | 4889 | WLT | HES WL RIH W/ (CAST-CBL-GR) TOOL STRING TO 6800', POOH WHILE RECORD CBL LOG TO 6000'- RIH RECORD REPEAT PASS FROM 6450' TO 6650'. | 7001 | 6800 | HWP | 09/27/2022 | SINO-12L | LOG | HWYH-518
2483 | 7001 | 6595 | LOG | E | 4889 | WLT | HPJSM, HES WL RIH W/ 3-1/8" CSG GUN#1, ( MAXFORCE 6 SPF ) ON GR-CCL TO 6604', CORRELATE DEPTH ON GOING. | 7001 | 6604 | HWP | 09/27/2022 | SINO-12L | LOG | HWYH-518
2484 | 15.75 | OOS | WCLN | 4828 | PERF | PERFORM C/O CMT FOR 4-1/2" LINER. | CAST CBL LOG & PERFORATE 4.5" LINER. | 15.75 | 4889 | 27 Sep 0200 | 09/27/2022 | SINO-12L | OOS | HWYH-518
2485
2486
2487
2488 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SINO-29N | Hrs | SFNY-2005
2489 | PCPF | ARN | 104.25 | 23 Sep 2045 - 0500 | 7202 | 902625 | 4 - 1/2" LINER DIFFERENTIALY STICKING AT CONNECTIONS IN OH, FOUND SHALE CAVINGS IN RETURNS, HOLE NOT STABLE | TH | NA |  | 09/27/2022 | SINO-29N | 24 | SFNY-2005
2490 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SINO-36L | Hrs | ANDR-378
2491 | FOT | SPS | 20.5 | 27 Sep 0530 - 0200 | 8112 | 902837 | HAD I CRUISE TOOL FAILURE, TROUBLE SHOOTING, NO SUCCESS. | BHA | RSS |  | 09/27/2022 | SINO-36L | 20.5 | ANDR-378
2492 | FOT | ARM | 3 | 27 Sep 0700 - 1000 | 40 | 902816 | LEAKING TWCV. DIFFICULTY TO RETRIEVE DUE TO ECCENTRIC LONG T-BAR RETRIEVING TOOL. | TF | BPV |  | 09/27/2022 | SND-2004 | 3 | BRRI-1148
2493 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SND-2004 | Hrs | BRRI-1148
2494 | FOT | HSL | 109.5 | 22 Sep 0500 - 0500 | 8196 | 902598 | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL. | TF | PLUGN |  | 09/27/2022 | SND-2004 | 21 | BRRI-1148
2495 | FOT | ARM | 3 | 27 Sep 0700 - 1000 | 40 | 902816 | LEAKING TWCV. DIFFICULTY TO RETRIEVE DUE TO ECCENTRIC LONG T-BAR RETRIEVING TOOL. | TF | BPV |  | 09/27/2022 | SND-2004 | 3 | BRRI-1148
2496 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SND-2007 | Hrs | AWTD-104001
2497 | TOWC | NPC | 60.5 | 25 Sep 1400 - 0500 | 15230 | 902688 | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF. | TF | JARS |  | 09/27/2022 | SND-2007 | 24 | AWTD-104001
2498 | FOT | RIG | 1 | 27 Sep 1800 - 1900 | 7039 | 902818 | HAD MALEFUNCTION IN ROUGH NECK WHILE ASSEMBLING BHA. | RR | HSYS |  | 09/27/2022 | SND-2010 | 1 | MNIF-868
2499 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SND-2010 | Hrs | MNIF-868
2500 | FOT | BC | 36 | 26 Sep 1600 - 0500 | 7039 | 902665 | 7.0" SLZXP PACKER DID NOT SHOW ANY INDICATION OF SETTING POOH - BAKER 7" X 9-5/8" SLZXP PKR ASSY LEFT IN THE HOLE | TF | PKR |  | 09/27/2022 | SND-2010 | 23 | MNIF-868
2501 | FOT | RIG | 1 | 27 Sep 1800 - 1900 | 7039 | 902818 | HAD MALEFUNCTION IN ROUGH NECK WHILE ASSEMBLING BHA. | RR | HSYS |  | 09/27/2022 | SND-2010 | 1 | MNIF-868
2502 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SNT-025 | Hrs | SFNY-517
2503 | WTHR | ARM | 24 | 27 Sep 0500 - 0500 | 0 | 902841 | WAIT ON WEATHER FOR BACKLOAD BOATS | WON | NA |  | 09/27/2022 | SNT-025 | 24 | SFNY-517
2504 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SP-110 | Hrs | MNIF-142
2505 | HERR | ITS | 33.5 | 25 Sep 0330 - 1300 | 4583 | 902728 | EXCESSIVE TIME TO RUN CSG. ITS EQT FAILLURE. INCOMPETENT ITS CREW. | JF | CTRQ |  | 09/27/2022 | SP-110 | 8 | MNIF-142
2506 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SP-121 | Hrs | BRRI-522
2507 | FOT | BLH | 5.75 | 27 Sep 2315 - 0500 | 15660 | 902831 | REAM DOWN INSIDE 7" LINER SHALLOWER THAN EXPECTED, DUE TO PRESENCE OF CMT RINGS. | TF | HGRL |  | 09/27/2022 | SP-121 | 5.75 | BRRI-522
2508 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SP-160 | Hrs | DYBN-1
2509 | HERR | RIG | 11.25 | 27 Sep 1030 - 2145 | 3063 | 902673 | WHILE PRESSURE TEST SL LUBRICATOR , PDHMS ENGINEER HAD PRESSURE READING INSIDE TBG . BAKER TROUBLESHOOT SCT , FOUND IT CLOSED & HOLDING PRESSURE . | JF | SFLN |  | 09/27/2022 | SP-160 | 11.25 | DYBN-1
2510 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SP-58 | Hrs | HRDH-795
2511 | FOT | SDM | 1 | 27 Sep 1845 - 1945 | 16131 | 902825 | LOST MWD SIGNAL, MWD IMPUSE SHUTDOWN, TROUBLESHOOTING SAME ,OK. | BHA | MWD |  | 09/27/2022 | SP-58 | 1 | HRDH-795
2512 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SSA-5865 | Hrs | FRHH-3
2513 | FOT | RIG | 1 | 27 Sep 1845 - 1945 | 11915 | 902826 | REPAIR ON IRON ROUGHNECK | RR | HSYS |  | 09/27/2022 | SSA-5865 | 1 | FRHH-3
2514 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SSA-5915 | Hrs | RGHB-704
2515 | FOT | RIG | 20.25 | 26 Sep 2330 - 1945 | 106 | 902730 | WHILE DRILLING 22'' SECTION, DRILLER CONSOLE LOST COMMUNICATION WITH VFD POWER SYSTEM | RR | PSYS |  | 09/27/2022 | SSA-5915 | 14.75 | RGHB-704
2516 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SSA-5964 | Hrs | UTMN-2015
2517 | FOT | WWL | 40 | 25 Sep 1600 - 0800 | 0 | 902725 | LOST TIME ON WFRD WL LOGGING DUE TO PREVIOUS LOGGING RUN DATA BAD QUALITY AS PER ARAMCO RDD. | TF | WLT |  | 09/27/2022 | SSA-5964 | 3 | UTMN-2015
2518 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SSA-5969 | Hrs | UTMN-3148
2519 | WC20 | ARM | 164.5 | 19 Sep 0430 - 0500 | 10092 | 902485 | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF. | WCNT | NA |  | 09/27/2022 | SSA-5969 | 23 | UTMN-3148
2520 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | SSA-5974 | Hrs | HRDH-1979
2521 | CWEL | ARM | 11.5 | 27 Sep 1730 - 0500 | 1648 | 902827 | AFTER CONNECTION STRING GOT STUCK, PRESSURE INCREASED AND NO MOVEMENT UP AND DOWN, HAD CIRCULATION RESTRECTION. | BHS | NA |  | 09/27/2022 | SSA-5974 | 11.5 | HRDH-1979
2522 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/27/2022 | WCL-83 | Hrs | MRJN-1002
2523 | WTHR | ARM | 24 | 27 Sep 0500 - 0500 | 0 | 902675 | WAIT ON WEATHER. NOT ABLE TO OFFLOAD BOAT OR USE CRANE TO PICK UP DP'S DUE TO ROUGH SEA AND STRONG WIND. | WON | NA |  | 09/27/2022 | WCL-83 | 24 | MRJN-1002
2524 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | 088TE | Hrs | QTIF-519
2525 | FOT | SDM | 40 | 27 Sep 0830 - 0500 | 14011 | 902819 | FAILURE OF LWD STETHOSCOPE TOOL, TROUBLSHOOT SAME, NO SUCCESS, POOH TO CHANGE TOOL. | BHA | LWD |  | 09/28/2022 | 088TE | 21 | QTIF-519
2526 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ADC-17 | Hrs | ZULF-1387
2527 | FPMP | RIG | .5 | 28 Sep 0300 - 0330 | 4735 | 902916 | PISTON & LINER FAILURE FOR MUD PUMP#1. | RR | MPMP |  | 09/28/2022 | ADC-17 | .5 | ZULF-1387
2528 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ADC-34 | Hrs | UTMN-2309
2529 | FOT | RIG | 1 | 28 Sep 0930 - 1030 | 12863 | 902898 | LEAKING JUMPER HOSE FROM PUMP # 2 TO MANIFOLD. | RR | CSYS |  | 09/28/2022 | ADC-34 | 1 | UTMN-2309
2530 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ADC-55L | Hrs | UTMN-3171
2531 | LCRW | TK3 | 171 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/28/2022 | ADC-55L | 24 | UTMN-3171
2532 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ADC-59L | Hrs | HWYH-1324
2533 | UNFM | ARM | 125.75 | 22 Sep 0030 - 0500 | 19319 | 902684 | CONT. WIPER TRIP. RIH W/ WBCU ASSAY FROM 16412 FT TO 19,319 FT ON ELEVATOR. NOTE: LINER PARTIALLY OBSTRUCTED DUE TO POSSIBLE LINER COLLAPSE. | WI | CSG |  | 09/28/2022 | ADC-59L | 24 | HWYH-1324
2534 | 12861 | 325 | TO | N |  | STDP | POOH WITH 6-1/8" DIR BHA ON 4" DP STDS F/4158 FT TO 325 FT.- MONITOR WELL ON TRIP TANK, OK | 12861 | 4158 | RIG | 09/28/2022 | ADC-62L | CT | ANDR-589
2535 | 12861 |  | HT | N |  | BHA | FLOW CHECK AT TOP BHA-WELL STATIC, CONT. POOH & L/D 6-1/8" RSS BHA TO SURFACE.- HOLD PJSM & REMOVE RA SOURCE- L/D ADN + MICROSCOPE & IMPULSE- B/O & L/D PDC BIT.- BIT DULL GRADING: 1-1-WT-A-X-I-NO-TD- MONITOR THE WELL WITH TRIP TANK. | 12861 |  | RIG | 09/28/2022 | ADC-62L | CT | ANDR-589
2536 | 12861 |  | RTRV | N |  | WBSH | PU MU RETRIVING TOOL & RETRIEVE 11" VG WEAR BUSHING, L/D SAME. | 12861 |  | RIG | 09/28/2022 | ADC-62L | WH | ANDR-589
2537 | 12861 |  | OTH | N |  | BOP | HPJSM, P/U & M/U BOP 11" TEST PLUG ASSY.- 3 STD'S OF 5" DP'S + 11" VETCO GRAY TP, 5" DP JT + SES + FOSV + PUP JT TO TDS.- OPEN CHH SOV.- RIH & LAND TP INTO CHH.- CONNECTED HP TEST UNIT TO SES & TO CM AS PER ADC PROCEDURE.- FUNCTION TEST BOP.- FLUSH AND CLEAN WELLHEAD, CHOKE MANIFOLD, MGS, FLARE LINES AND EMRG KILL LINE WITH WATER. | 12861 |  | RIG | 09/28/2022 | ADC-62L | BOP | ANDR-589
2538 | 12861 |  | BOPT | N |  | BOP | PERFORM BOP PRESSURE TEST AS PER FOLLOW:- PERFORM P/T #1:ANNULAR ON 4" DP, 2* CHECK VALVES, CM MASTER VALVE, 4" SPM VALVE & ROTARY HOSE.- TEST #2: UPPER RAM [VBR] ON 4" DP, KILL LINE MV (#1), EMKL MV(#2), CHOKE HCR , TDS HYD IBOP.- TEST #3: UPPER RAM [VBR] ON 4" DP, CHOKE LINE MV(#4), LK MV (#3), KILL LINE HCR , TDS MANUAL IBOP.- TEST #4: LOWER 4" PIPE RAM, LK MV (#2), FULL OPENING SAFETY VALVE.- TEST #5: BSR, KILL LINE MV(#3) ,LK HCR.- PERFORMED TEST#1@ 300/ 3,000 PSI , OTHER TESTS 300/2,550 PSI FOR 10 MIN EACH. | 12861 |  | RIG | 09/28/2022 | ADC-62L | BOP | ANDR-589
2539 | 12861 |  | OTH | N |  | BOP | POOH & L/D TEST PLUG ASSY, M/U 9-5/8" CUP TESTER ASSY. | 12861 |  | RIG | 09/28/2022 | ADC-62L | BOP | ANDR-589
2540 | 12861 |  | BOPT | N |  | BOP | P/T 13-5/8" BOP, TEST #6: 5" DP ON ANNULAR, BOTH THS SOV'S.-PERFORM ACCUMULATOR DRAW DOWN TEST. | 12861 |  | RIG | 09/28/2022 | ADC-62L | BOP | ANDR-589
2541 | 12861 |  | OTH | N |  | BOP | POOH & L/D 9-5/8'' CUP TESTER ASSY. | 12861 |  | RIG | 09/28/2022 | ADC-62L | BOP | ANDR-589
2542 | 12861 |  | SET | N |  | WBSH | PU MU SETTING TOOL & SET 11" VG WEAR BUSHING, L/D SAME. | 12861 |  | RIG | 09/28/2022 | ADC-62L | WH | ANDR-589
2543 | 12861 |  | OTH | E | 4892 | NA | HPJSM PRIOR TO RUN WL TLC LOGGING.- BRIEF JOB PROCEDURES & RELATED HAZARDS.- BRIEF SAFE DRIFTING STRING PROCEDURES.- SHARE CALIPER ALERT.- ENFORCE SAFE WORK & SWA. | 12861 |  | SWL | 09/28/2022 | ADC-62L | LOG | ANDR-589
2544 | 12861 |  | OTH | E | 4892 | NA | PU M/U SLB WL MECHANICAL CALIPER LOGGING TOOLS.- FUNCTION TEST LOGGING TOOLS - OK.- MONITOR WELL ON TRIP TANK - OK. | 12861 |  | SWL | 09/28/2022 | ADC-62L | LOG | ANDR-589
2545 | 12861 | 5500 | TI | E | 4892 | STDP | RIH SLB WL MECH CALIPER LOGGING TOOL ON 4" DRIFTED DP TO 5745 FT.- CONTROL RUNNING SPEED @ 2 MINS SLIP-TO-SLIP.- PASS SLOWLY THROUGH TOL@ 2,733 FT.- RIH WITH DRIFTED 4" DP.- FILL & BREAK CIRC. EVERY 10 STANDS.- MONITOR WELL ON TRIP TANK - OK. | 12861 | 0 | RIG | 09/28/2022 | ADC-62L | LOG | ANDR-589
2546 | 8.5 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | RUN SLB CALLIPER LOG TOOL | 8.5 | 4892 | 28 Sep 2030 | 09/28/2022 | ADC-62L | Type | ANDR-589
2547
2548
2549 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ADC-70 | Hrs | MRJN-761
2550 | UDWL | BHI | 42 | 27 Sep 1100 - 0500 | 455 | 902817 | RECORDED DIR SURVEY, FOUND WELL PATH OPPOSITE TO DIR PLAN. POH, FOUND BHI-MM ALIGNMENT SHIFTED 120 DEG. DECISION MADE TO PERFORM P&A CMT PLUG AND SIDE TRACK 22" OPEN HOLE. | DD | MMOT |  | 09/28/2022 | ADC-70 | 24 | MRJN-761
2551 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ADES-889 | Hrs | HRDH-2122
2552 | PCPF | ARM | 301.5 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/28/2022 | ADES-889 | 23.5 | HRDH-2122
2553 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ADM-657 | Hrs | SFNY-1263
2554 | WTHR | ARM | 43 | 26 Sep 1100 - 0600 | 0 | 902733 | UNABLE TO RIG MOVE DUE TO WEATHER | WON | NA |  | 09/28/2022 | ADM-657 | 1 | SFNY-1263
2555 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ARO-2001 | Hrs | MRJN-121
2556 | WTHR | ARM | 106.25 | 24 Sep 1845 - 0500 | 0 | 902713 | WAIT ON WEATHER TO RIG MOVE TO MRJN 121/126 PF | WON | NA |  | 09/28/2022 | ARO-2001 | 24 | MRJN-121
2557 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ARO-3001 | Hrs | MRJN-3001
2558 | FOT | GCD | 2.75 | 28 Sep 2015 - 2300 | 2137 | 902850 | GYRO TOOL FACE UNSTABLE | TF | GYRO |  | 09/28/2022 | ARO-3001 | 2.75 | MRJN-3001
2559 | FOT | RIG | 3.5 | 28 Sep 0130 - 0500 | 1308 | 902852 | WHILE CLEANING OUT 24" LANDING COLLAR OBSERVE TDS TORQUE TO 23K FT/LBS. LOST 80K STRING WEIGHT & ALL PUMP PRESSURE INDICATING STRING HAD TWISTED OFF. | DSF | DP |  | 09/28/2022 | ARO-3003 | 3.5 | SFNY-1157
2560 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ARO-3003 | Hrs | SFNY-1157
2561 | GRF | RIG | 9 | 28 Sep 1500 - 0000 | 1308 | 902847 | DURING DRILLING CEMENT IN 24 " CASING THE TOP DRIVE MALFUNCTIONED AND WOULD NOT ROTATE THE DRILL STRING. | UPRA | TDS |  | 09/28/2022 | ARO-3003 | 9 | SFNY-1157
2562 | FOT | RIG | 3.5 | 28 Sep 0130 - 0500 | 1308 | 902852 | WHILE CLEANING OUT 24" LANDING COLLAR OBSERVE TDS TORQUE TO 23K FT/LBS. LOST 80K STRING WEIGHT & ALL PUMP PRESSURE INDICATING STRING HAD TWISTED OFF. | DSF | DP |  | 09/28/2022 | ARO-3003 | 3.5 | SFNY-1157
2563 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ARO-3004 | Hrs | MRJN-2060
2564 | WTHR | ARM | 1.5 | 28 Sep 0600 - 0730 | 9578 | 902855 | WAIT ON WEATHER TO OFF-LOAD EWL UNIT & EQUIPMENT FROM STAND BY BOAT | WON | NA |  | 09/28/2022 | ARO-3004 | 1.5 | MRJN-2060
2565 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ED-85A | Hrs | ZULF-2066
2566 | FOT | RIG | 8.5 | 28 Sep 0830 - 0500 | 7360 | 902919 | LINK TILT CYLINDER WAS BROKEN | RR | TDS |  | 09/28/2022 | ED-85A | 8.5 | ZULF-2066
2567 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ENSCO-54 | Hrs | ABSF-146
2568 | WTHR | ARM | 10.5 | 27 Sep 0230 - 1300 | 4050 | 902830 | BOAT HADI-41 UNABLE TO APPROACH DUE TO ADVERSE WEATHER CONDITIONS - CARGO ON HADI-41 NEEDED FOR THE NEXT RUN- ESP COMPLETION. | WON | NA |  | 09/28/2022 | ENSCO-54 | 8 | ABSF-146
2569 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | EXL-IA | Hrs | ABSF-128
2570 | FOT | GEP | 24.5 | 27 Sep 0330 - 0500 | 217 | 902838 | UNABLE TO CLOSE MLC RT PORTS, PRESSURE TEST FAILED ON SAME. | WH | WH |  | 09/28/2022 | EXL-IA | 23 | ABSF-128
2571 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | MP-4 | Hrs | RBYN-65
2572 | WTHR | ARM | 40.5 | 27 Sep 1100 - 0330 | 1470 | 902836 | UNABLE TO OFFLOAD 18-5/8" CSG FROM BOAT DUE TO UNFAVORABLE WEATHER CONDITION. | WON | NA |  | 09/28/2022 | MP-4 | 22.5 | RBYN-65
2573 | FOT | RIG | 4.75 | 28 Sep 1615 - 2100 | 4309 | 902849 | HAD LEAK FROM TOP DRIVE LINK TILT HYDRAULIC OIL HOSE. | RR | TDS |  | 09/28/2022 | PA-218S | 4.75 | HRDH-1976
2574 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | PA-218S | Hrs | HRDH-1976
2575 | UXDF | ARN | 270.25 | 16 Sep 2000 - 0500 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/28/2022 | PA-218S | 16.75 | HRDH-1976
2576 | FOT | RIG | 1.5 | 25 Sep 1215 - 1415 | 1043 | 902685 | EXCESS TRIPPING TIME, DUE TO IRON ROUGHNECK MALFUNCTION. | RR | SLIPS |  | 09/28/2022 | PA-218S | .5 | HRDH-1976
2577 | FOT | RIG | 4.75 | 28 Sep 1615 - 2100 | 4309 | 902849 | HAD LEAK FROM TOP DRIVE LINK TILT HYDRAULIC OIL HOSE. | RR | TDS |  | 09/28/2022 | PA-218S | 4.75 | HRDH-1976
2578 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | PN-9 | Hrs | MRJN-673
2579 | CFST | HCM | 318.75 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 09/28/2022 | PN-9 | 22 | MRJN-673
2580 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | RM-74A | Hrs | HSBH-68
2581 | FOT | RIG | 2 | 28 Sep 0900 - 1100 | 6459 | 902878 | FAULTY 24 VOLT MAIN ENGINE CONTROL SYSTEM BATTERY CHARGER. REPLACE SAME WITH NEW ONE. | RR | PSYS |  | 09/28/2022 | RM-74A | 2 | HSBH-68
2582 | 7001 | 6604 | LOG | E | 4889 | WLT | (OOS) CONT. HES WL RIH W/ 3-1/8" CSG GUN#1, (MAX FORCE ,6 SPF,60 DEG PHASING) ON GR-CCL TO 6604', CORRELATE DEPTH, & PERF. 4-1/2" LNR F/ 6590' T/ 6595'. (5 FT) ( F/ 6600' T/ 6604' ( 4 FT)- HAD GOOD FIRE INDICATION, POH, GUN 100% FIRED, L/D 1ST GUN.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 6590 | HWP | 09/28/2022 | SINO-12L | LOG | HWYH-518
2583 | 7001 | 6588 | LOG | E | 4889 | WLT | (OOS) HPJSM, HES WL RIH W/ 3-1/8" CSG GUN#1, (MAX FORCE ,6 SPF,60 DEG PHASING) ON GR-CCL, CORRELATE DEPTH & PERF. 4-1/2" LNR F/ 6552' T/ 6566'. (14 FT) & F/6578' T/ 6588' (10 FT).- HAD GOOD FIRE INDICATION, POH, GUN 100% FIRED, L/D 2ND GUN.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 6552 | HWP | 09/28/2022 | SINO-12L | LOG | HWYH-518
2584 | 7001 |  | OTH | E | 4889 | NA | (OOS) HPJSM. R/D HES WL TOOLS & EQUIPMENT.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 |  | HWP | 09/28/2022 | SINO-12L | LOG | HWYH-518
2585 | 7001 |  | ND | E | 4889 | SNIP | (OOS) N/D 9-5/8" LTC SHOOTING NIPPLE & NU BELL NIPPLE.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 |  | RIG | 09/28/2022 | SINO-12L | LOG | HWYH-518
2586 | 7001 |  | HT | N |  | PEL | (OOS) R/U 2-3/8" DP POWER TONG & HANDLING TOOLS. | 7001 |  | RIG | 09/28/2022 | SINO-12L | CT | HWYH-518
2587 | 7001 | 2060 | LDP | N |  | STRG | (OOS). M/U & RIH 3-7/8" C/O ASSY. ON 2 3/8" D/P'S T/ 2060'.- FILL STRG & BREAK CIRC. EVERY 10 STD W/ 72 PCF VISCOUS BRINE.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 0 | RIG | 09/28/2022 | SINO-12L | CT | HWYH-518
2588 | 7001 |  | HT | N |  | PEL | (OOS) R/D 2-3/8" DP HANDLING TOOLS. R/U 4"DP HANDLING TOOLS. | 7001 |  | RIG | 09/28/2022 | SINO-12L | CT | HWYH-518
2589 | 7001 |  | HT | N |  | BHA | (OOS). M/U 1 STD X 4" , 4-3/4" JAR , 2 JT'S X 4" HWDP+ 6 STD'S X 4" HWDP. | 7001 |  | RIG | 09/28/2022 | SINO-12L | CT | HWYH-518
2590 | 7001 | 6850 | TI | N |  | STDP | (OOS). CONT. RIH W/ 3-7/8" C/O ASSY. ON 4" D/P'S F/ 2060' T/ 6850'.- FILL STRG & BREAK CIRC. EVERY 20 STD W/ 72 PCF VISCOUS BRINE.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 2060 | RIG | 09/28/2022 | SINO-12L | CT | HWYH-518
2591 | 7001 |  | CIRC | N |  | MPMP | (OOS). SWEEP HOLE & CHC W/ 72 PCF SOLID FREE NACL VISCOUS BRINE. | 7001 |  | RIG | 09/28/2022 | SINO-12L | CT | HWYH-518
2592 | 7001 |  | CIRC | N |  | MPMP | SPOT 15 BBL N-FLOW PILL (72 PCF), FLOW CHECK, WELL STATIC. | 7001 |  | RIG | 09/28/2022 | SINO-12L | CT | HWYH-518
2593 | 7001 | 2270 | LDP | N |  | STRG | POOH W/ 3-7/8" C/O ASSY. ON 4" D/P'S F/ 6850' T/ 2270' WHILE L/D 4" HWDP/ DP.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 7001 | 6850 | RIG | 09/28/2022 | SINO-12L | CT | HWYH-518
2594 | 25.75 | OOS | Category | DOOS ID | PERF | Out of Scope Summary | CAST CBL LOG & PERFORATE 4.5" LINER . | 10 | 4889 | 27 Sep 0200 | 09/28/2022 | SINO-12L | Type | HWYH-518
2595
2596
2597 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SINO-29N | Hrs | SFNY-2005
2598 | PCPF | ARN | 128.25 | 23 Sep 2045 - 0500 | 7202 | 902625 | 4 - 1/2" LINER DIFFERENTIALY STICKING AT CONNECTIONS IN OH, FOUND SHALE CAVINGS IN RETURNS, HOLE NOT STABLE | TH | NA |  | 09/28/2022 | SINO-29N | 24 | SFNY-2005
2599 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SND-2004 | Hrs | BRRI-1148
2600 | FOT | HSL | 133.5 | 22 Sep 0500 - 0500 | 8196 | 902598 | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL. | TF | PLUGN |  | 09/28/2022 | SND-2004 | 24 | BRRI-1148
2601 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SND-2007 | Hrs | AWTD-104001
2602 | TOWC | NPC | 84.5 | 25 Sep 1400 - 0500 | 15230 | 902688 | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF. | TF | JARS |  | 09/28/2022 | SND-2007 | 24 | AWTD-104001
2603 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SND-2008 | Hrs | HRDH-1291
2604 | UVLC | ARM | 46.5 | 27 Sep 0630 - 0500 | 12135 | 902798 | UNEXPECTED LOSSES IN KHUF-B FORMATION | LCIR | NA |  | 09/28/2022 | SND-2008 | 24 | HRDH-1291
2605 | FOT | RIG | .75 | 28 Sep 0200 - 0245 | 5110 | 902918 | TRY TO TEST PACKER FROM KILL LINE HAD PRESS INCREASE SUDDELNLY TO 600 PSI. KILL LINE PLUGGED. | BOP | CTRL |  | 09/28/2022 | SND-2010 | .75 | MNIF-868
2606 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SND-2010 | Hrs | MNIF-868
2607 | FOT | BC | 50 | 26 Sep 1600 - 0200 | 7039 | 902665 | 7.0" SLZXP PACKER DID NOT SHOW ANY INDICATION OF SETTING POOH - BAKER 7" X 9-5/8" SLZXP PKR ASSY LEFT IN THE HOLE | TF | PKR |  | 09/28/2022 | SND-2010 | 15 | MNIF-868
2608 | FOT | RIG | 2.5 | 27 Sep 1800 - 0715 | 7039 | 902818 | HAD MALEFUNCTION IN ROUGH NECK | RR | HSYS |  | 09/28/2022 | SND-2010 | 1.5 | MNIF-868
2609 | UNKN | RIG | 4.5 | 28 Sep 0830 - 1900 | 3985 | 902842 | FORKLIFT OPERATOR TRANSFERE POTABLE DIESEL TANK BY LIFTING IT ON LIFTER AND NOT PULLED IT BY THE PULLING DEVICE. STOP WORKING BY NAODD DIV# 3 SUPERINTENDENT AND HELD STAND DOWN MEETING WITH ALL RIG PERSONNEL. | HSEI | NA |  | 09/28/2022 | SND-2010 | 4.5 | MNIF-868
2610 | FOT | RIG | .75 | 28 Sep 0200 - 0245 | 5110 | 902918 | TRY TO TEST PACKER FROM KILL LINE HAD PRESS INCREASE SUDDELNLY TO 600 PSI. KILL LINE PLUGGED. | BOP | CTRL |  | 09/28/2022 | SND-2010 | .75 | MNIF-868
2611 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SNT-025 | Hrs | SFNY-517
2612 | WTHR | ARM | 34 | 27 Sep 0500 - 1500 | 0 | 902841 | WAIT ON WEATHER FOR BACKLOAD BOATS | WON | NA |  | 09/28/2022 | SNT-025 | 10 | SFNY-517
2613 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SP-120 | Hrs | MNIF-187
2614 | FOT | SCT | 8.5 | 28 Sep 1830 - 0500 | 20500 | 902848 | WORK TO FIX A LEAK FROM A SWIVEL CONNECTION AT COILED TUBING REEL FLUID INLET. | DSF | CTBG |  | 09/28/2022 | SP-120 | 8.5 | MNIF-187
2615 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SP-154 | Hrs | HRDH-457
2616 | XTTE | HCB | 16 | 28 Sep 1300 - 0500 | 4900 | 902917 | HALLIBURTON 7'' STAR GUIDE CEMENT STINGER FAILED TO STING INTO THE 7'' EZSV-CR | TF | RETNR |  | 09/28/2022 | SP-154 | 16 | HRDH-457
2617 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SP-160 | Hrs | DYBN-1
2618 | HERR | RIG | 25.75 | 27 Sep 1030 - 0100 | 3063 | 902673 | WHILE PRESSURE TEST SL LUBRICATOR , PDHMS ENGINEER HAD PRESSURE READING INSIDE TBG . BAKER TROUBLESHOOT SCT , FOUND IT CLOSED & HOLDING PRESSURE . | JF | SFLN |  | 09/28/2022 | SP-160 | 14.5 | DYBN-1
2619 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SP-165 | Hrs | FDHL-146
2620 | LHFL | RIG | 2 | 28 Sep 1430 - 1630 | 11910 | 902845 | LEAK BETWEEN ROTARY HOSE & STANDPIPE, CHANGED GASKET SEAL & PT, OK. | RR | HSYS |  | 09/28/2022 | SP-165 | 2 | FDHL-146
2621 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SP-167 | Hrs | HWYH-74
2622 | FOT | WWD | 22 | 28 Sep 0700 - 0500 | 5824 | 902851 | ATTEMPT TO SET 7" WFD WHIP STOCK SEVERAL TIMES WITHOUT SUCCESS. POOH. | TF | WPSTK |  | 09/28/2022 | SP-167 | 22 | HWYH-74
2623 | FOT | RIG | .5 | 28 Sep 0200 - 0230 | 245 | 902854 | TOPDRIVE LINK HYDRAULIC CLAMPS SLIPPED ON LINKS. ELEVATORS UNABLE TO CLOSE ON PIPE. | RR | TDS |  | 09/28/2022 | SSA-5915 | .5 | RGHB-704
2624 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SSA-5915 | Hrs | RGHB-704
2625 | FOT | RIG | 12.25 | 28 Sep 0500 - 2345 | 188 | 902844 | TDS ELEVATORS HANDLER SHOT PIN FAIL TO FUNCTION | RR | TDS |  | 09/28/2022 | SSA-5915 | 12.25 | RGHB-704
2626 | FOT | RIG | .5 | 28 Sep 0200 - 0230 | 245 | 902854 | TOPDRIVE LINK HYDRAULIC CLAMPS SLIPPED ON LINKS. ELEVATORS UNABLE TO CLOSE ON PIPE. | RR | TDS |  | 09/28/2022 | SSA-5915 | .5 | RGHB-704
2627 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SSA-5969 | Hrs | UTMN-3148
2628 | WC20 | ARM | 188.5 | 19 Sep 0430 - 0500 | 10092 | 902485 | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF. | WCNT | NA |  | 09/28/2022 | SSA-5969 | 24 | UTMN-3148
2629 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SSA-5971 | Hrs | HWYH-1215
2630 | FOT | BLH | 12 | 28 Sep 1700 - 0500 | 13434 | 902853 | CONTROL SET BAKER ROT FL-V LINER HANGER UNABLE TO RIH WITH HANGER AT 12087FT AND 4 1/2" SHOE AT 13434FT DURING CIRCULATION PRIOR RUN IN OPEN HOLE. (7" SHOE AT 13514FT). INDICATION OF PRE MATURE SETTING. ATTEMPTED SEVERAL TIMES TO RIH. NO GO. LINER WAS FREE UP. | TF | HGRL |  | 09/28/2022 | SSA-5971 | 12 | HWYH-1215
2631 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | SSA-5974 | Hrs | HRDH-1979
2632 | CWEL | ARM | 20.5 | 27 Sep 1730 - 1400 | 1648 | 902827 | AFTER CONNECTION STRING GOT STUCK, PRESSURE INCREASED AND NO MOVEMENT UP AND DOWN, HAD CIRCULATION RESTRECTION. | BHS | NA |  | 09/28/2022 | SSA-5974 | 9 | HRDH-1979
2633 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | STY-038 | Hrs | ZULF-2089
2634 | FOT | RIG | 2 | 28 Sep 1630 - 1830 | 2861 | 902846 | WHEN ATTEMPT TO FILL UP OBSERVED A LEAK IN TDS WASHPIPE. CHANE OUT THE SAME | RR | TDS |  | 09/28/2022 | STY-038 | 2 | ZULF-2089
2635 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | WCL-83 | Hrs | MRJN-1002
2636 | WTHR | ARM | 25 | 27 Sep 0500 - 0600 | 0 | 902675 | WAIT ON WEATHER. NOT ABLE TO OFFLOAD BOAT OR USE CRANE TO PICK UP DP'S DUE TO ROUGH SEA AND STRONG WIND. | WON | NA |  | 09/28/2022 | WCL-83 | 1 | MRJN-1002
2637 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/28/2022 | ZPEC-3 | Hrs | SFNY-200
2638 | FOT | RIG | 4 | 28 Sep 0500 - 0900 | 300 | 902877 | WHILE L/D FIRST JOINT 4 1/2" TBG, FOUND RIG TBG TONG JAWS STUCK AROUND TBG BODY, TRIED TO FREE NO SUCCES, SECURED THE WELL AND WORKED TO REPAIR TBG TONG AND FREE IT FROM TBG BODY OK FREE & CHECK TONG NOT FUNCTIONED WELL , REPLACED IT WITH THE BACK-UP ONE. | RR | SLIPS |  | 09/28/2022 | ZPEC-3 | 4 | SFNY-200
2639 | FOT | SPS | 7.5 | 29 Sep 2130 - 0500 | 14011 | 902927 | HALL. SPS MWD TOOLS FAILURE, NO SIGNAL, TROUBLESHOOT, NO SUCCESS. POOH. | BHA | MWD |  | 09/29/2022 | 088TE | 7.5 | QTIF-519
2640 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | 088TE | Hrs | QTIF-519
2641 | FOT | SDM | 56.5 | 27 Sep 0830 - 2130 | 14011 | 902819 | SLB SDM LWD STETHOSCOPE TOOL FAILURE, TROUBLSHOOT SAME, NO SUCCESS, POOH. | BHA | LWD |  | 09/29/2022 | 088TE | 16.5 | QTIF-519
2642 | FOT | SPS | 7.5 | 29 Sep 2130 - 0500 | 14011 | 902927 | HALL. SPS MWD TOOLS FAILURE, NO SIGNAL, TROUBLESHOOT, NO SUCCESS. POOH. | BHA | MWD |  | 09/29/2022 | 088TE | 7.5 | QTIF-519
2643 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ADC-31 | Hrs | ANDR-1006
2644 | FOT | GOC | 9 | 29 Sep 0900 - 1800 | 4560 | 902920 | WHILE RIH 18-5/8" 136# CASING OBSERVED THE RUBBER PACKING NOT GOING INSIDE THE CASING REMOVE THE RUBBER PACKING TO RESUME OPERATION AND OBSERVED CRT SEGMENTS STUCK INSIDE SEVERAL JOINTS. DECIDED TO RIG DOWN CRT AND RIG UP POWER TONG AND SPIDER ELEVATOR TO PROCEED WITH THE JOB. | TF | CTRQ |  | 09/29/2022 | ADC-31 | 9 | ANDR-1006
2645 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ADC-53L | Hrs | HRDH-1530
2646 | LHFL | RIG | 1 | 29 Sep 1730 - 1830 | 8591 | 902924 | LEAK ON WASH PIPE | RR | HSYS |  | 09/29/2022 | ADC-53L | 1 | HRDH-1530
2647 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ADC-55L | Hrs | UTMN-3171
2648 | LCRW | TK3 | 195 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/29/2022 | ADC-55L | 24 | UTMN-3171
2649 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ADC-59L | Hrs | HWYH-1324
2650 | CEDE | TK3 | 149.75 | 22 Sep 0030 - 0500 | 19319 | 902684 | CONT. WIPER TRIP. RIH W/ WBCU ASSAY FROM 16412 FT TO 19,319 FT ON ELEVATOR. NOTE: RUN LOGS TO INVESTIGATE | DRG | NA |  | 09/29/2022 | ADC-59L | 24 | HWYH-1324
2651 | 12861 | 8385 | TI | E | 4892 | STDP | RIH WITH SLB WL MECH CALIPER LOGGING ASSY ON 4" DP STDS F/5,745 FT TO 8,385 FT.- CONTROL RIH SPEED @ 2 MINS SLIP-TO-SLIP.- DRIFT ALL 4" DP STDS WITH 2.375" DRIFT SIZE.- FILL & BREAK CIRC. EVERY 10 STDS.- MONITOR WELL ON TRIP TANK - OK. | 12861 | 5745 | RIG | 09/29/2022 | ADC-62L | LOG | ANDR-589
2652 | 12861 |  | RR | E | 4892 | TDS | SERVICES TOP DRIVE SYSTEM AND CHANGE GRAPPER DIES.- MONITOR WELL ON TRIP TANK - WELL STATIC | 12861 |  | RIG | 09/29/2022 | ADC-62L | LOG | ANDR-589
2653 | 12861 |  | CIRC | E | 4892 | MPMP | CIRCULATE FOR 1.5 STRING VOLUMES. | 12861 |  | RIG | 09/29/2022 | ADC-62L | LOG | ANDR-589
2654 | 12861 |  | OTH | E | 4892 | NA | HPJSM, R/U WL SHEAVES.- M/U CABLE-SIDE ENTRY SUB.- M/U X/OS, DLG LEG REAMER.RIH TO 8,430 FT WITH CABLE.- MONITOR WELL ON TRIP TANK - WELL STATIC | 12861 |  | RIG | 09/29/2022 | ADC-62L | LOG | ANDR-589
2655 | 12861 |  | OTH | E | 4892 | NA | LATCH AS PER SLB WL ENGINEER INSTRUCTION.- CONFIRMED LATCH.- INSTALL CLAMP ON SIDE ENTRY SUB.- PULL TEST AT 3000LBS.- MONITOR WELL ON TRIP TANK - WELL STATIC | 12861 |  | SWL | 09/29/2022 | ADC-62L | LOG | ANDR-589
2656 | 12861 | 12844 | TI | E | 4892 | STDP | RIH TLC CALIPER LOGGING TOOL F/ 8,430 FT TO 12,844 FT.- RUNNING SPEED = 3 MIN/STAND SLIP TO SLIP.- MONITOR THE WELL WITH TRIP TANK.- FILL THE STRING AFTER 10 STDS.- MONITOR WELL ON TRIP TANK - WELL STATIC | 12861 | 8430 | RIG | 09/29/2022 | ADC-62L | LOG | ANDR-589
2657 | 12861 | 8648 | LOG | E | 4892 | WLT | LOG UP WL MULTI ARM CALIPER LOG AS PER SLB WL INSTRUCTION FROM 12,844 FT TO 8,648 FT.- LOGGING SPEED = 3 MINS SLIP-TO-SLIP.- OPEN HOLE IN GOOD CONDITION.- POOH STRING DRY.- MONITOR WELL ON TRIP TANK - WELL STATIC.- FLOW CHECK INSIDE L-1 WINDOW- WELL STATIC. | 12861 | 12844 | SWL | 09/29/2022 | ADC-62L | LOG | ANDR-589
2658 | 12861 |  | OTH | E | 4892 | NA | UNLATCH PWCH & R/D CSES AS PER SLB WL ENG'S INSTRUCTIONS IN PROGRESS.- REMOVE CABLE CLAMP ON CSES.- UNLATCH PWCH FROM LOGGING ASSY.- POOH WET CONNECTION (PWCH )& CABLE TO SURFACE.- L/D CABLE-SIDE ENTRY SUB, X/OS, DL REAMER....... IN PROGRESS AT RPT.- MONITOR WELL ON TRIP TANK - WELL STATIC | 12861 |  | SWL | 09/29/2022 | ADC-62L | LOG | ANDR-589
2659 | 32.5 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | RUN SLB CALLIPER LOG TOOL | 24 | 4892 | 28 Sep 2030 | 09/29/2022 | ADC-62L | Type | ANDR-589
2660
2661
2662 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ADES-889 | Hrs | HRDH-2122
2663 | PCPF | ARM | 325 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/29/2022 | ADES-889 | 23.5 | HRDH-2122
2664 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ADM-266 | Hrs | SFNY-263
2665 | SRVC | APF | 24 | 29 Sep 0500 - 0500 | 0 | 902921 | WAIT ON PROD. TO CONDUCT CORROSION LOG ON SFNY-261 BY ARABIYAH-6 BARGE, THEN BARGE TO SECURE WELL SFNY-259 W/ ME PLUG PRIOR TO RIG MOVE & SAFE APPROACH TO THE PF. | WO | NA |  | 09/29/2022 | ADM-266 | 24 | SFNY-263
2666 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ADM-339 | Hrs | MRJN-3013
2667 | XTRI | RIG | .75 | 29 Sep 0345 - 0430 | 0 | 902930 | EXCESSIVE TIME BUILDING X/O'S TO RUN FMC LOWER STAGE WEAR BUSHING DUE TO POOR PLANNING FROM RIG SIDE. | JF | WH |  | 09/29/2022 | ADM-339 | .75 | MRJN-3013
2668 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ARO-2001 | Hrs | MRJN-121
2669 | WTHR | ARM | 110.25 | 24 Sep 1845 - 0900 | 0 | 902713 | WAIT ON WEATHER TO RIG MOVE TO MRJN 121/126 PF | WON | NA |  | 09/29/2022 | ARO-2001 | 4 | MRJN-121
2670 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | ARO-3003 | Hrs | SFNY-1157
2671 | ETRQ | RIG | 10.5 | 28 Sep 0115 - 1145 | 1308 | 902852 | WHILE CLEANING OUT 24" LANDING COLLAR OBSERVE TDS TORQUE TO 23K FT/LBS. LOST 80K STRING WEIGHT & ALL PUMP PRESSURE INDICATING STRING HAD BACKED OFF. | BHA | BHA |  | 09/29/2022 | ARO-3003 | 6.75 | SFNY-1157
2672 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | DPS-46 | Hrs | SDGM-1111
2673 | FOT | SWL | 11.5 | 29 Sep 0500 - 1630 | 12655 | 902879 | SLB 2.5" RCT TUBING CUTTER FAILED TO CUT TUBING | TF | WLT |  | 09/29/2022 | DPS-46 | 11.5 | SDGM-1111
2674 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | DPS-5 | Hrs | HRDH-1917
2675 | FOT | WDS | 9.5 | 29 Sep 1930 - 0500 | 11719 | 902934 | LOST SIGNAL FROM WFD MWD. TROUBLESHOOTING MWD, NO SUCCESS. | BHA | MWD |  | 09/29/2022 | DPS-5 | 9.5 | HRDH-1917
2676 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | DQ-47 | Hrs | KHRS-1739
2677 | IDPR | BHI | 4 | 29 Sep 0100 - 0500 | 10987 | 902957 | DRILLING W/ CONTROLLED PARAMETERS TO MITIGATE RSS VIBRATIONS. | DD | RSS |  | 09/29/2022 | DQ-47 | 4 | KHRS-1739
2678 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | EXL-IA | Hrs | ABSF-128
2679 | FOT | GEP | 48.5 | 27 Sep 0330 - 0500 | 217 | 902838 | UNABLE TO CLOSE MLC RT PORTS, PRESSURE TEST FAILED ON SAME. | WH | WH |  | 09/29/2022 | EXL-IA | 24 | ABSF-128
2680 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | HI-4 | Hrs | BRRI-1002
2681 | ISEQ | ARM | 1 | 29 Sep 1030 - 1130 | 535 | 902933 | TRIED SEVERAL TIMES TO STING-IN INTO 24" F.SHOE, NO SUCCESS. | TF | ISC |  | 09/29/2022 | HI-4 | 1 | BRRI-1002
2682 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | MP-1 | Hrs | BRRI-310
2683 | WTHR | ARM | 18 | 29 Sep 1100 - 0500 | 0 | 902925 | WOW FOR WATER TIGHT INTEGRITY CHECK & RIG MOVE TO BRRI-129, 134, 310 PF. | WON | NA |  | 09/29/2022 | MP-1 | 18 | BRRI-310
2684 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | NBR-115S | Hrs | SDGM-1221
2685 | FOT | WCR | 2 | 29 Sep 1315 - 1515 | 12845 | 902932 | CRT TOOL NOT GIVING PROPER TORQUE | TF | CTRQ |  | 09/29/2022 | NBR-115S | 2 | SDGM-1221
2686 | FOT | RIG | 9.5 | 29 Sep 1930 - 0500 | 4309 | 902931 | HAD MALFUNCTION IN IRON ROUGHNECK . | RR | SLIPS |  | 09/29/2022 | PA-218S | 9.5 | HRDH-1976
2687 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | PA-218S | Hrs | HRDH-1976
2688 | UVLC | ARM | 284.75 | 16 Sep 2000 - 1930 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/29/2022 | PA-218S | 14.5 | HRDH-1976
2689 | FOT | RIG | 9.5 | 29 Sep 1930 - 0500 | 4309 | 902931 | HAD MALFUNCTION IN IRON ROUGHNECK . | RR | SLIPS |  | 09/29/2022 | PA-218S | 9.5 | HRDH-1976
2690 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SCTD-1 | Hrs | UTMN-3189
2691 | FOT | RIG | 13 | 29 Sep 1600 - 0500 | 0 | 902935 | FAILURE OF E-LINE INSULATION. | RR | EDR |  | 09/29/2022 | SCTD-1 | 13 | UTMN-3189
2692 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SINO-22 | Hrs | BRRI-1144
2693 | FOT | RIG | 1.25 | 29 Sep 2215 - 2330 | 2341 | 902926 | CHANGE TWO LEAKING HYDRAULIC HOSES ON TDS LINK TILT ASSEMBLY WITH NEW HYDRAULIC HOSES. | RR | TDS |  | 09/29/2022 | SINO-22 | 1.25 | BRRI-1144
2694 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SINO-29N | Hrs | SFNY-2005
2695 | PCPF | ARN | 152.25 | 23 Sep 2045 - 0500 | 7202 | 902625 | 4 - 1/2" LINER DIFFERENTIALY STICKING AT CONNECTIONS IN OH, FOUND SHALE CAVINGS IN RETURNS, HOLE NOT STABLE | TH | NA |  | 09/29/2022 | SINO-29N | 24 | SFNY-2005
2696 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SND-2004 | Hrs | BRRI-1148
2697 | FOT | HSL | 157.5 | 22 Sep 0500 - 0500 | 8196 | 902598 | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL. | TF | PLUGN |  | 09/29/2022 | SND-2004 | 24 | BRRI-1148
2698 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SND-2007 | Hrs | AWTD-104001
2699 | TOWC | NPC | 108.5 | 25 Sep 1400 - 0500 | 15230 | 902688 | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF. | TF | JARS |  | 09/29/2022 | SND-2007 | 24 | AWTD-104001
2700 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SND-2008 | Hrs | HRDH-1291
2701 | UVLC | ARM | 70.5 | 27 Sep 0630 - 0500 | 12135 | 902798 | UNEXPECTED LOSSES IN KHUF-B FORMATION | LCIR | NA |  | 09/29/2022 | SND-2008 | 24 | HRDH-1291
2702 | XTRI | RIG | 2.5 | 29 Sep 0030 - 0300 | 4583 | 902959 | EXCESSIVE TIME TO M/UP TEST ASSY AND FLUSH BOP STACK | JF | BOP |  | 09/29/2022 | SP-110 | 2.5 | MNIF-142
2703 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SP-110 | Hrs | MNIF-142
2704 | XTRI | RIG | 3.5 | 29 Sep 1730 - 2100 | 4583 | 902958 | EXCESSIVE TIME TO N/UP 13-5/8" BOPE STACK | JF | BOP |  | 09/29/2022 | SP-110 | 3.5 | MNIF-142
2705 | XTRI | RIG | 2.5 | 29 Sep 0030 - 0300 | 4583 | 902959 | EXCESSIVE TIME TO M/UP TEST ASSY AND FLUSH BOP STACK | JF | BOP |  | 09/29/2022 | SP-110 | 2.5 | MNIF-142
2706 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SP-120 | Hrs | MNIF-187
2707 | FOT | SCT | 15.5 | 28 Sep 1830 - 1200 | 20500 | 902848 | WORK TO FIX A LEAK FROM A SWIVEL CONNECTION AT COILED TUBING REEL FLUID INLET. | TF | CTBG |  | 09/29/2022 | SP-120 | 7 | MNIF-187
2708 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SP-167 | Hrs | HWYH-74
2709 | FOT | WWD | 25.5 | 28 Sep 0700 - 0830 | 5824 | 902851 | ATTEMPT TO SET 7" WFD WHIP STOCK SEVERAL TIMES WITHOUT SUCCESS. POOH. | TF | WPSTK |  | 09/29/2022 | SP-167 | 3.5 | HWYH-74
2710 | HELD | ARM | 6.75 | 29 Sep 2215 - 0500 | 1684 | 902929 | WHILE RIH 13-3/8" CSG, OBSERVED HELD UP AND SLACK OFF WT. 20 KLBS AT 1684', WORKING ON CASING TO PASS HELD UP POINT W/ PUMPING RATE 730 GPM & PRESS-250 PSI, APPLY SLACK WT UP TO 25 KLBS. RECIPROCATE CASING STING UP/DN, NO PROGRESS. . | JF | CSG |  | 09/29/2022 | SSA-101 | 6.75 | QTIF-526
2711 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SSA-101 | Hrs | QTIF-526
2712 | FOT | GOC | 2 | 29 Sep 1430 - 1630 | 208 | 902922 | AL-GHAITH POWER UNIT ENGINE SHUT DOWN. SWITCH TO OTHER POWER UNIT. MEANWHILE ALGHAITH CSG CREW CROSS TIGHT 13 3/8" JTS. L/DN & REPLACE WITH NEW ONE JOINT. | TF | CTRQ |  | 09/29/2022 | SSA-101 | 2 | QTIF-526
2713 | HELD | ARM | 6.75 | 29 Sep 2215 - 0500 | 1684 | 902929 | WHILE RIH 13-3/8" CSG, OBSERVED HELD UP AND SLACK OFF WT. 20 KLBS AT 1684', WORKING ON CASING TO PASS HELD UP POINT W/ PUMPING RATE 730 GPM & PRESS-250 PSI, APPLY SLACK WT UP TO 25 KLBS. RECIPROCATE CASING STING UP/DN, NO PROGRESS. . | JF | CSG |  | 09/29/2022 | SSA-101 | 6.75 | QTIF-526
2714 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SSA-303 | Hrs | HRDH-1989
2715 | HERR | RIG | 5.5 | 29 Sep 2130 - 0300 | 121 | 902956 | EXCESS TIME SPENT ON R/U BELL NIPPLE TO GET IT FIT PROPERLY WITH THE FLOW LINE. | BOP | DVRT |  | 09/29/2022 | SSA-303 | 5.5 | HRDH-1989
2716 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SSA-5868 | Hrs | HRDH-2364
2717 | FOT | HCA | 3.5 | 27 Sep 1430 - 0145 | 9813 | 902876 | AFTER 13-3/8" CSG 1ST STAGE CMT JOB, CHECK FLOAT, FOUND SAME NOT HOLDING. | TF | FS |  | 09/29/2022 | SSA-5868 | 2.5 | HRDH-2364
2718 | FOT | WUD | 9 | 29 Sep 2000 - 0500 | 10092 | 902928 | WFD MPD CHOKE MANIFOLD FAILED TO HOLD PRESSURE WHILE P/T. | BOP | RCD |  | 09/29/2022 | SSA-5969 | 9 | UTMN-3148
2719 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SSA-5969 | Hrs | UTMN-3148
2720 | WC20 | ARM | 203.5 | 19 Sep 0430 - 2000 | 10092 | 902485 | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF. | WCNT | NA |  | 09/29/2022 | SSA-5969 | 15 | UTMN-3148
2721 | FOT | WUD | 9 | 29 Sep 2000 - 0500 | 10092 | 902928 | WFD MPD CHOKE MANIFOLD FAILED TO HOLD PRESSURE WHILE P/T. | BOP | RCD |  | 09/29/2022 | SSA-5969 | 9 | UTMN-3148
2722 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/29/2022 | SSA-5971 | Hrs | HWYH-1215
2723 | FOT | BLH | 33 | 28 Sep 1700 - 0200 | 13434 | 902853 | RIH 4 1/2'' CONTROL SET ROT FL-V LINER HANGER TO 13434 FT TRIED TO CIRCULATE @ 6 BPM PRESSURE INCREASED AND LINER HANGER IT IS SUPPOSED TO BE PREMATURE SET. | TF | HGRL |  | 09/29/2022 | SSA-5971 | 21 | HWYH-1215
2724 | FOT | RIG | 5.75 | 30 Sep 2315 - 0500 | 14011 | 902992 | WHILE P/U SPS 8-1/2" RSS DIR. ASSY. SLIPS DIES DROPPED IN HOLE. | TF | SLIPS |  | 09/30/2022 | 088TE | 5.75 | QTIF-519
2725 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | 088TE | Hrs | QTIF-519
2726 | FOT | SPS | 25.75 | 29 Sep 2130 - 2315 | 14011 | 902927 | HALL. SPS MWD TOOLS FAILURE, NO SIGNAL, TROUBLESHOOT, NO SUCCESS. POOH TO CHANGE TOOLS. | BHA | MWD |  | 09/30/2022 | 088TE | 18.25 | QTIF-519
2727 | FOT | RIG | 5.75 | 30 Sep 2315 - 0500 | 14011 | 902992 | WHILE P/U SPS 8-1/2" RSS DIR. ASSY. SLIPS DIES DROPPED IN HOLE. | TF | SLIPS |  | 09/30/2022 | 088TE | 5.75 | QTIF-519
2728 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADC-17 | Hrs | ZULF-1387
2729 | XBTR | SEC | .5 | 30 Sep 1430 - 1500 | 4879 | 902981 | 16" SECURITY BIT PERFORMANCE WAS VERY POOR | LROP | BIT |  | 09/30/2022 | ADC-17 | .5 | ZULF-1387
2730 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADC-35 | Hrs | MAQL-6
2731 | FOT | RIG | 9.5 | 30 Sep 1930 - 0500 | 248 | 902986 | RIG REPAIR - BAD DECODING BETWEEN TDS AND VFD ( TDS MOTOR ENCODER PROBLEM ). | RR | TDS |  | 09/30/2022 | ADC-35 | 9.5 | MAQL-6
2732 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADC-41L | Hrs | SDGM-1244
2733 | FOT | TK3 | 23 | 26 Jul 0700 - 0500 | 6400 | 900240 | DRILL PIPE PLUGGING | DSF | DP |  | 09/30/2022 | ADC-41L | 11.5 | SDGM-1244
2734 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADC-55L | Hrs | UTMN-3171
2735 | LCRW | TK3 | 219 | 21 Sep 0200 - 0500 | 12503 | 902553 | WHILE DRILLING 7" LANDING COLLAR OBSERVED NO PROGRESS. DECISION WAS TAKEN TO DRY DRILL LC WITH NO PUMPS RESULTING IN BEING STUCK IN LC | STUK | STRG |  | 09/30/2022 | ADC-55L | 24 | UTMN-3171
2736 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADC-56L | Hrs | UTMN-3069
2737 | FOT | SWL | 2.25 | 30 Sep 0000 - 0215 | 14035 | 902987 | UNABLE TO START WIRELINE UNIT. | TF | WLU |  | 09/30/2022 | ADC-56L | 2.25 | UTMN-3069
2738 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADC-58L | Hrs | ABHD-183
2739 | FOT | RIG | 5 | 30 Sep 0000 - 0500 | 0 | 902996 | ATTEMPT TO TEST BOP ANNULAR TO 3000 PSI OFFLINE OBSERVED VISUAL LEAK FROM OFF-DRILLER SIDE SHEAR RAM BONNET | BOP | BOP |  | 09/30/2022 | ADC-58L | 5 | ABHD-183
2740 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADC-59L | Hrs | HWYH-1324
2741 | FOT | TK3 | 173.75 | 22 Sep 0030 - 0500 | 19319 | 902684 | CONT. WIPER TRIP. RIH W/ WBCU ASSAY FROM 16412 FT TO 19,319 FT ON ELEVATOR. NOTE: RUN LOGS TO INVESTIGATE | TF | LINR |  | 09/30/2022 | ADC-59L | 24 | HWYH-1324
2742 | 10794 | 10545 | LOG | E | 4627 | WLT | SLB WL TAKE SAMPLING POINT (USING DUAL PACKER)AS PERR ARAMCO RDD, COMPLETE 3RD SESSION ON SAMPLING POINT AT 10,545 FT AND COLLECT SAMPLE.- FORMATION: LFDR.- HAD STICKING TENDENCY AFTER 1ST SESSION (19 KLB O.PULL)- MONITOR WELL THROUGH TRIP TANK, WELL STATIC.- SAMPLE POINTS COMPLETED: 1 /7.- VIT COMPLETED: 0 /5. | 10794 | 10545 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2743 | 10794 | 10520 | LOG | E | 4627 | WLT | POSITION DUAL PACKER AT 10,520 FT (VIT @10,520'-10,505') AND PERFORM STICK TEST FOR 3, 8 , 15 & 30MIN BEFORE TEST.- WL TOOL MEASURE 4,900 LBF; 5,000 LBF; 10,500 LBF & 13,100LBF ACCORDINGLY. OBSERVE PROGRESSIVE O/P.- PERFORM CORRELATION PASS.- MONITOR WELL THROUGH TRIP TANK, WELL STATIC. | 10794 | 10505 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2744 | 10794 | 10520 | LOG | E | 4627 | WLT | SLB WL PERFORM VIT POINT AS PER ARAMCO RDD- ONE SESSION ON 1ST VIT POINT AT 10,520 FT - 10,505 FT.- FORMATION: LFDR.- HAD STICKING TENDENCY AFTER 1ST SESSION (30 KLB O.PULL), RDD REQUEST MORE SESSION.- DECISION MADE TO MOVE TO NEXT STATION.- MONITOR WELL THROUGH TRIP TANK, WELL STATICSAMPLE POINTS COMPLETED: 0 /7.- VIT COMPLETED: 1/5. | 10794 | 10505 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2745 | 10794 | 10495 | LOG | E | 4627 | WLT | PERFORM STICK TEST FOR 3, 8, 15 & 30 MIN BEFORE CONDUCT VIT / SAMPLE (VIT @ 10,480'-10,495' , SAMPLE @10,495 FT)- WL TOOL MEASURE 4,600 LBF; 6,200 LBF; 8,800 LBF; 12,800LBF ACCORDINGLY.- OBSERVE PROGRESSIVE O/P.- FORMATION: LFDR- MONITOR WELL THROUGH TRIP TANK, WELL STATIC. | 10794 | 10480 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2746 | 10794 | 10495 | LOG | E | 4627 | WLT | SLB WL PERFORM VIT / SAMPLING POINT AS PER ARAMCO RDD.- ONE SESSION ON 2ND VIT POINT AT 10,495 FT - 10,480 FT.- FORMATION: LFDR.- HAD STICKING TENDENCY AFTER 1ST SESSION (28 KLBO.PULL), RDD REQUEST MORE SESSION TO TAKE SAMPLE @10,495 FT- DECISION MADE BY ARAMCO TO MOVE TO NEXT STATION DUE HIGH TENDENCY TO STUCK .- MONITOR WELL THROUGH TRIP TANK, WELL STATIC.- SAMPLE POINTS COMPLETED: 0 /7.- VIT COMPLETED: 2/5. | 10794 | 10480 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2747 | 10794 | 10475 | LOG | E | 4627 | WLT | POSITION DUAL PACKER FOR SAMPLING AT 10,475 FT AND PERFORM STICK TEST FOR 3, 8 , 15 & 30 MIN BEFORE TEST.- WL TOOL MEASURE 4,800 LBF; 14,500 LBF; 17,500 LBF & 28,500 LBF ACCORDINGLY. OBSERVE PROGRESSIVE O/P.- DECISION MADE TO MOVE TO NEXT STATION.- MONITOR WELL THROUGH TRIP TANK, WELL STATIC. | 10794 | 10475 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2748 | 10794 | 10455 | LOG | E | 4627 | WLT | POSITION DUAL PACKER AT 10,470 FT (VIT @10,470'-10,455') AND PERFORM STICK TEST FOR 3, 8 , 15 & 30 MIN BEFORE TEST.- WL TOOL MEASURE 5,200 LBF; 6,300 LBF; 7,700 LBF & 9,000 LBF ACCORDINGLY.- PERFORM SCANNING USING XLD PROBE BEFORE VIT ASPER RDD.- MONITOR WELL THROUGH TRIP TANK, WELL STATIC | 10794 | 10470 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2749 | 10794 | 10455 | LOG | E | 4627 | WLT | SLB WL PERFORM VIT POINT AS PER ARAMCO RDD.- ONE SESSION ON 3RD VIT POINT AT 10,470 FT - 10,455 FT.- FORMATION: LFDR.- HAD STICKING TENDENCY AFTER 1ST SESSION (23 KLB O.PULL), RDD REQUEST MORE SESSION TO COMPLETE VIT.- DECISION MADE TO MOVE TO NEXT STATION.- MONITOR WELL THROUGH TRIP TANK, WELL STATIC.- SAMPLE POINTS COMPLETED: 1/7.- VIT COMPLETED: 2/5. | 10794 | 10470 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2750 | 10794 | 10440 | LOG | E | 4627 | WLT | POSITION DUAL PACKER FOR SAMPLING AT 10,440 FT AND PERFORM STICK TEST FOR 3, 8 , 15 & 30 MIN BEFORE SAMPLING.- WL TOOL MEASURE 4,900 LBF; 4,900 LBF; 6,000 LBF & 6,500 LBF ACCORDINGLY.- PERFORM SCANNING USING XLD PROBE BEFORE SAMPLING, IP.- MONITOR WELL THROUGH TRIP TANK, WELL STATIC | 10794 | 10440 | SWL | 09/30/2022 | ADC-68L | LOG | FDHL-174
2751 | 371.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | OOS OPEN HOLE LOGGING OPERATIONS. | 24 | 4627 | 08 Sep 0300 | 09/30/2022 | ADC-68L | Type | FDHL-174
2752
2753
2754 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADC-70 | Hrs | MRJN-761
2755 | UDWL | BHI | 77.5 | 27 Sep 1100 - 1630 | 455 | 902817 | RECORDED DIR SURVEY, FOUND WELL PATH OPPOSITE TO DIR PLAN. POH, FOUND BHI-MM ALIGNMENT SHIFTED 120 DEG. DECISION MADE TO PERFORM P&A CMT PLUG AND SIDE TRACK 22" OPEN HOLE. | DD | MMOT |  | 09/30/2022 | ADC-70 | 11.5 | MRJN-761
2756 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADES-889 | Hrs | HRDH-2122
2757 | PCPF | ARM | 348.5 | 15 Sep 0100 - 0500 | 10881 | 902524 | MANY ATTEMPTS TO ACCESS L-0-2 WITHOUT SUCCESS DUE TO WASH OUT BELOW 8-3/8" BOW. DECISION MADE TO SIDETRACK WELL. | BHS | NA |  | 09/30/2022 | ADES-889 | 23.5 | HRDH-2122
2758 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADM-266 | Hrs | SFNY-263
2759 | SRVC | APF | 48 | 29 Sep 0500 - 0500 | 0 | 902921 | WAIT ON PROD. ARABIYAH-6 BARGE TO SECURE WELL SFNY-259 W/ ME PLUG PRIOR TO RIG MOVE & SAFE APPROACH TO THE PF. | WO | NA |  | 09/30/2022 | ADM-266 | 24 | SFNY-263
2760 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ADM-337 | Hrs | MRJN-900
2761 | FOT | BCT | 5.75 | 30 Sep 1745 - 2330 | 13019 | 902988 | ATTEMPT TO PRESSURE TEST BAKER CT PUMING LINE WITH N2, NOT HOLDING PRESSURE. | TF | CTPMP |  | 09/30/2022 | ADM-337 | 5.75 | MRJN-900
2762 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | AOD-1 | Hrs | SFNY-4260
2763 | UNKN | RIG | 30 | 29 Sep 1130 - 1730 | 0 | 902939 | INVESTIGATE UNREPORTED INCIDENT ON SEPT 26. | HSEI | NA |  | 09/30/2022 | AOD-1 | 12.5 | SFNY-4260
2764 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ARO-3001 | Hrs | MRJN-3001
2765 | FOT | RIG | 2.5 | 29 Sep 0400 - 0630 | 319 | 902978 | ODS BRAKE SYSTEM | RR | DWKS |  | 09/30/2022 | ARO-3001 | 1.5 | MRJN-3001
2766 | FOT | RIG | 4.5 | 30 Sep 0030 - 0500 | 14186 | 902985 | LEAK ON STAND PIPE LINE. | RR | CSYS |  | 09/30/2022 | ARO-3002 | 4.5 | MRJN-814
2767 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | ARO-3002 | Hrs | MRJN-814
2768 | FOT | RIG | 4.25 | 30 Sep 1745 - 2200 | 14086 | 902984 | NOTICED SHORTAGE OF DRILLING LINE WRAPS ON DRAWWORKS DRUM. | RR | TRVL |  | 09/30/2022 | ARO-3002 | 4.25 | MRJN-814
2769 | FOT | RIG | 4.5 | 30 Sep 0030 - 0500 | 14186 | 902985 | LEAK ON STAND PIPE LINE. | RR | CSYS |  | 09/30/2022 | ARO-3002 | 4.5 | MRJN-814
2770 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | BB-84A | Hrs | ZULF-2054
2771 | UNKN | RIG | 4 | 30 Sep 1700 - 0100 | 52 | 902983 | NEAR MISS - WHILE LAYING DOWN DRILL PIPE FROM DERRICK ELEVATOR HORNS CAME IN CONTACT WITH MONKEY BOARD WHILE STAND WAS BEING LOWERED INTO MOUSE HOLE | HSEI | NA |  | 09/30/2022 | BB-84A | 4 | ZULF-2054
2772 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | DPS-5 | Hrs | HRDH-1917
2773 | FOT | WDS | 18 | 29 Sep 2000 - 1600 | 11719 | 902934 | LOST SIGNAL FROM WFD MWD. TROUBLESHOOTING MWD, NO SUCCESS. | BHA | MWD |  | 09/30/2022 | DPS-5 | 9.5 | HRDH-1917
2774 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | DQ-47 | Hrs | KHRS-1739
2775 | IDPR | BHI | 24 | 29 Sep 0100 - 0100 | 10987 | 902957 | POOH FOR BHA CHECK DUE TO SLOW ROP. | LROP | BHA |  | 09/30/2022 | DQ-47 | 20 | KHRS-1739
2776 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | EXL-IA | Hrs | ABSF-128
2777 | FOT | GEP | 50.25 | 27 Sep 0330 - 0645 | 217 | 902838 | UNABLE TO CLOSE MLC RT PORTS, PRESSURE TEST FAILED ON SAME. | WH | WH |  | 09/30/2022 | EXL-IA | 1.75 | ABSF-128
2778 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | EXL-IVA | Hrs | ZULF-2041
2779 | GRF | RIG | 1.5 | 30 Sep 2045 - 2215 | 6848 | 902982 | OBSERVE TDS RPM DROP TO 0 RPM WHILE DRILLING AT 6,848'. UNABLE TO ROTATE STRING OR BREAK OUT CONNECTION. TROUBLE SHOOT TDS ISSUE. | UPRA | TDS |  | 09/30/2022 | EXL-IVA | 1.5 | ZULF-2041
2780 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | MP-1 | Hrs | BRRI-310
2781 | FOT | RIG | 6 | 30 Sep 0900 - 1500 | 0 | 902942 | UNABLE TO JACK HULL DOWN, STARBOARD LEG JACKING SYSTEM NOT RESPONDING PROPERLY. | RR | PSYS |  | 09/30/2022 | MP-1 | 6 | BRRI-310
2782 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | NBR-654S | Hrs | ANDR-1018
2783 | FRFM | ARM | 21.5 | 29 Sep 1330 - 1100 | 1116 | 902961 | LOSSES DURING PRIMARY CEMENT JOB, UNABLE TO BRIUNG TOC TO SURFACE. | CMT | NA |  | 09/30/2022 | NBR-654S | 6 | ANDR-1018
2784 | FOT | RIG | 10.25 | 30 Sep 1845 - 0500 | 5000 | 902989 | HAD MALFUNCTION IN DRAWWORK EATON BREAK SERVO VALVE. | RR | DWKS |  | 09/30/2022 | PA-218S | 10.25 | HRDH-1976
2785 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | PA-218S | Hrs | HRDH-1976
2786 | UVLC | ARM | 306.75 | 16 Sep 2000 - 1845 | 7387 | 902417 | LOST RETURNS WHILE DRILLING 12" HOLE AT 7387' (HADRIYA RESERVOIR). | LCIR | NA |  | 09/30/2022 | PA-218S | 13.75 | HRDH-1976
2787 | FOT | RIG | 10.25 | 30 Sep 1845 - 0500 | 5000 | 902989 | HAD MALFUNCTION IN DRAWWORK EATON BREAK SERVO VALVE. | RR | DWKS |  | 09/30/2022 | PA-218S | 10.25 | HRDH-1976
2788 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | PN-9 | Hrs | MRJN-673
2789 | FOT | BHI | 1 | 30 Sep 0245 - 0345 | 15677 | 902994 | BAKER HUGHES TOOK EXCCIVE TIME TO PERFORM DOWNLINK. | BHA | LWD |  | 09/30/2022 | PN-9 | 1 | MRJN-673
2790 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SCTD-1 | Hrs | UTMN-3189
2791 | FOT | RIG | 37 | 29 Sep 1600 - 0500 | 0 | 902935 | FAILURE OF E-LINE INSULATION. | RR | EDR |  | 09/30/2022 | SCTD-1 | 24 | UTMN-3189
2792 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SINO-1L | Hrs | KHRS-75
2793 | HMWT | TK1 | 9.5 | 30 Sep 0700 - 1630 | 0 | 902979 | NO SUFFICIENT DRILLING WATER AT RIG SITE DUE TO TRUCKS WATER SUPPLY. | WO | NA |  | 09/30/2022 | SINO-1L | 9.5 | KHRS-75
2794 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SINO-29N | Hrs | SFNY-2005
2795 | PCPF | ARN | 171.25 | 23 Sep 2045 - 0000 | 7202 | 902625 | 4 - 1/2" LINER DIFFERENTIALY STICKING AT CONNECTIONS IN OH, FOUND SHALE CAVINGS IN RETURNS, HOLE NOT STABLE | TH | NA |  | 09/30/2022 | SINO-29N | 19 | SFNY-2005
2796 | 7150 | 6035 | ST | N |  | STDP | RIH 7" EZSV-CR F/ 1,280 T/ 6,035 FT | 7150 | 1280 | RIG | 09/30/2022 | SINO-42L | PA | HWYH-355
2797 | 7150 | 6035 | SET | N |  | BP | SPACE OUT EZSV TOP @ 6,035 FT. BREAK CIRCULATE. SET EZSV-CR @ 6,035 FT. SHEAR EXTENSION SLEEVE. ROTATE 30 R.H TURNS TO FREE THE MANDREL.>> STING-IN & S/D 30 K.LB, CLOSE BOP, P/T ANNULUS T/ 1,300 PSI, GOOD TEST. >> PERFORM INJECTIVITY TEST W/ 3 BPM @ 1,000 PSI>> P/U 15 FT ABOVE EZSV-CR, SPOT 15 BBL HVP.>> POOH 3 STANDS. CLOSE BOP, P/T EZSV-CR T/ 1,300 PSI FOR 10 MIN, HOLD OK. | 7150 | 6035 | HCB | 09/30/2022 | SINO-42L | PA | HWYH-355
2798 | 7150 |  | CIRC | N |  | MPMP | RIH 3 STANDS TO 15 FT ABOVE EZSV, CIRCULATE HVP OUT. HPJSM FOR CMT JOB. | 7150 |  | RIG | 09/30/2022 | SINO-42L | PA | HWYH-355
2799 | 7150 |  | PTST | N |  | RETNR | R/U CIRCULATING HEAD, R/U CMT LINE, P/T SAME T/ 3,000 PSI. | 7150 |  | RIG | 09/30/2022 | SINO-42L | PA | HWYH-355
2800 | 7150 | 6035 | CMP | N |  | SQZ | LINE UP TO CMT UNIT . PERFORMED PA CMT JOB AS PER PROG>> GOT FM LOCKED WITH 1500 PSI , SQUEEZED 0.5 BBLS INTO FM>> VOLUME OF CH & OH BELOW RETAINER: 41.5 BBL>> VOLUME CMT SLURRY PUMPED BELOW EZSV-CR: 42 BBL | 7150 | 6035 | HCM | 09/30/2022 | SINO-42L | PA | HWYH-355
2801 | 7150 |  | PBA | S |  | NA | P & A WITH EZSV @ 6035' & SQUEEZED CMT. | 7150 |  | RIG | 09/30/2022 | SINO-42L | OT | HWYH-355
2802 | 7150 |  | CIRC | N |  | MPMP | CLOSE BOP. REVERSE CIRCULATE 3 STRING VOLUME W/ 5 - 8 BPM @ 1,100 - 800 PSI. HAD 28 BBL CMT IN RETURNS. | 7150 |  | RIG | 09/30/2022 | SINO-42L | PA | HWYH-355
2803 | 7150 |  | CIRC | N |  | MPMP | P/T EZSV-CR T/ 1,300 PSI FOR 10 MIN. SPOT 40 BBL INHIBITED BRINE ON TOP OF EZSV. | 7150 |  | RIG | 09/30/2022 | SINO-42L | PA | HWYH-355
2804 | 7150 |  | CIRC | N |  | MPMP | FLOW CHECK, R/D CMT LINES. | 7150 |  | RIG | 09/30/2022 | SINO-42L | PA | HWYH-355
2805 | 7150 | 3000 | TO | N |  | STDP | POOH MST F/ 6,035 T/ 3,000 FT | 7150 | 6035 | RIG | 09/30/2022 | SINO-42L | PA | HWYH-355
2806 | 7150 | 210 | SET | N |  | RBP | M/U 9-5/8" RTTS PACKER W/ STORM VALVE, SET SAME @ 210 FT, P/T SAME T/ 1,000 PSI OK. RELEASE RUNNING TOOL, CLOSE SBR, P/T RTTS T/ 1,000 PSI OK | 7150 | 0 | HCB | 09/30/2022 | SINO-42L | WH | HWYH-355
2807 | 7150 |  | BOP | N |  | BOP | DISCONNECT EMERGENCY KILL LINE, HUNG UP BOP STACK. | 7150 |  | RIG | 09/30/2022 | SINO-42L | WH | HWYH-355
2808 | 7150 |  | OTH | N |  | NA | DIG 6 FT OF CELLAR: >> CELLAR COMPLETLY FULL WITH HARD CMT.>> PT 13-3/8'' X 9 5/8'' CCA TO 500 PSI, PRESSURE DROP TO 450 PSI, HOLD SAME FOR 30 MINS, NO INJECTIVITY.>> PT 9 5/8'' CSG SEALS AND SLIPS TO 1,000 PSI, HOLD OKAY.>> ALMANSORI INSPECT LANDING BASE & 18 5/8'' CSG, ACCEPTED THICKNESS. | 7150 |  | IWS | 09/30/2022 | SINO-42L | WH | HWYH-355
2809 | 7150 |  | OTH | N | 4948 | NA | HPJSM, OOSS: CHECK 18-5/8'' CONDUCTOR, FOUND SAME SEAL WELDED TO DONUT PLATE BOOTS & COATS HOT TAP 18-5/8'' CONDUCTOR, NO GAS FOUND | 7150 |  | IWS | 09/30/2022 | SINO-42L | WH | HWYH-355
2810 | 7150 |  | OTH | N |  | NA | HOT HED CUT 18 5/8" CASING WINDOW 10'' X 10'' >> ALMANSORY PERFORMED UT INSPECTION FOR 13 3/8" CASING , ACCEPTED. >> FILL ANNULUS WITH CEMENT. >> HOT HED WELED BACK 18 5/8" CASING WINDOW . >> ALMANSORY PERFORMED MPI INSPECTION ALL WELDING AREAS, ACCEPTED | 7150 |  | IWS | 09/30/2022 | SINO-42L | WH | HWYH-355
2811 | 1.5 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | HOT TAPPING | 1.5 | 4948 | 30 Sep 0130 | 09/30/2022 | SINO-42L | Type | HWYH-355
2812
2813
2814 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SND-2004 | Hrs | BRRI-1148
2815 | FOT | HSL | 181.5 | 22 Sep 0500 - 0500 | 8196 | 902598 | UNABLE TO RETRIEVE 4-1/2" HALLIBURTON MONOLOCK PLUG. ATTEMPTS WITH SLICK LINE AND CT RUNS, NO SUCCESS. TRY TO EVALUATE THE OBSTRUCTION WITH LIB'S AND MAGNETS RUNS. DECOMPLETE THE WELL. | TF | PLUGN |  | 09/30/2022 | SND-2004 | 24 | BRRI-1148
2816 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SND-2007 | Hrs | AWTD-104001
2817 | TOWC | NPC | 132.25 | 25 Sep 1400 - 0445 | 15230 | 902688 | WHILE NORMAL DRILLING SUDDENLY PRESSURE DROP 1500 PSI AND TORQUE DROP, JAR TWIST OFF. | TF | JARS |  | 09/30/2022 | SND-2007 | 23.75 | AWTD-104001
2818 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SND-2008 | Hrs | HRDH-1291
2819 | UVLC | ARM | 94.5 | 27 Sep 0630 - 0500 | 12135 | 902798 | UNEXPECTED LOSSES IN KHUF-B FORMATION | LCIR | NA |  | 09/30/2022 | SND-2008 | 24 | HRDH-1291
2820 | FOT | RIG | 4 | 30 Sep 1430 - 1830 | 4583 | 902998 | EXPERIENCED LEAKS ON BOPE STACK WHILE P/T. | BOP | BOP |  | 09/30/2022 | SP-110 | 4 | MNIF-142
2821 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SP-110 | Hrs | MNIF-142
2822 | XTRI | RIG | 4.5 | 30 Sep 0530 - 1000 | 4583 | 902941 | BOPE P/T FAILLURE. INCOMPETENT CREW TO PERFORM BOPE P/T AS PER STANDARDS. | JF | BOP |  | 09/30/2022 | SP-110 | 4.5 | MNIF-142
2823 | FOT | RIG | 2.75 | 30 Sep 1830 - 2115 | 4583 | 902995 | TDS GRAPLE AND SAVER SUB FAILURE. | RR | TDS |  | 09/30/2022 | SP-110 | 2.75 | MNIF-142
2824 | FOT | RIG | 4 | 30 Sep 1430 - 1830 | 4583 | 902998 | EXPERIENCED LEAKS ON BOPE STACK WHILE P/T. | BOP | BOP |  | 09/30/2022 | SP-110 | 4 | MNIF-142
2825 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SSA-101 | Hrs | QTIF-526
2826 | HELD | ARM | 30.75 | 29 Sep 2215 - 0500 | 1684 | 902929 | WHILE RIH 13-3/8" CSG, OBSERVED HELD UP AND SLACK OFF WT. 20 KLBS AT 1684', WORKING ON CASING TO PASS HELD UP POINT W/ PUMPING RATE 730 GPM & PRESS-250 PSI, APPLY SLACK WT UP TO 25 KLBS. RECIPROCATE CASING STING UP/DN, NO PROGRESS. . | JF | CSG |  | 09/30/2022 | SSA-101 | 24 | QTIF-526
2827 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SSA-102 | Hrs | QTIF-752
2828 | PCPF | ARM | 9.25 | 29 Sep 0030 - 1445 | 154 | 902940 | BIT & NBRR BALLED UP. | BB | NA |  | 09/30/2022 | SSA-102 | 5.75 | QTIF-752
2829 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SSA-303 | Hrs | HRDH-1989
2830 | FOT | RIG | 1.5 | 30 Sep 0230 - 0400 | 475 | 902997 | WORKING ON TOP DRIVE MAIN HYD POWER FEED, (BUSTED HYD HOSE). | RR | TDS |  | 09/30/2022 | SSA-303 | 1.5 | HRDH-1989
2831 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SSA-5859 | Hrs | HWYH-1217
2832 | FOT | RIG | 1.25 | 30 Sep 0345 - 0500 | 6755 | 902990 | HAD PROBLEM IN HIGH SPEED CLUTCH FOR DRAW WORKS | RR | DWKS |  | 09/30/2022 | SSA-5859 | 1.25 | HWYH-1217
2833 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SSA-5868 | Hrs | HRDH-2364
2834 | FOT | RIG | 7 | 30 Sep 2200 - 0500 | 9900 | 902991 | > WHILE DRILLING 12" HOLE WITH ROTARY MWD-GR ASSY., HAD LAEKAGE IN IBOP UPPER CONNECTION (QUAIL SHAFT WASH OUT). | RR | TDS |  | 09/30/2022 | SSA-5868 | 7 | HRDH-2364
2835 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SSA-5915 | Hrs | RGHB-704
2836 | FOT | RIG | 1.5 | 30 Sep 0330 - 0500 | 92 | 902993 | WHILE PICKING UP BHA BV-100 TONGS WOULD NOT UNPIN TO ADJUST FOR DIFFERENT TUBULARS | RR | SLIPS |  | 09/30/2022 | SSA-5915 | 1.5 | RGHB-704
2837 | FOT | WUD | 10 | 29 Sep 2000 - 0600 | 10092 | 902928 | WFD MPD CHOKE MANIFOLD FAILED TO HOLD PRESSURE WHILE P/T. | BOP | RCD |  | 09/30/2022 | SSA-5969 | 1 | UTMN-3148
2838 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SSA-5969 | Hrs | UTMN-3148
2839 | WC20 | ARM | 226 | 19 Sep 0430 - 0500 | 10092 | 902485 | WELL START FLOWING @ 10,092 FT WHILE DRILLING 8-3/8" HOLE SECTION WITH 142 PCF. | WCNT | NA |  | 09/30/2022 | SSA-5969 | 22.5 | UTMN-3148
2840 | FOT | WUD | 10 | 29 Sep 2000 - 0600 | 10092 | 902928 | WFD MPD CHOKE MANIFOLD FAILED TO HOLD PRESSURE WHILE P/T. | BOP | RCD |  | 09/30/2022 | SSA-5969 | 1 | UTMN-3148
2841 | FOT | RIG | 6 | 29 Sep 0200 - 0800 | 14560 | 902960 | DRAW WORK ELECTRICAL MOTOR MALFUNCATION AND TROUBLESHOOTING SAME IN PROGRESS. | RR | DWKS |  | 09/30/2022 | SSA-5971 | 3 | HWYH-1215
2842 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 09/30/2022 | SSA-5971 | Hrs | HWYH-1215
2843 | FOT | BLH | 54 | 28 Sep 1700 - 0500 | 14560 | 902853 | RIH 4 1/2'' CONTROL SET ROT FL-V LINER HANGER TO 13434 FT TRIED TO CIRCULATE @ 6 BPM PRESSURE INCREASED AND MANY TRIALS TO GO DOWN WITHOUT PROGRESS. | TF | HGRL |  | 09/30/2022 | SSA-5971 | 21 | HWYH-1215
2844 | FOT | RIG | 6 | 29 Sep 0200 - 0800 | 14560 | 902960 | DRAW WORK ELECTRICAL MOTOR MALFUNCATION AND TROUBLESHOOTING SAME IN PROGRESS. | RR | DWKS |  | 09/30/2022 | SSA-5971 | 3 | HWYH-1215