## Clean Jun-22
seq | Report Date | Rig Name | Well No | Company Name | Date and Time | Time in Hrs | Cummulative Hrs | LT ID | Parent LT ID | LT Type | Cause | Object | Depth | LT Summary
1 | 06/01/2022 | ADC-29 | NYYM-102 | BHI | 31 May 0800 - 0500 | 12.5 | 21.5 | 897252 |  | BHA | FOT | MMOT | 7892 | BHI DIR DRILLING UNABLE TO CATCH THE PLAN WHILE DRILLING 8-1/2" HOLE WITH MOTOR.
2 | 06/01/2022 | ADC-31 | SDGM-1181 | RIG | 01 Jun 0300 - 0500 | 2 | 2 | 897313 |  | RR | FPMP | MPMP | 11349 | LEAKING ON MANIFOLD MODULE SEAL PUMP N#2
4 | 06/01/2022 | ADC-31 | SDGM-1181 | RIG | 31 May 1000 - 1500 | 2 | 7 | 897255 |  | RR | FPMP | MPMP | 10730 | MUD PUMP FAILURE.
5 | 06/01/2022 | ADC-31 | SDGM-1181 | RIG | 01 Jun 0300 - 0500 | 2 | 2 | 897313 |  | RR | FPMP | MPMP | 11349 | LEAKING ON MANIFOLD MODULE SEAL PUMP N#2
7 | 06/01/2022 | ADC-43L | UTMN-3118 | TK3 | 24 May 0715 - 0500 | 24 | 204.5 | 896955 |  | LCIR | FRFM | NA | 6420 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES.
9 | 06/01/2022 | ADC-50 | SFNY-1176 | ARM | 31 May 1345 - 0500 | 2.5 | 6.75 | 897231 |  | JF | HELD | CSG | 410 | CASING HANGED @ 410', WORK CASING WITH MAX S/OFF WEIGHT, 100% FREE-UP, WITH NORMAL P/UP WEIGHT, UNABLE TO PASS HANG DEPTH @ 410', NO PROGRESS. POOH FOR 28" REAMING TRIP.
21 | 06/01/2022 | ADC-53L | UTMN-4069 | BC | 01 Jun 2200 - 0500 | 7 | 7 | 897303 |  | TF | FOT | SCRN | 10376 | RIH BHI LOWER COMPLETIONS AND OBSERVED COMMUNICATION BETWEEN STRING AND ANNULUS. LIKELY GPV FAILURE OR AN EQUILIZER IS OPEN.
45 | 06/01/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 87 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS.
47 | 06/01/2022 | ADC-66L | UTMN-2361 | RIG | 31 May 0200 - 0500 | 24 | 27 | 897264 |  | RR | FOT | TDS | 12311 | OBSERVE ABNORMAL SOUND FROM TDS AFTER KELLY DOWN.
49 | 06/01/2022 | AOD-1 | ZULF-696 | BHI | 01 Jun 0145 - 0245 | 1 | 1 | 897307 |  | BHA | FOT | RSS | 6972 | BHI TROUBLESHOOT RSS-AUTOTRACK, NOT RECEIVING DATA
51 | 06/01/2022 | ARO-4001 | MRJN-538 | BHI | 01 Jun 2030 - 0500 | 8.5 | 8.5 | 897305 |  | BHA | FOT | RSS | 13181 | BHI RSS TOOL HAD BEEN FAILURE DUE TO FAULTY ON TICK SENSOR OF STEERING UNIT.
53 | 06/01/2022 | DPS-74 | NJYN-54 | BLH | 13 Apr 0730 - 0500 | 24 | 1121.25 | 895421 |  | TF | FOT | HGRL | 14010 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION.
55 | 06/01/2022 | HI-9 | BRRI-238 | ARM | 01 Jun 1000 - 0500 | 19 | 19 | 897309 |  | WO | SRVC | NA | 0 | WAITING ON ARABIYAH-3 BARGE TO MOVE OUT OF PLATFORM BRRI-219/238 AFTER SECURING THE WELLS. ONCE ARABIYAH-3 BARGE MOVES OUT FROM BRRI-219/238 PLATFORM, REMOVE THE DEBRIS AS PER DEBRIS LOCATION MENTION IN DEBRIS SURVEY LOCATION RECEIVED ON 31-MAY-2022 AND THAN MOVE THE RIG TO BRRI-219/238 PLATFORM.
57 | 06/01/2022 | JACK-202 | HMYM-844 | RIG | 01 Jun 1330 - 1800 | 4.5 | 4.5 | 897289 |  | RR | FOT | PSYS | 280 | WAIT TO CHANGE FUEL PUMP ON RIG CARRER ENGINE N*2 AND CALIBRATE AND MAINTENANCE BY CATERPILLAR TECHNICIAN.
59 | 06/01/2022 | MP-1 | MRJN-79 | BAW | 01 Jun 1615 - 1645 | .5 | .5 | 897298 |  | TF | FOT | CORL | 5400 | WHILE RIH WITH WIRELINE CORROSION LOG TOOL (EMDEX/GR/CCL ) OBSERVED POWER PACK FLAILURE IN BAKER LOGGING UNIT. TROUBLESHOOT SAME, OBSERVED BACK TO NORMAL.
61 | 06/01/2022 | NBR-263S | QTIF-736 | RIG | 01 Jun 1745 - 1945 | 2 | 2 | 897312 |  | RR | FOT | HSYS | 3130 | MULFUNCTION OF ROUGHNECK DUE TO ELECTRICAL PROBLEM.
63 | 06/01/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 59 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
65 | 06/01/2022 | RM-74A | HSBH-68 | HCA | 31 May 1530 - 0500 | 24 | 31.5 | 897288 |  | TF | FOT | FS | 493 | FAILURE IN CEMENTING PROGRAM RESULTED IN WET SHOE.
67 | 06/01/2022 | SDA | MRJN-732 | HTS | 01 Jun 1500 - 1615 | 1.25 | 1.25 | 897299 |  | TF | FOT | FLR | 0 | OBSEERVED A LEAK AT KNOCK OUT TANK'S DRAIN LINE. REPARED LEAK BY TAKING OUT PORTION OF LINE AND SET BLANK PLUG INTO LINE THAT IS CONNECTING KNOCK OUT TANK (TANK IS STILL ABLE TO DRAIN OUT ANY FLUID THROIUGH SECOND COMPARTMENT).
81 | 06/01/2022 | SINO-25 | MNIF-104 | HSL | 01 Jun 0300 - 0500 | 2 | 2 | 897317 |  | TF | FOT | TPCH | 6287 | HALL UNABLE TO PUNCH 4-1/2" TBG USING DPU PUNCHER, PUNCHER STUCK AT DEPTH 6287
82 | 06/01/2022 | SINO-27N | HWYH-466 | RIG | 01 Jun 0600 - 0730 | 1.5 | 1.5 | 897301 |  | RR | FOT | MPMP | 7456 | DOWN TIME DUE TO RIG REPAIR IN MUD PUMP SUCTION LINE.
84 | 06/01/2022 | SINO-27N | HWYH-466 | WCS | 24 May 0500 - 0500 | 22.5 | 204.25 | 897182 |  | TF | FOT | CHAMP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
85 | 06/01/2022 | SINO-27N | HWYH-466 | RIG | 01 Jun 0600 - 0730 | 1.5 | 1.5 | 897301 |  | RR | FOT | MPMP | 7456 | DOWN TIME DUE TO RIG REPAIR IN MUD PUMP SUCTION LINE.
87 | 06/01/2022 | SINO-7N | FDHL-3 | HWP | 31 May 1000 - 0500 | 19 | 38 | 897248 |  | TF | FOT | WLT | 9870 | AFTER HALL W/L SET STRADDLE PKR AT SAMPLE POINT#1 @9870' (STRADDLE PKR DEPTH), AFTER 20 MIN LOST SIGNAL FROM STRADDLE PKR TOOL (TOTAL PUMP-OUT 15 LTRS WATER), TROUBLESHOOTING TRYING TO RECOVER THE SIGNAL BUT NO SUCCESS.
89 | 06/01/2022 | SND-1201 | KHRS-383 | RIG | 31 May 1100 - 0230 | 19 | 28.5 | 897262 |  | RR | FOT | HSYS | 0 | BOP HOIST MALFUNCTIONED
91 | 06/01/2022 | SND-2002 | WAQR-23 | HLH | 26 May 2000 - 0500 | 24 | 142.5 | 897098 |  | TF | FOT | HGRL | 10330 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES.
93 | 06/01/2022 | SND-3002 | DMMM-601 | WDV | 26 May 1500 - 0500 | 22 | 144 | 897076 |  | TF | FOT | DV | 3880 | WFD DV OPENING PLUG NOT BUMPED AFTER DISPLACMENT.
95 | 06/01/2022 | SP-110 | BRRI-562 | BHI | 31 May 1130 - 0500 | 22.5 | 40 | 897188 |  | BHA | FOT | MWD | 15089 | BAKER GR TOOL NOT WORKING DURING DRLG 8-1/2" L 0-1, RUN A DEDICATED TRIP TO LOG THE MISSED INTERVAL (2,699').
97 | 06/01/2022 | SP-258 | HZEM-450202 | RIG | 01 Jun 1000 - 1400 | 4 | 4 | 897290 |  | RR | FOT | DWKS | 4833 | DRAW WORKS LOW CLUTCH DIAPHRAGM LEAKING
99 | 06/01/2022 | SSA-101 | QTIF-785 | RIG | 01 Jun 1545 - 1900 | 3.25 | 3.25 | 897291 |  | RR | FOT | TDS | 20073 | OBSERVED LEAKAGE IN WASH PIPE
101 | 06/01/2022 | SSA-29 | QTIF-348 | ARM | 27 May 1300 - 0500 | 24 | 133 | 897210 |  | TH | NARW | NA | 12384 | NOT ABLE TO RUN IN OPEN HOLE WITH 4-1/2" OFF BOTTOM LINER
103 | 06/01/2022 | SSA-5859 | HWYH-1222 | CAM | 01 Jun 0600 - 2000 | 11.5 | 11.5 | 897302 |  | WH | FOT | WH | 5620 | FAILURE TO LOCK AND ENERGIZE CAM PACK OFF ASSY ON CHH.
104 | 06/01/2022 | SSA-5865 | ABJF-50 | RIG | 31 May 1900 - 0615 | 1.25 | 11.25 | 897230 |  | MUD | DIMF | NA | 14322 | CIRCULATING SYSTEM WAS NOT PROPERLY CLEAN BEFORE TO START THE MDT OPERATIONS. SURFACE LINE HAVE LCM AND PLUGGED HALLIBURTON LOGGING SCREEN.
106 | 06/01/2022 | SSA-5865 | ABJF-50 | RIG | 01 Jun 0615 - 0330 | 21.25 | 21.25 | 897211 |  | FISH | HERR | BHA | 14322 | UNFORTUNATELY DRILLER DROPPED LOGGING STRING IN HOLE. DISCONNECT TDS WITHOUT PUT SLIPS IN ROTARY TABLE.
107 | 06/01/2022 | SSA-5865 | ABJF-50 | RIG | 31 May 1900 - 0615 | 1.25 | 11.25 | 897230 |  | MUD | DIMF | NA | 14322 | CIRCULATING SYSTEM WAS NOT PROPERLY CLEAN BEFORE TO START THE MDT OPERATIONS. SURFACE LINE HAVE LCM AND PLUGGED HALLIBURTON LOGGING SCREEN.
109 | 06/01/2022 | SSA-5964 | HRDH-1383 | RIG | 01 Jun 0500 - 0500 | 24 | 24 | 897232 |  | UPRA | OTH | NA | 0 | EXCEEDED PLANNED RIG MAINTENANCE DAYS. WAITING ON TOP DRIVE, KILL LINE, CHOKE LINE PARTS AND DIESEL ENGINE# 4 REPAIR PARTS FOR COOLING SYSTEM.
111 | 06/01/2022 | T217 | UTMN-314 | RIG | 01 Jun 0500 - 0500 | 24 | 24 | 897300 |  | DSF | HERR | DP | 0 | HAD OBSTRUCTION @ 5148' AND THE DRILLER FAILED TO STOP EARLY & APPLIED SLACK FROM TDS WEIGHT ON THE STRING WHICH LED TO BENT THE TOP SINGLE OF 4" DP'S AND PARTIAL DAMAGE OF TDS SAVER SUB THREAD.
113 | 06/01/2022 | T218 | UTMN-1281 | EMC | 31 May 0945 - 0500 | 21.5 | 40.75 | 897268 |  | STUK | IPDF | DC | 7294 | STUCK PIPE WHILE WASH-UP
114 | 06/01/2022 | T902 | HZEM-162404 | RIG | 31 May 0715 - 0300 | 22 | 43.25 | 897254 |  | RR | FOT | TDS | 8708 | WHILE BACK REAMING OOH STRING BECAME STUCK DUE TO TDS NOT WORKING PROPERLY
116 | 06/01/2022 | T902 | HZEM-162404 | SDM | 30 May 0630 - 0500 | 2 | 24.25 | 897134 |  | DD | UDWL | RSS | 13416 | SLB NEO STEER COULDEN'T HOLD REQIURED INCLINATION.
117 | 06/01/2022 | T902 | HZEM-162404 | RIG | 31 May 0715 - 0300 | 22 | 43.25 | 897254 |  | RR | FOT | TDS | 8708 | WHILE BACK REAMING OOH STRING BECAME STUCK DUE TO TDS NOT WORKING PROPERLY
119 | 06/01/2022 | WCL-83 | MRJN-834 | SWL | 31 May 0030 - 0545 | .75 | 5.25 | 897271 |  | TF | FOT | PLT | 8975 | SLB WL MDT PACKER NOT ABLE TO SEAL PROPERLY. POOH & FOUND METAL DEBRIS ON THE PACKER ELEMENT. CHANGED TO BACK UP PACKER & RIH.
120 | 06/02/2022 | ADC-31 | SDGM-1181 | RIG | 02 Jun 0245 - 0500 | 2.25 | 2.25 | 897378 |  | RR | FOT | CSYS | 11531 | CHANGE MUD PUMP# 2 PISTON
122 | 06/02/2022 | ADC-31 | SDGM-1181 | RIG | 02 Jun 0745 - 1430 | 6.75 | 6.75 | 897371 |  | RR | FOT | CSYS | 11387 | ROTARY HOSE DEVELOPED BODY LEAK. POOH TO SHOE. CHANGE & P/T SAME. RIH TO BOTTOM.
123 | 06/02/2022 | ADC-31 | SDGM-1181 | RIG | 02 Jun 1515 - 1700 | 1.75 | 1.75 | 897372 |  | RR | FOT | MPMP | 11494 | REPAIR ON MUD PUMP SCREEN COUPLING.
124 | 06/02/2022 | ADC-31 | SDGM-1181 | RIG | 02 Jun 2300 - 0030 | 1.5 | 1.5 | 897373 |  | RR | FOT | MPMP | 11495 | REPAIR ON MUD PUMP# 2: MANIFOLD MODULE SEAL LEAKING, CHANGE SEAL.
125 | 06/02/2022 | ADC-31 | SDGM-1181 | RIG | 02 Jun 0245 - 0500 | 2.25 | 2.25 | 897378 |  | RR | FOT | CSYS | 11531 | CHANGE MUD PUMP# 2 PISTON
127 | 06/02/2022 | ADC-43L | UTMN-3118 | TK3 | 24 May 0715 - 1500 | 10 | 214.5 | 896955 |  | LCIR | FRFM | NA | 6420 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES.
129 | 06/02/2022 | ADC-50 | SFNY-1176 | ARM | 31 May 1345 - 0815 | 3.25 | 10 | 897231 |  | JF | HELD | CSG | 410 | CASING HANGED @ 410', WORK CASING WITH MAX S/OFF WEIGHT, 100% FREE-UP, WITH NORMAL P/UP WEIGHT, UNABLE TO PASS HANG DEPTH @ 410', NO PROGRESS. POOH FOR 28" REAMING TRIP.
138 | 06/02/2022 | ADC-53L | UTMN-4069 | BC | 01 Jun 2200 - 0500 | 24 | 31 | 897303 |  | TF | FOT | SCRN | 10376 | RIH BHI LOWER COMPLETIONS AND OBSERVED COMMUNICATION BETWEEN STRING AND ANNULUS. LIKELY GPV SHOE FAILURE OR AN EQUILIZER IS OPEN.
143 | 06/02/2022 | ADC-57L | FDHL-158 | TK3 | 02 Jun 1100 - 0500 | 17.25 | 17.25 | 897374 |  | BHA | IBHA | BHA | 0 | WHIPSTOCK HIGH FLOW BY-PASS VOLVE CLOSE AT LOWER FLOW RATE THAN PLANNED.
145 | 06/02/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 111 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS.
147 | 06/02/2022 | ADC-66L | UTMN-2361 | RIG | 31 May 0200 - 2030 | 15.5 | 42.5 | 897264 |  | RR | FOT | TDS | 12311 | OBSERVE ABNORMAL SOUND FROM TDS AFTER KELLY DOWN.
149 | 06/02/2022 | ADES-889 | HRDH-1858 | BC | 02 Jun 1700 - 0500 | 12 | 12 | 897386 |  | TF | FOT | PBR | 13468 | AFTER STING IN WITH BAKER SEALS INTO PBR, P/T TBG & TCA MANY TIMES NOT HOLD.
151 | 06/02/2022 | ADM-511 | MRJN-799 | BAW | 02 Jun 0245 - 0500 | 2.25 | 2.25 | 897389 |  | TF | FOT | WLT | 12050 | WHILE CARRYING OUT PUMP OUT WITH BAKER PCL LOGGING TOOL STRING RUN#3, TOOL STOP FUNCTIONING, TROUBLESHOOTING SAME, NO SUCCESS, POOH TO CHANGE OUT WITH BACK UP TOOL.
153 | 06/02/2022 | AOD-1 | ZULF-696 | BHI | 02 Jun 1830 - 1930 | 1 | 1 | 897391 |  | BHA | FOT | RSS | 7715 | AUTOTRACK NOT SENDING/RECIEVING DOWNLINK COMMANDS.
155 | 06/02/2022 | AOD-11 | SFNY-4280 | BCM | 02 Jun 2215 - 2245 | .5 | .5 | 897377 |  | CMT | FOP | TOP | 7804 | BAKER CEMENT UNIT COULDN'T PERFORM FLY MIX ON LEAD SLURRY.
156 | 06/02/2022 | ARO-4001 | MRJN-538 | RIG | 02 Jun 0015 - 0345 | 3.5 | 3.5 | 897376 |  | RR | LHFL | HSYS | 13684 | HAD LEAK OF HYDRALIC FLUID ON TDS SERVICE LOOP.
158 | 06/02/2022 | ARO-4001 | MRJN-538 | BHI | 01 Jun 2045 - 2000 | 15 | 23.25 | 897305 |  | BHA | FOT | RSS | 13181 | BHI RSS TOOL GOT FAILURE DUE TO FAULTY ON TICK SENSOR OF STEERING UNIT.
159 | 06/02/2022 | ARO-4001 | MRJN-538 | RIG | 02 Jun 0015 - 0345 | 3.5 | 3.5 | 897376 |  | RR | LHFL | HSYS | 13684 | HAD LEAK OF HYDRALIC FLUID ON TDS SERVICE LOOP.
161 | 06/02/2022 | BB-84A | MRJN-586 | HCO | 31 May 1545 - 0500 | 9 | 39.75 | 897253 |  | JF | DSFT | PKR | 7566 | MULE SHOE HUNG UP ON TOP OF WHIP STOCK AT 7,566'
163 | 06/02/2022 | DPS-74 | NJYN-54 | BLH | 13 Apr 0730 - 0500 | 24 | 1145.25 | 895421 |  | TF | FOT | HGRL | 14010 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION.
165 | 06/02/2022 | HI-9 | BRRI-238 | ARM | 01 Jun 1000 - 0500 | 24 | 43 | 897309 |  | WO | SRVC | NA | 0 | WAITING ON ARABIYAH-3 BARGE TO MOVE OUT OF PLATFORM BRRI-219/238 AFTER SECURING THE WELLS. ONCE ARABIYAH-3 BARGE MOVES OUT FROM BRRI-219/238 PLATFORM, REMOVE THE DEBRIS AS PER DEBRIS LOCATION MENTION IN DEBRIS SURVEY LOCATION RECEIVED ON 31-MAY-2022 AND THAN MOVE THE RIG TO BRRI-219/238 PLATFORM.
167 | 06/02/2022 | JACK-202 | HMYM-844 | RIG | 30 May 1900 - 0500 | 24 | 77.5 | 897261 |  | FISH | HERR | BHA | 3341 | LOST IN HOLE HAND OF 5" SLIPS WHILE THE TRAVELLING BLOCK FALL DOWN ON RIG FLOOR.
169 | 06/02/2022 | NA-128S | SAHB-28 | OTH | 02 Jun 0330 - 0500 | 1.5 | 1.5 | 897382 |  | WO | SRVC | NA | 15733 | STOP DRILLING @ 15733' AS PER GOC INSTRUCTION DUE TO V-SAT DOWN SINCE 05/31/2022 @ 19:00HRS & NO DATA TRANSMISSION FROM RIG TO GOC. CIRC WHILE WAITING ON GOC INSTRUCTION.
171 | 06/02/2022 | NA-207S | SHYB-132 | SWL | 30 May 0700 - 0500 | 24 | 94 | 897256 |  | WO | SRVC | NA | 15000 | SLB E.LINE ASSIGNED COMPANY UNABLE TO PROVIDE REQUIRED SERVICES (MPC).
172 | 06/02/2022 | NBR-20S | HMYM-433504 | RIG | 02 Jun 2230 - 2330 | 1 | 1 | 897388 |  | RR | FPMP | MPMP | 9060 | RELIEF VALVES ON MUD PUMP #2 & #3 LEAKING.
174 | 06/02/2022 | NBR-20S | HMYM-433504 | RIG | 02 Jun 2000 - 2230 | 2.5 | 2.5 | 897387 |  | RR | FOT | DWKS | 9060 | LOW PRESSURE ON DRAWWORKS OIL LUBE.
175 | 06/02/2022 | NBR-20S | HMYM-433504 | RIG | 02 Jun 2230 - 2330 | 1 | 1 | 897388 |  | RR | FPMP | MPMP | 9060 | RELIEF VALVES ON MUD PUMP #2 & #3 LEAKING.
177 | 06/02/2022 | NBR-654S | HRDH-1150 | RIG | 02 Jun 1730 - 2100 | 3.5 | 3.5 | 897375 |  | RR | FOT | TDS | 171 | TROUBLESHOOT TDS LINK/TILT SYSTEM. CHANGED OUT INPUT MODULE BUT PROBLEM PERSISTED. AFTER FURTHER INSPECTION IT WAS DISCOVERED THAT DIFFERENT INPUT MODULE HAD COME LOOSE. THE INPUT MODULE WAS FULLY REINSERTED AND TIE WRAPPED IN PLACE.
179 | 06/02/2022 | NBR-797S | UTMN-3130 | RIG | 02 Jun 0730 - 1830 | 11 | 11 | 897370 |  | RR | FOT | TDS | 12176 | ERRATIC TORQUE READING FROM TOP DRIVE
181 | 06/02/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 83 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
183 | 06/02/2022 | RBP-50A | KARN-51 | HSL | 02 Jun 2100 - 2200 | 1 | 1 | 897381 |  | TF | FOT | SLICK | 0 | SLICKLINE SPILT AT TOP OF LUBRICATOR
185 | 06/02/2022 | RM-74A | HSBH-68 | HCM | 31 May 1530 - 0500 | 24 | 55.5 | 897288 |  | CMT | WSHO | CSG | 493 | FAILURE IN CEMENTING OPERATION RESULTED IN WET SHOE.
194 | 06/02/2022 | SINO-25 | MNIF-104 | HSL | 01 Jun 0300 - 0900 | 4 | 6 | 897317 |  | TF | FOT | TPCH | 6287 | HALL UNABLE TO PUNCH 4-1/2" TBG USING DPU PUNCHER, PUNCHER STUCK AT DEPTH 6287'.
196 | 06/02/2022 | SINO-27N | HWYH-466 | WCS | 24 May 0500 - 0500 | 24 | 228.25 | 897182 |  | TF | FOT | CHAMP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
198 | 06/02/2022 | SINO-7N | FDHL-3 | HWP | 31 May 1000 - 0500 | 23.5 | 61.5 | 897248 |  | TF | FOT | WLT | 9870 | AFTER HALL W/L SET STRADDLE PKR AT SAMPLE POINT#1 @9870' (STRADDLE PKR DEPTH), AFTER 20 MIN LOST SIGNAL FROM STRADDLE PKR TOOL (TOTAL PUMP-OUT 15 LTRS WATER), TROUBLESHOOTING TRYING TO RECOVER THE SIGNAL BUT NO SUCCESS.
200 | 06/02/2022 | SND-3002 | DMMM-601 | WDV | 26 May 1500 - 0500 | 24 | 168 | 897076 |  | TF | FOT | DV | 3880 | WFD DV OPENING PLUG NOT BUMPED AFTER DISPLACMENT.
202 | 06/02/2022 | SNT-025 | SFNY-956 | SPL | 01 Jun 0000 - 1630 | 11.5 | 16.5 | 897330 |  | TF | FOT | SLICK | 3692 | SAPESCO SLICK LINE PX PLUG STUCK IN THE X-NIPPLE.
203 | 06/02/2022 | SP-110 | BRRI-562 | ITS | 02 Jun 0015 - 0145 | 1.5 | 1.5 | 897379 |  | TF | HERR | TTRQ | 993 | ITS NPT DUE TO OVERTORQUED CSG AND LED TO DAMAGE 3 JTS.
205 | 06/02/2022 | SP-110 | BRRI-562 | BHI | 31 May 1130 - 1615 | 5.5 | 45.5 | 897188 |  | BHA | FOT | MWD | 15089 | BAKER GR TOOL NOT WORKING DURING DRLG 8-1/2" L 0-1, RUN A DEDICATED TRIP TO LOG THE MISSED INTERVAL (2,699').
206 | 06/02/2022 | SP-110 | BRRI-562 | ITS | 02 Jun 0015 - 0145 | 1.5 | 1.5 | 897379 |  | TF | HERR | TTRQ | 993 | ITS NPT DUE TO OVERTORQUED CSG AND LED TO DAMAGE 3 JTS.
208 | 06/02/2022 | SP-120 | MNIF-188 | ARM | 02 Jun 1330 - 1430 | 1 | 1 | 897369 |  | TF | FOT | COMP | 20515 | LOST V-SAT COMMUNICATION, COMMUNICATED V-SAT TEAM TO FIX IT.
210 | 06/02/2022 | SP-258 | HZEM-450202 | ARM | 01 Jun 1400 - 0500 | 23.5 | 34.5 | 897328 |  | TF | FOT | CSG | 4833 | AFTER PULL OUT WITH 13 3/8" CASING FOUND OUT 4 EA BOW CENTS & 2 STOP COLLARS LEFT IN HOLE.
212 | 06/02/2022 | SSA-29 | QTIF-348 | ARM | 27 May 1300 - 0500 | 24 | 157 | 897210 |  | TH | NARW | NA | 12384 | NOT ABLE TO RUN IN OPEN HOLE WITH 4-1/2" OFF BOTTOM LINER
214 | 06/02/2022 | SSA-303 | HRDH-2306 | RIG | 02 Jun 1700 - 2030 | 3.5 | 3.5 | 897385 |  | RR | FOT | SLIPS | 9886 | EXCESS TIME DUE TO SLOW RIH USING RIG TONGS MEANWHILE FIXING BROKEN ROUGHNECK.
216 | 06/02/2022 | SSA-5964 | HRDH-1383 | RIG | 01 Jun 0500 - 0500 | 24 | 48 | 897232 |  | UPRA | OTH | NA | 0 | EXCEEDED PLANNED RIG MAINTENANCE DAYS. WAITING ON TOP DRIVE AND DIESEL ENGINE# 4 REPAIR PARTS FOR COOLING SYSTEM.
218 | 06/02/2022 | T217 | UTMN-314 | RIG | 01 Jun 0500 - 1400 | 7 | 31 | 897300 |  | DSF | HERR | DP | 0 | HIT OBSTRUCTION @ 5148' WHILE RIH.
220 | 06/02/2022 | T218 | UTMN-1281 | EMC | 31 May 0945 - 2115 | 16.25 | 57 | 897268 |  | STUK | IPDF | DC | 7294 | STUCK PIPE WHILE WASH-UP
221 | 06/02/2022 | T902 | HZEM-162404 | RIG | 02 Jun 2300 - 0500 | 6 | 6 | 897380 |  | UPRA | OTH | NA | 13416 | SEVER OIL LEAK ON TDS HYDRAULIC SYSTEM.
223 | 06/02/2022 | T902 | HZEM-162404 | SDM | 30 May 0630 - 2300 | 18 | 42.25 | 897134 |  | DD | UDWL | RSS | 13416 | SLB NEO STEER COULDEN'T HOLD REQIURED INCLINATION.
224 | 06/02/2022 | T902 | HZEM-162404 | RIG | 02 Jun 2300 - 0500 | 6 | 6 | 897380 |  | UPRA | OTH | NA | 13416 | SEVER OIL LEAK ON TDS HYDRAULIC SYSTEM.
225 | 06/03/2022 | ADC-31 | SDGM-1181 | RIG | 03 Jun 1100 - 1630 | 5.5 | 5.5 | 897492 |  | RR | FOT | MPMP | 11558 | RIG BLACKED OUT WITH MP-3 SHORT CIRCUIT. REPAIR ELECTRIC PLUG. REPAIR WASH OUT ON MP-2 5-WAY BLOCK.
227 | 06/03/2022 | ADC-31 | SDGM-1181 | RIG | 03 Jun 0730 - 0900 | 1.5 | 1.5 | 897472 |  | RR | FOT | CSYS | 11558 | REPAIR DISCONNECTED SUCTION LINE FOR MP-3.
228 | 06/03/2022 | ADC-31 | SDGM-1181 | RIG | 03 Jun 0900 - 0930 | .5 | .5 | 897491 |  | RR | FOT | DWKS | 11558 | OSHETA BREAK SELF-ENGAGING & LOCKED DRAWWORKS. RESET SAME.
229 | 06/03/2022 | ADC-31 | SDGM-1181 | RIG | 03 Jun 1100 - 1630 | 5.5 | 5.5 | 897492 |  | RR | FOT | MPMP | 11558 | RIG BLACKED OUT WITH MP-3 SHORT CIRCUIT. REPAIR ELECTRIC PLUG. REPAIR WASH OUT ON MP-2 5-WAY BLOCK.
231 | 06/03/2022 | ADC-43L | UTMN-3118 | TK3 | 03 Jun 1000 - 0500 | 15.25 | 15.25 | 897434 |  | LCIR | UXDF | NA | 7199 | WHILE DRILLING LOST COMPLETE RETURNS IN HANIFA FORMATION. PUMPING 3 X LCM PILLS TO CURE THE LOSSES WITHOUT SUCCESS.
239 | 06/03/2022 | ADC-53L | UTMN-4069 | BC | 01 Jun 2200 - 0500 | 24 | 55 | 897303 |  | TF | FOT | SCRN | 10376 | RIH BHI LOWER COMPLETIONS AND OBSERVED COMMUNICATION BETWEEN STRING AND ANNULUS. LIKELY GPV SHOE FAILURE OR AN EQUILIZER IS OPEN.
244 | 06/03/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 135 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS.
246 | 06/03/2022 | ADES-889 | HRDH-1858 | BC | 02 Jun 1700 - 0500 | 15 | 27 | 897386 |  | TF | FOT | PBR | 13468 | AFTER STING IN WITH BAKER SEALS INTO PBR, P/T TBG & TCA - NOT HOLD.
248 | 06/03/2022 | ADM-337 | MRJN-900 | RIG | 03 Jun 0730 - 0745 | .25 | .25 | 897473 |  | RR | FOT | RSSS | 13019 | PRE ALARM FOR EMERGENCY GENERATOR CO2 SYSTEM ACTIVATED, DUE TO A LOOSE LATCH (WRONG BOLT SIZE) IN THE CO2 ACTIVATION CABINET DOOR THAT RESULTED IN SLIGHT OPENING OF THE CABINET DOOR.
250 | 06/03/2022 | ADM-511 | MRJN-799 | BAW | 02 Jun 0245 - 0500 | 24 | 26.25 | 897389 |  | TF | FOT | WLT | 12050 | WHILE CARRYING OUT PUMP OUT WITH BAKER PCL LOGGING TOOL STRING RUN#3, TOOL STOP FUNCTIONING, TROUBLESHOOTING SAME, NO SUCCESS, POOH TO CHANGE OUT WITH BACK UP TOOL.
252 | 06/03/2022 | ARO-3004 | MRJN-2060 | RIG | 02 Jun 0700 - 1700 | 12 | 31 | 897392 |  | UPRA | GRF | DWKS | 8114 | AS DRILLER WORKED STRING UP ALLOWING SLUG TO FALL, HIGH DRUM CLUTCH SLIPPED ALLOWING BLOCKS TO TRAVEL TO RIG FLOOR
254 | 06/03/2022 | BB-84A | MRJN-586 | HCO | 31 May 1545 - 0500 | 24 | 85 | 897253 |  | JF | DSFT | PKR | 7566 | MULE SHOE HUNG UP ON TOP OF WHIP STOCK AT 7,566'
256 | 06/03/2022 | DPS-74 | NJYN-54 | BLH | 13 Apr 0730 - 0500 | 24 | 1169.25 | 895421 |  | TF | FOT | HGRL | 14010 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION.
278 | 06/03/2022 | HI-9 | BRRI-238 | ARM | 03 Jun 0500 - 0500 | 24 | 24 | 897435 |  | WO | SRVC | NA | 0 | RIG WAITING FOR RIG MOVE TO BRRI-219/238 PLATFORM, RIG WILL MOVE AFTER COMPLETION OF BRRI-219 WELL KILLING AND SECURING BY WELL SERVICES.
280 | 06/03/2022 | JACK-202 | HMYM-844 | RIG | 30 May 1900 - 0500 | 24 | 101.5 | 897261 |  | FISH | HERR | BHA | 3341 | LOST IN HOLE HAND OF 5" SLIPS WHILE THE TRAVELLING BLOCK FALL DOWN ON RIG FLOOR.
282 | 06/03/2022 | NBR-20S | HMYM-433504 | RIG | 03 Jun 0345 - 0500 | 1.25 | 1.25 | 897493 |  | RR | FOT | TDS | 11340 | WASH PIPE LEAKING
284 | 06/03/2022 | NBR-654S | HRDH-1150 | RIG | 03 Jun 0715 - 0945 | 2.5 | 2.5 | 897431 |  | RR | FOT | DWKS | 214 | REPAIR ON MARTIN DECKER. - FIX EZY TORQUE OIL LEAKS. - CHANGE MARTIN DECKER.
286 | 06/03/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 95 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
288 | 06/03/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 107 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
290 | 06/03/2022 | PA-785S | QTIF-269 | RIG | 19 May 2030 - 0800 | 1.75 | 16.25 | 896796 |  | BHA | HERR | HWDP | 0 | WRONG PIPE TALLY FROM RIG.
291 | 06/03/2022 | RM-74A | HSBH-68 | RIG | 03 Jun 1800 - 0300 | 9 | 9 | 897451 |  | RR | FOT | FL | 500 | INSTALL HCR VALVE ON TRIP TANK LINE TO BIG BORE DIVERTER.
293 | 06/03/2022 | RM-74A | HSBH-68 | HCM | 31 May 1530 - 0500 | 15 | 70.5 | 897288 |  | CMT | WSHO | CSG | 493 | FAILURE IN CEMENTING OPERATION RESULTED IN WET SHOE.
294 | 06/03/2022 | RM-74A | HSBH-68 | RIG | 03 Jun 1800 - 0300 | 9 | 9 | 897451 |  | RR | FOT | FL | 500 | INSTALL HCR VALVE ON TRIP TANK LINE TO BIG BORE DIVERTER.
300 | 06/03/2022 | SINO-11 | HWTH-62 | APC | 02 Jun 0100 - 0700 | 2 | 6 | 897393 |  | WO | WOTO | NA | 6287 | WHILE M/U AND RIH ESP ASSY APC ENGINEER CHECK CABLE INTEGRITY, NO READING.
316 | 06/03/2022 | SINO-27N | HWYH-466 | WCS | 24 May 0500 - 0500 | 24 | 252.25 | 897182 |  | TF | FOT | CHAMP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
318 | 06/03/2022 | SINO-43L | HWYH-2528 | BHI | 03 Jun 1500 - 0500 | 14 | 14 | 897432 |  | BHA | FOT | MMOT | 6936 | WHILE ROTARY DRILLING, OBSERVED SUDDEN DROP IN PRESSURE & TORQUE TO OFF-BTM VALUES. ATTEMPTED TO CONTINUE DRILLING ON ROTARY/SLIDE MODE WITH NO PROGRESS DUE TO BHI MUD MOTOR FAILURE.
320 | 06/03/2022 | SINO-7N | FDHL-3 | HWP | 31 May 1000 - 0530 | .5 | 62 | 897248 |  | TF | FOT | WLT | 9870 | AFTER HALL W/L SET STRADDLE PKR AT SAMPLE POINT#1 @9870' (STRADDLE PKR DEPTH), AFTER 20 MIN LOST SIGNAL FROM STRADDLE PKR TOOL (TOTAL PUMP-OUT 15 LTRS WATER), TROUBLESHOOTING TRYING TO RECOVER THE SIGNAL BUT NO SUCCESS.
322 | 06/03/2022 | SND-2002 | WAQR-23 | HLH | 26 May 2000 - 0500 | 24 | 190.5 | 897098 |  | TF | FOT | HGRL | 10330 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES.
324 | 06/03/2022 | SP-258 | HZEM-450202 | ARM | 01 Jun 1400 - 0200 | 21 | 55.5 | 897328 |  | TF | FOT | CSG | 4833 | AFTER PULL OUT WITH 13 3/8" CASING FOUND OUT 4 EA BOW CENTS & 2 STOP COLLARS LEFT IN HOLE.
326 | 06/03/2022 | SSA-29 | QTIF-348 | ARM | 27 May 1300 - 0400 | 23 | 180 | 897210 |  | TH | NARW | NA | 12384 | NOT ABLE TO RUN IN OPEN HOLE WITH 4-1/2" OFF BOTTOM LINER
328 | 06/03/2022 | SSA-5964 | HRDH-1383 | RIG | 01 Jun 0500 - 0500 | 24 | 72 | 897232 |  | UPRA | OTH | NA | 0 | EXCEEDED PLANNED RIG MAINTENANCE DAYS. WAITING ON TOP DRIVE AND DIESEL ENGINE# 4 REPAIR PARTS FOR COOLING SYSTEM.
330 | 06/03/2022 | SSA-5970 | UTMN-2340 | RIG | 03 Jun 1800 - 0500 | 11 | 11 | 897471 |  | BHA | FOT | DC | 300 | EXCESS TIME TO POOH 34" ROTARY BHA DUE TO DAMAGE THREAD ON 7 JTS X 9-1/2" DC.
332 | 06/03/2022 | T901 | JLMN-47 | ARM | 03 Jun 0930 - 1815 | 8.75 | 8.75 | 897456 |  | WON | WTHR | NA | 588 | HIGH SPEED WIND.
333 | 06/03/2022 | T902 | HZEM-162404 | RIG | 02 Jun 2300 - 2100 | 16 | 22 | 897380 |  | UPRA | OTH | NA | 13416 | SEVER OIL LEAK ON TDS HYDRAULIC SYSTEM.
335 | 06/03/2022 | T902 | HZEM-162404 | SDM | 30 May 0630 - 0500 | 8 | 50.25 | 897134 |  | DD | UDWL | RSS | 13416 | SLB NEO STEER COULDEN'T HOLD REQIURED INCLINATION.
336 | 06/03/2022 | T902 | HZEM-162404 | RIG | 02 Jun 2300 - 2100 | 16 | 22 | 897380 |  | UPRA | OTH | NA | 13416 | SEVER OIL LEAK ON TDS HYDRAULIC SYSTEM.
337 | 06/04/2022 | ADC-31 | SDGM-1181 | RIG | 04 Jun 1130 - 0030 | 13 | 13 | 897458 |  | RR | FOT | MPMP | 11946 | MP-3 MODULE FAILURE. POH TO SHOE. WAIT ON PARTS FOR MP-3 MODULE & MP-2 5-WAY BLOCK.
339 | 06/04/2022 | ADC-31 | SDGM-1181 | RIG | 04 Jun 0615 - 0715 | 1 | 1 | 897457 |  | RR | FOT | CSYS | 11875 | REPAIR MP-1 SUCTION LINE.
340 | 06/04/2022 | ADC-31 | SDGM-1181 | RIG | 04 Jun 1130 - 0030 | 13 | 13 | 897458 |  | RR | FOT | MPMP | 11946 | MP-3 MODULE FAILURE. POH TO SHOE. WAIT ON PARTS FOR MP-3 MODULE & MP-2 5-WAY BLOCK.
342 | 06/04/2022 | ADC-32 | SDGM-1228 | RIG | 04 Jun 1430 - 0500 | 14.5 | 14.5 | 897497 |  | JF | HERR | TESTT | 12436 | WHILE TRYING TO UNSET PACKER, DRAW WORKS SLIPPED & SLACK OFF 60 KLB MORE ON PACKER (120 KLB TOTAL SLACK OFF WT ON PACKER), AFTER SEVERAL ATTEMPTS CONFIRMED SAMAA TEST PACKER WAS LEAKING AND ANNULUS LEVEL DROP.
344 | 06/04/2022 | ADC-43L | UTMN-3118 | TK3 | 03 Jun 1000 - 0500 | 23.5 | 38.75 | 897434 |  | LCIR | UXDF | NA | 7199 | WHILE DRILLING LOST COMPLETE RETURNS IN HANIFA FORMATION. PUMPING 3 X LCM PILLS TO CURE THE LOSSES WITHOUT SUCCESS.
357 | 06/04/2022 | ADC-53L | UTMN-4069 | BC | 01 Jun 2200 - 0500 | 24 | 79 | 897303 |  | TF | FOT | SCRN | 10376 | RIH BHI LOWER COMPLETIONS AND OBSERVED COMMUNICATION BETWEEN STRING AND ANNULUS. LIKELY GPV SHOE FAILURE OR AN EQUILIZER IS OPEN.
362 | 06/04/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 159 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS.
364 | 06/04/2022 | ADC-70 | BRRI-1204 | ARM | 04 Jun 0400 - 0500 | 1 | 1 | 897475 |  | WON | WTHR | NA | 0 | WAIT ON SLACK TIDE TO COMMENCE CONDUCTOR OPERATION.
366 | 06/04/2022 | ADES-889 | HRDH-1858 | BC | 02 Jun 1700 - 0500 | 24 | 51 | 897386 |  | TF | FOT | PBR | 13468 | AFTER STING IN WITH BAKER SEALS INTO PBR, P/T TBG & TCA - NOT HOLD.
368 | 06/04/2022 | ADM-262 | MRJN-121 | AP2 | 04 Jun 1815 - 0500 | 10.75 | 10.75 | 897461 |  | WO | WOPF | NA | 0 | SHUT-IN WELL SUSPEND FLOW BACK OPERATION DUE TO TANAJIB ONSHORE PRODUCTION SUSPEND FLOW BACK OPERATION DUE TO PROCESS UPSET.
370 | 06/04/2022 | ADM-337 | MRJN-900 | RIG | 04 Jun 1430 - 1500 | .5 | .5 | 897474 |  | RR | FOT | EDR | 6200 | SLOW TRIPPING SPEED ONCE DP CHANGED FROM 5.5" TO 4" DUE TO CALIBRATION OF PIPE RACKER
372 | 06/04/2022 | ADM-511 | MRJN-799 | BAW | 02 Jun 0245 - 1230 | 7.5 | 33.75 | 897389 |  | TF | FOT | WLT | 12050 | WHILE CARRYING OUT PUMP OUT WITH BAKER PCL LOGGING TOOL STRING RUN#3, TOOL STOP FUNCTIONING, TROUBLESHOOTING SAME, NO SUCCESS, POOH TO CHANGE OUT WITH BACK UP TOOL.
374 | 06/04/2022 | AOD-111 | MRJN-724 | RIG | 04 Jun 0500 - 0800 | 3 | 3 | 897459 |  | UPRA | GRF | TDS | 0 | UNPLANNED RIG MAINTEANCE, TDS RIG REPAIRE, CHANGE OUT ROTATING LINK ADAPTOR OF TDS.
376 | 06/04/2022 | BB-84A | MRJN-586 | HCO | 31 May 1545 - 0500 | 24 | 109 | 897253 |  | JF | DSFT | PKR | 7566 | MULE SHOE HUNG UP ON TOP OF WHIP STOCK AT 7,566'
378 | 06/04/2022 | DPS-43 | SDGM-1196 | SPS | 04 Jun 1900 - 0430 | 9.5 | 9.5 | 897438 |  | BHA | FOT | LWD | 16263 | RESISTIVITY TOOL READINGS WERE NOT MATCHING THE PREVIOUS LOGS READINGS, SUSPECT TOOL FAILURE.
380 | 06/04/2022 | DPS-74 | NJYN-54 | BLH | 13 Apr 0730 - 0500 | 24 | 1193.25 | 895421 |  | TF | FOT | HGRL | 14010 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION.
400 | 06/04/2022 | EXL-IVA | SFNY-1800 | RIG | 04 Jun 1645 - 2000 | 3.25 | 3.25 | 897439 |  | RR | FOT | DWKS | 3535 | LOSS OF COMMUNICATION WITH DRILLER CONTROL PANELS
402 | 06/04/2022 | HI-9 | BRRI-238 | ARM | 03 Jun 0500 - 0500 | 24 | 48 | 897435 |  | WO | SRVC | NA | 0 | RIG WAITING FOR RIG MOVE TO BRRI-219/238 PLATFORM, RIG WILL MOVE AFTER COMPLETION OF BRRI-219 WELL KILLING AND SECURING BY WELL SERVICES.
404 | 06/04/2022 | JACK-202 | HMYM-844 | RIG | 30 May 1900 - 1200 | 7 | 108.5 | 897261 |  | FISH | HERR | BHA | 3341 | LOST IN HOLE HAND OF 5" SLIPS WHILE THE TRAVELLING BLOCK FALL DOWN ON RIG FLOOR.
406 | 06/04/2022 | NBR-20S | HMYM-433504 | RIG | 03 Jun 0345 - 0745 | 2.75 | 4 | 897493 |  | RR | FOT | TDS | 11340 | WASH PIPE LEAKING
408 | 06/04/2022 | NBR-263S | QTIF-736 | RIG | 04 Jun 2315 - 0045 | 1.5 | 1.5 | 897440 |  | RR | FOT | HSYS | 3130 | MULFUNCTION OF TEST UNIT PRIOR TO TEST BOP.
410 | 06/04/2022 | NBR-654S | HRDH-1150 | RIG | 04 Jun 1830 - 1930 | 1 | 1 | 897496 |  | RR | FOT | DWKS | 548 | OBSERVED LEAK ON DRAWWORK HPU UNIT. CHANGED SEALS ON CONTROL VALVE.
412 | 06/04/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 119 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
413 | 06/04/2022 | PA-70S | MDRK-64 | RIG | 04 Jun 1700 - 0430 | 11.5 | 11.5 | 897436 |  | RR | FOT | TDS | 6243 | TDS LINK TILT NOT WORKING
415 | 06/04/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 12.5 | 119.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
416 | 06/04/2022 | PA-70S | MDRK-64 | RIG | 04 Jun 1700 - 0430 | 11.5 | 11.5 | 897436 |  | RR | FOT | TDS | 6243 | TDS LINK TILT NOT WORKING
417 | 06/04/2022 | RM-74A | HSBH-68 | RIG | 04 Jun 1715 - 2245 | 5.5 | 5.5 | 897437 |  | RR | FOT | CRN | 502 | SWING DRIVE MALFUNCTION ON THE PORT AFT CRANE.
419 | 06/04/2022 | RM-74A | HSBH-68 | HCM | 31 May 1530 - 1245 | 7.75 | 78.25 | 897288 |  | CMT | WSHO | CSG | 493 | FAILURE IN CEMENTING OPERATION RESULTED IN WET SHOE.
420 | 06/04/2022 | RM-74A | HSBH-68 | RIG | 04 Jun 1715 - 2245 | 5.5 | 5.5 | 897437 |  | RR | FOT | CRN | 502 | SWING DRIVE MALFUNCTION ON THE PORT AFT CRANE.
426 | 06/04/2022 | SINO-27N | HWYH-466 | WCS | 24 May 0500 - 0500 | 24 | 276.25 | 897182 |  | TF | FOT | CHAMP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
428 | 06/04/2022 | SINO-43L | HWYH-2528 | BHI | 03 Jun 1500 - 1030 | 5.5 | 19.5 | 897432 |  | BHA | FOT | MMOT | 6936 | WHILE ROTARY DRILLING, OBSERVED SUDDEN DROP IN PRESSURE & TORQUE TO OFF-BTM VALUES. ATTEMPTED TO CONTINUE DRILLING ON ROTARY/SLIDE MODE WITH NO PROGRESS DUE TO BHI MUD MOTOR FAILURE.
430 | 06/04/2022 | SND-2002 | WAQR-23 | HLH | 26 May 2000 - 0500 | 24 | 214.5 | 897098 |  | TF | FOT | HGRL | 10330 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES.
432 | 06/04/2022 | SSA-5964 | HRDH-1383 | RIG | 01 Jun 0500 - 0500 | 24 | 96 | 897232 |  | UPRA | OTH | NA | 0 | EXCEEDED PLANNED RIG MAINTENANCE DAYS. WAITING ON TOP DRIVE AND DIESEL ENGINE# 4 REPAIR PARTS FOR COOLING SYSTEM.
434 | 06/04/2022 | T901 | JLMN-47 | CAM | 04 Jun 2315 - 0500 | 5.75 | 5.75 | 897495 |  | WH | HERR | WBSH | 900 | EXCESSIVE TIME TO RETRIEVE WEAR BUSHING.
435 | 06/04/2022 | T902 | HZEM-162404 | RIG | 04 Jun 1530 - 0500 | 13.5 | 13.5 | 897494 |  | RR | FOT | CSYS | 13416 | WHILE REAMING DOWN KELY HOSE DAMAGED
437 | 06/04/2022 | T902 | HZEM-162404 | SDM | 30 May 0630 - 1530 | 8 | 58.25 | 897134 |  | DD | UDWL | RSS | 13416 | SLB NEO STEER COULDEN'T HOLD REQIURED INCLINATION.
438 | 06/04/2022 | T902 | HZEM-162404 | RIG | 04 Jun 1530 - 0500 | 13.5 | 13.5 | 897494 |  | RR | FOT | CSYS | 13416 | WHILE REAMING DOWN KELY HOSE DAMAGED
440 | 06/04/2022 | T914 | UTMN-1272 | ARM | 04 Jun 2330 - 0345 | 4.25 | 4.25 | 897441 |  | STUK | STCT | EQLZR | 9100 | LOWER COMPLETION STUCK WHILE RIH.
442 | 06/05/2022 | 910TE | DMMM-525 | SDM | 05 Jun 1330 - 0500 | 15 | 15 | 897444 |  | BHA | FOT | MWD | 14273 | LOST MWD SIGNAL; TROUBLESHOOT; NO SUCCESS.
443 | 06/05/2022 | ADC-31 | SDGM-1181 | RIG | 05 Jun 0615 - 0015 | 18 | 18 | 897500 |  | RR | FOT | TDS | 12036 | TDS MOTOR FAILED. POH TO SHOE. REPLACE MOTOR.
445 | 06/05/2022 | ADC-31 | SDGM-1181 | RIG | 04 Jun 0400 - 0545 | .75 | 1.75 | 897498 |  | RR | FOT | TDS | 12019 | TDS LINKS NOT FUNCTIONING.
446 | 06/05/2022 | ADC-31 | SDGM-1181 | RIG | 05 Jun 0615 - 0015 | 18 | 18 | 897500 |  | RR | FOT | TDS | 12036 | TDS MOTOR FAILED. POH TO SHOE. REPLACE MOTOR.
448 | 06/05/2022 | ADC-32 | SDGM-1228 | RIG | 04 Jun 1430 - 1930 | 9 | 23.5 | 897497 |  | JF | HERR | TESTT | 12436 | WHILE TRYING TO UNSET PACKER, DRAW WORKS SLIPPED & SLACK OFF 60 KLB MORE ON PACKER (120 KLB TOTAL SLACK OFF WT ON PACKER), AFTER SEVERAL ATTEMPTS CONFIRMED SAMAA TEST PACKER WAS LEAKING AND ANNULUS LEVEL DROP.
450 | 06/05/2022 | ADC-34 | UTMN-2316 | SAM | 05 Jun 0500 - 1930 | 14.5 | 14.5 | 897499 |  | TF | XTTE | WBCL | 13104 | WHILE PERFORMING NEGATIVE TEST SAMAA PACKER FAILED
452 | 06/05/2022 | ADC-43L | UTMN-3118 | TK3 | 03 Jun 1000 - 0500 | 22.5 | 61.25 | 897434 |  | LCIR | UXDF | NA | 7199 | WHILE DRILLING LOST COMPLETE RETURNS IN HANIFA FORMATION. PUMPING 3 X LCM PILLS TO CURE THE LOSSES WITHOUT SUCCESS.
471 | 06/05/2022 | ADC-53L | UTMN-4069 | BC | 01 Jun 2200 - 1000 | 5 | 84 | 897303 |  | TF | FOT | SCRN | 10376 | RIH BHI LOWER COMPLETIONS AND OBSERVED COMMUNICATION BETWEEN STRING AND ANNULUS. LIKELY GPV SHOE FAILURE OR AN EQUILIZER IS OPEN.
476 | 06/05/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 183 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS.
478 | 06/05/2022 | ADC-70 | BRRI-1204 | ARM | 04 Jun 0400 - 0800 | 3 | 4 | 897475 |  | WON | WTHR | NA | 0 | WAIT ON SLACK TIDE TO COMMENCE CONDUCTOR OPERATION.
480 | 06/05/2022 | ADES-144 | UTMN-3152 | BCR | 05 Jun 1100 - 1400 | 3 | 3 | 897481 |  | TF | FOT | CTRQ | 685 | REPAIR ON BAKER POWER UNIT DUE TO HYDRAULIC LEAKS.
482 | 06/05/2022 | ADES-158 | ABQQ-736 | RIG | 04 Jun 0000 - 0700 | 2 | 7 | 897478 |  | JF | HERR | WH | 5205 | CSG SLIPS JUMPED & CAME OUT OF ITS POSITION WHILE PREPARING TO LIFT BOP & CUT CSG.
484 | 06/05/2022 | ADES-889 | HRDH-1858 | BC | 02 Jun 1700 - 0500 | 24 | 75 | 897386 |  | TF | FOT | PBR | 13468 | AFTER STING IN WITH BAKER SEALS INTO PBR, P/T TBG & TCA - NOT HOLD.
486 | 06/05/2022 | ADM-262 | MRJN-121 | AP2 | 04 Jun 1815 - 1145 | 6.75 | 17.5 | 897461 |  | WO | WOPF | NA | 0 | SHUT-IN WELL SUSPEND FLOW BACK OPERATION DUE TO TANAJIB ONSHORE PRODUCTION SUSPEND FLOW BACK OPERATION DUE TO PROCESS UPSET.
488 | 06/05/2022 | ARO-3002 | MRJN-812 | RIG | 05 Jun 2130 - 0500 | 7.5 | 7.5 | 897446 |  | BOP | FOT | CTRL | 8830 | PRESSURE SWITCH OF ACCUMULATOR TRIPPLEX PUMP FAILED TO CUT OFF POWER ON TRIPPLEX PUMP MOTOR.
490 | 06/05/2022 | ARO-3004 | MRJN-2060 | SWL | 05 Jun 1815 - 1930 | 1.25 | 1.25 | 897511 |  | TF | FOT | WLT | 9578 | WHILE SLB TESTING THEIR LOG BHA TOOLS FOUND MPRO NOT WORKING PROPERLY.
492 | 06/05/2022 | BB-84A | MRJN-586 | HCO | 31 May 1545 - 1200 | 7 | 116 | 897253 |  | JF | DSFT | PKR | 7566 | MULE SHOE HUNG UP ON TOP OF WHIP STOCK AT 7,566'
494 | 06/05/2022 | BCTD-3 | HWYH-1029 | RIG | 05 Jun 2200 - 0200 | 4 | 4 | 897532 |  | TF | FOT | CTU | 12692 | INJECTOR DEPTH ENCODER NOT WORKING.
496 | 06/05/2022 | DPS-43 | SDGM-1196 | SPS | 04 Jun 1900 - 0500 | 23.5 | 33 | 897438 |  | BHA | FOT | LWD | 16263 | RESISTIVITY TOOL READINGS WERE NOT MATCHING THE PREVIOUS LOGS READINGS, SUSPECT TOOL FAILURE.
498 | 06/05/2022 | DPS-74 | NJYN-54 | BLH | 13 Apr 0730 - 0500 | 24 | 1217.25 | 895421 |  | TF | FOT | HGRL | 14010 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION.
515 | 06/05/2022 | DQ-48 | KHRS-1420 | BHI | 05 Jun 1400 - 0500 | 15 | 15 | 897450 |  | BHA | FOT | RSS | 9598 | MRSS DRILL 15' NEW FORMATION T/ 9598'. LOST COMMUNICATION BETWEEN ATK & ONTRAK MWD. TROUBLESHOOTING WITHOUT SUCCESS, POOH & CHANGE RSS, MOTOR & MODULAR STAB, RIH
517 | 06/05/2022 | HI-2 | BRRI-440 | ARN | 05 Jun 0045 - 0115 | .5 | .5 | 897483 |  | LCIR | FRFM | NA | 2078 | LOST TOTAL RETURN AT 2078'. SWITCH TO SEA WATER & GEL SWEEPS.
519 | 06/05/2022 | HI-4 | SFNY-918 | SDM | 05 Jun 0500 - 2000 | 14.5 | 14.5 | 897477 |  | BHA | FOT | MWD | 5888 | MWD LOST SIGNAL DURING DRILLING 8-1/2" L-1 SECTION WITH RSS/MWD BHA.
521 | 06/05/2022 | HI-9 | BRRI-238 | ARM | 03 Jun 0500 - 0500 | 24 | 72 | 897435 |  | WO | SRVC | NA | 0 | RIG WAITING FOR RIG MOVE TO BRRI-219/238 PLATFORM, RIG WILL MOVE AFTER COMPLETION OF BRRI-219 WELL KILLING AND SECURING BY WELL SERVICES.
523 | 06/05/2022 | MP-1 | MRJN-79 | BHI | 05 Jun 1830 - 1945 | 1.25 | 1.25 | 897480 |  | BHA | IBHA | RSS | 7120 | BHI RSS ASSY UNABLE TO PASS WINDOW FREELY. ROTATE 1/4 TURN AT A TIME TO PASS WITHOUT SOW.
525 | 06/05/2022 | NA-18S | UTMN-2334 | NCS | 05 Jun 1715 - 2115 | 4 | 4 | 897443 |  | CMT | CFST | NA | 12450 | NPS CEMENT START TO SET AHEAD OF THICKNING TIME.
526 | 06/05/2022 | NBR-263S | QTIF-736 | RIG | 05 Jun 1030 - 0100 | 5.5 | 5.5 | 897449 |  | RR | FOT | HSYS | 3130 | HAD LEAK FROM RIG CUP TESTER ASSY. REPLACED CUP TESTER.
528 | 06/05/2022 | NBR-263S | QTIF-736 | RIG | 05 Jun 1230 - 2100 | 8.5 | 8.5 | 897448 |  | RR | FOT | TDS | 3130 | HAD TDS MALFUNCTION DUE TO ELECTRICAL PROBLEM. CAN-RIG TEAM ON RIG SITE REPLACED ENCODER WITH NEW.
529 | 06/05/2022 | NBR-263S | QTIF-736 | RIG | 05 Jun 1030 - 0100 | 5.5 | 5.5 | 897449 |  | RR | FOT | HSYS | 3130 | HAD LEAK FROM RIG CUP TESTER ASSY. REPLACED CUP TESTER.
530 | 06/05/2022 | NBR-654S | HRDH-1150 | RIG | 05 Jun 0000 - 0130 | 1.5 | 1.5 | 897509 |  | RR | FOT | DRRK | 548 | DOWN TIME DUE TO EXCESS TIME TO RUN BHA, SLOW CONNECTIONS DUE TO MALFUNCTIONING OF MONKEY BOARD WINCH.
532 | 06/05/2022 | NBR-654S | HRDH-1150 | RIG | 05 Jun 1730 - 1830 | 1 | 1 | 897503 |  | RR | FOT | DWKS | 548 | REPAIR LEAK ON DRILLER SIDE EZY-TORQUE. REPLACE OFF DRILLER SIDE EZY TORQUE LINE.
533 | 06/05/2022 | NBR-654S | HRDH-1150 | RIG | 05 Jun 0000 - 0130 | 1.5 | 1.5 | 897509 |  | RR | FOT | DRRK | 548 | DOWN TIME DUE TO EXCESS TIME TO RUN BHA, SLOW CONNECTIONS DUE TO MALFUNCTIONING OF MONKEY BOARD WINCH.
535 | 06/05/2022 | PA-218S | HRDH-1941 | RIG | 05 Jun 0130 - 0445 | 3.25 | 3.25 | 897531 |  | RR | FOT | TDS | 530 | TOP DRIVE COULD NOT B-OFF CONNECTION. TDS GRABBER NOT WORKING.
537 | 06/05/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 143 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
539 | 06/05/2022 | PA-604S | HRDH-1955 | RIG | 05 Jun 1945 - 2300 | 3.25 | 3.25 | 897510 |  | RR | FOT | TDS | 370 | TROUBLESHOOT AND REPAIR TDS ELECTRICAL PROBLEM.
541 | 06/05/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 143.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
548 | 06/05/2022 | SINO-27N | HWYH-466 | WCS | 24 May 0500 - 0500 | 23.5 | 297.25 | 897182 |  | TF | FOT | CHAMP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
550 | 06/05/2022 | SINO-45L | UTMN-486 | SPS | 05 Jun 0900 - 2300 | 14 | 14 | 897508 |  | BHA | FOT | MWD | 7326 | MWD TOOL FAILURE.
551 | 06/05/2022 | SND-2002 | WAQR-23 | HCB | 05 Jun 1000 - 0500 | 19 | 19 | 897479 |  | TF | FOT | RETNR | 9056 | STING INTO FAST DRILL EZSV AND TRIED TO ESTABLISH CIRC. HAD PRESSURE BUILD UP DUE TO EZSV SLIDDING VALVE CLOSED, TROUBLE SHOOT WITH NO SUCCESS
553 | 06/05/2022 | SND-2002 | WAQR-23 | HLH | 26 May 2000 - 1000 | 5 | 219.5 | 897098 |  | TF | FOT | HGRL | 10330 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES.
554 | 06/05/2022 | SND-2002 | WAQR-23 | HCB | 05 Jun 1000 - 0500 | 19 | 19 | 897479 |  | TF | FOT | RETNR | 9056 | STING INTO FAST DRILL EZSV AND TRIED TO ESTABLISH CIRC. HAD PRESSURE BUILD UP DUE TO EZSV SLIDDING VALVE CLOSED, TROUBLE SHOOT WITH NO SUCCESS
556 | 06/05/2022 | SSA-51 | MNIF-253 | BHI | 05 Jun 2030 - 2130 | 1 | 1 | 897463 |  | BHA | FOT | MWD | 17192 | TROUBLESHOOT MWD TOOL LOST SIGNAL.
557 | 06/05/2022 | SSA-5859 | HWYH-1222 | RIG | 05 Jun 1030 - 1230 | 2 | 2 | 897504 |  | RR | FOT | RSYS | 3000 | TROUBLESHOOTING IRON ROUGHNECK PROBLEMS WHILE M/U DRILL PIPE.
559 | 06/05/2022 | SSA-5859 | HWYH-1222 | RIG | 05 Jun 0330 - 0500 | 1.5 | 1.5 | 897462 |  | RR | FOT | TDS | 6000 | CUMULATIVE TIME TO TROUBLESHOOT SAIPEM TDS DUE TO SUDDEN STOPPAGE OF RPM WHILE DRILLING
560 | 06/05/2022 | SSA-5859 | HWYH-1222 | RIG | 05 Jun 1030 - 1230 | 2 | 2 | 897504 |  | RR | FOT | RSYS | 3000 | TROUBLESHOOTING IRON ROUGHNECK PROBLEMS WHILE M/U DRILL PIPE.
562 | 06/05/2022 | SSA-5964 | HRDH-1383 | RIG | 01 Jun 0500 - 0500 | 24 | 120 | 897232 |  | UPRA | OTH | NA | 0 | EXCEEDED PLANNED RIG MAINTENANCE DAYS.
564 | 06/05/2022 | SSA-5969 | UTMN-3021 | SDM | 05 Jun 2130 - 0200 | 3 | 3 | 897505 |  | BHA | FOT | MWD | 13004 | SLB MWD/GR TOOL FAILURE
565 | 06/05/2022 | SSA-5970 | UTMN-2340 | RIG | 05 Jun 0130 - 0500 | 3.5 | 3.5 | 897502 |  | BHA | FOT | DC | 610 | L/D DAMAGE DC.
567 | 06/05/2022 | SSA-5970 | UTMN-2340 | RIG | 05 Jun 0030 - 0130 | 1 | 1 | 897445 |  | RR | FOT | HSYS | 610 | RIG REPAIR ON EZY TORQUE.
568 | 06/05/2022 | SSA-5970 | UTMN-2340 | RIG | 05 Jun 1815 - 2045 | 2.5 | 2.5 | 897501 |  | RR | FOT | TDS | 610 | REPAIR ON TDS SOLINOD GRAPPER.
569 | 06/05/2022 | SSA-5970 | UTMN-2340 | RIG | 05 Jun 0130 - 0500 | 3.5 | 3.5 | 897502 |  | BHA | FOT | DC | 610 | L/D DAMAGE DC.
571 | 06/05/2022 | SSA-5971 | HRDH-2247 | HCM | 31 May 2030 - 0400 | 23 | 46 | 897292 |  | CMT | IFCS | NA | 5155 | EXCESS TIME TO RETRIEVE FMH RUNNING TOOL, OBSERVED CONTAMINATED CEMENT IN WELLHEAD AND AROUND
572 | 06/05/2022 | T902 | HZEM-162404 | RIG | 04 Jun 1530 - 0845 | 3.75 | 17.25 | 897494 |  | RR | FOT | CSYS | 13416 | WHILE REAMING DOWN KELY HOSE DAMAGED
574 | 06/05/2022 | T902 | HZEM-162404 | SDM | 30 May 0630 - 2100 | 12.25 | 70.5 | 897134 |  | DD | UDWL | RSS | 13416 | SLB NEO STEER COULDEN'T HOLD REQIURED INCLINATION.
575 | 06/05/2022 | T902 | HZEM-162404 | RIG | 04 Jun 1530 - 0845 | 3.75 | 17.25 | 897494 |  | RR | FOT | CSYS | 13416 | WHILE REAMING DOWN KELY HOSE DAMAGED
577 | 06/06/2022 | 910TE | DMMM-525 | SDM | 05 Jun 1330 - 2030 | 15 | 30 | 897444 |  | BHA | FOT | MWD | 14273 | LOST MWD SIGNAL; TROUBLESHOOT; NO SUCCESS.
579 | 06/06/2022 | ADC-34 | UTMN-2316 | SAM | 05 Jun 0500 - 2030 | 10 | 24.5 | 897499 |  | TF | XTTE | WBCL | 13104 | WHILE PERFORMING NEGATIVE TEST SAMAA PACKER FAILED
581 | 06/06/2022 | ADC-43L | UTMN-3118 | TK3 | 03 Jun 1000 - 0945 | 4.75 | 66 | 897434 |  | LCIR | UXDF | NA | 7199 | WHILE DRILLING LOST COMPLETE RETURNS IN HANIFA FORMATION. PUMPING 3 X LCM PILLS TO CURE THE LOSSES WITHOUT SUCCESS.
583 | 06/06/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 207 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS.
585 | 06/06/2022 | ADES-889 | HRDH-1858 | BC | 02 Jun 1700 - 0500 | 24 | 99 | 897386 |  | TF | FOT | PBR | 13468 | AFTER STING IN WITH BAKER SEALS INTO PBR, P/T TBG & TCA - NOT HOLD.
587 | 06/06/2022 | ADM-266 | SFNY-933 | AP2 | 06 Jun 1900 - 0500 | 10 | 10 | 897555 |  | WO | WOPF | NA | 0 | WAITING ON PRODUCING TO APPROVE "ZERO-FLARING" FLOW BACK TO SFNY GOSP.
589 | 06/06/2022 | ARO-3002 | MRJN-812 | RIG | 05 Jun 2130 - 0830 | 3.5 | 11 | 897446 |  | BOP | FOT | CTRL | 8830 | PRESSURE SWITCH OF ACCUMULATOR TRIPPLEX PUMP FAILED TO CUT OFF POWER ON TRIPPLEX PUMP MOTOR.
591 | 06/06/2022 | ARO-4001 | MRJN-538 | RIG | 06 Jun 1645 - 2115 | 4.5 | 4.5 | 897591 |  | RR | FOT | DRRK | 7080 | TROUBLE SHOOT AND REPLACE PRS ENCODER CABLE.
593 | 06/06/2022 | DPS-43 | SDGM-1196 | SPS | 04 Jun 1900 - 0730 | 2.5 | 35.5 | 897438 |  | BHA | FOT | LWD | 16263 | RESISTIVITY TOOL READINGS WERE NOT MATCHING THE PREVIOUS LOGS READINGS, SUSPECT TOOL FAILURE.
595 | 06/06/2022 | DPS-74 | NJYN-54 | BLH | 13 Apr 0730 - 0500 | 24 | 1241.25 | 895421 |  | TF | FOT | HGRL | 14010 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION.
615 | 06/06/2022 | DQ-48 | KHRS-1420 | BHI | 05 Jun 1400 - 1830 | 11.5 | 26.5 | 897450 |  | BHA | IBHA | RSS | 9598 | MRSS DRILL 15' NEW FORMATION T/ 9598'. LOST COMMUNICATION BETWEEN ATK & ONTRAK MWD. TROUBLESHOOTING WITHOUT SUCCESS, POOH & CHANGE RSS, MOTOR & MODULAR STAB, RIH
617 | 06/06/2022 | HI-9 | BRRI-238 | ARM | 03 Jun 0500 - 0500 | 24 | 96 | 897435 |  | WO | SRVC | NA | 0 | RIG WAITING FOR RIG MOVE TO BRRI-219/238 PLATFORM, RIG WILL MOVE AFTER COMPLETION OF BRRI-219 WELL KILLING AND SECURING BY WELL SERVICES.
619 | 06/06/2022 | NA-18S | UTMN-2334 | NCS | 05 Jun 1715 - 0500 | 19 | 23 | 897443 |  | CMT | CFST | NA | 12450 | NPS CEMENT START TO SET AHEAD OF THICKNING TIME.
620 | 06/06/2022 | NBR-20S | HMYM-433504 | RIG | 06 Jun 1000 - 1100 | 1 | 1 | 897593 |  | RR | FOT | MPMP | 16978 | BLEED OFF VALVES LEAKING
622 | 06/06/2022 | NBR-20S | HMYM-433504 | RIG | 05 Jun 0515 - 0645 | .75 | 1.25 | 897512 |  | RR | FOT | MPMP | 14146 | MUD PUMPS NOT FUNCTION PROPERLY
623 | 06/06/2022 | NBR-20S | HMYM-433504 | SPS | 06 Jun 1430 - 0500 | 12.5 | 12.5 | 897518 |  | BHA | FOT | MWD | 17360 | LOST SIGNAL ON SPS MWD
624 | 06/06/2022 | NBR-20S | HMYM-433504 | RIG | 06 Jun 1830 - 2030 | 2 | 2 | 897519 |  | RR | FOT | PSYS | 17360 | ENGINES SHUTDOWN
625 | 06/06/2022 | NBR-20S | HMYM-433504 | RIG | 06 Jun 1000 - 1100 | 1 | 1 | 897593 |  | RR | FOT | MPMP | 16978 | BLEED OFF VALVES LEAKING
627 | 06/06/2022 | NBR-210S | HRML-80 | WDS | 06 Jun 1215 - 0500 | 16.75 | 16.75 | 897574 |  | BHA | FOT | GMWD | 10816 | WFD MWD PULSAR UNABLE TO START UP, TROUBLE SHOOTING SEVERAL TIMES, NO SUCCESS.
629 | 06/06/2022 | NBR-263S | QTIF-736 | RIG | 06 Jun 1745 - 1900 | 1.25 | 1.25 | 897554 |  | RR | FPMP | MPMP | 3130 | HAD MUD PUMP PRESSURE FLUCTUATIONS FROM 150 TO 650 PSI @ 600 GPM. - CLEANED MUD PUMP SUCTION SCREENS.OK
631 | 06/06/2022 | NBR-654S | HRDH-1150 | RIG | 06 Jun 1430 - 1500 | .5 | .5 | 897553 |  | RR | FOT | DWKS | 980 | REPAIR ON DRAWWORKS: FIX LEAK IN DRAWWORKS HPU ( CHANGE "O" RING SEAL)
633 | 06/06/2022 | PA-218S | HRDH-1941 | RIG | 06 Jun 0900 - 1200 | 3 | 3 | 897515 |  | RR | FOT | TDS | 620 | TOP DRIVE HAD LOW LUBE OIL PRESSURE.
635 | 06/06/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 1245 | 7.75 | 150.75 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
637 | 06/06/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 167.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
639 | 06/06/2022 | PA-866S | SHHB-2 | RIG | 06 Jun 0515 - 0500 | 14.75 | 14.75 | 897517 |  | RR | FOT | DWKS | 11150 | ENCODER FAULT WARNING FROM SYSTEM FOR DRAWWORKS "A" MOTOR - MOTOR WILL NOT RUN
641 | 06/06/2022 | PN-9 | ABSF-16 | HCO | 06 Jun 1500 - 0500 | 14 | 14 | 897557 |  | TF | FOT | PDHMS | 0 | UNABLE TO INSTALL HALLIBURTON 3-1/2" PDHMS CABLE PROTECTOR CLAMPS.
647 | 06/06/2022 | SINO-15L | ANDR-482 | SPS | 06 Jun 0200 - 0500 | 3 | 3 | 897520 |  | BHA | FOT | RSS | 7994 | ICRUISE FAILURE
649 | 06/06/2022 | SINO-27N | HWYH-466 | WBP | 24 May 0500 - 0500 | 23.5 | 320.75 | 897182 |  | TF | FOT | BP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
651 | 06/06/2022 | SINO21 | ABQQ-502 | AZ1 | 06 Jun 1700 - 0500 | 12 | 12 | 897573 |  | TF | FOT | WLU | 0 | REPAIRE TAQA W/L UNIT.
653 | 06/06/2022 | SL-7 | ZULF-1334 | RIG | 06 Jun 0830 - 1100 | 2.5 | 2.5 | 897571 |  | BOP | FOT | RAMS | 0 | ATTEMPT TO INSTALL NEW DESING SHEAR RAM BLOCKS, BONNET WILL NOT FULLY CLOSE
654 | 06/06/2022 | SND-2002 | WAQR-23 | HCB | 05 Jun 1000 - 0230 | 21.5 | 40.5 | 897479 |  | TF | FOT | RETNR | 9056 | STING INTO FAST DRILL EZSV AND TRIED TO ESTABLISH CIRC. HAD PRESSURE BUILD UP DUE TO EZSV SLIDDING VALVE CLOSED, TROUBLE SHOOT WITH NO SUCCESS
656 | 06/06/2022 | SND-2002 | WAQR-23 | HLH | 26 May 2000 - 0500 | 2.5 | 222 | 897098 |  | TF | FOT | HGRL | 10330 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES.
657 | 06/06/2022 | SND-2002 | WAQR-23 | HCB | 05 Jun 1000 - 0230 | 21.5 | 40.5 | 897479 |  | TF | FOT | RETNR | 9056 | STING INTO FAST DRILL EZSV AND TRIED TO ESTABLISH CIRC. HAD PRESSURE BUILD UP DUE TO EZSV SLIDDING VALVE CLOSED, TROUBLE SHOOT WITH NO SUCCESS
659 | 06/06/2022 | SP-124 | FDHL-141 | BHI | 06 Jun 1530 - 0500 | 13.5 | 13.5 | 897572 |  | BHA | FOT | LWD | 10507 | HAD NO RESPONSE FROM BAKER MAGTRAK SENSOR, MANY TRIALS ATTEMPTING TO TROUBLE-SHOOT THE LOGGING TOOL, NO SUCCESS.
661 | 06/06/2022 | SP-261 | HZEM-160214 | ITS | 06 Jun 1700 - 1800 | 1 | 1 | 897516 |  | JF | XTRI | CTRQ | 250 | REPLACE DAMAGED CRT PACKER RUBBER.
663 | 06/06/2022 | SSA-101 | QTIF-785 | MSD | 06 Jun 2330 - 0200 | 2.5 | 2.5 | 897556 |  | TF | FOT | CTRQ | 5875 | AL-MASOOD SPIDER SLIP AIR FILTER LEAK & FAILURE TO OPEN, R/D SLIPS, R/U BACK SPIDER SLIP.
665 | 06/06/2022 | SSA-5859 | HWYH-1222 | RIG | 05 Jun 0330 - 1430 | 4 | 5.5 | 897462 |  | RR | FOT | TDS | 6000 | CUMULATIVE TIME TO TROUBLESHOOT TDS DUE TO SUDDEN STOP OF ROTATION WHILE DRILLING,
667 | 06/06/2022 | SSA-5964 | HRDH-1383 | RIG | 01 Jun 0500 - 0500 | 24 | 144 | 897232 |  | UPRA | OTH | NA | 0 | EXCEEDED PLANNED RIG MAINTENANCE DAYS.
669 | 06/06/2022 | SSA-5970 | UTMN-2340 | RIG | 06 Jun 1000 - 1300 | 3 | 3 | 897594 |  | RR | FOT | TDS | 0 | CHANGE OUT TDS GRIPPER GUIDE.
671 | 06/06/2022 | SSA-5971 | HRDH-2247 | HCM | 31 May 2030 - 1900 | 11.5 | 57.5 | 897292 |  | CMT | IFCS | NA | 5155 | EXCESS TIME TO RETRIEVE FMH RUNNING TOOL, OBSERVED CONTAMINATED CEMENT IN WELLHEAD AND AROUND
673 | 06/07/2022 | ADC-17 | ZULF-1217 | RIG | 07 Jun 0130 - 0330 | 2 | 2 | 897653 |  | BOP | HERR | BOP | 6747 | MANY ATTEMPTS TO N/U BELL NIPPLE, HAD MISALIGNMENT WITH FLOW LINE, WORK ON SAME TILL ADJUSTED THE ALIGNMENT.
675 | 06/07/2022 | ADC-52 | SDGM-1185 | ARM | 07 Jun 2300 - 0500 | 6 | 6 | 897634 |  | TH | NARW | NA | 815 | GOT OBSTRUCTION @ 815' WHILE RUNNING 18-5/8" CASING. WORK STRING AND TRY TO PASS WITH CIRCULATION 500 GPM X 160 PSI AND APPLY 60KLBS SOW WITHOUT SUCCESS.
677 | 06/07/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 231 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS.
679 | 06/07/2022 | ADES-144 | UTMN-3152 | RIG | 07 Jun 1730 - 1830 | 1 | 1 | 897631 |  | RR | FOT | TDS | 2150 | REPAIR TDS VFD AC SYSTEM, VFD BLOWER OVERHEATED CAUSING TDS TO TRIP. REPAIR TDS GRAPPER DICE.
681 | 06/07/2022 | ADES-889 | HRDH-1858 | BC | 02 Jun 1700 - 0500 | 24 | 123 | 897386 |  | TF | FOT | PBR | 13468 | AFTER STING IN WITH BAKER SEALS INTO PBR, P/T TBG & TCA - NOT HOLD.
683 | 06/07/2022 | ADM-261 | LWHH-9 | SPS | 07 Jun 1330 - 0500 | 15.5 | 15.5 | 897524 |  | BHA | FOT | RSS | 7580 | LOST HALL RSS TURBINE SIGNAL, LOST COMMUNICATION WITH SURFACE AND STOPPED RESPONDING.
685 | 06/07/2022 | AOD-1 | ZULF-696 | BCM | 07 Jun 2245 - 2330 | .75 | .75 | 897636 |  | TF | FOT | PUMP | 7730 | TROUBLE SHOOT CEMENT UNIT. MIX WATER PUMP NOT TRANSFERING FROM MIX FLUID TANK TO MIX TUB. FOUND HYDRAULIC HOSE ON TRANMISSION LEAKING & UNABLE TO REPAIR.
687 | 06/07/2022 | DPS-74 | NJYN-54 | BLH | 13 Apr 0730 - 0500 | 24 | 1265.25 | 895421 |  | TF | FOT | HGRL | 14010 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION.
688 | 06/07/2022 | ENSCO-54 | ABSF-28 | KSC | 07 Jun 1600 - 2300 | 7 | 7 | 897633 |  | TF | FOT | ESP | 0 | LOST POWER TO VSD UNIT -TROUBLE SHOOT WITHOUT SUCCESS - CHANGED TO ANOTHER VSD UNIT HAD ERROR WITH SENSOR.TROUBLE SHOOT & FIXED SAME.
690 | 06/07/2022 | ENSCO-54 | ABSF-28 | KSC | 07 Jun 0930 - 1300 | 3.5 | 3.5 | 897632 |  | TF | FOT | ESP | 0 | VSD MALFUNCTION - TROUBLE SHOOT & FIXED SAME
691 | 06/07/2022 | ENSCO-54 | ABSF-28 | KSC | 07 Jun 1600 - 2300 | 7 | 7 | 897633 |  | TF | FOT | ESP | 0 | LOST POWER TO VSD UNIT -TROUBLE SHOOT WITHOUT SUCCESS - CHANGED TO ANOTHER VSD UNIT HAD ERROR WITH SENSOR.TROUBLE SHOOT & FIXED SAME.
693 | 06/07/2022 | EXL-IA | SFNY-4240 | RIG | 07 Jun 1300 - 1430 | 1.5 | 1.5 | 897652 |  | TF | FOT | TESTT | 8479 | WHILE TRYING TO LINE TEST RIGS BOP TEST UNIT - UNABLE TO GET A TEST DUE TO LOW TORQUE VALVES LEAKING.
695 | 06/07/2022 | HI-9 | BRRI-238 | ARM | 03 Jun 0500 - 0500 | 24 | 120 | 897435 |  | WO | SRVC | NA | 0 | RIG WAITING FOR RIG MOVE TO BRRI-219/238 PLATFORM, RIG WILL MOVE AFTER COMPLETION OF BRRI-219 WELL KILLING AND SECURING BY WELL SERVICES.
697 | 06/07/2022 | MP-1 | MRJN-79 | BHI | 07 Jun 2100 - 0500 | 8 | 8 | 897651 |  | DD | ETRQ | RSS | 8560 | ENCOUNTERED ERRATIC TORQUE VALUES WHILE DRLG (5-14 KLB.FT) , WHICH RESULTED IN VERY POOR ROP (LESS THAN 15 FT/HR), DUE TO INABILITY TO PUT WOB MORE THAN 13 KLBS.
699 | 06/07/2022 | NA-393S | HWYH-1138 | BCR | 07 Jun 0600 - 1800 | 12 | 12 | 897521 |  | TF | FOT | CTRQ | 8745 | WHILE RIH W/EXPRO S/L 3.795" DRIFT, COULDN'T PASS, HAD OBSTRUCTION AT 2,914' (CONNECTION BETWEEN JTS#141&142).
701 | 06/07/2022 | NBR-20S | HMYM-433504 | SPS | 06 Jun 1430 - 0500 | 19.75 | 32.25 | 897518 |  | BHA | FOT | MWD | 17360 | LOST SIGNAL ON SPS MWD
703 | 06/07/2022 | NBR-210S | HRML-80 | WDS | 06 Jun 1215 - 1030 | 5.5 | 22.25 | 897574 |  | BHA | FOT | GMWD | 10816 | WFD MWD PULSAR UNABLE TO START UP, TROUBLE SHOOTING SEVERAL TIMES, NO SUCCESS.
704 | 06/07/2022 | NBR-263S | QTIF-736 | RIG | 07 Jun 0145 - 0245 | 1 | 1 | 897527 |  | RR | FOT | HSYS | 3140 | LOST TIME DUE TO IRON ROUGHNECK MALFUNCTION BECUSE OF ELECTERICAL PROBLEM. CAN-RIG TECHNICIAN FIXED SAME.
706 | 06/07/2022 | NBR-263S | QTIF-736 | RIG | 07 Jun 2030 - 2145 | 1.25 | 1.25 | 897526 |  | RR | FOT | MPMP | 3140 | HAD FLUCTUATION IN MUD PUMPS PRESSURE WHILE SHALLOW TEST. - CHANGED BETWWEN MUD PUMPS, USED ONLY ONE PUMP TO HAVE A GOOD SIGNAL.
707 | 06/07/2022 | NBR-263S | QTIF-736 | RIG | 07 Jun 0145 - 0245 | 1 | 1 | 897527 |  | RR | FOT | HSYS | 3140 | LOST TIME DUE TO IRON ROUGHNECK MALFUNCTION BECUSE OF ELECTERICAL PROBLEM. CAN-RIG TECHNICIAN FIXED SAME.
709 | 06/07/2022 | PA-326S | WDYH-16 | RIG | 07 Jun 1515 - 1630 | .75 | .75 | 897611 |  | RR | FOT | TDS | 15302 | TDS GRAPPER BLOCK DIES EXIT FORM IN PLACE.
711 | 06/07/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 191.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
713 | 06/07/2022 | PA-866S | SHHB-2 | RIG | 06 Jun 0515 - 0900 | 4 | 18.75 | 897517 |  | RR | FOT | DWKS | 11150 | ENCODER FAULT WARNING FROM SYSTEM FOR DRAWWORKS "A" MOTOR - MOTOR WILL NOT RUN
714 | 06/07/2022 | PN-9 | ABSF-16 | HCO | 06 Jun 1500 - 2130 | 16.5 | 30.5 | 897557 |  | TF | FOT | PDHMS | 0 | UNABLE TO INSTALL HALLIBURTON 3-1/2" PDHMS CABLE PROTECTOR CLAMPS.
716 | 06/07/2022 | PN-9 | ABSF-16 | RIG | 07 Jun 2230 - 0100 | 2.5 | 2.5 | 897529 |  | RR | FOT | PSYS | 0 | LOSS OF COMMUNICATION BETWEEN AMPHION SYSTEM & POWER SUPPLY.
717 | 06/07/2022 | PN-9 | ABSF-16 | HCO | 06 Jun 1500 - 2130 | 16.5 | 30.5 | 897557 |  | TF | FOT | PDHMS | 0 | UNABLE TO INSTALL HALLIBURTON 3-1/2" PDHMS CABLE PROTECTOR CLAMPS.
723 | 06/07/2022 | SINO-15L | ANDR-482 | TK1 | 06 Jun 0200 - 0500 | 24 | 27 | 897520 |  | JF | HERR | NA | 7994 | CAN NOT DROP INNCLINATION TO ACHEIVE LAND WELL WITH ICRUISE
725 | 06/07/2022 | SINO-27N | HWYH-466 | WBP | 24 May 0500 - 0500 | 23.5 | 344.25 | 897182 |  | TF | FOT | BP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
727 | 06/07/2022 | SINO21 | ABQQ-502 | AZ1 | 07 Jun 0500 - 1100 | 6 | 6 | 897635 |  | TF | FOT | WLT | 3000 | TAQA W/L TOOL FAILURE.
729 | 06/07/2022 | SND-2006 | UTMN-3165 | ARM | 06 Jun 1930 - 0500 | 24 | 33.5 | 897558 |  | LROP | LTHI | BIT | 10563 | VERY LOW PENETRATION RATE
731 | 06/07/2022 | SP-124 | FDHL-141 | BHI | 06 Jun 1530 - 0100 | 20 | 33.5 | 897572 |  | BHA | FOT | LWD | 10507 | HAD NO RESPONSE FROM BAKER MAGTRAK SENSOR, MANY TRIALS ATTEMPTING TO TROUBLE-SHOOT THE LOGGING TOOL, NO SUCCESS.
733 | 06/07/2022 | SP-229 | ABHD-7 | RIG | 07 Jun 2330 - 0500 | 5.5 | 5.5 | 897613 |  | BHA | ETRQ | BHA | 0 | HAD HIGH TORQUE WHEN MILLING OUT LANDING COLLAR, LOST WT AND PRESSURE
735 | 06/07/2022 | SSA-101 | QTIF-785 | MSD | 07 Jun 1145 - 1345 | 2 | 2 | 897523 |  | TF | FOT | CTRQ | 9965 | AL-MASOOD CASING CREW TIGHT CROSS CONNECTION, L/DN JOINT & REPLACED WITH NEW ONE, REPLACED LEAKED CSG POWER TONG HYDRAULIC LINE.
737 | 06/07/2022 | SSA-201 | HRDH-2112 | SWL | 07 Jun 1100 - 0000 | 13 | 13 | 897612 |  | TF | FOT | WLT | 14475 | WHILE RIH TO SET BAKER K1 BP, LOST CCL SIGNAL, POOH & CHANGE OUT CCL
739 | 06/07/2022 | SSA-5917 | HRDH-2261 | SPS | 07 Jun 0900 - 1000 | 1 | 1 | 897530 |  | BHA | FOT | GMWD | 13404 | S.SUN MWD SIGNAL LOST.
741 | 06/07/2022 | SSA-5964 | HRDH-1383 | RIG | 01 Jun 0500 - 0500 | 24 | 168 | 897232 |  | UPRA | OTH | NA | 0 | EXCEEDED PLANNED RIG MAINTENANCE DAYS.
742 | 06/07/2022 | T216 | ANDR-95 | ODJ | 07 Jun 1000 - 1230 | 2.5 | 2.5 | 897655 |  | TF | FOT | CRT | 0 | TBG GOT COLLAPS BY POWER TONG AND PACKER SAFETY JOINT SUB GOT BACK OFF, (LOOSE IN CONNECTION THREAD ON PACKER )
744 | 06/07/2022 | T216 | ANDR-95 | ODJ | 07 Jun 0500 - 0900 | 4 | 4 | 897654 |  | TF | FOT | PEL | 0 | POWER TONG NOT WORKING
745 | 06/07/2022 | T216 | ANDR-95 | ODJ | 07 Jun 1000 - 1230 | 2.5 | 2.5 | 897655 |  | TF | FOT | CRT | 0 | TBG GOT COLLAPS BY POWER TONG AND PACKER SAFETY JOINT SUB GOT BACK OFF, (LOOSE IN CONNECTION THREAD ON PACKER )
747 | 06/07/2022 | T218 | UTMN-1281 | HWP | 07 Jun 0800 - 1100 | 3 | 3 | 897528 |  | TF | XTTE | COMP | 7770 | NMR TOOL FREQUENCY OUT OF RANGE.
749 | 06/08/2022 | ADC-17 | ZULF-1217 | RIG | 08 Jun 1400 - 1700 | 3 | 3 | 897617 |  | RR | FOT | TDS | 0 | WHILE PRESSURE TESTING SURFACE LINE AGAINST UPPER IBOP, OBSREVED LEAK IN UPPER IBOP
751 | 06/08/2022 | ADC-31 | SDGM-1181 | GOC | 08 Jun 0800 - 1000 | 2 | 2 | 897672 |  | TF | FOT | CTRQ | 1680 | ALGAITH POWER TONG NOT FUNCTIONING PROPERLY RESULTING IN JOB DELAY.
753 | 06/08/2022 | ADC-51 | SDGM-1245 | SPS | 08 Jun 0630 - 0300 | 19.5 | 19.5 | 897656 |  | BHA | FOT | MWD | 12420 | LOST MWD/GR SIGNAL.
755 | 06/08/2022 | ADC-52 | SDGM-1185 | ARM | 07 Jun 2300 - 0500 | 24 | 30 | 897634 |  | TH | NARW | NA | 815 | GOT OBSTRUCTION @ 815' WHILE RUNNING 18-5/8" CASING. WORK STRING AND TRY TO PASS WITH CIRCULATION 500 GPM X 160 PSI AND APPLY 60KLBS SOW WITHOUT SUCCESS.
757 | 06/08/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 255 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
759 | 06/08/2022 | ADES-144 | UTMN-3152 | BCR | 08 Jun 2100 - 0000 | 3 | 3 | 897712 |  | TF | FOT | CTRQ | 2705 | BAKER POWER UNIT OUT OF SERVICE
761 | 06/08/2022 | ADES-889 | HRDH-1858 | BC | 02 Jun 1700 - 0530 | .5 | 123.5 | 897386 |  | TF | FOT | PBR | 13468 | AFTER STING IN WITH BAKER SEALS INTO PBR, P/T TBG & TCA - NOT HOLD.
762 | 06/08/2022 | ADM-261 | LWHH-9 | SPS | 08 Jun 1500 - 0500 | 14 | 14 | 897694 |  | BHA | FOT | RSS | 7612 | HALLIBURTON RSS LOST COMMUNICATION WITH SURFACE, TURBINE RSS SIGNAL STOPPED RESPONDING.
764 | 06/08/2022 | ADM-261 | LWHH-9 | SPS | 07 Jun 1330 - 1500 | 10 | 25.5 | 897524 |  | BHA | FOT | RSS | 7580 | LOST HALL RSS TURBINE SIGNAL, LOST COMMUNICATION WITH SURFACE AND STOPPED RESPONDING.
765 | 06/08/2022 | ADM-261 | LWHH-9 | SPS | 08 Jun 1500 - 0500 | 14 | 14 | 897694 |  | BHA | FOT | RSS | 7612 | HALLIBURTON RSS LOST COMMUNICATION WITH SURFACE, TURBINE RSS SIGNAL STOPPED RESPONDING.
767 | 06/08/2022 | ARO-4001 | MRJN-538 | RIG | 08 Jun 1445 - 1630 | 1.75 | 1.75 | 897616 |  | RR | FOT | DWKS | 11560 | TROUBLE SHOOT AND REPLACE HOOK LOAD SENSOR OF DEADMAN ANCHOR.
769 | 06/08/2022 | DPS-74 | NJYN-54 | BLH | 13 Apr 0730 - 1700 | 12 | 1277.25 | 895421 |  | TF | FOT | HGRL | 14010 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION.
786 | 06/08/2022 | HI-9 | BRRI-238 | ARM | 03 Jun 0500 - 1130 | 6.5 | 126.5 | 897435 |  | WO | SRVC | NA | 0 | RIG WAITING FOR RIG MOVE TO BRRI-219/238 PLATFORM, RIG WILL MOVE AFTER COMPLETION OF BRRI-219 WELL KILLING AND SECURING BY WELL SERVICES.
788 | 06/08/2022 | JACK-202 | HMYM-844 | RIG | 08 Jun 0900 - 0200 | 17 | 17 | 897678 |  | RR | FOT | DWKS | 1576 | WAIT TO CHANGE BRAKE BAND ON DRAWWORKS. HPJSM, CHANGE THE OLD BRAKE BAND FROM ITALY BY NEW ONE FROM USA (TAKE FROM JACK-203).
790 | 06/08/2022 | MP-1 | MRJN-79 | ARM | 07 Jun 2100 - 0500 | 23.5 | 31.5 | 897651 |  | DD | ETRQ | RSS | 8560 | ENCOUNTERED ERRATIC TORQUE VALUES WHILE DRLG (5-14 KLB.FT) , WHICH RESULTED IN VERY POOR ROP (LESS THAN 15 FT/HR), DUE TO INABILITY TO PUT WOB MORE THAN 13 KLBS (ERRATIC WITH 15 KFT-LBS). FOUND 1 EA BIT NOZZLE PLUGGED WITH FMN CUTTINGS.
792 | 06/08/2022 | NADRU-1 | BRRI-1217 | SCT | 08 Jun 0100 - 0500 | 4 | 4 | 897676 |  | TF | FOT | CTAC | 12700 | MINOR HYDRAULIC OIL LEAK IN SLB INJECTOR TRACTION CYLINDERS. TROUBLESHOOT TO FIX THE LEAK WITH NO SUCCESS. POOH AND REPLACE INJECTOR WITH A NEW ONE.
794 | 06/08/2022 | NBR-115S | HWYH-1220 | SDM | 08 Jun 1445 - 0500 | 14.25 | 14.25 | 897673 |  | BHA | FOT | MWD | 15194 | LOST SIGNAL IN SLB MWD TOOL.
796 | 06/08/2022 | NBR-196S | SDGM-1235 | SJC | 08 Jun 1630 - 2130 | 5 | 5 | 897674 |  | CMT | CFST | NA | 4540 | 18 5/8" CSING 2ND STAGE CMT FLASH SET WHILE DISPLACEMENT.
798 | 06/08/2022 | NBR-654S | HRDH-1150 | WCR | 08 Jun 1145 - 1800 | 6.25 | 6.25 | 897692 |  | TF | FOT | CTRQ | 2240 | TROUBLE SHOOTING ON WFD CRT, CRT TOOL STUCK INSIDE CSG. DECISION MADE TO L/D THE ASSY CRT/ CSG JT#05 IN ONE PIECE, TRY TO BREAK OUT CONNECTION BETWEEN JT#05 & JT#04 FOUND IT OVER TORQUED. CUT JT#05 & LD ASSY CRT/JT#05 & DISCONNECT JT#04 & L/D SAME. - L/D CRT TOOLS & R/U CONVENTIONAL RUNNING CASING EQUIPMENTS.
800 | 06/08/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 215.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
802 | 06/08/2022 | PA-785S | QTIF-269 | RIG | 08 Jun 0900 - 1230 | 3.5 | 3.5 | 897615 |  | RR | FOT | DWKS | 0 | RIG REPLACED TWO HOSES FOR LOW SPEED CLATCH AND AIR VENT VLAVE.
810 | 06/08/2022 | SINO-12L | HRDH-400 | SPS | 08 Jun 1900 - 2030 | 1.5 | 1.5 | 897695 |  | BHA | FOT | MWD | 7309 | TROUBLE SHOOTING MWD LOST SURVEY SIGNAL.
812 | 06/08/2022 | SINO-15L | ANDR-482 | TK1 | 06 Jun 0200 - 0500 | 12 | 39 | 897520 |  | DD | DFOR | RSS | 7994 | CAN NOT DROP INCLINATION TO ACHEIVE LANDING WELL WITH ICRUISE
814 | 06/08/2022 | SINO-27N | HWYH-466 | WBP | 24 May 0500 - 0500 | 23.5 | 367.75 | 897182 |  | TF | FOT | BP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
834 | 06/08/2022 | SND-2002 | WAQR-23 | HLH | 26 May 2000 - 0500 | 24 | 270 | 897098 |  | TF | FOT | HGRL | 10330 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES.
836 | 06/08/2022 | SND-2003 | RMTN-17 | HWP | 08 Jun 1500 - 0500 | 14 | 14 | 897677 |  | TF | FOT | WLT | 11299 | UNABLE TO CIRCULATE AFTER CONDUCTING 2ND SAMPLE.
838 | 06/08/2022 | SND-2006 | UTMN-3165 | ARM | 06 Jun 1930 - 0500 | 24 | 57.5 | 897558 |  | LROP | LTHI | BIT | 10563 | VERY LOW PENETRATION RATE
840 | 06/08/2022 | SP-110 | BRRI-562 | ARM | 08 Jun 1100 - 1500 | 4 | 4 | 897711 |  | WO | STOP | NA | 15096 | SUSPEND ALL OPERATION ON THE RIG UNTIL MEDIC AND AMBULANCE BACK TO RIG SITE .
841 | 06/08/2022 | SP-120 | MNIF-188 | RIG | 08 Jun 2245 - 2345 | 1 | 1 | 897698 |  | TF | HERR | TTRQ | 20970 | RETRACT AND SECURE CASING STABBING BOARD. DUE TO MISS COMMUNICATION BETWEEN DRILLER AND CASING STABBER, THE SPIDER ELEVATOR TOUCHED THE STABBING BOARD WHILE MOVING DOWN AND CAUSED IT TO BEND.
843 | 06/08/2022 | SP-120 | MNIF-188 | MSD | 08 Jun 0815 - 0915 | 1 | 1 | 897691 |  | TF | FOT | CTRQ | 20970 | EXCESS TIME TO ADJUST TORQUE GAUGE READING WITH THE JAM READING, REPLACE POWER TONG DUE TO FAILURE OF DIES.
844 | 06/08/2022 | SP-120 | MNIF-188 | RIG | 08 Jun 2245 - 2345 | 1 | 1 | 897698 |  | TF | HERR | TTRQ | 20970 | RETRACT AND SECURE CASING STABBING BOARD. DUE TO MISS COMMUNICATION BETWEEN DRILLER AND CASING STABBER, THE SPIDER ELEVATOR TOUCHED THE STABBING BOARD WHILE MOVING DOWN AND CAUSED IT TO BEND.
846 | 06/08/2022 | SP-229 | ABHD-7 | RIG | 07 Jun 2330 - 2200 | 17 | 22.5 | 897613 |  | BHA | ETRQ | BHA | 0 | HAD HIGH TORQUE WHEN MILLING OUT LANDING COLLAR, LOST WT AND PRESSURE
848 | 06/08/2022 | SP-261 | HZEM-160214 | ITS | 06 Jun 1700 - 1515 | 2.25 | 3.25 | 897516 |  | JF | XTRI | CTRQ | 250 | REPLACE DAMAGED CRT PACKER RUBBER.
850 | 06/08/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0500 | 5.5 | 5.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
852 | 06/08/2022 | SSA-5859 | HWYH-1222 | RIG | 08 Jun 1700 - 1900 | 2 | 2 | 897696 |  | RR | FOT | DWKS | 8743 | DRAW WORKS STOPPED DUE TO OVER HEAT INSIDE PCR BEACAUSE OF FAILURE IN AIR CONDITION.
854 | 06/08/2022 | SSA-5962 | HRDH-2230 | GOC | 08 Jun 2300 - 0330 | 4.5 | 4.5 | 897618 |  | TF | FOT | TTRQ | 14389 | AL-GHAITH JAM UNIT FAILURE.
856 | 06/08/2022 | SSA-5971 | HRDH-2247 | BHI | 08 Jun 1530 - 0500 | 13.5 | 13.5 | 897693 |  | BHA | FOT | RSS | 5573 | BAKER HUGHES DIRECTIONAL TOOLS LOST SIGNAL
858 | 06/08/2022 | T914 | UTMN-1272 | RIG | 08 Jun 0230 - 0500 | 2.5 | 2.5 | 897697 |  | RR | FOT | DWKS | 5747 | FAILURE IN TOP DRIVER BRAKE SYSTEM.
860 | 06/09/2022 | ADC-52 | SDGM-1185 | ARM | 07 Jun 0200 - 0045 | 19.75 | 46.75 | 897634 |  | TH | NARW | NA | 815 | GOT OBSTRUCTION @ 815' WHILE RUNNING 18-5/8" CASING. WORK STRING AND TRY TO PASS WITH CIRCULATION 500 GPM X 160 PSI AND APPLY 60KLBS SOW WITHOUT SUCCESS.
862 | 06/09/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 279 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
864 | 06/09/2022 | ADES-13 | HRDH-157 | RIG | 09 Jun 0030 - 0300 | 2.5 | 2.5 | 897745 |  | RR | FOT | TDS | 0 | DAMAGE ON TDS POWER CABLE PLUG HOUSING
866 | 06/09/2022 | ADM-261 | LWHH-9 | SPS | 08 Jun 1500 - 1300 | 8 | 22 | 897694 |  | BHA | FOT | RSS | 7612 | SECOND FAILURE FOR HALLIBURTON RSS LOST COMMUNICATION WITH SURFACE, TURBINE RSS SIGNAL STOPPED RESPONDING.
868 | 06/09/2022 | ARO-2003 | MNIF-30 | HCB | 09 Jun 1745 - 0500 | 11.25 | 11.25 | 897746 |  | TF | FOT | BP | 0 | UNABLE TO SET AND TEST 7" RBP
870 | 06/09/2022 | ARO-4001 | MRJN-538 | WWD | 09 Jun 1630 - 0500 | 9.75 | 9.75 | 897832 |  | TF | FOT | WPSTK | 11094 | WEATHERFORD WHIPSTOCK RELEASED AFTER SETTING.
872 | 06/09/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 6 | 6 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
889 | 06/09/2022 | DQ-48 | KHRS-1420 | RIG | 09 Jun 0600 - 0800 | 2 | 2 | 897771 |  | RR | FOT | TDS | 13800 | AFTER KELLY DOWN DRILLER CANNOT BREAKOUT & DISCONNECT STAND TO MAKE CONNECTION,TDS ENGINEER STARTED TROUBLESHOOTING, FOUND ONE CABLE WAS POOR CONTACT WITH LOCKING DETECTOR, THEN HE ISOLATED THIS CABLE & ACTIVATED THE BACKUP CABLE. TDS BACK TO WORK NORMALLY.
891 | 06/09/2022 | ENS-108 | ZULF-2015 | RIG | 09 Jun 0030 - 0500 | 4.5 | 4.5 | 897792 |  | RR | FOT | TDS | 1870 | WHILE DRILLING, TDS DEVELOPED AN INTERMITTENT ELECTRICAL FAULT ON THE TDS MOTORS RESULTING IN INTERMITTENT LOSS OF ROTATION.
893 | 06/09/2022 | JACK-202 | HMYM-844 | RIG | 09 Jun 1315 - 1345 | .5 | .5 | 897744 |  | RR | FOT | RSSS | 1571 | FIX AIR HOSE LEAKING ON DRILLER CONSOLE PANEL.
894 | 06/09/2022 | MP-1 | MRJN-79 | BHI | 09 Jun 0115 - 0200 | .75 | .75 | 897834 |  | BHA | FOT | LWD | 9146 | HAD BAD DECODING FROM LWD TOOLS, SO STOPPED DRLG TILL TROUBLESHOOTED SAME & GOT RELIABLE DATA
896 | 06/09/2022 | MP-1 | MRJN-79 | ARM | 07 Jun 2100 - 0545 | .75 | 32.25 | 897651 |  | DD | ETRQ | RSS | 8560 | ENCOUNTERED ERRATIC TORQUE VALUES WHILE DRLG (5-14 KLB.FT) , WHICH RESULTED IN VERY POOR ROP (LESS THAN 15 FT/HR), DUE TO INABILITY TO PUT WOB MORE THAN 13 KLBS (ERRATIC WITH 15 KFT-LBS). FOUND 1 EA BIT NOZZLE PLUGGED WITH FMN CUTTINGS.
897 | 06/09/2022 | MP-1 | MRJN-79 | BHI | 09 Jun 0115 - 0200 | .75 | .75 | 897834 |  | BHA | FOT | LWD | 9146 | HAD BAD DECODING FROM LWD TOOLS, SO STOPPED DRLG TILL TROUBLESHOOTED SAME & GOT RELIABLE DATA
899 | 06/09/2022 | NADRU-1 | BRRI-1217 | SCT | 08 Jun 0530 - 0500 | 24 | 36.75 | 897676 |  | TF | FOT | CTAC | 12700 | MINOR HYDRAULIC OIL LEAK IN SLB INJECTOR TRACTION CYLINDERS. TROUBLESHOOT TO FIX THE LEAK WITH NO SUCCESS. POOH AND REPLACE INJECTOR WITH A NEW ONE.
901 | 06/09/2022 | NBR-115S | HWYH-1220 | SDM | 08 Jun 1445 - 2300 | 16.5 | 30.75 | 897673 |  | BHA | FOT | MWD | 15194 | LOST SIGNAL IN SLB MWD TOOL.
903 | 06/09/2022 | NBR-196S | SDGM-1235 | SJC | 08 Jun 1630 - 0500 | 7 | 12 | 897674 |  | CMT | CFST | NA | 4540 | 18 5/8" CSING 2ND STAGE CMT FLASH SET WHILE DISPLACEMENT.
905 | 06/09/2022 | NBR-263S | QTIF-736 | RIG | 09 Jun 1100 - 2230 | 11.5 | 11.5 | 897831 |  | RR | FOT | TDS | 4540 | TDS GRAPPLE DIES ELEMENT BROKEN. CHC AND POOH TO 13-3/8" CSG SHOE TO REPLACE.
907 | 06/09/2022 | NBR-797S | UTMN-3130 | RIG | 09 Jun 1915 - 2300 | 3.75 | 3.75 | 897742 |  | RR | FOT | CATW | 2730 | CAT WALK MACHINE NOT WORKING WHILE PICKING UP 4" DP.
909 | 06/09/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 239.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
911 | 06/09/2022 | PA-785S | QTIF-269 | RIG | 09 Jun 0130 - 0300 | 1.5 | 1.5 | 897740 |  | RR | FOT | DWKS | 0 | CHANGE VALVE ON LOW CLUTCH AT DRAWWORKS.
913 | 06/09/2022 | PA-861S | HWYH-946 | HCM | 09 Jun 1700 - 2300 | 6 | 6 | 897811 |  | JF | FOT | SQZ | 0 | HALLIBURTON CMT UNIT FAIL TO HOLD PRESSURE. GREASED AL VALVES & TROBLE SHOOT LEAKING CEMENT UNIT MULTIPLE TIMES. NO SUCCSESS
914 | 06/09/2022 | RBP-50A | KARN-51 | ARM | 09 Jun 1300 - 1815 | 3.25 | 3.25 | 897736 |  | WON | WTHR | NA | 11775 | WAIT ON WEATHER, UNABLE TO FLOW BACK DUE TO UNFAVORABLE WIND CONDITION.
916 | 06/09/2022 | RBP-50A | KARN-51 | HTS | 09 Jun 0500 - 0630 | 1.5 | 1.5 | 897735 |  | TF | FOT | FLR | 11775 | TROUBLESHOOT FAULTY IGNITION SYSTEM FOR PILOT FLAMES. FOUND FAULT IN WIRING JUNCTION BOX. INSTALL NEW WIRE AND RE-CONNECT. TEST IGNITION SYSTEM 2X, GOOD.
917 | 06/09/2022 | RBP-50A | KARN-51 | ARM | 09 Jun 1300 - 1815 | 3.25 | 3.25 | 897736 |  | WON | WTHR | NA | 11775 | WAIT ON WEATHER, UNABLE TO FLOW BACK DUE TO UNFAVORABLE WIND CONDITION.
919 | 06/09/2022 | SDA | MRJN-732 | HTS | 09 Jun 1700 - 1830 | 1.5 | 1.5 | 897738 |  | TF | FOT | WTSE | 5750 | OBSERVE LEAKAGE IN SURG TANK DRAIN LINE.
925 | 06/09/2022 | SINO-15L | ANDR-482 | TK1 | 06 Jun 0200 - 2230 | 17.5 | 56.5 | 897520 |  | DD | DFOR | RSS | 7994 | CAN NOT DROP INCLINATION TO ACHEIVE LANDING WELL WITH ICRUISE
927 | 06/09/2022 | SINO-27N | HWYH-466 | WBP | 24 May 0500 - 0500 | 23.5 | 391.25 | 897182 |  | TF | FOT | BP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
929 | 06/09/2022 | SND-2002 | WAQR-23 | HLH | 26 May 2000 - 0500 | 24 | 264 | 897098 |  | TF | FOT | HGRL | 10330 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES.
931 | 06/09/2022 | SND-2006 | UTMN-3165 | ARM | 06 Jun 1930 - 0800 | 3 | 60.5 | 897558 |  | LROP | LTHI | BIT | 10563 | VERY LOW PENETRATION RATE
933 | 06/09/2022 | SP-258 | HZEM-450202 | SDM | 09 Jun 2145 - 0500 | 7.25 | 7.25 | 897793 |  | BHA | FOT | RSS | 9223 | RSS JAMMED AND UNABLE TO KICK-OFF. APPLY ANTI-JAMMING PROCEDURE AS PER SLB. NO SUCCESS. POH TO CHANGE RSS BHA.
935 | 06/09/2022 | SP-306 | MNIF-196 | WCR | 09 Jun 1300 - 1500 | 2 | 2 | 897737 |  | TF | XTTE | CTRQ | 10084 | EXCESS TIME FOR REPLACING SEVERAL 7" CSG JOINTS (26#, L-80, JPC-2) DUE TO NOT ACHIEVING THE ACCEPTED SHOULDER GRAPH AT JAM UNIT.
937 | 06/09/2022 | SSA-102 | QTIF-696 | SJT | 09 Jun 1700 - 0500 | 12 | 12 | 897772 |  | STUK | STBH | CTAC | 15975 | TAQA CT GOT STUCK WHILE RIH IN L-2
939 | 06/09/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0500 | 24 | 29.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
941 | 06/09/2022 | SSA-5892 | SMNH-521700 | BHI | 09 Jun 1430 - 0500 | 14.5 | 14.5 | 897751 |  | BHA | FOT | MWD | 0 | BAKER MWD PULSER STOP TRANSMITTING SIGNAL
943 | 06/09/2022 | SSA-5964 | HRDH-1383 | WWL | 09 Jun 0100 - 0500 | 4 | 4 | 897851 |  | STUK | HINW | WLT | 7800 | WFRD WL RIH TO SET HALL 4.5" EZSV-BP @ 12,140'. GOT OBSTRUCTION @ 7,800' WITH SUDDEN DROP 230 LBS IN TENSION, ATTEMPTED TO PICK UP, WL TOOL WITH EZSV-BP STUCK IN HOLE.
944 | 06/09/2022 | SSA-5971 | HRDH-2247 | RIG | 09 Jun 1700 - 1930 | 2.5 | 2.5 | 897733 |  | RR | FOT | CSYS | 5624 | OBSERVE LEAK ON WASH PIPE. STOP DRILLING AND POOH INTO 13-3/8" SHOE. REPLACE WASH PIPE SEAL AND P/TEST LINES TO 4000 PSI - OK. RIH AND WASH DOWN LAST STAND TO BOTTOM.
946 | 06/09/2022 | SSA-5971 | HRDH-2247 | BHI | 08 Jun 1530 - 1400 | 8.5 | 22 | 897693 |  | BHA | FOT | MWD | 5573 | BAKER HUGHES DIRECTIONAL TOOLS LOST SIGNAL
947 | 06/09/2022 | SSA-5971 | HRDH-2247 | RIG | 09 Jun 1700 - 1930 | 2.5 | 2.5 | 897733 |  | RR | FOT | CSYS | 5624 | OBSERVE LEAK ON WASH PIPE. STOP DRILLING AND POOH INTO 13-3/8" SHOE. REPLACE WASH PIPE SEAL AND P/TEST LINES TO 4000 PSI - OK. RIH AND WASH DOWN LAST STAND TO BOTTOM.
949 | 06/09/2022 | STY-038 | ZULF-2086 | RIG | 09 Jun 1100 - 2300 | 11.5 | 11.5 | 897739 |  | RR | FOT | TDS | 8136 | CHANGE OUT WASH PIPE ON TDS.
951 | 06/09/2022 | T901 | JLMN-47 | GCD | 09 Jun 1830 - 2330 | 5 | 5 | 897743 |  | TF | FOT | GYRO | 2090 | GYRO SURVEY FAILED.
953 | 06/09/2022 | T914 | UTMN-1272 | RIG | 08 Jun 0230 - 1630 | 11.5 | 14 | 897697 |  | RR | FOT | DWKS | 5747 | MAL-FUNCTION IN TOP DRIVER BRAKE SYSTEM.
954 | 06/10/2022 | ADC-17 | ZULF-1217 | SPS | 10 Jun 1930 - 0500 | 9.5 | 9.5 | 897914 |  | BHA | FOT | LWD | 8719 | SPS LOST SIGNAL FROM LWD DENISTY IMAGE TOOL, SPS MWD ENG TROUBLESHOOT TOOL WITH NO SUCCESS, DECISION MADE TO POOH & REPLACE FAULTY LWD TOOL.
956 | 06/10/2022 | ADC-17 | ZULF-1217 | BR1 | 10 Jun 1845 - 1930 | .75 | .75 | 897913 |  | WO | SRVC | NA | 8719 | LOST WELLLINK REALTIME CONNECTION
957 | 06/10/2022 | ADC-17 | ZULF-1217 | SPS | 10 Jun 1930 - 0500 | 9.5 | 9.5 | 897914 |  | BHA | FOT | LWD | 8719 | SPS LOST SIGNAL FROM LWD DENISTY IMAGE TOOL, SPS MWD ENG TROUBLESHOOT TOOL WITH NO SUCCESS, DECISION MADE TO POOH & REPLACE FAULTY LWD TOOL.
959 | 06/10/2022 | ADC-23 | KIDN-23 | ARM | 10 Jun 2000 - 0500 | 9 | 9 | 897912 |  | TF | FOT | CSG | 4000 | ATEMPT TO BREAK CIRCULATION AFTER PICKING UP DVT, PRESSURED UP WITH NO RETURN FLOW. AFTER MULTIPLE ATTEMPTS REQUIRING 1,000 PSI TO OBTAIN CIRCULATION.
961 | 06/10/2022 | ADC-31 | SDGM-1181 | RIG | 10 Jun 1500 - 1530 | .5 | .5 | 897872 |  | TF | FOT | MLS | 12500 | REPETITIVE TRIP TANK EXPANSION RUBBER LEAKS
963 | 06/10/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 303 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
965 | 06/10/2022 | ARO-2003 | MNIF-30 | HCB | 09 Jun 1745 - 0100 | 20 | 31.25 | 897746 |  | TF | FOT | BP | 0 | UNABLE TO SET AND TEST 7" RBP
966 | 06/10/2022 | ARO-4001 | MRJN-538 | WWD | 10 Jun 2245 - 0500 | 6.25 | 6.25 | 897895 |  | TF | FOT | WPSTK | 11089 | UNABLE TO SET WEATHERFORD WHIPSTOCK
968 | 06/10/2022 | ARO-4001 | MRJN-538 | WWD | 09 Jun 1630 - 2245 | 17.75 | 27.5 | 897832 |  | TF | FOT | WPSTK | 11094 | WEATHERFORD WHIPSTOCK RELEASED AFTER SETTING.
969 | 06/10/2022 | ARO-4001 | MRJN-538 | WWD | 10 Jun 2245 - 0500 | 6.25 | 6.25 | 897895 |  | TF | FOT | WPSTK | 11089 | UNABLE TO SET WEATHERFORD WHIPSTOCK
971 | 06/10/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 30 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
972 | 06/10/2022 | ENS-108 | ZULF-2015 | SDM | 10 Jun 2030 - 2100 | .5 | .5 | 897892 |  | BHA | FOT | MWD | 2205 | LOST MWD SIGNAL
974 | 06/10/2022 | ENS-108 | ZULF-2015 | RIG | 09 Jun 0030 - 1515 | 10.25 | 14.75 | 897792 |  | RR | FOT | TDS | 1870 | WHILE DRILLING, TDS DEVELOPED AN INTERMITTENT ELECTRICAL FAULT ON THE TDS MOTORS RESULTING IN INTERMITTENT LOSS OF ROTATION.
975 | 06/10/2022 | ENS-108 | ZULF-2015 | SDM | 10 Jun 2030 - 2100 | .5 | .5 | 897892 |  | BHA | FOT | MWD | 2205 | LOST MWD SIGNAL
977 | 06/10/2022 | NADRU-1 | BRRI-1217 | SCT | 08 Jun 0545 - 1615 | 11.25 | 47.75 | 897676 |  | TF | FOT | CTAC | 12700 | MINOR HYDRAULIC OIL LEAK IN SLB INJECTOR TRACTION CYLINDERS. TROUBLESHOOT TO FIX THE LEAK WITH NO SUCCESS. POOH AND REPLACE INJECTOR WITH A NEW ONE.
979 | 06/10/2022 | NBR-196S | SDGM-1235 | SJC | 08 Jun 1630 - 2345 | 18.75 | 30.75 | 897674 |  | CMT | CFST | NA | 4540 | 18 5/8" CSING 2ND STAGE CMT FLASH SET WHILE DISPLACEMENT.
981 | 06/10/2022 | NBR-263S | QTIF-736 | RIG | 10 Jun 0530 - 1300 | 5 | 5 | 897747 |  | RR | FPMP | MPMP | 5016 | HAD MUD PUMP PRESSURE FLUSTUATING. -CHECKED AND CLEANED MUD PUMPS SUCTION SCREENS. -FIXED MUD PUMP-3 SUPERCHARGE PUMP ELECTRICAL PROBLEM. -CHANGED PISTON IN MUD PUMP.
983 | 06/10/2022 | NBR-654S | HRDH-1150 | RIG | 10 Jun 0200 - 0330 | 1.5 | 1.5 | 897915 |  | BOP | FOT | BOP | 2240 | EXCESS TIME FOR BOP TEST DUE TO MULTIPLE LEAKS WHILE TESTING. - LEAKED CHOKE LINE TARGET FLANMGE GASKET - MP KILL LINE CHECK VALVE - MUD CROSS
985 | 06/10/2022 | OFGRL | KARN-19 | ARM | 10 Jun 1930 - 0500 | 9.5 | 9.5 | 897932 |  | WON | WTHR | NA | 0 | DUE TO HIGH WINDS, NOT ABLE TO WORK CRANES FOR SLICKLINE OPERATIONS.
987 | 06/10/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 263.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
993 | 06/10/2022 | SINO-12L | HRDH-400 | SPS | 10 Jun 1900 - 0500 | 9.5 | 9.5 | 897911 |  | BHA | FOT | LWD | 10564 | SPS RESTIVITY TOOL FAILURE
995 | 06/10/2022 | SINO-27N | HWYH-466 | WBP | 24 May 0500 - 1630 | 11 | 402.25 | 897182 |  | TF | FOT | BP | 7515 | WFD 7" HDL PKR GOT STUCK WHILE POOH.
997 | 06/10/2022 | SND-1502 | HRDH-487 | HWP | 10 Jun 1430 - 2200 | 7.5 | 7.5 | 897894 |  | TF | FOT | WLT | 7586 | HALL LOGGING TOOL FAILURE.
999 | 06/10/2022 | SND-2002 | WAQR-23 | ARM | 27 May 2300 - 1000 | 5 | 272.5 | 897731 |  | LCIR | UVLC | NA | 10330 | ENCOUNTERED COMPLETE LOSS OF CIRCULATION AFTER DRILLING LANDING COLLAR.
1001 | 06/10/2022 | SND-2003 | RMTN-17 | EMC | 10 Jun 0100 - 0500 | 4 | 4 | 897896 |  | MUD | HSCM | NA | 10114 | UNCLEANED MUD SUCTION LINES CONTAMINATED WITH LCM (NUT PLUG) PLUGGED THE DRILL STRING.
1003 | 06/10/2022 | SP-258 | HZEM-450202 | SDM | 09 Jun 2145 - 1745 | 12.75 | 20 | 897793 |  | BHA | FOT | RSS | 9223 | RSS JAMMED AND UNABLE TO KICK-OFF. APPLY ANTI-JAMMING PROCEDURE AS PER SLB. NO SUCCESS. POH TO CHANGE RSS BHA.
1005 | 06/10/2022 | SP-262 | HZEM-140812 | BHI | 10 Jun 0945 - 0400 | 18.25 | 18.25 | 897893 |  | BHA | FOT | RSS | 10537 | LOST SIGNAL ON RSS TOOLS, POH TO CHANGE RSS ASSY.
1007 | 06/10/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0500 | 24 | 53.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
1008 | 06/10/2022 | SSA-5892 | SMNH-521700 | BHI | 09 Jun 1430 - 2230 | 17.5 | 32 | 897751 |  | BHA | FOT | MWD | 0 | BAKER MWD PULSER STOP TRANSMITTING SIGNAL
1010 | 06/10/2022 | SSA-5892 | SMNH-521700 | BHI | 10 Jun 2230 - 0500 | 6.5 | 6.5 | 897748 |  | BHA | FOT | MWD | 20142 | MWD COMMUNICATION PORT COVER THREAD DAMAGE.
1011 | 06/10/2022 | SSA-5892 | SMNH-521700 | BHI | 09 Jun 1430 - 2230 | 17.5 | 32 | 897751 |  | BHA | FOT | MWD | 0 | BAKER MWD PULSER STOP TRANSMITTING SIGNAL
1013 | 06/10/2022 | SSA-5964 | HRDH-1383 | WWL | 09 Jun 0100 - 0500 | 24 | 28 | 897851 |  | STUK | HINW | WLT | 7810 | WFRD WL RIH TO SET HALL 4.5" EZSV-BP @ 12,140'. GOT OBSTRUCTION @ 7,800' WITH SUDDEN DROP 230 LBS IN TENSION, ATTEMPTED TO PICK UP, WL TOOL WITH EZSV-BP STUCK IN HOLE.
1015 | 06/10/2022 | SSA-5970 | UTMN-2340 | RIG | 10 Jun 1530 - 1730 | 2 | 2 | 897891 |  | RR | FOT | MPMP | 1970 | REPAIR ON MUD PUMP.
1017 | 06/10/2022 | T902 | HZEM-162404 | RIG | 10 Jun 2200 - 0500 | 7 | 7 | 897931 |  | TF | FOT | TESTT | 18044 | SEVERAL LEAKS AND TEST UNIT FAILURE DURING BOP TEST.
1019 | 06/11/2022 | ADC-17 | ZULF-1217 | SPS | 10 Jun 1930 - 0445 | 23.75 | 33.25 | 897914 |  | BHA | FOT | LWD | 8719 | SPS LOST SIGNAL FROM LWD DENISTY IMAGE TOOL, SPS TROUBLESHOOT TOOL WITH NO SUCCESS ( TOTAL DRLG 14.0 HRS/ TOTAL CIRCULATING 24.0 HRS).
1021 | 06/11/2022 | ADC-23 | KIDN-23 | ARM | 10 Jun 2000 - 0500 | 24 | 33 | 897912 |  | TF | FOT | CSG | 4000 | ATEMPT TO BREAK CIRCULATION AFTER PICKING JOINT # 73, PRESSURED UP WITH NO RETURN FLOW. AFTER MULTIPLE ATTEMPTS REQUIRING 1,000 PSI TO OBTAIN CIRCULATION.
1023 | 06/11/2022 | ADC-34 | UTMN-2316 | SPS | 11 Jun 0000 - 0500 | 5 | 5 | 897953 |  | BHA | FOT | RSS | 13976 | LOST RSS SIGNAL
1025 | 06/11/2022 | ADC-36 | SDGM-1236 | BCR | 11 Jun 1400 - 2100 | 7 | 7 | 897933 |  | TF | FOT | CTRQ | 4485 | TOTAL LOST TIME ON BAKER DUE TO EQUIPMENT FAILURE MANY TIMES & DELAY IN OPERATION WHILE RIH 18-5/8" CSG.
1027 | 06/11/2022 | ADC-50 | SFNY-1176 | RIG | 11 Jun 1230 - 1430 | 2 | 2 | 897975 |  | TF | FOT | SFLN | 1269 | AFTER SETTING CASING SLIPS, TRIED TO CIRCULATE, HAD PRESSURE SPIKE DUE TO RIG SURFACE HOSE PLUGGED
1054 | 06/11/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 327 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
1056 | 06/11/2022 | ADC-70 | BRRI-1204 | ARM | 11 Jun 2200 - 2245 | .75 | .75 | 897954 |  | LCIR | CFFM | MDCAP | 2230 | ENCOUNTERED TOTAL LOSSES AT 2230 FT. PUMP 100 BBLS 90 PCF INHIBITED MUD CAP IN ANNULUS. SWITCHED TO TREATED SEA WATER WITH GEL SWEEPS.
1058 | 06/11/2022 | ARO-4001 | MRJN-538 | WWD | 10 Jun 2245 - 0330 | 22.5 | 28.75 | 897895 |  | TF | FOT | WPSTK | 11089 | UNABLE TO SET WEATHERFORD 2ND WHIPSTOCK
1060 | 06/11/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 54 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1062 | 06/11/2022 | OFGRL | KARN-19 | ARM | 10 Jun 1930 - 0500 | 24 | 33.5 | 897932 |  | WON | WTHR | NA | 0 | DUE TO HIGH WINDS, NOT ABLE TO WORK CRANES FOR SLICKLINE OPERATIONS.
1064 | 06/11/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 287.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1078 | 06/11/2022 | SND-2003 | RMTN-17 | RIG | 10 Jun 0100 - 0500 | 24 | 28 | 897896 |  | MUD | HSCM | NA | 10114 | UNCLEANED MUD SUCTION LINES CONTAMINATED WITH SOLIDS PLUGGED THE DRILL STRING WITH MARBLE.
1080 | 06/11/2022 | SND-2006 | UTMN-3165 | RIG | 11 Jun 2230 - 0230 | 4 | 4 | 897952 |  | RR | FOT | DWKS | 11030 | TRACTOR MOTOR FAILED, REPLACED WITH A NEW ONE.
1082 | 06/11/2022 | SP-120 | MNIF-188 | MSD | 11 Jun 0730 - 0500 | 21.5 | 21.5 | 897951 |  | HSEI | UNKN | NA | 20970 | RIG SHUT-DOWN MEANWHILE DOECD INVESTIGATE THE STABBING BOARD INCIDENT (ASSET DAMAGE) OCCURRED WHILE RUNNING 7" LINER ON JUNE 07.
1084 | 06/11/2022 | SP-262 | HZEM-140812 | NPC | 11 Jun 1045 - 0500 | 18.25 | 18.25 | 897973 |  | TF | TOWC | JARS | 10821 | WHILE DRILLING THE 8-1/2" CURVE OBSERVED SUDDENLY 350 PSI PRESSURE DROP. PICKED UP OFF BOTTOM AND CHECKED ALL SURFACE EQUIPMENT AND MUD PUMPS OK, POOH AND OBSERVED TWIST OFF ON NAPESCO DRILLING JAR.
1086 | 06/11/2022 | SSA-102 | QTIF-696 | SJT | 11 Jun 2200 - 0030 | 2.5 | 2.5 | 897974 |  | HSEI | UNKN | NA | 0 | WATER & H2S FLOW TO SURFACE AFTER POOH TAQA MLT ASSY.
1088 | 06/11/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 19 | 19 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1090 | 06/11/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0500 | 24 | 77.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
1091 | 06/11/2022 | SSA-5892 | SMNH-521700 | BHI | 09 Jun 1430 - 0500 | 18 | 50 | 897751 |  | BHA | FOT | MWD | 0 | BAKER MWD PULSER STOP TRANSMITTING SIGNAL
1093 | 06/11/2022 | SSA-5892 | SMNH-521700 | BHI | 10 Jun 2230 - 1100 | 6 | 12.5 | 897748 |  | BHA | FOT | MWD | 20142 | MWD COMMUNICATION PORT COVER THREAD DAMAGE.
1094 | 06/11/2022 | SSA-5892 | SMNH-521700 | BHI | 09 Jun 1430 - 0500 | 18 | 50 | 897751 |  | BHA | FOT | MWD | 0 | BAKER MWD PULSER STOP TRANSMITTING SIGNAL
1096 | 06/11/2022 | SSA-5914 | WDYH-80 | RIG | 10 Jun 1700 - 0500 | 24 | 34.25 | 897991 |  | BOP | FOT | RAMS | 17117 | AFTER OPENING BLIND SHEAR RAMS, WE NOTICED ONE SIDE DIDN'T FULLY OPENED.
1098 | 06/11/2022 | SSA-5964 | HRDH-1383 | WWL | 09 Jun 0100 - 0500 | 24 | 52 | 897851 |  | STUK | HINW | WLT | 7810 | WFRD WL RIH TO SET HALL 4.5" EZSV-BP @ 12,140'. GOT OBSTRUCTION @ 7,800' WITH SUDDEN DROP 230 LBS IN TENSION, ATTEMPTED TO PICK UP, WL TOOL WITH EZSV-BP STUCK IN HOLE.
1099 | 06/11/2022 | SSA-5970 | UTMN-2340 | RIG | 11 Jun 1600 - 1630 | .5 | .5 | 897972 |  | RR | FOT | TDS | 2385 | REPAIR ON TDS COMMUNICATION CABLE.
1101 | 06/11/2022 | SSA-5970 | UTMN-2340 | RIG | 11 Jun 1215 - 1300 | .75 | .75 | 897971 |  | RR | FOT | DWKS | 2370 | REPAIR ON DRAW WORK HPU BRAKE.
1102 | 06/11/2022 | SSA-5970 | UTMN-2340 | RIG | 11 Jun 1600 - 1630 | .5 | .5 | 897972 |  | RR | FOT | TDS | 2385 | REPAIR ON TDS COMMUNICATION CABLE.
1104 | 06/11/2022 | T902 | HZEM-162404 | RIG | 10 Jun 2200 - 1100 | 6 | 13 | 897931 |  | TF | FOT | TESTT | 18044 | SEVERAL LEAKS AND TEST UNIT FAILURE DURING BOP TEST.
1106 | 06/12/2022 | ADC-23 | KIDN-23 | ARM | 10 Jun 2000 - 0500 | 24 | 57 | 897912 |  | TF | FOT | CSG | 4000 | ATEMPT TO BREAK CIRCULATION AFTER PICKING JOINT # 73, PRESSURED UP WITH NO RETURN FLOW. AFTER MULTIPLE ATTEMPTS REQUIRING 1,000 PSI TO OBTAIN CIRCULATION.
1108 | 06/12/2022 | ADC-34 | UTMN-2316 | SPS | 11 Jun 0000 - 0500 | 24 | 29 | 897953 |  | BHA | FOT | RSS | 13976 | LOST RSS SIGNAL
1119 | 06/12/2022 | ADC-57L | FDHL-158 | ARM | 12 Jun 0900 - 1900 | 10 | 10 | 898015 |  | WON | WTHR | NA | 15329 | WAIT ON WEATHER DUE TO SAND STORM (WIND SPEED 40-60 KM/HR)
1124 | 06/12/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 351 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
1126 | 06/12/2022 | ADC-68L | ABHD-176 | TK3 | 12 Jun 1230 - 1700 | 4.5 | 4.5 | 897945 |  | WON | WTHR | NA | 1085 | WAIT ON WEATHER. HIGH WIND SPEED, 60-70 KM/HR.
1128 | 06/12/2022 | AOD-1 | ZULF-694 | RIG | 12 Jun 1015 - 1045 | .5 | .5 | 897938 |  | RR | FOT | CSYS | 5200 | SHAKERS UNABLE TO HANDLE REQUIRED FLOW RATE @ 1000 GPM.
1130 | 06/12/2022 | EXL-IA | SFNY-4240 | BAW | 12 Jun 0415 - 0500 | .75 | .75 | 898016 |  | TF | FOT | WLT | 8479 | HAD DOWNHOLE FAILURE IN W/L HYDRAULIC POWER MODULE @ 5876'.
1132 | 06/12/2022 | OFGRL | KARN-19 | ARM | 10 Jun 1930 - 0500 | 24 | 57.5 | 897932 |  | WON | WTHR | NA | 0 | DUE TO HIGH WINDS, NOT ABLE TO WORK CRANES FOR SLICKLINE OPERATIONS.
1134 | 06/12/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 311.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1136 | 06/12/2022 | PA-866S | SHHB-2 | RIG | 12 Jun 0500 - 0500 | 24 | 24 | 897942 |  | RR | FOT | DWKS | 11150 | GROUND FAULT DETECTED ON DRAWWORKS "A" MOTOR
1138 | 06/12/2022 | PN-9 | MRJN-677 | ARM | 12 Jun 0930 - 0500 | 19.5 | 19.5 | 897943 |  | WON | WTHR | NA | 0 | WOW FOR RIG MOVE TO MRJN-670/679 PF.
1140 | 06/12/2022 | SCTD-2 | HRDH-2307 | SDM | 11 Jun 0030 - 0500 | 16.5 | 21 | 897937 |  | BHA | FOT | MMOT | 12575 | TURBINE STALLED WHILE DRILLING, ATTEMPT TO POH STRING GOT STUCK.
1142 | 06/12/2022 | SND-2003 | RMTN-17 | RIG | 10 Jun 0100 - 0200 | 21 | 49 | 897896 |  | MUD | HSCM | NA | 10114 | UNCLEANED MUD SUCTION LINES CONTAMINATED WITH SOLIDS PLUGGED THE DRILL STRING WITH MARBLE.
1144 | 06/12/2022 | SP-120 | MNIF-188 | MSD | 11 Jun 0730 - 1000 | 5 | 26.5 | 897951 |  | HSEI | UNKN | NA | 20970 | RIG SHUT-DOWN MEANWHILE DOECD INVESTIGATE THE STABBING BOARD INCIDENT (ASSET DAMAGE) OCCURRED WHILE RUNNING 7" LINER ON JUNE 07.
1146 | 06/12/2022 | SP-124 | FDHL-141 | ARM | 12 Jun 1130 - 1400 | 2.5 | 2.5 | 897944 |  | WON | WTHR | NA | 0 | SAND STORM AND WINDY
1148 | 06/12/2022 | SP-262 | HZEM-140812 | NPC | 11 Jun 1045 - 0500 | 24 | 42.25 | 897973 |  | TF | TOWC | JARS | 10821 | WHILE DRILLING THE 8-1/2" CURVE OBSERVED SUDDENLY 350 PSI PRESSURE DROP. PICKED UP OFF BOTTOM AND CHECKED ALL SURFACE EQUIPMENT AND MUD PUMPS OK, POOH AND OBSERVED TWIST OFF ON NAPESCO DRILLING JAR.
1149 | 06/12/2022 | SSA-102 | QTIF-696 | AZ1 | 12 Jun 1600 - 2030 | 4.5 | 4.5 | 898013 |  | TF | FOT | WLT | 800 | LOST COMMUNICATION WITH PLT ASSY.
1151 | 06/12/2022 | SSA-102 | QTIF-696 | SJT | 12 Jun 1130 - 1230 | 1 | 1 | 897941 |  | JF | HERR | CTAC | 0 | HELD STAND DOWN MEETING BY NAODD DIV#2 SUPT, TAREK ELDEEB, INCLUDE ALL RIG KEY PERSONNEL & TAQA CT SUPERVISORS. HIGHLIGHTED THE H2S RELEASE INCIDENT & LESSONS LEARNED.
1152 | 06/12/2022 | SSA-102 | QTIF-696 | AZ1 | 12 Jun 1600 - 2030 | 4.5 | 4.5 | 898013 |  | TF | FOT | WLT | 800 | LOST COMMUNICATION WITH PLT ASSY.
1154 | 06/12/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 43 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1156 | 06/12/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0500 | 24 | 101.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
1158 | 06/12/2022 | SSA-303 | HRDH-2306 | BLH | 11 Jun 0000 - 0500 | 24 | 29 | 897936 |  | TF | FOT | HGRL | 13120 | MECHANICAL FAILURE OF SLIPS 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY
1160 | 06/12/2022 | SSA-5892 | SMNH-521700 | BHI | 09 Jun 1430 - 1000 | 5 | 55 | 897751 |  | BHA | FOT | MWD | 0 | BAKER MWD PULSER STOP TRANSMITTING SIGNAL
1162 | 06/12/2022 | SSA-5914 | WDYH-80 | RIG | 10 Jun 1700 - 0500 | 24 | 58.25 | 897991 |  | BOP | FOT | RAMS | 17117 | AFTER OPENING BLIND SHEAR RAMS, NOTICED ONE SIDE DIDN'T FULLY OPENED.
1164 | 06/12/2022 | SSA-5964 | HRDH-1383 | WWL | 09 Jun 0100 - 0000 | 19 | 71 | 897851 |  | STUK | HINW | WLT | 7810 | WFRD WL RIH TO SET HALL 4.5" EZSV-BP @ 12,140'. GOT OBSTRUCTION @ 7,800' WITH SUDDEN DROP 230 LBS IN TENSION, ATTEMPTED TO PICK UP, WL TOOL WITH EZSV-BP STUCK IN HOLE.
1166 | 06/12/2022 | SSA-5969 | UTMN-3021 | RIG | 12 Jun 1030 - 2330 | 9.5 | 9.5 | 898011 |  | BOP | FOT | BOP | 13710 | DAMAGE IN ANNULAR ELEMENT NOT HOLDING PRESSURE DURING BOP TEST
1168 | 06/12/2022 | SSA-5970 | UTMN-2340 | RIG | 12 Jun 2000 - 2030 | .5 | .5 | 898014 |  | RR | FOT | HSYS | 2729 | REPAIR ON MAIN HPU (IRON ROUGHNECK SLIP).
1170 | 06/12/2022 | V140A | SFNY-1760 | RIG | 12 Jun 0300 - 0415 | 1.25 | 1.25 | 897946 |  | JF | XTRI | BOP | 8060 | OBSERVED DURING PT BOP, PRESSURE NOT HOLDING. TROUBLE SHOOT .
1171 | 06/13/2022 | 095TE | MNIF-226 | ARN | 13 Jun 0115 - 0500 | 3.75 | 3.75 | 898113 |  | BHS | PCPF | NA | 4315 | WHILE POH FOR WIPER TRIP, GOT O/PULL UP TO 30 KLBS AND UNABLE TO PASS FREE, HAD TO PERFORM HARD BACK REAM TO POH.
1173 | 06/13/2022 | 095TE | MNIF-226 | ARM | 13 Jun 0500 - 1030 | 5.5 | 5.5 | 898112 |  | LCIR | UVLC | NA | 4040 | DURING DRILLING ACROSS ARUMA FM, ENCOUTERED SEVER LOSSES UP TO 250 BPH, REDUCED PUMP RATE TO MANAGE LOSSES AND CONTINUE DRILLING. LOSSED DECREASED GRAUALLY AND STOP AFTER DRILLING 220 FT.
1174 | 06/13/2022 | 095TE | MNIF-226 | ARN | 13 Jun 0115 - 0500 | 3.75 | 3.75 | 898113 |  | BHS | PCPF | NA | 4315 | WHILE POH FOR WIPER TRIP, GOT O/PULL UP TO 30 KLBS AND UNABLE TO PASS FREE, HAD TO PERFORM HARD BACK REAM TO POH.
1176 | 06/13/2022 | ADC-23 | KIDN-23 | ARM | 10 Jun 2000 - 1400 | 9 | 66 | 897912 |  | TF | FOT | CSG | 4000 | ATEMPT TO BREAK CIRCULATION AFTER PICKING JOINT # 73, PRESSURED UP WITH NO RETURN FLOW. AFTER MULTIPLE ATTEMPTS REQUIRING 1,000 PSI TO OBTAIN CIRCULATION.
1178 | 06/13/2022 | ADC-34 | UTMN-2316 | SPS | 11 Jun 0000 - 0930 | 4.5 | 33.5 | 897953 |  | BHA | FOT | RSS | 13976 | LOST RSS SIGNAL
1190 | 06/13/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 375 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
1192 | 06/13/2022 | ADM-655 | SFNY-479 | ARN | 12 Jun 0500 - 0500 | 24 | 48 | 897993 |  | WO | ORDS | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT SFNY-21, 479/481 PF FOR SAFE RIG MOVE.
1194 | 06/13/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 102 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1196 | 06/13/2022 | EXL-IA | SFNY-4240 | BAW | 12 Jun 0415 - 0230 | 19 | 19.75 | 898016 |  | TF | FOT | WLT | 8479 | HAD DOWNHOLE FAILURE IN W/L HYDRAULIC POWER MODULE @ 5876'.
1198 | 06/13/2022 | HI-4 | SFNY-918 | RIG | 13 Jun 2015 - 2115 | 1 | 1 | 898092 |  | RR | FOT | TDS | 0 | CHANGE OUT TOP DRIVE IBOP CRANKS.
1200 | 06/13/2022 | OFGRL | KARN-19 | ARM | 10 Jun 1930 - 0500 | 24 | 81.5 | 897932 |  | WON | WTHR | NA | 0 | DUE TO HIGH WINDS, NOT ABLE TO WORK CRANES FOR SLICKLINE OPERATIONS.
1202 | 06/13/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 335.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1204 | 06/13/2022 | PA-866S | SHHB-2 | RIG | 12 Jun 0500 - 0100 | 20 | 44 | 897942 |  | RR | FOT | DWKS | 11150 | GROUND FAULT DETECTED ON DRAWWORKS "A" MOTOR
1206 | 06/13/2022 | PN-9 | MRJN-677 | ARM | 12 Jun 0930 - 0930 | 4.5 | 24 | 897943 |  | WON | WTHR | NA | 0 | WOW FOR RIG MOVE TO MRJN-670/679 PF.
1208 | 06/13/2022 | SCTD-2 | HRDH-2307 | SDM | 11 Jun 0030 - 0800 | 3 | 24 | 897937 |  | BHA | FOT | MMOT | 12575 | TURBINE STALLED WHILE DRILLING, ATTEMPT TO POH STRING GOT STUCK.
1210 | 06/13/2022 | SINO-28L | SHYB-711 | RIG | 13 Jun 0315 - 0500 | 1.75 | 1.75 | 898132 |  | DSF | HERR | DP | 4839 | DRILL PIPE DRIFT UNNOTICED BY DRILL CREW WAS LEFT IN PIPE. THE CREW NOTICED DRIFT WAS MISSING IMMEDIATLEY AFTER MAKING UP SINGLE OF PIPE. STOPPED JOB AND INFORMED ARAMCO AND BAKER FOREMEN
1212 | 06/13/2022 | SINO-42L | HWYH-608 | RIG | 13 Jun 0630 - 0800 | 1.5 | 1.5 | 898091 |  | RR | FOT | TDS | 6610 | WASH PIPE LEAKING.
1214 | 06/13/2022 | SINO-46L | SHYB-708 | RIG | 13 Jun 1730 - 2200 | 4.5 | 4.5 | 898111 |  | RR | FOT | EDR | 3000 | SINO RIG VDX SYSTEM FAILURE. TRIED TO TROUBLESHOOT AND FIX THE VDX SYSTEM, NO SUCCESS.
1215 | 06/13/2022 | SND-2006 | UTMN-3165 | WCR | 13 Jun 1900 - 2330 | 4.5 | 4.5 | 898093 |  | TF | FOT | CTRQ | 2800 | HAD FAILURE IN CRT ROTATIONAL BRACKET
1217 | 06/13/2022 | SND-2006 | UTMN-3165 | WCR | 13 Jun 1200 - 1400 | 2 | 2 | 898019 |  | TF | FOT | CTRQ | 11030 | REPAIR ON WFD POWER TONG
1218 | 06/13/2022 | SND-2006 | UTMN-3165 | WCR | 13 Jun 1900 - 2330 | 4.5 | 4.5 | 898093 |  | TF | FOT | CTRQ | 2800 | HAD FAILURE IN CRT ROTATIONAL BRACKET
1220 | 06/13/2022 | SP-262 | HZEM-140812 | NPC | 11 Jun 1045 - 0500 | 20.5 | 62.75 | 897973 |  | TF | TOWC | JARS | 10821 | WHILE DRILLING THE 8-1/2" CURVE OBSERVED SUDDENLY 350 PSI PRESSURE DROP. PICKED UP OFF BOTTOM AND CHECKED ALL SURFACE EQUIPMENT AND MUD PUMPS OK, POOH AND OBSERVED TWIST OFF ON NAPESCO DRILLING JAR.
1222 | 06/13/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0500 | 24 | 125.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
1223 | 06/13/2022 | SSA-303 | HRDH-2306 | RIG | 13 Jun 1415 - 0500 | 14.75 | 14.75 | 898094 |  | RR | FOT | TDS | 13120 | LOST HYDRAULIC FUNCTION, TOPDRIVE SHOW LOW ALERT ON HYDRAULIC SYSTEM
1225 | 06/13/2022 | SSA-303 | HRDH-2306 | BLH | 11 Jun 0000 - 1415 | 9.25 | 38.25 | 897936 |  | TF | FOT | HGRL | 13120 | MECHANICAL FAILURE OF SLIPS 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY
1226 | 06/13/2022 | SSA-303 | HRDH-2306 | RIG | 13 Jun 1415 - 0500 | 14.75 | 14.75 | 898094 |  | RR | FOT | TDS | 13120 | LOST HYDRAULIC FUNCTION, TOPDRIVE SHOW LOW ALERT ON HYDRAULIC SYSTEM
1228 | 06/13/2022 | SSA-5859 | HWYH-1222 | ARM | 12 Jun 0100 - 0600 | 1 | 5 | 898131 |  | LCIR | UVLC | NA | 11192 | DRLG 12" IN JDLM, COMPLETE LOSSES TOTAL 82 BBLS, THEN GOT PARTIAL RET'S, SWEEP WITH N-SEAL PILLS TO ATTEMPT REGAIN FULL RET'S,
1230 | 06/13/2022 | SSA-5892 | SMNH-521700 | BHI | 13 Jun 1330 - 0500 | 15.5 | 15.5 | 897948 |  | BHA | FOT | MWD | 20595 | BAKER MWD GAMMA RAY FALSE READING
1232 | 06/13/2022 | SSA-5914 | WDYH-80 | RIG | 10 Jun 1700 - 0500 | 24 | 82.25 | 897991 |  | BOP | FOT | RAMS | 17117 | AFTER OPENING BLIND SHEAR RAMS, NOTICED ONE SIDE DIDN'T FULLY OPENED.
1234 | 06/13/2022 | SSA-5964 | HRDH-1383 | WWL | 09 Jun 0100 - 1700 | 6 | 77 | 897851 |  | STUK | HINW | WLT | 7810 | WFRD WL RIH TO SET HALL 4.5" EZSV-BP @ 12,140'. GOT OBSTRUCTION @ 7,800' WITH SUDDEN DROP 230 LBS IN TENSION, ATTEMPTED TO PICK UP, WL TOOL WITH EZSV-BP STUCK IN HOLE.
1236 | 06/13/2022 | SSA-5969 | UTMN-3021 | RIG | 13 Jun 1400 - 1630 | 2.5 | 2.5 | 897949 |  | RR | FOT | HSYS | 13710 | FAILURE OF IR
1238 | 06/13/2022 | WCL-83 | MRJN-834 | BHI | 13 Jun 2000 - 2115 | 1.25 | 1.25 | 898020 |  | BHA | FOT | MWD | 9620 | TROUBLESHOT BHI MWD/LWD DUE TO POOR DATA QUALITY.
1240 | 06/14/2022 | 095TE | MNIF-226 | RIG | 14 Jun 0200 - 0500 | 3 | 3 | 898191 |  | RR | FOT | DRRK | 0 | DUE TO MISS ALIGNMENT OF ROATRY TABLE WITH THE MAST, UINABLE TO RUN 13-3/8" CSG PROPERLY. WORK ON ADJUSTING RIG ALIGNMENT.
1242 | 06/14/2022 | ADC-31 | SDGM-1181 | GOC | 14 Jun 1100 - 1400 | 3 | 3 | 898134 |  | TF | FOT | CRT | 10200 | CRT RUBBER CUP ELEMENT FAILURE.
1244 | 06/14/2022 | ADC-34 | UTMN-2316 | SPS | 14 Jun 0530 - 0500 | 22 | 22 | 898151 |  | BHA | FOT | MWD | 14201 | LOST MWD SIGNAL
1265 | 06/14/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 399 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
1267 | 06/14/2022 | ADC-65L | HWYH-1280 | BLH | 14 Jun 2200 - 0500 | 7 | 7 | 898136 |  | TF | FOT | HGRL | 14715 | WHILE RIH W/ 7"LH ON DP ENCOUNTER 15KLBS S/O AND PRESSURE SPIKES. POOH W/ LH TO SURFACE. NO NOTICEABLE MARKS ON SLIPS. OBSERVED SOLIDS BEHIND SLIPS MANDREL AND HALF BRASS SHEAR PIN JAMMED IN THE GAP BETWEEN MANDREL AND GAUGE RING
1269 | 06/14/2022 | ADM-337 | MRJN-900 | SWL | 14 Jun 0400 - 0500 | 1 | 1 | 898138 |  | TF | FOT | WLT | 12750 | SCHLUMBERGER USIT DETECTION TOOL FAILED, POOH TO CHANGE SAME AND RE-RUN IN HOLE.
1271 | 06/14/2022 | ADM-339 | MRJN-3013 | ARM | 14 Jun 1400 - 0500 | 15 | 15 | 898172 |  | BHS | CWEL | NA | 1660 | WHILE WORK STRING UP/DOWN BEFORE MAKE CONNECTION, TAG 68 FT HIGER. WELL COLLAPSE
1273 | 06/14/2022 | ADM-655 | SFNY-479 | ARN | 12 Jun 0500 - 0500 | 24 | 72 | 897993 |  | WO | ORDS | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT SFNY-21, 479/481 PF FOR SAFE RIG MOVE.
1275 | 06/14/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 126 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1277 | 06/14/2022 | ED-85A | ZULF-2063 | SDM | 14 Jun 0315 - 0500 | 1.75 | 1.75 | 898156 |  | SURV | FOT | GYRO | 403 | UNABLE TO OBTAIN GYRO SURVEY
1278 | 06/14/2022 | ENSCO-76 | MRJN-851 | BCR | 14 Jun 2130 - 2200 | .5 | .5 | 898133 |  | TF | FOT | CTRQ | 0 | CHANGE OUT FAULTY BAKER CASING POWER PACK (ELECTRIC UNIT FAILED)
1280 | 06/14/2022 | ENSCO-76 | MRJN-851 | BCR | 14 Jun 0130 - 0330 | 2 | 2 | 898116 |  | TF | FOT | CTRQ | 50 | BAKER CASING JAM UNIT FAILED.
1281 | 06/14/2022 | ENSCO-76 | MRJN-851 | BCR | 14 Jun 2130 - 2200 | .5 | .5 | 898133 |  | TF | FOT | CTRQ | 0 | CHANGE OUT FAULTY BAKER CASING POWER PACK (ELECTRIC UNIT FAILED)
1283 | 06/14/2022 | MP-1 | MRJN-79 | RIG | 14 Jun 2200 - 0500 | 7 | 7 | 898153 |  | BOP | FOT | BOP | 6944 | WHILE CIRCULATING AFTER 4 1/2" LNR CMT JOB, OBSERVED ANNULAR RUBBER PIECES ON SHAKERS. REMOVED SAME AND INSTALLED NEW ELEMENT AFTER POOH.
1285 | 06/14/2022 | NBR-115S | HWYH-1220 | SDM | 14 Jun 2000 - 0500 | 9 | 9 | 898135 |  | BHA | FOT | RSS | 18323 | LOST COMMUNICATION WITH SLB RSS TOOL.
1287 | 06/14/2022 | NBR-210S | HRML-80 | BC | 14 Jun 1400 - 1645 | 2.75 | 2.75 | 898192 |  | TF | FOT | PKR | 8891 | BAKER 4 1/2" X 7" TOP PACKER TEST FAILURE
1289 | 06/14/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 359.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1291 | 06/14/2022 | RM-74A | HSBH-68 | RIG | 14 Jun 1300 - 0500 | 15.5 | 15.5 | 898171 |  | RR | FOT | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
1293 | 06/14/2022 | SINO-47 | HRDH-1351 | FMC | 14 Jun 1715 - 1915 | 2 | 2 | 898115 |  | TF | XTTE | CTRQ | 1972 | EXCESSIVE TIME ON HANDLING CASING TONGS & CREW'S LOW PERFORMANCE.
1309 | 06/14/2022 | SND-1502 | HRDH-487 | HWP | 14 Jun 0700 - 0500 | 22 | 22 | 898154 |  | TF | FOT | WLT | 7200 | HALL. RDT LOGGING TOOL FAILURE.
1311 | 06/14/2022 | SSA-102 | QTIF-696 | AZ1 | 14 Jun 0030 - 0500 | 4.5 | 4.5 | 898155 |  | FISH | HERR | WLT | 0 | WHILE L/D TAQA PLT BHA ON 2-7/8'' CT WE OBSERVED ONE OF THE FOUR ARMS WAS LEFT IN THE HOLE.
1313 | 06/14/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 91 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1315 | 06/14/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0500 | 24 | 149.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
1316 | 06/14/2022 | SSA-303 | HRDH-2306 | RIG | 13 Jun 1415 - 0600 | 1 | 15.75 | 898094 |  | RR | FOT | TDS | 13120 | LOST HYDRAULIC FUNCTION, TOPDRIVE SHOW LOW ALERT ON HYDRAULIC SYSTEM
1318 | 06/14/2022 | SSA-303 | HRDH-2306 | BLH | 11 Jun 0000 - 0500 | 23 | 61.25 | 897936 |  | TF | FOT | HGRL | 13120 | MECHANICAL FAILURE OF SLIPS 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY
1319 | 06/14/2022 | SSA-303 | HRDH-2306 | RIG | 13 Jun 1415 - 0600 | 1 | 15.75 | 898094 |  | RR | FOT | TDS | 13120 | LOST HYDRAULIC FUNCTION, TOPDRIVE SHOW LOW ALERT ON HYDRAULIC SYSTEM
1321 | 06/14/2022 | SSA-5892 | SMNH-521700 | BHI | 13 Jun 1330 - 2100 | 16 | 31.5 | 897948 |  | BHA | FOT | MWD | 20595 | BAKER MWD GAMMA RAY FALSE READING
1323 | 06/14/2022 | SSA-5914 | WDYH-80 | RIG | 10 Jun 1700 - 0130 | 20.5 | 102.75 | 897991 |  | BOP | FOT | RAMS | 17117 | AFTER OPENING BLIND SHEAR RAMS, NOTICED ONE SIDE DIDN'T FULLY OPENED.
1325 | 06/14/2022 | SSA-5974 | HRDH-1970 | ARM | 14 Jun 1230 - 0330 | 15 | 15 | 898137 |  | STUK | STDP | DP | 18340 | L/D STD. TRY TO PICK-UP THE 3RD STD COULDN'T (20K LBS OVERPULL). ESTABLISHED FREE CIRCULATION WITH NO ROTATION. SLACK OFF (REPEATED THIS SEVERALLY ) -NO SUCCESS. (NO DOWNWARD MOVEMENT). SWITCH TO OVERPULL UP WITH O/PULL IN STAGES -NO SUCCESS (NO UPWARD MOVEMENT).
1327 | 06/14/2022 | V140A | SFNY-1760 | FMC | 14 Jun 1730 - 1830 | 1 | 1 | 898157 |  | JF | HERR | CTRQ | 8060 | CASING THREAD DEMAGED DUE TO NOT ALLIGNING CASING .
1329 | 06/15/2022 | 095TE | MNIF-226 | MSD | 15 Jun 0730 - 1400 | 5 | 5 | 898231 |  | TF | FOT | CTRQ | 200 | ALMASOOD CSG SPIDER ELEVATOR MALFUNCTION, ATEMPT TO FIX IT WITH NO SUCCESS, R/D SAME AND USE SIDE DOOR ELEVATOR UNTIL REPLACEMENT WITH NEW BACKUP
1331 | 06/15/2022 | ADC-32 | SDGM-1228 | BLH | 13 Jun 0630 - 0900 | 3.5 | 47.5 | 898158 |  | TF | FOT | HGRL | 12578 | UNABLE TO DRILL OUT 4-1/2" BOT LANDING COLLAR.
1333 | 06/15/2022 | ADC-34 | UTMN-2316 | SPS | 14 Jun 0530 - 1715 | 12.25 | 34.25 | 898151 |  | BHA | FOT | MWD | 14201 | LOST MWD SIGNAL
1335 | 06/15/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 423 | 897160 |  | HSEI | UNKN | NA | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
1337 | 06/15/2022 | ADC-65L | HWYH-1280 | BLH | 14 Jun 2200 - 0100 | 20 | 27 | 898136 |  | TF | FOT | HGRL | 14715 | WHILE RIH W/ 7"LH ON DP ENCOUNTER 15KLBS S/O AND PRESSURE SPIKES. POOH W/ LH TO SURFACE. NO NOTICEABLE MARKS ON SLIPS. OBSERVED SOLIDS BEHIND SLIPS MANDREL AND HALF BRASS SHEAR PIN JAMMED IN THE GAP BETWEEN MANDREL AND GAUGE RING
1338 | 06/15/2022 | ADM-337 | MRJN-900 | FMC | 15 Jun 0345 - 0445 | 1 | 1 | 898142 |  | TF | FOT | CTRQ | 40 | CHANGE OUT EXPRO POWER PACK DUE TO FAILURE.
1340 | 06/15/2022 | ADM-337 | MRJN-900 | SWL | 14 Jun 0400 - 0115 | 20.25 | 21.25 | 898138 |  | TF | FOT | WLT | 12750 | SCHLUMBERGER USIT DETECTION TOOL FAILED, POOH TO CHANGE SAME AND RE-RUN IN HOLE.
1341 | 06/15/2022 | ADM-337 | MRJN-900 | FMC | 15 Jun 0345 - 0445 | 1 | 1 | 898142 |  | TF | FOT | CTRQ | 40 | CHANGE OUT EXPRO POWER PACK DUE TO FAILURE.
1343 | 06/15/2022 | ADM-655 | SFNY-479 | ARN | 12 Jun 0500 - 0500 | 24 | 96 | 897993 |  | WO | ORDS | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT SFNY-21, 479/481 PF FOR SAFE RIG MOVE.
1345 | 06/15/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 150 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1347 | 06/15/2022 | HI-2 | BRRI-440 | HCM | 15 Jun 1945 - 0100 | 5.25 | 5.25 | 898216 |  | CMT | HERR | NA | 8480 | PRESSURE TEST 9-5/8" CSG FAILED DUE TO SOFT TAIL NOT SET.
1349 | 06/15/2022 | MP-1 | MRJN-79 | RIG | 14 Jun 2200 - 1300 | 8 | 15 | 898153 |  | BOP | FOT | BOP | 6944 | WHILE CIRCULATING AFTER 4 1/2" LNR CMT JOB, OBSERVED ANNULAR RUBBER PIECES ON SHAKERS. REMOVED SAME AND INSTALLED NEW ELEMENT AFTER POOH.
1351 | 06/15/2022 | MP-4 | LWHH-45 | AP2 | 15 Jun 1700 - 0500 | 12 | 12 | 898233 |  | WO | WOPF | NA | 0 | WAIT ON PRODUCTION DEPT. APPROVAL FOR FLOW BACK.
1353 | 06/15/2022 | NBR-115S | HWYH-1220 | SDM | 14 Jun 2000 - 0500 | 22 | 31 | 898135 |  | BHA | FOT | RSS | 18323 | LOST COMMUNICATION WITH SLB RSS TOOL.
1355 | 06/15/2022 | NBR-210S | HRML-80 | BC | 14 Jun 1400 - 0500 | 6 | 8.75 | 898192 |  | TF | FOT | PKR | 8891 | TRIED TO TEST BACK SIDE TO 700PSI SEVERAL TIMES W/O SUCCESS.
1357 | 06/15/2022 | PA-326S | WDYH-16 | SPS | 15 Jun 0530 - 0500 | 23.5 | 23.5 | 898140 |  | BHA | FOT | RSS | 16064 | LOST SIGNAL WITH RSS & NO CONTROL.
1359 | 06/15/2022 | PA-604S | HRDH-1955 | RIG | 15 Jun 2230 - 0100 | 2.5 | 2.5 | 898218 |  | RR | FOT | TDS | 4045 | FIX TOP DRIVE ISSUE : HYDRAULIC BAILS SYSTEM. ** FIX DERRICK BOARD AIR WINCH.
1361 | 06/15/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 383.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1363 | 06/15/2022 | RM-74A | HSBH-68 | RIG | 14 Jun 1300 - 0500 | 24 | 39.5 | 898171 |  | RR | FOT | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
1365 | 06/15/2022 | SINO-12L | HRDH-400 | HWP | 15 Jun 1530 - 0500 | 13.5 | 13.5 | 898214 |  | TF | FOT | WLT | 10150 | IMAGE /CALIPER LOG LOST COMMUNICATION.
1367 | 06/15/2022 | SINO-28L | SHYB-711 | BHI | 15 Jun 1830 - 0500 | 10.5 | 10.5 | 898213 |  | BHA | FOT | RSS | 8324 | AUTRAK RSS TOOL FAILURE TOOL NOT FULLY RETRACTED AND WILL NOT FULLY EXTEND
1369 | 06/15/2022 | SINO-46L | SHYB-708 | BWC | 15 Jun 2015 - 0500 | 8.75 | 8.75 | 898141 |  | BHA | FOT | DSBT | 4920 | UNABLE TO CLOSE CORETRAX PBL
1370 | 06/15/2022 | SL-7 | ZULF-1334 | RIG | 15 Jun 0000 - 0130 | 1.5 | 1.5 | 898215 |  | JF | XTRI | BOP | 0 | EXCESSIVE TIME SPENT TO PLAN & EXECUTE BOP JETTING.
1372 | 06/15/2022 | SL-7 | ZULF-1334 | RIG | 15 Jun 1515 - 1615 | 1 | 1 | 898139 |  | RR | FOT | FL | 5110 | TRIP TANK NOT FUNCTIONING PROPERLY
1373 | 06/15/2022 | SL-7 | ZULF-1334 | RIG | 15 Jun 0000 - 0130 | 1.5 | 1.5 | 898215 |  | JF | XTRI | BOP | 0 | EXCESSIVE TIME SPENT TO PLAN & EXECUTE BOP JETTING.
1375 | 06/15/2022 | SND-1501 | HRDH-496 | BAW | 15 Jun 1130 - 0500 | 17.5 | 17.5 | 898232 |  | TF | FOT | WLT | 0 | RUN BAKER RCT TO CUT 2-7/8" TBG NO SUCCESS
1377 | 06/15/2022 | SP-101 | ABQQ-710 | RIG | 15 Jun 0730 - 1400 | 6.5 | 6.5 | 898160 |  | TF | FOT | FV | 4100 | FLOAT VALVE FAILED
1379 | 06/15/2022 | SP-58 | MDRK-53 | HWP | 15 Jun 1145 - 0345 | 16 | 16 | 898212 |  | TF | FOT | WLT | 15385 | AFTER LATCHING THE WET CONNECTOR ON RDT TOOL, HALLIBURTON COULD NOT ESTABLISH ELECTRICAL COMMUNICATION WITH LOGGING TOOLS.
1381 | 06/15/2022 | SSA-102 | QTIF-696 | AZ1 | 14 Jun 0030 - 0700 | 2 | 6.5 | 898155 |  | FISH | HERR | WLT | 0 | WHILE L/D TAQA PLT BHA ON 2-7/8'' CT WE OBSERVED ONE OF THE FOUR ARMS WAS LEFT IN THE HOLE.
1383 | 06/15/2022 | SSA-201 | HRDH-2112 | ARM | 14 Jun 0130 - 0500 | 24 | 27.5 | 898211 |  | JF | HELD | STRG | 11882 | WHILE RIH W/7" WFD WHIPSTOCK, FACED OBSTRUCTION AT 11,882 FT & UNABLE TO PASS THROUGH, DESCION WAS TO POOH AND RUN WITH 7" WBCO ASSY.
1385 | 06/15/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 115 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1387 | 06/15/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0500 | 24 | 173.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
1388 | 06/15/2022 | SSA-303 | HRDH-2306 | RIG | 15 Jun 1730 - 2030 | 3 | 3 | 898161 |  | RR | FOT | TDS | 13120 | LOST ALL HYDRAULIC FUNCTION WHILE PUMPING PLUG PRIOR SET BACKER @12004'. HAD COMPLETE LEAK OF OIL FROM HYDRAULIC SERVICE LOOP CONNECTION. TROUGBLE SHOOT SAME, AND FOUND O-RING RUPTURED.
1390 | 06/15/2022 | SSA-303 | HRDH-2306 | BLH | 11 Jun 0000 - 0600 | 1 | 62.25 | 897936 |  | TF | FOT | HGRL | 13120 | MECHANICAL FAILURE OF SLIPS 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY
1391 | 06/15/2022 | SSA-303 | HRDH-2306 | RIG | 15 Jun 1730 - 2030 | 3 | 3 | 898161 |  | RR | FOT | TDS | 13120 | LOST ALL HYDRAULIC FUNCTION WHILE PUMPING PLUG PRIOR SET BACKER @12004'. HAD COMPLETE LEAK OF OIL FROM HYDRAULIC SERVICE LOOP CONNECTION. TROUGBLE SHOOT SAME, AND FOUND O-RING RUPTURED.
1393 | 06/15/2022 | SSA-5892 | SMNH-521700 | BHI | 13 Jun 1330 - 0500 | 19.75 | 51.25 | 897948 |  | BHA | FOT | MWD | 20595 | BAKER MWD GAMMA RAY FALSE READING
1395 | 06/15/2022 | WCL-83 | MRJN-834 | BHI | 15 Jun 2030 - 2100 | .5 | .5 | 898143 |  | BHA | FOT | MWD | 12545 | TROUBLESHOT BHI MWD/LWD DUE TO NO RESPONSE.
1397 | 06/16/2022 | ADC-14 | HRDH-612 | RIG | 16 Jun 2030 - 2145 | 1.25 | 1.25 | 898272 |  | RR | FPMP | MPMP | 10963 | RIG REPAIR ON MP#1
1399 | 06/16/2022 | ADC-36 | SDGM-1236 | SPS | 16 Jun 0200 - 0500 | 3 | 3 | 898276 |  | BHA | FOT | MWD | 6635 | HES TELEDRIFT MWD TOOL LOST SIGNAL.
1401 | 06/16/2022 | ADC-48 | HWYH-1256 | SPL | 16 Jun 1915 - 0130 | 6.25 | 6.25 | 898311 |  | JF | XTTE | SLICK | 1800 | WHILE 4 1/2" DRIFT THE TOOL GOT STUCK
1403 | 06/16/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 447 | 897160 |  | UPRA | GRF | TDS | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
1405 | 06/16/2022 | ADC-70 | BRRI-1204 | ARM | 16 Jun 1215 - 2345 | 11 | 11 | 898251 |  | LROP | LTHI | BIT | 3973 | SLOW ROP DUE TO VERY HARD CEMENT.
1407 | 06/16/2022 | ADM-337 | MRJN-900 | FMC | 16 Jun 1200 - 1230 | .5 | .5 | 898236 |  | TF | FOT | CTRQ | 909 | TROUBLE SHOOT TORQUE READINGS ON FRANKS JAMMING UNIT
1409 | 06/16/2022 | AOD-111 | MRJN-724 | ARM | 16 Jun 1615 - 0500 | 11.75 | 11.75 | 898275 |  | LCIR | UVLC | NA | 16052 | OBSERVED TOTAL LOSS AT 16052 FT IN RATAWI RESRV
1411 | 06/16/2022 | BCTD-3 | HWYH-962 | RIG | 16 Jun 2330 - 0030 | 1 | 1 | 898291 |  | TF | FOT | CFGE | 13220 | LEAK AT FLEX JOINT CONNECTION OF SUPERCHARGE PUMP.
1413 | 06/16/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 174 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1415 | 06/16/2022 | EXL-IA | SFNY-4240 | RIG | 16 Jun 1045 - 1815 | 7.5 | 7.5 | 898145 |  | RR | FOT | TDS | 4587 | HAD ELECTRICAL MALFUNCTION IN TDS (ALARM FOR TDS BLOWER PRESS SWITCH 1 &2 FAULTS), NO COMMUNICATION BETWEEN CONTROL PANEL & TDS (FUNCTIONS NOT WORKING).
1417 | 06/16/2022 | HI-2 | BRRI-440 | HCM | 15 Jun 1945 - 0400 | 20.5 | 25.75 | 898216 |  | CMT | HFFT | NA | 8480 | PRESSURE TEST 9-5/8" CSG FAILED DUE TO SOFT TAIL CMT NOT SET.
1419 | 06/16/2022 | MP-4 | LWHH-45 | ARM | 15 Jun 1700 - 1400 | 9 | 21 | 898233 |  | WO | SRVC | NA | 0 | WAIT ON TPD APPROVAL FOR FLOW BACK.
1420 | 06/16/2022 | NBR-115S | HWYH-1220 | RIG | 16 Jun 1230 - 2200 | 7.5 | 7.5 | 898146 |  | RR | FOT | TDS | 18323 | FAILURE OF TDS NOT GIVING PROPER TORQUE DUE TO FAULT OF POWER INVERTER.
1422 | 06/16/2022 | NBR-115S | HWYH-1220 | SDM | 15 Jun 1830 - 0500 | 13.5 | 44.5 | 898135 |  | BHA | FOT | RSS | 18323 | LOST COMMUNICATION WITH SLB RSS TOOL.
1423 | 06/16/2022 | NBR-115S | HWYH-1220 | RIG | 16 Jun 1230 - 2200 | 7.5 | 7.5 | 898146 |  | RR | FOT | TDS | 18323 | FAILURE OF TDS NOT GIVING PROPER TORQUE DUE TO FAULT OF POWER INVERTER.
1425 | 06/16/2022 | NBR-210S | HRML-80 | BC | 14 Jun 1400 - 1530 | 10.5 | 19.25 | 898192 |  | TF | FOT | PKR | 8891 | TRIED TO TEST BACK SIDE TO 700PSI SEVERAL TIMES W/O SUCCESS.
1427 | 06/16/2022 | NBR-575S | HRDH-2217 | OJR | 16 Jun 0830 - 0500 | 20.5 | 20.5 | 898150 |  | TF | TOMD | JARS | 3110 | LOST 800 PSI ON SPP & 70KLB HOOKLOAD WHILE DRLG 16" HOLE AT 3110'. POOH, FOUND JAR TWISTED-OFF AT BOTTOM SUB.
1429 | 06/16/2022 | OFGRL | KARN-19 | ARM | 10 Jun 1930 - 0500 | 7 | 40.5 | 897932 |  | WON | WTHR | NA | 0 | DUE TO HIGH WINDS, NOT ABLE TO WORK CRANES FOR SLICKLINE/WIRELINE OPERATIONS.
1431 | 06/16/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 407.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1433 | 06/16/2022 | PA-785S | QTIF-269 | RIG | 16 Jun 0400 - 0500 | 1 | 1 | 898351 |  | RR | FPMP | MPMP | 0 | MUD PUMP FAILURE
1435 | 06/16/2022 | RM-74A | HSBH-68 | RIG | 14 Jun 1300 - 0500 | 24 | 63.5 | 898171 |  | RR | FOT | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
1437 | 06/16/2022 | SINO-11 | GHNH-32 | WCS | 16 Jun 1700 - 2230 | 5.5 | 5.5 | 898274 |  | TF | FOT | RTTS | 4259 | ATTEMPT TO SET 7"DLT PKR ASSY FROM 4259' TO 4253' WITH NO SUCCESS UNDER WFD ENGINEER INSTRUCTIONS.
1439 | 06/16/2022 | SINO-12L | HRDH-400 | HWP | 15 Jun 1530 - 0830 | 3.5 | 17 | 898214 |  | TF | FOT | WLT | 10150 | IMAGE /CALIPER LOG LOST COMMUNICATION.
1441 | 06/16/2022 | SINO-28L | SHYB-711 | BHI | 15 Jun 1830 - 1315 | 8.25 | 18.75 | 898213 |  | BHA | FOT | RSS | 8324 | AUTRAK RSS TOOL FAILURE TOOL NOT FULLY RETRACTED AND WILL NOT FULLY EXTEND
1443 | 06/16/2022 | SINO-36L | SDGM-458 | TOT | 15 Jun 2230 - 0500 | 24 | 30.5 | 898271 |  | JF | HERR | MILL | 8132 | UNABLE TO PASS FREE TO THE FIRST I-PACK PACKER
1445 | 06/16/2022 | SINO-46L | SHYB-708 | CRT | 15 Jun 2015 - 0830 | 3.5 | 12.25 | 898141 |  | BHA | FOT | WBCL | 4920 | UNABLE TO CLOSE CORETRAX PBL
1447 | 06/16/2022 | SINO-7N | FDHL-3 | TOD | 16 Jun 0500 - 0600 | 1 | 1 | 898332 |  | TF | FOT | DV | 9500 | DART DID NOT LAUNCH FROM CEMENT HEAD DUE TO HAND UP IN FLAG INDICATOR.
1449 | 06/16/2022 | SND-2001 | UTMN-2329 | SDM | 16 Jun 1730 - 0500 | 11.5 | 11.5 | 898331 |  | BHA | FOT | RSS | 14879 | LOST MWD SIGNAL.
1451 | 06/16/2022 | SND-3001 | MHWZ-167101 | RIG | 16 Jun 1615 - 1800 | 1.75 | 1.75 | 898148 |  | RR | FOT | TDS | 16116 | LUBE PUMP MOTOR ON TDS FAILED.
1453 | 06/16/2022 | SP-229 | ABHD-7 | ARM | 15 Jun 1430 - 0500 | 24 | 38.5 | 898352 |  | JF | HERR | NA | 0 | NO IN-FLOW FROM PERFORATIONS
1455 | 06/16/2022 | SP-258 | HZEM-450202 | ITS | 16 Jun 1145 - 1830 | 1 | 1 | 898149 |  | JF | XTRI | CTRQ | 5715 | NOT MAKING UP THE TUBING PROPERLY LEADS TO OVER TORQUE AND DAMMAGE THE CONNECTION.
1457 | 06/16/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 139 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1459 | 06/16/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0430 | 23.5 | 197 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
1461 | 06/16/2022 | SSA-51 | MNIF-253 | HCM | 16 Jun 0200 - 0500 | 3 | 3 | 898292 |  | CMT | HFFT | NA | 18305 | DRILL OUT SOFT CMT IN SHOE TRACK.
1463 | 06/16/2022 | SSA-5859 | HWYH-1222 | RIG | 15 Jun 0100 - 0830 | 3.5 | 7.5 | 898234 |  | BOP | HERR | RAMS | 11240 | TESTING 9 5/8" CASING RAMS, OBSERVED LEAK WHEN PRESSURE INCREASED TO +/- 9000 PSI AS EVIDENT ON CHART
1465 | 06/16/2022 | SSA-5892 | SMNH-521700 | BHI | 13 Jun 1330 - 1430 | 9.5 | 60.75 | 897948 |  | BHA | FOT | MWD | 20595 | BAKER MWD GAMMA RAY FALSE READING
1466 | 06/16/2022 | SSA-5970 | UTMN-2340 | RIG | 16 Jun 1800 - 2200 | 4 | 4 | 898252 |  | JF | XTRI | BOP | 2732 | EXCESS TIME TO PERFORM BOP FUNCTION TEST.
1468 | 06/16/2022 | SSA-5970 | UTMN-2340 | RIG | 16 Jun 1030 - 1200 | 1.5 | 1.5 | 898147 |  | RR | FOT | CBLK | 2732 | REPAIR DWS BRAKE HPU.
1469 | 06/16/2022 | SSA-5970 | UTMN-2340 | RIG | 16 Jun 1800 - 2200 | 4 | 4 | 898252 |  | JF | XTRI | BOP | 2732 | EXCESS TIME TO PERFORM BOP FUNCTION TEST.
1471 | 06/17/2022 | ADC-14 | HRDH-612 | RIG | 17 Jun 1200 - 1300 | 1 | 1 | 898431 |  | RR | FPMP | MPMP | 11177 | REPAIR MUD PUMP #1 FIXED JUMPER HOSE VIBRATION .
1472 | 06/17/2022 | ADC-34 | UTMN-2316 | RIG | 17 Jun 0400 - 0500 | 1 | 1 | 898445 |  | RR | FOT | CSYS | 14788 | CONNECTION BETWEEN 4" SURFACE LINE & HOSE IS LEAKING
1474 | 06/17/2022 | ADC-34 | UTMN-2316 | RIG | 17 Jun 2000 - 0400 | 6.5 | 6.5 | 898438 |  | RR | FOT | TDS | 14788 | LEAKING SAVER SUB.
1475 | 06/17/2022 | ADC-34 | UTMN-2316 | RIG | 17 Jun 0400 - 0500 | 1 | 1 | 898445 |  | RR | FOT | CSYS | 14788 | CONNECTION BETWEEN 4" SURFACE LINE & HOSE IS LEAKING
1477 | 06/17/2022 | ADC-36 | SDGM-1236 | SPS | 16 Jun 0200 - 0330 | 22.5 | 25.5 | 898276 |  | BHA | FOT | MWD | 6635 | LOST SIGNAL FROM HES TELEDRIFT MWD TOOL.
1479 | 06/17/2022 | ADC-41L | SDGM-1244 | RIG | 17 Jun 0715 - 1115 | 4 | 4 | 898447 |  | RR | LHFL | HSYS | 82 | LEAK IN ROTARY HOSE CONNECTION TO TDS GOOSE NECK.
1481 | 06/17/2022 | ADC-48 | HWYH-1256 | SPL | 16 Jun 1915 - 0715 | 2.25 | 12 | 898311 |  | JF | XTTE | SLICK | 1800 | WHILE 4 1/2" DRIFT THE TOOL GOT STUCK
1504 | 06/17/2022 | ADC-58L | ABHD-169 | TK3 | 17 Jun 0900 - 1600 | 7 | 7 | 898435 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER, SUSPENDED R/U ACTIVITY DUE TO STRONG WIND STORM, WIND SPEED 45-55 KM/HR.
1506 | 06/17/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0500 | 24 | 471 | 897160 |  | UPRA | GRF | TDS | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
1508 | 06/17/2022 | ADC-67L | SDGM-1265 | SDM | 17 Jun 1315 - 0500 | 15.75 | 15.75 | 898450 |  | BHA | FOT | MWD | 11524 | MWD SIGNAL LOST, PERFORMED TROUBLE SHOOTING. NO SUCCESS.
1510 | 06/17/2022 | ADM-657 | ZULF-73 | SWT | 17 Jun 1530 - 0500 | 13.5 | 13.5 | 898436 |  | JF | HERR | TESTT | 0 | DURING TRANSFER OILY BRINE FROM SURGE TANK TO STORAGE TANK ON THE MAIN DECK, OBSERVED MINOR OVERFLOW FROM TOP OF THE STORAGE TANK
1512 | 06/17/2022 | AOD-1 | ZULF-696 | RIG | 17 Jun 0945 - 1545 | 6 | 6 | 898441 |  | RR | FOT | TDS | 7730 | UPPER KELLY COCK NOT CLOSING PROPERLY, TROUBLESHOOT AND REPLACE.
1514 | 06/17/2022 | AOD-111 | MRJN-724 | ARM | 16 Jun 1615 - 0500 | 24 | 35.75 | 898275 |  | LCIR | UVLC | NA | 16052 | OBSERVED TOTAL LOSS AT 16052 FT IN RATAWI RESRV
1516 | 06/17/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 198 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1518 | 06/17/2022 | HI-2 | BRRI-440 | HCM | 15 Jun 1945 - 1630 | 4 | 29.75 | 898216 |  | CMT | HFFT | NA | 8480 | PRESSURE TEST 9-5/8" CSG FAILED DUE TO SOFT TAIL CMT NOT SET.
1519 | 06/17/2022 | NBR-115S | HWYH-1220 | SDM | 17 Jun 1745 - 0500 | 9.5 | 9.5 | 898444 |  | BHA | FOT | RSS | 18672 | LOST COMMUNICATION WITH SLB RSS TOOL.
1521 | 06/17/2022 | NBR-115S | HWYH-1220 | SDM | 15 Jun 1830 - 0630 | 1.5 | 46 | 898135 |  | BHA | FOT | RSS | 18323 | LOST COMMUNICATION WITH SLB RSS TOOL.
1522 | 06/17/2022 | NBR-115S | HWYH-1220 | SDM | 17 Jun 1745 - 0500 | 9.5 | 9.5 | 898444 |  | BHA | FOT | RSS | 18672 | LOST COMMUNICATION WITH SLB RSS TOOL.
1524 | 06/17/2022 | NBR-575S | HRDH-2217 | OJR | 16 Jun 0830 - 0615 | 1.25 | 21.75 | 898150 |  | TF | TOMD | JARS | 3110 | LOST 800 PSI ON SPP & 70KLB HOOKLOAD WHILE DRLG 16" HOLE AT 3110'. POOH, FOUND JAR TWISTED-OFF AT BOTTOM SUB.
1526 | 06/17/2022 | NBR-654S | HRDH-1150 | RIG | 17 Jun 1100 - 1600 | 5 | 5 | 898440 |  | BOP | FOT | BOP | 4470 | LEAKAGE FROM BOP MUD CROSS DURING BOP TESTING
1528 | 06/17/2022 | NBR-783S | NJYN-93 | RIG | 17 Jun 1400 - 0500 | 15 | 15 | 898442 |  | UPRA | GRF | TDS | 395 | LOST TDS COMMUNICATION, NO ROTATE, TORQUE AND LINKS MOVE. TROUBLE SHOOTING SAME. UNBALE TO PULL OUT.
1530 | 06/17/2022 | OFGRL | KARN-19 | ARM | 10 Jun 1930 - 0500 | 24 | 64.5 | 897932 |  | WON | WTHR | NA | 0 | DUE TO HIGH WINDS, NOT ABLE TO WORK CRANES FOR SLICKLINE/WIRELINE OPERATIONS.
1532 | 06/17/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 431.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1534 | 06/17/2022 | RM-74A | HSBH-68 | RIG | 14 Jun 1300 - 0500 | 24 | 87.5 | 898171 |  | RR | FOT | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
1536 | 06/17/2022 | SDA | MRJN-739 | BCT | 17 Jun 0230 - 0500 | 2.5 | 2.5 | 898446 |  | TF | FOT | CTBG | 0 | WHILE ENGAGINGE REEL TO RIH, HYDRAULIC PRESSURE TO REEL DRIVE MOTORS WAS LOW AND OUT OF SPECIFICATION. TROUBLE-SHOOT HYDRAULIC SYSTEM. PRESSURE RELIEF BLOCK WAS BY-PASSING.
1538 | 06/17/2022 | SINO-16 | FDHL-601 | BAW | 16 Jun 2315 - 0500 | 24 | 29.75 | 898451 |  | JF | FOP | CUT | 9696 | BAKER WIRELINE FAILED TO CUT THE 4-1/2" TUBING
1540 | 06/17/2022 | SINO-1L | KHRS-593 | TK1 | 16 Jun 1830 - 0500 | 22.5 | 32.5 | 898371 |  | TH | NARW | NA | 6254 | - UNABLE TO PASS WITH DIRECTIONAL DRILLING ASSEMBLY THROUGH THE WINDOW.
1541 | 06/17/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 17.5 | 17.5 | 898452 |  | STUK | IPDF | DP | 8146 | STUCK PIPE
1543 | 06/17/2022 | SINO-36L | SDGM-458 | TOT | 15 Jun 2230 - 1130 | 6.5 | 37 | 898271 |  | JF | HERR | MILL | 8132 | UNABLE TO PASS
1544 | 06/17/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 17.5 | 17.5 | 898452 |  | STUK | IPDF | DP | 8146 | STUCK PIPE
1546 | 06/17/2022 | SND-2001 | UTMN-2329 | SDM | 16 Jun 1730 - 0500 | 23 | 34.5 | 898331 |  | BHA | FOT | RSS | 14879 | LOST MWD SIGNAL.
1548 | 06/17/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 0500 | 24 | 29.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
1550 | 06/17/2022 | SND-2006 | UTMN-3165 | RIG | 17 Jun 1700 - 2130 | 4.5 | 4.5 | 898433 |  | RR | FOT | DWKS | 10820 | UNABLE TO PICK UP DUE CLUTCH SLIPING .TROUBLESHOOTING THE DRAWWORK FOUND THE CLUTCH DISK TOOTH WORN OUT NEED TO REPLACE.
1552 | 06/17/2022 | SP-106 | JNAB-813 | ARM | 14 Jun 1230 - 0200 | 21 | 85.5 | 898312 |  | TH | NARW | NA | 175 | GOT TIGHT HOLE AT 175 FT WHILE POH WITH 28" BHA AND BIT CANNOT PASS THROUGH IT.
1554 | 06/17/2022 | SP-229 | ABHD-7 | ARM | 15 Jun 1430 - 0500 | 24 | 62.5 | 898352 |  | JF | HERR | NA | 0 | NO IN-FLOW FROM PERFORATIONS
1556 | 06/17/2022 | SP-306 | MNIF-196 | ARM | 16 Jun 0400 - 0500 | 21 | 22 | 898434 |  | TH | NARW | NA | 7530 | UNABLE TO PASS WITH WBCO ASSY THROUGH OBSTRUCTION AT 7,530 FT BIT DEPTH (DRIFT SUB ACROSS DV TOOL INTERVAL). POOH AND RUN MILLING BHA.
1558 | 06/17/2022 | SSA-101 | QTIF-785 | SPS | 17 Jun 2345 - 0500 | 5.25 | 5.25 | 898448 |  | BHA | FOT | MWD | 20111 | NO MWD SIGNAL,SPS TROUBLE SHOOTING TO GET MWD SIGNAL WITHOUT SUCCESS,POOH TO CHECK AND CHANGE SPS TOOLS.
1560 | 06/17/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 163 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1562 | 06/17/2022 | SSA-302 | HRDH-2113 | PKP | 08 Jun 2330 - 0700 | 2 | 199.5 | 897713 |  | TF | FOT | SEAL | 14327 | SLACK-OFF 5KLBS TO ENGAGE THE LATCH INTO THE TBR AS PER PACKER PLUS ENG & MARK ON TBG, PULL TO 5K OVER UP WT TO ENSURE LATCH. LATCH.OK W/ (280 KIB), SLACK OFF SLOWLY TO 30 KIBS (HOCK LOAD 170). CLOSE BOP, P/T TBG WITH TCA OPEN TO 2,000 PSI - PRESSURE NOT HOLDING, (DROPPED SUDDENLY TO ZERO) & HAD RETURNES. P/T TCA WITH TBG OPEN TO 2,000 PSI - PRESSURE NOT HOLDING & HAD RETURNES.
1564 | 06/17/2022 | SSA-51 | MNIF-253 | BHI | 17 Jun 2200 - 2330 | 1.5 | 1.5 | 898449 |  | TF | XTTE | LWD | 18684 | TROUBLE SHOOT BAKER IMAGE LOG.
1566 | 06/17/2022 | SSA-5964 | HRDH-1383 | RIG | 17 Jun 1145 - 1645 | 5 | 5 | 898443 |  | RR | DRIG | RSYS | 0 | INCORRECT ALIGMENT OF TDS TO HOLE CENTER.
1568 | 06/17/2022 | STY-038 | ZULF-2087 | ARM | 16 Jun 0745 - 0500 | 24 | 37.5 | 898437 |  | LCIR | FRFM | NA | 5579 | ENCOUNTERED 300 BPH LOSSES @ 5579
1570 | 06/18/2022 | ADC-29 | NYYM-102 | APR | 18 Jun 2300 - 0500 | 6 | 6 | 898461 |  | WO | WOTO | NA | 11272 | WAIT ON WFD LOGGING TOOLS (SHUTTLE MEMORY CALIPER LOGGING CONVEYED) DUE TO CHANGE OF PLAN FROM RDD (RUN CALIPER).
1572 | 06/18/2022 | ADC-45 | KHRS-573 | RIG | 12 Jun 0500 - 0500 | 24 | 168 | 898455 |  | UPRA | GRF | DRRK | 0 | AFTER LOWERING SUB- BASE OBSERVED 2 CRACKS ON RIG FLOOR BEAMS.
1574 | 06/18/2022 | ADC-50 | SFNY-1176 | BCR | 18 Jun 2200 - 2300 | 1 | 1 | 898472 |  | TF | FOT | CTRQ | 84 | FAILED TO CONNECT BAKER SPIDER ELEVATOR TO 13-3/8" CSG DUE TO GUIDE IN SPIDER SLIPS IS 12.5".
1576 | 06/18/2022 | ADC-55L | UTMN-3171 | RIG | 18 Jun 0300 - 0500 | 2 | 2 | 898482 |  | RR | FOT | RWCS | 4880 | PRESSURE TEST UNIT NOT ABLE TO APPLY MORE THAN 9000 PSI.
1601 | 06/18/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 4 | 4 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
1603 | 06/18/2022 | ADC-62L | ANDR-745 | RIG | 29 May 1400 - 0100 | 20 | 491 | 897160 |  | UPRA | GRF | TDS | 9094 | AFTER KELLY DOWN, WHILE TRYING TO DISCONNECT TDS FROM DRILL STRING, OBSERVED SAVER SUB DISCONNECTED FROM MANUAL IBOP. SLB/ADC DECIDED TO LIFT TDS GRABBER TO TORQUE UP CONNECTION WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP YOKE BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINKS ROTATED ALONG WITH STRING & HIT THREE PERSONS.
1604 | 06/18/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 4 | 4 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
1606 | 06/18/2022 | ADC-65L | HWYH-1280 | TK3 | 18 Jun 0500 - 1900 | 14 | 14 | 898474 |  | DRG | NARW | NA | 14715 | WHILE RIH W/ 7"BOT LH ON DP ENCOUNTER 15KLBS S/O AND PRESSURE SPIKES. POOH W/ LH TO SURFACE. NO NOTICEABLE MARKS ON SLIPS. OBSERVED SOLIDS BEHIND SLIPS MANDREL AND HALF BRASS SHEAR PIN JAMMED IN THE GAP BETWEEN MANDREL AND GAUGE RING
1608 | 06/18/2022 | ADC-67L | SDGM-1265 | SDM | 17 Jun 1315 - 1630 | 11.5 | 27.25 | 898450 |  | BHA | FOT | MWD | 11524 | MWD SIGNAL LOST, PERFORMED TROUBLE SHOOTING. NO SUCCESS.
1610 | 06/18/2022 | ADM-262 | MRJN-122 | SWL | 18 Jun 0600 - 0500 | 23 | 23 | 898476 |  | TF | FOT | WLT | 2368 | EZSV PREMATURE SET WHILE RIH ON SLB W/L AT 2368', ATTEMPTED TO FREE EZSV W/O SUCCESS.
1612 | 06/18/2022 | ADM-337 | MRJN-900 | FMC | 18 Jun 1415 - 1500 | .75 | .75 | 898473 |  | TF | FOT | CTRQ | 2405 | TROUBLE SHOOT FRANKS CASING TONGS.
1614 | 06/18/2022 | ADM-511 | MRJN-799 | WWD | 17 Jun 0545 - 0500 | 18.25 | 40 | 898454 |  | TF | FOT | WPSTK | 3141 | WHILE RIH WITH WHIPSTOCK AS PER WEATHERFORD DIRECTIONS. WHIPSTOCK PREMATURELY SET @ 3141'.
1616 | 06/18/2022 | ADM-657 | ZULF-73 | HTS | 17 Jun 1530 - 0500 | 24 | 37.5 | 898436 |  | JF | HERR | TESTT | 0 | DURING TRANSFER OILY BRINE FROM SURGE TANK TO STORAGE TANK ON THE MAIN DECK, OBSERVED MINOR OVERFLOW FROM TOP OF THE STORAGE TANK
1618 | 06/18/2022 | AOD-111 | MRJN-724 | ARM | 16 Jun 1615 - 0545 | .75 | 36.5 | 898275 |  | LCIR | UVLC | NA | 16052 | OBSERVED TOTAL LOSS AT 16052 FT IN RATAWI RESRV
1619 | 06/18/2022 | BCTD-4 | GHZL-55 | BHI | 18 Jun 0400 - 0500 | 1 | 1 | 898480 |  | BHA | FOT | MWD | 10200 | ORIENTOR (HPC/HOT) FAILED POH TO CHANGE BHA.
1621 | 06/18/2022 | BCTD-4 | GHZL-55 | BHI | 18 Jun 1430 - 0400 | 10.5 | 10.5 | 898479 |  | BHA | FOT | MWD | 14747 | USMPR TOOL FAIELD POH TO CHANGE BHA.
1622 | 06/18/2022 | BCTD-4 | GHZL-55 | BHI | 18 Jun 0400 - 0500 | 1 | 1 | 898480 |  | BHA | FOT | MWD | 10200 | ORIENTOR (HPC/HOT) FAILED POH TO CHANGE BHA.
1624 | 06/18/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 222 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1626 | 06/18/2022 | DQ-50L | HRDH-582 | TK2 | 18 Jun 0600 - 0500 | 23 | 23 | 898481 |  | DSF | FOT | STRG | 6028 | HAD LEAK WHILE TEST COMPL STRG TBG, TRY TO DETECT & FIX THE LEAK.
1628 | 06/18/2022 | ENS-108 | ZULF-2014 | RIG | 18 Jun 1700 - 0500 | 12 | 12 | 898460 |  | RR | FOT | TDS | 1518 | REPLACE SERVICE LOOP ON TDS AS PER RIG CONTRACT RECOMMENDATION.
1630 | 06/18/2022 | EXL-IA | SFNY-4240 | RIG | 18 Jun 2130 - 2200 | .5 | .5 | 898463 |  | RR | FOT | TDS | 8479 | WHILE CIRC. BTM UP, HAD ELECTRICAL MALFUNCTION AT VFD FOR TDS (HIGH TEMP ALARM AT VFD FOR TDS).
1632 | 06/18/2022 | NBR-115S | HWYH-1220 | SDM | 17 Jun 1745 - 2115 | 16.25 | 25.75 | 898444 |  | BHA | FOT | RSS | 18672 | LOST COMMUNICATION WITH SLB RSS TOOL.
1633 | 06/18/2022 | NBR-16S | HMYM-433114 | RIG | 18 Jun 2100 - 2200 | 1 | 1 | 898465 |  | RR | FOT | DRRK | 500 | RIG WAS NOT PROPER ALIGNED
1635 | 06/18/2022 | NBR-16S | HMYM-433114 | RIG | 18 Jun 2230 - 0230 | 4 | 4 | 898464 |  | RR | FOT | HSYS | 283 | PINS ON MANUAL TONGS WERE BENT & STUCK
1636 | 06/18/2022 | NBR-16S | HMYM-433114 | RIG | 18 Jun 2100 - 2200 | 1 | 1 | 898465 |  | RR | FOT | DRRK | 500 | RIG WAS NOT PROPER ALIGNED
1638 | 06/18/2022 | NBR-210S | HRML-80 | GEP | 18 Jun 0315 - 0500 | 1.75 | 1.75 | 898475 |  | WH | FOT | WH | 0 | P/T VOID BONNET TO 2,500PSI, PRESSURE DROPPED AND FOUND LEAK IN TUBING SPOOL.
1640 | 06/18/2022 | NBR-783S | NJYN-93 | RIG | 17 Jun 1400 - 0500 | 22.5 | 37.5 | 898442 |  | UPRA | GRF | TDS | 395 | LOST TDS COMMUNICATION, BLOWER MOTOR FAILED.
1642 | 06/18/2022 | OFGRL | KARN-19 | ARM | 10 Jun 1930 - 0100 | 20 | 84.5 | 897932 |  | WON | WTHR | NA | 0 | DUE TO HIGH WINDS, NOT ABLE TO WORK CRANES FOR SLICKLINE/WIRELINE OPERATIONS.
1644 | 06/18/2022 | PA-218S | HRDH-1941 | RIG | 18 Jun 1430 - 1530 | 1 | 1 | 898458 |  | RR | FOT | MPMP | 4861 | REPAIR MUD PUMP#2 STROKE COUNTER FAILURE.
1646 | 06/18/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 455.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1648 | 06/18/2022 | RM-74A | HSBH-68 | RIG | 14 Jun 1300 - 0500 | 23 | 110.5 | 898171 |  | RR | FOT | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
1650 | 06/18/2022 | SCTD-2 | HRDH-2307 | SDM | 18 Jun 1200 - 0500 | 17 | 17 | 898466 |  | BHA | FOT | MWD | 13934 | D&M LOST COMMUNICATION WITH DOWNHOLE TOOLS.
1652 | 06/18/2022 | SDA | MRJN-739 | BCT | 17 Jun 0230 - 0500 | 24 | 26.5 | 898446 |  | TF | FOT | CTBG | 0 | WHILE ENGAGINGE REEL TO RIH, HYDRAULIC PRESSURE TO REEL DRIVE MOTORS WAS LOW AND OUT OF SPECIFICATION. TROUBLE-SHOOT HYDRAULIC SYSTEM. PRESSURE RELIEF BLOCK WAS BY-PASSING.
1654 | 06/18/2022 | SINO-16 | FDHL-601 | BAW | 17 Jun 1800 - 0600 | 1 | 12 | 898470 |  | TF | FOT | WLT | 500 | RIH RCT CUTTER, CCL & ALTUS TRACTOR ON WL TO 500 FT, CHECK TRACTOR COMMUNICATION, FOUND HIGH CURRENT. BAKER WIRELINE TROUBLE SHOOTING NOT SUCCESSFUL.
1656 | 06/18/2022 | SINO-1L | KHRS-593 | TK1 | 16 Jun 1830 - 1045 | 5.25 | 37.75 | 898371 |  | TH | NARW | NA | 6254 | - UNABLE TO PASS WITH DIRECTIONAL DRILLING ASSEMBLY THROUGH THE WINDOW.
1658 | 06/18/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 41.5 | 898452 |  | STUK | IPDF | DP | 8146 | STUCK PIPE, CHANGE IN FLOW RATE WITHOUT APPROVAL
1660 | 06/18/2022 | SINO-5L | UTMN-1018 | RIG | 18 Jun 1230 - 2130 | 9 | 9 | 898478 |  | RR | FOT | HSYS | 7216 | LEAK BETWEEN ROTARY HOSE & STAND PIPE CONNECTION
1661 | 06/18/2022 | SL-7 | ZULF-1334 | SPS | 18 Jun 1600 - 2315 | 7.25 | 7.25 | 898459 |  | BHA | FOT | RSS | 2143 | SPERRY SUN RSSS IS SHOWING LOW TRUBINE READINGS,
1663 | 06/18/2022 | SL-7 | ZULF-1334 | RIG | 18 Jun 0500 - 1600 | 11 | 11 | 898456 |  | DSF | FOT | DP | 2143 | SPERRY TURBINE READINGS LOW, INVESTIGATE ISSUE FOUND RUBBER STUCK FROM FOX HOLE AT 1ST CONNECTION OF HWDP
1664 | 06/18/2022 | SL-7 | ZULF-1334 | SPS | 18 Jun 1600 - 2315 | 7.25 | 7.25 | 898459 |  | BHA | FOT | RSS | 2143 | SPERRY SUN RSSS IS SHOWING LOW TRUBINE READINGS,
1666 | 06/18/2022 | SND-2001 | UTMN-2329 | SDM | 16 Jun 1730 - 0545 | .75 | 35.25 | 898331 |  | BHA | FOT | RSS | 14879 | LOST MWD SIGNAL.
1668 | 06/18/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 0500 | 24 | 53.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
1670 | 06/18/2022 | SP-229 | ABHD-7 | ARM | 15 Jun 1430 - 0500 | 24 | 86.5 | 898352 |  | JF | HERR | NA | 0 | NO IN-FLOW FROM PERFORATIONS
1672 | 06/18/2022 | SP-306 | MNIF-196 | ARM | 16 Jun 0400 - 0530 | .5 | 22.5 | 898434 |  | TH | NARW | NA | 7530 | UNABLE TO PASS WITH WBCO ASSY THROUGH OBSTRUCTION AT 7,530 FT BIT DEPTH (DRIFT SUB ACROSS DV TOOL INTERVAL). POOH AND RUN MILLING BHA.
1674 | 06/18/2022 | SP-58 | MDRK-53 | HWP | 15 Jun 1145 - 1030 | 5.5 | 41 | 898212 |  | TF | FOT | WLT | 15385 | AFTER LATCHING THE WET CONNECTOR ON RDT TOOL, HALLIBURTON COULD NOT ESTABLISH ELECTRICAL COMMUNICATION WITH LOGGING TOOLS.
1676 | 06/18/2022 | SSA-101 | QTIF-785 | SPS | 17 Jun 2345 - 0500 | 24 | 29.25 | 898448 |  | BHA | FOT | MWD | 20111 | NO MWD SIGNAL,SPS TROUBLE SHOOTING TO GET MWD SIGNAL WITHOUT SUCCESS,POOH TO CHECK AND CHANGE SPS TOOLS.
1678 | 06/18/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 187 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1680 | 06/18/2022 | SSA-51 | MNIF-253 | BHI | 18 Jun 0600 - 0500 | 23 | 23 | 898457 |  | TF | XTTE | LWD | 19201 | BAKER DENSITY IMAGE LOG FAILURE
1682 | 06/18/2022 | STY-038 | ZULF-2087 | ARM | 16 Jun 0745 - 0500 | 21.5 | 59 | 898437 |  | LCIR | FRFM | NA | 5579 | ENCOUNTERED 300 BPH LOSSES @ 5579
1684 | 06/19/2022 | ADC-29 | NYYM-102 | RMD | 18 Jun 2300 - 1100 | 6 | 12 | 898461 |  | WO | WOTO | NA | 11272 | WAIT ON WFD LOGGING TOOLS (SHUTTLE MEMORY CALIPER LOGGING CONVEYED) DUE TO CHANGE OF PLAN FROM RDD TO RUN CALIPER LOG.
1686 | 06/19/2022 | ADC-45 | KHRS-573 | RIG | 12 Jun 0500 - 0500 | 24 | 192 | 898455 |  | UPRA | GRF | DRRK | 0 | AFTER LOWERING SUB- BASE OBSERVED 2 CRACKS ON RIG FLOOR BEAMS.
1688 | 06/19/2022 | ADC-55L | UTMN-3171 | RIG | 18 Jun 0300 - 0730 | 2.5 | 4.5 | 898482 |  | RR | FOT | RWCS | 4880 | PRESSURE TEST UNIT NOT ABLE TO APPLY MORE THAN 9000 PSI.
1716 | 06/19/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 28 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
1718 | 06/19/2022 | ADM-262 | MRJN-122 | SWL | 18 Jun 0600 - 1745 | 12.25 | 35.25 | 898476 |  | TF | FOT | WLT | 2368 | EZSV PREMATURE SET WHILE RIH ON SLB W/L AT 2368', ATTEMPTED TO FREE EZSV W/O SUCCESS.
1720 | 06/19/2022 | ADM-339 | MRJN-3013 | RIG | 19 Jun 0200 - 0300 | 1 | 1 | 898497 |  | RR | FOT | CSYS | 2620 | OBSERVE CMT BULK PRODUCT DELIVERY INTERRUPTION. UN-PLUG BULK CMT LINE AT MAIN DECK.
1722 | 06/19/2022 | ADM-656 | SFNY-396 | SBA | 19 Jun 0945 - 0500 | 19.25 | 19.25 | 898490 |  | TF | FOT | ESPL | 2368 | OBSERVED UNBALANCED PHASE TO PHASE READINGS ON ESP ELECTRICAL CABLE AT 2,368 FT. DECISION MADE TO POH AND CHANGE OUT ESP CABLE.
1724 | 06/19/2022 | ADM-657 | ZULF-73 | HTS | 17 Jun 1530 - 1000 | 5 | 42.5 | 898436 |  | JF | HERR | TESTT | 0 | DURING TRANSFER OILY BRINE FROM SURGE TANK TO STORAGE TANK ON THE MAIN DECK, OBSERVED MINOR OVERFLOW FROM TOP OF THE STORAGE TANK
1726 | 06/19/2022 | AOD-11 | SFNY-1810 | RIG | 19 Jun 0000 - 0345 | 3 | 3 | 898494 |  | RR | FOT | TDS | 1829 | WHILE BREAK OUT TDS FOR CONNECTION, OBSERVE THE CONNECTION BETWEEN SAVER SUB & IBOP OPENED, L/D TOP JTS OF DP WITH SAVER SUB, POOH TO CSG SHOE, INSPECT TDS CLAMP & INSTALL NEW SAVER SUB WITH CLAMP.
1728 | 06/19/2022 | AOD-111 | MRJN-724 | ARM | 19 Jun 1445 - 0445 | 14 | 14 | 898491 |  | LCIR | UVLC | NA | 16052 | AFTER DISPLACING THE HOLE FROM 74 PCF BARITE FREE RHELIANT OBM TO 76 VIS BRINE, OBSERVED LOSSES INCREASE IN RATAWI RESRV TO + 500 BPH
1730 | 06/19/2022 | BCTD-4 | GHZL-55 | BHI | 18 Jun 0400 - 1500 | 10 | 11 | 898480 |  | BHA | FOT | MWD | 10200 | ORIENTOR (HPC/HOT) FAILED POH TO CHANGE BHA.
1732 | 06/19/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 246 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1734 | 06/19/2022 | DPS-45 | UTMN-2324 | HCM | 19 Jun 0900 - 0500 | 20 | 20 | 898487 |  | TF | FOT | PUMP | 0 | HES PUMP UNIT QUIT DUE TO MALFUNCTION IN PRESSURE SENSOR IN THE PUMP UNIT PREVENTING PUMP FROM PROCEEDING WITH JOB. ABORT CMT JOB AND MIX NEW MIX FLUID.
1736 | 06/19/2022 | DQ-50L | HRDH-582 | TK2 | 18 Jun 0600 - 0500 | 19.75 | 42.75 | 898481 |  | DSF | FOT | STRG | 6028 | HAD LEAK WHILE TEST COMPL STRG TBG, TRY TO DETECT & FIX THE LEAK.
1738 | 06/19/2022 | ED-85A | ZULF-2063 | RIG | 19 Jun 1845 - 2100 | 2.25 | 2.25 | 898504 |  | JF | HERR | BHA | 2114 | WASH DOWN LAST CSG JT WITH CEMENT HEAD, DID NOT TAG. LAY DOWN CEMENT HEAD & P/U TWO PUP JOINTS AND P/U CEMENT HEAD WASH DOWN. TAGGED 6 FT DEEPER. DUE TO WRONG CSG TALLY MEASUREMENT .
1740 | 06/19/2022 | ENS-108 | ZULF-2014 | RIG | 18 Jun 1700 - 0630 | 1.5 | 13.5 | 898460 |  | RR | FOT | TDS | 1518 | REPLACE SERVICE LOOP ON TDS AS PER RIG CONTRACT RECOMMENDATION.
1742 | 06/19/2022 | NBR-115S | HWYH-1220 | SDM | 17 Jun 1745 - 0500 | 15 | 40.75 | 898444 |  | BHA | FOT | RSS | 18672 | LOST COMMUNICATION WITH SLB RSS TOOL.
1744 | 06/19/2022 | NBR-16S | HMYM-433114 | RIG | 19 Jun 0615 - 0715 | 1 | 1 | 898502 |  | JF | XTRI | NA | 0 | EXCESSIVE TIME TO LAY DOWN BHA
1746 | 06/19/2022 | NBR-210S | HRML-80 | GEP | 18 Jun 0315 - 0900 | 4 | 5.75 | 898475 |  | WH | FOT | WH | 0 | P/T VOID BONNET TO 2,500PSI, PRESSURE DROPPED AND FOUND LEAK IN TUBING SPOOL.
1748 | 06/19/2022 | NBR-783S | NJYN-93 | RIG | 17 Jun 1400 - 1600 | 11 | 48.5 | 898442 |  | UPRA | GRF | TDS | 395 | LOST TDS COMMUNICATION, BLOWER MOTOR FAILED.
1750 | 06/19/2022 | PA-218S | HRDH-1941 | RIG | 19 Jun 1230 - 1300 | .5 | .5 | 898488 |  | RR | FOT | DWKS | 5252 | MUD PUMPS & DRAWOKS TRIP OUT.
1752 | 06/19/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 479.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1754 | 06/19/2022 | PN-7 | MRJN-772 | BLH | 19 Jun 0200 - 0430 | 2.5 | 2.5 | 898501 |  | TF | FOT | HGRL | 11736 | DROPPED 1.5" BALL AND PUMPED DOWN. NO SUCCESS TO SET LINER HANGER.
1756 | 06/19/2022 | PN-9 | MRJN-677 | RIG | 19 Jun 0800 - 1400 | 6 | 6 | 898503 |  | DSF | HERR | STRG | 2564 | DRILLER TAG HOLE FILL WITH 50KLBS UNINTENTIONALLY, BIT NOZZLES PARTIALLY PLUGGED, POH TO CLEAR PLUGGED BIT NOZZLES.
1758 | 06/19/2022 | RM-74A | HSBH-68 | RIG | 14 Jun 1300 - 0500 | 24 | 134.5 | 898171 |  | RR | FOT | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
1760 | 06/19/2022 | SCTD-1 | SDGM-1152 | SDM | 19 Jun 1130 - 1300 | 1.5 | 1.5 | 898489 |  | BHA | FOT | MWD | 0 | D&M TESTED INSULATION ON SURFACE-FAILED,REBOOT & RETEST-OK.
1761 | 06/19/2022 | SDA | MRJN-739 | BCT | 19 Jun 1430 - 2200 | 7.5 | 7.5 | 898496 |  | TF | FOT | CTU | 1500 | COIL TUBING LOAD CELL STOPPED WORKING AT 1500' WHILE RIH.
1763 | 06/19/2022 | SDA | MRJN-739 | BCT | 17 Jun 0230 - 1315 | 8.25 | 34.75 | 898446 |  | TF | FOT | CTBG | 0 | WHILE ENGAGINGE CT REEL TO RIH, HYDRAULIC PRESSURE TO REEL DRIVE MOTORS WAS LOW AND OUT OF SPECIFICATION. TROUBLE-SHOOT HYDRAULIC SYSTEM. PRV BLOCK BY-PASSING.
1764 | 06/19/2022 | SDA | MRJN-739 | BCT | 19 Jun 1430 - 2200 | 7.5 | 7.5 | 898496 |  | TF | FOT | CTU | 1500 | COIL TUBING LOAD CELL STOPPED WORKING AT 1500' WHILE RIH.
1766 | 06/19/2022 | SINO-12L | HRDH-400 | RIG | 19 Jun 2215 - 0500 | 6.75 | 6.75 | 898505 |  | BHA | FOT | HWDP | 7170 | UNABLE TO SET OFF-BTM LINER DUE TO WASH OUT IN DP.
1768 | 06/19/2022 | SINO-18 | SRYN-14 | HWP | 19 Jun 1600 - 2300 | 7 | 7 | 898498 |  | TF | FOT | WLT | 11080 | THE DATA WAS INSUFFICIENT
1770 | 06/19/2022 | SINO-1L | KHRS-593 | TK1 | 19 Jun 0930 - 2200 | 12 | 12 | 898500 |  | WO | SRVC | NA | 7824 | - NO SUFFICIENT DRILLING WATER AT RIG SITE.
1772 | 06/19/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 65.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
1773 | 06/19/2022 | SND-2001 | UTMN-2329 | SDM | 19 Jun 1930 - 0500 | 9.5 | 9.5 | 898492 |  | BHA | FOT | RSS | 15637 | RSS UNABLE TO BUILD UP REQUIRED INCLINATION.
1775 | 06/19/2022 | SND-2001 | UTMN-2329 | SDM | 19 Jun 1230 - 1345 | 1.25 | 1.25 | 898486 |  | BHA | FOT | RSS | 15542 | LOWER TORQUER POWER SECTION OF RSS JAMMED UP
1776 | 06/19/2022 | SND-2001 | UTMN-2329 | SDM | 19 Jun 1930 - 0500 | 9.5 | 9.5 | 898492 |  | BHA | FOT | RSS | 15637 | RSS UNABLE TO BUILD UP REQUIRED INCLINATION.
1778 | 06/19/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 0500 | 24 | 77.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
1780 | 06/19/2022 | SND-2008 | HRDH-1812 | SDM | 19 Jun 0815 - 0500 | 20.75 | 20.75 | 898485 |  | BHA | FOT | MWD | 13854 | NO SIGNAL FROM MWD, TRUABLE SHOOTER, NO SUCCESS
1781 | 06/19/2022 | SP-229 | ABHD-7 | RIG | 19 Jun 0000 - 0500 | 5 | 5 | 898495 |  | FISH | HERR | BHA | 8750 | POH TO SURFACE AND FOUND 3-3/4" CP MILL LOST IN THE WELL.
1783 | 06/19/2022 | SP-229 | ABHD-7 | ARM | 15 Jun 1430 - 0000 | 19 | 105.5 | 898352 |  | JF | HERR | NA | 0 | NO IN-FLOW FROM PERFORATIONS
1784 | 06/19/2022 | SP-229 | ABHD-7 | RIG | 19 Jun 0000 - 0500 | 5 | 5 | 898495 |  | FISH | HERR | BHA | 8750 | POH TO SURFACE AND FOUND 3-3/4" CP MILL LOST IN THE WELL.
1786 | 06/19/2022 | SSA-101 | QTIF-785 | SPS | 17 Jun 2345 - 0500 | 24 | 53.25 | 898448 |  | BHA | FOT | MWD | 20111 | NO MWD SIGNAL,SPS TROUBLE SHOOTING TO GET MWD SIGNAL WITHOUT SUCCESS,POOH TO CHECK AND CHANGE SPS TOOLS.
1788 | 06/19/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 211 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1790 | 06/19/2022 | SSA-51 | MNIF-253 | BHI | 18 Jun 0600 - 2000 | 15 | 38 | 898457 |  | TF | XTTE | LWD | 19201 | BAKER DENSITY IMAGE LOG FAILURE
1792 | 06/19/2022 | SSA-5859 | HWYH-1222 | RIG | 19 Jun 0800 - 0930 | 1.5 | 1.5 | 898493 |  | BOP | FOT | BOP | 11240 | CUMULATIVE TIME LOST WHILE PRESSURE TESTING BOP STACK.
1794 | 06/19/2022 | STY-038 | ZULF-2087 | ARM | 16 Jun 0745 - 1715 | 12.25 | 71.25 | 898437 |  | LCIR | FRFM | NA | 5579 | ENCOUNTERED 300 BPH LOSSES @ 5579
1796 | 06/20/2022 | ADC-43L | UTMN-3118 | TK3 | 19 Jun 0245 - 0500 | 24 | 26.25 | 898513 |  | WCNT | WC20 | NA | 10535 | OBSERVED INCREASE IN MPD RETURN FLOW. WELL FLOWING . SHUT-IN WELL ON RCD W/ 5 RPM. RECORD INITIAL SIDPP-1100 PSI, SICP - 1400 PSI, & PIT GAIN - 7 BBL.
1798 | 06/20/2022 | ADC-45 | KHRS-573 | RIG | 20 Jun 0500 - 1800 | 13 | 13 | 898594 |  | UPRA | GRF | DRRK | 0 | MAST RAISING CYLINDERS FAILED PRESSURE TEST.
1800 | 06/20/2022 | ADC-56L | UTMN-2330 | ARM | 20 Jun 0245 - 0445 | 2 | 2 | 898612 |  | WO | SRVC | NA | 19397 | WAIT ON BPV CREW TO ARRIVE ON RIG.
1816 | 06/20/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 52 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
1818 | 06/20/2022 | ADC-67L | SDGM-1265 | SDM | 20 Jun 1600 - 0500 | 13 | 13 | 898518 |  | BHA | FOT | RSS | 12443 | RSS NOT RESPOND, PERFORMED TROUBLE SHOOTING. NO SUCCESS.
1819 | 06/20/2022 | ADES-158 | ABQQ-736 | RIG | 20 Jun 1500 - 1730 | 2.5 | 2.5 | 898592 |  | RR | FOT | DWKS | 8750 | REPLACE FAULTY CATHEAD WITH NEW ONE.
1821 | 06/20/2022 | ADES-158 | ABQQ-736 | ARM | 20 Jun 1730 - 0330 | 10 | 10 | 898577 |  | JF | HELD | STRG | 5206 | HAD OBSTRUCTION @ 5206' WHILE RIH WITH BAKER DIR BHA.
1822 | 06/20/2022 | ADES-158 | ABQQ-736 | RIG | 20 Jun 1500 - 1730 | 2.5 | 2.5 | 898592 |  | RR | FOT | DWKS | 8750 | REPLACE FAULTY CATHEAD WITH NEW ONE.
1824 | 06/20/2022 | ADM-337 | MRJN-900 | SLL | 18 Jun 0100 - 0500 | 24 | 44.5 | 898514 |  | TF | ISEQ | SB | 11365 | UNABLE TO PASS TOL WITH SCHLUMBERGER W/LINE TOOLS CBL & USIT
1826 | 06/20/2022 | ADM-656 | SFNY-396 | SBA | 19 Jun 0945 - 0500 | 24 | 43.25 | 898490 |  | TF | FOT | ESPL | 2368 | OBSERVED UNBALANCED PHASE TO PHASE READINGS ON ESP ELECTRICAL CABLE AT 2,368 FT. DECISION MADE TO POH AND CHANGE OUT ESP CABLE.
1828 | 06/20/2022 | ADM-657 | ZULF-73 | ARM | 20 Jun 1015 - 1230 | 2.25 | 2.25 | 898553 |  | WON | WTHR | NA | 0 | WIND SPEED DROPPED TO 1 KTS DURING FLARING. STOP OPERATION AND WAIT FOR WIND SPEED TO INCREASE.
1830 | 06/20/2022 | AOD-111 | MRJN-724 | ARM | 20 Jun 2100 - 0100 | 4 | 4 | 898595 |  | LCIR | UVLC | NA | 16052 | OBSERVED LOSSES IN RATAWI RESRV 150 BPH
1832 | 06/20/2022 | BCTD-4 | GHZL-55 | RIG | 20 Jun 1130 - 0230 | 15 | 15 | 898573 |  | BHA | FOT | CTAC | 14990 | USMPR TOOL FAIELD POH TO CHANGE BHA.
1833 | 06/20/2022 | CG-1 | ZULF-1201 | RIG | 20 Jun 2200 - 2230 | .5 | .5 | 898575 |  | RR | FOT | HSYS | 0 | RIG REPAIR- CHANGE OUT HOSE IRON ROUGHNECK ON RIG FLOOR.
1835 | 06/20/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 23.5 | 269.5 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1836 | 06/20/2022 | CG-1 | ZULF-1201 | RIG | 20 Jun 2200 - 2230 | .5 | .5 | 898575 |  | RR | FOT | HSYS | 0 | RIG REPAIR- CHANGE OUT HOSE IRON ROUGHNECK ON RIG FLOOR.
1838 | 06/20/2022 | DPS-45 | UTMN-2324 | HCM | 19 Jun 0900 - 0730 | 2.5 | 22.5 | 898487 |  | TF | FOT | PUMP | 0 | HES PUMP UNIT QUIT DUE TO MALFUNCTION IN PRESSURE SENSOR IN THE PUMP UNIT PREVENTING PUMP FROM PROCEEDING WITH JOB. ABORT CMT JOB AND MIX NEW MIX FLUID.
1840 | 06/20/2022 | DQ-50L | HRDH-582 | TK2 | 18 Jun 0600 - 2330 | 18.5 | 61.25 | 898481 |  | DSF | FOT | STRG | 6028 | HAD LEAK WHILE TEST COMPL STRG TBG, TRY TO DETECT & FIX THE LEAK.
1842 | 06/20/2022 | JACK-202 | HMYM-844 | RIG | 20 Jun 1445 - 0100 | 10.25 | 10.25 | 898576 |  | RR | FOT | DWKS | 346 | WAIT ON FIX BRAKE BAND OF DRAWWORKS DUE TOO MUCH VIBRATIONS WHILE TRAVELLING BLOCK LOWERING.
1844 | 06/20/2022 | MP-4 | LWHH-45 | SJT | 20 Jun 1030 - 1630 | 6 | 6 | 898517 |  | WO | MATL | NA | 7000 | WAIT ON NITROGEN FROM SANJEL TAQA CT FOR LIFTING THE WELL.
1846 | 06/20/2022 | NBR-115S | HWYH-1220 | SDM | 17 Jun 1745 - 1000 | 5 | 45.75 | 898444 |  | BHA | FOT | RSS | 18672 | LOST COMMUNICATION WITH SLB RSS TOOL.
1848 | 06/20/2022 | NBR-263S | QTIF-736 | ARM | 20 Jun 0900 - 1630 | 7.5 | 7.5 | 898593 |  | WCNT | WC20 | NA | 8307 | - WHILE CIRC, OBSERVE INCREASE IN ACTIVE MUD TANKS, - STOP PUMP & FLOW CHECK OBSERVE WELL FLOWING, SHUT IN WELL, BLEED OFF PRESS IN STAGES NO PRESS BUILD UP. CIRC ONE COMPLETE CYCLE THROUGH OPEN CHOKE & OBSERVE WELL ON TRIP TANK FOR 1 HR. RETURN DECREASED GRADUALLY TO ZERO, OK. OPEN BOP
1849 | 06/20/2022 | NBR-304S | HRDH-1958 | FMC | 20 Jun 0030 - 0115 | .75 | .75 | 898556 |  | TF | FOT | PEL | 2675 | REPAIR ON FRANKS SINGLE ELEVATOR
1851 | 06/20/2022 | NBR-304S | HRDH-1958 | FMC | 20 Jun 1530 - 1815 | 2.75 | 2.75 | 898555 |  | TF | XTTE | CRT | 0 | REPAIR CRT TOOLS
1852 | 06/20/2022 | NBR-304S | HRDH-1958 | FMC | 20 Jun 0030 - 0115 | .75 | .75 | 898556 |  | TF | FOT | PEL | 2675 | REPAIR ON FRANKS SINGLE ELEVATOR
1854 | 06/20/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 503.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1856 | 06/20/2022 | RBP-50A | KARN-51 | ARM | 20 Jun 0500 - 1245 | 7.75 | 7.75 | 898552 |  | WON | WTHR | NA | 11775 | WAIT ON WEATHER WINDOW TO MIX ACID STIMULATION FLUID.
1858 | 06/20/2022 | RM-74A | HSBH-68 | RIG | 14 Jun 1300 - 0500 | 23.5 | 158 | 898171 |  | UPRA | GRF | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
1860 | 06/20/2022 | SA5898 | MDRK-57 | RIG | 20 Jun 0000 - 0500 | 5 | 5 | 898574 |  | TF | FOT | SLIPS | 15500 | DROP IN HOLE 2 DIES OF 4-3/4" DC SLIPS.
1862 | 06/20/2022 | SINO-12L | HRDH-400 | RIG | 19 Jun 2230 - 0500 | 24 | 30.5 | 898505 |  | BHA | FOT | HWDP | 7170 | UNABLE TO SET OFF-BTM LINER DUE STRING LEAK.
1864 | 06/20/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 89.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
1866 | 06/20/2022 | SND-2001 | UTMN-2329 | SDM | 19 Jun 1930 - 0500 | 12 | 21.5 | 898492 |  | BHA | FOT | RSS | 15637 | RSS UNABLE TO BUILD UP REQUIRED INCLINATION.
1868 | 06/20/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 0500 | 24 | 101.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
1870 | 06/20/2022 | SND-2006 | UTMN-3165 | ARM | 19 Jun 0000 - 2300 | 18 | 23 | 898554 |  | WCNT | WC11 | NA | 11580 | WHILE DRLG OBSERIVE LEL 25% - PERFORMED KILLING OPERATION IN JILH FORMATION USING W&W METHOD.
1872 | 06/20/2022 | SND-2008 | HRDH-1812 | SDM | 19 Jun 0815 - 0930 | 4 | 24.75 | 898485 |  | BHA | FOT | MWD | 13854 | NO SIGNAL FROM MWD, TRUABLE SHOOTER, NO SUCCESS
1874 | 06/20/2022 | SND-3002 | DMMM-601 | SDM | 20 Jun 1900 - 0500 | 10 | 10 | 898516 |  | BHA | FOT | RSS | 12127 | SDM RSS/MWD UNABLE TO HOLD INC ANGLE.
1875 | 06/20/2022 | SP-229 | ABHD-7 | RIG | 19 Jun 0000 - 0230 | 21 | 26 | 898495 |  | FISH | HERR | BHA | 8750 | POH TO SURFACE AND FOUND 3-3/4" CP MILL LOST IN THE WELL.
1877 | 06/20/2022 | SP-229 | ABHD-7 | ARM | 15 Jun 1430 - 0500 | 3 | 108.5 | 898352 |  | JF | HERR | NA | 0 | NO IN-FLOW FROM PERFORATIONS
1878 | 06/20/2022 | SP-229 | ABHD-7 | RIG | 19 Jun 0000 - 0230 | 21 | 26 | 898495 |  | FISH | HERR | BHA | 8750 | POH TO SURFACE AND FOUND 3-3/4" CP MILL LOST IN THE WELL.
1880 | 06/20/2022 | SSA-101 | QTIF-785 | SPS | 19 Jun 1330 - 0500 | 24 | 39.5 | 898508 |  | BHA | FOT | RSS | 9795 | SPS RSS GIVING WRONG VALUES AT MID WAY TOOL CHECK WHILE RIH,SPS TROUBLE SHOOT BY PUMPING HI VIS PILL AND JERKING STRING, NO PROGRESS(2ND SPS TOOL FAILURE IN 6 1/8" L-0 HOLE) - DECISION TO CHANGE DIRECTIONAL COMPANY FROM SPS TO SDM.
1882 | 06/20/2022 | SSA-201 | HRDH-2112 | SCD | 20 Jun 0500 - 0700 | 2 | 2 | 898515 |  | TF | FOT | GYRO | 13650 | OBSERVE LOST COMMUNICATION FROM GYRO TOOL. POOH WITH GYRO TOOL TO SURFACE. REPLACE TOOL & RIH.
1884 | 06/20/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 235 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1886 | 06/20/2022 | SSA-303 | HRDH-2306 | ITS | 20 Jun 2200 - 0330 | 5.5 | 5.5 | 898557 |  | TF | FOT | PEL | 0 | DIFFICULTY WITH OPENING AND CLOSING ITS 4-1/2" ELEVATORS.
1888 | 06/22/2022 | ADC-43L | UTMN-3118 | SDM | 22 Jun 1200 - 0500 | 17 | 17 | 898665 |  | BHA | FOT | MWD | 10818 | OBSERVED MWD SIGNAL PROBLEMS, TROUBLESHOOTED SAME AND PERFORMED ANTI-JAM PROCEDURE WITH NO SUCCESS.
1890 | 06/22/2022 | ADC-54L | HRDH-1499 | TK2 | 22 Jun 0330 - 0500 | 1.5 | 1.5 | 898697 |  | STUK | STBH | BHA | 3440 | HAD COMPLETE LOSSES @ 3501' IN SHUAIBA FM, P/U TDS WHILE CIRC. & RECIPROCATIONG STRING & PUMP MUD CAP 75 PCF FROM BACK SIDE. STRING STALL 60' OFF-BTM & GOT STUCK @ 3440' (NO MOUVMENT UP/DOWN). WORK ON STUCK.
1892 | 06/22/2022 | ADC-55L | UTMN-3171 | TK3 | 21 Jun 1415 - 2345 | 18.75 | 33 | 898634 |  | WCNT | WC11 | NA | 6243 | OBSERVED INCREASE IN FLOW OUT
1913 | 06/22/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 100 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
1915 | 06/22/2022 | ADES-158 | ABQQ-736 | RIG | 20 Jun 1730 - 2030 | 15.5 | 42 | 898654 | 897478 | JF | HERR | STRG | 5206 | HAD OBSTRUCTION @ 5206' WHILE RIH WITH BAKER DIR BHA.
1917 | 06/22/2022 | ADM-337 | MRJN-900 | SLL | 18 Jun 0100 - 0600 | 1 | 69.5 | 898514 |  | TF | ISEQ | SB | 11365 | UNABLE TO PASS TOL WITH SCHLUMBERGER W/LINE TOOLS CBL & USIT
1918 | 06/22/2022 | AOD-11 | SFNY-1810 | BCR | 22 Jun 0300 - 0500 | 2 | 2 | 898698 |  | TF | HERR | TTRQ | 4401 | SLIPPAGE OF CONNECTION BETWEEN STC X-OVER & MLC PUP JT, CONSEQUENTLY THE 13-3/8" CSG JT BELOW THE X-OVER DROPPED INSIDE ROTARY HAND CSG SLIPS & GET COLLAPSED.
1920 | 06/22/2022 | AOD-11 | SFNY-1810 | BCR | 22 Jun 0030 - 0045 | .25 | .25 | 898639 |  | TF | FOT | CRT | 3555 | BAKER CRT MALFUNCTION.
1921 | 06/22/2022 | AOD-11 | SFNY-1810 | BCR | 22 Jun 1930 - 2000 | .5 | .5 | 898663 |  | TF | FOT | CTRQ | 2206 | OIL LEAK IN BAKER FMS.
1922 | 06/22/2022 | AOD-11 | SFNY-1810 | BCR | 22 Jun 0300 - 0500 | 2 | 2 | 898698 |  | TF | HERR | TTRQ | 4401 | SLIPPAGE OF CONNECTION BETWEEN STC X-OVER & MLC PUP JT, CONSEQUENTLY THE 13-3/8" CSG JT BELOW THE X-OVER DROPPED INSIDE ROTARY HAND CSG SLIPS & GET COLLAPSED.
1923 | 06/22/2022 | ARO-3004 | MRJN-2060 | RIG | 22 Jun 0045 - 0500 | 4.25 | 4.25 | 898695 |  | RR | FOT | RWCS | 7820 | ARO LT: RELIEF VALVES ON ACCUMULATOR SYSTEM BOTTLES NO FUNCTIONING (7 FAILED OF TOTAL 10 RELIEF VALVES), REPLACING SAME
1925 | 06/22/2022 | ARO-3004 | MRJN-2060 | RIG | 22 Jun 1515 - 1600 | .75 | .75 | 898678 |  | RR | LHFL | HSYS | 8800 | ARO LT : LINK/TILT NOT FUNCTIONING, OBSERVED LEAKAGE IN AIR HOSE, REPLACED SAME, OK
1926 | 06/22/2022 | ARO-3004 | MRJN-2060 | RIG | 22 Jun 0045 - 0500 | 4.25 | 4.25 | 898695 |  | RR | FOT | RWCS | 7820 | ARO LT: RELIEF VALVES ON ACCUMULATOR SYSTEM BOTTLES NO FUNCTIONING (7 FAILED OF TOTAL 10 RELIEF VALVES), REPLACING SAME
1928 | 06/22/2022 | ARO-4001 | MRJN-538 | ARM | 21 Jun 0145 - 0500 | 24 | 27.25 | 898664 |  | STUK | PSSW | NA | 14130 | UNABLE TO RUN MPAS ASSY WITH INNER STRING TO SETTING DEPTH FROM PIPE STICKING & LOCKUP DUE TO WELLBORE GEOMETRY
1930 | 06/22/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 317.5 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
1931 | 06/22/2022 | ED-85A | ZULF-2063 | RIG | 22 Jun 1400 - 1445 | .75 | .75 | 898677 |  | RR | FOT | RWCS | 2112 | WHILE FILL AND FUNCTION TEST THE DIVERTER SYSTEM, FOUND A LEAK ON THE OVERSHOT SEAL. TROUBLESHOOT SHOT AND FIX SAME.
1933 | 06/22/2022 | ED-85A | ZULF-2063 | SDM | 14 Jun 0315 - 2345 | .75 | 2.5 | 898156 |  | SURV | FOT | GYRO | 403 | UNABLE TO OBTAIN GYRO SURVEY
1934 | 06/22/2022 | ED-85A | ZULF-2063 | RIG | 22 Jun 1400 - 1445 | .75 | .75 | 898677 |  | RR | FOT | RWCS | 2112 | WHILE FILL AND FUNCTION TEST THE DIVERTER SYSTEM, FOUND A LEAK ON THE OVERSHOT SEAL. TROUBLESHOOT SHOT AND FIX SAME.
1936 | 06/22/2022 | EXL-IA | SFNY-4240 | RIG | 22 Jun 1515 - 1715 | 2 | 2 | 898692 |  | RR | FOT | DWKS | 0 | WHILE SLIPPING AND CUTTING DRILLING OBSERVED LEAK ON PARK BRAKE CYLINDER
1938 | 06/22/2022 | NBR-16S | HMYM-433114 | RIG | 22 Jun 0100 - 0300 | 2 | 2 | 898638 |  | JF | XTRI | NA | 0 | EXCESSIVE TIME TO L/D BHA. TIGHT CONNECTIONS.
1939 | 06/22/2022 | NBR-263S | QTIF-736 | ARM | 22 Jun 0630 - 0500 | 19.5 | 19.5 | 898674 |  | LCIR | UVLC | NA | 8541 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES.
1941 | 06/22/2022 | NBR-263S | QTIF-736 | ARM | 21 Jun 1830 - 0630 | 1.5 | 12 | 898523 |  | WCNT | WC20 | NA | 8541 | WHILE WASH & REAM PRIOR CONNECTION OBSERVE INCREASE IN ACTIVE MUD TANKS. STOP PUMP & FLOW CHECK OBSERVE WELL FLOWING, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=160 PSI, PUMP OUT FLOAT VALVE AND OBSERVE SIDPP=70 PSI. - LINE UP TO TRIP TANK AND BLEED OFF PRESS 50 PSI, CLOSE CHOKE OBSERVE PRESS BUILD UP. - KILL WELL WITH DRILLER METHOD.
1942 | 06/22/2022 | NBR-263S | QTIF-736 | RIG | 22 Jun 2115 - 0015 | 3 | 3 | 898666 |  | RR | FOT | DWKS | 5920 | OBSERVE DEPTH SENSOR FOR SLB MUD LOGGING & SPS COME OUT FROM DRAWWORKS ENCODER SHAFT, FIX DRAWWORK ENCODER SHAFT.
1943 | 06/22/2022 | NBR-263S | QTIF-736 | ARM | 22 Jun 0630 - 0500 | 19.5 | 19.5 | 898674 |  | LCIR | UVLC | NA | 8541 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES.
1945 | 06/22/2022 | NBR-654S | HRDH-1150 | ARM | 22 Jun 0545 - 0645 | 1 | 1 | 898672 |  | STUK | STBH | BHA | 7516 | STALLED ROTARY WHILE DRILLING. P/U AND ESTABLISH ROTATION. BACKREAM TO 7516 FT AND GOT STUCK, HAD FULL CIRCULATION. WORK WITH STRING AND JAR DOWN GOT STRING FREE.
1947 | 06/22/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 185 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
1949 | 06/22/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 551.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
1951 | 06/22/2022 | RM-74A | HSBH-68 | RIG | 22 Jun 1900 - 0500 | 10 | 10 | 898635 |  | UPRA | GRF | RWCS | 1573 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
1971 | 06/22/2022 | SND-2001 | UTMN-2329 | SDM | 19 Jun 1930 - 1830 | 13.5 | 58 | 898492 |  | BHA | FOT | RSS | 15637 | RSS UNABLE TO BUILD UP REQUIRED INCLINATION.
1973 | 06/22/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 0500 | 24 | 149.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
1975 | 06/22/2022 | SP-110 | BRRI-562 | RIG | 22 Jun 1500 - 0500 | 14 | 14 | 898693 |  | BOP | FOT | BOP | 16758 | OBSERVED A LEAK ON BOP SHEAR RAM BONNET, RUN RTTS TO SECURE THE WELL & CHANGE BONNET SEAL
1977 | 06/22/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 283 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
1979 | 06/22/2022 | SSA-5868 | HRDH-2413 | RIG | 22 Jun 1530 - 0500 | 13.5 | 13.5 | 898636 |  | JF | HERR | DWKS | 4890 | WHILE LOWERING TDS AFTER RACKING BACK A STAND OF 5.5" DP A LOUD BANG WAS HEARD. ON INVESTIGATION IT WAS DISCOVERED THE DRILLINE CLAMP HAD CAME LOOSE FROM THE SOCKET.
1980 | 06/22/2022 | SSA-5891 | HRDH-1292 | RIG | 22 Jun 0230 - 0500 | 2.5 | 2.5 | 898696 |  | JF | HERR | HWDP | 13007 | DRIFTING 5" HWDP OUT OF DERRICK AND DRIFT WENT DOWN DRILL STRING TO TOP OF 7" LINER.
1982 | 06/22/2022 | SSA-5891 | HRDH-1292 | WCR | 22 Jun 0800 - 1830 | 6.5 | 6.5 | 898673 |  | TF | XTTE | CTRQ | 13007 | WORK ON WEATHERFORD EQUIPMENT TO PU & TORQUE UP 7" LINER.(POWER TONGS, POWER UNITS & PU/LD MACHINE). WAIT ON POWER UNIT FROM WFD YARD.
1983 | 06/22/2022 | SSA-5891 | HRDH-1292 | RIG | 22 Jun 0230 - 0500 | 2.5 | 2.5 | 898696 |  | JF | HERR | HWDP | 13007 | DRIFTING 5" HWDP OUT OF DERRICK AND DRIFT WENT DOWN DRILL STRING TO TOP OF 7" LINER.
1985 | 06/22/2022 | WCL-83 | MRJN-834 | ARM | 21 Jun 0530 - 0500 | 24 | 47.5 | 898656 |  | STUK | STCT | SCRN | 11680 | WORK ON STUCK COMPLETION STRING BY DIFFERENT PARAMETERS
1987 | 06/23/2022 | 095TE | MNIF-226 | MSD | 23 Jun 1530 - 1730 | 2 | 2 | 898642 |  | TF | FOT | CTRQ | 5880 | ALMASOOD CASING SPIDER ELEVATOR MALFUNCTION ,ATTEMPT TO FIX IT, WITHOUT SUCCESS, RIG DOWN SAME AND R/U NEW BACK UP ONE.
1989 | 06/23/2022 | ADC-16 | JAHM-6 | SWL | 22 Jun 1345 - 1200 | 7 | 22.25 | 898640 |  | TF | FOT | WLT | 11586 | ORA TOOL FAILED
1990 | 06/23/2022 | ADC-35 | MAQL-5 | BAW | 23 Jun 0100 - 0500 | 4 | 4 | 898686 |  | TF | FOT | WLT | 11655 | BAKER START PUMPING TO INFLATE THE PACKER THE TOOL STARTED DREW HIGH CURRENT, BAKER PERFORMED TROUBLE SHOOTING W/OUT SUCCESS.
1992 | 06/23/2022 | ADC-35 | MAQL-5 | BAW | 23 Jun 1430 - 2200 | 7.5 | 7.5 | 898669 |  | TF | FOT | WLT | 11655 | BAKER START PUMPING TO INFLATE THE PACKER THE TOOL STARTED DREW HIGH CURRENT, BAKER PERFORMED TROUBLE SHOOTING W/OUT SUCCESS.
1993 | 06/23/2022 | ADC-35 | MAQL-5 | BAW | 23 Jun 0100 - 0500 | 4 | 4 | 898686 |  | TF | FOT | WLT | 11655 | BAKER START PUMPING TO INFLATE THE PACKER THE TOOL STARTED DREW HIGH CURRENT, BAKER PERFORMED TROUBLE SHOOTING W/OUT SUCCESS.
1994 | 06/23/2022 | ADC-43L | UTMN-3118 | SDM | 22 Jun 1200 - 2345 | 13.75 | 30.75 | 898665 |  | BHA | FOT | MWD | 10818 | OBSERVED MWD SIGNAL PROBLEMS, TROUBLESHOOTED SAME AND PERFORMED ANTI-JAM PROCEDURE WITH NO SUCCESS.
1996 | 06/23/2022 | ADC-43L | UTMN-3118 | TK3 | 19 Jun 0245 - 0500 | 5.25 | 43.5 | 898513 |  | WCNT | WCC8 | NA | 10535 | OBSERVED INCREASE IN MPD RETURN FLOW. WELL FLOWING. SHUT-IN WELL ON RCD W/ 5 RPM. RECORD INITIAL SIDPP-1100 PSI, SICP - 1400 PSI, & PIT GAIN - 25 BBL.
1997 | 06/23/2022 | ADC-43L | UTMN-3118 | SDM | 22 Jun 1200 - 2345 | 13.75 | 30.75 | 898665 |  | BHA | FOT | MWD | 10818 | OBSERVED MWD SIGNAL PROBLEMS, TROUBLESHOOTED SAME AND PERFORMED ANTI-JAM PROCEDURE WITH NO SUCCESS.
1999 | 06/23/2022 | ADC-54L | HRDH-1499 | TK2 | 22 Jun 0330 - 0500 | 24 | 25.5 | 898697 |  | STUK | STBH | BHA | 3440 | HAD COMPLETE LOSSES @ 3501' IN SHUAIBA FM, P/U TDS WHILE CIRC. & RECIPROCATIONG STRING & PUMP MUD CAP 75 PCF FROM BACK SIDE. STRING STALL 60' OFF-BTM & GOT STUCK @ 3440' (NO MOUVMENT UP/DOWN). WORK ON STUCK.
2018 | 06/23/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 124 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
2020 | 06/23/2022 | ADC-67L | SDGM-1265 | SDM | 23 Jun 1200 - 0500 | 13.25 | 13.25 | 898687 |  | BHA | FOT | RSS | 13214 | RSS NOT RESPOND, PERFORMED TROUBLESHOOTING, NO SUCCESS.
2022 | 06/23/2022 | ADM-262 | MRJN-122 | RIG | 23 Jun 0930 - 1130 | 2 | 2 | 898699 |  | RR | FOT | TDS | 5920 | TDS GRIPPER DIES ENGAGED ONTO SAVER SUB PIN DAMAGING THREADS. CHANGE SAVER SUB.
2024 | 06/23/2022 | ADM-511 | MRJN-799 | ARN | 23 Jun 1200 - 1315 | 1.25 | 1.25 | 898670 |  | TF | FOT | VSAT | 9378 | HAD V-SAT ISSUE UNABLE TO TRANSMIT REAL TIME DATA TO GOC.
2026 | 06/23/2022 | ADM-657 | ZULF-73 | ARM | 20 Jun 1015 - 1830 | 6.25 | 17 | 898553 |  | WON | WTHR | NA | 0 | WIND SPEED DROPPED TO 1 KTS DURING FLARING. STOP OPERATION AND WAIT FOR WIND SPEED TO INCREASE.
2028 | 06/23/2022 | ARO-3004 | MRJN-2060 | RIG | 22 Jun 0045 - 0600 | 1 | 5.25 | 898695 |  | RR | FOT | RWCS | 7820 | ARO LT: RELIEF VALVES ON ACCUMULATOR SYSTEM BOTTLES NO FUNCTIONING (7 FAILED OF TOTAL 10 RELIEF VALVES), REPLACING SAME
2030 | 06/23/2022 | ARO-4001 | MRJN-538 | ARM | 21 Jun 0145 - 0500 | 24 | 51.25 | 898664 |  | STUK | PSSW | NA | 14130 | UNABLE TO RUN MPAS ASSY WITH INNER STRING TO SETTING DEPTH FROM PIPE STICKING & LOCKUP DUE TO WELLBORE GEOMETRY
2032 | 06/23/2022 | BCTD-3 | HWYH-962 | BHI | 23 Jun 2000 - 0500 | 7 | 7 | 898752 |  | BHA | FOT | MWD | 13444 | LOSS OF TELEMETRY OF DOWNHOLE TOOL
2034 | 06/23/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 341.5 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
2036 | 06/23/2022 | ENSCO-54 | ABSF-17 | SPS | 23 Jun 1530 - 0500 | 13.5 | 13.5 | 898671 |  | BHA | FOT | RSS | 6164 | RSS NOT RESPONDING - TROUBLE SHOOT - NO SUCCESS
2038 | 06/23/2022 | EXL-IVA | SFNY-1650 | RIG | 23 Jun 1315 - 1730 | 4.25 | 4.25 | 898685 |  | BOP | FOT | DVRT | 335 | ATTEMPT TO FUNCTION TEST 30" DIVERTER WITHOUT SUCCESS, TROUBLE SHOOT AND REPAIR. **DISCONNECT CONTROL LINES AND PURGE, RETIGHTEN DIVERTER CONNECTION FROM LEAKING, FUNCTION TEST DIVERTER OK.
2040 | 06/23/2022 | HI-9 | BRRI-238 | EX1 | 23 Jun 1100 - 0500 | 18 | 18 | 898684 |  | TF | FOT | SLICK | 0 | EXPRO SLICK LINE STUFFING BOX WHEEL WAS BROKEN WHILE RETRIEVING PUMP THRU PLUG FROM XN NIPPLE.
2042 | 06/23/2022 | MP-1 | MRJN-79 | HCO | 23 Jun 2345 - 0500 | 5.25 | 5.25 | 898733 |  | TF | FOT | HVLV | 223 | AFTER RIH ON SLICKLINE HAL WRSSSV, ATTEMPTED TO FUCTION TEST. NO SUCCESS. CONTROL LINE PRESSURE IMMEDIATELY BUILDING WHEN TRYING TO OPEN THE WRSSSV. TROUBLE SHOOT WITH NO SUCCESS. RETRIEVED WITH SLICKLINE AND CONTINUED TO TROUBLE SHOOT.
2044 | 06/23/2022 | NBR-115S | HWYH-1220 | RIG | 23 Jun 0630 - 0830 | 2 | 2 | 898683 |  | RR | FOT | TDS | 20614 | OBSERVED LEAK AT LOWER CONTROL VALVE & 5.5" DP CONNECTION. OBSERVED FAULT WITH TDS TORQUE;
2045 | 06/23/2022 | NBR-263S | QTIF-736 | RIG | 23 Jun 0400 - 0500 | 1 | 1 | 898754 |  | RR | FOT | EDR | 4600 | ROUGHNECK MALFUNCTION DUE TO ELECTERICAL PROBLEM. CAN-RIG TECHNICIAN WORKING TO FIX
2047 | 06/23/2022 | NBR-263S | QTIF-736 | ARM | 22 Jun 0630 - 0400 | 20.25 | 39.75 | 898674 |  | LCIR | UVLC | NA | 8541 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG.
2048 | 06/23/2022 | NBR-263S | QTIF-736 | RIG | 23 Jun 1930 - 2145 | 2.25 | 2.25 | 898712 |  | RR | FOT | HSYS | 8551 | PRAGMA HYDRAULIC HOSE LEAK.
2049 | 06/23/2022 | NBR-263S | QTIF-736 | RIG | 23 Jun 0400 - 0500 | 1 | 1 | 898754 |  | RR | FOT | EDR | 4600 | ROUGHNECK MALFUNCTION DUE TO ELECTERICAL PROBLEM. CAN-RIG TECHNICIAN WORKING TO FIX
2051 | 06/23/2022 | PA-218S | HRDH-1941 | CAM | 23 Jun 1630 - 2030 | 4 | 4 | 898688 |  | WH | FOT | WH | 5845 | EXCESS TIME ON CAMERON TO INSTALL FMH PACK-OFF ASSY. IN MANY TRIALS.
2053 | 06/23/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 209 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
2055 | 06/23/2022 | PA-604S | HRDH-1955 | RIG | 23 Jun 1200 - 2100 | 9 | 9 | 898667 |  | RR | FOT | PSYS | 6470 | RIG POWER SYSTEM BLACKOUT DURING DRILLING DUE TO OVER HEATED.
2057 | 06/23/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 575.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
2059 | 06/23/2022 | RM-74A | HSBH-68 | RIG | 22 Jun 1900 - 0500 | 24 | 34 | 898635 |  | UPRA | GRF | RWCS | 1573 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
2061 | 06/23/2022 | SIN30L | KHRS-180 | BCR | 23 Jun 2030 - 2230 | 2 | 2 | 898689 |  | TF | FOT | CRT | 0 | CRT FAILURE
2070 | 06/23/2022 | SINO-15L | ANDR-482 | BC | 22 Jun 1100 - 1100 | 6 | 24 | 898682 |  | TF | HERR | TBG | 0 | TRSSSV CONTROL LINE NOT SUPPORTED AROUND TBG.
2075 | 06/23/2022 | SINO-22 | BRRI-579 | RIG | 23 Jun 1400 - 1515 | 1.25 | 1.25 | 898641 |  | RR | FOT | HSYS | 208 | CSG STABBING BOARD'S DIVING BOARD HYD CYLINDER DAMAGED, LEAD TO MISALIGN TWO CSG JTS AND DAMAGE THREADS.
2076 | 06/23/2022 | SINO-36L | SDGM-458 | NC1 | 23 Jun 1400 - 0500 | 15 | 15 | 898690 |  | TF | FOT | FISHT | 5325 | DOWN TIME ON HALLIBURTON LSTK1 DUE TO STRING PARTED.
2078 | 06/23/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 1400 | 9 | 146.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
2079 | 06/23/2022 | SINO-36L | SDGM-458 | NC1 | 23 Jun 1400 - 0500 | 15 | 15 | 898690 |  | TF | FOT | FISHT | 5325 | DOWN TIME ON HALLIBURTON LSTK1 DUE TO STRING PARTED.
2081 | 06/23/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 0500 | 24 | 173.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
2083 | 06/23/2022 | SND-3003 | HRDH-1816 | RIG | 23 Jun 0400 - 0500 | 1 | 1 | 898755 |  | RR | FOT | TDS | 455 | TDS STOP FUNCTIONING AND ROTAING.
2085 | 06/23/2022 | SP-110 | BRRI-562 | RIG | 22 Jun 1500 - 0500 | 14.5 | 28.5 | 898693 |  | BOP | FOT | BOP | 16758 | OBSERVED A LEAK ON BOP SHEAR RAM BONNET, RUN RTTS TO SECURE THE WELL & CHANGE BONNET SEAL
2087 | 06/23/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 307 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
2088 | 06/23/2022 | SSA-5859 | HWYH-1222 | RIG | 23 Jun 1300 - 1630 | 3.5 | 3.5 | 898773 |  | RR | FOT | TDS | 11905 | EXCESS TORQUE OFF BOTTOM
2090 | 06/23/2022 | SSA-5859 | HWYH-1222 | SPS | 23 Jun 1200 - 0500 | 11 | 11 | 898772 |  | BHA | FOT | MWD | 11905 | MWD LOST SIGNAL
2091 | 06/23/2022 | SSA-5859 | HWYH-1222 | RIG | 23 Jun 1300 - 1630 | 3.5 | 3.5 | 898773 |  | RR | FOT | TDS | 11905 | EXCESS TORQUE OFF BOTTOM
2093 | 06/23/2022 | SSA-5868 | HRDH-2413 | RIG | 22 Jun 1530 - 0530 | .5 | 14 | 898636 |  | JF | HERR | DWKS | 4890 | WHILE LOWERING TDS AFTER RACKING BACK A STAND OF 5.5" DP A LOUD BANG WAS HEARD. ON INVESTIGATION IT WAS DISCOVERED THE DRILLINE CLAMP HAD CAME LOOSE FROM THE SOCKET.
2095 | 06/23/2022 | SSA-5891 | HRDH-1292 | RIG | 22 Jun 0230 - 2200 | 17 | 19.5 | 898696 |  | JF | HERR | HWDP | 13007 | DRIFTING 5" HWDP OUT OF DERRICK AND DRIFT WENT DOWN DRILL STRING TO TOP OF 7" LINER.
2097 | 06/23/2022 | SSA-5917 | HRDH-2261 | RIG | 23 Jun 1000 - 1115 | 1.25 | 1.25 | 898700 |  | TF | FOT | SFLN | 12955 | SUSPECT PLLUGGED ON SURFACE LINE OR DOWN ANNULAR WHILE REVERSE OUT ACID TRAIN AFTER PUMPING 33 BBL, PRESSURE INCREASED &LOST RETURN TRY SEVERAL TIME TO UPPLUGGED , SWITCH TO SANJEL UNITE AND TRY FROM TCA ENCOUTRNED SAME SITUATION SVERAL TIME UNTILL UNPLUGGED AND GOT RETURN.
2099 | 06/23/2022 | WCL-83 | MRJN-834 | ARM | 21 Jun 0530 - 0500 | 24 | 71.5 | 898656 |  | STUK | STCT | SCRN | 11680 | WORK ON STUCK COMPLETION STRING BY DIFFERENT PARAMETERS
2101 | 06/24/2022 | ADC-35 | MAQL-5 | BAW | 23 Jun 0100 - 0500 | 24 | 28 | 898686 |  | TF | FOT | WLT | 11655 | BAKER START PUMPING TO INFLATE THE PACKER THE TOOL STARTED DREW HIGH CURRENT, BAKER PERFORMED TROUBLE SHOOTING W/OUT SUCCESS.
2103 | 06/24/2022 | ADC-43L | UTMN-3118 | TK3 | 23 Jun 2345 - 0500 | 22 | 27.25 | 898774 |  | WCNT | WC11 | NA | 10818 | PUMP OUT OF HOLE, OBSERVED HOLE NOT TAKING THE RIGHT AMOUNT OF MUD. FLOW CHECK - WELL FLOWING. SHUT IN WELL, SICP = 250 PSI.
2105 | 06/24/2022 | ADC-51 | SDGM-1245 | HCM | 24 Jun 0015 - 0215 | 2 | 2 | 898776 |  | CMT | HERR | NA | 0 | EXCESS TIME DUE TO LEAK ON SURFACE LINES/PUMP UNIT
2107 | 06/24/2022 | ADC-54L | HRDH-1499 | TK2 | 22 Jun 0330 - 0500 | 24 | 49.5 | 898697 |  | STUK | STBH | BHA | 3440 | HAD COMPLETE LOSSES @ 3501' IN SHUAIBA FM, P/U TDS WHILE CIRC. & RECIPROCATIONG STRING & PUMP MUD CAP 75 PCF FROM BACK SIDE. STRING STALL 60' OFF-BTM & GOT STUCK @ 3440' (NO MOUVMENT UP/DOWN). WORK ON STUCK.
2123 | 06/24/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 148 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
2125 | 06/24/2022 | ADC-67L | SDGM-1265 | SDM | 23 Jun 1200 - 0500 | 24 | 37.25 | 898687 |  | BHA | FOT | RSS | 13214 | RSS NOT RESPOND, PERFORMED TROUBLESHOOTING, NO SUCCESS.
2127 | 06/24/2022 | ADC-68L | ABHD-176 | SDM | 24 Jun 0800 - 0500 | 20.5 | 20.5 | 898796 |  | BHA | FOT | MMOT | 4490 | OBSERVED SLOW ROP WHILE DRILLING, TROUBLESHOOT SDM MUD MOTOR.
2129 | 06/24/2022 | AOD-111 | MRJN-724 | RIG | 24 Jun 0245 - 0500 | 2.25 | 2.25 | 898795 |  | TF | HERR | TBG | 16067 | WHILE LIFTING THE BOP, THE RISER CONTACTED & DAMAGED PDHMS CABLE UNION CONNECTION ON THE HANGER.
2131 | 06/24/2022 | BB-84A | MRJN-587 | RIG | 24 Jun 1015 - 1815 | 8 | 8 | 898797 |  | RR | FOT | DWKS | 0 | DRAWWORKS NOT WORKING ( NOT SEEING LUBE OIL PRESSURE : 30 PSI ), ET REPLACED TRANSMITTER & ELECTIRC WIRE WITH NEW ONE, NO SUCCESS.
2133 | 06/24/2022 | BCTD-3 | HWYH-962 | BHI | 23 Jun 2000 - 1200 | 7 | 14 | 898752 |  | BHA | FOT | MWD | 13444 | LOSS OF TELEMETRY OF DOWNHOLE TOOL
2135 | 06/24/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 365.5 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
2137 | 06/24/2022 | ENSCO-54 | ABSF-17 | SPS | 23 Jun 1530 - 1300 | 8 | 21.5 | 898671 |  | BHA | FOT | RSS | 6164 | RSS NOT RESPONDING - TROUBLE SHOOT - NO SUCCESS
2139 | 06/24/2022 | EXL-IA | SFNY-4240 | ARM | 23 Jun 0400 - 0315 | 6.75 | 7.5 | 898703 |  | LCIR | FRFM | NA | 8536 | WHILE DRILLING HAD 60BBL/HR LOSSES
2141 | 06/24/2022 | HI-9 | BRRI-238 | EX1 | 23 Jun 1100 - 1400 | 9 | 27 | 898684 |  | TF | FOT | SLICK | 0 | EXPRO SLICK LINE STUFFING BOX WHEEL WAS BROKEN WHILE RETRIEVING PUMP THRU PLUG FROM XN NIPPLE.
2143 | 06/24/2022 | MP-1 | MRJN-79 | HCO | 23 Jun 2345 - 0500 | 24 | 29.25 | 898733 |  | TF | FOT | HVLV | 223 | AFTER RIH ON SLICKLINE HAL WRSSSV, ATTEMPTED TO FUCTION TEST. NO SUCCESS. CONTROL LINE PRESSURE IMMEDIATELY BUILDING WHEN TRYING TO OPEN THE WRSSSV. TROUBLE SHOOT WITH NO SUCCESS. RETRIEVED WITH SLICKLINE AND CONTINUED TO TROUBLE SHOOT.
2145 | 06/24/2022 | NBR-115S | HWYH-1220 | RIG | 24 Jun 0700 - 1230 | 5.5 | 5.5 | 898756 |  | RR | FOT | TDS | 21085 | WHILE SETTING THE RSS TO NEUTRAL THE TOP DRIVE FAILED AND STOPPED ROTATING.
2147 | 06/24/2022 | PA-218S | HRDH-1941 | RIG | 24 Jun 0000 - 0300 | 3 | 3 | 898705 |  | BOP | FOT | BOP | 5845 | EXCESS TIME WHILE TESTING BOPE DUE TO LEAKING CONNECTIONS.
2149 | 06/24/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 233 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
2151 | 06/24/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 599.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
2153 | 06/24/2022 | PA-785S | QTIF-269 | RIG | 24 Jun 1530 - 1630 | 1 | 1 | 898759 |  | RR | FOT | TDS | 0 | RIG CHANGE DIE BLOCKS FOR GRIPPER ON TOP DRIVE.
2155 | 06/24/2022 | PA-866S | SHHB-2 | WCR | 24 Jun 1345 - 1615 | 2.5 | 2.5 | 898765 |  | TF | FOT | CTRQ | 5053 | MULTIPLE POWER UNIT FAILURES WHILE RIH 9-5/8" CSG. ALL WFD POWER UNITS ON LOCATION REQUIRE REPAIRS.
2157 | 06/24/2022 | RM-74A | HSBH-68 | RIG | 22 Jun 1900 - 0500 | 24 | 58 | 898635 |  | UPRA | GRF | RWCS | 1573 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
2159 | 06/24/2022 | SCTD-1 | SDGM-1152 | SDM | 24 Jun 1900 - 0500 | 10 | 10 | 898761 |  | BHA | FOT | MWD | 15594 | MWD FAILURE & COMPLETE LOSS OF COMMUNICATION.
2161 | 06/24/2022 | SINO-36L | SDGM-458 | NC1 | 23 Jun 1400 - 0500 | 24 | 39 | 898690 |  | TF | FOT | FISHT | 5325 | DOWN TIME ON HALLIBURTON LSTK1 DUE TO STRING PARTED.
2178 | 06/24/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 0500 | 24 | 197.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
2180 | 06/24/2022 | SNT-025 | SFNY-652 | WWD | 24 Jun 1915 - 0500 | 9.75 | 9.75 | 898760 |  | TF | FOT | WPSTK | 82 | SHEAR BOLT ON WHIPSTOCK ASSY FAILED WHILE RIH ACROSS WELLHEAD.
2182 | 06/24/2022 | SP-110 | BRRI-562 | RIG | 22 Jun 1500 - 0530 | .5 | 29 | 898693 |  | BOP | FOT | BOP | 16758 | OBSERVED A LEAK ON BOP SHEAR RAM BONNET, RUN RTTS TO SECURE THE WELL & CHANGE BONNET SEAL
2184 | 06/24/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 331 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
2186 | 06/24/2022 | SSA-5859 | HWYH-1222 | SPS | 23 Jun 1200 - 0500 | 23.5 | 34.5 | 898772 |  | BHA | FOT | MWD | 11905 | MWD LOST SIGNAL
2188 | 06/24/2022 | SSA-5969 | UTMN-3021 | ARM | 24 Jun 2030 - 0500 | 8.5 | 8.5 | 898762 |  | LROP | LTHI | BIT | 14375 | OBSERVED VERY LOW ROP.
2190 | 06/24/2022 | WCL-83 | MRJN-834 | ARM | 21 Jun 0530 - 0645 | 1.75 | 73.25 | 898656 |  | STUK | STCT | SCRN | 11680 | WORK ON STUCK COMPLETION STRING BY DIFFERENT PARAMETERS
2192 | 06/25/2022 | ADC-35 | MAQL-5 | BAW | 23 Jun 0100 - 0930 | 4.5 | 32.5 | 898686 |  | TF | FOT | WLT | 11655 | BAKER START PUMPING TO INFLATE THE PACKER THE TOOL STARTED DREW HIGH CURRENT, BAKER PERFORMED TROUBLE SHOOTING W/OUT SUCCESS.
2193 | 06/25/2022 | ADC-43L | UTMN-3118 | TK3 | 23 Jun 2345 - 0030 | 19.5 | 46.75 | 898774 |  | WCNT | WC11 | NA | 10818 | PUMP OUT OF HOLE, OBSERVED HOLE NOT TAKING THE RIGHT AMOUNT OF MUD. FLOW CHECK - WELL FLOWING. SHUT IN WELL, SICP = 250 PSI.
2195 | 06/25/2022 | ADC-43L | UTMN-3118 | SDM | 22 Jun 1200 - 0500 | 4.5 | 40.25 | 898665 |  | BHA | FOT | MWD | 10818 | OBSERVED MWD SIGNAL PROBLEMS, TROUBLESHOOTED SAME AND PERFORMED ANTI-JAM PROCEDURE WITH NO SUCCESS.
2196 | 06/25/2022 | ADC-43L | UTMN-3118 | TK3 | 23 Jun 2345 - 0030 | 19.5 | 46.75 | 898774 |  | WCNT | WC11 | NA | 10818 | PUMP OUT OF HOLE, OBSERVED HOLE NOT TAKING THE RIGHT AMOUNT OF MUD. FLOW CHECK - WELL FLOWING. SHUT IN WELL, SICP = 250 PSI.
2198 | 06/25/2022 | ADC-54L | HRDH-1499 | TK2 | 22 Jun 0330 - 0500 | 24 | 73.5 | 898697 |  | STUK | STBH | BHA | 3440 | HAD COMPLETE LOSSES @ 3501' IN SHUAIBA FM, P/U TDS WHILE CIRC. & RECIPROCATIONG STRING & PUMP MUD CAP 75 PCF FROM BACK SIDE. STRING STALL 60' OFF-BTM & GOT STUCK @ 3440' (NO MOUVMENT UP/DOWN). WORK ON STUCK.
2200 | 06/25/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 172 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
2202 | 06/25/2022 | ADC-67L | SDGM-1265 | SDM | 23 Jun 1200 - 1400 | 9 | 46.25 | 898687 |  | BHA | FOT | RSS | 13214 | RSS NOT RESPOND, PERFORMED TROUBLESHOOTING, NO SUCCESS.
2203 | 06/25/2022 | ADC-68L | ABHD-176 | TK3 | 25 Jun 0030 - 0500 | 4 | 4 | 898815 |  | LROP | VPFM | BIT | 4547 | SLOW ROP WHILE DRILLING, PUMPED 2 DISPERSANT PILL WITHOUT SUCCESS.
2205 | 06/25/2022 | ADC-68L | ABHD-176 | TK3 | 24 Jun 0800 - 0530 | .5 | 21 | 898796 |  | LROP | VPFM | BIT | 4490 | OBSERVED SLOW ROP WHILE DRILLING, TROUBLESHOOT SDM MUD MOTOR.
2206 | 06/25/2022 | ADC-68L | ABHD-176 | TK3 | 25 Jun 0030 - 0500 | 4 | 4 | 898815 |  | LROP | VPFM | BIT | 4547 | SLOW ROP WHILE DRILLING, PUMPED 2 DISPERSANT PILL WITHOUT SUCCESS.
2208 | 06/25/2022 | ADM-656 | SFNY-397 | AP2 | 25 Jun 0830 - 0500 | 20.5 | 20.5 | 898767 |  | WO | WOPF | NA | 0 | HOLD FLOW BACK ACTIVITIES DUE TO RECIEVING HI-WATER CUT AT GOSP.
2210 | 06/25/2022 | ADM-657 | ZULF-73 | ARM | 20 Jun 1015 - 0730 | 2.5 | 19.5 | 898553 |  | WON | WTHR | NA | 0 | WIND STILL WEATHER CONDITION. STOP OPERATION AND WAIT FOR WIND SPEED TO INCREASE ABOVE 5 KTS.
2212 | 06/25/2022 | ARO-2001 | BRRI-94 | BAW | 25 Jun 1600 - 0330 | 11.5 | 11.5 | 898768 |  | FISH | HERR | WLT | 68 | WHILE POOH W/MPC CUTTER AT SUFRACE. FOUND TOOLS LOST IN HOLE
2213 | 06/25/2022 | CG-1 | ZULF-1201 | CRT | 25 Jun 1730 - 0500 | 11.5 | 11.5 | 898816 |  | TF | FOT | SCRP | 6635 | CORETRAX CASING SCRAPER FAILED. SCRAPER BLADES MAKING SEVERAL DRAG INSIDE 7" CASING- COULD'T PASS.
2215 | 06/25/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0900 | 4 | 369.5 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
2216 | 06/25/2022 | CG-1 | ZULF-1201 | CRT | 25 Jun 1730 - 0500 | 11.5 | 11.5 | 898816 |  | TF | FOT | SCRP | 6635 | CORETRAX CASING SCRAPER FAILED. SCRAPER BLADES MAKING SEVERAL DRAG INSIDE 7" CASING- COULD'T PASS.
2218 | 06/25/2022 | DPS-5 | HRDH-2319 | FMC | 25 Jun 1700 - 1800 | 1 | 1 | 898799 |  | TF | FOT | CTRQ | 9497 | FAILURE ON FRANKS POWER TONG SENSOR & JAM UNIT SCREEN.
2219 | 06/25/2022 | MP-1 | MRJN-79 | HCO | 23 Jun 2345 - 0500 | 23 | 52.25 | 898733 |  | TF | FOT | HVLV | 223 | AFTER RIH ON SLICKLINE HAL WRSSSV, ATTEMPTED TO FUCTION TEST. NO SUCCESS. CONTROL LINE PRESSURE IMMEDIATELY BUILDING WHEN TRYING TO OPEN THE WRSSSV. TROUBLE SHOOT WITH NO SUCCESS. RETRIEVED WITH SLICKLINE AND CONTINUED TO TROUBLE SHOOT.
2221 | 06/25/2022 | MP-1 | MRJN-79 | RIG | 25 Jun 0100 - 0200 | 1 | 1 | 898707 |  | RR | FOT | DWKS | 2150 | DRAWWORKS KENETIC ENERGY MANAGEMENT SYSTEM (KEMS) ENGAGING, STOPPING THE TRAVELLING BLOCKS. TROUBLE SHOOT. RESOLVED.
2222 | 06/25/2022 | MP-1 | MRJN-79 | HCO | 23 Jun 2345 - 0500 | 23 | 52.25 | 898733 |  | TF | FOT | HVLV | 223 | AFTER RIH ON SLICKLINE HAL WRSSSV, ATTEMPTED TO FUCTION TEST. NO SUCCESS. CONTROL LINE PRESSURE IMMEDIATELY BUILDING WHEN TRYING TO OPEN THE WRSSSV. TROUBLE SHOOT WITH NO SUCCESS. RETRIEVED WITH SLICKLINE AND CONTINUED TO TROUBLE SHOOT.
2224 | 06/25/2022 | NA-393S | UTMN-2290 | SDM | 25 Jun 2115 - 0345 | 6.5 | 6.5 | 898814 |  | BHA | FOT | RSS | 11244 | ARCCHER TOOL JAMMED
2226 | 06/25/2022 | NBR-115S | HWYH-1220 | RIG | 24 Jun 0700 - 1545 | 2 | 7.5 | 898756 |  | RR | FOT | TDS | 21085 | WHILE SETTING THE RSS TO NEUTRAL THE TOP DRIVE FAILED AND STOPPED ROTATING.
2228 | 06/25/2022 | NBR-20S | HMYM-433514 | RIG | 25 Jun 0815 - 0915 | 1 | 1 | 898798 |  | RR | FOT | CSYS | 921 | LEAKS ON HIGH PRESSURE LINES
2230 | 06/25/2022 | NBR-263S | QTIF-736 | ARM | 22 Jun 0630 - 0500 | 24 | 84 | 898674 |  | LCIR | UVLC | NA | 8541 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG.
2232 | 06/25/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 257 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
2234 | 06/25/2022 | PA-622S | UTMN-3600 | RIG | 25 Jun 1230 - 0130 | 13 | 13 | 898800 |  | RR | FOT | TDS | 94 | TROUBLESHOOT TOP DRIVE (ELECTRICAL/COMMUNICATION ISSUES)
2236 | 06/25/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 623.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
2238 | 06/25/2022 | RBP-50A | KARN-51 | ARM | 09 Jun 1300 - 0700 | 2 | 5.25 | 897736 |  | WON | WTHR | NA | 11775 | WAIT ON WEATHER, UNABLE TO FLOW BACK DUE TO UNFAVORABLE WIND CONDITION.
2240 | 06/25/2022 | RM-74A | HSBH-68 | RIG | 22 Jun 1900 - 0500 | 24 | 82 | 898635 |  | UPRA | GRF | RWCS | 1573 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
2242 | 06/25/2022 | SCTD-1 | SDGM-1152 | SDM | 24 Jun 1900 - 1230 | 7.5 | 17.5 | 898761 |  | BHA | FOT | MWD | 15594 | MWD FAILURE & COMPLETE LOSS OF COMMUNICATION.
2244 | 06/25/2022 | SCTD-2 | HRDH-2307 | RIG | 25 Jun 1600 - 0030 | 8.5 | 8.5 | 898779 |  | BHA | FOT | MMOT | 14312 | LOST COMMUNICATION WITH DOWNHOLE TOOLS. TROUBLESHOOT WITHOUT SUCCESS.
2246 | 06/25/2022 | SINO-36L | SDGM-458 | NC1 | 23 Jun 1400 - 0500 | 24 | 63 | 898690 |  | TF | FOT | FISHT | 5325 | DOWN TIME ON HALLIBURTON LSTK1 DUE TO STUCK PIPE.
2248 | 06/25/2022 | SL-7 | ZULF-1334 | SPS | 25 Jun 1400 - 0500 | 15 | 15 | 898709 |  | BHA | FOT | RSS | 4250 | SPERRY SUN RSS IS SHOWING LOW TURBINE READING.
2250 | 06/25/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 1700 | 12 | 209.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
2252 | 06/25/2022 | SND-2003 | RMTN-17 | HWP | 25 Jun 2300 - 0500 | 6 | 6 | 898781 |  | TF | FOT | WLT | 12353 | CAST TOOL FAILED TO FUNCTION
2254 | 06/25/2022 | SND-2004 | BRRI-1148 | SWL | 25 Jun 0915 - 1145 | 2.5 | 2.5 | 898766 |  | TF | FOT | WLU | 8500 | SLB WIRELINE UNIT ENGINE SHUT DOWN.
2256 | 06/25/2022 | SND-2009 | GHZL-71 | BAW | 25 Jun 0630 - 0500 | 20.75 | 20.75 | 898780 |  | TF | FOT | WLT | 9300 | FTEX (PRESSURE POINTS) LOGGING TOOL CALIBRATION FAILURE.
2258 | 06/25/2022 | SND-3003 | HRDH-1816 | RIG | 25 Jun 1015 - 0500 | 18.75 | 18.75 | 898770 |  | RR | FOT | TDS | 632 | TDS STOP FUNCTIONING.
2260 | 06/25/2022 | SNF036 | MRJN-901 | RIG | 25 Jun 1300 - 1800 | 5 | 5 | 898710 |  | MUD | IPDF | NA | 11845 | DRILL STRING PLUGGED DUE TO MUD ACTIVE PIT ACCIDENTALLY CONTAMINATED WITH LCM. UNLATCH WL CABLE, CLEANED ACTIVE PIT AND CIRCULATING SYSTEM. CONTINUED CIRCULATION TILL HAVE NORMAL PARAMETERS. LATCH WL CABLE AND RESUME OPERATIONS.
2262 | 06/25/2022 | SNT-025 | SFNY-652 | WWD | 24 Jun 1915 - 2115 | 16.25 | 26 | 898760 |  | TF | FOT | WPSTK | 82 | SHEAR BOLT ON WHIPSTOCK ASSY FAILED WHILE RIH ACROSS WELLHEAD.
2264 | 06/25/2022 | SP-276 | JNAB-810 | ARM | 24 Jun 1200 - 0600 | 1 | 18 | 898769 |  | DSF | FOT | STRG | 5756 | TRIED TO DISPLACE SODIUM HEXAMETAPHOSPHATE TO BRINE, PUMP PRESSURE INCREASED, POOH TO CHECK STRING, FOUND JETTING TOOL PLUGGED WITH SOLIDS. L/D PLUGGED JETTING TOOL AND CLEANED SAME AND RIH BACK TO BTM.
2265 | 06/25/2022 | SSA-29 | QTIF-348 | RIG | 25 Jun 0500 - 1400 | 9 | 9 | 898813 |  | RR | FOT | TDS | 0 | LEAK FROM HYDRAULIC MANIFOLD ON TOP DRIVE
2267 | 06/25/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 15 | 346 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
2268 | 06/25/2022 | SSA-29 | QTIF-348 | RIG | 25 Jun 0500 - 1400 | 9 | 9 | 898813 |  | RR | FOT | TDS | 0 | LEAK FROM HYDRAULIC MANIFOLD ON TOP DRIVE
2270 | 06/25/2022 | SSA-5969 | UTMN-3021 | ARM | 24 Jun 2030 - 0500 | 10.5 | 19 | 898762 |  | LROP | LTHI | BIT | 14375 | OBSERVED VERY LOW ROP.
2272 | 06/26/2022 | ADC-34 | UTMN-2316 | SPS | 26 Jun 1730 - 0500 | 11.5 | 11.5 | 898823 |  | BHA | FOT | RSS | 16725 | LOST RSS SIGNAL
2274 | 06/26/2022 | ADC-43L | UTMN-3118 | SDM | 22 Jun 1200 - 0500 | 24 | 61.25 | 898665 |  | BHA | FOT | MWD | 10818 | OBSERVED MWD SIGNAL PROBLEMS, TROUBLESHOOTED SAME AND PERFORMED ANTI-JAM PROCEDURE WITH NO SUCCESS.
2276 | 06/26/2022 | ADC-54L | HRDH-1499 | TK2 | 22 Jun 0330 - 1900 | 14 | 87.5 | 898697 |  | STUK | STBH | BHA | 3440 | HAD COMPLETE LOSSES @ 3501' IN SHUAIBA FM, P/U TDS WHILE CIRC. & RECIPROCATIONG STRING & PUMP MUD CAP 75 PCF FROM BACK SIDE. STRING STALL 60' OFF-BTM & GOT STUCK @ 3440' (NO MOUVMENT UP/DOWN). WORK ON STUCK.
2278 | 06/26/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 196 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
2280 | 06/26/2022 | ADC-68L | ABHD-176 | TK3 | 25 Jun 0030 - 2200 | 15.25 | 19.25 | 898815 |  | LROP | VPFM | BIT | 4547 | SLOW ROP WHILE DRILLING, PUMPED 2 DISPERSANT PILL WITHOUT SUCCESS.
2282 | 06/26/2022 | ADES-144 | UTMN-3152 | BCR | 26 Jun 1830 - 2030 | 2 | 2 | 898827 |  | TF | FOT | CRT | 7350 | EXCESSIVE TIME WHILE RUNNING 9-5/8" CASING DUE TO CRT UNABLE TO RELEASE THE CASING JNT.
2284 | 06/26/2022 | ADM-511 | MRJN-799 | ARM | 26 Jun 0045 - 0430 | 3.75 | 3.75 | 898861 |  | DRG | PCPF | NA | 7881 | HAD 15 KLBS S/O WHILE RIH @7763' & 7825',M/U TDS AND WASH DOWN TILL PASS FREE, CONTINUE RIH HAD OBSTRUCTION @7881FT,CHECKED STRING WT FREE UP/DOWN AND HAD FULL CIRCULATION.
2286 | 06/26/2022 | ADM-656 | SFNY-397 | AP2 | 25 Jun 0830 - 0500 | 24 | 44.5 | 898767 |  | WO | WOPF | NA | 0 | HOLD FLOW BACK ACTIVITIES DUE TO RECIEVING HI-WATER CUT AT GOSP.
2288 | 06/26/2022 | ADM-657 | ZULF-73 | ARM | 20 Jun 1015 - 1600 | 4.5 | 24 | 898553 |  | WON | WTHR | NA | 0 | WIND STILL WEATHER CONDITION. STOP OPERATION AND WAIT FOR WIND SPEED TO INCREASE ABOVE 5 KTS.
2290 | 06/26/2022 | AOD-11 | SFNY-1810 | HMS | 26 Jun 2015 - 2030 | .25 | .25 | 898830 |  | TF | FOT | MLOG | 822 | HALLIBURTON DEPTH SENSOR ON DRAWWORK MALFUNCTION.
2292 | 06/26/2022 | CG-1 | ZULF-1201 | CRW | 25 Jun 1730 - 0400 | 23 | 34.5 | 898816 |  | TF | FOT | SCRP | 6635 | CORETRAX CASING SCRAPER FAILED. SCRAPER BLADES MAKING SEVERAL DRAG INSIDE 7" CASING- COULD'T PASS.
2294 | 06/26/2022 | DPS-46 | SDGM-727 | CRT | 26 Jun 1515 - 0500 | 13.75 | 13.75 | 898822 |  | BHA | FOT | WBCL | 13360 | STRING GOT PLUGGED
2296 | 06/26/2022 | HI-4 | SFNY-918 | SCP | 26 Jun 1500 - 0500 | 14 | 14 | 898833 |  | TF | FOT | STING | 4888 | UNABLE TO UNSTING FROM SLB SEAL ASSY.
2297 | 06/26/2022 | MP-1 | MRJN-79 | RIG | 26 Jun 1600 - 1800 | 2 | 2 | 898852 |  | HSEI | UNKN | NA | 1645 | DRILLER LOWERED TDS ONTO 4-1/2" TBG. BENT TBG. SAFETY STAND DOWN HELD. INSPECTED LOWER 5 JTS, NO DAMAGE. REPLACED DAMAGED JOINT.
2299 | 06/26/2022 | MP-1 | MRJN-79 | HCO | 23 Jun 2345 - 0500 | 22 | 74.25 | 898733 |  | TF | FOT | SSSV | 223 | AFTER RIH ON SLICKLINE HAL WRSSSV, ATTEMPTED TO FUCTION TEST. NO SUCCESS. CONTROL LINE PRESSURE IMMEDIATELY BUILDING WHEN TRYING TO OPEN THE WRSSSV. TROUBLE SHOOT WITH NO SUCCESS. RETRIEVED WITH SLICKLINE AND CONTINUED TO TROUBLE SHOOT.
2300 | 06/26/2022 | MP-1 | MRJN-79 | RIG | 26 Jun 1600 - 1800 | 2 | 2 | 898852 |  | HSEI | UNKN | NA | 1645 | DRILLER LOWERED TDS ONTO 4-1/2" TBG. BENT TBG. SAFETY STAND DOWN HELD. INSPECTED LOWER 5 JTS, NO DAMAGE. REPLACED DAMAGED JOINT.
2302 | 06/26/2022 | NA-393S | UTMN-2290 | SDM | 25 Jun 2115 - 1900 | 14 | 20.5 | 898814 |  | BHA | FOT | RSS | 11244 | ARCCHER TOOL JAMMED
2304 | 06/26/2022 | NBR-115S | HWYH-1220 | RIG | 26 Jun 0500 - 0600 | 1 | 1 | 898819 |  | RR | FOT | TDS | 21085 | GRIPPER DIES ON PIPE HANDLER NOT OPENING AND CLOSING CORRECTLY.
2305 | 06/26/2022 | NBR-783S | NJYN-93 | MSD | 26 Jun 1030 - 1330 | 3 | 3 | 898825 |  | TF | FOT | FUT | 3851 | ALMASAOOD SPIDER ELEVATOR GOT STUCK WITH FILL-UP TOOL. > MADE SEVERAL ATTEMPT AND EVENTUALLY FREED SAME. > LD ALMASAOOD FILL-UP TOOL.
2307 | 06/26/2022 | NBR-783S | NJYN-93 | RIG | 26 Jun 0830 - 1015 | 1.75 | 1.75 | 898824 |  | RR | FOT | CATW | 3851 | SANAD CAT WALK PRAGMA FAILURE.
2308 | 06/26/2022 | NBR-783S | NJYN-93 | MSD | 26 Jun 1030 - 1330 | 3 | 3 | 898825 |  | TF | FOT | FUT | 3851 | ALMASAOOD SPIDER ELEVATOR GOT STUCK WITH FILL-UP TOOL. > MADE SEVERAL ATTEMPT AND EVENTUALLY FREED SAME. > LD ALMASAOOD FILL-UP TOOL.
2310 | 06/26/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 281 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
2311 | 06/26/2022 | PA-70S | MDRK-64 | NWL | 26 Jun 0800 - 0030 | 16.5 | 16.5 | 898859 |  | TF | FOT | WLT | 15451 | NESR WIRELINE FAILED TO SET EZSV BRIDGE PLUG. UNABLE TO SET THE PLUG AND RELEASE SETTING TOOL. BRIGHE PLUG WAS FREE DOWN ONLY AND COULD NOT POOH WITH THE PLUG.
2313 | 06/26/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 7.5 | 631 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
2314 | 06/26/2022 | PA-70S | MDRK-64 | NWL | 26 Jun 0800 - 0030 | 16.5 | 16.5 | 898859 |  | TF | FOT | WLT | 15451 | NESR WIRELINE FAILED TO SET EZSV BRIDGE PLUG. UNABLE TO SET THE PLUG AND RELEASE SETTING TOOL. BRIGHE PLUG WAS FREE DOWN ONLY AND COULD NOT POOH WITH THE PLUG.
2316 | 06/26/2022 | PN-9 | MRJN-677 | RIG | 26 Jun 1045 - 0130 | 2.5 | 2.5 | 898860 |  | RR | FOT | DWKS | 2850 | POWER FAILURE IN DRILLING EQ, LOST COMMUNICATION BETWEEN AMPHION SYSTEM & DRILLING PACKAGE.
2318 | 06/26/2022 | RM-74A | HSBH-68 | RIG | 22 Jun 1900 - 0500 | 24 | 106 | 898635 |  | UPRA | GRF | RWCS | 1573 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
2320 | 06/26/2022 | SCTD-2 | HRDH-2307 | RIG | 25 Jun 1600 - 0000 | 8 | 16.5 | 898779 |  | BHA | FOT | MMOT | 14312 | LOST COMMUNICATION WITH DOWNHOLE TOOLS. TROUBLESHOOT WITHOUT SUCCESS.
2322 | 06/26/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 209.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
2324 | 06/26/2022 | SINO-42L | HWYH-608 | HCB | 26 Jun 2130 - 0500 | 7.5 | 7.5 | 898854 |  | TF | FOT | BP | 200 | UNABLE TO SHEAR DPU MOTOR FROM HALLIBURTON MONO-LOCK BP.
2326 | 06/26/2022 | SL-7 | ZULF-1334 | SPS | 25 Jun 1400 - 0530 | .5 | 15.5 | 898709 |  | BHA | FOT | RSS | 4250 | SPERRY SUN RSS IS SHOWING LOW TURBINE READING.
2328 | 06/26/2022 | SND-2003 | RMTN-17 | HWP | 25 Jun 2300 - 1200 | 7 | 13 | 898781 |  | TF | FOT | WLT | 12353 | CAST TOOL FAILED TO FUNCTION
2330 | 06/26/2022 | SND-2009 | GHZL-71 | BAW | 25 Jun 0630 - 0630 | 1.5 | 22.25 | 898780 |  | TF | FOT | WLT | 9300 | FTEX (PRESSURE POINTS) LOGGING TOOL CALIBRATION FAILURE.
2332 | 06/26/2022 | SND-3003 | HRDH-1816 | RIG | 25 Jun 1015 - 0745 | 2.75 | 21.5 | 898770 |  | RR | FOT | TDS | 632 | TDS STOP FUNCTIONING.
2334 | 06/26/2022 | SP-259 | THRY-371612 | RIG | 26 Jun 1930 - 2200 | 2.5 | 2.5 | 898832 |  | TRQ | INTQ | BHA | 380 | OVER TORQED BHA
2336 | 06/26/2022 | SSA-5969 | UTMN-3021 | ARM | 24 Jun 2030 - 1000 | 5 | 24 | 898762 |  | LROP | LTHI | BIT | 14375 | OBSERVED VERY LOW ROP.
2338 | 06/26/2022 | T217 | UTMN-475 | OCT | 26 Jun 1215 - 1545 | 3.5 | 3.5 | 898831 |  | CMT | HERR | NA | 2845 | HAD MALFUNCTION ON CMT UNIT AFTER PUMPING 30 BBL'S CMT SLURRY.
2340 | 06/26/2022 | T218 | UTMN-1281 | WDS | 26 Jun 0500 - 0500 | 23.25 | 23.25 | 898853 |  | BHA | FOT | RSS | 7401 | WDS RSS MALFUNCTION & LOW ROP.
2342 | 06/26/2022 | T901 | JLMN-47 | NRC | 26 Jun 2015 - 0000 | 3.75 | 3.75 | 898829 |  | TF | FOT | CRT | 82 | NAPESCO THREAD PROTECTOR BECAME STUCK INSIDE CRT.
2344 | 06/26/2022 | WCL-83 | MRJN-834 | WI1 | 26 Jun 2100 - 0500 | 8 | 8 | 898858 |  | JF | SROP | MILL | 6476 | UNABLE TO MAKE PROGRESS MILLING WINDOW IN 9 5/8" CSG WITH WIS 8.5" FAST TRACK TRI-MILL ASS'Y.
2346 | 06/27/2022 | ADC-17 | ZULF-1214 | RIG | 27 Jun 0245 - 0500 | 2.25 | 2.25 | 898931 |  | RR | FOT | CSYS | 8966 | AFTER MAKING A CONNECTION & STARTING CIRCULATION, FOUND A LEAK BETWEEN HIGH PRESSURE BLOCK & DISCHARGE LINE FLANGE OF MP #1.
2348 | 06/27/2022 | ADC-31 | SDGM-1181 | SPS | 27 Jun 0000 - 0100 | 1 | 1 | 898920 |  | BHA | FOT | MWD | 14357 | TROUBLESHOOTING ON SPERY-SUN PWD HCIM. (PWD INTERNAL SENSOR STOP WORKING)
2350 | 06/27/2022 | ADC-34 | UTMN-2316 | SPS | 26 Jun 1730 - 0500 | 24 | 35.5 | 898823 |  | BHA | FOT | RSS | 16725 | LOST RSS SIGNAL
2352 | 06/27/2022 | ADC-36 | SDGM-1236 | BCR | 27 Jun 1930 - 2230 | 3 | 3 | 898923 |  | TF | FOT | CTRQ | 4456 | UNABLE TO RELEASE CSG FROM FMS "FLUSH MOUNTED SLIPS", TROUBLESHOOT AND REPLACE DAMAGED HOSE.
2354 | 06/27/2022 | ADC-43L | UTMN-3118 | SDM | 22 Jun 1200 - 0145 | 18.25 | 79.5 | 898665 |  | BHA | FOT | MWD | 10818 | OBSERVED MWD SIGNAL PROBLEMS, TROUBLESHOOTED SAME AND PERFORMED ANTI-JAM PROCEDURE WITH NO SUCCESS.
2356 | 06/27/2022 | ADC-53L | HRDH-530 | SLC | 27 Jun 1815 - 0015 | 6 | 6 | 898934 |  | TF | FOT | CDS | 1641 | SLB BDT CRT FAILED TO OPERATE AND WAIT ON ARRIVAL FOR SECOND ONE.
2358 | 06/27/2022 | ADC-54L | HRDH-1499 | ARM | 27 Jun 1900 - 2100 | 2 | 2 | 898933 |  | WON | WTHR | NA | 4040 | WAIT ON WEATHER, SUSPEND CRANE LIFTING OP DUE TO HIGH WIND SPEED +/- 50 KPH.
2360 | 06/27/2022 | ADC-55L | UTMN-3171 | TK3 | 21 Jun 1415 - 2115 | 7.25 | 40.25 | 898634 |  | WCNT | WC11 | NA | 6243 | OBSERVED INCREASE IN FLOW OUT
2366 | 06/27/2022 | ADC-58L | ABHD-169 | OTH | 27 Jun 1800 - 2100 | 3 | 3 | 898929 |  | WON | WTHR | NA | 289 | WAIT ON WEATHER DUE TO HIGH WIND SPEED FOR CRANE LIFTING OPERATION.
2368 | 06/27/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 220 | 898471 |  | JF | HERR | TDS | 9094 | ERROR RESULT : DRILL STRING STUCK.
2370 | 06/27/2022 | ADES-144 | UTMN-3152 | BCR | 26 Jun 1830 - 1000 | 2 | 4 | 898827 |  | TF | FOT | CRT | 7350 | EXCESSIVE TIME WHILE RUNNING 9-5/8" CASING, DUE TO CRT UNABLE TO RELEASE FROM CASING JNT.
2371 | 06/27/2022 | ADES-173 | UTMN-1964 | RIG | 27 Jun 1530 - 0500 | 13.5 | 13.5 | 898922 |  | DSF | FOT | DP | 7460 | PLUGGED STRING DUE TO ACCUMULATION OF CUTTINGS & COATINGS FOUND ABOVE FLOAT VALVE.
2373 | 06/27/2022 | ADES-173 | UTMN-1964 | RIG | 27 Jun 0830 - 1000 | 1.5 | 1.5 | 898913 |  | RR | FOT | DWKS | 15057 | TROUBLE SHOOT DRAW WORKS BRAKE.
2374 | 06/27/2022 | ADES-173 | UTMN-1964 | RIG | 27 Jun 1530 - 0500 | 13.5 | 13.5 | 898922 |  | DSF | FOT | DP | 7460 | PLUGGED STRING DUE TO ACCUMULATION OF CUTTINGS & COATINGS FOUND ABOVE FLOAT VALVE.
2376 | 06/27/2022 | ADM-337 | MRJN-900 | SWT | 27 Jun 1215 - 1400 | 1.75 | 1.75 | 898873 |  | TF | FOT | DSTT | 466 | OBSERVE LEAKS ON SCHLUMBERGER PUMPING SUB WHILE TESTING PTV ( PIPE TEST VALVE ) BLEED OFF PRESSURE. RE-TORQUE CONNECTIONS, RE-TEST LINES.
2377 | 06/27/2022 | ADM-339 | MRJN-3011 | FMC | 27 Jun 1630 - 1700 | .5 | .5 | 898912 |  | TF | FOT | CRT | 1803 | FRANKS CASING POWER PACK FAILED.
2379 | 06/27/2022 | ADM-339 | MRJN-3011 | FMC | 27 Jun 1045 - 1130 | .75 | .75 | 898892 |  | TF | FOT | CTRQ | 483 | LEAK ON HOSE FOR FRANKS POWER TONG.
2380 | 06/27/2022 | ADM-339 | MRJN-3011 | FMC | 27 Jun 1630 - 1700 | .5 | .5 | 898912 |  | TF | FOT | CRT | 1803 | FRANKS CASING POWER PACK FAILED.
2382 | 06/27/2022 | ADM-511 | MRJN-799 | ARM | 26 Jun 0045 - 0430 | 23.5 | 27.75 | 898861 |  | DRG | PCPF | NA | 7881 | HAD 15 KLBS S/O WHILE RIH @7763' & 7825',M/U TDS AND WASH DOWN TILL PASS FREE, CONTINUE RIH HAD OBSTRUCTION @7881FT,CHECKED STRING WT FREE UP/DOWN AND HAD FULL CIRCULATION.
2384 | 06/27/2022 | ADM-656 | SFNY-397 | AP2 | 25 Jun 0830 - 1730 | 12.5 | 57 | 898767 |  | WO | WOPF | NA | 0 | HOLD FLOW BACK ACTIVITIES DUE TO RECIEVING HI-WATER CUT AT GOSP.
2386 | 06/27/2022 | AOD-11 | SFNY-1810 | RIG | 27 Jun 1400 - 1500 | 1 | 1 | 898918 |  | RR | FPMP | MPMP | 4993 | HAD PRESSURE DROP, FOUND LEAK IN STAND PIPE MANIFOLD & PISTION IN MP #3
2388 | 06/27/2022 | DPS-43 | SDGM-1196 | SPS | 27 Jun 2000 - 0130 | 5.5 | 5.5 | 898921 |  | BHA | FOT | RSS | 18193 | RESISTIVITY LOG DATA QUALITY ISSUE.
2390 | 06/27/2022 | DPS-46 | SDGM-727 | CRW | 26 Jun 1515 - 0500 | 22.75 | 36.5 | 898822 |  | BHA | FOT | WBCL | 13360 | STRING GOT PLUGGED
2392 | 06/27/2022 | EXL-IVA | SFNY-1650 | BCM | 27 Jun 1830 - 2230 | 4 | 4 | 898924 |  | WO | SRVC | NA | 1120 | BAKER CEMENTING LOST TIME: ATTEMPT TO PERFORM TOP CEMENT JOB PLUG #3, SEA WATER COOLING LINE LEAKING AND CEMENT MIXING LINE BLOCKED. ** REPAIR SEA WATER COOLING LINES FOR BAKER CEMENT UNIT, CLEAN BLOCKAGE IN BAKER CEMENT MIXING LINE.
2394 | 06/27/2022 | HI-4 | SFNY-918 | SCP | 26 Jun 1500 - 0500 | 24 | 38 | 898833 |  | TF | FOT | STING | 4888 | UNABLE TO UNSTING SCHLUMBERGER WET CONNECTOR SEAL ASSEMBLY FROM WET CONNECTOR RECEPTACLE WITH STANDARD PROCEDURES (10 -15 KBLS OVERPULL). STRING ROTATION AND 50 KLBS OVERPULL WAS REQUIRED TO BE ABLE TO RELEASE STINGER WET CONNECTOR SEAL ASSEMBLY.
2396 | 06/27/2022 | MP-1 | MRJN-79 | HCO | 23 Jun 2345 - 0500 | 24 | 98.25 | 898733 |  | TF | FOT | SSSV | 223 | AFTER RIH ON SLICKLINE HAL WRSSSV, ATTEMPTED TO FUCTION TEST. NO SUCCESS. CONTROL LINE PRESSURE IMMEDIATELY BUILDING WHEN TRYING TO OPEN THE WRSSSV. TROUBLE SHOOT WITH NO SUCCESS. RETRIEVED WITH SLICKLINE AND CONTINUED TO TROUBLE SHOOT.
2398 | 06/27/2022 | NBR-263S | QTIF-736 | ARM | 22 Jun 0630 - 2200 | 17 | 125 | 898674 |  | LCIR | UVLC | NA | 8541 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG.
2400 | 06/27/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 305 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
2402 | 06/27/2022 | PA-604S | HRDH-1955 | RIG | 27 Jun 1915 - 2215 | 3 | 3 | 898927 |  | RR | FOT | TDS | 9214 | TRY TO CONT. DRILLING. UNABLE TO ROTATE TDS, FOUND OIL LOOP PUMP BROKEN.
2404 | 06/27/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 655 | 897183 |  | TF | FOT | LLAP | 15492 | CONFIRMED THAT THERE IS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THAT CONNECTION WAS MADE-UP AT WFD WORKSHOP.
2406 | 06/27/2022 | PN-9 | MRJN-677 | RIG | 26 Jun 1045 - 1030 | 1.5 | 4 | 898860 |  | RR | FOT | DWKS | 2850 | POWER FAILURE IN DRILLING EQ, LOST COMMUNICATION BETWEEN AMPHION SYSTEM & DRILLING PACKAGE.
2408 | 06/27/2022 | RBP-50A | KARN-51 | HTS | 27 Jun 0145 - 0500 | 3.25 | 3.25 | 898928 |  | TF | FOT | FLR | 11775 | UNABLE TO IGNITE PILOT FLAMES FOR VENTING OVER FLARE BOOM, TROUBLE SHOOT IGNITION SYSTEM.
2410 | 06/27/2022 | RM-74A | HSBH-68 | RIG | 22 Jun 1900 - 0500 | 24 | 130 | 898635 |  | UPRA | GRF | RWCS | 1573 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
2412 | 06/27/2022 | SINO-25 | MNIF-329 | GD1 | 27 Jun 1330 - 1500 | 1.5 | 1.5 | 898917 |  | TF | FOT | SLICK | 5680 | GDMC SL RIH W/ 3.42" INTERWELL ME PLUG AND SET @ 5680 ' (SL DEPTH), POH, PT ME PLUG & 9-5/8" CASING ABOVE THE PACKER T/ 1000 PSI, READ PRESSURE FROM TBG SIDE ONLY, TCA SIDE IS ZERO, RE-CORRELATE PLUG DEPTH, FOUND SL UNIT DEPTH COUNTER PROBLEM.
2414 | 06/27/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 233.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
2416 | 06/27/2022 | SINO-42L | HWYH-608 | HCB | 26 Jun 2130 - 0430 | 23.5 | 31 | 898854 |  | TF | FOT | BP | 200 | UNABLE TO SHEAR DPU MOTOR FROM HALLIBURTON MONO-LOCK BP.
2418 | 06/27/2022 | SSA-202 | QTIF-191 | ARM | 26 Jun 2130 - 1100 | 6 | 13.5 | 898862 |  | LCIR | CFFM | LCM | 417 | ENCOUNTERED TOTAL LOSSES @ 417'
2420 | 06/27/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 394 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
2422 | 06/27/2022 | SSA-5962 | HRDH-2230 | RIG | 27 Jun 1600 - 2315 | 7.25 | 7.25 | 898914 |  | RR | FOT | DWKS | 15215 | REPAIR ON DRAW WORKS (LUBRICANT OIL PUMP FAILURE).
2424 | 06/27/2022 | T218 | UTMN-1281 | WDS | 26 Jun 0500 - 1115 | 6.25 | 29.5 | 898853 |  | BHA | FOT | RSS | 7401 | WDS RSS MALFUNCTION & LOW ROP.
2426 | 06/27/2022 | WCL-83 | MRJN-834 | WI3 | 26 Jun 2100 - 0745 | 2.75 | 10.75 | 898858 |  | TF | FOT | WPSTK | 6476 | UNABLE TO MAKE PROGRESS MILLING WINDOW IN 9 5/8" CSG WITH WIS 8.5" FAST TRACK TRI-MILL ASS'Y.
2428 | 06/28/2022 | 088TE | QTIF-330 | SWL | 28 Jun 2330 - 0500 | 5.5 | 5.5 | 898939 |  | TF | FOT | WLT | 7043 | WHILE PERFORMING 4TH V.I.T, SLB W/L LOGGING LOST COMMUNICATION WITH TOOLS. TRIED TO REGAIN COMMUNICATION WITH NO SUCCESS
2430 | 06/28/2022 | ADC-17 | ZULF-1214 | RIG | 27 Jun 0245 - 0500 | 23.5 | 25.75 | 898931 |  | RR | FOT | CSYS | 8966 | AFTER MAKING A CONNECTION & STARTING CIRCULATION, FOUND A LEAK BETWEEN HIGH PRESSURE BLOCK & DISCHARGE LINE FLANGE OF MP #1.
2432 | 06/28/2022 | ADC-34 | UTMN-2316 | SPS | 26 Jun 1730 - 2000 | 7 | 42.5 | 898823 |  | BHA | FOT | RSS | 16725 | LOST RSS SIGNAL
2434 | 06/28/2022 | ADC-50 | SFNY-1176 | ARM | 26 Jun 1845 - 0500 | 24 | 57.5 | 898935 |  | LCIR | UVLC | NA | 2864 | HAD SEVERE LOSSES WHILE DRLG 12-1/4" HOLE @ 2,864', OPEN PBL SUB AND SPOT 2EA LCM PILLS WITH NO SUCCESS.
2436 | 06/28/2022 | ADC-53L | HRDH-530 | TK3 | 28 Jun 1330 - 1730 | 4 | 4 | 898936 |  | STUK | SCSG | CSG | 3230 | OBSERVED CSG STUCK AFTER CONNECTION WHILE CWD, NO MOVEMENT & NO ROTATION ONLY CIRCULATION W/ LOW GPM.
2442 | 06/28/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 244 | 898471 |  | JF | HERR | TDS | 9094 | ERROR RESULT : DRILL STRING STUCK.
2444 | 06/28/2022 | ADES-14 | HWYH-530 | MSL | 28 Jun 1800 - 0200 | 8 | 8 | 898974 |  | TF | FOT | SLICK | 5005 | MANSOORI SLICKLINE UNABLE TO SET PX/PXN PLUG.
2446 | 06/28/2022 | ADES-144 | UTMN-3152 | RIG | 28 Jun 1400 - 2030 | 6.5 | 6.5 | 898972 |  | RR | FOT | RWCS | 0 | WHILE TESTING BOPE, ATTEMPT TO TEST TDS IBOP WITH NO SUCCESS. IBOP WERE NOT FULLY CLOSING AND HOLD PRESSURE.
2447 | 06/28/2022 | ADES-173 | UTMN-1964 | RIG | 27 Jun 1530 - 0900 | 1.75 | 15.25 | 898922 |  | DSF | FOT | DP | 15057 | PLUGGED STRING DUE TO SOME LCM & LOTS OF DP COATINGS FOUND ABOVE FLOAT VALVE.
2449 | 06/28/2022 | ADES-173 | UTMN-1964 | RIG | 28 Jun 0600 - 0745 | 1.75 | 1.75 | 898893 |  | RR | FOT | TDS | 15057 | TOPDRIVE TRACK NOT ALIGNED PROPERLY
2450 | 06/28/2022 | ADES-173 | UTMN-1964 | RIG | 27 Jun 0830 - 0400 | 2.75 | 4.25 | 898913 |  | RR | FOT | DWKS | 15057 | TROUBLE SHOOT DRAW WORKS BRAKE.
2451 | 06/28/2022 | ADES-173 | UTMN-1964 | RIG | 27 Jun 1530 - 0900 | 1.75 | 15.25 | 898922 |  | DSF | FOT | DP | 15057 | PLUGGED STRING DUE TO SOME LCM & LOTS OF DP COATINGS FOUND ABOVE FLOAT VALVE.
2453 | 06/28/2022 | ADM-511 | MRJN-799 | ARM | 26 Jun 0045 - 0215 | 8.75 | 36.5 | 898861 |  | DRG | PCPF | NA | 7881 | HAD 15 KLBS S/O WHILE RIH @7763' & 7825',M/U TDS AND WASH DOWN TILL PASS FREE, CONTINUE RIH HAD OBSTRUCTION @7881FT,CHECKED STRING WT FREE UP/DOWN AND HAD FULL CIRCULATION, ATTEMPTED SEVERAL TIMES TO PASS WITH DIFFERENT PARAMETERS , NO SUCCESS.
2455 | 06/28/2022 | DPS-44 | UTMN-3174 | SPS | 28 Jun 0930 - 0500 | 19 | 19 | 898937 |  | BHA | FOT | MWD | 11151 | LOST COMMUNCATION WITH SPERRY SUN MWD TOOLS. TROUBLESHOOT SAME WITH NO SUCCESS.
2457 | 06/28/2022 | DPS-46 | SDGM-727 | CRW | 26 Jun 1515 - 0500 | 24 | 60.5 | 898822 |  | BHA | FOT | WBCL | 13360 | STRING GOT STUCK AFTER CIRC THRU CORETRAX CIRC SUB
2459 | 06/28/2022 | DQ-47 | KHRS-497 | BHI | 28 Jun 0800 - 0500 | 21 | 21 | 898952 |  | DD | HERR | MMOT | 5832 | BAKER DIREC DRILLER MISSED THE TARGET ENTRY DUE TO NOT FOLLOWING THE INSTRUCTION FROM GOC.
2461 | 06/28/2022 | HI-4 | SFNY-918 | SCP | 26 Jun 1500 - 0500 | 17 | 41.5 | 898833 |  | TF | FOT | STING | 4899 | UNABLE TO UNSTING SCHLUMBERGER WETCONNECTOR SEAL ASSEMBLY FROM WET CONNECTOR RECEPTACLE WITH STANDARD PROCEDURES (10 -25 KBLS OVERPULL). STRING ROTATION AND 50 KLBS OVERPULL WAS REQUIRED TO BE ABLE TO RELEASE STINGER WET CONNECTOR SEAL ASSEMBLY.
2463 | 06/28/2022 | MP-1 | MRJN-79 | HCO | 23 Jun 2345 - 1300 | 8 | 105.75 | 898733 |  | TF | FOT | SSSV | 223 | AFTER RIH ON SLICKLINE HAL WRSV, ATTEMPTED TO FUCTION TEST. NO SUCCESS. CONTROL LINE PRESSURE IMMEDIATELY BUILDING WHEN TRYING TO OPEN THE WRSV. TROUBLE SHOOT WITH NO SUCCESS. RETRIEVED WITH SLICKLINE AND CONTINUED TO TROUBLE SHOOT.
2465 | 06/28/2022 | NA-207S | SHYB-132 | ARM | 28 Jun 0000 - 0500 | 5 | 5 | 898940 |  | STUK | STBH | MILL | 4749 | STRING STUCK WHILE MILLING OUT 7" LINER
2467 | 06/28/2022 | NBR-20S | HMYM-433514 | RIG | 28 Jun 1900 - 0000 | 5 | 5 | 898958 |  | WO | SRVC | NA | 4827 | RENTAL CRANE NOT WORKING
2468 | 06/28/2022 | NBR-263S | QTIF-736 | RIG | 28 Jun 1230 - 1430 | 2 | 2 | 898946 |  | RR | FOT | DWKS | 0 | OBSERVE DEPTH SENSOR FOR SLB MUD LOGGING & SPS COME OUT FROM DRAWWORKS ENCODER SHAFT, FIX DRAWWORK ENCODER SHAFT
2470 | 06/28/2022 | NBR-263S | QTIF-736 | ARM | 22 Jun 0630 - 0500 | 14 | 139 | 898674 |  | LCIR | UVLC | NA | 8541 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG.
2471 | 06/28/2022 | NBR-263S | QTIF-736 | RIG | 28 Jun 1230 - 1430 | 2 | 2 | 898946 |  | RR | FOT | DWKS | 0 | OBSERVE DEPTH SENSOR FOR SLB MUD LOGGING & SPS COME OUT FROM DRAWWORKS ENCODER SHAFT, FIX DRAWWORK ENCODER SHAFT
2473 | 06/28/2022 | NBR-783S | NJYN-93 | RIG | 28 Jun 1100 - 1700 | 6 | 6 | 898942 |  | BOP | FOT | BOP | 3851 | EXCESSIVE TIME TO NU BOP N/U 26-3/4" 3M "A" BOP STACK AND ALL RELATED LINES AND EQUIP.
2475 | 06/28/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 10.75 | 665.75 | 897183 |  | TF | FOT | LLAP | 15492 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP.
2476 | 06/28/2022 | PN-9 | MRJN-677 | HCM | 28 Jun 0400 - 0500 | 1 | 1 | 898951 |  | TF | FOT | PUMP | 0 | UNABLE TO MAINTAIN CMT SLURRY WEIGHT DURING DUMMY TEST, DUMP & CLEAN SURGE TANK.
2478 | 06/28/2022 | PN-9 | MRJN-677 | RIG | 28 Jun 1330 - 1530 | 2 | 2 | 898949 |  | JF | XTRI | NA | 5535 | EXCESS TIME DUE TO INTERMITTENT CEMENT DELIVERY FROM RIG BULK SYSTEM & BLOCKAGE LINES.
2479 | 06/28/2022 | PN-9 | MRJN-677 | HCM | 28 Jun 0930 - 1030 | 1 | 1 | 898950 |  | TF | FOT | PUMP | 5535 | HYDRAULIC OIL LEAKAGE FROM HALL CMT UNIT ENGINE.
2480 | 06/28/2022 | PN-9 | MRJN-677 | HCM | 28 Jun 0400 - 0500 | 1 | 1 | 898951 |  | TF | FOT | PUMP | 0 | UNABLE TO MAINTAIN CMT SLURRY WEIGHT DURING DUMMY TEST, DUMP & CLEAN SURGE TANK.
2482 | 06/28/2022 | RBP-50A | KARN-51 | HTS | 27 Jun 0145 - 0530 | .5 | 3.75 | 898928 |  | TF | FOT | FLR | 11775 | UNABLE TO IGNITE PILOT FLAMES FOR VENTING OVER FLARE BOOM, TROUBLE SHOOT IGNITION SYSTEM.
2484 | 06/28/2022 | RM-74A | HSBH-68 | RIG | 22 Jun 1900 - 0500 | 24 | 154 | 898635 |  | UPRA | GRF | RWCS | 1573 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
2486 | 06/28/2022 | SCTD-1 | SDGM-1152 | RIG | 28 Jun 1600 - 0500 | 13 | 13 | 898938 |  | BHA | FOT | MMOT | 15037 | TURBINE DOWNHOLE FAILURE.
2488 | 06/28/2022 | SIN30L | KHRS-180 | TK2 | 28 Jun 0245 - 0500 | 2.25 | 2.25 | 898975 |  | STUK | STBH | BHA | 6450 | STUCK PIPE DURING SLIDING
2490 | 06/28/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 257.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
2491 | 06/28/2022 | SND-2001 | UTMN-2329 | BHI | 28 Jun 0030 - 0130 | 1 | 1 | 898959 | 898954 | BHA | FOT | RSS | 18550 | BHI TOOL LOST CUMMUNICATION
2493 | 06/28/2022 | SND-2001 | UTMN-2329 | BHI | 28 Jun 0215 - 0500 | 2.75 | 3.75 | 898954 |  | BHA | FOT | RSS | 18537 | BHI TOOL LOST CUMMUNICATION
2494 | 06/28/2022 | SND-2001 | UTMN-2329 | BHI | 28 Jun 0030 - 0130 | 1 | 1 | 898959 | 898954 | BHA | FOT | RSS | 18550 | BHI TOOL LOST CUMMUNICATION
2496 | 06/28/2022 | SND-3002 | DMMM-601 | WCR | 28 Jun 0400 - 0500 | 1 | 1 | 898956 |  | TF | FOT | CTRQ | 13972 | WFD FMS SLIPS NOT FUNCTIONAL
2498 | 06/28/2022 | SP-110 | BRRI-562 | BHI | 28 Jun 0300 - 0500 | 2 | 2 | 898947 |  | BHA | FOT | GMWD | 12934 | BAKER BCPM TURBINE LOST SIGNAL
2500 | 06/28/2022 | SP-120 | MNIF-188 | SCT | 28 Jun 0330 - 0500 | 1.5 | 1.5 | 899012 |  | TF | FOT | CTBG | 8169 | CT COULDN'T PASS WHILE POOH AT 8,169'.
2502 | 06/28/2022 | SP-260 | HMYM-531814 | BHI | 28 Jun 1730 - 0500 | 11.5 | 11.5 | 898973 |  | BHA | FOT | RSS | 18074 | ROTARY STEERABLE SYSTEM LOST COMMUNICATION
2504 | 06/28/2022 | SSA-101 | QTIF-785 | RIG | 28 Jun 0030 - 0230 | 2 | 2 | 898953 |  | RR | FOT | TDS | 24580 | DURING CIRCULATION OBSERVED LEAK IN MAIN HOSE OF TDS HYDRAULIC SERVICE LOOP,CHANGED BY NEW HOSE.
2506 | 06/28/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0500 | 24 | 418 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
2508 | 06/28/2022 | T914 | UTMN-463 | WWD | 28 Jun 1300 - 0500 | 16 | 16 | 898994 |  | TF | FOT | WPSTK | 0 | WFD WHIPSTOCK FAILED TO SET
2510 | 06/29/2022 | ADC-17 | ZULF-1214 | RIG | 27 Jun 0245 - 1515 | 10.25 | 36 | 898931 |  | RR | FOT | CSYS | 8966 | AFTER MAKING A CONNECTION & STARTING CIRCULATION, FOUND A LEAK BETWEEN HIGH PRESSURE BLOCK & DISCHARGE LINE FLANGE OF MP #1.
2512 | 06/29/2022 | ADC-50 | SFNY-1176 | ARM | 26 Jun 1845 - 0500 | 24 | 81.5 | 898935 |  | LCIR | UVLC | NA | 2864 | HAD SEVERE LOSSES WHILE DRLG 12-1/4" HOLE @ 2,864', OPEN PBL SUB AND SPOT 2EA LCM PILLS WITH NO SUCCESS.
2514 | 06/29/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 268 | 898471 |  | JF | HERR | TDS | 9094 | ERROR RESULT : DRILL STRING STUCK.
2516 | 06/29/2022 | ADM-511 | MRJN-799 | ARM | 26 Jun 0045 - 0500 | 24 | 63.25 | 898861 |  | DRG | PCPF | NA | 7881 | HAD 15 KLBS S/O WHILE RIH @7763' & 7825',M/U TDS AND WASH DOWN TILL PASS FREE, CONTINUE RIH HAD OBSTRUCTION @7881FT,CHECKED STRING WT FREE UP/DOWN AND HAD FULL CIRCULATION, ATTEMPTED SEVERAL TIMES TO PASS WITH DIFFERENT PARAMETERS , NO SUCCESS.
2518 | 06/29/2022 | CG-1 | ZULF-1201 | RIG | 29 Jun 1430 - 1530 | 1 | 1 | 899074 |  | RR | FOT | ACDC | 11600 | RIG REPAIR- VFD SYSTEM POWER FAILED
2520 | 06/29/2022 | DPS-44 | UTMN-3174 | SPS | 28 Jun 0930 - 0200 | 20.5 | 39.5 | 898937 |  | BHA | FOT | MWD | 11151 | LOST COMMUNCATION WITH SPERRY SUN MWD TOOLS. TROUBLESHOOT SAME WITH NO SUCCESS.
2522 | 06/29/2022 | DPS-46 | SDGM-727 | CRW | 26 Jun 2300 - 0500 | 24 | 76.75 | 898822 |  | BHA | FOT | WBCL | 13360 | STRING GOT STUCK AFTER CIRC THRU CORETRAX CIRC SUB
2524 | 06/29/2022 | DQ-47 | KHRS-497 | ARM | 28 Jun 0800 - 0500 | 24 | 45 | 898952 |  | JF | HERR | NA | 5832 | GOC UNABLE TO REACH TARGET ENTRY OF ARB-1 DUE TO SHALLOWER TOP FORMATION W/42'.
2541 | 06/29/2022 | EXL-IVA | SFNY-1650 | ARM | 27 Jun 1315 - 1600 | 11 | 46.75 | 899053 |  | LCIR | UVLC | NA | 1120 | PERFORMING TOP JOBS ABOVE LOSS ZONE. ** CURE LOSSES WITH CEMENT PLUGS, 5 EA.
2543 | 06/29/2022 | HI-4 | SFNY-918 | SCP | 26 Jun 1500 - 0500 | 24 | 65.5 | 898833 |  | TF | FOT | SEAL | 4899 | UNABLE TO UNSTING SCHLUMBERGER WETCONNECTOR SEAL ASSEMBLY FROM WET CONNECTOR RECEPTACLE WITH STANDARD PROCEDURES (10 -25 KBLS OVERPULL). STRING ROTATION AND 50 KLBS OVERPULL WAS REQUIRED TO BE ABLE TO RELEASE STINGER WET CONNECTOR SEAL ASSEMBLY.
2545 | 06/29/2022 | JACK-202 | HMYM-844 | RIG | 29 Jun 0800 - 0900 | 1 | 1 | 898976 |  | RR | FOT | DWKS | 0 | ADJUST BREAK OF DRAWWORKS BY AMERICAN BLOCK DUE TO VIBRATIONS ON BRAKE BAND.
2547 | 06/29/2022 | NA-207S | SHYB-132 | ARM | 28 Jun 0000 - 0500 | 24 | 29 | 898940 |  | STUK | STBH | MILL | 4749 | STRING STUCK WHILE MILLING OUT 7" LINER
2549 | 06/29/2022 | NBR-20S | HMYM-433514 | RIG | 29 Jun 0730 - 1030 | 3 | 3 | 899054 |  | JF | XTRI | BOP | 4827 | EXCESS TIME TO NIPPLE UP BOPE.
2550 | 06/29/2022 | NBR-263S | QTIF-736 | RIG | 29 Jun 0330 - 0500 | 1.5 | 1.5 | 899056 |  | RR | FOT | PSYS | 600 | RIG POWER BLACK OUT, TROUBLESHOOTING RIG POWER & RESTART ELECTRICAL RIG OPERTIONAL SYSTEM.
2552 | 06/29/2022 | NBR-263S | QTIF-736 | ARM | 22 Jun 0630 - 0330 | 22.5 | 161.5 | 898674 |  | LCIR | UVLC | NA | 8541 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG.
2553 | 06/29/2022 | NBR-263S | QTIF-736 | RIG | 29 Jun 0330 - 0500 | 1.5 | 1.5 | 899056 |  | RR | FOT | PSYS | 600 | RIG POWER BLACK OUT, TROUBLESHOOTING RIG POWER & RESTART ELECTRICAL RIG OPERTIONAL SYSTEM.
2555 | 06/29/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 689.75 | 897183 |  | TF | FOT | LLAP | 15492 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP.
2557 | 06/29/2022 | PN-9 | MRJN-677 | HCM | 28 Jun 0400 - 0600 | 1 | 2 | 898951 |  | TF | FOT | PUMP | 0 | UNABLE TO MAINTAIN CMT SLURRY WEIGHT DURING DUMMY TEST, DUMP & CLEAN SURGE TANK.
2559 | 06/29/2022 | RM-74A | HSBH-68 | RIG | 22 Jun 1900 - 1845 | 13.75 | 167.75 | 898635 |  | UPRA | GRF | RWCS | 1573 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
2561 | 06/29/2022 | SCTD-1 | SDGM-1152 | RIG | 28 Jun 1600 - 0500 | 24 | 37 | 898938 |  | BHA | FOT | MMOT | 15037 | TURBINE DOWNHOLE FAILURE.
2563 | 06/29/2022 | SIN30L | KHRS-180 | TK2 | 28 Jun 0245 - 1015 | 5.25 | 7.5 | 898975 |  | STUK | STBH | BHA | 6450 | STUCK PIPE DURING SLIDING
2565 | 06/29/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 281.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
2567 | 06/29/2022 | SINO-7N | FDHL-130 | WWL | 29 Jun 1300 - 2100 | 8 | 8 | 898977 |  | TF | FOT | WLT | 910 | WHILE WFD WL RUN W/ RCT PUNCHER (1.693"), FAILD TO PASS WITH WL CABLE THROUGH WFD WL FLOWTUBE (CABLE HEAD) @ 910' SEVERAL TIMES.
2569 | 06/29/2022 | SND-1201 | KHRS-385 | BC | 29 Jun 1200 - 2200 | 10 | 10 | 899077 |  | TF | FOT | STING | 5482 | STING IN W/ BAKER SMART UPPER COMPLETION WCT STINGER INTO RECEPTACLE, UNABLE TO COMUNICATE WITH ICV'S.
2571 | 06/29/2022 | SND-2002 | WAQR-23 | HLH | 29 Jun 1815 - 0500 | 10.75 | 10.75 | 899055 |  | TF | FOT | HGRL | 11770 | AFTER COMPLETING SETTING HALLIBURTON EXTREME GRIP LINER HGR, UNABLE TO RELEASE TOOL DUE TO MECHANICAL FAILURE.
2573 | 06/29/2022 | SND-3002 | DMMM-601 | WCR | 28 Jun 0400 - 0600 | 1 | 2 | 898956 |  | TF | FOT | CTRQ | 13972 | WFD FMS SLIPS NOT FUNCTIONAL
2575 | 06/29/2022 | SP-110 | BRRI-562 | BHI | 28 Jun 0300 - 0500 | 24 | 26 | 898947 |  | BHA | FOT | GMWD | 12934 | BAKER BCPM TURBINE LOST SIGNAL
2577 | 06/29/2022 | SP-120 | MNIF-188 | SCT | 28 Jun 0330 - 1800 | 8 | 9.5 | 899012 |  | TF | FOT | CTBG | 8169 | CT COULDN'T PASS WHILE POOH AT 8,169'.
2579 | 06/29/2022 | SP-122 | UTMN-1938 | RIG | 29 Jun 0830 - 0500 | 20.5 | 20.5 | 899014 |  | DSF | HERR | STRG | 11586 | APPLIED EXCESSIVE LOAD ON STRING.
2581 | 06/29/2022 | SSA-29 | QTIF-348 | ARM | 11 Jun 1000 - 0545 | .75 | 418.75 | 897934 |  | STUK | STBH | BHA | 18494 | 3 3/4" CLEAN OUT BHA GOT STUCK AFTER CONNECTION @18494
2583 | 06/29/2022 | SSA-5859 | HWYH-1222 | RIG | 29 Jun 0000 - 0100 | 1 | 1 | 899076 |  | RR | FOT | HSYS | 7775 | REPAIR ON IRON ROUGHNECK: BROKEN HYDRAULIC CYLINDER.
2585 | 06/29/2022 | SSA-5868 | HRDH-2413 | RIG | 29 Jun 2200 - 0200 | 4 | 4 | 899072 |  | RR | FOT | TDS | 3770 | TDS IBOP BODY LEAKED.
2587 | 06/29/2022 | SSA-5914 | WDYH-80 | BHI | 29 Jun 1900 - 2015 | 1.25 | 1.25 | 899075 |  | TF | FOT | MS | 15400 | BAKER LOST SIGNAL WHILE TESTING MWD TOOL.
2589 | 06/29/2022 | SSA-5964 | HRDH-1383 | SJC | 29 Jun 2100 - 2200 | 1 | 1 | 899073 |  | CMT | HFFT | NA | 10206 | AFTER 4 1/2" LINER CEMENT JOB, TRIED TO REVERSE CIRCULATION, OBSERVED PRESSURE RAISED UP GRADUALLY.
2591 | 06/29/2022 | SSA-5970 | UTMN-2340 | RIG | 29 Jun 0400 - 0500 | 1 | 1 | 899057 |  | RR | FOT | CSYS | 6090 | REPAIR ON MUD PUMPS.
2593 | 06/29/2022 | T914 | UTMN-463 | WWD | 28 Jun 1300 - 1300 | 8 | 24 | 898994 |  | TF | FOT | WPSTK | 0 | WFD WHIPSTOCK FAILED TO SET
2595 | 06/30/2022 | ADC-14 | HRDH-612 | RIG | 30 Jun 0500 - 2230 | 17 | 17 | 899058 |  | DSF | FOT | DP | 11265 | UNABLE TO LATCH BAKER WIRE LINE WET CONNECTOR TO LOGGING TOOLS DUE TO SCALE FROM DP COATING ACCUMULATED INSIDE LATCH ASSY.
2596 | 06/30/2022 | ADC-35 | MAQL-5 | RIG | 30 Jun 0100 - 0400 | 3 | 3 | 899083 |  | RR | FOT | DWKS | 10000 | RIG REPAIR DRWWORKS.
2598 | 06/30/2022 | ADC-35 | MAQL-5 | ARN | 30 Jun 1415 - 0500 | 11.75 | 11.75 | 899082 |  | BHS | CWEL | NA | 11925 | HAD HOLE PACKED OFF, AND UNABLE TO CIRCULATE.
2599 | 06/30/2022 | ADC-35 | MAQL-5 | RIG | 30 Jun 0100 - 0400 | 3 | 3 | 899083 |  | RR | FOT | DWKS | 10000 | RIG REPAIR DRWWORKS.
2601 | 06/30/2022 | ADC-50 | SFNY-1176 | ARM | 26 Jun 1845 - 0500 | 24 | 105.5 | 898935 |  | LCIR | UVLC | NA | 2864 | HAD SEVERE LOSSES WHILE DRLG 12-1/4" HOLE @ 2,864', OPEN PBL SUB AND SPOT 2EA LCM PILLS WITH NO SUCCESS.
2603 | 06/30/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 292 | 898471 |  | JF | HERR | TDS | 9094 | ERROR RESULT : DRILL STRING STUCK.
2605 | 06/30/2022 | ADES-144 | UTMN-3152 | SPS | 30 Jun 2100 - 0030 | 3.5 | 3.5 | 899080 |  | BHA | FOT | MWD | 0 | WHILE SPERRY SUN PROGRAMMING THE TOOL STRING ON RIG FLOOR, ENCOUNTERED MWD COMMUNICATION FAILURE. SPERRY SUN PERFORMED TROUBLE SHOOTING WITHOUT SUCCESS.
2607 | 06/30/2022 | ADES-173 | UTMN-1964 | GCD | 30 Jun 2245 - 0500 | 6.25 | 6.25 | 899015 |  | SURV | FOT | SS | 12220 | GYRO TOOL FACE GIVING DIFFERENT READINGS AFTER LATCH IN UBHO.
2608 | 06/30/2022 | DPS-44 | UTMN-3174 | WUD | 30 Jun 0000 - 0430 | 4.5 | 4.5 | 899079 |  | TF | FOT | MPD | 11419 | OBSERVE MAJOR LEAK FROM WFD RCD BEARING ASSY.
2610 | 06/30/2022 | DPS-44 | UTMN-3174 | SPS | 28 Jun 0930 - 1700 | 2 | 40.5 | 898937 |  | BHA | FOT | MWD | 11151 | LOST COMMUNCATION WITH SPERRY SUN MWD TOOLS. TROUBLESHOOT SAME WITH NO SUCCESS.
2611 | 06/30/2022 | DPS-44 | UTMN-3174 | WUD | 30 Jun 0000 - 0430 | 4.5 | 4.5 | 899079 |  | TF | FOT | MPD | 11419 | OBSERVE MAJOR LEAK FROM WFD RCD BEARING ASSY.
2613 | 06/30/2022 | DPS-46 | SDGM-727 | CRW | 26 Jun 2300 - 0500 | 24 | 100.75 | 898822 |  | BHA | FOT | WBCL | 13360 | STRING GOT STUCK AFTER CIRC THRU CORETRAX CIRC SUB
2615 | 06/30/2022 | DQ-47 | KHRS-497 | ARM | 28 Jun 0800 - 0500 | 24 | 69 | 898952 |  | JF | HERR | NA | 5832 | GOC UNABLE TO REACH TARGET ENTRY OF ARB-1 DUE TO SHALLOWER TOP FORMATION W/42'.
2638 | 06/30/2022 | EXL-IA | SFNY-4240 | RIG | 30 Jun 1530 - 1545 | .25 | .25 | 899059 |  | RR | FOT | RSSS | 8060 | BUMP TEST & CALIBRATE H2S & LEL GAS SENSORS
2640 | 06/30/2022 | HI-4 | SFNY-918 | SCP | 26 Jun 1500 - 0500 | 24 | 89.5 | 898833 |  | TF | FOT | SEAL | 4899 | UNABLE TO UNSTING SCHLUMBERGER WETCONNECTOR SEAL ASSEMBLY FROM WET CONNECTOR RECEPTACLE WITH STANDARD PROCEDURES (25 -35 KBLS OVERPULL). STRING ROTATION AND 50 KLBS OVERPULL WAS REQUIRED TO BE ABLE TO RELEASE STINGER WET CONNECTOR SEAL ASSEMBLY.
2642 | 06/30/2022 | NA-207S | SHYB-132 | ARM | 28 Jun 0000 - 0500 | 24 | 53 | 898940 |  | STUK | STBH | MILL | 4749 | STRING STUCK WHILE MILLING OUT 7" LINER
2643 | 06/30/2022 | NBR-263S | QTIF-736 | RIG | 29 Jun 0330 - 0700 | 2 | 3.5 | 899056 |  | RR | FOT | PSYS | 600 | RIG POWER BLACK OUT, TROUBLESHOOTING RIG POWER & RESTART ELECTRICAL RIG OPERTIONAL SYSTEM.
2645 | 06/30/2022 | NBR-263S | QTIF-736 | ARM | 22 Jun 0630 - 0500 | 21.5 | 183 | 898674 |  | LCIR | UVLC | NA | 8541 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG.
2646 | 06/30/2022 | NBR-263S | QTIF-736 | RIG | 29 Jun 0330 - 0700 | 2 | 3.5 | 899056 |  | RR | FOT | PSYS | 600 | RIG POWER BLACK OUT, TROUBLESHOOTING RIG POWER & RESTART ELECTRICAL RIG OPERTIONAL SYSTEM.
2648 | 06/30/2022 | PA-529S | SHYB-108 | ENV | 25 May 1045 - 0500 | 24 | 377 | 896965 |  | TF | FOT | EXPND | 0 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY.
2650 | 06/30/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 713.75 | 897183 |  | TF | FOT | LLAP | 15492 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP.
2652 | 06/30/2022 | PN-9 | MRJN-677 | DEL | 30 Jun 0030 - 0500 | 4.5 | 4.5 | 899085 |  | WH | FOT | WH | 0 | OBSERVE DELTA TEST PLUG LEAKING AT 3000 PSI THROUGH SOV DURING BOP TEST. POH TEST PLUG, OBSERVED TEST PLUG SEALS DAMAGED, REPLACE SEALS AND RUN TEST PLUG. HOLD 300 PSI & FAIL ON 3000 PSI.
2654 | 06/30/2022 | RM-74A | HSBH-68 | RIG | 30 Jun 2245 - 0500 | 6.25 | 6.25 | 898983 |  | UPRA | GRF | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
2656 | 06/30/2022 | SCTD-1 | SDGM-1152 | RIG | 28 Jun 1600 - 0500 | 24 | 61 | 898938 |  | BHA | FOT | MMOT | 15037 | TURBINE DOWNHOLE FAILURE.
2658 | 06/30/2022 | SIN30L | KHRS-180 | RIG | 30 Jun 1115 - 1645 | 5.5 | 5.5 | 899062 |  | RR | FOT | CSYS | 6450 | GOT FAILURE ON ROTARTY HOSE (SLIGHT LEAKING WAS OBSERVED ON THE HOSE BODY WHILE PERFORMING REPLOG PRIOR TO RESUME DRILLING)
2660 | 06/30/2022 | SINO-10 | JLDI-38 | SPR | 30 Jun 0000 - 0030 | .5 | .5 | 898984 |  | TF | FOT | CRT | 8000 | JAM BATTERY ON SAPESCO CRT RUN OUT
2662 | 06/30/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 305.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
2664 | 06/30/2022 | SINO-43L | UTMN-4068 | ARM | 30 Jun 1530 - 0430 | 11.75 | 11.75 | 899060 |  | LCIR | FRFM | NA | 192 | ENCOUNTERED LCZ AT 192'. ATTEMPT TO CURE LOSSES WITH CMT PLUG.
2679 | 06/30/2022 | SINO-47 | HRDH-1351 | SPS | 30 Jun 1815 - 0500 | 2 | 2 | 899084 |  | SURV | FOT | MS | 11467 | NOT ABLE TO GET MWD SURVEY
2681 | 06/30/2022 | SND-2002 | WAQR-23 | HLH | 29 Jun 1815 - 2300 | 18 | 28.75 | 899055 |  | TF | FOT | HGRL | 11770 | AFTER COMPLETING SETTING HALLIBURTON EXTREME GRIP LINER HGR, UNABLE TO RELEASE TOOL DUE TO MECHANICAL FAILURE.
2683 | 06/30/2022 | SND-3003 | HRDH-1816 | OJR | 30 Jun 0500 - 0500 | 23.5 | 23.5 | 898981 |  | BHA | FOT | JARS | 2251 | AFTER CO F.S SUDDENLY LOST 220 PSI AND LOST 70KLB STRING WT, JAR TWISTED OFF
2685 | 06/30/2022 | SP-110 | BRRI-562 | BHI | 28 Jun 0300 - 1200 | 7 | 33 | 898947 |  | BHA | FOT | GMWD | 12934 | BAKER BCPM TURBINE LOST SIGNAL
2687 | 06/30/2022 | SP-122 | UTMN-1938 | RIG | 29 Jun 0830 - 1730 | 12.5 | 33 | 899014 |  | DSF | HERR | STRG | 11586 | APPLIED EXCESSIVE LOAD ON STRING.
2689 | 06/30/2022 | SSA-5914 | WDYH-80 | BHI | 30 Jun 1345 - 0500 | 15.25 | 15.25 | 899078 |  | TF | FOT | MS | 15400 | UNABLE TO READ SIGNAL FROM RSS ASSY. TROUBLESHOOT ON THE PULSER (ROTOR) AS PER BAKER DIRECTIONAL. NO SUCCESS.
2691 | 06/30/2022 | SSA-5964 | HRDH-1383 | SJC | 29 Jun 2100 - 0500 | 3.25 | 4.25 | 899073 |  | CMT | HFFT | NA | 10206 | AFTER 4 1/2" LINER CEMENT JOB, TRIED TO REVERSE CIRCULATION, OBSERVED PRESSURE RAISED UP GRADUALLY.
2693 | 06/30/2022 | SSA-5971 | HRDH-2247 | RIG | 30 Jun 0200 - 0330 | 1.5 | 1.5 | 899081 |  | RR | FOT | TDS | 12573 | TOP DRIVE DIES OUT.
2695 | 06/30/2022 | T218 | UTMN-1281 | WDS | 30 Jun 1730 - 0500 | 11.5 | 11.5 | 899061 |  | DD | UDWL | RSS | 9692 | WDS DD UNABLE TO FOLLOW GOC PLAN.
1 | 06/21/2022 | ADC-43L | UTMN-3118 | TK3 | 19 Jun 0245 - 1700 | 12 | 38.25 | 898513 |  | WCNT | WCC8 | NA | 10535 | OBSERVED INCREASE IN MPD RETURN FLOW. WELL FLOWING. SHUT-IN WELL ON RCD W/ 5 RPM. RECORD INITIAL SIDPP-1100 PSI, SICP - 1400 PSI, & PIT GAIN - 25 BBL.
3 | 06/21/2022 | ADC-55L | UTMN-3171 | TK3 | 21 Jun 1415 - 0500 | 14.25 | 14.25 | 898634 |  | WCNT | WC11 | NA | 6243 | OBSERVED INCREASE IN FLOW OUT
23 | 06/21/2022 | ADC-62L | ANDR-745 | RIG | 18 Jun 0100 - 0500 | 24 | 76 | 898471 |  | STUK | STDP | DP | 9094 | DRILL STRING STUCK.
25 | 06/21/2022 | ADC-67L | SDGM-1265 | SDM | 20 Jun 1600 - 0430 | 23.5 | 36.5 | 898518 |  | BHA | FOT | RSS | 12443 | RSS NOT RESPOND, PERFORMED TROUBLE SHOOTING. NO SUCCESS.
27 | 06/21/2022 | ADES-14 | HWYH-530 | GOC | 21 Jun 1830 - 2000 | 1.5 | 1.5 | 898521 |  | TF | XTTE | CRT | 10635 | EXCESS TIME DUE TO POOR HANDLING EQUIPMENT
29 | 06/21/2022 | ADES-158 | ABQQ-736 | RIG | 20 Jun 1730 - 0500 | 16.5 | 26.5 | 898654 | 897478 | JF | HERR | STRG | 5206 | HAD OBSTRUCTION @ 5206' WHILE RIH WITH BAKER DIR BHA.
31 | 06/21/2022 | ADM-337 | MRJN-900 | SLL | 18 Jun 0100 - 0500 | 24 | 68.5 | 898514 |  | TF | ISEQ | SB | 11365 | UNABLE TO PASS TOL WITH SCHLUMBERGER W/LINE TOOLS CBL & USIT
33 | 06/21/2022 | ADM-656 | SFNY-396 | SBA | 19 Jun 0945 - 2145 | 16.75 | 60 | 898490 |  | TF | FOT | ESPL | 2368 | OBSERVED UNBALANCED PHASE TO PHASE READINGS ON ESP ELECTRICAL CABLE AT 2,368 FT. DECISION MADE TO POH AND CHANGE OUT ESP CABLE.
35 | 06/21/2022 | AOD-111 | MRJN-724 | ARM | 20 Jun 2100 - 1715 | 11 | 18 | 898595 |  | LCIR | UVLC | NA | 16052 | OBSERVED LOSSES IN RATAWI RESRV 150 BPH
37 | 06/21/2022 | ARO-4001 | MRJN-538 | RIG | 21 Jun 2015 - 2315 | 3 | 3 | 898522 |  | RR | FOT | TDS | 16171 | REPAIRED LEAKING WATER COOLING HOSE IN TDS MOTOR.
39 | 06/21/2022 | CG-1 | ZULF-1201 | ARM | 09 Jun 2300 - 0500 | 24 | 293.5 | 897833 |  | STUK | STCT | SCRN | 9545 | SIDETRACK WELL DUE TO THE STUCK OF LOWER COMPLETION STRING.
41 | 06/21/2022 | NA-207S | SHYB-132 | RIG | 21 Jun 1330 - 1530 | 2 | 2 | 898519 |  | RR | FOT | ACDC | 4327 | OBSERVE FAULTY ENGINE CONTROL MODULE (AC MODULE).
43 | 06/21/2022 | NBR-16S | HMYM-433114 | RIG | 21 Jun 0845 - 1245 | 4 | 4 | 898658 |  | JF | XTRI | NA | 0 | EXCESSIVE TIME TO MAKE UP BHA, TROUBESHHOTING AND REPLACING MANUAL TONGS & JAWS, IRON ROUGHNECK NOT WORKING)
44 | 06/21/2022 | NBR-263S | QTIF-736 | ARM | 20 Jun 0500 - 1430 | 9.5 | 26 | 898597 |  | LCIR | UVLC | NA | 8307 | WHILE DRLG START FROM 8200' TO 8307' (ARAB B), OBSERVE LOSSES 30 TO 40 BPH. DECREASE FLOW RATE FROM 550 GPM TO 250 GPM OBSERVE NO LOSSES.
46 | 06/21/2022 | NBR-263S | QTIF-736 | ARM | 21 Jun 1830 - 0500 | 10.5 | 10.5 | 898523 |  | WCNT | WC20 | NA | 8541 | WHILE WASH & REAM PRIOR CONNECTION OBSERVE INCREASE IN ACTIVE MUD TANKS. STOP PUMP & FLOW CHECK OBSERVE WELL FLOWING, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=160 PSI, PUMP OUT FLOAT VALVE AND OBSERVE SIDPP=70 PSI. - LINE UP TO TRIP TANK AND BLEED OFF PRESS 50 PSI, CLOSE CHOKE OBSERVE PRESS BUILD UP. - KILL WELL WITH DRILLER METHOD.
47 | 06/21/2022 | NBR-263S | QTIF-736 | ARM | 20 Jun 0500 - 1430 | 9.5 | 26 | 898597 |  | LCIR | UVLC | NA | 8307 | WHILE DRLG START FROM 8200' TO 8307' (ARAB B), OBSERVE LOSSES 30 TO 40 BPH. DECREASE FLOW RATE FROM 550 GPM TO 250 GPM OBSERVE NO LOSSES.
49 | 06/21/2022 | NBR-783S | NJYN-93 | RIG | 17 Jun 1400 - 0500 | 6.25 | 54.75 | 898442 |  | UPRA | GRF | TDS | 395 | LOST TDS COMMUNICATION, BLOWER MOTOR FAILED.
51 | 06/21/2022 | PA-70S | MDRK-64 | WLH | 30 May 1800 - 0500 | 24 | 527.5 | 897183 |  | TF | FOT | LLAP | 15492 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK.
53 | 06/21/2022 | RM-74A | HSBH-68 | RIG | 14 Jun 1300 - 1700 | 12 | 170 | 898171 |  | UPRA | GRF | RWCS | 1905 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT
55 | 06/21/2022 | SA5898 | MDRK-57 | RIG | 20 Jun 0000 - 0300 | 22 | 27 | 898574 |  | TF | FOT | SLIPS | 15500 | DROP IN HOLE 2 DIES OF 4-3/4" DC SLIPS.
57 | 06/21/2022 | SCTD-2 | HRDH-2307 | RIG | 21 Jun 1730 - 1830 | 1 | 1 | 898520 |  | MUD | HPMR | NA | 14992 | FAILURE IN THE ELECTRIC PUMP, REPLACE SUCTION PUMP & CLEAN SAME.
59 | 06/21/2022 | SINO-12L | HRDH-400 | TK1 | 19 Jun 2230 - 0800 | 3 | 33.5 | 898505 |  | TF | FOT | LINR | 7170 | UNABLE TO SET OFF-BTM LINER DUE STRING LEAK.
100 | 06/21/2022 | SINO-36L | SDGM-458 | TK1 | 17 Jun 1130 - 0500 | 24 | 113.5 | 898452 |  | STUK | IPDF | DP | 8146 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY.
102 | 06/21/2022 | SND-2001 | UTMN-2329 | SDM | 19 Jun 1930 - 0500 | 23 | 44.5 | 898492 |  | BHA | FOT | RSS | 15637 | RSS UNABLE TO BUILD UP REQUIRED INCLINATION.
104 | 06/21/2022 | SND-2002 | WAQR-23 | ARM | 16 Jun 2330 - 0500 | 24 | 125.5 | 898293 |  | LCIR | UVLC | NA | 10620 | ENCOUNTERED PARTIAL LOSSES WHILE DRILLING AT 10,510 FT AND SEVERE LOSSES AT 10,620 FT
106 | 06/21/2022 | SND-2005 | MHKK-2 | SWL | 20 Jun 0230 - 0730 | 2.5 | 5 | 898655 |  | TF | FOT | WLT | 13195 | SCHLUMBERGER ASSURED EXPLORATION THE CBL/IBC/USIT WOULD WORK WITH THE 126 PCF, HOWEVER, WHEN USED, INADEQUATE SIGNAL.
108 | 06/21/2022 | SND-3002 | DMMM-601 | SDM | 20 Jun 1900 - 2300 | 16 | 26 | 898516 |  | BHA | FOT | RSS | 12127 | SDM RSS/MWD UNABLE TO HOLD INC ANGLE.
110 | 06/21/2022 | SP-110 | BRRI-562 | ARM | 21 Jun 1215 - 1315 | 1 | 1 | 898657 |  | STUK | STBH | BHA | 16745 | WHEN WASHING UP AT KELLY DOWN STRING GOT STUCK, RELEASE STUCK PIPE WITH WORK STRING UP & DOWN
111 | 06/21/2022 | SSA-101 | QTIF-785 | SDM | 21 Jun 0530 - 0700 | 1.5 | 1.5 | 898633 |  | BHA | FOT | MWD | 16910 | NO SDM MWD SIGNAL, SDM TROUBLE SHOOTING TO GET MWD SIGNAL WITHOUT SUCCESS, RIH TO BOTTOM AND DISPLACE HOLE TO 78 PCF WBM.
113 | 06/21/2022 | SSA-101 | QTIF-785 | SPS | 19 Jun 1330 - 0900 | 2.5 | 42 | 898508 |  | BHA | FOT | RSS | 9795 | SPS RSS GIVING WRONG VALUES AT MID WAY TOOL CHECK WHILE RIH,SPS TROUBLE SHOOT BY PUMPING HI VIS PILL AND JERKING STRING, NO PROGRESS(2ND SPS TOOL FAILURE IN 6 1/8" L-0 HOLE) - DECISION TO CHANGE DIRECTIONAL COMPANY FROM SPS TO SDM.
114 | 06/21/2022 | SSA-101 | QTIF-785 | SDM | 21 Jun 0530 - 0700 | 1.5 | 1.5 | 898633 |  | BHA | FOT | MWD | 16910 | NO SDM MWD SIGNAL, SDM TROUBLE SHOOTING TO GET MWD SIGNAL WITHOUT SUCCESS, RIH TO BOTTOM AND DISPLACE HOLE TO 78 PCF WBM.
116 | 06/21/2022 | WCL-83 | MRJN-834 | RIG | 21 Jun 0530 - 0500 | 23.5 | 23.5 | 898656 |  | STUK | STCT | SCRN | 11680 | WORK ON STUCK COMPLETION STRING BY DIFFERENT PARAMETERS