## Sheet1
seq | Report Date | Rig Name | Well No | Company Name | Date and Time | Time in Hrs | Cummulative Hrs | LT ID | Parent LT ID | LT Type | Cause | Object | Depth | LT Summary
1 | 04/26/2022 | ADC-58L | ABHD-178 | TK3 | 23 Apr 0045 - 0500 | 24 | 75.75 | 895847 |  | TH | PCPF | NA | 6966 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
3 | 04/26/2022 | ADC-62L | ANDR-745 | ARN | 25 Apr 0045 - 1115 | 6.25 | 10.5 | 895925 |  | WO | HMWT | NA | 2072 | WAIT ON FIXING THE WATER LINES AND FILL THE WATER PIT & MUD TANKS
5 | 04/26/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 1400 | 9 | 100 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
7 | 04/26/2022 | ADES-144 | UTMN-3099 | RIG | 25 Apr 1100 - 0500 | 14 | 30.5 | 895940 |  | BHA | ISEQ | RM | 9666 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
9 | 04/26/2022 | ADES-40 | ANDR-469 | WI1 | 17 Apr 1000 - 0500 | 24 | 228.5 | 895817 |  | TF | FOT | FISHT | 0 | WIS 6-1/8" MILL & RETRIEVING TOOL PARTED FROM TOP OF SPEAR MANDREL AND LEFT FISH INSIDE 7" PKR SEAL BORE EXTENSION.
11 | 04/26/2022 | ADM-261 | MRJN-137 | SCM | 26 Apr 1600 - 1700 | 1 | 1 | 895979 |  | TF | FOT | PUMP | 0 | FAILURE IN CEMENT UNIT MANIFOLD SEALS WHILE PRESSURE TESTING COIL REEL.
13 | 04/26/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 24 | 157.75 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
15 | 04/26/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 321.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
17 | 04/26/2022 | HI-2 | BRRI-464 | RIG | 26 Apr 2230 - 2330 | 1 | 1 | 895983 |  | RR | FPMP | MPMP | 15450 | OBSERVED DROP IN SPP& LEAK IN STAND PIPE MANIFOLD HAMMER UNION SEAL. CHANGED RUBBER RING GASKET.
18 | 04/26/2022 | HI-9 | QTIF-557 | ARM | 26 Apr 1000 - 0500 | 19 | 19 | 895987 |  | WON | WTHR | NA | 0 | DIVING SERVICES UNABLE TO INSTALL BUOYS AT NEW LOCATION QTIF 71, 557/558 DUE TO BAD WEATHER.
20 | 04/26/2022 | HI-9 | QTIF-557 | ARN | 22 Apr 0900 - 1000 | 5 | 97 | 895793 |  | WO | SRVC | NA | 0 | RIG IS WAITING ON SEA BED SURVEY FROM HSU DUE TO BAD WEATHER, UNABLE TO PROCEED TO NEXT LOCATION PLATFORM QTIF-71, 557/558.
21 | 04/26/2022 | HI-9 | QTIF-557 | ARM | 26 Apr 1000 - 0500 | 19 | 19 | 895987 |  | WON | WTHR | NA | 0 | DIVING SERVICES UNABLE TO INSTALL BUOYS AT NEW LOCATION QTIF 71, 557/558 DUE TO BAD WEATHER.
23 | 04/26/2022 | NBR-16S | HMYM-433302 | SDM | 25 Apr 0300 - 2100 | 14.75 | 16.75 | 895941 |  | SURV | FOT | MS | 8785 | LOST MWD SIGNAL
25 | 04/26/2022 | NBR-196S | SDGM-1226 | BHI | 25 Apr 1415 - 2030 | 11 | 25.25 | 895895 |  | BHA | FOT | RSS | 10755 | LOST SIGNAL FROM BAKER AUTOTRAC (RSS) BAKER AUTOTRAC SYSTEM FAILED - UNABLE TO RECEIVE SIGNAL FROM RSS TO MWD.
27 | 04/26/2022 | NBR-591S | HRDH-1921 | ARM | 25 Apr 0515 - 0500 | 24 | 47.75 | 895917 |  | LCIR | UVLC | NA | 8910 | ROTARY DRILL 12" HOLE NEW FORMATION BY 5 FT TO 8915'. HAD TOTAL LOSSES.
29 | 04/26/2022 | NBR-654S | HRDH-2210 | RIG | 26 Apr 1715 - 1915 | 2 | 2 | 895978 |  | JF | HERR | TDS | 14431 | DUE THE HIGH WIND SPEED (41.4 KM/H) TDS SERVICE LOOP HANGS ON THE MAST AND TORQUE TUBE BECAUSE OF SERVICE LOOP WAS NOT SECURED PROPERLY AND HYDRAULIC LINES IN SERVICE LOOP ARE DIFFERENT LENGTH.
31 | 04/26/2022 | PA-622S | AFLJ-4 | ARM | 24 Apr 1000 - 0500 | 20 | 63 | 895875 |  | STUK | PSSW | NA | 6896 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENTLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION.
33 | 04/26/2022 | RM-74A | KARN-60 | GEP | 25 Apr 1000 - 1400 | 9 | 23.75 | 895936 |  | WO | SRVC | NA | 0 | MODIFIED BLANKING PLUG FOR 6 3/8" K-TYPE BPV, PASSING.
35 | 04/26/2022 | SCTD-1 | SDGM-1240 | RIG | 26 Apr 1630 - 0500 | 12.5 | 12.5 | 895976 |  | DSF | FOT | STRG | 14769 | LOSS OF TELMETRY TO DOWNHOLE TOOLS
37 | 04/26/2022 | SINO-27N | UTMN-432 | ENP | 26 Apr 0645 - 1045 | 4 | 4 | 895988 |  | TF | MAOS | CSG | 4885 | ELEVATOR PROVIDED BY ENPRO SLIP UP ON TBG COLLAR.
54 | 04/26/2022 | SND-1501 | UTMN-567 | MSL | 26 Apr 1115 - 0500 | 17.75 | 17.75 | 895984 |  | TF | FOT | SLICK | 0 | AFTER DISPLACED WELL TO DIESEL OBERVED PX PLUG PRONG LEAKING
56 | 04/26/2022 | SND-2002 | WAQR-23 | ARM | 24 Apr 0700 - 0500 | 24 | 70 | 895892 |  | STUK | STBH | BHA | 4233 | AFTER CONNECTION, IBOP OPENED AFTER FEW ATTEMPTS AND FOUND THE STRING STUCK 3 FT OFF-BTM (NO MOVING, NO ROTATION AND NO CIRCULATION).
58 | 04/26/2022 | SNF036 | MRJN-901 | SWL | 26 Apr 1745 - 1945 | 2 | 2 | 895985 |  | TF | FOT | WLT | 9368 | SLB WL PINCHED ABOVE CABLE HEAD WHILE R/U SHEAVE ON DERRICK. CUT THE PINCHED PART AND RECONNECT CABLE HEAD. CHECK ROPE SOKET AND CABLE COMMUNIACTION - OK. RESUME OPERATIONS
60 | 04/26/2022 | SP-259 | HZEM-160402 | RIG | 26 Apr 1100 - 1200 | 1 | 1 | 895956 |  | BHA | HERR | DC | 0 | EXESS TIME TO M/U BHA
62 | 04/26/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 16.5 | 219.5 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
64 | 04/26/2022 | SSA-5914 | WDYH-80 | BHI | 26 Apr 0800 - 1300 | 5 | 5 | 895982 |  | BHA | IBHA | MMOT | 16074 | OBSERVED SET DOWN WEIGHT WHILE RIH WITH BAKER 8-3/8" K.O ASSY. THROUGH 9-5/8" CSG.
66 | 04/26/2022 | SSA-5962 | HRDH-2230 | WDS | 26 Apr 1830 - 0500 | 10.5 | 10.5 | 895986 |  | BHA | FOT | RSS | 7716 | HAD SPIKE OF PRESSURE OVER THAN 4800 PSI THEN WFD MOTOR STALLED & FAILED TO FUNCTION.
68 | 04/26/2022 | SSA-5969 | UTMN-3021 | ARM | 23 Apr 2030 - 0500 | 24 | 78 | 895881 |  | LCIR | UVLC | NA | 8585 | HAD COMPLETE LOSSES AT 8,585'
70 | 04/26/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0500 | 14 | 110 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL.
72 | 04/26/2022 | T901 | JLMN-79 | RIG | 24 Apr 0430 - 0915 | 4.25 | 8.5 | 895891 |  | BOP | FOT | BOP | 0 | LEAKING FROM ANNULAR BOP WEEP HOLE DUE TO OPENING CHAMBER FAILURE.
74 | 04/27/2022 | 095TE | MNIF-220 | RIG | 27 Apr 1730 - 2100 | 3.5 | 3.5 | 896017 |  | RR | FOT | DRRK | 4949 | RIG ATTEMPT TO FIX STABBING BOARD MOTOR WITHOUT SUCCESS, MANAGED TO RIH WITHOUT MOVING STABBING BOARD.
76 | 04/27/2022 | ADC-56L | UTMN-2330 | ARM | 27 Apr 0000 - 0100 | 1 | 1 | 896057 |  | WON | WTHR | NA | 10955 | HIGH WINDS, HEAVY RAIN AND LIGHTNING WHILE TRIPPING PIPE
78 | 04/27/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 0500 | 10.5 | 110.5 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
80 | 04/27/2022 | ADES-144 | UTMN-3099 | RIG | 25 Apr 1100 - 0500 | 23.5 | 54 | 895940 |  | BHA | ISEQ | RM | 9666 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
82 | 04/27/2022 | ADES-40 | ANDR-469 | WI1 | 17 Apr 1000 - 1500 | 10 | 238.5 | 895817 |  | TF | FOT | FISHT | 0 | WIS 6-1/8" MILL & RETRIEVING TOOL PARTED FROM TOP OF SPEAR MANDREL AND LEFT FISH INSIDE 7" PKR SEAL BORE EXTENSION.
84 | 04/27/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 494 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
86 | 04/27/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 24 | 181.75 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
88 | 04/27/2022 | DPS-5 | HRDH-2318 | FMC | 27 Apr 0200 - 0330 | 1.5 | 1.5 | 896029 |  | TF | FOT | CTRQ | 0 | FRANKS MAIN & BACK UP POWER TONG STOP WORKING AFTER MAKE UP 7"F/C DUE TO LEAK ON HYDRAULIC SYSTEM.
90 | 04/27/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 345.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
92 | 04/27/2022 | HI-9 | QTIF-557 | ARN | 26 Apr 1000 - 0500 | 24 | 43 | 895987 |  | WO | SRVC | NA | 0 | DIVING SERVICES UNABLE TO INSTALL BUOYS AT NEW LOCATION QTIF-71, 557/558 PF DUE TO BAD WEATHER.
94 | 04/27/2022 | MP-1 | MRJN-305 | ARM | 27 Apr 0115 - 0145 | .5 | .5 | 896059 |  | HSEI | UNKN | NA | 6100 | WORKING VESSEL ALONGSIDE MP-1 HAD A FIRE IN THE ENGINE ROOM, LOST ALL ENGINE POWER AND STARTED DRFTING TOWARDS THE RIG. GENERAL MUSTER CALLED, VESSEL DRIFTED PASSED MP-1 AND OUT OF THE 500M ZONE. ECC CONTACTED.
96 | 04/27/2022 | NBR-16S | HMYM-433302 | SDM | 27 Apr 0645 - 0200 | 19.25 | 19.25 | 896016 |  | BHA | FOT | RSS | 9316 | SLB NEOSTEER RSS UNABLE TO BUILD REQUIRED TRAJECTORY
98 | 04/27/2022 | NBR-196S | SDGM-1226 | WUD | 27 Apr 1030 - 1445 | 3.75 | 3.75 | 895998 |  | BOP | FOT | RCD | 10952 | WHILE DRILLING OBSERVED WFD RCD UNIT COOLER LINE LEAK & RCD LEAK MUD THRU RCD HEAD CLAMP. NOTE TOTAL ROTATING HOURS 26.5 BEFORE FAILURE.
100 | 04/27/2022 | NBR-591S | HRDH-1921 | ARM | 25 Apr 0515 - 0500 | 22.5 | 70.25 | 895917 |  | LCIR | UVLC | NA | 8910 | ROTARY DRILL 12" HOLE NEW FORMATION BY 5 FT TO 8915'. HAD TOTAL LOSSES.
102 | 04/27/2022 | NBR-783S | NJYN-89 | RIG | 27 Apr 2000 - 2030 | .5 | .5 | 896027 |  | RR | FOT | CSYS | 15320 | CEMENT LINE LOWER TORQ VALVE LEAKING CHANGE SAME
104 | 04/27/2022 | NBR-797S | UTMN-3130 | RIG | 27 Apr 0300 - 0400 | 1 | 1 | 896039 |  | RR | FOT | CSYS | 2890 | STAND PIPE MANIFOLD GASKET FAILED AT HAMMER UNION CONNECTION.
106 | 04/27/2022 | PA-622S | AFLJ-4 | ARM | 24 Apr 1000 - 0500 | 24 | 87 | 895875 |  | STUK | PSSW | NA | 6896 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENTLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION.
108 | 04/27/2022 | RM-74A | KARN-60 | GEP | 25 Apr 1000 - 1815 | 3 | 26.75 | 895936 |  | WO | SRVC | NA | 0 | MODIFIED BLANKING PLUG FOR 6 3/8" K-TYPE BPV, PASSING.
109 | 04/27/2022 | SCTD-1 | SDGM-1240 | RIG | 27 Apr 2330 - 0500 | 5.5 | 5.5 | 896023 |  | DSF | FOT | STRG | 14858 | LOSS OF TELMETRY OF DOWNHOLE TOOLS
111 | 04/27/2022 | SCTD-1 | SDGM-1240 | RIG | 26 Apr 1630 - 1030 | 5.5 | 18 | 895976 |  | DSF | FOT | STRG | 14769 | LOSS OF TELMETRY OF DOWNHOLE TOOLS
112 | 04/27/2022 | SCTD-1 | SDGM-1240 | RIG | 27 Apr 2330 - 0500 | 5.5 | 5.5 | 896023 |  | DSF | FOT | STRG | 14858 | LOSS OF TELMETRY OF DOWNHOLE TOOLS
114 | 04/27/2022 | SINO-19L | UTMN-1587 | RIG | 27 Apr 0500 - 2200 | 5 | 5 | 896022 |  | RR | FOT | HSYS | 0 | BOP HOIST SYSTEM DRILLER SIDE FAIL TO PASS LOAD TEST, OBSERVED OIL LEAK FROM ITS PISTON.
116 | 04/27/2022 | SINO-32L | SHYB-570 | TK2 | 27 Apr 1700 - 1930 | 2.5 | 2.5 | 896030 |  | LROP | VPFM | BIT | 170 | LOW ROP WHILE DRILLING 28" SECTION, ROP 2-3 FT/HR. POOH & CHANGE.
155 | 04/27/2022 | SINO-5L | UTMN-1289 | TK1 | 26 Apr 1900 - 0500 | 24 | 31.5 | 895989 |  | TH | NARW | NA | 8518 | GOT RESTRICTION @ 8518' WHILE RIH W/LOWER COMPLETION.
156 | 04/27/2022 | SND-1501 | UTMN-567 | HSL | 27 Apr 0045 - 0500 | 4.25 | 4.25 | 896058 |  | TF | FOT | SLICK | 0 | HALL MONO-LOCK FAILURE (PRONG) AFTER DISPLACE WELL TO DIESEL
158 | 04/27/2022 | SND-1501 | UTMN-567 | MSL | 26 Apr 1115 - 0045 | 19.75 | 37.5 | 895984 |  | TF | FOT | SLICK | 0 | AFTER DISPLACED WELL TO DIESEL OBERVED PX PLUG PRONG LEAKING
159 | 04/27/2022 | SND-1501 | UTMN-567 | HSL | 27 Apr 0045 - 0500 | 4.25 | 4.25 | 896058 |  | TF | FOT | SLICK | 0 | HALL MONO-LOCK FAILURE (PRONG) AFTER DISPLACE WELL TO DIESEL
161 | 04/27/2022 | SND-2002 | WAQR-23 | ARM | 24 Apr 0700 - 0500 | 24 | 94 | 895892 |  | STUK | STBH | BHA | 4233 | AFTER CONNECTION, IBOP OPENED AFTER FEW ATTEMPTS AND FOUND THE STRING STUCK 3 FT OFF-BTM (NO MOVING, NO ROTATION AND NO CIRCULATION).
163 | 04/27/2022 | SND-2003 | RMTN-17 | RIG | 27 Apr 2200 - 0330 | 5.5 | 5.5 | 896026 |  | RR | FOT | TDS | 2800 | UNABLE TO ROTATE DUE TO DAMEGE IN ONE OF MAIN POWER PHASE CABLES IN TDS.
165 | 04/27/2022 | SND-2004 | BRRI-1148 | ARM | 27 Apr 2330 - 0500 | 5.5 | 5.5 | 896028 |  | LCIR | FRFM | NA | 5630 | HAD PARTIAL LOSSES 120 BPH @ 5630 FT (99 FT INSIDE SHUAIBA)- ATTEMPTS TO CURE LOSSES WITH LCM PILL
167 | 04/27/2022 | SND-2007 | ADHN-370100 | RIG | 27 Apr 2315 - 0315 | 4 | 4 | 896025 |  | RR | FPMP | MPMP | 15135 | PUMP PRESSURE DROP DUE TO WASH ON PUMP GASKETS
169 | 04/27/2022 | SP-101 | ABQQ-710 | WI1 | 27 Apr 1100 - 0500 | 18 | 18 | 896019 |  | TF | FOT | FISHT | 2398 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG.
171 | 04/27/2022 | SP-261 | HZEM-160204 | RIG | 27 Apr 2230 - 0115 | 2.75 | 2.75 | 896021 |  | JF | XTRI | NA | 1167 | TIGHTEN LEAKING DIVERTER VENT LINES
173 | 04/27/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 24 | 243.5 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
175 | 04/27/2022 | SSA-303 | HRDH-2306 | ARM | 17 Apr 0500 - 0500 | 24 | 260.5 | 895697 |  | TH | PCPF | NA | 2710 | WHILE RUNNING 18-5/8" CSG ENCOUNTERED OBSTRUCTION @ 871' AND NOT ABLE TO PASS
177 | 04/27/2022 | SSA-5820 | SDGM-1215 | RIG | 27 Apr 0100 - 0500 | 4 | 4 | 896024 |  | RR | FOT | TDS | 0 | TDS HPU1 COMMUNICATION & OVERLOAD DEVICE TRIPPED (HYRAULIC SERVICE LOOP IS NOT WORKING).
179 | 04/27/2022 | SSA-5865 | ABJF-50 | WCR | 27 Apr 1500 - 1530 | .5 | .5 | 896037 |  | TF | FOT | FUT | 164 | STUNG INTO SHOE TRACK AND FILLED AND PUMPED THROUGH. WHEN STUNG OUT FOUND THE FILLUP HOSE LEAKING JUST BELOW THE CRIMPED CONNECTION.
181 | 04/27/2022 | SSA-5962 | HRDH-2230 | WDS | 26 Apr 1830 - 2030 | 15.5 | 26 | 895986 |  | BHA | FOT | RSS | 7716 | HAD SPIKE OF PRESSURE OVER THAN 4800 PSI THEN WFD MOTOR STALLED & FAILED TO FUNCTION.
183 | 04/27/2022 | SSA-5969 | UTMN-3021 | ARM | 23 Apr 2030 - 0430 | 10 | 88 | 895881 |  | LCIR | UVLC | NA | 8585 | HAD COMPLETE LOSSES AT 8,585'
185 | 04/27/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0230 | 21.5 | 131.5 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL.
187 | 04/27/2022 | T901 | JLMN-79 | RIG | 27 Apr 0745 - 1845 | 11 | 11 | 896018 |  | MUD | HSCM | NA | 1504 | ENCOUNTERED ABNORMAL PRESSURE DURING SHALLOW TEST.
189 | 04/28/2022 | ADC-49 | HRDH-2128 | RIG | 28 Apr 0030 - 0230 | 2 | 2 | 896096 |  | RR | FOT | PSYS | 5085 | EXCESSIVE HEAT OBSERVED ON DRILLER CONSOLE SENSORS FOR GENERATOR NO.3
191 | 04/28/2022 | ADC-57L | FDHL-158 | TK3 | 27 Apr 2230 - 0700 | 2 | 8.5 | 896041 |  | CMT | WSHO | CSG | 13135 | DRILL OUT 7" LNR SHOE TRACK 20 FT ABOVE FLOAT SHOE. P/T 7" CSG LNR TO 650 PSI PRESSURE DROP NOT HOLDING
193 | 04/28/2022 | ADC-58L | ABHD-178 | TK3 | 23 Apr 0045 - 0500 | 24 | 123.75 | 895847 |  | TH | PCPF | NA | 6966 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
195 | 04/28/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 0500 | 23 | 133.5 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
197 | 04/28/2022 | ADES-144 | UTMN-3099 | RIG | 25 Apr 1100 - 0500 | 23.5 | 77.5 | 895940 |  | BHA | ISEQ | RM | 9666 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
199 | 04/28/2022 | ADES-798 | JFYN-11 | BCR | 28 Apr 0500 - 1200 | 7 | 7 | 895999 |  | JF | HERR | CTRQ | 15675 | SL DRIFT COULDN'T PASS TBG OBSTRUCTION AT 1501 FT DUE TO OVER-TORQUED CONNECTION. POOH & CHANGE OUT DAMAGED COLLAR.
201 | 04/28/2022 | AOD-1 | ZULF-692 | SCB | 28 Apr 2130 - 0130 | 4 | 4 | 896070 |  | TF | FOT | RBP | 4511 | SET SLB SIM RBP AT 4511'. WHEN RELEASING RUNNING TOOL FOUND PLUG HAD DISCONNECTED. RIH AND TAG PLUG AT 4567'.
203 | 04/28/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 518 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
205 | 04/28/2022 | ARO-4001 | MRJN-539 | RIG | 28 Apr 0130 - 0200 | .5 | .5 | 896001 |  | RR | FOT | RSYS | 7944 | HAD MALFUNCTION IN IRON ROUGHNECK, TROUBLESHOOTING SAME.
207 | 04/28/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 22.75 | 204.5 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
209 | 04/28/2022 | DPS-5 | HRDH-2318 | WDV | 28 Apr 1515 - 0500 | 13.75 | 13.75 | 896046 |  | TF | FOT | DV | 3680 | HAD RESTRICTION @ 3680' ( 02 STDS AFTER 7" LNR HRG), PICK UP STRING, ENGAGED TDS & WASH DOWN- NOT ABLE TO PASS.
211 | 04/28/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 21.5 | 366.75 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
213 | 04/28/2022 | HI-9 | QTIF-557 | AP2 | 28 Apr 0500 - 0500 | 24 | 24 | 896076 |  | WO | WPD3 | NA | 0 | RIG IS WAITING ON WELL SERVICES BARGE ARABIYA-3 TO INSTALL ISOLATION PLUGS AND DEPRESSURIZE QTIF-71, 557/558 PLATFORM.
215 | 04/28/2022 | NBR-591S | HRDH-1921 | ARM | 25 Apr 0515 - 0500 | 21 | 91.25 | 895917 |  | LCIR | UVLC | NA | 8910 | ROTARY DRILL 12" HOLE NEW FORMATION BY 5 FT TO 8915'. HAD TOTAL LOSSES.
217 | 04/28/2022 | PA-622S | AFLJ-4 | ARM | 24 Apr 1000 - 0500 | 24 | 111 | 895875 |  | STUK | PSSW | NA | 6896 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENTLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION.
219 | 04/28/2022 | RTC-2 | TRYQ-5 | SWL | 28 Apr 0800 - 1530 | 7.5 | 7.5 | 896045 |  | TF | FOT | WLT | 7100 | SLB WL PLT WIRELINE TOOL MALFUNCTIONED, COMMENCED TROUBLESHOOTING, NO SUCCESS.
221 | 04/28/2022 | SCTD-1 | SDGM-1240 | RIG | 27 Apr 2330 - 0230 | 21.5 | 27 | 896023 |  | DSF | FOT | STRG | 14858 | LOSS OF TELMETRY OF DOWNHOLE TOOLS
223 | 04/28/2022 | SDA | MRJN-735 | BCT | 28 Apr 1130 - 1330 | 2 | 2 | 896068 |  | JF | HERR | CTAC | 0 | WHILE INSTALLING BAKER COIL TUBING HEAD INTO INJECTOR LOCATED ON CANTILEVER DECK A STABBING GUIDE (740 GRM) CAME OUT FROM COIL TUBING AND FELL TO MAIN DECK (40 FT). STOP OPERATION FOR INVESTIGATION. CONDUCT SAFETY SHUT STAND DOWN MEETING WITH CREWS.
225 | 04/28/2022 | SINO-12L | HRDH-1454 | TK1 | 28 Apr 2130 - 0500 | 7.5 | 7.5 | 896069 |  | STUK | STBG | TBG | 8710 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION
268 | 04/28/2022 | SINO-5L | UTMN-1289 | TK1 | 26 Apr 1900 - 0500 | 24 | 55.5 | 895989 |  | TH | NARW | NA | 8518 | GOT RESTRICTION @ 8518' WHILE RIH W/LOWER COMPLETION.
270 | 04/28/2022 | SND-1501 | UTMN-567 | HSL | 27 Apr 0045 - 0500 | 24 | 28.25 | 896058 |  | TF | FOT | SLICK | 0 | HALL MONO-LOCK FAILURE (PRONG) AFTER DISPLACE WELL TO DIESEL
272 | 04/28/2022 | SND-2002 | WAQR-23 | ARM | 24 Apr 0700 - 1600 | 11 | 105 | 895892 |  | STUK | STBH | BHA | 4233 | AFTER CONNECTION, IBOP OPENED AFTER FEW ATTEMPTS AND FOUND THE STRING STUCK 3 FT OFF-BTM (NO MOVING, NO ROTATION AND NO CIRCULATION).
274 | 04/28/2022 | SND-2004 | BRRI-1148 | ARM | 27 Apr 2330 - 0500 | 13.5 | 19 | 896028 |  | LCIR | FRFM | NA | 5630 | HAD PARTIAL LOSSES 120 BPH @ 5630 FT (99 FT INSIDE SHUAIBA)- ATTEMPTS TO CURE LOSSES WITH LCM PILL
276 | 04/28/2022 | SND-2007 | ADHN-370100 | RIG | 28 Apr 0530 - 2100 | 15.5 | 15.5 | 896042 |  | RR | FPMP | MPMP | 15158 | PSI LOSS ON MUD PUMPS, CAP GASKETS LEAKING ON MUD PUMP MODULES ON #1 & #2.
278 | 04/28/2022 | SP-101 | ABQQ-710 | WI1 | 27 Apr 1100 - 0500 | 24 | 42 | 896019 |  | TF | FOT | FISHT | 2398 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG.
280 | 04/28/2022 | SP-262 | HZEM-140814 | BHI | 28 Apr 1300 - 0500 | 16 | 16 | 896002 |  | BHA | FOT | MWD | 16449 | BAKER TOOLS LOST MWD SIGNAL
282 | 04/28/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 24 | 267.5 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
284 | 04/28/2022 | SSA-5868 | HRDH-2336 | RIG | 28 Apr 0245 - 0500 | 2.25 | 2.25 | 896071 |  | RR | FOT | TDS | 12782 | OBSERVED LEAKAGE IN TDS IBOP.
286 | 04/28/2022 | SSA-5969 | UTMN-3021 | ARM | 23 Apr 2030 - 0430 | 23.5 | 111.5 | 895881 |  | LCIR | UVLC | NA | 8585 | HAD COMPLETE LOSSES AT 8,585'
288 | 04/28/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0500 | 24 | 155.5 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL.
290 | 04/29/2022 | 088TE | QTIF-176 | MSD | 29 Apr 1200 - 1300 | 1 | 1 | 896137 |  | TF | FOT | CTRQ | 1640 | MALFUNCTION AL-MASAOOD JAM UNIT, TROUBLESHOOT, FIXED SAME.
292 | 04/29/2022 | ADC-12 | ABQQ-84 | RIG | 29 Apr 0215 - 0500 | 2.75 | 2.75 | 896142 |  | RR | FOT | ACDC | 5377 | WHILE CHECKING WINDOW TO PASS FREE UP/DOWN HAD RIG REAL TIME PASON SYSTEM DOWN @ DRILLER CONSOLE
294 | 04/29/2022 | ADC-50 | SFNY-1177 | NC1 | 28 Apr 1900 - 1915 | 14.25 | 24.25 | 896004 |  | TF | FOT | ACV | 6795 | OBSERVED SURFACE PRESSURE DROPPED BY 500 PSI WHILE DRLG @ 6,795', TROUBLESHOOTING AND TESTED SURFACE LINE-OK, SUSPECT NOV ANDEREAMER NOZZLES OPEN, POH TO SURFACE, TESTED ANDEREMAER AT SURFACE, GOT RETURN FROM TWO NOZZLES OF NOV ANDERREAMER WHILE CIRCULATION.
296 | 04/29/2022 | ADC-57L | FDHL-158 | TK3 | 27 Apr 2230 - 0500 | 24 | 38.5 | 896041 |  | CMT | WSHO | CSG | 13135 | DRILL OUT 7" LNR SHOE TRACK 20 FT ABOVE FLOAT SHOE. P/T 7" CSG LNR TO 650 PSI PRESSURE DROP NOT HOLDING
298 | 04/29/2022 | ADC-58L | ABHD-178 | TK3 | 23 Apr 0045 - 0500 | 24 | 147.75 | 895847 |  | TH | PCPF | NA | 6966 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
300 | 04/29/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 0500 | 23.5 | 157 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
302 | 04/29/2022 | ADES-144 | UTMN-3099 | RIG | 25 Apr 1100 - 0500 | 15 | 92.5 | 895940 |  | BHA | ISEQ | RM | 9666 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
304 | 04/29/2022 | ADM-266 | SFNY-934 | RIG | 29 Apr 2300 - 0500 | 6 | 6 | 896141 |  | RR | FOT | TDS | 5262 | TOP DRIVE IBOP ACTUATOR NOT FUNCTION.
306 | 04/29/2022 | ADM-656 | SFNY-397 | RIG | 29 Apr 1700 - 0500 | 10 | 10 | 896107 |  | RR | FPMP | MPMP | 0 | MUD PUMP1 LINER WASHER DAMAGED
307 | 04/29/2022 | AOD-11 | SFNY-4280 | RIG | 29 Apr 1800 - 2200 | 4 | 4 | 896007 |  | RR | FOT | TDS | 325 | RACK BACK ONE STAND. ACCUMULATOR ON TDS CANNOT HOLD PRESSURE DUE TO BROKEN FITTINGS. TROUBLESHOT & FIX.
309 | 04/29/2022 | AOD-11 | SFNY-4280 | RIG | 29 Apr 1330 - 1615 | 2.75 | 2.75 | 896006 |  | RR | FOT | TDS | 309 | RACK BACK ONE STAND & FIX CRACK ON TDS HEAT EXCHANGER.
310 | 04/29/2022 | AOD-11 | SFNY-4280 | RIG | 29 Apr 1800 - 2200 | 4 | 4 | 896007 |  | RR | FOT | TDS | 325 | RACK BACK ONE STAND. ACCUMULATOR ON TDS CANNOT HOLD PRESSURE DUE TO BROKEN FITTINGS. TROUBLESHOT & FIX.
312 | 04/29/2022 | AOD-111 | MRJN-721 | BHI | 29 Apr 1930 - 2200 | 2.5 | 2.5 | 896074 |  | BHA | FOT | FV | 2220 | WHILE RIH OBSERVED OPEN END PIPE DISPLACEMENT. FLOAT VALVE FAILURE
314 | 04/29/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 542 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
316 | 04/29/2022 | ARO-4001 | MRJN-539 | RIG | 29 Apr 2230 - 0130 | 3 | 3 | 896075 |  | RR | FOT | CSYS | 11000 | THE HOPPER ON MAIN DECK GOT PLUGGED MANY TIMES, FIX AIR HOSE AND UN-PLUG SAME.
318 | 04/29/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 24 | 228.75 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
320 | 04/29/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 23.5 | 390.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
322 | 04/29/2022 | EXL-IVA | SFNY-1800 | RIG | 29 Apr 1915 - 1945 | .5 | .5 | 896157 |  | RR | FPMP | MPMP | 6670 | PUMP PRV TRIPPED OUT WHILE DRILLING,
324 | 04/29/2022 | HI-9 | QTIF-557 | AP2 | 28 Apr 0500 - 0500 | 24 | 48 | 896076 |  | WO | WPD3 | NA | 0 | RIG IS WAITING ON WELL SERVICES BARGE ARABIYAH-3 TO INSTALL ISOLATION PLUGS AND DEPRESSURIZE QTIF-71, 557/558 PLATFORM.
326 | 04/29/2022 | NBR-304S | HRDH-1952 | SPS | 29 Apr 1030 - 1630 | 6 | 6 | 896108 |  | BHA | FOT | MWD | 12900 | SPERRY SUN MWD FAILURE, TROUBLESHOOT THE SAME WITH NO SUCCESS.
327 | 04/29/2022 | NBR-654S | HRDH-2210 | RIG | 29 Apr 1815 - 0500 | 10.75 | 10.75 | 896156 |  | HSEI | UNKN | NA | 4950 | JOINT DISLODGED FROM TUBING PICK UP MACHINE
329 | 04/29/2022 | NBR-654S | HRDH-2210 | FMC | 29 Apr 0530 - 1815 | 12.25 | 12.25 | 896109 |  | JF | HERR | CTRQ | 14431 | UNABLE TO DRIFT 4 1/2" LINER
330 | 04/29/2022 | NBR-654S | HRDH-2210 | RIG | 29 Apr 1815 - 0500 | 10.75 | 10.75 | 896156 |  | HSEI | UNKN | NA | 4950 | JOINT DISLODGED FROM TUBING PICK UP MACHINE
332 | 04/29/2022 | PA-622S | AFLJ-4 | ARM | 24 Apr 1000 - 0500 | 22 | 133 | 895875 |  | STUK | PSSW | NA | 6896 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION.
334 | 04/29/2022 | PA-861S | HRDH-1060 | ARM | 29 Apr 1700 - 0500 | 12 | 12 | 896139 |  | STUK | STBH | RM | 11784 | WHILE RIH W/ REAMING BHA STRING GOT STUCK AT THE OPEN HOLE WHIPSTOCK
336 | 04/29/2022 | PN-9 | MRJN-91 | RIG | 29 Apr 1800 - 2030 | 2.5 | 2.5 | 896008 |  | RR | FOT | TDS | 8327 | TOP DRIVE WASH PIPE LEAKED, CHANGE WITH NEW WASH PIPE.
338 | 04/29/2022 | SDA | MRJN-735 | BCT | 29 Apr 0000 - 0500 | 5 | 5 | 896161 |  | JF | HERR | CTAC | 0 | BAKER CTU: UNABLE TO CONNECT BOP CONTROL LINES TO CTU BOP INSTALLED ON TOP OF TREE DUE TO INSUFFICIUENT LENGHT OF CONTROL LINES (150FT) . R/D 2" IRON LINE, L/D CTU RISER JOINTS, N/D CTU QUAD BOP FROM TREE. N/U RISER TO TOP OF PRODUCTION TREE, REPOSITION BOP ON TOP OF RISER, CONNECT CONTROL LINES, RE-INSTALL 2" IRON LINES.
340 | 04/29/2022 | SINO-12L | HRDH-1454 | TK1 | 28 Apr 2130 - 0500 | 24 | 31.5 | 896069 |  | STUK | STBG | TBG | 8710 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION
354 | 04/29/2022 | SINO-32L | SHYB-570 | BCM | 29 Apr 2300 - 0500 | 6 | 6 | 896105 |  | CMT | HFFT | NA | 902 | WILE 24" CSG CMT JOB, CMT WEIGHT NOT MAINTAINED 122 PCF AS PG, FLUCTUATED BETWEEN 105-122, SWITCHED TO THE BACKUP CEMENT UNIT BUT HAD SAME PROBLEM, DECIDED TO CIRCULATE OUT CMT SLURRY.
388 | 04/29/2022 | SND-1501 | UTMN-567 | BC | 26 Apr 1115 - 0500 | 24 | 89.75 | 895984 |  | TF | FOT | PKR | 0 | AFTER DISPLACED WELL TO DIESEL OBERVED WELL NOT STATIC W/ STEADY RETURNS
390 | 04/29/2022 | SND-2004 | BRRI-1148 | ARM | 27 Apr 2330 - 1215 | 7.25 | 26.25 | 896028 |  | LCIR | FRFM | NA | 5630 | HAD PARTIAL LOSSES 120 BPH @ 5630 FT (99 FT INSIDE SHUAIBA)- ATTEMPTS TO CURE LOSSES WITH LCM PILL
391 | 04/29/2022 | SND-2007 | ADHN-370100 | RIG | 29 Apr 1700 - 0130 | 8.5 | 8.5 | 896138 |  | RR | FOT | TDS | 15294 | GRAPPER FOR TDS GET STUCK ON ITS POSITION.
393 | 04/29/2022 | SND-2007 | ADHN-370100 | RIG | 29 Apr 0845 - 0500 | 11.75 | 11.75 | 896104 |  | RR | FOT | RWCS | 15294 | LEAK OF OBM FROM UPPER WELL CONTROL VALVE.
394 | 04/29/2022 | SND-2007 | ADHN-370100 | RIG | 29 Apr 1700 - 0130 | 8.5 | 8.5 | 896138 |  | RR | FOT | TDS | 15294 | GRAPPER FOR TDS GET STUCK ON ITS POSITION.
396 | 04/29/2022 | SP-101 | ABQQ-710 | WI1 | 27 Apr 1100 - 0500 | 24 | 66 | 896019 |  | TF | FOT | FISHT | 2398 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG.
398 | 04/29/2022 | SP-260 | HZEM-161012 | BHI | 29 Apr 1015 - 0500 | 18.75 | 18.75 | 896158 |  | BHA | FOT | RSS | 16114 | BAD COMMUNICATION FROM RSS, TROUBLE SHOOT, NO SUCCESS. DECIDE TO POOH AND CHANGE BAKER TOOLS.
400 | 04/29/2022 | SP-262 | HZEM-140814 | BHI | 28 Apr 1300 - 0500 | 24 | 40 | 896002 |  | BHA | FOT | MWD | 16449 | BAKER TOOLS LOST MWD SIGNAL
401 | 04/29/2022 | SSA-101 | QTIF-785 | ARN | 29 Apr 0330 - 0500 | 1.5 | 1.5 | 896159 |  | BHS | CWEL | NA | 1701 | STRING STUCK AT 1701', WORK ON STRING
403 | 04/29/2022 | SSA-101 | QTIF-785 | ARM | 28 Apr 0345 - 2330 | 18 | 19.25 | 896098 |  | BHS | CWEL | NA | 1616 | OBSERVED ERRATIC TORQUE FR 5 TO 17 KLB-FT AND ROTARY STALL,POOH TO CHANGE BHA TO ROTARY BHA W/ MWD.
404 | 04/29/2022 | SSA-101 | QTIF-785 | ARN | 29 Apr 0330 - 0500 | 1.5 | 1.5 | 896159 |  | BHS | CWEL | NA | 1701 | STRING STUCK AT 1701', WORK ON STRING
406 | 04/29/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 24 | 291.5 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
408 | 04/29/2022 | SSA-303 | HRDH-2306 | RIG | 29 Apr 0030 - 0430 | 4 | 4 | 896160 |  | WO | SRVC | NA | 2710 | EXCESS TIME TO HANDLE 26-3/4" BOPE
410 | 04/29/2022 | SSA-5868 | HRDH-2336 | RIG | 29 Apr 0500 - 0645 | 1.75 | 1.75 | 896071 |  | RR | FOT | TDS | 12782 | OBSERVED LEAKAGE IN TDS IBOP.
412 | 04/29/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0500 | 24 | 179.5 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL.
414 | 04/30/2022 | ADC-12 | ABQQ-84 | RIG | 29 Apr 0215 - 0800 | 3 | 5.75 | 896142 |  | RR | FOT | EDR | 5377 | RIG REAL TIME SYESTEM DISCONNECTED @ DRILLER CONSOLE.
416 | 04/30/2022 | ADC-14 | HRDH-986 | SAM | 30 Apr 1945 - 0500 | 9.25 | 9.25 | 896110 |  | BHA | FOT | WBCL | 10338 | SAMAA SET 9-5/8" FSC PACKER WITH 60 KLBS S/O WT, CLOSE BOP, ATTEMPTS TO PRESSURE TEST SAMAA PACKER BACK SIDE TO 1,000 PSI, PACKER CANNOT HOLD PRESSURE. UNSET PACKER.
418 | 04/30/2022 | ADC-57L | FDHL-158 | TK3 | 27 Apr 2230 - 0500 | 24 | 62.5 | 896041 |  | CMT | WSHO | CSG | 13135 | DRILL OUT 7" LNR SHOE TRACK 20 FT ABOVE FLOAT SHOE. P/T 7" CSG LNR TO 650 PSI PRESSURE DROP NOT HOLDING
420 | 04/30/2022 | ADC-58L | ABHD-178 | TK3 | 23 Apr 0045 - 0500 | 24 | 171.75 | 895847 |  | TH | PCPF | NA | 6966 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
422 | 04/30/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 1300 | 8 | 165 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
424 | 04/30/2022 | ADES-144 | UTMN-3099 | RIG | 25 Apr 1100 - 2245 | 16 | 108.5 | 895940 |  | BHA | ISEQ | RM | 9666 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
426 | 04/30/2022 | ADM-266 | SFNY-934 | RIG | 29 Apr 2300 - 0500 | 24 | 30 | 896141 |  | RR | FOT | TDS | 5262 | TOP DRIVE IBOP ACTUATOR NOT FUNCTION.
428 | 04/30/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 566 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
430 | 04/30/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 1300 | 8 | 236.75 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
432 | 04/30/2022 | DPS-46 | SDGM-1106 | BHI | 30 Apr 0130 - 0500 | 3.5 | 3.5 | 896147 |  | DD | HERR | RSS | 0 | CAN'T PROGRAM BAKER TOOLS, TROUBLE SHOOTING COMMUNICATION ERROR.
434 | 04/30/2022 | DPS-5 | HRDH-2318 | WDV | 28 Apr 1515 - 1930 | 10 | 21.25 | 896046 |  | TF | FOT | DV | 3680 | HAD RESTRICTION @ 3680' ( 02 STDS AFTER 7" LNR HRG), PICK UP STRING, ENGAGED TDS & WASH DOWN- NOT ABLE TO PASS.
436 | 04/30/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 23.5 | 413.75 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
442 | 04/30/2022 | DQ-47 | KHRS-1416 | BAW | 30 Apr 0945 - 2045 | 11 | 11 | 896164 |  | TF | FOT | WLT | 7550 | HAD VERY POOR LOGGING DATA QUALITY WHILE LOGGING TOP & BOTTOM INTERVALS IN GAS AQUSITION MODE.
447 | 04/30/2022 | ED-85A | ZULF-2062 | SDM | 30 Apr 1230 - 1730 | 3.5 | 3.5 | 896144 |  | DD | AINC | BHA | 4040 | ENCOUNTER SEVERAL TIGHT SPOTS FROM 3700 FT. UNABLE TO PASS. DUE TO EXCESSIVE DOGLEG AND NOT FOLLOWING THE PLAN
449 | 04/30/2022 | HI-9 | QTIF-557 | AP2 | 28 Apr 0500 - 0500 | 24 | 72 | 896076 |  | WO | WPD3 | NA | 0 | RIG IS WAITING ON WELL SERVICES BARGE ARABIYAH-3 TO INSTALL ISOLATION PLUGS AND DEPRESSURIZE QTIF-71, 557/558 PLATFORM.
451 | 04/30/2022 | NBR-196S | SDGM-1226 | RIG | 30 Apr 1400 - 1600 | 2 | 2 | 896163 |  | RR | FOT | EDR | 12015 | RACK BACK STANDS & INSTALL SAFETY VALVE AND CIRCULATION SWEDGE, ROTATE STRING IN SLIPS SLOWLY & CIRCULATE AT 300 GPM WHILE REPAIR RIG WEIGHT INDICATOR.
453 | 04/30/2022 | NBR-654S | HRDH-2210 | FMC | 29 Apr 1100 - 1600 | 11 | 27.5 | 896109 |  | JF | HERR | CTRQ | 14431 | UNABLE TO DRIFT 4 1/2" LINER DUE TO DAMAGE CAUSED BY FRANKS POWER TONG
455 | 04/30/2022 | PA-622S | AFLJ-4 | ARM | 24 Apr 1000 - 0400 | 23 | 156 | 895875 |  | STUK | PSSW | NA | 6896 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION.
457 | 04/30/2022 | PA-861S | HRDH-1060 | ARM | 29 Apr 1700 - 1645 | 11.75 | 23.75 | 896139 |  | STUK | STBH | RM | 11784 | WHILE RIH W/ REAMING BHA STRING GOT STUCK AT THE OPEN HOLE WHIPSTOCK
459 | 04/30/2022 | PN-9 | MRJN-91 | BHI | 30 Apr 0200 - 0500 | 3 | 3 | 896012 |  | LROP | IDPR | BHA | 9223 | SLOW ROP, EQUIVALENT EXCESSIVE HRS FOR DAILY ROP LESS THAN 35 FPH.
461 | 04/30/2022 | SINO-12L | HRDH-1454 | TK1 | 28 Apr 2130 - 0500 | 17 | 48.5 | 896069 |  | STUK | STBG | TBG | 8710 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION
463 | 04/30/2022 | SINO-27N | UTMN-432 | SCB | 30 Apr 1545 - 0500 | 13.25 | 13.25 | 896010 |  | TF | FOT | BP | 1500 | SLB COULD'T RETREIVE RBP 4.5" SIMPLUS PLUG.
473 | 04/30/2022 | SINO-32L | SHYB-570 | BCM | 29 Apr 2300 - 0700 | 2 | 8 | 896105 |  | CMT | HFFT | NA | 902 | WHILE 24" CSG CMT JOB, CMT WEIGHT NOT MAINTAINED 122 PCF AS PG, FLUCTUATED BETWEEN 105-122, SWITCHED TO THE BACKUP CEMENT UNIT BUT HAD SAME PROBLEM, DECIDED TO CIRCULATE OUT CMT SLURRY.
478 | 04/30/2022 | SND-1501 | UTMN-567 | BC | 26 Apr 1115 - 0500 | 21.5 | 111.25 | 895984 |  | TF | FOT | PKR | 0 | AFTER DISPLACED WELL TO DIESEL OBERVED WELL NOT STATIC W/ STEADY RETURNS
480 | 04/30/2022 | SNF036 | MRJN-901 | RIG | 30 Apr 2330 - 0130 | 2 | 2 | 896112 |  | BOP | FOT | BOP | 0 | WHILE CONDUCTING BOP TEST HAD LEAKS FROM HCR VALVE UPPER CHOKE LINE, HCR VALVE UPPER KILL LINE AND MANUAL VALVE#11.
482 | 04/30/2022 | SP-101 | ABQQ-710 | WI1 | 27 Apr 1100 - 0500 | 24 | 90 | 896019 |  | TF | FOT | FISHT | 2398 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG.
484 | 04/30/2022 | SP-161 | HWYH-680 | ARM | 30 Apr 2300 - 0500 | 6 | 6 | 896146 |  | STUK | STBH | CORC | 7185 | CORING BHA STRING GOT STUCK AFTER BREAKING THE CORE.
486 | 04/30/2022 | SP-259 | HZEM-160402 | RIG | 30 Apr 1430 - 0430 | 14 | 14 | 896113 |  | RR | FOT | TDS | 6708 | OVERHEAT ON TDS VFD
487 | 04/30/2022 | SP-260 | HZEM-161012 | BHI | 29 Apr 1015 - 1845 | 13.75 | 32.5 | 896158 |  | BHA | FOT | RSS | 16114 | BAD COMMUNICATION FROM RSS, TROUBLE SHOOT, NO SUCCESS. DECIDE TO POOH AND CHANGE BAKER TOOLS.
489 | 04/30/2022 | SP-260 | HZEM-161012 | BHI | 30 Apr 0300 - 0445 | 1.75 | 1.75 | 896111 |  | BHA | FOT | RSS | 16856 | BAKER RSS DIRECTIONAL SENSOR SIGNAL IS LOST.
490 | 04/30/2022 | SP-260 | HZEM-161012 | BHI | 29 Apr 1015 - 1845 | 13.75 | 32.5 | 896158 |  | BHA | FOT | RSS | 16114 | BAD COMMUNICATION FROM RSS, TROUBLE SHOOT, NO SUCCESS. DECIDE TO POOH AND CHANGE BAKER TOOLS.
492 | 04/30/2022 | SP-262 | HZEM-140814 | BHI | 28 Apr 1300 - 1000 | 5 | 45 | 896002 |  | BHA | FOT | MWD | 16449 | BAKER TOOLS LOST MWD SIGNAL
494 | 04/30/2022 | SSA-101 | QTIF-785 | ARN | 29 Apr 0330 - 0400 | 18 | 19.5 | 896159 |  | BHS | CWEL | NA | 1701 | STRING STUCK AT 1701', WORK ON STRING,SPOT 100 BBL CITRIC ACID PILL,GOT FREE
496 | 04/30/2022 | SSA-102 | QTIF-696 | RIG | 30 Apr 0300 - 0500 | 2 | 2 | 896114 |  | RR | FOT | TDS | 16762 | TDS ENCODER FAILED.
498 | 04/30/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 24 | 315.5 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
500 | 04/30/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0500 | 24 | 203.5 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL.
502 | 04/30/2022 | STY-038 | ZULF-2083 | HCO | 30 Apr 0300 - 0500 | 2 | 2 | 896011 |  | TF | FOT | SEAL | 5497 | HALLIBURTON UNSUCCESSFULLY ATTEMPT TO STING RATCH-LATCH INTO VHR PACKER
504 | 04/01/2022 | 088TE | QTIF-176 | RIG | 01 Apr 0230 - 0500 | 2.5 | 2.5 | 894610 |  | RR | FOT | PSYS | 3650 | WHILE CIRC HAD BLACKOUT & COMPLETE SHUT DOWN OF RIG ENGINE FOR 20 MIN
506 | 04/01/2022 | ADC-17 | ZULF-1214 | RIG | 31 Mar 1800 - 0645 | 1.75 | 12.75 | 894549 |  | RR | FOT | MPMP | 3173 | REPLACING DISCHARGE MODULE OF MP-1
508 | 04/01/2022 | ADC-50 | SFNY-1177 | ARM | 28 Mar 1230 - 0500 | 24 | 112.5 | 894353 |  | LCIR | UVLC | NA | 4190 | AFTER DISPLACING 72 PCF WBM WITH 88 PCF OBM, WE OBSERVED TOTAL MUD LOSSES.
512 | 04/01/2022 | ADC-55L | UTMN-3199 | TK3 | 01 Apr 1830 - 2030 | 2 | 2 | 894629 |  | JF | HERR | NA | 6330 | REPEATED BOP PRESSURE TESTS DONE OFF LINE WITH NO BLEED OFF PRESSURE SIGNS RECORDED ON CHART
514 | 04/01/2022 | ADC-55L | UTMN-3199 | RIG | 01 Apr 1130 - 1830 | 7 | 7 | 894608 |  | RR | FOT | MPMP | 6330 | PT IBOP. OBSERVED LEAKING IBOP
515 | 04/01/2022 | ADC-55L | UTMN-3199 | TK3 | 01 Apr 1830 - 2030 | 2 | 2 | 894629 |  | JF | HERR | NA | 6330 | REPEATED BOP PRESSURE TESTS DONE OFF LINE WITH NO BLEED OFF PRESSURE SIGNS RECORDED ON CHART
520 | 04/01/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0500 | 24 | 86.5 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
521 | 04/01/2022 | ADC-62L | ANDR-743 | ARN | 01 Apr 1700 - 0500 | 12 | 12 | 894609 |  | TF | FOT | VSAT | 8875 | LOST COMMUNICATION WITH WELLLINK DUE TO VSAT SOFTWARE UPDATE.
523 | 04/01/2022 | ADC-62L | ANDR-743 | SDM | 31 Mar 1600 - 1545 | 10.25 | 23.25 | 894587 |  | BHA | FOT | LWD | 8869 | HAD INTERMITTENT DATA FROM MICROSCOPE RESISTIVITY IMAGE
524 | 04/01/2022 | ADC-62L | ANDR-743 | ARN | 01 Apr 1700 - 0500 | 12 | 12 | 894609 |  | TF | FOT | VSAT | 8875 | LOST COMMUNICATION WITH WELLLINK DUE TO VSAT SOFTWARE UPDATE.
526 | 04/01/2022 | ADC-67L | UTMN-3156 | TK3 | 29 Mar 1315 - 2330 | 18.5 | 82.25 | 894387 |  | LCIR | CFFM | MDCAP | 6652 | WHILE DRILLING 12" HOLE ENCOUNTERED LOSSES
528 | 04/01/2022 | ADES-40 | ANDR-469 | RIG | 01 Apr 0100 - 0500 | 4 | 4 | 894647 |  | RR | FOT | RWCS | 0 | PT BOP, OBSERVED PRESSURE NOT HOLDING.
530 | 04/01/2022 | ADM-261 | MRJN-137 | RIG | 01 Apr 1700 - 1745 | .75 | .75 | 894649 |  | RR | FOT | MPMP | 7015 | WASH RIG MUD PUMP SWAB AND LINER.
532 | 04/01/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 22.75 | 181.75 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
534 | 04/01/2022 | ARO-3003 | SFNY-1740 | RIG | 01 Apr 0830 - 1030 | 2 | 2 | 894607 |  | JF | XTRI | CTRQ | 1154 | EXCESSIVE TIME TO RUN 18-5/8" CSG.
535 | 04/01/2022 | ARO-3004 | MRJN-2060 | SBT | 31 Mar 0600 - 0500 | 21 | 44 | 894566 |  | TF | FOT | BIT | 5505 | UNABLE TO DRILL AHEAD 12.25" HOLE, POOH AND FOUND PDC BIT HAD A BROKEN OFF BLADE.
537 | 04/01/2022 | ARO-3004 | MRJN-2060 | RIG | 01 Apr 1315 - 1615 | 3 | 3 | 894555 |  | RR | FOT | TDS | 5505 | HAD TO STOP MILLING OPERATIONS DUE TO TDS ENCODER ISSUE, REPLACED SAME WITH NEW ONE AND RESUME MILLING.
538 | 04/01/2022 | ARO-3004 | MRJN-2060 | SBT | 31 Mar 0600 - 0500 | 21 | 44 | 894566 |  | TF | FOT | BIT | 5505 | UNABLE TO DRILL AHEAD 12.25" HOLE, POOH AND FOUND PDC BIT HAD A BROKEN OFF BLADE.
540 | 04/01/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0815 | 3.25 | 328 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
542 | 04/01/2022 | DPS-4 | MDRK-54 | RIG | 01 Apr 0830 - 1300 | 4.5 | 4.5 | 894645 |  | RR | FOT | DWKS | 6656 | CHANGED DRAWWORKS AUXILLIARY BRAKE DUE TO LOW PERFORMANCE.
544 | 04/01/2022 | DPS-44 | UTMN-3151 | ARM | 28 Mar 0500 - 0500 | 24 | 88.5 | 894325 |  | TH | NARW | NA | 3032 | OBSERVED TIGHT SPOT AND CASING DID NOT PASS THROUGH. TRIED SEVERAL TIMES NO SUCCESS.
546 | 04/01/2022 | DQ-48 | KHRS-1411 | HCO | 31 Mar 0030 - 0500 | 24 | 28.5 | 894398 |  | TF | FOT | SEAL | 12163 | WHILE SET THE HAL MFR PKRS, ATTEMPTED TO PRESSURE UP THE STRING, OBSERVED PRESSURE DROPPING CONTINUOUSLY BEFORE THE PRESSURE REACHED 400 PSI. TROUBLESHOOTING HAL ICV'S.
548 | 04/01/2022 | DQ-50L | HRDH-1492 | SCP | 01 Apr 0700 - 1100 | 4 | 4 | 894625 |  | TF | FOT | PDHMS | 3370 | AFTER INSTALLING THE PDHMS#4, OBSERVED THAT IT IS NOT READING THE ANNULUS DATA.
550 | 04/01/2022 | ED-85A | ZULF-2060 | RIG | 31 Mar 1745 - 0500 | 24 | 35.25 | 894547 |  | UPRA | OTH | NA | 0 | OBSERVED LEAK BETWEEN SHEAR RAM BONNET AND BOP BODY. WHILE PRESSURE TEST WELLHEAD BY CUP TESTER
552 | 04/01/2022 | EXL-IA | SFNY-4050 | ARM | 01 Apr 1200 - 0500 | 17 | 17 | 894646 |  | TF | FOT | FISHT | 236 | OBSERVED ONE CUTTER BLADE MISSING FROM 30''CONDUCTOR CUTTER TOOL AFTER POH. ATTEMPT TO FISH WITH MAGNET.
554 | 04/01/2022 | HI-4 | BRRI-780 | RIG | 01 Apr 1330 - 2000 | 6.5 | 6.5 | 894628 |  | BOP | LHFL | RWCS | 0 | ATTEMPTED TO TEST ANNULAR PREVENTER, FOUND SAME LEAKING
556 | 04/01/2022 | MP-1 | SFNY-994 | SDM | 01 Apr 0500 - 2300 | 18 | 18 | 894399 |  | BHA | FOT | LWD | 1500 | ELECTRICAL COMMUNICATION ISSUE ON LWD TOOLS BELOW MWD TOOL.
558 | 04/01/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 0500 | 24 | 142.5 | 894425 |  | LCIR | UVLC | NA | 8416 | ENCOUNTERED TOTAL LOSSES AT 8,416' WHILE ROTARY DRILLING 12" HOLE SECTION (BASE LOWER FADHILI RESERVOIR) FRACTURE /28' FORMATION CAVERN/VOID.
560 | 04/01/2022 | PA-218S | QTIF-515 | BHI | 01 Apr 1300 - 0045 | 4.75 | 4.75 | 894605 |  | BHA | FOT | MWD | 18990 | HAD NOISY SIGNAL ON LWD TOOL.
565 | 04/01/2022 | SINO-22 | BRRI-381 | ARM | 01 Apr 1830 - 0030 | 6 | 6 | 894552 |  | WO | STOP | NA | 13171 | STOP DRILLING DUE TO V-SAT COMMUINCATION ISSUE PRVENTING DATA TRASMISSION TO GOC.
567 | 04/01/2022 | SINO-28L | SHYB-709 | RIG | 01 Apr 0900 - 1330 | 4.5 | 4.5 | 894556 |  | RR | LHFL | HSYS | 4770 | LEAK ON 4"-1502 HAMMER UNION CONNECTION OF STAND PIPE MANIFOLD.
569 | 04/01/2022 | SND-2001 | UTMN-2329 | GOC | 01 Apr 1115 - 1300 | 1.75 | 1.75 | 894627 |  | WO | MATL | NA | 3718 | EXCESSIVE TIME TO TROUBLESHOOT THE POWER UNIT FOR ALGAITH POWER TONG.
571 | 04/01/2022 | SND-2008 | HRDH-2190 | WDS | 01 Apr 1530 - 0500 | 13.5 | 13.5 | 894554 |  | BHA | FOT | RSS | 11000 | OBSERVE SLIGHT/GRADUAL PR DROP, SUSPECT WFD RSS WASHOUT. POH
573 | 04/01/2022 | SSA-5820 | SDGM-1215 | RIG | 31 Mar 0430 - 1930 | 10.5 | 11 | 894568 |  | RR | FOT | TDS | 11100 | TDS ENCODER FAILURE, LOSE RPM, AND HAVE TO P/U AND RESTART.
575 | 04/01/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 529 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
577 | 04/01/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 889.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
578 | 04/02/2022 | 088TE | QTIF-176 | SDM | 02 Apr 0330 - 0430 | 1 | 1 | 894631 |  | BHA | FOT | LWD | 5126 | HAD GAP ON GR LOG F/ 4884' TO 4980' WHILE DRLG.
580 | 04/02/2022 | 088TE | QTIF-176 | RIG | 01 Apr 0230 - 0800 | 3 | 5.5 | 894610 |  | RR | FOT | PSYS | 3650 | WHILE CIRC HAD BLACKOUT & COMPLETE SHUT DOWN OF RIG ENGINE FOR 20 MIN, TROUBLESHOOT TO START ENGINES.
581 | 04/02/2022 | 088TE | QTIF-176 | SDM | 02 Apr 0330 - 0430 | 1 | 1 | 894631 |  | BHA | FOT | LWD | 5126 | HAD GAP ON GR LOG F/ 4884' TO 4980' WHILE DRLG.
586 | 04/02/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0500 | 13.25 | 99.75 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
588 | 04/02/2022 | ADC-62L | ANDR-743 | ARN | 01 Apr 1700 - 0745 | 2.75 | 14.75 | 894609 |  | TF | FOT | VSAT | 8875 | LOST COMMUNICATION WITH WELLLINK DUE TO VSAT SOFTWARE UPDATE.
590 | 04/02/2022 | ADC-64L | UTMN-2310 | SDM | 01 Apr 1930 - 0500 | 12.5 | 22 | 894630 |  | BHA | FOT | LWD | 17156 | LOST SIGNAL ON LWD (NEUTRON & DENSITY IMAGE NOT WORKING ), FINAL DECISION POOH & CHANGE LWD TOOL
592 | 04/02/2022 | ADES-40 | ANDR-469 | RIG | 01 Apr 0100 - 0730 | 2.5 | 6.5 | 894647 |  | RR | FOT | RWCS | 0 | PT BOP, OBSERVED PRESSURE NOT HOLDING.
594 | 04/02/2022 | ADM-510 | ABSF-224 | SPS | 02 Apr 1545 - 0500 | 13.25 | 13.25 | 894562 |  | DD | AINC | BHA | 8568 | SPERRY RSS UNABLE TO DROP INCLINATION.
596 | 04/02/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 23 | 204.75 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
598 | 04/02/2022 | ARO-3004 | MRJN-2060 | SBT | 31 Mar 0600 - 0500 | 24 | 68.5 | 894566 |  | TF | FOT | BIT | 5505 | UNABLE TO DRILL AHEAD 12.25" HOLE, POOH AND FOUND PDC BIT HAD A BROKEN-OFF BLADE.
600 | 04/02/2022 | DPS-74 | NJYN-54 | ARM | 02 Apr 0700 - 0500 | 22 | 22 | 894611 |  | STUK | STDP | DP | 15550 | WHILE MAKE CONNECTION @15,550' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
602 | 04/02/2022 | DQ-48 | KHRS-1411 | BC | 31 Mar 0030 - 0500 | 24 | 52.5 | 894398 |  | TF | FOT | SEAL | 12163 | WHILE SET HAL MFR PKRS, ATTEMPTED TO PRESSURE UP THE STRING, OBSERVED PRESSURE DROPPING CONTINUOUSLY BEFORE THE PRESSURE REACHED 400 PSI. TROUBLESHOOTING HAL ICV'S & PT EACH ASSEMBLY, GOT BAKER MIV LEAKING.
604 | 04/02/2022 | ED-85A | ZULF-2060 | RIG | 31 Mar 1745 - 0500 | 24 | 59.25 | 894547 |  | UPRA | OTH | NA | 0 | OBSERVED LEAK BETWEEN SHEAR RAM BONNET AND BOP BODY. WHILE PRESSURE TEST WELLHEAD BY CUP TESTER
606 | 04/02/2022 | ENS-108 | SFNY-1720 | SDM | 02 Apr 2230 - 0500 | 6.5 | 6.5 | 894561 |  | BHA | FOT | MWD | 4016 | LOST SLB MWD/GR SIGNAL.
608 | 04/02/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 0500 | 24 | 166.5 | 894425 |  | LCIR | UVLC | NA | 8416 | ENCOUNTERED TOTAL LOSSES AT 8,416' WHILE ROTARY DRILLING 12" HOLE SECTION (BASE LOWER FADHILI RESERVOIR) FRACTURE /28' FORMATION CAVERN/VOID.
610 | 04/02/2022 | PA-218S | QTIF-515 | RIG | 02 Apr 1630 - 2315 | 6.75 | 6.75 | 894559 |  | RR | FOT | TDS | 19814 | HAD LEAK FROM WASH PIPE.
612 | 04/02/2022 | RBP-50A | KARN-51 | RIG | 02 Apr 1600 - 2145 | 5.75 | 5.75 | 894653 |  | RR | FOT | ACDC | 11296 | RIG CREW TROUBLE SHOOT RIG POWER SYSTEMS
616 | 04/02/2022 | SND-2001 | UTMN-2329 | GOC | 01 Apr 1115 - 1000 | 4 | 5.75 | 894627 |  | WO | MATL | NA | 3718 | EXCESSIVE TIME TO TROUBLESHOOT THE POWER UNIT FOR ALGAITH POWER TONG.
618 | 04/02/2022 | SND-2001 | UTMN-2329 | GOC | 02 Apr 2330 - 0000 | .5 | .5 | 894612 |  | TF | XTTE | CRT | 6545 | EXCESS TIME TO RELEASE CRT FROM CSG JT.
619 | 04/02/2022 | SND-2001 | UTMN-2329 | GOC | 01 Apr 1115 - 1000 | 4 | 5.75 | 894627 |  | WO | MATL | NA | 3718 | EXCESSIVE TIME TO TROUBLESHOOT THE POWER UNIT FOR ALGAITH POWER TONG.
621 | 04/02/2022 | SND-2008 | HRDH-2190 | WDS | 01 Apr 1530 - 1700 | 9.75 | 23.25 | 894554 |  | BHA | FOT | RSS | 11000 | OBSERVE SLIGHT/GRADUAL PR DROP, SUSPECT WFD RSS WASHOUT. POH
622 | 04/02/2022 | SNF036 | MRJN-901 | RIG | 02 Apr 1130 - 0500 | 17.5 | 17.5 | 894558 |  | RR | FOT | MPMP | 5790 | WHILE DRILLING OBSERVED MUD PUMP #1 & PUMP #3 FAILURE, POOH TO SHOE,CHANGE PUMP #3 SUCTION MANIFOLD & GASKET & PUMP #1 DISCHARGE MANIFOLD, GASKET & MODULES.
624 | 04/02/2022 | SNF036 | MRJN-901 | RIG | 02 Apr 0500 - 0600 | 1 | 1 | 894557 |  | RR | FOT | MPMP | 5702 | OBSERVED MUD PUMP #3 PRESSURE FLACULATION, TROUBLESHOOT PROBLEM, OK.
625 | 04/02/2022 | SNF036 | MRJN-901 | RIG | 02 Apr 1130 - 0500 | 17.5 | 17.5 | 894558 |  | RR | FOT | MPMP | 5790 | WHILE DRILLING OBSERVED MUD PUMP #1 & PUMP #3 FAILURE, POOH TO SHOE,CHANGE PUMP #3 SUCTION MANIFOLD & GASKET & PUMP #1 DISCHARGE MANIFOLD, GASKET & MODULES.
627 | 04/02/2022 | SP-260 | HZEM-161002 | BHI | 02 Apr 1130 - 0500 | 14.75 | 14.75 | 894560 |  | BHA | FOT | MWD | 9550 | BKR MWD FAILED
629 | 04/02/2022 | SSA-201 | HRDH-1818 | SCD | 02 Apr 1500 - 2230 | 7.5 | 7.5 | 894652 |  | SURV | FOT | GYRO | 12369 | OBSERVE LOST COMMUNICATION FROM GYRO TOOL TO SURFACE. POOH WITH GYRO TOOL TO SURFACE AND TROUBLESHOOT ACCORDING TO SCIENTIFIC DRILLING PROCEDURES
631 | 04/02/2022 | SSA-5820 | SDGM-1215 | RIG | 02 Apr 1630 - 0445 | 12.25 | 12.25 | 894651 |  | RR | FOT | CSYS | 11598 | WHILE DRILLING THE GOSSENECK LEAKED.
633 | 04/02/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 553 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
635 | 04/02/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 913.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
637 | 04/03/2022 | ADC-31 | SDGM-1192 | RIG | 03 Apr 2230 - 0500 | 6.5 | 6.5 | 894632 |  | RR | FOT | DWKS | 6976 | DRAW WORK BREAK ISSUE
639 | 04/03/2022 | ADC-50 | SFNY-1177 | ARM | 28 Mar 1230 - 0500 | 17.75 | 154.25 | 894353 |  | LCIR | UVLC | NA | 4190 | AFTER DISPLACING 72 PCF WBM WITH 88 PCF OBM, WE OBSERVED TOTAL MUD LOSSES.
640 | 04/03/2022 | ADC-55L | UTMN-3199 | RIG | 03 Apr 2230 - 0500 | 6.5 | 6.5 | 894616 |  | RR | FOT | MPMP | 6408 | OBSERVED LEAKING SUCTION LINE ISOLATION VALVE
642 | 04/03/2022 | ADC-55L | UTMN-3199 | RIG | 03 Apr 1615 - 2000 | 3.75 | 3.75 | 894615 |  | RR | FOT | MPMP | 6340 | WHILE DRILLING OBSERVED MUD PUMP TAKING AIR IN SUCTION
643 | 04/03/2022 | ADC-55L | UTMN-3199 | RIG | 03 Apr 2230 - 0500 | 6.5 | 6.5 | 894616 |  | RR | FOT | MPMP | 6408 | OBSERVED LEAKING SUCTION LINE ISOLATION VALVE
648 | 04/03/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0500 | 24 | 119.75 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
650 | 04/03/2022 | ADC-62L | ANDR-743 | SDM | 03 Apr 0330 - 0500 | 1.5 | 1.5 | 894633 |  | BHA | FOT | MWD | 10157 | ** HAD INTERMITTENT COMMUNICATION BETWEEN RSS AND MWD WHILE DRILLING, COMMUNICATION RESUME WHEN DRILL OFF AND PICK STRING OFF BOTTOM, TROUBLESHOOT WITH VERY LOW ROP AND DIFFERENT RPM, PUMPED LOW/HI VIS SWEEP, STILL LOSING COMMUNICATION ON BTM, DECIDED TO POOH TO CHANGE TOOLS.
652 | 04/03/2022 | ADC-64L | UTMN-2310 | SDM | 01 Apr 1930 - 0200 | 21 | 43 | 894630 |  | BHA | FOT | LWD | 17156 | LOST SIGNAL ON LWD (NEUTRON & DENSITY IMAGE NOT WORKING ), FINAL DECISION POOH & CHANGE LWD TOOL
654 | 04/03/2022 | ADM-510 | ABSF-224 | SPS | 02 Apr 1545 - 0245 | 21.25 | 34.5 | 894562 |  | DD | AINC | BHA | 8568 | SPERRY RSS UNABLE TO DROP INCLINATION. POOH & CHANGE OUT RSS
656 | 04/03/2022 | ADM-511 | MRJN-799 | RIG | 03 Apr 0900 - 0930 | .5 | .5 | 894654 |  | RR | FOT | TDS | 4930 | BX ELEVATOR HYDRAULIC HOSE FAILURE
657 | 04/03/2022 | AOD-111 | MRJN-726 | BHI | 03 Apr 1145 - 0500 | 17.25 | 17.25 | 894666 |  | BHA | FOT | MWD | 10114 | LOST SIGNAL FROM MWD PULSER, ATTEMPT TO TROUBLESHOOT MWD PULSER WITHOUT SUCCESS.
659 | 04/03/2022 | AOD-111 | MRJN-726 | BHI | 03 Apr 0715 - 0800 | .75 | .75 | 894665 |  | BHA | FOT | MWD | 9958 | OBSERVED INTERMITTENT SINGNAL FROM MWD PULSER.
660 | 04/03/2022 | AOD-111 | MRJN-726 | BHI | 03 Apr 1145 - 0500 | 17.25 | 17.25 | 894666 |  | BHA | FOT | MWD | 10114 | LOST SIGNAL FROM MWD PULSER, ATTEMPT TO TROUBLESHOOT MWD PULSER WITHOUT SUCCESS.
662 | 04/03/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 24 | 228.75 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
664 | 04/03/2022 | ARO-3004 | MRJN-2060 | SBT | 31 Mar 0600 - 0500 | 24 | 92.5 | 894566 |  | TF | FOT | BIT | 5505 | UNABLE TO DRILL AHEAD 12.25" HOLE, POOH AND FOUND PDC BIT HAD A BROKEN-OFF BLADE.
666 | 04/03/2022 | DPS-74 | NJYN-54 | ARM | 02 Apr 0700 - 0030 | 19.5 | 41.5 | 894611 |  | STUK | STDP | DP | 15550 | WHILE MAKE CONNECTION @15,550' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
671 | 04/03/2022 | DQ-48 | KHRS-1411 | BC | 31 Mar 0030 - 0500 | 24 | 76.5 | 894398 |  | TF | FOT | SEAL | 12163 | WHILE SET HAL MFR PKRS, ATTEMPTED TO PRESSURE UP THE STRING, OBSERVED PRESSURE DROPPING CONTINUOUSLY BEFORE THE PRESSURE REACHED 400 PSI. TROUBLESHOOTING HAL ICV'S & PT EACH ASSEMBLY, GOT BAKER MIV LEAKING.
673 | 04/03/2022 | ED-85A | ZULF-2060 | RIG | 31 Mar 1745 - 0500 | 24 | 83.25 | 894547 |  | UPRA | OTH | NA | 0 | OBSERVED LEAK BETWEEN SHEAR RAM BONNET AND BOP BODY. WHILE PRESSURE TEST WELLHEAD BY CUP TESTER
675 | 04/03/2022 | ENS-108 | SFNY-1720 | SDM | 02 Apr 2230 - 1845 | 13.75 | 20.25 | 894561 |  | BHA | FOT | MWD | 4016 | LOST SLB MWD/GR SIGNAL.
677 | 04/03/2022 | HI-9 | MRJN-257 | BC | 03 Apr 0900 - 0500 | 20 | 20 | 894656 |  | TF | FOT | HVLV | 0 | WHILE FUNCTION TESTING BAKER 3-1/2" ICV VALVE TO OPEN POSITION AND DURING THE 5TH CYCLE, ICV VALVE STOP MOVING FURTHER TO OPEN POSITION. TROUBLE SHOOT AND MADE SEVERAL ATTEMPTS TO CYCLE THE VALVE, WITHOUT SUCCESS. 3-1/2" ICV VALVE NEED TO BE REPLACE, WAITING ON BAKER REPLACEMENT 3-1/2" ICV ASSY. (LOST TIME BAKER COMPLETION)
679 | 04/03/2022 | MP-1 | SFNY-994 | RIG | 03 Apr 0030 - 0200 | 1.5 | 1.5 | 894659 |  | RR | FOT | TDS | 8490 | DUE TO OVER TORQUE TDS SAVER SUB BREAK OUT FROM LOWER IBOP INSTEAD OF DP CONNECTION.
681 | 04/03/2022 | NA-393S | HWYH-1138 | SAM | 03 Apr 0100 - 0500 | 4 | 4 | 894660 |  | WO | WOTO | NA | 6767 | 9-5/8" SAMAA CSG SCRAPPER TWISTED OFF FROM ITS BODY WITHOUT ANY INDICATION (BAD QUALITY), 2' FROM SCRAPPER BODY LOST IN HOLE IN ADDITION TO 8-3/8" STRING MILL, JUNK BASKET, 8-3/8" FBM.
683 | 04/03/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 0500 | 24 | 190.5 | 894425 |  | LCIR | UVLC | NA | 8416 | ENCOUNTERED TOTAL LOSSES AT 8,416' WHILE ROTARY DRILLING 12" HOLE SECTION (BASE LOWER FADHILI RESERVOIR) FRACTURE /28' FORMATION CAVERN/VOID.
685 | 04/03/2022 | NBR-987S | ABTL-2 | RIG | 03 Apr 1515 - 1930 | 4.25 | 4.25 | 894658 |  | RR | FOT | TDS | 20213 | TOP DRIVE LINK TILT TROUBLESHOOT.
687 | 04/03/2022 | RBP-50A | KARN-51 | HWP | 02 Apr 0345 - 1200 | 7 | 8.25 | 894614 |  | TF | ISEQ | TPCH | 9391 | HALLIBURTON DPU DOUBLE ARM TOOL DID NOT PUNCH TUBING DUE TO LACK OF POWER THROUGH SLB WIRELINE.
692 | 04/03/2022 | SND-2007 | ADHN-370100 | RIG | 03 Apr 0200 - 0500 | 3 | 3 | 894661 |  | RR | FOT | TDS | 15626 | TROUBLE SHOOTING AUTO DRILLER SYSTEM WHILE CIRC AND RECP.
694 | 04/03/2022 | SNF036 | MRJN-901 | RIG | 02 Apr 1130 - 1230 | 7.5 | 25 | 894558 |  | RR | FOT | MPMP | 5790 | WHILE DRILLING OBSERVED MUD PUMP #1 & PUMP #3 FAILURE, POOH TO SHOE,CHANGE PUMP #3 SUCTION MANIFOLD & GASKET & PUMP #1 DISCHARGE MANIFOLD, GASKET & MODULES.
696 | 04/03/2022 | SP-260 | HZEM-161002 | BHI | 02 Apr 1130 - 0830 | 2.25 | 17 | 894560 |  | BHA | FOT | MWD | 9550 | BKR MWD FAILED
698 | 04/03/2022 | SP-261 | HZEM-162204 | SDM | 03 Apr 1915 - 0500 | 9.75 | 9.75 | 894617 |  | BHA | FOT | LWD | 12494 | LOST LWD SIGNAL WHILE DRILLING LATERAL SECTION.
700 | 04/03/2022 | SSA-5865 | ABJF-50 | RIG | 03 Apr 1330 - 1830 | 5 | 5 | 894655 |  | RR | FOT | DWKS | 9162 | DRAW WORKS DISK BREAK ENGAGED WHILE DRILLER EXTEND TDS LINK TILT TO RACK BACK STD.
702 | 04/04/2022 | ADC-31 | SDGM-1192 | RIG | 03 Apr 2300 - 1000 | 5 | 11 | 894632 |  | RR | FOT | DWKS | 6976 | DRAW WORK BREAK ISSUE
704 | 04/04/2022 | ADC-50 | SFNY-1177 | ARM | 28 Mar 1230 - 0500 | 24 | 178.25 | 894353 |  | LCIR | UVLC | NA | 4190 | AFTER DISPLACING 72 PCF WBM WITH 88 PCF OBM, OBSERVED TOTAL LOSSES. CUT DOWN MW TO 80 PCF OBM, AND PUMPED 1ST CMT PLUG, CURED LOSSES. DRILLED 3' NEW FORMATION, OBSERVED TOTAL LOSSES. SPOT 2ND, 3RD, AND 4TH CMT PLUGS, CURE LOSSES. DISPLACE TO 80 PCF WBM. DRILL 105' ADDITIONAL FT WITH MWD BHA, TOTAL LOSSES. SPOT 5TH AND 6TH CMT PLUGS, LOSSES REDUCED TO 55 BPH STATIC.
706 | 04/04/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0500 | 24 | 143.75 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
708 | 04/04/2022 | ADC-62L | ANDR-743 | SDM | 03 Apr 0330 - 0730 | 2.5 | 4 | 894633 |  | BHA | FOT | MWD | 10157 | HAD INTERMITTENT COMMUNICATION BETWEEN RSS AND MWD WHILE DRILLING, TROUBLESHOOT WITH VERY LOW ROP AND DIFFERENT RPM, PUMPED LOW/HI VIS SWEEP, STILL LOSING COMMUNICATION ON BTM.
710 | 04/04/2022 | ADM-339 | RBYN-55 | RIG | 04 Apr 1400 - 1630 | 2.5 | 2.5 | 894726 |  | RR | FOT | DRRK | 4123 | 4" DP WAS R/B IN DERRICK MANUALLY VERY CLOSE TO EACH OTHER DUE TO ISSUE WITH XY RACKER. DURING RIH WITH 6-1/8" BHA ON 4" DP, RIG COULD NOT USE RACKER CAUSE OF THIGHT CLEARANCE BETWEEN 4" DP STD'S.
712 | 04/04/2022 | ADM-510 | ABSF-224 | SPS | 04 Apr 1300 - 0500 | 16 | 16 | 894687 |  | DD | AINC | BHA | 8654 | SPERRY RSS UNABLE TO DROP INCLINATION. POOH FOR MUD MOTOR ASSLY
713 | 04/04/2022 | ADM-511 | MRJN-799 | BHT | 04 Apr 1445 - 0500 | 14.25 | 14.25 | 894729 |  | LROP | ETRQ | BIT | 5178 | UNABLE TO CONTINUE DRILLING AT 5178 FT MD - BHA BECAME STUCK ON BOTTOM - FREED BHA WITH JARRING - BACKREAMED ABOVE LZ - REAMED 8 FT FROM BOTTOM AND COULD NOT CONTINUE DUE TO HIGH TORQUE - PULLED OUT OF HOLE - BIT SHOULDER VERY BAD CONDITION
715 | 04/04/2022 | ADM-511 | MRJN-799 | RIG | 04 Apr 0915 - 1100 | 1.75 | 1.75 | 894725 |  | RR | FOT | PSYS | 5121 | RIG ENGINES WENT OFFLINE DUE TO OVERHEATING CAUSED BY DEEP WELL PUMP MALFUNCTION
716 | 04/04/2022 | ADM-511 | MRJN-799 | BHT | 04 Apr 1445 - 0500 | 14.25 | 14.25 | 894729 |  | LROP | ETRQ | BIT | 5178 | UNABLE TO CONTINUE DRILLING AT 5178 FT MD - BHA BECAME STUCK ON BOTTOM - FREED BHA WITH JARRING - BACKREAMED ABOVE LZ - REAMED 8 FT FROM BOTTOM AND COULD NOT CONTINUE DUE TO HIGH TORQUE - PULLED OUT OF HOLE - BIT SHOULDER VERY BAD CONDITION
718 | 04/04/2022 | AOD-111 | MRJN-726 | BHI | 03 Apr 1145 - 0500 | 24 | 41.25 | 894666 |  | BHA | FOT | MWD | 10114 | LOST SIGNAL FROM MWD PULSER, ATTEMPT TO TROUBLESHOOT MWD PULSER WITHOUT SUCCESS.
720 | 04/04/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 1515 | 10.25 | 239 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
722 | 04/04/2022 | ARO-3004 | MRJN-2060 | SBT | 31 Mar 0600 - 1030 | 5.5 | 98 | 894566 |  | TF | FOT | BIT | 5505 | UNABLE TO DRILL AHEAD 12.25" HOLE, POOH AND FOUND PDC BIT HAD A BROKEN-OFF BLADE.
724 | 04/04/2022 | DPS-74 | NJYN-54 | ARM | 02 Apr 0700 - 0500 | 15.75 | 57.25 | 894611 |  | STUK | STDP | DP | 15550 | WHILE MAKE CONNECTION @15,550' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
729 | 04/04/2022 | DQ-48 | KHRS-1411 | BC | 31 Mar 0030 - 1300 | 8 | 82.5 | 894398 |  | TF | FOT | SEAL | 12163 | WHILE SET HAL MFR PKRS, ATTEMPTED TO PRESSURE UP THE STRING, OBSERVED PRESSURE DROPPING CONTINUOUSLY BEFORE THE PRESSURE REACHED 400 PSI. TROUBLESHOOTING HAL ICV'S & PT EACH ASSEMBLY, GOT BAKER MIV LEAKING.
731 | 04/04/2022 | ED-85A | ZULF-2060 | RIG | 31 Mar 1745 - 0500 | 24 | 107.25 | 894547 |  | UPRA | OTH | NA | 0 | OBSERVED LEAK BETWEEN SHEAR RAM BONNET AND BOP BODY. WHILE PRESSURE TEST WELLHEAD BY CUP TESTER
733 | 04/04/2022 | EXL-IA | SFNY-4240 | RIG | 04 Apr 0930 - 0500 | 19.5 | 19.5 | 894705 |  | UPRA | PPMP | NA | 0 | WHILE JACKING DOWN DURING RM JACKING SYSTEM FAILED. TWO TEETH BROKEN & ONE DAMAGED FROM THE PORT LEG K CORD. WORKING WITH ARO SHOREBASE TO CORRECT.
735 | 04/04/2022 | HI-9 | MRJN-257 | BC | 03 Apr 0900 - 0500 | 24 | 44 | 894656 |  | TF | FOT | HVLV | 0 | WHILE FUNCTION TESTING BAKER 3-1/2" ICV VALVE TO OPEN POSITION AND DURING THE 5TH CYCLE, ICV VALVE STOP MOVING FURTHER TO OPEN POSITION. TROUBLE SHOOT AND MADE SEVERAL ATTEMPTS TO CYCLE THE VALVE, WITHOUT SUCCESS. 3-1/2" ICV VALVE NEED TO BE REPLACE, WAITING ON BAKER REPLACEMENT 3-1/2" ICV ASSY. (LOST TIME BAKER COMPLETION)
737 | 04/04/2022 | HWU-1 | HMYM-450812 | RIG | 03 Apr 1900 - 1400 | 9 | 19 | 894685 |  | RR | IHFL | HSYS | 0 | HYDRAULIC SYSTEM NOT ADJUSTED PROPERLY FOR TASK AT HAND
739 | 04/04/2022 | NA-393S | HWYH-1138 | SAM | 03 Apr 0100 - 0500 | 24 | 28 | 894660 |  | BHA | FOT | WBCL | 6767 | 9-5/8" SAMAA CSG SCRAPPER TWISTED OFF FROM ITS BODY WITHOUT ANY INDICATION (BAD QUALITY), 2' FROM SCRAPPER BODY LOST IN HOLE IN ADDITION TO 8-3/8" STRING MILL, JUNK BASKET, 8-3/8" FBM.
741 | 04/04/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 0500 | 24 | 214.5 | 894425 |  | LCIR | UVLC | NA | 8416 | ENCOUNTERED TOTAL LOSSES AT 8,416' WHILE ROTARY DRILLING 12" HOLE SECTION (BASE LOWER FADHILI RESERVOIR) FRACTURE /28' FORMATION CAVERN/VOID.
743 | 04/04/2022 | NBR-654S | HRDH-2210 | RIG | 04 Apr 0230 - 0345 | 1.25 | 1.25 | 894727 |  | RR | FOT | TDS | 13655 | EXTRA TIME TO CHANGE WASH PIPE
745 | 04/04/2022 | PA-785S | QTIF-641 | WDS | 04 Apr 2000 - 2100 | 1 | 1 | 894686 |  | BHA | FOT | RSS | 0 | SHALLOW TEST FAIL FOR RSS
747 | 04/04/2022 | SINO-10 | JLDI-37 | RIG | 04 Apr 2115 - 2200 | .75 | .75 | 894688 |  | RR | FPMP | MPMP | 3886 | OBSERVED SURFACE PRESSURE DROP ON MUD PUMP
749 | 04/04/2022 | SND-2007 | ADHN-370100 | RIG | 03 Apr 0200 - 0815 | 3.25 | 6.25 | 894661 |  | RR | FOT | TDS | 15626 | TROUBLE SHOOTING AUTO DRILLER SYSTEM WHILE CIRC AND RECP.
751 | 04/04/2022 | SP-258 | HZEM-160612 | SDM | 04 Apr 1730 - 1930 | 2 | 2 | 894706 |  | DD | HERR | RSS | 11550 | EXESSIVE TIME TO DOWNLINK.
753 | 04/04/2022 | SP-261 | HZEM-162204 | SDM | 03 Apr 1915 - 0445 | 23.25 | 33 | 894617 |  | BHA | FOT | LWD | 12494 | LOST LWD SIGNAL WHILE DRILLING LATERAL SECTION.
755 | 04/04/2022 | SP-262 | HZEM-140804 | BHI | 04 Apr 1030 - 0500 | 18.5 | 18.5 | 894690 |  | BHA | FOT | MWD | 14557 | LOST ALL COMMUNICATION WITH BAKER RSS.
757 | 04/04/2022 | SSA-5859 | HRDH-1967 | RIG | 04 Apr 1330 - 1500 | 1.5 | 1.5 | 894707 |  | RR | FOT | EDR | 9514 | FAILURE ON DATA PRESSURE RECORD SYSTEM
759 | 04/04/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 16 | 16 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
761 | 04/04/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 601 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
763 | 04/04/2022 | T218 | UTMN-564 | RIG | 04 Apr 1800 - 2130 | 3.5 | 3.5 | 894745 |  | RR | FOT | TDS | 6526 | WHILE PASSING WINDOW WITH MMOT AND GYRO ORIENTATION, TDS BREAK FAILED TO HOLD STRING AT HIGH SIDE AND STRING BACKWARD, LOOSING HIGH SIDE POSITION
765 | 04/04/2022 | WCL-83 | MRJN-837 | ARM | 03 Apr 0215 - 0500 | 24 | 26.75 | 894667 |  | TH | PCPF | NA | 9420 | OBSERVED INCREASED DRAG WHILE RIH 7" LINER AT 9420'. POH THROUGH TIGHT SPOT WITH MAX 20K OVERPULL.
767 | 04/05/2022 | ADC-17 | ZULF-1218 | RIG | 05 Apr 0930 - 2015 | 10.75 | 10.75 | 894789 |  | RR | FOT | MPMP | 2268 | CONTROL CABLE IN MUD PUMPS HAD FAILURE. FAILURE CAUSED GROUND FAULT IN PLC SYSTEM
769 | 04/05/2022 | ADC-31 | SDGM-1192 | RIG | 03 Apr 2300 - 1330 | 1 | 13 | 894632 |  | RR | FOT | DWKS | 6976 | DRAW WORK BREAK FAILURE
771 | 04/05/2022 | ADC-50 | SFNY-1177 | ARM | 28 Mar 1230 - 0500 | 24 | 202.25 | 894353 |  | LCIR | UVLC | NA | 4190 | AFTER DISPLACING 72 PCF WBM WITH 88 PCF OBM, OBSERVED TOTAL LOSSES. CUT DOWN MW TO 80 PCF OBM, AND PUMPED 1ST CMT PLUG, CURED LOSSES. DRILLED 3' NEW FORMATION, OBSERVED TOTAL LOSSES. SPOT 2ND, 3RD, AND 4TH CMT PLUGS, CURE LOSSES. DISPLACE TO 80 PCF WBM. DRILL 105' ADDITIONAL FT WITH MWD BHA, TOTAL LOSSES. SPOT 5TH AND 6TH CMT PLUGS, LOSSES REDUCED TO 55 BPH STATIC.
776 | 04/05/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0500 | 24 | 167.75 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
778 | 04/05/2022 | ADES-173 | HRDH-2256 | RIG | 05 Apr 0100 - 0500 | 4 | 4 | 894790 |  | RR | FOT | CSYS | 14218 | OUTER SKIN OF KELLY HOSE PEELED, CHANGED SAME.
780 | 04/05/2022 | ADM-510 | ABSF-224 | SPS | 02 Apr 1545 - 0500 | 20.75 | 71.25 | 894562 |  | DD | AINC | BHA | 8568 | SPERRY RSS UNABLE TO DROP INCLINATION AS PER GOC REQUEST
782 | 04/05/2022 | AOD-111 | MRJN-726 | BHI | 03 Apr 1145 - 2030 | 15.5 | 56.75 | 894666 |  | BHA | FOT | MWD | 10114 | LOST SIGNAL FROM MWD PULSER, ATTEMPT TO TROUBLESHOOT MWD PULSER WITHOUT SUCCESS.
784 | 04/05/2022 | DPS-74 | NJYN-54 | ARM | 02 Apr 0700 - 1430 | 9.5 | 66.75 | 894611 |  | STUK | STDP | DP | 15550 | WHILE MAKE CONNECTION @15,550' STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, STRING GOT STUCK.
786 | 04/05/2022 | ED-85A | ZULF-2060 | RIG | 31 Mar 1745 - 0930 | 4.5 | 111.75 | 894547 |  | UPRA | OTH | NA | 0 | OBSERVED LEAK BETWEEN SHEAR RAM BONNET AND BOP BODY. WHILE PRESSURE TEST WELLHEAD BY CUP TESTER
788 | 04/05/2022 | ENSCO-54 | ABSF-31 | BAW | 05 Apr 1500 - 1830 | 3.5 | 3.5 | 894788 |  | TF | FOT | WLT | 0 | LOST COMMUNICATION TO BAKER MPC CUTTER, TROUBLESHOOT THE PROBLEM, POH TO CHECK THE TOOL.
790 | 04/05/2022 | EXL-IA | SFNY-4240 | RIG | 04 Apr 0930 - 1430 | 9.5 | 29 | 894705 |  | UPRA | PPMP | NA | 0 | WHILE JACKING DOWN DURING RM JACKING SYSTEM FAILED. TWO TEETH BROKEN & ONE DAMAGED FROM THE PORT LEG K CORD. WORKING WITH ARO SHOREBASE TO CORRECT.
792 | 04/05/2022 | HI-9 | MRJN-257 | BC | 03 Apr 0900 - 2200 | 17 | 61 | 894656 |  | TF | FOT | HVLV | 0 | WHILE FUNCTION TESTING BAKER 3-1/2" ICV VALVE TO OPEN POSITION AND DURING THE 5TH CYCLE, ICV VALVE STOP MOVING FURTHER TO OPEN POSITION. TROUBLE SHOOT AND MADE SEVERAL ATTEMPTS TO CYCLE THE VALVE, WITHOUT SUCCESS. 3-1/2" ICV VALVE NEED TO BE REPLACE, WAITING ON BAKER REPLACEMENT 3-1/2" ICV ASSY. (LOST TIME BAKER COMPLETION)
794 | 04/05/2022 | NA-393S | HWYH-1138 | SAM | 03 Apr 0100 - 0500 | 23.5 | 51.5 | 894660 |  | BHA | FOT | WBCL | 6767 | 9-5/8" SAMAA CSG SCRAPPER TWISTED OFF FROM ITS BODY WITHOUT ANY INDICATION (BAD QUALITY), 2' FROM SCRAPPER BODY LOST IN HOLE IN ADDITION TO 8-3/8" STRING MILL, JUNK BASKET, 8-3/8" FBM.
796 | 04/05/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 1945 | 14.75 | 229.25 | 894425 |  | LCIR | UVLC | NA | 8416 | ENCOUNTERED TOTAL LOSSES AT 8,416' WHILE ROTARY DRILLING 12" HOLE SECTION (BASE LOWER FADHILI RESERVOIR) FRACTURE /28' FORMATION CAVERN/VOID.
798 | 04/05/2022 | NBR-304S | HRDH-1952 | ARM | 05 Apr 2000 - 0500 | 9 | 9 | 894787 |  | BHA | IBHA | BHA | 5833 | POOH TO CHANGE BHA,RUN WITH VMWD AND BPL SUB
799 | 04/05/2022 | NBR-987S | ABTL-2 | RIG | 05 Apr 1200 - 1300 | 1 | 1 | 894769 |  | UPRA | OTH | NA | 0 | DRILL LINE IMPROPER WRAPING ON DRUM
801 | 04/05/2022 | NBR-987S | ABTL-2 | RIG | 05 Apr 0600 - 0715 | 1.25 | 1.25 | 894746 |  | UPRA | IRES | DWKS | 5500 | HAD TO SLIP DRILL LINE AGAIN DUE TO IMPROPER SLIP/CUT
802 | 04/05/2022 | NBR-987S | ABTL-2 | RIG | 05 Apr 1200 - 1300 | 1 | 1 | 894769 |  | UPRA | OTH | NA | 0 | DRILL LINE IMPROPER WRAPING ON DRUM
804 | 04/05/2022 | SCTD-1 | UTMN-3141 | RIG | 05 Apr 0130 - 0500 | 3.5 | 3.5 | 894791 |  | STUK | STBH | CTAC | 14043 | COIL STRING STUCK WHILE POH
806 | 04/05/2022 | SINO-18 | ADHN-10 | BAW | 05 Apr 1230 - 0500 | 16.5 | 16.5 | 894765 |  | TF | FOT | WLT | 15161 | WHILE ATTEMPT TO TAKE SAMPL#3 COMMUNICATION LOST FROM THE TOOL.
811 | 04/05/2022 | SND-2004 | BRRI-1148 | ARM | 05 Apr 1100 - 2030 | 4 | 4 | 894766 |  | BB | PCPF | NA | 246 | 28" BALLED UP BIT DUE TO STICKY FORMATION, TRIP OUT TO CLEAN THE BIT.
813 | 04/05/2022 | SP-106 | HRDH-3541 | WWL | 05 Apr 2200 - 0300 | 5 | 5 | 894805 |  | TF | FOT | WLT | 4070 | WHILE LOGGING A FALUIRE IN COMPACT LATEROLOG SUB (RESISTIVITY TOOL) OCCURED
815 | 04/05/2022 | SP-110 | BRRI-562 | RIG | 05 Apr 1345 - 1630 | 2.75 | 2.75 | 894786 |  | RR | FOT | TDS | 3390 | TDS BRAKE SYSTEM MALFUNCTION DUE TO THE WORKING PRESSURE OF THE BRAKE CYLINDER LOWER THAN NORMAL. ADJUST THE PRESSURE AND TEST THE BRAKE, OK. BACK TO NORMAL OPERATION.
817 | 04/05/2022 | SP-261 | HZEM-162204 | SDM | 03 Apr 1915 - 0600 | 1 | 33.25 | 894617 |  | BHA | FOT | LWD | 12494 | LOST LWD SIGNAL WHILE DRILLING LATERAL SECTION.
819 | 04/05/2022 | SP-262 | HZEM-140804 | BHI | 04 Apr 1030 - 0430 | 22.5 | 41 | 894690 |  | BHA | FOT | MWD | 14557 | LOST ALL COMMUNICATION WITH BAKER RSS.
821 | 04/05/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 21.5 | 37.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
823 | 04/05/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 625 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
825 | 04/05/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 985.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
827 | 04/05/2022 | T218 | UTMN-564 | ARM | 03 Apr 0500 - 0500 | 24 | 69.5 | 894771 |  | TF | FCLK | CSG | 6300 | WHILE CLEANING OUT 4-1/2" LINER WITH 3-7/8", HAD TIGHT SPOT AT SEVERAL DEPTHS AND SUSPECTED LINER PARTED.
829 | 04/05/2022 | WCL-83 | MRJN-837 | ARM | 03 Apr 0215 - 0500 | 22 | 48.75 | 894667 |  | TH | PCPF | NA | 9420 | OBSERVED INCREASED DRAG WHILE RIH 7" LINER AT 9420'. POH THROUGH TIGHT SPOT WITH MAX 20K OVERPULL & PACK OFF. POOH 7" LINER & PERFORM REAMING RUN.
831 | 04/06/2022 | ADC-50 | SFNY-1177 | ARM | 28 Mar 1230 - 0500 | 24 | 226.25 | 894353 |  | LCIR | UVLC | NA | 4190 | AFTER DISPLACING 72 PCF WBM WITH 88 PCF OBM, OBSERVED TOTAL LOSSES. CUT DOWN MW TO 80 PCF OBM, AND PUMPED 1ST CMT PLUG, CURED LOSSES. DRILLED 3' NEW FORMATION, OBSERVED TOTAL LOSSES. SPOT 2ND, 3RD, AND 4TH CMT PLUGS, CURE LOSSES. DISPLACE TO 80 PCF WBM. DRILL 105' ADDITIONAL FT WITH MWD BHA, TOTAL LOSSES. SPOT 5TH AND 6TH CMT PLUGS, LOSSES REDUCED TO 55 BPH STATIC.
836 | 04/06/2022 | ADES-158 | ABQQ-737 | BCR | 06 Apr 1300 - 1700 | 4 | 4 | 894886 |  | JF | XTRI | CTRQ | 45 | EXCESS TIME TO MAKE UP ASSY#1 & 2 DUE TO MAKE UP GRAPH NOT ACCEPTED BY JAM UNIT (IMPROPER TORQUE).
837 | 04/06/2022 | ADES-173 | HRDH-2256 | SPS | 06 Apr 2030 - 2130 | 1 | 1 | 894869 |  | TF | XTTE | MWD | 14218 | AFTER M/U THE TDS TO START WASH DOWN OBSERVED BAD MWD DETECTION, TROUBLESHOOTING PROBLEM TILL GOT GOOD DETECTION.
839 | 04/06/2022 | ADES-173 | HRDH-2256 | RIG | 05 Apr 0100 - 0700 | 2 | 6 | 894790 |  | RR | FOT | CSYS | 14218 | OUTER SKIN OF KELLY HOSE PEELED, CHANGED SAME.
840 | 04/06/2022 | ADES-173 | HRDH-2256 | RIG | 06 Apr 1000 - 1200 | 2 | 2 | 894865 |  | JF | XTRI | NA | 1180 | EXCESS TIME TO P/UP AND M/UP 5-7/8" BHA.
841 | 04/06/2022 | ADES-173 | HRDH-2256 | SPS | 06 Apr 2030 - 2130 | 1 | 1 | 894869 |  | TF | XTTE | MWD | 14218 | AFTER M/U THE TDS TO START WASH DOWN OBSERVED BAD MWD DETECTION, TROUBLESHOOTING PROBLEM TILL GOT GOOD DETECTION.
843 | 04/06/2022 | ADES-174 | GHZL-88 | WDS | 06 Apr 1000 - 1400 | 4 | 4 | 894885 |  | DD | HERR | RSS | 5070 | W'FORD OBSERVED SIGNAL INTERUPTION AND PRESSURE FLUCTUATION IN THEIR SYSTEM, CIRC, ROTATE & RECEIPROCATE STRING MEANWHILE TROUBLESHOOTING W'FORD POWER SUPPLY, SEVERAL ATTEMPTS TO C/O POWER SUPPLY SOURCE TO THE UNIT TILL SIGNAL CLEAR.
845 | 04/06/2022 | ADES-798 | JFYN-11 | RIG | 06 Apr 2300 - 0500 | 6 | 6 | 894890 |  | RR | FOT | TDS | 11495 | TDS TROUBLE SHOOTING. CHANGE OUT TOP DRIVE SYSTEM ENCODER.
847 | 04/06/2022 | ADM-510 | ABSF-224 | SPS | 02 Apr 1545 - 0800 | 3 | 74.25 | 894562 |  | DD | AINC | BHA | 8568 | SPERRY RSS UNABLE TO DROP INCLINATION AS PER GOC REQUEST
849 | 04/06/2022 | ADM-511 | MRJN-799 | BHT | 04 Apr 1430 - 0500 | 9.5 | 24 | 894729 |  | LROP | ETRQ | BIT | 5178 | UNABLE TO CONTINUE DRILLING AT 5178 FT MD - BHA BECAME STUCK ON BOTTOM - FREED BHA WITH JARRING - BACKREAMED ABOVE LZ - REAMED 8 FT FROM BOTTOM AND COULD NOT CONTINUE DUE TO HIGH TORQUE - PULLED OUT OF HOLE - BIT SHOULDER VERY BAD CONDITION
851 | 04/06/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 42.5 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
856 | 04/06/2022 | DQ-48 | KHRS-1411 | HCO | 06 Apr 1100 - 1830 | 7.5 | 7.5 | 894895 |  | JF | DSFT | PKR | 436 | WHILE HALL DOING THE EXTERNAL FMJ PRESSURE TEST FROM BTM OF PACKER ON LINE TO LINE SPLICE GOT LEAKED, CHANGED FITTINGS & FERRULES MANY TIMES TILL FIXED.
858 | 04/06/2022 | NA-393S | HWYH-1138 | SAM | 03 Apr 0100 - 0500 | 24 | 75.5 | 894660 |  | BHA | FOT | WBCL | 6767 | 9-5/8" SAMAA CSG SCRAPPER TWISTED OFF FROM ITS BODY WITHOUT ANY INDICATION (BAD QUALITY), 2' FROM SCRAPPER BODY LOST IN HOLE IN ADDITION TO 8-3/8" STRING MILL, JUNK BASKET, 8-3/8" FBM.
860 | 04/06/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 1815 | 12.75 | 242 | 894425 |  | LCIR | UVLC | NA | 8416 | ENCOUNTERED TOTAL LOSSES AT 8,416' WHILE ROTARY DRILLING 12" HOLE SECTION (BASE LOWER FADHILI RESERVOIR) FRACTURE /28' FORMATION CAVERN/VOID.
861 | 04/06/2022 | PA-218S | QTIF-515 | RIG | 06 Apr 1900 - 2000 | 1 | 1 | 894889 |  | RR | FOT | MPMP | 23510 | HAD LEAK ON MUD PUMP# 3
863 | 04/06/2022 | PA-218S | QTIF-515 | BHI | 06 Apr 1800 - 1900 | 1 | 1 | 894888 |  | BHA | FOT | LWD | 23510 | BAKER LOST NMR SIGNAL.
864 | 04/06/2022 | PA-218S | QTIF-515 | RIG | 06 Apr 1900 - 2000 | 1 | 1 | 894889 |  | RR | FOT | MPMP | 23510 | HAD LEAK ON MUD PUMP# 3
866 | 04/06/2022 | PA-326S | WDYH-16 | FMC | 06 Apr 2230 - 0130 | 3 | 3 | 894894 |  | TF | HERR | TTRQ | 1408 | THREADS ON THE SHOE TRACK WERE CROSSED.
868 | 04/06/2022 | PA-70S | MDRK-64 | ARN | 06 Apr 1730 - 2100 | 3.5 | 3.5 | 894905 |  | WO | SRVC | NA | 15745 | GOC UNABLE TO RECEIVE GR LOG DATA DUE TO V-SAT COMMUNICATION ISSUE. CIRCULATE AND WORK PIPE WHILE V-SAT TROUBLESHOOTING COMMUNICATION PROBLEM & GOC CONFIRM LOG DATA.
870 | 04/06/2022 | SCTD-1 | UTMN-3141 | RIG | 05 Apr 0130 - 0500 | 24 | 27.5 | 894791 |  | STUK | STBH | CTAC | 14043 | COIL STRING STUCK WHILE POH
872 | 04/06/2022 | SINO-18 | ADHN-10 | BAW | 05 Apr 1230 - 0500 | 12.75 | 29.25 | 894765 |  | TF | FOT | WLT | 15161 | WHILE ATTEMPT TO TAKE SAMPL#3 COMMUNICATION LOST FROM THE TOOL.
874 | 04/06/2022 | SND-2004 | BRRI-1148 | ARM | 05 Apr 1100 - 2300 | 3 | 7 | 894766 |  | BB | PCPF | NA | 246 | 28" BALLED UP BIT DUE TO STICKY FORMATION, TRIP OUT TO CLEAN THE BIT.
876 | 04/06/2022 | SND-3003 | HRDH-2311 | BLH | 06 Apr 0030 - 0500 | 4.5 | 4.5 | 894868 |  | TF | FOT | HGRL | 12850 | WHILE SPACE OUT W/ 15K BOT LINER ON BTM, SUDDEN INCREASE IN PRESSURE W/ NO RETURN, ABLE TO PICK UP AND ROTATE WITH NO RESTRICTION BUT UNABLE TO BACK DOWN.
878 | 04/06/2022 | SP-122 | ANDR-602 | SDM | 06 Apr 1430 - 0500 | 14.5 | 14.5 | 894893 |  | BHA | FOT | MWD | 12080 | SLB MWD TOOL HAD NO SIGNAL
880 | 04/06/2022 | SP-258 | HZEM-160612 | ARN | 06 Apr 0415 - 0500 | .75 | .75 | 894887 |  | TF | FOT | VSAT | 17873 | ACCUMULATED STOPPAGE DRILLING TIME AS PER IOC DUE TO V-SAT DATA TRANSMISSION ISSUE.
882 | 04/06/2022 | SSA-5820 | SDGM-1215 | RIG | 27 Mar 0600 - 0430 | 19.5 | 43.5 | 894485 |  | HC | LEFP | MPMP | 9225 | WHILE RUNNING IN HOLE ON 13 3/8" CASING, HIT HARD OBSTRUCTION AT 9229, CEMENT TOP 1144' HIGH.
884 | 04/06/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 24 | 61.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
886 | 04/06/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 10.75 | 635.75 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
888 | 04/06/2022 | T914 | HWYH-135 | RIG | 06 Apr 1315 - 1730 | 4.25 | 4.25 | 894891 |  | RR | FPMP | MPMP | 7013 | REPAIR ON MUD PUMPS' SUPERCHARGING.
890 | 04/06/2022 | V140A | RBYN-100 | EX1 | 06 Apr 1915 - 0500 | 9.75 | 9.75 | 894867 |  | TF | FOT | SLICK | 6507 | DURING EXPRO SLICKLINE RIG UP - LOWER SHEAVE BECAME DETACHED FROM ANCHOR POINT AND CONTACTED DEPTH COUNTER. DEPTH COUNTER BEYOND REPAIR
892 | 04/06/2022 | WCL-83 | MRJN-837 | ARM | 03 Apr 0215 - 0500 | 23.5 | 72.25 | 894667 |  | TH | PCPF | NA | 9420 | OBSERVED INCREASED DRAG WHILE RIH 7" LINER AT 9420'. POH THROUGH TIGHT SPOT WITH MAX 20K OVERPULL & PACK OFF. POOH 7" LINER & PERFORM REAMING RUN.
894 | 04/07/2022 | ADC-50 | SFNY-1177 | ARM | 28 Mar 1230 - 0745 | 2.75 | 229 | 894353 |  | LCIR | UVLC | NA | 4190 | AFTER DISPLACING 72 PCF WBM WITH 88 PCF OBM, OBSERVED TOTAL LOSSES. CUT DOWN MW TO 80 PCF OBM, AND PUMPED 1ST CMT PLUG, CURED LOSSES. DRILLED 3' NEW FORMATION, OBSERVED TOTAL LOSSES. SPOT 2ND, 3RD, AND 4TH CMT PLUGS, CURE LOSSES. DISPLACE TO 80 PCF WBM. DRILL 105' ADDITIONAL FT WITH MWD BHA, TOTAL LOSSES. SPOT 5TH AND 6TH CMT PLUGS, LOSSES REDUCED TO 55 BPH STATIC. SPOTTED 7TH AND 8TH CMT PLUGS, HOLE STATIC. DRILLED OUT CMT, ENCOUNTERED DYNAMIC LOSSES WHICH GRADUALLY REDUCED TO ZERO.
898 | 04/07/2022 | ADC-59L | HRDH-2232 | TSC | 07 Apr 1030 - 1300 | 2.5 | 2.5 | 894988 |  | TF | FOT | CTRQ | 300 | OBSERVED DRIFT NOT PASSING THROUGH THE CONNECTION BETWEEEN SECOND & THIRD PUP JOINTS AFTER SPACE OUT
900 | 04/07/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0500 | 21.5 | 213.25 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
901 | 04/07/2022 | ADC-59L | HRDH-2232 | TSC | 07 Apr 1030 - 1300 | 2.5 | 2.5 | 894988 |  | TF | FOT | CTRQ | 300 | OBSERVED DRIFT NOT PASSING THROUGH THE CONNECTION BETWEEEN SECOND & THIRD PUP JOINTS AFTER SPACE OUT
903 | 04/07/2022 | ADES-158 | ABQQ-737 | HCO | 07 Apr 0230 - 0500 | 2.5 | 2.5 | 894968 |  | TF | HERR | TBG | 509 | FOUND ICV#B HYDRAULIC LINES CONNECTED IN WRONG POSITION
905 | 04/07/2022 | ADES-173 | HRDH-2256 | SPS | 07 Apr 2115 - 0500 | 7.75 | 7.75 | 894967 |  | TF | FOT | MS | 14394 | MWD GR DETECTION LOST, TROUPLESHOOTING PROBLEM -NO DETECTION
907 | 04/07/2022 | ADES-40 | ANDR-469 | HCB | 07 Apr 2130 - 0500 | 7.5 | 7.5 | 894986 |  | TF | FOT | BP | 0 | FAILURE TO STING IN 9 5/8" FAS DRIL PLUG AND OPEN THE VALVE TO COMMENCE SQUEEZE OPS.
909 | 04/07/2022 | ADES-798 | JFYN-11 | RIG | 06 Apr 2300 - 1130 | 6.5 | 12.5 | 894890 |  | RR | FOT | TDS | 11495 | CHANGE OUT TOP DRIVE SYSTEM ENCODER & ENCODER SHAFT DRIVE.
911 | 04/07/2022 | ADM-510 | ABSF-224 | SPS | 02 Apr 0500 - 2130 | 16.5 | 132.75 | 894562 |  | DD | AINC | BHA | 8568 | SPERRY RSS UNABLE TO DROP INCLINATION AS PER GOC REQUEST
913 | 04/07/2022 | ADM-511 | MRJN-799 | ARM | 04 Apr 1430 - 1300 | 8 | 32 | 894729 |  | LROP | FNFS | BIT | 5178 | UNABLE TO CONTINUE DRILLING @ 5178 FT WITH 16" BHI MM/MWD ASSY DUE TO HIGH TQ, POOH AND CHANGE BHA CONFIGURATION TO BE ABLE TO CONTINUE DRILLING.
915 | 04/07/2022 | ADM-655 | SFNY-475 | AP2 | 07 Apr 0500 - 0500 | 24 | 24 | 894945 |  | WO | WPD3 | NA | 0 | WAIT ON SFNY FIELD SERVICE TO SECURE PLATFORM SFNY-470/475 FOR SAFE RIG APPROACH.
917 | 04/07/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 66.5 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
919 | 04/07/2022 | NA-207S | SHYB-194 | SDM | 07 Apr 0800 - 0500 | 21 | 21 | 894965 |  | BHA | FOT | RSS | 6683 | WHILE DRLG L-0-1, HAD FAILURE OF SLB RSS, SLB DIR DRILLER SEND COMMANDS TO RSS, NO RESPONSE.
921 | 04/07/2022 | NA-393S | HWYH-1138 | SAM | 03 Apr 0100 - 0500 | 23.5 | 99 | 894660 |  | BHA | FOT | WBCL | 6767 | 9-5/8" SAMAA CSG SCRAPPER TWISTED OFF FROM ITS BODY WITHOUT ANY INDICATION (BAD QUALITY), 2' FROM SCRAPPER BODY LOST IN HOLE IN ADDITION TO 8-3/8" STRING MILL, JUNK BASKET, 8-3/8" FBM.
922 | 04/07/2022 | NBR-16S | HMYM-433314 | ITS | 07 Apr 0500 - 0630 | 1.5 | 1.5 | 894946 |  | TF | FOT | CTRQ | 18395 | ITS POWER TONG NOT ABLE TO APPLY REQUIRED MAKE UP TORQUE FOR CASING
924 | 04/07/2022 | NBR-16S | HMYM-433314 | RIG | 07 Apr 1930 - 2230 | 3 | 3 | 894928 |  | RR | FOT | CATW | 18395 | TROUBLE SHOOT RIG HYDRAULIC CAT WALK AS PIPE SLIDER FAILED TO OPERATE PROPERLY
925 | 04/07/2022 | NBR-16S | HMYM-433314 | ITS | 07 Apr 0500 - 0630 | 1.5 | 1.5 | 894946 |  | TF | FOT | CTRQ | 18395 | ITS POWER TONG NOT ABLE TO APPLY REQUIRED MAKE UP TORQUE FOR CASING
927 | 04/07/2022 | NBR-654S | HRDH-2210 | RIG | 07 Apr 1000 - 1100 | 1 | 1 | 894987 |  | RR | FOT | CSYS | 13655 | TRIP TANK FILL UP HOSE BURST
928 | 04/07/2022 | PA-218S | QTIF-515 | RIG | 07 Apr 0230 - 0500 | 2.5 | 2.5 | 894989 |  | RR | FOT | CSYS | 23883 | HAD LEAK ON STANDPIPE MANIFOLD
930 | 04/07/2022 | PA-218S | QTIF-515 | RIG | 07 Apr 1045 - 0230 | 9.75 | 9.75 | 894985 |  | RR | FOT | MPMP | 23883 | HAD LEAK FROM MUD PUMP-2&3.
931 | 04/07/2022 | PA-218S | QTIF-515 | RIG | 07 Apr 0230 - 0500 | 2.5 | 2.5 | 894989 |  | RR | FOT | CSYS | 23883 | HAD LEAK ON STANDPIPE MANIFOLD
933 | 04/07/2022 | SCTD-1 | UTMN-3141 | RIG | 05 Apr 0130 - 0500 | 24 | 51.5 | 894791 |  | STUK | STBH | CTAC | 14043 | COIL STRING STUCK WHILE POH
935 | 04/07/2022 | SDA | MRJN-735 | BHI | 07 Apr 1945 - 2145 | 2 | 2 | 894991 |  | LROP | IDPR | BHA | 6050 | BHI RSS UNABLE TO HANDLE STEERING WORKS AT REQUIRED DRILLING PARAMETERS.
936 | 04/07/2022 | SINO-18 | ADHN-10 | BAW | 07 Apr 2000 - 0500 | 9 | 9 | 894947 |  | TF | FOT | WLT | 14500 | ATTEMPT TO LATCH WET CONNECTOR WITH NO SUCCESS.
938 | 04/07/2022 | SINO-18 | ADHN-10 | BAW | 05 Apr 1230 - 2000 | 15 | 44.25 | 894765 |  | TF | FOT | WLT | 15161 | WHILE ATTEMPT TO TAKE SAMPL#3 COMMUNICATION LOST FROM THE TOOL.
939 | 04/07/2022 | SINO-18 | ADHN-10 | BAW | 07 Apr 2000 - 0500 | 9 | 9 | 894947 |  | TF | FOT | WLT | 14500 | ATTEMPT TO LATCH WET CONNECTOR WITH NO SUCCESS.
941 | 04/07/2022 | SINO-43L | UTMN-4063 | BCM | 06 Apr 0215 - 0500 | 24 | 26.75 | 894870 |  | CMT | WSHO | CSG | 7456 | PRESSURE TEST 7" LINER TO 1250 PSI ( 30' ABOVE SHOE) PRESS DROP 250 PSI/10 MINTS.
943 | 04/07/2022 | SL-7 | ZULF-1333 | HWP | 07 Apr 1630 - 1845 | 2.25 | 2.25 | 894966 |  | JF | XTRI | WLT | 0 | EXSSIVE TIME PREPARING HES LOGGING TOOLS
945 | 04/07/2022 | SND-2001 | UTMN-2329 | ARM | 07 Apr 2215 - 0500 | 6.75 | 6.75 | 894990 |  | LCIR | FRFM | NA | 6552 | RIH WITH OEDP TO PERFORM SQUEEZE CMT
946 | 04/07/2022 | SND-3003 | HRDH-2311 | WCR | 07 Apr 1245 - 1330 | .75 | .75 | 894927 |  | TF | FOT | CTRQ | 615 | FAILED POWER TONG WHILE BREAK OUT CONNECTION
948 | 04/07/2022 | SND-3003 | HRDH-2311 | BLH | 06 Apr 0030 - 0500 | 23.25 | 27.75 | 894868 |  | TF | FOT | HGRL | 12850 | WHILE SPACE OUT W/ 15K BOT LINER ON BTM, SUDDEN INCREASE IN PRESSURE W/ NO RETURN, ABLE TO PICK UP AND ROTATE WITH NO RESTRICTION BUT UNABLE TO BACK DOWN.
949 | 04/07/2022 | SND-3003 | HRDH-2311 | WCR | 07 Apr 1245 - 1330 | .75 | .75 | 894927 |  | TF | FOT | CTRQ | 615 | FAILED POWER TONG WHILE BREAK OUT CONNECTION
951 | 04/07/2022 | SP-122 | ANDR-602 | SDM | 06 Apr 1430 - 0500 | 24 | 38.5 | 894893 |  | BHA | FOT | MWD | 12080 | SLB MWD TOOL HAD NO SIGNAL
953 | 04/07/2022 | SP-306 | MNIF-197 | BHI | 07 Apr 0415 - 0500 | .75 | .75 | 894992 |  | BHA | FOT | RSS | 6203 | LOST COMMUNICATION BETWEEN STEER. HEAD & ONTRAK.
955 | 04/07/2022 | SSA-5820 | SDGM-1215 | RIG | 25 Mar 0500 - 1330 | 1 | 3.5 | 894201 |  | DSF | FOT | DP | 0 | LAY DOWN 9 STANDS (27JNTS) OF 5.5" DP DUE TO WASH OUTS
957 | 04/07/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 24 | 85.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
959 | 04/07/2022 | SSA-5962 | HRDH-2230 | ARM | 07 Apr 2130 - 0500 | 7.5 | 7.5 | 895005 |  | TF | FOT | CSG | 4900 | CSG 18-5/8'' PARTED AFTER 1ST STAGE OF CMT JOB & BUMPED PLUG UP TO 1000 PSI AS PER PROGRAM.
961 | 04/07/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 20 | 655.75 | 893136 |  | STUK | SDIR | RSS | 1867 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
963 | 04/07/2022 | V140A | RBYN-100 | EX1 | 07 Apr 0500 - 0500 | 24 | 24 | 894896 |  | TF | FOT | SLICK | 6507 | DURING EXPRO SLICK LINE RIG UP - LOWER SHEAVE BECAME DETACHED FROM ANCHOR POINT AND CONTACTED DEPTH COUNTER. DEPTH COUNTER BEYOND REPAIR
965 | 04/07/2022 | WCL-83 | MRJN-837 | ARM | 03 Apr 0215 - 0215 | 21.25 | 93.5 | 894667 |  | TH | PCPF | NA | 9420 | OBSERVED INCREASED DRAG WHILE RIH 7" LINER AT 9420'. POH THROUGH TIGHT SPOT WITH MAX 20K OVERPULL & PACK OFF. POOH 7" LINER & PERFORM REAMING RUN.
971 | 04/08/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0500 | 24 | 237.25 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
976 | 04/08/2022 | ADES-173 | HRDH-2256 | SPS | 07 Apr 2115 - 2330 | 18.5 | 26.25 | 894967 |  | BHA | FOT | MWD | 14394 | MWD GR DETECTION LOST, TROUPLESHOOTING PROBLEM -NO DETECTION
977 | 04/08/2022 | ADES-40 | ANDR-469 | RIG | 08 Apr 0400 - 0445 | .75 | .75 | 895029 |  | JF | HERR | NA | 0 | MUD-MAN FAILED TO FOLLOW INSTRUCTIONS
979 | 04/08/2022 | ADES-40 | ANDR-469 | HCB | 07 Apr 2130 - 0145 | 20.75 | 28.25 | 894986 |  | TF | FOT | BP | 0 | FAILURE TO STING IN 9 5/8" FAS DRIL PLUG AND OPEN THE VALVE TO COMMENCE SQUEEZE OPS.
980 | 04/08/2022 | ADES-40 | ANDR-469 | RIG | 08 Apr 0400 - 0445 | .75 | .75 | 895029 |  | JF | HERR | NA | 0 | MUD-MAN FAILED TO FOLLOW INSTRUCTIONS
982 | 04/08/2022 | ADM-510 | ABSF-224 | WCR | 08 Apr 0000 - 0130 | 1.5 | 1.5 | 895068 |  | TF | FOT | CTRQ | 0 | WHILE CONNECTING HYDRAULIC HOSES TO WEATHERFORD CRT, ONE HOSE FITTING BROKE
984 | 04/08/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 90.5 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
986 | 04/08/2022 | CG-1 | ZULF-1203 | RIG | 08 Apr 1615 - 1700 | .75 | .75 | 895067 |  | RR | FOT | HSYS | 2044 | TROUBLESHOOTING ON PRS SYSTEM (PIPE RACKING SYSTEM).
988 | 04/08/2022 | NA-207S | SHYB-194 | SDM | 07 Apr 0800 - 0800 | 3 | 24 | 894965 |  | BHA | FOT | RSS | 6683 | WHILE DRLG L-0-1, HAD FAILURE OF SLB RSS, SLB DIR DRILLER SEND COMMANDS TO RSS, NO RESPONSE.
990 | 04/08/2022 | NA-393S | HWYH-1138 | SAM | 03 Apr 0100 - 1730 | 11 | 110 | 894660 |  | BHA | FOT | WBCL | 6767 | 9-5/8" SAMAA CSG SCRAPPER TWISTED OFF FROM ITS BODY WITHOUT ANY INDICATION (BAD QUALITY), 2' FROM SCRAPPER BODY LOST IN HOLE IN ADDITION TO 8-3/8" STRING MILL, JUNK BASKET, 8-3/8" FBM.
991 | 04/08/2022 | PA-218S | QTIF-515 | RIG | 07 Apr 0230 - 0615 | 1.25 | 3.75 | 894989 |  | RR | FOT | CSYS | 23883 | HAD LEAK ON STANDPIPE MANIFOLD
993 | 04/08/2022 | PA-218S | QTIF-515 | RIG | 07 Apr 1045 - 0915 | 3 | 12.75 | 894985 |  | RR | FOT | MPMP | 23883 | HAD LEAK FROM MUD PUMP-2&3.
994 | 04/08/2022 | PA-218S | QTIF-515 | RIG | 07 Apr 0230 - 0615 | 1.25 | 3.75 | 894989 |  | RR | FOT | CSYS | 23883 | HAD LEAK ON STANDPIPE MANIFOLD
996 | 04/08/2022 | SCTD-1 | UTMN-3141 | RIG | 05 Apr 0130 - 0500 | 24 | 75.5 | 894791 |  | STUK | STBH | CTAC | 14043 | COIL STRING STUCK WHILE POH
998 | 04/08/2022 | SINO-18 | ADHN-10 | BAW | 07 Apr 2000 - 2000 | 15 | 24 | 894947 |  | TF | FOT | WLT | 14500 | ATTEMPT TO LATCH WET CONNECTOR WITH NO SUCCESS.
1003 | 04/08/2022 | SINO-36L | SDGM-256 | SPS | 08 Apr 1400 - 1600 | 2 | 2 | 895025 |  | BHA | FOT | LWD | 0 | SPS TROUBLE SHOOTING LWD COMMUNICATION
1005 | 04/08/2022 | SINO-43L | UTMN-4063 | BCM | 06 Apr 0215 - 0245 | 21.75 | 48.5 | 894870 |  | CMT | WSHO | CSG | 7456 | PRESSURE TEST 7" LINER TO 1250 PSI ( 30' ABOVE SHOE) PRESS DROP 250 PSI/10 MINTS.
1007 | 04/08/2022 | SND-2001 | UTMN-2329 | ARM | 07 Apr 2215 - 2130 | 16.5 | 23.25 | 894990 |  | LCIR | FRFM | NA | 6552 | RIH WITH OEDP TO PERFORM SQUEEZE CMT JOB
1009 | 04/08/2022 | SND-2008 | HRDH-2190 | RIG | 08 Apr 1930 - 2200 | 2.5 | 2.5 | 895065 |  | RR | FOT | DWKS | 0 | REPLACE DRAWWORKS HIGH CLUTCH CHAIN WITH NEW ONE.
1011 | 04/08/2022 | SND-3003 | HRDH-2311 | BLH | 06 Apr 0030 - 0430 | 23.5 | 51.25 | 894868 |  | TF | FOT | HGRL | 12850 | WHILE SPACE OUT W/ 15K BOT LINER ON BTM, SUDDEN INCREASE IN PRESSURE W/ NO RETURN, ABLE TO PICK UP AND ROTATE WITH NO RESTRICTION BUT UNABLE TO BACK DOWN.
1013 | 04/08/2022 | SP-261 | HZEM-162204 | SDM | 03 Apr 1915 - 0300 | 18.25 | 51.5 | 894617 |  | BHA | FOT | LWD | 12494 | LOST LWD SIGNAL WHILE DRILLING LATERAL SECTION.
1014 | 04/08/2022 | SP-306 | MNIF-197 | BHI | 08 Apr 2000 - 0500 | 7.5 | 7.5 | 895045 |  | BHA | FOT | RSS | 6203 | LOST COMMUNICATION BETWEEN ONTRAK & STEERING HEAD.
1016 | 04/08/2022 | SP-306 | MNIF-197 | ARM | 07 Apr 0415 - 1300 | 8 | 8.75 | 894992 |  | LCIR | UXDF | NA | 6203 | HAD PARTIAL LOSSES @ 6100'.(ACROSS SFNY.)
1017 | 04/08/2022 | SP-306 | MNIF-197 | BHI | 08 Apr 2000 - 0500 | 7.5 | 7.5 | 895045 |  | BHA | FOT | RSS | 6203 | LOST COMMUNICATION BETWEEN ONTRAK & STEERING HEAD.
1019 | 04/08/2022 | SSA-51 | MNIF-259 | BHI | 08 Apr 1030 - 1130 | 1 | 1 | 894969 |  | BHA | FOT | MWD | 14193 | BAKER TROUBLESHOOT MWD SIGNAL
1021 | 04/08/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 24 | 109.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1023 | 04/08/2022 | SSA-5917 | HRDH-2344 | RIG | 08 Apr 1430 - 0130 | 11 | 11 | 895027 |  | RR | FOT | TDS | 735 | HAD COMMUNICATION LOSS IN TDS HYDRAULIC SYS. NO FUNCTION
1025 | 04/08/2022 | SSA-5962 | HRDH-2230 | ARM | 07 Apr 2130 - 0500 | 24 | 31.5 | 895005 |  | TF | FOT | CSG | 4900 | 18-5/8'' CSG PARTED DURING 1ST STAGE CMT JOB WHILE BUMPED DVT PLUG .
1027 | 04/08/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 679.75 | 893136 |  | STUK | SDIR | RSS | 1867 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1029 | 04/08/2022 | T217 | UTMN-488 | ARM | 07 Apr 0100 - 1400 | 9 | 13 | 894993 |  | STUK | SCSG | LINR | 7820 | 4-1/2" LINER STUCK AT CONNECTION.
1031 | 04/08/2022 | V140A | RBYN-100 | EX1 | 07 Apr 0500 - 1330 | 8.5 | 32.5 | 894896 |  | TF | FOT | SLICK | 6507 | DURING EXPRO SLICK LINE RIG UP - LOWER SHEAVE BECAME DETACHED FROM ANCHOR POINT AND CONTACTED DEPTH COUNTER. DEPTH COUNTER BEYOND REPAIR
1033 | 04/08/2022 | WCL-83 | MRJN-837 | RIG | 08 Apr 2130 - 0500 | 7.5 | 7.5 | 895028 |  | UPRA | IRES | TDS | 0 | TDS CRITICAL LOAD PARTS INSPECTION IS REQUIRED EVERY 6 MONTH. RIG DID NOT DO IT DURING RIG MOVE.
1035 | 04/09/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0545 | .75 | 238 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
1039 | 04/09/2022 | ADES-40 | ANDR-469 | OES | 09 Apr 0715 - 0945 | 2.5 | 2.5 | 895076 |  | MUD | DIMF | NA | 0 | MUD PUMP SUCTION FULL WITH MUD MATERIALS.
1041 | 04/09/2022 | ADES-40 | ANDR-469 | HCB | 08 Apr 0400 - 0500 | 21.5 | 22.25 | 895029 |  | TF | FOT | BP | 0 | FAILURE TO STING IN 9 5/8" FAS-DRILL PLUG.
1042 | 04/09/2022 | ADES-40 | ANDR-469 | OES | 09 Apr 0715 - 0945 | 2.5 | 2.5 | 895076 |  | MUD | DIMF | NA | 0 | MUD PUMP SUCTION FULL WITH MUD MATERIALS.
1044 | 04/09/2022 | ADM-261 | MRJN-137 | RIG | 09 Apr 1800 - 0500 | 11 | 11 | 895055 |  | RR | FOT | TDS | 8521 | TOP DRIVE SYSTEM HYDRAULIC PUMP FAILURE.
1046 | 04/09/2022 | ADM-266 | SFNY-934 | ARN | 09 Apr 0500 - 0500 | 24 | 24 | 895074 |  | WO | ORDS | NA | 0 | WAIT ON HSU TO PERFORM SBS & PROVIDE DATA.
1048 | 04/09/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 114.5 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1050 | 04/09/2022 | NA-393S | HWYH-1138 | ARM | 08 Apr 0200 - 0500 | 24 | 27 | 895051 |  | WCNT | WCC2 | NA | 6764 | WHILE REDRESSING 9-5/8" CSG AT 6,764', WELL STARTED FLOWING.
1052 | 04/09/2022 | NBR-591S | HRDH-1921 | RIG | 09 Apr 0300 - 0500 | 2 | 2 | 895053 |  | RR | FOT | CATW | 4090 | AUTOMATIC CATWALK FAILED.
1054 | 04/09/2022 | PA-218S | QTIF-515 | RIG | 09 Apr 1915 - 2015 | 1 | 1 | 895052 |  | RR | FOT | CSYS | 23883 | TEST UNIT NOT WORKING PROPERLY
1056 | 04/09/2022 | RM-74A | KARN-60 | RIG | 09 Apr 1530 - 1700 | 1.5 | 1.5 | 895072 |  | RR | FOT | PSYS | 12410 | ARO ATTEMPT TO CONDUCT BLACKOUT DRILL, NO SUCCESS. ARO TROUBLESHOOT POWER ISSUES.
1058 | 04/09/2022 | SCTD-1 | UTMN-3141 | ARM | 06 Apr 1300 - 0500 | 24 | 88 | 895046 |  | FISH | FWTS | STRG | 14043 | WHILE WORKING ON THE STUCK COIL AFTER SEVERAL ATTEMPTS FOUND THE COIL PARTED AT 1165 FT, FISH IN HOLE ( 3.625" RR HTC BIT , D&M BHA , 12755 FT 2.375" COIL W/ 12940 FT E/L)
1060 | 04/09/2022 | SINO-16 | ABHD-123 | BC | 09 Apr 2130 - 0000 | 2.5 | 2.5 | 895070 |  | JF | FOT | GP | 3000 | BAKER WIRE LINE CCL LOGGING TOOL FAILED WHILE RIH WITH PUNCHER ASSEMBLY TO 3,000FT. TROUBLE SHOOTING NO SUCCESS, POOH & REPLACED NEW BACK UP BAKER CCL TOOL.
1062 | 04/09/2022 | SINO-27N | UTMN-432 | BHI | 06 Apr 1930 - 1100 | 3 | 36.75 | 895071 |  | DD | IDPR | MMOT | 6470 | EXTRA TIME SPEND ON SLIDE DRILLING TO CATCH UP WITH DIRECTIONAL PLAN.
1067 | 04/09/2022 | SINO-43L | UTMN-4063 | BHI | 09 Apr 0300 - 0500 | 2 | 2 | 895054 |  | BHA | FOT | RSS | 7776 | DURING DRILLING 6-1/8" HOLE TO DEPTH 7776', HAD RSS RIBS FAILURE .
1069 | 04/09/2022 | SND-2007 | ADHN-370100 | RIG | 09 Apr 1815 - 2315 | 5 | 5 | 895048 |  | RR | FOT | DWKS | 2042 | EATON BRAKE OF DWKS NOT REPONDING TO ITS CONTROL VALUE
1070 | 04/09/2022 | SNF036 | MRJN-901 | FMC | 09 Apr 0400 - 0500 | 1 | 2 | 895069 |  | TF | FOT | CTRQ | 8192 | UNABLE TO LATCH FRANKS SINGLE JOINT ELEVATOR ON CASING JOINT.
1072 | 04/09/2022 | SNF036 | MRJN-901 | FMC | 09 Apr 1000 - 1100 | 1 | 1 | 895047 | 895069 | TF | FOT | CTRQ | 8192 | UNABLE TO LATCH FRANKS SINGLE JOINT ELEVATOR ON CASING JOINT.
1073 | 04/09/2022 | SNF036 | MRJN-901 | FMC | 09 Apr 0400 - 0500 | 1 | 2 | 895069 |  | TF | FOT | CTRQ | 8192 | UNABLE TO LATCH FRANKS SINGLE JOINT ELEVATOR ON CASING JOINT.
1075 | 04/09/2022 | SP-259 | HZEM-160414 | SJC | 09 Apr 2200 - 0500 | 7 | 7 | 895049 |  | TF | ISEQ | PUMP | 7668 | SANJEL PROVIDED WORNG EQUIPMENT SPECIFICATION
1077 | 04/09/2022 | SP-261 | HZEM-162204 | SPR | 09 Apr 0045 - 0415 | 2.75 | 2.75 | 895056 |  | TF | FOT | CTRQ | 18160 | SAPESCO EQUIPMENT IN DISREPAIR. CHANGE OUT POWER TONGS 2 X AND CHANGE OUT HYDRAULIC POWER UNIT.
1079 | 04/09/2022 | SP-306 | MNIF-197 | BHI | 08 Apr 2000 - 1445 | 9.75 | 17.25 | 895045 |  | BHA | FOT | RSS | 6203 | LOST COMMUNICATION BETWEEN DIRECTIONAL TOOLS (ONTRAK & STEERING HEAD).
1081 | 04/09/2022 | SSA-302 | HRDH-2113 | RTC | 09 Apr 0500 - 0500 | 24 | 24 | 895073 |  | TF | FOT | BIT | 5177 | LOW ROP AND HIGH TQ. ( ROTARY STALLING ) POOH LOST 2 CONES OFF OF BIT
1083 | 04/09/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 1515 | 10.25 | 119.75 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1085 | 04/09/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0430 | 23.5 | 703.25 | 893136 |  | STUK | SDIR | RSS | 1867 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1087 | 04/09/2022 | T218 | UTMN-564 | WDS | 09 Apr 0600 - 1200 | 5 | 5 | 895075 |  | TF | XTTE | LWD | 0 | LOST SIGNAL OF LWD TOOL DURING SHALLOW TEST.
1089 | 04/09/2022 | WCL-83 | MRJN-837 | RIG | 08 Apr 2130 - 0700 | 2 | 9.5 | 895028 |  | UPRA | IRES | TDS | 0 | TDS CRITICAL LOAD PARTS INSPECTION IS REQUIRED EVERY 6 MONTH. RIG DID NOT DO IT DURING RIG MOVE.
1091 | 04/10/2022 | ADC-17 | ZULF-1211 | RIG | 10 Apr 2230 - 0045 | 2.25 | 2.25 | 895063 |  | BOP | HERR | BOP | 0 | RIG FABRICATED BELL NIPPLE ONCE INSTALLED BELL NIPPLE FOUND NOT ALIGNED
1096 | 04/10/2022 | ADM-261 | MRJN-137 | RIG | 09 Apr 1800 - 0545 | .75 | 11.75 | 895055 |  | RR | FOT | TDS | 8521 | TOP DRIVE SYSTEM HYDRAULIC PUMP FAILURE.
1098 | 04/10/2022 | ADM-266 | SFNY-934 | ARN | 09 Apr 0500 - 0500 | 24 | 48 | 895074 |  | WO | ORDS | NA | 0 | WAIT ON HSU TO PERFORM SBS & PROVIDE DATA.
1100 | 04/10/2022 | ADM-339 | RBYN-55 | RIG | 10 Apr 2345 - 0215 | 2.5 | 2.5 | 895095 |  | RR | FOT | PSYS | 11916 | HPU POWER FAILURE ON RIG FLOOR - UNABLE TO OPERATE XY RACKER AND IRON ROUGHNECK.
1102 | 04/10/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 20.5 | 135 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1104 | 04/10/2022 | ARO-4001 | MRJN-539 | RIG | 10 Apr 1500 - 1900 | 4 | 4 | 895059 |  | RR | FOT | CSYS | 15545 | DUE TO THE LEAK ON MUD PITS AND MIXING MANIFOLD FOR 13 HRS, DISPLACEMENT SPACER & BRINE NOT READY, CIRCULATE WHILE PREPARING TO DISPLACE .
1106 | 04/10/2022 | BCTD-4 | GHZL-67 | RIG | 10 Apr 0300 - 0500 | 2 | 2 | 895096 |  | BHA | FOT | CTAC | 14414 | SLOW DRILLING AND HIGH DIFFERENTIAL PRESSURE.
1108 | 04/10/2022 | DPS-4 | MDRK-54 | SDM | 10 Apr 0015 - 0145 | 1.5 | 1.5 | 895094 |  | TF | XTTE | MWD | 2400 | NO MWD SIGNAL WHILE PERFORM SHALLOW TEST.
1109 | 04/10/2022 | DPS-46 | SDGM-1106 | SWL | 10 Apr 1300 - 1600 | 3 | 3 | 895089 |  | TF | FOT | WLT | 1500 | LOST COMMUNICATION WITH TUBING CUTTER TOOL.
1111 | 04/10/2022 | DPS-46 | SDGM-1106 | SWL | 10 Apr 0500 - 1000 | 5 | 5 | 895088 |  | WO | SRVC | NA | 0 | SLB WIRELINE MISSED X-OVER FOR E-LINE SURFACE EQUIPMENT.
1112 | 04/10/2022 | DPS-46 | SDGM-1106 | SWL | 10 Apr 1300 - 1600 | 3 | 3 | 895089 |  | TF | FOT | WLT | 1500 | LOST COMMUNICATION WITH TUBING CUTTER TOOL.
1114 | 04/10/2022 | DQ-48 | KHRS-1411 | SBA | 10 Apr 1300 - 1700 | 4 | 4 | 895058 |  | TF | FOT | ESP | 7400 | DURING FLOWBACK ESP MOTOR TEMPERATURE INCREASED, SAWAFI BORETS TROUBLESHOOT THE ESP, DECIDED TO CONTINUE FLOWBACK WITH BYPASSING MOTOR TEMPERATURE READING.
1119 | 04/10/2022 | HI-4 | SFNY-918 | BC | 09 Apr 2300 - 0500 | 24 | 30 | 894970 |  | TF | FOT | SSSV | 0 | OBSERVED BAKERHUGHES TRSSSV ON WELL BRRI-786 PASSING PRESSURE WHILE HANDOVER PLATFORM TO PRODUCTION.
1120 | 04/10/2022 | NA-393S | HWYH-1138 | ARM | 10 Apr 0545 - 0500 | 23.25 | 23.25 | 895079 |  | LCIR | UVLC | NA | 6764 | AFTER KILLING THE WELL, HAD COMPLETE LOSS FROM 9-5/8" COLLAPSED CSG.
1122 | 04/10/2022 | NA-393S | HWYH-1138 | ARM | 08 Apr 0200 - 0545 | .75 | 27.75 | 895051 |  | WCNT | WCC2 | NA | 6764 | WHILE REDRESSING 9-5/8" CSG AT 6,764', WELL STARTED FLOWING.
1123 | 04/10/2022 | NA-393S | HWYH-1138 | ARM | 10 Apr 0545 - 0500 | 23.25 | 23.25 | 895079 |  | LCIR | UVLC | NA | 6764 | AFTER KILLING THE WELL, HAD COMPLETE LOSS FROM 9-5/8" COLLAPSED CSG.
1125 | 04/10/2022 | PA-218S | QTIF-515 | RIG | 10 Apr 1200 - 2030 | 2 | 2 | 895091 |  | RR | FOT | DWKS | 23883 | MULFUNCTION OF DRAWWORKS HIGH GEAR.
1127 | 04/10/2022 | PN-7 | MRJN-775 | RIG | 10 Apr 0230 - 0400 | 1.5 | 1.5 | 895062 |  | RR | FOT | EDR | 11734 | LOST COMMUNICATION WITH GOC DUE TO SWITCH FAILURE IN RIG ELECTRICAL JUNCTION BOX.
1129 | 04/10/2022 | SCTD-1 | UTMN-3141 | ARM | 06 Apr 1300 - 1200 | 7 | 95 | 895046 |  | FISH | FWTS | STRG | 14043 | COIL PARTED WHILE WORKING AND ATTEMPTING TO FREE THE STUCK PIPE
1131 | 04/10/2022 | SINO-11 | HWTH-36 | AP1 | 10 Apr 1930 - 2330 | 4 | 4 | 895060 |  | WO | WOPF | NA | 4020 | GOT HIGH PRESSURE IN PRODUCTION LINE, CHECKED ALL VALVES FOUND 3" MCV VALVE IS LOOSEN.
1136 | 04/10/2022 | SINO-43L | UTMN-4063 | BHI | 09 Apr 0300 - 2130 | 16.5 | 18.5 | 895054 |  | BHA | FOT | RSS | 7776 | DURING DRILLING 6-1/8" HOLE TO DEPTH 7776', HAD RSS RIBS FAILURE .
1138 | 04/10/2022 | SND-2004 | BRRI-1148 | RIG | 10 Apr 0400 - 0500 | 1 | 1 | 895064 |  | RR | FPMP | MPMP | 2850 | RIG REPAIR ON MUD PUMPS 1 & 3.
1140 | 04/10/2022 | SND-2006 | UTMN-3135 | RIG | 10 Apr 0500 - 0500 | 22 | 22 | 895093 |  | JF | HERR | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1142 | 04/10/2022 | SP-259 | HZEM-160414 | SJC | 09 Apr 2200 - 1200 | 7 | 14 | 895049 |  | TF | ISEQ | PUMP | 7668 | SANJEL PROVIDED WORNG EQUIPMENT SPECIFICATION
1144 | 04/10/2022 | SP-261 | HZEM-162204 | SPR | 09 Apr 0045 - 0615 | .75 | 3.5 | 895056 |  | TF | FOT | CTRQ | 18160 | SAPESCO EQUIPMENT IN DISREPAIR. CHANGE OUT POWER TONGS 2 X AND CHANGE OUT HYDRAULIC POWER UNIT.
1146 | 04/10/2022 | SSA-302 | HRDH-2113 | RTC | 09 Apr 0500 - 0500 | 24 | 48 | 895073 |  | TF | FOT | BIT | 5177 | LOW ROP AND HIGH TQ. ( ROTARY STALLING ) POOH LOST 2 CONES OFF OF BIT
1148 | 04/10/2022 | SSA-5820 | SDGM-1215 | WCR | 10 Apr 2000 - 2100 | 1 | 1 | 895092 |  | TF | FOT | FUT | 3568 | FILL TOOL NOT COMPATIBLE WITH CSG WT.
1150 | 04/10/2022 | SSA-5859 | HRDH-1967 | FMC | 10 Apr 1030 - 1100 | .5 | .5 | 895061 |  | TF | FOT | CTRQ | 11675 | TROUBLE SHOOTING ON POWER TONG , LEAKING OIL
1151 | 04/10/2022 | SSA-5865 | ABJF-50 | RIG | 10 Apr 0615 - 0715 | 1 | 1 | 895085 |  | RR | FOT | HSYS | 7640 | IRON ROUGHNECK HPU MOTOR MALFUNCTION AFTER TORQUED-UP DRILL PIPE CONNECTION AND COULD NOT RETRACT BACK. HPU ELECTRIC MOTOR NEED TO CHANGE.
1153 | 04/10/2022 | SSA-5865 | ABJF-50 | RIG | 10 Apr 2330 - 0130 | 2 | 2 | 894973 |  | RR | FOT | HSYS | 4268 | LOST TIME DUE TO IRON ROUGHNECK CONTROL DEVICE MALFUNCTION AND IMPACT TRIPPING PERFORMANCE. TROUBLE SHOOTING WITH NO SUCCESS.
1154 | 04/10/2022 | SSA-5865 | ABJF-50 | RIG | 10 Apr 0615 - 0715 | 1 | 1 | 895085 |  | RR | FOT | HSYS | 7640 | IRON ROUGHNECK HPU MOTOR MALFUNCTION AFTER TORQUED-UP DRILL PIPE CONNECTION AND COULD NOT RETRACT BACK. HPU ELECTRIC MOTOR NEED TO CHANGE.
1155 | 04/10/2022 | SSA-5914 | WDYH-80 | RIG | 10 Apr 1045 - 1145 | 1 | 1 | 895086 |  | TF | FOT | TESTT | 13703 | WHILE P/U 11" CUP TESTER, OBSERVED DAMAGE ON RUBBER OF CUP TESTER.
1157 | 04/10/2022 | SSA-5914 | WDYH-80 | RIG | 10 Apr 0500 - 0700 | 2 | 2 | 895057 |  | TF | FOT | TESTT | 13703 | OBSERVED LEAK WHILE TESTING LOWER PIPE RAMS THROUGH SES & PJ AND.
1158 | 04/10/2022 | SSA-5914 | WDYH-80 | RIG | 10 Apr 1045 - 1145 | 1 | 1 | 895086 |  | TF | FOT | TESTT | 13703 | WHILE P/U 11" CUP TESTER, OBSERVED DAMAGE ON RUBBER OF CUP TESTER.
1160 | 04/10/2022 | SSA-5962 | HRDH-2230 | ARM | 07 Apr 2130 - 1415 | 9.25 | 64.75 | 895005 |  | TF | FOT | CSG | 4900 | 18-5/8'' CSG PARTED DURING 1ST STAGE CMT JOB WHILE BUMPED DVT PLUG .
1162 | 04/10/2022 | SSA-5969 | UTMN-3021 | RIG | 10 Apr 1200 - 0500 | 17 | 17 | 895087 |  | RR | FOT | TDS | 4720 | TOP DRIVE HYDRAULIC MANIFOLD CRACK
1164 | 04/10/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 8.5 | 702.75 | 893136 |  | STUK | SDIR | RSS | 1867 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1165 | 04/10/2022 | T914 | HWYH-135 | SPS | 10 Apr 1500 - 0500 | 9.5 | 9.5 | 894972 |  | BHA | FOT | LWD | 6491 | NO DATA FROM LWD DINISTY TOOL.
1167 | 04/10/2022 | T914 | HWYH-135 | HUD | 10 Apr 0700 - 2030 | 11.5 | 11.5 | 894971 |  | TF | FOT | MPD | 8096 | LEAKING FROM HALL RCD.
1168 | 04/10/2022 | T914 | HWYH-135 | SPS | 10 Apr 1500 - 0500 | 9.5 | 9.5 | 894972 |  | BHA | FOT | LWD | 6491 | NO DATA FROM LWD DINISTY TOOL.
1170 | 04/11/2022 | ADC-12 | ABQQ-64 | EX1 | 11 Apr 2300 - 0100 | 2 | 2 | 895192 |  | TF | FOT | SLICK | 0 | SLICK LINE UNIT MALFUNCTION
1172 | 04/11/2022 | ADC-45 | KHRS-153 | WWL | 11 Apr 0130 - 0500 | 3.5 | 3.5 | 895193 |  | JF | XTRI | WLT | 0 | DURIING MU LOGGING TOOLS, OBSERVED INCREASE IN W/L TENSION WHILE PULLING TOOLS UP INTO WFD DP.
1174 | 04/11/2022 | ADC-51 | SDGM-1164 | RIG | 11 Apr 1200 - 2030 | 8.5 | 8.5 | 895125 |  | RR | FOT | DWKS | 19100 | DRAWWORKS STOPPED WORKING
1178 | 04/11/2022 | ADES-144 | UTMN-3099 | RIG | 11 Apr 0400 - 0500 | 1 | 1 | 895157 |  | RR | FOT | DWKS | 3020 | WHILE RUN IN HOLE WITH 5.5" DP STD, APPROXIMATELY 45FT FROM KELLY DOWN, DRAWWORK BREAK MALFUNCTIONED RESULTING ON TRAVELING BLOCK TRAVEL DOWN AND TDS PIPE ELEVATOR TO LAND ON ROTARY TABLE.
1180 | 04/11/2022 | ADES-144 | UTMN-3099 | WDV | 11 Apr 2230 - 0100 | 2.5 | 2.5 | 895156 |  | TF | FOT | DV | 2042 | WHILE CLEANING CEMENT ABOVE DV AT 2042 FT, THE WOB SUDDENLY INCREASED AND THE STRING WEIGHT DROPPED FROM 170K TO 45K AND STRING SHIFTED UP RESULTING ON BENDING THE STAND ABOVE THE ROTARY TABLE.
1181 | 04/11/2022 | ADES-144 | UTMN-3099 | RIG | 11 Apr 0400 - 0500 | 1 | 1 | 895157 |  | RR | FOT | DWKS | 3020 | WHILE RUN IN HOLE WITH 5.5" DP STD, APPROXIMATELY 45FT FROM KELLY DOWN, DRAWWORK BREAK MALFUNCTIONED RESULTING ON TRAVELING BLOCK TRAVEL DOWN AND TDS PIPE ELEVATOR TO LAND ON ROTARY TABLE.
1183 | 04/11/2022 | ADES-174 | GHZL-88 | ARM | 11 Apr 0230 - 0500 | 2.5 | 2.5 | 895152 |  | LCIR | UVLC | NA | 9667 | HAD TOTAL LOSS WHILE DRLG. AT 9,667' WITH 100 PCF OBM
1185 | 04/11/2022 | ADM-261 | MRJN-137 | RIG | 11 Apr 1430 - 0500 | 14.5 | 14.5 | 895189 |  | RR | FOT | TDS | 9631 | SECOND GEAR-OIL PUMP FAILURE.
1187 | 04/11/2022 | ADM-262 | MRJN-123 | ARN | 11 Apr 0830 - 1230 | 4 | 4 | 895126 |  | DD | DFOR | RSS | 9862 | FORMATION TOPS CAME DEEPER THAN PLAN, DIRECTIONAL PLAN NEED TO BE REVISED, STOP DRLG AND CIRCULATE HOLE CLEAN.
1189 | 04/11/2022 | ADM-266 | SFNY-934 | ARN | 09 Apr 0500 - 0500 | 24 | 72 | 895074 |  | WO | ORDS | NA | 0 | WAIT ON HSU TO PERFORM SBS & PROVIDE DATA.
1191 | 04/11/2022 | ADM-510 | ABSF-222 | RIG | 11 Apr 1930 - 2230 | 3 | 3 | 895194 |  | JF | HERR | NA | 337 | RIH W. CLEAN OUT ASSLY AND TAGGED ABOVE DV. ATTEMPT TO CIRCULATE AND FOUND STRING PLUGGED
1193 | 04/11/2022 | ADM-511 | MRJN-799 | MSD | 11 Apr 0300 - 0500 | 2 | 2 | 895154 |  | TF | FOT | CRT | 5808 | ALMASAOOD BALES NOT FITTING CORRECTLY TO THE TDS, RD SAME AND RU DRILLING BALES
1195 | 04/11/2022 | AOD-11 | SFNY-4250 | HWP | 11 Apr 1045 - 1230 | 1.75 | 1.75 | 895155 |  | TF | FOT | WLT | 6505 | HALLIBURTON RDT TOOL STRING FAILURE DUE TO ELECTRICAL ISSUE.
1197 | 04/11/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 159 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1199 | 04/11/2022 | BCTD-4 | GHZL-67 | RIG | 10 Apr 0300 - 1930 | 12 | 14 | 895096 |  | BHA | FOT | CTAC | 14414 | SLOW DRILLING AND HIGH DIFFERENTIAL PRESSURE.
1201 | 04/11/2022 | DPS-4 | MDRK-54 | SDM | 10 Apr 0015 - 2045 | 15.75 | 20.5 | 895094 |  | TF | XTTE | MWD | 2400 | NO MWD SIGNAL WHILE PERFORM SHALLOW TEST.
1206 | 04/11/2022 | ED-85A | ZULF-2060 | RIG | 11 Apr 1030 - 1545 | 5.25 | 5.25 | 895186 |  | RR | FOT | RWCS | 6731 | PRESSURE TEST TOP RAMS AND ANNULAR NOT HOLDING, LEAK IN THE TESTING ASSEMBLY.
1208 | 04/11/2022 | HI-4 | SFNY-918 | BC | 09 Apr 2300 - 0500 | 24 | 54 | 894970 |  | TF | FOT | SSSV | 0 | OBSERVED BAKERHUGHES TRSSSV ON WELL BRRI-786 PASSING PRESSURE WHILE HANDOVER PLATFORM TO PRODUCTION.
1210 | 04/11/2022 | NBR-196S | SDGM-1226 | SJC | 11 Apr 1500 - 0500 | 14 | 14 | 895147 |  | TF | FOT | PUMP | 10329 | WHILE PUMPING 9-5/8" LINER CMT JOB SANJEL CMT UNIT COULD NOT MAINTANE EVEN CMT SLURRY WT WAS BETWEEN 101 TO 113 PCF & SHOULD OF BEEN 118 PCF. CMT UNIT PLUGGED DURING PUMPING AND NOT ABLE TO CONTINUE WITH LINER CMT JOB.
1212 | 04/11/2022 | PA-218S | QTIF-515 | RIG | 10 Apr 1200 - 1600 | 7 | 9 | 895091 |  | RR | FOT | DWKS | 23883 | MULFUNCTION OF DRAWWORKS HIGH GEAR.
1214 | 04/11/2022 | SA5898 | HRDH-1978 | WWL | 11 Apr 1730 - 0300 | 9.5 | 9.5 | 895166 |  | WO | MATL | NA | 0 | WAIT TO RECIEVE WFD SAMPLING LOGGING TOOLS
1216 | 04/11/2022 | SINO-12L | HRDH-1454 | HSL | 11 Apr 2000 - 2300 | 3 | 3 | 895153 |  | TF | FOT | SLICK | 6886 | SLICKLINE UNIT HYDRAULIC SYSTEM FAILED.
1220 | 04/11/2022 | SND-2006 | UTMN-3135 | EMC | 09 Apr 1900 - 1700 | 12 | 34 | 895106 |  | MUD | HSCM | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1222 | 04/11/2022 | SND-2006 | UTMN-3135 | RIG | 09 Apr 0900 - 0500 | 12 | 34 | 895080 |  | JF | HERR | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1223 | 04/11/2022 | SND-2006 | UTMN-3135 | EMC | 09 Apr 1900 - 1700 | 12 | 34 | 895106 |  | MUD | HSCM | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1225 | 04/11/2022 | SSA-201 | HRDH-1818 | RIG | 11 Apr 1930 - 0330 | 8 | 8 | 895151 |  | RR | FOT | TDS | 0 | TDS ELECTRICAL GROUND FAULT PROBLEM
1227 | 04/11/2022 | SSA-29 | QTIF-348 | RIG | 11 Apr 1800 - 0300 | 9 | 9 | 895168 |  | RR | FOT | DWKS | 2300 | MECHANICAL FAILURE IN DRAWWORK MOTOR FLEXIBLE COUPLING #1.
1229 | 04/11/2022 | SSA-302 | HRDH-2113 | RTC | 09 Apr 0500 - 0500 | 24 | 72 | 895073 |  | TF | FOT | BIT | 5177 | LOW ROP AND HIGH TQ. ( ROTARY STALLING ) POOH LOST 2 CONES OFF OF BIT
1231 | 04/11/2022 | SSA-5820 | SDGM-1215 | ARM | 11 Apr 0800 - 0900 | 1 | 1 | 895099 |  | WON | WTHR | NA | 6616 | STOP RUNNING CASING DUE TO HIGH WINDS, BLOWING SERVICE LOOP I TO DERRICK, RISK OF SNAG AND DAMAGE.
1233 | 04/11/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 13.75 | 133.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1235 | 04/11/2022 | SSA-5969 | UTMN-3021 | RIG | 10 Apr 1200 - 0900 | 4 | 21 | 895087 |  | RR | FOT | TDS | 4720 | TOP DRIVE HYDRAULIC MANIFOLD CRACK
1236 | 04/11/2022 | SSA-5970 | HWYH-1257 | SDM | 11 Apr 0615 - 0500 | 22.75 | 22.75 | 895149 |  | BHA | FOT | LWD | 18032 | FAILURE OF SLB LWD
1238 | 04/11/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0615 | 1.25 | 704 | 893136 |  | STUK | SDIR | RSS | 1867 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1239 | 04/11/2022 | SSA-5970 | HWYH-1257 | SDM | 11 Apr 0615 - 0500 | 22.75 | 22.75 | 895149 |  | BHA | FOT | LWD | 18032 | FAILURE OF SLB LWD
1240 | 04/11/2022 | SSA-5971 | UTMN-2302 | ARM | 11 Apr 2100 - 0500 | 8 | 8 | 895190 |  | TH | NARW | NA | 13675 | HAD OBSTRUCTION WHILE RIH WITH LOGGING TOOLS @ 13,675'
1242 | 04/11/2022 | SSA-5971 | UTMN-2302 | BAW | 11 Apr 0630 - 2100 | 14.5 | 14.5 | 895187 |  | TF | FOT | WLT | 13765 | LOST SEAL WHILE TAKING FLUID SAMPLE @ 13,765 AFTER 3.5 HR'S, MANY TRIALS TO SEAL BACK WITHOUT SUCCESS, POOH TO INSIDE 7" LINER, TRIALS TO GET SEAL BACK WITH OUT SUCCESS.
1243 | 04/11/2022 | SSA-5971 | UTMN-2302 | ARM | 11 Apr 2100 - 0500 | 8 | 8 | 895190 |  | TH | NARW | NA | 13675 | HAD OBSTRUCTION WHILE RIH WITH LOGGING TOOLS @ 13,675'
1245 | 04/11/2022 | T907 | DYBN-2 | SPS | 11 Apr 0200 - 0500 | 3 | 3 | 895191 |  | BHA | FOT | MWD | 10945 | UNABLE TO COMMUNICATE WITH HALL RSS
1247 | 04/11/2022 | T914 | HWYH-135 | SPS | 10 Apr 1500 - 2300 | 18 | 27.5 | 894972 |  | BHA | FOT | LWD | 6491 | NO DATA FROM LWD DENSITY TOOL.
1249 | 04/11/2022 | V140A | RBYN-100 | SWT | 11 Apr 0015 - 0115 | 1 | 1 | 895206 |  | HSEI | UNKN | NA | 6740 | SLB WELL TEST OPERATOR HIT HIS FINGER WHILE USE HAMMER DURING RIG UP WELL TEST EQUIPMENT.
1251 | 04/11/2022 | ZPEC-1 | HMYM-846 | RIG | 11 Apr 0500 - 1930 | 14.5 | 14.5 | 895188 |  | BOP | LHFL | RWCS | 3700 | WHILE PERFORMING PRESSURE TEST ON BOP THE PRESSUER NOT HOLDING AND DROPPED 100 PSI, FOUND LEAK ON SEAL OF ANNULAR, REPLACED BOP WITH OTHER ONE.
1253 | 04/12/2022 | ADC-45 | KHRS-153 | WWL | 11 Apr 0130 - 0900 | 4 | 7.5 | 895193 |  | JF | XTRI | WLT | 0 | DURIING MU LOGGING TOOLS, OBSERVED INCREASE IN W/L TENSION WHILE PULLING TOOLS UP INTO WFD DP.
1254 | 04/12/2022 | ADC-56L | UTMN-2330 | MI2 | 12 Apr 1800 - 2100 | 3 | 3 | 895312 |  | HC | DFLI | NA | 6600 | WHILE DRILLING CEMENT IN 18 5/8" SHOE TRACK H2S ALRM SOUNDED. CLOSED IN WELL AND MUSTERED.
1256 | 04/12/2022 | ADC-56L | UTMN-2330 | RIG | 12 Apr 0530 - 1300 | 3.5 | 3.5 | 895310 |  | RR | FOT | TDS | 6600 | WHILE P/U DP OBSERVED HYRAULIC LEAK FROM TDS LINK TILT TANK
1257 | 04/12/2022 | ADC-56L | UTMN-2330 | MI2 | 12 Apr 1800 - 2100 | 3 | 3 | 895312 |  | HC | DFLI | NA | 6600 | WHILE DRILLING CEMENT IN 18 5/8" SHOE TRACK H2S ALRM SOUNDED. CLOSED IN WELL AND MUSTERED.
1259 | 04/12/2022 | ADES-144 | UTMN-3099 | RIG | 11 Apr 0400 - 1800 | 13 | 14 | 895157 |  | RR | FOT | DWKS | 3020 | WHILE RUN IN HOLE WITH 5.5" DP STD, APPROXIMATELY 45FT FROM KELLY DOWN, DRAWWORK BREAK MALFUNCTIONED RESULTING ON TRAVELING BLOCK TRAVEL DOWN AND TDS PIPE ELEVATOR TO LAND ON ROTARY TABLE.
1261 | 04/12/2022 | ADM-261 | MRJN-137 | RIG | 11 Apr 1430 - 0715 | 2.25 | 16.75 | 895189 |  | RR | FOT | TDS | 9631 | SECOND GEAR-OIL PUMP FAILURE.
1263 | 04/12/2022 | ADM-266 | SFNY-934 | ARN | 09 Apr 0500 - 0500 | 24 | 96 | 895074 |  | WO | ORDS | NA | 0 | WAIT ON HSU TO PERFORM SBS & PROVIDE DATA.
1264 | 04/12/2022 | ADM-511 | MRJN-799 | MSD | 12 Apr 0945 - 1100 | 1.25 | 1.25 | 895246 |  | TF | FOT | CTRQ | 5808 | MU FIRST 13 3/8" CSG JT AFTER SHOE TRACK JTS TO 30 KFT.LB AS PER PLAN, TRY TO DISENGAGE CRT, CONNECTION BACKED OUT FROM XO BETWEEN CRT & SAVER SUB, MU THE XO TO 55 KFT.LB, OK.
1266 | 04/12/2022 | ADM-511 | MRJN-799 | MSD | 11 Apr 0300 - 0615 | 1.25 | 3.25 | 895154 |  | TF | FOT | CRT | 5808 | ALMASAOOD BALES NOT FITTING CORRECTLY TO THE TDS, RD SAME AND RU DRILLING BALES
1267 | 04/12/2022 | ADM-511 | MRJN-799 | MSD | 12 Apr 0945 - 1100 | 1.25 | 1.25 | 895246 |  | TF | FOT | CTRQ | 5808 | MU FIRST 13 3/8" CSG JT AFTER SHOE TRACK JTS TO 30 KFT.LB AS PER PLAN, TRY TO DISENGAGE CRT, CONNECTION BACKED OUT FROM XO BETWEEN CRT & SAVER SUB, MU THE XO TO 55 KFT.LB, OK.
1268 | 04/12/2022 | ARO-3001 | ZULF-2058 | BAW | 12 Apr 0600 - 0500 | 23 | 23 | 895327 |  | TF | FOT | WLT | 9598 | BAKER DECT CUTTER UNABLE TO CUT TBG DUE TO BROKEN BLADE.
1270 | 04/12/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0600 | 1 | 160 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1271 | 04/12/2022 | ARO-3001 | ZULF-2058 | BAW | 12 Apr 0600 - 0500 | 23 | 23 | 895327 |  | TF | FOT | WLT | 9598 | BAKER DECT CUTTER UNABLE TO CUT TBG DUE TO BROKEN BLADE.
1273 | 04/12/2022 | CG-1 | ZULF-1203 | RIG | 08 Apr 1615 - 2200 | .75 | 1.5 | 895067 |  | RR | FOT | HSYS | 2044 | TROUBLESHOOTING ON PRS SYSTEM (PIPE RACKING SYSTEM).
1278 | 04/12/2022 | DQ-57L | KHRS-233 | HWP | 12 Apr 2330 - 0500 | 5.5 | 5.5 | 895332 |  | TF | FOT | WLT | 7916 | - HAD LOWER QUALITY OF CALIPER/IMAGE LOGGING DATA.
1280 | 04/12/2022 | HI-4 | SFNY-918 | BC | 12 Apr 0500 - 0500 | 24 | 24 | 895307 |  | WO | WOTO | NA | 0 | WAIT ON REQUIRED CREW AND EQUIPMENT FOR WELL BRRI-786 TRSSSV FAILURE.
1282 | 04/12/2022 | NBR-196S | SDGM-1226 | SJC | 11 Apr 1500 - 1000 | 5 | 19 | 895147 |  | TF | FOT | PUMP | 10329 | WHILE PUMPING 9-5/8" LINER CMT JOB SANJEL CMT UNIT COULD NOT MAINTANE EVEN CMT SLURRY WT WAS BETWEEN 101 TO 113 PCF & SHOULD OF BEEN 118 PCF. CMT UNIT PLUGGED DURING PUMPING AND NOT ABLE TO CONTINUE WITH LINER CMT JOB DUE TO FAILED FLOWMETER.
1284 | 04/12/2022 | NBR-783S | NJYN-89 | RIG | 12 Apr 2130 - 2330 | 2 | 2 | 895309 |  | RR | FOT | MPMP | 300 | GOT AIR ON MUD PUMP SUCTION LINES WHILE MWD SHALLOW TEST.
1286 | 04/12/2022 | PA-218S | QTIF-515 | RIG | 12 Apr 0615 - 0715 | 1 | 1 | 895226 |  | DSF | HERR | DP | 23883 | STAND DOWN MEETING TO DISCUSSES A HIGH POTENTIAL NEARMISS. THE DERRICK MAN MISSED THE ELEVATOR WHEN HE TRIED TO LATCH AND PIPE WENT TO OTHER SIDE OF THE DERRICK.
1288 | 04/12/2022 | PA-326S | WDYH-16 | FMC | 12 Apr 1330 - 1600 | 2.5 | 2.5 | 895326 |  | JF | XTRI | CTRQ | 4168 | EXCESS TIME TO MAKE UP SHOE TRACK
1290 | 04/12/2022 | SINO-27N | UTMN-432 | RIG | 12 Apr 1200 - 1330 | 1.5 | 1.5 | 895329 |  | RR | FOT | TDS | 7805 | WHILE DRLG @ 7805' OBSERVE SMALL LEAK FROM TDS SAVER SUB CONNECTION.
1292 | 04/12/2022 | SINO-47 | HRDH-1957 | BLH | 12 Apr 1830 - 0500 | 10.5 | 10.5 | 895306 |  | TF | FOT | SEAL | 10149 | BAKER 9-5/8" TIE-BACK SEAL ASSY NOT HOLDING PRESSURE AFTER STING INTO TBR.
1294 | 04/12/2022 | SINO21 | ABQQ-430 | SDM | 12 Apr 2100 - 0500 | 8 | 8 | 895330 |  | LROP | IDPR | BHA | 6470 | LOW ROP.
1295 | 04/12/2022 | SND-2006 | UTMN-3135 | EMC | 09 Apr 1900 - 0500 | 12 | 46 | 895106 |  | MUD | HSCM | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1297 | 04/12/2022 | SND-2006 | UTMN-3135 | RIG | 09 Apr 0900 - 1700 | 12 | 46 | 895080 |  | JF | HERR | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1298 | 04/12/2022 | SND-2006 | UTMN-3135 | EMC | 09 Apr 1900 - 0500 | 12 | 46 | 895106 |  | MUD | HSCM | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1300 | 04/12/2022 | SND-2007 | ADHN-370100 | RIG | 12 Apr 0600 - 1530 | 9.5 | 9.5 | 895328 |  | RR | FOT | DWKS | 16145 | SANAD EMS REPLACED FAULTY EDDY CURRENT BRAKE UNIT
1302 | 04/12/2022 | SP-306 | MNIF-197 | WCR | 12 Apr 1230 - 1530 | 3 | 3 | 895286 |  | TF | FOT | CTRQ | 4649 | MALFUNCTION OF WEATHERFORD TRS EQUIPMENT, FIX & SET UP SAME.
1304 | 04/12/2022 | SSA-302 | HRDH-2113 | RTC | 09 Apr 0500 - 0500 | 21.5 | 93.5 | 895073 |  | TF | FOT | BIT | 5177 | LOW ROP AND HIGH TQ. ( ROTARY STALLING ) POOH LOST 2 CONES OFF OF BIT
1306 | 04/12/2022 | SSA-303 | HRDH-2306 | RIG | 12 Apr 1630 - 0330 | 11 | 11 | 895266 |  | RR | FOT | TDS | 793 | OBSERVED LEAKING IN HYDRAULIC GRAPPLE HOSE ON TOPDRIVE. CHANGE OUT SAME
1308 | 04/12/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 21.75 | 155.25 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1310 | 04/12/2022 | SSA-5962 | HRDH-2230 | ARM | 07 Apr 2130 - 0500 | 24 | 98.75 | 895005 |  | TF | FOT | CSG | 4900 | 18-5/8'' CSG PARTED DURING 1ST STAGE CMT JOB WHILE BUMPED DVT PLUG .
1312 | 04/12/2022 | SSA-5970 | HWYH-1257 | SDM | 11 Apr 0815 - 0500 | 24 | 44.75 | 895149 |  | BHA | FOT | LWD | 18032 | FAILURE OF SLB LWD
1314 | 04/12/2022 | T907 | DYBN-2 | SPS | 11 Apr 0200 - 2300 | 18 | 21 | 895191 |  | BHA | FOT | MWD | 10935 | UNABLE TO COMMUNICATE WITH HALL RSS
1316 | 04/12/2022 | WCL-83 | MRJN-837 | BHI | 12 Apr 2300 - 2345 | .75 | .75 | 895331 |  | BHA | FOT | MWD | 12560 | BHI MWD HAD VIBRATION AND BAD DE-CODING. SEND DOWN LINKS AND RE-CYCLED MUP PUMPS.
1318 | 04/12/2022 | ZPEC-2 | HMYM-847 | ARM | 11 Apr 0230 - 0300 | 22 | 24.5 | 895308 |  | BHS | CWEL | NA | 125 | OBSERVED HOLE CAVED AFTER POOH W/ 34" SLICK BHA TO SURFACE.
1320 | 04/13/2022 | ADC-58L | ABHD-178 | TK3 | 13 Apr 0030 - 0400 | 3.5 | 3.5 | 895427 |  | WO | SRVC | NA | 4320 | PRECAUTIONARY SUSBENDED OPERATION AS THE RIG AMBULANCE AND THE MEDIC WAS SENT AS EMERGENCY TO THE HOSPITAL WITH THE CAMPBOSS (PATIENT) WHO WAS SUFFERING V.HIGH BLOOD PRESSURE AND DIFFICULTY IN BREATHING.
1322 | 04/13/2022 | ADM-266 | SFNY-934 | ARN | 09 Apr 0500 - 0500 | 24 | 120 | 895074 |  | WO | ORDS | NA | 0 | WAIT ON HSU TO PERFORM SBS & PROVIDE DATA.
1324 | 04/13/2022 | AOD-11 | SFNY-4250 | HWP | 13 Apr 1630 - 1900 | 2.5 | 2.5 | 895413 |  | TF | FOT | WLT | 6505 | WHILE WORKING STRING TO NEXT VIT POINT, OBSERVED WIRELINE CABLE MISSING A STRAND OF CABLE,.
1325 | 04/13/2022 | ARO-3001 | ZULF-2058 | BAW | 12 Apr 0600 - 0545 | .75 | 23.75 | 895327 |  | TF | FOT | WLT | 9598 | BAKER DECT CUTTER UNABLE TO CUT TBG DUE TO BROKEN BLADE.
1327 | 04/13/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 1545 | 10 | 170 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1328 | 04/13/2022 | ARO-3001 | ZULF-2058 | BAW | 12 Apr 0600 - 0545 | .75 | 23.75 | 895327 |  | TF | FOT | WLT | 9598 | BAKER DECT CUTTER UNABLE TO CUT TBG DUE TO BROKEN BLADE.
1330 | 04/13/2022 | ARO-4001 | MRJN-539 | RIG | 13 Apr 0230 - 0500 | 2.5 | 2.5 | 895418 |  | UPRA | FRCM | RWCS | 15545 | CHANGE OUT E-KILL COFFLEX HOSE
1335 | 04/13/2022 | DQ-57L | KHRS-233 | HWP | 12 Apr 2330 - 2330 | 18.5 | 24 | 895332 |  | TF | FOT | WLT | 7916 | - HAD LOWER QUALITY OF CALIPER/IMAGE LOGGING DATA.
1337 | 04/13/2022 | ENSCO-54 | ABSF-31 | KSC | 13 Apr 1800 - 2200 | 4 | 4 | 895408 |  | TF | FOT | ESPL | 0 | ALKHORAYEF CABLE SPOOLING MACHINE DOWN, TROUBLESHOOT WITHOUT SUCCESS, REPLACED SAME WITH THE BACKUP SPOOLING MACHINE.
1339 | 04/13/2022 | HI-4 | SFNY-918 | BC | 09 Apr 2300 - 0500 | 24 | 78 | 894970 |  | TF | FOT | SSSV | 0 | OBSERVED BAKERHUGHES TRSSSV ON WELL BRRI-786 PASSING PRESSURE WHILE HANDOVER PLATFORM TO PRODUCTION.
1341 | 04/13/2022 | MP-1 | SFNY-994 | RIG | 13 Apr 0800 - 1115 | 3.25 | 3.25 | 895406 |  | TF | HERR | TBG | 0 | OBSERVED ESP CABLE INSULATION DAMAGED DUE TO RUNNING BPV. CHECKED CABLE INTEGRITY, OK. ARAMCO ARTIFICIAL LIFT ENGINEER ONBOARD EVALUATED & MADE DECISION TO PROCEED WITH ESP FLOW TEST.
1343 | 04/13/2022 | PA-218S | QTIF-515 | RIG | 13 Apr 1130 - 1215 | .75 | .75 | 895407 |  | RR | FOT | CATW | 23883 | HAD A LEAKED HYDRAULIC HOSE IN AUTOMATIC CAT WALK.
1345 | 04/13/2022 | PA-622S | AFLJ-4 | WCR | 13 Apr 1745 - 2145 | 4 | 4 | 895426 |  | TF | XTTE | CTRQ | 6530 | EXCESSIVE TIME MAKING UP CASING CONNECTIONS, TROBLESHOOT CASING JAM UNIT & POWER TONG
1347 | 04/13/2022 | PA-785S | QTIF-641 | RIG | 13 Apr 1200 - 1500 | 3 | 3 | 895386 |  | RR | FOT | TDS | 6290 | TDS WASH PIPE STARTED LEAKING WHILE RIH WITH 6-1/8" STIFF ASSY AT 6290FT
1349 | 04/13/2022 | RM-74A | KARN-60 | RIG | 13 Apr 2030 - 2130 | 1 | 1 | 895411 |  | RR | FOT | FLR | 12410 | ARO TROUBLESHOOTING PORT FLARE BOOM IGNITION SYSTEM
1351 | 04/13/2022 | SA5898 | HRDH-1978 | WWL | 13 Apr 1300 - 0400 | 15 | 15 | 895409 |  | TF | FOT | WLT | 11088 | WFD HAD MISS COMMUNICATION WITH SAMPLING TOOL & FIALED TO TAKE SAMPLE @ 11082', TROUBLSHOOTING TOOL WITHOUT SUCCESS.
1357 | 04/13/2022 | SINO-47 | HRDH-1957 | BLH | 12 Apr 1830 - 0500 | 24 | 34.5 | 895306 |  | TF | FOT | SEAL | 10149 | BAKER 9-5/8" TIE-BACK SEAL ASSY NOT HOLDING PRESSURE AFTER STING INTO TBR.
1362 | 04/13/2022 | SL-7 | ZULF-1331 | SPS | 13 Apr 0230 - 0500 | 2.5 | 2.5 | 895415 |  | DD | HERR | MMOT | 5645 | SPERRY SUN FAILED TO SIDE TRACK WELL AWAY FROM MB & L-1
1364 | 04/13/2022 | SND-2004 | BRRI-1148 | SJC | 13 Apr 1130 - 1200 | .5 | .5 | 895419 |  | CMT | CFST | NA | 3225 | PRESSURE INCREASE WHILE DISPLACEMENT OF THE LAST 184 BBLS OF 18-5/8" CSG 1ST STAGE CEMENT JOB.
1365 | 04/13/2022 | SND-2006 | UTMN-3135 | EMC | 09 Apr 1900 - 1600 | 11 | 57 | 895106 |  | MUD | HSCM | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1367 | 04/13/2022 | SND-2006 | UTMN-3135 | RIG | 09 Apr 0900 - 0300 | 11 | 57 | 895080 |  | JF | HERR | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1368 | 04/13/2022 | SND-2006 | UTMN-3135 | EMC | 09 Apr 1900 - 1600 | 11 | 57 | 895106 |  | MUD | HSCM | NA | 14281 | TAGGED 508' OF FORMATION CUTTINGS INSIDE 4-1/2" LINER DURING FINAL DRIFT
1370 | 04/13/2022 | SP-261 | HZEM-162204 | SPR | 11 Apr 1715 - 1145 | 6.75 | 42.5 | 895346 |  | TF | FOT | CTRQ | 18130 | UN-ABLE TO DRIFT CASING DUE TO DAMAGED COUPLINGS CAUSED BY SAPESCO CRT. PULL CASING AND REPLACE CASING.
1372 | 04/13/2022 | SSA-302 | HRDH-2113 | RTC | 09 Apr 0500 - 0145 | 20.75 | 116.75 | 895073 |  | TF | FOT | BIT | 5177 | LOW ROP AND HIGH TQ. ( ROTARY STALLING ) POOH LOST 2 CONES OFF OF BIT
1374 | 04/13/2022 | SSA-303 | HRDH-2306 | RIG | 13 Apr 2330 - 0230 | 3 | 3 | 895428 |  | RR | FOT | TDS | 1201 | THE PAD EYE OF TILT PISTON ONTDS LINK WAS BROKEN
1376 | 04/13/2022 | SSA-5891 | HRDH-2016 | HSL | 13 Apr 0730 - 0915 | 1.75 | 1.75 | 895366 |  | WO | WOTO | NA | 0 | MISSING CROSS OVER FROM LUBRICATOR TO X TREE.
1378 | 04/13/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 16.5 | 171.75 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1380 | 04/13/2022 | SSA-5962 | HRDH-2230 | WCM | 07 Apr 2130 - 0500 | 3.5 | 102.25 | 895005 |  | TF | CCAT | CSTR | 2280 | WFD DV PORTS PREMATURE OPENED WHILE PUMPING FIRST STAGE SHUT OFF PLUG.
1382 | 04/13/2022 | SSA-5964 | HRDH-1343 | BCM | 13 Apr 1600 - 0500 | 13 | 13 | 895416 |  | CMT | HERR | NA | 12915 | TAQA BULKER CONTINUALLY BLOCKED CAUSING TAQA TO TAKE 2 1/2 HOURS TO MIX 34 BBLS OF 125 PCF. AFTER CONSULTING ARAMCO CEMENT SPECIALIST , THE DECISION WAS MADE TO DUMP CEMENT MIXTURE.
1383 | 04/13/2022 | SSA-5970 | HWYH-1257 | SDM | 11 Apr 0815 - 1245 | 7.75 | 52.5 | 895149 |  | BHA | FOT | LWD | 18032 | FAILURE OF SLB LWD
1385 | 04/13/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0430 | 15.75 | 723.25 | 893136 |  | STUK | SDIR | RSS | 1867 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1386 | 04/13/2022 | SSA-5970 | HWYH-1257 | SDM | 11 Apr 0815 - 1245 | 7.75 | 52.5 | 895149 |  | BHA | FOT | LWD | 18032 | FAILURE OF SLB LWD
1388 | 04/13/2022 | SSA-5972 | JFYN-10 | RIG | 13 Apr 1700 - 2000 | 3 | 3 | 895417 |  | RR | FOT | RWCS | 0 | RIG CHANGED AND INSTALLED NEW IBOP AND TESTED 5000 PSI OK.
1390 | 04/13/2022 | V141A | MRJN-758 | SCP | 13 Apr 1430 - 0500 | 14.5 | 14.5 | 895410 |  | TF | FOT | SEAL | 5828 | UNABLE TO OPEN SLB MFIV WITH MECHANICAL SHIFTING TOOL.
1395 | 04/14/2022 | ADC-55L | UTMN-3199 | TSC | 14 Apr 2100 - 2200 | 1 | 1 | 895492 |  | TF | FOT | CTRQ | 10756 | HYDRAULIC CATWALK MALFUNCTION WHILE PICK UP CSG.
1400 | 04/14/2022 | ADES-144 | UTMN-3099 | RIG | 14 Apr 1800 - 2300 | 5 | 5 | 895508 |  | RR | FOT | TDS | 6625 | REPAIR ON TDS SAVER SUB AND ACTUATOR SUB LEAKED & LOSE CONNECTION.
1402 | 04/14/2022 | ADES-798 | JFYN-11 | ARM | 13 Apr 1030 - 2330 | 18.5 | 21.5 | 895466 |  | LCIR | UVLC | NA | 15387 | SEVERE LOSSES AT TOP OF UNZ-B RESERVOIR.
1404 | 04/14/2022 | ADM-266 | SFNY-934 | ARN | 09 Apr 0500 - 0500 | 24 | 144 | 895074 |  | WO | ORDS | NA | 0 | WAIT ON HSU TO PERFORM SBS & PROVIDE DATA.
1406 | 04/14/2022 | ADM-337 | MRJN-900 | BLH | 14 Apr 0400 - 0500 | 1 | 1 | 895475 |  | TF | FOT | HGRL | 11858 | LINER HANGER DID NOT SET AFTER DROPPING FIRST SETTING BALL.
1408 | 04/14/2022 | ADM-510 | ABSF-222 | SPS | 11 Apr 1930 - 0500 | 10 | 13 | 895194 |  | DD | UDWL | RSS | 6568 | SPERRY UNABLE TO ACHIEVE WELL PATH AS PER DIRECTIONAL PLAN REQUIREMENTS, 8.8FT RIGHT OF THE PLAN @ 6568FT & INCREASING DUE TO BEENING UNABLE TO TURN TO LEFT
1410 | 04/14/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 15.25 | 185.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1411 | 04/14/2022 | ARO-4001 | MRJN-539 | HML | 14 Apr 1930 - 2000 | .5 | .5 | 895489 |  | TF | FOT | WPSML | 8300 | WORKING ON MILLING MACHINE TO RETURN IT TO IT'S PROFILE.
1413 | 04/14/2022 | ARO-4001 | MRJN-539 | RIG | 13 Apr 0230 - 1300 | 8 | 10.5 | 895418 |  | UPRA | IRES | RWCS | 15545 | CHANGE OUT E-KILL COFFLEX HOSE
1414 | 04/14/2022 | ARO-4001 | MRJN-539 | HML | 14 Apr 1930 - 2000 | .5 | .5 | 895489 |  | TF | FOT | WPSML | 8300 | WORKING ON MILLING MACHINE TO RETURN IT TO IT'S PROFILE.
1416 | 04/14/2022 | DPS-4 | MDRK-54 | ARM | 14 Apr 2145 - 0500 | 7.25 | 7.25 | 895515 |  | WCNT | WCC5 | NA | 16095 | OBSERVED WELL FLOWING AT 0.4 BPH DURING FLOW CHECK.
1418 | 04/14/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 45.5 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1423 | 04/14/2022 | ENSCO-54 | ABSF-31 | HCO | 14 Apr 0130 - 0430 | 3 | 3 | 895512 |  | TF | FOT | SSSV | 0 | ATTEMPT TO SET WRSSV WITHOUT SUCCESS, TROUBLESHOOT, POH TO CHECK THE VALVE SEALS.
1425 | 04/14/2022 | ENSCO-76 | MRJN-851 | RIG | 14 Apr 0430 - 0500 | .5 | .5 | 895511 |  | BOP | FOT | BOP | 6100 | RIG ACCUMULATOR FAIL TO PASS ARAMCO WELL CONTROL STANDARDS.
1427 | 04/14/2022 | HI-4 | SFNY-918 | BC | 09 Apr 2300 - 0500 | 24 | 102 | 894970 |  | TF | FOT | SSSV | 0 | OBSERVED BAKERHUGHES TRSSSV ON WELL BRRI-786 PASSING PRESSURE WHILE HANDOVER PLATFORM TO PRODUCTION.
1429 | 04/14/2022 | MP-1 | SFNY-994 | AP2 | 14 Apr 0800 - 0500 | 21 | 21 | 895507 |  | WO | WOPF | NA | 0 | WAITING ON SAFANIYA GOSP TO GIVE PERMISSION FOR FLOWBACK.
1431 | 04/14/2022 | NA-207S | SHYB-194 | RIG | 14 Apr 0700 - 0830 | 1.5 | 1.5 | 895423 |  | RR | FOT | PSYS | 1600 | WHILE RIH CLEAN OUT ASSY, HAD POWER SHUT-IN OF 4 X RIG GENERATORS DUE TO HUMAN ERROR (SOMEONE CLOSED DIESEL VALVE FEEDING GENERATOS).
1432 | 04/14/2022 | NBR-797S | UTMN-3130 | RIG | 14 Apr 2200 - 0200 | 4 | 4 | 895510 |  | RR | FOT | TDS | 1305 | TDS UNRESPONSIVE & SHUTTING DOWN, BLOWER MOTOR FRAME CRACKED
1434 | 04/14/2022 | NBR-797S | UTMN-3130 | RIG | 14 Apr 0830 - 1515 | 2 | 2 | 895509 |  | RR | FOT | TDS | 1054 | TDS UNRESPONSIVE & SHUTTING DOWN
1435 | 04/14/2022 | NBR-797S | UTMN-3130 | RIG | 14 Apr 2200 - 0200 | 4 | 4 | 895510 |  | RR | FOT | TDS | 1305 | TDS UNRESPONSIVE & SHUTTING DOWN, BLOWER MOTOR FRAME CRACKED
1437 | 04/14/2022 | PA-326S | WDYH-16 | CAM | 14 Apr 0500 - 2200 | 17 | 17 | 895486 |  | WH | FOT | WH | 0 | PACK-OFF SEALS NOT FULLY ENGAGED INTO CSG SPOOL.
1439 | 04/14/2022 | PA-70S | MDRK-64 | ARM | 14 Apr 0800 - 0830 | .5 | .5 | 895447 |  | STUK | STBH | CORC | 15800 | STRING GOT STUCK AFTER CONNECTION @ 15,800'.
1441 | 04/14/2022 | SINO-10 | JLDI-37 | ARM | 14 Apr 1115 - 1700 | 5.75 | 5.75 | 895490 |  | BHS | CWEL | NA | 7685 | OBSEDVED SUDDEN LOST RETURN & ANNULUS LEVEL STATIC, PRESSURE INCREASED TO 1500 PSI DUE TO HOLE BACK OFF
1443 | 04/14/2022 | SINO-11 | HWTH-806 | KSC | 14 Apr 2000 - 2300 | 3 | 3 | 895491 |  | TF | FOT | ESP | 0 | WHILE M/U NEW ESP PUMP, BOLT GOT BROKEN INSIDE THE PUMP THREADS.
1445 | 04/14/2022 | SINO-22 | BRRI-381 | MSD | 14 Apr 0015 - 0130 | 1.25 | 1.25 | 895473 |  | TF | FOT | TTRQ | 12197 | OBSERVE POWER TONG NOT ABLE TO APPLY THE REQUIRED TORQUE. AL-MASAOOD TROUBLESHOOT POWER TONG AND POWER UNIT SEVERAL TIMES WITHOUT SUCCESS, REPLACE BOTH.
1447 | 04/14/2022 | SINO-25 | MNIF-300 | SLL | 14 Apr 1700 - 2000 | 3 | 3 | 895450 |  | TF | FOT | PLUGT | 5485 | FAILED TO SET SLB PUMP THRU PLUG @ 5485 FT.
1449 | 04/14/2022 | SINO-47 | HRDH-1957 | BLH | 12 Apr 1830 - 0500 | 19 | 49.5 | 895306 |  | TF | FOT | SEAL | 10149 | BAKER 9-5/8" TIE-BACK SEAL ASSY NOT HOLDING PRESSURE AFTER STING INTO TBR.
1450 | 04/14/2022 | SINO21 | ABQQ-430 | ARM | 14 Apr 0345 - 0500 | 1.25 | 1.25 | 895476 |  | WO | SRVC | NA | 6504 | V-SAT DOWN.
1452 | 04/14/2022 | SINO21 | ABQQ-430 | ARM | 12 Apr 2100 - 1800 | 2 | 10 | 895330 |  | WO | SRVC | NA | 6470 | LOW ROP.
1453 | 04/14/2022 | SINO21 | ABQQ-430 | ARM | 14 Apr 0345 - 0500 | 1.25 | 1.25 | 895476 |  | WO | SRVC | NA | 6504 | V-SAT DOWN.
1455 | 04/14/2022 | SL-7 | ZULF-1331 | SPS | 13 Apr 0230 - 2000 | 15 | 17.5 | 895415 |  | DD | HERR | MMOT | 5645 | EXCESSIVE TIME TO SIDE TRACK HOLE
1457 | 04/14/2022 | SND-3002 | DMMM-602 | RAC | 14 Apr 2130 - 0500 | 7.5 | 7.5 | 895472 |  | TF | FOT | CUT | 7701 | ATTEMPT TO CLOSE SSD WITH RAWABI SSD SHIFTING TOOL- NO SUCCESS
1459 | 04/14/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 24 | 195.75 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1461 | 04/14/2022 | SSA-5962 | HRDH-2230 | WCM | 07 Apr 2130 - 0500 | 24 | 128 | 895005 |  | TF | CCAT | CSTR | 2280 | WFD DV PORTS PREMATURE OPENED WHILE PUMPING FIRST STAGE SHUT OFF PLUG.
1463 | 04/14/2022 | SSA-5964 | HRDH-1343 | SJC | 13 Apr 1600 - 1000 | 5 | 18 | 895416 |  | CMT | HERR | NA | 12915 | TAQA BULKER CONTINUALLY BLOCKED CAUSING TAQA TO TAKE 2 1/2 HOURS TO MIX 34 BBLS OF 125 PCF. AFTER CONSULTING ARAMCO CEMENT SPECIALIST , THE DECISION WAS MADE TO DUMP CEMENT MIXTURE.
1465 | 04/14/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0200 | 21 | 744.25 | 893136 |  | STUK | SDIR | RSS | 1867 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1467 | 04/14/2022 | SSA-5971 | UTMN-2302 | TK2 | 14 Apr 1530 - 0500 | 13.5 | 13.5 | 895488 |  | STUK | HINW | WLT | 13635 | STUCK WITH RCX TOOLS AFTER 4 HRS SAMPLING
1469 | 04/14/2022 | SSA-5974 | HRDH-1970 | BHI | 14 Apr 1400 - 0500 | 15 | 15 | 895514 |  | STUK | SDIR | RSS | 14870 | WASH AND REAM DOWN W/ 5-7/8" BAKER RSS & LWD-GR BHA DUE TO TIGHT HOLE JUST BELOW THE SHOE. ENCOUNTER ERATIC TQ, STOP REAMING DOWN @ 14904' WHILE BAKER ATTEMPT TO CENTER RSS TOOL/BIT TO ALIGN TO TRACK MODE. BAKER ACTIVATE DOWNLINK WHILE ROTATING @ 55 RPM & 200 GPM/2300 PSI -OBSERVE STRING STALL OUT & LOST CIRC W/PRESSURE INCREASE FROM 2300 PSI TO 3300 PSI. WORK STRING UP WAY FROM 20' BELOW SHOE TO INSIDE SHOE BY 15' FROM 14904' TO 14,870' -NO FURTHER MOVEMENT, NO ROTATION & NO CIRC.
1471 | 04/14/2022 | T218 | UTMN-564 | ARM | 14 Apr 2230 - 0500 | 6.5 | 6.5 | 895513 |  | BHA | IBHA | BHA | 7887 | REAMING BHA RE-CONFIRGURATION.
1473 | 04/14/2022 | V141A | MRJN-758 | SCP | 13 Apr 1430 - 0930 | 4.5 | 19 | 895410 |  | TF | FOT | SEAL | 5828 | UNABLE TO OPEN SLB MFIV WITH MECHANICAL SHIFTING TOOL.
1475 | 04/14/2022 | WCL-83 | MRJN-837 | ARM | 14 Apr 1530 - 1645 | 1.25 | 1.25 | 895451 |  | WO | WOTO | NA | 14160 | LOST REAL TIME DATA TRANSMISSION WHILE DRILLING DUE TO V-SAT WAS DOWN.
1477 | 04/14/2022 | ZPEC-2 | HMYM-847 | ARM | 11 Apr 0230 - 2000 | 15 | 65.5 | 895308 |  | BHS | CWEL | NA | 125 | OBSERVED HOLE CAVED AFTER POOH W/ 34" SLICK BHA TO SURFACE.
1479 | 04/15/2022 | 910TE | DMMM-521 | RIG | 14 Apr 0145 - 0630 | 1 | 3.75 | 895494 |  | RR | FOT | TDS | 11549 | OBSERVED ROTARY KELLY HOSE LEAKING, POOH TO CSG SHOE & REPLACE SAME.
1481 | 04/15/2022 | ADC-29 | NYYM-104 | BAW | 15 Apr 1330 - 0500 | 15.5 | 15.5 | 895519 |  | TF | FOT | WLT | 11621 | BHI RCX LOGGING ATTEMP TO TAKE PRESSURE POINTS, NO SEAL, TOOL FAILED.
1483 | 04/15/2022 | ADC-49 | HRDH-2128 | RIG | 15 Apr 1200 - 0500 | 17 | 17 | 895521 |  | TF | HERR | FV | 600 | WHILE WASHING DOWN DRILLER SLACKED OFF 30K ON BOTTOM CAUSING FLOAT SHOE PLUGED.
1485 | 04/15/2022 | ADC-58L | ABHD-178 | TK3 | 13 Apr 0500 - 0500 | 24 | 68.5 | 895420 |  | CMT | CEDE | NA | 4320 | DVT PARTIALLY CLOSED & NOT HOLDING PRESS WHILE CLOSING PLUG NOT LANDED AFTER PUMPED THEORETICAL CALCULATED VOL DUE TO MUD PUMPS MALFUNCTION.
1487 | 04/15/2022 | ADC-68L | KRSN-706 | SDM | 14 Apr 1130 - 1430 | 9.5 | 27 | 895478 |  | BHA | FOT | MMOT | 12280 | PRESSURE DROP & MOTOR RUBBER OBSERVED ON SHAKER
1489 | 04/15/2022 | ADES-144 | UTMN-3099 | RIG | 15 Apr 0500 - 0500 | 22 | 22 | 895536 |  | BHA | ISEQ | RM | 6625 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
1491 | 04/15/2022 | ADES-173 | HRDH-2256 | RIG | 15 Apr 1745 - 1915 | 1.5 | 1.5 | 895516 |  | RR | FOT | DWKS | 15654 | TROUBLE-SHOOT & CALIBRATE BLOCK CONTROL SYSTEM.
1493 | 04/15/2022 | ADM-510 | ABSF-222 | SPS | 11 Apr 1930 - 0500 | 24 | 37 | 895194 |  | DD | UDWL | RSS | 6568 | SPERRY UNABLE TO ACHIEVE WELL PATH AS PER DIRECTIONAL PLAN REQUIREMENTS, 8.8FT RIGHT OF THE PLAN @ 6568FT & INCREASING DUE TO BEENING UNABLE TO TURN TO LEFT
1495 | 04/15/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 209.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1496 | 04/15/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 10 | 10 | 895518 |  | STUK | STDP | DP | 16058 | STRING GOT DIFFERENTIAL STUCK.
1498 | 04/15/2022 | DPS-4 | MDRK-54 | ARM | 14 Apr 2145 - 1900 | 14 | 21.25 | 895515 |  | WCNT | WCC5 | NA | 16095 | OBSERVED WELL FLOWING AT 0.4 BPH DURING FLOW CHECK.
1499 | 04/15/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 10 | 10 | 895518 |  | STUK | STDP | DP | 16058 | STRING GOT DIFFERENTIAL STUCK.
1501 | 04/15/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 69.5 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1506 | 04/15/2022 | ENSCO-76 | MRJN-851 | RIG | 14 Apr 0430 - 2230 | 17.5 | 18 | 895511 |  | BOP | FOT | BOP | 6100 | RIG ACCUMULATOR FAIL TO PASS ARAMCO WELL CONTROL STANDARDS.
1508 | 04/15/2022 | HI-4 | SFNY-918 | BC | 09 Apr 2300 - 1330 | 8.5 | 110.5 | 894970 |  | TF | FOT | SSSV | 0 | OBSERVED BAKERHUGHES TRSSSV ON WELL BRRI-786 PASSING PRESSURE WHILE HANDOVER PLATFORM TO PRODUCTION.
1510 | 04/15/2022 | MP-1 | SFNY-994 | AP2 | 14 Apr 0800 - 1100 | 6 | 27 | 895507 |  | WO | WOPF | NA | 0 | WAITING ON SAFANIYA GOSP TO GIVE PERMISSION FOR FLOWBACK.
1512 | 04/15/2022 | NBR-16S | HMYM-433302 | ITS | 15 Apr 1900 - 2100 | 2 | 2 | 895576 |  | TF | FOT | CTRQ | 310 | POWER TONG FAILED TO OPERATE, LAY DOWN POWER TONG & RIG UP CRT
1514 | 04/15/2022 | NBR-633S | HRDH-2234 | RIG | 15 Apr 2100 - 0000 | 3 | 3 | 895537 |  | RR | FOT | CSYS | 1285 | EXCESS TIME WHILE P/U BHA DUE TO MULFUNCTION IN AIR ROUGHNECK.
1515 | 04/15/2022 | NBR-654S | HRDH-2210 | RIG | 15 Apr 1830 - 2100 | 2.5 | 2.5 | 895556 |  | RR | LHFL | HSYS | 10495 | OBSERVED LEAK ON TDS SERVICE LOOP HYDRALIC LINE
1517 | 04/15/2022 | NBR-654S | HRDH-2210 | RIG | 15 Apr 0145 - 0300 | 1.25 | 1.25 | 895523 |  | RR | FOT | TDS | 5805 | TDS LINK TILT NOT WORKING.
1518 | 04/15/2022 | NBR-654S | HRDH-2210 | RIG | 15 Apr 1830 - 2100 | 2.5 | 2.5 | 895556 |  | RR | LHFL | HSYS | 10495 | OBSERVED LEAK ON TDS SERVICE LOOP HYDRALIC LINE
1520 | 04/15/2022 | NBR-783S | NJYN-89 | RIG | 15 Apr 0200 - 0500 | 3 | 3 | 895577 |  | RR | FPMP | MPMP | 13034 | HAD WASH OUT ON HP SURFACE VALVE AND LEAK ON HOSE.
1522 | 04/15/2022 | PA-785S | QTIF-641 | RIG | 15 Apr 0000 - 0200 | 2 | 2 | 895538 |  | BOP | FOT | RAMS | 0 | EXTRA TIME USED TO PRESSURE TEST TOP BOP RAM.
1524 | 04/15/2022 | SA5898 | HRDH-1978 | WWL | 13 Apr 1300 - 2030 | 15.5 | 35.5 | 895409 |  | TF | FOT | WLT | 11088 | WFD HAD MISS COMMUNICATION WITH SAMPLING TOOL & FAILED TO TAKE SAMPLE @ 11082', TROUBLSHOOTING TOOL WITHOUT SUCCESS.
1526 | 04/15/2022 | SINO-47 | HRDH-1957 | BLH | 12 Apr 1830 - 0500 | 24 | 73.5 | 895306 |  | TF | FOT | SEAL | 10149 | BAKER 9-5/8" TIE-BACK SEAL ASSY NOT HOLDING PRESSURE AFTER STING INTO TBR.
1528 | 04/15/2022 | SND-2001 | UTMN-2329 | ARM | 13 Apr 1100 - 0500 | 24 | 58.25 | 895520 |  | LCIR | FRFM | NA | 8835 | OBSERVED TOTAL LOSSES AT 8835 FT ( LOWER FADHILI RES)
1530 | 04/15/2022 | SND-3002 | DMMM-602 | RAC | 14 Apr 2130 - 1200 | 7 | 14.5 | 895472 |  | TF | FOT | CUT | 7701 | UNABLE TO CLOSE SSD DUE TO RUPTURE DISC OF RAWABI SHIFTING TOOL OPENED
1532 | 04/15/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 23 | 218.75 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1534 | 04/15/2022 | SSA-5962 | HRDH-2230 | WCM | 07 Apr 2130 - 0500 | 20.75 | 148.75 | 895005 |  | TF | CCAT | CSTR | 2280 | WFD DV PORTS PREMATURE OPENED AFTER BUMPED FIRST STAGE SHUT OFF PLUG.
1536 | 04/15/2022 | SSA-5971 | UTMN-2302 | TK2 | 14 Apr 1530 - 1600 | 11 | 24.5 | 895488 |  | STUK | HINW | WLT | 13635 | STUCK WITH RCX TOOLS AFTER 4 HRS SAMPLING
1538 | 04/15/2022 | SSA-5974 | HRDH-1970 | ARM | 14 Apr 1400 - 0500 | 24 | 39 | 895514 |  | STUK | SDIR | RSS | 14870 | WASH AND REAM DOWN W/ 5-7/8" BAKER RSS & LWD-GR BHA DUE TO TIGHT HOLE JUST BELOW THE SHOE. ENCOUNTER ERATIC TQ, STOP REAMING DOWN @ 14904' WHILE BAKER ATTEMPT TO CENTER RSS TOOL/BIT TO ALIGN TO TRACK MODE. BAKER ACTIVATE DOWNLINK WHILE ROTATING @ 55 RPM & 200 GPM/2300 PSI -OBSERVE STRING STALL OUT & LOST CIRC W/PRESSURE INCREASE FROM 2300 PSI TO 3300 PSI. WORK STRING UP WAY FROM 20' BELOW SHOE TO INSIDE SHOE BY 15' FROM 14904' TO 14,870' -NO FURTHER MOVEMENT, NO ROTATION & NO CIRC.
1540 | 04/15/2022 | T218 | UTMN-564 | ARM | 14 Apr 2230 - 0500 | 21.5 | 28 | 895513 |  | BHA | IBHA | BHA | 7887 | UNABLE TO ACCESS 7" WINDOW
1542 | 04/15/2022 | V140A | RBYN-100 | HSL | 15 Apr 1330 - 0500 | 15.5 | 15.5 | 895452 |  | STUK | HINW | SLICK | 5965 | WHILE POH WITH PX PLUG ON SLICK LINE , PX PLUG BECOME STUCK IN UPPER ASSY#7 X-NIPPLE .
1544 | 04/15/2022 | ZPEC-2 | HMYM-847 | ARM | 15 Apr 2000 - 0500 | 9 | 9 | 895522 |  | JF | HELD | CSG | 64 | WHILE RIH 30" CONDUCTOR GOT OBSTRCTION @ 64'RKB.
1546 | 04/16/2022 | ADC-29 | NYYM-104 | BAW | 15 Apr 1330 - 1800 | 11.5 | 27 | 895519 |  | TF | FOT | WLT | 11621 | BHI RCX LOGGING ATTEMP TO TAKE PRESSURE POINTS, NO SEAL, TOOL FAILED.
1548 | 04/16/2022 | ADC-49 | HRDH-2128 | RIG | 15 Apr 1200 - 1030 | 5.5 | 22.5 | 895521 |  | TF | HERR | FV | 600 | WHILE WASHING DOWN DRILLER SLACKED OFF 45K ON BOTTOM CAUSING FLOAT SHOE PLUGED.
1553 | 04/16/2022 | ADM-510 | ABSF-222 | SPS | 11 Apr 1930 - 0500 | 24 | 61 | 895194 |  | DD | UDWL | RSS | 6568 | SPERRY UNABLE TO ACHIEVE WELL PATH AS PER DIRECTIONAL PLAN REQUIREMENTS, 8.8FT RIGHT OF THE PLAN @ 6568FT & INCREASING DUE TO BEENING UNABLE TO TURN TO LEFT
1555 | 04/16/2022 | ADM-655 | SFNY-475 | ARM | 16 Apr 1800 - 0500 | 11 | 11 | 895557 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO RECEIVE COILED TUBING EQPT & CREW.
1557 | 04/16/2022 | AOD-11 | SFNY-4250 | BCM | 16 Apr 1415 - 0500 | 14.75 | 14.75 | 895558 |  | JF | CEDE | NA | 6510 | LOST TIME BCM: BAKER ATTEMPT TO PERFORM FIRST STAGE PRIMARY CEMENTATION, JOB FAILURE AFTER PUMPING 54 BBLS NONHOMOGENEOUS LEAD SLURRY, JOB ABANDONED.
1559 | 04/16/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 233.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1561 | 04/16/2022 | ARO-3003 | SFNY-1740 | CRW | 16 Apr 2100 - 0500 | 8 | 8 | 895580 |  | BHA | FOT | AVDS | 4600 | UNABLE TO CLOSE PBL SUB AND RE-GAIN CIRCULATION DOWN STRING.
1563 | 04/16/2022 | BCTD-3 | HRDH-1961 | ARM | 16 Apr 0930 - 1530 | 6 | 6 | 895539 |  | WO | HMWT | NA | 11000 | GEARHEAD FOR WATER WELL WAS NOT WORKING.
1564 | 04/16/2022 | DPS-4 | MDRK-54 | RIG | 16 Apr 2330 - 0030 | 1 | 1 | 895560 |  | RR | FOT | CSYS | 16058 | OBSERVED A LEAK FROM STAND PIPE.
1566 | 04/16/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 23 | 33 | 895518 |  | STUK | STDP | DP | 16058 | STRING GOT DIFFERENTIAL STUCK.
1567 | 04/16/2022 | DPS-4 | MDRK-54 | RIG | 16 Apr 2330 - 0030 | 1 | 1 | 895560 |  | RR | FOT | CSYS | 16058 | OBSERVED A LEAK FROM STAND PIPE.
1569 | 04/16/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 93.5 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1574 | 04/16/2022 | RBP-50A | KARN-51 | RIG | 16 Apr 0415 - 0500 | .75 | .75 | 895581 |  | RR | FOT | HSYS | 872 | CHANGE OUT LIFT CYLINDER ON THE IRON ROUGH NECK.
1576 | 04/16/2022 | RM-74A | KARN-60 | HSL | 16 Apr 0115 - 0500 | 3.75 | 3.75 | 895540 |  | TF | FOT | SLICK | 12410 | HALLIBURTON SLICKLINE BOP BOTTOM RAMS REMAIN IN CLOSED POSITION AND UNABLE TO OPEN.
1578 | 04/16/2022 | SIN30L | KHRS-1409 | TK2 | 16 Apr 1800 - 0500 | 11 | 11 | 895541 |  | CMT | WSHO | CSG | 9988 | TRIED TO PRESS. TEST CSG TO 1550 PSI ( 2000 PSI WTER EQUIVALENT). - PRESS DROPPED 250 PSI/10 MINTS , PRESS. UP AGAIN TO 1550 PSI , PRESS. DROPPED 250 PSI / 10 MINTS.
1580 | 04/16/2022 | SINO-46L | SHYB-558 | BHI | 16 Apr 0200 - 0400 | 2 | 2 | 895582 |  | BHA | FOT | RSS | 3770 | ATTEMPT TO DOWN LINK TO RSS WITHOUT SUCCESS, TROUBLE SHOOTING AND FOUND MALFUNCTION OF BY PASS ACTUATOR.
1582 | 04/16/2022 | SINO-47 | HRDH-1957 | BLH | 12 Apr 1830 - 0215 | 21.25 | 94.75 | 895306 |  | TF | FOT | SEAL | 10149 | BAKER 9-5/8" TIE-BACK SEAL ASSY NOT HOLDING PRESSURE AFTER STING INTO TBR.
1584 | 04/16/2022 | SND-2001 | UTMN-2329 | ARM | 13 Apr 1100 - 0500 | 24 | 82.25 | 895520 |  | LCIR | FRFM | NA | 8835 | OBSERVED TOTAL LOSSES AT 8835 FT ( LOWER FADHILI RES)
1586 | 04/16/2022 | SND-2004 | BRRI-1148 | SJC | 13 Apr 1130 - 1215 | 7 | 7.5 | 895419 |  | CMT | CFST | NA | 3225 | PRESSURE INCREASE WHILE DISPLACEMENT OF THE LAST 184 BBLS OF 18-5/8" CSG 1ST STAGE CEMENT JOB, CLEAN OUT 595 FT EXCESS CEMENT.
1588 | 04/16/2022 | SP-120 | MNIF-189 | MSI | 15 Apr 0800 - 1830 | 10 | 15.5 | 895559 |  | JF | FOI | TBG | 5817 | CASING CREW OVER TORQUE STRING.
1590 | 04/16/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 24 | 242.75 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1591 | 04/16/2022 | SSA-5962 | HRDH-2230 | RIG | 16 Apr 0645 - 1330 | 6.75 | 6.75 | 895579 |  | RR | FOT | TDS | 3505 | TDS FAILURE, TROUBLESHOOTING, HYDRAULIC PUMP NOT WORKING.
1593 | 04/16/2022 | SSA-5962 | HRDH-2230 | WCM | 07 Apr 2130 - 1700 | 5.25 | 154 | 895005 |  | TF | CCAT | CSTR | 2280 | WFD DV PORTS PREMATURE OPENED AFTER BUMPED FIRST STAGE SHUT OFF PLUG.
1594 | 04/16/2022 | SSA-5962 | HRDH-2230 | RIG | 16 Apr 0645 - 1330 | 6.75 | 6.75 | 895579 |  | RR | FOT | TDS | 3505 | TDS FAILURE, TROUBLESHOOTING, HYDRAULIC PUMP NOT WORKING.
1596 | 04/16/2022 | SSA-5974 | HRDH-1970 | ARM | 14 Apr 1400 - 0500 | 24 | 63 | 895514 |  | STUK | SDIR | RSS | 14870 | WASH AND REAM DOWN W/ 5-7/8" BAKER RSS & LWD-GR BHA DUE TO TIGHT HOLE JUST BELOW THE SHOE. ENCOUNTER ERATIC TQ, STOP REAMING DOWN @ 14904' WHILE BAKER ATTEMPT TO CENTER RSS TOOL/BIT TO ALIGN TO TRACK MODE. BAKER ACTIVATE DOWNLINK WHILE ROTATING @ 55 RPM & 200 GPM/2300 PSI -OBSERVE STRING STALL OUT & LOST CIRC W/PRESSURE INCREASE FROM 2300 PSI TO 3300 PSI. WORK STRING UP WAY FROM 20' BELOW SHOE TO INSIDE SHOE BY 15' FROM 14904' TO 14,870' -NO FURTHER MOVEMENT, NO ROTATION & NO CIRC.
1598 | 04/16/2022 | T218 | UTMN-564 | ARM | 14 Apr 2230 - 1800 | 13 | 41 | 895513 |  | BHA | IBHA | BHA | 7887 | UNABLE TO ACCESS 7" WINDOW
1600 | 04/16/2022 | ZPEC-2 | HMYM-847 | ARM | 15 Apr 2000 - 1600 | 11 | 20 | 895522 |  | JF | HELD | CSG | 64 | WHILE RIH 30" CONDUCTOR GOT OBSTRCTION @ 64'RKB.
1602 | 04/17/2022 | ADC-48 | HWYH-1256 | WCR | 17 Apr 1700 - 1800 | 1 | 1 | 895566 |  | TF | FOT | CTRQ | 7020 | WFD HYDRAULIC TONG MALFUNTION. UNABLE TO TORQUE, REPAIRED THE SAME
1607 | 04/17/2022 | ADC-58L | ABHD-178 | TK3 | 17 Apr 1315 - 0500 | 15.75 | 15.75 | 895526 |  | LROP | IBSL | BIT | 4320 | ATTEMPTED D/O FREE FALL PLUG WITH SDM BHA USING DIFFERENT PARAMETERS WITHOUT SUCCESS.
1609 | 04/17/2022 | ADES-144 | UTMN-3099 | RIG | 14 Apr 1630 - 0500 | 23 | 76.5 | 895536 |  | BHA | ISEQ | RM | 6625 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
1611 | 04/17/2022 | ADM-510 | ABSF-222 | SPS | 11 Apr 1930 - 0900 | 4 | 65 | 895194 |  | DD | UDWL | RSS | 6568 | SPERRY UNABLE TO ACHIEVE WELL PATH AS PER DIRECTIONAL PLAN REQUIREMENTS, 8.8FT RIGHT OF THE PLAN @ 6568FT & INCREASING DUE TO BEENING UNABLE TO TURN TO LEFT
1613 | 04/17/2022 | ADM-655 | SFNY-475 | ARM | 16 Apr 1800 - 1100 | 6 | 17 | 895557 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO RECEIVE COILED TUBING EQPT & CREW.
1615 | 04/17/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 257.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1617 | 04/17/2022 | ARO-3003 | SFNY-1740 | CRW | 16 Apr 2100 - 0815 | 3.25 | 11.25 | 895580 |  | BHA | FOT | AVDS | 4600 | UNABLE TO CLOSE PBL SUB AND RE-GAIN CIRCULATION DOWN STRING.
1619 | 04/17/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 24 | 58 | 895518 |  | STUK | STDP | DP | 16058 | STRING GOT DIFFERENTIAL STUCK.
1621 | 04/17/2022 | DPS-44 | UTMN-3151 | OCT | 17 Apr 1530 - 2130 | 6 | 6 | 895567 |  | CMT | IFCS | NA | 10850 | DELAYED TO RUN ARAMCO SPACER COMPATBILTY TEST AND SPACER WAS NOT COMPATABLE. AS A RESULT PREPARED AN OTHER BATCH OF OIL SERV SPACER
1623 | 04/17/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 117.5 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1628 | 04/17/2022 | NBR-304S | HRDH-1952 | SPS | 17 Apr 2330 - 0400 | 4.5 | 4.5 | 895543 |  | BHA | FOT | MWD | 9610 | LOST SIGNAL OF SPERRY SUN MWD
1630 | 04/17/2022 | NBR-633S | HRDH-2234 | RIG | 17 Apr 1100 - 1200 | 1 | 1 | 895562 |  | RR | FOT | TDS | 3450 | HAD TDS TORQUE TOO HIGH, INVESTIGATE THE PROBLEM AND CHANGE TORQUE ENCODER.
1632 | 04/17/2022 | PA-529S | SHYB-45 | HCO | 17 Apr 0700 - 0830 | 1.5 | 1.5 | 895563 |  | TF | HERR | TBG | 0 | LOST TIME ON HALL. COMPLETION (DUE TO UN-AVAILABILITY OF SS C.LINE SPOOLING MACHINE TOOK ADDITIONAL TIME TO REPLACE & INSTALL SS C.LINE DRUM ON PREVIUOS INC. C.LINE SPOOLING MACHINE)
1634 | 04/17/2022 | PA-604S | HRDH-1953 | RIG | 17 Apr 1415 - 1545 | 1.5 | 1.5 | 895561 |  | RR | FPMP | MPMP | 8140 | TROUBLESHOOT & REPAIR MUD PUMPS #1, 3.
1636 | 04/17/2022 | RBP-50A | KARN-51 | RIG | 16 Apr 0415 - 0745 | 2.75 | 3.5 | 895581 |  | RR | FOT | HSYS | 872 | CHANGE OUT LIFT CYLINDER ON THE IRON ROUGH NECK.
1638 | 04/17/2022 | RM-74A | KARN-60 | HSL | 16 Apr 0115 - 0600 | 1 | 4.75 | 895540 |  | TF | FOT | SLICK | 12410 | HALLIBURTON SLICKLINE BOP BOTTOM RAMS REMAIN IN CLOSED POSITION AND UNABLE TO OPEN.
1640 | 04/17/2022 | SIN30L | KHRS-1409 | TK2 | 16 Apr 1800 - 1445 | 8.5 | 19.5 | 895541 |  | CMT | WSHO | CSG | 9988 | TRIED TO PRESS. TEST CSG TO 1550 PSI ( 2000 PSI WTER EQUIVALENT). - PRESS DROPPED 250 PSI/10 MINTS , PRESS. UP AGAIN TO 1550 PSI , PRESS. DROPPED 250 PSI / 10 MINTS.
1642 | 04/17/2022 | SINO-19L | UTMN-1199 | TK1 | 17 Apr 0600 - 0500 | 23 | 23 | 895544 |  | DRG | CEDE | NA | 5430 | UNABLE TO PASS W/3.5" GC @ 5430'.
1647 | 04/17/2022 | SINO-43L | UTMN-4063 | BLH | 17 Apr 1530 - 0500 | 13.5 | 13.5 | 895528 |  | TF | FOT | HGRL | 11454 | ATTEMPT TO SET 5" BAKER SLZXP LINER TOP PACKER, DROPPED 1.5" BALL, PRESSURE UP TO 1700 PSI, SUDDENLY PRESSURE DROPPED TO ZERO, POOH, FOUND LINER RUNNING TOOL RELEASED AND LINER HANGER PACKER WITH LOWER COMPLETION LEFT IN HOLE.
1649 | 04/17/2022 | SINO-7N | FDHL-616 | WTS | 17 Apr 0700 - 1500 | 8 | 8 | 895584 |  | TF | FOT | FISHT | 0 | WFD INTERNAL PIPE CUTTER TOOL SHALLOW SURFACE TEST FAILED, CUTTER'S BLADES FAILED TO RETRACT AFTER PUMP-OFF, WFD ENG PUSH BLADES BY HAND, BLADES BACAME LOOS AND SIDE PLAY.
1651 | 04/17/2022 | SL-7 | ZULF-1331 | RIG | 17 Apr 0430 - 0500 | .5 | .5 | 895527 |  | RR | LHFL | HSYS | 5436 | RIG WORK AND REPAIRE LEAKING O-RING ON TDS/BX ELEVATOR HYDRAULIC SYSTEM
1653 | 04/17/2022 | SND-2001 | UTMN-2329 | ARM | 13 Apr 1100 - 0500 | 23 | 105.25 | 895520 |  | LCIR | FRFM | NA | 8835 | OBSERVED TOTAL LOSSES AT 8835 FT ( LOWER FADHILI RES)
1655 | 04/17/2022 | SP-306 | MNIF-197 | RIG | 17 Apr 0500 - 0600 | 1 | 1 | 895585 |  | RR | EDIS | CSYS | 9230 | LEAK FROM CONNECTION BETWEEN STAND PIPE GOOSE NECK & T-PIECE, FIXED SAME
1657 | 04/17/2022 | SSA-303 | HRDH-2306 | RIG | 17 Apr 1800 - 1930 | 1.5 | 1.5 | 895565 |  | RR | FOT | TDS | 2710 | CHANGED OUT WORN OUT TOPDRIVE GRAPPLE DIES
1659 | 04/17/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 22.75 | 265.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1661 | 04/17/2022 | SSA-5971 | UTMN-2302 | SWL | 17 Apr 0030 - 0300 | 2.5 | 2.5 | 895525 |  | TF | FOT | WLT | 13801 | LOST SEAL WHILE CIRCULATE THE TOOL FOR SAMPLING
1663 | 04/17/2022 | SSA-5974 | HRDH-1970 | ARM | 14 Apr 1400 - 0500 | 24 | 87 | 895514 |  | STUK | SDIR | RSS | 14870 | WASH AND REAM DOWN W/ 5-7/8" BAKER RSS & LWD-GR BHA DUE TO TIGHT HOLE JUST BELOW THE SHOE. ENCOUNTER ERATIC TQ, STOP REAMING DOWN @ 14904' WHILE BAKER ATTEMPT TO CENTER RSS TOOL/BIT TO ALIGN TO TRACK MODE. BAKER ACTIVATE DOWNLINK WHILE ROTATING @ 55 RPM & 200 GPM/2300 PSI -OBSERVE STRING STALL OUT & LOST CIRC W/PRESSURE INCREASE FROM 2300 PSI TO 3300 PSI. WORK STRING UP WAY FROM 20' BELOW SHOE TO INSIDE SHOE BY 15' FROM 14904' TO 14,870' -NO FURTHER MOVEMENT, NO ROTATION & NO CIRC.
1665 | 04/17/2022 | T218 | UTMN-564 | RIG | 17 Apr 1300 - 1400 | 1 | 1 | 895524 |  | RR | FOT | MPMP | 7071 | LINER GASKET ON PUMP#2 FAILED.
1667 | 04/18/2022 | ADC-36 | SDGM-1234 | HCM | 18 Apr 0300 - 0500 | 2 | 2 | 895573 |  | WO | WOTO | NA | 12651 | WAIT ON SECOND CMT PUMP UNIT
1669 | 04/18/2022 | ADES-144 | UTMN-3099 | RIG | 14 Apr 1630 - 0500 | 24 | 100.5 | 895536 |  | BHA | ISEQ | RM | 6625 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
1671 | 04/18/2022 | ADES-174 | GHZL-88 | WDS | 18 Apr 2300 - 0500 | 6 | 6 | 895550 |  | BHA | FOT | MWD | 11200 | WHILE DRLG. @ 10,300' HAD MWD-GR TOOL STOP PULSING.
1673 | 04/18/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 281.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1675 | 04/18/2022 | DPS-4 | MDRK-54 | ARM | 17 Apr 0815 - 0245 | 21.75 | 42.5 | 895596 | 895515 | LCIR | UVLC | NA | 16095 | TOTAL LOSS WHILE CIRCULATING VDA ACID PILL OUT OF HOLE
1677 | 04/18/2022 | DPS-46 | SDGM-1106 | RIG | 18 Apr 1430 - 1730 | 3 | 3 | 895600 |  | RR | FOT | MPMP | 11578 | IBOP MALFUNCTION LED TO PUMP POP-OFF SHEARED.
1679 | 04/18/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 141.5 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1681 | 04/18/2022 | DQ-47 | KHRS-1416 | TK2 | 18 Apr 1130 - 1415 | 2.75 | 2.75 | 895551 |  | BB | VPFM | BIT | 540 | OBSERVED VERY LOW ROP TRIED DIFFERENT DRILLING PARAMETERS WITHOUT PROGRESS
1686 | 04/18/2022 | ENS-108 | SFNY-1720 | SWL | 18 Apr 1530 - 2130 | 6 | 6 | 895599 |  | TF | FOT | WLT | 6290 | WL TOOL FAILURE (MRX).
1688 | 04/18/2022 | NBR-783S | NJYN-89 | BHI | 18 Apr 2030 - 0500 | 8.5 | 8.5 | 895601 |  | TF | FOT | FV | 13959 | DRILL WITH BHI RSS TO 13959', LOAST COMMNICATION WITH RSS TOOL, UNABLE TO CONTINUE DRILLING
1690 | 04/18/2022 | PA-861S | HRDH-1060 | WUD | 18 Apr 1600 - 0000 | 8 | 8 | 895548 |  | WO | MATL | NA | 0 | WEATHERFORD RCD ARRIVED ON LOCATION WITH 13-5/8" ADAPTER SPOOL NOT COMPATIBLE WITH 11" BOP
1692 | 04/18/2022 | SDA | MRJN-735 | ARM | 18 Apr 2030 - 0000 | 3.5 | 3.5 | 895549 |  | TH | PCPF | NA | 11033 | TAG OBSTRUCTION WITH 4-1/2" LOWER COMPLETION AT 11085' AND UNABLE TO RUN FURTHER.
1694 | 04/18/2022 | SINO-19L | UTMN-1199 | TK1 | 17 Apr 0600 - 0500 | 24 | 47 | 895544 |  | DRG | CEDE | NA | 5430 | UNABLE TO PASS W/3.5" GC @ 5430'.
1699 | 04/18/2022 | SINO-43L | UTMN-4063 | BLH | 17 Apr 1530 - 0500 | 17.5 | 30 | 895528 |  | TF | FOT | HGRL | 11454 | ATTEMPT TO SET 5" BAKER SLZXP LINER TOP PACKER, DROPPED 1.5" BALL, PRESSURE UP TO 1700 PSI, SUDDENLY PRESSURE DROPPED TO ZERO, POOH, FOUND LINER RUNNING TOOL RELEASED AND LINER HANGER PACKER WITH LOWER COMPLETION LEFT IN HOLE.
1701 | 04/18/2022 | SL-7 | ZULF-1331 | RIG | 17 Apr 0430 - 0645 | 1.75 | 2.25 | 895597 |  | RR | LHFL | HSYS | 5436 | TDS SOLENOID O-RING IS LEAKING FOR BX ELEVATOR FUNCTION.
1703 | 04/18/2022 | SND-2001 | UTMN-2329 | ARM | 13 Apr 1100 - 0500 | 23.5 | 128.75 | 895520 |  | LCIR | FRFM | NA | 8835 | OBSERVED TOTAL LOSSES AT 8835 FT ( LOWER FADHILI RES)
1705 | 04/18/2022 | SND-2007 | ADHN-370100 | RIG | 18 Apr 1300 - 0500 | 16 | 16 | 895570 |  | RR | FOT | TDS | 14375 | LOST COMMUNICATION WITH TDS DUE TO DAMAGE ELECTRICAL SERVICE LOOP.
1707 | 04/18/2022 | SP-161 | HWYH-680 | BHI | 18 Apr 1930 - 2030 | 1 | 1 | 895616 |  | DD | HERR | RSS | 3652 | BHI TROUBLESHOOT RSS SYSTEM DUE TO HIGH TORQUE.
1709 | 04/18/2022 | SSA-201 | HRDH-1818 | SWL | 17 Apr 1500 - 0500 | 24 | 38 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
1711 | 04/18/2022 | SSA-302 | HRDH-2113 | RIG | 18 Apr 0500 - 0800 | 3 | 3 | 895569 |  | BOP | HERR | BOP | 5385 | EXCESSIVE TIME TESTING BOP DEW TO WRONG RING GASKETS INSTALLED AND LEAKS
1713 | 04/18/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 24 | 289.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1715 | 04/18/2022 | SSA-5974 | HRDH-1970 | ARM | 14 Apr 1400 - 0500 | 24 | 111 | 895514 |  | STUK | SDIR | RSS | 14870 | WASH AND REAM DOWN W/ 5-7/8" BAKER RSS & LWD-GR BHA DUE TO TIGHT HOLE JUST BELOW THE SHOE. ENCOUNTER ERATIC TQ, STOP REAMING DOWN @ 14904' WHILE BAKER ATTEMPT TO CENTER RSS TOOL/BIT TO ALIGN TO TRACK MODE. BAKER ACTIVATE DOWNLINK WHILE ROTATING @ 55 RPM & 200 GPM/2300 PSI -OBSERVE STRING STALL OUT & LOST CIRC W/PRESSURE INCREASE FROM 2300 PSI TO 3300 PSI. WORK STRING UP WAY FROM 20' BELOW SHOE TO INSIDE SHOE BY 15' FROM 14904' TO 14,870' -NO FURTHER MOVEMENT, NO ROTATION & NO CIRC.
1717 | 04/18/2022 | T914 | HWYH-135 | ARN | 18 Apr 1730 - 0500 | 11.5 | 11.5 | 895571 |  | STUK | PSSW | NA | 7883 | 4-1/2" OBL STUCK
1719 | 04/18/2022 | ZPEC-1 | HMYM-846 | ARM | 18 Apr 0930 - 1930 | 10 | 10 | 895572 |  | TH | NARW | NA | 5302 | WHILE RIH 9-5/8" LINER TAGGED IN OPEN HOLE @5302' DUE TO SHALE FORMATION . CONTINUE WASH DOWN CSG TO BTM.
1721 | 04/19/2022 | ADC-55L | UTMN-3199 | RIG | 19 Apr 0830 - 1130 | 3 | 3 | 895639 |  | RR | FPMP | MPMP | 10766 | - DECREASED SPP WHILE CHC - LEAKING MUD PUMP SUCTION LINE
1723 | 04/19/2022 | ADC-56L | UTMN-2330 | RIG | 19 Apr 0500 - 0600 | 1 | 1 | 895640 |  | RR | FOT | HSYS | 8175 | WHILE TESTING BOP OBSERVED LEAK IN THE HIGH PRESSURE LINE FROM TEST PUMP TO BOP.
1725 | 04/19/2022 | ADC-58L | ABHD-178 | TK3 | 17 Apr 1315 - 1445 | 9.75 | 31 | 895526 |  | LROP | IBSL | BIT | 4320 | ATTEMPTED D/O SHUTOFF PLUG WITH SDM BHA USING DIFFERENT PARAMETERS WITHOUT SUCCESS.
1727 | 04/19/2022 | ADES-144 | UTMN-3099 | RIG | 14 Apr 1630 - 0500 | 24 | 124.5 | 895536 |  | BHA | ISEQ | RM | 6625 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
1729 | 04/19/2022 | ADES-174 | GHZL-88 | WDS | 18 Apr 2300 - 0400 | 23 | 29 | 895550 |  | BHA | FOT | MWD | 11200 | WHILE DRLG. @ 10,300' HAD MWD-GR TOOL STOP PULSING.
1731 | 04/19/2022 | ADM-510 | ABSF-222 | SDM | 19 Apr 1900 - 0500 | 10 | 10 | 895644 |  | DD | IDPR | RSS | 7264 | SLB CONTROLLED DRILLING PARAMETERS TO MAINTAIN RSS STEERING AND ACHIEVE WELL PATH AS PER DIRECTIONAL PLAN REQUIREMENTS WITHOUT SUCCESS.
1733 | 04/19/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 305.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1735 | 04/19/2022 | DPS-4 | MDRK-54 | ARM | 17 Apr 0815 - 1600 | 10.5 | 55.25 | 895596 | 895515 | LCIR | UVLC | NA | 16095 | TOTAL LOSS WHILE CIRCULATING VDA ACID PILL OUT OF HOLE
1737 | 04/19/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 11.75 | 153.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1741 | 04/19/2022 | HI-5 | MHRH-58 | RIG | 19 Apr 1930 - 0500 | 9.5 | 9.5 | 895641 |  | BOP | HERR | BOP | 10731 | POH TO PERFORM BOP TEST.
1743 | 04/19/2022 | HI-5 | MHRH-58 | SDM | 19 Apr 0730 - 0900 | 1.5 | 1.5 | 895552 |  | DD | DFOR | RSS | 10718 | SCHLUMBERGER DD CHANGED INCLINATION THAN PROPOSAL WITHOUT DISCUSSING WITH WOE.
1744 | 04/19/2022 | HI-5 | MHRH-58 | RIG | 19 Apr 1930 - 0500 | 9.5 | 9.5 | 895641 |  | BOP | HERR | BOP | 10731 | POH TO PERFORM BOP TEST.
1746 | 04/19/2022 | NBR-783S | NJYN-89 | BHI | 18 Apr 2030 - 2230 | 17.5 | 26 | 895601 |  | TF | FOT | FV | 13959 | DRILL WITH BHI RSS TO 13959', LOAST COMMNICATION WITH RSS TOOL, UNABLE TO CONTINUE DRILLING
1748 | 04/19/2022 | NBR-797S | UTMN-3130 | CTC | 19 Apr 0400 - 0500 | 1 | 1 | 895553 |  | BHA | FOT | SKSUB | 2608 | ATTEMPT TO BREAK NBRR FROM SHOCK-SUB, NO SUCCESS.
1750 | 04/19/2022 | PA-529S | SHYB-45 | RIG | 19 Apr 1730 - 1930 | 2 | 2 | 895642 |  | RR | FPMP | MPMP | 0 | SURFACE LINE PT WAS NOT HOLDING TRIED SEVERAL ATTEMPTS NO PROGRESS
1752 | 04/19/2022 | SINO-19L | UTMN-1199 | TK1 | 17 Apr 0600 - 0400 | 23 | 70 | 895544 |  | DRG | CEDE | NA | 5430 | UNABLE TO PASS W/3.5" GC @ 5430'.
1754 | 04/19/2022 | SINO-43L | UTMN-4063 | BLH | 17 Apr 1530 - 0500 | 24 | 54 | 895528 |  | TF | FOT | HGRL | 11454 | ATTEMPT TO SET 5" BAKER SLZXP LINER TOP PACKER, DROPPED 1.5" BALL, PRESSURE UP TO 1700 PSI, SUDDENLY PRESSURE DROPPED TO ZERO, POOH, FOUND LINER RUNNING TOOL RELEASED AND LINER HANGER PACKER WITH LOWER COMPLETION LEFT IN HOLE.
1756 | 04/19/2022 | SINO21 | ABQQ-430 | ARM | 19 Apr 0915 - 1200 | 2.75 | 2.75 | 895656 |  | WO | STOP | NA | 0 | WAIT ON FINAL LOWER COMPLETION HOOK UP
1758 | 04/19/2022 | SL-7 | ZULF-1331 | RIG | 19 Apr 0915 - 1730 | 8.25 | 8.25 | 895575 |  | RR | FOT | TDS | 6190 | MAIN SHAFT IS NOT DIS-ENGAGING FROM PIPE HANDLAR CAUSING BOTH TO ROTARE WHEN ATTEMPTING TO M/U TDS.
1760 | 04/19/2022 | SND-2001 | UTMN-2329 | ARM | 13 Apr 1100 - 0500 | 24 | 152.75 | 895520 |  | LCIR | FRFM | NA | 8835 | OBSERVED TOTAL LOSSES AT 8835 FT ( LOWER FADHILI RES)
1762 | 04/19/2022 | SND-2002 | WAQR-23 | ARM | 18 Apr 1745 - 0500 | 24 | 33.5 | 895574 |  | CMT | FRFM | NA | 2790 | WHILE C/O 18-5/8"CSG SHOE TRACK AND AFTER FLOAT SHOE, HAD TOTAL LOSSES
1763 | 04/19/2022 | SND-2005 | MHKK-2 | RIG | 19 Apr 0900 - 1800 | 9 | 9 | 895637 |  | RR | FOT | TDS | 9190 | OBSERVE LEAK ON TOP DRIVE ACTUATOR VALVE.
1765 | 04/19/2022 | SND-2005 | MHKK-2 | RIG | 19 Apr 2000 - 0500 | 9 | 9 | 895554 |  | RR | FOT | TDS | 9190 | AFTER REPLACING THE ACTUATER VALVE, WHILE PUMPING WITH 2,150 PSI AND DRILLING, OBSERVED LEAK AGAIN FROM SAME PLACE AS PREVIOUS. CONFIRM THE QUAIL SHAFT WAS WASHED OR HAS WEAK THREADS AND NEEDED TO BE REPLACED.
1766 | 04/19/2022 | SND-2005 | MHKK-2 | RIG | 19 Apr 0900 - 1800 | 9 | 9 | 895637 |  | RR | FOT | TDS | 9190 | OBSERVE LEAK ON TOP DRIVE ACTUATOR VALVE.
1768 | 04/19/2022 | SND-2007 | ADHN-370100 | RIG | 18 Apr 1300 - 1000 | 5 | 21 | 895570 |  | RR | FOT | TDS | 14375 | LOST COMMUNICATION WITH TDS DUE TO DAMAGE ELECTRICAL SERVICE LOOP.
1770 | 04/19/2022 | SSA-201 | HRDH-1818 | SWL | 17 Apr 1500 - 0500 | 24 | 62 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
1772 | 04/19/2022 | SSA-46 | JAHM-7 | SWL | 19 Apr 1545 - 1700 | 1.25 | 1.25 | 895645 |  | TF | FOT | WLT | 5170 | WHILE TAKING PRESURE POINTS OBSERED SLB PACKER LEAKING, POOH TOOLSTRING RUN#5 (XPT-GR), CHANGE SAME AND RIH.
1774 | 04/19/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 19.75 | 309.25 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1776 | 04/19/2022 | SSA-5974 | HRDH-1970 | ARM | 14 Apr 1400 - 0500 | 24 | 135 | 895514 |  | STUK | SDIR | RSS | 14870 | WASH AND REAM DOWN W/ 5-7/8" BAKER RSS & LWD-GR BHA DUE TO TIGHT HOLE JUST BELOW THE SHOE. ENCOUNTER ERATIC TQ, STOP REAMING DOWN @ 14904' WHILE BAKER ATTEMPT TO CENTER RSS TOOL/BIT TO ALIGN TO TRACK MODE. BAKER ACTIVATE DOWNLINK WHILE ROTATING @ 55 RPM & 200 GPM/2300 PSI -OBSERVE STRING STALL OUT & LOST CIRC W/PRESSURE INCREASE FROM 2300 PSI TO 3300 PSI. WORK STRING UP WAY FROM 20' BELOW SHOE TO INSIDE SHOE BY 15' FROM 14904' TO 14,870' -NO FURTHER MOVEMENT, NO ROTATION & NO CIRC.
1778 | 04/19/2022 | T914 | HWYH-135 | ARN | 18 Apr 1730 - 0500 | 24 | 35.5 | 895571 |  | STUK | PSSW | NA | 7883 | 4-1/2" OBL STUCK
1780 | 04/20/2022 | 095TE | MNIF-220 | RIG | 20 Apr 0630 - 1200 | 5.5 | 5.5 | 895736 |  | RR | FOT | TDS | 480 | TOP DRIVE LOST COMMUNICATION, TROUBLESHOOTING FOUND THE THREE INVERTERS IN THE VFD UNIT MALFUNCTION CHANGE OUT SAME , FUNCTION TEST TOP DRIVE OK.
1782 | 04/20/2022 | ADC-56L | UTMN-2330 | TK3 | 20 Apr 1145 - 1415 | 2.5 | 2.5 | 895739 |  | MUD | IPDF | NA | 7125 | WHILE DRILL CEMENT H2S ALARM WENT OF. CLOSED WELL IN AND CHECKED FOR PRESSURE, NO PRESSURE.
1784 | 04/20/2022 | ADES-144 | UTMN-3099 | RIG | 14 Apr 1630 - 0500 | 20.5 | 145 | 895536 |  | BHA | ISEQ | RM | 6625 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
1786 | 04/20/2022 | ADES-174 | GHZL-88 | WDS | 18 Apr 2300 - 1430 | 9.5 | 27.75 | 895550 |  | BHA | FOT | MWD | 11200 | WHILE DRLG. @ 10,300' HAD MWD-GR TOOL STOP PULSING.
1788 | 04/20/2022 | ADM-339 | RBYN-55 | SBA | 20 Apr 0300 - 0500 | 2 | 2 | 895747 |  | JF | HERR | ESP | 0 | WHILE TORQUEING DISCHARGE HEAD, THE SPANNER HOOKED TO TORQUE WRENCH FALL IN THE WELL.
1790 | 04/20/2022 | ADM-510 | ABSF-222 | SDM | 19 Apr 1900 - 2200 | 13.5 | 23.5 | 895644 |  | DD | IDPR | RSS | 7264 | SLB CONTROLLED DRILLING PARAMETERS TO MAINTAIN RSS STEERING AND ACHIEVE WELL PATH AS PER DIRECTIONAL PLAN REQUIREMENTS WITHOUT SUCCESS.
1792 | 04/20/2022 | ADM-511 | MRJN-799 | RIG | 20 Apr 0130 - 0245 | 1.25 | 1.25 | 895714 |  | RR | FOT | MPMP | 6466 | RIG REPAIR HAD MALUFUNCTION IN PUMP#1 AND PUMP# 3 FIXED SAME,
1794 | 04/20/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 329.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1795 | 04/20/2022 | ARO-3003 | SFNY-1740 | SPS | 20 Apr 1700 - 1845 | 1.75 | 1.75 | 895762 |  | TF | XTTE | RSS | 0 | EXCESSIVE TIME FOR LAY DOWN SPS BHA.
1797 | 04/20/2022 | ARO-3003 | SFNY-1740 | RIG | 20 Apr 0145 - 0500 | 3.25 | 3.25 | 895729 |  | DSF | FOT | STRG | 4678 | UNABLE TO CIRCULATE THROUGH STRING.
1798 | 04/20/2022 | ARO-3003 | SFNY-1740 | SPS | 20 Apr 1700 - 1845 | 1.75 | 1.75 | 895762 |  | TF | XTTE | RSS | 0 | EXCESSIVE TIME FOR LAY DOWN SPS BHA.
1800 | 04/20/2022 | DPS-4 | MDRK-54 | ARM | 14 Apr 2145 - 0500 | 24 | 141.5 | 895515 |  | WCNT | WCC5 | NA | 16095 | OBSERVED WELL FLOWING AT 0.4 BPH DURING FLOW CHECK.
1802 | 04/20/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 177.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1804 | 04/20/2022 | ENS-108 | SFNY-1720 | RIG | 20 Apr 1700 - 2300 | 6 | 6 | 895702 |  | RR | FOT | DWKS | 3150 | OBSERVED DAMAGE ON DRILLING LINE
1806 | 04/20/2022 | HI-5 | MHRH-58 | RIG | 19 Apr 1930 - 2330 | 13 | 22.5 | 895641 |  | BOP | HERR | BOP | 10731 | POH TO PERFORM BOP TEST.
1808 | 04/20/2022 | NA-128S | SAHB-28 | ARM | 20 Apr 1715 - 2100 | 3.75 | 3.75 | 895777 |  | STUK | STBH | MILL | 10568 | GOT STUCK PIPE MEANWHILE MILLING 7" HALL. EXPANDABLE LINER HANGER.
1810 | 04/20/2022 | NBR-196S | SDGM-1226 | RIG | 20 Apr 0900 - 1300 | 4 | 4 | 895696 |  | RR | FOT | RWCS | 10329 | AFTER BOP PRESSURE TEST DURING ACCUMULATOR REMOTE PANEL FUNCTION TEST AT TOOLPUSHER OFFICE AREA THE SHEAR RAM CONTROL WOULD NOT FUNCTION/ACTIVATE. TROUBLE SHOOT ISSUE.
1812 | 04/20/2022 | NBR-591S | HRDH-1921 | GOC | 20 Apr 2000 - 2130 | 1.5 | 1.5 | 895763 |  | TF | FOT | CRT | 4037 | CRT O-RING SEAL LEAKS WHILE ATTEMPT TO CIRC AT SHOE
1814 | 04/20/2022 | NBR-783S | NJYN-89 | BHI | 20 Apr 1700 - 0500 | 12 | 12 | 895719 |  | TF | FOT | FV | 14553 | DRILL TO 14553', BAKER RSS TOOL FAILED, UNBALE TO CONT DRLG.
1815 | 04/20/2022 | RM-74A | KARN-60 | SCT | 20 Apr 2345 - 0500 | 5.25 | 5.25 | 895771 |  | TF | FOT | CTAC | 12410 | SLB CT BLEED OFF LINE LOW TORQUE VALVES ON RIG FLOOR DEVELOPED LEAKS WHEN PRESSURE TEST WITH N2.
1817 | 04/20/2022 | RM-74A | KARN-60 | SCT | 20 Apr 0615 - 0815 | 2 | 2 | 895716 |  | WO | SRVC | NA | 0 | SLB CT ENCOUNTER ISSUES INSTALLING COIL SCAN.
1818 | 04/20/2022 | RM-74A | KARN-60 | SCT | 20 Apr 2345 - 0500 | 5.25 | 5.25 | 895771 |  | TF | FOT | CTAC | 12410 | SLB CT BLEED OFF LINE LOW TORQUE VALVES ON RIG FLOOR DEVELOPED LEAKS WHEN PRESSURE TEST WITH N2.
1820 | 04/20/2022 | SINO-43L | UTMN-4063 | BLH | 17 Apr 1530 - 0500 | 24 | 78 | 895528 |  | TF | FOT | HGRL | 11454 | ATTEMPT TO SET 5" BAKER SLZXP LINER TOP PACKER, DROPPED 1.5" BALL, PRESSURE UP TO 1700 PSI, SUDDENLY PRESSURE DROPPED TO ZERO, POOH, FOUND LINER RUNNING TOOL RELEASED AND LINER HANGER PACKER WITH LOWER COMPLETION LEFT IN HOLE.
1822 | 04/20/2022 | SINO-45L | UTMN-1098 | HWP | 20 Apr 2100 - 0300 | 6 | 6 | 895713 |  | TF | FOT | CUT | 0 | MECHANICAL CUTTER FAIL TO CUT TBG
1824 | 04/20/2022 | SND-2001 | UTMN-2329 | ARM | 13 Apr 1100 - 0500 | 18 | 170.75 | 895520 |  | LCIR | FRFM | NA | 8835 | OBSERVED TOTAL LOSSES AT 8835 FT ( LOWER FADHILI RES)
1826 | 04/20/2022 | SND-2002 | WAQR-23 | ARM | 18 Apr 1745 - 0500 | 24 | 57.5 | 895574 |  | CMT | FRFM | NA | 2790 | WHILE C/O 18-5/8"CSG SHOE TRACK AND AFTER FLOAT SHOE, HAD TOTAL LOSSES
1828 | 04/20/2022 | SND-2004 | BRRI-1148 | BHT | 20 Apr 0500 - 2145 | 15.75 | 15.75 | 895758 |  | LROP | ETRQ | BIT | 4665 | HAD CONTINIOUS ERRATIC TORQUE LEADING TO SLOW ROP. TRIP OUT TO CHANGE THE BIT
1830 | 04/20/2022 | SND-2005 | MHKK-2 | RIG | 19 Apr 2000 - 0500 | 24 | 33 | 895554 |  | RR | FOT | TDS | 9190 | AFTER REPLACING THE ACTUATER VALVE, WHILE PUMPING WITH 2,150 PSI AND DRILLING, OBSERVED LEAK AGAIN FROM SAME PLACE AS PREVIOUS. CONFIRM THE QUAIL SHAFT WAS WASHED OR HAS WEAK THREADS AND NEEDED TO BE REPLACED.
1832 | 04/20/2022 | SP-306 | MNIF-197 | ARM | 20 Apr 0630 - 0500 | 22.5 | 22.5 | 895783 |  | STUK | KSFM | STRG | 13076 | DRILL STRING STUCK IN 8-1/2" HOLE. WORK TO RELEASE STUCK PIPE.
1834 | 04/20/2022 | SSA-201 | HRDH-1818 | SWL | 17 Apr 1500 - 0500 | 22 | 84 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
1836 | 04/20/2022 | SSA-303 | HRDH-2306 | ARM | 17 Apr 0500 - 0500 | 24 | 94 | 895697 |  | TH | PCPF | NA | 2710 | ENCOUNTERED OBSTRUCTION @ 871'
1838 | 04/20/2022 | SSA-5891 | HRDH-2016 | SCD | 20 Apr 0030 - 0500 | 4.5 | 4.5 | 895780 |  | TF | FOT | MS | 12800 | LOST COMMUNICATION WITH TOOL.
1840 | 04/20/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 23.25 | 332.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1842 | 04/20/2022 | SSA-5974 | HRDH-1970 | ARM | 14 Apr 1400 - 0500 | 22 | 157 | 895514 |  | STUK | SDIR | RSS | 14870 | WASH AND REAM DOWN W/ 5-7/8" BAKER RSS & LWD-GR BHA DUE TO TIGHT HOLE JUST BELOW THE SHOE. ENCOUNTER ERATIC TQ, STOP REAMING DOWN @ 14904' WHILE BAKER ATTEMPT TO CENTER RSS TOOL/BIT TO ALIGN TO TRACK MODE. BAKER ACTIVATE DOWNLINK WHILE ROTATING @ 55 RPM & 200 GPM/2300 PSI -OBSERVE STRING STALL OUT & LOST CIRC W/PRESSURE INCREASE FROM 2300 PSI TO 3300 PSI. WORK STRING UP WAY FROM 20' BELOW SHOE TO INSIDE SHOE BY 15' FROM 14904' TO 14,870' -NO FURTHER MOVEMENT, NO ROTATION & NO CIRC.
1844 | 04/20/2022 | T914 | HWYH-135 | ARN | 18 Apr 1730 - 0500 | 24 | 59.5 | 895571 |  | STUK | PSSW | NA | 7883 | 4-1/2" OBL STUCK
1846 | 04/20/2022 | V140A | RBYN-100 | ARM | 20 Apr 1400 - 1515 | 1.25 | 1.25 | 895698 |  | WON | WTHR | NA | 6105 | WIND SPEED 0-1 KNTS NOT SUITABLE AND RECOMMENDED TO FLARE OFF OIL FROM SURGE TANKS.
1848 | 04/21/2022 | 910TE | DMMM-521 | SDM | 21 Apr 1130 - 2130 | 5.25 | 5.25 | 895818 |  | BHA | FOT | LWD | 15351 | TROUBLE SHOOT COMMUNICATION BETWEEN MWD & LWD, MADE SERVERAL ATTEMPTS TO DEPLOY THE PROB; NO SUCCESS. DECISION TO RESUME DRILLING.
1850 | 04/21/2022 | ADC-17 | ZULF-1215 | RIG | 21 Apr 1030 - 1100 | .5 | .5 | 895820 |  | RR | FOT | MPMP | 6890 | HAD FAILURE IN MUD PUMP VALVE SEAT
1852 | 04/21/2022 | ADC-41L | UTMN-3142 | TK3 | 21 Apr 1200 - 2030 | 8.5 | 8.5 | 895803 |  | STUK | PSSW | NA | 2560 | WHILE RIH 18-5/8" CSG GET HELD UP AT 2560 FT AND CSG GOT STUCK.
1854 | 04/21/2022 | ADC-49 | HRDH-2128 | RIG | 21 Apr 2300 - 0200 | 3 | 3 | 895819 |  | RR | FOT | ACDC | 2611 | BOP TEST PUMP MALFUNCTION
1855 | 04/21/2022 | ADC-50 | SFNY-1177 | RIG | 21 Apr 1630 - 1715 | .75 | .75 | 895801 |  | JF | XTRI | CTRQ | 0 | EXCESSIVE TIME FOR P/U & M/U SHOE TRACK.
1857 | 04/21/2022 | ADC-50 | SFNY-1177 | RIG | 21 Apr 1545 - 1630 | .75 | .75 | 895800 |  | TF | FOT | CTRQ | 0 | CASING POWER TONG FAILED TO MAKE UP CASING.
1858 | 04/21/2022 | ADC-50 | SFNY-1177 | RIG | 21 Apr 1630 - 1715 | .75 | .75 | 895801 |  | JF | XTRI | CTRQ | 0 | EXCESSIVE TIME FOR P/U & M/U SHOE TRACK.
1860 | 04/21/2022 | ADES-144 | UTMN-3099 | RIG | 14 Apr 1630 - 1400 | 9 | 154 | 895536 |  | BHA | ISEQ | RM | 6625 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
1862 | 04/21/2022 | ADES-40 | ANDR-469 | WI1 | 17 Apr 1000 - 0500 | 24 | 115 | 895817 |  | TF | FOT | FISHT | 0 | WIS 6-1/8" MILL & RETRIEVING TOOL PARTED FROM TOP OF SPEAR MANDREL AND LEFT FISH INSIDE 7" PKR SEAL BORE EXTENSION.
1864 | 04/21/2022 | ADM-339 | RBYN-55 | SBA | 20 Apr 0300 - 0500 | 24 | 26 | 895747 |  | JF | HERR | ESP | 0 | WHILE TORQUEING DISCHARGE HEAD, THE SPANNER HOOKED TO TORQUE WRENCH FALL IN THE WELL.
1866 | 04/21/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 353.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1868 | 04/21/2022 | ARO-3003 | SFNY-1740 | ARM | 20 Apr 0145 - 1900 | 14 | 17.25 | 895729 |  | DSF | FOT | STRG | 4678 | UNABLE TO CIRCULATE THROUGH STRING.
1870 | 04/21/2022 | BB-84A | MRJN-586 | RIG | 21 Apr 0200 - 0400 | 2 | 2 | 895802 |  | RR | FOT | MPMP | 8353 | PUMPS REPAIRE, CHANGE MUD PUMP SEAT.
1872 | 04/21/2022 | DPS-4 | MDRK-54 | ARM | 14 Apr 2145 - 1400 | 9 | 150.5 | 895515 |  | WCNT | WCC5 | NA | 16095 | OBSERVED WELL FLOWING AT 0.4 BPH DURING FLOW CHECK.
1874 | 04/21/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 201.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1876 | 04/21/2022 | NBR-633S | HRDH-2234 | RIG | 15 Apr 2100 - 0500 | 1 | 4 | 895537 |  | RR | FOT | CSYS | 1285 | EXCESS TIME WHILE P/U BHA DUE TO MULFUNCTION IN AIR ROUGHNECK.
1878 | 04/21/2022 | NBR-783S | NJYN-89 | BHI | 20 Apr 1700 - 0500 | 24 | 36 | 895719 |  | TF | FOT | FV | 14553 | DRILL TO 14553', BAKER RSS TOOL FAILED, UNBALE TO CONT DRLG.
1880 | 04/21/2022 | PA-866S | SHHB-2 | RIG | 21 Apr 1800 - 2000 | 2 | 2 | 895821 |  | BOP | FOT | BOP | 1480 | FIX VARIOUS LEAKS WHILE PRESSURE TESTING
1882 | 04/21/2022 | SDA | MRJN-735 | RIG | 21 Apr 1045 - 1330 | 2.75 | 2.75 | 895773 |  | RR | FOT | DWKS | 165 | WHILST HOISTING TDS FOR M/UP DP STAND FROM DERRICK, CROWN-OMATIC ACTIVATED AND CAUSING SUDDEN STOP OF DRAW WORKS AND BACKLASH OF DRILLING LINE.
1887 | 04/21/2022 | SINO-43L | UTMN-4063 | BLH | 17 Apr 1530 - 0500 | 24 | 102 | 895528 |  | TF | FOT | HGRL | 11454 | ATTEMPT TO SET 5" BAKER SLZXP LINER TOP PACKER, DROPPED 1.5" BALL, PRESSURE UP TO 1700 PSI, SUDDENLY PRESSURE DROPPED TO ZERO, POOH, FOUND LINER RUNNING TOOL RELEASED AND LINER HANGER PACKER WITH LOWER COMPLETION LEFT IN HOLE.
1889 | 04/21/2022 | SINO-5L | UTMN-1289 | ARN | 21 Apr 1415 - 1515 | 1 | 1 | 895792 |  | WO | STOP | NA | 8030 | BROADBAND SYSTEM INTERMITTENT DATA TRANSMISSION.
1891 | 04/21/2022 | SND-2002 | WAQR-23 | ARM | 18 Apr 1745 - 2145 | 16.75 | 74.25 | 895574 |  | CMT | FRFM | NA | 2790 | WHILE C/O 18-5/8"CSG SHOE TRACK AND AFTER FLOAT SHOE, HAD TOTAL LOSSES
1893 | 04/21/2022 | SND-2005 | MHKK-2 | RIG | 19 Apr 2000 - 1500 | 10 | 43 | 895554 |  | RR | FOT | TDS | 9190 | AFTER REPLACING THE ACTUATER VALVE, WHILE PUMPING WITH 2,150 PSI AND DRILLING, OBSERVED LEAK AGAIN FROM SAME PLACE AS PREVIOUS. CONFIRM THE QUILL SHAFT WAS WASHED OR HAS WEAK THREADS AND NEEDED TO BE REPLACED.
1895 | 04/21/2022 | SP-306 | MNIF-197 | ARM | 20 Apr 0630 - 0500 | 24 | 46.5 | 895783 |  | STUK | KSFM | STRG | 13076 | DRILL STRING STUCK IN 8-1/2" HOLE. WORK TO RELEASE STUCK PIPE.
1897 | 04/21/2022 | SSA-102 | QTIF-696 | GOC | 21 Apr 0500 - 0700 | 2 | 2 | 895816 |  | TF | FOT | CTRQ | 4875 | POWER TONG DID NOT WORK
1899 | 04/21/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 24 | 108 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
1901 | 04/21/2022 | SSA-303 | HRDH-2306 | ARM | 17 Apr 0500 - 0500 | 24 | 118 | 895697 |  | TH | PCPF | NA | 2710 | WHILE RUNNING 18-5/8" CSG ENCOUNTERED OBSTRUCTION @ 871' AND NOT ABLE TO PASS
1903 | 04/21/2022 | SSA-5859 | HRDH-1967 | RIG | 21 Apr 0330 - 0430 | 1 | 1 | 895822 |  | RR | FOT | SLIPS | 12790 | IRON ROUGHNECK FAILURE.
1905 | 04/21/2022 | SSA-5891 | HRDH-2016 | SCD | 20 Apr 0030 - 0930 | 4.5 | 9 | 895780 |  | TF | FOT | MS | 12800 | MULTIPLE INCONSISTENT SURVEYS & LOST COMMUNICATION WITH TOOL.
1907 | 04/21/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 22 | 354.5 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
1908 | 04/21/2022 | SSA-5974 | HRDH-1970 | BHI | 21 Apr 0200 - 0500 | 3 | 3 | 895774 |  | DD | HERR | RSS | 14884 | LOST TIME ON BAKER GEOMECHANICAL DUE TO INADEQUATE SUPPORT LEADING TO ENCOUNTER SEVERE HOLE UNSTABILITY ISSUE.
1910 | 04/21/2022 | SSA-5974 | HRDH-1970 | ARM | 14 Apr 1400 - 1700 | 12 | 169 | 895514 |  | STUK | SDIR | RSS | 14870 | WASH AND REAM DOWN W/ 5-7/8" BAKER RSS & LWD-GR BHA DUE TO TIGHT HOLE JUST BELOW THE SHOE. ENCOUNTER ERATIC TQ, STOP REAMING DOWN @ 14904' WHILE BAKER ATTEMPT TO CENTER RSS TOOL/BIT TO ALIGN TO TRACK MODE. BAKER ACTIVATE DOWNLINK WHILE ROTATING @ 55 RPM & 200 GPM/2300 PSI -OBSERVE STRING STALL OUT & LOST CIRC W/PRESSURE INCREASE FROM 2300 PSI TO 3300 PSI. WORK STRING UP WAY FROM 20' BELOW SHOE TO INSIDE SHOE BY 15' FROM 14904' TO 14,870' -NO FURTHER MOVEMENT, NO ROTATION & NO CIRC.
1911 | 04/21/2022 | SSA-5974 | HRDH-1970 | BHI | 21 Apr 0200 - 0500 | 3 | 3 | 895774 |  | DD | HERR | RSS | 14884 | LOST TIME ON BAKER GEOMECHANICAL DUE TO INADEQUATE SUPPORT LEADING TO ENCOUNTER SEVERE HOLE UNSTABILITY ISSUE.
1913 | 04/21/2022 | T914 | HWYH-135 | ARM | 18 Apr 1730 - 0500 | 24 | 83.5 | 895571 |  | STUK | SCSG | LINR | 7883 | 4-1/2" OBL STUCK
1914 | 04/22/2022 | 095TE | MNIF-220 | RIG | 22 Apr 0300 - 0500 | 2 | 2 | 895840 |  | RR | FOT | TDS | 6349 | TDS LOST COMMUNICATION, TROUBLESHOOTING . THE COMMS CABLE BETWEEN THE VFD AND DRILLER'S PANEL FOUND TO BE A FAULTY CONNECTION, REPLACE SAME. ATEMPT TO FUNCTION TEST FOUND THE CB AUX CONTACT GOT STUCK AND WAS NOT ALLOWING TDS PLC TO WORK PROPERLY, CHANGED THE AUX CONTACT AND RE-TESTED. OK
1916 | 04/22/2022 | 095TE | MNIF-220 | RIG | 22 Apr 0900 - 1000 | 1 | 1 | 895839 |  | RR | FOT | MPMP | 5288 | CIRCULATE USING MP#1 MEANWHILE REPAIR MUD PUMP #2,3
1917 | 04/22/2022 | 095TE | MNIF-220 | RIG | 22 Apr 0300 - 0500 | 2 | 2 | 895840 |  | RR | FOT | TDS | 6349 | TDS LOST COMMUNICATION, TROUBLESHOOTING . THE COMMS CABLE BETWEEN THE VFD AND DRILLER'S PANEL FOUND TO BE A FAULTY CONNECTION, REPLACE SAME. ATEMPT TO FUNCTION TEST FOUND THE CB AUX CONTACT GOT STUCK AND WAS NOT ALLOWING TDS PLC TO WORK PROPERLY, CHANGED THE AUX CONTACT AND RE-TESTED. OK
1919 | 04/22/2022 | ADC-52 | SDGM-1254 | RIG | 22 Apr 2100 - 0500 | 8 | 8 | 895827 |  | RR | FOT | TDS | 5260 | TDS SHOWING FAULT ON BLOWER MOTOR - CAN'T ROTATE UNDER LOAD.
1921 | 04/22/2022 | ADC-57L | FDHL-158 | TK3 | 22 Apr 2300 - 0100 | 2 | 2 | 895841 |  | STUK | SCSG | LINR | 13135 | DIFFERENTIAL STUCK AFTER CONNECTION CAN'T MOVE CSG LNR, HAVE CIRC.
1923 | 04/22/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 0500 | 22 | 22 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
1925 | 04/22/2022 | ADC-67L | UTMN-3156 | SDM | 22 Apr 0145 - 0500 | 3.25 | 3.25 | 895859 |  | BHA | FOT | RSS | 11885 | RSS FAILED TO BUILD UP.
1927 | 04/22/2022 | ADES-13 | HRDH-503 | GOC | 22 Apr 1600 - 2030 | 4.5 | 4.5 | 895837 |  | TF | FOT | TTRQ | 670 | WAIT ON AL-GHAITH TO REPLACE THE POWER UNIT- A PIN ON PRESSURE PUMP BROKEN.
1929 | 04/22/2022 | ADES-40 | ANDR-469 | WI1 | 17 Apr 1000 - 0500 | 23.5 | 138 | 895817 |  | TF | FOT | FISHT | 0 | WIS 6-1/8" MILL & RETRIEVING TOOL PARTED FROM TOP OF SPEAR MANDREL AND LEFT FISH INSIDE 7" PKR SEAL BORE EXTENSION.
1931 | 04/22/2022 | ADM-339 | RBYN-55 | SBA | 20 Apr 0300 - 0500 | 24 | 50 | 895747 |  | JF | HERR | ESP | 0 | WHILE TORQUEING DISCHARGE HEAD, THE SPANNER HOOKED TO TORQUE WRENCH FALL IN THE WELL.
1933 | 04/22/2022 | ADM-510 | ABSF-222 | WCR | 22 Apr 0100 - 0400 | 3 | 3 | 895826 |  | TF | FOT | CTRQ | 165 | WFD CRT CONTROL PANNEL NOT FUNCTIONING AS PER DESIGN SLIPS NOT OPENING WHEN THEY SHOULD & CTR DRIVE HEAD SLIPS NOT RELEASING
1935 | 04/22/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 377.25 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
1937 | 04/22/2022 | ARO-4001 | MRJN-539 | RIG | 22 Apr 2030 - 2130 | 1 | 1 | 895825 |  | UPRA | OTH | NA | 11048 | CREW NOT FOCUSING ON THE JOB AND NOT DOING THE PROPER PLANNING WHICH LED TO EXCESS TIME FOR THE OPERATION.
1939 | 04/22/2022 | CR-36A | ZULF-2030 | EX1 | 22 Apr 2100 - 0500 | 8 | 8 | 895846 |  | TF | FOT | SLICK | 5399 | ACCORDING TO PDHMS DOWN HOLE GAUGES EXPRO SLICKLINE HAS FAILED TO CLOSE SSD AS REQUIRED IN ORDER FOR US TO CONTINUE OUR FLOWBACK OPERATIONS SUCESSFULLY.
1941 | 04/22/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 21.5 | 73.25 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
1943 | 04/22/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 225.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
1945 | 04/22/2022 | ENSCO-76 | MRJN-851 | HWP | 22 Apr 2215 - 2315 | 1 | 1 | 895838 |  | STUK | HINW | WLT | 6190 | WHILE POH WITH WIRLELINE, TAKE 8K OVERPULL @ 6190'. (MOVING DOWN FREE) THEN ATTEMPT SEVERAL TIMES UNTIL PASSING UP FREE.
1947 | 04/22/2022 | HI-4 | SFNY-918 | GCD | 22 Apr 1500 - 0500 | 14 | 14 | 895876 |  | SURV | FOT | GYRO | 227 | ATTEMPT TO PERFORM SHALOW TEST ON GWD, HAVE NO SIGNAL F/ GWD
1949 | 04/22/2022 | HI-9 | QTIF-557 | ARN | 22 Apr 0900 - 0500 | 20 | 20 | 895793 |  | WO | SRVC | NA | 0 | RIG IS WAITING ON SEA BED SURVEY FROM HSU DUE TO BAD WEATHER, UNABLE TO PROCEED TO NEXT LOCATION PLATFORM QTIF-71, 557/558.
1951 | 04/22/2022 | NBR-196S | SDGM-1226 | RIG | 22 Apr 2000 - 0500 | 9 | 9 | 895794 |  | RR | FPMP | MPMP | 8020 | WHILE RIH WITH BAKER DIR. RSS/MWD/GR BHA OBSERVE SPP INCREASE FROM 2450PSI TO 3900PSI IN 20 STANDS. TROUBLE SHOOT ISSUE.
1953 | 04/22/2022 | NBR-575S | HRDH-1942 | ARM | 20 Apr 2330 - 0500 | 24 | 53.5 | 895791 |  | TH | NARW | NA | 2985 | RIH WITH 13 3/8" CASING HAD OBESTRUCTION @ 2985 FT.
1955 | 04/22/2022 | NBR-783S | NJYN-89 | BHI | 20 Apr 1700 - 2000 | 15 | 51 | 895719 |  | TF | FOT | FV | 14553 | DRILL TO 14553', BAKER RSS TOOL FAILED, UNBALE TO CONT DRLG.
1956 | 04/22/2022 | PA-604S | HRDH-1953 | FMC | 22 Apr 1830 - 2230 | 4 | 4 | 895828 |  | TF | XTTE | CTRQ | 680 | AFTER REVIEWING JAM CHART IT WAS NOTICED 1 JNT OVERTORQUED & 1 JNT OVERTURNED, PULL 3JTS.
1958 | 04/22/2022 | PA-604S | HRDH-1953 | RIG | 22 Apr 1530 - 1730 | 2 | 2 | 895824 |  | RR | DRIG | RSYS | 780 | UNABLE TO EFFECTIVELY RUN 9-5/8" CASING AS PER KPI DUE TO MISALIGNMENT OF TDS & BOP.
1959 | 04/22/2022 | PA-604S | HRDH-1953 | FMC | 22 Apr 1830 - 2230 | 4 | 4 | 895828 |  | TF | XTTE | CTRQ | 680 | AFTER REVIEWING JAM CHART IT WAS NOTICED 1 JNT OVERTORQUED & 1 JNT OVERTURNED, PULL 3JTS.
1961 | 04/22/2022 | SINO-43L | UTMN-4063 | BLH | 17 Apr 1530 - 1900 | 14 | 116 | 895528 |  | TF | FOT | HGRL | 11454 | ATTEMPT TO SET 5" BAKER SLZXP LINER TOP PACKER, DROPPED 1.5" BALL, PRESSURE UP TO 1700 PSI, SUDDENLY PRESSURE DROPPED TO ZERO, POOH, FOUND LINER RUNNING TOOL RELEASED AND LINER HANGER PACKER WITH LOWER COMPLETION LEFT IN HOLE.
1963 | 04/22/2022 | SND-1501 | UTMN-567 | RIG | 21 Apr 2330 - 0630 | 1.5 | 3 | 895834 |  | JF | XTRI | NA | 0 | RIG UNABLE TO RACK BACK 2-3/8" DP IN MAST
1965 | 04/22/2022 | SND-2001 | UTMN-2329 | ARM | 13 Apr 1100 - 0500 | 24 | 175.75 | 895520 |  | LCIR | FRFM | NA | 8835 | OBSERVED TOTAL LOSSES AT 8835 FT ( LOWER FADHILI RES)
1967 | 04/22/2022 | SND-2002 | WAQR-23 | ARM | 18 Apr 1745 - 0230 | 21.5 | 103 | 895574 |  | CMT | FRFM | NA | 2790 | WHILE C/O 18-5/8"CSG SHOE TRACK AND AFTER FLOAT SHOE, HAD TOTAL LOSSES
1969 | 04/22/2022 | SP-306 | MNIF-197 | ARM | 20 Apr 0630 - 0500 | 24 | 70.5 | 895783 |  | STUK | KSFM | STRG | 13076 | DRILL STRING STUCK IN 8-1/2" HOLE. WORK TO RELEASE STUCK PIPE.
1971 | 04/22/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 23 | 131 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
1973 | 04/22/2022 | SSA-202 | QTIF-500 | BHT | 21 Apr 2300 - 1600 | 10.75 | 16.75 | 895823 |  | LROP | ETRQ | BIT | 12586 | HAD CONTINIOUS ERRATIC TORQUE , TRIP OUT CHECK THE TCI BIT, FOUND BIT DAMAGED.
1975 | 04/22/2022 | SSA-303 | HRDH-2306 | ARM | 17 Apr 0500 - 0500 | 23.5 | 141.5 | 895697 |  | TH | PCPF | NA | 2710 | WHILE RUNNING 18-5/8" CSG ENCOUNTERED OBSTRUCTION @ 871' AND NOT ABLE TO PASS
1977 | 04/22/2022 | SSA-5868 | HRDH-2336 | WCR | 22 Apr 0330 - 0500 | 1.5 | 1.5 | 895830 |  | TF | FOT | CTRQ | 10140 | WEATHERFORD CSG EQUIPMENT FAILURE, REPLACED JTS DUE TO EQUIPMENT ISSUES AND CRT RUBBER FAILURE - STOPPED AND REPLACED SAME.
1979 | 04/22/2022 | SSA-5962 | HRDH-2230 | WDS | 22 Apr 1500 - 0430 | 13.5 | 13.5 | 895857 |  | BHA | FOT | RSS | 6733 | WFD RSS FAILURE, NO RESPONSE FROM MAGNUS RSS.
1981 | 04/22/2022 | SSA-5969 | UTMN-3021 | ARM | 22 Apr 0100 - 0500 | 4 | 4 | 895795 |  | LCIR | UVLC | NA | 8545 | HAD COMPLETE LOSSES AT 8,545'
1983 | 04/22/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0500 | 24 | 24 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE.
1985 | 04/22/2022 | T914 | HWYH-135 | ARM | 18 Apr 1730 - 0500 | 20 | 103.5 | 895571 |  | STUK | SCSG | LINR | 7883 | 4-1/2" OBL STUCK
1987 | 04/23/2022 | 095TE | MNIF-220 | RIG | 22 Apr 0300 - 2300 | 18 | 20 | 895840 |  | RR | FOT | TDS | 6349 | TDS LOST COMMUNICATION, TROUBLESHOOTING . THE COMMS CABLE BETWEEN THE VFD AND DRILLER'S PANEL FOUND TO BE A FAULTY CONNECTION, REPLACE SAME. ATEMPT TO FUNCTION TEST FOUND THE CB AUX CONTACT GOT STUCK AND WAS NOT ALLOWING TDS PLC TO WORK PROPERLY, CHANGED THE AUX CONTACT AND RE-TESTED. OK
1989 | 04/23/2022 | ADC-23 | RMLH-15 | SCM | 23 Apr 0500 - 1330 | 8.5 | 8.5 | 895860 |  | CMT | CFST | NA | 2800 | STRING PLUG BY CEMENT AFTER PUMP CEMENT PLUG#4
1991 | 04/23/2022 | ADC-50 | SFNY-1177 | RIG | 23 Apr 2230 - 0215 | 3.75 | 3.75 | 895883 |  | RR | FPMP | MPMP | 0 | PRESSURE DROPPED WHILE TESTING UPPER PIPE RAM. STOPPED PRESSURE TESTING AND TROUBLE SHOOTING FOUND RIG TEST UNIT CHECK VALVE IS LEAKING
1993 | 04/23/2022 | ADC-52 | SDGM-1254 | RIG | 22 Apr 2100 - 0800 | 3 | 11 | 895827 |  | RR | FOT | TDS | 5260 | TDS SHOWING FAULT ON BLOWER MOTOR - CAN'T ROTATE UNDER LOAD.
1995 | 04/23/2022 | ADC-58L | ABHD-178 | TK3 | 23 Apr 0045 - 0500 | 4.25 | 4.25 | 895847 |  | TH | PCPF | NA | 6966 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
1997 | 04/23/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 0500 | 22 | 44 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
1999 | 04/23/2022 | ADC-67L | UTMN-3156 | SDM | 22 Apr 0145 - 0330 | 22.5 | 25.75 | 895859 |  | BHA | FOT | RSS | 11885 | RSS FAILED TO BUILD UP.
2001 | 04/23/2022 | ADES-40 | ANDR-469 | WI1 | 17 Apr 1000 - 0500 | 18.5 | 156.5 | 895817 |  | TF | FOT | FISHT | 0 | WIS 6-1/8" MILL & RETRIEVING TOOL PARTED FROM TOP OF SPEAR MANDREL AND LEFT FISH INSIDE 7" PKR SEAL BORE EXTENSION.
2003 | 04/23/2022 | ADM-339 | RBYN-55 | SBA | 20 Apr 0300 - 0900 | 4 | 54 | 895747 |  | JF | HERR | ESP | 0 | WHILE TORQUEING DISCHARGE HEAD, THE SPANNER HOOKED TO TORQUE WRENCH FALL IN THE WELL.
2005 | 04/23/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 20.75 | 398 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
2007 | 04/23/2022 | ARO-3004 | MRJN-2060 | RIG | 23 Apr 1930 - 0500 | 9.5 | 9.5 | 895865 |  | RR | FOT | PSYS | 5800 | RIG LOST POWER TO DRILLING CONSOLE TROUBLE SHOOT TO REGAIN POWER
2009 | 04/23/2022 | CR-36A | ZULF-2030 | EX1 | 23 Apr 0500 - 1115 | 6.25 | 6.25 | 895885 |  | TF | FOT | SLICK | 5399 | ACCORDING TO PDHMS DOWN HOLE GAUGES EXPRO SLICKLINE HAS FAILED TO CLOSE SSD AS REQUIRED IN ORDER FOR US TO CONTINUE OUR FLOWBACK OPERATIONS SUCESSFULLY.
2011 | 04/23/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 13 | 86.25 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
2013 | 04/23/2022 | DPS-46 | SDGM-1106 | GOC | 23 Apr 1330 - 1430 | 1 | 1 | 895832 |  | TF | FOT | CTRQ | 80 | POWER TONG FAILURE
2015 | 04/23/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 249.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
2017 | 04/23/2022 | EXL-IA | SFNY-4240 | RTC | 23 Apr 0100 - 0500 | 4 | 4 | 895849 |  | TF | FOT | BIT | 4007 | BIT WOULD NOT DRILL, HIGH TORQUE ON BOTTOM.
2019 | 04/23/2022 | HI-4 | SFNY-918 | GCD | 22 Apr 1500 - 0115 | 20.25 | 34.25 | 895876 |  | SURV | FOT | GYRO | 227 | ATTEMPT TO PERFORM SHALOW TEST ON GWD, HAVE NO SIGNAL F/ GWD
2021 | 04/23/2022 | HI-9 | QTIF-557 | ARN | 22 Apr 0900 - 0500 | 24 | 44 | 895793 |  | WO | SRVC | NA | 0 | RIG IS WAITING ON SEA BED SURVEY FROM HSU DUE TO BAD WEATHER, UNABLE TO PROCEED TO NEXT LOCATION PLATFORM QTIF-71, 557/558.
2022 | 04/23/2022 | NBR-196S | SDGM-1226 | BHI | 23 Apr 0100 - 0500 | 4 | 4 | 895882 |  | BHA | FOT | RSS | 10411 | LOST SIGNAL FROM BAKER AUTOTRAC (RSS) BAKER AUTOTRAC SYSTEM FAILED - UNABLE TO RECEIVE SIGNAL FROM RSS TO MWD.
2024 | 04/23/2022 | NBR-196S | SDGM-1226 | RIG | 22 Apr 2000 - 1100 | 6 | 15 | 895794 |  | RR | FPMP | MPMP | 8020 | WHILE RIH WITH BAKER DIR. RSS/MWD/GR BHA OBSERVE SPP INCREASE FROM 2450PSI TO 3900PSI IN 20 STANDS. TROUBLE SHOOT ISSUE.
2025 | 04/23/2022 | NBR-196S | SDGM-1226 | BHI | 23 Apr 1430 - 1600 | 1.5 | 1.5 | 895842 |  | DD | HERR | MMOT | 10140 | TROUBLE SHOOT MUD PUMP LOSS OF PRESSURE & LOSS OF SUCTION.
2026 | 04/23/2022 | NBR-196S | SDGM-1226 | BHI | 23 Apr 0100 - 0500 | 4 | 4 | 895882 |  | BHA | FOT | RSS | 10411 | LOST SIGNAL FROM BAKER AUTOTRAC (RSS) BAKER AUTOTRAC SYSTEM FAILED - UNABLE TO RECEIVE SIGNAL FROM RSS TO MWD.
2028 | 04/23/2022 | NBR-575S | HRDH-1942 | ARM | 20 Apr 2330 - 1130 | 6.5 | 60 | 895791 |  | TH | NARW | NA | 2985 | RIH WITH 13 3/8" CASING HAD OBESTRUCTION @ 2985 FT.
2030 | 04/23/2022 | NBR-783S | NJYN-89 | RIG | 23 Apr 0530 - 0500 | 23.5 | 23.5 | 895831 |  | RR | FPMP | MPMP | 14818 | 2 PUMPS DOWN UNABLE TO REPAIR WHILE DRILLING POOH TO CASING SHOE FOR REPAIR
2032 | 04/23/2022 | PA-622S | AFLJ-4 | BHI | 23 Apr 0745 - 0915 | 1.5 | 1.5 | 895861 |  | TF | XTTE | MWD | 350 | WHILE PERFORMING SHALLOW TEST OF BAKER MWD TOOL, NOTICED TOOL NOT ABLE TO DECODE DATA SENT TO SURFACE.
2034 | 04/23/2022 | RBP-50A | KARN-51 | HCO | 23 Apr 0230 - 0500 | 2.5 | 2.5 | 895864 |  | TF | FOT | SSSV | 11775 | HALLIBURTON PRIMARY AND SECONDARY TRSSSV'S FAILED PRESSURE TESTS. AWAITING RESULT P/TEST BAKER GE TRSSSV.
2055 | 04/23/2022 | SL-7 | ZULF-1331 | SPS | 23 Apr 0430 - 0500 | .5 | .5 | 895845 |  | BHA | FOT | FV | 3500 | SPERRY SUN FLOAT VALVE IS PASSING.
2056 | 04/23/2022 | SND-2001 | UTMN-2329 | ARM | 23 Apr 2000 - 2100 | 1 | 1 | 895844 |  | LCIR | FRFM | NA | 8967 | OBSERVED TOTAL LOSSES AT 8967 FT ( LOWER FADHILI RES)
2058 | 04/23/2022 | SND-2001 | UTMN-2329 | ARM | 13 Apr 1100 - 1800 | 10 | 185.75 | 895520 |  | LCIR | FRFM | NA | 8835 | OBSERVED TOTAL LOSSES AT 8835 FT ( LOWER FADHILI RES)
2059 | 04/23/2022 | SND-2001 | UTMN-2329 | ARM | 23 Apr 2000 - 2100 | 1 | 1 | 895844 |  | LCIR | FRFM | NA | 8967 | OBSERVED TOTAL LOSSES AT 8967 FT ( LOWER FADHILI RES)
2061 | 04/23/2022 | SNF036 | MRJN-901 | SWL | 23 Apr 1615 - 1915 | 3 | 3 | 895863 |  | TF | FOT | WLT | 9368 | SLB WL MRX TOOL ANTENNA SHUT DOWN. POOH WITH FAILED TOOL AND P/U BACKUP TOOL. RESUME LOGGING OPERATIONS.
2063 | 04/23/2022 | SP-306 | MNIF-197 | ARM | 20 Apr 0630 - 2130 | 16.5 | 87 | 895783 |  | STUK | KSFM | STRG | 13076 | DRILL STRING STUCK IN 8-1/2" HOLE. WORK TO RELEASE STUCK PIPE.
2065 | 04/23/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 24 | 155 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
2067 | 04/23/2022 | SSA-303 | HRDH-2306 | ARM | 17 Apr 0500 - 0500 | 23.5 | 165 | 895697 |  | TH | PCPF | NA | 2710 | WHILE RUNNING 18-5/8" CSG ENCOUNTERED OBSTRUCTION @ 871' AND NOT ABLE TO PASS
2069 | 04/23/2022 | SSA-5868 | HRDH-2336 | WCR | 22 Apr 0330 - 1415 | 3 | 4.5 | 895830 |  | TF | FOT | CTRQ | 10140 | WEATHERFORD CSG EQUIPMENT FAILURE, REPLACED JTS DUE TO EQUIPMENT ISSUES AND CRT RUBBER FAILURE - STOPPED AND REPLACED SAME.
2070 | 04/23/2022 | SSA-5962 | HRDH-2230 | WDS | 22 Apr 1500 - 1700 | 9.5 | 23 | 895857 |  | BHA | FOT | RSS | 6733 | WFD RSS FAILURE, NO RESPONSE FROM MAGNUS RSS.
2072 | 04/23/2022 | SSA-5962 | HRDH-2230 | CRW | 23 Apr 2200 - 0430 | 6.5 | 6.5 | 895843 |  | TF | FOT | PCPD | 6787 | POOH DUE LOST PRESSURE OFF/ON BOTTOM - FOUND CORETRAX PBL FAILED & OPENED WHILE DRILLING 16'' SECTION
2073 | 04/23/2022 | SSA-5962 | HRDH-2230 | WDS | 22 Apr 1500 - 1700 | 9.5 | 23 | 895857 |  | BHA | FOT | RSS | 6733 | WFD RSS FAILURE, NO RESPONSE FROM MAGNUS RSS.
2074 | 04/23/2022 | SSA-5969 | UTMN-3021 | ARM | 23 Apr 2030 - 0500 | 8.5 | 8.5 | 895881 |  | LCIR | UVLC | NA | 8585 | HAD COMPLETE LOSSES AT 8,585'
2076 | 04/23/2022 | SSA-5969 | UTMN-3021 | ARM | 22 Apr 0100 - 2030 | 11 | 15 | 895795 |  | LCIR | UVLC | NA | 8545 | HAD COMPLETE LOSSES AT 8,545'
2077 | 04/23/2022 | SSA-5969 | UTMN-3021 | ARM | 23 Apr 2030 - 0500 | 8.5 | 8.5 | 895881 |  | LCIR | UVLC | NA | 8585 | HAD COMPLETE LOSSES AT 8,585'
2079 | 04/23/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0500 | 24 | 48 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE.
2081 | 04/23/2022 | T901 | JLMN-79 | FMC | 23 Apr 1630 - 0430 | 2.25 | 2.25 | 895884 |  | JF | XTRI | CTRQ | 0 | CUMULATIVE EXCESS TIME TO RUN 9-5/8" DUE TO USING RIG CRANE.
2083 | 04/23/2022 | T901 | JLMN-79 | FMC | 23 Apr 1630 - 0430 | 2.25 | 2.25 | 895884 |  | JF | XTRI | CTRQ | 0 | CUMULATIVE EXCESS TIME TO RUN 9-5/8" DUE TO USING RIG CRANE.
2085 | 04/23/2022 | T914 | HWYH-135 | ARM | 18 Apr 1730 - 2000 | 15 | 118.5 | 895571 |  | STUK | SCSG | LINR | 7883 | 4-1/2" OBL STUCK
2087 | 04/24/2022 | 095TE | MNIF-220 | RIG | 24 Apr 0400 - 0500 | 1 | 1 | 895893 |  | RR | FOT | MPMP | 7655 | CHC WITH MP#3 WHILE REPAIR MP#1&2
2088 | 04/24/2022 | ADC-42L | UTMN-2327 | RIG | 24 Apr 2300 - 0130 | 2.5 | 2.5 | 895890 |  | JF | XTRI | BOP | 8050 | OBSERVED UPPER PIPE RAM WAS LEAKING. REMAINING BOP TESTS CARRIED OUT WHILE WAITING FOR NEW UPPER PIPE RAM PACKER AND BLOCK.
2090 | 04/24/2022 | ADC-42L | UTMN-2327 | RIG | 24 Apr 2130 - 2300 | 1.5 | 1.5 | 895850 |  | JF | XTRI | TESTT | 8050 | TROUBLE SHOOT TEST UNIT, UNABLE TO REPAIR IT.
2091 | 04/24/2022 | ADC-42L | UTMN-2327 | RIG | 24 Apr 2300 - 0130 | 2.5 | 2.5 | 895890 |  | JF | XTRI | BOP | 8050 | OBSERVED UPPER PIPE RAM WAS LEAKING. REMAINING BOP TESTS CARRIED OUT WHILE WAITING FOR NEW UPPER PIPE RAM PACKER AND BLOCK.
2093 | 04/24/2022 | ADC-50 | SFNY-1177 | RIG | 24 Apr 1500 - 1800 | 3 | 3 | 895919 |  | JF | XTRI | BOP | 0 | EXCESS TIME WHILE M/UP BOPS TEST ASSY AND PRESSURE TEST BOPS DUE TO IMPROPER PLANNING.TEST PLUG PLUGGED DUE TO FOLLOWING WRONG PRACTICE DURING BOP TEST.
2095 | 04/24/2022 | ADC-55L | UTMN-3199 | TK3 | 24 Apr 2315 - 0500 | 5.75 | 5.75 | 895851 |  | TF | FOT | LINR | 12953 | WHILE REMAING LINER DOWN AT 12457 FT OBSERVED 10 KLBS SLACK-OFF
2097 | 04/24/2022 | ADC-56L | UTMN-2330 | TSC | 24 Apr 0600 - 0830 | 2.5 | 2.5 | 895869 |  | TF | FOT | CTRQ | 10955 | ATTEMPT TO INSTALL CRT PACKER INTO 9 5/8" CSG. OBSERVED RUBBER PACKER ON CRT CUT AND 1 X PIECE OF RUBBER FELL INTO CSG.
2099 | 04/24/2022 | ADC-58L | ABHD-178 | TK3 | 23 Apr 0045 - 0500 | 24 | 28.25 | 895847 |  | TH | PCPF | NA | 6966 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
2100 | 04/24/2022 | ADC-59L | HRDH-1987 | RIG | 24 Apr 2045 - 2330 | 2.75 | 2.75 | 895871 |  | RR | FOT | TDS | 734 | OBSERVED LEAKING ON IBOP
2102 | 04/24/2022 | ADC-59L | HRDH-1987 | RIG | 24 Apr 1515 - 1630 | 1.25 | 1.25 | 895870 |  | RR | FOT | TDS | 640 | WHILE TRYING TO BREAK CONNECTION BETWEEN TOP DRIVE AND DP, OBSERVED BROKEN CONNECTION BETWEEN IBOPS.
2103 | 04/24/2022 | ADC-59L | HRDH-1987 | RIG | 24 Apr 2045 - 2330 | 2.75 | 2.75 | 895871 |  | RR | FOT | TDS | 734 | OBSERVED LEAKING ON IBOP
2105 | 04/24/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 0500 | 23 | 67 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
2107 | 04/24/2022 | ADC-70 | SFNY-1820 | SDM | 24 Apr 1945 - 2100 | 1.25 | 1.25 | 895898 |  | DD | HERR | MMOT | 1127 | WELLLINK TROUBLE SHOOT DATA TRANSMISSION ISSUE FROM SLB. MEANWHILE, CHC.
2109 | 04/24/2022 | ADES-40 | ANDR-469 | WI1 | 17 Apr 1000 - 0500 | 24 | 180.5 | 895817 |  | TF | FOT | FISHT | 0 | WIS 6-1/8" MILL & RETRIEVING TOOL PARTED FROM TOP OF SPEAR MANDREL AND LEFT FISH INSIDE 7" PKR SEAL BORE EXTENSION.
2111 | 04/24/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 422 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
2113 | 04/24/2022 | ARO-3004 | MRJN-2060 | RIG | 23 Apr 1930 - 0500 | 24 | 33.5 | 895865 |  | RR | FOT | PSYS | 5800 | RIG LOST POWER TO DRILLING CONSOLE TROUBLE SHOOT TO REGAIN POWER
2114 | 04/24/2022 | ARO-4001 | MRJN-539 | RIG | 24 Apr 1715 - 1800 | .75 | .75 | 895916 |  | RR | FPMP | MPMP | 11351 | MUD PUMP TRIPPED SEVERAL TIMES, RESET RIG MUD PUMP SEVERAL TIMES.
2116 | 04/24/2022 | ARO-4001 | MRJN-539 | HCM | 24 Apr 1345 - 1445 | 1 | 1 | 895835 |  | JF | CEDE | NA | 11048 | WORK STRING UP AND DOWN WHILE INVESTIGATING THE SOFT CMT ABOVE THE SHOE, DECISION MADE TO CONTINUE DRILLING AS THE MUD WT. WILL BE THE SAME 78 PCF.
2117 | 04/24/2022 | ARO-4001 | MRJN-539 | BHI | 24 Apr 2100 - 2145 | .75 | .75 | 895899 |  | BHA | ISEQ | LWD | 11351 | GOT BAD DECODING FROM BHI LWD ASSY., SENT DOWN LINKS AND RELOG THE INTERVAL AGAIN. ** REPEATED BAD DECODING WHILE DRILLING.
2118 | 04/24/2022 | ARO-4001 | MRJN-539 | RIG | 24 Apr 1715 - 1800 | .75 | .75 | 895916 |  | RR | FPMP | MPMP | 11351 | MUD PUMP TRIPPED SEVERAL TIMES, RESET RIG MUD PUMP SEVERAL TIMES.
2120 | 04/24/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 23.5 | 109.75 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
2122 | 04/24/2022 | DPS-44 | UTMN-3151 | RIG | 24 Apr 0800 - 1000 | 2 | 2 | 895897 |  | RR | FOT | TDS | 11640 | FOUND LEAK IN TDS SAVER SUB, POH TO SHOE, REPLACED SAME AND RAN BACK TO BOTTOM..
2124 | 04/24/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 273.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
2126 | 04/24/2022 | EXL-IA | SFNY-4240 | RTC | 23 Apr 0100 - 1600 | 11 | 15 | 895849 |  | TF | FOT | BIT | 4007 | BIT WOULD NOT DRILL, HIGH TORQUE ON BOTTOM.
2128 | 04/24/2022 | HI-9 | QTIF-557 | ARN | 22 Apr 0900 - 0500 | 24 | 68 | 895793 |  | WO | SRVC | NA | 0 | RIG IS WAITING ON SEA BED SURVEY FROM HSU DUE TO BAD WEATHER, UNABLE TO PROCEED TO NEXT LOCATION PLATFORM QTIF-71, 557/558.
2130 | 04/24/2022 | NBR-16S | HMYM-433302 | SDM | 24 Apr 0215 - 0500 | 2.75 | 2.75 | 895872 |  | SURV | FOT | MS | 8165 | LOST MWD SIGNAL
2132 | 04/24/2022 | NBR-196S | SDGM-1226 | BHI | 23 Apr 0100 - 0030 | 19.5 | 23.5 | 895882 |  | BHA | FOT | RSS | 10411 | LOST SIGNAL FROM BAKER AUTOTRAC (RSS) BAKER AUTOTRAC SYSTEM FAILED - UNABLE TO RECEIVE SIGNAL FROM RSS TO MWD.
2134 | 04/24/2022 | NBR-783S | NJYN-89 | RIG | 23 Apr 0530 - 0500 | 12.5 | 36 | 895831 |  | RR | FPMP | MPMP | 14818 | 2 PUMPS DOWN UNABLE TO REPAIR WHILE DRILLING POOH TO CASING SHOE FOR REPAIR
2136 | 04/24/2022 | NBR-797S | UTMN-3130 | HTD | 24 Apr 2100 - 0200 | 5 | 5 | 895894 |  | WH | HERR | WH | 2780 | HOTHEAD WELLHEAD PRE-HEATER WHILE PICKING UP AFTER HEATED THE WELLHEAD FELL DOWN DUE TO SOCKET ON HOIST WIRE ROPE PARTING DUE TO EXCESS OF HEAT.
2138 | 04/24/2022 | PA-622S | AFLJ-4 | ARM | 24 Apr 1000 - 0500 | 19 | 19 | 895875 |  | STUK | PSSW | NA | 6896 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENTLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION.
2139 | 04/24/2022 | PN-9 | MRJN-91 | BHI | 24 Apr 0500 - 0500 | 22 | 22 | 895902 |  | LROP | IDPR | BHA | 5788 | SLOW ROP, UNABLE TO APPLY DIFFERENTIAL PRESSURE MORE THAN 200 PSI ACROSS BHI MUD MTR. LOST TIME BAKER DIRECTIONAL.
2141 | 04/24/2022 | PN-9 | MRJN-91 | RIG | 24 Apr 1230 - 1430 | 2 | 2 | 895901 |  | RR | FOT | CSYS | 5802 | T-PIECE/ GOOSE NECK CONNECTION LEAKING, SECURE & REPLACED O-RING SEAL.
2142 | 04/24/2022 | PN-9 | MRJN-91 | BHI | 24 Apr 0500 - 0500 | 22 | 22 | 895902 |  | LROP | IDPR | BHA | 5788 | SLOW ROP, UNABLE TO APPLY DIFFERENTIAL PRESSURE MORE THAN 200 PSI ACROSS BHI MUD MTR. LOST TIME BAKER DIRECTIONAL.
2144 | 04/24/2022 | RBP-50A | KARN-51 | HCO | 23 Apr 0230 - 2030 | 15.5 | 18 | 895864 |  | TF | FOT | SSSV | 11775 | HALLIBURTON PRIMARY AND SECONDARY TRSSSV'S FAILED PRESSURE TESTS. AWAITING RESULT P/TEST BAKER GE TRSSSV.
2146 | 04/24/2022 | RM-74A | KARN-60 | CAM | 24 Apr 2100 - 2300 | 2 | 2 | 895889 |  | WH | FOT | WH | 0 | CAMERON 10K PUMP UNABLE TO REACH 10K PSI FOR PRESSURE TESTING.
2148 | 04/24/2022 | SCTD-1 | SDGM-1240 | SDM | 24 Apr 2100 - 0500 | 8 | 8 | 895873 |  | BHA | FOT | MMOT | 14664 | SUSPECT TURBINE FAILURE DUE TO SUDDEN INCREASE IN CIRC & DIFF PRESSURE. POH TO SURFACE, FOUND TURBINE SEIZED.
2150 | 04/24/2022 | SINO-22 | BRRI-381 | RIG | 24 Apr 1130 - 1215 | .75 | .75 | 895887 |  | RR | FOT | TDS | 19326 | RIG TDS STOPPED WORKING, FOUND MALFUNCTION ON ELECTRICAL TDS UPS . ELECTICIAN FIXED THE ISSUE.
2152 | 04/24/2022 | SL-7 | ZULF-1331 | SPS | 23 Apr 0430 - 0900 | 4 | 4.5 | 895845 |  | BHA | FOT | FV | 3500 | SPERRY SUN FLOAT VALVE IS PASSING.
2154 | 04/24/2022 | SND-1501 | UTMN-567 | MSL | 24 Apr 1730 - 2000 | 2.5 | 2.5 | 895874 |  | TF | FOT | SLICK | 0 | LUBRICATOR O- RING RUBBER SEAL FOUND DAMAGED.
2156 | 04/24/2022 | SND-1502 | HRDH-121 | WDS | 24 Apr 1430 - 2100 | 6.5 | 6.5 | 895853 |  | DD | IDPR | MMOT | 6414 | WFD MUD MOTOR BEARING FAILURE.
2158 | 04/24/2022 | SND-2001 | UTMN-2329 | ARM | 23 Apr 2000 - 0500 | 16.5 | 17.5 | 895844 |  | LCIR | FRFM | NA | 8967 | OBSERVED TOTAL LOSSES AT 8967 FT ( LOWER FADHILI RES)
2160 | 04/24/2022 | SND-2002 | WAQR-23 | ARM | 24 Apr 0700 - 0500 | 22 | 22 | 895892 |  | STUK | STBH | BHA | 4233 | AFTER CONNECTION, IBOP OPENED AFTER FEW ATTEMPTS AND FOUND THE STRING STUCK 3 FT OFF-BTM (NO MOVING, NO ROTATION AND NO CIRCULATION).
2162 | 04/24/2022 | SNF036 | MRJN-901 | SWL | 24 Apr 1130 - 1445 | 3.25 | 3.25 | 895868 |  | TF | FOT | WLT | 9368 | MDT LOGGING TOOL FAILED DUE TO OIL LEAK IN THE TOOL. POOH & CHANGE FAILED TOOL. RESUME LOGGING OPERATIONS
2164 | 04/24/2022 | SP-58 | MDRK-53 | ARM | 24 Apr 0900 - 1100 | 2 | 2 | 895938 |  | STUK | HINW | WLT | 15445 | HES RDT W/L TOOLS GOT STUCK @ 15,445' WHILE RIH ON DP (7' INSIDE OH), WORKED STRING FREE, POH W/L TO SURFACE FOR INSPECTION & RIH 5-7/8" REAMING BHA.
2166 | 04/24/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 24 | 179 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
2168 | 04/24/2022 | SSA-303 | HRDH-2306 | ARM | 17 Apr 0500 - 0500 | 24 | 189 | 895697 |  | TH | PCPF | NA | 2710 | WHILE RUNNING 18-5/8" CSG ENCOUNTERED OBSTRUCTION @ 871' AND NOT ABLE TO PASS
2170 | 04/24/2022 | SSA-5914 | WDYH-80 | ARM | 04 Apr 1300 - 0500 | 16.75 | 371.25 | 894728 |  | STUK | STBH | BHA | 14590 | OBSERVED STRING STUCK WHILE POOH AT 14590 FT. UNABLE TO PULL.
2172 | 04/24/2022 | SSA-5962 | HRDH-2230 | CRW | 23 Apr 2200 - 1630 | 11.5 | 18 | 895843 |  | TF | FOT | PCPD | 6787 | POOH DUE LOST PRESSURE OFF/ON BOTTOM - FOUND CORETRAX PBL FAILED & OPENED WHILE DRILLING 16'' SECTION
2174 | 04/24/2022 | SSA-5969 | UTMN-3021 | ARM | 23 Apr 2030 - 0500 | 21.5 | 30 | 895881 |  | LCIR | UVLC | NA | 8585 | HAD COMPLETE LOSSES AT 8,585'
2176 | 04/24/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0500 | 24 | 72 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE.
2178 | 04/24/2022 | T901 | JLMN-79 | RIG | 24 Apr 0430 - 0500 | .5 | .5 | 895891 |  | BOP | FOT | BOP | 0 | LEAKING FROM ANNULAR BOP WEEP HOLE DUE TO OPENING CHAMBER FAILURE.
2180 | 04/25/2022 | 095TE | MNIF-220 | RIG | 24 Apr 0400 - 0730 | 2.5 | 3.5 | 895893 |  | RR | FOT | MPMP | 7655 | CHC WITH MP#3 WHILE REPAIR MP#1&2
2181 | 04/25/2022 | ADC-31 | SDGM-1181 | RIG | 25 Apr 2130 - 2245 | 1.25 | 1.25 | 895922 |  | RR | FOT | TDS | 980 | FIX TDS GRABBERS.
2183 | 04/25/2022 | ADC-31 | SDGM-1181 | RIG | 25 Apr 0630 - 1000 | 3.5 | 3.5 | 895921 |  | RR | LHFL | HSYS | 660 | FIX LEAKING HYDRAULIC HOSES ON TDS.
2184 | 04/25/2022 | ADC-31 | SDGM-1181 | RIG | 25 Apr 2130 - 2245 | 1.25 | 1.25 | 895922 |  | RR | FOT | TDS | 980 | FIX TDS GRABBERS.
2186 | 04/25/2022 | ADC-42L | UTMN-2327 | RIG | 24 Apr 2300 - 1630 | 2.25 | 4.75 | 895890 |  | JF | XTRI | BOP | 8050 | OBSERVED UPPER PIPE RAM WAS LEAKING. REMAINING BOP TESTS CARRIED OUT WHILE WAITING FOR NEW UPPER PIPE RAM PACKER AND BLOCK.
2187 | 04/25/2022 | ADC-55L | UTMN-3199 | TK3 | 25 Apr 1630 - 2245 | 6.25 | 6.25 | 895924 |  | CMT | HERR | NA | 12953 | OBSERVED UNSAFE CRANE OPERATION PRACTICES & DISREGARD FOR ENVIRONMENTAL SAFETY WHILE MIXING CEMENT MIX FLUID AT CEMENT TANK.
2189 | 04/25/2022 | ADC-55L | UTMN-3199 | TK3 | 24 Apr 2315 - 1045 | 5.75 | 11.5 | 895851 |  | TF | FOT | LINR | 12953 | WHILE REMAING LINER DOWN AT 12457 FT OBSERVED 10 KLBS SLACK-OFF
2190 | 04/25/2022 | ADC-55L | UTMN-3199 | TK3 | 25 Apr 1630 - 2245 | 6.25 | 6.25 | 895924 |  | CMT | HERR | NA | 12953 | OBSERVED UNSAFE CRANE OPERATION PRACTICES & DISREGARD FOR ENVIRONMENTAL SAFETY WHILE MIXING CEMENT MIX FLUID AT CEMENT TANK.
2192 | 04/25/2022 | ADC-58L | ABHD-178 | TK3 | 23 Apr 0045 - 0500 | 23.5 | 51.75 | 895847 |  | TH | PCPF | NA | 6966 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS.
2194 | 04/25/2022 | ADC-62L | ANDR-745 | ARN | 25 Apr 0045 - 0500 | 4.25 | 4.25 | 895925 |  | WO | HMWT | NA | 2072 | WAIT ON FIXING THE WATER LINES AND FILL THE WATER PIT & MUD TANKS
2196 | 04/25/2022 | ADC-66L | UTMN-2361 | TK3 | 22 Apr 0630 - 0500 | 24 | 91 | 895877 |  | HC | CFFM | NA | 680 | WORKED CASING STRING UP/DOWN WITH DIFFERENT FLOW RATES FROM 10 - 20 BPM, NO CHANGE IN PRESSURE, WITH OUT SUCCESS, UNABLE TO PASS.
2198 | 04/25/2022 | ADES-144 | UTMN-3099 | RIG | 25 Apr 1100 - 0330 | 16.5 | 16.5 | 895940 |  | BHA | ISEQ | RM | 9666 | LOST IN HOLE ONE OF THE ROLLER BLOCK FROM THE RIG STRING ROLLER REAMERS.
2200 | 04/25/2022 | ADES-40 | ANDR-469 | WI1 | 17 Apr 1000 - 0500 | 24 | 204.5 | 895817 |  | TF | FOT | FISHT | 0 | WIS 6-1/8" MILL & RETRIEVING TOOL PARTED FROM TOP OF SPEAR MANDREL AND LEFT FISH INSIDE 7" PKR SEAL BORE EXTENSION.
2202 | 04/25/2022 | ARO-3001 | ZULF-2058 | ARM | 05 Apr 1030 - 0500 | 24 | 446 | 894792 |  | STUK | STCT | SCRN | 10340 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN
2204 | 04/25/2022 | ARO-3004 | MRJN-2060 | RIG | 23 Apr 1930 - 1415 | 9.25 | 42.75 | 895865 |  | RR | FOT | PSYS | 5800 | RIG LOST POWER TO DRILLING CONSOLE TROUBLE SHOOT TO REGAIN POWER
2206 | 04/25/2022 | ARO-4001 | MRJN-539 | RIG | 25 Apr 0845 - 1030 | 1.75 | 1.75 | 895942 |  | RR | FOT | DWKS | 12738 | DRAW WORK CONTROLLER FROZEN, UN ABLE TO MOVE, RESET SAME, RACK BACK ONE STD AND CALIBRATE.
2208 | 04/25/2022 | DPS-4 | MDRK-54 | ARM | 15 Apr 1900 - 0500 | 24 | 133.75 | 895547 | 895515 | STUK | STBH | BHA | 16058 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL.
2210 | 04/25/2022 | DPS-74 | NJYN-54 | ARM | 13 Apr 0730 - 0500 | 24 | 297.25 | 895421 |  | STUK | SCSG | LINR | 14010 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION.
2212 | 04/25/2022 | EXL-IA | SFNY-4240 | RIG | 25 Apr 1730 - 0400 | 10.5 | 10.5 | 895920 |  | RR | FOT | TDS | 4687 | WHILE TRIPPING IN, OBSERVE TDS MALFUNCTION, TROUBLESHOOT VFD POWER MODULE.
2214 | 04/25/2022 | HI-2 | BRRI-464 | ARN | 25 Apr 1030 - 1245 | 2.25 | 2.25 | 895937 |  | WO | STOP | NA | 11460 | GOC STOPPED DRLG TO EVALUATE LWD LOG WITH RDD.
2216 | 04/25/2022 | HI-9 | QTIF-557 | ARN | 22 Apr 0900 - 0500 | 24 | 92 | 895793 |  | WO | SRVC | NA | 0 | RIG IS WAITING ON SEA BED SURVEY FROM HSU DUE TO BAD WEATHER, UNABLE TO PROCEED TO NEXT LOCATION PLATFORM QTIF-71, 557/558.
2217 | 04/25/2022 | NBR-16S | HMYM-433302 | SDM | 25 Apr 0300 - 0500 | 2 | 2 | 895941 |  | SURV | FOT | MS | 8785 | LOST MWD SIGNAL
2219 | 04/25/2022 | NBR-16S | HMYM-433302 | SDM | 24 Apr 0215 - 1800 | 13 | 15.75 | 895872 |  | SURV | FOT | MS | 8165 | LOST MWD SIGNAL
2220 | 04/25/2022 | NBR-16S | HMYM-433302 | SDM | 25 Apr 0300 - 0500 | 2 | 2 | 895941 |  | SURV | FOT | MS | 8785 | LOST MWD SIGNAL
2222 | 04/25/2022 | NBR-196S | SDGM-1226 | BHI | 25 Apr 1415 - 0500 | 14.25 | 14.25 | 895895 |  | BHA | FOT | RSS | 10755 | LOST SIGNAL FROM BAKER AUTOTRAC (RSS) BAKER AUTOTRAC SYSTEM FAILED - UNABLE TO RECEIVE SIGNAL FROM RSS TO MWD.
2224 | 04/25/2022 | NBR-591S | HRDH-1921 | ARM | 25 Apr 0515 - 0500 | 23.75 | 23.75 | 895917 |  | LCIR | UVLC | NA | 8910 | ROTARY DRILL 12" HOLE NEW FORMATION BY 5 FT TO 8915'. HAD TOTAL LOSSES.
2226 | 04/25/2022 | NBR-633S | HRDH-2234 | RIG | 25 Apr 0000 - 0200 | 2 | 2 | 895944 |  | BOP | HERR | BOP | 5100 | EXCESS TIME WHILE N/U & P/T BOPE.
2228 | 04/25/2022 | NBR-783S | NJYN-89 | RIG | 23 Apr 0530 - 0900 | 4 | 40 | 895831 |  | RR | FPMP | MPMP | 14818 | 2 PUMPS DOWN UNABLE TO REPAIR WHILE DRILLING POOH TO CASING SHOE FOR REPAIR
2230 | 04/25/2022 | PA-622S | AFLJ-4 | ARM | 24 Apr 1000 - 0500 | 24 | 43 | 895875 |  | STUK | PSSW | NA | 6896 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENTLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION.
2232 | 04/25/2022 | PN-9 | MRJN-91 | BHI | 24 Apr 0500 - 0030 | 19.5 | 41.5 | 895902 |  | LROP | IDPR | BHA | 5788 | SLOW ROP, UNABLE TO APPLY DIFFERENTIAL PRESSURE MORE THAN 200 PSI ACROSS BHI MUD MTR. LOST TIME BAKER DIRECTIONAL.
2234 | 04/25/2022 | RM-74A | KARN-60 | GEP | 25 Apr 1000 - 0500 | 14.75 | 14.75 | 895936 |  | WO | SRVC | NA | 0 | MODIFIED BLANKING PLUG FOR 6 3/8" K-TYPE BPV, PASSING.
2236 | 04/25/2022 | SND-1502 | HRDH-121 | WDS | 25 Apr 0700 - 1000 | 3 | 3 | 895852 |  | DD | KSFM | RSS | 4890 | REAM TIGHT SPOTS.
2238 | 04/25/2022 | SND-2001 | UTMN-2329 | ARM | 23 Apr 2000 - 0500 | 15.5 | 33 | 895844 |  | LCIR | FRFM | NA | 8967 | OBSERVED TOTAL LOSSES AT 8967 FT ( LOWER FADHILI RES)
2240 | 04/25/2022 | SND-2002 | WAQR-23 | ARM | 24 Apr 0700 - 0500 | 24 | 46 | 895892 |  | STUK | STBH | BHA | 4233 | AFTER CONNECTION, IBOP OPENED AFTER FEW ATTEMPTS AND FOUND THE STRING STUCK 3 FT OFF-BTM (NO MOVING, NO ROTATION AND NO CIRCULATION).
2242 | 04/25/2022 | SP-103 | KRSN-70 | ARM | 25 Apr 1830 - 0500 | 10.5 | 10.5 | 895923 |  | STUK | STDP | DP | 13035 | AFTER POH WITH 3-7/8" CLEAN OUT ASSY ON 4" DP IN OPEN HOLE FREELY WITH 4 STD'S 4" DP, STRING GOT STUCK DUE TO HOLE CONDITION.
2244 | 04/25/2022 | SSA-201 | HRDH-1818 | ARM | 17 Apr 1500 - 0500 | 24 | 203 | 895529 |  | STUK | HINW | WLT | 14502 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH.
2246 | 04/25/2022 | SSA-5969 | UTMN-3021 | ARM | 23 Apr 2030 - 0500 | 24 | 54 | 895881 |  | LCIR | UVLC | NA | 8585 | HAD COMPLETE LOSSES AT 8,585'
2248 | 04/25/2022 | SSA-5974 | HRDH-1970 | ARM | 22 Apr 0500 - 0500 | 24 | 96 | 895858 |  | BHS | CWEL | NA | 14884 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE.
2249 | 04/25/2022 | T901 | JLMN-79 | ARM | 25 Apr 2330 - 0430 | 5 | 5 | 895943 |  | WON | WTHR | NA | 0 | SUSPENDED OPERATION DUE TO STRONG WIND AND HEAVY RAIN.
2251 | 04/25/2022 | T901 | JLMN-79 | RIG | 24 Apr 0430 - 0500 | 3.75 | 4.25 | 895891 |  | BOP | FOT | BOP | 0 | LEAKING FROM ANNULAR BOP WEEP HOLE DUE TO OPENING CHAMBER FAILURE.
2252 | 04/25/2022 | T901 | JLMN-79 | ARM | 25 Apr 2330 - 0430 | 5 | 5 | 895943 |  | WON | WTHR | NA | 0 | SUSPENDED OPERATION DUE TO STRONG WIND AND HEAVY RAIN.