## Sheet1
| Cause | Company Name | Cummulative Hrs | Date and Time | Depth | LT ID | LT Summary | LT Type | Object | Parent LT ID | Report Date | Rig Name | Time in Hrs | Well No
0 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADC-14 | Hrs | HRDH-612
1 | FOT | RIG | 47.5 | 30 Jun 0500 - 0500 | 11265 | 899058 | UNABLE TO LATCH BAKER WIRE LINE WET CONNECTOR TO LOGGING TOOLS DUE TO SCALE FROM DP COATING ACCUMULATED INSIDE LATCH ASSY. | DSF | DP |  | 07/01/2022 | ADC-14 | 24 | HRDH-612
2 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADC-16 | Hrs | JAHM-6
3 | FOT | BAW | 17.5 | 01 Jul 0630 - 0000 | 11505 | 898988 | BAKER STRADDLE PACKER UNABLE TO SEAL. | TF | WLT |  | 07/01/2022 | ADC-16 | 17.5 | JAHM-6
4 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADC-31 | Hrs | SDGM-1181
5 | UDWL | SPS | 5 | 01 Jul 0000 - 0500 | 15410 | 899023 | SPERRY RSS FAILURE. RSS UNABLE TO KEEP ANGLE. | DD | RSS |  | 07/01/2022 | ADC-31 | 5 | SDGM-1181
6 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADC-35 | Hrs | MAQL-5
7 | FOT | BLH | 32 | 30 Jun 1415 - 0500 | 11925 | 899082 | HOLE PACKED OFF ,TRY TO RE-GAIN CIRCULATION, WITHOUT SUCCESS, POOH 2 STD, HOLE FREE UP, AND RESTRICTED GOING DOWN, REGAIN CIRCULATION, TRY TO GO DOWN STILL HAD OBSTRUCTION. DECISION WAS MADE TO POOH, OBSERVED SWABBING, DECEIDED TO PUMP OUT. - 0 STAIC LOSSES. - 80 BBL/ MIN DYNAMIC LOSSES AT 2.6 BPM. | TF | HGRL |  | 07/01/2022 | ADC-35 | 20.25 | MAQL-5
8 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADC-50 | Hrs | SFNY-1176
9 | UVLC | ARM | 129.5 | 26 Jun 1845 - 0500 | 2864 | 898935 | HAD SEVERE LOSSES WHILE DRLG 12-1/4" HOLE @ 2,864', OPEN PBL SUB AND SPOT 2EA LCM PILLS WITH NO SUCCESS. | LCIR | NA |  | 07/01/2022 | ADC-50 | 24 | SFNY-1176
10 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADC-62L | Hrs | ANDR-745
11 | HERR | RIG | 316 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/01/2022 | ADC-62L | 24 | ANDR-745
12 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADC-70 | Hrs | BRRI-1204
13 | FOT | HWP | 4.5 | 01 Jul 2330 - 0400 | 8926 | 899020 | HAD HALL RDT TOOL FAILURE. TROUBLSHOOT SAME; NO SUCCESS. ROUN TRIP TO CHANGE OUT RDT TOOL. | TF | WLT |  | 07/01/2022 | ADC-70 | 4.5 | BRRI-1204
14 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADES-173 | Hrs | UTMN-1964
15 | FOT | RIG | 14 | 30 Jun 2245 - 1245 | 12220 | 899015 | GYRO TOOL FACE GIVING DIFFERENT READINGS. GYRO NOT ABLE TO LATCH IN THE UBHO PROPERLY. | DSF | DP |  | 07/01/2022 | ADES-173 | 7.75 | UTMN-1964
16 | FOT | BCT | 2.75 | 01 Jul 2300 - 0145 | 0 | 899094 | IMMD CONNECTOR ON BAKER COIL TUBING LEAKING ON HIGH PRESSURE | TF | CTAC |  | 07/01/2022 | ADM-337 | 2.75 | MRJN-900
17 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ADM-337 | Hrs | MRJN-900
18 | FOT | BCT | 1 | 01 Jul 1500 - 1600 | 0 | 899093 | LEAKING BOP CONTROL HOSE ON BAKER COIL TUBING UNIT | TF | CTAC |  | 07/01/2022 | ADM-337 | 1 | MRJN-900
19 | FOT | BCT | 2.75 | 01 Jul 2300 - 0145 | 0 | 899094 | IMMD CONNECTOR ON BAKER COIL TUBING LEAKING ON HIGH PRESSURE | TF | CTAC |  | 07/01/2022 | ADM-337 | 2.75 | MRJN-900
20 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | ARO-4001 | Hrs | MRJN-538
21 | FOT | RIG | 4.25 | 01 Jul 1830 - 2245 | 16606 | 899092 | OBSERVED POWER SHORTAGE IN THE RIG DRAWWORKS & MUD PUMPS. TROUBLE SHOOT AND REBOOTED SBC (SINGLE BASE COMPUTER) IN RIG POWER SYSTEM | RR | PSYS |  | 07/01/2022 | ARO-4001 | 4.25 | MRJN-538
22 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | CG-1 | Hrs | ZULF-1201
23 | FOT | RIG | 3.5 | 01 Jul 1300 - 1630 | 9065 | 898991 | RIG REPAIR- TROUBLE SHOOTING ON TDS PIPE HANDLER | RR | TDS |  | 07/01/2022 | CG-1 | 3.5 | ZULF-1201
24 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | DPS-46 | Hrs | SDGM-727
25 | FOT | CRW | 102.25 | 26 Jun 2300 - 0630 | 13360 | 898822 | STRING GOT STUCK AFTER CIRC THRU CORETRAX CIRC SUB | BHA | WBCL |  | 07/01/2022 | DPS-46 | 1.5 | SDGM-727
26 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | DQ-47 | Hrs | KHRS-497
27 | HERR | ARM | 93 | 28 Jun 0800 - 0500 | 3570 | 898952 | GOC UNABLE TO REACH TARGET ENTRY OF ARB-1 DUE TO SHALLOWER TOP FORMATION W/42'. | JF | NA |  | 07/01/2022 | DQ-47 | 24 | KHRS-497
28 | 11490 | 8235 | TI | N | 3534 | SPDP | - CONTINUE RIH W/ 4 1/2 CO ON 5' DP F/ 6400 T/ 8235 FT - P/U,M/U 12 JTS 5" DP- PASS CARFULLY FROM IMPAS PACKER 1-ST @ 6724 FT ,2-ND @ 7353 , 3RD@ 8227 FT - WASH DOWN LAST STAND -PASS CARFULLY FROM 7" TOL @ 5886 FT-FILL STRING EVERY 10 STANDS WITH 75 75 PCF VISCOUS BRINE - KEEP TRIP TANK RUNNING W/75 PCF VISCOUS BRINE @ 60-70 BPH | 11490 | 6400 | RIG | 07/01/2022 | DQ-57L | CT | KHRS-399
29 | 11490 |  | CIRC | N | 3534 | MPMP | - BULLHEAD ANNULUS W/50 BBL HI-VIS FOLLOWED BY 550 BBL 75 PCF VISCOUS BRINE @ 6BPM&180 PSI- FLOW CHECK ,WELL IN COMPLETE LOSS | 11490 |  | RIG | 07/01/2022 | DQ-57L | CT | KHRS-399
30 | 11490 | 2836 | LDP | N | 3534 | STRG | - POOH W/4 1/2 CO ON 5" DP/HWDP F/8235 T/2836 FT- L/D 4 3/4 NOV DRILLING JAR | 11490 | 8235 | RIG | 07/01/2022 | DQ-57L | CT | KHRS-399
31 | 11490 |  | HT | N | 3534 | PEL | - R/D 5" DP POWER TONG& HANDLING TOOLS ,R/U 2 7/8 DP POWER TONG & HANDLING TOOLS | 11490 |  | RIG | 07/01/2022 | DQ-57L | CT | KHRS-399
32 | 11490 | 0 | LDP | N | 3534 | STRG | - CONTINUE POOH W/ 4 1/2 CO ASSY. ,L/D 2 7/8 HTPAC DP TO SURFACE ( 90 JTS)- KEEP TRIP TANK RUNNING W/75 PCF VISCOUS BRINE ,60-70 BPH.- L/D 4 1/2 CO ASSEMBLY | 11490 | 2836 | RIG | 07/01/2022 | DQ-57L | CT | KHRS-399
33 | 11490 |  | OTH | N | 3534 | NA | - HPJSM ,PU,M/U & RIH W/ 5 1/2 ME INTERWELL PLUG T/2836 FT - CIRCULATE STRING VOLUME EVERY 10 STAND W/75 PCF VISCOUS BRINE USING NON-SEALED HOSE AND SUPERCHARGE PUMP - KEEP TRIP TANK RUNNING W/75 PCF VISCOUS BRINE ,60-70 BPH. | 11490 |  | RIG | 07/01/2022 | DQ-57L | PA | KHRS-399
34 | 11490 |  | OTH | N | 3534 | NA | - R/D 2 7/8 DP POWER TONG & HANDLING TOOLS .R/U 5" DP POWER TONG & HANDLING TOOLS | 11490 |  | RIG | 07/01/2022 | DQ-57L | PA | KHRS-399
35 | 11490 |  | OTH | N | 3534 | NA | - CONTINUE RIH W/5 1/2 ME INTERWELL PLUG T/8100 FT SETTING DEPTH - CIRCULATE STRING VOLUME EVERY 10 STAND W/75 PCF VISCOUS BRINE USING NON-SEALED HOSE AND SUPERCHARGE PUMP - KEEP TRIP TANK RUNNING W/75 PCF VISCOUS BRINE ,60-70 BPH. | 11490 |  | RIG | 07/01/2022 | DQ-57L | PA | KHRS-399
36 | 11490 |  | OTH | N | 3534 | NA | - RECORDED P/U ,S/O WT ,194/150 KLB- BULLHEAD ANNULUS W/50 BBL HI-VIS BRINE FOLLOWED BY 550 BBL 75 PCF VISCOUS BRINE @ 6BPM&180 PSI | 11490 |  | RIG | 07/01/2022 | DQ-57L | PA | KHRS-399
37 | 24 | OOS | Category | DOOS ID | RPBP | Out of Scope Summary | RIH W/ 5 1/2 ME INTERWELL PLUG , SET @ 8100 FT | 24 | 3534 | 01 Jul 0300 | 07/01/2022 | DQ-57L | Type | KHRS-399
38
39
40 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | HI-4 | Hrs | SFNY-918
41 | FOT | SCP | 94 | 26 Jun 1500 - 0930 | 4899 | 898833 | UNABLE TO UNSTING SCHLUMBERGER WETCONNECTOR SEAL ASSEMBLY FROM WET CONNECTOR RECEPTACLE WITH STANDARD PROCEDURES (25 -35 KBLS OVERPULL). STRING ROTATION AND 50 KLBS OVERPULL WAS REQUIRED TO BE ABLE TO RELEASE STINGER WET CONNECTOR SEAL ASSEMBLY. | TF | SEAL |  | 07/01/2022 | HI-4 | 4.5 | SFNY-918
42 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | HI-9 | Hrs | BRRI-155
43 | WOTR | MRN | 7 | 01 Jul 0730 - 1430 | 0 | 899063 | RIG MOVE BOAT ZAMIL-57 HAD PORT AZI THRUSTER (PROPELLER) FAILURE & UNABLE TO PERFORM THE RIG MOVE. | WO | NA |  | 07/01/2022 | HI-9 | 7 | BRRI-155
44 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | NA-18S | Hrs | UTMN-1886
45 | FOT | BAW | 3.5 | 01 Jul 1230 - 1600 | 500 | 898989 | WHILE RUNNING MPC CUTTER ON BAKER E-LINE AT 500FT HAD POWER SHORTAGE. POH. | TF | WLT |  | 07/01/2022 | NA-18S | 3.5 | UTMN-1886
46 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | NA-207S | Hrs | SHYB-132
47 | STBH | ARM | 77 | 28 Jun 0000 - 0500 | 4749 | 898940 | STRING STUCK WHILE MILLING OUT 7" LINER | STUK | MILL |  | 07/01/2022 | NA-207S | 24 | SHYB-132
48 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | NBR-115S | Hrs | HWYH-1220
49 | SCSG | ARM | 4.5 | 01 Jul 0030 - 0500 | 19850 | 899065 | DURING WASH IN THE HOLE WITH SLB MSF COMPLETION STRING STUCK ON CONNECTION. | STUK | LINR |  | 07/01/2022 | NBR-115S | 4.5 | HWYH-1220
50 | UNKN | RIG | 1 | 01 Jul 1400 - 1500 | 0 | 899095 | SAFETY STAND DOWN MEETING WAS HELD WITH ALL CREWS, DISCUSSED THE INCIDENT, HAZARD ASSOCIATED AND LESSON LEARNED. | HSEI | NA |  | 07/01/2022 | NBR-263S | 1 | QTIF-736
51 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | NBR-263S | Hrs | QTIF-736
52 | UVLC | ARM | 206 | 22 Jun 0630 - 0500 | 8541 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/01/2022 | NBR-263S | 23 | QTIF-736
53 | UNKN | RIG | 1 | 01 Jul 1400 - 1500 | 0 | 899095 | SAFETY STAND DOWN MEETING WAS HELD WITH ALL CREWS, DISCUSSED THE INCIDENT, HAZARD ASSOCIATED AND LESSON LEARNED. | HSEI | NA |  | 07/01/2022 | NBR-263S | 1 | QTIF-736
54 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | NBR-654S | Hrs | HRDH-1150
55 | FOT | RIG | 19.75 | 01 Jul 0730 - 0500 | 5136 | 899087 | A MAIN BREAKER FAILURE FOR THE TOP DRIVE VFD. | RR | PSYS |  | 07/01/2022 | NBR-654S | 19.75 | HRDH-1150
56 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | PA-529S | Hrs | SHYB-108
57 | FOT | ENV | 388.75 | 25 May 1045 - 1645 | 0 | 896965 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY. | TF | EXPND |  | 07/01/2022 | PA-529S | 11.75 | SHYB-108
58 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | PA-604S | Hrs | HRDH-1955
59 | HERR | SJC | 2.5 | 01 Jul 1715 - 1945 | 9280 | 898990 | UNABLE TO SCREW IN SANJEL CEMENTING HEAD TO CSG. CEMENTING HEAD CROSSOVER IS NOT RIGHT AS LABELED. | CMT | NA |  | 07/01/2022 | PA-604S | 2.5 | HRDH-1955
60 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | PA-70S | Hrs | MDRK-64
61 | FOT | WLH | 737.75 | 30 May 1800 - 0500 | 15492 | 897183 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP. | TF | LLAP |  | 07/01/2022 | PA-70S | 24 | MDRK-64
62 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | PN-9 | Hrs | MRJN-677
63 | FOT | DEL | 5.5 | 30 Jun 0030 - 0600 | 0 | 899085 | OBSERVE DELTA TEST PLUG LEAKING AT 3000 PSI THROUGH SOV DURING BOP TEST. POH TEST PLUG, OBSERVED TEST PLUG SEALS DAMAGED, REPLACE SEALS AND RUN TEST PLUG. HOLD 300 PSI & FAIL ON 3000 PSI. | WH | WH |  | 07/01/2022 | PN-9 | 1 | MRJN-677
64 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | RBP-50A | Hrs | KARN-51
65 | FOT | HSL | 5.5 | 01 Jul 0500 - 1030 | 11775 | 898987 | LEAK ON HSL RISER CONNECTION BELOW RIG FLOOR. R/DN AND REPLACE OTIS O-RING, STILL LEAKING REPLACE 10FT OF RISER. | TF | SLICK |  | 07/01/2022 | RBP-50A | 5.5 | KARN-51
66 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | RM-74A | Hrs | HSBH-68
67 | GRF | RIG | 30.25 | 30 Jun 2245 - 0500 | 1905 | 898983 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT | UPRA | RWCS |  | 07/01/2022 | RM-74A | 24 | HSBH-68
68 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SCTD-1 | Hrs | SDGM-1152
69 | FOT | RIG | 74.5 | 28 Jun 1600 - 1830 | 15037 | 898938 | TURBINE DOWNHOLE FAILURE. | BHA | MMOT |  | 07/01/2022 | SCTD-1 | 13.5 | SDGM-1152
70 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SINO-36L | Hrs | SDGM-458
71 | IPDF | TK1 | 329.5 | 17 Jun 1130 - 0500 | 8146 | 898452 | WORK ON FREEING STUCK 3-7/8" CLEAN OUT ASSEMBLY. | STUK | DP |  | 07/01/2022 | SINO-36L | 24 | SDGM-458
72 | 9129 |  | CIRC | N | 3505 | MPMP | PUMPED 30 BBL LOW-VIS / HI-VIS AND CHC.- DYNAMIC LOSSES 130 BPH.- FLOW CHECK 80 BBLS STATIC LOSSES. | 9129 |  | RIG | 07/01/2022 | SINO-46L | CT | SHYB-708
73 | 9129 | 4800 | RW | N | 3505 | BIT | POOH PUMP OUT FROM BTM @ 9129' TO 7580' , CIRC BTM/UP, CONT PUMP OUT TO 4,800'.** DYNAMIC LOSSES 120 BPH. | 9129 | 9129 | RIG | 07/01/2022 | SINO-46L | CT | SHYB-708
74 | 9129 |  | CIRC | N | 3505 | MPMP | PUMPED SWEEPS AND CHC UNTIL SHAKER CLEAN.- DYNAMIC LOSSES 120 BPH.- FLOW CHECK 80 BBLS STATIC LOSSES | 9129 |  | RIG | 07/01/2022 | SINO-46L | CT | SHYB-708
75 | 9129 | 250 | TO | N | 3505 | BHA | POOH 6-1/8" CO ASSY TO TOP OF BHA @ 250 FT.- FLOW CHECK - 80 BPH STATIC LOSSES. | 9129 | 4800 | RIG | 07/01/2022 | SINO-46L | CT | SHYB-708
76 | 9129 |  | HT | N | 3505 | BHA | POOH & LD CO ASSY. | 9129 |  | RIG | 07/01/2022 | SINO-46L | DRLG | SHYB-708
77 | 9129 |  | HT | N | 3492 | BHA | HPJSM, PU MU & RIH BHI P&A KIT (MPASS PACKER)- BHA: GPV SHOE, 2X 4-1/2" PUP JT, WELL BORE ISOLATION VALVE, 4-1/2" TBG, 4 1/2'' 12.6 MPAS, 4-1/2" TBG, 4 1/2'' 12.6 MPAS, 4-1/2" TBG, SETTING TOOL, X/O, 4" DP. | 9129 |  | RIG | 07/01/2022 | SINO-46L | PA | SHYB-708
78 | 9129 | 7490 | TI | N | 3492 | STDP | RIH BHI P&A KIT (MPASS PACKER)FROM 225 FT TO TOW @ 7,490 FT.- PASSED 7" TOL WITHOUT ANY OBSTRUCTION.- F/U STRING EVERY 20 STDS. MONITOR THE WELL ON TT. | 9129 | 225 | RIG | 07/01/2022 | SINO-46L | PA | SHYB-708
79 | 9129 |  | CIRC | N | 3492 | MPMP | CIRC. STRING CAPACITY , RECORD PU / SO WT. | 9129 |  | RIG | 07/01/2022 | SINO-46L | PA | SHYB-708
80 | 9129 | 9050 | HT | N | 3492 | STRG | RIH BHI P&A KIT (MPASS PACKER) FROM 7,490 FT TO 9,050 FT (SETTING DEPTH).- NO OBSTRUCTION WHILE PASSING L1 WINDOW AND WHILE RIH IN OPEN HOLE. | 9129 | 7490 | RIG | 07/01/2022 | SINO-46L | PA | SHYB-708
81 | 9129 |  | CIRC | N | 3492 | MPMP | SET BHI P&A KIT (MPASS PACKER) - RECORD PU / SO WT. PU : 155 KLBS, SOW: 90 KLBS. - DROP THE PACKERS SETTING BALL AND PUMP 20 BBL HI-VIS. PUMPED DOWN THE BALL IN BALL SEAT- INCREASE PRESSURE TO 2700 PSI AND HOLD FOR 10 MIN.- SET THE PACKER & CONFIRM THE SETTING WITH 5 KLBS OVERPULL & 5 KLBS SLOCK-OFF.- BLEED PRESSURE TO 400 PSI AND RELEASE RUNNING TOOL WITH 15 RHT.- GOOD INDICATION OF SETTING TOOL RELEASE AS PRESSURE DROPPED FROM 400 PSI TO 0. OBSERVED NORMAL PICK UP STRING WEIGHT.- MPAS #1 @ 8,967 FT, MPAS #2 @ 8,904 FT.- FLOW CHECK, WELL STATIC. | 9129 |  | RIG | 07/01/2022 | SINO-46L | PA | SHYB-708
82 | 9129 |  | CIRC | N | 3492 | MPMP | DISPLACED HOLE TO 73 PCF CACL2 VISCOUS BRINE... INC@RPT. | 9129 |  | RIG | 07/01/2022 | SINO-46L | PA | SHYB-708
83 | 10 | OOS | HCRM | 3505 | PAKT | CLEAN OUT RUN PRIOR RUN P&A KIT | RUN AND SET P&A KIT | 10 | 3492 | 01 Jul 0045 | 07/01/2022 | SINO-46L | OOS | SHYB-708
84
85
86
87 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SINO-47 | Hrs | HRDH-1351
88 | FOT | SPS | 26 | 30 Jun 1815 - 0500 | 11467 | 899084 | NOT ABLE TO GET MWD SURVEY | SURV | MS |  | 07/01/2022 | SINO-47 | 24 | HRDH-1351
89 | LHFL | RIG | 2 | 01 Jul 0100 - 0300 | 6940 | 899019 | TDS BROKEN HOSE LEAKING IN THE EXTENDED FUNCTION (DOLLY) WAS DISCOVERED. | RR | HSYS |  | 07/01/2022 | SL-7 | 2 | ZULF-1334
90 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SL-7 | Hrs | ZULF-1334
91 | FOT | RIG | .5 | 01 Jul 0600 - 0630 | 0 | 899018 | RIG DAMAGED FITTING ON TDS WHILE EXCHANGING BAILS. DUE TO HYDRULIC TUBE CONTACTED BY AIR WINCH SHACKLE. | RR | TDS |  | 07/01/2022 | SL-7 | .5 | ZULF-1334
92 | LHFL | RIG | 2 | 01 Jul 0100 - 0300 | 6940 | 899019 | TDS BROKEN HOSE LEAKING IN THE EXTENDED FUNCTION (DOLLY) WAS DISCOVERED. | RR | HSYS |  | 07/01/2022 | SL-7 | 2 | ZULF-1334
93 | FOT | RIG | 3 | 01 Jul 0630 - 0930 | 210 | 899086 | RIG'S PRAGMA (HYDRAULIC CATWALK) NOT FUNCTIONING CORRECTLY TO LIFT 9-5/8" CASING JTS TO RIG FLOOR. | RR | HSYS |  | 07/01/2022 | SND-2005 | 3 | MHKK-2
94 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SND-2005 | Hrs | MHKK-2
95 | FOT | WCR | 6 | 01 Jul 2300 - 0500 | 3782 | 899064 | WFD HYDRUALIC FLUSH MOUNT SLIPS NOT FUNCTIONING CORRECTLY, TROUBLESHOOT SAME WITH NO SUCCESS. | TF | CTRQ |  | 07/01/2022 | SND-2005 | 6 | MHKK-2
96 | FOT | RIG | 3 | 01 Jul 0630 - 0930 | 210 | 899086 | RIG'S PRAGMA (HYDRAULIC CATWALK) NOT FUNCTIONING CORRECTLY TO LIFT 9-5/8" CASING JTS TO RIG FLOOR. | RR | HSYS |  | 07/01/2022 | SND-2005 | 3 | MHKK-2
97 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SND-3002 | Hrs | DMMM-601
98 | HFFT | HCM | 40 | 30 Jun 1300 - 0500 | 13963 | 898985 | CMT PILOT & CONFIRMATION TEST FOR 9.5/8" SHOWED DISCREPANCY BETWEEN HALLIBURTON & ARAMCO LAB RESULT. | CMT | NA |  | 07/01/2022 | SND-3002 | 24 | DMMM-601
99 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SND-3003 | Hrs | HRDH-1816
100 | FOT | OJR | 44.25 | 30 Jun 0500 - 0300 | 2251 | 898981 | AFTER CO F.S SUDDENLY LOST 220 PSI AND LOST 70KLB STRING WT, JAR TWISTED OFF | BHA | JARS |  | 07/01/2022 | SND-3003 | 20.75 | HRDH-1816
101 | IHFL | RIG | 1 | 01 Jul 2330 - 0030 | 6285 | 899022 | WEIGHT INDICATOR STOPPED FUNCTIONING DUE TO HYDRAULIC LEAKAGE | RR | HSYS |  | 07/01/2022 | SP-229 | 1 | ABHD-13
102 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SP-229 | Hrs | ABHD-13
103 | FOT | RIG | 2 | 01 Jul 0930 - 1130 | 60 | 899021 | MANUAL AND DP POWER TONGS UNABLE TO GRIP THE BHA FOR MAKING PROPER TORQUE. | TF | TTRQ |  | 07/01/2022 | SP-229 | 2 | ABHD-13
104 | IHFL | RIG | 1 | 01 Jul 2330 - 0030 | 6285 | 899022 | WEIGHT INDICATOR STOPPED FUNCTIONING DUE TO HYDRAULIC LEAKAGE | RR | HSYS |  | 07/01/2022 | SP-229 | 1 | ABHD-13
105 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SSA-5865 | Hrs | ABJF-50
106 | FOT | CRT | 23.5 | 30 Jun 0230 - 0500 | 13490 | 899016 | AFTER CONDUCTING POSITIVE TEST ATTEMPTED TO DISPLACE STRING TO WATER FOR NEGATIVE TEST AND COULD NOT DISPLACE PACKER WOULD SET EACH TIME. | BHA | WBCL |  | 07/01/2022 | SSA-5865 | 21 | ABJF-50
107 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SSA-5914 | Hrs | WDYH-80
108 | FOT | BHI | 39.25 | 30 Jun 1345 - 0500 | 15400 | 899078 | UNABLE TO READ SIGNAL FROM RSS ASSY. TROUBLESHOOT ON THE PULSER (ROTOR) AS PER BAKER DIRECTIONAL. NO SUCCESS. | TF | MS |  | 07/01/2022 | SSA-5914 | 24 | WDYH-80
109 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | SSA-5964 | Hrs | HRDH-1383
110 | HFFT | SJC | 27.75 | 29 Jun 2100 - 0430 | 10206 | 899073 | AFTER 4 1/2" LINER CEMENT JOB, ATTEMPTED TO REVERSE CIRCULATE, PRESSURE INCREASED TO 3000 PSI GRADUALLY, WITH NO RETURNS OBSERVED. THE STRING WAS PICKED AN EXTRA 9 FOOT ABOVE THE INITAL 21 FOOT. AND ATTEMPTED TO REVERSE CIRCULATE WITHOUT SUCCESS. THE DECISION WAS MADE TO POOH ABOVE EXPECTED TOC. | CMT | NA |  | 07/01/2022 | SSA-5964 | 23.5 | HRDH-1383
111 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/01/2022 | T218 | Hrs | UTMN-1281
112 | UDWL | WDS | 23.5 | 30 Jun 1730 - 0500 | 9692 | 899061 | WDS DD UNABLE TO FOLLOW GOC PLAN. | DD | RSS |  | 07/01/2022 | T218 | 12 | UTMN-1281
113 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADC-14 | Hrs | HRDH-612
114 | FOT | RIG | 51.5 | 30 Jun 0500 - 0930 | 11265 | 899058 | UNABLE TO LATCH BAKER WIRE LINE WET CONNECTOR TO LOGGING TOOLS DUE TO SCALE FROM DP COATING ACCUMULATED INSIDE LATCH ASSY. | DSF | DP |  | 07/02/2022 | ADC-14 | 4.5 | HRDH-612
115 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADC-16 | Hrs | JAHM-6
116 | FOT | BAW | 33.5 | 01 Jul 0630 - 0500 | 11505 | 898988 | BAKER STRADDLE PACKER UNABLE TO SEAL. | TF | WLT |  | 07/02/2022 | ADC-16 | 16 | JAHM-6
117 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADC-23 | Hrs | KIDN-23
118 | FOT | SWL | 2 | 02 Jul 0300 - 0500 | 0 | 899025 | ONE ARM CALIPER IS NOT RESPONDING PROPERLY | TF | WLT |  | 07/02/2022 | ADC-23 | 2 | KIDN-23
119 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADC-31 | Hrs | SDGM-1181
120 | UDWL | SPS | 24 | 01 Jul 0000 - 0000 | 15410 | 899023 | SPERRY RSS FAILURE. RSS UNABLE TO KEEP ANGLE. | DD | RSS |  | 07/02/2022 | ADC-31 | 19 | SDGM-1181
121 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADC-35 | Hrs | MAQL-5
122 | FOT | BLH | 38.5 | 30 Jun 1415 - 1130 | 11925 | 899082 | HOLE PACKED OFF ,TRY TO RE-GAIN CIRCULATION, WITHOUT SUCCESS, POOH 2 STD, HOLE FREE UP, AND RESTRICTED GOING DOWN, REGAIN CIRCULATION, TRY TO GO DOWN STILL HAD OBSTRUCTION. DECISION WAS MADE TO POOH, OBSERVED SWABBING, DECEIDED TO PUMP OUT. - 0 STAIC LOSSES. - 80 BBL/ MIN DYNAMIC LOSSES AT 2.6 BPM. POOH WITH LINER & FOUND; - THE SETTING PIN OF THE LINER SLIPS IS SHEARED & SLIPS PREMATURE SET. - HAD GAP 3/4'' IN THE PISTON CONE ( THE STANDARD SHOULD BE 0 '' GAP.) | TF | HGRL |  | 07/02/2022 | ADC-35 | 6.5 | MAQL-5
123 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADC-36 | Hrs | SDGM-1236
124 | FOT | RIG | 4 | 02 Jul 0800 - 1200 | 10780 | 899024 | HAD FAILURE IN WICHITA BRAKE SYSTEM, CHANGE WICHITA RUBBER AIR BLADDER, FUNCTION TEST SAME, OK. | RR | DWKS |  | 07/02/2022 | ADC-36 | 4 | SDGM-1236
125 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADC-62L | Hrs | ANDR-745
126 | HERR | RIG | 340 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/02/2022 | ADC-62L | 24 | ANDR-745
127 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADM-261 | Hrs | LWHH-9
128 | FOT | SAM | 13.5 | 02 Jul 1530 - 0500 | 7173 | 899112 | NOV 6-1/8" X 7" ANDEREAMER FAILED TO ACTIVATE CUTTER BLOCK. DEBRIS WAS FOUND IN SAMAA MAC'S BALL CATCHER SLEEVE. PREVENTED ACTIVATION BALL TO PASS FREELY & ACTIVATE ANDEREAMER CUTTER BLOCK. | BHA | MACS |  | 07/02/2022 | ADM-261 | 13.5 | LWHH-9
129 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADM-337 | Hrs | MRJN-900
130 | FOT | BCT | 1 | 02 Jul 0400 - 0500 | 2434 | 899098 | CT UNIT LOST POWER @ 2434 FT, GENERATOR FAILED | TF | CTBG |  | 07/02/2022 | ADM-337 | 1 | MRJN-900
131 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | ADM-655 | Hrs | SFNY-1355
132 | WPD3 | AP2 | 24 | 02 Jul 0500 - 0500 | 0 | 899096 | WAIT ON SFNY CENTRAL FIELD SERVICE TO DE-PRESSURIZE SFNY-34, 562/566, 1354/1355 PF FOR SAFE RIG APPROACH. | WO | NA |  | 07/02/2022 | ADM-655 | 24 | SFNY-1355
133 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | AOD-1 | Hrs | ZULF-694
134 | FOT | RIG | .75 | 02 Jul 1945 - 2030 | 7280 | 899069 | IRON ROUGHNECK PIPE SPINNER FAILURE. | RR | HSYS |  | 07/02/2022 | AOD-1 | .75 | ZULF-694
135 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | DPS-5 | Hrs | HRDH-2319
136 | FOT | FMC | 1.75 | 02 Jul 0045 - 0230 | 13860 | 899114 | FAILURE ON BOTH FRANKS POWER TONG, MAIN AND BACKUP. | TF | CTRQ |  | 07/02/2022 | DPS-5 | 1.75 | HRDH-2319
137 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | DQ-47 | Hrs | KHRS-497
138 | HERR | ARM | 117 | 28 Jun 0800 - 0500 | 3570 | 898952 | GOC UNABLE TO REACH TARGET ENTRY OF ARB-1 DUE TO SHALLOWER TOP FORMATION W/42'. | JF | NA |  | 07/02/2022 | DQ-47 | 24 | KHRS-497
139 | 11490 | 8100 | SET | N | 3534 | RBP | - SPACE OUT & SET 5 1/2" ME INTERWELL PLUG @ 8,100 FT (TOP OF PLUG)- DROP 1/2" INCH SETTING BALL AND PUMP IT DOWN TO THE BALL SEAT, ONCE THE BALL LANDED, BUILD UP PRESSURE IN DRILL PIPE T/ 3,600 PSI.- P/U STRING 10 FT CONFIRMED RELEASING RUNNINGTOOL THEN CONFIRMED BP SETTING BY 6 KLBS S/O,OK. | 11490 | 8100 | INW | 07/02/2022 | DQ-57L | PA | KHRS-399
140 | 11490 |  | OTH | N | 3534 | NA | - FILLING ANNULUS W/ 75 PCF VISCOUS BRINE FROM KILL LINE W/ 6 BPM# NO RETURNS.- KEEP TRIP TANK RUNNING WITH 75 PCF VISCOUS BRINE AT 60-70 BPH- FLOW CHECK: WELL IN COMPLETE LOSSES. | 11490 |  | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
141 | 11490 | 3813 | TO | N | 3534 | SPHDP | - POOH WITH 5 1/2" ME INTERWELL PLUG RUNNING TOOL ON 5" DP/HWDP T/ 3,813'.- KEEP TRIP TANK RUNNING WITH 75 PCF VISCOUS BRINE AT 60-70 BPH. | 11490 | 8100 | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
142 | 11490 |  | OTH | N |  | NA | - SLIP 30FT OF DRILLING LINE. | 11490 |  | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
143 | 11490 |  | HT | N | 3534 | BHA | - R/D 5" DP'S HANDLING TOOLS , R/U 2 7/8" DP HANDLING TOOLS | 11490 |  | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
144 | 11490 |  | OTH | N | 3534 | NA | - CONTINUE POOH WITH 5.5" INTERWELL ME PLUG RUNNING TOOL ON 5" DP/HWDP TO SURFACE.- CHECKED RUNNING TOOL @ SURFACE # OK. | 11490 |  | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
145 | 11490 | 5815 | TI | N |  | SPHDP | -HPJSM. P/U, M/U WFD 9 5/8" RBP - TRIP TANK RUNNING ALL TIME FILLING BACK SIDE WITH 75 PCF VISCOUS BRINE AT 60 BPH.-RIH W/ WFD 9 5/8" RBP ON 5" HWDP/ DP TO SETTING DEPTH AT 5,815'.- TRIP TANK RUNNING ALL TIME& FILLING BACK SIDE WITH 75 PCF VISCOUS BRINE AT 60 BPH. | 11490 | 0 | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
146 | 11490 |  | CIRC | N |  | MPMP | - BULLHEAD ANNULUS W/ 50 BBL. OF HI-VIS BRINE, FOLLOWED BY 430 BBL 75PCF VISCOUS BRINE AT 6 BPM/ 850 PSI. | 11490 |  | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
147 | 11490 | 5815 | SET | N |  | RBP | - SET 9 5/8" WFD RBP @ 5,815' AS FOLLOWS:- ROTATE STRING 3 RIGHT TURNS AND SOW ON PLUG 35 KLBS THEN CONFIRMED SETTING WITH 35 KLBS O/P. | 11490 | 5815 | WBP | 07/02/2022 | DQ-57L | PA | KHRS-399
148 | 11490 |  | PTST | N |  | BP | - FILLED HOLE WITH 34 BBLS, CLOSE BOP'S & P/T CSG T/ 1100 PSI , OK, CONFIRMED CSG INTEGRITY.- UNSET 9 5/8" WFD RBP BY S/O 6 KLBS AND ROTATE 2 TURNS TO RIGHT, P/U 5 FT AND WAIT FOR 15 MIN FOR ELEMENTS TO RETRACT.- TRIP TANK RUNNING ALL TIME FILLING BACK SIDE WITH 75 PCF VISCOUS BRINE AT 60 BPH. | 11490 |  | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
149 | 11490 | 5089 | TO | N |  | SPHDP | - RELEASE 9 5/8 WFD RBP - POOH W/ 9 5/8" WFD RBP T/ 5,089.-SET 9 5/8" WFD RBP @ 5,086' AS FOLLOWS: ROTATE STRING 3 RIGHT TURNS AND S/O ON PLUG 38 KLBS ,CONFIRMED SETTING WITH 38 KLBS O/P. | 11490 | 5815 | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
150 | 11490 |  | PTST | N |  | BP | -FILLED HOLE WITH 34 BBLS- P/T CSG T/ 1100 PSI, OK, CONFIRMED CSG INTEGRITY.-OBSERVED 9 5/8 X 13 3/8 CCA WHILE P/T , NO PRESSURE BUILDUP.- POOH W/ WFD 9 5/8" RBP RUNNING TOOL T/4810.- P/U & M/U 9 5/8 HES RTTS + 6 1/8 STORM VALVE ONGOING | 11490 |  | RIG | 07/02/2022 | DQ-57L | PA | KHRS-399
151 | 33 | OOS | Category | DOOS ID | RPBP | Out of Scope Summary | RIH W/ 5 1/2 ME INTERWELL PLUG , SET @ 8100 FT | 9 | 3534 | 01 Jul 0300 | 07/02/2022 | DQ-57L | Type | KHRS-399
152
153
154 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | EXL-IVA | Hrs | SFNY-1650
155 | FPMP | RIG | .75 | 02 Jul 2230 - 2315 | 2825 | 899113 | ARO LOST TIME: CIRCULATE AT REDUCED RATE WHILE REPAIR #1 AND #2 MUD PUMPS, CHANGE OUT PISTON #3 ON MUD PUMP #1, TROUBLE SHOOT #2 MUD PUMP RHEOSTAT. | RR | MPMP |  | 07/02/2022 | EXL-IVA | .75 | SFNY-1650
156 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | MP-4 | Hrs | LWHH-45
157 | SRVC | SCT | 12 | 02 Jul 1000 - 2200 | 0 | 899115 | WAIT ON DELIVERING CTU TOOLS & EQUIPMENT TO TANAJIB | WO | NA |  | 07/02/2022 | MP-4 | 12 | LWHH-45
158 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | NA-207S | Hrs | SHYB-132
159 | STBH | ARM | 101 | 28 Jun 0000 - 0500 | 4749 | 898940 | STRING STUCK WHILE MILLING OUT 7" LINER | STUK | MILL |  | 07/02/2022 | NA-207S | 24 | SHYB-132
160 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | NBR-115S | Hrs | HWYH-1220
161 | SCSG | ARM | 6.5 | 01 Jul 0030 - 0700 | 19850 | 899065 | DURING WASH IN THE HOLE WITH SLB MSF COMPLETION STRING STUCK ON CONNECTION. | STUK | LINR |  | 07/02/2022 | NBR-115S | 2 | HWYH-1220
162 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | NBR-263S | Hrs | QTIF-736
163 | UVLC | ARM | 230 | 22 Jun 0630 - 0500 | 8541 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/02/2022 | NBR-263S | 24 | QTIF-736
164 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | NBR-654S | Hrs | HRDH-1150
165 | FOT | RIG | 20.25 | 01 Jul 0730 - 0530 | 5136 | 899087 | A MAIN BREAKER FAILURE FOR THE TOP DRIVE VFD. | RR | PSYS |  | 07/02/2022 | NBR-654S | .5 | HRDH-1150
166 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | PA-70S | Hrs | MDRK-64
167 | FOT | WLH | 761.75 | 30 May 1800 - 0500 | 15492 | 897183 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP. | TF | LLAP |  | 07/02/2022 | PA-70S | 24 | MDRK-64
168 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | PN-9 | Hrs | MRJN-677
169 | FOT | RIG | 1 | 02 Jul 0230 - 0330 | 3658 | 899116 | OBSERVED HYDRAULIC LEAK IN 5" BX ELEVATOR. CHANGE OUT 5" ELEVATOR. | RR | HSYS |  | 07/02/2022 | PN-9 | 1 | MRJN-677
170 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | RM-74A | Hrs | HSBH-68
171 | GRF | RIG | 54.25 | 30 Jun 2245 - 0500 | 1905 | 898983 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT | UPRA | RWCS |  | 07/02/2022 | RM-74A | 24 | HSBH-68
172 | 9129 |  | CIRC | N |  | MPMP | DISPLACE HOLE TO 73 PCF CACL2 VISCOUS BRINE. | 9129 |  | RIG | 07/02/2022 | SINO-46L | PA | SHYB-708
173 | 9129 |  | OTH | N |  | NA | EXTENDED 01 HR FLOW CHECK, WELL STATIC. | 9129 |  | RIG | 07/02/2022 | SINO-46L | PA | SHYB-708
174 | 9129 | 7490 | TO | N | 3492 | STDP | POOH BHI P&A KIT SETTING ASSY ON 4" DP FREELY ON ELEVATOR FROM 8,844 FT TO TOW @ 7,490 FT.- CIRC BTM/UP 100' BELOW BOW.- FLOW CHECK WELL STATIC. | 9129 | 8844 | RIG | 07/02/2022 | SINO-46L | PA | SHYB-708
175 | 9129 | 0 | TO | N | 3492 | STDP | CONT. POOH BHI P&A KIT SETTING ASSY ON 4" DP IN CASED HOLE TO TOP BHA.- FLOW CHECK @ TOL & TOP OF BHA : WELL STATIC | 9129 | 7490 | RIG | 07/02/2022 | SINO-46L | PA | SHYB-708
176 | 9129 |  | HT | N | 3492 | BHA | L/D BHI P&A KIT SETTING ASSY. | 9129 |  | RIG | 07/02/2022 | SINO-46L | PA | SHYB-708
177 | 9129 | 0 | RTRV | N |  | WPSTK | P/U & M/U COMBINED L-1 WSTK RETRIEVING HOOK AND 7" WBCO ASSY & MWD, ALIGN MWD WITH HOOK.- BHA. HOOK, X/O, 1 JT 4" DP, X.O,FLOAT SUB,MWD, FILTER SUB, X/O, 4 EAX 7"MAGNETS.- SHALLOW TEST OK. | 9129 | 0 | WI3 | 07/02/2022 | SINO-46L | FISH | SHYB-708
178 | 9129 | 7490 | TI | N |  | STDP | RIH COMBINED L-1 WSTK RETRIEVING HOOK AND 7" MAGNETS ASSY TO TOW @ 7,490 FT.- MONITOR WELL ON TRIP TANK & TRIP SHEET.- FILL THE STRING EACH 20 STDS. | 9129 | 0 | RIG | 07/02/2022 | SINO-46L | FISH | SHYB-708
179 | 9129 | 7500 | RTRV | N |  | WPSTK | ORIENT THE HOOK TO 135 DEG. & WASHED WHIPSTOCK SLOT SEVERAL TIMES.- ORIENT THE HOOK TO 315 DEG, ENGAGE L1 WHIPSTOCK & RELEASE SAME WITH 50 KLB OVERPULL.- FILL UP WELL WITH 5 BBLS BRINE.- WAIT FOR RUBBER ELEMENT TO RETRACT, MEANWHILE OBSERVED WELL THROUGH TRIP TANK. HAD 6 BPH STATIC LOSSES. | 9129 | 7490 | WWD | 07/02/2022 | SINO-46L | FISH | SHYB-708
180 | 9129 | 4945 | TO | N |  | STDP | HPJSM, POOH WITH L-1 WFRD WPSTK AT CONTROLLED SPEED FROM 7490 FT TO 4,945 FT (PAC VALVE).- HAD OVERPULL @ 4,945 FT (PAC VALVE) DISCUSSED WITH WEATHERFORD ENG RELEASE THE TOOL WITH 50 KLBS OVERPULL.- FLOW CHECK 2 BPH STATIC LOSSES.- POOH PUMP OUT FIRST 10 STDS. | 9129 | 7490 | RIG | 07/02/2022 | SINO-46L | FISH | SHYB-708
181 | 9129 |  | CIRC | N |  | MPMP | CIRCULATE ONE CYCLE. FR: 200 GPM, PR: 970 PSI. | 9129 |  | RIG | 07/02/2022 | SINO-46L | FISH | SHYB-708
182 | 9129 | 4270 | TO | N |  | STDP | POOH PUMP OUT FROM 4,945 FT TO 4,270 FT.SUSPECTED 6 BBL SWAP. | 9129 | 4945 | RIG | 07/02/2022 | SINO-46L | FISH | SHYB-708
183 | 9129 |  | CIRC | N |  | MPMP | EXTENDED FLOW CHECK, WELL STATIC. - CHC. NO CUT IN MUD IN= OUT= 73 PCF- MEANWHILE DISCUSSED WITH ARAMCO TEAM DECISION WAS MADE TO BULLHEAD THE WELL. | 9129 |  | RIG | 07/02/2022 | SINO-46L | FISH | SHYB-708
184 | 16.75 | OOS | Category | DOOS ID | PAKT | Out of Scope Summary | RUN AND SET P&A KIT | 6.75 | 3492 | 01 Jul 0045 | 07/02/2022 | SINO-46L | Type | SHYB-708
185
186
187 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SINO-47 | Hrs | HRDH-1351
188 | FOT | SPS | 26 | 30 Jun 1815 - 1845 | 11467 | 899084 | NOT ABLE TO GET MWD SURVEY | SURV | MS |  | 07/02/2022 | SINO-47 | 11.5 | HRDH-1351
189 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SND-2005 | Hrs | MHKK-2
190 | FOT | WCR | 29.75 | 01 Jul 2300 - 0445 | 3782 | 899064 | WFD HYDRUALIC FLUSH MOUNT SLIPS NOT FUNCTIONING CORRECTLY, TROUBLESHOOT SAME WITH NO SUCCESS. | TF | CTRQ |  | 07/02/2022 | SND-2005 | 23.75 | MHKK-2
191 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SND-3002 | Hrs | DMMM-601
192 | HFFT | HCM | 52 | 30 Jun 1300 - 1700 | 13963 | 898985 | CMT PILOT & CONFIRMATION TEST FOR 9.5/8" SHOWED DISCREPANCY BETWEEN HALLIBURTON & ARAMCO LAB RESULT. | CMT | NA |  | 07/02/2022 | SND-3002 | 12 | DMMM-601
193 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SP-103 | Hrs | KRSN-72
194 | FOT | SLL | 2 | 02 Jul 1500 - 1700 | 0 | 899119 | SLB PLUG FALIURE | TF | PLUGT |  | 07/02/2022 | SP-103 | 2 | KRSN-72
195 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SP-257 | Hrs | HZEM-141012
196 | FOT | BHI | 3.5 | 02 Jul 0000 - 0500 | 7842 | 899097 | BAKER UNABLE TO GET SURVEY | BHA | MWD |  | 07/02/2022 | SP-257 | 3.5 | HZEM-141012
197 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SSA-5865 | Hrs | ABJF-50
198 | FOT | CRW | 25.5 | 30 Jun 0230 - 0700 | 13490 | 899016 | AFTER CONDUCTING POSITIVE TEST ATTEMPTED TO DISPLACE STRING TO WATER FOR NEGATIVE TEST AND COULD NOT DISPLACE PACKER WOULD SET EACH TIME. | BHA | WBCL |  | 07/02/2022 | SSA-5865 | 2 | ABJF-50
199 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SSA-5892 | Hrs | SMNH-521700
200 | FOT | ITS | 5.25 | 02 Jul 2045 - 0200 | 19059 | 899066 | WHILE CLOSING THE FLUSH MOUNTED SLIPS THE INTERNAL PISTON ON ONE OF THE CLOSING SLIP SEGMENTS GAVE WAY AND FAILED | TF | CTRQ |  | 07/02/2022 | SSA-5892 | 5.25 | SMNH-521700
201 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SSA-5914 | Hrs | WDYH-80
202 | FOT | BHI | 49.75 | 30 Jun 1345 - 1530 | 15400 | 899078 | UNABLE TO READ SIGNAL FROM RSS ASSY. TROUBLESHOOT ON THE PULSER (ROTOR) AS PER BAKER DIRECTIONAL. NO SUCCESS. | TF | MS |  | 07/02/2022 | SSA-5914 | 10.5 | WDYH-80
203 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | SSA-5964 | Hrs | HRDH-1383
204 | HFFT | SJC | 44.75 | 29 Jun 2100 - 2200 | 10206 | 899073 | AFTER 4 1/2" LINER CEMENT JOB, ATTEMPTED TO REVERSE CIRCULATE, PRESSURE INCREASED TO 3000 PSI GRADUALLY, WITH NO RETURNS OBSERVED. THE STRING WAS PICKED AN EXTRA 9 FOOT ABOVE THE INITAL 21 FOOT. AND ATTEMPTED TO REVERSE CIRCULATE WITHOUT SUCCESS. THE DECISION WAS MADE TO POOH ABOVE EXPECTED TOC. | CMT | NA |  | 07/02/2022 | SSA-5964 | 17 | HRDH-1383
205 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | STY-038 | Hrs | ZULF-2086
206 | FOT | SPS | 2.5 | 02 Jul 0230 - 0500 | 8883 | 899120 | TROUBLE SHOOT LWD COMMUNICATION ISSUE. | BHA | LWD |  | 07/02/2022 | STY-038 | 2.5 | ZULF-2086
207 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/02/2022 | T218 | Hrs | UTMN-1281
208 | UDWL | WDS | 38.25 | 30 Jun 1730 - 1945 | 9692 | 899061 | WDS DD UNABLE TO FOLLOW GOC PLAN. | DD | RSS |  | 07/02/2022 | T218 | 14.75 | UTMN-1281
209 | HINW | BAW | 3 | 03 Jul 0200 - 0500 | 11346 | 899135 | AFTER FINISH PT 5 @ 11,346FT. UNSET STRADDLE PACKER. ATTEMPT TO GO UP WITH 20KLBS OVERPULL. NO SUCCESS, ATTEMPT TO GO DOWN WITH 20KLBS SLACK OFF NO SUCCESS. | STUK | WLT |  | 07/03/2022 | ADC-16 | 3 | JAHM-6
210 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADC-16 | Hrs | JAHM-6
211 | FOT | BAW | 36.5 | 01 Jul 0630 - 0800 | 11505 | 898988 | BAKER STRADDLE PACKER UNABLE TO SEAL. | TF | WLT |  | 07/03/2022 | ADC-16 | 3 | JAHM-6
212 | HINW | BAW | 3 | 03 Jul 0200 - 0500 | 11346 | 899135 | AFTER FINISH PT 5 @ 11,346FT. UNSET STRADDLE PACKER. ATTEMPT TO GO UP WITH 20KLBS OVERPULL. NO SUCCESS, ATTEMPT TO GO DOWN WITH 20KLBS SLACK OFF NO SUCCESS. | STUK | WLT |  | 07/03/2022 | ADC-16 | 3 | JAHM-6
213 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADC-23 | Hrs | KIDN-23
214 | FOT | SWL | 3 | 02 Jul 0300 - 0600 | 0 | 899025 | ONE ARM CALIPER IS NOT RESPONDING PROPERLY | TF | WLT |  | 07/03/2022 | ADC-23 | 1 | KIDN-23
215 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADC-42L | Hrs | SDGM-1258
216 | FOT | TK3 | 12.75 | 03 Jul 0830 - 2115 | 4392 | 899134 | CASING BACKED OUT AT 46' BELOW 18-5/8" CASING HANGER DURING PUMPING TAIL SLURRY 118 PCF OF 2ND STAGE CMT. | TF | CSG |  | 07/03/2022 | ADC-42L | 12.75 | SDGM-1258
217 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADC-50 | Hrs | SFNY-1176
218 | UVLC | ARM | 170.5 | 26 Jun 1845 - 2200 | 2864 | 898935 | HAD SEVERE LOSSES WHILE DRLG 12-1/4" HOLE @ 2,864', OPEN PBL SUB AND SPOT 2EA LCM PILLS WITH NO SUCCESS. | LCIR | NA |  | 07/03/2022 | ADC-50 | 17 | SFNY-1176
219 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADC-56L | Hrs | UTMN-3069
220 | ABFM | TK3 | 1 | 03 Jul 1445 - 1545 | 225 | 899132 | TDS HMI TORQUE CONTROL SCREEN STOPPED RESPONDING, TROUBLESHOOT SAME. | TF | AVDS |  | 07/03/2022 | ADC-56L | 1 | UTMN-3069
221 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADC-62L | Hrs | ANDR-745
222 | HERR | RIG | 364 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/03/2022 | ADC-62L | 24 | ANDR-745
223 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADM-261 | Hrs | LWHH-9
224 | FOT | SAM | 19 | 02 Jul 1530 - 1030 | 7173 | 899112 | NOV 6-1/8" X 7" ANDEREAMER FAILED TO ACTIVATE CUTTER BLOCK. DEBRIS WAS FOUND IN SAMAA MAC'S BALL CATCHER SLEEVE. PREVENTED ACTIVATION BALL TO PASS FREELY & ACTIVATE ANDEREAMER CUTTER BLOCK. | BHA | MACS |  | 07/03/2022 | ADM-261 | 5.5 | LWHH-9
225 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADM-337 | Hrs | MRJN-900
226 | FOT | BCT | 6 | 02 Jul 0400 - 1000 | 2434 | 899098 | CT UNIT LOST POWER @ 2434 FT, GENERATOR FAILED | TF | CTBG |  | 07/03/2022 | ADM-337 | 5 | MRJN-900
227 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ADM-655 | Hrs | SFNY-1355
228 | WPD3 | AP2 | 48 | 02 Jul 0500 - 0500 | 0 | 899096 | WAIT ON SFNY CENTRAL FIELD SERVICE TO DE-PRESSURIZE SFNY-34, 562/566, 1354/1355 PF FOR SAFE RIG APPROACH. | WO | NA |  | 07/03/2022 | ADM-655 | 24 | SFNY-1355
229 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | AOD-1 | Hrs | ZULF-694
230 | FOT | RIG | .75 | 03 Jul 0315 - 0400 | 194 | 899156 | UNABLE TO RELEASE PIPE SPINNER FROM STAND. | RR | KELLY |  | 07/03/2022 | AOD-1 | .75 | ZULF-694
231 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | DQ-47 | Hrs | KHRS-497
232 | HERR | ARM | 141 | 28 Jun 0800 - 0500 | 3570 | 898952 | GOC UNABLE TO REACH TARGET ENTRY OF ARB-1 DUE TO SHALLOWER TOP FORMATION W/42'. | JF | NA |  | 07/03/2022 | DQ-47 | 24 | KHRS-497
233 | 11490 | 210 | SET | N |  | RTTS | - P/U & M/U 9-5/8" HES RTTS + 6-1/8" STORM VALVE AND RIH & SET@ 210 FT & CONFIRM SETTING OK.- P/T BACKSIDE TO 1000 PSI WHILE KEEP TBG SIDE OPEN FOR 10MIN, OK.- RELEASED SETTING TOOL, POOH AND RACKBACK THREE STAND.- P/T CSG TO 1,000 PSI FOR 10MIN, PRESSUREHOLD, OK. | 11490 | 0 | HCO | 07/03/2022 | DQ-57L | PA | KHRS-399
234 | 11490 |  | PTST | E |  | MPMP | -HPJSM, DIG OUT CELLAR TO 6' BELOW LANDING BASE FLANGE .- P/T 9-5/8" CSG SEALS & SLIPS TO 1,000 PSI -PRESSURE NOT HOLD.- P/T 13-3/8" X 9-5/8" CCA TO 500 PSI,PRESSURE HOLD AT 150 PSI FOR 30 MIN . | 11490 |  | RIG | 07/03/2022 | DQ-57L | CT | KHRS-399
235 | 11490 |  | WCNT | E |  | NA | - HPJSM, AL-MANSOORI PERFORMED UT INSPECTION FOR 24" & 18-5/8" SURFACE CSG & LANDING BASE:- INSPECTED 24" & 18-5/8" SURFACE CSG WALL THICKNESS IN ACCEPTABLE CONDITION.- PERFORMED MPI ON WELDING BETWEEN 18-5/8"CASING & 13-5/8" 3M LANDING BASE DONUT PLATE - LANDING BASE IN GOOD CONDITION. | 11490 |  | HCT | 07/03/2022 | DQ-57L | WH | KHRS-399
236 | 11490 |  | WCNT | E | 3565 | HTAP | - HOT HEAD WELD 1 EA NIPPLE IN 18-5/8"CSG. AL-MANSOORI INSPECTED WELDING AREA.- BOOTS & COOTS PERFORM HOT TAPPING ON 18-5/8" CSG, INSTALL 1" VALVES ON NIPPLE & P/T SAME TO 1,000 PSI# OK, DRILLED 1/2" HOLE IN 18-5/8" CSG THRU THE VALVE, MONITOR 13 3/8'' X 18-5/8" CCA NO PRESSURE & NO GAS READINGS.- PERFORM UT INSPECTION FOR 13 3/8" CSG, OK. FILLED 13 3/8" X 13 5/8" ANNULUS WITH CMT & REWELD WINDOWS, INSPECT, OK. ALMANSOORI PERFORM UT INSPECTION FOR BOTH LANDING BASE AND SURFACE CASING BELOW IT, FOUND SURFACECASING & LANDING BASE IN GOOD CONDITION, | 11490 |  | HCT | 07/03/2022 | DQ-57L | WH | KHRS-399
237 | 11490 |  | WCNT | E |  | NA | - HPJSM, N/D BELL NIPPLE ,HANG UP 13 5/8" BOP STACK.- N/D 13 5/8" X 11"- 3M WG THS.- CHECK CAVITY AREA AND 9 5/8" CASING STUB {FOUND STUB 5"} IN GOOD CONDITION | 11490 |  | HCT | 07/03/2022 | DQ-57L | WH | KHRS-399
238 | 11490 |  | WCNT | E |  | NA | - HOT HEAD WELD & RE-STUB 9 5/8" CSG,- AL MANSOORI PERFORMED MPI ON WELDING,OK.- N/U NEW GE 13-5/8" X 13-5/8" X 9-5/8", 3M DSDPOF, P/T DSDPOF T/ 1,000 PSI,OK.- N/U 13 5/8" X 11"- 3M NEW FMC THS WITH 2X 2 1/16" CIW GATE VALVES.- PRESSURE TEST THS BETWEEN TWO SEALS TO 1000 PSI, OK | 11490 |  | HCT | 07/03/2022 | DQ-57L | WH | KHRS-399
239 | 11490 |  | BOPT | N |  | RAMS | - CHANGED TOP PIPE RAM TO 3 1/2"-57/8" VBR.- N/U 13 5/8"- 5M BOP STACK WITH 11" 3K X 135/8" 5K DSA, N/U BELL NIPPLE AND FLOW LINE- M/U & RIH WITH 2 STD'S 5" HWDP + 9 5/8"CUP TESTER SET SAME BELOW WH.- FUNCTION TEST BOP, OK.- P/T VBR WITH 5" DP AGAINST BOP CONNECTION / THS / 2 X 2 1/16" CIW GATE VALVES TO 300/2500PSI FOR 10MIN, OK- POOH AND L/D CUP TESTER. | 11490 |  | RIG | 07/03/2022 | DQ-57L | BOP | KHRS-399
240 | 11490 | 0 | TO | N |  | SPDP | - RIH W/5" DP & RETRIEVE RTTS PACKER - POOH AND L/D SAME, FLOW CHECK, WELL STATIC.- POOH AND RACK BACK ALL 5" DP STANDS. | 11490 | 210 | RIG | 07/03/2022 | DQ-57L | PA | KHRS-399
241 | 11490 |  | OTH | N |  | NA | - RIH 3 STD'S, WASH DOWN ABOVE TOP OF RBP PLUG, STOP PUMP.- ENGAGED OVERSHOT INTO 9 5/8" WFD RBP S/O 10 KLBS AND ROTATE 3 RH TURNS, OK.- UNSET 9 5/8" WFD RBP WITH 15 KLB O/P,- P/U 10 FEET AND WAIT 10 MIN FOR ELEMENTS RETRACTION.- KEPT TRIP TANK RUNNING ALL TIME FILLING BACK SIDE WITH 75 PCF VISCOUS BRINE AT 60 BPH. | 11490 |  | RIG | 07/03/2022 | DQ-57L | PA | KHRS-399
242 | 11490 |  | CIRC | N |  | MPMP | - BULLHEAD ANNULUS W/ 50 BBL. OF HI-VIS BRINE, FOLLOWED BY 430 BBL 75PCF VISCOUS BRINE @ 7BPM/ 740 PSI. | 11490 |  | RIG | 07/03/2022 | DQ-57L | CT | KHRS-399
243 | 11490 | 3000 | TO | N |  | SPHDP | POOH W/ 9 5/8" WFD RBP F/5089' T/3000 FT- TRIP TANK RUNNING ALL TIME FILLING BACK SIDE WITH 75 PCF VISCOUS BRINE AT 60 BPH. | 11490 | 5089 | RIG | 07/03/2022 | DQ-57L | PA | KHRS-399
244 | 2 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | HOT HEAD WELD 1 EA NIPPLE IN 18-5/8" CSG. | 2 | 3565 | 03 Jul 1200 | 07/03/2022 | DQ-57L | Type | KHRS-399
245
246
247 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | ENS-108 | Hrs | ZULF-2014
248 | FOT | SDM | 1.5 | 03 Jul 1900 - 2030 | 6399 | 899157 | OBSERVED THREAD DAMAGED BETWEEN SLB ARC TOOL & TELESCOPE WHILE L/D. M/U NEW SAVER SUB, TORQUED SAME. L/D SLB TOOLS SAFELY. RESUME OPERATIONS. | BHA | LWD |  | 07/03/2022 | ENS-108 | 1.5 | ZULF-2014
249 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | HI-4 | Hrs | SFNY-918
250 | WOPF | AP2 | 17 | 03 Jul 1200 - 0500 | 10698 | 899153 | WAIT ON PERMISSION FROM FIELD SERVICES TO FLOW WELL THROUGH PRODUCTION LINE. | WO | NA |  | 07/03/2022 | HI-4 | 17 | SFNY-918
251 | FOT | SWL | 5 | 03 Jul 0500 - 1000 | 4673 | 899027 | FAILURE OF SCHLUMBERGER W/L COLLIDING TOOL / EXPLOSIVE ASSY (MISS FIRE DUE TO SHORT CIRCIUT). | TF | WLT |  | 07/03/2022 | NA-207S | 5 | SHYB-132
252 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | NA-207S | Hrs | SHYB-132
253 | STBH | ARM | 113 | 28 Jun 0000 - 2200 | 4749 | 898940 | STRING STUCK WHILE MILLING OUT 7" LINER | STUK | MILL |  | 07/03/2022 | NA-207S | 12 | SHYB-132
254 | FOT | SWL | 5 | 03 Jul 0500 - 1000 | 4673 | 899027 | FAILURE OF SCHLUMBERGER W/L COLLIDING TOOL / EXPLOSIVE ASSY (MISS FIRE DUE TO SHORT CIRCIUT). | TF | WLT |  | 07/03/2022 | NA-207S | 5 | SHYB-132
255 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | NA-393S | Hrs | UTMN-2290
256 | FOT | BAW | 15 | 03 Jul 1400 - 0500 | 12837 | 899130 | AFTER LATCHING WIRELINE TO LOGGING TOOLS DOWN HOLE, RESISTIVITY TOOL FAILED TO GIVE SIGNAL. | TF | WLT |  | 07/03/2022 | NA-393S | 15 | UTMN-2290
257 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | NBR-115S | Hrs | HWYH-1220
258 | SCSG | ARM | 15 | 01 Jul 0030 - 0500 | 19850 | 899065 | DURING WASH IN THE HOLE WITH SLB MSF COMPLETION STRING STUCK ON CONNECTION. | STUK | LINR |  | 07/03/2022 | NBR-115S | 8.5 | HWYH-1220
259 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | NBR-263S | Hrs | QTIF-736
260 | UVLC | ARM | 254 | 22 Jun 0630 - 0500 | 8541 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/03/2022 | NBR-263S | 24 | QTIF-736
261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | NBR-575S | Hrs | HRDH-2217
262 | FOT | GOC | 1.5 | 03 Jul 1730 - 1900 | 8550 | 899154 | TROUBLE SHOOT CRT & JAM UNIT. | TF | CTRQ |  | 07/03/2022 | NBR-575S | 1.5 | HRDH-2217
263 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | PA-529S | Hrs | SHYB-108
264 | FOT | INW | 4.75 | 03 Jul 0745 - 1230 | 1010 | 899100 | RUN IN HOLE WITH 4 1/2" INTERWELL PLUG SET AT 1,000', UN-SUCCESS AND DROP DOWN TO 4,428 FT. | TF | PLUGN |  | 07/03/2022 | PA-529S | 4.75 | SHYB-108
265 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | PA-70S | Hrs | MDRK-64
266 | FOT | WLH | 785.75 | 30 May 1800 - 0500 | 15492 | 897183 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP. | TF | LLAP |  | 07/03/2022 | PA-70S | 24 | MDRK-64
267 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | RM-74A | Hrs | HSBH-68
268 | GRF | RIG | 78.25 | 30 Jun 2245 - 0500 | 1905 | 898983 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT | UPRA | RWCS |  | 07/03/2022 | RM-74A | 24 | HSBH-68
269 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | SCTD-1 | Hrs | SDGM-1152
270 | FOT | RIG | 6.5 | 03 Jul 1900 - 0130 | 0 | 899155 | FAILED TEST OF BHA @ SURFACE DUE TO ASSEMBLING HUK. | BHA | MMOT |  | 07/03/2022 | SCTD-1 | 6.5 | SDGM-1152
271 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | SINO-46L | Hrs | SHYB-708
272 | SRVC | TK2 | 10 | 03 Jul 1900 - 0500 | 7800 | 899172 | CLEAN OUT RUN PRIOR TO SET L-2 WPSTK DUE TO DIFFICULTY WHILE POOH WITH L-1 WPSTK. | WO | NA |  | 07/03/2022 | SINO-46L | 10 | SHYB-708
273 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | SND-2004 | Hrs | BRRI-1148
274 | HFFT | SJC | 14 | 03 Jul 1500 - 0500 | 10545 | 899173 | PERFORMED SLB CEMENT BOND LOGGING @ 7" LINER FROM 10,545' TO 10,000'. NO CEMENT BOND RECORDED. | CMT | NA |  | 07/03/2022 | SND-2004 | 14 | BRRI-1148
275 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | SND-2005 | Hrs | MHKK-2
276 | FOT | WCR | 4 | 03 Jul 0730 - 0045 | 4269 | 899099 | WFD 9-5/8" SPIDER SLIPS NOT RELEASING F/ CSG JT IN ROTARY. | TF | CTRQ |  | 07/03/2022 | SND-2005 | 4 | MHKK-2
277 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | SP-110 | Hrs | BRRI-562
278 | FOT | BHI | 4 | 03 Jul 1615 - 2015 | 17272 | 899104 | BAKER DENSITY TOOLS (SDN) NOT WORKING FROM BIT DEPTH @ 17,167'. | BHA | LWD |  | 07/03/2022 | SP-110 | 4 | BRRI-562
279 | FOT | BHI | 12.25 | 03 Jul 1645 - 0500 | 8006 | 899105 | BHI MWD FAILURE 2ND TOOL. | BHA | MWD |  | 07/03/2022 | SP-257 | 12.25 | HZEM-141012
280 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | SP-257 | Hrs | HZEM-141012
281 | FOT | BHI | 15.25 | 02 Jul 0000 - 1645 | 7842 | 899097 | BHI MWD FAILURE. | BHA | MWD |  | 07/03/2022 | SP-257 | 11.75 | HZEM-141012
282 | FOT | BHI | 12.25 | 03 Jul 1645 - 0500 | 8006 | 899105 | BHI MWD FAILURE 2ND TOOL. | BHA | MWD |  | 07/03/2022 | SP-257 | 12.25 | HZEM-141012
283 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | SSA-101 | Hrs | QTIF-785
284 | FOT | RIG | 5 | 03 Jul 1545 - 2045 | 18900 | 899152 | HAD KINK/DAMAGE SIGNS ON SEVERAL SPOTS IN TDS ELECTRIC CONTROL CABLE LOOP SHIELD, PRECAUTIONARY REPLACED TDS ELECTRIC CONTROL CABLE LOOP W/ NEW ONE. | RR | TDS |  | 07/03/2022 | SSA-101 | 5 | QTIF-785
285 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | SSA-5964 | Hrs | HRDH-1383
286 | XTTE | WCR | 1 | 03 Jul 0600 - 0700 | 12864 | 899122 | LOST TIME DUE TO WFD EQUIPMENT NOT PROFORMING AS REQUIRED | TF | CTRQ |  | 07/03/2022 | SSA-5964 | 1 | HRDH-1383
287 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/03/2022 | STY-038 | Hrs | ZULF-2086
288 | FOT | SDM | 2.25 | 03 Jul 1115 - 1330 | 8883 | 899129 | NO SIGNAL FROM MWD TOOL | BHA | MWD |  | 07/03/2022 | STY-038 | 2.25 | ZULF-2086
289 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | ADC-16 | Hrs | JAHM-6
290 | HINW | ARM | 27 | 03 Jul 0200 - 0500 | 11346 | 899135 | AFTER FINISHED PT 5 @ 11,346FT. UNSET STRADDLE PACKER. ATTEMPT TO GO UP HAD OVERPULL. ATTEMPT TO GO DOWN HAD SLACK OFF .GOT STRING STUCK | STUK | WLT |  | 07/04/2022 | ADC-16 | 24 | JAHM-6
291 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | ADC-35 | Hrs | MAQL-5
292 | FOT | BLH | 104 | 30 Jun 1415 - 0500 | 11925 | 899082 | HOLE PACKED OFF ,TRY TO RE-GAIN CIRCULATION, WITHOUT SUCCESS, POOH 2 STD, HOLE FREE UP, AND RESTRICTED GOING DOWN, REGAIN CIRCULATION, TRY TO GO DOWN STILL HAD OBSTRUCTION. DECISION WAS MADE TO POOH, OBSERVED SWABBING, DECEIDED TO PUMP OUT. - 0 STAIC LOSSES. - 80 BBL/ MIN DYNAMIC LOSSES AT 2.6 BPM. POOH WITH LINER & FOUND; - THE SETTING PIN OF THE LINER SLIPS IS SHEARED & SLIPS PREMATURE SET. - HAD GAP 3/4'' IN THE PISTON CONE ( THE STANDARD SHOULD BE 0 '' GAP.) | TF | HGRL |  | 07/04/2022 | ADC-35 | 24 | MAQL-5
293 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | ADC-49 | Hrs | HWYH-1104
294 | HERR | RIG | 5 | 04 Jul 1330 - 1830 | 4420 | 899170 | EXTRA TIME TO N/U BOP'S, CHANGE 4-WAY BLOCK AND ADJUST CHOKE LINE AS RISER SPOOL IS 4 FT HIGHER THAN GROUND LEVEL. | BOP | BOP |  | 07/04/2022 | ADC-49 | 5 | HWYH-1104
295 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | ADC-54L | Hrs | HRDH-1499
296 | FOT | RIG | 16 | 04 Jul 1030 - 0230 | 6893 | 899164 | AFTER CONNECTION & SURVEY, ANABLE TO ROTATE TDS. TROUBLESHOOTING & BYPASS CHOPPER RESISTOR BANK TO BREAK OUT THE CONNECTION. POOH TO SHOE, CHANGED FAULTY TEMPERATURE SWITCH (THERMOSTAT) & FUNCTION TEST TDS, OK. RIH BACK TO BTM & RESUME DRLG. | RR | TDS |  | 07/04/2022 | ADC-54L | 16 | HRDH-1499
297 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | ADC-62L | Hrs | ANDR-745
298 | HERR | RIG | 388 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/04/2022 | ADC-62L | 24 | ANDR-745
299 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | ADES-173 | Hrs | UTMN-1964
300 | FOT | SPS | 9.25 | 04 Jul 1945 - 0500 | 12588 | 899142 | RSS STOP WORKING. FLAGS SHOWS RSS JAMMING. | BHA | RSS |  | 07/04/2022 | ADES-173 | 9.25 | UTMN-1964
301 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | ADM-655 | Hrs | SFNY-1355
302 | WTHR | ARM | 72 | 02 Jul 0500 - 0500 | 0 | 899096 | WAIT ON WEATHER FOR BARGE ATCO KHADIJAH TO MOVE AND SECURE PLATFORM SFNY-34, 562/566, 1354/1355 PF FOR SAFE RIG APPROACH. | WON | NA |  | 07/04/2022 | ADM-655 | 24 | SFNY-1355
303 | FOT | RIG | 3 | 04 Jul 1915 - 2215 | 8950 | 899165 | WHEN PREPARING TANKS TO MIX BRINE FOUND FLOWLINE VALVES TO PIT# 2 AND PIT#3 BY-PASSING | RR | CSYS |  | 07/04/2022 | ARO-2001 | 3 | BRRI-94
304 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | ARO-2001 | Hrs | BRRI-94
305 | FOT | RIG | 3 | 04 Jul 2345 - 0245 | 9300 | 899143 | WASH PIPE LEAKING. | RR | TDS |  | 07/04/2022 | ARO-2001 | 3 | BRRI-94
306 | FOT | RIG | 3 | 04 Jul 1915 - 2215 | 8950 | 899165 | WHEN PREPARING TANKS TO MIX BRINE FOUND FLOWLINE VALVES TO PIT# 2 AND PIT#3 BY-PASSING | RR | CSYS |  | 07/04/2022 | ARO-2001 | 3 | BRRI-94
307 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | DQ-47 | Hrs | KHRS-497
308 | HERR | ARM | 153 | 28 Jun 0800 - 1700 | 3570 | 898952 | GOC UNABLE TO REACH TARGET ENTRY OF ARB-1 DUE TO SHALLOWER TOP FORMATION W/42'. | JF | NA |  | 07/04/2022 | DQ-47 | 12 | KHRS-497
309 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | HI-4 | Hrs | SFNY-918
310 | WOPF | AP2 | 22.5 | 03 Jul 1200 - 1030 | 10698 | 899153 | WAIT ON PERMISSION FROM FIELD SERVICES TO FLOW WELL THROUGH PRODUCTION LINE. | WO | NA |  | 07/04/2022 | HI-4 | 5.5 | SFNY-918
311 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | NA-393S | Hrs | UTMN-2290
312 | FOT | BAW | 33.5 | 03 Jul 1400 - 2330 | 12837 | 899130 | AFTER LATCHING WIRELINE TO LOGGING TOOLS DOWN HOLE, RESISTIVITY TOOL FAILED TO GIVE SIGNAL. | TF | WLT |  | 07/04/2022 | NA-393S | 18.5 | UTMN-2290
313 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | NBR-115S | Hrs | HWYH-1220
314 | SCSG | ARM | 39 | 01 Jul 0030 - 0500 | 19850 | 899065 | DURING WASH IN THE HOLE WITH SLB MSF COMPLETION STRING STUCK ON CONNECTION. | STUK | LINR |  | 07/04/2022 | NBR-115S | 24 | HWYH-1220
315 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | NBR-20S | Hrs | HMYM-433514
316 | UITE | FME | 16 | 04 Jul 1300 - 0500 | 7170 | 899167 | RESTRICTED INSIDE DIAMETER OF FMH NOT ALLOWING 8-1/2" BIT TO PASS THROUGH. | WH | WBSH |  | 07/04/2022 | NBR-20S | 16 | HMYM-433514
317 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | NBR-263S | Hrs | QTIF-736
318 | UVLC | ARM | 278 | 22 Jun 0630 - 0500 | 8541 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/04/2022 | NBR-263S | 24 | QTIF-736
319 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | NBR-654S | Hrs | HRDH-1150
320 | SRVC | RUE | 30.5 | 03 Jul 2230 - 0500 | 10000 | 899158 | GEOLOG UNABLE TO PICK THE CASING POINT IN BASE JILD DOLOMITE. | WO | NA |  | 07/04/2022 | NBR-654S | 24 | HRDH-1150
321 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | PA-604S | Hrs | HRDH-1955
322 | FOT | RIG | 3.5 | 04 Jul 1900 - 2230 | 9280 | 899166 | TDS UNABLE TO GIVE REQUESTED RPM DUE TO SIGNAL ERROR. | RR | TDS |  | 07/04/2022 | PA-604S | 3.5 | HRDH-1955
323 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | PA-622S | Hrs | UTMN-3600
324 | XTTE | ITS | 3.5 | 04 Jul 2000 - 2330 | 3160 | 899146 | EXCEESS TIME TO M/U & REMOVE 18-5/8" PIPE JOINT, REPLACED DAMAGED PUP JT. | TF | CTRQ |  | 07/04/2022 | PA-622S | 3.5 | UTMN-3600
325 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | PA-70S | Hrs | MDRK-64
326 | FOT | WLH | 809.75 | 30 May 1800 - 0500 | 15492 | 897183 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP. | TF | LLAP |  | 07/04/2022 | PA-70S | 24 | MDRK-64
327 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | RM-74A | Hrs | HSBH-68
328 | GRF | RIG | 102.25 | 30 Jun 2245 - 0500 | 1905 | 898983 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT | UPRA | RWCS |  | 07/04/2022 | RM-74A | 24 | HSBH-68
329 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | SINO-46L | Hrs | SHYB-708
330 | SRVC | TK2 | 18 | 03 Jul 1900 - 1300 | 7800 | 899172 | CLEAN OUT RUN PRIOR TO SET L-2 WPSTK DUE TO DIFFICULTY WHILE POOH WITH L-1 WPSTK. | WO | NA |  | 07/04/2022 | SINO-46L | 8 | SHYB-708
331 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | SND-2004 | Hrs | BRRI-1148
332 | HFFT | SJC | 37 | 03 Jul 1500 - 0500 | 10545 | 899173 | PERFORMED SLB CEMENT BOND LOGGING @ 7" LINER FROM 10,545' TO 10,000'. NO CEMENT BOND RECORDED. | CMT | NA |  | 07/04/2022 | SND-2004 | 23 | BRRI-1148
333 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | SND-2007 | Hrs | AWTD-104001
334 | FOT | ARM | 3 | 04 Jul 0700 - 1000 | 0 | 899140 | FOUND DSA LEAKING BETWEEN FMC 15K TUBING SPOOL & DSA BOTTOM FLANGE WHILE TESTING THE BOPS. LVA # 130966908. | BOP | BOP |  | 07/04/2022 | SND-2007 | 3 | AWTD-104001
335 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | SP-257 | Hrs | HZEM-141012
336 | FOT | BHI | 17.5 | 03 Jul 1645 - 1015 | 8006 | 899105 | BHI MWD FAILURE 2ND TOOL. | BHA | MWD |  | 07/04/2022 | SP-257 | 5.25 | HZEM-141012
337 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | SSA-5891 | Hrs | HRDH-1292
338 | XTTE | WCR | 4.25 | 04 Jul 0500 - 1300 | 13601 | 899106 | DUMP VALVE FAILED TO RELEASE HYDRULIC PRESSURE. 4-1/2" TBG SLIPS NOT HOLDING. | TF | CTRQ |  | 07/04/2022 | SSA-5891 | 4.25 | HRDH-1292
339 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | SSA-5914 | Hrs | WDYH-80
340 | FOT | WUD | 4.75 | 04 Jul 0015 - 0500 | 16203 | 899144 | OBSERVED A LEAK THROUGH WFD MPD BEARING ASSEMBLY WHILE PREPARING TO PERFORM PORE PRESSURE TEST. | TF | MPD |  | 07/04/2022 | SSA-5914 | 4.75 | WDYH-80
341 | FOT | RIG | 4.75 | 04 Jul 1100 - 1545 | 4465 | 899169 | EMERGENCY GENERATOR/ MAIN ENGINE COMMUNICATION FAILURE CAUSING MAIN ENGINE TO TRIP. | RR | PSYS |  | 07/04/2022 | V140A | 4.75 | SFNY-1830
342 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/04/2022 | V140A | Hrs | SFNY-1830
343 | FOT | RIG | .75 | 04 Jul 2030 - 2115 | 4241 | 899168 | WHILE ATTEMPTING TO RACK STAND IN DERRICK, NOTED FINGER LATCH NOT FULLY OPENING, ATTEMPT TO OPEN FINGER MULTIPLE TIMES FROM AD PRS CONTROL, UPON OPENING OF FINGER LATCH TWO ADDITIONAL FINGER LATCHES OPENED ALLOWING TWO STANDS TO EXIT FINGER. | RR | DRRK |  | 07/04/2022 | V140A | .75 | SFNY-1830
344 | FOT | RIG | 4.75 | 04 Jul 1100 - 1545 | 4465 | 899169 | EMERGENCY GENERATOR/ MAIN ENGINE COMMUNICATION FAILURE CAUSING MAIN ENGINE TO TRIP. | RR | PSYS |  | 07/04/2022 | V140A | 4.75 | SFNY-1830
345 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADC-16 | Hrs | JAHM-6
346 | HINW | ARM | 38.5 | 03 Jul 0200 - 1630 | 11346 | 899135 | AFTER FINISHED PT 5 @ 11,346FT. UNSET STRADDLE PACKER. ATTEMPT TO GO UP HAD OVERPULL. ATTEMPT TO GO DOWN HAD SLACK OFF .GOT STRING STUCK | STUK | WLT |  | 07/05/2022 | ADC-16 | 11.5 | JAHM-6
347 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADC-42L | Hrs | SDGM-1258
348 | FOT | TK3 | 22.75 | 03 Jul 0830 - 1700 | 4392 | 899134 | CASING BACKED OUT AT 46' BELOW 18-5/8" CASING HANGER DURING PUMPING TAIL SLURRY 118 PCF OF 2ND STAGE CMT. | TF | CSG |  | 07/05/2022 | ADC-42L | 10 | SDGM-1258
349 | FOT | RIG | 10.5 | 05 Jul 1830 - 0500 | 560 | 899181 | DRAWWORKS PARKING BRAKE ENGAGED & NOT RESPONDING TO COMMEND FROM DRILLER CABIN, REPAIR & TROUBLESHOOTING BRAKE ISSUE. | RR | DWKS |  | 07/05/2022 | ADC-54L | 10.5 | HRDH-1499
350 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADC-54L | Hrs | HRDH-1499
351 | FOT | BHI | 11 | 05 Jul 0730 - 1830 | 6988 | 899180 | LOST COMMUNICATION WITH RSS, TROUBLE SHOOTING DIRECTIONAL ASSY WITHOUT SUCCESS. DECIDED TO POOH TO SURFACE. | BHA | RSS |  | 07/05/2022 | ADC-54L | 11 | HRDH-1499
352 | FOT | RIG | 10.5 | 05 Jul 1830 - 0500 | 560 | 899181 | DRAWWORKS PARKING BRAKE ENGAGED & NOT RESPONDING TO COMMEND FROM DRILLER CABIN, REPAIR & TROUBLESHOOTING BRAKE ISSUE. | RR | DWKS |  | 07/05/2022 | ADC-54L | 10.5 | HRDH-1499
353 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADC-62L | Hrs | ANDR-745
354 | HERR | RIG | 412 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/05/2022 | ADC-62L | 24 | ANDR-745
355 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADES-144 | Hrs | UTMN-3152
356 | FOT | BCR | 6.75 | 05 Jul 2100 - 0345 | 320 | 899254 | BKR CASING POWER TONG LOST COMMUNICATION WITH JAM UNIT, TORQUE TURN GRAPH CANNOT BE GENERATED. | TF | CTRQ |  | 07/05/2022 | ADES-144 | 6.75 | UTMN-3152
357 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADES-173 | Hrs | UTMN-1964
358 | FOT | SPS | 30.25 | 04 Jul 1945 - 0300 | 12588 | 899142 | RSS STOP WORKING. FLAGS SHOWS RSS JAMMING. | BHA | RSS |  | 07/05/2022 | ADES-173 | 21 | UTMN-1964
359 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADM-261 | Hrs | LWHH-9
360 | FOT | SPS | 12 | 05 Jul 1700 - 0500 | 1500 | 899253 | OBSERVE ERROR IN DM COLLAR SIGNALS WHILE SHALLOW TEST TOOLS. | BHA | MWD |  | 07/05/2022 | ADM-261 | 12 | LWHH-9
361 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADM-339 | Hrs | MRJN-3017
362 | FOT | FMC | 1 | 05 Jul 0800 - 0900 | 236 | 899232 | OBSERVED AIRLINE FITTING TO FRANKS SPYDER ELEVATOR BURST. | TF | CRT |  | 07/05/2022 | ADM-339 | 1 | MRJN-3017
363 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADM-655 | Hrs | SFNY-1355
364 | WTHR | ARM | 96 | 02 Jul 0500 - 0500 | 0 | 899096 | WAIT ON WEATHER FOR BARGE ATCO KHADIJAH TO MOVE AND SECURE PLATFORM SFNY-34, 562/566, 1354/1355 PF FOR SAFE RIG APPROACH. | WON | NA |  | 07/05/2022 | ADM-655 | 24 | SFNY-1355
365 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | ADM-657 | Hrs | ZULF-73
366 | SRVC | APF | 24 | 05 Jul 0500 - 0500 | 0 | 899179 | WAIT ON ZULF ONSHORE AND OFFSHORE GOSP APPROVAL FOR ZERO FLARING FLOW BACK ZULF-73 TO GOSP-1. | WO | NA |  | 07/05/2022 | ADM-657 | 24 | ZULF-73
367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | AOD-111 | Hrs | MRJN-728
368 | FOT | BHI | 1.75 | 05 Jul 0315 - 0500 | 13284 | 899234 | OBSERVED BAD DECODDING FROM THE MWD/LWD SIGNAL | BHA | MWD |  | 07/05/2022 | AOD-111 | 1.75 | MRJN-728
369 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | BCTD-4 | Hrs | GHZL-91
370 | FOT | BHI | 11.5 | 05 Jul 1200 - 2330 | 13991 | 899215 | DTF, DEAD SHORT TO TOOLS & UNABLE TO RE-GAIN COMMUNICATION, POH & CHANGE BHA. | BHA | MWD |  | 07/05/2022 | BCTD-4 | 11.5 | GHZL-91
371 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | DQ-50L | Hrs | HRDH-1494
372 | NARW | TK2 | 7.25 | 05 Jul 2145 - 0500 | 2980 | 899183 | RIH W/ 9-5/8" CSG , HAD OBSTRUCTION @ 2980', WORK ON SAME WASH DOWN WITHOUT SUCCESS. | TH | NA |  | 07/05/2022 | DQ-50L | 7.25 | HRDH-1494
373 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | NBR-115S | Hrs | HWYH-1220
374 | SCSG | ARM | 42.75 | 01 Jul 0030 - 1015 | 19850 | 899065 | DURING WASH IN THE HOLE WITH SLB MSF COMPLETION STRING STUCK ON CONNECTION. | STUK | LINR |  | 07/05/2022 | NBR-115S | 3.75 | HWYH-1220
375 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | NBR-263S | Hrs | QTIF-736
376 | UVLC | ARM | 302 | 22 Jun 0630 - 0500 | 8541 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/05/2022 | NBR-263S | 24 | QTIF-736
377 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | NBR-654S | Hrs | HRDH-1150
378 | SRVC | RUE | 44.5 | 03 Jul 2230 - 2000 | 10000 | 899158 | GEOLOG UNABLE TO PICK THE CASING POINT IN BASE JILD DOLOMITE. | WO | NA |  | 07/05/2022 | NBR-654S | 14 | HRDH-1150
379 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | PA-218S | Hrs | HRDH-1941
380 | FOT | XLG | 97.75 | 01 Jul 0315 - 0500 | 11270 | 899150 | FAILED TO DETECT 9 5/8'' CASING POINT. | TF | MLOG |  | 07/05/2022 | PA-218S | 24 | HRDH-1941
381 | FOT | SWL | 3 | 05 Jul 0900 - 1200 | 15918 | 899149 | FOUND ECS DATA QAULITY NOT GOOD, DECISION TAKEN TO REPEAT THE LOG. | TF | WLT |  | 07/05/2022 | PA-70S | 3 | MDRK-64
382 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | PA-70S | Hrs | MDRK-64
383 | FOT | WLH | 830.75 | 30 May 1800 - 0500 | 15492 | 897183 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP. | TF | LLAP |  | 07/05/2022 | PA-70S | 21 | MDRK-64
384 | FOT | SWL | 3 | 05 Jul 0900 - 1200 | 15918 | 899149 | FOUND ECS DATA QAULITY NOT GOOD, DECISION TAKEN TO REPEAT THE LOG. | TF | WLT |  | 07/05/2022 | PA-70S | 3 | MDRK-64
385 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | RM-74A | Hrs | HSBH-68
386 | GRF | RIG | 126.25 | 30 Jun 2245 - 0500 | 1905 | 898983 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT | UPRA | RWCS |  | 07/05/2022 | RM-74A | 24 | HSBH-68
387 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SINO-28L | Hrs | SHYB-711
388 | XTTE | BCR | 4 | 05 Jul 2100 - 0100 | 2417 | 899259 | EXCESSIVE TIME WHILE RIH WITH SMART COMPLETION ON 4-1/2" 11.6# J-55 NEW VAM TUBING | TF | TTRQ |  | 07/05/2022 | SINO-28L | 4 | SHYB-711
389 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SINO-7N | Hrs | FDHL-130
390 | FOT | HCO | 1.5 | 05 Jul 1030 - 1200 | 0 | 899233 | LOST TIME ON HALL PDHMS DUE TO HAND PUMP FAILD TO APPLY PRESSURE TO PT UPPER PDHMS (NO BACK-UP HAND PUMP ON LOCATION), WAIT ON NEW ONE. | TF | PDHMS |  | 07/05/2022 | SINO-7N | 1.5 | FDHL-130
391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SL-7 | Hrs | ZULF-1334
392 | FPMP | RIG | 1 | 05 Jul 1400 - 1500 | 0 | 899182 | RIG SURFACE LINE NOT HOLDING PRESSURE. | RR | MPMP |  | 07/05/2022 | SL-7 | 1 | ZULF-1334
393 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SND-2004 | Hrs | BRRI-1148
394 | HFFT | SJC | 61 | 03 Jul 1500 - 0500 | 10545 | 899173 | PERFORMED SLB CEMENT BOND LOGGING @ 7" LINER FROM 10,545' TO 10,000'. NO CEMENT BOND RECORDED. | CMT | NA |  | 07/05/2022 | SND-2004 | 24 | BRRI-1148
395 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SND-2005 | Hrs | MHKK-2
396 | FOT | RIG | 1 | 05 Jul 0400 - 0500 | 0 | 899257 | TDS HPU FAULT ALARM, FAULT SHOWING HIGH HYDRAULIC RETURN PRESSURE. | RR | TDS |  | 07/05/2022 | SND-2005 | 1 | MHKK-2
397 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SND-2008 | Hrs | HRDH-1812
398 | FOT | SAM | 19.5 | 05 Jul 0930 - 0500 | 10535 | 899272 | AFTER SUCCESSFULL NEGATIVE TEST, EQUALIZE DIFFERENTIAL PRESSURE TO 4200 PSI. UNSET SAMAA FSC PACKER, ALLOW RUBBER ELEMENT TO RELAX FOR 30 MIN. ATTEMPTED TO PICK UP STRING, UP/DOWN IN DIFFERENT POSITION WITH MAX O.P 60 KLBS O. PULL WITHOUT SUCCESS. | BHA | WBCL |  | 07/05/2022 | SND-2008 | 19.5 | HRDH-1812
399 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SP-101 | Hrs | ABQQ-559
400 | FOT | ND1 | 14 | 04 Jul 0245 - 1645 | 5860 | 899178 | NESR FLOAT VALVE FAILED. | TF | FV |  | 07/05/2022 | SP-101 | 11.75 | ABQQ-559
401 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SP-258 | Hrs | JNAB-872212
402 | STBH | ARM | 24 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/05/2022 | SP-258 | 24 | JNAB-872212
403 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SSA-201 | Hrs | HRDH-2112
404 | FOT | SAM | .25 | 05 Jul 2230 - 2245 | 10625 | 899151 | AFTER SUCCESSFULL NEGATIVE TEST AND DURING CIRCULATION OF THE WELL FOR CLEAN UP, A SIGNIFICANT RETURN OF PIECES OF THE FSC PACKER RUBBER ELEMENT WAS NOTICED AND RECOVERED ON THE SHAKERS. WHEN CIRC/CLEAN UP WAS FINISHED AND THE BHA PULLED TO SURFACE IT WAS NOTICED THAT ABOUT 1/3 OF THE FSC PACKER ELEMENT IS TORN OFF FROM THE UNIT. A CLOSE LOOK AT THE REMAINING ELEMENTS ON THE FSC SEEM TO REVEAL THAT THIS IS NOT WEAR FROM DEBRIS BUT RATHER A MECHANICAL TEAR. | BHA | WBCL |  | 07/05/2022 | SSA-201 | .25 | HRDH-2112
405 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SSA-5820 | Hrs | SDGM-1230
406 | FOT | WUD | 2.5 | 05 Jul 2300 - 0130 | 11318 | 899184 | LEAKING ON WFD RCD SEAL ASSY (BEARING). | TF | UBDO |  | 07/05/2022 | SSA-5820 | 2.5 | SDGM-1230
407 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | SSA-5914 | Hrs | WDYH-80
408 | FOT | WUD | 11.25 | 04 Jul 0015 - 1215 | 16203 | 899144 | OBSERVED A LEAK THROUGH WFD MPD BEARING ASSEMBLY WHILE PREPARING TO PERFORM PORE PRESSURE TEST. | TF | MPD |  | 07/05/2022 | SSA-5914 | 6.5 | WDYH-80
409 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/05/2022 | T216 | Hrs | ANDR-338
410 | CEDE | ARM | 18 | 05 Jul 0830 - 0500 | 4970 | 899256 | UNABLE TO PASS W/ WFD 7" WHIPSTOCK. | DRG | NA |  | 07/05/2022 | T216 | 18 | ANDR-338
411 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | ADC-54L | Hrs | HRDH-1499
412 | FOT | RIG | 34.5 | 05 Jul 1830 - 0500 | 560 | 899181 | DRAWWORKS PARKING BRAKE ENGAGED & NOT RESPONDING TO COMMEND FROM DRILLER CABIN, REPAIR & TROUBLESHOOTING BRAKE ISSUE. | RR | DWKS |  | 07/06/2022 | ADC-54L | 24 | HRDH-1499
413 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | ADC-55L | Hrs | UTMN-3171
414 | FOT | SDM | 35 | 05 Jul 1800 - 0500 | 10221 | 899235 | OBSERVED LOSS IN DIFF PRESSURE WHILE DRILLING WITH MUD MOTOR | BHA | MMOT |  | 07/06/2022 | ADC-55L | 24 | UTMN-3171
415 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | ADC-56L | Hrs | UTMN-3069
416 | SRVC | ARM | 1.5 | 06 Jul 0330 - 0500 | 2500 | 899372 | LOST NETWORK CONNECTION GOC UNABLE TO PICK FORMATION TOPS. UNABLE TO CONTINUE DRILLING TILL NETWORK BACK | WO | NA |  | 07/06/2022 | ADC-56L | 1.5 | UTMN-3069
417 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | ADC-62L | Hrs | ANDR-745
418 | HERR | RIG | 436 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/06/2022 | ADC-62L | 24 | ANDR-745
419 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | ADM-261 | Hrs | LWHH-9
420 | FOT | ARN | 1.75 | 06 Jul 0315 - 0500 | 9318 | 899294 | VSAT CONNECTION DROPPED WHILE DRILLING, GOC UNABLE TO MONITOR DRILLING DATA | TF | VSAT |  | 07/06/2022 | ADM-261 | 1.75 | LWHH-9
421 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | ADM-655 | Hrs | SFNY-1355
422 | WTHR | ARM | 120 | 02 Jul 0500 - 0500 | 0 | 899096 | WAIT ON WEATHER FOR BARGE ATCO KHADIJAH TO MOVE AND SECURE PLATFORM SFNY-34, 562/566, 1354/1355 PF FOR SAFE RIG APPROACH. | WON | NA |  | 07/06/2022 | ADM-655 | 24 | SFNY-1355
423 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | ADM-657 | Hrs | ZULF-73
424 | SRVC | APF | 48 | 05 Jul 0500 - 0500 | 0 | 899179 | WAIT ON ZULF ONSHORE AND OFFSHORE GOSP APPROVAL FOR ZERO FLARING FLOW BACK ZULF-73 TO GOSP-1. | WO | NA |  | 07/06/2022 | ADM-657 | 24 | ZULF-73
425 | FOT | BHI | 13.25 | 06 Jul 1515 - 0500 | 13284 | 899334 | PERFORMED VERIFICATION TEST FOR OLD BHA, FOUND PROBLEM W/ BCPM, ONTRAK & MODULAR STAB | BHA | MWD |  | 07/06/2022 | AOD-111 | 13.25 | MRJN-728
426 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | AOD-111 | Hrs | MRJN-728
427 | FOT | BHI | 12 | 05 Jul 0315 - 1515 | 13284 | 899234 | OBSERVED BAD DECODDING FROM THE MWD/LWD SIGNAL. | BHA | MWD |  | 07/06/2022 | AOD-111 | 10.25 | MRJN-728
428 | FOT | BHI | 13.25 | 06 Jul 1515 - 0500 | 13284 | 899334 | PERFORMED VERIFICATION TEST FOR OLD BHA, FOUND PROBLEM W/ BCPM, ONTRAK & MODULAR STAB | BHA | MWD |  | 07/06/2022 | AOD-111 | 13.25 | MRJN-728
429 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | BCTD-3 | Hrs | HWYH-962
430 | FOT | BHI | 7 | 06 Jul 2200 - 0500 | 15520 | 899293 | MOTOR STALLED WHILE DRILLING, ATTEMPT TO POH STRING GOT STUCK. | BHA | MMOT |  | 07/06/2022 | BCTD-3 | 7 | HWYH-962
431 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | DQ-50L | Hrs | HRDH-1494
432 | NARW | TK2 | 31.25 | 05 Jul 2145 - 0500 | 2980 | 899183 | RIH W/ 9-5/8" CSG , HAD OBSTRUCTION @ 2980', WORK ON SAME WASH DOWN WITHOUT SUCCESS. | TH | NA |  | 07/06/2022 | DQ-50L | 24 | HRDH-1494
433 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | ENSCO-76 | Hrs | MRJN-853
434 | FOT | RIG | .5 | 06 Jul 1730 - 1800 | 6008 | 899312 | HOPPER LINE GOT PLUGGED WITH BARITE WHILE MIXING MUD CAP, UNPLUG SAME | RR | CSYS |  | 07/06/2022 | ENSCO-76 | .5 | MRJN-853
435 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | NBR-263S | Hrs | QTIF-736
436 | UVLC | ARM | 326 | 22 Jun 0630 - 0500 | 8541 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/06/2022 | NBR-263S | 24 | QTIF-736
437 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | NBR-633S | Hrs | HRDH-2234
438 | FOT | SWL | 9.5 | 05 Jul 0330 - 1300 | 14000 | 899189 | RIH SLB. WL WITH PWCH AND LATCH LOGGING TOOLS, LATCHED CABLE HEAD (PWCH) INSIDE DOWNHOLE WET CONNECT (DWCH), TESTED TOOL FOUND NO COMMUNICATION BETWEEN LOGGING TOOL. | TF | WLT |  | 07/06/2022 | NBR-633S | 8 | HRDH-2234
439 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | PA-622S | Hrs | UTMN-3600
440 | HERR | ITS | 5.5 | 06 Jul 2330 - 0500 | 3200 | 899295 | WHILE DISPLACING CEMENT, CASING CONNECTION JUMPED OUT LEAVING THE CEMENT INSIDE THE CASING. | JF | CTRQ |  | 07/06/2022 | PA-622S | 5.5 | UTMN-3600
441 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | RM-74A | Hrs | HSBH-68
442 | GRF | RIG | 142 | 30 Jun 2245 - 0500 | 1905 | 898983 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT | UPRA | RWCS |  | 07/06/2022 | RM-74A | 24 | HSBH-68
443 | 6849 | 1400 | LOG | E |  | WLT | CONTINUE RECORD MPET CORROSION LOG FROM 550' TO SURFACE WITH 5 FPM, RIH & RECORD REPEAT SECTION FROM 1900' TO 1400' WITH 5 FPM, POOH & L/D HES LOGGING TOOL, R/D W/L SHEAVES. | 6849 | 1900 | HWP | 07/06/2022 | SINO-37L | LOG | HWYH-277
444 | 6849 |  | OTH | N | 3585 | NA | (OOS). HPJSM, PERFORM HOT TAPPING FOR SEAL WELDED 18 5/8" CASING AS FOLLOWS:-- HOTHED WELD 1.5" NIPPLE, INSTALL 1.5" BALL VALVE AT 5' BELOW LANDING BASE IN 18 5/8" CASING.- PERFORM MPI ON WELDING AREA BY MANSOURI, OK.- PRESSURE TEST THE CONNECTION AGAINST WELDING TO 500/1200 PSI BY HOTHED, HOLD OK.- DRILL HOLE INSIDE 18 5/8" CASING THROUGH BALL VALVE WITH HOTHED TOOLS.- CHECK PRESSURE INSIDE 18 5/8" CASING, NO PRESSURE. | 6849 |  | HTD | 07/06/2022 | SINO-37L | WH | HWYH-277
445 | 6849 |  | OTH | N |  | NA | HPJSM, PERFORM UT INSPECTION FOR 13 3/8"CASING AS FOLLOWS:-- HOTHED CUT 10" X 10" WINDOWS ON BOTH SIDES OF 18 5/8" CASING, CLEAN CEMENT AROUND 13 3/8" CASING.- PERFORM UT INSPECTION FOR 13 3/8"CASING, THICKNESS ACCEPTED.- FILL CEMENT BETWEEN 18 5/8" & 13 3/8" CASING.- HOTHED RE WELDED WINDOWS, MPI INSPECTION, OK.- FILL CELLAR WITH SWEET SAND. | 6849 |  | HTD | 07/06/2022 | SINO-37L | WH | HWYH-277
446 | 6849 |  | HT | N |  | BHA | HPJSM, P/U & M/U WFD 7" HYDRAULIC WHIPSTOCK ASSEMBLY {5.5" RHN QC WHIPSTOCK ATTACHED WITH 43 KLB BOLT, 6 1/8" LEAD MILL, 6 1/8" FLEX MILL, 1 JT 3 1/2" HWDP, FLOAT SUB {FLOAT VALVE}, UBHO, X-O}, - ALIGN WIPHSTOCK WITH UBHO. - CHECK LEAD & FLEX MILL GAUGE - FULL GAUGE.- DRIFT XO ABOVE UBHO SUB W/ 2.25" DRIFT. | 6849 |  | RIG | 07/06/2022 | SINO-37L | TINL | HWYH-277
447 | 6849 | 1695 | ST | N |  | STDP | RIH WITH 7" WFD HYDRAULIC WHIPSTOCK ASSEMBLY ON DRIFTED 4" HWDP STANDS TO 1695'.- RIH WITH CONTROLLED SPEED 3 MINS PER STAND AS PER WFD REQUEST.- DRIFT ALL HWDP STANDS WITH 2.25" DRIFT WHILE RIH.- FILL STRING EACH STAND WITH 75 PCF FRESH BRINE. | 6849 | 0 | RIG | 07/06/2022 | SINO-37L | TINL | HWYH-277
448 | 6849 | 5476 | ST | N |  | SPDP | CONT. RIH WITH 7" WFD HYDRAULIC WHIPSTOCK ASSEMBLY ON DRIFTED 4" DP FROM 1695' TO 5476' {BOTTOM OF WHIPSTOCK}- P/U & M/U 105 JOINTS 4" DP FROM GROUND.- RIH WITH CONTROLLED SPEED 3 MINS PER STAND AS PER WFD REQUEST.- DRIFT ALL DP WITH 2.375" DRIFT WHILE RIH.- FILL STRING EACH STAND WITH 75 PCF FRESH BRINE.- BREAK CIRC & CIRC STRING CAPACITY EVERY 2000' WITH 80 GPM. | 6849 | 1695 | RIG | 07/06/2022 | SINO-37L | TINL | HWYH-277
449 | 6849 |  | CIRC | N |  | MPMP | M/U CIRC. HEAD, CIRCULATE 1.5 STRING CAPACITY WITH 90 GPM @ 100 PSI. | 6849 |  | RIG | 07/06/2022 | SINO-37L | TINL | HWYH-277
450 | 6849 |  | SURV | N |  | GYRO | HPJSM, R/U NAPESCO GYRO SHEAVES AND M/U GYRO TOOL.- RIH WITH GYRO TOOL, SET SAME IN UBHO, ORIENT WHIPSTOCK TO 334.0 DEG AZIMUTH.- CONFIRM WHIPSTOCK ORIENTATION WITH THREE GYRO SHOTS. | 6849 |  | NGS | 07/06/2022 | SINO-37L | TINL | HWYH-277
451 | 6849 |  | SURV | N |  | GYRO | POOH WITH GYRO, RECORD MULTISHOT SURVEY EVERY 100'.... INC..@RPT | 6849 |  | NGS | 07/06/2022 | SINO-37L | TINL | HWYH-277
452 | 1.5 | OOSS | Category | DOOS ID | HTAP | Out of Scope Summary | PERFORM HOT TAPPING ON SEAL WELDED 18-5/8" CSG. | 1.5 | 3585 | 06 Jul 1200 | 07/06/2022 | SINO-37L | Type | HWYH-277
453
454
455 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | SND-2004 | Hrs | BRRI-1148
456 | HFFT | SJC | 72 | 03 Jul 1500 - 1600 | 10545 | 899173 | PERFORMED SLB CEMENT BOND LOGGING @ 7" LINER FROM 10,545' TO 10,000'. NO CEMENT BOND RECORDED. | CMT | NA |  | 07/06/2022 | SND-2004 | 11 | BRRI-1148
457 | FOT | RIG | 1.5 | 06 Jul 1915 - 2045 | 0 | 899292 | UNABLE TO RETRACT TDS LINKS DUE TO ELECTRICAL FAILURE. | RR | TDS |  | 07/06/2022 | SND-2005 | 1.5 | MHKK-2
458 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | SND-2005 | Hrs | MHKK-2
459 | FOT | RIG | 14 | 05 Jul 0400 - 1800 | 0 | 899257 | TDS HPU FAULT ALARM, FAULT SHOWING HIGH HYDRAULIC RETURN PRESSURE. | RR | TDS |  | 07/06/2022 | SND-2005 | 13 | MHKK-2
460 | FOT | RIG | 1.5 | 06 Jul 1915 - 2045 | 0 | 899292 | UNABLE TO RETRACT TDS LINKS DUE TO ELECTRICAL FAILURE. | RR | TDS |  | 07/06/2022 | SND-2005 | 1.5 | MHKK-2
461 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | SND-2008 | Hrs | HRDH-1812
462 | FOT | SAM | 43.5 | 05 Jul 0930 - 0500 | 10535 | 899272 | AFTER SUCCESSFULL NEGATIVE TEST, EQUALIZE DIFFERENTIAL PRESSURE TO 4200 PSI. UNSET SAMAA FSC PACKER, ALLOW RUBBER ELEMENT TO RELAX FOR 30 MIN. ATTEMPTED TO PICK UP STRING, UP/DOWN IN DIFFERENT POSITION WITH MAX O.P 60 KLBS O. PULL WITHOUT SUCCESS. | BHA | WBCL |  | 07/06/2022 | SND-2008 | 24 | HRDH-1812
463 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | SND-3001 | Hrs | MHWZ-167101
464 | FOT | RIG | 2.25 | 06 Jul 0200 - 0415 | 19158 | 899333 | OBSERVE WASH OUT ON SAVER SUB | RR | TDS |  | 07/06/2022 | SND-3001 | 2.25 | MHWZ-167101
465 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | SP-258 | Hrs | JNAB-872212
466 | STBH | ARM | 48 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/06/2022 | SP-258 | 24 | JNAB-872212
467 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | SSA-5868 | Hrs | HRDH-2413
468 | FOT | WCR | 2.5 | 06 Jul 0945 - 1215 | 9720 | 899191 | AFTER PICKING 13-3/8" SHOE JT WFD CRT FAILED TO FUNCTION. TROUBLE SHOOT ISSUE AND REPLACED CRT SERVICE LOOP. | TF | CTRQ |  | 07/06/2022 | SSA-5868 | 2.5 | HRDH-2413
469 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/06/2022 | T914 | Hrs | UTMN-463
470 | FOT | SPS | 21.5 | 06 Jul 0645 - 0500 | 7740 | 899352 | SPERRY SUN LWD TOOLS LOST SIGNAL. | BHA | LWD |  | 07/06/2022 | T914 | 21.5 | UTMN-463
471 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADC-16 | Hrs | JAHM-6
472 | FOT | RIG | 6.5 | 07 Jul 1130 - 1800 | 550 | 899335 | WHILE POOH WITH C/O BHA, OBSERVED TDS BLOCK HARDLY MOVE UP & DOWN. AFTER TROUBLE SHOOTING FOUND DRAW WORKS LOW CLUTCH DRUM MALFUNCTION | RR | DWKS |  | 07/07/2022 | ADC-16 | 6.5 | JAHM-6
473 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADC-17 | Hrs | ZULF-1218
474 | FOT | SPS | 1 | 07 Jul 1100 - 1200 | 6704 | 899452 | HALLIBURTON EXPERIENCED DATA QUALITY ISSUES WHEN UPLOADING DATA TO WELL LINK. RE-UPLOAD DATA TO CORRECT ISSUE, AND BE ACCEPTED BY GOC. | TF | COMP |  | 07/07/2022 | ADC-17 | 1 | ZULF-1218
475 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADC-51 | Hrs | SDGM-1225
476 | FOT | RIG | 7 | 07 Jul 1400 - 2200 | 1400 | 899432 | OBSERVED TDS GRABBER STUCK HALF CLOSED POSITION. | RR | TDS |  | 07/07/2022 | ADC-51 | 7 | SDGM-1225
477 | FOT | RIG | 51.5 | 05 Jul 1830 - 2200 | 560 | 899181 | DRAWWORKS PARKING BRAKE ENGAGED & NOT RESPONDING TO COMMEND FROM DRILLER CABIN, REPAIR & TROUBLESHOOTING BRAKE ISSUE. | RR | DWKS |  | 07/07/2022 | ADC-54L | 17 | HRDH-1499
478 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADC-54L | Hrs | HRDH-1499
479 | FOT | BHI | 18 | 05 Jul 0730 - 0500 | 6988 | 899180 | LOST COMMUNICATION WITH RSS, TROUBLE SHOOTING DIRECTIONAL ASSY WITHOUT SUCCESS. DECIDED TO POOH TO SURFACE. | BHA | RSS |  | 07/07/2022 | ADC-54L | 7 | HRDH-1499
480 | FOT | RIG | 51.5 | 05 Jul 1830 - 2200 | 560 | 899181 | DRAWWORKS PARKING BRAKE ENGAGED & NOT RESPONDING TO COMMEND FROM DRILLER CABIN, REPAIR & TROUBLESHOOTING BRAKE ISSUE. | RR | DWKS |  | 07/07/2022 | ADC-54L | 17 | HRDH-1499
481 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADC-55L | Hrs | UTMN-3171
482 | FOT | SDM | 46.25 | 05 Jul 1800 - 0500 | 10221 | 899235 | OBSERVED LOSS IN DIFF PRESSURE WHILE DRILLING WITH MUD MOTOR | BHA | MMOT |  | 07/07/2022 | ADC-55L | 11.25 | UTMN-3171
483 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADC-56L | Hrs | UTMN-3069
484 | SRVC | ARM | 2.5 | 06 Jul 0330 - 0600 | 2500 | 899372 | LOST NETWORK CONNECTION GOC UNABLE TO PICK FORMATION TOPS. UNABLE TO CONTINUE DRILLING TILL NETWORK BACK | WO | NA |  | 07/07/2022 | ADC-56L | 1 | UTMN-3069
485 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADC-62L | Hrs | ANDR-745
486 | HERR | RIG | 460 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/07/2022 | ADC-62L | 24 | ANDR-745
487 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADM-261 | Hrs | LWHH-9
488 | FOT | ARN | 2.25 | 06 Jul 0315 - 0530 | 9318 | 899294 | VSAT CONNECTION DROPPED FROM TOWN SIDE WHILE DRILLING, GOC UNABLE TO MONITOR DRILLING DATA | TF | VSAT |  | 07/07/2022 | ADM-261 | .5 | LWHH-9
489 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADM-655 | Hrs | SFNY-1355
490 | WTHR | ARM | 144 | 02 Jul 0500 - 0500 | 0 | 899096 | WAIT ON WEATHER FOR BARGE ATCO KHADIJAH TO MOVE AND SECURE PLATFORM SFNY-34, 562/566, 1354/1355 PF FOR SAFE RIG APPROACH. | WON | NA |  | 07/07/2022 | ADM-655 | 24 | SFNY-1355
491 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | ADM-657 | Hrs | ZULF-73
492 | SRVC | APF | 67 | 05 Jul 0500 - 0000 | 0 | 899179 | WAIT ON ZULF ONSHORE AND OFFSHORE GOSP APPROVAL FOR ZERO FLARING FLOW BACK ZULF-73 TO GOSP-1. | WO | NA |  | 07/07/2022 | ADM-657 | 19 | ZULF-73
493 | FOT | BHI | 24.75 | 06 Jul 0500 - 0615 | 13284 | 899334 | OBSERVED BAD DECODING FROM THE MWD/LWD SIGNAL. | BHA | MWD |  | 07/07/2022 | AOD-111 | 1.25 | MRJN-728
494 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | AOD-111 | Hrs | MRJN-728
495 | FOT | BHI | 7 | 07 Jul 2200 - 0500 | 14340 | 899300 | OBSERVED BAD DECODING FROM THE MWD/LWD SIGNAL. | BHA | MWD |  | 07/07/2022 | AOD-111 | 7 | MRJN-728
496 | FOT | BHI | 24.75 | 06 Jul 0500 - 0615 | 13284 | 899334 | OBSERVED BAD DECODING FROM THE MWD/LWD SIGNAL. | BHA | MWD |  | 07/07/2022 | AOD-111 | 1.25 | MRJN-728
497 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | BCTD-3 | Hrs | HWYH-962
498 | FOT | RIG | 10.5 | 06 Jul 2200 - 0830 | 15520 | 899293 | MOTOR STALLED WHILE DRILLING, ATTEMPT TO POH STRING GOT STUCK. | BHA | MMOT |  | 07/07/2022 | BCTD-3 | 3.5 | HWYH-962
499 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | DQ-50L | Hrs | HRDH-1494
500 | NARW | TK2 | 49.25 | 05 Jul 2145 - 2300 | 2980 | 899183 | RIH W/ 9-5/8" CSG , HAD OBSTRUCTION @ 2980', WORK ON SAME WASH DOWN WITHOUT SUCCESS. | TH | NA |  | 07/07/2022 | DQ-50L | 18 | HRDH-1494
501 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | EXL-IVA | Hrs | SFNY-1650
502 | FOT | RIG | 3 | 07 Jul 2315 - 0215 | 4393 | 899433 | UNABLE TO ROTATE TDS. | RR | TDS |  | 07/07/2022 | EXL-IVA | 3 | SFNY-1650
503 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | NBR-196S | Hrs | SDGM-1235
504 | IHFL | RIG | 3 | 07 Jul 1930 - 2230 | 10860 | 899434 | TDS HYDRAULIC SYSTEM PROBLEMS | RR | HSYS |  | 07/07/2022 | NBR-196S | 3 | SDGM-1235
505 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | NBR-263S | Hrs | QTIF-736
506 | UVLC | ARM | 345.25 | 22 Jun 0630 - 0500 | 8541 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/07/2022 | NBR-263S | 24 | QTIF-736
507 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | PA-622S | Hrs | UTMN-3600
508 | HERR | ITS | 29.5 | 06 Jul 2330 - 0500 | 3200 | 899295 | WHILE DISPLACING CEMENT, X-OVER CONNECTION JUMPED OUT 27 FT BELOW CEMENTING HEAD LEAVING THE CEMENT INSIDE THE CASING. | JF | CTRQ |  | 07/07/2022 | PA-622S | 24 | UTMN-3600
509 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | RM-74A | Hrs | HSBH-68
510 | GRF | RIG | 166 | 30 Jun 2245 - 0500 | 1905 | 898983 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT | UPRA | RWCS |  | 07/07/2022 | RM-74A | 24 | HSBH-68
511 | 10339 | 0 | LOG | E |  | WLT | CONT. RECORD MPET CORROSION LOG FROM 4980' TO SURFACE, RIH & RECORD REPEAT SECTION FROM 2300' TO 2000' WITH 5 FPM, POOH & L/D HES LOGGING TOOL, R/D W/L SHEAVES. | 10339 | 4890 | HWP | 07/07/2022 | SINO-42L | LOG | HWYH-353
512 | 10339 |  | OTH | N |  | NA | HPJSM, ISSUE REQUIRED PTW & DISCUSSED JSA .CHECK WH & CSG INTEGRITY :>> HANG UP & SECURE BOP STACK .>> CHECK 9" X 13" CCA IS ZERO PRESSURE .>> P/T 9" X 13" CCA TO 500 PSI W/ INHIBITED WATER - HOLD .>> DIG CELLAR 6 FT BELOW LANDING BASE..>> MANSOORI PERFORM UT INSPECTION FOR LANDING BASE ( GOOD CONDITION ) ,18-5/8" CSG , 87.5# ( SEAL WELDED TO DONUT PLATE ), ( GOOD CONDITION ). | 10339 |  | RIG | 07/07/2022 | SINO-42L | WH | HWYH-353
513 | 10339 |  | OTH | N | 3605 | NA | (OOS) WILD WELL PERFORM HOT-TAPPING TO 18-5/8" CSG. NO PRESSURE & NO GASSES. | 10339 |  | WWC | 07/07/2022 | SINO-42L | WH | HWYH-353
514 | 10339 |  | OTH | N |  | NA | - HOT HED CUT 18 5/8" CASING WINDOW, HAVE GOOD CMT. - ALMANSORI PERFORM UT INSPECTION FOR 13 3/8" CASING, ACCEPTED. (NO ACTION REQUIRED).- FILL ANNULUS BACK WITH CEMENT.- HOT HED SEAL WELD 18 5/8" NEW CASING WINDOW.- ALMANSORI PERFORM MPI INSPECTION FOR WELDED AREAS. OK- FILL CELLAR WITH SWEET SAND. | 10339 |  | HTD | 07/07/2022 | SINO-42L | WH | HWYH-353
515 | 10339 |  | HT | N |  | BHA | HPJSM, P/U & M/U WFD 7" HYDRAULIC WHIPSTOCK ASSEMBLY {5.5" RHN QC WHIPSTOCK ATTACHED WITH 43 KLB BOLT, 6 1/8" LEAD MILL, 6 1/8" FLEX MILL, 1 JT 3 1/2" HWDP, FLOAT SUB {FLOAT VALVE}, UBHO, X-O}, - ALIGN WIPHSTOCK WITH UBHO. - CHECK LEAD & FLEX MILL GAUGE - FULL GAUGE.- DRIFT XO ABOVE UBHO SUB W/ 2.25" DRIFT. | 10339 |  | RIG | 07/07/2022 | SINO-42L | TINL | HWYH-353
516 | 10339 | 4100 | ST | N |  | STDP | RIH WITH 7" WFD HYDRAULIC WHIPSTOCK ASSEMBLY ON DRIFTED 4" HWDP STANDS TO 4100'.....INC@RPT- RIH WITH CONTROLLED SPEED 3 MINS PER STAND AS PER WFD REQUEST.- DRIFT ALL HWDP STANDS WITH 2.25" DRIFT WHILE RIH.- FILL STRING EACH STAND WITH 73 PCF FRESH BRINE. | 10339 | 0 | RIG | 07/07/2022 | SINO-42L | TINL | HWYH-353
517 | 1 | OOSS | Category | DOOS ID | HTAP | Out of Scope Summary | HOT-HED PERFORM HOT TAPPING ON 18-5/8" CSG . | 1 | 3605 | 07 Jul 2130 | 07/07/2022 | SINO-42L | Type | HWYH-353
518
519
520 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | SINO-47 | Hrs | HRDH-1351
521 | FOT | BAW | 4.75 | 07 Jul 1945 - 0030 | 14470 | 899336 | DURING TEST AND CALIBRATION OF BAKER LOGGING TOOLS RUN#2 AT 9-5/8" CSG SHOE, ONE OF ZDL TOOLS FAILLED. | TF | WLT |  | 07/07/2022 | SINO-47 | 4.75 | HRDH-1351
522 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | SND-2008 | Hrs | HRDH-1812
523 | FOT | SAM | 65.5 | 05 Jul 0930 - 0300 | 10535 | 899272 | AFTER SUCCESSFULL NEGATIVE TEST, EQUALIZE DIFFERENTIAL PRESSURE TO 4200 PSI. UNSET SAMAA FSC PACKER, ALLOW RUBBER ELEMENT TO RELAX FOR 30 MIN. ATTEMPTED TO PICK UP STRING, UP/DOWN IN DIFFERENT POSITION WITH MAX O.P 60 KLBS O. PULL WITHOUT SUCCESS. | BHA | WBCL |  | 07/07/2022 | SND-2008 | 22 | HRDH-1812
524 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | SP-258 | Hrs | JNAB-872212
525 | STBH | ARM | 72 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/07/2022 | SP-258 | 24 | JNAB-872212
526 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | SP-261 | Hrs | HZEM-160212
527 | HERR | RIG | 23.5 | 07 Jul 0500 - 0500 | 4006 | 899337 | AFTER RUNNING 13 3/8" CASING IN THE HOLE, WHILE WASHING DOWN TO LAND FMH PRESSURE SPIKED & RIG WAS UNABLE TO CIRCULATE. | JF | NA |  | 07/07/2022 | SP-261 | 23.5 | HZEM-160212
528 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | SSA-101 | Hrs | QTIF-785
529 | FOT | ARN | 2 | 07 Jul 0630 - 0830 | 19516 | 899392 | V-SAT COMMUNICATION DOWN. V-SAT TEAM TROUBLE SHOOT AND FIX V-SAT COMMUNICATION. | TF | VSAT |  | 07/07/2022 | SSA-101 | 2 | QTIF-785
530 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | SSA-5859 | Hrs | HWYH-1222
531 | CFFM | ARM | 38 | 06 Jul 1500 - 0500 | 11240 | 899374 | GOT LOSSES WHILE CEMENTING 9"5/8 CSG | CMT | NA |  | 07/07/2022 | SSA-5859 | 24 | HWYH-1222
532 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | SSA-5914 | Hrs | WDYH-80
533 | FOT | WUD | 51 | 05 Jul 0200 - 0500 | 16235 | 899296 | OBSERVED DROP IN PRESSURE OF 1,000 PSI. POOH & CHECK BHA. FOUND 5-7/8" HOLE CURVE BHA TWISTED OFF FROM THE PIN OF 2ND WFD FLOAT SUB. | BHA | FV |  | 07/07/2022 | SSA-5914 | 24 | WDYH-80
534 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | SSA-5971 | Hrs | HRDH-2247
535 | FOT | BAW | 1.5 | 07 Jul 0330 - 0500 | 14108 | 899338 | LOGGING TOOLS NOT RESPONDING WHILE TAKING FORMATION PRESSURE AT 14108'. | TF | WLT |  | 07/07/2022 | SSA-5971 | 1.5 | HRDH-2247
536 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/07/2022 | T914 | Hrs | UTMN-463
537 | FOT | SPS | 35 | 06 Jul 0645 - 2015 | 7740 | 899352 | SPERRY SUN LWD TOOLS LOST SIGNAL. | BHA | LWD |  | 07/07/2022 | T914 | 12.75 | UTMN-463
538 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | ADC-51 | Hrs | SDGM-1225
539 | FOT | RIG | 2 | 08 Jul 1030 - 1230 | 2251 | 899479 | OBSERVED ROTARY HOSE CONNECTION LEAKING ON STAND PIPE BETWEEN HES MWD SPP SENSOR AND ROTARY HOSE. | RR | CSYS |  | 07/08/2022 | ADC-51 | 2 | SDGM-1225
540 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | ADC-54L | Hrs | HRDH-1499
541 | FOT | BHI | 30.5 | 05 Jul 0730 - 1700 | 6988 | 899180 | LOST COMMUNICATION WITH RSS, TROUBLE SHOOTING DIRECTIONAL ASSY WITHOUT SUCCESS. DECIDED TO POOH TO SURFACE. | BHA | RSS |  | 07/08/2022 | ADC-54L | 12 | HRDH-1499
542 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | ADC-55L | Hrs | UTMN-3171
543 | FOT | SDM | 64.75 | 05 Jul 1800 - 2330 | 10221 | 899235 | OBSERVED LOSS IN DIFF PRESSURE WHILE DRILLING WITH MUD MOTOR | BHA | MMOT |  | 07/08/2022 | ADC-55L | 18.5 | UTMN-3171
544 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | ADC-56L | Hrs | UTMN-3069
545 | SCSG | TK3 | 3.25 | 08 Jul 0145 - 0500 | 2655 | 899426 | WHILE WORKING CASING STRING AT 2,655' HAD PRESSURE SHOOT UP TO 550 PSI & NO MOVEMENT UP/DOWN & NO CIRCULATION. GET STUCKED . | STUK | CSG |  | 07/08/2022 | ADC-56L | 3.25 | UTMN-3069
546 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | ADC-60 | Hrs | ABSF-217
547 | FOT | WCS | 10.25 | 07 Jul 0015 - 1030 | 5496 | 899423 | FIBRE OPTIC CABLE FOR PDHMS WAS DAMAGED DURING TERMINATION. | TF | PDHMS |  | 07/08/2022 | ADC-60 | 5.5 | ABSF-217
548 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | ADC-62L | Hrs | ANDR-745
549 | HERR | RIG | 484 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/08/2022 | ADC-62L | 24 | ANDR-745
550 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | ADES-144 | Hrs | UTMN-3152
551 | FOT | RIG | 2 | 08 Jul 1730 - 1930 | 9450 | 899480 | SERVICE AND ADJUST OF THE DRAWWROKS BREAKS. DRAWWORKS MALFUNCTION. | RR | DWKS |  | 07/08/2022 | ADES-144 | 2 | UTMN-3152
552 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | AOD-11 | Hrs | SFNY-1810
553 | FOT | BCR | 1.5 | 08 Jul 1630 - 1800 | 0 | 899309 | BAKER POWER UNIT CABLE HEAD CONNECTER NOT COMPATIBLE WITH RIG POWER SUPPLY. | TF | CTRQ |  | 07/08/2022 | AOD-11 | 1.5 | SFNY-1810
554 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | AOD-111 | Hrs | MRJN-728
555 | FOT | BHI | 28.25 | 07 Jul 2200 - 0215 | 14340 | 899300 | OBSERVED BAD DECODING FROM THE MWD/LWD SIGNAL. | BHA | MWD |  | 07/08/2022 | AOD-111 | 21.25 | MRJN-728
556 | XTTE | BCR | 2 | 08 Jul 2200 - 0000 | 2515 | 899495 | EXESS TIME WHILE POOH WITH CASING | TF | CTRQ |  | 07/08/2022 | DPS-4 | 2 | MDRK-63
557 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | DPS-4 | Hrs | MDRK-63
558 | NARW | ARM | 29.75 | 07 Jul 2000 - 0500 | 5300 | 899482 | TAKE SLACK OFF WEIGHT AT 5300' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS. | TH | NA |  | 07/08/2022 | DPS-4 | 20.75 | MDRK-63
559 | XTTE | BCR | 2 | 08 Jul 2200 - 0000 | 2515 | 899495 | EXESS TIME WHILE POOH WITH CASING | TF | CTRQ |  | 07/08/2022 | DPS-4 | 2 | MDRK-63
560 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | ENSCO-54 | Hrs | ABSF-17
561 | STCT | ARM | 54 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/08/2022 | ENSCO-54 | 24 | ABSF-17
562 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | NBR-115S | Hrs | HWYH-1220
563 | FOT | WCR | 2 | 08 Jul 0230 - 0430 | 1884 | 899425 | CAM UNIT READING HIGH TORQUE. C/O JOINTS TWICE. FOUND ISSUE IN THE WEATHERFORD CAM UNIT. | TF | CTRQ |  | 07/08/2022 | NBR-115S | 2 | HWYH-1220
564 | FOT | RIG | 1 | 08 Jul 0300 - 0400 | 7978 | 899493 | RIG REPAIR, CHANGE LINER ON MUD PUMP#1 AND CLEAN SUCCTION SCREEN ON MUD PUMP#3 MEANWHILE CIRC WITH MUD PUMP#2. | RR | MPMP |  | 07/08/2022 | NBR-263S | 1 | QTIF-736
565 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | NBR-263S | Hrs | QTIF-736
566 | UVLC | ARM | 368.25 | 22 Jun 0630 - 0500 | 8053 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/08/2022 | NBR-263S | 23 | QTIF-736
567 | FOT | RIG | 1 | 08 Jul 0300 - 0400 | 7978 | 899493 | RIG REPAIR, CHANGE LINER ON MUD PUMP#1 AND CLEAN SUCCTION SCREEN ON MUD PUMP#3 MEANWHILE CIRC WITH MUD PUMP#2. | RR | MPMP |  | 07/08/2022 | NBR-263S | 1 | QTIF-736
568 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | NBR-654S | Hrs | HRDH-1150
569 | FOT | RIG | 1.5 | 08 Jul 2330 - 0100 | 10000 | 899481 | THREAD DAMAGED ON TDS SAVER SUB | RR | TDS |  | 07/08/2022 | NBR-654S | 1.5 | HRDH-1150
570 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | PA-622S | Hrs | UTMN-3600
571 | HERR | ITS | 53 | 06 Jul 2330 - 0500 | 3200 | 899295 | WHILE DISPLACING CEMENT, X-OVER CONNECTION JUMPED OUT 28 FT BELOW ROTARY TABLE LEAVING THE CEMENT INSIDE THE CASING. | JF | CTRQ |  | 07/08/2022 | PA-622S | 23.5 | UTMN-3600
572 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | RM-74A | Hrs | HSBH-68
573 | GRF | RIG | 179 | 30 Jun 2245 - 1800 | 1905 | 898983 | BIG BORE DIVERTER OVERSHOT LEAKING DURING DRILLING/HOLE ENLARGEMENT | UPRA | RWCS |  | 07/08/2022 | RM-74A | 13 | HSBH-68
574 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SINO-28L | Hrs | SHYB-711
575 | HERR | TK2 | 5 | 08 Jul 0830 - 1330 | 7386 | 899308 | WHILE L/D LOWER PART OF BOPE TOUCHED THE SMART COMPLETION TEC AND BENT THE 1/4" TUBE (STEEL ARMOR). | JF | NA |  | 07/08/2022 | SINO-28L | 5 | SHYB-711
576 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SINO-47 | Hrs | HRDH-1351
577 | FOT | BAW | 14 | 08 Jul 1500 - 0500 | 14470 | 899492 | FAILLURE OF XMAC (SONIC) TOOL DURING RUN#2. | TF | WLT |  | 07/08/2022 | SINO-47 | 14 | HRDH-1351
578 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SND-2005 | Hrs | MHKK-2
579 | FOT | RIG | 3 | 08 Jul 0500 - 0800 | 5638 | 899304 | ACTUATOR VALVE ON TDS LEAKING WHEN FILLING DP. | RR | TDS |  | 07/08/2022 | SND-2005 | 3 | MHKK-2
580 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SND-2007 | Hrs | AWTD-104001
581 | FOT | RIG | 4.25 | 08 Jul 2315 - 0330 | 16830 | 899494 | WHILE TESTING BOPE, FOUND LEAKAGE IN BONNET OF SHEAR/BLIND RAMS . | BOP | BOP |  | 07/08/2022 | SND-2007 | 4.25 | AWTD-104001
582 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SND-2008 | Hrs | HRDH-1812
583 | STDP | RIG | 88.5 | 05 Jul 0930 - 0500 | 10535 | 899272 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS, POH TO CHECK STRG FOUND STRG TWISTED OFF AT 2ND DC ABOVE MILL. CHECK FOR SND OVERSHOT, NOT AVAILABLE | STUK | DP |  | 07/08/2022 | SND-2008 | 23 | HRDH-1812
584 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SP-258 | Hrs | JNAB-872212
585 | STBH | ARM | 96 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/08/2022 | SP-258 | 24 | JNAB-872212
586 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SP-261 | Hrs | HZEM-160212
587 | HERR | EMC | 47 | 07 Jul 0500 - 0500 | 4006 | 899337 | AFTER RUNNING 13 3/8" CASING IN THE HOLE, WHILE WASHING DOWN TO LAND FMH PRESSURE SPIKED & RIG WAS UNABLE TO CIRCULATE. | JF | SCS |  | 07/08/2022 | SP-261 | 23.5 | HZEM-160212
588 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SSA-5859 | Hrs | HWYH-1222
589 | CFFM | ARM | 62 | 06 Jul 1500 - 0500 | 11240 | 899374 | GOT LOSSES WHILE CEMENTING 9"5/8 CSG | CMT | NA |  | 07/08/2022 | SSA-5859 | 24 | HWYH-1222
590 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SSA-5914 | Hrs | WDYH-80
591 | FOT | WUD | 71 | 05 Jul 0200 - 0230 | 16235 | 899296 | OBSERVED DROP IN PRESSURE OF 1,000 PSI. POOH & CHECK BHA. FOUND 5-7/8" HOLE CURVE BHA TWISTED OFF FROM THE PIN OF 2ND WFD FLOAT SUB. | BHA | FV |  | 07/08/2022 | SSA-5914 | 21.5 | WDYH-80
592 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/08/2022 | SSA-5971 | Hrs | HRDH-2247
593 | FOT | BAW | 2.5 | 07 Jul 0330 - 0600 | 14108 | 899338 | LOGGING TOOLS NOT RESPONDING WHILE TAKING FORMATION PRESSURE AT 14108'. | TF | WLT |  | 07/08/2022 | SSA-5971 | 1 | HRDH-2247
594 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | ADC-50 | Hrs | SFNY-1176
595 | FRFM | ARM | 86.25 | 06 Jul 1445 - 0500 | 3801 | 899340 | AT 3801', LOST COMPLETE CIRCULATION WITH 89 PCF WBM. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS. | LCIR | NA |  | 07/09/2022 | ADC-50 | 24 | SFNY-1176
596 | 6844 |  | D | N |  | TDS | DRILLED 6-1/8" HOLE SECTION W/SLB 6-1/8" ROTARY/MWD DRLG BHA TO TD AT 6,844 FT WITH TOTAL LOSS CIRC AND USING WGS.- CONTROL PARAMETERS TILL BHA OUT OF 7" LINER SHOE.- CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS.- PUMPED 30 BBLS HVP EVERY SINGLE DRILLED.- BACKREAM & REAM DOWN FULL STD WITH FULL PARAMETERS.- WOB: -10 KLB, RPM: 40, TRQ: 2-4 FT-LBS- FR: 290 GPM, SPP:1700 PSI | 6625 |  | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
597 | 6844 |  | CIRC | N |  | MPMP | SWEPT HOLE WITH TANDEM 30 BBL HI-VIS MUD CIRC HOLE. - CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS.- 290 GPM, PRESS: 1,910 PSI, 40-60 RPM TQ 4 - 6 KLB-FT . | 6844 |  | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
598 | 6844 | 6456 | ST | N |  | STDP | HPJSM. POOH & WIPER TRIP 6-1/8" BHA ON ELEVATOR FROM BTM @6,844 FT TO 6,456 FT (SHOE). WELL IN GOOD CONDITION.- CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS. | 6844 | 6844 | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
599 | 6844 | 6844 | ST | N |  | STDP | RIH BACK 6-1/8" BHA ON ELEVATOR AND TAGGED BOTTOM AT 6,844 FT. - CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS.- WASH DOWN LAST STD TO BTM- OPEN HOLE IN GOOD CONDITION | 6844 | 6456 | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
600 | 6844 |  | CIRC | N |  | MPMP | PUMPED WITH TANDEM 30 BBL HI-VIS MUD CIRC HOLE. - CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS.- 290 GPM, PRESS: 1,910 PSI, 40-60 RPM TQ 2 - 4 KLB-FT | 6844 |  | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
601 | 6844 | 6456 | TO | N |  | STDP | HPJSM. POOH 6-1/8" BHA ON ELEVATOR FROM BTM @6,844 FT TO 6,456 FT (SHOE). WELL IN GOOD CONDITION.- CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS. | 6844 | 6844 | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
602 | 6844 | 1118 | TO | N |  | STDP | CONTINUE POOH 6-1/8" BHA DRLG BHA ON ELEVATOR F/6,456 FT TO TOP OF BHA @ 1,118 FT.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
603 | 6844 | 0 | TO | N |  | BHA | CONTINUE POOH 6-1/8" BHA DRLG BHA ON ELEVATOR F/1,118 FT TO SURFACE.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 1118 | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
604 | 6844 |  | HT | N |  | BHA | HPJSM, L/D 6-1/8" ROTARY BHA, L/D MWD & PDC BIT.- BIT DULL GRADING : 1-2-WT-A-X-I-BT-TD- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SDM | 07/09/2022 | ADC-53L | DRLG | HRDH-530
605 | 6844 |  | RR | N |  | TDS | SERVICE TOP DRIVE.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/09/2022 | ADC-53L | DRLG | HRDH-530
606 | 6844 |  | PJSM | E | 3625 | NA | HPJSM WITH ALL INVOLVED CREW, DISCUSS RISKS, MITIGATIONS & DISTRIBUTE THE TASKS AND THE GOOD COMMUNICATE BETWEEN ALL CREWS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/09/2022 | ADC-53L | LOG | HRDH-530
607 | 6844 |  | OTH | E | 3625 | NA | P/U & M/U 1ST LOGGING RUN FMI/PPC/GR ON TLC & RIH TO 63 FT. - CHECK TLC TOOLS ON SURFACE, OK.- TOOL LENGTH: 63.67 FT. MAX TOOL OD: 5 INCHES.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | SWL | 07/09/2022 | ADC-53L | LOG | HRDH-530
608 | 6844 | 2780 | TI | E | 3625 | STDP | RIH 1ST LOGGING RUN FMI/PPC/GR ON TLC ON 4" DP F/ 63 FT TO 2780 FT W/ CONTROL SPEED. - FILL UP STRING EVERY 10 STANDS. DRIFT ALL STANDS RIH WITH 2.25" DRIFT.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 | 63 | RIG | 07/09/2022 | ADC-53L | LOG | HRDH-530
609 | 5.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 5.5 | 3625 | 09 Jul 0000 | 07/09/2022 | ADC-53L | Type | HRDH-530
610
611
612 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | ADC-56L | Hrs | UTMN-3069
613 | SCSG | TK3 | 5.75 | 08 Jul 0145 - 0730 | 2655 | 899426 | WHILE WORKING CASING STRING AT 2,655' HAD PRESSURE SHOOT UP TO 550 PSI & NO MOVEMENT UP/DOWN & NO CIRCULATION. GET STUCKED . | STUK | CSG |  | 07/09/2022 | ADC-56L | 2.5 | UTMN-3069
614 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | ADC-62L | Hrs | ANDR-745
615 | HERR | RIG | 508 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/09/2022 | ADC-62L | 24 | ANDR-745
616 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | ADES-144 | Hrs | UTMN-3152
617 | XTTE | SCM | 2 | 09 Jul 2200 - 0000 | 12122 | 899429 | CMT PUMP UNIT MANIFOLD IS LEAKING. EXCESSIVE TIME TO REPAIR AND PRESSURE TEST. | TF | PUMP |  | 07/09/2022 | ADES-144 | 2 | UTMN-3152
618 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | ADES-173 | Hrs | UTMN-1964
619 | FOT | RIG | .75 | 09 Jul 1900 - 1945 | 200 | 899502 | EXCESS TIME WHILE TRIPPING OUT OF HOLE DUE TO IRON ROUGHNECK DOWN. | RR | RSYS |  | 07/09/2022 | ADES-173 | .75 | UTMN-1964
620 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | AOD-111 | Hrs | MRJN-728
621 | UVLC | ARM | 4.5 | 09 Jul 1115 - 1545 | 14890 | 899513 | WHILE DRILLING 6-1/8" HOLE AT 14,890 FT, HAD SEVERE LOSSES (DYNAMIC LOSSES: 250 BPH / STATIC LOSSES: 80 BPH). | LCIR | NA |  | 07/09/2022 | AOD-111 | 4.5 | MRJN-728
622 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | ARO-3004 | Hrs | MRJN-2060
623 | FOT | RIG | 3.25 | 09 Jul 0800 - 1115 | 9578 | 899500 | ISSUE WITH LINK-TILT CONTROL DUMP VALVES. DISCOVERED FAILED SOLENOID VALVE | RR | TDS |  | 07/09/2022 | ARO-3004 | 3.25 | MRJN-2060
624 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | DPS-4 | Hrs | MDRK-63
625 | NARW | ARM | 53.75 | 07 Jul 2000 - 0500 | 5300 | 899482 | TAKE SLACK OFF WEIGHT AT 5300' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS. | TH | NA |  | 07/09/2022 | DPS-4 | 24 | MDRK-63
626 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | DPS-44 | Hrs | UTMN-3174
627 | SRVC | ITS | 2.5 | 09 Jul 1530 - 1800 | 11929 | 899501 | ASSIGNED TRS COMPANY "ITS" COULD NOT HANDLE 4-1/2" UPPER COMPLETION JOB, MEANWHILE WAIT ON ODFJELL ALTERNATE COMPANY TO ARRIVE ON LOCATION. | WO | NA |  | 07/09/2022 | DPS-44 | 2.5 | UTMN-3174
628 | 7857 |  | D | N |  | RSS | DRILLING AHEAD 8 1/2" LATERAL SECTION L-0-1 F/ 7,734' T/ 7,857' W/ 75 PCF OBM, FULL RETURN.WASH UP AND REAM DOWN ONE SINGLE EVERYSTAND.SWEEP HOLE WITH 10 BBL LV & 20 BBL HW TANDEM PILL EVERY 45 FT. | 7734 |  | SPS | 07/09/2022 | DQ-57L | DRLG | KHRS-399
629 | 7857 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH 15 / 30 BBLS LO-VIS / HI-WT-VIS PILLS TWICE, CHC WITH 550 GPM @ 3,170 PSI & 100% RETURNS.MW IN = MW OUT = 75 PCF OBMFLOW CHECK: WELL STATIC. | 7857 |  | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
630 | 7857 | 6400 | TO | N |  | BHA | WIPER TRIP: POOH WITH 8 1/2" ICRUISE RSS/ LWD ASSY FROM 7,857' TO 6,400' WHILE RE-LOG W/ 6 3/4" LITHOSTARMONITOR WELL ON TRIP TANK, WELL STATICFLOW CHECK, WELL STATIC. | 7857 | 7857 | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
631 | 7857 | 7857 | TI | N |  | BHA | RIH W/ 8 1/2" ICRUISE RSS/ LWD ASSY F/ 6,400' T/7,857'. MONITOR WELL ON TRIP TANK, WELL STATIC | 7857 | 6400 | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
632 | 7857 |  | CIRC | N |  | MPMP | DISPLACE WELL WITH 500 BBLS 75 PCF SOLID FREE BRINE, MWT IN/ OUT 75 PCF.FLOW CHECK: 6 BBLS STATIC LOSSES | 7857 |  | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
633 | 7857 | 7321 | TO | N |  | BHA | POOH WITH 8 1/2" ICRUISE RSS/ LWD F/ 7,857 FT T/7,321 FT (5 STDS)KEEP RUNNING TRIP TANK WITH 75 PCF SOLID FREE BRINE, 6 BBLS STATIC LOSSSSFLOW CHECK 6 BBLS STATIC LOSSSS | 7857 | 7857 | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
634 | 7857 | 5570 | TO | N |  | BHA | POOH WITH 8 1/2" ICRUISE RSS/ LWD F/ 7,321' T/ 5,570 FT KEEP RUNNING TRIP TANK WITH 75 PCF SOLID FREE BRINEFLOW CHECK, 4 BBLS STATIC LOSSES | 7857 | 7321 | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
635 | 7857 | 308 | TO | N |  | BHA | POOH WITH 8 1/2" ICRUISE RSS/ LWD F/ 5,570 FT T/ 308 FT KEEP RUNNING TRIP TANK WITH 63 PCF SOLID FREE WATER, 4BBLS STATIC LOSSESFLOW CHECK: WELL STATIC | 7857 | 5570 | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
636 | 7857 | 0 | LDP | N |  | BHA | L/D 6 3/4 WDF DRILLING JAR, 2 JTS X 5" HWDP | 7857 | 308 | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
637 | 7857 |  | PJSM | N |  | NA | HPJSM, RETRIEVE RADIOACTIVE SOURCE,DOWNLOAD LWD DATA. | 7857 |  | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
638 | 7857 | 0 | LDP | N |  | BHA | L/D 8 1/2" ICRUISE RSS/ LWD DRILLING BHA. | 7857 | 0 | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
639 | 7857 |  | PJSM | N | 3565 | NA | (OOS) HPJSM, P/U & M/U HES WIRELINE CALIPER LOGGING TOOLS STRING, CHECKED CABLEHEAD. LATCHED WITH TOOLS & CHECKED SIGNAL ANDTOOLS AT SURFACE# OK. KEEP RUNNING TRIP TANK WITH 75 PCF SOLID FREEBRINE, 4 BBLS STATIC LOSSES. | 7857 |  | RIG | 07/09/2022 | DQ-57L | DRLG | KHRS-399
640 | 7857 | 4445 | LOG | N | 3565 | CORRL | (OOS) RIH W/ HES WIRELINE 6-ARM MECHANICAL CALIPER LOGGING TOOLS STRING ON 5" DP T/ 4,445'DRIFT 5" DP WHILE RIH, DRIFT SIZE 3.18" APIDRIFT.HPJSM, CIRCULATE 1.2 STRING VOLUME(82 BBLS) WITH 75 PCF VISC BRINE WITH 4.0BPM/200 PSI R/U HES W/LSHEAVES & SPLIT BUSHING.P/U & M/U HES SIDE ENTRY SUB & CONNECT TDS. | 7857 | 0 | HSL | 07/09/2022 | DQ-57L | LOG | KHRS-399
641 | 7857 | 7857 | LOG | N | 3565 | CORRL | (OOS)RIH WITH CABLE HEAD TO LATCH TOP OF LOGGINGTOOLS..ONGOING | 7857 | 4445 | HSL | 07/09/2022 | DQ-57L | LOG | KHRS-399
642 | 10 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RIH W/ IMAGE CALIPER LOG | 8 | 3565 | 03 Jul 1200 | 07/09/2022 | DQ-57L | Type | KHRS-399
643
644
645 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | ED-85A | Hrs | ZULF-2063
646 | FOT | RIG | 5 | 09 Jul 0000 - 0500 | 8793 | 899485 | WASH PIPE LEAKAGE | RR | TDS |  | 07/09/2022 | ED-85A | 5 | ZULF-2063
647 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | ENSCO-54 | Hrs | ABSF-17
648 | STCT | ARM | 78 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/09/2022 | ENSCO-54 | 24 | ABSF-17
649 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | MP-1 | Hrs | MRJN-78
650 | FOT | BHI | .5 | 09 Jul 0900 - 0930 | 7055 | 899498 | LOSS OF COMMUNICATION WITH THE RSS. TROUBLE SHOOT. DECISION TO POH EARLY FOR PLANNED BHA CHANGE OUT. | BHA | RSS |  | 07/09/2022 | MP-1 | .5 | MRJN-78
651 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | NBR-115S | Hrs | HWYH-1220
652 | FOT | WCR | 2 | 09 Jul 0500 - 0700 | 2208 | 899483 | TUBING TONGS NOT RELEASING FROM STRING | TF | CTRQ |  | 07/09/2022 | NBR-115S | 2 | HWYH-1220
653 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | NBR-263S | Hrs | QTIF-736
654 | UVLC | ARM | 376.25 | 22 Jun 0630 - 0415 | 8452 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/09/2022 | NBR-263S | 8 | QTIF-736
655 | FOT | RIG | 6 | 09 Jul 0500 - 1100 | 10000 | 899512 | LEAK ON THE FLANGE BETWEEN MUD CROSS & UPPER PIPE RAMS DUE TO RING GASKET. | BOP | BOP |  | 07/09/2022 | NBR-654S | 6 | HRDH-1150
656 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | NBR-654S | Hrs | HRDH-1150
657 | FOT | RIG | .5 | 09 Jul 0215 - 0245 | 1300 | 899487 | IRON ROUGHNECH OIL LEAKING | RR | SLIPS |  | 07/09/2022 | NBR-654S | .5 | HRDH-1150
658 | FOT | RIG | 6 | 09 Jul 0500 - 1100 | 10000 | 899512 | LEAK ON THE FLANGE BETWEEN MUD CROSS & UPPER PIPE RAMS DUE TO RING GASKET. | BOP | BOP |  | 07/09/2022 | NBR-654S | 6 | HRDH-1150
659 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | PA-622S | Hrs | UTMN-3600
660 | HERR | ITS | 77 | 06 Jul 2330 - 0500 | 3200 | 899295 | WHILE DISPLACING CEMENT, X-OVER CONNECTION JUMPED OUT 28 FT BELOW ROTARY TABLE LEAVING THE CEMENT INSIDE THE CASING. | JF | CTRQ |  | 07/09/2022 | PA-622S | 24 | UTMN-3600
661 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SINO-15L | Hrs | ANDR-420
662 | LCRW | TK1 | 7 | 09 Jul 2200 - 0500 | 5606 | 899430 | DOWN TIME ON HALLIBURTON LSTK1 DUE TO STUCK PIPE. | STUK | STRG |  | 07/09/2022 | SINO-15L | 7 | ANDR-420
663 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SINO-27N | Hrs | KHRS-672
664 | FOT | INW | 9.5 | 08 Jul 2100 - 0630 | 5400 | 899497 | WORKING ON RETRIEVING 2-7/8" ME-PLUG W/O SUCCESS. | TF | BP |  | 07/09/2022 | SINO-27N | 1.5 | KHRS-672
665 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SINO-47 | Hrs | HRDH-1351
666 | FOT | BAW | 19 | 08 Jul 1500 - 1000 | 14470 | 899492 | FAILLURE OF XMAC (SONIC) TOOL DURING RUN#2. | TF | WLT |  | 07/09/2022 | SINO-47 | 5 | HRDH-1351
667 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SND-2001 | Hrs | UTMN-2329
668 | FOT | HWP | 11.25 | 09 Jul 1745 - 0500 | 19000 | 899428 | LOST SIGNAL DUE TO DOWNHOLE TOOLS FAILURE. | TF | WLT |  | 07/09/2022 | SND-2001 | 11.25 | UTMN-2329
669 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SND-2007 | Hrs | AWTD-104001
670 | FOT | RIG | 2 | 09 Jul 0500 - 0700 | 14610 | 899486 | WHILE PRESSURE TESTING OBSERVED LEAK BETWEEN DSA & TBGS POOL. | BOP | BOP |  | 07/09/2022 | SND-2007 | 2 | AWTD-104001
671 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SND-2008 | Hrs | HRDH-1812
672 | STDP | RIG | 115.5 | 05 Jul 0930 - 0500 | 14993 | 899272 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS, POH TO CHECK STRG FOUND STRG TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/09/2022 | SND-2008 | 24 | HRDH-1812
673 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SP-124 | Hrs | FDHL-141
674 | FOT | HCO | 1.5 | 09 Jul 1130 - 1300 | 50 | 899503 | PROBLEM WITH HALL PDHMS LOWER GUAGE SIGNAL | TF | PDHMS |  | 07/09/2022 | SP-124 | 1.5 | FDHL-141
675 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SP-258 | Hrs | JNAB-872212
676 | STBH | ARM | 120 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/09/2022 | SP-258 | 24 | JNAB-872212
677 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SP-261 | Hrs | HZEM-160212
678 | HERR | EMC | 49.5 | 07 Jul 0500 - 0730 | 4006 | 899337 | AFTER RUNNING 13 3/8" CASING IN THE HOLE, WHILE WASHING DOWN TO LAND FMH PRESSURE SPIKED & RIG WAS UNABLE TO CIRCULATE. | JF | SCS |  | 07/09/2022 | SP-261 | 2.5 | HZEM-160212
679 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/09/2022 | SSA-5914 | Hrs | WDYH-80
680 | FOT | WUD | 80 | 05 Jul 0200 - 0500 | 16235 | 899296 | OBSERVED DROP IN PRESSURE OF 1,000 PSI. POOH & CHECK BHA. FOUND 5-7/8" HOLE CURVE BHA TWISTED OFF FROM THE PIN OF 2ND WFD FLOAT SUB. | BHA | FV |  | 07/09/2022 | SSA-5914 | 9 | WDYH-80
681 | SRVC | GOC | .5 | 10 Jul 2030 - 2100 | 18497 | 899506 | EXTRA TIME TAKEN FOR AL-GHAITH PULD MACHINE FOR RE-ARRANGING EQUIPMENT PRIOR TO START JOB. | WO | NA |  | 07/10/2022 | ADC-34 | .5 | UTMN-2316
682 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ADC-34 | Hrs | UTMN-2316
683 | SRVC | FMC | 1 | 10 Jul 1930 - 2030 | 18497 | 899505 | EXTRA TIME TAKEN FOR FRANKS, FAILURE TO PRE-INSPECT EQUIPMENT PRIOR TO RIG UP, RE-ARRANGE EQUIPMENT PRIOR TO STARTING JOB. | WO | NA |  | 07/10/2022 | ADC-34 | 1 | UTMN-2316
684 | SRVC | GOC | .5 | 10 Jul 2030 - 2100 | 18497 | 899506 | EXTRA TIME TAKEN FOR AL-GHAITH PULD MACHINE FOR RE-ARRANGING EQUIPMENT PRIOR TO START JOB. | WO | NA |  | 07/10/2022 | ADC-34 | .5 | UTMN-2316
685 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ADC-35 | Hrs | MAQL-5
686 | FOT | SWL | 5.5 | 10 Jul 2200 - 0330 | 8300 | 899537 | SLB IBC ( IMAGING BORE CONTROL) SUB FACING WRONG READINGS IN 4.5"CASING. | TF | WLT |  | 07/10/2022 | ADC-35 | 5.5 | MAQL-5
687 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ADC-43L | Hrs | UTMN-3118
688 | WOTO | PM1 | .75 | 10 Jul 0015 - 0100 | 255 | 899517 | CUMULATIVE NON PRODUCTIVE TIME DURING M/U SHOETRACK, DUE TO PRIMADRILL EQUIPMENT NOT WORKING. | WO | NA |  | 07/10/2022 | ADC-43L | .75 | UTMN-3118
689 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ADC-49 | Hrs | HWYH-1104
690 | FOT | RIG | 1 | 10 Jul 0100 - 0200 | 8770 | 899516 | WASH PIPE IS LEAKING, SET BACK ONE STD, CHANGE WASH PIPE WHILE CIRC. WITH CIRC. HEAD AND HARD LINES. | RR | CSYS |  | 07/10/2022 | ADC-49 | 1 | HWYH-1104
691 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ADC-50 | Hrs | SFNY-1176
692 | FRFM | ARM | 110.25 | 06 Jul 1445 - 0500 | 3801 | 899340 | AT 3801', LOST COMPLETE CIRCULATION WITH 89 PCF WBM. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS. | LCIR | NA |  | 07/10/2022 | ADC-50 | 24 | SFNY-1176
693 | 6844 | 6156 | TI | E | 3625 | STDP | RIH 1ST LOGGING RUN FMI/PPC/GR ON TLC ON 4" DP F/ 2780 FT TO LATCH POINT AT 6,156 FT AT CONTROL SPEED. - FILL UP STRING EVERY 10 STANDS. DRIFT ALL STANDS RIH WITH 2.25" DRIFT.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 2780 | RIG | 07/10/2022 | ADC-53L | LOG | HRDH-530
694 | 6844 |  | CIRC | E | 3625 | MPMP | CIRC 1.5 STRING VOLUME. MEANWHILE HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW.- FR: 200 GPM & PRESS: 150 PSI. - CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/10/2022 | ADC-53L | LOG | HRDH-530
695 | 6844 |  | OTH | E | 3625 | NA | R/U SLB WIRELINE SHEAVES. M/U SLB W/L CABLE S.E.S. & FEED THROUGH WIRE LINE CABLE.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/10/2022 | ADC-53L | LOG | HRDH-530
696 | 6844 |  | OTH | E | 3625 | NA | RIH WIRE LINE CABLE, LATCH INTO CONNECTOR AS PER SLB WIRELINE ENGINEER INSTRUCTION.- APPLY 300 PSI PUMP PRESS TO ASSIST IN LATCHING PROCESS AS PER SLB ENG.- LATCH INTO WET CONNECTOR PROFILE, FUNCTION TEST SLB TOOLS, OK.- PERFORM PULL TENSION TEST TO 3,200 LBS, OK.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/10/2022 | ADC-53L | LOG | HRDH-530
697 | 6844 | 6824 | TI | E | 3625 | STDP | RIH LOG #1 TOOLS FMI/PPC/GR ON TLC ON 4" DP F/ 6,156 FT TO 6,824 FT AT CONTROL SPEED. - CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6156 | RIG | 07/10/2022 | ADC-53L | LOG | HRDH-530
698 | 6844 | 6456 | LOG | E | 3625 | WLT | PERFORMED LOG #1 FMI/PPC/GR ON TLC AS PER SLB WIRELINE ENGINEER- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6824 | SWL | 07/10/2022 | ADC-53L | LOG | HRDH-530
699 | 6844 | 6156 | TO | E | 3625 | STDP | POOH LOG #1 TOOLS FMI/PPC/GR ON TLC ON 4" DP TO UNLATCH POINT AT 6,156 FT AT CONTROL SPEED. - CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/10/2022 | ADC-53L | LOG | HRDH-530
700 | 6844 |  | OTH | E | 3625 | NA | KEPT STRING STATIONARY INSIDE CASING SHOE AS PER WL ENGR INSTRUCTION WHILE ARAMCO RDD PROCESSING THE DATA.- DATA CONFIRMED BY ARAMCO RDD- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | SWL | 07/10/2022 | ADC-53L | LOG | HRDH-530
701 | 6844 |  | OTH | E | 3625 | NA | HPJSM, SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE & POOH WITH WL CABLE TO SURFACE. L/D SES AND WIRE LINE SHEAVES.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | SWL | 07/10/2022 | ADC-53L | LOG | HRDH-530
702 | 6844 | 63 | TO | E | 3625 | STDP | CONT'D POOH AT CONTROLLED SPEED W/ FMI/PPC/GR - TLC STRING ON 4" DP F/ 6,156 FT TO TOP OF LOGGING TOOLS @ 63 FT.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 | 6156 | RIG | 07/10/2022 | ADC-53L | LOG | HRDH-530
703 | 6844 |  | OTH | E | 3625 | NA | HPJSM, L/D SLB FMI/PPC/GR LOGGING TOOL.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | SWL | 07/10/2022 | ADC-53L | LOG | HRDH-530
704 | 6844 |  | HT | E | 3625 | BHA | HPJSM, P/U & M/U 8-1/2" CONTD. TRIP BHA AND RIH TO 357 FT.SMITH FV SN/ RK0350 W/ 6 X 18" NOZZLES.- FILL STRING.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | RIG | 07/10/2022 | ADC-53L | CT | HRDH-530
705 | 6844 | 3975 | TI | E | 3625 | STDP | CONTINUE RIH 6-1/8" BHA ON 4" DP'S STANDS FROM 357' TO 3975 FT. ON GOING AT REPORT TIME.- FILL STRING EVERY 20 STD RAN- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 | 357 | RIG | 07/10/2022 | ADC-53L | CT | HRDH-530
706 | 29.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/10/2022 | ADC-53L | Type | HRDH-530
707
708
709 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ADC-62L | Hrs | ANDR-745
710 | HERR | RIG | 532 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/10/2022 | ADC-62L | 24 | ANDR-745
711 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ADES-157 | Hrs | HRDH-1844
712 | FOT | ITS | 12.25 | 10 Jul 1645 - 0500 | 9738 | 899575 | WHILE RIH W/SLICK LINE TO DRIFT BEFORE PICK UP THE UPPER R NIPPLE ASSY. WE TAGGED @ 4,171' WITH 3.795" & 3.75" DRIFTS. | TF | TTRQ |  | 07/10/2022 | ADES-157 | 12.25 | HRDH-1844
713 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ADM-337 | Hrs | MRJN-900
714 | FOT | SWL | 11.5 | 10 Jul 0630 - 1800 | 0 | 899489 | SCHLUMBERGER WIRELINE UNABLE TO COMMUNICATE THROUGH 1.69" CCL TOOLS BOTH THE PRIMARY AND BACK UP. | TF | WLT |  | 07/10/2022 | ADM-337 | 11.5 | MRJN-900
715 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ARO-4001 | Hrs | MRJN-538
716 | FOT | HCO | 3.25 | 10 Jul 1845 - 2200 | 745 | 899576 | DAMAGED HYDRAULIC FITTINGS ON THE ICV DRIVE MECHANISM ON THE SPOOLER. | TF | PDHMS |  | 07/10/2022 | ARO-4001 | 3.25 | MRJN-538
717 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | DPS-4 | Hrs | MDRK-63
718 | NARW | ARM | 77.75 | 07 Jul 2000 - 0500 | 5300 | 899482 | TAKE SLACK OFF WEIGHT AT 5300' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS. | TH | NA |  | 07/10/2022 | DPS-4 | 24 | MDRK-63
719 | 7857 | 300 | LOG | N | 3565 | CORRL | (OOS) RIH WITH CABLE HEAD TO 300' ABOVE LATCH POINTPUMP 10 BBL'S LOW SALINITY PILL,DISPLACE W/58 BBL'S OF 75 PCF BRINE. CONTINUE RIH WITH CABLE HEAD WITH 9BPM PUMPING RATE @ 630 PSI INSTALLED CABLE CLAMP AND TENSION TEST SAME TO 3,500 LB FOR 10 MIN# OK, INSTALL 3RD SHEAVE WHEEL 3RD SHEAVE WHEEL. | 7857 | 0 | HWP | 07/10/2022 | DQ-57L | LOG | KHRS-399
720 | 7857 | 6700 | LOG | N | 3565 | CORRL | (OOS)RIH W/ HES WIRELINE CALIPER LOGGING TOOLS STRING ON 5" DP/HWDP F/4,445' T/ 6,700'M/U HES CIRCULATION SUB W/ MUD SCREEN &FILL STRING EVERY 10 STANDS WITH 75PCF SOLIDFREE BRINE.KEEP RUNNING TRIP TANK WITH 75 PCF SOLID FREE BRINE, 2 BBLS STATIC LOSSES. | 7857 | 4445 | HWP | 07/10/2022 | DQ-57L | LOG | KHRS-399
721 | 7857 | 5479 | LOG | N | 3565 | CORRL | (OOS) ACTIVATE LOGGING TOOLS, POOH LOGGING UP MAIN PASS F/ 6,700'' T/ 5,479' KEEP RUNNING TRIP TANK WITH 75 PCF SOLID FREE BRINE, 2 BBLS STATIC LOSSES. | 7857 | 6700 | HWP | 07/10/2022 | DQ-57L | LOG | KHRS-399
722 | 7857 | 5800 | LOG | N | 3565 | CORRL | (OOS) CLOSE CALIPER ARMS, RIH W/ LOGGING TOOLS F/ 5,479' T/ 5,800' | 7857 | 5479 | HWP | 07/10/2022 | DQ-57L | LOG | KHRS-399
723 | 7857 | 5580 | LOG | N | 3565 | CORRL | (OOS) ACTIVATE LOGGING TOOLS, POOHLOGGING UP REPEAT PASS F/ 5,800' T/ 5,580' KEEP RUNNING TRIP TANK WITH 75 PCF SOLID FREE BRINE, 2 BBLS STATIC LOSSES. | 7857 | 5800 | HWP | 07/10/2022 | DQ-57L | LOG | KHRS-399
724 | 7857 | 4445 | LOG | N | 3565 | CORRL | (OOS) CLOSE CALIPER ARMS, POOH W/ LOGGING TOOLS F/ 5,580' T/ 4,445'. KEEP RUNNING TRIP TANK WITH 75 PCF SOLID FREE BRINE, 2 BBLS STATIC LOSSES. | 7857 | 5580 | HWP | 07/10/2022 | DQ-57L | LOG | KHRS-399
725 | 7857 | 0 | LOG | N | 3565 | CORRL | (OOS) UNLATCH CABLE, POOH W/ CABLE TO SURFACE, R/D SES & E/WL SHEAVES. POOH W/ HES WIRELINE CALIPER LOGGING TOOLS STRING ON 5" DP F/ 4,445' TO SURFACE.L/D HES WIRELINE CALIPER LOGGING TOOLS. | 7857 | 4445 | HWP | 07/10/2022 | DQ-57L | LOG | KHRS-399
726 | 7857 |  | PJSM | N |  | NA | HPJSM, P/U & M/U 8 1/2" STIFF REAMING BHA AS FOLLOWS: 8 1/2" WELDED TRI-CONE BIT SN: 836683R,(HES) 8 1/2" NEAR BIT REAMER (NBR), WITH FLOAT VALVE INSERTED, SAWAFI SN: 14491. 1 JT X 6 1/4" D/C. 8 7/16" GDR, SAWAFI, SN: 160559 2 JT'S X 6 1/4" D/C. 8 1/2" STRING RR, SAWAFI, SN: 11257 1 JT X 6 1/4" D/C. 3 JT'S X 5" HWDP'S. 6 1/2" JAR WFD, SN: 17602147. 2 JT'S X 5" HWDP'S. KEEP RUNNING TRIP TANK WITH 75 PCF SOLID FREE BRINE, 4 BBLS STATIC LOSSES. | 7857 |  | RIG | 07/10/2022 | DQ-57L | DRLG | KHRS-399
727 | 7857 | 5515 | TI | N |  | BHA | RIH WITH 8 1/2" STIFF REAMING BHA ON 5"DP/HWDP F/ 0 T/ 1,140'. P/U & M/U 4 X 9-5/8" STRING MEGAMAGNET. RIH WITH 8 1/2" STIFF REAMING BHA ON 5"DP/HWDP TO 5,515' | 7857 | 0 | RIG | 07/10/2022 | DQ-57L | DRLG | KHRS-399
728 | 7857 | 6740 | TI | N |  | BHA | M/U TDS & PASSING 9 5/8" T.O.W @ 5,589' WASHING DOWN T/ 5,610'. CONTINUE RIH WITH 8 1/2" STIFF REAMING BHA ON 5" DP/HWDP WASH & REAM F/ 5,610' T/6,740'. | 7857 | 5515 | RIG | 07/10/2022 | DQ-57L | DRLG | KHRS-399
729 | 7857 |  | CIRC | N |  | MPMP | SWEEP HOLE W/ 50 BBL HI-VIS PILL & CHC WITH 550 GPM / 870 PSI...ONGOING | 7857 |  | RIG | 07/10/2022 | DQ-57L | DRLG | KHRS-399
730 | 22.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RIH W/ CALIPER LOG | 12.5 | 3565 | 03 Jul 1200 | 07/10/2022 | DQ-57L | Type | KHRS-399
731
732
733 | FOT | RIG | 17 | 10 Jul 1200 - 0500 | 8838 | 899554 | MALFACTION ON DRAWWORK RESISTOR GRID | RR | DWKS | 899485 | 07/10/2022 | ED-85A | 17 | ZULF-2063
734 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ED-85A | Hrs | ZULF-2063
735 | FOT | RIG | 28.25 | 09 Jul 0000 - 1115 | 8793 | 899485 | WASH PIPE LEAKAGE | RR | TDS |  | 07/10/2022 | ED-85A | 6.25 | ZULF-2063
736 | FOT | RIG | 17 | 10 Jul 1200 - 0500 | 8838 | 899554 | MALFACTION ON DRAWWORK RESISTOR GRID | RR | DWKS | 899485 | 07/10/2022 | ED-85A | 17 | ZULF-2063
737 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | ENSCO-54 | Hrs | ABSF-17
738 | STCT | ARM | 102 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/10/2022 | ENSCO-54 | 24 | ABSF-17
739 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | EXL-IVA | Hrs | SFNY-1650
740 | FOT | RIG | 1.25 | 10 Jul 1330 - 1445 | 6039 | 899515 | IBOP VALVE WOULD NOT FUNCTION PROPERLY (COULD NOT CLOSE PNEUMATICALLY) DUE TO FAILED ACTUATOR CAM. | RR | TDS |  | 07/10/2022 | EXL-IVA | 1.25 | SFNY-1650
741 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | JACK-203 | Hrs | HZEM-849
742 | LCRW | ARM | 13.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/10/2022 | JACK-203 | 13.5 | HZEM-849
743 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | NBR-20S | Hrs | HMYM-433514
744 | FPMP | RIG | 3.5 | 10 Jul 0900 - 2300 | 13075 | 899504 | EXCESSIVE NOISE FROM MUD PUMPS. | RR | MPMP |  | 07/10/2022 | NBR-20S | 3.5 | HMYM-433514
745 | FOT | RIG | .5 | 10 Jul 1230 - 1300 | 8598 | 899518 | RIG POWER BLACK OUT, TROUBLESHOOTING RIG POWER & RE START ELECTRICAL RIG OPERATIONAL SYSTEM, | RR | PSYS |  | 07/10/2022 | NBR-263S | .5 | QTIF-736
746 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | NBR-263S | Hrs | QTIF-736
747 | UVLC | ARM | 378.25 | 22 Jun 0630 - 0830 | 8550 | 898674 | OBSERVE 20 BPH STATIC LOSSES AFTER KILLING, DYNAMIC LOSSES 180 BPH AT 350 GPM. SPOT LCM TO CURE LOSSES, NO SUCCESS, SPOT CMT PLUG. | LCIR | NA |  | 07/10/2022 | NBR-263S | 2 | QTIF-736
748 | FOT | RIG | .5 | 10 Jul 1230 - 1300 | 8598 | 899518 | RIG POWER BLACK OUT, TROUBLESHOOTING RIG POWER & RE START ELECTRICAL RIG OPERATIONAL SYSTEM, | RR | PSYS |  | 07/10/2022 | NBR-263S | .5 | QTIF-736
749 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | NBR-633S | Hrs | HRDH-2234
750 | HFFT | HCM | 11.75 | 10 Jul 1715 - 0500 | 0 | 899431 | WHILE HALLIBURTON BATCH MIXING CEMENT SLURRY, HAD HALLIBURTON COMPRESSOR STOP WORKING & TRY TO FIX THE ISSUE WITHOUT SUCCESS, POOR PLANNING FROM HALLIBURTON FOR THE CRITICAL JOB. | CMT | NA |  | 07/10/2022 | NBR-633S | 11.75 | HRDH-2234
751 | FOT | RIG | 2.75 | 10 Jul 1845 - 2130 | 9821 | 899491 | OBSERVED LEAKS OF OIL ON TOP DRIVE (ACTUATOR VALVE) | RR | TDS |  | 07/10/2022 | NBR-654S | 2.75 | HRDH-1150
752 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | NBR-654S | Hrs | HRDH-1150
753 | FOT | RIG | 1.25 | 10 Jul 1500 - 1615 | 9600 | 899490 | TRIP IN SPEED DECREASED DUE TO IRON ROUGHNECK ISSUES | RR | SLIPS |  | 07/10/2022 | NBR-654S | 1.25 | HRDH-1150
754 | FOT | RIG | 2.75 | 10 Jul 1845 - 2130 | 9821 | 899491 | OBSERVED LEAKS OF OIL ON TOP DRIVE (ACTUATOR VALVE) | RR | TDS |  | 07/10/2022 | NBR-654S | 2.75 | HRDH-1150
755 | FPMP | RIG | .75 | 10 Jul 0145 - 0230 | 8294 | 899573 | CAP GASKETS LEAKING ON MUD PUMP | RR | MPMP |  | 07/10/2022 | NBR-783S | .75 | NJYN-93
756 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | NBR-783S | Hrs | NJYN-93
757 | FOT | RIG | 1.25 | 10 Jul 1830 - 1945 | 8160 | 899572 | MUD PUMP CAP GASKET LEAKING | RR | MPMP |  | 07/10/2022 | NBR-783S | 1.25 | NJYN-93
758 | FPMP | RIG | .75 | 10 Jul 0145 - 0230 | 8294 | 899573 | CAP GASKETS LEAKING ON MUD PUMP | RR | MPMP |  | 07/10/2022 | NBR-783S | .75 | NJYN-93
759 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | PA-622S | Hrs | UTMN-3600
760 | HERR | ITS | 100.75 | 06 Jul 2330 - 0445 | 3200 | 899295 | WHILE DISPLACING CEMENT, X-OVER CONNECTION JUMPED OUT 28 FT BELOW ROTARY TABLE LEAVING THE CEMENT INSIDE THE CASING. | JF | CTRQ |  | 07/10/2022 | PA-622S | 23.75 | UTMN-3600
761 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | PA-70S | Hrs | MDRK-64
762 | FOT | WLH | 881.75 | 30 May 1800 - 0500 | 15492 | 897183 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP. | TF | LLAP |  | 07/10/2022 | PA-70S | 24 | MDRK-64
763 | SRVC | WCR | 2.5 | 10 Jul 2200 - 0030 | 1881 | 899574 | WFD DAMAGED THREADS WHILE MAKING UP. BREAK OUT AND INSPECT, REPLACE 2 JTS. | WO | NA |  | 07/10/2022 | RM-74A | 2.5 | HSBH-68
764 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | RM-74A | Hrs | HSBH-68
765 | SRVC | WCR | 1 | 10 Jul 0715 - 0815 | 1881 | 899488 | WEATHERFORD 30" SAFETY CLAMP NOT FIT FOR PURPOSE. | WO | NA |  | 07/10/2022 | RM-74A | 1 | HSBH-68
766 | SRVC | WCS | 1 | 10 Jul 0400 - 0500 | 1881 | 899536 | WFD CSG TONG MALFUNCTION. CHANGE OUT SAME | WO | NA |  | 07/10/2022 | RM-74A | 1 | HSBH-68
767 | SRVC | WCR | 2.5 | 10 Jul 2200 - 0030 | 1881 | 899574 | WFD DAMAGED THREADS WHILE MAKING UP. BREAK OUT AND INSPECT, REPLACE 2 JTS. | WO | NA |  | 07/10/2022 | RM-74A | 2.5 | HSBH-68
768 | FOT | BCT | 1.5 | 10 Jul 1300 - 1430 | 0 | 899553 | FAILED COIL TUBING VALVE AT KILL LINE WHILE ATTEMPTING TO PERFROM LOW AND HIGH PRESSURE TESTING. OBSERVE PRESSURE DROPPING. REPLACED VALVE AND PRESSURE TESTED. | TF | CTAC |  | 07/10/2022 | SDA | 1.5 | MRJN-739
769 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SDA | Hrs | MRJN-739
770 | SRVC | BCT | 4.5 | 10 Jul 0830 - 1300 | 0 | 899552 | PERFORMED SLACK MANITENANCE ON BAKER TELECOIL WIRE. SCHEDULING SLACK MAINTENANCE HAS NOT BEEN COMMUNICATED TO RIG FOREMEN. | WO | NA |  | 07/10/2022 | SDA | 4.5 | MRJN-739
771 | FOT | BCT | 1.5 | 10 Jul 1300 - 1430 | 0 | 899553 | FAILED COIL TUBING VALVE AT KILL LINE WHILE ATTEMPTING TO PERFROM LOW AND HIGH PRESSURE TESTING. OBSERVE PRESSURE DROPPING. REPLACED VALVE AND PRESSURE TESTED. | TF | CTAC |  | 07/10/2022 | SDA | 1.5 | MRJN-739
772 | LCRW | TK1 | 11.5 | 10 Jul 1730 - 0500 | 5606 | 899534 | DRESSING WINDOW AFTER STUCK IN IT WITH DRILLING BHA | STUK | STRG |  | 07/10/2022 | SINO-15L | 11.5 | ANDR-420
773 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SINO-15L | Hrs | ANDR-420
774 | LCRW | TK1 | 19.5 | 09 Jul 2200 - 1730 | 5606 | 899430 | DOWN TIME ON HALLIBURTON LSTK1 DUE TO STUCK PIPE. | STUK | STRG |  | 07/10/2022 | SINO-15L | 12.5 | ANDR-420
775 | LCRW | TK1 | 11.5 | 10 Jul 1730 - 0500 | 5606 | 899534 | DRESSING WINDOW AFTER STUCK IN IT WITH DRILLING BHA | STUK | STRG |  | 07/10/2022 | SINO-15L | 11.5 | ANDR-420
776 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SINO-46L | Hrs | SHYB-708
777 | FOT | BHI | 2 | 10 Jul 0300 - 0500 | 6901 | 899577 | LOSS SIGNAL WITH BCPM | BHA | MWD |  | 07/10/2022 | SINO-46L | 2 | SHYB-708
778 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SND-2001 | Hrs | UTMN-2329
779 | FOT | HWP | 35.25 | 09 Jul 1745 - 0500 | 19000 | 899428 | LOST SIGNAL DUE TO DOWNHOLE TOOLS FAILURE. | TF | WLT |  | 07/10/2022 | SND-2001 | 24 | UTMN-2329
780 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SND-2005 | Hrs | MHKK-2
781 | FOT | RIG | .75 | 10 Jul 0415 - 0500 | 13150 | 899507 | DRILLER'S RIG WATCH SCREEN NOT WORKING, ELECTRICIAN TROUBLE SHOOT RIG WATCH SYSTEM (RE-BOOT SYSTEM). | RR | EDR |  | 07/10/2022 | SND-2005 | .75 | MHKK-2
782 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SND-2008 | Hrs | HRDH-1812
783 | STDP | RIG | 96 | 07 Jul 0500 - 0500 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS, POH TO CHECK STRG FOUND STRG TWISTED OFF AT 2ND DC ABOVE MILL | STUK | DP |  | 07/10/2022 | SND-2008 | 24 | HRDH-1812
784 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SP-124 | Hrs | FDHL-141
785 | FOT | ODJ | 1 | 10 Jul 0100 - 0200 | 3050 | 899535 | POWER TONG HYRDAULIC LEAKAGE | TF | CRT |  | 07/10/2022 | SP-124 | 1 | FDHL-141
786 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SP-258 | Hrs | JNAB-872212
787 | STBH | ARM | 144 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/10/2022 | SP-258 | 24 | JNAB-872212
788 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SSA-302 | Hrs | HRDH-2512
789 | WSHO | SJC | 5.25 | 10 Jul 2345 - 0500 | 1898 | 899532 | RIH WITH 16" BHA TO DRILL OUT CMT AND CLEAN OUT 18 5/8" CSG SHOE TRACK, FOUND CEMENT IS VERY SOFT AT SHOE TRACK AND WET CSG SHOE THOUGH CMT WAS IN PLACE FOR 36HRS. | CMT | CSG |  | 07/10/2022 | SSA-302 | 5.25 | HRDH-2512
790 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/10/2022 | SSA-5914 | Hrs | WDYH-80
791 | FOT | WUD | 98.75 | 05 Jul 0200 - 0200 | 16235 | 899296 | OBSERVED DROP IN PRESSURE OF 1,000 PSI. POOH & CHECK BHA. FOUND 5-7/8" HOLE CURVE BHA TWISTED OFF FROM THE PIN OF 2ND WFD FLOAT SUB. | BHA | FV |  | 07/10/2022 | SSA-5914 | 18.75 | WDYH-80
792 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | 095TE | Hrs | MNIF-226
793 | HERR | RIG | 9.75 | 11 Jul 1915 - 0500 | 9474 | 899579 | WHILE RIH INSIDE 7'' LINER, AT 9474' TAG OBSTRACTION, HAD S/W RESULTED TWO JOINTS BEND. | DSF | STRG |  | 07/11/2022 | 095TE | 9.75 | MNIF-226
794 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ADC-35 | Hrs | MAQL-5
795 | FOT | SWL | 1 | 11 Jul 1345 - 1445 | 30 | 899580 | TRY TO RIH WITH SLB CEMENT BOND LOGGING TOOLS, NOT ABLE TO PASS IN THE WELL, POOH, CHANGE POSITION OF CENTERLIZING SUB, OK PASSED, RIH. | TF | WLT |  | 07/11/2022 | ADC-35 | 1 | MAQL-5
796 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ADC-48 | Hrs | HRDH-2316
797 | UNKN | RIG | 24 | 11 Jul 0500 - 0500 | 0 | 899539 | HSE INCD | HSEI | NA |  | 07/11/2022 | ADC-48 | 24 | HRDH-2316
798 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ADC-50 | Hrs | SFNY-1176
799 | FRFM | ARM | 118.25 | 06 Jul 1445 - 1300 | 3801 | 899340 | AT 3801', LOST COMPLETE CIRCULATION WITH 89 PCF WBM. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS. | LCIR | NA |  | 07/11/2022 | ADC-50 | 8 | SFNY-1176
800 | 6844 | 6456 | TI | E | 3625 | STDP | CONTINUE RIH 6-1/8" BHA ON 4" DP'S STANDS FROM 3,975' TO 6,456 FT- FILL STRING EVERY 20 STD RAN- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 3975 | RIG | 07/11/2022 | ADC-53L | CT | HRDH-530
801 | 6844 | 6844 | RW | E | 3625 | BIT | REAM/WASH HOLE F/6456 FT AND TAGGED BOTTOM AT 6,844 FT.- 310 GPM, PRESS: 1,220 PSI, 100 RPM TQ 1 - 1.5 KLB-FT- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/11/2022 | ADC-53L | CT | HRDH-530
802 | 6844 |  | CIRC | E | 3625 | MPMP | PUMPED WITH TANDEM 30 BBL HI-VIS MUD CIRC HOLE. - CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS.- 310 GPM, PRESS: 1,220 PSI, 100 RPM TQ 1 - 1.5 KLB-FT | 6844 |  | RIG | 07/11/2022 | ADC-53L | CT | HRDH-530
803 | 6844 | 6456 | ST | E | 3625 | STDP | HPJSM. POOH 6-1/8" BHA ON ELEVATOR FROM BTM @6,844 FT TO 6,456 FT (SHOE). WELL IN GOOD CONDITION.- CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS. | 6844 | 6844 | RIG | 07/11/2022 | ADC-53L | CT | HRDH-530
804 | 6844 | 356 | TO | E | 3625 | STDP | CONTINUE POOH 6-1/8" BHA ON ELEVATOR F/6,456 FT TO TOP OF BHA @ 356 FT.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/11/2022 | ADC-53L | CT | HRDH-530
805 | 6844 |  | HT | E | 3625 | BHA | CONTINUED POOH 6-1/8" BHA ON ELEVATOR F/356 FT TO SURFACE. L/D BIT 9RR.- BIT GRADING: 1, 1, WT, A, E, NO, I, LOG- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/11/2022 | ADC-53L | CT | HRDH-530
806 | 6844 |  | RR | E |  | TDS | SERICED TDS. CLEANED AND CLEARED RIG FLOOR.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/11/2022 | ADC-53L | LOG | HRDH-530
807 | 6844 |  | PJSM | E |  | NA | HPJSM WITH ALL INVOLVED CREW, DISCUSS RISKS, MITIGATIONS & DISTRIBUTE THE TASKS AND THE GOOD COMMUNICATE BETWEEN ALL CREWS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/11/2022 | ADC-53L | LOG | HRDH-530
808 | 6844 |  | OTH | E |  | NA | P/U & M/U 2ND LOGGING RUN AIT/TLD/HGNS/MCFL/ADT/GR (TRIPLE-COMBO) ON TLC & RIH TO 86 FT. - CHECK TOOLS ON SURFACE, OK.- TOOL LENGTH: 86.18 FT. MAX TOOL OD: 5.0 INCHES.- RA SOURCE LOADED AT 15.30 HOURS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/11/2022 | ADC-53L | LOG | HRDH-530
809 | 6844 | 6156 | TI | E |  | STDP | RIH 2ND LOGGING RUN AIT/TLD/HGNS/MCFL/ADT/GR (TRIPLE-COMBO) ON TLC ON 4" DP F/ 86 FT TO 6,156 FT AT CONTROL SPEED. - FILL UP STRING EVERY 10 STANDS RAN- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 86 | RIG | 07/11/2022 | ADC-53L | LOG | HRDH-530
810 | 6844 |  | CIRC | E |  | MPMP | CIRC 1.5 STRING VOLUME. MEANWHILE HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW.- FR: 300 GPM & PRESS: 200 PSI. - CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/11/2022 | ADC-53L | LOG | HRDH-530
811 | 6844 |  | OTH | E |  | NA | R/U SLB WIRELINE SHEAVES. M/U SLB W/L CABLE S.E.S. & FEED THROUGH WIRE LINE CABLE.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/11/2022 | ADC-53L | LOG | HRDH-530
812 | 6844 |  | OTH | E |  | NA | RIH WIRE LINE CABLE, LATCH INTO CONNECTOR AS PER SLB WIRELINE ENGINEER INSTRUCTION.- APPLY 250 PSI PUMP PRESS TO ASSIST IN LATCHING PROCESS AS PER SLB ENG.- LATCH INTO WET CONNECTOR PROFILE, FUNCTION TEST SLB TOOLS, OK.- PERFORM PULL TENSION TEST TO 3,100 LBS, OK.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/11/2022 | ADC-53L | LOG | HRDH-530
813 | 6844 | 6824 | TI | E |  | STDP | RIH LOG #2 AIT/TLD/HGNS/MCFL/ADT/GR (TRIPLE-COMBO) ON TLC ON 4" DP F/ 6,156 FT TO 6,824 FT AT CONTROL SPEED. - CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6156 | RIG | 07/11/2022 | ADC-53L | LOG | HRDH-530
814 | 6844 | 6261 | LOG | E |  | WLT | PERFORMED LOG #2 AIT/TLD/HGNS/MCFL/ADT/GR (TRIPLE-COMBO) ON TLC F/6,824 FT TO 6,261 FT AS PER SLB WIRELINE ENGINEER- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6824 | SWL | 07/11/2022 | ADC-53L | LOG | HRDH-530
815 | 6844 |  | OTH | E |  | NA | KEPT STRING STATIONARY INSIDE CASING SHOE AS PER WL ENGR INSTRUCTION WHILE ARAMCO RDD PROCESSING THE DATA.- DATA CONFIRMED BY ARAMCO RDD- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | SWL | 07/11/2022 | ADC-53L | LOG | HRDH-530
816 | 6844 |  | OTH | E |  | NA | HPJSM, PULLED STRING TO 6,156 FT. SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE & POOH WITH WL CABLE. ON GOING AT REPORT TIME.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | SWL | 07/11/2022 | ADC-53L | LOG | HRDH-530
817 | 38.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 9 | 3625 | 09 Jul 0000 | 07/11/2022 | ADC-53L | Type | HRDH-530
818
819
820 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ADC-62L | Hrs | ANDR-745
821 | HERR | RIG | 556 | 18 Jun 0100 - 0500 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/11/2022 | ADC-62L | 24 | ANDR-745
822 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ADC-66L | Hrs | UTMN-3155
823 | FOT | SDM | 9.5 | 11 Jul 1330 - 0500 | 4670 | 899593 | MISCOMMUNICATION W/ RSS TOOL. | BHA | RSS |  | 07/11/2022 | ADC-66L | 9.5 | UTMN-3155
824 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ADES-144 | Hrs | UTMN-3152
825 | FOT | SPS | 4.5 | 11 Jul 0000 - 0500 | 12194 | 899538 | LOST MWD SIGNAL WHILE DRILLING AHEAD. | BHA | MWD |  | 07/11/2022 | ADES-144 | 4.5 | UTMN-3152
826 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ADES-157 | Hrs | HRDH-1844
827 | FOT | ITS | 17 | 10 Jul 1645 - 0945 | 9738 | 899575 | WHILE RIH W/SLICK LINE TO DRIFT BEFORE PICK UP THE UPPER R NIPPLE ASSY. WE TAGGED @ 4,171' WITH 3.795" & 3.75" DRIFTS. | TF | TTRQ |  | 07/11/2022 | ADES-157 | 4.75 | HRDH-1844
828 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | DPS-4 | Hrs | MDRK-63
829 | NARW | ARM | 101.75 | 07 Jul 2000 - 0500 | 5300 | 899482 | TAKE SLACK OFF WEIGHT AT 5300' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS. | TH | NA |  | 07/11/2022 | DPS-4 | 24 | MDRK-63
830 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | DPS-5 | Hrs | HRDH-2319
831 | FOT | HWP | 12.5 | 11 Jul 1200 - 0030 | 14195 | 899592 | HALLIBURTON W/L LOGGING UNIT DRUM FAILED TO POOH, WHILE TROUBLESHOOTING FOUND AN ISSUE WITH DRUM GEAR. | TF | WLT |  | 07/11/2022 | DPS-5 | 12.5 | HRDH-2319
832 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ED-85A | Hrs | ZULF-2063
833 | FOT | RIG | 41 | 10 Jul 1200 - 0500 | 8838 | 899582 | MALFACTION ON DRAWWORK RESISTOR GRID | RR | DWKS |  | 07/11/2022 | ED-85A | 24 | ZULF-2063
834 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | ENSCO-54 | Hrs | ABSF-17
835 | STCT | ARM | 126 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/11/2022 | ENSCO-54 | 24 | ABSF-17
836 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | EXL-IVA | Hrs | SFNY-1650
837 | FOT | RIG | 3.75 | 11 Jul 1645 - 2030 | 7015 | 899509 | WHILE DRILLING PRESSURE DROPPED FROM 3,271 PSI TO 2,476 PSI. SHUT DOWN PUMPS AND ISOLATE #1 PUMP. BROUGHT PUMPS BACK ONLINE, PRESURE CONTINUED TO DECLINE. SURFACE TESTED PUMPS, WOULD NOT HOLD PRESSURE. ISOLATED #3 PUMP, PUMP OK. BROUGHT #2 PUMP ONLINE, WOULD NOT PUMP FLUID. CIRCULATE WHILE GOING THROUGH PUMP #1 AND PUMP#2. | RR | MPMP |  | 07/11/2022 | EXL-IVA | 3.75 | SFNY-1650
838 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | JACK-203 | Hrs | HZEM-849
839 | LCRW | ARM | 37.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/11/2022 | JACK-203 | 24 | HZEM-849
840 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | NBR-263S | Hrs | QTIF-736
841 | FOT | SPS | 17.5 | 11 Jul 0500 - 2230 | 9022 | 899583 | IMPROPER COMMUNICATION WITH SPS GEO-TAP & MWD TOOLS, TOUBLE SHOOT WITH NO SUCCESS, POOH TO CHANGE FAILED TOOLS. | BHA | LWD |  | 07/11/2022 | NBR-263S | 17.5 | QTIF-736
842 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | NBR-633S | Hrs | HRDH-2234
843 | HFFT | HCM | 35.75 | 10 Jul 1715 - 0500 | 0 | 899431 | WHILE HALLIBURTON BATCH MIXING CEMENT SLURRY, HAD HALLIBURTON COMPRESSOR STOP WORKING & TRY TO FIX THE ISSUE WITHOUT SUCCESS, POOR PLANNING FROM HALLIBURTON FOR THE CRITICAL JOB. | CMT | NA |  | 07/11/2022 | NBR-633S | 24 | HRDH-2234
844 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SINO-15L | Hrs | ANDR-420
845 | LCRW | TK1 | 35.5 | 10 Jul 1730 - 0500 | 5606 | 899534 | DRESSING WINDOW AFTER STUCK IN IT WITH DRILLING BHA | STUK | STRG |  | 07/11/2022 | SINO-15L | 24 | ANDR-420
846 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SINO-1L | Hrs | ABJF-20
847 | GRF | RIG | 48 | 10 Jul 0500 - 0500 | 0 | 899520 | WHILE PERFORMING CAT-III (MPI) ON MAST AND SUBSTRUCTURE, OBSERVED CRACKS IN (3/9) RAISING SHEAVES ...REPLACED SAME WITH NEW SHEAVES. | UPRA | RSYS |  | 07/11/2022 | SINO-1L | 24 | ABJF-20
848 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SINO-36L | Hrs | SDGM-458
849 | HELD | TK1 | 101 | 07 Jul 2330 - 0500 | 5400 | 899508 | PROBLEM IN HOLE ACCESSIBILITY. TK1 | JF | LINR |  | 07/11/2022 | SINO-36L | 23.5 | SDGM-458
850 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SINO-46L | Hrs | SHYB-708
851 | FOT | BHI | 15.5 | 10 Jul 0300 - 1830 | 6901 | 899577 | LOSS SIGNAL WITH BCPM | BHA | MWD |  | 07/11/2022 | SINO-46L | 13.5 | SHYB-708
852 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SND-2001 | Hrs | UTMN-2329
853 | FOT | HWP | 50.5 | 09 Jul 1745 - 2015 | 19000 | 899428 | LOST SIGNAL DUE TO DOWNHOLE TOOLS FAILURE. | TF | WLT |  | 07/11/2022 | SND-2001 | 15.25 | UTMN-2329
854 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SND-2005 | Hrs | MHKK-2
855 | FOT | RIG | 4.75 | 10 Jul 0415 - 0900 | 13150 | 899507 | DRILLER'S RIG WATCH SCREEN NOT WORKING, ELECTRICIAN TROUBLE SHOOT RIG WATCH SYSTEM (RE-BOOT SYSTEM). | RR | EDR |  | 07/11/2022 | SND-2005 | 4 | MHKK-2
856 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SND-2008 | Hrs | HRDH-1812
857 | STDP | RIG | 120 | 07 Jul 0500 - 0500 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS, POH TO CHECK STRG FOUND STRG TWISTED OFF AT 2ND DC ABOVE MILL | STUK | DP |  | 07/11/2022 | SND-2008 | 24 | HRDH-1812
858 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SP-124 | Hrs | FDHL-141
859 | FOT | ODJ | 1 | 11 Jul 0500 - 0600 | 3600 | 899519 | PROBLEM WITH BACK UP POWER TONG NOT BITING ON 4-1/2"TUBING | TF | CTRQ |  | 07/11/2022 | SP-124 | 1 | FDHL-141
860 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SP-258 | Hrs | JNAB-872212
861 | STBH | ARM | 168 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/11/2022 | SP-258 | 24 | JNAB-872212
862 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/11/2022 | SSA-5971 | Hrs | HRDH-2247
863 | FOT | BAW | 1.5 | 11 Jul 0330 - 0500 | 13309 | 899581 | LOST ONE SEAL PACKER FROM DH LOG TOOLS IN HOLE WHILE FORMATION SAMPLING. | TF | WLT |  | 07/11/2022 | SSA-5971 | 1.5 | HRDH-2247
864 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | 095TE | Hrs | MNIF-226
865 | HERR | RIG | 14.25 | 11 Jul 1915 - 0930 | 9474 | 899579 | WHILE RIH INSIDE 7'' LINER, AT 9474' TAG OBSTRACTION, HAD S/W RESULTED TWO JOINTS BEND. | DSF | STRG |  | 07/12/2022 | 095TE | 4.5 | MNIF-226
866 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ADC-14 | Hrs | HRDH-612
867 | FOT | RIG | 9 | 12 Jul 1100 - 2000 | 0 | 899523 | REPAIR DAMAGE THREAD PROFILE OF THE UPPER RAM BONNET. | BOP | BOP |  | 07/12/2022 | ADC-14 | 9 | HRDH-612
868 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ADC-36 | Hrs | SDGM-1236
869 | FOT | BHI | 4 | 12 Jul 0100 - 0500 | 13628 | 899546 | LOST SIGNAL FROM BHI MWD TOOL, ATTEMPTED TO TROUBLESHOOT MWD TOOL WITHOUT SUCCESS, DECIDED TO POOH TO CHANGE MWD TOOL. | BHA | MWD |  | 07/12/2022 | ADC-36 | 4 | SDGM-1236
870 | FOT | RIG | .75 | 12 Jul 1045 - 1130 | 3801 | 899543 | INVESTIGATED ON DIFFERENT READING BETWEEN CHOCK HYDRAULIC GAUGE AND ELECTRONIC ONE . FOUND THE ELECTRONIC GAUGE DISCONNECTED. FIXED IT AND VERIFIED ALL CHOCK GAUGES READ THE SAME. | RR | CHK |  | 07/12/2022 | ADC-50 | .75 | SFNY-1176
871 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ADC-50 | Hrs | SFNY-1176
872 | FRFM | ARM | 128 | 06 Jul 1445 - 0500 | 3801 | 899340 | AT 3801', LOST COMPLETE CIRCULATION WITH 89 PCF WBM. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS. PUMPED 8 CMT PLUGS AND RECURE LOSSES. | LCIR | NA |  | 07/12/2022 | ADC-50 | 9.75 | SFNY-1176
873 | XTRI | RIG | .75 | 12 Jul 1000 - 1045 | 3801 | 899542 | EXCESSIVE TIME TO TEST WITH CAP TESTER. | JF | BOP |  | 07/12/2022 | ADC-50 | .75 | SFNY-1176
874 | FOT | RIG | .75 | 12 Jul 1045 - 1130 | 3801 | 899543 | INVESTIGATED ON DIFFERENT READING BETWEEN CHOCK HYDRAULIC GAUGE AND ELECTRONIC ONE . FOUND THE ELECTRONIC GAUGE DISCONNECTED. FIXED IT AND VERIFIED ALL CHOCK GAUGES READ THE SAME. | RR | CHK |  | 07/12/2022 | ADC-50 | .75 | SFNY-1176
875 | 6844 |  | OTH | E |  | NA | POOH SLB WL CABLE TO SURFACE. L/D SES AND WIRE LINE SHEAVES.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/12/2022 | ADC-53L | LOG | HRDH-530
876 | 6844 | 86 | TO | E |  | STDP | POOH LOG #2 AIT/TLD/HGNS/MCFL/ADT/GR (TRIPLE-COMBO) - TLC STRING ON 4" DP AT CONTROL SPEED F/ 6,156 FT TO TOP OF LOGGING TOOLS @ 86 FT.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6156 | RIG | 07/12/2022 | ADC-53L | LOG | HRDH-530
877 | 6844 |  | OTH | E |  | NA | HPJSM, L/D SLB AIT/TLD/HGNS/MCFL/ADT/GR (TRIPLE-COMBO) LOGGING TOOL.- HPJSM AND REMOVED RA SOURCE.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/12/2022 | ADC-53L | LOG | HRDH-530
878 | 6844 |  | RR | E |  | TDS | SERICED TDS. CLEANED AND CLEARED RIG FLOOR.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/12/2022 | ADC-53L | LOG | HRDH-530
879 | 6844 |  | HT | E |  | BHA | HPJSM, P/U & M/U 6-1/8" BHA WITH MAGNETS AND 7" SCRAPPER. RIH TO 698 FT.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | RIG | 07/12/2022 | ADC-53L | CT | HRDH-530
880 | 6844 | 6456 | TI | E |  | STDP | RIH 6-1/8" BHA ON 4" DP'S STANDS FROM 698 FT TO 6,456 FT.- FILL STRING EVERY 20 STD RAN- SLOW DOWN AT 7" TOL- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 698 | RIG | 07/12/2022 | ADC-53L | CT | HRDH-530
881 | 6844 | 6844 | CIRC | E |  | MPMP | SCRAPE & BRUSH UPPER COMPLETION PACKER SETTING INTERVAL 3X F/5,898 FT T/6,146 FT (6,596 FT - 6,844 FT BIT DEPTH). TAGGED BOTTOM AT 6,844 FT.- 320 GPM, PRESS: 1,250 PSI, 100 RPM TQ 2 - 3 KLB-FT- CONTINOUSLY PUMPING 87 PCF MUD CAP AT BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/12/2022 | ADC-53L | CT | HRDH-530
882 | 6844 |  | CIRC | E |  | MPMP | PUMPED 40 BBL HI-VIS MUD CIRC HOLE. - CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS. | 6844 |  | RIG | 07/12/2022 | ADC-53L | CT | HRDH-530
883 | 6844 | 6456 | ST | E |  | STDP | HPJSM. POOH 6-1/8" BHA ON ELEVATOR FROM BTM @6,844 FT TO 6,456 FT (SHOE). WELL IN GOOD CONDITION.- CONTINUOUSLY PUMP 2 BPM 87 PCF LSND MUD IN ANNULUS. | 6844 | 6844 | RIG | 07/12/2022 | ADC-53L | CT | HRDH-530
884 | 6844 | 698 | TO | E |  | STDP | CONTINUE POOH 6-1/8" BHA ON ELEVATOR F/6,456 FT TO TOP OF BHA @ 698 FT.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/12/2022 | ADC-53L | CT | HRDH-530
885 | 6844 |  | HT | E |  | STRG | CONTINUED POOH 6-1/8" BHA ON ELEVATOR F/356 FT TO SURFACE. L/D MAGNETS, 7" SCRAPPERBIT & BIT #9RR.- BIT GRADING: 1, 1, WT, A, E, NO, I, LOG- RECOVERED 5 KG METAL FROM MAGNETS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/12/2022 | ADC-53L | CT | HRDH-530
886 | 6844 |  | OTH | E | 3625 | NA | HPJSM, P/U & M/U WL LOGGING 3RD RUN (CMR / GR ) ASSY & RIH TO 66 FT.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM | 6844 |  | SWL | 07/12/2022 | ADC-53L | LOG | HRDH-530
887 | 6844 | 1474 | TI | E | 3625 | STDP | RIH LOG #3 CMR/GR ON TLC ON 4" DP STDS F/ 66 FT TO 1474 FT.- CONTROL SPEED 3 MIN/STD SLIP TO SLIP.- FILL STRING AND BREAK CIRC EVERY 10 STD.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 66 | RIG | 07/12/2022 | ADC-53L | LOG | HRDH-530
888 | 41.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 3 | 3625 | 09 Jul 0000 | 07/12/2022 | ADC-53L | Type | HRDH-530
889
890
891 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ADC-62L | Hrs | ANDR-745
892 | HERR | RIG | 562.5 | 18 Jun 0100 - 1130 | 9094 | 898471 | ERROR RESULT : DRILL STRING STUCK. | JF | TDS |  | 07/12/2022 | ADC-62L | 6.5 | ANDR-745
893 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ADC-65L | Hrs | HWYH-1280
894 | FOT | RIG | 2 | 12 Jul 0100 - 0300 | 21480 | 899596 | COOLING FAN ON TDS WAS NOT WORKING & CAUSING HIGH TEMP. PROBLEMS. | RR | TDS |  | 07/12/2022 | ADC-65L | 2 | HWYH-1280
895 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ADC-66L | Hrs | UTMN-3155
896 | FOT | SDM | 13 | 11 Jul 1330 - 0900 | 4670 | 899593 | MISCOMMUNICATION W/ RSS TOOL. | BHA | RSS |  | 07/12/2022 | ADC-66L | 3.5 | UTMN-3155
897 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ADES-144 | Hrs | UTMN-3152
898 | FOT | SPS | 21.25 | 11 Jul 0000 - 2145 | 12194 | 899538 | LOST MWD SIGNAL WHILE DRILLING AHEAD. | BHA | MWD |  | 07/12/2022 | ADES-144 | 16.75 | UTMN-3152
899 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ARO-3002 | Hrs | MRJN-812
900 | FOT | RIG | .5 | 12 Jul 0430 - 0500 | 15119 | 899549 | OBSERVED LEAK ON SWIVEL PACKING. | RR | SWVL |  | 07/12/2022 | ARO-3002 | .5 | MRJN-812
901 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | DPS-4 | Hrs | MDRK-63
902 | NARW | ARM | 114.25 | 07 Jul 2000 - 1830 | 5300 | 899482 | TAKE SLACK OFF WEIGHT AT 5300' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS. | TH | NA |  | 07/12/2022 | DPS-4 | 13.5 | MDRK-63
903 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | DQ-47 | Hrs | KHRS-497
904 | FOT | BHI | 154 | 28 Jun 0800 - 1715 | 10060 | 898952 | BAKER MWD TOOLS LOST SIGNAL. | BHA | LWD |  | 07/12/2022 | DQ-47 | 1 | KHRS-497
905 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | ED-85A | Hrs | ZULF-2063
906 | GRF | RIG | 65 | 10 Jul 1200 - 0500 | 8838 | 899582 | MALFACTION ON DRAWWORK RESISTOR GRID | UPRA | DWKS |  | 07/12/2022 | ED-85A | 24 | ZULF-2063
907 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | JACK-203 | Hrs | HZEM-849
908 | LCRW | ARM | 61.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/12/2022 | JACK-203 | 24 | HZEM-849
909 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | NA-393S | Hrs | UTMN-2290
910 | FOT | SDM | 6.5 | 12 Jul 2230 - 0500 | 13577 | 899614 | SLB MWD LOST SIGNAL, TROUBLE SHOOT AS PER SLB, NO SUCCESS. | BHA | MWD |  | 07/12/2022 | NA-393S | 6.5 | UTMN-2290
911 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | NBR-196S | Hrs | SDGM-1235
912 | FOT | BLH | 17.5 | 12 Jul 1130 - 0500 | 2995 | 899524 | 7" LINER HANGER STUCK IN CASED VERTICAL SECTION OF WELL, 767' BELOW ROTARY TABLE. | TF | LLAP |  | 07/12/2022 | NBR-196S | 17.5 | SDGM-1235
913 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | NBR-20S | Hrs | HMYM-433514
914 | FOT | SPS | 2.25 | 12 Jul 1530 - 1745 | 17529 | 899615 | MWD LOST SIGNAL | BHA | MWD |  | 07/12/2022 | NBR-20S | 2.25 | HMYM-433514
915 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | NBR-263S | Hrs | QTIF-736
916 | FOT | SPS | 31 | 11 Jul 0500 - 0500 | 9022 | 899583 | IMPROPER COMMUNICATION WITH SPS GEO-TAP & MWD TOOLS, TOUBLE SHOOT WITH NO SUCCESS, POOH TO CHANGE FAILED TOOLS. | BHA | LWD |  | 07/12/2022 | NBR-263S | 13.5 | QTIF-736
917 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | NBR-633S | Hrs | HRDH-2234
918 | HFFT | HCM | 40 | 10 Jul 1715 - 0915 | 0 | 899431 | WHILE HALLIBURTON BATCH MIXING CEMENT SLURRY, HAD HALLIBURTON COMPRESSOR STOP WORKING & TRY TO FIX THE ISSUE WITHOUT SUCCESS, POOR PLANNING FROM HALLIBURTON FOR THE CRITICAL JOB. | CMT | NA |  | 07/12/2022 | NBR-633S | 4.25 | HRDH-2234
919 | FOT | RIG | 1.5 | 12 Jul 0330 - 0500 | 9901 | 899548 | KELLY HOSE LEAKING ON GOOSENECK | RR | CSYS |  | 07/12/2022 | NBR-783S | 1.5 | NJYN-93
920 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | NBR-783S | Hrs | NJYN-93
921 | WTHR | ARM | 10.5 | 12 Jul 1700 - 0330 | 9901 | 899547 | LIGHTNING DISABLED RIGWATCH & RTDTS | WON | NA |  | 07/12/2022 | NBR-783S | 10.5 | NJYN-93
922 | FOT | RIG | 1.5 | 12 Jul 0330 - 0500 | 9901 | 899548 | KELLY HOSE LEAKING ON GOOSENECK | RR | CSYS |  | 07/12/2022 | NBR-783S | 1.5 | NJYN-93
923 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | PA-70S | Hrs | MDRK-64
924 | FOT | WLH | 908.5 | 30 May 1800 - 0745 | 15492 | 897183 | CONFIRMED THAT THERE WAS A LEAK IN THE CONNECTION IN WFD LOWER COMPLATION, WHERE THOSE CONNECTIONS WERE MADE-UP AT WFD WORKSHOP. | TF | LLAP |  | 07/12/2022 | PA-70S | 2.75 | MDRK-64
925 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | PA-861S | Hrs | HRDH-1973
926 | FOT | SLL | 1.5 | 12 Jul 1030 - 1200 | 0 | 899541 | UNABLE TO SET SLB PLUG ON UPPER R-NIPPLE | TF | SLICK |  | 07/12/2022 | PA-861S | 1.5 | HRDH-1973
927 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | RM-74A | Hrs | HSBH-68
928 | SRVC | HCA | 16.25 | 12 Jul 1245 - 0500 | 1905 | 899598 | HALLIBURTON MIX WATER WAS NOT BUILD AS PER RECIPE/PROCEDURE. HALLIBURTON REPLACE AND RE-BUILD CEMENT MIX WATER | WO | NA |  | 07/12/2022 | RM-74A | 16.25 | HSBH-68
929 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SCTD-2 | Hrs | HRDH-2148
930 | FOT | SDM | 9 | 12 Jul 2000 - 0500 | 12750 | 899595 | D&M LOST COMMUNICATION WITH DOWNHOLE TOOLS. | BHA | MWD |  | 07/12/2022 | SCTD-2 | 9 | HRDH-2148
931 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SINO-10 | Hrs | JLDI-38
932 | UVLC | ARM | 88.5 | 09 Jul 1230 - 0500 | 10185 | 899540 | TOTAL LOSSED DURING CEMENT JOB FOR 7" LINER , UN-CONTROLLED LOSSES | LCIR | NA |  | 07/12/2022 | SINO-10 | 24 | JLDI-38
933 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SINO-15L | Hrs | ANDR-420
934 | LCRW | TK1 | 47.5 | 10 Jul 1730 - 1700 | 5606 | 899534 | DRESSING WINDOW AFTER STUCK IN IT WITH DRILLING BHA | STUK | STRG |  | 07/12/2022 | SINO-15L | 12 | ANDR-420
935 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SND-2002 | Hrs | WAQR-23
936 | WTHR | OTH | 2.5 | 12 Jul 1730 - 2000 | 15006 | 899526 | WAIT ON BAD WEATHER | WON | NA |  | 07/12/2022 | SND-2002 | 2.5 | WAQR-23
937 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SP-110 | Hrs | BRRI-562
938 | FOT | RIG | 5 | 12 Jul 0930 - 1430 | 9375 | 899612 | RIG POWER SHUT DOWN DURING RIH WITH 4-1/2" TEMPORARY COMPLETION. | RR | PSYS |  | 07/12/2022 | SP-110 | 5 | BRRI-562
939 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SP-258 | Hrs | JNAB-872212
940 | STBH | ARM | 192 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/12/2022 | SP-258 | 24 | JNAB-872212
941 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SP-58 | Hrs | HRDH-795
942 | WOTO | MSL | 5 | 12 Jul 1000 - 1500 | 0 | 899522 | WAIT ON MANSOORI S/L T-SUB FOR R/U PCE TO RETRIVE PR PLUG. | WO | NA |  | 07/12/2022 | SP-58 | 5 | HRDH-795
943 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SSA-202 | Hrs | QTIF-191
944 | FOT | SPS | 9 | 12 Jul 2000 - 0500 | 8048 | 899545 | SPS LOST SIGNAL FOR MWD, TROUBLESHOOT, NO SUCCESS. | BHA | MWD |  | 07/12/2022 | SSA-202 | 9 | QTIF-191
945 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SSA-51 | Hrs | MNIF-257
946 | FOT | GOC | 1.5 | 12 Jul 0730 - 0900 | 775 | 899544 | HAD A MECHANICAL PROBLEM IN AL-GHAITH POWER UNITS, FIXED SAME. | TF | CTRQ |  | 07/12/2022 | SSA-51 | 1.5 | MNIF-257
947 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | SSA-5971 | Hrs | HRDH-2247
948 | FOT | BAW | 25.5 | 11 Jul 0330 - 0500 | 13309 | 899581 | LOST ONE SEAL PACKER FROM DH LOG TOOLS IN HOLE WHILE FORMATION SAMPLING. | TF | WLT |  | 07/12/2022 | SSA-5971 | 24 | HRDH-2247
949 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/12/2022 | V140A | Hrs | SFNY-1830
950 | FOT | SWL | 1.5 | 12 Jul 0300 - 0430 | 3100 | 899597 | LOST TELEMETRY ENTIRELY TO TOOLSTRING FOR LOGGING RUN#2. POOH FOR TROUBLESHOOTING | TF | WLT |  | 07/12/2022 | V140A | 1.5 | SFNY-1830
951 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | ADC-31 | Hrs | SDGM-1181
952 | FOT | RIG | 33.5 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | RR | TDS |  | 07/13/2022 | ADC-31 | 24 | SDGM-1181
953 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | ADC-36 | Hrs | SDGM-1236
954 | FOT | BHI | 28 | 12 Jul 0100 - 0500 | 13628 | 899546 | LOST SIGNAL FROM BHI MWD TOOL, ATTEMPTED TO TROUBLESHOOT MWD TOOL WITHOUT SUCCESS, DECIDED TO POOH TO CHANGE MWD TOOL. | BHA | MWD |  | 07/13/2022 | ADC-36 | 24 | SDGM-1236
955 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | ADC-50 | Hrs | SFNY-1176
956 | FRFM | ARM | 152 | 06 Jul 1445 - 0500 | 3801 | 899340 | AT 3801', LOST COMPLETE CIRCULATION WITH 89 PCF WBM. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS. PUMPED 8 CMT PLUGS AND RECURE LOSSES. | LCIR | NA |  | 07/13/2022 | ADC-50 | 24 | SFNY-1176
957 | 6844 | 6156 | TI | E | 3625 | STDP | RIH AT CONTROL SPEED LOG #3 CMR/GR - TLC ON 4" DP STDS F/ 1474 FT TO LATCH POINT AT 6,156 FT.- CONTROL SPEED 3 MIN/STD SLIP TO SLIP.- FILL STRING AND BREAK CIRC EVERY 10 STD.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 1474 | RIG | 07/13/2022 | ADC-53L | LOG | HRDH-530
958 | 6844 |  | CIRC | E | 3625 | MPMP | CIRC 1.5 STRING VOLUME. MEANWHILE HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW.- FR: 300 GPM & PRESS: 200 PSI. - CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/13/2022 | ADC-53L | LOG | HRDH-530
959 | 6844 |  | OTH | E | 3625 | NA | HPJSM. M/U SLB S.E.S. & FEED WIRE LINE CABLE. RIH WIRE LINE CABLE AND LATCH INTO CONNECTOR AS PER SLB WIRELINE ENGINEER INSTRUCTION.- APPLY 250 PSI PUMP PRESS TO ASSIST IN LATCHING PROCESS AS PER SLB ENG.- LATCH INTO WET CONNECTOR PROFILE, FUNCTION TEST SLB TOOLS, OK.- PERFORM PULL TENSION TEST TO 3,100 LBS, OK.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/13/2022 | ADC-53L | LOG | HRDH-530
960 | 6844 | 6824 | ST | E | 3625 | STDP | RIH LOG #3 CMR/GR - TLC ON 4" DP F/ 6,156 FT TO 6,829 FT AT CONTROL SPEED. - CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS- CALIBRATE TOOLS 2X WHILE RIH.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6156 | RIG | 07/13/2022 | ADC-53L | LOG | HRDH-530
961 | 6844 | 6456 | LOG | E | 3625 | WLT | PERFORMED LOG # 3 CMR/GR ON TLC F/6,829FT TO 6,456 FT AS PER SLB WIRELINE ENGINEER. RIH BACK AND RELOG F/6,829 FT TO 6,456 FT.- CONTROLLED SPEED AT 2 FT/MIN.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6824 | SWL | 07/13/2022 | ADC-53L | LOG | HRDH-530
962 | 6844 |  | OTH | E | 3625 | NA | KEPT STRING STATIONARY INSIDE CASING SHOE AS PER WL ENGR INSTRUCTION WHILE ARAMCO RDD PROCESSING THE DATA.- DATA CONFIRMED BY ARAMCO RDD- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | SWL | 07/13/2022 | ADC-53L | LOG | HRDH-530
963 | 6844 |  | OTH | E | 3625 | NA | HPJSM, PULLED STRING TO 6,156 FT. SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE & POOH WL CABLE TO SURFACE. L/D SES AND WIRE LINE SHEAVES.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | SWL | 07/13/2022 | ADC-53L | LOG | HRDH-530
964 | 6844 | 2974 | TO | E | 3625 | STDP | POOH LOG #3 CMR/GR - TLC ON 4" DP AT CONTROL SPEED F/ 6,156 FT TO 2974 FT. ON GOING AT REPORT TIME.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6156 | RIG | 07/13/2022 | ADC-53L | LOG | HRDH-530
965 | 65.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/13/2022 | ADC-53L | Type | HRDH-530
966
967
968 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | ADC-57L | Hrs | KRSN-175
969 | CFFM | TK3 | 26.25 | 12 Jul 0515 - 0730 | 358 | 899616 | WELL IN TOTAL LOSSES | LCIR | SQZ |  | 07/13/2022 | ADC-57L | 2.5 | KRSN-175
970 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | ARO-3002 | Hrs | MRJN-812
971 | FOT | RIG | 8 | 12 Jul 0430 - 1230 | 15119 | 899549 | OBSERVED LEAK ON SWIVEL PACKING. | RR | SWVL |  | 07/13/2022 | ARO-3002 | 7.5 | MRJN-812
972 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | DPS-5 | Hrs | HRDH-2319
973 | LTHI | XLG | 41 | 12 Jul 1130 - 0500 | 14195 | 899530 | PICK 7" LINER POINT WRONG @ 88' INSIDE UNZ-A INSTEAD OF 450' INTO KFDA. | DD | AVDS |  | 07/13/2022 | DPS-5 | 23.5 | HRDH-2319
974 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | ED-85A | Hrs | ZULF-2063
975 | GRF | RIG | 89 | 10 Jul 1200 - 0500 | 8838 | 899582 | MALFACTION ON DRAWWORK RESISTOR GRID | UPRA | DWKS |  | 07/13/2022 | ED-85A | 24 | ZULF-2063
976 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | ENSCO-54 | Hrs | ABSF-17
977 | STCT | ARM | 174 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/13/2022 | ENSCO-54 | 24 | ABSF-17
978 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | EXL-IA | Hrs | SFNY-1790
979 | LHFL | RIG | .75 | 13 Jul 0330 - 0415 | 230 | 899600 | WHILE DRILLING OIL LEAKING FROM TDS HYDRAULIC SYSTEM | RR | HSYS |  | 07/13/2022 | EXL-IA | .75 | SFNY-1790
980 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | JACK-203 | Hrs | HZEM-849
981 | LCRW | ARM | 85.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/13/2022 | JACK-203 | 24 | HZEM-849
982 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | NA-18S | Hrs | UTMN-1886
983 | XTTE | FMC | 1.5 | 13 Jul 1200 - 1700 | 1 | 899528 | FRANKS TEAM DELAY IN RIGGING UP AND IMPROPER DIES IN USE. | TF | CTRQ |  | 07/13/2022 | NA-18S | 1.5 | UTMN-1886
984 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | NA-393S | Hrs | UTMN-2290
985 | FOT | SDM | 29.25 | 12 Jul 2230 - 0500 | 13577 | 899614 | SLB MWD LOST SIGNAL, TROUBLE SHOOT AS PER SLB, NO SUCCESS. | BHA | MWD |  | 07/13/2022 | NA-393S | 22.75 | UTMN-2290
986 | FOT | RIG | 16.5 | 13 Jul 1230 - 0500 | 12671 | 899529 | ELECTRICAL ISSUES ENCOUNTERED WITH TDS OPERATION. | RR | TDS |  | 07/13/2022 | NBR-196S | 16.5 | SDGM-1235
987 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | NBR-196S | Hrs | SDGM-1235
988 | FOT | BLH | 25 | 12 Jul 1130 - 1230 | 2995 | 899524 | 7" LINER HANGER STUCK IN CASED VERTICAL SECTION OF WELL, 767' BELOW ROTARY TABLE. | TF | HGRL |  | 07/13/2022 | NBR-196S | 7.5 | SDGM-1235
989 | FOT | RIG | 16.5 | 13 Jul 1230 - 0500 | 12671 | 899529 | ELECTRICAL ISSUES ENCOUNTERED WITH TDS OPERATION. | RR | TDS |  | 07/13/2022 | NBR-196S | 16.5 | SDGM-1235
990 | FOT | SPS | 1 | 13 Jul 0215 - 0315 | 9320 | 899625 | OBSERVE NO RESPONSE FROM GEO-TAP AFTER DOWNLINK, TROUBLESHOOT & FIX SAME, OK. | BHA | LWD |  | 07/13/2022 | NBR-263S | 1 | QTIF-736
991 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | NBR-263S | Hrs | QTIF-736
992 | FOT | SPS | 33.75 | 11 Jul 0500 - 0745 | 9022 | 899583 | IMPROPER COMMUNICATION WITH SPS GEO-TAP & MWD TOOLS, TOUBLE SHOOT WITH NO SUCCESS, POOH TO CHANGE FAILED TOOLS. | BHA | LWD |  | 07/13/2022 | NBR-263S | 2.75 | QTIF-736
993 | FOT | SPS | 1 | 13 Jul 0215 - 0315 | 9320 | 899625 | OBSERVE NO RESPONSE FROM GEO-TAP AFTER DOWNLINK, TROUBLESHOOT & FIX SAME, OK. | BHA | LWD |  | 07/13/2022 | NBR-263S | 1 | QTIF-736
994 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | NBR-783S | Hrs | NJYN-93
995 | FOT | RIG | 5.5 | 12 Jul 0330 - 0900 | 9901 | 899548 | KELLY HOSE UNION LEAKING | RR | CSYS |  | 07/13/2022 | NBR-783S | 4 | NJYN-93
996 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | PA-861S | Hrs | HRDH-1973
997 | FOT | FMC | .75 | 13 Jul 2115 - 2200 | 8140 | 899618 | HYDRAULIC LEAK ON POWER TONG | TF | TTRQ |  | 07/13/2022 | PA-861S | .75 | HRDH-1973
998 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | RM-74A | Hrs | HSBH-68
999 | SRVC | HCA | 27.5 | 12 Jul 1245 - 1615 | 1905 | 899598 | HALLIBURTON MIX WATER WAS NOT BUILD AS PER RECIPE/PROCEDURE. HALLIBURTON REPLACE AND RE-BUILD CEMENT MIX WATER | WO | NA |  | 07/13/2022 | RM-74A | 11.25 | HSBH-68
1000 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SCTD-1 | Hrs | SDGM-1034
1001 | FOT | SDM | 5.5 | 13 Jul 2330 - 0500 | 11985 | 899652 | DOWNHOLE MWD TOOL FAILURE. | BHA | MWD |  | 07/13/2022 | SCTD-1 | 5.5 | SDGM-1034
1002 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SCTD-2 | Hrs | HRDH-2148
1003 | FOT | SDM | 12.5 | 12 Jul 2000 - 0830 | 12750 | 899595 | D&M LOST COMMUNICATION WITH DOWNHOLE TOOLS. | BHA | MWD |  | 07/13/2022 | SCTD-2 | 3.5 | HRDH-2148
1004 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SINO-25 | Hrs | MNIF-364
1005 | FOT | OWT | 9.5 | 13 Jul 0600 - 1530 | 6140 | 899527 | OILSERV AJUSTABLE CHOKE & FLOW METER, ( FAILED FUNCTION TEST ). TROUBLE SHOOT OILSERV FLOW METER AND AJUSTABLE CHOKE FAILURES. >> FOUND BROKEN METAL FRAGMENT STUCK INSIDE FLOW METER TURBINE. >> OPENED UP AJUSTABLE CHOKE AND FOUND PART OF THE METAL SEALING SECTION BROKEN >> WAIT ON REPLACEMENT CHOKE MANIFOLD FROM 08:00 TO 15:00. | TF | TESTT |  | 07/13/2022 | SINO-25 | 9.5 | MNIF-364
1006 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SND-2008 | Hrs | HRDH-1812
1007 | STDP | RIG | 144 | 07 Jul 0500 - 0500 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS, POH TO CHECK STRG FOUND STRG TWISTED OFF AT 2ND DC ABOVE MILL | STUK | DP |  | 07/13/2022 | SND-2008 | 24 | HRDH-1812
1008 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SP-258 | Hrs | JNAB-872212
1009 | STBH | ARM | 216 | 05 Jul 0500 - 0500 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/13/2022 | SP-258 | 24 | JNAB-872212
1010 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SP-306 | Hrs | MNIF-193
1011 | FOT | MSD | 1 | 13 Jul 1000 - 1100 | 3651 | 899551 | MALFUNCTION IN AL-MASOOD POWER UNIT/ SPIDER SLIPS | TF | CTRQ |  | 07/13/2022 | SP-306 | 1 | MNIF-193
1012 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SSA-202 | Hrs | QTIF-191
1013 | FOT | SPS | 23 | 12 Jul 2000 - 1930 | 8048 | 899545 | SPS LOST SIGNAL FOR MWD, TROUBLESHOOT, NO SUCCESS. | BHA | MWD |  | 07/13/2022 | SSA-202 | 14 | QTIF-191
1014 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SSA-5917 | Hrs | HRDH-2201
1015 | FPMP | RIG | 2 | 13 Jul 1900 - 2100 | 4347 | 899621 | HAD PRESSURE DROP WHILE DRILLING 16" HOLE DUE TO DAMAGE IN PUMP SEAT VALVES OF MP #1 & MP #2. | RR | MPMP |  | 07/13/2022 | SSA-5917 | 2 | HRDH-2201
1016 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | SSA-5971 | Hrs | HRDH-2247
1017 | FOT | BAW | 27.5 | 11 Jul 0330 - 0700 | 13309 | 899581 | LOST ONE SEAL PACKER FROM DH LOG TOOLS IN HOLE WHILE FORMATION SAMPLING. | TF | WLT |  | 07/13/2022 | SSA-5971 | 2 | HRDH-2247
1018 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/13/2022 | T216 | Hrs | ANDR-338
1019 | FOT | WDS | 20.5 | 13 Jul 0830 - 0500 | 7422 | 899619 | WFD LWD TOOLS LOST SIGNAL. | BHA | LWD |  | 07/13/2022 | T216 | 20.5 | ANDR-338
1020 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | 088TE | Hrs | QTIF-330
1021 | FOT | RIG | 4.5 | 14 Jul 0500 - 0930 | 7842 | 899635 | DRAW WORKS HIGH CLUTCH MALFUNCTION, UNABLE TO DISENGAGE FROM GEAR. | RR | DWKS |  | 07/14/2022 | 088TE | 4.5 | QTIF-330
1022 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ADC-17 | Hrs | ZULF-1210
1023 | FOT | SCP | 16.75 | 14 Jul 1215 - 0500 | 5212 | 899678 | PACKER #1 FAILING TO HOLD PRESSURE. STARTED RE-SET PACKER OPERATION | TF | PKR |  | 07/14/2022 | ADC-17 | 16.75 | ZULF-1210
1024 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ADC-31 | Hrs | SDGM-1181
1025 | STDP | RIG | 57.5 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/14/2022 | ADC-31 | 24 | SDGM-1181
1026 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ADC-36 | Hrs | SDGM-1236
1027 | FOT | BHI | 29.5 | 12 Jul 0100 - 0630 | 13628 | 899546 | LOST SIGNAL FROM BHI MWD TOOL, ATTEMPTED TO TROUBLESHOOT MWD TOOL WITHOUT SUCCESS, DECIDED TO POOH TO CHANGE MWD TOOL. | BHA | MWD |  | 07/14/2022 | ADC-36 | 1.5 | SDGM-1236
1028 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ADC-50 | Hrs | SFNY-1176
1029 | FRFM | ARM | 176 | 06 Jul 1445 - 0500 | 3801 | 899340 | AT 3801', LOST COMPLETE CIRCULATION WITH 89 PCF WBM. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS. PUMPED 8 CMT PLUGS AND RECURE LOSSES. | LCIR | NA |  | 07/14/2022 | ADC-50 | 24 | SFNY-1176
1030 | 6844 | 66 | TO | E | 3625 | STDP | POOH LOG #3 CMR/GR - TLC ON 4" DP AT CONTROL SPEED F/ 2,974 FT TO TOP OF LOGGING TOOLS @ 66 FT- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 2974 | RIG | 07/14/2022 | ADC-53L | LOG | HRDH-530
1031 | 6844 |  | OTH | E | 3625 | NA | HPJSM, L/D LOG #3 CMR/GR LOGGING TOOL.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/14/2022 | ADC-53L | LOG | HRDH-530
1032 | 6844 |  | HT | E | 3625 | BHA | HPJSM, P/U & M/U 6-1/8" CONDITIONING TRIP BHA AND RIH TO 356 FT.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2BPM. | 6844 |  | RIG | 07/14/2022 | ADC-53L | CT | HRDH-530
1033 | 6844 | 6456 | TI | E | 3625 | STDP | RIH 6-1/8" BHA ON 4" DP'S STANDS FROM 356 FT TO 6,456 FT.- FILL STRING EVERY 20 STD RAN- SLOW DOWN AT 7" TOL- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 356 | RIG | 07/14/2022 | ADC-53L | CT | HRDH-530
1034 | 6844 | 6844 | RW | E | 3625 | BIT | REAM AND WASH HOLE F/6,456 FT AND TAGGED BOTTOM AT 6,844 FT.- 300 GPM, PRESS: 1,130 PSI, 800 RPM TQ 1 - 2 KLB-FT- CONTINUOUSLY PUMPING 87 PCF MUD CAP AT BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/14/2022 | ADC-53L | CT | HRDH-530
1035 | 6844 |  | CIRC | E | 3625 | MPMP | PUMPED TANDEM 30 BBL HI-VIS MUD AND CIRC HOLE. - CONTINOUSLY PUMPING 87 PCF MUD CAP AT BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/14/2022 | ADC-53L | CT | HRDH-530
1036 | 6844 | 6456 | ST | E | 3625 | STDP | HPJSM. POOH 6-1/8" BHA ON ELEVATOR FROM BTM @6,844 FT TO 6,456 FT (SHOE). HOLE IN GOOD CONDITION.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6488 | RIG | 07/14/2022 | ADC-53L | CT | HRDH-530
1037 | 6844 | 356 | TO | E | 3625 | STDP | CONTINUE POOH 6-1/8" BHA ON ELEVATOR F/6,456 FT TO TOP OF BHA @ 356 FT.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/14/2022 | ADC-53L | CT | HRDH-530
1038 | 6844 |  | HT | E | 3625 | BHA | CONTINUED POOH 6-1/8" BHA ON ELEVATOR F/356 FT TO SURFACE. L/D BIT #9RR.- BIT GRADING: 1, 1, WT, A, E, NO, I, LOG- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/14/2022 | ADC-53L | CT | HRDH-530
1039 | 6844 |  | OTH | E | 3625 | NA | HPJSM, P/U & M/U WL LOGGING TOOLS RUN #4 MDT & RIH TO 162 FT.- CHECK TOOLS ON SURFACE, OK.- TOOL LENGTH: 162.12 FT. MAX TOOL OD: 5.284 INCHES.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM | 6844 |  | SWL | 07/14/2022 | ADC-53L | LOG | HRDH-530
1040 | 6844 | 6156 | TI | E | 3625 | STDP | RIH LOG #4 MDT - TLC ON 4" DP STDS F/ 162 FT TO 5,018 FT. ON GOING AT REPORT TIME.- CONTROL SPEED 3 MIN/STD SLIP TO SLIP.- FILL STRING AND BREAK CIRC EVERY 10 STD.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 162 | RIG | 07/14/2022 | ADC-53L | LOG | HRDH-530
1041 | 89.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/14/2022 | ADC-53L | Type | HRDH-530
1042
1043
1044 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ADC-56L | Hrs | UTMN-3069
1045 | INTQ | TK3 | 19.5 | 13 Jul 0300 - 2230 | 4561 | 899602 | MEANWHILE DRLG 22" VERTICAL HOLE F/ 4164' TO 4,561, HAD PROBLEM WITH DRILL-OPS AND SOFT TORQUE SYSTEM . | TRQ | BHA |  | 07/14/2022 | ADC-56L | 17.5 | UTMN-3069
1046 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ADES-157 | Hrs | HRDH-1844
1047 | FOT | GEP | 29.5 | 13 Jul 2330 - 0500 | 14932 | 899679 | N/U WG TBG BONNET AND TEST VOIDS, NOT HOLD. | WH | WH |  | 07/14/2022 | ADES-157 | 24 | HRDH-1844
1048 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ADES-174 | Hrs | GHZL-29
1049 | FOT | SDM | 6.5 | 14 Jul 2230 - 0500 | 13750 | 899638 | SLB NEAR BIT GR FAILURE DURING DRILLING | BHA | LWD |  | 07/14/2022 | ADES-174 | 6.5 | GHZL-29
1050 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ADM-266 | Hrs | ZULF-255
1051 | MATL | ARM | 11 | 14 Jul 1600 - 0300 | 0 | 899676 | WAIT ON NITROGEN GAS WHICH IS REQUIRED TO LIFT THE WELL, SINCE THE WELL COULD NOT FLOW NATRUALLY. | WO | NA |  | 07/14/2022 | ADM-266 | 11 | ZULF-255
1052 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | DPS-5 | Hrs | HRDH-2319
1053 | LTHI | XLG | 65 | 12 Jul 1130 - 0500 | 14195 | 899530 | PICK 7" LINER POINT WRONG @ 88' INSIDE UNZ-A INSTEAD OF 450' INTO KFDA. | DD | AVDS |  | 07/14/2022 | DPS-5 | 24 | HRDH-2319
1054 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ED-85A | Hrs | ZULF-2063
1055 | GRF | RIG | 110 | 10 Jul 1200 - 0200 | 8838 | 899582 | MALFACTION ON DRAWWORK RESISTOR GRID | UPRA | DWKS |  | 07/14/2022 | ED-85A | 21 | ZULF-2063
1056 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | ENSCO-54 | Hrs | ABSF-17
1057 | FOT | WI1 | 38.5 | 13 Jul 1100 - 0500 | 6231 | 899656 | WFD HYRAULIC TBG CUTTER FAILED TO CUT 4-1/2" LOWER COMPLETION TBG. | TF | CUT |  | 07/14/2022 | ENSCO-54 | 24 | ABSF-17
1058 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | JACK-203 | Hrs | HZEM-849
1059 | LCRW | ARM | 109.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/14/2022 | JACK-203 | 24 | HZEM-849
1060 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | NA-207S | Hrs | SHYB-132
1061 | FOT | RIG | 1.75 | 14 Jul 1730 - 1915 | 4829 | 899606 | OBSERVED WASHOUT IN RIG MUD PUMP #1, HAD TO STOP DRILLING. | RR | MPMP |  | 07/14/2022 | NA-207S | 1.75 | SHYB-132
1062 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | NA-393S | Hrs | UTMN-2290
1063 | FOT | SDM | 32.5 | 12 Jul 2230 - 0830 | 13577 | 899614 | SLB MWD LOST SIGNAL, TROUBLE SHOOT AS PER SLB, NO SUCCESS. | BHA | MWD |  | 07/14/2022 | NA-393S | 3.5 | UTMN-2290
1064 | FOT | RIG | 23 | 13 Jul 1230 - 1130 | 12671 | 899529 | ELECTRICAL ISSUES ENCOUNTERED WITH TDS OPERATION. | RR | TDS |  | 07/14/2022 | NBR-196S | 6.5 | SDGM-1235
1065 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | NBR-196S | Hrs | SDGM-1235
1066 | FOT | BLH | 42.5 | 12 Jul 1130 - 0500 | 2995 | 899524 | 7" LINER HANGER STUCK IN CASED VERTICAL SECTION OF WELL, 818' BELOW ROTARY TABLE. | TF | HGRL |  | 07/14/2022 | NBR-196S | 17.5 | SDGM-1235
1067 | FOT | RIG | 23 | 13 Jul 1230 - 1130 | 12671 | 899529 | ELECTRICAL ISSUES ENCOUNTERED WITH TDS OPERATION. | RR | TDS |  | 07/14/2022 | NBR-196S | 6.5 | SDGM-1235
1068 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | SCTD-1 | Hrs | SDGM-1034
1069 | FOT | SDM | 20.5 | 13 Jul 2330 - 2000 | 11985 | 899652 | DOWNHOLE MWD TOOL FAILURE. | BHA | MWD |  | 07/14/2022 | SCTD-1 | 15 | SDGM-1034
1070 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | SINO-36L | Hrs | SDGM-458
1071 | HELD | TK1 | 173 | 07 Jul 2330 - 0500 | 5400 | 899508 | PROBLEM IN HOLE ACCESSIBILITY. TK1 | JF | LINR |  | 07/14/2022 | SINO-36L | 24 | SDGM-458
1072 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | SND-2005 | Hrs | MHKK-2
1073 | HERR | RIG | 11.5 | 14 Jul 1730 - 0500 | 13903 | 899640 | FOUND A SMALL PIECE OF METAL LODGED IN BETWEEN BIT BLADES & 1 PIECE LODGED IN NEAR BIT REAMER. | FISH | BHA |  | 07/14/2022 | SND-2005 | 11.5 | MHKK-2
1074 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | SND-2008 | Hrs | HRDH-1812
1075 | STDP | RIG | 168 | 07 Jul 0500 - 0500 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS, POH TO CHECK STRG FOUND STRG TWISTED OFF AT 2ND DC ABOVE MILL | STUK | DP |  | 07/14/2022 | SND-2008 | 24 | HRDH-1812
1076 | FOT | ITS | 4 | 14 Jul 1900 - 2300 | 128 | 899636 | ITS POWER TONGUE CAN'T APPLY M/U REUIRED FOR M/U SHOE TRACK- LEAK ENCOUNTERED WITHIN CRT PKR CUP SEAL | TF | CTRQ |  | 07/14/2022 | SP-258 | 4 | JNAB-872212
1077 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | SP-258 | Hrs | JNAB-872212
1078 | STBH | ARM | 236 | 05 Jul 0500 - 0500 | 820 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/14/2022 | SP-258 | 20 | JNAB-872212
1079 | FOT | ITS | 4 | 14 Jul 1900 - 2300 | 128 | 899636 | ITS POWER TONGUE CAN'T APPLY M/U REUIRED FOR M/U SHOE TRACK- LEAK ENCOUNTERED WITHIN CRT PKR CUP SEAL | TF | CTRQ |  | 07/14/2022 | SP-258 | 4 | JNAB-872212
1080 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | SSA-202 | Hrs | QTIF-191
1081 | LHFL | RIG | 2.5 | 14 Jul 1130 - 1400 | 9002 | 899654 | OBSERVED LEAK ON STAND PIPE CONNECTION | RR | HSYS |  | 07/14/2022 | SSA-202 | 2.5 | QTIF-191
1082 | FOT | WDS | 22.5 | 13 Jul 0830 - 0700 | 7422 | 899619 | WFD LWD TOOLS LOST SIGNAL. | BHA | LWD |  | 07/14/2022 | T216 | 2 | ANDR-338
1083 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/14/2022 | T216 | Hrs | ANDR-338
1084 | IDPR | WDS | 5 | 14 Jul 0000 - 0500 | 7815 | 899607 | LOW ROP | LROP | BHA |  | 07/14/2022 | T216 | 5 | ANDR-338
1085 | FOT | WDS | 22.5 | 13 Jul 0830 - 0700 | 7422 | 899619 | WFD LWD TOOLS LOST SIGNAL. | BHA | LWD |  | 07/14/2022 | T216 | 2 | ANDR-338
1086 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ADC-17 | Hrs | ZULF-1210
1087 | FOT | SCP | 29.5 | 14 Jul 1215 - 0145 | 5212 | 899678 | PACKER #1 FAILING TO HOLD PRESSURE. STARTED RE-SET PACKER OPERATION | TF | PKR |  | 07/15/2022 | ADC-17 | 12.75 | ZULF-1210
1088 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ADC-23 | Hrs | KIDN-23
1089 | FOT | SWL | 3 | 15 Jul 0200 - 0500 | 14414 | 899754 | W/L XPT/GR TOOL PRESSURE GAUGE FAILED WHILE TAKING PRESSURES | TF | WLT |  | 07/15/2022 | ADC-23 | 3 | KIDN-23
1090 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ADC-31 | Hrs | SDGM-1181
1091 | STDP | RIG | 79.75 | 12 Jul 1930 - 0315 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/15/2022 | ADC-31 | 22.25 | SDGM-1181
1092 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ADC-50 | Hrs | SFNY-1176
1093 | FRFM | ARM | 200 | 06 Jul 1445 - 0500 | 3801 | 899340 | AT 3801', LOST COMPLETE CIRCULATION WITH 89 PCF WBM. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS. PUMPED 8 CMT PLUGS AND RECURE LOSSES. | LCIR | NA |  | 07/15/2022 | ADC-50 | 24 | SFNY-1176
1094 | 6844 | 6156 | TI | E | 3625 | STDP | CONTD RIH LOG #4 MDT - TLC ON 4" DP STDS F/ 5,018 FT TO LATCH DEPTH AT 6,156 FT.- CONTROL SPEED 3 MIN/STD SLIP TO SLIP.- FILL STRING AND BREAK CIRC EVERY 10 STD.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 5018 | RIG | 07/15/2022 | ADC-53L | LOG | HRDH-530
1095 | 6844 |  | CIRC | E | 3625 | MPMP | CIRC 1.5 STRING VOLUME. MEANWHILE HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW.- FR: 250 GPM & PRESS: 280 PSI. - CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/15/2022 | ADC-53L | LOG | HRDH-530
1096 | 6844 |  | OTH | E | 3625 | NA | HPJSM. M/U SLB S.E.S. & FEED WIRE LINE CABLE. RIH WIRE LINE CABLE AND LATCH INTO CONNECTOR AS PER SLB WIRELINE ENGINEER INSTRUCTION.- APPLY 250 PSI PUMP PRESS TO ASSIST IN LATCHING PROCESS AS PER SLB ENG.- LATCH INTO WET CONNECTOR PROFILE, FUNCTION TEST SLB TOOLS, OK.- PERFORM PULL TENSION TEST TO 3,100 LBS, OK.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/15/2022 | ADC-53L | LOG | HRDH-530
1097 | 6844 | 6481 | ST | E | 3625 | STDP | RIH LOG #4 MDT - TLC ON 4" DP F/ 6,156 FT TO 6,481 FT AT CONTROL SPEED. - CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6156 | RIG | 07/15/2022 | ADC-53L | LOG | HRDH-530
1098 | 6844 | 6629 | LOG | E | 3625 | WLT | PERFORM LOG #4. TOOK PRESS POINTS FROM 6,481 FT TO 6,629 FT (TOP TO BOTTOM) AS PER PROGRAM. ON GOING AT REPORT TIME.- PERFORMED 5 & 10 MINS STICKY TEST PRIOR PP AND 20 MINS MAX STATIONARY TIME.- 20/21 TOTAL PP: 19 VALID & 1 TIGHT.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6481 | SWL | 07/15/2022 | ADC-53L | LOG | HRDH-530
1099 | 113.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/15/2022 | ADC-53L | Type | HRDH-530
1100
1101
1102 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ADES-14 | Hrs | HWYH-379
1103 | UNKN | SWL | 3 | 15 Jul 0530 - 0830 | 11243 | 899713 | WAIT ON SLB TO CHANGE WIRE LINE SHEAVE | HSEI | NA |  | 07/15/2022 | ADES-14 | 3 | HWYH-379
1104 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ADES-157 | Hrs | HRDH-1844
1105 | FOT | GEP | 53.5 | 13 Jul 2330 - 0500 | 14932 | 899679 | N/U WG TBG BONNET AND TEST VOIDS, NOT HOLD. | WH | WH |  | 07/15/2022 | ADES-157 | 24 | HRDH-1844
1106 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ADES-174 | Hrs | GHZL-29
1107 | FOT | SDM | 21.5 | 14 Jul 2230 - 0500 | 13750 | 899638 | SLB NEAR BIT GR FAILURE DURING DRILLING | BHA | LWD |  | 07/15/2022 | ADES-174 | 15 | GHZL-29
1108 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | AOD-111 | Hrs | MRJN-728
1109 | HERR | HCO | .75 | 15 Jul 0700 - 0745 | 0 | 899734 | HALLIBURTON PDHMS CABLE DISCONNECTED AT THE SPLICE ON THE RIG FLOOR. | JF | TBG |  | 07/15/2022 | AOD-111 | .75 | MRJN-728
1110 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ARO-3003 | Hrs | SFNY-4220
1111 | FOT | RIG | 22.25 | 15 Jul 0645 - 0500 | 105 | 899752 | WHILE DRLLING 34" HOLE AT 239', 5-1/2" HWDP SHEARED OFF 2.5" ABOVE TOOL JT, LEAVING TOF +/-3' BELOW THE SEA LEVEL, CANNOT GO OVER FISH W/ OVERSHOT DUE TO LEANING OVER IN THE WATER TOO FAR OFF CENTER OF WELL | BHA | HWDP |  | 07/15/2022 | ARO-3003 | 22.25 | SFNY-4220
1112 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ARO-3004 | Hrs | MRJN-2060
1113 | FOT | SWL | 3 | 15 Jul 1400 - 1700 | 9578 | 899732 | FAIL PRESSURE TEST ON SLB WIRELINE / PCE RIG UP. | TF | WLT |  | 07/15/2022 | ARO-3004 | 3 | MRJN-2060
1114 | FOT | WI1 | 39.5 | 13 Jul 1100 - 0600 | 6231 | 899656 | WFD HYRAULIC TBG CUTTER FAILED TO CUT 4-1/2" LOWER COMPLETION TBG. | TF | CUT |  | 07/15/2022 | ENSCO-54 | 1 | ABSF-17
1115 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | ENSCO-54 | Hrs | ABSF-17
1116 | STCT | ARM | 182.5 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/15/2022 | ENSCO-54 | 23 | ABSF-17
1117 | FOT | WI1 | 39.5 | 13 Jul 1100 - 0600 | 6231 | 899656 | WFD HYRAULIC TBG CUTTER FAILED TO CUT 4-1/2" LOWER COMPLETION TBG. | TF | CUT |  | 07/15/2022 | ENSCO-54 | 1 | ABSF-17
1118 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | JACK-203 | Hrs | HZEM-849
1119 | LCRW | ARM | 133.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/15/2022 | JACK-203 | 24 | HZEM-849
1120 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | MP-1 | Hrs | MRJN-78
1121 | FOT | ARN | 1.5 | 15 Jul 0130 - 0300 | 12293 | 899755 | LOST COMMUNICATION WITH ARAMCO V-SAT WHILE GEO-STEERING THROUGH THE RESERVOIR & CHC UNTIL COMMENCE COMMUNICATION. | TF | COMP |  | 07/15/2022 | MP-1 | 1.5 | MRJN-78
1122 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | NBR-196S | Hrs | SDGM-1235
1123 | FOT | BLH | 66.5 | 12 Jul 1130 - 0500 | 2995 | 899524 | 7" LINER HANGER STUCK IN CASED VERTICAL SECTION OF WELL, 818' BELOW ROTARY TABLE. | TF | HGRL |  | 07/15/2022 | NBR-196S | 24 | SDGM-1235
1124 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | NBR-20S | Hrs | HMYM-433514
1125 | HERR | SPR | 1 | 15 Jul 2245 - 2345 | 2828 | 899753 | CRT STINGER BACKED OUT OF CRT. | JF | CTRQ |  | 07/15/2022 | NBR-20S | 1 | HMYM-433514
1126 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | NBR-304S | Hrs | HRDH-1958
1127 | CFFM | ARM | 13.75 | 15 Jul 1515 - 0500 | 9537 | 899714 | HAD LOSSES ON 1ST STAGE CEMENTING OF 9-5/8" CASING | CMT | NA |  | 07/15/2022 | NBR-304S | 13.75 | HRDH-1958
1128 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | PA-326S | Hrs | WDYH-16
1129 | IBHA | SAM | 18.75 | 14 Jul 1815 - 1300 | 17052 | 899608 | WHILE RIH WITH SAMAA WBCO HAD HELD DOWN WITH MAX 5-10 K,LB'S (SOWT) AT 17,052 FT, TRIED TO PASS AT SEVERAL TIMES WITH ROTATE STRING WITHOUT SUCCESS. | BHA | WBCL |  | 07/15/2022 | PA-326S | 8 | WDYH-16
1130 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | SCTD-2 | Hrs | HRDH-2148
1131 | FOT | RIG | 9 | 15 Jul 2000 - 0500 | 12250 | 899733 | LEAK IN THE REEL MONIFOLD. SHUT-IN THE WELL. WORK ON LEAK. | RR | CSYS |  | 07/15/2022 | SCTD-2 | 9 | HRDH-2148
1132 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | SINO-10 | Hrs | JLDI-38
1133 | XTTE | SAM | 1.5 | 15 Jul 1000 - 1130 | 10140 | 899692 | UN-ABLE TO UN-SET SAMA PACKER | TF | WBCL |  | 07/15/2022 | SINO-10 | 1.5 | JLDI-38
1134 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | SINO-36L | Hrs | SDGM-458
1135 | HELD | TK1 | 197 | 07 Jul 2330 - 0500 | 5400 | 899508 | PROBLEM IN HOLE ACCESSIBILITY. TK1 | JF | LINR |  | 07/15/2022 | SINO-36L | 24 | SDGM-458
1136 | 6780 |  | HT | N |  | BHA | CONT. POOH WITH 8-1/2" MOTOR BHA SURFACE, L/D SAME .- BIT DULL: 1-1-WT-A-X-I-NO-TD. | 6780 |  | RIG | 07/15/2022 | SINO-43L | DRLG | UTMN-4068
1137 | 6780 |  | OTH | E | 3665 | NA | HPJSM, R/U BH W/L LOGGING EQUIPMENT, M/U BH W/L LOGGING TOOLS RUN #1 [GR-WGI-HDIL-MLL]. (OOS)> TOOL LENGTH: 95', MAX OD: 4.2".> FUNCTION TESTED & PERFORM TOOL CALIBRATION @ SURFACE.> MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6780 |  | BAW | 07/15/2022 | SINO-43L | LOG | UTMN-4068
1138 | 6780 | 0 | LOG | E | 3665 | WLT | RIH BH W/L LOGGING TOOLS RUN #1 [GR-WGI-HDIL-MLL] TO BTM @ 6780', LOG UP TO 9-5/8" CSG, CONT. POOH TO SURFACE & L/D TOOLS. (OOS).> LOG UP MAIN PASS LOG F/ 6780' TO 5921'.> LOG UP REPEAT PASS F/ 6150' TO 5950'.> AVERAGE HOLE DIAMETER: 8.80".> MONITOR WELL ON TRIP TANK, WELL STATIC. | 6780 | 6780 | BAW | 07/15/2022 | SINO-43L | LOG | UTMN-4068
1139 | 6780 | 0 | LOG | E | 3665 | WLT | HPJSM, P/U, M/U & RIH W/ BH W/L RUN # 2 [GR -CN-ZDL] TO 6775', POOH WHILE LOGGING UP TO 9-5/8" CSG, CONT. POOH TO SURFACE WHILE LOG UP GR, L/D TOOLS & R/D BH WIRELINE. (OOS).> FUNCTION TESTED LOGGING TOOLS STRING @ SURFACE BEFORE RIH.> TOTAL LENGTH: 63', MAX OD: 4.88".> LOG UP MAIN PASS F/ 6775' TO 5921'. > LOG REPEAT PASS F/ 6150' TO 5950'.> MONITOR WELLON TRIP TANK, WELL STATIC. | 6780 | 6780 | BAW | 07/15/2022 | SINO-43L | LOG | UTMN-4068
1140 | 6780 |  | HT | E | 3665 | BHA | HPJSM, P/U, M/U & RIH 8 1/2" CONDITION TRIP ROTARY BHA. (OOS).> BHA: 8-1/2" TCI BIT, 8-1/2" NBRR W/ FV, 1 X 6-1/2" DC, 8-1/2" STRR, 1 X 6-1/2" DC, 8-1/2" STRR, 1 X 6-1/2" DC, X/O, 18 X 5" HWDP, 6-1/2" JAR, 12 X 5" HWDP.> MONITOR WELL ON TRIP TANK. | 6780 |  | RIG | 07/15/2022 | SINO-43L | CT | UTMN-4068
1141 | 6780 | 6780 | TI | E | 3665 | STDP | RIH 8 1/2" CONDITION TRIP BHA ON 5" D/P TO BTM @ 6780'. (OOS).> HOLE IN GOOD CONDITION.> MONITOR WELL ON TRIP TANK.> WASH DOWN LAST STAND TO BTM. | 6780 | 500 | RIG | 07/15/2022 | SINO-43L | CT | UTMN-4068
1142 | 6780 |  | CIRC | E | 3665 | MPMP | SWEEP HOLE WITH 2 X 50 BBL HI-VIS PILL AND CIRCULATE TILL SHALE SHAKERS CLEAN. ONGOING. (OOS). | 6780 |  | RIG | 07/15/2022 | SINO-43L | CT | UTMN-4068
1143 | 23 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" SECTION WIRELINE LOGGING. | 23 | 3665 | 15 Jul 0045 | 07/15/2022 | SINO-43L | Type | UTMN-4068
1144
1145
1146 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | SND-2005 | Hrs | MHKK-2
1147 | HERR | RIG | 35.5 | 14 Jul 1730 - 0500 | 13903 | 899640 | FOUND A SMALL PIECE OF METAL LODGED IN BETWEEN BIT BLADES (1.5") & 1 PIECE (2" U-SHAPED) LODGED IN NEAR BIT REAMER. | FISH | BHA |  | 07/15/2022 | SND-2005 | 24 | MHKK-2
1148 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | SND-2008 | Hrs | HRDH-1812
1149 | STDP | RIG | 192 | 07 Jul 0500 - 0500 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS, POH TO CHECK STRG FOUND STRG TWISTED OFF AT 2ND DC ABOVE MILL | STUK | DP |  | 07/15/2022 | SND-2008 | 24 | HRDH-1812
1150 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | SP-258 | Hrs | JNAB-872212
1151 | STBH | ARM | 241 | 05 Jul 0500 - 1000 | 858 | 899258 | 22" HOLE PACK OFF RESULTING IN PIPE STUCK. | STUK | HWDP |  | 07/15/2022 | SP-258 | 5 | JNAB-872212
1152 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/15/2022 | T216 | Hrs | ANDR-338
1153 | FOT | RIG | 4 | 15 Jul 1030 - 1430 | 7900 | 899712 | TDS WASH PIPE FAILURE | RR | TDS |  | 07/15/2022 | T216 | 4 | ANDR-338
1154 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | ADC-31 | Hrs | SDGM-1181
1155 | STDP | RIG | 88.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/16/2022 | ADC-31 | 8.5 | SDGM-1181
1156 | 8885 |  | D | N |  | RSS | DRILLED 16" HOLE SECTION WITH STAND ALONE RSS BHA FROM 8,645 FT. TO 8,885 FT. WITH FULL CIRCULATION. ENCOUNTERD PARTIAL LOSSES AT 8,885 FT. OF180 BBLS/HR.- PUMPED 100 BBLS OF 40 LB/BBL LCM PILL WHILE DRILLING AHEAD- WHILE DRILLING HOURLY ADDITIONS OF 10 SX EA MICA FINE AND MED, PLUS 1 BIG BAG EA OF MARBLE FINE AND MED EVERY 4 HOURS FOR LOSS CIRCPREVENTION AND PUMPING 50 BBLS OF 40 PPB BRIDGING PILL EVERY STD.- SURVEY BEFORE CONNECTION, 30 FT OFF BTM.- ERRATIC TORQUE. HIGH STICK-SLIP OBSERVED THROUGH OUT THE SECTION, ADJUSTED RPM AND WOB TO MITIGATE.- FR: 800-850 GPM, SPP: 2,400-2,600 PSI, RPM: 140-150, TQ: 9-18 KFT LBS, WOB: 25-45 KLBS.- AVG ROP: 23.5 FT/HR. | 8645 |  | SDM | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1157 | 8935 |  | D | N |  | RSS | DRILL 16" HOLE WITH RSS DRILLING BHA FROM 8,885 FT TO 8,935 FT TO OPEN LOSS ZONE.- PUMPED A SECOND 100 BBL, 40 LB/BBL LCM PILL WHILE DRILLING AHEAD- EVALUATE PARTIAL LOSSES REDUCE FROM 180 BBL/HR TO 120 BBLS/HR. | 8885 |  | SDM | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1158 | 8935 |  | CIRC | N | 3685 | MPMP | CIRCULATE AND PUMP A THIRD 100 BBL 40 PPB LCM PILL.- EVALUATE PARTIAL LOSS RATE LOSSES INCREASED- 600 BPH AT 850 GPM- 400 BPH AT 500 GPM- 200 BPH AT 300 GPM | 8935 |  | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1159 | 8935 |  | OTH | N | 3685 | NA | PERFORM FLOWCHECK.- OBSERVED 180 BPH STATIC LOSSES. | 8935 |  | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1160 | 8935 | 8705 | BR | N | 3685 | STRG | POOH WHILE BACK REAMING 2 STDS FROM 8,935 FT TO 8,705 FT TO ENSURE FREE MOVEMENT UP OF THE DRILL STRING BEFORE OPENING PBL CIRCULATION SUB.- 500 GPM, 900 PSI, 40 RPM.- 400 BPH DOWNHOLE LOSSES. | 8935 | 8935 | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1161 | 8935 | 8935 | RW | N | 3685 | BIT | RUN BACK TO BTM WITH 2 STDS FROM 8,705 FT TO 8,8935 FT TO ENSURE THE FREE MOVEMENT OF THE DRILL STRING PRIOR TO OPENING PBL CIRCULATION SUB.- 500 GPM, 900 PSI, 40 RPM.- 400 BPH DOWNHOLE LOSSES. | 8935 | 8705 | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1162 | 8935 |  | CIRC | N | 3685 | DSBT | DROP 2-1/2" ACTIVATION BALL, PUMP DOWN AND OPEN PBL CIRCULATION SUB.- 500 GPM, 900 PSI BEFORE OPENING PBL PORTS- 500 GPM, 550 PSI AFTER OPENING PBL PORTS | 8935 |  | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1163 | 8935 |  | CIRC | N | 3685 | DSBT | SPOT 1ST 100 BBL 200 PPB LCM PILL THROUGH PBL SUB.- 400 GPM, 350 PSI, 20 RPM. | 8935 |  | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1164 | 8935 | 8000 | ST | N | 3685 | STDP | POOH 9 STDS FROM 8,935 FT TO 8,000 FT.- HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK. OBS. 180 BBLS/HR STATIC LOSSES | 8935 | 8935 | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1165 | 8935 |  | CIRC | N | 3685 | DSBT | ALLOW LCM TO SOAK.- MONITOR WELL ON TRIP TANK. OBS STATIC LOSSES REDUCED TO 150 BBLS/HR.(30 BBL / HR IMPROVEMENT)- ROTATE WITH 15 RPM/RECIPROCATE STRING. | 8935 |  | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1166 | 8935 | 8935 | ST | N | 3685 | STDP | RIH 16" RSS BHA FROM 8,000 FT TO 8,935 FT TO SPOT 2ND LCM PILL.- MONITOR WELL ON TRIP TANK. OBS. 150 BBLS/HR STATIC LOSSES. | 8935 | 8000 | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1167 | 8935 |  | CIRC | N | 3685 | DSBT | SPOT 2ND 100 BBL 200 PPB LCM PILL THROUGH PBL SUB.- 400 GPM, 300 PSI, 20 RPM. | 8935 |  | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1168 | 8935 | 8200 | ST | N | 3685 | STDP | POOH 7 STDS FROM 8,935 FT TO 8,200 FT.- HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK. OBS. 150 BBLS/HR STATIC LOSSES. | 8935 | 8935 | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1169 | 8935 |  | CIRC | N | 3685 | DSBT | ALLOW LCM TO SOAK.- MONITOR WELL ON TRIP TANK. OBS STATIC LOSSES REDUCE TO 140 BBLS/HR. (10 BBL / HR IMPROVEMENT)- ROTATE WITH 15 RPM/RECIPROCATE STRING. | 8935 |  | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1170 | 8935 | 8935 | ST | N | 3685 | STDP | RIH 16" RSS BHA FROM 8,200 FT TO 8,935 FT TO SPOT 3RD LCM PILL- MONITOR WELL ON TRIP TANK. OBS. 140 BBLS/HR STATIC LOSSES | 8935 | 8200 | RIG | 07/16/2022 | ADC-41L | DRLG | SDGM-1244
1171 | 11.75 | OOS | Category | DOOS ID | CDHL | Out of Scope Summary | WHILE DRILLING AHEAD IN THE BLFR FORMATION, PARTIAL LOSSES WERE ENCOUNTERED AT 8,885 FT. AT 600 BPH AT 20 BPM PUMP RATE. 3 X 100 BBLS OF 40 LB/BBL LCM PILL WERE PUMPED WHILE DRILLING AHEAD TO 8,935 FT TO EXPOSE THE LCZ, A TOTAL OF 3 X 100 BBL 200 PPB LCM PILLS WERE THEN PUMPED THROUGH THE PBL SUB, STRING PULLED ABOVE PILL EACH TIME AND ALLOWED TO SOAK FOR 1.5 HRS EA. AND THEN RAN BACK TO BTM TO PUMP THE FOLLOWING ONE. LOSS RATE WHILE STATIC AFTER FIRST PILL WENT FROM 180 BBL/HR TO 150 BBLS/HR, AFTER SECOND PILL PUMPED AND SOAKED LOSSES IMPROVED TO 140 BBLS/HRS AND STAYED AT 140 BBLS/HRS. | 11.75 | 3685 | 16 Jul 0030 | 07/16/2022 | ADC-41L | Type | SDGM-1244
1172
1173
1174 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | ADC-49 | Hrs | HWYH-1104
1175 | WOTO | SCM | 3 | 16 Jul 1930 - 2230 | 4100 | 899717 | WAIT ON SLB CEMENT UNIT FROM ANOTHER LOCATION. MEANWHILE CONT TO CIRC THROUGH WELLHEAD SIDE OUTLET VALVES | WO | NA |  | 07/16/2022 | ADC-49 | 3 | HWYH-1104
1176 | WC20 | ARM | 13 | 16 Jul 1600 - 0500 | 3944 | 899719 | WHILE DRILLING 12-1/4" HOLE, ENCOUNTERED TOTAL LOSS OF CIRCULATION AT 3805'. ATTEMPT WITH MUD CAP DRILLING. OBSERVE WELL KICK. | WCNT | NA |  | 07/16/2022 | ADC-50 | 13 | SFNY-1176
1177 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | ADC-50 | Hrs | SFNY-1176
1178 | FRFM | ARM | 208 | 06 Jul 1445 - 1300 | 3801 | 899340 | AT 3801', LOST COMPLETE CIRCULATION WITH 89 PCF WBM. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS. PUMPED 8 CMT PLUGS AND RECURE LOSSES. | LCIR | NA |  | 07/16/2022 | ADC-50 | 8 | SFNY-1176
1179 | WC20 | ARM | 13 | 16 Jul 1600 - 0500 | 3944 | 899719 | WHILE DRILLING 12-1/4" HOLE, ENCOUNTERED TOTAL LOSS OF CIRCULATION AT 3805'. ATTEMPT WITH MUD CAP DRILLING. OBSERVE WELL KICK. | WCNT | NA |  | 07/16/2022 | ADC-50 | 13 | SFNY-1176
1180 | 6844 | 6689 | LOG | E | 3625 | WLT | PERFORM LOG #4. TOOK PRESS POINTS FROM 6,629 FT TO 6,689 FT (TOP TO BOTTOM) AS PER PROGRAM.- PERFORMED 5 & 10 MINS STICKY TEST PRIOR PP AND 20 MINS MAX STATIONARY TIME.- 21/21 TOTAL PP: 20 VALID & 1 TIGHT.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6629 | SWL | 07/16/2022 | ADC-53L | LOG | HRDH-530
1181 | 6844 | 6578 | LOG | E | 3625 | WLT | PERFORM LOG #4 MDT-TLC. PUMPED OUT AND COLLECTED SAMPLES F/6,629 FT TO 6,578 FT (BOTTOM TO TOP) AS PER PROGRAM. ON GOING AT REPORT TIME.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- MOVE STRING EVERY 4 HOURS/SESSION & CONFIRM STRING FREE, OK.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 1/11.- PUMP OUT COMPLETED: 3/11.- PUMP OUT INTO WELLBORE 1.85 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 1.85 BBLS, - PUMP OUT FLUID TYPE: 1X OIL & 2X WATER.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6629 | SWL | 07/16/2022 | ADC-53L | LOG | HRDH-530
1182 | 137.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/16/2022 | ADC-53L | Type | HRDH-530
1183
1184
1185 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | ADC-59L | Hrs | HWYH-1324
1186 | FOT | TSC | 7 | 16 Jul 1230 - 0500 | 5568 | 899716 | OBSERVED HYDRAULIC CATWALK MULFUNCTION. | TF | PEL |  | 07/16/2022 | ADC-59L | 7 | HWYH-1324
1187 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | ADES-157 | Hrs | HRDH-1844
1188 | FOT | GEP | 77.5 | 13 Jul 2330 - 0500 | 14932 | 899679 | N/U WG TBG BONNET AND TEST VOIDS, NOT HOLD. | WH | WH |  | 07/16/2022 | ADES-157 | 24 | HRDH-1844
1189 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | AOD-111 | Hrs | MRJN-728
1190 | XTTE | SPL | 16 | 16 Jul 0815 - 0015 | 7882 | 899740 | ATTEMPTED RETRIEVING PXN WITH NO SUCCESS. | JF | SLICK |  | 07/16/2022 | AOD-111 | 16 | MRJN-728
1191 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | DQ-47 | Hrs | KHRS-497
1192 | DSFT | BC | 6.5 | 16 Jul 1900 - 0500 | 9554 | 899760 | RIH W/ P&A KIT TO ISOLATE LOSS ZONE AT 9600', WHILE PRESS. UP STRG TO 3000 PSI TO SET THE PKR, HAD SUDDEN PRESS. DROP TO ZERO ONCE REACHED 3000 PSI. | JF | PKR |  | 07/16/2022 | DQ-47 | 6.5 | KHRS-497
1193 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | ED-85A | Hrs | ZULF-2063
1194 | FOT | RIG | 3 | 16 Jul 1745 - 2045 | 10001 | 899737 | LEAKAGE IN MUD PUMP VALVE AND SEAT | RR | MPMP |  | 07/16/2022 | ED-85A | 3 | ZULF-2063
1195 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | ENSCO-54 | Hrs | ABSF-17
1196 | STCT | ARM | 206.5 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/16/2022 | ENSCO-54 | 24 | ABSF-17
1197 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | ENSCO-76 | Hrs | MRJN-853
1198 | CFFM | ARM | 84 | 13 Jul 1145 - 0500 | 6116 | 899694 | LOST CIRCULATION UPON PENETRATING LAWHAH (LHHR) | LCIR | LCM |  | 07/16/2022 | ENSCO-76 | 22.25 | MRJN-853
1199 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | HI-5 | Hrs | MHRH-57
1200 | UNKN | RIG | 3 | 16 Jul 1730 - 2030 | 1125 | 899758 | WHILE FLOOR HAND SET 4" DP SLIPS IN ROTARY, SLIPS CAME IN CONTACT WITH FLOOR HAND RIGHT FOOT TOE, SHUT DOWN OPERATION AND TRANSFER INJURY PERSON TO RIG CLINIC, MEDIC APPLY FIRST AID AND ASK FOR MEDIVAC FOR FURTHER EXAMINATION, REQUEST MEDIVAC CHOPPER, CHOPPER ARRIVED @ 18:30, TAKE INJURY PERSON AND DEPART @ 19:00 HR'S. | HSEI | NA |  | 07/16/2022 | HI-5 | 3 | MHRH-57
1201 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | JACK-203 | Hrs | HZEM-849
1202 | LCRW | ARM | 157.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/16/2022 | JACK-203 | 24 | HZEM-849
1203 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | MP-1 | Hrs | MRJN-78
1204 | FOT | BHI | .5 | 16 Jul 1730 - 1800 | 12695 | 899736 | LOST MWD/LWD SIGNAL WHILE DRILLING THROUGH MKFJ RESERVOIR. | BHA | LWD |  | 07/16/2022 | MP-1 | .5 | MRJN-78
1205 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | NBR-196S | Hrs | SDGM-1235
1206 | FOT | BLH | 90.5 | 12 Jul 1130 - 0500 | 2995 | 899524 | 7" LINER HANGER STUCK IN CASED VERTICAL SECTION OF WELL, 818' BELOW ROTARY TABLE. | TF | HGRL |  | 07/16/2022 | NBR-196S | 24 | SDGM-1235
1207 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | NBR-20S | Hrs | HMYM-433514
1208 | HERR | SPR | 1.75 | 15 Jul 2245 - 0700 | 2828 | 899753 | CRT STINGER BACKED OUT OF CRT. DAMAGED PACKER RUBBER FROM STABBING CRT WITH NO PROTECTOR INSTALLED. | JF | CTRQ |  | 07/16/2022 | NBR-20S | .75 | HMYM-433514
1209 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | NBR-304S | Hrs | HRDH-1958
1210 | CFFM | ARM | 37.75 | 15 Jul 1515 - 0500 | 9537 | 899714 | HAD LOSSES ON 1ST STAGE CEMENTING OF 9-5/8" CASING | CMT | NA |  | 07/16/2022 | NBR-304S | 24 | HRDH-1958
1211 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | NBR-633S | Hrs | HRDH-2234
1212 | FOT | SAM | 24 | 16 Jul 0500 - 0500 | 16810 | 899756 | RUNNING INCORRECT SAMA BRUSH GRADE AND COULDN'T PASS 7" 35# LINER AT DEPTH 12356' AND POH & FOUND MARK ON BRUSH OD. | BHA | WBCL |  | 07/16/2022 | NBR-633S | 24 | HRDH-2234
1213 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SCTD-2 | Hrs | HRDH-2148
1214 | FOT | RIG | 33 | 15 Jul 2000 - 0500 | 12250 | 899733 | LEAK IN THE REEL MONIFOLD. SHUT-IN THE WELL. WORK ON LEAK. | RR | CSYS |  | 07/16/2022 | SCTD-2 | 24 | HRDH-2148
1215 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SINO-15L | Hrs | ANDR-420
1216 | FOT | RIG | 2.5 | 16 Jul 0230 - 0500 | 10395 | 899697 | TOP DRIVE STOPPED ROTATION, UNABLE TO BREAK TDS CONNECTION | RR | TDS |  | 07/16/2022 | SINO-15L | 2.5 | ANDR-420
1217 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SINO-19L | Hrs | UTMN-252
1218 | FOT | SPS | 2 | 16 Jul 0300 - 0500 | 8696 | 899759 | LOST SIGNAL FROM MWD | SURV | MS |  | 07/16/2022 | SINO-19L | 2 | UTMN-252
1219 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SINO-1L | Hrs | ABJF-20
1220 | FOT | RIG | 6.5 | 16 Jul 1700 - 2330 | 0 | 899741 | HAD FAILURE IN DRAWWORKS SYSTEM, NOT ABLE TO ROTATE DRAWWORKS DRUM. | RR | DWKS |  | 07/16/2022 | SINO-1L | 6.5 | ABJF-20
1221 | FOT | SPS | 20 | 16 Jul 0900 - 0500 | 8001 | 899735 | WHILE RE-LOG WITH LWD TOOLS, HAD LWD_CTN TOOL FAILURE, TROUBLE SHOOTING, NO SUCCESS. | BHA | LWD |  | 07/16/2022 | SINO-36L | 20 | SDGM-458
1222 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SINO-36L | Hrs | SDGM-458
1223 | HELD | TK1 | 201 | 07 Jul 2330 - 0900 | 5400 | 899508 | PROBLEM IN HOLE ACCESSIBILITY. TK1 | JF | LINR |  | 07/16/2022 | SINO-36L | 4 | SDGM-458
1224 | FOT | SPS | 20 | 16 Jul 0900 - 0500 | 8001 | 899735 | WHILE RE-LOG WITH LWD TOOLS, HAD LWD_CTN TOOL FAILURE, TROUBLE SHOOTING, NO SUCCESS. | BHA | LWD |  | 07/16/2022 | SINO-36L | 20 | SDGM-458
1225 | 6780 |  | CIRC | E | 3665 | MPMP | SWEEP HOLE WITH 2 X 50 BBL HI-VIS PILL AND CIRCULATE TILL SHALE SHAKERS CLEAN. SPOT 150 BBL LUBRICATED PILL ON BTM. (OOS). | 6780 |  | RIG | 07/16/2022 | SINO-43L | CT | UTMN-4068
1226 | 6780 |  | CIRC | E | 3665 | MPMP | FLOW CHECK, WELL STATIC.(OOS). | 6780 |  | RIG | 07/16/2022 | SINO-43L | CT | UTMN-4068
1227 | 6780 | 5923 | ST | E | 3665 | STDP | POOH W/ 8-1/2" CONDITION TRIP TO 5923' (9-5/8" CSG SHOE), HOLE IN GOOD CONDITION. (OOS).- MONITOR WELL ON TRIP TANK. | 6780 | 6780 | RIG | 07/16/2022 | SINO-43L | CT | UTMN-4068
1228 | 6780 |  | CIRC | E | 3665 | MPMP | FLOW CHECK, WELL STATIC. (OOS). | 6780 |  | RIG | 07/16/2022 | SINO-43L | CT | UTMN-4068
1229 | 6780 | 108 | TO | E | 3665 | STDP | POOH W/ 8-1/2" CONDITION TRIP F/ 5923' TO TOP OF BHA. (OOS).- MONITOR WELL ON TRIP TANK. | 6780 | 5923 | RIG | 07/16/2022 | SINO-43L | CT | UTMN-4068
1230 | 6780 |  | CIRC | E | 3665 | MPMP | FLOW CHECK, WELL STATIC. (OOS). | 6780 |  | RIG | 07/16/2022 | SINO-43L | CT | UTMN-4068
1231 | 6780 |  | HT | E | 3665 | BHA | POOH W/ 8-1/2" CONDITION TRIP TO SURFACE & L/D BHA. (OOS).- MONITOR WELL ON TRIP TANK. | 6780 |  | RIG | 07/16/2022 | SINO-43L | CT | UTMN-4068
1232 | 6780 |  | OTH | E | 3665 | NA | HPJSM, R/U BH W/L TOOLS & SHEAVES,P/U, M/U & RIH W/ RUN #3 (GR - FTEX) (PRESSURE TESTING) TO 6306'. (OOS).> TOTAL LOGGING TOOL LENGTH: 71.25', MAX OD: 4.25".> FUNCTION TEST TOOLS @ SURFACE.> MONITOR WELL ON TRIP TANK, WELL STATIC. | 6780 |  | BAW | 07/16/2022 | SINO-43L | LOG | UTMN-4068
1233 | 6780 | 6618 | LOG | E | 3665 | WLT | CONT. RIH W/ BH LOGGING TOOLS RUN #3 (GR - FTEX) ON W/L WHILE LOG-DOWN F/ 6306' T/ 6618'. (OOS).> PERFORM STICKY TEST @ 6306' FOR 20 MIN - OK, NO OVERPULL OBSERVED.> RECORD 10 OUT OF 10 PRESSURE POINTS F/ 6306' T/ 63618'. > PRESSURE POINTS @ 6306', 6310', 6316', 6406', 6540', 6585', 6590', 6594', 6610', 6610', 6618'.> MONITOR WELL ON TRIP TANK. | 6780 | 6306 | BAW | 07/16/2022 | SINO-43L | LOG | UTMN-4068
1234 | 6780 |  | OTH | E | 3665 | NA | POOH WITH BH RUN #3 TO SURFACE & L/D SAME. (OOS).> MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6780 |  | BAW | 07/16/2022 | SINO-43L | LOG | UTMN-4068
1235 | 6780 |  | OTH | N |  | NA | REMOVE 11" CAMERON WEAR BUSHING. | 6780 |  | RIG | 07/16/2022 | SINO-43L | WH | UTMN-4068
1236 | 6780 | 0 | LDP | N |  | STRG | P/U & M/U 6 STD 5" HWDP ON DERRICK.- MONITOR WELL ON TRIP TANK. | 6780 | 0 | RIG | 07/16/2022 | SINO-43L | DRLG | UTMN-4068
1237 | 6780 |  | HT | N |  | PEL | PJSM, R/D DP HANDLING EQUIPMENT. R/U TRS 7" POWER TONG AND JAM UNIT. | 6780 |  | BCR | 07/16/2022 | SINO-43L | CSG | UTMN-4068
1238 | 6780 | 294 | RCSG | N |  | CSTR | HPJSM, P/U, M/U & RIH 7" LINER (26#, J-55,N.VAM) TO 294 FT (7/111 JTS).- (DHP F.SHOE + 5 X 7" CSG JT + DHP F.COLLAR + 1 X 7" CSG JT + BAKER LANDING COLLAR + 1 X 7" CSG JT).- CHECK FLOAT EQUIPMENT ON SURFACE - OK. - THREAD LOCK ALL SHOE TRACK CONNECTIONS. | 6780 | 0 | BCR | 07/16/2022 | SINO-43L | CSG | UTMN-4068
1239 | 6780 | 4514 | RCSG | N |  | CTRQ | CONT. RIH 7" LINER (26#, J-55, N.VAM) F/ 249' T/ 3011' (74 / 111 JTS). ONGOING.- FILL UP CSG EVERY 5 JTS. | 6780 | 294 | BCR | 07/16/2022 | SINO-43L | CSG | UTMN-4068
1240 | 37.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" SECTION WIRELINE LOGGING. | 14.75 | 3665 | 15 Jul 0045 | 07/16/2022 | SINO-43L | Type | UTMN-4068
1241
1242
1243 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SND-2005 | Hrs | MHKK-2
1244 | HERR | RIG | 58 | 14 Jul 1730 - 0500 | 13903 | 899640 | FOUND A SMALL PIECE OF METAL LODGED IN BETWEEN BIT BLADES (1.5") & 1 PIECE (2" U-SHAPED) LODGED IN NEAR BIT REAMER. | FISH | BHA |  | 07/16/2022 | SND-2005 | 22.5 | MHKK-2
1245 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SND-2008 | Hrs | HRDH-1812
1246 | STDP | RIG | 216 | 07 Jul 0500 - 0500 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS, POH TO CHECK STRG FOUND STRG TWISTED OFF AT 2ND DC ABOVE MILL | STUK | DP |  | 07/16/2022 | SND-2008 | 24 | HRDH-1812
1247 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SP-103 | Hrs | KRSN-72
1248 | FOT | RIG | 2 | 16 Jul 0300 - 0500 | 9105 | 899739 | RIG REPAIR (TDS ELECTRIC PROBLEM) | RR | TDS |  | 07/16/2022 | SP-103 | 2 | KRSN-72
1249 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SP-110 | Hrs | BRRI-562
1250 | FOT | SJT | 12.5 | 16 Jul 1630 - 0500 | 13282 | 899695 | TAQA E-COIL TUBING CYCLING VALVE OPEN AND DEACTIVATED THE MLT ( MULTI LATERAL TOOLS) WHICH DIDN'T ALLOW TOOL TO ENTER LATERAL L-1-1. | BHA | CTAC |  | 07/16/2022 | SP-110 | 12.5 | BRRI-562
1251 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SP-260 | Hrs | HMYM-531802
1252 | FOT | BHI | 9.5 | 16 Jul 1930 - 0500 | 9067 | 899718 | BAD COMMUNICATION FROM RSS, TROUBLE SHOOTED, NO SUCCESS. DECIDED TO POOH AND CHANGE BAKER TOOLS. | BHA | RSS |  | 07/16/2022 | SP-260 | 9.5 | HMYM-531802
1253 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SP-261 | Hrs | HZEM-160212
1254 | FOT | SDM | 14.75 | 16 Jul 0615 - 0500 | 9110 | 899715 | SLB MWD SIGNAL LOSS. | BHA | MWD |  | 07/16/2022 | SP-261 | 14.75 | HZEM-160212
1255 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SP-306 | Hrs | MNIF-193
1256 | ISEQ | BHI | 1 | 16 Jul 2230 - 2330 | 9404 | 899696 | TROUBLESHOOT MWD POOR SIGNAL. | BHA | MWD |  | 07/16/2022 | SP-306 | 1 | MNIF-193
1257 | CFFM | ARM | 1 | 16 Jul 1800 - 1900 | 4107 | 899757 | GOT TOTAL LOSSES WHILE DRILLING ARUMA FM. | LCIR | MDCAP |  | 07/16/2022 | SSA-51 | 1 | MNIF-257
1258 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/16/2022 | SSA-51 | Hrs | MNIF-257
1259 | SDIR | BHI | .5 | 16 Jul 2300 - 2330 | 4313 | 899738 | STRING STALLED WHILE DRLG AT 4313', TRIED TO PICK STRG OFF BTM, FOUND SAME STUCK. | STUK | MMOT |  | 07/16/2022 | SSA-51 | .5 | MNIF-257
1260 | CFFM | ARM | 1 | 16 Jul 1800 - 1900 | 4107 | 899757 | GOT TOTAL LOSSES WHILE DRILLING ARUMA FM. | LCIR | MDCAP |  | 07/16/2022 | SSA-51 | 1 | MNIF-257
1261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADC-31 | Hrs | SDGM-1181
1262 | STDP | RIG | 112.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/17/2022 | ADC-31 | 24 | SDGM-1181
1263 |  |  | RIG | CIRC | 3685 | 8935 | SPOT 100 BBLS OF 200 PPB LCM PILL (3RD) IN OH THROUGH PBL SUB.- 400 GPM, 300 PSI, 20 RPM.- 250 BBLS/HR DYNAMIC LOSSES. |  |  | 8935 | 07/17/2022 | ADC-41L | MPMP | SDGM-1244
1264 | 8200 |  | RIG | TI | 3685 | 8935 | POOH 7 STDS F/ 8,935 FT TO 8,200 FT.- HOLE IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK.OBS. 140 BBLS/HR STATIC LOSSES. | 8935 |  | 8935 | 07/17/2022 | ADC-41L | SPDP | SDGM-1244
1265 |  |  | RIG | OTH | 3685 | 8935 | ALLOW LCM TO SOAK.- MONITOR WELL ON TRIP TANK. OBS STATIC LOSSES @143 BBLS/HR.- ROTATE WITH 15 RPM/RECIPROCATE STRING. |  |  | 8935 | 07/17/2022 | ADC-41L | NA | SDGM-1244
1266 | 8935 |  | RIG | TI | 3685 | 8935 | RIH 16" RSS BHA F/ 8000 FT TO 8935 FT.- MONITOR WELL ON TRIP TANK. OBS. 140 BBLS/HR STATIC LOSSES. | 8000 |  | 8935 | 07/17/2022 | ADC-41L | SPDP | SDGM-1244
1267 |  |  | RIG | CIRC | 3685 | 8935 | DROP 2 X 1-3/4DE-ACTIVATION BALLS, PUMP DOWN AND CLOSE PBL CIRCULATION SUB.- 300 GPM, 110 PSI BEFORE CLOSING PBL INCREASE TO 3150 PSI, CONFIRM BPL SUB CLOSED.- 300 GPM, 250 PSI AFTER CLOSING PBL CIRC SUB. |  |  | 8935 | 07/17/2022 | ADC-41L | MPMP | SDGM-1244
1268 |  |  | SDM | DMR |  | 8935 | DRILL 16" HOLE WITH RSS DRILLING BHA FROM 8,935 FT TO 9,010 FT TO EXPOSED LOSS ZONE IN LOWER FADHILI.- 25 - 30 KLBS, 600 GPM, 800-650 PSI, 150 RPM, 9-18 KFT-LBS.- LOSSES REDUCED FROM 400 BBL/HR TO 40 BBLS/HR- AV. ROP = 18 FT/HR. |  |  | 9010 | 07/17/2022 | ADC-41L | MRSS | SDGM-1244
1269 |  |  | RIG | OTH |  | 9010 | FLOW CHECK, STATIC LOSSES @ 4 BBL/HR. |  |  | 9010 | 07/17/2022 | ADC-41L | NA | SDGM-1244
1270 |  | 899747 | RIG | CIRC | 3705 | 9010 | ATTEMPTED TO RESUME DRILLING, START PUMP GRADUALLY TO 630 GPM, OBSERVED INCREASE IN FLOW OUT.- SHUT IN WELL, SIDPP AND SICP BOTH ARE ZERO. |  | WCNT | 9010 | 07/17/2022 | ADC-41L | MPMP | SDGM-1244
1271 |  | 899747 | RIG | CIRC | 3705 | 9010 | CIRCULATE THROUGH CHOKE WITH 245 BBLS 78 PCF MUD, OBSERVED CUT IN MUD WEIGHT FROM 78 PCF TO 74 PCF, OBS REDUCTION IN RETURN FLOW AND CIRCULATION PRESSURE DROPPED TO ZERO, INDICATING PUMPING INTO LCZ.- STOP CIRCULATION. SHUT IN WELL, NO BUILD UP IN SICP OBS. |  | WCNT | 9010 | 07/17/2022 | ADC-41L | MPMP | SDGM-1244
1272 |  | 899747 | RIG | OTH | 3705 | 9010 | DISCUSS FORWARD PLAN MEANWHILE MONITOR. SIDP = SICP = 0 PSI.- BUILD UP SUFFICIENT 78 PCF MUD AND 88 PCF MUD CAP.- PLAN AHEAD TO BULLHEAD THROUGH KILL LINE WITH 78 PCF MUD. |  | WCNT | 9010 | 07/17/2022 | ADC-41L | NA | SDGM-1244
1273 |  | 899747 | RIG | PJSM | 3705 | 9010 | PJSM FOR BULLHEADING OPERATION.- DISCUSS GAME PLAN AND SAFETY POINTS WITH THE CREW. |  | WCNT | 9010 | 07/17/2022 | ADC-41L | NA | SDGM-1244
1274 |  | 899747 | RIG | CIRC | 3705 | 9010 | LINE UP MUD PUMP THROUGH KILL LINE AND BULL HEAD THE WELL WITH 78 PCF MUD. ONGOING AT RT.STAGE UP PUMP FROM 1 BPM TO 3 BPM , AS BELOW.- 1 BPM, 130 PSI- 2 BPM, 185 PSI- 3 BPM, 235 PSI. |  | WCNT | 9010 | 07/17/2022 | ADC-41L | MPMP | SDGM-1244
1275 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADC-41L | Hrs | SDGM-1244
1276 | WC20 | TK3 | 15 | 17 Jul 1400 - 0500 | 9010 | 899747 | AT 9010 FT OBSERVED INCREASE IN FLOW OUT. SHUT IN WELL AND MONITORED PRESSURE. SIDP = SICP = 0 PSI. | WCNT | NA |  | 07/17/2022 | ADC-41L | 15 | SDGM-1244
1277 | 15 | OOS | CDHL | 3685 | OTHR | WHILE DRILLING AHEAD IN THE BLFR FORMATION, PARTIAL LOSSES WERE ENCOUNTERED AT 8,885 FT. AT 600 BPH AT 20 BPM PUMP RATE. 3 X 100 BBLS OF 40 LB/BBL LCM PILL WERE PUMPED WHILE DRILLING AHEAD TO 8,935 FT TO EXPOSE THE LCZ, A TOTAL OF 3 X 100 BBL 200 PPB LCM PILLS WERE THEN PUMPED THROUGH THE PBL SUB, STRING PULLED ABOVE PILL EACH TIME AND ALLOWED TO SOAK FOR 1.5 HRS EA. AND THEN RAN BACK TO BTM TO PUMP THE FOLLOWING ONE. LOSS RATE WHILE STATIC AFTER FIRST PILL WENT FROM 180 BBL/HR TO 150 BBLS/HR, AFTER SECOND PILL PUMPED AND SOAKED LOSSES IMPROVED TO 140 BBLS/HRS AND STAYED AT 140 BBLS/HRS. | AT 9,010 FT OBSERVED INCREASE IN FLOW OUT. SHUT IN WELL AND MONITORED PRESSURE. SIDP = SICP = 0 PSI. PREPAREDTO AND PERFORM BULLHEAD OPERATION THROUGH KILL LINE WITH 78 PCF MUD. | 15 | 3705 | 17 Jul 0000 | 07/17/2022 | ADC-41L | OOS | SDGM-1244
1278
1279
1280
1281 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADC-49 | Hrs | HWYH-1104
1282 | FOT | CAM | 4 | 17 Jul 0800 - 1200 | 9710 | 899703 | EXCESS TIME TO INSTALL FMH PO: TRIED TO RELEASE RUNNING TOOLS WITHOUT SUCCESS, TROUBLESHOOTING, DISENGAGE FMH PO AND POOH PO ASSY. TO RUN NEW ONE. | WH | WH |  | 07/17/2022 | ADC-49 | 4 | HWYH-1104
1283 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADC-50 | Hrs | SFNY-1176
1284 | WC20 | ARM | 37 | 16 Jul 1600 - 0500 | 3944 | 899719 | WHILE DRILLING 12-1/4" HOLE, ENCOUNTERED TOTAL LOSS OF CIRCULATION AT 3805'. ATTEMPT WITH MUD CAP DRILLING. OBSERVE WELL KICK. | WCNT | NA |  | 07/17/2022 | ADC-50 | 24 | SFNY-1176
1285 | 6844 | 6578 | LOG | E | 3625 | WLT | PERFORM LOG #4 MDT-TLC. PUMPED OUT AND COLLECTED SAMPLES AT 6,578 FT (BOTTOM TO TOP) AS PER PROGRAM.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- MOVE STRING EVERY 4 HOURS/SESSION & CONFIRM STRING FREE, OK.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 2/11.- PUMP OUT COMPLETED: 3/11.- PUMP OUT INTO WELLBORE 0.31 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 2.16 BBLS, - PUMP OUT FLUID TYPE: 1X OIL & 2X WATER.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6578 | SWL | 07/17/2022 | ADC-53L | LOG | HRDH-530
1286 | 6844 |  | OTH | E | 3625 | NA | OBSERVED MUD RETURNED AT ANNULUS. STOPPED PUMPING AT ANNULUS AND OBSERVED WELL. CONTD PUMPING 2 BPM 87 PCF AT ANNULUS AND OBSERVED 0.5 - 1 BPH LOSSES. DISCUSSED WITH DRLG SUPT AND DECIDED TO CANCEL SAMPLING #4 AND CIRCULATE HOLE. | 6844 |  | RIG | 07/17/2022 | ADC-53L | LOG | HRDH-530
1287 | 6844 | 6156 | OTH | E | 3625 | NA | PULLED BACK LOG #4 MDT - TLC TO 6,165 FT. HPJSM. SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE & POOH WL CABLE TO SURFACE. L/D SES AND WIRE LINE SHEAVES.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE WITH 0.5 BPH LOSSES. | 6844 | 6578 | SWL | 07/17/2022 | ADC-53L | LOG | HRDH-530
1288 | 6844 | 6796 | ST | E | 3625 | STDP | HPJSM. RIH LOG #4 MDT - TLC TO 6,796 FT (CIRC PORT @ 6,634 FT). | 6844 | 6156 | RIG | 07/17/2022 | ADC-53L | LOG | HRDH-530
1289 | 6844 |  | CIRC | E | 3625 | MPMP | CIRCULATED WELL 1.5X ANNULUS VOLUME (375 BBLS) THROUGH CHOKE WITH 77 PCF MW. OBSERVED PARTIAL RETURNED THEN COMPLETE LOSS CIRC AFTER PUMPING 150 BBLS MUD- PUMP 87 PCF MUD CAP IN BACK SIDE @ 2 BPM ON TOTAL LOSS. | 6844 |  | RIG | 07/17/2022 | ADC-53L | LOG | HRDH-530
1290 | 6844 | 6456 | ST | E | 3625 | STDP | PULLED BACK LOG #4 MDT - TLC TO 7" SHOE. OBSERVED MUD RETURNED WHILE PUMPING 87 PCF MUD CAP AT ANNULUS. | 6844 | 6796 | RIG | 07/17/2022 | ADC-53L | LOG | HRDH-530
1291 | 6844 |  | CIRC | E | 3625 | MPMP | M/U TDS AND CIRCULATE WELL 1.5X ANNULUS VOLUME (350 BBLS) THROUGH CHOKE UNTIL 77 PCF MW IN/OUT. OBSERVED WELL AT TRIP TANK WITH 25 BPH LOSSES. | 6844 |  | RIG | 07/17/2022 | ADC-53L | LOG | HRDH-530
1292 | 6844 | 4835 | TO | E | 3625 | STDP | POOH LOG #4 MDT - TLC ON 4" DP STANDS F/6,456 FT TO 4835 FT.- CONTINUOUSLY PUMPING 77 PCF MUD AT ANNULUS. | 6844 | 6456 | RIG | 07/17/2022 | ADC-53L | LOG | HRDH-530
1293 | 6844 |  | CIRC | E | 3625 | MPMP | OBSERVED HOLE NOT TAKING CORRECT AMOUNT OF MUD AT 4835 FT. FLOW CHECK - WELL STATIC. M/U TDS AND CIRCULATE BOTTOMS UP THROUGH CHOKE UNTIL 77 PCF MW IN/OUT. OBSERVED WELL AT TRIP TANK WITH 100 BPH LOSSES. | 6844 |  | RIG | 07/17/2022 | ADC-53L | LOG | HRDH-530
1294 | 6844 | 162 | TO | E | 3625 | STDP | CONTD POOH LOG #4 MDT - TLC ON 4" DP STANDS F/4835 FT TO 162 FT.- CONTINUOUSLY PUMPING 77 PCF MUD AT ANNULUS.- CIRCULATED EVERY 10 STANDS PULLED.- WHILE CIRC AT 880 FT, OBSERVED SEVERE LOSSES TO TOTAL LOSS. SWITCH TO 87 PCF MUD CAP AT ANNULUS | 6844 | 4835 | RIG | 07/17/2022 | ADC-53L | LOG | HRDH-530
1295 | 6844 |  | OTH | E | 3625 | NA | HPJSM, L/D LOG #4 MDT LOGGING TOOL.- CONTINUOUSLY PUMPED 87 PCF MUD CAP AT ANNULUS @ 2 BPM. | 6844 |  | SWL | 07/17/2022 | ADC-53L | LOG | HRDH-530
1296 | 6844 |  | HT | E | 3625 | BHA | HPJSM, P/U & M/U 6-1/8" CLEANOUT TRIP BHA AND RIH TO 356 FT.- CONTINUOUSLY PUMPING 87 PCF MUD CAP AT ANNULUS @ 2 BPM. | 6844 |  | RIG | 07/17/2022 | ADC-53L | CT | HRDH-530
1297 | 6844 | 6456 | TI | E | 3625 | STDP | RIH WITH W/ 6-1/8" REAMING BHA F/356 FT TO 7" CSG SHOE @ 6,456 FT.- FILL STRING AND BREAK CIRC EVERY 20 STD.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 356 | RIG | 07/17/2022 | ADC-53L | CT | HRDH-530
1298 | 6844 |  | RR | E | 3625 | DWKS | SLIP & CUT DRILL LINE. ON GOING AT REPORT TIME.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/17/2022 | ADC-53L | CT | HRDH-530
1299 | 161.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/17/2022 | ADC-53L | Type | HRDH-530
1300
1301
1302 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADC-55L | Hrs | UTMN-3171
1303 | FOT | SDM | 6.5 | 17 Jul 2230 - 0500 | 10788 | 899722 | LOST SIGNAL TO MWD | BHA | MWD |  | 07/17/2022 | ADC-55L | 6.5 | UTMN-3171
1304 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADC-56L | Hrs | UTMN-3069
1305 | HERR | TK3 | 16 | 17 Jul 1300 - 0500 | 4598 | 899745 | UNABLE TO DROP 2ND STAGE CLOSING PLUG INSIDE CASING, PLUG STUCK INSIDE 18-5/8CMT HEAD XO. | CMT | NA |  | 07/17/2022 | ADC-56L | 16 | UTMN-3069
1306 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADC-59L | Hrs | HWYH-1324
1307 | FOT | TSC | 8 | 16 Jul 1230 - 0700 | 5568 | 899716 | OBSERVED HYDRAULIC CATWALK MULFUNCTION. | TF | PEL |  | 07/17/2022 | ADC-59L | 1 | HWYH-1324
1308 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADC-68L | Hrs | ABHD-176
1309 | SRVC | TK3 | 14.5 | 17 Jul 0500 - 0500 | 10265 | 899763 | TRIED TO HUNG THE BOP FOUND BOP CRANE HAD MULFUNCTION | WO | NA |  | 07/17/2022 | ADC-68L | 14.5 | ABHD-176
1310 | FOT | SPS | 10 | 17 Jul 1830 - 0500 | 8720 | 899765 | RSS UNABLE TO TRANSFER DATA TO SURFACE. UNSUCCESSFUL SURVEY. | BHA | RSS |  | 07/17/2022 | ADES-144 | 10 | UTMN-3152
1311 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADES-144 | Hrs | UTMN-3152
1312 | FOT | SPS | 5 | 17 Jul 0700 - 1200 | 94 | 899699 | COMMUNICATION UNSUCCESSFUL BETWEEN SPERRY SUN RSS AND MWD. | BHA | RSS |  | 07/17/2022 | ADES-144 | 5 | UTMN-3152
1313 | FOT | SPS | 10 | 17 Jul 1830 - 0500 | 8720 | 899765 | RSS UNABLE TO TRANSFER DATA TO SURFACE. UNSUCCESSFUL SURVEY. | BHA | RSS |  | 07/17/2022 | ADES-144 | 10 | UTMN-3152
1314 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADES-157 | Hrs | HRDH-1844
1315 | FOT | GEP | 101.5 | 13 Jul 2330 - 0500 | 14932 | 899679 | N/U WG TBG BONNET AND TEST VOIDS, NOT HOLD. | WH | WH |  | 07/17/2022 | ADES-157 | 24 | HRDH-1844
1316 | CWEL | ARM | 31 | 16 Jul 0600 - 1300 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/17/2022 | ADM-511 | 8 | MRJN-799
1317 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ADM-511 | Hrs | MRJN-799
1318 | FOT | BHI | 16 | 17 Jul 1300 - 0500 | 346 | 899721 | EXCESSIVE PRESSURE OBSERVED DURING ATTEMPT TO SHALLOW TEST BHI TOOLS | BHA | RSS |  | 07/17/2022 | ADM-511 | 16 | MRJN-799
1319 | CWEL | ARM | 31 | 16 Jul 0600 - 1300 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/17/2022 | ADM-511 | 8 | MRJN-799
1320 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | AOD-111 | Hrs | MRJN-726
1321 | WOTO | RIG | 9.25 | 17 Jul 1945 - 0500 | 0 | 899723 | WHILE PRESSURE TEST BOP, OBSERVED LEAK AT BODY OF THE CHOKE COFLEX HOSE. ISOLATED AND CONTINUE WITH BOP TEST. | WO | NA |  | 07/17/2022 | AOD-111 | 9.25 | MRJN-726
1322 | HERR | HCO | 3.5 | 17 Jul 2030 - 0000 | 9578 | 899766 | UNABLE TO FULLY MAKE UP CONTROL LINE FITTING TO TOP OF TUBING HANGER PORT. | TF | TBG |  | 07/17/2022 | ARO-3004 | 3.5 | MRJN-2060
1323 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ARO-3004 | Hrs | MRJN-2060
1324 | HERR | HCO | 2 | 17 Jul 0230 - 0430 | 9578 | 899705 | HES HCO LT: EXCESS TIME FOR HES TRSSV HAND TO MAKE UP AND TEST TRSSV | TF | TBG |  | 07/17/2022 | ARO-3004 | 2 | MRJN-2060
1325 | HERR | HCO | 3.5 | 17 Jul 2030 - 0000 | 9578 | 899766 | UNABLE TO FULLY MAKE UP CONTROL LINE FITTING TO TOP OF TUBING HANGER PORT. | TF | TBG |  | 07/17/2022 | ARO-3004 | 3.5 | MRJN-2060
1326 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | DQ-47 | Hrs | KHRS-497
1327 | DSFT | BLH | 25.25 | 16 Jul 1900 - 0500 | 9554 | 899760 | RIH W/ P&A KIT TO ISOLATE LOSS ZONE AT 9600', WHILE PRESS. UP STRG TO 3000 PSI TO SET THE PKR, HAD SUDDEN PRESS. DROP TO ZERO ONCE REACHED 3000 PSI. | JF | LLAP |  | 07/17/2022 | DQ-47 | 18.75 | KHRS-497
1328 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ENSCO-54 | Hrs | ABSF-17
1329 | STCT | ARM | 230.5 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/17/2022 | ENSCO-54 | 24 | ABSF-17
1330 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | ENSCO-76 | Hrs | MRJN-853
1331 | CFFM | ARM | 108 | 13 Jul 1145 - 0500 | 6116 | 899694 | LOST CIRCULATION UPON PENETRATING LAWHAH (LHHR) | LCIR | LCM |  | 07/17/2022 | ENSCO-76 | 24 | MRJN-853
1332 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | JACK-203 | Hrs | HZEM-849
1333 | LCRW | ARM | 181.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/17/2022 | JACK-203 | 24 | HZEM-849
1334 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | NBR-196S | Hrs | SDGM-1235
1335 | FOT | BLH | 114.5 | 12 Jul 1130 - 0500 | 2995 | 899524 | 7" LINER HANGER STUCK IN CASED VERTICAL SECTION OF WELL, 818' BELOW ROTARY TABLE. | TF | HGRL |  | 07/17/2022 | NBR-196S | 24 | SDGM-1235
1336 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | NBR-263S | Hrs | QTIF-736
1337 | FOT | SPS | .5 | 17 Jul 0930 - 1000 | 12360 | 899748 | UNABLE TO SEND DOWNLINK, TROUBLESHOOT BY RESETTING PWD TOOL, FIX, OK. | BHA | LWD |  | 07/17/2022 | NBR-263S | .5 | QTIF-736
1338 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | NBR-304S | Hrs | HRDH-1958
1339 | CFFM | ARM | 61.75 | 15 Jul 1515 - 0500 | 9537 | 899714 | HAD LOSSES ON 1ST STAGE CEMENTING OF 9-5/8" CASING | CMT | NA |  | 07/17/2022 | NBR-304S | 24 | HRDH-1958
1340 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | NBR-633S | Hrs | HRDH-2234
1341 | FOT | SAM | 26.5 | 16 Jul 0500 - 0730 | 16810 | 899756 | WHILE RIH WITH SAMAA WBCO ASSY., HAD OBSTRUCTION @ 16,810' (291' ABOVE PBTD / 247' ABOVE TBR), WORKED ON SAME REAM DOWN WITH 15 KLB S.O.W, HAD NO PROGRESS ALMOST WITHOUT CLEAR INCREASE IN TORQUE OR PRESSURE, WHICH CONFIRM THAT THE OBSTRUCTION ON SAMA DRIFT SUB & BRUSH COULDN'T PASS 7" 35# LINER AT DEPTH 12,356', SAMAA RUNNING INCORRECT DRFIT SUB & BRUSH GRADE AND POH & FOUND MARK ON BRUSH OD. (NEED DTD TO INVESTIGATE INCIDENT) | BHA | WBCL |  | 07/17/2022 | NBR-633S | 2.5 | HRDH-2234
1342 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | NBR-783S | Hrs | NJYN-93
1343 | HERR | MSD | 2 | 17 Jul 0300 - 0500 | 0 | 899746 | EXCESS TIME DUE TO POOR EQUIPMENT/CREW | JF | CTRQ |  | 07/17/2022 | NBR-783S | 2 | NJYN-93
1344 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SCTD-1 | Hrs | SDGM-1034
1345 | FOT | RIG | 19 | 17 Jul 1000 - 0500 | 12830 | 899720 | TURBINE DOWNHOLE FAILURE | BHA | MMOT |  | 07/17/2022 | SCTD-1 | 19 | SDGM-1034
1346 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SCTD-2 | Hrs | HRDH-2148
1347 | FOT | RIG | 57 | 15 Jul 2000 - 0500 | 12250 | 899733 | LEAK IN THE COIL REEL MANIFOLD; BOTH SHAFTS CRACKED AND WORN DOWN. | RR | CSYS |  | 07/17/2022 | SCTD-2 | 24 | HRDH-2148
1348 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SINO-15L | Hrs | ANDR-420
1349 | FOT | RIG | 5.5 | 16 Jul 0230 - 0800 | 10395 | 899697 | TOP DRIVE STOPPED ROTATION, UNABLE TO BREAK TDS CONNECTION | RR | TDS |  | 07/17/2022 | SINO-15L | 3 | ANDR-420
1350 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SINO-19L | Hrs | UTMN-252
1351 | FOT | SPS | 26 | 16 Jul 0300 - 0500 | 8696 | 899759 | LOST SIGNAL FROM MWD | SURV | MS |  | 07/17/2022 | SINO-19L | 24 | UTMN-252
1352 | FOT | SPS | 21.5 | 16 Jul 0900 - 0630 | 8001 | 899735 | WHILE RE-LOG WITH LWD TOOLS, HAD LWD_CTN TOOL FAILURE, TROUBLE SHOOTING, NO SUCCESS. | BHA | LWD |  | 07/17/2022 | SINO-36L | 1.5 | SDGM-458
1353 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SINO-36L | Hrs | SDGM-458
1354 | HELD | TK1 | 221 | 07 Jul 2330 - 0230 | 5400 | 899508 | PROBLEM IN HOLE ACCESSIBILITY. TK1 | JF | LINR |  | 07/17/2022 | SINO-36L | 20 | SDGM-458
1355 | FOT | SPS | 2.5 | 17 Jul 0230 - 0500 | 8855 | 899706 | WHILE DRILLING WITH LWD TOOLS, HAD LWD_AFR TOOL FAILURE, TROUBLE SHOOTING, NO SUCCESS. | BHA | LWD |  | 07/17/2022 | SINO-36L | 2.5 | SDGM-458
1356 | FOT | SPS | 21.5 | 16 Jul 0900 - 0630 | 8001 | 899735 | WHILE RE-LOG WITH LWD TOOLS, HAD LWD_CTN TOOL FAILURE, TROUBLE SHOOTING, NO SUCCESS. | BHA | LWD |  | 07/17/2022 | SINO-36L | 1.5 | SDGM-458
1357 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SINO-43L | Hrs | UTMN-4068
1358 | FOT | BLH | 12.5 | 17 Jul 1400 - 0230 | 6780 | 899702 | TRIED MANY TIMES TO SET BAKER LINER HGR SLIPS USING DIFFERENT PRESSURE VALUES BUT NO SUCCESS. | TF | HGRL |  | 07/17/2022 | SINO-43L | 12.5 | UTMN-4068
1359 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SND-2005 | Hrs | MHKK-2
1360 | HERR | RIG | 82 | 14 Jul 1730 - 0500 | 13903 | 899640 | FOUND A SMALL PIECE OF METAL LODGED IN BETWEEN BIT BLADES (1.5") & 1 PIECE (2" U-SHAPED) LODGED IN NEAR BIT REAMER. | FISH | BHA |  | 07/17/2022 | SND-2005 | 24 | MHKK-2
1361 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SND-2008 | Hrs | HRDH-1812
1362 | STDP | RIG | 240 | 07 Jul 0500 - 0500 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/17/2022 | SND-2008 | 24 | HRDH-1812
1363 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SND-2010 | Hrs | MNIF-869
1364 | FPMP | RIG | 25 | 16 Jul 0400 - 0500 | 3148 | 899698 | PUMP VALVES ACTUATED ON MUD PUMPS AND COULD NOT RESET. CANNOT USE MUD PUMPS WITHOUT POP VALVE RE-SET. | RR | MPMP |  | 07/17/2022 | SND-2010 | 24 | MNIF-869
1365 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SP-103 | Hrs | KRSN-72
1366 | FOT | RIG | 16 | 16 Jul 0300 - 1900 | 9105 | 899739 | RIG REPAIR (TDS ELECTRIC PROBLEM) | RR | TDS |  | 07/17/2022 | SP-103 | 14 | KRSN-72
1367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SP-110 | Hrs | BRRI-562
1368 | FOT | SJT | 18.5 | 16 Jul 1630 - 1100 | 13282 | 899695 | TAQA E-COIL TUBING CYCLING VALVE OPEN AND DEACTIVATED THE MLT ( MULTI LATERAL TOOLS) WHICH DIDN'T ALLOW TOOL TO ENTER LATERAL L-1-1. | BHA | CTAC |  | 07/17/2022 | SP-110 | 6 | BRRI-562
1369 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SP-120 | Hrs | MNIF-187
1370 | FOT | RIG | 7 | 17 Jul 0930 - 1630 | 2039 | 899742 | FIX AND REAPAIR A WASHOUT ON A WELDED CONNECTION ON THE STANDPIPE MANIFOLD. | RR | CSYS |  | 07/17/2022 | SP-120 | 7 | MNIF-187
1371 | FOT | BHI | 14 | 17 Jul 1430 - 0430 | 9252 | 899743 | BAKER ROTARY STEERABLE SYSTEM FAILED TO RESPOND TO THE RECEIVED DOWNLINKS | BHA | RSS |  | 07/17/2022 | SP-260 | 14 | HMYM-531802
1372 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SP-260 | Hrs | HMYM-531802
1373 | FOT | BHI | 16 | 16 Jul 1930 - 1130 | 9067 | 899718 | BAD COMMUNICATION FROM RSS, TROUBLE SHOOTED, NO SUCCESS. DECIDED TO POOH AND CHANGE BAKER TOOLS. | BHA | RSS |  | 07/17/2022 | SP-260 | 6.5 | HMYM-531802
1374 | FOT | BHI | 14 | 17 Jul 1430 - 0430 | 9252 | 899743 | BAKER ROTARY STEERABLE SYSTEM FAILED TO RESPOND TO THE RECEIVED DOWNLINKS | BHA | RSS |  | 07/17/2022 | SP-260 | 14 | HMYM-531802
1375 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SP-261 | Hrs | HZEM-160212
1376 | FOT | SDM | 19.25 | 16 Jul 0615 - 0930 | 9110 | 899715 | SLB MWD SIGNAL LOSS. | BHA | MWD |  | 07/17/2022 | SP-261 | 4.5 | HZEM-160212
1377 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SP-306 | Hrs | MNIF-193
1378 | FOT | RIG | 5 | 17 Jul 0000 - 0500 | 10778 | 899701 | LEAK ON KELLY HOSE. | RR | KELLY |  | 07/17/2022 | SP-306 | 5 | MNIF-193
1379 | ORDS | ARM | 1.25 | 17 Jul 1615 - 1730 | 13054 | 899744 | WAIT ON GOC DECISION TO RESUME DRILLING.GOC REQUESTED DENSITY IMAGE FR 12850' TO CASING POINT WITCH IS NOT INCLUDED IN DRILLING PROGRAM. | WO | NA |  | 07/17/2022 | SSA-202 | 1.25 | QTIF-191
1380 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SSA-202 | Hrs | QTIF-191
1381 | FOT | RIG | 6.75 | 17 Jul 1830 - 0115 | 13093 | 899700 | OBSERVED TOP DRIVE RPM STOPPED DURING DRILLING . | RR | TDS |  | 07/17/2022 | SSA-202 | 6.75 | QTIF-191
1382 | ORDS | ARM | 1.25 | 17 Jul 1615 - 1730 | 13054 | 899744 | WAIT ON GOC DECISION TO RESUME DRILLING.GOC REQUESTED DENSITY IMAGE FR 12850' TO CASING POINT WITCH IS NOT INCLUDED IN DRILLING PROGRAM. | WO | NA |  | 07/17/2022 | SSA-202 | 1.25 | QTIF-191
1383 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/17/2022 | SSA-5859 | Hrs | HWYH-1222
1384 | FOT | SPS | 6 | 17 Jul 0930 - 1530 | 17236 | 899764 | FAILURE ON COMMUNICATION CONNECTION TOOL . | SURV | MS |  | 07/17/2022 | SSA-5859 | 6 | HWYH-1222
1385 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | 910TE | Hrs | DMMM-102
1386 | FOT | RIG | 2 | 18 Jul 1930 - 2130 | 11600 | 899818 | WHILE TRIP-IN, GOT TDS BLOWER GROUND FAULT; STOP & TROUBLESHOOT. | RR | TDS |  | 07/18/2022 | 910TE | 2 | DMMM-102
1387 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADC-31 | Hrs | SDGM-1181
1388 | STDP | RIG | 136.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/18/2022 | ADC-31 | 24 | SDGM-1181
1389 | WC20 | TK3 | 4 | 18 Jul 0100 - 0500 | 9010 | 899776 | WHILE CIRCULATING THRU CHOKE OBSERVED CUT IN MUD FROM 78 PCF TO 70 PCF. SHUT IN WELL AND MONITOR PRESSURE. | WCNT | NA |  | 07/18/2022 | ADC-41L | 4 | SDGM-1244
1390 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADC-41L | Hrs | SDGM-1244
1391 | WC20 | TK3 | 30 | 17 Jul 1400 - 2000 | 9010 | 899747 | AT 9010 FT OBSERVED INCREASE IN FLOW OUT. SHUT IN WELL AND MONITORED PRESSURE. SIDP = SICP = 0 PSI. | WCNT | NA |  | 07/18/2022 | ADC-41L | 15 | SDGM-1244
1392 | WC20 | TK3 | 4 | 18 Jul 0100 - 0500 | 9010 | 899776 | WHILE CIRCULATING THRU CHOKE OBSERVED CUT IN MUD FROM 78 PCF TO 70 PCF. SHUT IN WELL AND MONITOR PRESSURE. | WCNT | NA |  | 07/18/2022 | ADC-41L | 4 | SDGM-1244
1393 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADC-50 | Hrs | SFNY-1176
1394 | WC20 | ARM | 61 | 16 Jul 1600 - 0500 | 3944 | 899719 | WHILE DRILLING 12-1/4" HOLE, ENCOUNTERED TOTAL LOSS OF CIRCULATION AT 3805'. ATTEMPT WITH MUD CAP DRILLING. OBSERVE WELL KICK. | WCNT | NA |  | 07/18/2022 | ADC-50 | 24 | SFNY-1176
1395 | 6844 |  | RR | E |  | DWKS | SLIP & CUT DRILL LINE.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM | 6844 |  | RIG | 07/18/2022 | ADC-53L | CT | HRDH-530
1396 | 6844 | 6844 | RW | E | 3625 | BIT | REAM AND WASH HOLE F/6,456 FT AND TAGGED BOTTOM AT 6,844 FT.- 290 GPM, PRESS: 460 PSI, 80 RPM TQ 1 - 2 KLB-FT- CONTINUOUSLY PUMPING 87 PCF MUD CAP AT BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/18/2022 | ADC-53L | CT | HRDH-530
1397 | 6844 |  | CIRC | E | 3625 | MPMP | PUMPED TANDEM 30 BBL HI-VIS MUD AND CIRC HOLE. - CONTINUOUSLY PUMPING 87 PCF MUD CAP AT BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/18/2022 | ADC-53L | CT | HRDH-530
1398 | 6844 | 6456 | ST | E | 3625 | STDP | HPJSM. POOH 6-1/8" BHA ON ELEVATOR FROM BTM @6,844 FT TO 6,456 FT (SHOE). HOLE IN GOOD CONDITION.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6844 | RIG | 07/18/2022 | ADC-53L | CT | HRDH-530
1399 | 6844 | 356 | TO | E | 3625 | STDP | CONTINUE POOH 6-1/8" BHA ON ELEVATOR F/6,456 FT TO TOP OF BHA @ 356 FT.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6456 | RIG | 07/18/2022 | ADC-53L | CT | HRDH-530
1400 | 6844 |  | HT | E | 3625 | BHA | CONTINUED POOH 6-1/8" BHA ON ELEVATOR F/356 FT TO SURFACE. L/D BIT #9RR.- BIT GRADING: 1, 1, WT, A, E, NO, I, LOG- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/18/2022 | ADC-53L | CT | HRDH-530
1401 | 6844 |  | OTH | E | 3625 | NA | HPJSM, P/U & M/U WL LOGGING TOOLS RUN #4 MDT & RIH TO 162 FT.- CHECK TOOLS ON SURFACE, OK.- TOOL LENGTH: 162.12 FT. MAX TOOL OD: 5.284 INCHES.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM | 6844 |  | SWL | 07/18/2022 | ADC-53L | LOG | HRDH-530
1402 | 6844 | 6156 | TI | E | 3625 | STDP | RIH LOG #4 MDT - TLC ON 4" DP STDS F/ 162 FT TO LATCH DEPTH AT 6,156 FT.- CONTROL SPEED 3 MIN/STD SLIP TO SLIP.- FILL STRING AND BREAK CIRC EVERY 10 STD.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 162 | RIG | 07/18/2022 | ADC-53L | LOG | HRDH-530
1403 | 6844 |  | CIRC | E | 3625 | MPMP | CIRC 1.5 STRING VOLUME. MEANWHILE HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW.- FR: 250 GPM & PRESS: 280 PSI. - CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/18/2022 | ADC-53L | LOG | HRDH-530
1404 | 6844 |  | OTH | E | 3625 | NA | HPJSM. M/U SLB S.E.S. & FEED WIRE LINE CABLE. RIH WIRE LINE CABLE AND LATCH INTO CONNECTOR AS PER SLB WIRELINE ENGINEER INSTRUCTION.- APPLY 250 PSI PUMP PRESS TO ASSIST IN LATCHING PROCESS AS PER SLB ENG.- LATCH INTO WET CONNECTOR PROFILE, FUNCTION TEST SLB TOOLS, OK.- PERFORM PULL TENSION TEST TO 3,100 LBS, OK.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SWL | 07/18/2022 | ADC-53L | LOG | HRDH-530
1405 | 6844 | 6680 | ST | E | 3625 | STDP | RIH LOG #4 MDT - TLC ON 4" DP F/ 6,156 FT TO 6,481 FT AT CONTROL SPEED. - CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS- MEANWHILE PUMPED 250 BBLS 87 PCF MUD CAP AT ANNULUS. | 6844 | 6156 | RIG | 07/18/2022 | ADC-53L | LOG | HRDH-530
1406 | 6844 | 6518 | LOG | E | 3625 | WLT | PERFORM LOG #4 MDT-TLC. PUMPED OUT AND COLLECTED SAMPLES F/6,511 FT TO 6,511 FT (BOTTOM TO TOP) AS PER PROGRAM. ON GOING AT REPORT TIME.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- MOVE STRING EVERY 4 HOURS/SESSION & CONFIRM STRING FREE, OK.- PUMPED 250 BBLS 87 PCD MUD CAP BEFORE EVERY SAMPLING.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 2/6.- PUMP OUT COMPLETED: 3/6.- PUMP OUT INTO WELLBORE 0 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 0 BBLS, - PUMP OUT FLUID TYPE: 1X OIL & 2X WATER.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM WHILE SAMPLING | 6844 | 6518 | SWL | 07/18/2022 | ADC-53L | LOG | HRDH-530
1407 | 183.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 23 | 3625 | 09 Jul 0000 | 07/18/2022 | ADC-53L | Type | HRDH-530
1408
1409
1410 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADC-54L | Hrs | HRDH-1499
1411 | FOT | RIG | 8.5 | 18 Jul 2030 - 0500 | 12153 | 899773 | DRAW-WORKS BRAKES ENGAGED DUE TO ELECTRICAL FAULT IN RESISTOR BANK. | RR | DWKS |  | 07/18/2022 | ADC-54L | 8.5 | HRDH-1499
1412 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADC-55L | Hrs | UTMN-3171
1413 | FOT | SDM | 22.75 | 17 Jul 2230 - 2115 | 10788 | 899722 | LOST SIGNAL TO MWD | BHA | MWD |  | 07/18/2022 | ADC-55L | 16.25 | UTMN-3171
1414 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADC-62L | Hrs | ANDR-745
1415 | FPMP | RIG | 38 | 17 Jul 0900 - 2300 | 13046 | 899749 | TRY TO PUMP MUDZYME PILL, RIG PUMP NOT ABLE TO PUMP, TRANSFER TO DIFFERNT TANK -NO SUCCESS. | RR | MPMP |  | 07/18/2022 | ADC-62L | 18 | ANDR-745
1416 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADC-64L | Hrs | UTMN-3074
1417 | FOT | SDM | 13.75 | 18 Jul 1515 - 0500 | 13032 | 899821 | RSS DRILLED 5-7/8" HOLE TO 13032 FT, OBSERVED MWD LOST SIGNAL. TROUBLE SHOOTING A SEVERAL TIME NO SUCCESS. | BHA | MWD |  | 07/18/2022 | ADC-64L | 13.75 | UTMN-3074
1418 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADES-144 | Hrs | UTMN-3152
1419 | FOT | SPS | 21.75 | 17 Jul 0700 - 1215 | 94 | 899699 | COMMUNICATION UNSUCCESSFUL BETWEEN SPERRY SUN RSS AND MWD. RSS UNABLE TO TRANSFER DATA TO SURFACE. UNSUCCESSFUL SURVEY. | BHA | RSS |  | 07/18/2022 | ADES-144 | 7.25 | UTMN-3152
1420 | FOT | ITS | 1 | 18 Jul 1100 - 1200 | 12254 | 899793 | RIH W/ BRUSH AND DRIFT COULD NOT PASS AT 31'. POH AND CHECK, OVER TORQUED CONNECTION BETWEEN LANDING SUB AND LANDING JT. | TF | TTRQ |  | 07/18/2022 | ADES-157 | 1 | HRDH-1844
1421 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADES-157 | Hrs | HRDH-1844
1422 | FOT | GEP | 116 | 13 Jul 2330 - 2030 | 14932 | 899679 | N/U WG TBG BONNET AND TEST VOIDS, NOT HOLD. | WH | WH |  | 07/18/2022 | ADES-157 | 14.5 | HRDH-1844
1423 | FOT | ITS | 1 | 18 Jul 1100 - 1200 | 12254 | 899793 | RIH W/ BRUSH AND DRIFT COULD NOT PASS AT 31'. POH AND CHECK, OVER TORQUED CONNECTION BETWEEN LANDING SUB AND LANDING JT. | TF | TTRQ |  | 07/18/2022 | ADES-157 | 1 | HRDH-1844
1424 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADM-262 | Hrs | MRJN-122
1425 | FOT | RIG | 1 | 18 Jul 0300 - 0400 | 2647 | 899797 | CHAIN OF HIGH CLUTCH OF DRAW WORKS BROKE | RR | DWKS |  | 07/18/2022 | ADM-262 | 1 | MRJN-122
1426 | FOT | BCT | 1 | 18 Jul 0100 - 0200 | 0 | 899836 | HYDRAULIC LEAKS ON THE BAKER CT BOP - OUTLET KILL HCR ON OPEN SIDE. | TF | CTU |  | 07/18/2022 | ADM-337 | 1 | MRJN-900
1427 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADM-337 | Hrs | MRJN-900
1428 | FOT | SWT | 2 | 18 Jul 1630 - 1830 | 0 | 899770 | ADAPTER FLANGE ON KILL WING SIDE OF FLOW HEAD LEAKED ON HIGH PRESSURE TEST. | TF | WTSE |  | 07/18/2022 | ADM-337 | 2 | MRJN-900
1429 | FOT | BWT | 1.5 | 18 Jul 1830 - 2000 | 0 | 899832 | FAILED TEST COMBI BLIND RAMS DUE TO LEAK ON LO-TQ VALVE OF CT KILL LINE. | TF | WTSE |  | 07/18/2022 | ADM-337 | 1.5 | MRJN-900
1430 | FOT | BCT | 1 | 18 Jul 0100 - 0200 | 0 | 899836 | HYDRAULIC LEAKS ON THE BAKER CT BOP - OUTLET KILL HCR ON OPEN SIDE. | TF | CTU |  | 07/18/2022 | ADM-337 | 1 | MRJN-900
1431 | CWEL | ARM | 53.75 | 16 Jul 0600 - 0500 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/18/2022 | ADM-511 | 22.75 | MRJN-799
1432 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ADM-511 | Hrs | MRJN-799
1433 | FOT | BHI | 17.25 | 17 Jul 1300 - 0615 | 346 | 899721 | EXCESSIVE PRESSURE OBSERVED DURING ATTEMPT TO SHALLOW TEST BHI TOOLS | BHA | RSS |  | 07/18/2022 | ADM-511 | 1.25 | MRJN-799
1434 | CWEL | ARM | 53.75 | 16 Jul 0600 - 0500 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/18/2022 | ADM-511 | 22.75 | MRJN-799
1435 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | AOD-111 | Hrs | MRJN-726
1436 | WOTO | RIG | 15.25 | 17 Jul 1945 - 1100 | 0 | 899723 | WHILE PRESSURE TEST BOP, OBSERVED LEAK AT BODY OF THE CHOKE COFLEX HOSE. ISOLATED AND CONTINUE WITH BOP TEST. | WO | NA |  | 07/18/2022 | AOD-111 | 6 | MRJN-726
1437 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ARO-2003 | Hrs | MNIF-435
1438 | XTTE | MSL | 4.75 | 18 Jul 0015 - 0500 | 5761 | 899835 | MANSOORI SLICKLINE LOST TOOLSTRING | JF | SLICK |  | 07/18/2022 | ARO-2003 | 4.75 | MNIF-435
1439 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ARO-3003 | Hrs | SFNY-4220
1440 | FOT | RIG | 76.75 | 15 Jul 0645 - 1130 | 105 | 899752 | WHILE DRLLING 34" HOLE AT 239', 5-1/2" HWDP SHEARED OFF 2.5" ABOVE TOOL JT, LEAVING TOF +/-3' BELOW THE SEA LEVEL, CANNOT GO OVER FISH W/ OVERSHOT DUE TO LEANING OVER IN THE WATER TOO FAR OFF CENTER OF WELL | BHA | HWDP |  | 07/18/2022 | ARO-3003 | 6.5 | SFNY-4220
1441 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ARO-4001 | Hrs | MRJN-532
1442 | FOT | RIG | 1.5 | 18 Jul 0930 - 1100 | 5925 | 899816 | OBSERVED COOLING WATER LEAKING FROM TDS MOTOR B-SIDE, REPLACE COOLING WATER HOSE. | RR | TDS |  | 07/18/2022 | ARO-4001 | 1.5 | MRJN-532
1443 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | BB-84A | Hrs | MRJN-587
1444 | IHFL | RIG | 1 | 18 Jul 0315 - 0415 | 10121 | 899839 | TDS SWIVEL HOUSING LOW ON OIL | RR | HSYS |  | 07/18/2022 | BB-84A | 1 | MRJN-587
1445 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | DQ-47 | Hrs | KHRS-497
1446 | DSFT | BLH | 32 | 16 Jul 1900 - 1245 | 9554 | 899760 | RIH W/ P&A KIT TO ISOLATE LOSS ZONE AT 9600', WHILE PRESS. UP STRG TO 3000 PSI TO SET THE PKR, HAD SUDDEN PRESS. DROP TO ZERO ONCE REACHED 3000 PSI. | JF | LLAP |  | 07/18/2022 | DQ-47 | 6.75 | KHRS-497
1447 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ED-85A | Hrs | ZULF-2063
1448 | FOT | RIG | 6.5 | 18 Jul 0530 - 1200 | 10455 | 899769 | SAVER SUB LEAKED. | RR | TDS |  | 07/18/2022 | ED-85A | 6.5 | ZULF-2063
1449 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ENSCO-54 | Hrs | ABSF-17
1450 | STCT | ARM | 254.5 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/18/2022 | ENSCO-54 | 24 | ABSF-17
1451 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | ENSCO-76 | Hrs | MRJN-853
1452 | CFFM | ARM | 119 | 13 Jul 1145 - 1600 | 6116 | 899694 | LOST CIRCULATION UPON PENETRATING LAWHAH (LHHR) | LCIR | LCM |  | 07/18/2022 | ENSCO-76 | 11 | MRJN-853
1453 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | EXL-IVA | Hrs | SFNY-1650
1454 | FOT | BAW | 8 | 18 Jul 2100 - 0500 | 187 | 899837 | COULD NOT GET WIRELINE COMMUNICATIONS WITH THE TOOLS RCX-RCL-GR-PCL AFTER PICKING UP. TROUBLESHOOT TOOLS BY CHANGING OUT TOOLS ONE BY ONE. | TF | WLT |  | 07/18/2022 | EXL-IVA | 8 | SFNY-1650
1455 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | HI-2 | Hrs | BRRI-440
1456 | WOPF | AP2 | 3.75 | 18 Jul 0700 - 1045 | 17947 | 899834 | WAIT ON PERMISSION TO COMMENCE FLOW BACK THRU PRODUCTION LINE TO GOSP. | WO | NA |  | 07/18/2022 | HI-2 | 3.75 | BRRI-440
1457 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | JACK-203 | Hrs | HZEM-849
1458 | LCRW | ARM | 205.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/18/2022 | JACK-203 | 24 | HZEM-849
1459 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | NBR-196S | Hrs | SDGM-1235
1460 | FOT | BLH | 138.5 | 12 Jul 1130 - 0500 | 2995 | 899524 | 7" LINER HANGER STUCK IN CASED VERTICAL SECTION OF WELL, 818' BELOW ROTARY TABLE. | TF | HGRL |  | 07/18/2022 | NBR-196S | 24 | SDGM-1235
1461 | FOT | RIG | .75 | 18 Jul 0830 - 0915 | 13211 | 899822 | RIG REPAIR, CIRC WITH MUD PUMP#3 WHILE FIXING MUD PUMP#1&2. | RR | MPMP |  | 07/18/2022 | NBR-263S | .75 | QTIF-736
1462 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | NBR-263S | Hrs | QTIF-736
1463 | FOT | RIG | 4.25 | 18 Jul 0045 - 0500 | 13686 | 899819 | FOUND LEAK BETWEEN TOP DRIVE S.PIPE & WASH PIPE WECO UNION CONNECTION. | RR | CSYS |  | 07/18/2022 | NBR-263S | 4.25 | QTIF-736
1464 | FOT | RIG | .75 | 18 Jul 0830 - 0915 | 13211 | 899822 | RIG REPAIR, CIRC WITH MUD PUMP#3 WHILE FIXING MUD PUMP#1&2. | RR | MPMP |  | 07/18/2022 | NBR-263S | .75 | QTIF-736
1465 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | NBR-304S | Hrs | HRDH-1958
1466 | CFFM | ARM | 62.75 | 15 Jul 1515 - 0600 | 9537 | 899714 | HAD LOSSES ON 1ST STAGE CEMENTING OF 9-5/8" CASING | CMT | NA |  | 07/18/2022 | NBR-304S | 1 | HRDH-1958
1467 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | NBR-654S | Hrs | HRDH-1150
1468 | FOT | WCR | 2.25 | 18 Jul 1430 - 1645 | 12283 | 899812 | MALFUNCTIONING OF THE POWER TONG, CHANGE WFD POWER TONG. | TF | CTRQ |  | 07/18/2022 | NBR-654S | 2.25 | HRDH-1150
1469 | FOT | MSD | 2.75 | 18 Jul 0915 - 1330 | 6540 | 899750 | FILL UP TOOL LEAKING | TF | CTRQ |  | 07/18/2022 | NBR-783S | 2.75 | NJYN-93
1470 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | NBR-783S | Hrs | NJYN-93
1471 | HERR | MSD | 2.75 | 17 Jul 0300 - 0915 | 0 | 899746 | EXCESS TIME DUE TO POOR EQUIPMENT | JF | CTRQ |  | 07/18/2022 | NBR-783S | .75 | NJYN-93
1472 | FOT | MSD | 2.75 | 18 Jul 0915 - 1330 | 6540 | 899750 | FILL UP TOOL LEAKING | TF | CTRQ |  | 07/18/2022 | NBR-783S | 2.75 | NJYN-93
1473 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SCTD-1 | Hrs | SDGM-1034
1474 | FOT | RIG | 32.5 | 17 Jul 1000 - 1830 | 12830 | 899720 | TURBINE DOWNHOLE FAILURE | BHA | MMOT |  | 07/18/2022 | SCTD-1 | 13.5 | SDGM-1034
1475 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SCTD-2 | Hrs | HRDH-2148
1476 | FOT | RIG | 81 | 15 Jul 2000 - 0500 | 12250 | 899733 | LEAK IN THE COIL REEL MANIFOLD; BOTH SHAFTS CRACKED AND WORN DOWN. | RR | CSYS |  | 07/18/2022 | SCTD-2 | 24 | HRDH-2148
1477 | PCPF | TK1 | 52.75 | 15 Jul 0215 - 0700 | 7780 | 899840 | HAD S/O ON WL TOOLS TRY PASS OBSTRUCTION SEVERAL TIME WITHOUT SUCCESS. | TH | NA |  | 07/18/2022 | SINO-12L | 2 | HRDH-498
1478 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SINO-12L | Hrs | HRDH-498
1479 | FOT | RIG | 3 | 18 Jul 0930 - 1230 | 10440 | 899801 | DRILLING LINE SLIPPED FROM THE DRILL LINE CLAMP IN DRAWWORK DRUM, | RR | DWKS |  | 07/18/2022 | SINO-12L | 3 | HRDH-498
1480 | PCPF | TK1 | 52.75 | 15 Jul 0215 - 0700 | 7780 | 899840 | HAD S/O ON WL TOOLS TRY PASS OBSTRUCTION SEVERAL TIME WITHOUT SUCCESS. | TH | NA |  | 07/18/2022 | SINO-12L | 2 | HRDH-498
1481 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SINO-26 | Hrs | UTMN-1231
1482 | FOT | HUD | 5.5 | 18 Jul 2330 - 0500 | 8825 | 899838 | OBSERVED HALLIBURTON MPD BEARING ELEMENT START SLIGHT LEAKING. | TF | MPD |  | 07/18/2022 | SINO-26 | 5.5 | UTMN-1231
1483 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SND-2005 | Hrs | MHKK-2
1484 | HERR | RIG | 98.25 | 14 Jul 1730 - 2115 | 13903 | 899640 | FOUND A SMALL PIECE OF METAL LODGED IN BETWEEN BIT BLADES (1.5") & 1 PIECE (2" U-SHAPED) LODGED IN NEAR BIT REAMER. | FISH | BHA |  | 07/18/2022 | SND-2005 | 16.25 | MHKK-2
1485 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SND-2007 | Hrs | AWTD-104001
1486 | HERR | RIG | 9 | 18 Jul 2000 - 0500 | 14393 | 899817 | DRILLER CLOSE BLIND/SHEAR RAM ON 5.5" DRILL PIPE TEST JT, CUT THE JOINT, POOH WIH CUT JT. | JF | BOP |  | 07/18/2022 | SND-2007 | 9 | AWTD-104001
1487 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SND-2008 | Hrs | HRDH-1812
1488 | STDP | RIG | 264 | 07 Jul 0500 - 0500 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/18/2022 | SND-2008 | 24 | HRDH-1812
1489 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SND-2010 | Hrs | MNIF-869
1490 | FPMP | RIG | 39 | 16 Jul 0400 - 1900 | 3148 | 899698 | PUMP VALVES ACTUATED ON MUD PUMPS AND COULD NOT RESET. CANNOT USE MUD PUMPS WITHOUT POP VALVE RE-SET. | RR | MPMP |  | 07/18/2022 | SND-2010 | 14 | MNIF-869
1491 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SNF036 | Hrs | MRJN-901
1492 | FOT | HWP | 18.25 | 18 Jul 0945 - 0400 | 12800 | 899796 | OBSERVED BAD RESPONSE OF HALL WL (XMR) TOOL AT 12,800 FT. POOH & CHANGE TO BACK UP TOOL WITH SAME BAD RESPONSE. | TF | WLT |  | 07/18/2022 | SNF036 | 18.25 | MRJN-901
1493 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SP-101 | Hrs | ABQQ-559
1494 | HMWT | ARN | 11.5 | 18 Jul 0700 - 2230 | 11200 | 899795 | WAIT ON WATER DUE TO WATER WELL FAILURE. | WO | NA |  | 07/18/2022 | SP-101 | 11.5 | ABQQ-559
1495 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SP-160 | Hrs | HWTH-75
1496 | FOT | TIL | 20 | 18 Jul 0830 - 0500 | 7048 | 899772 | THE DART PLUG STUCK ACROSS BALL VALVE IN CEMENT HEAD. | TF | HGRL |  | 07/18/2022 | SP-160 | 20 | HWTH-75
1497 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SP-161 | Hrs | HRDH-532
1498 | CWEL | ARM | 35 | 17 Jul 1730 - 0500 | 2962 | 899794 | ATTEMPT TO PASS OBSTRUCTION AT 2962' SEVERAL TIMES, NO SUCCESS. | BHS | NA |  | 07/18/2022 | SP-161 | 23.5 | HRDH-532
1499 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SP-229 | Hrs | ABHD-122
1500 | HERR | RIG | 6.5 | 18 Jul 2030 - 0300 | 0 | 899775 | LACK OF DSA OR RISER FOR BOP SPACE OUT. LONG TIME TAKEN TO CONNECT BOP OUTLETS WITH ADDITIONAL CONNECTIONS. | BOP | SPOOL |  | 07/18/2022 | SP-229 | 6.5 | ABHD-122
1501 | FOT | RIG | 7.5 | 18 Jul 1145 - 1945 | 9411 | 899800 | SCR RECTIFIER CUBICLES SAME 2 AND 5 ARE DOWN | RR | PSYS |  | 07/18/2022 | SP-260 | 7.5 | HMYM-531802
1502 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SP-260 | Hrs | HMYM-531802
1503 | FOT | BHI | 17 | 17 Jul 1430 - 0800 | 9252 | 899743 | BAKER ROTARY STEERABLE SYSTEM FAILED TO RESPOND TO THE RECEIVED DOWNLINKS | BHA | RSS |  | 07/18/2022 | SP-260 | 3 | HMYM-531802
1504 | FOT | RIG | 7.5 | 18 Jul 1145 - 1945 | 9411 | 899800 | SCR RECTIFIER CUBICLES SAME 2 AND 5 ARE DOWN | RR | PSYS |  | 07/18/2022 | SP-260 | 7.5 | HMYM-531802
1505 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SP-261 | Hrs | HZEM-160212
1506 | FOT | SDM | 20 | 18 Jul 0600 - 0500 | 10783 | 899707 | SLB MWD LOST SIGNAL. | BHA | MWD |  | 07/18/2022 | SP-261 | 20 | HZEM-160212
1507 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SP-306 | Hrs | MNIF-193
1508 | FOT | RIG | 6 | 17 Jul 0000 - 0600 | 10778 | 899701 | LEAK ON KELLY HOSE. | RR | KELLY |  | 07/18/2022 | SP-306 | 1 | MNIF-193
1509 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SSA-5859 | Hrs | HWYH-1222
1510 | FOT | SPS | 1 | 18 Jul 0930 - 1030 | 17236 | 899792 | TROUBLE SHOOTING ON SIGNAL (NOISE ) | SURV | SS |  | 07/18/2022 | SSA-5859 | 1 | HWYH-1222
1511 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SSA-5868 | Hrs | HRDH-2413
1512 | HERR | RIG | 14.5 | 18 Jul 0700 - 2130 | 427 | 899833 | WHILE RIH 8 3/8" BHA, REACTIVE LEFT HAND ACTION UNSPINNED THE LIFTING SUB PARTIALLY, ONCE SAFETY CLAMP REMOVED, STRING PICKED UP ON PARTIALLY UNCREWED LIFTING SUB AND SLIPS PULLED OUT (HAD BHA DROPPED IN THE HOLE). | FISH | BHA |  | 07/18/2022 | SSA-5868 | 14.5 | HRDH-2413
1513 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/18/2022 | SSA-5970 | Hrs | UTMN-2340
1514 | STBH | ARN | 4.5 | 18 Jul 0030 - 0500 | 10200 | 899774 | OBSERVED PIPE STUCK AFTER SHUT IN & CIRC FOR WELL CONTROL. | STUK | BHA |  | 07/18/2022 | SSA-5970 | 4.5 | UTMN-2340
1515 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ADC-31 | Hrs | SDGM-1181
1516 | STDP | RIG | 160.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/19/2022 | ADC-31 | 24 | SDGM-1181
1517 | LCRW | ARM | 10.5 | 19 Jul 1830 - 0500 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/19/2022 | ADC-50 | 10.5 | SFNY-1176
1518 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ADC-50 | Hrs | SFNY-1176
1519 | WC20 | ARM | 73.25 | 16 Jul 1600 - 1715 | 3944 | 899719 | WHILE DRILLING 12-1/4" HOLE, ENCOUNTERED TOTAL LOSS OF CIRCULATION AT 3805'. ATTEMPT WITH MUD CAP DRILLING. OBSERVE WELL KICK. | WCNT | NA |  | 07/19/2022 | ADC-50 | 12.25 | SFNY-1176
1520 | LCRW | ARM | 10.5 | 19 Jul 1830 - 0500 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/19/2022 | ADC-50 | 10.5 | SFNY-1176
1521 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ADC-51 | Hrs | SDGM-1225
1522 | WC20 | ARM | 2 | 19 Jul 0300 - 0500 | 9000 | 899893 | AFTER PUMPED 3RD 100 BBL LCM PILL AT 80 PPB & WHILE DISPLACING SAME HAD RETURN FLOW INCREASED, FLOW CHECK - WELL FLOWING. SHUT IN WELL. SICP: ZERO ; SIDP: 0 PSI , CIRCULATE THROUGH CHOKE WHILE BUILDING UP MUD WT TO 78 PCF. | WCNT | NA |  | 07/19/2022 | ADC-51 | 2 | SDGM-1225
1523 | 6844 | 6499 | LOG | E | 3625 | WLT | PERFORM LOG #4 MDT-TLC. PUMPED OUT AND COLLECTED SAMPLES F/6,511 FT TO 6,499 FT (BOTTOM TO TOP) AS PER PROGRAM.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- MOVE STRING EVERY 4 HOURS/SESSION & CONFIRM STRING FREE, OK.- PUMPED 250 BBLS 87 PCF MUD CAP BEFORE EVERY SAMPLING.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 5/6.- PUMP OUT COMPLETED: 5/6.- PUMP OUT INTO WELLBORE 0.56 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 1.86 BBLS, - PUMP OUT FLUID TYPE: 2X OIL & 4X WATER.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM WHILE SAMPLING | 6844 | 6511 | SWL | 07/19/2022 | ADC-53L | LOG | HRDH-530
1524 | 6844 |  | OTH | E | 3625 | NA | PULLED BACK LOG #4 MDT - TLC TO 6,165 FT. HPJSM. SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE & POOH WL CABLE TO SURFACE. L/D SES AND WIRE LINE SHEAVES.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE WITH 2 BPH LOSSES. | 6844 |  | SWL | 07/19/2022 | ADC-53L | LOG | HRDH-530
1525 | 6844 | 162 | TO | E | 3625 | STDP | POOH LOG #4 MDT - TLC ON 4" DP STANDS F/6,165 FT TO 162 FT.- CONTROL SPEED 3 MIN/STD SLIP TO SLIP.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM | 6844 | 6165 | RIG | 07/19/2022 | ADC-53L | LOG | HRDH-530
1526 | 6844 |  | OTH | E | 3625 | NA | HPJSM, L/D LOG #4 MDT LOGGING TOOL.- CONTINUOUSLY PUMPED 87 PCF MUD CAP AT ANNULUS @ 2 BPM. | 6844 |  | SWL | 07/19/2022 | ADC-53L | LOG | HRDH-530
1527 | 6844 |  | HT | E | 3625 | BHA | M/U & RIH W/ 2 3/8" CMT STINGER ON 2 3/8" D/P FROM RACK & 4" D/P T/315 FT.- RIH TOTAL 10/32 JTS X 2 3/8" D/P.-CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/19/2022 | ADC-53L | PA | HRDH-530
1528 | 207.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/19/2022 | ADC-53L | Type | HRDH-530
1529
1530
1531 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ADC-54L | Hrs | HRDH-1499
1532 | FOT | RIG | 32.5 | 18 Jul 2030 - 0500 | 12153 | 899773 | DRAW-WORKS BRAKES ENGAGED DUE TO ELECTRICAL FAULT IN RESISTOR BANK. | RR | DWKS |  | 07/19/2022 | ADC-54L | 24 | HRDH-1499
1533 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ADC-62L | Hrs | ANDR-745
1534 | FPMP | RIG | 29 | 17 Jul 0900 - 1515 | 13046 | 899749 | TRY TO PUMP MUDZYME PILL, RIG PUMP NOT ABLE TO PUMP, TRANSFER TO DIFFERNT TANK -NO SUCCESS. | RR | MPMP |  | 07/19/2022 | ADC-62L | 4.25 | ANDR-745
1535 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ADC-64L | Hrs | UTMN-3074
1536 | FOT | SDM | 20.75 | 18 Jul 1515 - 1200 | 13032 | 899821 | RSS DRILLED 5-7/8" HOLE TO 13032 FT, OBSERVED MWD LOST SIGNAL. TROUBLE SHOOTING A SEVERAL TIME NO SUCCESS. | BHA | MWD |  | 07/19/2022 | ADC-64L | 7 | UTMN-3074
1537 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ADM-339 | Hrs | MRJN-3014
1538 | FOT | RIG | 1 | 19 Jul 2045 - 2145 | 2336 | 899915 | OBSERVED BROKEN HYD. HOSE ON CAT WALK TIPPER ARM. | RR | CATW |  | 07/19/2022 | ADM-339 | 1 | MRJN-3014
1539 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ADM-511 | Hrs | MRJN-799
1540 | CWEL | ARM | 77.75 | 16 Jul 0600 - 0500 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/19/2022 | ADM-511 | 24 | MRJN-799
1541 | XTTE | SLL | 3 | 19 Jul 0200 - 0500 | 190 | 899857 | RBP STUCK BETWEEN LANDING JT AND TIW. | JF | SLICK |  | 07/19/2022 | ARO-2003 | 3 | MNIF-435
1542 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ARO-2003 | Hrs | MNIF-435
1543 | XTTE | MSL | 11.25 | 18 Jul 0015 - 1130 | 5761 | 899835 | MANSOORI SLICKLINE LOST TOOLSTRING | JF | SLICK |  | 07/19/2022 | ARO-2003 | 6.5 | MNIF-435
1544 | XTTE | SLL | 3 | 19 Jul 0200 - 0500 | 190 | 899857 | RBP STUCK BETWEEN LANDING JT AND TIW. | JF | SLICK |  | 07/19/2022 | ARO-2003 | 3 | MNIF-435
1545 | LHFL | RIG | 1 | 19 Jul 1200 - 1300 | 7575 | 899914 | MARTIN DECKER WEIGHT INDICATOR MALFUNCTION, | RR | HSYS |  | 07/19/2022 | ENSCO-54 | 1 | ABSF-17
1546 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | ENSCO-54 | Hrs | ABSF-17
1547 | STCT | ARM | 277.5 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/19/2022 | ENSCO-54 | 23 | ABSF-17
1548 | LHFL | RIG | 1 | 19 Jul 1200 - 1300 | 7575 | 899914 | MARTIN DECKER WEIGHT INDICATOR MALFUNCTION, | RR | HSYS |  | 07/19/2022 | ENSCO-54 | 1 | ABSF-17
1549 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | JACK-203 | Hrs | HZEM-849
1550 | LCRW | ARM | 229.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/19/2022 | JACK-203 | 24 | HZEM-849
1551 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | NBR-196S | Hrs | SDGM-1235
1552 | FOT | BLH | 161.5 | 12 Jul 1130 - 0400 | 2995 | 899524 | 7" LINER HANGER STUCK IN CASED VERTICAL SECTION OF WELL, 818' BELOW ROTARY TABLE. | TF | HGRL |  | 07/19/2022 | NBR-196S | 23 | SDGM-1235
1553 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | NBR-263S | Hrs | QTIF-736
1554 | FOT | RIG | 7.75 | 18 Jul 0045 - 0830 | 13686 | 899819 | FOUND LEAK BETWEEN TOP DRIVE S.PIPE & WASH PIPE WECO UNION CONNECTION. | RR | CSYS |  | 07/19/2022 | NBR-263S | 3.5 | QTIF-736
1555 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SCTD-1 | Hrs | SDGM-1034
1556 | FOT | SCT | 2 | 19 Jul 0300 - 0500 | 0 | 899856 | HAD LEAK WHILE PT CONNECTOR, DUE TO DAMAGED WECO SEAL AT 2" CONNECTION ON REEL SIDE. | TF | CTBG |  | 07/19/2022 | SCTD-1 | 2 | SDGM-1034
1557 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SCTD-2 | Hrs | HRDH-2148
1558 | FOT | RIG | 105 | 15 Jul 2000 - 0500 | 12250 | 899733 | LEAK IN THE COIL REEL MANIFOLD; BOTH SHAFTS CRACKED AND WORN DOWN. | RR | CSYS |  | 07/19/2022 | SCTD-2 | 24 | HRDH-2148
1559 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SINO-25 | Hrs | MNIF-383
1560 | DSFT | BC | 13.5 | 19 Jul 1530 - 0500 | 7064 | 899913 | BKR COMPLETION PRESSURE UP THE TBG T/3600 PSI & SET 9-5/8" ELECPACK ESP PACKER @ 6850' ATTEMPTED TO TEST TCA TO 1000 PSI F/ 20 MINS WITH NO SUCCESS . TRIED SEVERAL TIMES; TEST FAILED. | JF | PKR |  | 07/19/2022 | SINO-25 | 13.5 | MNIF-383
1561 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SINO-26 | Hrs | UTMN-1231
1562 | FOT | HUD | 13.5 | 18 Jul 2330 - 1300 | 8825 | 899838 | OBSERVED HALLIBURTON MPD BEARING ELEMENT START SLIGHT LEAKING. | TF | MPD |  | 07/19/2022 | SINO-26 | 8 | UTMN-1231
1563 | FOT | SPS | 34 | 17 Jul 0230 - 1230 | 8855 | 899706 | WHILE DRILLING WITH LWD TOOLS, HAD LWD_AFR TOOL FAILURE, TROUBLE SHOOTING, NO SUCCESS. | BHA | LWD |  | 07/19/2022 | SINO-36L | 7.5 | SDGM-458
1564 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SINO-36L | Hrs | SDGM-458
1565 | HELD | TK1 | 237.5 | 07 Jul 2330 - 0500 | 5400 | 899508 | PROBLEM IN HOLE ACCESSIBILITY. TK1 | JF | LINR |  | 07/19/2022 | SINO-36L | 16.5 | SDGM-458
1566 | FOT | SPS | 34 | 17 Jul 0230 - 1230 | 8855 | 899706 | WHILE DRILLING WITH LWD TOOLS, HAD LWD_AFR TOOL FAILURE, TROUBLE SHOOTING, NO SUCCESS. | BHA | LWD |  | 07/19/2022 | SINO-36L | 7.5 | SDGM-458
1567 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SINO-5L | Hrs | UTMN-1029
1568 | FOT | SPS | 12 | 19 Jul 0600 - 1800 | 0 | 899892 | UNABLE TO DOWNLOAD LWD TOOLS. | BHA | LWD |  | 07/19/2022 | SINO-5L | 12 | UTMN-1029
1569 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SND-2004 | Hrs | BRRI-1148
1570 | FOT | RIG | 2.5 | 19 Jul 0100 - 0330 | 5892 | 899873 | TDS HYDRAULIC HOSE LEAKING | RR | TDS |  | 07/19/2022 | SND-2004 | 2.5 | BRRI-1148
1571 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SND-2005 | Hrs | MHKK-2
1572 | FOT | RIG | 3.25 | 19 Jul 0500 - 0815 | 13903 | 899823 | WHILE IN PROCESS OF TRYING TO PRESSURE TEST BLIND/SHEAR RAMS, OBSERVED PRESSURE BLEEDING OFF ON HIGH TEST (10,000 PSI) WITH NO VISIBLE LEAKS AT BOP. | RR | CHK |  | 07/19/2022 | SND-2005 | 3.25 | MHKK-2
1573 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SND-2007 | Hrs | AWTD-104001
1574 | HERR | RIG | 33 | 18 Jul 2000 - 0500 | 14393 | 899817 | DRILLER CLOSE BLIND/SHEAR RAM ON 5.5" DRILL PIPE TEST JT, CUT THE JOINT, POOH WIH CUT JT. | JF | BOP |  | 07/19/2022 | SND-2007 | 24 | AWTD-104001
1575 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SND-2008 | Hrs | HRDH-1812
1576 | STDP | RIG | 279.75 | 07 Jul 0500 - 2045 | 15070 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/19/2022 | SND-2008 | 15.75 | HRDH-1812
1577 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SND-3002 | Hrs | DMMM-601
1578 | FOT | WWL | 9 | 19 Jul 2000 - 0500 | 17144 | 899854 | WFD COMPACT SHUTTLE LOGGING TOOL LOST IN HOLE. | TF | WLT |  | 07/19/2022 | SND-3002 | 9 | DMMM-601
1579 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SP-160 | Hrs | HWTH-75
1580 | FOT | TIL | 10.75 | 18 Jul 1600 - 0500 | 7048 | 899772 | THE DART PLUG STUCK ACROSS BALL VALVE IN CEMENT HEAD. | TF | HGRL |  | 07/19/2022 | SP-160 | 2.25 | HWTH-75
1581 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SP-161 | Hrs | HRDH-532
1582 | CWEL | ARM | 43 | 17 Jul 1730 - 1300 | 2962 | 899794 | ATTEMPT TO PASS OBSTRUCTION AT 2962' SEVERAL TIMES, NO SUCCESS. | BHS | NA |  | 07/19/2022 | SP-161 | 8 | HRDH-532
1583 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SP-261 | Hrs | HZEM-160212
1584 | FOT | SDM | 24 | 18 Jul 0600 - 0900 | 10783 | 899707 | SLB MWD LOST SIGNAL. | BHA | MWD |  | 07/19/2022 | SP-261 | 4 | HZEM-160212
1585 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SSA-5970 | Hrs | UTMN-2340
1586 | STBH | ARN | 18 | 18 Jul 0030 - 1830 | 10200 | 899774 | OBSERVED PIPE STUCK AFTER SHUT IN & CIRC FOR WELL CONTROL. | STUK | BHA |  | 07/19/2022 | SSA-5970 | 13.5 | UTMN-2340
1587 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/19/2022 | SSA-5972 | Hrs | SHDN-19
1588 | UVLC | ARM | 15.5 | 19 Jul 1245 - 0500 | 7017 | 899855 | ENCOUNTERED COMPLETE LOSS CIRCULATION WHILE DRILLING 12" HOLE SECTION | LCIR | NA |  | 07/19/2022 | SSA-5972 | 15.5 | SHDN-19
1589 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADC-17 | Hrs | ZULF-1210
1590 | FOT | RIG | 1.5 | 20 Jul 0230 - 0400 | 0 | 899882 | STARBOARD CRANE HAS ELECTRICAL FAULT, | RR | CRN |  | 07/20/2022 | ADC-17 | 1.5 | ZULF-1210
1591 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADC-50 | Hrs | SFNY-1176
1592 | LCRW | ARM | 34.5 | 19 Jul 1830 - 0500 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/20/2022 | ADC-50 | 24 | SFNY-1176
1593 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADC-52 | Hrs | SDGM-1185
1594 | FOT | SPS | 14.5 | 20 Jul 1430 - 0500 | 15043 | 899879 | MWD QUIT RELAYING DATA TO SURFACE | BHA | MWD |  | 07/20/2022 | ADC-52 | 14.5 | SDGM-1185
1595 | 6844 |  | HT | E | 3625 | BHA | P/U & RIH 2 3/8" CMT STRING F/315 FT T/1005 FT. M/U TDS AND FLUSHED STRING, OK.- RIH TOTAL 32/32 JTS X 2 3/8" D/P.- DRIFT & FLUSHED ALL STRING.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/20/2022 | ADC-53L | PA | HRDH-530
1596 | 6844 | 6456 | TI | E | 3625 | STDP | RIH 2 3/8" CMT STRING ON 4" STANDS DP F/1005 FT T/6456 FT- FLUSHED STRING EVERY 20 STANDS RAN.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 1005 | RIG | 07/20/2022 | ADC-53L | PA | HRDH-530
1597 | 6844 |  | CIRC | E | 3625 | MPMP | WASHED HOLE F/6456 FT AND TAGGED BOTTOM AT 6844 FT. CIRCULATE HOLE.- FLOW RATE 150 GPM, PRESS 850 PSI- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/20/2022 | ADC-53L | PA | HRDH-530
1598 | 6844 |  | OTH | E | 3625 | NA | PJSM. LINE UP CEMENTING LINE AND PRESSSURE TEST TO 500/3000 PSI 5/10 MINS, OK.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SCM | 07/20/2022 | ADC-53L | PA | HRDH-530
1599 | 6844 | 6340 | CMP | E | 3625 | OEDP | PERFORM CEMENT PLUG #1 SET AT 6,840 FT AS FOLLOWS.- SLB PUMPED 45 BBLS 90 PCF MUDPUSH SPACER AHEAD.- SLB BATCH MIX & PUMPED 22 BBLS 127 PCF CEMENT SLURRY- SLB PUMPED 15 BBLS 90 PCF MUDPUSH SPACER BEHIND.- SLB PUMPED AND DISPLACED WITH 44 BBLS 77 PCF WBM.- BLEED OFF AND WELL UNDER VACUUM.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6840 | SCM | 07/20/2022 | ADC-53L | PA | HRDH-530
1600 | 6844 | 5900 | TO | E | 3625 | STDP | POOH CEMENT STRING F/6,840 FT T/5,900 FT.- POOH 5 MIN/STD F/6,840 FT T/6,240 FT.- POOH NORMAL SPEED F/6,240 FT T/5,900 FT.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6840 | RIG | 07/20/2022 | ADC-53L | PA | HRDH-530
1601 | 6844 |  | CIRC | E | 3625 | MPMP | DROPPED FOAM BALL & CIRCULATE 2X DP VOLUME WITH 77 PCF WBM.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/20/2022 | ADC-53L | PA | HRDH-530
1602 | 6844 |  | WOC | N | 3625 | SQZ | WAIT ON CMT TO REACH 500 PSI UCA, MEANWHILE:-M/U & STD BACK 4" D/P ON DRK - RECIPROCATE STRING EVERY HOURS.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | SCM | 07/20/2022 | ADC-53L | PA | HRDH-530
1603 | 6844 | 6515 | BR | N | 3625 | STRG | WASH DOWN F/5,900 FT T/6150 FT WITH 77 PCF WBM AT 70 GPM 50 PSI. ON GOING AT REPORT TIME.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 5900 | RIG | 07/20/2022 | ADC-53L | PA | HRDH-530
1604 | 231.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/20/2022 | ADC-53L | Type | HRDH-530
1605
1606
1607 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADC-54L | Hrs | HRDH-1499
1608 | FOT | RIG | 37 | 18 Jul 2030 - 0930 | 12153 | 899773 | DRAW-WORKS BRAKES ENGAGED DUE TO ELECTRICAL FAULT IN RESISTOR BANK. | RR | DWKS |  | 07/20/2022 | ADC-54L | 4.5 | HRDH-1499
1609 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADC-59L | Hrs | HWYH-1324
1610 | FOT | RIG | 2 | 20 Jul 0800 - 1000 | 8212 | 899959 | OBSERVED RIG POWER SHUT DOWN. | RR | PSYS |  | 07/20/2022 | ADC-59L | 2 | HWYH-1324
1611 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADC-64L | Hrs | UTMN-3074
1612 | FOT | SDM | 22 | 20 Jul 0630 - 0500 | 13432 | 899884 | RSS DRILLED 5-7/8" HOLE TO 13032 FT, OBSERVED MWD LOST SIGNAL. TROUBLE SHOOTING A SEVERAL TIME NO SUCCESS. | BHA | MWD |  | 07/20/2022 | ADC-64L | 22 | UTMN-3074
1613 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADES-144 | Hrs | UTMN-3152
1614 | WC20 | ARM | 21.5 | 19 Jul 1600 - 1330 | 13300 | 899875 | OBSERVED 20 BBLS DYNAMIC LOSSES THEN INCREASE IN FLOW OUT; STOPPED PUMP AND FLOW CHECK; WELL IS FLOWING. | WCNT | NA |  | 07/20/2022 | ADES-144 | 8.5 | UTMN-3152
1615 | WOTO | SDM | 1.25 | 20 Jul 2315 - 0030 | 3428 | 899955 | WAITING FOR SLB LWD BACKUP TOOLS MEANWHILE CIRCULATE HOLE CLEAN. | WO | NA |  | 07/20/2022 | ADM-510 | 1.25 | ABSF-231
1616 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADM-510 | Hrs | ABSF-231
1617 | FOT | SDM | 18.5 | 20 Jul 0845 - 0500 | 7792 | 899954 | LOST COMMUNICATION WITH LWD TOOLS. | BHA | LWD |  | 07/20/2022 | ADM-510 | 18.5 | ABSF-231
1618 | WOTO | SDM | 1.25 | 20 Jul 2315 - 0030 | 3428 | 899955 | WAITING FOR SLB LWD BACKUP TOOLS MEANWHILE CIRCULATE HOLE CLEAN. | WO | NA |  | 07/20/2022 | ADM-510 | 1.25 | ABSF-231
1619 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ADM-655 | Hrs | SFNY-308
1620 | WPD3 | AP2 | 31 | 19 Jul 2200 - 0500 | 0 | 899952 | WAIT ON SFNY NORTH FIELD SERVICE TO DE-PRESSURIZE PLATFORM SFNY-306/311 PF FOR SAFE RIG APPROACH. | WO | NA |  | 07/20/2022 | ADM-655 | 24 | SFNY-308
1621 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ARO-2003 | Hrs | MNIF-435
1622 | XTTE | SLL | 3.5 | 19 Jul 0200 - 0530 | 190 | 899857 | SLB RBP STUCK BETWEEN LANDING JT AND TIW. | JF | SLICK |  | 07/20/2022 | ARO-2003 | .5 | MNIF-435
1623 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ARO-4001 | Hrs | MRJN-532
1624 | FPMP | RIG | 1 | 20 Jul 1945 - 2045 | 6621 | 899953 | HAD VALVE LEAKS WHILE TRANFER MUD FROM PIT TO CMT UNIT AND REPLACE WITH NEW VALVE. | RR | MPMP |  | 07/20/2022 | ARO-4001 | 1 | MRJN-532
1625 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | DPS-5 | Hrs | HRDH-2319
1626 | HERR | WDS | 47 | 19 Jul 0500 - 0500 | 13101 | 899943 | WEATHERFORD UNABLE TO INITIATE SIDETRACK. | DD | MMOT |  | 07/20/2022 | DPS-5 | 23.5 | HRDH-2319
1627 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ENSCO-54 | Hrs | ABSF-17
1628 | STCT | ARM | 305 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/20/2022 | ENSCO-54 | 24 | ABSF-17
1629 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | ENSCO-76 | Hrs | MRJN-853
1630 | FOT | RIG | 2.25 | 20 Jul 1915 - 2215 | 6732 | 899937 | WHILE RUNNING CASING U-BOLTS ON EVEVATOR LINKS SLIPPED, UNABLE TO REACH V-DOOR TO LATCH ONTO CASING | RR | TDS |  | 07/20/2022 | ENSCO-76 | 2.25 | MRJN-853
1631 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | EXL-IA | Hrs | SFNY-1790
1632 | FOT | FMC | .75 | 20 Jul 2230 - 2315 | 0 | 899935 | FRANKS TONG FAILED TO OPERATE DUE TO BROKEN CONTROL LEVER | TF | CTRQ |  | 07/20/2022 | EXL-IA | .75 | SFNY-1790
1633 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | JACK-203 | Hrs | HZEM-849
1634 | LCRW | ARM | 253.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/20/2022 | JACK-203 | 24 | HZEM-849
1635 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | NBR-20S | Hrs | HMYM-433514
1636 | XTTE | RIG | 11.25 | 15 Jul 2245 - 0500 | 0 | 899753 | EXCESS TIME TO LAYDOWN 5" DRILL PIPE. | TF | DP |  | 07/20/2022 | NBR-20S | 9.5 | HMYM-433514
1637 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | NBR-263S | Hrs | QTIF-736
1638 | FOT | RIG | 1.5 | 20 Jul 1330 - 1500 | 14068 | 899934 | IRON-ROUGH NECK MALFUNCTIONED, FIXED SAME. | RR | HSYS |  | 07/20/2022 | NBR-263S | 1.5 | QTIF-736
1639 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | PA-218S | Hrs | HRDH-1941
1640 | FOT | MSD | 1.5 | 20 Jul 0030 - 0200 | 1000 | 899880 | EXCESS TIME ON AL-MASAOOD CASING RUNNING SERVICE. DUE TO MALFUNCTION OF POWER TONGE AND POWER UNIT LED TO CHANGE SAME AND P/U THE PACK UP TONGE & POWER UNIT. | TF | CTRQ |  | 07/20/2022 | PA-218S | 1.5 | HRDH-1941
1641 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | PA-622S | Hrs | UTMN-3600
1642 | FOT | RIG | 6 | 20 Jul 2200 - 0400 | 7234 | 899957 | WHILE DRILLING 12" HOLE TDS ROTARY MALFUNCTION, TROUBLESHOOT TDS NO SUCCESS. POOH TO 13-3/8" SHOE, FOUND AC NOT WORKING CAUSING CANRIG TDS ROOM TO OVERHEATE. | RR | TDS |  | 07/20/2022 | PA-622S | 6 | UTMN-3600
1643 | FOT | RIG | 6.5 | 20 Jul 0530 - 1300 | 2184 | 899960 | MALFUNCTION ON BX ELEVATORS, TROUBLESHOOT AND REPAIR SAME | RR | TDS |  | 07/20/2022 | RM-74A | 6.5 | HSBH-68
1644 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | RM-74A | Hrs | HSBH-68
1645 | FOT | RIG | 2 | 20 Jul 1530 - 1730 | 2226 | 899941 | OBSERVED PUMP SWAB ISSUE ON PUMP 3 & 1 | RR | MPMP |  | 07/20/2022 | RM-74A | 2 | HSBH-68
1646 | FOT | RIG | 6.5 | 20 Jul 0530 - 1300 | 2184 | 899960 | MALFUNCTION ON BX ELEVATORS, TROUBLESHOOT AND REPAIR SAME | RR | TDS |  | 07/20/2022 | RM-74A | 6.5 | HSBH-68
1647 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SCTD-1 | Hrs | SDGM-1034
1648 | FOT | SCT | 6 | 19 Jul 0300 - 0900 | 0 | 899856 | HAD LEAK WHILE PT CONNECTOR, DUE TO DAMAGED WECO SEAL AT 2" CONNECTION ON REEL SIDE. | TF | CTBG |  | 07/20/2022 | SCTD-1 | 4 | SDGM-1034
1649 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SCTD-2 | Hrs | HRDH-2148
1650 | FOT | RIG | 129 | 15 Jul 2000 - 0500 | 12250 | 899733 | LEAK IN THE COIL REEL MANIFOLD; BOTH SHAFTS CRACKED AND WORN DOWN. | RR | CSYS |  | 07/20/2022 | SCTD-2 | 24 | HRDH-2148
1651 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SINO-16 | Hrs | JLDI-858
1652 | EXPL | ARM | 12 | 20 Jul 1700 - 0500 | 0 | 899938 | WAIT ON EXPLOSIVE MATERIAL FROM BAGGAH EXPLOSIVE SHOP TO BE RELEASED NEXT DAY MORING. | WO | NA |  | 07/20/2022 | SINO-16 | 12 | JLDI-858
1653 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SINO-19L | Hrs | UTMN-252
1654 | FOT | HWP | 6 | 20 Jul 2030 - 0230 | 10780 | 899972 | XRMI-IMAGE TOOL FAILURE | TF | CORRL |  | 07/20/2022 | SINO-19L | 6 | UTMN-252
1655 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SINO-25 | Hrs | MNIF-383
1656 | DSFT | BC | 37.5 | 19 Jul 1530 - 0500 | 7064 | 899913 | BKR COMPLETION PRESSURE UP THE TBG T/3600 PSI & SET 9-5/8" ELECPACK ESP PACKER @ 6850' ATTEMPTED TO TEST TCA TO 1000 PSI F/ 20 MINS WITH NO SUCCESS . TRIED SEVERAL TIMES; TEST FAILED. | JF | PKR |  | 07/20/2022 | SINO-25 | 24 | MNIF-383
1657 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SINO-36L | Hrs | SDGM-458
1658 | HELD | TK1 | 261.5 | 07 Jul 2330 - 0500 | 5400 | 899508 | PROBLEM IN HOLE ACCESSIBILITY. TK1 | JF | LINR |  | 07/20/2022 | SINO-36L | 24 | SDGM-458
1659 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SINO-5L | Hrs | UTMN-1029
1660 | FOT | SPS | 3.5 | 20 Jul 0130 - 0500 | 8989 | 899942 | UNABLE TO BUILD INCLINITION AS PER GOC REQUEST. | BHA | RSS |  | 07/20/2022 | SINO-5L | 3.5 | UTMN-1029
1661 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SND-2004 | Hrs | BRRI-1148
1662 | FOT | RIG | 1 | 20 Jul 2315 - 0015 | 4894 | 899939 | IRON ROUGHNECK HYDRAULIC HOSE LEAKING THAT FUNCTION FORWARD AND BACKWARD MOVEMENT. | RR | HSYS |  | 07/20/2022 | SND-2004 | 1 | BRRI-1148
1663 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SND-2007 | Hrs | AWTD-104001
1664 | HERR | RIG | 34 | 18 Jul 2000 - 0600 | 14393 | 899817 | DRILLER CLOSE BLIND/SHEAR RAM ON 5.5" DRILL PIPE TEST JT, CUT THE JOINT, POOH WIH CUT JT. | JF | BOP |  | 07/20/2022 | SND-2007 | 1 | AWTD-104001
1665 | FOT | WI3 | 19.5 | 20 Jul 0930 - 0500 | 12992 | 899932 | AFTER DRILLING 9 FT OF FM, UNABLE TO DRILL AHEAD, POH TO CHECK DIR ASSY AND BIT, FOUND THAT BIT IS COMPLETELY WORNED OUT AND THE RSS TOOL HAD SCRATCH FROM THE WHIPSTOCK | TF | WPSTK |  | 07/20/2022 | SND-2008 | 19.5 | HRDH-1812
1666 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SND-2008 | Hrs | HRDH-1812
1667 | STDP | RIG | 292.5 | 07 Jul 0500 - 0930 | 12992 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/20/2022 | SND-2008 | 4.5 | HRDH-1812
1668 | FOT | WI3 | 19.5 | 20 Jul 0930 - 0500 | 12992 | 899932 | AFTER DRILLING 9 FT OF FM, UNABLE TO DRILL AHEAD, POH TO CHECK DIR ASSY AND BIT, FOUND THAT BIT IS COMPLETELY WORNED OUT AND THE RSS TOOL HAD SCRATCH FROM THE WHIPSTOCK | TF | WPSTK |  | 07/20/2022 | SND-2008 | 19.5 | HRDH-1812
1669 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SND-3001 | Hrs | MHWZ-167101
1670 | XTRI | MSD | 1.25 | 20 Jul 2345 - 0100 | 7021 | 899883 | ONGOING ISSUES WITH POWER SUPPLY TO JAM UNIT | JF | CTRQ |  | 07/20/2022 | SND-3001 | 1.25 | MHWZ-167101
1671 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SND-3002 | Hrs | DMMM-601
1672 | FOT | WWL | 24 | 19 Jul 2000 - 2230 | 17144 | 899854 | WFD COMPACT SHUTTLE LOGGING TOOL LOST IN HOLE. | TF | WLT |  | 07/20/2022 | SND-3002 | 15 | DMMM-601
1673 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SP-110 | Hrs | BRRI-562
1674 | FOT | RIG | 5.5 | 20 Jul 1330 - 1900 | 15089 | 899878 | REPLACED TDS HYDRAULIC IBOP DUE TO LEAK. | RR | TDS |  | 07/20/2022 | SP-110 | 5.5 | BRRI-562
1675 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SP-160 | Hrs | HWTH-75
1676 | FOT | TIL | 14 | 18 Jul 1600 - 0815 | 7048 | 899772 | THE DART PLUG STUCK ACROSS BALL VALVE IN CEMENT HEAD. | TF | HGRL |  | 07/20/2022 | SP-160 | 3.25 | HWTH-75
1677 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SSA-101 | Hrs | QTIF-785
1678 | FOT | WWD | 18 | 20 Jul 1100 - 0500 | 18419 | 899877 | WFD 7" WHIP STOCK ANCHOR SLIPS NOT ENGAGE / SET. TRY SEVERAL ATTEMPTS BUT WHIP STOCK FAIL TO SET. | TF | WPSTK |  | 07/20/2022 | SSA-101 | 18 | QTIF-785
1679 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SSA-5859 | Hrs | HWYH-1222
1680 | FOT | SPS | 3 | 20 Jul 2000 - 2300 | 18370 | 899933 | TROUBLE SHOOTING ON MWD SIGNAL | SURV | SS |  | 07/20/2022 | SSA-5859 | 3 | HWYH-1222
1681 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SSA-5972 | Hrs | SHDN-19
1682 | UVLC | ARM | 39 | 19 Jul 1245 - 0500 | 7017 | 899855 | ENCOUNTERED COMPLETE LOSS CIRCULATION WHILE DRILLING 12" HOLE SECTION | LCIR | NA |  | 07/20/2022 | SSA-5972 | 23.5 | SHDN-19
1683 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/20/2022 | SSA-5974 | Hrs | HRDH-2187
1684 | UVLC | ARM | 39.5 | 19 Jul 1230 - 0500 | 910 | 899958 | GOT TOTAL LOSSES @ 900' WHILE DRILLING 22" HOLE. | LCIR | NA |  | 07/20/2022 | SSA-5974 | 23 | HRDH-2187
1685 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADC-17 | Hrs | ZULF-1210
1686 | HINW | MSL | 11 | 21 Jul 1800 - 0500 | 5490 | 899948 | MANSOORI SLICKLINE 3.5" SHIFTING TOOL STUCK WHILE POH @5490 FT | STUK | SLICK |  | 07/21/2022 | ADC-17 | 11 | ZULF-1210
1687 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADC-31 | Hrs | SDGM-1181
1688 | STDP | RIG | 208.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/21/2022 | ADC-31 | 24 | SDGM-1181
1689 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADC-35 | Hrs | MAQL-5
1690 | FOT | RIG | 2.5 | 21 Jul 0000 - 0230 | 11940 | 900012 | SECONDARY KELLY HOSE GATE VALVE ON STAND PIPE IS LEAKING. | RR | CSYS |  | 07/21/2022 | ADC-35 | 2.5 | MAQL-5
1691 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADC-50 | Hrs | SFNY-1176
1692 | LCRW | ARM | 58.5 | 19 Jul 1830 - 0500 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/21/2022 | ADC-50 | 24 | SFNY-1176
1693 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADC-52 | Hrs | SDGM-1185
1694 | FOT | SPS | 36.5 | 20 Jul 1430 - 0500 | 15043 | 899879 | SPERRY RSS TOOL NOT RESPONDING.LOST SIGNAL. | BHA | RSS |  | 07/21/2022 | ADC-52 | 22 | SDGM-1185
1695 | 6844 |  | OTH | E | 3625 | NA | WASH DOWN F/6,150 FT AND TAGGED TOP OF CP #1 AT 6,524 FT WITH 77 PCF WBM AT 70 GPM 50 PSI.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1696 | 6844 | 1005 | TO | E | 3625 | STDP | POOH 2-3/8" CEMENT STRING ON 4" STANDS DP TO 1005 FT.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 6524 | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1697 | 6844 |  | HT | E | 3625 | BHA | HPJSM. L/D 32 JOINTS 2-3/8 CEMENT STRING.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1698 | 6844 |  | HT | E | 3625 | BHA | PJSM. P/U & M/U 7" SCRAPPER WITH BIT #9RR AND RIH TO 447 FT.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1699 | 6844 | 6100 | TI | E | 3625 | STDP | RIH 7" SCRAPPER BHA ON 4" DP STANDS F/510 FT T/6100 FT- FILL UP STRING EVERY 20 STANDS RAN- CAREFULLY PASS 7" TOL AT 1613 FT.- TRIP SPEED 150 FT/MIN- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 510 | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1700 | 6844 |  | OTH | E | 3625 | NA | M/U TDS AND SCRAPPED DEPTH INTERVAL 6,180 FT - 6,250 FT (BIT DEPTH 6,216 FT - 6,286 FT) 3 TIMES UP & DOWN.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1701 | 6844 | 2250 | TO | E | 3625 | STDP | POOH 7" SCRAPER ASSY FROM 6,286 FT TO 2,250 FT- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM.- DECISION MADE FROM OFFICE TO RUN BACK AND SCRAP INTERVAL F/ 5,757 FT TO 5,957 FT (CMT RETAINER SETTING DEPTH @ 5,857 FT). | 6844 | 6286 | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1702 | 6844 | 5793 | TI | E | 3625 | STDP | RIH WITH 7" SCRAPER ASSY ON 4" DP STDS F/ 2,250 FT TO 5,793 FT.- FILL UP STRING EVERY 20 STANDS RAN- TRIP SPEED 150 FT/MIN- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 2250 | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1703 | 6844 |  | OTH | E | 3625 | NA | M/U TDS AND SCRAPPED DEPTH INTERVAL 5,757 FT - 5,957 FT (BIT DEPTH 5,793 FT - 5,993 FT) 3 TIMES UP & DOWN.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1704 | 6844 | 1650 | TO | E | 3625 | STDP | POOH 7" SCRAPER ASSY FROM 5,993 FT TO 1,650 FT. ON GOING AT REPORT TIME.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 5993 | RIG | 07/21/2022 | ADC-53L | PA | HRDH-530
1705 | 255.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 6-1/8" HOLE | 24 | 3625 | 09 Jul 0000 | 07/21/2022 | ADC-53L | Type | HRDH-530
1706
1707
1708 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADC-64L | Hrs | UTMN-3074
1709 | FOT | SDM | 24.5 | 20 Jul 0630 - 0730 | 13432 | 899884 | RSS DRILLED 5-7/8" HOLE TO 13032 FT, OBSERVED MWD LOST SIGNAL. TROUBLE SHOOTING A SEVERAL TIME NO SUCCESS. | BHA | MWD |  | 07/21/2022 | ADC-64L | 2.5 | UTMN-3074
1710 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADES-144 | Hrs | UTMN-3152
1711 | WC20 | ARM | 37 | 19 Jul 1600 - 2330 | 13300 | 899875 | OBSERVED 20 BBLS DYNAMIC LOSSES THEN INCREASE IN FLOW OUT; STOPPED PUMP AND FLOW CHECK; WELL IS FLOWING. | WCNT | NA |  | 07/21/2022 | ADES-144 | 15.5 | UTMN-3152
1712 | FPMP | RIG | .5 | 21 Jul 0330 - 0400 | 8212 | 899996 | HAD FAILURE IN MUD PUMP # 1 & 2, STOP DRILLING. | RR | MPMP |  | 07/21/2022 | ADM-510 | .5 | ABSF-231
1713 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADM-510 | Hrs | ABSF-231
1714 | AINC | SDM | 2 | 21 Jul 0230 - 0500 | 8176 | 899949 | OBSERVE DIFFICULTIES TO STEER UP SLB RSS TO CATCH THE DIRECTION PLAN. | LROP | BHA |  | 07/21/2022 | ADM-510 | 2 | ABSF-231
1715 | FOT | SDM | 35.5 | 20 Jul 0845 - 2200 | 7792 | 899954 | LOST COMMUNICATION WITH LWD TOOLS. POOH TO CHANGE BHA. | BHA | LWD |  | 07/21/2022 | ADM-510 | 17 | ABSF-231
1716 | FPMP | RIG | .5 | 21 Jul 0330 - 0400 | 8212 | 899996 | HAD FAILURE IN MUD PUMP # 1 & 2, STOP DRILLING. | RR | MPMP |  | 07/21/2022 | ADM-510 | .5 | ABSF-231
1717 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADM-511 | Hrs | MRJN-799
1718 | CWEL | ARM | 125.75 | 16 Jul 0600 - 0500 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/21/2022 | ADM-511 | 24 | MRJN-799
1719 | DAY | ARM | 11 | 21 Jul 1800 - 0500 | 0 | 899997 | WAIT ON DAYLIGHT TO MOVE RIG TO SFNY-306/311 PF. | WON | NA |  | 07/21/2022 | ADM-655 | 11 | SFNY-308
1720 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ADM-655 | Hrs | SFNY-308
1721 | WPD3 | AP2 | 44 | 19 Jul 2200 - 1800 | 0 | 899952 | WAIT ON SFNY NORTH FIELD SERVICE TO DE-PRESSURIZE PLATFORM SFNY-306/311 PF FOR SAFE RIG APPROACH. | WO | NA |  | 07/21/2022 | ADM-655 | 13 | SFNY-308
1722 | DAY | ARM | 11 | 21 Jul 1800 - 0500 | 0 | 899997 | WAIT ON DAYLIGHT TO MOVE RIG TO SFNY-306/311 PF. | WON | NA |  | 07/21/2022 | ADM-655 | 11 | SFNY-308
1723 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ARO-4001 | Hrs | MRJN-532
1724 | FOT | RIG | 1 | 21 Jul 1615 - 1715 | 6338 | 899887 | FOUND LEAKS ON ACTUATOR CYLINDER OF IBOP. REPLACE WITH NEW CYLINDER. | RR | TDS |  | 07/21/2022 | ARO-4001 | 1 | MRJN-532
1725 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | DPS-4 | Hrs | MDRK-63
1726 | ORDS | ARM | 11.5 | 21 Jul 1600 - 0330 | 11878 | 899889 | WAITING ON SCHLUMBERGER MWD-GR TOOLS DUE TO LAST-MINUTE DECISION BY GOC TO PICK UP 9-5/8" CASING POINT USING MWD-GR | WO | NA |  | 07/21/2022 | DPS-4 | 11.5 | MDRK-63
1727 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | DPS-5 | Hrs | HRDH-2319
1728 | FOT | WI3 | 43.75 | 20 Jul 0500 - 0245 | 13101 | 899947 | WEATHERFORD UNABLE TO INITIATE SIDETRACK DUE TO SETTING WIS WHIPSTOCK. | TF | WPSTK |  | 07/21/2022 | DPS-5 | 20.25 | HRDH-2319
1729 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | DQ-57L | Hrs | KHRS-399
1730 | FOT | SBA | 24 | 21 Jul 0500 - 0500 | 4443 | 899950 | PRAXIS ESP ISOPAX PACKER 9 5/8 FAIL TO SET . | TF | PKR |  | 07/21/2022 | DQ-57L | 24 | KHRS-399
1731 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | ENSCO-54 | Hrs | ABSF-17
1732 | STCT | ARM | 329 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/21/2022 | ENSCO-54 | 24 | ABSF-17
1733 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | EXL-IA | Hrs | SFNY-1790
1734 | HERR | BCM | 1 | 21 Jul 1415 - 1515 | 1470 | 899995 | WHILE CIRCULATING CSG, OBSERVED CMT HEAD LEAKING. RIG DOWN CEMENT HEAD CLEANED OUT THREADS & RE-INSTALLED SAME. BROKE CIRCULATION NO LEAKS | CMT | NA |  | 07/21/2022 | EXL-IA | 1 | SFNY-1790
1735 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | HWU-1 | Hrs | HZEM-163012
1736 | HERR | RIG | 22.25 | 20 Jul 1445 - 1300 | 4077 | 899885 | 1.901'' DRIFT WOULD NOT PASS TOOL JT @ 1807', POOH 51 JTS, MAKE DRIFT RUN,GOOD. | JF | TBG |  | 07/21/2022 | HWU-1 | 8 | HZEM-163012
1737 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | JACK-203 | Hrs | HZEM-849
1738 | LCRW | ARM | 277.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/21/2022 | JACK-203 | 24 | HZEM-849
1739 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | NBR-20S | Hrs | HMYM-433514
1740 | XTTE | RIG | 31 | 20 Jul 1930 - 0230 | 18240 | 899946 | EXCESSIVE TIME TO LAYDOWN DRILLPIPE. | TF | DP |  | 07/21/2022 | NBR-20S | 21.5 | HMYM-433514
1741 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | NBR-797S | Hrs | UTMN-3119
1742 | FOT | RIG | 2 | 21 Jul 0000 - 0200 | 190 | 899891 | OBSERVE SPARKS COMING OUT OF THE TDS BLOWER MOTOR. INSPECT BLOWER MOTOR & FOUND BASE PLATE BOLTS ALL LOOSE & WASHED OUT | RR | TDS |  | 07/21/2022 | NBR-797S | 2 | UTMN-3119
1743 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | PA-785S | Hrs | QTIF-269
1744 | FOT | BAW | 20 | 21 Jul 0630 - 0230 | 11596 | 900013 | BAKER E/L TOOL FAILURE AND LOST COMMUNICATION | TF | WLT |  | 07/21/2022 | PA-785S | 20 | QTIF-269
1745 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SCTD-1 | Hrs | SDGM-1034
1746 | FOT | RIG | 14 | 21 Jul 0530 - 1930 | 12722 | 899992 | D&M LOST TELEMETRY WITH DOWN HOLE TOOLS. | BHA | MMOT |  | 07/21/2022 | SCTD-1 | 14 | SDGM-1034
1747 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SCTD-2 | Hrs | HRDH-2148
1748 | GRF | RIG | 153 | 15 Jul 2000 - 0500 | 12250 | 899733 | LEAK IN THE COIL REEL MANIFOLD; BOTH SHAFTS CRACKED AND WORN DOWN. | UPRA | CSYS |  | 07/21/2022 | SCTD-2 | 24 | HRDH-2148
1749 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SINO-16 | Hrs | JLDI-858
1750 | EXPL | BAW | 28 | 20 Jul 1700 - 2100 | 0 | 899938 | WAIT ON EXPLOSIVE MATERIAL FROM BAGGAH EXPLOSIVE SHOP TO BE RELEASED NEXT DAY MORING. DELAY EXPLOSIVE JOB REQUEST DUE TO BAKER DENIED THE JOB & CHANGED THE EXPOLSIVE REQUEST TO NESR. | WO | NA |  | 07/21/2022 | SINO-16 | 16 | JLDI-858
1751 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SINO-19L | Hrs | UTMN-252
1752 | FOT | HWP | 32.5 | 20 Jul 2030 - 0500 | 10780 | 899972 | XRMI-IMAGE TOOL FAILURE | TF | CORRL |  | 07/21/2022 | SINO-19L | 24 | UTMN-252
1753 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SINO-25 | Hrs | MNIF-383
1754 | DSFT | BC | 61.5 | 19 Jul 1530 - 0500 | 7064 | 899913 | AS PER BAKER COMPLETION INSTRUCTIONS SET 9-5/8" ELECPACK ESP PACKER @ 6850' ATTEMPTED TO PRESSSURE TEST TCA TO 1000 PSI F/ 20 MINS ( PT FAILED ) . REPEATED TCA PT SEVERAL TIMES; TCA PRESSURE TEST FAILED. | JF | PKR |  | 07/21/2022 | SINO-25 | 24 | MNIF-383
1755 | 7408 |  | HT | N |  | STRG | CONTINUE RIH W/ 3-7/8" TANDEM C/O ASSY ON 4" DP TO 7230' - FILL UP & BREAK CIRC EVERY 15 STDS.- WORK 7" SCRAPER ACROSS COMPL. PKR SETTING DEPTH- TAG PBR NO-GO AT 4,876 FT POLISH MILL DEPTH | 7408 |  | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1756 | 7408 |  | CIRC | N |  | MPMP | SWEEP HOLE W/ 20 BBLS HVP & CHC W/ 74 PCF BRINE. FLOW CHECK FOR HALF HOUR. WELL STATIC. | 7408 |  | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1757 | 7408 | 4910 | TO | N |  | SPDP | POH WITH 3 7/8" C/O ASSY FROM 7,230 FT TO 4,910 FT | 7408 | 7230 | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1758 | 7408 |  | CIRC | N |  | MPMP | CIRC. BTM-UP BELOW 4 1/2" LINER. | 7408 |  | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1759 | 7408 | 2785 | TO | N |  | STDP | POH WITH 3 7/8" C/O ASSY FROM 4,910 FT TO 2,785 FT | 7408 | 4910 | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1760 | 7408 |  | HT | N |  | BHA | POH WITH 3 7/8" C/O ASSY FROM 2,785 FT TO 2,340 FT MEANWHILE L/D TANDEM CLEAN OUT BHA. | 7408 |  | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1761 | 7408 |  | HT | N |  | PEL | R/D 4'' DP HANDLLNG TOOLS & R/U 2 3/8'' HANDLING TOOLS. | 7408 |  | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1762 | 7408 |  | CIRC | N |  | MPMP | L/D 9 JTS OF 2-3/8'' D/P ( +/- 50 FT BELOW 7'' TOL), CIRC. BTM-UP BELOW 7" LINER. | 7408 |  | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1763 | 7408 | 0 | LDP | N |  | STRG | POH WITH 3 7/8" C/O ASSY MEANWHILE L/D 2-3/8'' D/P FROM 2,058 FT TO BHA. | 7408 | 2058 | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1764 | 7408 |  | HT | N |  | BHA | HPJSM, L/D 3-7/8" PDC BIT AND CLEAN OUT BHA. | 7408 |  | RIG | 07/21/2022 | SINO-42L | CT | HWYH-353
1765 | 7408 |  | NU | E | 3747 | SNIP | (OOS) R/D BELL NIPPLE & RU 9 5/8" SHOOTING NIPPLE | 7408 |  | HWP | 07/21/2022 | SINO-42L | LOG | HWYH-353
1766 | 7408 |  | OTH | E | 3747 | NA | (OOS) HPJSM WITH ALL INVOLVED PERSONEL.- P/U GR-CCL-2-7/8"PERFORATION GUN.- 1 X 2-7/8" MAXFORCE GUNS - 6 SPF - TOTAL: 10+12 FT. - RIH RUN #01, W/ GR-CCL-GUN #1 ASSY. T/ 7050'- CONFIRMED PERFORATION DEPTHS W/ ARAMCO WOE, FIRED GUN AND PERFORATED INTERVALS FROM 6930'-6940/ 6910'-6922' (24') ARBD- POOH W/ GR-CCL-3-1/8" GUN TO SURFACE.- CONFIRMED GUNS 100% FIRED.- FLOW CHECK. WELL STATIC. | 7408 |  | HWP | 07/21/2022 | SINO-42L | LOG | HWYH-353
1767 | 7408 |  | OTH | E | 3747 | NA | (OOS) P/U GR-CCL-2-7/8"PERFORATION GUN.- 1 X 2-7/8" MAXFORCE GUNS - 6 SPF - TOTAL: 15 FT. - RIH RUN #02, W/ GR-CCL-GUN #2 ASSY. T/ 6900'- CORRELATE DEPTH FOR GUNS RUN #2....INC@RPT. | 7408 |  | HWP | 07/21/2022 | SINO-42L | LOG | HWYH-353
1768 | 13 | OOS | Category | DOOS ID | PERF | Out of Scope Summary | PERFORATE 4.5" LINER. | 13 | 3747 | 21 Jul 0230 | 07/21/2022 | SINO-42L | Type | HWYH-353
1769
1770
1771 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SINO-5L | Hrs | UTMN-1029
1772 | FOT | SPS | 26.5 | 20 Jul 0130 - 0400 | 8989 | 899942 | UNABLE TO BUILD INCLINITION AS PER GOC REQUEST. | BHA | RSS |  | 07/21/2022 | SINO-5L | 23 | UTMN-1029
1773 | DSFT | SCP | 1 | 21 Jul 1100 - 1200 | 2650 | 899994 | EXCESS TIME M/U SLB LBFV TO LINER HANGER & SCREENS ASSY. | JF | PKR |  | 07/21/2022 | SL-7 | 1 | ZULF-1332
1774 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SL-7 | Hrs | ZULF-1332
1775 | DSFT | HLH | 1 | 21 Jul 1000 - 1100 | 2850 | 899993 | EXCESS TIME M/U HALL LINER HANGER | JF | LLAP |  | 07/21/2022 | SL-7 | 1 | ZULF-1332
1776 | DSFT | SCP | 1 | 21 Jul 1100 - 1200 | 2650 | 899994 | EXCESS TIME M/U SLB LBFV TO LINER HANGER & SCREENS ASSY. | JF | PKR |  | 07/21/2022 | SL-7 | 1 | ZULF-1332
1777 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SND-2008 | Hrs | HRDH-1812
1778 | FOT | WWD | 43.5 | 20 Jul 0930 - 0500 | 12992 | 899932 | AFTER DRILLING 9 FT OF FM, UNABLE TO DRILL AHEAD, POH TO CHECK DIR ASSY AND BIT, FOUND THAT BIT IS COMPLETELY WORNED OUT AND THE RSS TOOL HAD SCRATCH FROM THE WHIPSTOCK | TF | WPSTK |  | 07/21/2022 | SND-2008 | 24 | HRDH-1812
1779 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SND-3002 | Hrs | DMMM-601
1780 | FOT | WWL | 25.25 | 19 Jul 2000 - 0500 | 17144 | 899854 | WFD COMPACT SHUTTLE LOGGING TOOL LOST IN HOLE. | TF | WLT |  | 07/21/2022 | SND-3002 | 1.25 | DMMM-601
1781 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SND-3003 | Hrs | HRDH-1816
1782 | FOT | SPS | 8 | 21 Jul 2100 - 0500 | 11395 | 899890 | SPS I-CRUSIE RSS TURBINE FAILURE. | BHA | RSS |  | 07/21/2022 | SND-3003 | 8 | HRDH-1816
1783 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SP-110 | Hrs | BRRI-562
1784 | FOT | RIG | 1 | 21 Jul 0715 - 0815 | 15089 | 899945 | RIG POWER TONG MALFUNCTIONED. | RR | HSYS |  | 07/21/2022 | SP-110 | 1 | BRRI-562
1785 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SP-58 | Hrs | HRDH-795
1786 | FOT | SPS | 5.5 | 21 Jul 2330 - 0500 | 14282 | 899974 | LOST COMMNICATION WITH MWD, MWD PULSER FAILED | BHA | MWD |  | 07/21/2022 | SP-58 | 5.5 | HRDH-795
1787 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SSA-101 | Hrs | QTIF-785
1788 | FOT | WWD | 41.5 | 20 Jul 1100 - 0500 | 18419 | 899877 | WFD 7" WHIP STOCK ANCHOR SLIPS NOT ENGAGE / SET. TRY SEVERAL ATTEMPTS BUT WHIP STOCK FAIL TO SET. | TF | WPSTK |  | 07/21/2022 | SSA-101 | 23.5 | QTIF-785
1789 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SSA-5859 | Hrs | HWYH-1222
1790 | FOT | SPS | 7.5 | 20 Jul 2000 - 2230 | 18370 | 899933 | TROUBLE SHOOTING ON MWD SIGNAL | SURV | SS |  | 07/21/2022 | SSA-5859 | 4.5 | HWYH-1222
1791 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SSA-5868 | Hrs | HRDH-2413
1792 | FOT | BHI | 9.5 | 21 Jul 1930 - 0500 | 11770 | 899888 | WHILE DRLG 5-7/8" HOLE, MWD PULSER FAILED. TROUBLESHOOTING TRIALS: > CHANGED ACTIVE PUMP > CHANGED GPM > PUMPED TANDEM PILL LOW VIS/HIGH VIS ,NO TOOL RESPONSE. | BHA | MWD |  | 07/21/2022 | SSA-5868 | 9.5 | HRDH-2413
1793 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/21/2022 | SSA-5972 | Hrs | SHDN-19
1794 | UVLC | ARM | 62.5 | 19 Jul 1245 - 0500 | 7017 | 899855 | ENCOUNTERED COMPLETE LOSS CIRCULATION WHILE DRILLING 12" HOLE SECTION | LCIR | NA |  | 07/21/2022 | SSA-5972 | 23.5 | SHDN-19
1795 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | 088TE | Hrs | QTIF-330
1796 | FOT | SCM | 2 | 22 Jul 0115 - 0315 | 6367 | 899980 | P/T SLB SURFACE LINE TO 2,000 PSI PRIOR TESTING HALL VHR PKR. PRESSURE NOT HOLDING. TROUBLESHOOT LEAKAGE SOURCE, OBSERVED SLB CMT UNIT NOT HOLDING PRESSURE. | TF | PUMP |  | 07/22/2022 | 088TE | 2 | QTIF-330
1797 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADC-17 | Hrs | ZULF-1210
1798 | HINW | ARM | 15.5 | 21 Jul 1800 - 0930 | 5490 | 899948 | MANSOORI SLICKLINE 3.5" SHIFTING TOOL STUCK WHILE POH @5490 FT | STUK | SLICK |  | 07/22/2022 | ADC-17 | 4.5 | ZULF-1210
1799 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADC-31 | Hrs | SDGM-1181
1800 | STDP | RIG | 232.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/22/2022 | ADC-31 | 24 | SDGM-1181
1801 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADC-35 | Hrs | MAQL-5
1802 | XTTE | HSL | 2 | 22 Jul 0500 - 0700 | 11700 | 899977 | EXCESS TIME ON HALL S/L TO P/T LUBRICATOR DUE TO MULTIPLE LEAKS IN LUBRICATOR STUFFING BOX. | JF | SLICK |  | 07/22/2022 | ADC-35 | 2 | MAQL-5
1803 | FOT | BAW | 3 | 22 Jul 2230 - 0130 | 3911 | 900021 | OBSERVED FREE POINT INDICATOR TOOL NOT RESPOND OBSERVED LOWER ANCHOR NOT RESPOND | TF | FREE |  | 07/22/2022 | ADC-50 | 3 | SFNY-1176
1804 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADC-50 | Hrs | SFNY-1176
1805 | LCRW | ARM | 79.5 | 19 Jul 1830 - 0500 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/22/2022 | ADC-50 | 21 | SFNY-1176
1806 | FOT | BAW | 3 | 22 Jul 2230 - 0130 | 3911 | 900021 | OBSERVED FREE POINT INDICATOR TOOL NOT RESPOND OBSERVED LOWER ANCHOR NOT RESPOND | TF | FREE |  | 07/22/2022 | ADC-50 | 3 | SFNY-1176
1807 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADC-52 | Hrs | SDGM-1185
1808 | FOT | SPS | 38.75 | 20 Jul 1430 - 0715 | 15043 | 899879 | SPERRY RSS TOOL NOT RESPONDING.LOST SIGNAL. | BHA | RSS |  | 07/22/2022 | ADC-52 | 2.25 | SDGM-1185
1809 | 6844 | 509 | TO | E | 3727 | STDP | CONTD POOH 7" SCRAPER ASSY ON 4" STANDS DP'S FROM 1650 FT TO 509 FT.- CONTINOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 1650 | RIG | 07/22/2022 | ADC-53L | PA | HRDH-530
1810 | 6844 |  | HT | E | 3727 | BHA | CONTD POOH 7" SCRAPPER BHA TO SURFACE AND L/D BIT #9RR.- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 |  | RIG | 07/22/2022 | ADC-53L | PA | HRDH-530
1811 | 6844 | 5856 | TI | E | 3727 | STDP | HPJSM. P/U & M/U 7" CEMENT RETAINER AND RIH ON 4" STANDS OF HWDP'S & DP'S TO 5856 FT.- TRIP SPEED 150 FT/MIN- CONTINUOUSLY PUMPING 87 PCF MUD CAP IN BACK SIDE @ 2 BPM. | 6844 | 0 | RIG | 07/22/2022 | ADC-53L | PA | HRDH-530
1812 | 6844 |  | OTH | E | 3727 | NA | SPACEOUT AND RIG UP SAFETY VALVE & SES. SET 7" CEMENT RETAINER AT 5856 FT AS PER BAKER ENGINEER INSTURCTIONS.- STOP PUMPING AT ANNULUS.- ROTATE 10X TO THE RIGHT AND PULL & PUSH WITH 40 KLBS OVERPULL 3X, CONFIRM RETAINER SET OK. | 6844 |  | BC1 | 07/22/2022 | ADC-53L | PA | HRDH-530
1813 | 6844 |  | CIRC | E | 3727 | MPMP | - FILLED UP ANNULUS WITH 77 PCF WBM UNTIL MUD RETURNS TO SURFACE. - CLOSED RAM AND PRESSURE TESTED ANNULUS TO 500 PSI AS PER BAKER INSTRUCTIONS, OK. BLEED OFF PRESSURE.- STING OUT AND CIRCULATE UNTIL 77 PCF MW IN/OUT.- PRESSURE TESTED RETAINER TO 500 PSI AS PER BAKER INSTRUCTIONS, OK. BLEED OFF PRESSURE. | 6844 |  | RIG | 07/22/2022 | ADC-53L | PA | HRDH-530
1814 | 6844 |  | PTST | E | 3727 | MPMP | RIG UP CEMENTING LINES AND PRESSURE TESTED TO 500 / 3000 PSI FOR 10 MINS EACH TEST, OK. | 6844 |  | RIG | 07/22/2022 | ADC-53L | PA | HRDH-530
1815 | 6844 |  | OTH | E | 3727 | NA | SLB PUMP AND SPOTTED 40 BBLS 87 PCF SLB SPACER ON TOP OF RETAINER. STING IN BACK TO PERFORM INJECTIVITY TEST. | 6844 |  | SCM | 07/22/2022 | ADC-53L | PA | HRDH-530
1816 | 6844 |  | OTH | E | 3727 | NA | PERFORMED INJECTIVITY TEST USING SLB CEMENTING UNIT WITH THE FF PUMP RATES.- 1 BPM - 0 PSI W/ 6 BBLS PUMPED.- 2 BPM - 0 PSI W/ 14 BBLS PUMPED.- 3 BPM - 0 PSI W/ 18 BBLS PUMPED.- 4 BPM - 160 PSI W/ 28 BBLS PUMPED.- 5 BPM - 280 PSI W/ 45 BBLS PUMPED- 6 BPM - 380 PSI W/ 60 BBLS PUMPED- 7 BPM - 540 PSI W/ 90 BBLS PUMPED.- STOPPED PUMPING AND IMMEDIATELY PRESS WENT TO 0 PSI. | 6844 |  | SCM | 07/22/2022 | ADC-53L | PA | HRDH-530
1817 | 6844 | 5856 | CMP | E | 3727 | RETNR | HPJSM. PERFORMED P&A CEMENTING JOB AS FOLLOWS.- CLOSED BOP AND APPLIED 300 PSI AT ANNULUS.- SLB PUMPED 50 BBLS 90 PCF SLB SPACER.- SLB PUMPED 100 BBLS 118 PCF CEMENT SLURRY ON FLY.- SLB PUMPED 20 BBLS 90 PCF SLB SPACER.- SLB PUMPED 12 BBLS 77 PCF WBM.- STOPPED PUMPING AND WELL UNDER VACUUM. | 6844 | 6524 | BCM | 07/22/2022 | ADC-53L | PA | HRDH-530
1818 | 6844 |  | CIRC | E | 3727 | MPMP | BLEED OF PRESS AT ANNULUS AND OPEN BOP. STING OUT AND PICK UP 20 FT ABOVE CEMENT RETAINER. PERFORMED REVERSED CIRCULATION WITH 2X STRING VOLUME. RIG DOWN CEMENT LINES, SES & SAFETY VALVE.- RECOVERED 25 BBLS 114 PCF CEMENT AND 15 BBLS CONTAMINATED SPACER. | 6844 |  | RIG | 07/22/2022 | ADC-53L | PA | HRDH-530
1819 | 6844 | 0 | TO | E | 3727 | STDP | POOH CEMENT RETAINER SETTING TOOL ON 4" STANDS OF DP'S & HWDP'S. L/D SETTING TOOL. | 6844 | 5856 | RIG | 07/22/2022 | ADC-53L | PA | HRDH-530
1820 | 6844 |  | OTH | N |  | BOP | RETREIVE 11" WEAR BUSHING FROM THS. | 6844 |  | RIG | 07/22/2022 | ADC-53L | BOP | HRDH-530
1821 | 6844 |  | OTH | N |  | BOP | P/U & M/U 13-5/8" BOP TEST PLUG ASSY.- FLUSHED BOP STACK, CHOKE MANIFOLD, MGS & FLARE LINES WITH WATER.- FUNCTION TEST BOP STACK. | 6844 |  | RIG | 07/22/2022 | ADC-53L | BOP | HRDH-530
1822 | 6844 |  | BOPT | N |  | BOP | HPJSM, P/T 13-5/8" 5 K CLASS A BOP AS PER ARAMCO STANDARD @ 300 PSI / 2,550 PSI 10 MIN .- TEST# 1: ANNULAR, CHOKE MANIFOLD MASTER VALVE, LOWER K.L MANUAL VALVE., MANUAL IBOP, UPPER K.L HCR. TO 300-3,000 PSI)- TEST# 2: UPR PIPE RAMS, UPPER K.L MANUAL VALVE, EMERGENCY KL MANUAL VALVE #1., CHOKE LINE HCR, IBOP.- TEST# 3: UPR PIPE RAMS, KILL & CHOKE LINE MANUAL VALVE, EMERGENCY KL HCR, UPR IBOP.- UNSCREW DP FROM TEST PLUG- TEST #4: BLIND SHEAR RAMS, KILL LINES & VALVES, CHECK VALVES, CHOKE MANIFOLD VALVES 13,14 & 15. | 6844 |  | RIG | 07/22/2022 | ADC-53L | BOP | HRDH-530
1823 | 6844 |  | OTH | N |  | BOP | L/D TEST PLUG ASSY & P/U 9-5/8" CUP TESTER ASSY.- 2 STD'S 5" HWDP'S + CUP TESTER + 1 STD 4" DP. | 6844 |  | RIG | 07/22/2022 | ADC-53L | BOP | HRDH-530
1824 | 6844 |  | BOPT | N |  | BOP | CONT. P/T 13-5/8'' 5K BOP @ 300 / 2,550 PSI 10 MIN EA.- TEST #5: P/T 4" LOWER PIPE RAMS, SOV 1&2. | 6844 |  | RIG | 07/22/2022 | ADC-53L | BOP | HRDH-530
1825 | 6844 |  | BOPT | N |  | BOP | PERFORMED ACCUMULATOR DRAW DOWN TEST:- INITIAL PRESSURES: ACCUM / MANIFOLD / ANNULAR = 3150/1520 / 1150 PSI.- ISOLATED THE PUMPS.- RECORDED FINAL ACC. PRESSURE:1800 PSI, RECHARGED TO 3,100 PSI IN 01 MIN & 22 SEC. | 6844 |  | RIG | 07/22/2022 | ADC-53L | BOP | HRDH-530
1826 | 6844 |  | OTH | N |  | BOP | POOH & L/D 9-5/8" CUP TESTER ASSY, RACK BACK 2 STD OF 5" HWDP & 1 STD OF 4" DP. | 6844 |  | RIG | 07/22/2022 | ADC-53L | BOP | HRDH-530
1827 | 6844 |  | OTH | N |  | BOP | P/U & INSTALL 11" VG WEAR BUSHING ON THS. | 6844 |  | RIG | 07/22/2022 | ADC-53L | BOP | HRDH-530
1828 | 6844 |  | PJSM | N |  | NA | HPJSM, DISCUSSED WITH CREW ABOUT WHIPSTOCK AND MILL WINDOW OPERATION | 6844 |  | RIG | 07/22/2022 | ADC-53L | DRLG | HRDH-530
1829 | 64.25 | OOS | Category | DOOS ID | PLUG | Out of Scope Summary | P&A FOR SIDE TRACKING | 15 | 3727 | 19 Jul 0345 | 07/22/2022 | ADC-53L | Type | HRDH-530
1830
1831
1832 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADC-56L | Hrs | UTMN-3069
1833 | FOT | RIG | 10 | 22 Jul 1900 - 0500 | 6516 | 900055 | OBSERVED MUD LEAK ON TDS. R/B ONE STD, EVALUATED THE LEAK, SUSPECTED THE LEAK ON TDS UPPER STEM LINER THAT CONNECTED BETWEEN THE SPIPE AND WASH PIPE | RR | TDS |  | 07/22/2022 | ADC-56L | 10 | UTMN-3069
1834 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADES-144 | Hrs | UTMN-3152
1835 | FOT | SPS | 13 | 22 Jul 0930 - 0230 | 13626 | 900053 | LOST RSS SIGNAL, TROUBLE SHOOT WITHOUT SUCESS. | BHA | RSS |  | 07/22/2022 | ADES-144 | 13 | UTMN-3152
1836 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADM-510 | Hrs | ABSF-231
1837 | AINC | SDM | 4 | 21 Jul 0230 - 0700 | 8176 | 899949 | OBSERVE DIFFICULTIES TO STEER UP SLB RSS TO CATCH THE DIRECTION PLAN. | LROP | BHA |  | 07/22/2022 | ADM-510 | 2 | ABSF-231
1838 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ADM-511 | Hrs | MRJN-799
1839 | CWEL | ARM | 149.75 | 16 Jul 0600 - 0500 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/22/2022 | ADM-511 | 24 | MRJN-799
1840 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ARO-3002 | Hrs | MRJN-812
1841 | FOT | HML | 7.25 | 22 Jul 1900 - 0215 | 7949 | 900018 | DID NOT RECOVER THE WHIPSTOCK, UNABLE TO WASH OVER | TF | WPSTK |  | 07/22/2022 | ARO-3002 | 7.25 | MRJN-812
1842 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ARO-4001 | Hrs | MRJN-532
1843 | IBHA | BHI | .5 | 22 Jul 0300 - 0330 | 7036 | 899982 | HAD CABLE CONNECTION ISSUE WHILE DOWNLOAD DATA, UNABLE TO DOWNLOAD THE WHOLE DATA, DECISION MADE TO L/D BHI BHA AND COMPLETE DOWNLOAD THE DATA. | BHA | MWD |  | 07/22/2022 | ARO-4001 | .5 | MRJN-532
1844 | FOT | WI3 | 41.25 | 19 Jul 1700 - 2200 | 13101 | 899947 | WEATHERFORD UNABLE TO INITIATE SIDETRACK DUE TO SETTING WIS WHIPSTOCK. | TF | WPSTK |  | 07/22/2022 | DPS-5 | 7.5 | HRDH-2319
1845 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | DPS-5 | Hrs | HRDH-2319
1846 | HERR | WDS | 41 | 19 Jul 0500 - 0500 | 13101 | 899943 | WEATHERFORD UNABLE TO INITIATE SIDETRACK. | DD | MMOT |  | 07/22/2022 | DPS-5 | 7.5 | HRDH-2319
1847 | FOT | WI3 | 41.25 | 19 Jul 1700 - 2200 | 13101 | 899947 | WEATHERFORD UNABLE TO INITIATE SIDETRACK DUE TO SETTING WIS WHIPSTOCK. | TF | WPSTK |  | 07/22/2022 | DPS-5 | 7.5 | HRDH-2319
1848 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | DQ-49L | Hrs | HRDH-575
1849 | CFFM | TK2 | 3 | 22 Jul 1000 - 1300 | 555 | 900035 | LOST RETURNS ON CELLAR SUDDENLY WHILE POH W/ 28" DRILLING BHA. VISIBLE LEVEL DISAPPERARED. KEEP FILLING HOLE. CALCULATED LOSSES @ 120 BPH. | LCIR | LCM |  | 07/22/2022 | DQ-49L | 3 | HRDH-575
1850 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | DQ-57L | Hrs | KHRS-399
1851 | FOT | SBA | 48 | 21 Jul 0500 - 0500 | 4443 | 899950 | PRAXIS ESP ISOPAX PACKER 9 5/8 FAIL TO SET . | TF | PKR |  | 07/22/2022 | DQ-57L | 24 | KHRS-399
1852 | XTRI | RIG | 1.5 | 22 Jul 0930 - 1100 | 0 | 900034 | EXCESSIVE TIME CHANGING OUT TEST ASSEMBLIES. | JF | NA |  | 07/22/2022 | ED-85A | 1.5 | ZULF-2063
1853 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ED-85A | Hrs | ZULF-2063
1854 | FOT | RIG | 7.75 | 22 Jul 2115 - 0500 | 11328 | 900020 | 9-5/8" CSG RAMS NOT HOLDING PRESSURE. | BOP | RAMS |  | 07/22/2022 | ED-85A | 7.75 | ZULF-2063
1855 | XTRI | RIG | 1.5 | 22 Jul 0930 - 1100 | 0 | 900034 | EXCESSIVE TIME CHANGING OUT TEST ASSEMBLIES. | JF | NA |  | 07/22/2022 | ED-85A | 1.5 | ZULF-2063
1856 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | ENSCO-54 | Hrs | ABSF-17
1857 | STCT | ARM | 354 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/22/2022 | ENSCO-54 | 24 | ABSF-17
1858 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | HI-4 | Hrs | BRRI-1000
1859 | CFFM | ARM | 49.5 | 20 Jul 0330 - 0500 | 189 | 899975 | HAD COMPLETE LOSSES AT 189' (13' ABOVE CONDUCTOR SHOE) | LCIR | SQZ |  | 07/22/2022 | HI-4 | 24 | BRRI-1000
1860 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | JACK-203 | Hrs | HZEM-849
1861 | LCRW | ARM | 301.5 | 10 Jul 1530 - 0500 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/22/2022 | JACK-203 | 24 | HZEM-849
1862 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | MP-1 | Hrs | MRJN-78
1863 | FOT | BCR | .5 | 22 Jul 1145 - 1215 | 1403 | 900033 | OBSERVED BAKER DIESEL POWER UNIT MALFUNCTIONED. RU ELECTRICAL POWER PACK. | TF | CTRQ |  | 07/22/2022 | MP-1 | .5 | MRJN-78
1864 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | NBR-16S | Hrs | HMYM-433102
1865 | FOT | RIG | 6 | 22 Jul 1845 - 0045 | 6585 | 900062 | RIG MANAGER'S BOP REMOTE CONTROL PANEL NOT WORKING | RR | RWCS |  | 07/22/2022 | NBR-16S | 6 | HMYM-433102
1866 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | NBR-783S | Hrs | NJYN-93
1867 | FOT | RIG | 4.5 | 22 Jul 0500 - 0930 | 6200 | 899976 | DRUM CLUTCH NOT DIS-ENGAUGING | RR | DWKS |  | 07/22/2022 | NBR-783S | 4.5 | NJYN-93
1868 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | RM-74A | Hrs | HSBH-68
1869 | FOT | RIG | 7.75 | 22 Jul 1715 - 0100 | 3121 | 900057 | TROUBLESHOOT AND REPAIR MALFUNCTION ON DRAWWORKS JOHNSTON BRAKE | RR | DWKS |  | 07/22/2022 | RM-74A | 7.75 | HSBH-68
1870 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SCTD-1 | Hrs | SDGM-1034
1871 | ETRQ | RIG | 18 | 22 Jul 1100 - 0500 | 12953 | 900015 | DOWN HOLE TOOLS FAILURE. | BHA | BHA |  | 07/22/2022 | SCTD-1 | 18 | SDGM-1034
1872 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SCTD-2 | Hrs | HRDH-2148
1873 | GRF | RIG | 157.5 | 16 Jul 0630 - 2000 | 12250 | 899733 | LEAK IN THE COIL REEL MANIFOLD; BOTH SHAFTS CRACKED AND WORN DOWN. | UPRA | CSYS |  | 07/22/2022 | SCTD-2 | 15 | HRDH-2148
1874 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SINO-10 | Hrs | JLDI-38
1875 | FOT | SWL | 13.75 | 21 Jul 2330 - 1315 | 11030 | 900017 | POOR QUALITY OF LOGS DURING CMR RUN | TF | WLT |  | 07/22/2022 | SINO-10 | 8.25 | JLDI-38
1876 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SINO-25 | Hrs | MNIF-383
1877 | DSFT | BC | 85.5 | 19 Jul 1530 - 0500 | 7064 | 899913 | AS PER BAKER COMPLETION INSTRUCTIONS SET 9-5/8" ELECPACK ESP PACKER @ 6850' ATTEMPTED TO PRESSSURE TEST TCA TO 1000 PSI F/ 20 MINS ( PT FAILED ) . REPEATED TCA PT SEVERAL TIMES; TCA PRESSURE TEST FAILED. | JF | PKR |  | 07/22/2022 | SINO-25 | 24 | MNIF-383
1878 | 7408 |  | OTH | E | 3747 | NA | (OOS) CONT. RIH RUN #02, W/ GR-CCL-GUN #1 ASSY. T/ 6900',- CORRELATE DEPTH FOR GUNS RUN #2, CONFIRMED PERFORATION DEPTHS W/ ARAMCO WOE, FIRED GUN AND PERFORATED INTERVALS FROM 6885'-6900' (15') ARBD- POOH W/ GR-CCL-2-7/8" GUN TO SURFACE.- CONFIRMED GUNS 100% FIRED.- FLOW CHECK. WELL STATIC. | 7408 |  | HWP | 07/22/2022 | SINO-42L | LOG | HWYH-353
1879 | 7408 |  | OTH | E | 3747 | NA | OOS ) R/D HES WL PERFORATION TOOLS AND EQUIPMENT. | 7408 |  | HWP | 07/22/2022 | SINO-42L | LOG | HWYH-353
1880 | 7408 |  | ND | E | 3747 | SNIP | (OOS) R/D 9 5/8" SHOOTING NIPPLE & RU BELL NIPPLE. | 7408 |  | HWP | 07/22/2022 | SINO-42L | LOG | HWYH-353
1881 | 7408 | 2164 | LDP | N | 3846 | STRG | (OOS). M/U & RIH 3 7/8" CLEAN OUT ASSEMBLY TO 2,164 FT MEANWHILE P/U 2-3/8" D/P'S.- TOTAL 70 JTS OF 2 3/8 DP.- FILL UP & BREAK CIRC EVERY 20 JTS. | 7408 | 0 | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1882 | 7408 |  | HT | N | 3846 | PEL | (OOS). R/D 2 3/8'' DP HANDLING EQUIPMENT. & R/U 4'' HANDLING EQUIPMENT. | 7408 |  | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1883 | 7408 |  | HT | N | 3846 | BHA | (OOS). M/U JAR STAND, 2 STANDS HWDP'S. | 7408 |  | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1884 | 7408 | 7000 | TI | N | 3846 | STDP | (OOS). CONTINUE RIH WITH 3 7/8'' CLEAN OUT ASSY ON 4'' DP TO 7,000 FT- FILLED UP & BREAK CIRC EVERY 15 STDS .- CONTROL SPEED INSIDE 4.5'' LNR. | 7408 | 2164 | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1885 | 7408 |  | CIRC | N | 3846 | MPMP | (OOS). SWEEP HOLE & CHC, SPOT 15 BBL N-FLOW. | 7408 |  | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1886 | 7408 | 4935 | LDP | N |  | STRG | POH WITH CLEAN OUT ASSY FROM 7,000 FT TO 4,935 FT. WHILE L/D 4" DP. | 7408 | 7000 | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1887 | 7408 |  | CIRC | N | 3846 | MPMP | (OOS). CIRC. BTM-UP BELOW 4 1/2" LINER. | 7408 |  | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1888 | 7408 | 2164 | LDP | N |  | STRG | POH WITH 3 7/8" C/O ASSY FROM 4,910 FT TO 2,164 FT WHILE L/D 4" DP. | 7408 | 4935 | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1889 | 7408 |  | HT | N | 3846 | PEL | (OOS). R/D 4'' DP HANDLLNG TOOLS & R/U 2 3/8'' HANDLING TOOLS. | 7408 |  | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1890 | 7408 | 0 | LDP | N | 3846 | STRG | (OOS). POH WITH 3 7/8" C/O ASSY MEANWHILE L/D 2-3/8'' D/P FROM 2,164 FT TO SURFACE. L/D BIT & FLOAT SUB. | 7408 | 2164 | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1891 | 7408 |  | CIRC | N |  | MPMP | M/U JETTING TOOL, JET BOPE & WELL HEAD W/74 PCF BRINE. | 7408 |  | RIG | 07/22/2022 | SINO-42L | CT | HWYH-353
1892 | 11.5 | OOS | PERF | 3747 | WCLN | PERFORATE 4.5" LINER. | ADDITIONAL CLEAN OUT TO SPOT N-FLOW. | 11.5 | 3846 | 22 Jul 0030 | 07/22/2022 | SINO-42L | OOS | HWYH-353
1893
1894
1895
1896 | 7206 | 6780 | LOG | E | 3665 | WLT | RECORD NMR LOG RUN# 1 (MREX)..........(OOS)- RECORDED UP MAIN PASS LOG F/ 7,193' T/ 6,780'.- RECORDED REPEAT PASS LOG F/ 7,193' T/ 6,780'.- MONITOR WELL ON TRIP TANK - STATIC LOSSES 3.5 BPH. | 7206 | 7200 | BAW | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1897 | 7206 | 6514 | ST | E | 3665 | STDP | POOH W/ BKR LOGGING RUN#1 TO SES DEPTH AT 6514'...........(OOS) | 7206 | 6855 | RIG | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1898 | 7206 |  | OTH | E |  | NA | UNLATCH & POOH CABLE TO SURFACE. L/D CABLE, SHEAVES AND SES. | 7206 |  | BAW | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1899 | 7206 | 7170 | ST | E | 3665 | STDP | RIH STRING INTO OPEN HOLE TO 7170'...........(OOS)- HOLE IN GOOD CONDITION.- STATIC LOSSES - 3.5 BPH. | 7206 | 6514 | RIG | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1900 | 7206 |  | CIRC | E | 3665 | MPMP | CIRCULATE AND CONDITON MUD PRIOR POH LOGGING TOOLS W/ 6 BPM & 250 PSI...........(OOS)- DYNAMIC LOSSES 10 BPH. | 7206 |  | RIG | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1901 | 7206 |  | WCNT | E | 3665 | NA | FLOW CHECK - STATIC LOSSES 3.5 BPH...........(OOS) | 7206 |  | RIG | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1902 | 7206 | 157 | ST | E |  | STDP | POOH BKR LOGGING RUN#1 W/ TRIPLE-COMBO/NMR ON 4"/5" DP STD'S F/7170' TO TOP OF BHA AT 157'.- FLOW CHECK AT TOP OF BHA - 3.5 BPH STATIC LOSSES. | 7206 | 7170 | RIG | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1903 | 7206 |  | OTH | E |  | NA | HPJSM. L/D BKR LOGGING TOOLS RUN#1. | 7206 |  | BAW | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1904 | 7206 |  | OTH | E | 3665 | NA | M/U BKR W/L LOGGING TOOLS RUN #2 W/ RESISTIVITY IMAGE TOOL [STAR/GR]..........(OOS)- TOOL LENGTH: 75.69', MAX OD: 5.25".- FUNCTION TESTED & PERFORM TOOL CALIBRATION AT SURFACE.- MONITOR THE WELL THROUGH TRIP TANK, STATIC LOSSES 3.5 BPH. | 7206 |  | BAW | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1905 | 7206 | 2971 | ST | E | 3665 | STDP | RIH BKR W/L LOGGING TOOLS RUN #2 RESISTIVITY IMAGE TOOL [STAR/GR] ON DRIFTED 4"/5" DP TO 2971' AT CONTROLLED SPEED.............(OOS)- SLOW DOWN AND PASSED 7" TOL AT 2214'.- FILL UP STRING EVERY 10 STD'S.- MONITOR WELL ON TRIP TANK - STATIC LOSSES 3.5 BPH. | 7206 | 75 | RIG | 07/22/2022 | SINO-43L | LOG | UTMN-4068
1906 | 54.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" & 6-1/8" SECTION WIRELINE LOGGING. | 16.5 | 3665 | 15 Jul 0045 | 07/22/2022 | SINO-43L | Type | UTMN-4068
1907
1908
1909 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SINO-47 | Hrs | HRDH-1351
1910 | FOT | HCA | 12.25 | 22 Jul 1645 - 0500 | 14467 | 900054 | CEMENT DART RELEASED ACCIDENTLY FROM A FAILED CEMENT HEAD & NOT ABLE TO CIRCULATE. | TF | ACCSS |  | 07/22/2022 | SINO-47 | 12.25 | HRDH-1351
1911 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SINO-5L | Hrs | UTMN-1029
1912 | FOT | SPS | 51.5 | 20 Jul 0130 - 0500 | 8989 | 899942 | UNABLE TO BUILD INCLINITION AS PER GOC REQUEST. | BHA | RSS |  | 07/22/2022 | SINO-5L | 24 | UTMN-1029
1913 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SND-2007 | Hrs | AWTD-104001
1914 | FPMP | RIG | 4.5 | 22 Jul 0030 - 0500 | 14713 | 900056 | HAD PRESSURE DROP DUE TO WASH OUT ON MODULES ON RIG PUMP #2, #3 | RR | MPMP |  | 07/22/2022 | SND-2007 | 4.5 | AWTD-104001
1915 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SND-2008 | Hrs | HRDH-1812
1916 | PCPF | ARM | 67.5 | 20 Jul 0930 - 0500 | 12992 | 899932 | UNABLE TO SIDETRACK FROM WFD WHIPSTOCK DUE TO SUSPECTED POOR CEMENT BEHIND THE CASING | TH | NA |  | 07/22/2022 | SND-2008 | 24 | HRDH-1812
1917 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SND-3002 | Hrs | DMMM-601
1918 | FOT | WWL | 49.25 | 19 Jul 2000 - 0500 | 17144 | 899854 | WFD COMPACT SHUTTLE LOGGING TOOL LOST IN HOLE. | TF | WLT |  | 07/22/2022 | SND-3002 | 24 | DMMM-601
1919 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SND-3003 | Hrs | HRDH-1816
1920 | FOT | SPS | 20.75 | 21 Jul 2100 - 1815 | 11395 | 899890 | SPS I-CRUSIE RSS TURBINE FAILURE. | BHA | RSS |  | 07/22/2022 | SND-3003 | 12.75 | HRDH-1816
1921 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SP-103 | Hrs | KRSN-72
1922 | FOT | BHI | 4 | 22 Jul 0500 - 0900 | 12413 | 900052 | WHILE DRILLING AT 12413, OBSERVED LOST SIGNAL BETWEEN MWD AND RSS. BHI MWD TROUBLE SHOOTING WITH NO SUCCESS MEANWHILE | BHA | RSS |  | 07/22/2022 | SP-103 | 4 | KRSN-72
1923 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SP-167 | Hrs | HRDH-218
1924 | XTTE | SDM | 7.5 | 22 Jul 2130 - 0500 | 5464 | 899981 | OBSERVE PRESSURE FLUCTUATION AND MWD SIGNAL LOSS. TOOL FAILED | TF | MWD |  | 07/22/2022 | SP-167 | 7.5 | HRDH-218
1925 | FPMP | RIG | .5 | 22 Jul 0130 - 0200 | 14571 | 900060 | PUMP FAILURE | RR | MPMP |  | 07/22/2022 | SP-259 | .5 | THRY-371612
1926 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SP-259 | Hrs | THRY-371612
1927 | FPMP | RIG | .5 | 22 Jul 0030 - 0100 | 14530 | 900059 | PUMP FAILURE. | RR | MPMP |  | 07/22/2022 | SP-259 | .5 | THRY-371612
1928 | FPMP | RIG | .5 | 22 Jul 0130 - 0200 | 14571 | 900060 | PUMP FAILURE | RR | MPMP |  | 07/22/2022 | SP-259 | .5 | THRY-371612
1929 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SP-58 | Hrs | HRDH-795
1930 | FOT | SPS | 29.5 | 21 Jul 2330 - 0500 | 14282 | 899974 | LOST COMMNICATION WITH MWD, MWD PULSER FAILED | BHA | MWD |  | 07/22/2022 | SP-58 | 24 | HRDH-795
1931 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SSA-101 | Hrs | QTIF-785
1932 | FOT | WWD | 53.5 | 20 Jul 1100 - 1700 | 18419 | 899877 | WFD 7" WHIP STOCK ANCHOR SLIPS NOT ENGAGE / SET. TRY SEVERAL ATTEMPTS BUT WHIP STOCK FAIL TO SET. | TF | WPSTK |  | 07/22/2022 | SSA-101 | 12 | QTIF-785
1933 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SSA-5868 | Hrs | HRDH-2413
1934 | FOT | BHI | 18.5 | 21 Jul 1930 - 1400 | 11770 | 899888 | WHILE DRLG 5-7/8" HOLE, MWD PULSER FAILED. TROUBLESHOOTING TRIALS: > CHANGED ACTIVE PUMP > CHANGED GPM > PUMPED TANDEM PILL LOW VIS/HIGH VIS ,NO TOOL RESPONSE. | BHA | MWD |  | 07/22/2022 | SSA-5868 | 9 | HRDH-2413
1935 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/22/2022 | SSA-5972 | Hrs | SHDN-19
1936 | UVLC | ARM | 86 | 19 Jul 1245 - 0500 | 7017 | 899855 | ENCOUNTERED COMPLETE LOSS CIRCULATION WHILE DRILLING 12" HOLE SECTION | LCIR | NA |  | 07/22/2022 | SSA-5972 | 23.5 | SHDN-19
1937 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ADC-31 | Hrs | SDGM-1181
1938 | STDP | RIG | 255.25 | 12 Jul 1930 - 0400 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/23/2022 | ADC-31 | 23 | SDGM-1181
1939 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ADC-50 | Hrs | SFNY-1176
1940 | LCRW | ARM | 98.75 | 19 Jul 1830 - 0345 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/23/2022 | ADC-50 | 22.75 | SFNY-1176
1941 | 6844 |  | HT | N |  | BHA | P/U & M/U 7" WIS WSTK & MILLING ASSY. W/3 EA X 7" MAGNETS AS PER WIS ENGINEER INSTRUCTION.- DRIFT ALL X-OVERS & SUB ABOVE UBHO WITH 2".- DRIFT C/O TOOLS WITH 2". | 6844 |  | RIG | 07/23/2022 | ADC-53L | TINL | HRDH-530
1942 | 6844 | 5355 | TI | N |  | STDP | RIH W/ 7" WIS WSTK & MILLING ASSY AND 7" MAGNET TOAT CONTROL SPEED TO WSTK SITTING DEPTH @ 5,355'.- RIH WITH CONTROLLED SPEED: 3 MIN/STD.- P/U 21 JTS X 4" HWDP WHILE RIH.- DRIFT STRING WITH 2.4" WHILE RIH. | 6844 | 212 | TK3 | 07/23/2022 | ADC-53L | TINL | HRDH-530
1943 | 6844 |  | OTH | N | 3826 | NA | R/U GYRO SHEAVES & UNIT. RIH WITH GYRO SINGLE SHOT TO 5,274 UBHO SUB DEPTH. | 6844 |  | GCD | 07/23/2022 | ADC-53L | TINL | HRDH-530
1944 | 6844 |  | SURV | N | 3826 | SS | ORIENT 7" WSTK TO 37 DEG, TAKE 1ST READING, REPEAT 03 TIME TO CONFIRM TOOL FACE REPEATABILITY, SLACK THE CABLE AND WORK THE PIPE ON ELEVATOR UP AND DOWN TO CONFIRM FREE TORQUE, ORIENTATED THE WHIPSTOCK, RE-SEATED THREE MORE TIMES THE GYRO TOOL TO CONFIRM TOOL FACE ORIENTATION (L 0-1 TOOL FACE AT 37 DEG AZM). | 6844 |  | GCD | 07/23/2022 | ADC-53L | TINL | HRDH-530
1945 | 6844 |  | OTH | N | 3826 | NA | POOH WITH GYRO TOOL TO SURFACE. R/D GYRO TOOL & SHEAVES AND SURFACE EQUIPMENT. | 6844 |  | GCD | 07/23/2022 | ADC-53L | TINL | HRDH-530
1946 | 6844 | 5335 | SET | N |  | WPSTK | SET 7" WIS WSTK AT 5,335' (BTM OF WSTK) & CONFIRM SETTING BY SOW & PUW 15 KLBS & SHEAR MILL WITH 30 K.LBS, SOW, BREAK THE HOSE W/ 05 K.LBS O/P.- P/U 10 FT, CHECK STRING FREE.- TOP OF WINDOW (TOW) @ 5,315 FT.- BTM OF WINDOW (BOW) @ 5,325 FT.- BTM OF W.S @ 5,334.5 FT. | 6844 | 5335 | WI3 | 07/23/2022 | ADC-53L | TINL | HRDH-530
1947 | 6844 |  | CIRC | N |  | MPMP | DISPLACE HOLE TO 79 PCF LSND MUD. | 6844 |  | RIG | 07/23/2022 | ADC-53L | TINL | HRDH-530
1948 | 6844 | 5325 | MILL | N |  | MILL | MILLED L 0-1 WINDOW W/ 79 PCF LSND MUD FROM 5,315' TO 5,325'** PUMP 15 BBLS HI-VIS PILL EVERY 1 FT. MILLED.** MILLING PARAMETERS: 5,325' - BOTTOM WHIPSTOCK: 5,335' | 6844 | 5315 | WI1 | 07/23/2022 | ADC-53L | TINL | HRDH-530
1949 | 5324 |  | TINL | S |  | NA | TIE IN NEW LATERIAL L 0-1 | 5324 |  | RIG | 07/23/2022 | ADC-53L | OT | HRDH-530
1950 | 5335 |  | D | N |  | TDS | DRILLED 11' NEW FORMATION RAT-HOLE FROM 5,325' TO 5,335'.- FR: 260 GPM; SPP: 1,400 PSI.- WOB: 5-10 KLB; RPM: 70 ; TQ: 4-7 KFT-LB. | 5324 |  | RIG | 07/23/2022 | ADC-53L | DRLG | HRDH-530
1951 | 5335 |  | CIRC | N |  | MPMP | DRESSED MILLED WINDOW BY REAM WINDOW SEVERAL TIMES & PASS THROUGH WITH/WITHOUT ROTATION & CIRCULATION. | 5335 |  | RIG | 07/23/2022 | ADC-53L | DRLG | HRDH-530
1952 | 5335 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH 2 X 25 BBLS HIS-VIS PILLS. CIRCULATE HOLE CLEAN.-FR:300 GPM, P.P:1,350 PSI | 5335 |  | RIG | 07/23/2022 | ADC-53L | DRLG | HRDH-530
1953 | 5335 |  | OTH | N |  | NA | FLOW CHECK WELL STATICK. | 5335 |  | RIG | 07/23/2022 | ADC-53L | DRLG | HRDH-530
1954 | 5335 | 3100 | TO | N |  | STDP | POOH W/ 6-1/8" MILLING ASSY F/ 5,335 FT TO 3,100 FT- MONITORED WELL AT TRIP TANK. | 5335 | 5335 | RIG | 07/23/2022 | ADC-53L | DRLG | HRDH-530
1955 | 2.75 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | R/U GYRO SHEAVES & UNIT. RIH WITH GYRO SINGLE SHOT, ORIENT 7 " WSTKS TO 37 DEG AZM, POOH WITH GYRO TOOL TO SURFACE. R/D GYRO ALL | 2.75 | 3826 | 23 Jul 1530 | 07/23/2022 | ADC-53L | Type | HRDH-530
1956
1957
1958 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ADC-56L | Hrs | UTMN-3069
1959 | FOT | RIG | 21.5 | 22 Jul 1900 - 1630 | 6516 | 900055 | OBSERVED MUD LEAK ON TDS. R/B ONE STD, EVALUATED THE LEAK, SUSPECTED THE LEAK ON TDS UPPER STEM LINER THAT CONNECTED BETWEEN THE SPIPE AND WASH PIPE | RR | TDS |  | 07/23/2022 | ADC-56L | 11.5 | UTMN-3069
1960 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ADES-144 | Hrs | UTMN-3152
1961 | FOT | SPS | 30.5 | 22 Jul 0930 - 0500 | 13626 | 900053 | LOST RSS SIGNAL, TROUBLE SHOOT WITHOUT SUCESS. | BHA | RSS |  | 07/23/2022 | ADES-144 | 17.5 | UTMN-3152
1962 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ADM-510 | Hrs | ABSF-231
1963 | AINC | SDM | 16.5 | 23 Jul 1230 - 0500 | 8570 | 900065 | INCLINATION INCREASED RAPIDLY FROM 84 DEGREES TO 90. 7 DEGREES. OBSERVED DIFFICULTIES TO DROP INCLINATION | LROP | BHA |  | 07/23/2022 | ADM-510 | 16.5 | ABSF-231
1964 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ADM-511 | Hrs | MRJN-799
1965 | CWEL | ARM | 173.75 | 16 Jul 0600 - 0500 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/23/2022 | ADM-511 | 24 | MRJN-799
1966 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | AOD-1 | Hrs | ZULF-694
1967 | FOT | RIG | 1 | 23 Jul 0400 - 0500 | 6094 | 899984 | EXCESS OF TIME TO LAY DOWN 5-1/2" DP SINGLES | RR | SLIPS |  | 07/23/2022 | AOD-1 | 1 | ZULF-694
1968 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ARO-3002 | Hrs | MRJN-812
1969 | FOT | HML | 28.25 | 22 Jul 1900 - 0315 | 7949 | 900018 | HALL MLT UNABLE TO RECOVER THE WHIPSTOCK, UNABLE TO WASH OVER | TF | WPSTK |  | 07/23/2022 | ARO-3002 | 21.25 | MRJN-812
1970 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | BB-84A | Hrs | MRJN-587
1971 | FOT | RIG | 1 | 23 Jul 0900 - 1000 | 10003 | 900064 | PREVENTIVE MAINTENANCE - REPLACE 2 X HCR HYDRAULIC LINES | RR | RWCS |  | 07/23/2022 | BB-84A | 1 | MRJN-587
1972 | FOT | WI3 | 52.75 | 19 Jul 1700 - 1700 | 13000 | 899947 | WEATHERFORD UNABLE TO INITIATE SIDETRACK DUE TO SETTING WIS WHIPSTOCK. | TF | WPSTK |  | 07/23/2022 | DPS-5 | 11.5 | HRDH-2319
1973 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | DPS-5 | Hrs | HRDH-2319
1974 | HERR | WDS | 53 | 19 Jul 0500 - 0500 | 13000 | 899943 | WEATHERFORD UNABLE TO INITIATE SIDETRACK. | DD | MMOT |  | 07/23/2022 | DPS-5 | 12 | HRDH-2319
1975 | FOT | WI3 | 52.75 | 19 Jul 1700 - 1700 | 13000 | 899947 | WEATHERFORD UNABLE TO INITIATE SIDETRACK DUE TO SETTING WIS WHIPSTOCK. | TF | WPSTK |  | 07/23/2022 | DPS-5 | 11.5 | HRDH-2319
1976 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | DQ-57L | Hrs | KHRS-399
1977 | FOT | SBA | 72 | 21 Jul 0500 - 0500 | 4443 | 899950 | PRAXIS ESP ISOPAX PACKER 9 5/8 FAIL TO SET . | TF | PKR |  | 07/23/2022 | DQ-57L | 24 | KHRS-399
1978 | FOT | RIG | 1 | 23 Jul 1015 - 1115 | 0 | 900037 | RIG FLOOR LOST RIG AIR AND UNABLE TO MOVE TDS DUE TO RIG AIR COMPRESSOR COUPLING FAILED | RR | PSYS |  | 07/23/2022 | ED-85A | 1 | ZULF-2063
1979 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ED-85A | Hrs | ZULF-2063
1980 | FOT | RIG | 13 | 22 Jul 2115 - 1015 | 11328 | 900020 | 9-5/8" CSG RAMS NOT HOLDING PRESSURE. | BOP | RAMS |  | 07/23/2022 | ED-85A | 5.25 | ZULF-2063
1981 | FOT | RIG | 1 | 23 Jul 1015 - 1115 | 0 | 900037 | RIG FLOOR LOST RIG AIR AND UNABLE TO MOVE TDS DUE TO RIG AIR COMPRESSOR COUPLING FAILED | RR | PSYS |  | 07/23/2022 | ED-85A | 1 | ZULF-2063
1982 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | ENSCO-54 | Hrs | ABSF-17
1983 | STCT | ARM | 378 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/23/2022 | ENSCO-54 | 24 | ABSF-17
1984 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | EXL-IA | Hrs | SFNY-1790
1985 | LHFL | RIG | 3 | 23 Jul 1215 - 1515 | 1470 | 900022 | FUNCTION TEST & PRESSURE TEST DIVERTER SYSTEM TO 500 PSI. * OBSERVED ACCUMULATOR PRESSURE LEAKING OFF SLOWLY. * OBSERVED LEAKING HOSE ON DIVERTER. * OBSERVED OVER BOARD LINE FLANGE WAS LEAKING AND NOT HOLDING PRESSURE. | BOP | RWCS |  | 07/23/2022 | EXL-IA | 3 | SFNY-1790
1986 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | HI-4 | Hrs | BRRI-1000
1987 | CFFM | ARM | 69.75 | 20 Jul 0330 - 0500 | 189 | 899975 | HAD COMPLETE LOSSES AT 189' (13' ABOVE CONDUCTOR SHOE) | LCIR | SQZ |  | 07/23/2022 | HI-4 | 20.25 | BRRI-1000
1988 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | JACK-203 | Hrs | HZEM-849
1989 | LCRW | ARM | 305.5 | 10 Jul 1530 - 0900 | 626 | 899533 | STRING GOT STUCK WHILE POOH. | STUK | STRG |  | 07/23/2022 | JACK-203 | 4 | HZEM-849
1990 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | NBR-575S | Hrs | HRDH-2217
1991 | HERR | GOC | 8.75 | 23 Jul 1745 - 0230 | 1823 | 900042 | MAKING UP JOINT #75 ALGHAITH JAM UNIT MALFUNCTIONED WHICH LEAD THE CASING RUNNING CREW TO MAKE UP THE JOINT TWICE TO GET A READING. | TF | TTRQ |  | 07/23/2022 | NBR-575S | 8.75 | HRDH-2217
1992 | FPMP | RIG | .75 | 23 Jul 0745 - 0830 | 10065 | 900066 | STOPPED MILLING DECREASE IN SPP DUE TO LEAK ON MUD PUMP 2 LINER GASKET STOPPED PUMPS ISOLATED MUD PUMP 2 AND CONTINUED TO CIRCULATE WITH MUD PUMP 1 WHILST REPAIRING MUD PUMP 2 | RR | MPMP |  | 07/23/2022 | PA-861S | .75 | HRDH-1973
1993 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | PA-861S | Hrs | HRDH-1973
1994 | FPMP | RIG | 1.25 | 23 Jul 0930 - 1045 | 10067 | 900040 | STOP MILLING DUE TO DECREASE IN SPP DUE TO LEAK ON MUD PUMP 1 PISTON. ISOLATE MUD PUMP 1 AND PERFORM REPAIR WHILST CIRCULATING WITH MUD PUMP 2 | RR | MPMP |  | 07/23/2022 | PA-861S | 1.25 | HRDH-1973
1995 | FPMP | RIG | .75 | 23 Jul 0745 - 0830 | 10065 | 900066 | STOPPED MILLING DECREASE IN SPP DUE TO LEAK ON MUD PUMP 2 LINER GASKET STOPPED PUMPS ISOLATED MUD PUMP 2 AND CONTINUED TO CIRCULATE WITH MUD PUMP 1 WHILST REPAIRING MUD PUMP 2 | RR | MPMP |  | 07/23/2022 | PA-861S | .75 | HRDH-1973
1996 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | PN-9 | Hrs | MRJN-673
1997 | CFST | HCM | 6 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/23/2022 | PN-9 | 6 | MRJN-673
1998 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SCTD-1 | Hrs | SDGM-1034
1999 | ETRQ | RIG | 28 | 22 Jul 1100 - 1500 | 12953 | 900015 | DOWN HOLE TOOLS FAILURE. POH TO SURFACE & FOUND FLOAT VALVE STUCK IN OPEN POSITION AND WHITESH DEBRIS INSIDE BHA. | BHA | BHA |  | 07/23/2022 | SCTD-1 | 10 | SDGM-1034
2000 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SCTD-2 | Hrs | HRDH-2148
2001 | FOT | RIG | 15.5 | 15 Jul 2000 - 1530 | 12250 | 899978 | LOST COMMUNICATION WITH DOWNHOLE TOOLS. TROUBLESHOOT WITHOUT SUCCESS. | RR | CSYS |  | 07/23/2022 | SCTD-2 | 5 | HRDH-2148
2002 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SINO-25 | Hrs | MNIF-383
2003 | DSFT | BC | 107 | 19 Jul 1530 - 0230 | 7064 | 899913 | AS PER BAKER COMPLETION INSTRUCTIONS SET 9-5/8" ELECPACK ESP PACKER @ 6850' ATTEMPTED TO PRESSSURE TEST TCA TO 1000 PSI F/ 20 MINS ( PT FAILED ) . REPEATED TCA PT SEVERAL TIMES; TCA PRESSURE TEST FAILED. | JF | PKR |  | 07/23/2022 | SINO-25 | 21.5 | MNIF-383
2004 | 7206 | 6525 | ST | E | 3665 | STDP | CONT. RIH BKR W/L LOGGING TOOLS RUN #2 RESISTIVITY IMAGE TOOL [STAR/GR] ON DRIFTED 4"/5" DP TO 6525' AT CONTROLLED SPEED.............(OOS)- FILL UP STRING EVERY 10 STD'S.- MONITOR WELL ON TRIP TANK - STATIC LOSSES 3.5 BPH. | 7206 | 2971 | RIG | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2005 | 7206 |  | CIRC | E | 3665 | MPMP | CIRC 2 X STRING CAPACITY AT 220 GPM & 320 PSI..............(OOS)- DYNAMIC LOSSES 8 BPH. | 7206 |  | RIG | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2006 | 7206 |  | OTH | E | 3665 | NA | HPJSM. R/U BHI W/L SHEAVES AND INSTALL SES. | 7206 |  | BAW | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2007 | 7206 |  | OTH | E | 3665 | NA | RIH W/ W/L INSIDE DP W/ LATCH HEAD AND LATCH INTO LOGGING TOOL. TEST CONNECTIVITY- OK..............(OOS)- PERFORM PULL TEST ON SES CABLE CLAMP W/ 5 KLBS - OK. | 7206 |  | BAW | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2008 | 7206 | 7173 | ST | E | 3665 | STDP | RIH BKR W/L LOGGING TOOLS RUN #2 RESISTIVITY IMAGE TOOL [STAR/GR] ON DRIFTED 5" DP F/ 6525' T/ 7173' AT CONTROLLED SPEED..............(OOS).- STATIC LOSSES - 3.5 BPH. | 7206 | 6525 | RIG | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2009 | 7206 | 6780 | LOG | E | 3665 | WLT | RECORD RESISTIVITY IMAGE LOG RUN# 2 (STAR/GR)..............(OOS)- RECORDED UP MAIN PASS LOG F/ 7,173' T/ 6,780'.- REPEATED UP MAIN PASS LOG F/ 7,173' T/ 6,780'.- RECORDED 200 FT REPEAT PASS LOG F/ 6,980' T/ 6,780'.- MONITOR WELL ON TRIP TANK - STATIC LOSSES 3.5 BPH. | 7206 | 7173 | BAW | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2010 | 7206 | 6525 | ST | E | 3665 | STDP | POOH W/ BKR LOGGING RUN#2 TO SES DEPTH AT 6525'...........(OOS) | 7206 | 6780 | RIG | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2011 | 7206 |  | OTH | E | 3665 | NA | UNLATCH & POOH CABLE TO SURFACE. L/D CABLE, SHEAVES AND SES..............(OOS) | 7206 |  | BAW | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2012 | 7206 | 75 | ST | E | 3665 | STDP | POOH BKR LOGGING RUN#2 W/ RESISTIVY IMAGE TOOL F/6525' TO TOP OF BHA AT 75'..............(OOS)- FLOW CHECK AT TOP OF BHA - 3.5 BPH STATIC LOSSES. | 7206 | 6525 | RIG | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2013 | 7206 |  | OTH | E | 3665 | NA | HPJSM. L/D BKR LOGGING TOOLS RUN#2..............(OOS) | 7206 |  | BAW | 07/23/2022 | SINO-43L | LOG | UTMN-4068
2014 | 7206 |  | HT | E | 3665 | BHA | HPJSM, P/U, M/U & RIH 6-1/8" CONDITION TRIP REAMING ASSY ON 4"/5" DP & HWDP TO 266 FT.............(OOS).BHA: 6-1/8" WELDED CONE BIT + 6-1/8" NBRR W/ FV + 1X4-3/4" DC + 6-1/8" STRR + 1X4-3/4" DC + 6-1/8" STRR + 1X4-3/4" DC + XO + 2XSTD 4" HWDP + 4-3/4" JAR + 3XSTD 4" HWDP + 4" & 5" DP. | 7206 |  | RIG | 07/23/2022 | SINO-43L | CT | UTMN-4068
2015 | 7206 | 5180 | TI | E | 3665 | STDP | RIH 6-1/8" REAMING BHA ON 4" DP F/ 266' T/ 5180'.............(OOS).- FILL UP STRING EVERY 20 STDS.- STATIC LOSSES 3.5 BPH. | 7206 | 266 | RIG | 07/23/2022 | SINO-43L | CT | UTMN-4068
2016 | 7206 |  | HT | E | 3665 | STRG | CHANGE HANDLING TOOLS FROM 4" TO 5".............(OOS). | 7206 |  | RIG | 07/23/2022 | SINO-43L | CT | UTMN-4068
2017 | 7206 | 6777 | TI | E | 3665 | STDP | CONT. RIH 6-1/8" REAMING BHA ON 5" DP F/ 5180' T/ 6777'.............(OOS).- FILL UP STRING EVERY 20 STDS.- STATIC LOSSES 3.5 BPH. | 7206 | 5180 | RIG | 07/23/2022 | SINO-43L | CT | UTMN-4068
2018 | 7206 | 7206 | ST | E | 3665 | SPDP | CONT. RIH 6-1/8" REAMING BHA ON 4" DP FROM 7" LP AT 6777' TO TD AT 7206'...............(OOS).- WASHED DOWN LAST STAND, HOLE IN GOOD CONDITION. | 7206 | 6777 | RIG | 07/23/2022 | SINO-43L | CT | UTMN-4068
2019 | 7206 |  | CIRC | E | 3665 | MPMP | SWEEP HOLE W/ 30 BBLS HI-VIS PILL & CHC..............(OOS). ON GOING.- DYNAMIC LOSSES 20 BPH. | 7206 |  | RIG | 07/23/2022 | SINO-43L | CT | UTMN-4068
2020 | 78.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" & 6-1/8" SECTION WIRELINE LOGGING. | 24 | 3665 | 15 Jul 0045 | 07/23/2022 | SINO-43L | Type | UTMN-4068
2021
2022
2023 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SINO-47 | Hrs | HRDH-1351
2024 | FOT | HLH | 36.25 | 22 Jul 1645 - 0500 | 14467 | 900054 | CEMENT DART RELEASED ACCIDENTLY FROM A FAILED CEMENT HEAD & NOT ABLE TO CIRCULATE. | TF | HGRL |  | 07/23/2022 | SINO-47 | 24 | HRDH-1351
2025 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SINO-5L | Hrs | UTMN-1029
2026 | FOT | SPS | 75.5 | 20 Jul 0130 - 0500 | 8935 | 899942 | UNABLE TO BUILD INCLINITION AS PER GOC REQUEST. CHECK MWD/LWD FOUND INTERMITTENT SIGNAL THEN NO SIGNAL. | BHA | LWD |  | 07/23/2022 | SINO-5L | 24 | UTMN-1029
2027 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SL-7 | Hrs | ZULF-1332
2028 | FOT | RIG | 1.5 | 23 Jul 0930 - 1100 | 0 | 900041 | RIG TROUBLESHOOT AMPHION SYSTEM. | RR | EDR |  | 07/23/2022 | SL-7 | 1.5 | ZULF-1332
2029 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SND-2008 | Hrs | HRDH-1812
2030 | PCPF | ARM | 91.5 | 20 Jul 0930 - 0500 | 12992 | 899932 | UNABLE TO SIDETRACK FROM WFD WHIPSTOCK DUE TO SUSPECTED POOR CEMENT BEHIND THE CASING | TH | NA |  | 07/23/2022 | SND-2008 | 24 | HRDH-1812
2031 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SND-3002 | Hrs | DMMM-601
2032 | FOT | WWL | 72.75 | 19 Jul 2000 - 0430 | 17144 | 899854 | WFD COMPACT SHUTTLE LOGGING TOOL LOST IN HOLE. | TF | WLT |  | 07/23/2022 | SND-3002 | 23.5 | DMMM-601
2033 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SP-167 | Hrs | HRDH-218
2034 | XTTE | SDM | 21 | 22 Jul 2130 - 1830 | 5464 | 899981 | OBSERVE PRESSURE FLUCTUATION AND MWD SIGNAL LOSS. TOOL FAILED | TF | MWD |  | 07/23/2022 | SP-167 | 13.5 | HRDH-218
2035 | IDPR | SDM | 3 | 22 Jul 0130 - 1500 | 14571 | 900060 | LOST SIGNAL. | DD | RSS |  | 07/23/2022 | SP-259 | 2.5 | THRY-371612
2036 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SP-259 | Hrs | THRY-371612
2037 | FPMP | RIG | 1.5 | 23 Jul 1800 - 1930 | 15477 | 900039 | FAILURE ON PUMPS 1&2. | RR | MPMP |  | 07/23/2022 | SP-259 | 1.5 | THRY-371612
2038 | IDPR | SDM | 3 | 22 Jul 0130 - 1500 | 14571 | 900060 | LOST SIGNAL. | DD | RSS |  | 07/23/2022 | SP-259 | 2.5 | THRY-371612
2039 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SSA-102 | Hrs | QTIF-693
2040 | SRVC | GOC | 2 | 23 Jul 1300 - 1500 | 0 | 900038 | WAIT ON CSG RUNNING CREW | WO | NA |  | 07/23/2022 | SSA-102 | 2 | QTIF-693
2041 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SSA-303 | Hrs | HRDH-2411
2042 | HERR | RIG | 4.25 | 23 Jul 2145 - 0200 | 5295 | 900067 | WHEN STARTING MIXING CMT, OBSERVED MIX FLUID OF LEAD TRANSFERED TO TANK OF TAIL MIX FLUID. DUMPED ALL MIX FLUID AND MIXED NEW MIX FLUID. | JF | CSYS |  | 07/23/2022 | SSA-303 | 4.25 | HRDH-2411
2043 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/23/2022 | SSA-5972 | Hrs | SHDN-19
2044 | UVLC | ARM | 106.5 | 19 Jul 1245 - 0500 | 7017 | 899855 | ENCOUNTERED COMPLETE LOSS CIRCULATION WHILE DRILLING 12" HOLE SECTION | LCIR | NA |  | 07/23/2022 | SSA-5972 | 20.5 | SHDN-19
2045 | FOT | SCT | 1.5 | 24 Jul 0330 - 0500 | 22133 | 900114 | ATTEMPT TO RIH SLB MFIV SHIFTING TOOL ON SCHL 2-7/8" CT, GOT HELD AT 32.5' (AT TOP OF TBG HGR), MANY ATTEMPTS TO PASS WITH WITHOUT SUCCESS , MAX ALLOWABLE SLACK OFF WT 15 KLBS , | TF | CTAC |  | 07/24/2022 | 095TE | 1.5 | MNIF-226
2046 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | 095TE | Hrs | MNIF-226
2047 | FOT | SCT | 10 | 24 Jul 1200 - 2200 | 22133 | 900029 | FUNCTION TEST AND PRESSURE TEST CT EQUIPMENT / MULTIPLE EQUIPMENT FAILURES ( CT GENERATOR AND PUMP TRUCK ) LEAKS DURING TESTING OF HP SURFACE EQUIPMENT | TF | CTPMP |  | 07/24/2022 | 095TE | 10 | MNIF-226
2048 | FOT | SCT | 1.5 | 24 Jul 0330 - 0500 | 22133 | 900114 | ATTEMPT TO RIH SLB MFIV SHIFTING TOOL ON SCHL 2-7/8" CT, GOT HELD AT 32.5' (AT TOP OF TBG HGR), MANY ATTEMPTS TO PASS WITH WITHOUT SUCCESS , MAX ALLOWABLE SLACK OFF WT 15 KLBS , | TF | CTAC |  | 07/24/2022 | 095TE | 1.5 | MNIF-226
2049 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADC-17 | Hrs | ZULF-1215
2050 | FOT | SJT | 1.25 | 24 Jul 1115 - 1230 | 5000 | 900093 | TAQA/SANJEL STOP PUMPING NITROGEN IN THE WELL DUTE AND N2 PUMP LOST PRIME DUE TO PROBLEM IN N2 TANK | TF | CTAC |  | 07/24/2022 | ADC-17 | 1.25 | ZULF-1215
2051 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADC-31 | Hrs | SDGM-1181
2052 | STDP | RIG | 280.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/24/2022 | ADC-31 | 24 | SDGM-1181
2053 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADC-50 | Hrs | SFNY-1176
2054 | LCRW | ARM | 119.25 | 19 Jul 1830 - 0500 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/24/2022 | ADC-50 | 24 | SFNY-1176
2055 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADC-59L | Hrs | HWYH-1324
2056 | FPMP | RIG | 1 | 24 Jul 1700 - 1800 | 10818 | 900112 | LOST MUD PUMP PSI. | RR | MPMP |  | 07/24/2022 | ADC-59L | 1 | HWYH-1324
2057 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADC-62L | Hrs | ANDR-745
2058 | WOTO | TK3 | 8.5 | 24 Jul 1130 - 2300 | 0 | 900113 | PRESSURE TESTED X-MASS TREE, PRESSURE NOT HOLDING, POOH TWCV AND CHANGE SEAL, TRY AGAIN, NOT HOLD. | WO | NA |  | 07/24/2022 | ADC-62L | 8.5 | ANDR-745
2059 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADES-144 | Hrs | UTMN-3152
2060 | FOT | SPS | 43 | 22 Jul 0930 - 1730 | 13626 | 900053 | LOST RSS SIGNAL, TROUBLE SHOOT WITHOUT SUCESS. | BHA | RSS |  | 07/24/2022 | ADES-144 | 12.5 | UTMN-3152
2061 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADM-266 | Hrs | MRJN-115
2062 | FOT | BCT | 10 | 24 Jul 1900 - 0500 | 0 | 900071 | FAILURE OF BAKER COIL TUBING INJECTORS HEAD HYD SYS. | TF | CTBG |  | 07/24/2022 | ADM-266 | 10 | MRJN-115
2063 | AINC | SDM | 36.75 | 23 Jul 1230 - 0500 | 8570 | 900065 | INCLINATION INCREASED RAPIDLY FROM 84 DEGREES TO 90. 7 DEGREES. OBSERVED DIFFICULTIES TO DROP INCLINATION | LROP | BHA |  | 07/24/2022 | ADM-510 | 20.25 | ABSF-231
2064 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADM-510 | Hrs | ABSF-231
2065 | FPMP | RIG | 3.25 | 21 Jul 0330 - 1430 | 8700 | 899996 | HAD FAILURE IN MUD PUMP # 1 & 2, STOP DRILLING. | RR | MPMP |  | 07/24/2022 | ADM-510 | 2.75 | ABSF-231
2066 | AINC | SDM | 36.75 | 23 Jul 1230 - 0500 | 8570 | 900065 | INCLINATION INCREASED RAPIDLY FROM 84 DEGREES TO 90. 7 DEGREES. OBSERVED DIFFICULTIES TO DROP INCLINATION | LROP | BHA |  | 07/24/2022 | ADM-510 | 20.25 | ABSF-231
2067 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ADM-511 | Hrs | MRJN-799
2068 | CWEL | ARM | 193.75 | 16 Jul 0600 - 0100 | 7763 | 899762 | UNABLE TO RUN 7'' LINER IN LAT-1 FIRST HUD 7763 FT, ATTEMPTED REAMING TRIP, UNABLE TO PASS 8250 FT, PUMPED OPEN HOLE SIDE TRACK CEMENT PLUG, SUPSENDED WELL OPERATIONS AND PERFORMED WELL CONTROL EQUIPMENT CHANGE OUT, RESUMED WELL OPERATIONS TO SIDETRACK AND DRILL LAT-1-1 | BHS | NA |  | 07/24/2022 | ADM-511 | 20 | MRJN-799
2069 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | BB-84A | Hrs | MRJN-587
2070 | FOT | BHI | 1 | 24 Jul 1100 - 1430 | 14170 | 900069 | LWD TOOL LOST SIGNEL | BHA | LWD |  | 07/24/2022 | BB-84A | 1 | MRJN-587
2071 | FOT | WI3 | 64.75 | 19 Jul 1700 - 0500 | 13000 | 899947 | WEATHERFORD UNABLE TO INITIATE SIDETRACK DUE TO SETTING WIS WHIPSTOCK. | TF | WPSTK |  | 07/24/2022 | DPS-5 | 12 | HRDH-2319
2072 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | DPS-5 | Hrs | HRDH-2319
2073 | HERR | WDS | 65 | 19 Jul 0500 - 1730 | 13000 | 899943 | WEATHERFORD UNABLE TO INITIATE SIDETRACK. | DD | MMOT |  | 07/24/2022 | DPS-5 | 12 | HRDH-2319
2074 | FOT | WI3 | 64.75 | 19 Jul 1700 - 0500 | 13000 | 899947 | WEATHERFORD UNABLE TO INITIATE SIDETRACK DUE TO SETTING WIS WHIPSTOCK. | TF | WPSTK |  | 07/24/2022 | DPS-5 | 12 | HRDH-2319
2075 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | DQ-57L | Hrs | KHRS-399
2076 | FOT | SBA | 84.5 | 21 Jul 0500 - 1730 | 4443 | 899950 | PRAXIS ESP ISOPAX PACKER 9 5/8 FAIL TO SET . | TF | PKR |  | 07/24/2022 | DQ-57L | 12.5 | KHRS-399
2077 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | ENSCO-54 | Hrs | ABSF-17
2078 | STCT | ARM | 402 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/24/2022 | ENSCO-54 | 24 | ABSF-17
2079 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | EXL-IA | Hrs | SFNY-1790
2080 | FOT | RIG | 2 | 24 Jul 0800 - 1000 | 1470 | 900070 | DISK BRAKE ASSEMBLY OBSERVED OVER HEATING DUE TO SERVICE BRAKE CALIPER OUT OF ADJUSTMENT. | RR | DWKS |  | 07/24/2022 | EXL-IA | 2 | SFNY-1790
2081 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | HI-4 | Hrs | BRRI-1000
2082 | CFFM | ARM | 93 | 20 Jul 0330 - 0500 | 189 | 899975 | HAD COMPLETE LOSSES AT 189' (13' ABOVE CONDUCTOR SHOE) | LCIR | SQZ |  | 07/24/2022 | HI-4 | 23.25 | BRRI-1000
2083 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | MP-4 | Hrs | LWHH-45
2084 | FOT | WWD | 18 | 24 Jul 1100 - 0500 | 9415 | 900092 | DRILLED 2 FT RAT HOLE WITH WEATHERFORD MILLING ASSY AND NO MORE PROGRESS, RIH WITH 2ND MILLING ASSY TO DRILL THE REMAINING RAT HOLE. | TF | WPSTK |  | 07/24/2022 | MP-4 | 18 | LWHH-45
2085 | WC20 | ARM | 16.25 | 24 Jul 0500 - 2145 | 14034 | 900030 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=160 PSI, PUMP OPEN FLOAT VALVE AND OBSERVE SIDPP=160 PSI. | WCNT | NA |  | 07/24/2022 | NBR-263S | 16.25 | QTIF-736
2086 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | NBR-263S | Hrs | QTIF-736
2087 | CWEL | ARN | 7.25 | 24 Jul 2145 - 0500 | 14068 | 899991 | OPENED BOP AFTER WELL OBSERVATION, WELL IS STATIC. TRY TO MOVE STRIN HAD STRING STUCK. WORK ON STUCK PIPE | BHS | NA |  | 07/24/2022 | NBR-263S | 7.25 | QTIF-736
2088 | WC20 | ARM | 16.25 | 24 Jul 0500 - 2145 | 14034 | 900030 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=160 PSI, PUMP OPEN FLOAT VALVE AND OBSERVE SIDPP=160 PSI. | WCNT | NA |  | 07/24/2022 | NBR-263S | 16.25 | QTIF-736
2089 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | PN-9 | Hrs | MRJN-673
2090 | CFST | HCM | 30 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/24/2022 | PN-9 | 24 | MRJN-673
2091 | 7206 |  | CIRC | E | 3665 | MPMP | CONT. SWEEP & CHC..............(OOS).- SPOT 40 BBLS LUBRICATED HI-VIS PILL.- DYNAMIC LOSSES 20 BPH. | 7206 |  | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2092 | 7206 |  | WCNT | E | 3665 | NA | FLOW CHECK - STATIC LOSSES 3 BPH..............(OOS). | 7206 |  | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2093 | 7206 | 6777 | ST | E | 3665 | STDP | POH 6-1/8" REAMING ASSY TO 7" LP AT 6777'..............(OOS).- HOLE IN GOOD CONDITION | 7206 | 7206 | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2094 | 7206 |  | WCNT | E | 3665 | NA | FLOW CHECK AT LINER SHOE - STATIC LOSSES 3 BPH..............(OOS). | 7206 |  | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2095 | 7206 | 5180 | TO | E | 3665 | STDP | POH 6-1/8" REAMING ASSY F/ 6777' TO 5180' ON 5" DP..............(OOS). | 7206 | 6777 | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2096 | 7206 |  | HT | E | 3665 | STRG | CHANGE HANDLING TOOLS FROM 5" TO 4".............(OOS). | 7206 |  | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2097 | 7206 | 266 | TO | E | 3665 | STDP | CONT. POH 6-1/8" REAMING ASSY F/ 5180' TO 266' ON 4" DP..............(OOS). | 7206 | 5180 | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2098 | 7206 |  | WCNT | E | 3665 | NA | FLOW CHECK AT TOP OF BHA - STATIC LOSSES 3 BPH..............(OOS). | 7206 |  | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2099 | 7206 |  | HT | E | 3665 | BHA | POOH & L/D 6-1/8" REAMING BHA..............(OOS). | 7206 |  | RIG | 07/24/2022 | SINO-43L | CT | UTMN-4068
2100 | 7206 |  | PJSM | E | 3665 | NA | HPJSM WITH ARAMCO, BAKER DSV, RIG CREW, & BAKER W/L TEAM & DISSCUS OPEN HOLE PRESSURE POINTS SAMPLING JOB & RELATED RISK..............(OOS). | 7206 |  | ARM | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2101 | 7206 |  | OTH | E | 3665 | NA | R/U & M/U BKR W/L LOGGING TOOLS RUN#3 [RCX - GR] ............(OOS).- TOTAL LOGGING TOOL LENGTH: 156.37', MAX OD: 5.6".- FUNCTION TESTED & PERFORM TOOL CALIBRATION AT SURFACE.- MONITOR THE WELL THROUGH TRIP TANK, STATIC LOSSES 3 BPH. | 7206 |  | BAW | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2102 | 7206 | 6510 | ST | E | 3665 | STDP | RIH BKR LOGGING TOOLS RUN#3 [RCX - GR] AT CONTROLLED SPEED TO LATCH POINT AT 6510'. ............(OOS).- FILL STRING EVERY 10 STD.- CONTROLLED RUNNING SPEED TO 2 MIN / STD.- MONITOR HOLE ON TRIP TANK - 3 BPH STATIC LOSSES. | 7206 | 156 | RIG | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2103 | 7206 |  | CIRC | E | 3665 | MPMP | CIRC 2 X STRING CAPACITY AT 250 GPM & 360 PSI..............(OOS).- DYNAMIC LOSSES 8 BPH. | 7206 |  | RIG | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2104 | 7206 |  | OTH | E | 3665 | NA | HPJSM. R/U BHI W/L SHEAVES AND INSTALL SES..............(OOS). | 7206 |  | BAW | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2105 | 7206 |  | OTH | E | 3665 | NA | RIH INSIDE DP W/ LATCH HEAD AND LATCH INTO LOGGING TOOL. TEST CONNECTIVITY- OK..............(OOS).- PERFORM PULL TEST ON SES CABLE CLAMP W/ 5 KLBS - OK. | 7206 |  | BAW | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2106 | 7206 | 7051 | LOG | E | 3665 | CORRL | CONT. RIH W/ BHI RUN#3 [RCX - GR] T/ 7051' AND CORRELATE GR ..............(OOS). | 7206 | 6510 | BAW | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2107 | 7206 |  | OTH | E | 3665 | NA | PERFORMED STUCK TENDENCY TEST AT 6794' FOR 30 MINS - OK, NO OVER PULL ............(OOS). | 7206 |  | BAW | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2108 | 7206 | 6794 | LOG | E | 3665 | WLT | RECORDED 1 OUT OF 19 PRESSURE POINTS AT 6794'. ............(OOS).- MONITOR HOLE ON TRIP TANK - 3 BPH STATIC LOSSES. | 7206 | 6794 | BAW | 07/24/2022 | SINO-43L | LOG | UTMN-4068
2109 | 102.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" & 6-1/8" SECTION WIRELINE LOGGING. | 24 | 3665 | 15 Jul 0045 | 07/24/2022 | SINO-43L | Type | UTMN-4068
2110
2111
2112 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SINO-47 | Hrs | HRDH-1351
2113 | FOT | HLH | 51.75 | 22 Jul 1645 - 2030 | 14467 | 900054 | CEMENT DART RELEASED ACCIDENTLY FROM A FAILED CEMENT HEAD & NOT ABLE TO CIRCULATE. | TF | HGRL |  | 07/24/2022 | SINO-47 | 15.5 | HRDH-1351
2114 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SINO-5L | Hrs | UTMN-1029
2115 | FOT | SPS | 91.5 | 20 Jul 0130 - 2100 | 8935 | 899942 | UNABLE TO BUILD INCLINITION AS PER GOC REQUEST. CHECK MWD/LWD FOUND INTERMITTENT SIGNAL THEN NO SIGNAL. | BHA | LWD |  | 07/24/2022 | SINO-5L | 16 | UTMN-1029
2116 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SND-2008 | Hrs | HRDH-1812
2117 | PCPF | ARM | 115.5 | 20 Jul 0930 - 0500 | 1299 | 899932 | UNABLE TO SIDETRACK FROM WFD WHIPSTOCK DUE TO SUSPECTED POOR CEMENT BEHIND THE CASING | TH | NA |  | 07/24/2022 | SND-2008 | 24 | HRDH-1812
2118 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SND-3001 | Hrs | MHWZ-167101
2119 | FOT | EX1 | 9.25 | 24 Jul 1200 - 0500 | 1000 | 899985 | WHEN JARRING ON INTERWELL PLUG EXPRO SLICKLINE BROKE APPROX 100' FROM ROPE SOCKET | TF | SLICK |  | 07/24/2022 | SND-3001 | 9.25 | MHWZ-167101
2120 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SND-3002 | Hrs | DMMM-601
2121 | FOT | WWL | 95 | 19 Jul 2000 - 0245 | 17144 | 899854 | WFD COMPACT SHUTTLE LOGGING TOOL LOST IN HOLE. | TF | WLT |  | 07/24/2022 | SND-3002 | 21.75 | DMMM-601
2122 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SP-122 | Hrs | HWYH-1178
2123 | HERR | RIG | 12 | 24 Jul 0630 - 2030 | 6427 | 900074 | STRING PLUGGED DUE TO INADEQUATE LINEUP. | DSF | STRG |  | 07/24/2022 | SP-122 | 12 | HWYH-1178
2124 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SP-261 | Hrs | HZEM-160212
2125 | XTRI | ITS | 1 | 24 Jul 0730 - 0830 | 0 | 899990 | REPLACE DAMAGED CRT PACKER RUBBER. | JF | CTRQ |  | 07/24/2022 | SP-261 | 1 | HZEM-160212
2126 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SSA-5859 | Hrs | HWYH-1222
2127 | FOT | SPS | 9.5 | 20 Jul 2000 - 0400 | 18370 | 899933 | TROUBLE SHOOTING ON MWD SIGNAL | SURV | SS |  | 07/24/2022 | SSA-5859 | 2 | HWYH-1222
2128 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | SSA-5972 | Hrs | SHDN-19
2129 | UVLC | ARM | 123.5 | 19 Jul 1245 - 0030 | 7017 | 899855 | ENCOUNTERED COMPLETE LOSS CIRCULATION WHILE DRILLING 12" HOLE SECTION | LCIR | NA |  | 07/24/2022 | SSA-5972 | 17 | SHDN-19
2130 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/24/2022 | T216 | Hrs | ANDR-338
2131 | FOT | RIG | 4 | 24 Jul 0500 - 0900 | 2240 | 899989 | REPAIR ON DRAW WORKS | RR | DWKS |  | 07/24/2022 | T216 | 4 | ANDR-338
2132 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | 095TE | Hrs | MNIF-226
2133 | FOT | SCT | 5.5 | 25 Jul 2100 - 0230 | 10 | 900172 | MANY TRIALS TO RIH ACID BHA ON SLB CT WITH NO SUCCESS, GOT HELD UP INSIDE SLB CT BOP, HAD TO POH AND DISCONNECT IH 3 TIMES TO ADD OR REMOVE STRAIGH BAR FROM BHA AND TRY AGAIN, MANAGED TO PASS FINALLY ON 3 RD TRIALS WITH ONE STRAIGHT BAR AND AGITATOR HELP. | TF | CTBG |  | 07/25/2022 | 095TE | 5.5 | MNIF-226
2134 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | ADC-32 | Hrs | ANDR-1010
2135 | HERR | RIG | 19.25 | 25 Jul 0945 - 0500 | 2689 | 900138 | WHILE L/D 22" DRILLING BHA, TOTCO BAR DROPPED IN HOLE. | JF | TOTCO |  | 07/25/2022 | ADC-32 | 19.25 | ANDR-1010
2136 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | ADC-41L | Hrs | SDGM-1244
2137 | UVLC | TK3 | 168 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 07/25/2022 | ADC-41L | 24 | SDGM-1244
2138 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | ADC-50 | Hrs | SFNY-1176
2139 | LCRW | ARM | 139 | 19 Jul 1830 - 0115 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/25/2022 | ADC-50 | 19.75 | SFNY-1176
2140 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | ADES-157 | Hrs | HRDH-642
2141 | FOT | GD2 | 1 | 25 Jul 2045 - 2145 | 0 | 900140 | RIGGED UP GDMC N2 UNIT, PROBLEM ON THE PRESSURE SENSOR. CHANGED PRESSURE SENSOR. | TF | CTPMP |  | 07/25/2022 | ADES-157 | 1 | HRDH-642
2142 | AINC | SDM | 1 | 25 Jul 1430 - 1530 | 8565 | 900136 | REAM UP/DOWN ACROSS HIGH DOG LEG SEVERITY (DLS) INTERVAL. | DD | BHA |  | 07/25/2022 | ADM-510 | 1 | ABSF-231
2143 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | ADM-510 | Hrs | ABSF-231
2144 | AINC | SDM | 43.25 | 23 Jul 1230 - 1130 | 8570 | 900065 | INCLINATION INCREASED RAPIDLY FROM 84 DEGREES TO 90. 7 DEGREES. OBSERVED DIFFICULTIES TO DROP INCLINATION | LROP | BHA |  | 07/25/2022 | ADM-510 | 6.5 | ABSF-231
2145 | AINC | SDM | 1 | 25 Jul 1430 - 1530 | 8565 | 900136 | REAM UP/DOWN ACROSS HIGH DOG LEG SEVERITY (DLS) INTERVAL. | DD | BHA |  | 07/25/2022 | ADM-510 | 1 | ABSF-231
2146 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | ARO-4001 | Hrs | MRJN-532
2147 | STBH | ARM | 24 | 25 Jul 0500 - 0500 | 6546 | 900100 | GOT STRING STUCK DUE TO TOTAL LOSSES WHICH LED TO HOLE BACK OFF, WORKING ON SAME | STUK | BHA |  | 07/25/2022 | ARO-4001 | 24 | MRJN-532
2148 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | BB-84A | Hrs | MRJN-587
2149 | SDIR | BHI | 6.75 | 25 Jul 2215 - 0500 | 15560 | 900154 | WHILE REAMING STAND AT TD, PIPE BECAME STUCK WHILE REAMING UP | STUK | RSS |  | 07/25/2022 | BB-84A | 6.75 | MRJN-587
2150 | FOT | WI3 | 74.5 | 19 Jul 1700 - 0045 | 13000 | 899947 | AFTER SETTING WIS WHIPSTOCK, MILL WINDOW & DRILL 11' OF RAT HOLE W/OUT PROBLEM, RIH WFD DIR. DRILL ASSY, SLIDE DRILL 36' W/ STRING HANGING & MMOTOR STALLING, PU 30' FOR CONNECTION,RUN BACK & ATTEMPT TO CONTINUE SLIDE DRILLING W/OUT SUCCESS, NO WOB & NO DIFFERENTIAL PRESSURE, ABLE TO WASH DOWN FREELY 418' AND TAG @ 13599', W/OUT GETTING CUTTINGS @ SURFACE, DISCUSS W/ OFFICE & POOH. | TF | WPSTK |  | 07/25/2022 | DPS-5 | 9.75 | HRDH-2319
2151 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | DPS-5 | Hrs | HRDH-2319
2152 | HERR | WDS | 74.5 | 19 Jul 0500 - 1430 | 13000 | 899943 | AFTER SETTING WIS WHIPSTOCK, MILL WINDOW & DRILL 11' OF RAT HOLE W/OUT PROBLEM, RIH WFD DIR. DRILL ASSY, SLIDE DRILL 36' W/ STRING HANGING & MMOTOR STALLING, PU 30' FOR CONNECTION,RUN BACK & ATTEMPT TO CONTINUE SLIDE DRILLING W/OUT SUCCESS, NO WOB & NO DIFFERENTIAL PRESSURE, ABLE TO WASH DOWN FREELY 418' AND TAG @ 13599', W/OUT GETTING CUTTINGS @ SURFACE, DISCUSS W/ OFFICE & POOH. | DD | MMOT |  | 07/25/2022 | DPS-5 | 9.5 | HRDH-2319
2153 | FOT | WI3 | 74.5 | 19 Jul 1700 - 0045 | 13000 | 899947 | AFTER SETTING WIS WHIPSTOCK, MILL WINDOW & DRILL 11' OF RAT HOLE W/OUT PROBLEM, RIH WFD DIR. DRILL ASSY, SLIDE DRILL 36' W/ STRING HANGING & MMOTOR STALLING, PU 30' FOR CONNECTION,RUN BACK & ATTEMPT TO CONTINUE SLIDE DRILLING W/OUT SUCCESS, NO WOB & NO DIFFERENTIAL PRESSURE, ABLE TO WASH DOWN FREELY 418' AND TAG @ 13599', W/OUT GETTING CUTTINGS @ SURFACE, DISCUSS W/ OFFICE & POOH. | TF | WPSTK |  | 07/25/2022 | DPS-5 | 9.75 | HRDH-2319
2154 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | ENSCO-54 | Hrs | ABSF-17
2155 | STCT | ARM | 426 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/25/2022 | ENSCO-54 | 24 | ABSF-17
2156 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | HI-4 | Hrs | BRRI-1000
2157 | CFFM | ARM | 100 | 20 Jul 0330 - 1200 | 189 | 899975 | HAD COMPLETE LOSSES AT 189' (13' ABOVE CONDUCTOR SHOE) | LCIR | SQZ |  | 07/25/2022 | HI-4 | 7 | BRRI-1000
2158 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | MP-4 | Hrs | LWHH-45
2159 | FOT | WWD | 32.5 | 24 Jul 1100 - 2330 | 9415 | 900092 | DRILLED 2 FT RAT HOLE WITH WEATHERFORD MILLING ASSY AND NO MORE PROGRESS, RIH WITH 2ND MILLING ASSY TO DRILL THE REMAINING RAT HOLE. | TF | WPSTK |  | 07/25/2022 | MP-4 | 14.5 | LWHH-45
2160 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | NA-207S | Hrs | SHYB-132
2161 | FOT | RIG | 10 | 25 Jul 1900 - 0500 | 11155 | 900134 | WASH PIPE LEAK DURING DRILLING 6 1/8" HOLE SECTION. SAME TIME TOP DRIVER POWER SHUT DOWN | RR | TDS |  | 07/25/2022 | NA-207S | 10 | SHYB-132
2162 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | NBR-263S | Hrs | QTIF-736
2163 | STBH | ARM | 20.5 | 24 Jul 2145 - 1815 | 14038 | 899991 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 07/25/2022 | NBR-263S | 13.25 | QTIF-736
2164 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | PA-866S | Hrs | SHHB-2
2165 | FOT | SWL | 20.25 | 25 Jul 0845 - 0500 | 13840 | 900115 | UNABLE TO ACTIVATE SATURN PACKER | TF | WLT |  | 07/25/2022 | PA-866S | 20.25 | SHHB-2
2166 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | PN-9 | Hrs | MRJN-673
2167 | CFST | HCM | 42 | 23 Jul 2300 - 0430 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/25/2022 | PN-9 | 12 | MRJN-673
2168 | FOT | SCT | 6.75 | 25 Jul 1145 - 2200 | 12595 | 900173 | MULTIPLE LEAKS ON SLB SURFACE LINE LINES | TF | CTPMP |  | 07/25/2022 | RBP-50A | 6.75 | HSBH-52
2169 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | RBP-50A | Hrs | HSBH-52
2170 | FOT | HTS | 2 | 25 Jul 1830 - 2030 | 12595 | 900101 | LEAKS OBSERVED ON HWT CHOKE MANIFOLD FLANGE | TF | WTSE |  | 07/25/2022 | RBP-50A | 2 | HSBH-52
2171 | FOT | SCT | 6.75 | 25 Jul 1145 - 2200 | 12595 | 900173 | MULTIPLE LEAKS ON SLB SURFACE LINE LINES | TF | CTPMP |  | 07/25/2022 | RBP-50A | 6.75 | HSBH-52
2172 | 7206 | 6794 | LOG | E | 3665 | WLT | RECORDED 19 OUT OF 19 PRESSURE POINTS. ............(OOS).- MONITOR HOLE ON TRIP TANK - 3 BPH STATIC LOSSES. | 7206 | 6794 | BAW | 07/25/2022 | SINO-43L | LOG | UTMN-4068
2173 | 7206 |  | OTH | E | 3665 | NA | PERFORMED STUCK TENDENCY TEST AT 6,967' FOR 1 HOUR - OK, NO OVER PULL ............(OOS). | 7206 |  | BAW | 07/25/2022 | SINO-43L | LOG | UTMN-4068
2174 | 7206 | 6967 | LOG | E | 3665 | WLT | POSITION STRING & COLLECTED SAMPLE#1 AT 6,967' USING MAGNA PROPE (1 OF 10 ) 1 CYCLE.............(OOS).- TOTAL DUMPING IN ANN. = 194 LITERS OIL/ WATER. COLLECT ONE BOTTLE OF SAMPLE .- MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 3 BPH. | 7206 | 6967 | BAW | 07/25/2022 | SINO-43L | LOG | UTMN-4068
2175 | 7206 | 6926 | LOG | E | 3665 | WLT | MOVED STRING & COLLECTED SAMPLE#2 USING MAGNA PROPE AT 6,926' (2 OF 10 ) 1 CYCLE.............(OOS).- PUMPED OUT= 197 LITERS, TOTAL DUMPING IN ANN. = 391 LITERS OIL/ WATER. COLLECT ONE BOTTLE OF SAMPLE .- MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 3 BPH. | 7206 | 6926 | BAW | 07/25/2022 | SINO-43L | LOG | UTMN-4068
2176 | 7206 | 6919 | LOG | E | 3665 | WLT | MOVED STRING TO SAMPLE#3 USING MAGNA PROPE AT 6,919' (3 OF 10 ). ONGOING.............(OOS).- PUMPED OUT = 275 LITERS, TOTAL DUMPING IN ANN. = 666 LITERS OIL/ WATER.- MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 3 BPH. | 7206 | 6919 | BAW | 07/25/2022 | SINO-43L | LOG | UTMN-4068
2177 | 126.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" & 6-1/8" SECTION WIRELINE LOGGING. | 24 | 3665 | 15 Jul 0045 | 07/25/2022 | SINO-43L | Type | UTMN-4068
2178
2179
2180 | PCPF | ARM | 126.5 | 20 Jul 0930 - 1600 | 1299 | 899932 | UNABLE TO SIDETRACK FROM WFD WHIPSTOCK DUE TO SUSPECTED POOR CEMENT BEHIND THE CASING | TH | NA |  | 07/25/2022 | SND-2008 | 11 | HRDH-1812
2181 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | SND-2008 | Hrs | HRDH-1812
2182 | STDP | RIG | 305.5 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/25/2022 | SND-2008 | 13 | HRDH-1812
2183 | PCPF | ARM | 126.5 | 20 Jul 0930 - 1600 | 1299 | 899932 | UNABLE TO SIDETRACK FROM WFD WHIPSTOCK DUE TO SUSPECTED POOR CEMENT BEHIND THE CASING | TH | NA |  | 07/25/2022 | SND-2008 | 11 | HRDH-1812
2184 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | SND-3001 | Hrs | MHWZ-167101
2185 | FOT | EX1 | 33.25 | 24 Jul 1200 - 0500 | 1000 | 899985 | WHEN JARRING ON INTERWELL PLUG EXPRO SLICKLINE BROKE APPROX 100' FROM ROPE SOCKET | TF | SLICK |  | 07/25/2022 | SND-3001 | 24 | MHWZ-167101
2186 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | SP-121 | Hrs | BRRI-522
2187 | FOT | RIG | 1.5 | 25 Jul 0330 - 0500 | 4660 | 900155 | FOUND TDS POWER SUPPLY CABLE IN TOP DRIVE HOUSE OVER LOADED. WORK ON REPLACING POWER SUPPLY CABLE. | RR | TDS |  | 07/25/2022 | SP-121 | 1.5 | BRRI-522
2188 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | SSA-5859 | Hrs | HWYH-1222
2189 | FOT | SPS | 15 | 20 Jul 2000 - 1200 | 18370 | 899933 | TROUBLE SHOOTING ON MWD SIGNAL | SURV | SS |  | 07/25/2022 | SSA-5859 | 5.5 | HWYH-1222
2190 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | SSA-5891 | Hrs | HRDH-1205
2191 | STOP | ARM | 1.25 | 25 Jul 1915 - 2030 | 0 | 900152 | GWS, COULD NOT RETRIEVE BPV AS NO EXTENSION BUSHING & COUPLING FOR RETREIVING TOOL ON TRUCK. HAD TO RETURN TO HRDH TO GET COUPLING & BUSHING FOR RETREIVING TOOL. | WO | NA |  | 07/25/2022 | SSA-5891 | 1.25 | HRDH-1205
2192 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | SSA-5962 | Hrs | HRDH-2513
2193 | SRVC | HCM | 1.5 | 25 Jul 0930 - 1100 | 1860 | 900135 | HALLIBURTON CMT UNIT FAILURE. | WO | NA |  | 07/25/2022 | SSA-5962 | 1.5 | HRDH-2513
2194 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | SSA-5964 | Hrs | HRDH-916
2195 | SRVC | NCT | 6 | 25 Jul 0700 - 1300 | 0 | 900132 | NESR ASSIGNED COMPANY FOR N2 PRESSURE TESTING DID NOT PROVIDE UNIT AND CREW. CONTACTED DWO MARKET SHARE AND RE-ASSIGNED HALL FOR THE JOB. | WO | NA |  | 07/25/2022 | SSA-5964 | 6 | HRDH-916
2196 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/25/2022 | T218 | Hrs | UTMN-1281
2197 | FOT | HWP | 18 | 25 Jul 1100 - 0500 | 10654 | 900102 | MECHANICAL CUTTER TOOL FAILURE. | TF | WLTT |  | 07/25/2022 | T218 | 18 | UTMN-1281
2198 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ADC-21 | Hrs | MZLJ-155201
2199 | XTTE | WUD | 1.5 | 26 Jul 0300 - 0430 | 0 | 900110 | EXCESS TIME TO R/D MPD FLOWLINE AND ROT WELLHEAD DUE TO BROKEN IMPACT WRENCH | TF | RCD |  | 07/26/2022 | ADC-21 | 1.5 | MZLJ-155201
2200 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ADC-31 | Hrs | SDGM-1181
2201 | STDP | RIG | 328.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/26/2022 | ADC-31 | 24 | SDGM-1181
2202 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ADC-32 | Hrs | ANDR-1010
2203 | HERR | RIG | 43.25 | 25 Jul 0945 - 0500 | 2689 | 900138 | WHILE L/D 22" DRILLING BHA, TOTCO BAR DROPPED IN HOLE. | JF | TOTCO |  | 07/26/2022 | ADC-32 | 24 | ANDR-1010
2204 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ADC-41L | Hrs | SDGM-1244
2205 | UVLC | TK3 | 180.5 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 07/26/2022 | ADC-41L | 24 | SDGM-1244
2206 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ADC-43L | Hrs | UTMN-3118
2207 | FOT | TK3 | 2.5 | 26 Jul 1200 - 0500 | 12039 | 900178 | LEAKAGE ON CRT RUBBER CUP PACKER. | TF | CSG |  | 07/26/2022 | ADC-43L | 2.5 | UTMN-3118
2208 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ADC-58L | Hrs | ABHD-169
2209 | FOT | RIG | 1.5 | 26 Jul 2030 - 2200 | 8586 | 900162 | OBSERVED DISCREPANCY IN HOOK LOAD, INVESTIGATE PROBLEM FOUND LEAK FROM LOAD CELL DIGHFRAGM. | RR | EDR |  | 07/26/2022 | ADC-58L | 1.5 | ABHD-169
2210 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ADES-157 | Hrs | HRDH-642
2211 | FOT | GD2 | 1.5 | 26 Jul 0500 - 0630 | 0 | 900105 | EXCESS TIME TO P/T WELLHEAD WITH N2. MANY LEAKS ON GDMC LINES AND VAIVES | TF | CTU |  | 07/26/2022 | ADES-157 | 1.5 | HRDH-642
2212 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ADM-262 | Hrs | MRJN-122
2213 | LHFL | RIG | 4.75 | 26 Jul 1145 - 1630 | 0 | 900158 | OBSERVE LEAK IN HYDRAULIC SERVICE LOOP OF TOP DRIVE SYSTEM. | RR | HSYS |  | 07/26/2022 | ADM-262 | 4.75 | MRJN-122
2214 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | AOD-1 | Hrs | ZULF-694
2215 | FOT | RIG | 13 | 26 Jul 0500 - 1800 | 8630 | 900107 | WHILE DRILLING, OBSERVED WASHPIPE LEAKING. TROUBLESHOOT & FOUND WASHPPE LEAKING PASSED PACKING SEALS. REPLACE ENTIRE WASHPIPE ASSEMBLY. | RR | CSYS |  | 07/26/2022 | AOD-1 | 13 | ZULF-694
2216 | FOT | RIG | 1 | 26 Jul 1800 - 1900 | 3880 | 900161 | 2 X HYDRAULIC HOSES BURST ON ST-160. REPLACE WITH NEW HOSES. | RR | HSYS |  | 07/26/2022 | ARO-4001 | 1 | MRJN-532
2217 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ARO-4001 | Hrs | MRJN-532
2218 | STBH | ARM | 30.5 | 25 Jul 0500 - 1130 | 6546 | 900100 | GOT STRING STUCK DUE TO TOTAL LOSSES WHICH LED TO HOLE BACK OFF. | STUK | BHA |  | 07/26/2022 | ARO-4001 | 6.5 | MRJN-532
2219 | FOT | RIG | 1 | 26 Jul 1800 - 1900 | 3880 | 900161 | 2 X HYDRAULIC HOSES BURST ON ST-160. REPLACE WITH NEW HOSES. | RR | HSYS |  | 07/26/2022 | ARO-4001 | 1 | MRJN-532
2220 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | BB-84A | Hrs | MRJN-587
2221 | PSSW | ARM | 22.25 | 25 Jul 2215 - 2030 | 15560 | 900154 | WHILE REAMING STAND AT TD, PIPE BECAME STUCK WHILE REAMING UP | STUK | NA |  | 07/26/2022 | BB-84A | 15.5 | MRJN-587
2222 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | DQ-49L | Hrs | HRDH-575
2223 | STBH | TK1 | 9 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 07/26/2022 | DQ-49L | 9 | HRDH-575
2224 | HERR | RIG | .5 | 26 Jul 1100 - 1130 | 9126 | 900193 | DRILLER UNABLE TO DISENGAGE CRT AND SLACKED OFF EXCESSIVE WEIGHT CASUED DRILL-LINE TO BACKLASH. | JF | CRT |  | 07/26/2022 | ED-85A | .5 | ZULF-2063
2225 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ED-85A | Hrs | ZULF-2063
2226 | CFST | BCM | 3.25 | 26 Jul 0145 - 0500 | 11328 | 900111 | CEMENT SET WHILE DISPLACING DV OPENNING PLUG. | CMT | NA |  | 07/26/2022 | ED-85A | 3.25 | ZULF-2063
2227 | HERR | RIG | .5 | 26 Jul 1100 - 1130 | 9126 | 900193 | DRILLER UNABLE TO DISENGAGE CRT AND SLACKED OFF EXCESSIVE WEIGHT CASUED DRILL-LINE TO BACKLASH. | JF | CRT |  | 07/26/2022 | ED-85A | .5 | ZULF-2063
2228 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | ENSCO-54 | Hrs | ABSF-17
2229 | STCT | ARM | 450 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/26/2022 | ENSCO-54 | 24 | ABSF-17
2230 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | JACK-202 | Hrs | THRY-829
2231 | OTH | RIG | 24 | 26 Jul 0500 - 0500 | 0 | 900159 | **RECEIVE CSG ELEVATORS & DC & CSG SLIPS & BUSHING WITHOUT COC & INSPECTION CERTIFICATE.RECEIVE SOME CERTIFICATES AND WAIT FOR ANOTHERS. **WHILE TEST ACCUMLATOR THE AIR PUMP NOT WORKING, WAIT TO REPAIR. **WAIT TO CHANGE IMPELLER OF CENTRIFUGAL PUMP OF CEMENT TANK. **WAIT TO RECEIVE 30" & 24" BUSHING. | UPRA | NA |  | 07/26/2022 | JACK-202 | 24 | THRY-829
2232 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | NA-128S | Hrs | GHZL-112
2233 | FOT | SPS | 9 | 26 Jul 2000 - 0500 | 12402 | 900108 | GOT ERROR READING FROM RSS WHILE DRILLING AT 12402' | BHA | RSS |  | 07/26/2022 | NA-128S | 9 | GHZL-112
2234 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | NA-207S | Hrs | SHYB-132
2235 | FOT | RIG | 18 | 25 Jul 1900 - 1300 | 11155 | 900134 | OBSERVED WASH PIPE LEAK DURING DRILLING 6 1/8" HOLE SECTION. SAME TIME TOP DRIVE LOST COMMUNICATION AND SHUT DOWN. | RR | SWVL |  | 07/26/2022 | NA-207S | 8 | SHYB-132
2236 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | PA-866S | Hrs | SHHB-2
2237 | FOT | SWL | 44.25 | 25 Jul 0845 - 0500 | 13840 | 900115 | UNABLE TO ACTIVATE SATURN PACKER | TF | WLT |  | 07/26/2022 | PA-866S | 24 | SHHB-2
2238 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | PN-9 | Hrs | MRJN-673
2239 | CFST | HCM | 78 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/26/2022 | PN-9 | 24 | MRJN-673
2240 | 7206 | 6919 | LOG | E | 3665 | WLT | CONT. COLLECTING SAMPLE#3 USING STANDARD PROBE AT 6,919' (3 OF 10 ). 1 CYCLE.............(OOS).- PUMPED OUT = 280 LITERS, TOTAL DUMPING IN ANN. = 671 LITERS OIL/ WATER.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH | 7206 | 6919 | BAW | 07/26/2022 | SINO-43L | LOG | UTMN-4068
2241 | 7206 | 6911 | LOG | E | 3665 | WLT | POSITION STRING & COLLECTED SAMPLE#4 AT 6,911' USING STANDARD PROBE (4 OF 10 ) 1 CYCLE.............(OOS).- PUMPED OUT VOL. = 272 LITERS. TOTAL DUMPING IN ANN. = 943 OIL/ WATER. COLLECT ONE BOTTLE OF SAMPLE .- MAX STATIONARY 4 HRS, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6911 | BAW | 07/26/2022 | SINO-43L | LOG | UTMN-4068
2242 | 7206 | 6911 | LOG | E | 3665 | WLT | POSITION STRING & COLLECTED SAMPLE#5 AT 6,903' USING MANGNA PROBE (5 OF 10 ) 2 CYCLES.............(OOS).- PUMPED OUT VOL. = 440 LITERS. TOTAL DUMPING IN ANN. = 1383 LITERS OIL/ WATER. COLLECT ONE BOTTLE OF SAMPLE .- MAX STATIONARY 4 HRS FOR , MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6911 | BAW | 07/26/2022 | SINO-43L | LOG | UTMN-4068
2243 | 7206 | 7126 | ST | E | 3665 | STDP | RIH W/ BKR LOGGING TOOLS AT CONTROLLED SPEED F/ 6,911' T/ 7,126'. POSITION CIRCULATING SUB BELOW 1ST SAMPLING DEPTH ............(OOS). | 7206 | 6911 | RIG | 07/26/2022 | SINO-43L | CT | UTMN-4068
2244 | 7206 |  | CIRC | E | 3665 | MPMP | CIRC. 1.5 X BTM-UP & CONDITION MUD IN & OUT = 64 PCF [160 GPM & 320 PSI ]. ............(OOS).- PRECAUTIONARY CIRCULATE THROUGH FULL OPEN CHOKE TO MGS W/ ANNULAR PREVENTER CLOSED. | 7206 |  | RIG | 07/26/2022 | SINO-43L | CT | UTMN-4068
2245 | 7206 |  | WCNT | E | 3665 | NA | FLOW CHECK - STATIC LOSSES 2 BPH ............(OOS). | 7206 |  | RIG | 07/26/2022 | SINO-43L | CT | UTMN-4068
2246 | 7206 | 6872 | LOG | E | 3665 | WLT | POSITION STRING FOR SAMPLE#6 AT 6,872' USING STANDARD PROBE (6 OF 10 ) ONGOING ............(OOS).- PUMPED OUT VOL. = 210 LITERS. TOTAL DUMPING IN ANN. = 210 LITERS OIL/ WATER.- MAX STATIONARY 4 HRS FOR , MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6872 | BAW | 07/26/2022 | SINO-43L | LOG | UTMN-4068
2247 | 150.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" & 6-1/8" SECTION WIRELINE LOGGING. | 24 | 3665 | 15 Jul 0045 | 07/26/2022 | SINO-43L | Type | UTMN-4068
2248
2249
2250 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | SND-2007 | Hrs | AWTD-104001
2251 | AINC | SDM | 17 | 26 Jul 1200 - 0500 | 14992 | 900160 | SLB. DIRECTIONAL SEND MANY DOWN LINKS TO ARCHER RSS TROUBLE SHOUTING, BUT FAILED TO BUILD ANGLE AND THE INCLINATION DROP. | DD | BHA |  | 07/26/2022 | SND-2007 | 17 | AWTD-104001
2252 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | SND-2008 | Hrs | HRDH-1812
2253 | STDP | RIG | 329.5 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/26/2022 | SND-2008 | 24 | HRDH-1812
2254 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | SP-103 | Hrs | KRSN-72
2255 | FOT | RIG | 1 | 26 Jul 1100 - 1200 | 5930 | 900106 | REPAIR ON AUTO-DRILL CLUTCH AND DISCONNECTED SAME FROM DRAWWORK | RR | DWKS |  | 07/26/2022 | SP-103 | 1 | KRSN-72
2256 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | SP-121 | Hrs | BRRI-522
2257 | FOT | RIG | 3 | 25 Jul 0330 - 0630 | 4660 | 900155 | FOUND TDS POWER SUPPLY CABLE IN TOP DRIVE HOUSE OVER LOADED. WORK ON REPLACING POWER SUPPLY CABLE. | RR | TDS |  | 07/26/2022 | SP-121 | 1.5 | BRRI-522
2258 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | SSA-102 | Hrs | QTIF-693
2259 | EDIS | RIG | .5 | 26 Jul 1230 - 1300 | 10928 | 900103 | POWER SHUT DOWN DUE TO UNDER-FREQUENCY IN PCR. | RR | PSYS |  | 07/26/2022 | SSA-102 | .5 | QTIF-693
2260 | FOT | RIG | .75 | 26 Jul 1500 - 1545 | 5295 | 900194 | SERVICE TDS, CHANGE GRAPPER DISES. | RR | TDS |  | 07/26/2022 | SSA-303 | .75 | HRDH-2411
2261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | SSA-303 | Hrs | HRDH-2411
2262 | XTRI | RIG | 2.5 | 26 Jul 2200 - 0030 | 5000 | 900109 | EXCESS TIME FOR P/U 5.5'' JOINT FROM RACK. | JF | NA |  | 07/26/2022 | SSA-303 | 2.5 | HRDH-2411
2263 | FOT | RIG | .75 | 26 Jul 1500 - 1545 | 5295 | 900194 | SERVICE TDS, CHANGE GRAPPER DISES. | RR | TDS |  | 07/26/2022 | SSA-303 | .75 | HRDH-2411
2264 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/26/2022 | T218 | Hrs | UTMN-1281
2265 | FOT | HWP | 33 | 25 Jul 1100 - 2000 | 10654 | 900102 | MECHANICAL CUTTER TOOL FAILURE. | TF | WLTT |  | 07/26/2022 | T218 | 15 | UTMN-1281
2266 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | 088TE | Hrs | QTIF-330
2267 | FOT | HCO | 15 | 27 Jul 1400 - 0500 | 7459 | 900184 | ATTEMPT SEVERAL TIMES TO STING IN W/ DUMMY RUN INSIDE THE PBR WITH NO SUCCESS. | TF | STING |  | 07/27/2022 | 088TE | 15 | QTIF-330
2268 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ADC-14 | Hrs | HRDH-1312
2269 | LHFL | RIG | 14.5 | 27 Jul 1430 - 0500 | 930 | 900213 | LEAK OF OIL ON ROTATING LINK ADAPTOR OF TOP DRIVE | RR | HSYS |  | 07/27/2022 | ADC-14 | 14.5 | HRDH-1312
2270 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ADC-31 | Hrs | SDGM-1181
2271 | STDP | RIG | 352.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/27/2022 | ADC-31 | 24 | SDGM-1181
2272 | FOT | MSD | 4.25 | 27 Jul 2315 - 0330 | 1046 | 900201 | AL MASOOD CRT NOT WORKING PROPERLY. | TF | CTRQ |  | 07/27/2022 | ADC-32 | 4.25 | ANDR-1010
2273 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ADC-32 | Hrs | ANDR-1010
2274 | HERR | RIG | 52.25 | 25 Jul 0945 - 1400 | 2689 | 900138 | WHILE L/D 22" DRILLING BHA, TOTCO BAR DROPPED IN HOLE. | JF | TOTCO |  | 07/27/2022 | ADC-32 | 9 | ANDR-1010
2275 | FOT | MSD | 4.25 | 27 Jul 2315 - 0330 | 1046 | 900201 | AL MASOOD CRT NOT WORKING PROPERLY. | TF | CTRQ |  | 07/27/2022 | ADC-32 | 4.25 | ANDR-1010
2276 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ADC-41L | Hrs | SDGM-1244
2277 | UVLC | TK3 | 203 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 07/27/2022 | ADC-41L | 22.5 | SDGM-1244
2278 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ADC-43L | Hrs | UTMN-3118
2279 | FOT | TK3 | 2.5 | 27 Jul 0530 - 2030 | 12036 | 900200 | UNAIBLE TO RELEASE SPIDER SLIPS FROM CASING JOINT. | TF | CSG |  | 07/27/2022 | ADC-43L | 2.5 | UTMN-3118
2280 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ADC-50 | Hrs | SFNY-1176
2281 | LCRW | ARM | 146.75 | 19 Jul 1830 - 0500 | 3911 | 899874 | AFTER KILLING THE WELL AND OPENING THE BOP, OBSERVED PIPE STUCK. | STUK | STRG |  | 07/27/2022 | ADC-50 | 7.75 | SFNY-1176
2282 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ADM-510 | Hrs | ABSF-231
2283 | HERR | GOC | 2.5 | 27 Jul 1730 - 2000 | 0 | 900185 | UNABLE TO EXTEND ALGHAITH BAILS TO REQUIRED POSITION ( TO P/U CASING JOINT DUE TO INCOMPATIBILITY WITH RIG TDS. | JF | CRT |  | 07/27/2022 | ADM-510 | 2.5 | ABSF-231
2284 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ARO-3004 | Hrs | MRJN-2060
2285 | SRVC | HTS | .75 | 27 Jul 0500 - 0545 | 9566 | 900164 | AT PLANNED TIME TO RESUME LIFTING OPERATIONS HES WELL TEST NOT READY | WO | NA |  | 07/27/2022 | ARO-3004 | .75 | MRJN-2060
2286 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ARO-4001 | Hrs | MRJN-532
2287 | STBH | ARM | 70.25 | 25 Jul 0500 - 0500 | 6546 | 900100 | GOT STRING STUCK DUE TO TOTAL LOSSES WHICH LED TO HOLE BACK OFF. | STUK | BHA |  | 07/27/2022 | ARO-4001 | 24 | MRJN-532
2288 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | DQ-49L | Hrs | HRDH-575
2289 | STBH | TK2 | 33 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 07/27/2022 | DQ-49L | 24 | HRDH-575
2290 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ED-85A | Hrs | ZULF-2063
2291 | CFST | BCM | 18.25 | 26 Jul 0145 - 0500 | 11328 | 900111 | CEMENT SET WHILE DISPLACING DV OPENNING PLUG. | CMT | NA |  | 07/27/2022 | ED-85A | 15 | ZULF-2063
2292 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | ENSCO-54 | Hrs | ABSF-17
2293 | STCT | ARM | 471.5 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/27/2022 | ENSCO-54 | 21.5 | ABSF-17
2294 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | HI-2 | Hrs | BRRI-433
2295 | CFFM | ARM | .5 | 27 Jul 2215 - 2245 | 780 | 900216 | LOST TOTAL RETURNS @ 780'. | LCIR | MDCAP |  | 07/27/2022 | HI-2 | .5 | BRRI-433
2296 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | HI-4 | Hrs | BRRI-1001
2297 | PCPF | ARN | 4 | 27 Jul 0100 - 0500 | 223 | 900217 | WHILE RIH 24" 176# X-42 CSG TO 208' (32" CONDUCTOR SHOE), PASS UNTIL 223' AND OBSERVED OBSTRUCTION. | TH | NA |  | 07/27/2022 | HI-4 | 4 | BRRI-1001
2298 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | JACK-202 | Hrs | THRY-829
2299 | OTH | RIG | 24 | 27 Jul 0500 - 0500 | 0 | 900182 | **WAIT FOR SOME CERTIFICATES ON CSG ELEVATORS & DC & CSG SLIPS & BUSHING WITHOUT COC. **INTER-CARAVANE REPAIR AIR PUMP ON ACCUMULATOR. **WAIT TO REPAIR MUD PUMP RELIEF VALVE ENGINE OK. **WAIT TO CHANGE IMPELLER OF CENTRIFUGAL PUMP OF CEMENT TANK. **WAIT TO FIX PASON. **WAIT TO RECEIVE 30" & 24" BUSSHING AND WAIT FOR INSPECTION. | UPRA | NA |  | 07/27/2022 | JACK-202 | 24 | THRY-829
2300 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | MP-4 | Hrs | LWHH-45
2301 | FOT | SPS | 15 | 27 Jul 1400 - 0500 | 3670 | 900183 | AFTER RIH WITH 6-1/8" SPS RSS/MWD/LWD SHALLOW TEST FOUND MWD/LWD LOST SIGNAL TROUBLESHOOTING NO SUCCESS POH TO SURFACE & CHANGE SPS RSS/MWD/LWD ASSY. | BHA | MWD |  | 07/27/2022 | MP-4 | 15 | LWHH-45
2302 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | NA-128S | Hrs | GHZL-112
2303 | FOT | SPS | 27.75 | 26 Jul 2000 - 2345 | 12402 | 900108 | GOT ERROR READING FROM RSS WHILE DRILLING AT 12402' | BHA | RSS |  | 07/27/2022 | NA-128S | 18.75 | GHZL-112
2304 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | NA-207S | Hrs | SHYB-132
2305 | FOT | BHI | .5 | 27 Jul 0500 - 0530 | 12757 | 900212 | LOST COMMUNICATION WITH WELLLINK. | TF | COMP |  | 07/27/2022 | NA-207S | .5 | SHYB-132
2306 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | NBR-210S | Hrs | DILM-100
2307 | FPMP | RIG | 2.5 | 27 Jul 0200 - 0430 | 5750 | 900202 | LEAK IN EXPANTION RUBBER IN SUCTION LINE FOR MUD PUMP NO#2. | RR | MPMP |  | 07/27/2022 | NBR-210S | 2.5 | DILM-100
2308 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | PA-866S | Hrs | SHHB-2
2309 | FOT | SWL | 66.25 | 25 Jul 0845 - 0500 | 13840 | 900115 | UNABLE TO ACTIVATE SATURN PACKER | TF | WLT |  | 07/27/2022 | PA-866S | 22 | SHHB-2
2310 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | PN-9 | Hrs | MRJN-673
2311 | CFST | HCM | 102 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/27/2022 | PN-9 | 24 | MRJN-673
2312 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | SCTD-2 | Hrs | HRDH-2148
2313 | FOT | RIG | 11 | 27 Jul 1500 - 0500 | 12484 | 900199 | POH DUE TO MWD FAILURE | RR | CSYS |  | 07/27/2022 | SCTD-2 | 11 | HRDH-2148
2314 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | SINO-26 | Hrs | UTMN-1231
2315 | SCSG | ARM | 17 | 27 Jul 1200 - 0500 | 7947 | 900215 | GOT STRING 4-1/2" OFF-BTM LINER STUCK WHILE RIH. | STUK | LINR |  | 07/27/2022 | SINO-26 | 17 | UTMN-1231
2316 | 7206 | 6872 | LOG | E | 3665 | WLT | CONT. COLLECTING SAMPLE#6 USING STANDARD PROBE AT 6,872' (6 OF 10). 1 CYCLE.............(OOS).- PUMPED OUT = 251 LITERS, TOTAL DUMPING IN ANN. = 251 LITERS OIL/ WATER.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH | 7206 | 6872 | BAW | 07/27/2022 | SINO-43L | LOG | UTMN-4068
2317 | 7206 | 6859 | LOG | E | 3665 | WLT | POSITION STRING & COLLECTED SAMPLE#7 AT 6859' USING STANDARD PROBE (7 OF 10 ) 1 CYCLE.............(OOS).- PUMPED OUT VOL. = 226 LITERS. TOTAL DUMPING IN ANN. = 477 OIL/ WATER. COLLECT ONE BOTTLE OF SAMPLE .- MAX STATIONARY 4 HRS, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6859 | BAW | 07/27/2022 | SINO-43L | LOG | UTMN-4068
2318 | 7206 | 6859 | LOG | E | 3665 | WLT | POSITION STRING AT 6845' USING STANDARD PROBE. STATION WAS CANCELLED DUE TO LOW MOBILITY.............(OOS).- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6859 | BAW | 07/27/2022 | SINO-43L | LOG | UTMN-4068
2319 | 7206 | 6827 | LOG | E | 3665 | WLT | POSITION STRING & COLLECTED SAMPLE#8 AT 6827' USING STANDARD PROBE (8 OF 9) 1 CYCLE.............(OOS).- PUMPED OUT VOL. = 173 LITERS. TOTAL DUMPING IN ANN. = 650 OIL/ WATER. COLLECT ONE BOTTLE OF SAMPLE .- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6827 | BAW | 07/27/2022 | SINO-43L | LOG | UTMN-4068
2320 | 7206 | 6811 | LOG | E | 3665 | WLT | POSITION STRING & COLLECTED SAMPLE#9 AT 6811' USING STANDARD PROBE (9 OF 9) 1 CYCLE.............(OOS).- PUMPED OUT VOL. = 205 LITERS. TOTAL DUMPING IN ANN. = 855 LITERS OIL/ WATER. COLLECT ONE BOTTLE OF SAMPLE .- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6811 | BAW | 07/27/2022 | SINO-43L | LOG | UTMN-4068
2321 | 7206 | 6943 | LOG | E | 3665 | WLT | MOVED STRING TO PUMP-OUT STATION#1 AT 6943' (1 OF 3) 1 CYCLE.............(OOS).- PUMPED OUT VOL. = 173 LITERS. TOTAL DUMPING IN ANN. = 1028 OIL/ WATER.- MAX STATIONARY 4 HRS, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6943 | BAW | 07/27/2022 | SINO-43L | LOG | UTMN-4068
2322 | 7206 | 6890 | LOG | E | 3665 | WLT | POSITION STRING AT PUMP-OUT STATION#2 AT 6890' (2 OF 3) ON GOING .............(OOS).- PUMPED OUT VOL. = 145 LITERS. TOTAL DUMPING IN ANN. = 1173 OIL/ WATER.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6890 | BAW | 07/27/2022 | SINO-43L | LOG | UTMN-4068
2323 | 174.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" & 6-1/8" SECTION WIRELINE LOGGING. | 24 | 3665 | 15 Jul 0045 | 07/27/2022 | SINO-43L | Type | UTMN-4068
2324
2325
2326 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | SINO-5L | Hrs | UTMN-1029
2327 | FOT | HWP | 12 | 27 Jul 1700 - 0500 | 11450 | 900186 | LOST SIGNAL FROM XRMI-IMAGE TOOLS. | TF | WLT |  | 07/27/2022 | SINO-5L | 12 | UTMN-1029
2328 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | SND-2007 | Hrs | AWTD-104001
2329 | AINC | SDM | 36 | 26 Jul 1200 - 0000 | 14992 | 900160 | SLB/ARCHER FAILED TO BUILD ANGLE | DD | BHA |  | 07/27/2022 | SND-2007 | 19 | AWTD-104001
2330 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | SND-2008 | Hrs | HRDH-1812
2331 | STDP | RIG | 353.5 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/27/2022 | SND-2008 | 24 | HRDH-1812
2332 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | SSA-101 | Hrs | QTIF-785
2333 | FOT | ARN | 3.25 | 27 Jul 1330 - 1645 | 20545 | 900214 | V-SAT TECHNICIAN REPLACE MODEM AND TROUBLE SHOOT W/ V-SAT | TF | VSAT |  | 07/27/2022 | SSA-101 | 3.25 | QTIF-785
2334 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | SSA-5917 | Hrs | HRDH-2201
2335 | HERR | RIG | 10.5 | 27 Jul 0730 - 1800 | 10910 | 900233 | L/D BELL NIPPLE TO SURFACE OPEN 2 SHACKELS FROM THE BELL NILLPLE AND MAKE UP ON THE AIR WINCHE WIRE , ONE SHACKEL NO GOOD TIGHT BOLT , POOH AIR WINCHE WIRE ACROSS ROTARY TABLE ONE SHACKEL DROP IN THE WELL WITH OUT PIN. > SHACKEL: 4.5"X3"X5/8". | JF | RSSS |  | 07/27/2022 | SSA-5917 | 10.5 | HRDH-2201
2336 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | SSA-5964 | Hrs | HRDH-916
2337 | HINW | HWP | 8.5 | 27 Jul 2030 - 0500 | 11700 | 900232 | HALL WL 3.59" DPU3-MECHANICAL PUNCHER TOOL STUCK INSIDE 4.5" TBG PBR SEAL UNIT 3.72" ID WORKED ON STUCK WL TOOL. | STUK | WLT |  | 07/27/2022 | SSA-5964 | 8.5 | HRDH-916
2338 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | T217 | Hrs | UTMN-306
2339 | XTTE | HCT | 2 | 27 Jul 2200 - 0000 | 7700 | 900187 | EXCESSIVE TIME TO NU & P/T RCD TOOL. | TF | RCD |  | 07/27/2022 | T217 | 2 | UTMN-306
2340 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | T907 | Hrs | SRYN-1
2341 | HERR | GOC | 27 | 26 Jul 0200 - 0500 | 10000 | 900197 | WHEN ATTEMPTING TO DO FINAL DRIFT BEFORE SETTING UPPER COMPLETION PACKER, FOUND DRIFT WOULD NOT PASS. | TF | TTRQ |  | 07/27/2022 | T907 | 24 | SRYN-1
2342 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/27/2022 | WCL-83 | Hrs | MRJN-834
2343 | FOT | BCT | 4 | 27 Jul 1400 - 1800 | 2000 | 900198 | BAKER N2 PUMP STARTER MALFUNCTION WHILE RIH WITH BAKER C/T. | TF | CTPMP |  | 07/27/2022 | WCL-83 | 4 | MRJN-834
2344 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | 088TE | Hrs | QTIF-330
2345 | FOT | HCO | 24.5 | 27 Jul 1400 - 1500 | 7459 | 900184 | ATTEMPT SEVERAL TIMES TO STING IN W/ DUMMY RUN INSIDE THE PBR WITH NO SUCCESS. | TF | STING |  | 07/28/2022 | 088TE | 9.5 | QTIF-330
2346 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ADC-14 | Hrs | HRDH-1312
2347 | LHFL | RIG | 18.75 | 27 Jul 1430 - 0915 | 930 | 900213 | LEAK OF OIL ON ROTATING LINK ADAPTOR OF TOP DRIVE | RR | HSYS |  | 07/28/2022 | ADC-14 | 4.25 | HRDH-1312
2348 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ADC-23 | Hrs | KIDN-23
2349 | FOT | RIG | 2.5 | 28 Jul 0230 - 0500 | 14440 | 900274 | WACHITA BRAKE NOT ENGAIGING | RR | DWKS |  | 07/28/2022 | ADC-23 | 2.5 | KIDN-23
2350 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ADC-31 | Hrs | SDGM-1181
2351 | STDP | RIG | 376.25 | 12 Jul 1930 - 0500 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/28/2022 | ADC-31 | 24 | SDGM-1181
2352 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ADC-48 | Hrs | HRDH-2316
2353 | FOT | RIG | 7.25 | 28 Jul 2145 - 0500 | 4111 | 900255 | TDS SOLONOID MANIFOLD DAMAGE. | RR | TDS |  | 07/28/2022 | ADC-48 | 7.25 | HRDH-2316
2354 | FPMP | RIG | 7 | 28 Jul 0900 - 1600 | 1456 | 900236 | PRESSURE TESTED SURFACE LINE PRIOR TO DRILL CMT, FOUND MUD PUMP ISOLATION VALVE LEAKING. FIXED SAME. | RR | MPMP |  | 07/28/2022 | ADC-50 | 7 | SFNY-1176
2355 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ADC-50 | Hrs | SFNY-1176
2356 | LCRW | ARM | 163.75 | 19 Jul 1830 - 0500 | 3911 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 07/28/2022 | ADC-50 | 17 | SFNY-1176
2357 | FPMP | RIG | 7 | 28 Jul 0900 - 1600 | 1456 | 900236 | PRESSURE TESTED SURFACE LINE PRIOR TO DRILL CMT, FOUND MUD PUMP ISOLATION VALVE LEAKING. FIXED SAME. | RR | MPMP |  | 07/28/2022 | ADC-50 | 7 | SFNY-1176
2358 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ADES-157 | Hrs | HRDH-642
2359 | FOT | ITS | 5.5 | 28 Jul 2230 - 0400 | 9100 | 900239 | DIES CARRIER (DIES FRAME) ON ITS POWER TONG BROKEN. WAIT FOR ANOTHER SET FROM ITS YARD. - CONT POOH USING RIG TONG | TF | CTRQ |  | 07/28/2022 | ADES-157 | 5.5 | HRDH-642
2360 | GRF | RIG | 11.5 | 28 Jul 0730 - 1900 | 5600 | 900238 | FAILURE OF DEEP WELL PUMP AT PORT SIDE AND STBD SIDE, INSTALLED NEW DEEP WELL PUMP ON PORT SIDE. ** STBD DEEP WELL PUMP STILL OUT OF SERVICE | UPRA | RSSS |  | 07/28/2022 | ARO-4001 | 11.5 | MRJN-532
2361 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ARO-4001 | Hrs | MRJN-532
2362 | STBH | ARM | 75.5 | 25 Jul 0500 - 2145 | 6546 | 900100 | GOT STRING STUCK DUE TO TOTAL LOSSES WHICH LED TO HOLE BACK OFF. | STUK | BHA |  | 07/28/2022 | ARO-4001 | 5.25 | MRJN-532
2363 | CPNF | HCM | 7.25 | 28 Jul 2145 - 0500 | 6210 | 900222 | FAILURE OF HALLIBURTON CEMENT PLUG, UNABLE TO TAG HARD CMT. | CMT | NA |  | 07/28/2022 | ARO-4001 | 7.25 | MRJN-532
2364 | GRF | RIG | 11.5 | 28 Jul 0730 - 1900 | 5600 | 900238 | FAILURE OF DEEP WELL PUMP AT PORT SIDE AND STBD SIDE, INSTALLED NEW DEEP WELL PUMP ON PORT SIDE. ** STBD DEEP WELL PUMP STILL OUT OF SERVICE | UPRA | RSSS |  | 07/28/2022 | ARO-4001 | 11.5 | MRJN-532
2365 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | DPS-45 | Hrs | UTMN-2331
2366 | FOT | WUD | 3.5 | 28 Jul 1730 - 2100 | 11025 | 900277 | WFD BEARING PACKER ELEMENT FAILED. STRIPPED OUT TO LAST CSG SHOE TO CHANGE SAME. | BOP | RCD |  | 07/28/2022 | DPS-45 | 3.5 | UTMN-2331
2367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | DQ-49L | Hrs | HRDH-575
2368 | STBH | TK2 | 57 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 07/28/2022 | DQ-49L | 24 | HRDH-575
2369 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ED-85A | Hrs | ZULF-2063
2370 | CFST | BCM | 42.25 | 26 Jul 0145 - 0500 | 11328 | 900111 | CEMENT SET WHILE DISPLACING DV OPENNING PLUG. | CMT | NA |  | 07/28/2022 | ED-85A | 24 | ZULF-2063
2371 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ENSCO-54 | Hrs | ABSF-17
2372 | STCT | ARM | 495.5 | 06 Jul 2300 - 0500 | 9465 | 899310 | WHILE RIH WITH LOWER COMPLETION , STRG GOT DIFFERENTIALLY STUCK. | STUK | EQLZR |  | 07/28/2022 | ENSCO-54 | 24 | ABSF-17
2373 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | ENSCO-76 | Hrs | MRJN-853
2374 | FPMP | RIG | 4.5 | 28 Jul 1530 - 2000 | 7732 | 900256 | WHILE SETTING BOT LINER HANGER @ 6526' PRESSURE WAS INCREASED TO 3500 PSI W/ RIG PUMP TO BLOW BALL SEAT WHEN POP OFF VALVE ON #2 MUD PUMP FAILED CONTAMINATING SLB MUD PUSH SPACER IN MUD PIT. PO SETTING SHOULD HAVE BEEN 5000 PSI. | RR | MPMP |  | 07/28/2022 | ENSCO-76 | 4.5 | MRJN-853
2375 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | HI-4 | Hrs | BRRI-1001
2376 | PCPF | ARN | 28 | 27 Jul 0100 - 0500 | 223 | 900217 | WHILE RIH 24" 176# X-42 CSG TO 208' (32" CONDUCTOR SHOE), PASS UNTIL 223' AND OBSERVED OBSTRUCTION. | TH | NA |  | 07/28/2022 | HI-4 | 24 | BRRI-1001
2377 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | JACK-202 | Hrs | THRY-829
2378 | FOT | RIG | .5 | 28 Jul 0430 - 0500 | 42 | 900284 | WAIT TO FIX CELLAR PUMP, PLUGGED. | RR | CSYS |  | 07/28/2022 | JACK-202 | .5 | THRY-829
2379 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | NBR-196S | Hrs | SDGM-1235
2380 | FOT | SPS | 3.5 | 28 Jul 1400 - 1845 | 13588 | 900235 | WHILE DRILLING AT 13,588 FT/MD SPERRY SUN LOST MWD/GR TOOL SIGNAL. PULSER STOP PULSING. | BHA | MWD |  | 07/28/2022 | NBR-196S | 3.5 | SDGM-1235
2381 | UVLC | ARM | 6.5 | 28 Jul 0500 - 1130 | 14068 | 900254 | WHILE CIRC @ BTM, HAD 70 BPH LOSSES @ 150 GPM THEN NO RETURN. | LCIR | NA |  | 07/28/2022 | NBR-263S | 6.5 | QTIF-736
2382 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | NBR-263S | Hrs | QTIF-736
2383 | WC20 | ARM | 17.25 | 28 Jul 1130 - 0445 | 14068 | 900253 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 07/28/2022 | NBR-263S | 17.25 | QTIF-736
2384 | UVLC | ARM | 6.5 | 28 Jul 0500 - 1130 | 14068 | 900254 | WHILE CIRC @ BTM, HAD 70 BPH LOSSES @ 150 GPM THEN NO RETURN. | LCIR | NA |  | 07/28/2022 | NBR-263S | 6.5 | QTIF-736
2385 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | NBR-654S | Hrs | HRDH-1150
2386 | FOT | HWP | 2.25 | 28 Jul 0245 - 0500 | 12803 | 900275 | HIGH CURRENT ON WL INSTRUMENTS - LOST COMMUNICATION WITH TOOLS. | TF | WLT |  | 07/28/2022 | NBR-654S | 2.25 | HRDH-1150
2387 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | PA-866S | Hrs | SHHB-2
2388 | FOT | SWL | 90.25 | 25 Jul 0845 - 0500 | 13840 | 900115 | UNABLE TO ACTIVATE SATURN PACKER | TF | WLT |  | 07/28/2022 | PA-866S | 24 | SHHB-2
2389 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | PN-9 | Hrs | MRJN-673
2390 | CFST | HCM | 126 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/28/2022 | PN-9 | 24 | MRJN-673
2391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SCTD-2 | Hrs | HRDH-2148
2392 | FOT | RIG | 13.5 | 27 Jul 1500 - 0730 | 12484 | 900199 | HAD FAULTY READING FROM PRESSURE SENSORS | BHA | MMOT |  | 07/28/2022 | SCTD-2 | 2.5 | HRDH-2148
2393 | FOT | HUD | 8 | 28 Jul 0600 - 1400 | 7947 | 900223 | OBSERVED HALL MPD BEARING ASSY STARTED SLIGHT LEAK FROM THE CLAMP. | TF | MPD |  | 07/28/2022 | SINO-26 | 8 | UTMN-1231
2394 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SINO-26 | Hrs | UTMN-1231
2395 | SCSG | ARM | 33 | 27 Jul 1200 - 0500 | 7947 | 900215 | GOT STRING 4-1/2" OFF-BTM LINER STUCK WHILE RIH. | STUK | LINR |  | 07/28/2022 | SINO-26 | 16 | UTMN-1231
2396 | FOT | HUD | 8 | 28 Jul 0600 - 1400 | 7947 | 900223 | OBSERVED HALL MPD BEARING ASSY STARTED SLIGHT LEAK FROM THE CLAMP. | TF | MPD |  | 07/28/2022 | SINO-26 | 8 | UTMN-1231
2397 | 7206 | 6890 | LOG | E | 3665 | WLT | CONT. PUMP-OUT STATION#2 AT 6890' (2 OF 3) ON GOING .............(OOS).- PUMPED OUT VOL. = 216 LITERS. TOTAL DUMPING IN ANN. = 1244 LIT. OIL/ WATER.- MAX STATIONARY 4 HRS, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6890 | BAW | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2398 | 7206 | 6880 | LOG | E | 3665 | WLT | POSITION STRING & COLLECTED SAMPLE#10 AT 6880' USING STANDARD PROBE (10 OF 10) 1 CYCLE.............(OOS).- PUMPED OUT VOL. = 310 LITERS. TOTAL DUMPING IN ANN. = 1554 LITERS , COLLECTED ONE BOTTLE OF SAMPLE .- MAX STATIONARY 4 HRS, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 6880 | BAW | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2399 | 7206 | 7004 | LOG | E | 3665 | WLT | MOVED STRING TO PUMP-OUT STATION#3 AT 7004' (3 OF 3) 1 CYCLE.............(OOS).- PUMPED OUT VOL. = 237 LITERS. TOTAL DUMPING IN ANN. = 1791 OIL/ WATER.- MAX STATIONARY 4 HRS, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE UP & DOWN.- MONITOR HOLE ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 7004 | BAW | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2400 | 7206 | 7148 | ST | E | 3665 | STDP | RIH W/ BKR LOGGING TOOLS AT CONTROLLED SPEED F/ 7,004' T/ 7,148'. ...........(OOS). | 7206 | 7004 | RIG | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2401 | 7206 |  | CIRC | E | 3665 | MPMP | CIRC. 1.5 X BTM-UP & CONDITION MUD IN & OUT = 64 PCF [250 GPM & 330 PSI ].............(OOS).- PRECAUTIONARY CIRCULATE THROUGH FULL OPEN CHOKE TO MGS W/ ANNULAR PREVENTER CLOSED. | 7206 |  | RIG | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2402 | 7206 |  | WCNT | E | 3665 | NA | FLOW CHECK, STATIC LOSSES - 2 BPH. | 7206 |  | RIG | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2403 | 7206 | 6518 | ST | E | 3665 | STDP | POOH W/ BKR LOGGING RUN#3 TO SES DEPTH AT 6518'. | 7206 | 7148 | RIG | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2404 | 7206 |  | OTH | E | 3665 | NA | UNLATCH & POOH CABLE TO SURFACE. L/D CABLE, SHEAVES AND SES. | 7206 |  | BAW | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2405 | 7206 | 156 | ST | E | 3665 | STDP | POOH W/ BKR LOGGING RUN#3 [RCX - GR] TOOL F/6518' TO TOP OF BHA AT 156'.- FLOW CHECK AT TOP OF BHA - 2 BPH STATIC LOSSES. | 7206 | 6518 | RIG | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2406 | 7206 |  | OTH | E | 3665 | NA | HPJSM. L/D BKR LOGGING TOOLS RUN#3 [RCX - GR]...ONGOING. | 7206 |  | BAW | 07/28/2022 | SINO-43L | LOG | UTMN-4068
2407 | 176.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" & 6-1/8" SECTION WIRELINE LOGGING. | 24 | 3665 | 15 Jul 0045 | 07/28/2022 | SINO-43L | Type | UTMN-4068
2408
2409
2410 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SINO-5L | Hrs | UTMN-1029
2411 | FOT | HWP | 28 | 27 Jul 1700 - 0000 | 11450 | 900186 | LOST SIGNAL FROM XRMI-IMAGE TOOLS. | TF | WLT |  | 07/28/2022 | SINO-5L | 16 | UTMN-1029
2412 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SND-1502 | Hrs | HRDH-124
2413 | FOT | WDS | 19 | 28 Jul 1000 - 0500 | 7515 | 900220 | WFD LWD TOOL FAILURE | BHA | LWD |  | 07/28/2022 | SND-1502 | 19 | HRDH-124
2414 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SND-2007 | Hrs | AWTD-104001
2415 | AINC | SDM | 24 | 28 Jul 0500 - 0500 | 15045 | 900276 | SCHL. ARCHER RSS FAILED TO BUILD THE ANGLE | DD | BHA |  | 07/28/2022 | SND-2007 | 24 | AWTD-104001
2416 | FOT | BHI | 1 | 28 Jul 0400 - 0500 | 6065 | 900285 | BHI ATTEMPT TO CONTINUE DRILLING BUT COULD NOT DUE TO NO MOTOR DIFFERENTIAL PRESSURE OBSERVED WITH UP TO 50 KLBS WOB. | BHA | MMOT |  | 07/28/2022 | SP-120 | 1 | MNIF-187
2417 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SP-120 | Hrs | MNIF-187
2418 | FOT | RIG | 3 | 28 Jul 1230 - 1530 | 5764 | 900221 | TROUBLESHOOT POWER LOSS FROM DRAWWORKS AND MUD PUMPS. | RR | PSYS |  | 07/28/2022 | SP-120 | 3 | MNIF-187
2419 | FOT | BHI | 1 | 28 Jul 0400 - 0500 | 6065 | 900285 | BHI ATTEMPT TO CONTINUE DRILLING BUT COULD NOT DUE TO NO MOTOR DIFFERENTIAL PRESSURE OBSERVED WITH UP TO 50 KLBS WOB. | BHA | MMOT |  | 07/28/2022 | SP-120 | 1 | MNIF-187
2420 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SP-306 | Hrs | MNIF-193
2421 | XCIR | ARM | 6.5 | 28 Jul 0830 - 1500 | 16564 | 900237 | SUSPECTED MUD NOT HOMOGENEOUS | MUD | NA |  | 07/28/2022 | SP-306 | 6.5 | MNIF-193
2422 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SP-58 | Hrs | HRDH-795
2423 | XTRI | RIG | 1.5 | 28 Jul 2330 - 0100 | 3990 | 900272 | EXCESSIVE TIME TO SLIP AND CUT DRILLING LINE. | JF | NA |  | 07/28/2022 | SP-58 | 1.5 | HRDH-795
2424 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SSA-102 | Hrs | QTIF-693
2425 | FOT | SPS | 4.5 | 28 Jul 1000 - 1430 | 0 | 900190 | NO SIGNAL WHILE SHALLOW TEST MWD. | BHA | MWD |  | 07/28/2022 | SSA-102 | 4.5 | QTIF-693
2426 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SSA-5891 | Hrs | HRDH-1205
2427 | FOT | WCR | .75 | 28 Jul 0345 - 0430 | 9800 | 900286 | WEATHERFORD CHANGE DIESEL POWER UNIT BECAUSE OF LEAK IN DIESEL FUEL LINE. | TF | CTRQ |  | 07/28/2022 | SSA-5891 | .75 | HRDH-1205
2428 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SSA-5964 | Hrs | HRDH-916
2429 | HINW | HWP | 32.5 | 27 Jul 2030 - 0500 | 11700 | 900232 | HALL WL 3.59" DPU3-MECHANICAL PUNCHER TOOL STUCK INSIDE 4.5" TBG PBR SEAL UNIT 3.72" ID WORKED ON STUCK WL TOOL. NOT FREE, PULLED CABLE, PLANNED TO RUN 1-11/16" EXPLOSIVE PUNCHER TOOL. | STUK | WLT |  | 07/28/2022 | SSA-5964 | 24 | HRDH-916
2430 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | SSA-5970 | Hrs | UTMN-2340
2431 | FOT | GOC | 3.5 | 28 Jul 0930 - 1300 | 3785 | 900234 | TROUBLE SHOOT ON JAM UNIT SIGNAL TRANSMISSION. | TF | CTRQ |  | 07/28/2022 | SSA-5970 | 3.5 | UTMN-2340
2432 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | T907 | Hrs | SRYN-1
2433 | HERR | GOC | 31 | 26 Jul 0200 - 0900 | 10000 | 900197 | WHEN ATTEMPTING TO DO FINAL DRIFT BEFORE SETTING UPPER COMPLETION PACKER, FOUND DRIFT WOULD NOT PASS. | TF | TTRQ |  | 07/28/2022 | T907 | 4 | SRYN-1
2434 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/28/2022 | WCL-83 | Hrs | MRJN-834
2435 | FOT | BCT | 4 | 28 Jul 1200 - 1600 | 6800 | 900191 | BAKER BOOSTER PUMP OF N2 PUMP BROKEN WHILE LIFTING THE WELL WITH N2. | TF | CTPMP |  | 07/28/2022 | WCL-83 | 4 | MRJN-834
2436 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADC-16 | Hrs | JAHM-6
2437 | WOTR | SWF | 22 | 29 Jul 0500 - 0300 | 11690 | 900241 | WAIT ON SLB CO2 SUPPLY. | WO | NA |  | 07/29/2022 | ADC-16 | 22 | JAHM-6
2438 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADC-17 | Hrs | ZULF-1217
2439 | WTHR | ARM | 2.75 | 29 Jul 1515 - 1800 | 0 | 900243 | HIGH WIND SPEED AND FLARE IS NOT STABLE, WAIT ON WEATHER | WON | NA |  | 07/29/2022 | ADC-17 | 2.75 | ZULF-1217
2440 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADC-23 | Hrs | KIDN-23
2441 | FOT | RIG | 7 | 28 Jul 0230 - 0930 | 14440 | 900274 | WACHITA BRAKE NOT ENGAIGING | RR | DWKS |  | 07/29/2022 | ADC-23 | 4.5 | KIDN-23
2442 | FOT | SDM | 2 | 29 Jul 0300 - 0500 | 14232 | 900246 | UNABL TO CONTIONUE DRILLING WITH MP# 1 AND MP# 2 AS WE HAVE A NOISEY SIGNAL FROM SLB MWD. | BHA | MWD |  | 07/29/2022 | ADC-31 | 2 | SDGM-1181
2443 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADC-31 | Hrs | SDGM-1181
2444 | STDP | RIG | 398.25 | 12 Jul 1930 - 0300 | 15900 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/29/2022 | ADC-31 | 22 | SDGM-1181
2445 | FOT | SDM | 2 | 29 Jul 0300 - 0500 | 14232 | 900246 | UNABL TO CONTIONUE DRILLING WITH MP# 1 AND MP# 2 AS WE HAVE A NOISEY SIGNAL FROM SLB MWD. | BHA | MWD |  | 07/29/2022 | ADC-31 | 2 | SDGM-1181
2446 | UVLC | ARM | 22.5 | 28 Jul 0115 - 0500 | 9010 | 900290 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 07/29/2022 | ADC-41L | 18.75 | SDGM-1244
2447 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADC-41L | Hrs | SDGM-1244
2448 | UVLC | ARM | 5.25 | 29 Jul 1045 - 1600 | 4466 | 900230 | DUE TO PLUGGING OF MOST OF DP STRG ON DERRICK AND TOOK MUCH TIME FOR CLEANING. | LCIR | NA |  | 07/29/2022 | ADC-41L | 5.25 | SDGM-1244
2449 | UVLC | ARM | 22.5 | 28 Jul 0115 - 0500 | 9010 | 900290 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 07/29/2022 | ADC-41L | 18.75 | SDGM-1244
2450 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADC-48 | Hrs | HRDH-2316
2451 | FOT | RIG | 31.25 | 28 Jul 2145 - 0500 | 4111 | 900255 | WHILE RIH 12" BHA W/5-1/2" DP SINGLE , TDS HIT DP CAUSING BEND DP & DAMAGE TO TDS HYD MANIFOLD, SUSPECND OPER FOR INVESTIGATION, MEANWHILE ARRANGE HTDRAULIC MANIFOLD FROM ADC STORE | RR | TDS |  | 07/29/2022 | ADC-48 | 24 | HRDH-2316
2452 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADC-52 | Hrs | SDGM-1185
2453 | HINW | BAW | 16 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 07/29/2022 | ADC-52 | 16 | SDGM-1185
2454 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADC-64L | Hrs | UTMN-3074
2455 | FOT | TK3 | 17.5 | 29 Jul 1130 - 0500 | 0 | 900263 | WHILE RIH WITH UPPER COMPLETION , THE PIN OF STABBING GUIDE GOT LOST ,SEARCH FOR IT NO SUCESS ,POH COMPLETION STRING , RIH WITH C/O BHA TO MILL IT | TF | TBG |  | 07/29/2022 | ADC-64L | 17.5 | UTMN-3074
2456 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ADES-798 | Hrs | HRDH-2302
2457 | FOT | BCR | 3 | 29 Jul 1415 - 1715 | 6360 | 900312 | BAKER POWER TONG GEAR BROKE DOWN, REPLACE SAME WITH BACKUP EQPT, UNABLE TO READ TORQUE ON JAM UNIT. | TF | CTRQ |  | 07/29/2022 | ADES-798 | 3 | HRDH-2302
2458 | LHFL | RIG | 1 | 29 Jul 1845 - 1945 | 5826 | 900244 | FOUND LEAKS ON TDS COOLING WATER LINE, REPLACE WITH NEW HOSE. | RR | HSYS | 900222 | 07/29/2022 | ARO-4001 | 1 | MRJN-532
2459 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ARO-4001 | Hrs | MRJN-532
2460 | CPNF | HCM | 31.25 | 28 Jul 2145 - 0500 | 6210 | 900222 | FAILURE OF HALLIBURTON CEMENT PLUG, UNABLE TO TAG HARD CMT. | CMT | NA |  | 07/29/2022 | ARO-4001 | 23 | MRJN-532
2461 | LHFL | RIG | 1 | 29 Jul 1845 - 1945 | 5826 | 900244 | FOUND LEAKS ON TDS COOLING WATER LINE, REPLACE WITH NEW HOSE. | RR | HSYS | 900222 | 07/29/2022 | ARO-4001 | 1 | MRJN-532
2462 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | DQ-47 | Hrs | KHRS-280
2463 | PCPF | TK2 | 9.5 | 29 Jul 1715 - 0245 | 78 | 900264 | HAD TIGHT HOLE WHILE RIH W/ 24" CSG AT 78', HAD TO PERFORM REAMING TRIPS TILL PASSED FREE AFTER TWO TRIPS. | TH | NA |  | 07/29/2022 | DQ-47 | 9.5 | KHRS-280
2464 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | DQ-49L | Hrs | HRDH-575
2465 | STBH | TK2 | 81 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 07/29/2022 | DQ-49L | 24 | HRDH-575
2466 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | ED-85A | Hrs | ZULF-2063
2467 | CFST | BCM | 53 | 26 Jul 0145 - 1545 | 11328 | 900111 | CEMENT SET WHILE DISPLACING DV OPENNING PLUG. | CMT | NA |  | 07/29/2022 | ED-85A | 10.75 | ZULF-2063
2468 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | HI-4 | Hrs | BRRI-1001
2469 | PCPF | ARN | 29 | 27 Jul 0100 - 0600 | 223 | 900217 | WHILE RIH 24" 176# X-42 CSG TO 208' (32" CONDUCTOR SHOE), PASS UNTIL 223' AND OBSERVED OBSTRUCTION. | TH | NA |  | 07/29/2022 | HI-4 | 1 | BRRI-1001
2470 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | JACK-202 | Hrs | THRY-829
2471 | FOT | RIG | 3 | 29 Jul 1600 - 1900 | 81 | 900258 | WAIT TO FIX CELLAR PUMP | RR | CSYS |  | 07/29/2022 | JACK-202 | 3 | THRY-829
2472 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | NA-128S | Hrs | GHZL-112
2473 | FOT | SPS | 21.5 | 29 Jul 0730 - 0500 | 12866 | 900314 | WHILE ATTEMPTING TO TAKE SURVEY, MWD TOOL LOST COMMUNICATION WITH ITS LOWER COMPONENTS. | BHA | MWD |  | 07/29/2022 | NA-128S | 21.5 | GHZL-112
2474 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | NBR-20S | Hrs | HMYM-433502
2475 | FOT | RIG | 1.5 | 29 Jul 1900 - 2030 | 440 | 900262 | LEAK ON DIVERTER CONNECTION | BOP | DVRT |  | 07/29/2022 | NBR-20S | 1.5 | HMYM-433502
2476 | STBH | ARM | 2.5 | 29 Jul 0230 - 0500 | 13944 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 07/29/2022 | NBR-263S | 2.5 | QTIF-736
2477 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | NBR-263S | Hrs | QTIF-736
2478 | WC20 | ARM | 39 | 28 Jul 1130 - 0230 | 14068 | 900253 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 07/29/2022 | NBR-263S | 21.5 | QTIF-736
2479 | STBH | ARM | 2.5 | 29 Jul 0230 - 0500 | 13944 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 07/29/2022 | NBR-263S | 2.5 | QTIF-736
2480 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | NBR-654S | Hrs | HRDH-1150
2481 | FOT | HWP | 26.25 | 28 Jul 0245 - 0500 | 12803 | 900275 | HIGH CURRENT ON WL INSTRUMENTS - LOST COMMUNICATION WITH TOOLS. | TF | WLT |  | 07/29/2022 | NBR-654S | 24 | HRDH-1150
2482 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | PN-9 | Hrs | MRJN-673
2483 | CFST | HCM | 150 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/29/2022 | PN-9 | 24 | MRJN-673
2484 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SCTD-1 | Hrs | SDGM-1034
2485 | FOT | RIG | 14 | 29 Jul 1500 - 0500 | 13000 | 900231 | POOH DUE TO DTF (TELEMETRY). | BHA | MMOT |  | 07/29/2022 | SCTD-1 | 14 | SDGM-1034
2486 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SINO-22 | Hrs | BRRI-579
2487 | IDCS | ARN | 33 | 28 Jul 2000 - 0500 | 16000 | 900227 | GOC FAILED TO PICK UP LINER POINT AND SET 7" LINER SHALLOWER THAN THE TARGETED ZONE (ZONE 4 ARAB-D RES.). RUN 4-1/2" ISOLATION KIT. | WI | NA |  | 07/29/2022 | SINO-22 | 24 | BRRI-579
2488 | 7206 |  | OTH | E | 3665 | NA | CONT. L/D BKR LOGGING TOOLS RUN#3 [RCX - GR]. | 7206 |  | BAW | 07/29/2022 | SINO-43L | LOG | UTMN-4068
2489 | 7206 |  | RTRV | C |  | WBSH | RETRIEVE 11" CAMERON WEAR BUSHING. | 7206 |  | RIG | 07/29/2022 | SINO-43L | WH | UTMN-4068
2490 | 7206 |  | OTH | C |  | BOP | HPJSM. P/U BOP JETTING ASSY (8-1/2" SURFACE JUNK CATCHER + 1 X 5'' DP + BOP JETTING TOOL + X/O + 2 X 5" DP).- JET BOP & THS, FUNCTION PIPE RAMS, L/D JETTING ASSY. | 7206 |  | RIG | 07/29/2022 | SINO-43L | BOP | UTMN-4068
2491 | 7206 |  | SET | C |  | WBSH | INSTALL 11" CAMERON WEAR BUSHING. | 7206 |  | RIG | 07/29/2022 | SINO-43L | WH | UTMN-4068
2492 | 7206 |  | HT | C |  | BHA | HPJSM. P/U, M/U & RIH W/ 6-1/8" REAMING/7" C/O BHA TO 778'.(6-1/8" WELDED CONE BIT + 6-1/8" NBRR + 4-3/4" DC + 6-1/8" STRR + 4-3/4"DC + 6-1/8" STRR +4-3/4"DC+ XO + 1 STD * 4" HWDP + 4-3/4" JAR + 2 STD * 4" HWDP+ 3 STD * 4" DP+7" SCRAPER + 7" BRUSH + 2 * 7" STRING MAGNETS + FILTER + 2 * 7" STRING MAGNETS). | 7206 |  | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2493 | 7206 | 6750 | TI | C |  | STDP | CONT. RIH W/ COMBINED 6-1/8'' REAMING / 7'' CLEAN OUT BHA ON 4"/5" DP STDS F/ 778' T/ 6750'.- CONNECT TDS AND PASS TOL FREELY @ 2214'.- MONITOR WELL ON TRIP TANK, STATIC LOSSES - 2 BPH. | 7206 | 778 | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2494 | 7206 |  | CIRC | C |  | MPMP | CUMULATIVE TIME TO FILL STRG. WHILE RIH. | 7206 |  | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2495 | 7206 | 7206 | ST | C |  | STDP | CONT. RIH ON ELEVATOR W/ COMBINED 6-1/8" REAMING / 7" C/O BHA F/ 6750' TO BTM @ 7206'.- HOLE IN GOOD CONDITION.- SCRAP UPPER COMPLETION PACKER PLANNED DEPTH F/ 6100' TO 6300'.- SCRAP LOWER COMPLETION 5" SLZX LINER TOP PACKER PLANNED DEPTH F/ 6350' TO 6500'. | 7206 | 6750 | RIG | 07/29/2022 | SINO-43L | SUSP | UTMN-4068
2496 | 7206 |  | CIRC | C |  | MPMP | SWEEP HOLE TWICE W/ 20 HI-VIS PILL & CHC.-SPOT 40 BBL LUBRICANT PILL WITH 3 % LUBRICANT & 6 PPB LUBRAGLIDE ON BOTTOM.-DYNAMIC LOSSES +/- 5 BPH. | 7206 |  | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2497 | 7206 |  | WCNT | C |  | NA | FLOW CHECK, STATIC LOSSES - 1.3 BPH. | 7206 |  | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2498 | 7206 | 6777 | ST | C |  | STDP | POOH W/ COMBINED 6-1/8" REAMING & 7" C/O BHA TO 7" LINER SHOE @ 6777'.- MONITOR WELL ON TRIP TANK.- HOLE IN GOOD CONDITION. | 7206 | 7206 | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2499 | 7206 |  | WCNT | C |  | NA | FLOW CHECK, STATIC LOSSES - 1.3 BPH. | 7206 |  | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2500 | 7206 | 778 | TO | C |  | STDP | POOH W/ 6-1/8" REAMING/7" C/O BHA F/ 6777' TO TOP OF BHA @ 778'.- MONITOR WELL ON TRIP TANK. | 7206 | 6777 | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2501 | 7206 |  | WCNT | C |  | NA | FLOW CHECK, STATIC LOSSES - 1.3 BPH. | 7206 |  | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2502 | 7206 |  | HT | C |  | BHA | POOH W/ 6-1/8" REAMING/7" C/O BHA TO SURFACE & L/D SAME.- L/D SCRAPER , BRUSH , 4 * 7" STRING MAGNETS & FILTER , 4 3/4" JAR , 2* 6 1/8" STRR, 6 1/8" NBRR & 6 1/8" BIT.- CHECK MAGNETS- ARE CLEAN. | 7206 |  | RIG | 07/29/2022 | SINO-43L | CT | UTMN-4068
2503 | 7206 |  | RTRV | C |  | WBSH | RETRIEVE 11" CAMERON WEAR BUSHING. | 7206 |  | RIG | 07/29/2022 | SINO-43L | WH | UTMN-4068
2504 | 7206 |  | BOPT | C |  | BOP | HPJSM. P/T 13-5/8" 5M CLASS A BOPS AND RELATED EQUIPMENT AS PER ARAMCO PROCEDURES (300/2550 PSI).- FLUSH BOP, CHOKE LINE, KILL LINE, SECONDARY KILL LINE, CHOKE MANIFOLD AND POOR BOY WITH WATER.- P/T ANNULAR, SIDE OUTLETS.- P/T ALL RAMS/LINES/VLV'S / HYDROLIC VALVES FOR 10 MINS EACH..- P/T SHEAR/BLIND RAM.- PT/ IBOP, FOSV, ROTARY HOSE FOR 10 MINS EACH.- KILL & CHOKE LINES COFLEX HOSES.- CHOKE MANIFOLD VALVES. (OFFLINE).- P/T FLARE LINES TO 1200 PSI. (OFFLINE).- PERFORM ACCUMULATOR DRILL. | 7206 |  | RIG | 07/29/2022 | SINO-43L | BOP | UTMN-4068
2505 | 177 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" & 6-1/8" SECTION WIRELINE LOGGING. | 0.5 | 3665 | 15 Jul 0045 | 07/29/2022 | SINO-43L | Type | UTMN-4068
2506
2507
2508 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SND-1502 | Hrs | HRDH-124
2509 | FOT | WDS | 31.5 | 28 Jul 1000 - 1730 | 7515 | 900220 | WFD LWD TOOL FAILURE | BHA | LWD |  | 07/29/2022 | SND-1502 | 12.5 | HRDH-124
2510 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SND-2005 | Hrs | MHKK-2
2511 | FOT | SWL | 3.25 | 29 Jul 2145 - 0100 | 134 | 900242 | WHILE SURFACE TESTING WIRELINE SAMPLING TOOLS , FOUND PROBLEM WITH THE ORA SAMPLING PUMP MODULE , TROOBLESHOOTING , REPLACED WITH NEW ONE , OK . | TF | WLT |  | 07/29/2022 | SND-2005 | 3.25 | MHKK-2
2512 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SND-2006 | Hrs | UTMN-3165
2513 | FOT | WCR | 1 | 29 Jul 0630 - 0730 | 2000 | 900259 | HAD PROBLEM IN WFD TRS POWER UNIT. | TF | CTRQ |  | 07/29/2022 | SND-2006 | 1 | UTMN-3165
2514 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SND-2007 | Hrs | AWTD-104001
2515 | AINC | SDM | 40.5 | 28 Jul 0500 - 2330 | 15045 | 900276 | SCHL. ARCHER RSS FAILED TO BUILD THE ANGLE | DD | BHA |  | 07/29/2022 | SND-2007 | 16.5 | AWTD-104001
2516 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SND-2008 | Hrs | HRDH-1812
2517 | STDP | RIG | 402 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/29/2022 | SND-2008 | 24 | HRDH-1812
2518 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SND-2010 | Hrs | MNIF-869
2519 | FPMP | RIG | 2.5 | 29 Jul 0830 - 1100 | 6825 | 900293 | REPAIR SUCTION VALVES IN PUMP #1 | RR | MPMP |  | 07/29/2022 | SND-2010 | 2.5 | MNIF-869
2520 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SP-120 | Hrs | MNIF-187
2521 | FRFM | ARM | 11.5 | 29 Jul 1730 - 0500 | 6340 | 900228 | CURE LOSSES AT WARA FORMATION WITH LCM PILL AND CEMENT PLUG. | LCIR | NA |  | 07/29/2022 | SP-120 | 11.5 | MNIF-187
2522 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SP-259 | Hrs | THRY-371612
2523 | HERR | RIG | 5.75 | 29 Jul 1815 - 0000 | 14894 | 900245 | WHILE RUNNING WITH 5-1/2" CASING FLOORHAND LOST WRENCH INSIDE THE HOLE. | FISH | STRG |  | 07/29/2022 | SP-259 | 5.75 | THRY-371612
2524 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SSA-101 | Hrs | QTIF-785
2525 | FOT | SDM | 25.5 | 28 Jul 0330 - 0500 | 22626 | 900288 | SDM LWD RESISTIVITY TOOL LOST SIGNAL, TROUBLE SHOOTING WITH LWD TOOLS, NO SUCCESS. | BHA | LWD |  | 07/29/2022 | SSA-101 | 24 | QTIF-785
2526 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SSA-102 | Hrs | QTIF-693
2527 | FOT | ARM | 1 | 29 Jul 0930 - 1030 | 11987 | 900226 | GOC LOST DATA COMMUNICATION DUE TO V-SAT FAILURE | TF | COMP |  | 07/29/2022 | SSA-102 | 1 | QTIF-693
2528 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SSA-5964 | Hrs | HRDH-916
2529 | HINW | HWP | 51.5 | 27 Jul 2030 - 0000 | 11700 | 900232 | HALL WL 3.59" DPU3-MECHANICAL PUNCHER TOOL STUCK INSIDE 4.5" TBG PBR SEAL UNIT 3.72" ID WORKED ON STUCK WL TOOL. NOT FREE, PULLED CABLE, PLANNED TO RUN 1-11/16" EXPLOSIVE PUNCHER TOOL. | STUK | WLT |  | 07/29/2022 | SSA-5964 | 19 | HRDH-916
2530 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | SSA-5970 | Hrs | UTMN-2340
2531 | FOT | RIG | 5 | 29 Jul 0730 - 1230 | 10654 | 900229 | TROUBLESHOOT ON DW CLUTCH (LOW CLUTCH DRIVE PLATES FAILED TO ENGAGE). | RR | DWKS |  | 07/29/2022 | SSA-5970 | 5 | UTMN-2340
2532 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/29/2022 | WCL-83 | Hrs | MRJN-834
2533 | FOT | BCT | 6 | 29 Jul 0600 - 1200 | 6800 | 900292 | BAKER BOOSTER PUMP OF N2 PUMP BROKEN. | TF | CTPMP |  | 07/29/2022 | WCL-83 | 6 | MRJN-834
2534 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADC-12 | Hrs | ABQQ-529
2535 | STOP | ARN | 4 | 30 Jul 1100 - 1500 | 7681 | 900294 | LOST COMMUNICATION WITH GOC. | WO | NA |  | 07/30/2022 | ADC-12 | 4 | ABQQ-529
2536 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADC-14 | Hrs | HRDH-1312
2537 | FOT | RIG | 1.25 | 30 Jul 2100 - 2215 | 9770 | 900324 | REPLACED HYDRAULIC HOSE LEAKING ON TOP DRIVE . | RR | TDS |  | 07/30/2022 | ADC-14 | 1.25 | HRDH-1312
2538 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADC-31 | Hrs | SDGM-1181
2539 | FOT | SDM | 24 | 30 Jul 0500 - 0500 | 14234 | 900334 | MWD FAILURE DUE TO LOST SIGNAL. | BHA | MWD |  | 07/30/2022 | ADC-31 | 24 | SDGM-1181
2540 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADC-43L | Hrs | UTMN-3118
2541 | FRFM | TK3 | 3.75 | 30 Jul 0115 - 0500 | 12637 | 900352 | WHILE DRILLING LOST COMPLETE RETURNS IN KHUFF B CARBONATE. PUMPING LCM TO CURE THE LOSSES. | LCIR | NA |  | 07/30/2022 | ADC-43L | 3.75 | UTMN-3118
2542 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADC-48 | Hrs | HRDH-2316
2543 | FOT | RIG | 50.25 | 28 Jul 2145 - 0000 | 4111 | 900255 | WHILE RIH 12" BHA W/5-1/2" DP SINGLE , TDS HIT DP CAUSING BEND DP & DAMAGE TO TDS HYD MANIFOLD, SUSPECND OPER FOR INVESTIGATION, MEANWHILE ARRANGE HTDRAULIC MANIFOLD FROM ADC STORE | RR | TDS |  | 07/30/2022 | ADC-48 | 19 | HRDH-2316
2544 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADC-52 | Hrs | SDGM-1185
2545 | HINW | BAW | 40 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 07/30/2022 | ADC-52 | 24 | SDGM-1185
2546 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADC-55L | Hrs | UTMN-3171
2547 | STBH | TK3 | 20.5 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP BALLS FOUND STRING STUCK. | STUK | BHA |  | 07/30/2022 | ADC-55L | 20.5 | UTMN-3171
2548 | 7019 | 1407 | TO | N |  | BHA | POOH 8-1/2" RSS BHA FROM 4,819 FT TO TOP OF BHA AT 1,407FT. - MONITOR THE WELL WITH TRIP TANK.- FLOW CHECK AT TOP BHA- WELL STATIC. | 7019 | 4819 | RIG | 07/30/2022 | ADC-57L | DRLG | KRSN-175
2549 | 7019 | 0 | LDP | N |  | BHA | HPJSM,POOH AND L/D 8-1/2" RSS BHA FROM 1,407 FT TO SURFACE.- BIT DULL GRADING:1-2-WT-A-X-I-NO-TD- MONITOR THE WELL WITH TRIP TANK. | 7019 | 1407 | RIG | 07/30/2022 | ADC-57L | DRLG | KRSN-175
2550 | 7019 |  | RR | N |  | TDS | SERVICES TOP DRIVE SYSTEM. | 7019 |  | RIG | 07/30/2022 | ADC-57L | DRLG | KRSN-175
2551 | 7019 |  | NU | E |  | SNIP | R/D BELL NIPPLE AND INSTALL 9-5/8" SHOOTING NIPPLE.- PRESSURE TEST TO 500 PSI AGAINST B/S RAM- MONITOR THE WELL THRU SOV AND BELL NIPPLE TO TRIP TANK. | 7019 |  | RIG | 07/30/2022 | ADC-57L | LOG | KRSN-175
2552 | 7019 |  | OTH | E |  | NA | HPJSM,R/U SLB WL SURFACE EQUIPMENT.- MONITOR THE WELL THROUG TRIP TANK. | 7019 |  | SWL | 07/30/2022 | ADC-57L | LOG | KRSN-175
2553 | 7019 |  | OTH | E |  | NA | M/U SLB WL LOGGING TOOL STRING (AIT/TLD/HGNS/MCFL/GR).- MONITOR THE WELL THROUG TRIP TANK. | 7019 |  | SWL | 07/30/2022 | ADC-57L | LOG | KRSN-175
2554 | 7019 |  | OTH | E |  | NA | RIH W/TRIPLE COMBO WL LOGGING TOOL ON CABLE TO BTM AT 7019 FT.- MONITOR THE WELL THROUG TRIP TANK. | 7019 |  | SWL | 07/30/2022 | ADC-57L | LOG | KRSN-175
2555 | 7019 | 0 | LOG | E |  | WLT | LOGGING UP W/TRIPLE COMBO WL LOGGING TOOL FROM 7,019 FT TO SURFACE.- MONITOR THE WELL THROUG TRIP TANK. | 7019 | 7019 | SWL | 07/30/2022 | ADC-57L | LOG | KRSN-175
2556 | 7019 |  | OTH | E |  | NA | HPJSM, R/D SLB WL SURFACE EQUIPMENT.- MONITOR THE WELL THROUG TRIP TANK. | 7019 |  | SWL | 07/30/2022 | ADC-57L | LOG | KRSN-175
2557 | 7019 |  | OTH | E |  | NA | R/D 9-5/8" SHOOTING NIPPLE,INSTALL BELL NIPPLE AND CONNECT FLOW LINE.- MONITOR THE WELL THRU SOV TO TRIP TANK. | 7019 |  | RIG | 07/30/2022 | ADC-57L | LOG | KRSN-175
2558 | 7019 | 959 | LDP | E | 3885 | STRG | HPJSM, P/U M/U 8-1/2" CO RUN # 1 PRIOR NMR LOG AND RIH TO 959 FT.- 8-1/2" PDC BIT (SN: SM0369)- BIT SUB WITH FV- 24 JNTS X 5" HWDP- 6-1/2" JAR- 6 JNTS X 5" HWDP- MONITOR THE WELL THROUG TRIP TANK. | 7019 | 0 | RIG | 07/30/2022 | ADC-57L | CT | KRSN-175
2559 | 1.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | NMR LOGGING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH LOW CHLORIDE. | 1.75 | 3885 | 30 Jul 0315 | 07/30/2022 | ADC-57L | Type | KRSN-175
2560
2561
2562 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADES-14 | Hrs | HWYH-536
2563 | WTHR | OTH | 1 | 30 Jul 1600 - 1700 | 0 | 900336 | EXPERIENCED HEAVY WIND STORM WITH DUST | WON | NA |  | 07/30/2022 | ADES-14 | 1 | HWYH-536
2564 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADM-510 | Hrs | ABSF-229
2565 | FOT | RIG | 1.5 | 30 Jul 0330 - 0500 | 0 | 900251 | INSUFFICIENT BRAKE TEST AFTER SLIP AND CUT. | RR | DWKS |  | 07/30/2022 | ADM-510 | 1.5 | ABSF-229
2566 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ADM-655 | Hrs | SFNY-308
2567 | FOT | KSC | 4 | 30 Jul 0530 - 0930 | 416 | 900332 | LOST PHASE TO PHASE ESP ELECTRICAL CABLE READINGS 8 JOINTS AFTER THE ESP PACKER. | TF | ESP |  | 07/30/2022 | ADM-655 | 4 | SFNY-308
2568 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | AOD-11 | Hrs | SFNY-1670
2569 | FOT | HMS | 3 | 30 Jul 1830 - 2130 | 4838 | 900271 | HALLIBURTON MUD LOGGING CUTTING METAL PLATE STUCK ON SKIP & SHIP AUGER SYSTEM. | TF | MLOG |  | 07/30/2022 | AOD-11 | 3 | SFNY-1670
2570 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ARO-3002 | Hrs | MRJN-812
2571 | FOT | HCO | 5 | 30 Jul 2300 - 0400 | 7958 | 900322 | SEAL ASSEMBLY UNABLE TO ENGAGE ON PBR DBD L0. | TF | SEAL |  | 07/30/2022 | ARO-3002 | 5 | MRJN-812
2572 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | ARO-4001 | Hrs | MRJN-532
2573 | CPNF | HCM | 45 | 28 Jul 2145 - 1845 | 6210 | 900222 | FAILURE OF HALLIBURTON CEMENT PLUG, UNABLE TO TAG HARD CMT. | CMT | NA |  | 07/30/2022 | ARO-4001 | 13.75 | MRJN-532
2574 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | DPS-44 | Hrs | UTMN-2342
2575 | FOT | BHT | 9 | 30 Jul 0930 - 1830 | 2884 | 900270 | VERY LOW ROP COMPARED TO EXPECTED WHILE DRILLING IN AHMADI BELOW CSG SHOE. | TF | BIT |  | 07/30/2022 | DPS-44 | 9 | UTMN-2342
2576 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | DQ-49L | Hrs | HRDH-575
2577 | STBH | TK2 | 105 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 07/30/2022 | DQ-49L | 24 | HRDH-575
2578 | FOT | SCD | .75 | 30 Jul 0630 - 0715 | 825 | 900297 | UNABLE TO TAKE GWD SURVEY DUE TO BAD SIGNAL. | SURV | GYRO |  | 07/30/2022 | HI-2 | .75 | BRRI-434
2579 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | HI-2 | Hrs | BRRI-434
2580 | UVLC | ARM | .25 | 30 Jul 0545 - 0600 | 785 | 900296 | LOST TOTAL RETURNS @ 785'. | LCIR | NA |  | 07/30/2022 | HI-2 | .25 | BRRI-434
2581 | FOT | SCD | .75 | 30 Jul 0630 - 0715 | 825 | 900297 | UNABLE TO TAKE GWD SURVEY DUE TO BAD SIGNAL. | SURV | GYRO |  | 07/30/2022 | HI-2 | .75 | BRRI-434
2582 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | NA-128S | Hrs | GHZL-112
2583 | FOT | SPS | 26.75 | 29 Jul 0730 - 1015 | 12866 | 900314 | WHILE ATTEMPTING TO TAKE SURVEY, MWD TOOL LOST COMMUNICATION WITH ITS LOWER COMPONENTS. | BHA | MWD |  | 07/30/2022 | NA-128S | 5.25 | GHZL-112
2584 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | NA-207S | Hrs | SHYB-132
2585 | SRVC | SDM | 1.5 | 30 Jul 1700 - 1830 | 6521 | 900249 | WAIT ON SCHLUMBERGER OFFICE DECISION TO PICK UP RSS/MWD BHA | WO | NA |  | 07/30/2022 | NA-207S | 1.5 | SHYB-132
2586 | STBH | ARM | 11.5 | 29 Jul 0230 - 2030 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 07/30/2022 | NBR-263S | 9 | QTIF-736
2587 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | NBR-263S | Hrs | QTIF-736
2588 | FOT | RIG | 7.5 | 30 Jul 2030 - 0400 | 13970 | 900250 | MAST TOP SECTION PIN (OFF-DRILLER SIDE) DROPPED TO GROUND WHILE WORKING TO FREE STUCK STRG. | RR | DRRK |  | 07/30/2022 | NBR-263S | 7.5 | QTIF-736
2589 | WC20 | ARM | 46.5 | 28 Jul 1130 - 0500 | 14068 | 900253 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 07/30/2022 | NBR-263S | 7.5 | QTIF-736
2590 | STBH | ARM | 11.5 | 29 Jul 0230 - 2030 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 07/30/2022 | NBR-263S | 9 | QTIF-736
2591 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | NBR-654S | Hrs | HRDH-1150
2592 | FOT | HWP | 29 | 28 Jul 0245 - 0745 | 12809 | 900275 | HIGH CURRENT ON WL INSTRUMENTS - LOST COMMUNICATION WITH TOOLS. | TF | WLT |  | 07/30/2022 | NBR-654S | 2.75 | HRDH-1150
2593 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | NBR-797S | Hrs | UTMN-3119
2594 | FOT | RIG | 3.5 | 30 Jul 0900 - 1230 | 2440 | 900320 | CROWN VALVE ON STAND PIPE MANIFOLD LEAKING | RR | CSYS |  | 07/30/2022 | NBR-797S | 3.5 | UTMN-3119
2595 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | PA-218S | Hrs | HRDH-1941
2596 | FOT | HWP | 5.5 | 30 Jul 1000 - 1630 | 13956 | 900247 | MCS SECTION IN THE LOGGING TOOLS STRING NOT FUNCTIONING PROBERLY. POOH TO SURFACE & CHANGE OUT MCS TOOL. | TF | WLT |  | 07/30/2022 | PA-218S | 5.5 | HRDH-1941
2597 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | PA-622S | Hrs | UTMN-3600
2598 | FPMP | RIG | 2 | 30 Jul 1445 - 1645 | 11015 | 900248 | WHILE DRILLING-OUT CEMENT AT 11,015 WITH 82 PCF MUD WEIGHT, OBSERVED PRESSURE DROP ON MUD PUMPS. | RR | MPMP |  | 07/30/2022 | PA-622S | 2 | UTMN-3600
2599 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | PA-866S | Hrs | SHHB-2
2600 | FOT | SWL | 138.25 | 25 Jul 0845 - 0500 | 13840 | 900115 | UNABLE TO ACTIVATE SATURN PACKER | TF | WLT |  | 07/30/2022 | PA-866S | 24 | SHHB-2
2601 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | PN-7 | Hrs | MRJN-776
2602 | FOT | HML | 12.25 | 30 Jul 1645 - 0500 | 5487 | 900326 | UNABLE TO LATCH IN WITH WHIPSTOCK. | TF | WPSTK |  | 07/30/2022 | PN-7 | 12.25 | MRJN-776
2603 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | PN-9 | Hrs | MRJN-673
2604 | CFST | HCM | 174 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/30/2022 | PN-9 | 24 | MRJN-673
2605 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | RM-74A | Hrs | HSBH-68
2606 | FOT | RIG | 4.5 | 30 Jul 0030 - 0500 | 4300 | 900295 | SWING DRIVE WAS MALFUNCTION ON THE PORT AFT CRANE, AND CANNOT ASSIST THE RIG FLOOR TO HANDLE CASING JOINTS. | RR | CRN |  | 07/30/2022 | RM-74A | 4.5 | HSBH-68
2607 | FOT | RIG | 1.5 | 30 Jul 0330 - 0500 | 1478 | 900325 | INJECTOR BEARING FAILURE WHILE RIH. | RR | RSYS |  | 07/30/2022 | SCTD-1 | 1.5 | SDGM-1034
2608 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SCTD-1 | Hrs | SDGM-1034
2609 | FOT | RIG | 36.5 | 29 Jul 1500 - 0330 | 13000 | 900231 | POOH DUE TO DTF (TELEMETRY). | BHA | MMOT |  | 07/30/2022 | SCTD-1 | 22.5 | SDGM-1034
2610 | FOT | RIG | 1.5 | 30 Jul 0330 - 0500 | 1478 | 900325 | INJECTOR BEARING FAILURE WHILE RIH. | RR | RSYS |  | 07/30/2022 | SCTD-1 | 1.5 | SDGM-1034
2611 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SINO-10 | Hrs | JLDI-38
2612 | FOT | SWL | .5 | 30 Jul 0430 - 0500 | 10402 | 900353 | AFTER WORKING TOOLS WITH 2-3K OVERPULL AFTER SETTING SAME IN WASHED OUT SECTION OF HOLE TOOL WAS FOUND TO BE WORKING INCORRECTLY | TF | WLT |  | 07/30/2022 | SINO-10 | .5 | JLDI-38
2613 | 10423 |  | HT | N |  | PEL | R/D 4" HANDLING TOOLS AND POWER TONG, R/U 2-3/8" HANDLING TOOLS AND POWER TONG. | 10423 |  | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2614 | 10423 | 7306 | LDP | N |  | STRG | RIH BACK W/ 3 7/8" CLEAN OUT ASSY ON 2-3/8" DP'S PICKED UP FROM PIPE RACK TO 7,306 FT.( 112 JTS).- MONITOR WELL ON TRIP TANK, WELL STATIC. | 10423 | 3824 | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2615 | 10423 |  | HT | N |  | PEL | R/D 2-3/8" HANDLING TOOLS AND POWER TONG, R/U 4" HANDLING TOOLS AND POWER TONG. | 10423 |  | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2616 | 10423 |  | HT | N |  | BHA | M/U 7" SCRAPER, 2 X 7" STRING MAGNETS, 1 X 4" HWDP STAND, 4-3/4" WFD JAR & 2 X 4" HWDP JTS.- MONITOR WELL ON TRIP TANK, WELL STATIC. | 10423 |  | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2617 | 10423 | 10423 | TI | N |  | STHDP | CONT'D RIH W/ 3-7/8" CLEAN OUT ASSY ON 4" DP'S TO TD @ 10,423 FT.- SCRAP ESP PACKER SETTING DEPTH.- FILL & CIRC STRING VOLUME EVERY 10 STD W/70 PCF OBM- MONITOR WELL ON TRIP TANK, WELL STATIC. | 10423 | 7306 | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2618 | 10423 |  | CIRC | N |  | MPMP | DISPLACE HOLE TO 70 PCF SOLIDS FREE BRINE. | 10423 |  | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2619 | 10423 |  | WCNT | N |  | NA | FLOW CHECK, STATIC LOSSES 10-12 BPH. | 10423 |  | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2620 | 10423 |  | PJSM | C | 3905 | NA | HELD PRE-JOB SAFETY MEETING WITH ALL INVOLVED PARTIES. DISCUSS COMBINED JSA FOR ACID WASH JOB.- KEEP MONITORING WELL THRU TRIP TANK - 10 BPH LOSSES. | 10423 |  | RIG | 07/30/2022 | SINO-1L | STIM | ABJF-20
2621 | 10423 |  | OTH | C | 3905 | NA | HPJSM, NPS MU SES, TIW VALVE & RU AND PT SURFACE HARD LINES TO 3000 PSI, PERFORMED ACID WASH JOB AS FOLLOWED :- PUMPED 150 BBLS OF PRE-FLUSH FLUID.- PUMPED 155 BBLS OF ACIDIC BRINE. - PUMPED 50 BBLS OF POST-FLUSH FLUID.- KEEP TRIP TANK RUNNING CONTINUSLY WITH 70 PCF SOLID FREE BRINE @ 75 BPH - WELL IN TOTAL LOSSES. | 10423 |  | NST | 07/30/2022 | SINO-1L | STIM | ABJF-20
2622 | 10423 |  | HT | N | 3905 | STRG | LD SURFACE HARD LINES & TIW VALVE AND SES.- KEEP TRIP TANK RUNNING CONTINUSLY WITH 70 PCF SOLID FREE BRINE @ 75 BPH - WELL IN TOTAL LOSSES. | 10423 |  | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2623 | 10423 | 7514 | TO | N |  | STHDP | POOH W/ 3-7/8" CLEAN OUT ASSY ON 4" DP'S FROM 10,423 FT TO 7,514 FT.- KEEP TRIP TANK RUNNING CONTINUSLY WITH 70 PCF SOLID FREE BRINE @ 75 BPH - WELL IN TOTAL LOSSES. | 10423 | 10423 | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2624 | 10423 |  | HT | N |  | STRG | LD 7" SCRAPER, 2 X 7" STRING MAGNETS, 1 X 4" HWDP STAND, 4-3/4" WFD JAR & 2 X 4" HWDP JTS.-RECOVRED 1.5 KG JUK.- KEEP TRIP TANK RUNNING CONTINUSLY WITH 70 PCF SOLID FREE BRINE @ 75 BPH - WELL IN TOTAL LOSSES. | 10423 |  | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2625 | 10423 |  | HT | N |  | PEL | R/D 4" HANDLING TOOLS AND POWER TONG, R/U 2-3/8" HANDLING TOOLS AND POWER TONG.- KEEP TRIP TANK RUNNING CONTINUSLY WITH 70 PCF SOLID FREE BRINE @ 75 BPH - WELL IN TOTAL LOSSES. | 10423 |  | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2626 | 10423 | 4650 | LDP | N |  | STRG | POOH W/ 3-7/8" CLEAN OUT ASSY WHILE LD 2-3/8" DP FROM 7,514 FT TO TOP OF BHA..INC@RT.- KEEP TRIP TANK RUNNING CONTINUSLY WITH 70 PCF SOLID FREE BRINE @ 75 BPH - WELL IN TOTAL LOSSES. | 10423 | 7514 | RIG | 07/30/2022 | SINO-1L | CT | ABJF-20
2627 | 4 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | ACID WASH JOB. | 4 | 3905 | 30 Jul 1800 | 07/30/2022 | SINO-1L | Type | ABJF-20
2628
2629
2630 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SINO-22 | Hrs | BRRI-579
2631 | IDCS | ARN | 57 | 28 Jul 2000 - 0500 | 16000 | 900227 | GOC FAILED TO PICK UP LINER POINT AND SET 7" LINER SHALLOWER THAN THE TARGETED ZONE (ZONE 4 ARAB-D RES.). RUN 4-1/2" ISOLATION KIT. | WI | NA |  | 07/30/2022 | SINO-22 | 24 | BRRI-579
2632 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SINO-45L | Hrs | UTMN-1107
2633 | ORDS | ARM | 5 | 30 Jul 1130 - 1630 | 7060 | 900317 | STOP DRLG DUE TO GOC SERVER FAILURE | WO | NA |  | 07/30/2022 | SINO-45L | 5 | UTMN-1107
2634 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SND-1502 | Hrs | HRDH-124
2635 | STOP | ARM | 6.5 | 30 Jul 0930 - 1600 | 8050 | 900315 | LOST COMMUNICATION WITH GOC. | WO | NA |  | 07/30/2022 | SND-1502 | 6.5 | HRDH-124
2636 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SND-2008 | Hrs | HRDH-1812
2637 | STDP | RIG | 426 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/30/2022 | SND-2008 | 24 | HRDH-1812
2638 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SP-120 | Hrs | MNIF-187
2639 | FOT | RIG | 1.5 | 30 Jul 1600 - 1730 | 6439 | 900333 | RIG TROUBLESHOOT AND CHANGE POWER TONG DIES.. | TF | PEL |  | 07/30/2022 | SP-120 | 1.5 | MNIF-187
2640 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SP-161 | Hrs | HRDH-532
2641 | FOT | RIG | 1 | 30 Jul 0500 - 0600 | 0 | 900266 | RIG POWER GOT BLACK OUT WHILE CHANGING TDS SAVER SUB. | RR | PSYS |  | 07/30/2022 | SP-161 | 1 | HRDH-532
2642 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SP-258 | Hrs | JNAB-872212
2643 | FOT | SDM | 9.25 | 30 Jul 1945 - 0500 | 10515 | 900327 | GR IS READING FINE IN THE BEAGGING THEN START GIVING ERRATIC GR. | BHA | LWD |  | 07/30/2022 | SP-258 | 9.25 | JNAB-872212
2644 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SSA-101 | Hrs | QTIF-785
2645 | FOT | SDM | 49.5 | 28 Jul 0330 - 0500 | 22626 | 900288 | SDM LWD RESISTIVITY TOOL LOST SIGNAL, TROUBLE SHOOTING WITH LWD TOOLS, NO SUCCESS. | BHA | LWD |  | 07/30/2022 | SSA-101 | 24 | QTIF-785
2646 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | SSA-5962 | Hrs | HRDH-2513
2647 | FOT | HDV | 9.5 | 30 Jul 1830 - 0400 | 1555 | 900298 | HALLIBURTON 13-3/8" ISOLOCK DVT (TRIAL TEST) FAILED TO BE CLOSED AFTER PERFORMED 13-3/8" CSG SECOND STAGE CMT JOB. | TF | DV |  | 07/30/2022 | SSA-5962 | 9.5 | HRDH-2513
2648 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | T901 | Hrs | JLMN-59
2649 | FOT | RIG | 17.75 | 30 Jul 1115 - 0500 | 0 | 900321 | MALFUNCTION IN DRAWWORK BRAKE. | RR | DWKS |  | 07/30/2022 | T901 | 17.75 | JLMN-59
2650 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/30/2022 | T902 | Hrs | MHWZ-906
2651 | XTRI | RIG | 5.75 | 30 Jul 1345 - 1930 | 903 | 900319 | DIVERTER MAIN CONNECTION LEAKING. | JF | NA |  | 07/30/2022 | T902 | 5.75 | MHWZ-906
2652 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | 088TE | Hrs | QTIF-330
2653 | FOT | WEP | 9.5 | 31 Jul 1930 - 0500 | 5926 | 900302 | UNABLE TO RUN 4-1/2" HALLIBURTON COMPLETION SEAL THROUGH WFD MCL (7" CASING PATCH). | TF | CPCH |  | 07/31/2022 | 088TE | 9.5 | QTIF-330
2654 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-21 | Hrs | MZLJ-155201
2655 | GRF | RIG | 1.25 | 31 Jul 2345 - 0100 | 14835 | 900329 | CROWN-O-MATIC VALVE MALFUNTION, UNABLE TO FUNCTION DRAWWORKS. | UPRA | DWKS |  | 07/31/2022 | ADC-21 | 1.25 | MZLJ-155201
2656 | FOT | SDM | 27.75 | 30 Jul 0500 - 0845 | 14234 | 900334 | LOST SLB MWD SIGNAL | BHA | MWD |  | 07/31/2022 | ADC-31 | 3.75 | SDGM-1181
2657 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-31 | Hrs | SDGM-1181
2658 | STDP | RIG | 420.5 | 12 Jul 1930 - 0500 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 07/31/2022 | ADC-31 | 20.25 | SDGM-1181
2659 | FOT | SDM | 27.75 | 30 Jul 0500 - 0845 | 14234 | 900334 | LOST SLB MWD SIGNAL | BHA | MWD |  | 07/31/2022 | ADC-31 | 3.75 | SDGM-1181
2660 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-34 | Hrs | UTMN-2309
2661 | CFFM | ARM | 12 | 31 Jul 1000 - 2200 | 615 | 900338 | ATTEMPTED TO RUN 30" CASING TAGGING @ 485' UNABLE TO PASS. | BHS | NA |  | 07/31/2022 | ADC-34 | 12 | UTMN-2309
2662 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-41L | Hrs | SDGM-1244
2663 | UVLC | ARM | 70.5 | 28 Jul 0115 - 0500 | 9010 | 900290 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 07/31/2022 | ADC-41L | 24 | SDGM-1244
2664 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-43L | Hrs | UTMN-3118
2665 | FRFM | TK3 | 27.75 | 30 Jul 0115 - 0500 | 12637 | 900352 | WHILE DRILLING LOST COMPLETE RETURNS IN KHUFF B CARBONATE. PUMPING LCM TO CURE THE LOSSES. | LCIR | NA |  | 07/31/2022 | ADC-43L | 24 | UTMN-3118
2666 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-50 | Hrs | SFNY-1176
2667 | LCRW | ARM | 235.75 | 19 Jul 1830 - 0500 | 3911 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 07/31/2022 | ADC-50 | 24 | SFNY-1176
2668 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-52 | Hrs | SDGM-1185
2669 | HINW | BAW | 64 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 07/31/2022 | ADC-52 | 24 | SDGM-1185
2670 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-55L | Hrs | UTMN-3171
2671 | STBH | TK3 | 42.5 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 07/31/2022 | ADC-55L | 22 | UTMN-3171
2672 | 7019 | 6954 | TI | E | 3885 | STDP | RIH 8-1/2" CO RUN #1 FROM 959 FT TO 6,954 FT - FILL THE STRING EVERY 20 STANDS- MONITOR THE WELL WITH TRIP TANK | 7019 | 959 | RIG | 07/31/2022 | ADC-57L | CT | KRSN-175
2673 | 7019 | 7019 | RW | E | 3885 | BIT | REAM DN PRECAUTIONALY FROM 6,954 FT TO 7,019 FT. - MONITORE WELL THROUGH TRIP TANK, WELL STATIC | 7019 | 6954 | RIG | 07/31/2022 | ADC-57L | CT | KRSN-175
2674 | 7019 |  | CIRC | E | 3885 | MPMP | SWEEP THE HOLE WITH TWO TIMES 30 BBLS HI-VIS, CIRCULATE TILL SHAKERS CLEAN AND DISPLACE WELL BORE FLUID TO 78 PCF LOW CHLOIRDE MUD.-FLOW CHECK WELL -STATIC. | 7019 |  | RIG | 07/31/2022 | ADC-57L | CT | KRSN-175
2675 | 7019 | 4819 | TO | E | 3885 | BHA | POOH 8-1/2" CO BHA #2 ON ELEVATOR FROM 7,019 FT TO 9-5/8" CSG SHOE AT 4,819 FT.- HOLE IN GOOD CONDITION- FLOW CHECK AFTER 5 STANDS FROM BTM-WELL STATIC.- FLOW CHECK AT 9-5/8" FS -WELL STATIC.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 7019 | RIG | 07/31/2022 | ADC-57L | CT | KRSN-175
2676 | 7019 | 960 | TO | E | 3885 | STDP | POOH 8-1/2" CO BHA # 1 FROM 4,819 FT TO TOP BHA AT 960 FT.- MONITOR THE WELL WITH TRIP TANK- FLOW CHECK WELL STATIC. | 7019 | 4819 | RIG | 07/31/2022 | ADC-57L | CT | KRSN-175
2677 | 7019 |  | RR | E | 3885 | TDS | SERVICES TOP DRIVE SYSTEM. | 7019 |  | RIG | 07/31/2022 | ADC-57L | CT | KRSN-175
2678 | 7019 | 0 | LDP | E | 3885 | STRG | POOH 8-1/2" CO BHA # 1 FROM 960 FT TO SURFACE AND L/D JAR & BIT. - MONITOR THE WELL WITH TRIP TANK. | 7019 | 960 | RIG | 07/31/2022 | ADC-57L | CT | KRSN-175
2679 | 7019 |  | OTH | E | 3885 | NA | HPJSM, TLC RUN #1: P/U & M/U SLB TLC NMR LOGGING TOOLS & RIH TO 51 FT.- CHECK TLC TOOLS ON SURFACE. OK.- MONITOR WELL ON TRIP TANK. | 7019 |  | SWL | 07/31/2022 | ADC-57L | LOG | KRSN-175
2680 | 7019 | 4606 | TI | E | 3885 | STDP | RIH TLC LOGGING TOOLS ON 5" HWDP X 5" DP FROM 56 FT TO 4,606 FT WITH CONTROLLED SPEED.- FILL UP STRING EVERY 10 STANDS.- DRIFTED ALL STANDS RIH WITH 2.625" DRIFT. | 7019 | 51 | RIG | 07/31/2022 | ADC-57L | LOG | KRSN-175
2681 | 7019 |  | CIRC | E | 3885 | MPMP | CIRCULATE 1.5 STRING VOLUME W/LOW CHLORIDE MUD.- MEANWHILE R/U WL SHEAVES.- HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW. | 7019 |  | RIG | 07/31/2022 | ADC-57L | LOG | KRSN-175
2682 | 25.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | NMR LOGGING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH LOW CHLORIDE. | 24 | 3885 | 30 Jul 0315 | 07/31/2022 | ADC-57L | Type | KRSN-175
2683
2684
2685 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADC-64L | Hrs | UTMN-3074
2686 | FOT | TK3 | 41.5 | 29 Jul 1130 - 0500 | 0 | 900263 | WHILE RIH WITH UPPER COMPLETION , THE PIN OF STABBING GUIDE GOT LOST ,SEARCH FOR IT NO SUCESS ,POH COMPLETION STRING , RIH WITH C/O BHA TO MILL IT | TF | TBG |  | 07/31/2022 | ADC-64L | 24 | UTMN-3074
2687 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | ADM-337 | Hrs | MRJN-900
2688 | SRVC | BCT | 13.75 | 31 Jul 1115 - 0100 | 13019 | 900306 | ATTEMPTED TO P/T CT LINES, SEVERAL LOW-TORQUE VALVES LEAKING. REPLACE AND RE-GREASE VALVES. | WO | NA |  | 07/31/2022 | ADM-337 | 13.75 | MRJN-900
2689 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | DQ-49L | Hrs | HRDH-575
2690 | STBH | TK2 | 129 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 07/31/2022 | DQ-49L | 24 | HRDH-575
2691 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | JACK-202 | Hrs | THRY-829
2692 | FOT | RIG | 2 | 31 Jul 1230 - 1430 | 0 | 900337 | WAIT TO FIX KOOMY UNIT ELECTRIC PUMP | RR | RWCS |  | 07/31/2022 | JACK-202 | 2 | THRY-829
2693 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | JACK-203 | Hrs | HZEM-849
2694 | FOT | RIG | 1.5 | 31 Jul 1400 - 1530 | 651 | 900300 | TORQUE GAGE WRONG READING. | RR | HSYS |  | 07/31/2022 | JACK-203 | 1.5 | HZEM-849
2695 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | MP-1 | Hrs | MRJN-78
2696 | TOWC | NOJ | 2.25 | 31 Jul 0245 - 0500 | 9345 | 900303 | LOST +/- 500 PSI DPP @ 9345 FT. SAME STRING W.T, CHECKED ALL SURFACE LINES & SWABBED MUD PUMPS FOUND SAME PRESSURE, AFTER POH FOUND NOV BULLNOSE LOST IN HOLE FROM THE CONNECTION. | TF | SKSUB |  | 07/31/2022 | MP-1 | 2.25 | MRJN-78
2697 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | NBR-115S | Hrs | SDGM-1221
2698 | GRF | RIG | 2 | 31 Jul 1600 - 1800 | 64 | 900305 | EPOCH DRILLING SYSTEM STOP OPERATING. | UPRA | EDR |  | 07/31/2022 | NBR-115S | 2 | SDGM-1221
2699 | XTTE | ITS | 1 | 31 Jul 1930 - 2030 | 19308 | 900309 | DAMAGED CRT RUBBER SEALS | TF | CTRQ |  | 07/31/2022 | NBR-16S | 1 | HMYM-433102
2700 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | NBR-16S | Hrs | HMYM-433102
2701 | HERR | RIG | 1.5 | 31 Jul 1330 - 1500 | 19308 | 900308 | EXCESSIVE TIME TO CHANGE PIPE RAM | BOP | BOP |  | 07/31/2022 | NBR-16S | 1.5 | HMYM-433102
2702 | XTTE | ITS | 1 | 31 Jul 1930 - 2030 | 19308 | 900309 | DAMAGED CRT RUBBER SEALS | TF | CTRQ |  | 07/31/2022 | NBR-16S | 1 | HMYM-433102
2703 | STBH | ARM | 31 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 07/31/2022 | NBR-263S | 19.5 | QTIF-736
2704 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | NBR-263S | Hrs | QTIF-736
2705 | WC20 | ARM | 51 | 28 Jul 1130 - 0100 | 14068 | 900253 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 07/31/2022 | NBR-263S | 4.5 | QTIF-736
2706 | STBH | ARM | 31 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 07/31/2022 | NBR-263S | 19.5 | QTIF-736
2707 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | PA-866S | Hrs | SHHB-2
2708 | FOT | SWL | 141.75 | 25 Jul 0845 - 0830 | 13840 | 900115 | UNABLE TO ACTIVATE SATURN PACKER | TF | WLT |  | 07/31/2022 | PA-866S | 3.5 | SHHB-2
2709 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | PN-7 | Hrs | MRJN-776
2710 | FOT | HML | 26.75 | 30 Jul 1645 - 1930 | 5487 | 900326 | UNABLE TO LATCH IN WITH WHIPSTOCK. | TF | WPSTK |  | 07/31/2022 | PN-7 | 14.5 | MRJN-776
2711 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | PN-9 | Hrs | MRJN-673
2712 | CFST | HCM | 198 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 07/31/2022 | PN-9 | 24 | MRJN-673
2713 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | RM-74A | Hrs | HSBH-68
2714 | FOT | FMC | 1.25 | 31 Jul 1700 - 1815 | 4300 | 900328 | FRANKS TONG STUCK IN CLOSE POSITION, FIX SAME. | TF | CTRQ |  | 07/31/2022 | RM-74A | 1.25 | HSBH-68
2715 | FOT | RIG | 3.5 | 30 Jul 0330 - 0700 | 1478 | 900325 | INJECTOR BEARING FAILURE WHILE RIH. | RR | RSYS |  | 07/31/2022 | SCTD-1 | 2 | SDGM-1034
2716 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SCTD-1 | Hrs | SDGM-1034
2717 | FOT | RIG | 41 | 29 Jul 1500 - 1130 | 13000 | 900231 | POOH DUE TO DTF (TELEMETRY). | BHA | MMOT |  | 07/31/2022 | SCTD-1 | 4.5 | SDGM-1034
2718 | FOT | RIG | 3.5 | 30 Jul 0330 - 0700 | 1478 | 900325 | INJECTOR BEARING FAILURE WHILE RIH. | RR | RSYS |  | 07/31/2022 | SCTD-1 | 2 | SDGM-1034
2719 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SCTD-2 | Hrs | HRDH-2148
2720 | FOT | RIG | 11.5 | 31 Jul 0530 - 1700 | 13400 | 900356 | SLB COMPUTER IN THE COIL CAB WHICH IS USED TO TRANSFER DATA TO ALL PARTIES ON THE RIG STOPPED WORKING. TROUBLESHOOT ISSUE WITH NO SUCCESS | RR | EDR |  | 07/31/2022 | SCTD-2 | 11.5 | HRDH-2148
2721 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SINO-10 | Hrs | JLDI-38
2722 | FOT | SWL | 5.5 | 30 Jul 0430 - 1000 | 10402 | 900353 | AFTER WORKING TOOLS WITH 2-3K OVERPULL AFTER SETTING SAME IN WASHED OUT SECTION OF HOLE TOOL WAS FOUND TO BE WORKING INCORRECTLY | TF | WLT |  | 07/31/2022 | SINO-10 | 5 | JLDI-38
2723 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SINO-15L | Hrs | ANDR-566
2724 | FOT | HSL | 10 | 31 Jul 1200 - 2200 | 6369 | 900340 | HES SLICK LINE FAILED TO RETRIEVE PXN PLUG | TF | SLICK |  | 07/31/2022 | SINO-15L | 10 | ANDR-566
2725 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SINO-1L | Hrs | ABJF-20
2726 | FOT | RIG | 4 | 31 Jul 1700 - 2100 | 0 | 900307 | REPAIR ON DRWWORK PUMP & CHANGE TDS SAVER SUB | RR | DWKS |  | 07/31/2022 | SINO-1L | 4 | ABJF-20
2727 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SND-1502 | Hrs | HRDH-124
2728 | SDIR | WDS | 3.5 | 31 Jul 2315 - 0500 | 8168 | 900358 | STUCK PIPE DUE TO HOLE GEOMETRY | STUK | RSS |  | 07/31/2022 | SND-1502 | 3.5 | HRDH-124
2729 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SND-2008 | Hrs | HRDH-1812
2730 | STDP | RIG | 450 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 07/31/2022 | SND-2008 | 24 | HRDH-1812
2731 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SND-2010 | Hrs | MNIF-869
2732 | OTH | RIG | 2 | 31 Jul 1500 - 1700 | 7072 | 900299 | FOUND CONVENTIONAL DV TOOL PLUGS MISSING, AFTER INVESTIGATION FOUND SANAD FORKLIFT OPERATOR MISTAKENLY LOADED FRIDAY NIGHT 7 PM IN THE GARBAGE TRUCK | UPRA | NA |  | 07/31/2022 | SND-2010 | 2 | MNIF-869
2733 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SP-120 | Hrs | MNIF-187
2734 | FRFM | ARM | 57.5 | 29 Jul 1730 - 0500 | 6340 | 900228 | CURE LOSSES AT WARA FORMATION WITH LCM PILL AND CEMENT PLUG. | LCIR | NA |  | 07/31/2022 | SP-120 | 24 | MNIF-187
2735 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SP-122 | Hrs | HWYH-1178
2736 | HERR | RIG | 13.5 | 31 Jul 1530 - 0500 | 11862 | 900339 | WHILE RIH W/ WBCO BHA INSIDE 7" LINER DRILLER PUT 50KLBS S/O WT. | DSF | DP |  | 07/31/2022 | SP-122 | 13.5 | HWYH-1178
2737 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SP-154 | Hrs | SDGM-353
2738 | IDPR | SDM | 16.5 | 31 Jul 0500 - 0030 | 7545 | 900359 | LOW ROP. | LROP | BIT |  | 07/31/2022 | SP-154 | 16.5 | SDGM-353
2739 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SP-257 | Hrs | HZEM-162412
2740 | LCRW | ARM | 16 | 31 Jul 1300 - 0500 | 445 | 900304 | 22" BHA STUCK WHILE TOOH WITH TOTAL LOSSES. | STUK | STRG |  | 07/31/2022 | SP-257 | 16 | HZEM-162412
2741 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SP-258 | Hrs | JNAB-872212
2742 | FOT | SDM | 33.25 | 30 Jul 1945 - 0500 | 10515 | 900327 | GR IS READING FINE IN THE BEAGGING THEN START GIVING ERRATIC GR. | BHA | LWD |  | 07/31/2022 | SP-258 | 24 | JNAB-872212
2743 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SSA-101 | Hrs | QTIF-785
2744 | FOT | SDM | 64.25 | 28 Jul 0330 - 1945 | 22626 | 900288 | SDM LWD RESISTIVITY TOOL LOST SIGNAL, TROUBLE SHOOTING WITH LWD TOOLS, NO SUCCESS. | BHA | LWD |  | 07/31/2022 | SSA-101 | 14.75 | QTIF-785
2745 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SSA-5859 | Hrs | HWYH-1222
2746 | FOT | RIG | 1 | 31 Jul 1900 - 2000 | 0 | 900357 | DELAY IN OPERATIONS DUE TO DRIFT STUCK INSIDE HWDP | RR | SLIPS |  | 07/31/2022 | SSA-5859 | 1 | HWYH-1222
2747 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SSA-5891 | Hrs | HRDH-1205
2748 | FOT | RIG | 1.25 | 31 Jul 1330 - 1615 | 11450 | 900355 | LOST ROTARY ON TOPDRIVE, ELCTRICIAN/MECHANIC DIAGNOSE TOPDRIVE ISSUE - APPEARS TO BE ELECTRICAL. MEANWHILE CIRC HOLE WHILE WAITING ON ELCTRICAL SUPERVISOR TO DIAGNOSE & FIX TOPDRIVE. | RR | TDS |  | 07/31/2022 | SSA-5891 | 1.25 | HRDH-1205
2749 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 07/31/2022 | SSA-5917 | Hrs | HRDH-2201
2750 | FOT | XLG | 56.75 | 29 Jul 2015 - 0500 | 10955 | 900301 | AT 10955' ENCOUNTER PARTIAL LOSS ( 90BBLS/H ), SWEEP HOLE WITH 2X LCM PILLS @ 40 PPB EACH -NO SUCCES | TF | MLOG |  | 07/31/2022 | SSA-5917 | 24 | HRDH-2201