## Sheet1
Seq | Report Date | Rig Name | Well No | Company Name | Date and Time | Time in Hrs | Cummulative Hrs | LT ID | Parent LT ID | LT Type | Cause | Object | Depth | LT Summary
1 | 03/01/2022 | ADC-15 | HRDH-1915 | RIG | 01 Mar 1000 - 1730 | 1 | 1 | 892725 |  | RR | FPMP | MPMP | 10919 | ROTARY HOSE BURST.
3 | 03/01/2022 | ADC-34 | UTMN-2317 | WDV | 20 Dec 0500 - 0330 | 22.5 | 139 | 885525 |  | TF | FOT | DV | 7107 | WFD DV TOOL FAILURE, UNABLE TO SET PKR & OPEN DV PORTS TO PERFORM 2ND STAGE CEMENT JOB.
5 | 03/01/2022 | ADC-43L | HWYH-1226 | TK3 | 01 Mar 0145 - 0500 | 3.25 | 3.25 | 892692 |  | WO | MATL | NA | 11005 | LEAKAGE ON CRT RUBBER CUP PACKER.
7 | 03/01/2022 | ADC-50 | SFNY-1179 | INW | 01 Mar 1545 - 0500 | 13.25 | 13.25 | 892707 |  | TF | FOT | SLICK | 8413 | AFTER SETTING 3-1/2" INTERWELL PLUG, OBSERVED PLUG SHEAR ROD MISSING FROM RUNNING TOOL.
9 | 03/01/2022 | ADC-65L | HWYH-1273 | SDM | 01 Mar 1000 - 2200 | 12 | 12 | 892710 |  | BHA | FOT | MMOT | 4616 | OBSERVED INCREASED SPP, NO DIFFERENTIAL PRESSURE AND SLOW ROP
11 | 03/01/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 260 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
13 | 03/01/2022 | ARO-2003 | SFNY-988 | ARM | 27 Feb 0500 - 0500 | 24 | 72 | 892673 |  | WON | WTHR | NA | 0 | WAITING ON WEATHER FOR RIG MOVE TO SFNY 980/989 PLTF.
15 | 03/01/2022 | DPS-45 | UTMN-3175 | RIG | 01 Mar 1400 - 1515 | 1.25 | 1.25 | 892708 |  | RR | FOT | HSYS | 238 | UNABLE TO MOVE STABBING BOARD.
17 | 03/01/2022 | ENS-108 | SFNY-1560 | ARM | 01 Mar 0315 - 0500 | 1.75 | 1.75 | 892709 |  | WCNT | WCC6 | NA | 9252 | HAD 14 BBLS GAIN WHILE DRILLING. SHUT IN THE WELL
19 | 03/01/2022 | HI-4 | BRRI-780 | SWL | 28 Feb 2315 - 0730 | 2.5 | 8.25 | 892648 |  | TF | FOT | WLT | 10223 | ATTEMPT TO POSITING WIRELINE DOWN, NO SUCCESS, WIRELINE WILL NOT GO DOWN, SUSPECT WIRELINE CABLE CLAMP SLIP
21 | 03/01/2022 | MP-1 | LWHH-28 | AP1 | 01 Mar 0245 - 0500 | 2.25 | 2.25 | 892726 |  | WO | WOPF | NA | 6990 | UNPLANNED PRODUCTION SHUT DOWN ON GOSP3. INSTRUCTED TO SUSPEND ALL FLOW BACKS TO PLATFORM. SHUT IN LWHH-28. POOH WITH COIL TUBING.
22 | 03/01/2022 | MP-4 | LWHH-20 | SAM | 01 Mar 1400 - 0500 | 15 | 15 | 892691 |  | BHA | FOT | MACS | 10090 | WHILE DRILLING AT 10090 FT, OBSERVED SUDDEN PRESSURE DROP OF 2000 PSI & LOST MWD/LWD SIGNAL.
24 | 03/01/2022 | MP-4 | LWHH-20 | ARM | 26 Feb 1530 - 1300 | 7.5 | 63 | 892543 |  | DD | DFOR | RSS | 9845 | UNABLE TO GEOSTEER TO REQUIRED INCLINATION WITHIN DESIRED DLS DUE TO FORMATION DIP
25 | 03/01/2022 | MP-4 | LWHH-20 | SAM | 01 Mar 1400 - 0500 | 15 | 15 | 892691 |  | BHA | FOT | MACS | 10090 | WHILE DRILLING AT 10090 FT, OBSERVED SUDDEN PRESSURE DROP OF 2000 PSI & LOST MWD/LWD SIGNAL.
27 | 03/01/2022 | NA-393S | HWYH-1087 | ARM | 28 Feb 1800 - 0500 | 22.5 | 33.5 | 892685 |  | STUK | STDP | DP | 14950 | WHILE DRLG AT 14,950', HAD ERRATIC TQ, TRIED TO DRILL OFF TO GET SMOOTH TQ, HAD STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, HAD STRING STUCK.
29 | 03/01/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 22 | 388.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
31 | 03/01/2022 | NBR-633S | TRYQ-5 | ARN | 27 Feb 2000 - 0500 | 24 | 53 | 892567 |  | JF | HELD | RBHA | 3822 | RUN FINAL DRIFT STRING WITH 3.625" HAD OBSTRUCTION AT 3,822'. TRY TO PASS WITHOUT SUCSSES.
33 | 03/01/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 1015.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
35 | 03/01/2022 | PA-218S | QTIF-515 | RIG | 01 Mar 0900 - 1100 | 2 | 2 | 892705 |  | RR | FOT | CSYS | 0 | AFTER FUNCTION TEST BAKER TEST TRACK OBSERVED RUBBER PIECES IN BAKER FILTER SUB, CHECK FOUND RUBBER COME FROM EXPANSION FLANGE ON SUCTION LINE, CHANGE SAME.
37 | 03/01/2022 | PA-529S | SHYB-45 | BC | 25 Feb 0130 - 0500 | 24 | 98.75 | 892607 |  | TF | FOT | PKR | 6014 | PACKER SLEEVE FAILED TO SHIFT
39 | 03/01/2022 | SINO-22 | BRRI-381 | ARM | 01 Mar 1830 - 1930 | 1 | 1 | 892727 |  | TH | PCPF | NA | 8989 | HAD DRILL STRING STALLED WHILE BACKREAMING
41 | 03/01/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0500 | 24 | 276.5 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
43 | 03/01/2022 | SND-1502 | UTMN-1102 | WDS | 01 Mar 0730 - 0445 | 21.25 | 21.25 | 892706 |  | BHA | FOT | LWD | 8182 | WFD LWD TOOLS FAILURE.
45 | 03/01/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 196.5 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
46 | 03/01/2022 | SSA-5971 | UTMN-2302 | CRT | 28 Feb 2100 - 0800 | 3 | 11 | 892687 |  | BHA | FOT | WBCL | 9050 | DROP PBL OPENING DART AND PUMP DOWN. PRESSURE INCREASED TO 3600 PSI WITHOUT OPENING PORTS. UNABLE TO CIRCULATE - STRING PLUGGED
48 | 03/01/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 21 | 209 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
49 | 03/01/2022 | SSA-5971 | UTMN-2302 | CRT | 28 Feb 2100 - 0800 | 3 | 11 | 892687 |  | BHA | FOT | WBCL | 9050 | DROP PBL OPENING DART AND PUMP DOWN. PRESSURE INCREASED TO 3600 PSI WITHOUT OPENING PORTS. UNABLE TO CIRCULATE - STRING PLUGGED
51 | 03/01/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 136.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
53 | 03/01/2022 | T914 | HWYH-512 | ARM | 01 Mar 0730 - 0500 | 21.5 | 21.5 | 892689 |  | JF | HELD | LINR | 4980 | LINER SHOE UNABLE TO PASS WINDOW.
55 | 03/02/2022 | ADC-43L | HWYH-1226 | TK3 | 01 Mar 0145 - 0630 | 1.5 | 4.75 | 892692 |  | WO | MATL | NA | 11005 | LEAKAGE ON CRT RUBBER CUP PACKER.
57 | 03/02/2022 | ADC-50 | SFNY-1179 | INW | 01 Mar 1545 - 1000 | 5 | 18.25 | 892707 |  | TF | FOT | SLICK | 8413 | AFTER SETTING 3-1/2" INTERWELL PLUG, OBSERVED PLUG SHEAR ROD MISSING FROM RUNNING TOOL.
59 | 03/02/2022 | ADC-62L | ANDR-743 | TK3 | 02 Mar 0530 - 1400 | 8.5 | 8.5 | 892810 |  | WCNT | WC20 | NA | 5203 | LOST TIME DUE TO WELL CONTROL OPERATION.
61 | 03/02/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 284 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
63 | 03/02/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 12 | 12 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE.
65 | 03/02/2022 | BCTD-3 | HRDH-1924 | RIG | 02 Mar 1800 - 0200 | 8 | 8 | 892806 |  | DSF | FOT | STRG | 10000 | LOST COMMUNICATION WITH DOWNHOLE TOOL.
67 | 03/02/2022 | ENS-108 | SFNY-1560 | ARM | 01 Mar 0315 - 2130 | 16.5 | 18.25 | 892709 |  | WCNT | WCC6 | NA | 9252 | HAD 14 BBLS GAIN WHILE DRILLING. SHUT IN THE WELL
68 | 03/02/2022 | ENSCO-76 | MRJN-2004 | RIG | 02 Mar 0130 - 0500 | 3.5 | 3.5 | 892808 |  | UPRA | GRF | DWKS | 9000 | EL MAGCO BRAKE UNIT OF DRAWWORK FAILED..
70 | 03/02/2022 | ENSCO-76 | MRJN-2004 | RIG | 02 Mar 1730 - 0130 | 8 | 8 | 892807 |  | RR | FOT | DWKS | 9000 | EL MAGCO BRAKE UNIT OF DRAWWORK FAILED..
71 | 03/02/2022 | ENSCO-76 | MRJN-2004 | RIG | 02 Mar 0130 - 0500 | 3.5 | 3.5 | 892808 |  | UPRA | GRF | DWKS | 9000 | EL MAGCO BRAKE UNIT OF DRAWWORK FAILED..
73 | 03/02/2022 | EXL-IA | SFNY-4050 | RIG | 02 Mar 0500 - 0700 | 2 | 2 | 892788 |  | RR | FOT | RWCS | 0 | RELAY VALVE ON ACCUMULATOR WOULD NOT OPERATE
75 | 03/02/2022 | HI-5 | MHRH-58 | WFS | 02 Mar 0700 - 0430 | 14 | 14 | 892765 |  | TF | XTTE | FISHT | 6779 | DRILLED 5 FT RAT HOLE WITH WEATHERFORD MILLING ASSY AND NO MORE PROGRESS, RIH WITH 2ND MILLING ASSY TO DRILL THE REMAINING RAT HOLE.
77 | 03/02/2022 | NA-393S | HWYH-1087 | ARM | 28 Feb 1800 - 0400 | 23 | 56.5 | 892685 |  | STUK | STDP | DP | 14950 | WHILE DRLG AT 14,950', HAD ERRATIC TQ, TRIED TO DRILL OFF TO GET SMOOTH TQ, HAD STRING STALL WITH 100% CIRC, TRIED TO P/U STRING, HAD STRING STUCK.
79 | 03/02/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 412.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
81 | 03/02/2022 | NBR-210S | HRDH-1491 | WWL | 02 Mar 0300 - 0500 | 2 | 2 | 892826 |  | TF | FOT | WLU | 0 | FIXING THE BACK SPOOL OF WIRE LINE DRUM.
83 | 03/02/2022 | NBR-633S | TRYQ-5 | ARN | 27 Feb 2000 - 0500 | 24 | 77 | 892567 |  | JF | HELD | RBHA | 3822 | RUN FINAL DRIFT STRING WITH 3.625" HAD OBSTRUCTION AT 3,822'. TRY TO PASS WITHOUT SUCSSES.
85 | 03/02/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 1039.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
87 | 03/02/2022 | PA-218S | QTIF-515 | RIG | 02 Mar 1015 - 1115 | 1 | 1 | 892746 |  | RR | FOT | EDR | 14702 | OBSERVED MALFUNCTION IN JOYSTIC BRAKE AND RIG SENSE SYSTEM, FIX SAME.
89 | 03/02/2022 | SINO-10 | UMTW-1 | SPR | 02 Mar 1615 - 1645 | .5 | .5 | 892809 |  | TF | FOT | CTRQ | 9541 | CHANGE CSG POWER TONG.
90 | 03/02/2022 | SND-2006 | UTMN-3135 | SPS | 02 Mar 2330 - 0500 | 5.5 | 5.5 | 892790 |  | BHA | FOT | RSS | 11993 | FAILED TO OPERATE DUE TO MISSING CUMMUNICATION OF RSS W/ MWD TOOL
92 | 03/02/2022 | SND-2006 | UTMN-3135 | RIG | 02 Mar 1630 - 1800 | 1.5 | 1.5 | 892789 |  | RR | LHFL | HSYS | 11983 | OBSERVED LEAK WHILE PERFORMING RELOG OPERATION IN STANDPIPE JUMPER HOSE
93 | 03/02/2022 | SND-2006 | UTMN-3135 | SPS | 02 Mar 2330 - 0500 | 5.5 | 5.5 | 892790 |  | BHA | FOT | RSS | 11993 | FAILED TO OPERATE DUE TO MISSING CUMMUNICATION OF RSS W/ MWD TOOL
95 | 03/02/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 2130 | 16.5 | 213 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
97 | 03/02/2022 | SP-261 | HZEM-162202 | ITS | 02 Mar 1030 - 1545 | 3.25 | 3.25 | 892825 |  | JF | XTRI | CTRQ | 4920 | CRT NOT FULLY DISENGAGING WHEN STINGING OUT OF CASING. EQUIPMENT IN DIS-REPAIR. USED POWER TONGS TO M/U CASING AND CRT AS FILL UP TOOL AND ELEVATORS ONLY.
99 | 03/02/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 23.5 | 232.5 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
101 | 03/02/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 180 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
103 | 03/02/2022 | T914 | HWYH-512 | ARM | 01 Mar 0730 - 1615 | 11.25 | 32.75 | 892689 |  | JF | HELD | LINR | 4980 | LINER SHOE UNABLE TO PASS WINDOW.
105 | 03/03/2022 | ADC-34 | UTMN-2317 | WDV | 20 Dec 0500 - 2300 | 18 | 182.5 | 885525 |  | TF | FOT | DV | 7107 | WFD DV TOOL FAILURE, UNABLE TO SET PKR & OPEN DV PORTS TO PERFORM 2ND STAGE CEMENT JOB.
107 | 03/03/2022 | ADC-48 | HWYH-1258 | BHI | 02 Mar 1000 - 0500 | 22.25 | 41.25 | 892812 |  | BHA | FOT | MWD | 17780 | UNABLE TO COMMUNICATE TO TAKE SURVEY DUE TO LOST SIGNAL OF BHI MWD.
109 | 03/03/2022 | ADES-173 | HRDH-2256 | BCR | 03 Mar 0230 - 0345 | 1.25 | 1.25 | 892927 |  | TF | FOT | CTRQ | 5660 | SPIDER SLIPS CONTROL UNIT NOT WORKING.
111 | 03/03/2022 | ADES-40 | SDGM-139 | RIG | 03 Mar 1315 - 2315 | 10 | 10 | 892917 |  | RR | FOT | DWKS | 0 | DRAW WARKS MANUAL BRAKE MALFUNCTIONED (RELEASED FREE) RESULTED IN UNCONTROLLED DESCENT OF THE TDS.
112 | 03/03/2022 | ADM-337 | MRJN-900 | RIG | 03 Mar 0215 - 0400 | 1.75 | 1.75 | 892926 |  | BOP | FOT | RAMS | 9325 | OBSERVE WATER LEAKING FROM PORT SIDE UPR BONNET DOOR. OPEN BONNET FOR INSPECTION. FOUND BONNET SEAL PINCHED/CUT
114 | 03/03/2022 | ADM-337 | MRJN-900 | RIG | 03 Mar 1900 - 0030 | 5.5 | 5.5 | 892912 |  | TF | FOT | TESTT | 9325 | TROUBLEHSOOT AND REPAIR BOP TST PUMP
115 | 03/03/2022 | ADM-337 | MRJN-900 | RIG | 03 Mar 0215 - 0400 | 1.75 | 1.75 | 892926 |  | BOP | FOT | RAMS | 9325 | OBSERVE WATER LEAKING FROM PORT SIDE UPR BONNET DOOR. OPEN BONNET FOR INSPECTION. FOUND BONNET SEAL PINCHED/CUT
117 | 03/03/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 308 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
119 | 03/03/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 24 | 36 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE.
121 | 03/03/2022 | ARO-4001 | MRJN-533 | HCM | 03 Mar 0300 - 0500 | 2 | 2 | 892916 |  | TF | FOT | PUMP | 12318 | WHILE BATCH MIXING TAIL CMT SLURRY ONE AGITATOR WENT DOWN AND ONE PUMP DOWN THE OTHER PUMP NOT WORKING PROPERLY, DUMP CMT IN BATCH MIXER AND TROUBLESHOOTING SAME.
122 | 03/03/2022 | CR-36A | ZULF-2038 | RIG | 03 Mar 0000 - 0500 | 5 | 5 | 892915 |  | UPRA | OTH | NA | 2555 | PERFORM UNPLANED MAINTAINANCE FOR TOP DRIVE,
124 | 03/03/2022 | CR-36A | ZULF-2038 | RIG | 02 Mar 0300 - 0630 | 1.5 | 3.5 | 892846 |  | STUK | STDP | DP | 5070 | FLOW CHECK @ SHOE FOR 15 MIN, WELL STATIC, ATTEMP TO CIRCULATE, HAD CUTTING PACK OFF, NO MOVE UP AND DOWN, WORK ON STRING STUCK, GOT STRING FREE DOWN, STILL NO RETURN,
125 | 03/03/2022 | CR-36A | ZULF-2038 | RIG | 03 Mar 0000 - 0500 | 5 | 5 | 892915 |  | UPRA | OTH | NA | 2555 | PERFORM UNPLANED MAINTAINANCE FOR TOP DRIVE,
127 | 03/03/2022 | DPS-4 | MDRK-54 | ARM | 03 Mar 1130 - 1530 | 4 | 4 | 892907 |  | LCIR | UVLC | NA | 1302 | LOST FULL RETURN WHILE DRILLING 22" HOLE SECTION IN UMER FORMATION, ATTEMPT TO CURE LOSSES WITH LCM PILLS.
129 | 03/03/2022 | ENSCO-76 | MRJN-2004 | RIG | 02 Mar 1730 - 1730 | 12.5 | 24 | 892808 |  | RR | FOT | DWKS | 9000 | EL MAGCO BRAKE UNIT OF DRAWWORK FAILED..
131 | 03/03/2022 | EXL-IA | SFNY-4050 | RIG | 03 Mar 2330 - 0500 | 4.5 | 4.5 | 892913 |  | BOP | HERR | DVRT | 4498 | WHILE CIRCULATING HOLE RETURN FLOW OVERFLOWING BELL NIPPLE OVERSHOT HOUSING. TROUBLE SHOOT FLOW RESTRICTION IN FLOW LINE. FLOW LINE CLEAR. FOUND OVER SHOT HOUSING NOT INSTALLED PROPERLY RESTRICTING RETURN FLOW TO FLOW LINE.
133 | 03/03/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 436.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
135 | 03/03/2022 | NBR-210S | HRDH-1491 | WWL | 03 Mar 0500 - 0900 | 4 | 4 | 892909 |  | TF | FOT | WLTT | 0 | NO CONNECTIVITY FROM THE TRACTOR JUMPER, FIXED SAME.
137 | 03/03/2022 | NBR-633S | TRYQ-5 | ARN | 27 Feb 2000 - 0500 | 24 | 101 | 892567 |  | JF | HELD | RBHA | 3822 | RUN FINAL DRIFT STRING WITH 3.625" HAD OBSTRUCTION AT 3,822'. TRY TO PASS WITHOUT SUCSSES.
139 | 03/03/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 1063.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
141 | 03/03/2022 | RM-74A | KARN-61 | BC | 03 Mar 0700 - 0830 | 1.5 | 1.5 | 892906 |  | WO | SRVC | NA | 12220 | BAKER DAB PACKER HYDRAULIC RELEASE FAILURE.
142 | 03/03/2022 | SINO-43L | UTMN-4808 | RIG | 03 Mar 0815 - 1630 | 2 | 2 | 892928 |  | RR | FOT | MPMP | 9007 | WHILE DRILLING OBSERVED LEAK ON GRAUND HIGH PRESS FLEXIBLE HOSE.
144 | 03/03/2022 | SINO-43L | UTMN-4808 | ARM | 17 Feb 1930 - 0815 | 3.25 | 303.75 | 891992 |  | STUK | STBH | BHA | 9361 | AFTER THE WELL WAS KILLED BHA GOT STUCK
145 | 03/03/2022 | SINO-43L | UTMN-4808 | RIG | 03 Mar 0815 - 1630 | 2 | 2 | 892928 |  | RR | FOT | MPMP | 9007 | WHILE DRILLING OBSERVED LEAK ON GRAUND HIGH PRESS FLEXIBLE HOSE.
147 | 03/03/2022 | SINO-47 | HRDH-1957 | RIG | 03 Mar 0500 - 0800 | 3 | 3 | 892911 |  | RR | FOT | TDS | 608 | HAD LEAK ON TDS IBOP (OPRATING CRANK) WHILE DRILLING.
149 | 03/03/2022 | SND-2006 | UTMN-3135 | SPS | 02 Mar 2330 - 0000 | 18.5 | 24 | 892790 |  | BHA | FOT | RSS | 11993 | FAILED TO OPERATE DUE TO MISSING CUMMUNICATION OF RSS W/ MWD TOOL
150 | 03/03/2022 | SP-120 | MNIF-189 | SDM | 02 Mar 0300 - 1130 | 6.5 | 8.5 | 892814 |  | WO | MATL | NA | 18015 | WAITING ON SCHLUMBERGER MWD TOOL
152 | 03/03/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 17 | 228.5 | 892159 |  | CMT | FOHL | NA | 22213 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
153 | 03/03/2022 | SP-120 | MNIF-189 | SDM | 02 Mar 0300 - 1130 | 6.5 | 8.5 | 892814 |  | WO | MATL | NA | 18015 | WAITING ON SCHLUMBERGER MWD TOOL
155 | 03/03/2022 | SP-257 | HZEM-141202 | FMC | 03 Mar 0800 - 0845 | .75 | .75 | 892905 |  | TF | FOT | CRT | 4915 | EXCESSIVE TIME NEEDED TO BREAK OUT CRT.
157 | 03/03/2022 | SSA-5970 | HWYH-1257 | SDM | 03 Mar 0500 - 0500 | 23.5 | 23.5 | 892908 |  | BHA | FOT | RSS | 17800 | RSS UNABLE TO CONTROL INCLINATION.
159 | 03/03/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 22 | 254.5 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
161 | 03/03/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 184.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
163 | 03/04/2022 | ADC-17 | ZULF-1218 | RIG | 04 Mar 0000 - 0500 | 5 | 5 | 892991 |  | BHA | HERR | HWDP | 1503 | WHILE WASH UP STD DRILLER PULL W/ 45KLB OVER PULL 2 FT OFF BOTTOM, PUMP PRESSURE JUMPED FROM 1495 PSI TO 2506 PSI AND STRING ROTATE TO LEFT AND BLINDLY BACKED OFF, LOST STRING WEIGHT AND PRESSURE. CHECKED TDS FOUND IBOP LEAKING FROM CONNECTION.
165 | 03/04/2022 | ADC-48 | HWYH-1258 | BHI | 02 Mar 1000 - 0000 | 18 | 59.25 | 892812 |  | BHA | FOT | MWD | 17780 | UNABLE TO COMMUNICATE TO TAKE SURVEY DUE TO LOST SIGNAL OF BHI MWD.
167 | 03/04/2022 | ADES-40 | SDGM-139 | RIG | 03 Mar 1315 - 2130 | 15 | 25 | 892917 |  | RR | FOT | DWKS | 0 | DRAW WARKS MANUAL BRAKE MALFUNCTIONED (RELEASED FREE) RESULTED IN UNCONTROLLED DESCENT OF THE TDS.
169 | 03/04/2022 | ADM-261 | MRJN-138 | RIG | 04 Mar 0730 - 1445 | 7.25 | 7.25 | 892968 |  | RR | FOT | CSYS | 9195 | SWIVEL PACKING LEAKING. CBU, POOH TO WINDOW, CHANGE SWIVEL PACKING, RIH.
170 | 03/04/2022 | ADM-262 | MRJN-122 | BTT | 04 Mar 1400 - 0500 | 15 | 15 | 893010 |  | TF | ISEQ | SLICK | 0 | BAKER THRU TUBING FISHING SUPPLIED THE INCORRECT SPEAR SPECIFICATION (2.3" SHIPPED, 2.476" REQUIRED).
172 | 03/04/2022 | ADM-262 | MRJN-122 | BCT | 04 Mar 0800 - 1230 | 4.5 | 4.5 | 893009 |  | TF | FOT | CTBG | 0 | 24V POWER SUPPLY IN BAKER COIL UNIT FAILED.
173 | 03/04/2022 | ADM-262 | MRJN-122 | BTT | 04 Mar 1400 - 0500 | 15 | 15 | 893010 |  | TF | ISEQ | SLICK | 0 | BAKER THRU TUBING FISHING SUPPLIED THE INCORRECT SPEAR SPECIFICATION (2.3" SHIPPED, 2.476" REQUIRED).
175 | 03/04/2022 | ADM-337 | MRJN-900 | RIG | 04 Mar 1915 - 2015 | 1 | 1 | 892971 |  | TF | FOT | TESTT | 9325 | TROUBLESHOOT RIG TEST PUMP.
177 | 03/04/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 332 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
179 | 03/04/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 24 | 60 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE.
181 | 03/04/2022 | ARO-3002 | MRJN-813 | RIG | 04 Mar 1045 - 1415 | 3.5 | 3.5 | 892969 |  | RR | FOT | SWVL | 11450 | OBSERVED LEAK IN SWIVEL PACKING
183 | 03/04/2022 | ARO-4001 | MRJN-533 | HCM | 03 Mar 0300 - 2330 | 18.5 | 20.5 | 892967 |  | TF | FOT | PUMP | 12318 | WHILE BATCH MIXING TAIL CMT SLURRY AGITATOR WENT DOWN AND ONE PUMP WENT DOWN DUMP CMT IN BATCH MIXER AND TROUBLESHOOTING .
185 | 03/04/2022 | CR-36A | ZULF-2038 | RIG | 03 Mar 0000 - 0800 | 3 | 8 | 892915 |  | UPRA | OTH | NA | 2555 | PERFORM UNPLANED MAINTAINANCE FOR TOP DRIVE,
187 | 03/04/2022 | DPS-4 | MDRK-54 | RIG | 04 Mar 1215 - 1815 | 5.5 | 5.5 | 892970 |  | JF | HERR | NA | 2323 | PRESSURE SHOOT UP AFTER CONNECTION. WORK STRG & TRIED TO ESTABLISH NORMAL CIRCULATION-NO SUCCESS
189 | 03/04/2022 | DPS-5 | HRDH-1909 | BLH | 04 Mar 0630 - 1300 | 6.5 | 6.5 | 893007 |  | TF | FOT | HGRL | 2920 | HAD RESTRICTION AT 2920'. PICK UP STRING W/ 7" BOT LINER HANGER, ENGAGED TDS AND WASH DOWN- NOT ABLE TO PASS. PICK UP AND ROTATE AND TRY TO WASH DOWN AGAIN- NO SUCESS. POOH TO CHANGE OUT 7" BAKER LINER HANGER.
191 | 03/04/2022 | ED-85A | SFNY-4060 | WLH | 04 Mar 0100 - 0200 | 1 | 1 | 892992 |  | TF | FOT | LLAP | 10344 | ATTEMPT TO SET W.FORD 7" LINER TOP PKR, BUT NO SUCCESS
193 | 03/04/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 460.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
195 | 03/04/2022 | NBR-633S | TRYQ-5 | ARN | 27 Feb 2000 - 0500 | 24 | 125 | 892567 |  | JF | HELD | RBHA | 3822 | RUN FINAL DRIFT STRING WITH 3.625" HAD OBSTRUCTION AT 3,822'. TRY TO PASS WITHOUT SUCSSES.
197 | 03/04/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 1087.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
199 | 03/04/2022 | PA-218S | QTIF-515 | RIG | 04 Mar 1500 - 1900 | 4 | 4 | 892990 |  | RR | FOT | TDS | 16030 | OBSERVE ERRATIC FROM 8-19 KLB-FT. TROUBLESHOOT ERRATIC TORQUE ISSUES. CHANGE TDS ENCODER
201 | 03/04/2022 | PA-70S | MDRK-64 | ARM | 04 Mar 1930 - 2300 | 3.5 | 3.5 | 893011 |  | LCIR | UVLC | NA | 3912 | ENCOUNTERED COMPLETE LOSSES @3912' INTO WASIA FORMATION,P/U OFF-BTM.
203 | 03/04/2022 | SCTD-1 | UTMN-3126 | SDM | 04 Mar 0030 - 0500 | 4.5 | 4.5 | 893012 |  | BHA | FOT | MWD | 11978 | POH TO SURFACE DUE TO DTF.,
205 | 03/04/2022 | SINO-8 | ABQQ-493 | INW | 04 Mar 1400 - 0500 | 15 | 15 | 892987 |  | TF | FOT | SLICK | 200 | FISH ME PLUG RODE.
207 | 03/04/2022 | SL-7 | ZULF-1335 | SCP | 04 Mar 1215 - 1615 | 4 | 4 | 892988 |  | TF | FOT | HVLV | 7047 | SLB LBFV FAILED TO HOLD PRESSURE.
209 | 03/04/2022 | SND-2002 | WAQR-9 | BAW | 03 Mar 2030 - 0730 | 2.5 | 11 | 892966 |  | TF | FOT | WLT | 16011 | GR AND DENSITY WL TOOLS FAILED TO ACQUIRE GOOD QUALITY DATA. RDD REQUESTED TO REPEAT THE LOGS.
211 | 03/04/2022 | SND-3003 | HRDH-2311 | WCR | 04 Mar 2230 - 0130 | 3 | 3 | 893008 |  | TF | XTTE | CTRQ | 560 | - FAILURE POWER TONG AND UNIT, CHANGED SAME AFTER RUN 10 JTS CSG - DIFFICULTIES TO OPEN POWER TONG DOOR AFTER MAKE UP CONNECTION. - DIFFICULTIES TO OPEN THE SIDE DOOR ELEVATOR AFTER SET ON SLIPS. - LACK OF CREW COMPETENCY AND COMMUNICATION BETWEEN OPERATOR AND DRILLER. - EXCESSIVE TIME TO MAKE UP CONNECTIONS CSG , BREAK OUT MANY TIMES .
213 | 03/04/2022 | SNF036 | MRJN-901 | HWP | 04 Mar 1830 - 0130 | 7 | 7 | 892989 |  | TF | FOT | WLT | 8189 | NO COMMUNICATION WITH HALL WL AST SONIC TOOLS. TROUBLE SHOOTING AND CHANGE SAME WITH NO PROGRESS, NO COMMUNICATIONS WITH MAIN AND BACKUP SONIC TOOL. DECISION TO RIH RUN# 2 AND MOBILIZE EXTRA TWO SET OF SONIC TOOLS.
215 | 03/04/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 252.5 | 892159 |  | CMT | FOHL | NA | 17985 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
217 | 03/04/2022 | SSA-51 | MNIF-259 | OES | 03 Mar 1600 - 0500 | 20.25 | 26.25 | 892918 |  | HC | IPDF | NA | 5907 | HOLE PACK OFF, MUD PARAMETERS BELOW REQUIRMENTS.
219 | 03/04/2022 | SSA-5914 | WDYH-80 | WCR | 04 Mar 1600 - 1730 | 1.5 | 1.5 | 893026 |  | TF | FOT | CRT | 1950 | UNABLE TO UNLATCH CRT TOOL FROM CASING.
221 | 03/04/2022 | SSA-5970 | HWYH-1257 | SDM | 03 Mar 0500 - 0500 | 21.75 | 45.25 | 892908 |  | BHA | FOT | RSS | 17800 | RSS UNABLE TO CONTROL INCLINATION.
223 | 03/04/2022 | SSA-5971 | UTMN-2302 | ARM | 19 Feb 1530 - 0500 | 24 | 278.5 | 892152 |  | LCIR | UVLC | NA | 9105 | ENCOUNTERED TOTAL LOSSES AT 9,105' WHILE ROTARY DRILLING 12" HOLE SECTION (LOWER FADHILI RESERVOIR).
225 | 03/04/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 223 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
227 | 03/05/2022 | ADC-17 | ZULF-1218 | RIG | 04 Mar 0000 - 1830 | 13.5 | 18.5 | 892991 |  | BHA | HERR | HWDP | 1503 | WHILE WASH UP STD DRILLER PULL W/ 45KLB OVER PULL 2 FT OFF BOTTOM, PUMP PRESSURE JUMPED FROM 1495 PSI TO 2506 PSI AND STRING ROTATE TO LEFT AND BLINDLY BACKED OFF, LOST STRING WEIGHT AND PRESSURE. CHECKED TDS FOUND IBOP LEAKING FROM CONNECTION.
228 | 03/05/2022 | ADC-31 | SDGM-1192 | FMC | 04 Mar 0230 - 1330 | 3 | 5.5 | 893014 |  | JF | XTRI | CTRQ | 2741 | EXCESS TIME TO ALIGHN CSG JT BY CSG RUNNING CREW.
230 | 03/05/2022 | ADC-31 | SDGM-1192 | OTH | 05 Mar 1330 - 1500 | 1.5 | 1.5 | 892999 |  | WON | WTHR | NA | 2741 | STOP OPERATION DUE TO HIGH WIND SPEED AND BAD WEATHER.
231 | 03/05/2022 | ADC-31 | SDGM-1192 | RIG | 04 Mar 0100 - 1030 | 2.5 | 4 | 893013 |  | JF | XTRI | NA | 2741 | EXCESS TIME TO RUN CSG DUE TO RIG MAST MISS ALIGNMENT.
232 | 03/05/2022 | ADC-31 | SDGM-1192 | FMC | 04 Mar 0230 - 1330 | 3 | 5.5 | 893014 |  | JF | XTRI | CTRQ | 2741 | EXCESS TIME TO ALIGHN CSG JT BY CSG RUNNING CREW.
234 | 03/05/2022 | ADES-157 | HRDH-1204 | SPS | 05 Mar 1730 - 0500 | 11.5 | 11.5 | 893032 |  | BHA | FOT | MWD | 14580 | WHILE DRILLING 5 7/8" HOLE AT 14,580' MWD SIGNAL WAS LOST. MWD UNABLE TO RECOVER SIGNAL.
236 | 03/05/2022 | ADES-173 | HRDH-2256 | HCO | 04 Mar 1815 - 0145 | 2 | 3 | 893051 |  | TF | FOT | PKR | 5660 | HALLIBURTON DV TOOL FAILURE. NO RETURNS TO SURFACE.
238 | 03/05/2022 | ADES-40 | SDGM-139 | ARM | 05 Mar 1600 - 1930 | 3.5 | 3.5 | 893046 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER.
240 | 03/05/2022 | ADM-262 | MRJN-122 | BFW | 04 Mar 1400 - 0500 | 24 | 39 | 893010 |  | TF | FOT | FISHT | 0 | BAKER THRU TUBING FISHING SUPPLIED THE INCORRECT SPEAR SPECIFICATION (2.3" SHIPPED, 2.476" REQUIRED).
241 | 03/05/2022 | ADM-339 | RBYN-50 | FMC | 05 Mar 0215 - 0415 | 2 | 2 | 893017 |  | JF | HERR | CTRQ | 6048 | POOH 5X TBG JTS, L/D 2X JTS DUE TO BAD MAKE UP GRAPH AFTER REVIEW WITH FRANKS (JTS # 31, 32).
243 | 03/05/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 22 | 354 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
244 | 03/05/2022 | ADM-339 | RBYN-50 | FMC | 05 Mar 0215 - 0415 | 2 | 2 | 893017 |  | JF | HERR | CTRQ | 6048 | POOH 5X TBG JTS, L/D 2X JTS DUE TO BAD MAKE UP GRAPH AFTER REVIEW WITH FRANKS (JTS # 31, 32).
246 | 03/05/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 24 | 84 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE.
248 | 03/05/2022 | DPS-5 | HRDH-1909 | BLH | 04 Mar 0630 - 0415 | 8.5 | 15 | 893007 |  | TF | FOT | HGRL | 2920 | HAD RESTRICTION AT 2920'. PICK UP STRING W/ 7" BOT LINER HANGER, ENGAGED TDS AND WASH DOWN- NOT ABLE TO PASS. PICK UP AND ROTATE AND TRY TO WASH DOWN AGAIN- NO SUCESS. POOH TO CHANGE OUT 7" BAKER LINER HANGER.
250 | 03/05/2022 | DPS-74 | NJYN-54 | RIG | 05 Mar 0500 - 0500 | 24 | 24 | 893045 |  | BOP | FOT | BOP | 0 | WHILE PERFORMING TEST #4 WHILE PRESSURE TESTING 13-5/8" 10M BOP, OBSERVED RAPID PRESSURE DROP & VISUAL LEAK BETWEEN FMC 11" X 13-5/8" TBG SPOOL & RIG DSA.
252 | 03/05/2022 | HWU-1 | HMYM-450602 | ARM | 05 Mar 1700 - 0015 | 7.25 | 7.25 | 893015 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER / HIGH WINDS
254 | 03/05/2022 | MP-4 | LWHH-20 | ARM | 05 Mar 0330 - 0500 | 1.5 | 1.5 | 892998 |  | WON | WTHR | NA | 8532 | CREW CHANGE CHOPPER FOR FRI CANCELLED DUE TO POOR VISIBILITY, TANAJIB PORT CLOSED DUE TO INCLEMENT WEATHER CONDITIONS.
256 | 03/05/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 484.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
257 | 03/05/2022 | NBR-16S | HMYM-433304 | RIG | 05 Mar 1900 - 0215 | 2.25 | 2.25 | 893048 |  | RR | FOT | TDS | 13346 | PIPE HANDLER ON TDS (FOR ROTATING & LOCKING LINKS) FAILED TO OPERATE.
259 | 03/05/2022 | NBR-16S | HMYM-433304 | RIG | 05 Mar 0645 - 0830 | 1.75 | 1.75 | 893047 |  | RR | FOT | PSYS | 17171 | RIG BLACKED OUT DUE TO OVER HEATED ENGINE.
260 | 03/05/2022 | NBR-16S | HMYM-433304 | RIG | 05 Mar 1900 - 0215 | 2.25 | 2.25 | 893048 |  | RR | FOT | TDS | 13346 | PIPE HANDLER ON TDS (FOR ROTATING & LOCKING LINKS) FAILED TO OPERATE.
262 | 03/05/2022 | NBR-633S | TRYQ-5 | ARN | 27 Feb 2000 - 0500 | 24 | 149 | 892567 |  | JF | HELD | RBHA | 3822 | RUN FINAL DRIFT STRING WITH 3.625" HAD OBSTRUCTION AT 3,822'. TRY TO PASS WITHOUT SUCSSES.
264 | 03/05/2022 | NBR-783S | NJYN-89 | BHT | 05 Mar 0300 - 0500 | 2 | 2 | 893035 |  | TF | FOT | BIT | 6603 | ENCOUNTERED LOW ROP, POOH TO SURFACE FOUND TWO CONES W/ TWO LEGS LOST IN HOLE FROM BHI KEMERA BIT
266 | 03/05/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 1111.25 | 887787 |  | STUK | STDP | DP | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
268 | 03/05/2022 | SCTD-1 | UTMN-3126 | SDM | 04 Mar 0030 - 1500 | 10 | 14.5 | 893012 |  | BHA | FOT | MWD | 11978 | POH TO SURFACE DUE TO DTF.,
270 | 03/05/2022 | SINO-18 | ADHN-10 | RIG | 05 Mar 1845 - 2000 | 1.25 | 1.25 | 893049 |  | RR | FOT | SWVL | 14462 | REPAIR ON WASH PIPE.
272 | 03/05/2022 | SINO-27N | UTMN-438 | ARM | 05 Mar 1700 - 0500 | 12 | 12 | 893033 |  | WON | WTHR | NA | 0 | HAD SAND STORM WITH LOW VISIBILTY & HIGH WIND SPEED UP TO 45 KM/HR.
274 | 03/05/2022 | SINO-8 | ABQQ-493 | INW | 04 Mar 1400 - 0500 | 24 | 39 | 892987 |  | TF | FOT | SLICK | 200 | FISH ME PLUG RODE.
276 | 03/05/2022 | SND-2004 | BRRI-528 | WDS | 05 Mar 0630 - 0745 | 1.25 | 1.25 | 893029 |  | DD | HERR | RSS | 10826 | WFD ENABLE TO ACQUIRE LWD DATA WHILE DRILLING , RELOG INTERVAL
278 | 03/05/2022 | SND-2005 | MHKK-2 | RIG | 05 Mar 0315 - 0500 | 1.75 | 1.75 | 893031 |  | RR | FOT | EDR | 4150 | LOST COMMUNICATIONS TO RIG WATCH SERVER
280 | 03/05/2022 | SNF036 | MRJN-901 | HWP | 05 Mar 0130 - 0500 | 3.5 | 3.5 | 892997 |  | TF | FOT | WLT | 8189 | HALL WL LOST COMMUNICATION WITH XMR TOOLS.
282 | 03/05/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 276.5 | 892159 |  | CMT | FOHL | NA | 17985 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
284 | 03/05/2022 | SP-260 | HZEM-161014 | RIG | 05 Mar 0030 - 0500 | 4.5 | 4.5 | 893034 |  | BOP | FOT | BOP | 7670 | EXESS TIME BOP PRESSURE TEST, OBSERVED LEAKS BETWEEN BOP & DSA, TIGHTED NUTS, NO SUCCESS.
286 | 03/05/2022 | SP-58 | MDRK-53 | HWP | 05 Mar 1000 - 1930 | 9.5 | 9.5 | 893016 |  | TF | FOT | WLT | 14871 | HES FAILED TO PUNCH TBG WITH W/L TBG PUNCHER IN FIRST ATTEMPT, MADE SECOND RUN AND SUCCESSFULLY PUNCHED TBG.
288 | 03/05/2022 | SSA-202 | QTIF-674 | SCT | 05 Mar 1000 - 0500 | 19 | 19 | 892995 |  | TF | FOT | CTBG | 12591 | AFTER BREAK CERAMIC DISC ATTEMPT TO POOH CT ASSY GOT 10 KLB O/P. ATTEMPTED TO RIH GOT SLACK WT, CONT. POOH W/ 8 KLB DRAG TILL 10000 FT AND WT BACK TO NORMAL.
290 | 03/05/2022 | SSA-51 | MNIF-259 | OES | 03 Mar 1600 - 1630 | 11.5 | 37.75 | 892918 |  | HC | IPDF | NA | 5907 | HOLE PACK OFF, MUD PARAMETERS BELOW REQUIRMENTS.
292 | 03/05/2022 | SSA-5820 | SDGM-1215 | RIG | 05 Mar 1715 - 0500 | 11.75 | 11.75 | 893030 |  | RR | FOT | TDS | 5508 | TDS FAILURE DUE ELECTRICAL ISSUE
294 | 03/05/2022 | SSA-5964 | HRDH-1343 | WWL | 05 Mar 0900 - 0500 | 20 | 20 | 893028 |  | FISH | HERR | WLT | 8750 | WFRD RIH TO SET HALL 4.5" EZSV-BP @ 12,000'. GOT OBSTRUCTION @ 8,750' WITH APPLIED EXCESS IN S/O WT TO 500 LBS, ATTEMPTED TO PICK UP, WL TOOL WITH BP STUCK IN HOLE. FAILED TO FREE, CABLE RELEASED FROM WEAK POINT. DECISION TO RUN CT TO RETRIEVE STUCK RT & FISH/PUSH STUCK BP.
296 | 03/05/2022 | SSA-5970 | HWYH-1257 | SDM | 03 Mar 0500 - 0730 | 2.5 | 47.75 | 892908 |  | BHA | FOT | RSS | 17800 | RSS UNABLE TO CONTROL INCLINATION.
298 | 03/05/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 247 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
300 | 03/05/2022 | T218 | UTMN-564 | ARM | 05 Mar 1300 - 0000 | 11 | 11 | 893050 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER
302 | 03/06/2022 | ADES-157 | HRDH-1204 | SPS | 05 Mar 1730 - 2330 | 18.5 | 30 | 893032 |  | BHA | FOT | MWD | 14580 | WHILE DRILLING 5 7/8" HOLE AT 14,580' MWD SIGNAL WAS LOST. MWD UNABLE TO RECOVER SIGNAL.
304 | 03/06/2022 | ADES-173 | HRDH-2256 | HCO | 04 Mar 1815 - 1015 | 1.25 | 4.25 | 893051 |  | TF | FOT | PKR | 5660 | HALLIBURTON DV TOOL FAILURE. NO RETURNS TO SURFACE.
305 | 03/06/2022 | ADM-262 | MRJN-122 | BFW | 06 Mar 1600 - 0500 | 13 | 13 | 893041 |  | TF | FOT | FISHT | 0 | BAKER FISHING SUPPLIED THE INCORRECT SPEAR SPECIFICATION, IT DID NOT HAVE THE REQUIRED LENGTH TO REACH THE 2.476" INTERNAL ID ON THE SSSV.
307 | 03/06/2022 | ADM-262 | MRJN-122 | BFW | 04 Mar 1400 - 1600 | 11 | 50 | 893010 |  | TF | FOT | FISHT | 0 | BAKER FISHING SUPPLIED THE INCORRECT SPEAR SPECIFICATION (2.3" SHIPPED, 2.476" REQUIRED).
308 | 03/06/2022 | ADM-262 | MRJN-122 | BFW | 06 Mar 1600 - 0500 | 13 | 13 | 893041 |  | TF | FOT | FISHT | 0 | BAKER FISHING SUPPLIED THE INCORRECT SPEAR SPECIFICATION, IT DID NOT HAVE THE REQUIRED LENGTH TO REACH THE 2.476" INTERNAL ID ON THE SSSV.
310 | 03/06/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 378 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
312 | 03/06/2022 | ADM-511 | MRJN-799 | RIG | 06 Mar 1800 - 0500 | 11 | 11 | 893004 |  | UPRA | PPMP | NA | 0 | HAD MALFUNCTION IN JACKING SYSTEM,
314 | 03/06/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 24 | 108 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE.
316 | 03/06/2022 | ARO-4001 | MRJN-533 | RIG | 06 Mar 1200 - 1230 | .5 | .5 | 893042 |  | HSEI | UNKN | NA | 12318 | HELD SAFETY STAND DOWN WITH ALL RIG CREWS, DISCUSSED HAND PLACEMENT AND BODY POSITION AND BEING AWARE OF YOUR SURROUNDINGS WHILE HANDLING TUBLARS.
318 | 03/06/2022 | DPS-74 | NJYN-54 | RIG | 05 Mar 0500 - 0500 | 24 | 48 | 893045 |  | BOP | FOT | BOP | 0 | WHILE PERFORMING TEST #4 WHILE PRESSURE TESTING 13-5/8" 10M BOP, OBSERVED RAPID PRESSURE DROP & VISUAL LEAK BETWEEN FMC 11" X 13-5/8" TBG SPOOL & RIG DSA.
320 | 03/06/2022 | HI-5 | MHRH-58 | SDM | 06 Mar 1830 - 2130 | 3 | 3 | 893038 |  | BHA | FOT | LWD | 8478 | RDD REQUESTED SLB TO RE-LOG THE INTERVALS THAT HAD BAD LOGGING QUALITY WHILE DRILLING.
321 | 03/06/2022 | MP-1 | SFNY-994 | ARM | 06 Mar 1745 - 0500 | 11.25 | 11.25 | 893040 |  | WON | DAY | NA | 0 | WAIT ON DAYLIGHT TO CONTINUE RIG MOVE, MOVE FROM PLATFORM.
323 | 03/06/2022 | MP-1 | SFNY-994 | OTH | 05 Mar 0500 - 1515 | 10.25 | 34.25 | 893018 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO COMMENCE RIG MOVE OPERATION.
324 | 03/06/2022 | MP-1 | SFNY-994 | ARM | 06 Mar 1745 - 0500 | 11.25 | 11.25 | 893040 |  | WON | DAY | NA | 0 | WAIT ON DAYLIGHT TO CONTINUE RIG MOVE, MOVE FROM PLATFORM.
326 | 03/06/2022 | MP-4 | LWHH-20 | ARM | 05 Mar 0330 - 1800 | 13 | 14.5 | 892998 |  | WON | WTHR | NA | 8532 | CREW CHANGE CHOPPER FOR FRI CANCELLED DUE TO POOR VISIBILITY, TANAJIB PORT CLOSED DUE TO INCLEMENT WEATHER CONDITIONS.
328 | 03/06/2022 | NBR-16S | HMYM-433304 | RIG | 06 Mar 0915 - 0500 | 19.75 | 19.75 | 893021 |  | STUK | STDP | DP | 8880 | STUCK PIPE DUE TO DRILLER NOT FOLLOWING ORDERS AND APPLYING WRONG BACK REAMING PRACTICES WHICH LEAD TO EXCESSIVE OVERPULL.
330 | 03/06/2022 | NBR-210S | HRDH-1491 | WDS | 06 Mar 1030 - 0500 | 18.5 | 18.5 | 893020 |  | BHA | FOT | MWD | 11450 | LOST SIGNAL FROM WEATHERFORD MWD TOOL.
332 | 03/06/2022 | NBR-633S | TRYQ-5 | ARN | 27 Feb 2000 - 0230 | 21.5 | 170.5 | 892567 |  | JF | HELD | RBHA | 3822 | RUN FINAL DRIFT STRING WITH 3.625" HAD OBSTRUCTION AT 3,822'. TRY TO PASS WITHOUT SUCSSES.
334 | 03/06/2022 | NBR-783S | NJYN-89 | BHT | 05 Mar 0300 - 2100 | 16 | 18 | 893035 |  | TF | FOT | BIT | 6603 | ENCOUNTERED LOW ROP, POOH TO SURFACE FOUND TWO CONES W/ TWO LEGS LOST IN HOLE FROM BHI KEMERA BIT
335 | 03/06/2022 | NBR-797S | UTMN-3145 | RIG | 06 Mar 1430 - 1830 | 4 | 4 | 893066 |  | RR | FOT | TDS | 16199 | FIX TDS SERVICE LOOP
337 | 03/06/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 20 | 1131.25 | 887787 |  | STUK | STDP | DP | 16199 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
338 | 03/06/2022 | NBR-797S | UTMN-3145 | RIG | 06 Mar 1430 - 1830 | 4 | 4 | 893066 |  | RR | FOT | TDS | 16199 | FIX TDS SERVICE LOOP
340 | 03/06/2022 | PA-529S | SHYB-45 | RIG | 06 Mar 1900 - 0430 | 9.5 | 9.5 | 893057 |  | FISH | HERR | BHA | 7088 | THE BHA TALLY WAS FOUND TO BE INCORRECT. 3 STANDS 4" HWDP WERE ENTERED AS 457' 274'.
342 | 03/06/2022 | RM-74A | KARN-61 | RIG | 06 Mar 0230 - 0500 | 2.5 | 2.5 | 893039 |  | DSF | HERR | STRG | 12220 | LEAK WAS OVERSERVED ON THE LANDING STRING X/O (VX-54 X HTHC PIN).
344 | 03/06/2022 | SCTD-1 | UTMN-3126 | RIG | 06 Mar 2300 - 0500 | 6 | 6 | 893067 |  | BHA | FOT | MMOT | 12383 | POH TO SURFACE DUE TO DTF.
346 | 03/06/2022 | SINO-15L | ANDR-234 | SPS | 06 Mar 1130 - 0500 | 17.5 | 17.5 | 893056 |  | BHA | FOT | MMOT | 6890 | DOWN TIME ON SPS DUE TO MOTOR FAILURE WHILE DRILLING CURVE SECTION.
348 | 03/06/2022 | SINO-27N | UTMN-438 | ARM | 05 Mar 1700 - 0700 | 2 | 14 | 893033 |  | WON | WTHR | NA | 0 | HAD SAND STORM WITH LOW VISIBILTY & HIGH WIND SPEED UP TO 45 KM/HR.
350 | 03/06/2022 | SINO-32L | SHYB-385 | TK2 | 05 Mar 0400 - 1000 | 5 | 6 | 893000 |  | LROP | IBSL | BIT | 2192 | LOW ROP WHILE DRILLING 16" DIR HOLE.
352 | 03/06/2022 | SINO-8 | ABQQ-493 | INW | 04 Mar 1400 - 0330 | 22.5 | 61.5 | 892987 |  | TF | FOT | SLICK | 200 | FISH ME PLUG ROD.
354 | 03/06/2022 | SND-2004 | BRRI-528 | WDS | 06 Mar 0230 - 0500 | 2.5 | 2.5 | 893022 |  | BHA | FOT | RSS | 14268 | WFD RSS LOST COMMUNICATION.
356 | 03/06/2022 | SND-2005 | MHKK-2 | RIG | 05 Mar 0315 - 0700 | 2 | 3.75 | 893031 |  | RR | FOT | EDR | 4150 | LOST COMMUNICATIONS TO RIG WATCH SERVER
358 | 03/06/2022 | SNF036 | MRJN-901 | HWP | 05 Mar 0130 - 0300 | 22 | 25.5 | 892997 |  | TF | FOT | WLT | 8189 | HALL WL LOST COMMUNICATION WITH XMR TOOLS.
360 | 03/06/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 300.5 | 892159 |  | CMT | FOHL | NA | 17985 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
362 | 03/06/2022 | SP-260 | HZEM-161014 | RIG | 05 Mar 1830 - 0700 | 2 | 12.5 | 893034 |  | BOP | FOT | BOP | 7670 | EXESS TIME BOP PRESSURE TEST, OBSERVED LEAKS BETWEEN BOP & DSA, TIGHTED NUTS, NO SUCCESS.
364 | 03/06/2022 | SSA-202 | QTIF-674 | SCT | 05 Mar 1930 - 1400 | 9 | 18.5 | 892995 |  | TF | FOT | CTBG | 12591 | AFTER BREAK CERAMIC DISC ATTEMPT TO POOH CT ASSY GOT 10 KLB O/P. ATTEMPTED TO RIH GOT SLACK WT, CONT. POOH W/ 8 KLB DRAG TILL 10000 FT AND WT BACK TO NORMAL.
366 | 03/06/2022 | SSA-5914 | WDYH-80 | HDV | 06 Mar 0500 - 1600 | 11 | 11 | 893019 |  | TF | FOT | DV | 3963 | DV CIRC PORTS REOPENED AFTER BUMPING CLOSING PLUG.
368 | 03/06/2022 | SSA-5964 | HRDH-1343 | WWL | 05 Mar 0900 - 0500 | 24 | 44 | 893028 |  | FISH | HERR | WLT | 8750 | WFRD RIH TO SET HALL 4.5" EZSV-BP @ 12,000'. GOT OBSTRUCTION @ 8,750' WITH APPLIED EXCESS IN S/O WT TO 500 LBS, ATTEMPTED TO PICK UP, WL TOOL WITH BP STUCK IN HOLE. FAILED TO FREE, CABLE RELEASED FROM WEAK POINT. DECISION TO RUN CT TO RETRIEVE STUCK RT & FISH/PUSH STUCK BP.
370 | 03/06/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 271 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
372 | 03/06/2022 | T218 | UTMN-564 | HUD | 06 Mar 1630 - 0500 | 12.5 | 12.5 | 893068 |  | JF | FOP | MPD | 0 | HALLIBURTON MPD FAILED TO MAINTAIN ECD @ 110 PCF.
373 | 03/07/2022 | ADC-48 | HWYH-1258 | BHI | 07 Mar 2100 - 0500 | 7.25 | 7.25 | 893090 |  | BHA | FOT | LWD | 19433 | RECEIVING INTERMITTENT LWD DATA DUE TO SDN TOOL FAILURE
375 | 03/07/2022 | ADC-48 | HWYH-1258 | BHI | 07 Mar 0945 - 1730 | 3.75 | 3.75 | 893088 |  | BHA | FOT | MWD | 19266 | BHI LOST MWD SIGNAL.
376 | 03/07/2022 | ADC-48 | HWYH-1258 | BHI | 07 Mar 1900 - 2030 | 1.5 | 1.5 | 893089 |  | BHA | FOT | RSS | 19423 | LOST COMMUNICATION WITH RSS
377 | 03/07/2022 | ADC-48 | HWYH-1258 | BHI | 07 Mar 2100 - 0500 | 7.25 | 7.25 | 893090 |  | BHA | FOT | LWD | 19433 | RECEIVING INTERMITTENT LWD DATA DUE TO SDN TOOL FAILURE
379 | 03/07/2022 | ADM-262 | MRJN-122 | BFW | 06 Mar 1600 - 0330 | 22.5 | 35.5 | 893041 |  | TF | FOT | FISHT | 0 | BAKER FISHING SUPPLIED THE INCORRECT SPEAR SPECIFICATION, IT DID NOT HAVE THE REQUIRED LENGTH TO REACH THE 2.476" INTERNAL ID ON THE SSSV.
381 | 03/07/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 402 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
383 | 03/07/2022 | ADM-511 | MRJN-799 | RIG | 06 Mar 1800 - 0745 | 2.75 | 13.75 | 893004 |  | UPRA | PPMP | NA | 0 | HAD MALFUNCTION IN JACKING SYSTEM,
385 | 03/07/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 24 | 132 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE.
387 | 03/07/2022 | ARO-3003 | SFNY-1150 | RIG | 07 Mar 1530 - 1600 | .5 | .5 | 893094 |  | RR | FOT | HSYS | 3323 | OIL LEAK ON HYDRAULIC UNIT AT RIG FLOOR.
389 | 03/07/2022 | BB-84A | MRJN-588 | BCM | 07 Mar 1245 - 1315 | .5 | .5 | 893107 |  | CMT | CEDE | NA | 13053 | BAKER CMT MIXING LINE PLUGED (WITH CEMENT POWDER) AFTER PUMPED 10BLLS LEAD, CLEAR PLUGGING & CONTINUE PUMPING.
391 | 03/07/2022 | DPS-74 | NJYN-54 | RIG | 05 Mar 0500 - 0900 | 4 | 52 | 893045 |  | BOP | FOT | BOP | 0 | WHILE PERFORMING TEST #4 WHILE PRESSURE TESTING 13-5/8" 10M BOP, OBSERVED RAPID PRESSURE DROP & VISUAL LEAK BETWEEN FMC 11" X 13-5/8" TBG SPOOL & RIG DSA.
393 | 03/07/2022 | ENSCO-54 | ABSF-45 | KSC | 07 Mar 1030 - 0230 | 16 | 16 | 893146 |  | TF | FOT | ESPL | 4312 | LOST COMMUNICATION WITH ESP CABLE. PHASE TO GROUND - GROUNDED TROUBLE SHOOT- NO SUCCESS.
395 | 03/07/2022 | NBR-16S | HMYM-433304 | RIG | 06 Mar 0915 - 1730 | 12.5 | 32.25 | 893021 |  | STUK | STDP | DP | 8880 | STUCK PIPE DUE TO APPLYING EXCESSIVE OVERPULL ACROSS TROUBLE FORMATION.
397 | 03/07/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 532.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
398 | 03/07/2022 | NBR-210S | HRDH-1491 | WDS | 07 Mar 2230 - 0500 | 6.5 | 6.5 | 893106 |  | BHA | FOT | LWD | 12105 | NEUTRON LWD TOOL HAS FAILED, POOH TO CHANGE IT.
400 | 03/07/2022 | NBR-210S | HRDH-1491 | WDS | 06 Mar 1030 - 1030 | 5.5 | 24 | 893020 |  | BHA | FOT | MWD | 11450 | LOST SIGNAL FROM WEATHERFORD MWD TOOL.
401 | 03/07/2022 | NBR-210S | HRDH-1491 | WDS | 07 Mar 2230 - 0500 | 6.5 | 6.5 | 893106 |  | BHA | FOT | LWD | 12105 | NEUTRON LWD TOOL HAS FAILED, POOH TO CHANGE IT.
403 | 03/07/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 1155.25 | 887787 |  | STUK | STDP | DP | 16199 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
404 | 03/07/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 1715 - 1800 | .75 | .75 | 893095 |  | RR | FOT | MPMP | 17682 | RIG REPAIR MUD PUMPS#2 & 3.
406 | 03/07/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 0845 - 0945 | 1 | 1 | 893091 |  | RR | FOT | MPMP | 17584 | RIG REPAIR MUD PUMPS#1 & 3
407 | 03/07/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 0945 - 1300 | 3.25 | 3.25 | 893092 |  | RR | FOT | TDS | 17584 | TDS NOT ABLE TO INCREASE ROTATION ABOVE 65 RPM.TROUBLESHOOT FOUND ENCODER SHAFT RETAINER LOOSE
408 | 03/07/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 2100 - 0500 | 7 | 7 | 893093 |  | RR | FOT | TDS | 17743 | WHILE DRLG TDS SHOWED ERRATIC TORQUE & STOP ROTATION WHILE WORKING ON TIGHT SPOT,POOH TO FIX ERRATIC TORQUE & RELATED ISSUES.
409 | 03/07/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 1715 - 1800 | .75 | .75 | 893095 |  | RR | FOT | MPMP | 17682 | RIG REPAIR MUD PUMPS#2 & 3.
411 | 03/07/2022 | RM-74A | KARN-61 | RIG | 06 Mar 0230 - 1415 | 9.25 | 11.75 | 893039 |  | DSF | HERR | STRG | 12220 | LEAK OBSERVED ON LANDING STRING X/O (VX-54 X HTHC PIN), DUE TO INCORRECT TORQUE APPLIED
413 | 03/07/2022 | SCTD-1 | UTMN-3126 | RIG | 06 Mar 2300 - 1630 | 11.5 | 17.5 | 893067 |  | BHA | FOT | MMOT | 12383 | D&M LOSING TELEMETRY WHENEVER TAG BOTTOM.
414 | 03/07/2022 | SINO-15L | ANDR-234 | SPS | 07 Mar 1530 - 0500 | 13.5 | 13.5 | 893147 |  | BHA | FOT | MMOT | 7008 | DOWN TIME ON SPS DUE TO SLOW ROP.
416 | 03/07/2022 | SINO-15L | ANDR-234 | SPS | 06 Mar 1130 - 0600 | 1 | 18.5 | 893056 |  | BHA | FOT | MMOT | 6890 | DOWN TIME ON SPS DUE TO MOTOR FAILURE WHILE DRILLING CURVE SECTION.
417 | 03/07/2022 | SINO-15L | ANDR-234 | SPS | 07 Mar 1530 - 0500 | 13.5 | 13.5 | 893147 |  | BHA | FOT | MMOT | 7008 | DOWN TIME ON SPS DUE TO SLOW ROP.
419 | 03/07/2022 | SND-2004 | BRRI-528 | WDS | 06 Mar 0230 - 0500 | 24 | 26.5 | 893022 |  | BHA | FOT | RSS | 14268 | WFD RSS LOST COMMUNICATION.
421 | 03/07/2022 | SND-2009 | NJYN-81 | RIG | 07 Mar 1130 - 1400 | 2.5 | 2.5 | 893125 |  | RR | FOT | HSYS | 11840 | FAILURE OF RIG HPU ( HYDRAULIC POWER UNIT).
423 | 03/07/2022 | SP-106 | HRDH-3541 | RIG | 07 Mar 1630 - 0500 | 12.5 | 12.5 | 893145 |  | FISH | FWTS | STRG | 792 | 24" CASING GOT PARTED.
425 | 03/07/2022 | SP-120 | MNIF-189 | ARM | 17 Feb 0400 - 0500 | 24 | 324.5 | 892159 |  | CMT | FOHL | NA | 17985 | REMEDIAL CEMENT JOB FOR 7" LINER MAIN CEMENT JOB DUE TO 7" LINER STUCK 4400' OF PLANNED LINER POINT.
427 | 03/07/2022 | SSA-5859 | HRDH-1967 | ARM | 06 Mar 1800 - 2130 | 16.5 | 27.5 | 893105 |  | LCIR | UVLC | NA | 481 | ENCOUTERED SEVERE LOSSES
429 | 03/07/2022 | SSA-5964 | HRDH-1343 | WWL | 05 Mar 0900 - 0500 | 24 | 68 | 893028 |  | FISH | HERR | WLT | 8750 | WFRD RIH TO SET HALL 4.5" EZSV-BP @ 12,000'. GOT OBSTRUCTION @ 8,750' WITH APPLIED EXCESS IN S/O WT TO 500 LBS, ATTEMPTED TO PICK UP, WL TOOL WITH BP STUCK IN HOLE. FAILED TO FREE, CABLE RELEASED FROM WEAK POINT. DECISION TO RUN CT TO RETRIEVE STUCK RT & FISH/PUSH STUCK BP.
431 | 03/07/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 295 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
433 | 03/08/2022 | ADC-48 | HWYH-1258 | BHI | 07 Mar 2100 - 0815 | 3.25 | 10.5 | 893090 |  | BHA | FOT | LWD | 19433 | RECEIVING INTERMITTENT LWD DATA DUE TO SDN TOOL FAILURE
435 | 03/08/2022 | ADES-144 | UTMN-3041 | SAM | 08 Mar 1000 - 1200 | 2 | 2 | 893132 |  | BHA | FOT | WBCL | 12204 | FOUND SAMAA PACKER RUBBER ELEMENT DAMAGED
437 | 03/08/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0500 | 24 | 426 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
439 | 03/08/2022 | AOD-111 | MRJN-721 | RIG | 08 Mar 1515 - 1715 | 2 | 2 | 893134 |  | RR | FOT | PSYS | 4000 | RIG BLACKOUT DUE TO ENGINE FAILURE. TIME TO RECOVER POWER & REST DRILLING EQUIPMENT.
441 | 03/08/2022 | ARO-4001 | MRJN-533 | BHI | 08 Mar 1730 - 0500 | 11.5 | 11.5 | 893185 |  | BHA | FOT | RSS | 12358 | BHI LOST COMMUNICATION WITH ATK TOOL, TROUBLESHOOTING, NO SUCCESS, POOH TO CHANGE FAILED 4 3/4" ATK TOOL.
443 | 03/08/2022 | ENSCO-54 | ABSF-45 | KSC | 07 Mar 1030 - 0500 | 24 | 42.5 | 893146 |  | TF | FOT | ESPL | 4312 | LOST COMMUNICATION WITH ESP CABLE. PHASE TO GROUND - GROUNDED TROUBLE SHOOT- NO SUCCESS.
445 | 03/08/2022 | MP-1 | SFNY-994 | ARM | 08 Mar 0500 - 0500 | 24 | 24 | 893150 |  | WON | WTHR | NA | 0 | WAITING ON WEATHER FOR FINAL APPROACH TO PF SFNY 990/999.
447 | 03/08/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 556.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
449 | 03/08/2022 | NBR-16S | HMYM-433304 | RIG | 08 Mar 0700 - 1530 | 7 | 7 | 893133 |  | RR | FOT | DWKS | 7628 | TROUBLE SHOOTING DRAW WORKS DEPTH ENCODER FAULT (NO MOVEMENT UP OR DOWN),
451 | 03/08/2022 | NBR-210S | HRDH-1491 | WDS | 07 Mar 2230 - 0400 | 21.5 | 28 | 893106 |  | BHA | FOT | LWD | 12105 | NEUTRON LWD TOOL HAS FAILED, POOH TO CHANGE IT.
453 | 03/08/2022 | NBR-797S | UTMN-3145 | ARM | 11 Jan 0530 - 0500 | 24 | 1179.25 | 887787 |  | STUK | STDP | DP | 16199 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
455 | 03/08/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 2100 - 0500 | 20 | 27 | 893093 |  | RR | FOT | TDS | 17743 | WHILE DRLG TDS SHOWED ERRATIC TORQUE & STOP ROTATION WHILE WORKING ON TIGHT SPOT,POOH TO FIX ERRATIC TORQUE & RELATED ISSUES.
457 | 03/08/2022 | PA-70S | MDRK-64 | RIG | 08 Mar 0600 - 0800 | 2 | 2 | 893128 |  | RR | FOT | TDS | 5599 | DS MAULFUNCTION, SPOT 75 HI VISC PILL ON BTM AND POOH 3 STANDS, REPAIR TDS.
459 | 03/08/2022 | PA-785S | QTIF-641 | RAC | 07 Mar 0730 - 0500 | 24 | 45.5 | 893109 |  | BHA | FOT | MILL | 4842 | RAWABI ARCHER 5-7/8" PILOT MILL TWISTED OFF FROM THE MIDDLE WITH CLEAR WASH OUT FOUND AT THE TWISTED AREA.
461 | 03/08/2022 | SCTD-2 | HWYH-1193 | RIG | 08 Mar 0500 - 2300 | 18 | 18 | 893165 |  | BHA | FOT | MMOT | 2500 | LOST COMMUNICATION WITH TOOL
463 | 03/08/2022 | SDA | MRJN-733 | RIG | 08 Mar 1015 - 1115 | 1 | 1 | 893153 |  | RR | FOT | TDS | 8811 | MALFUNCTION OF TDS DOLLY RETACT SYSTEM. REPLACED CONTROLLER, NETWORK CARD, FUNCTION TEST TDS AND DOLLY, RESUMED OPERATION.
464 | 03/08/2022 | SINO-19L | UTMN-1074 | SPS | 08 Mar 0215 - 0500 | 2.75 | 2.75 | 893138 |  | BHA | FOT | LWD | 7080 | SPS FAIL TO PERFORM SHALLOW FUNCTION TEST, PULSER NOT FUNCTIONING.
466 | 03/08/2022 | SINO-19L | UTMN-1074 | SPS | 08 Mar 1230 - 1400 | 1.5 | 1.5 | 893137 |  | BHA | FOT | MMOT | 7080 | SPS MTR HANGING AND UNABLE TO SLIDE THEN LOST DIFFERENTIAL PRESSURE.
467 | 03/08/2022 | SINO-19L | UTMN-1074 | SPS | 08 Mar 0215 - 0500 | 2.75 | 2.75 | 893138 |  | BHA | FOT | LWD | 7080 | SPS FAIL TO PERFORM SHALLOW FUNCTION TEST, PULSER NOT FUNCTIONING.
469 | 03/08/2022 | SND-2004 | BRRI-528 | WDS | 06 Mar 0230 - 1545 | 10.75 | 37.25 | 893022 |  | BHA | FOT | RSS | 14268 | WFD RSS LOST COMMUNICATION.
471 | 03/08/2022 | SND-2006 | UTMN-3135 | ARM | 08 Mar 0630 - 1400 | 7.5 | 7.5 | 893135 |  | WCNT | WCC7 | NA | 14111 | OBSERVED INCREASE IN BACKGROUND GASSES AND MUD BUBLLING.
473 | 03/08/2022 | SND-2007 | ADHN-370100 | RIG | 08 Mar 2030 - 0500 | 8.5 | 8.5 | 893154 |  | RR | FOT | DWKS | 5092 | FAILURE OF TRACTION MOTOR "B" ON DRAW WORKS.
475 | 03/08/2022 | SP-106 | HRDH-3541 | RIG | 07 Mar 1630 - 0500 | 24 | 36.5 | 893145 |  | FISH | FWTS | STRG | 792 | 24" CASING GOT PARTED.
477 | 03/08/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 9 | 9 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
479 | 03/08/2022 | SP-260 | HZEM-161014 | RIG | 08 Mar 1000 - 1100 | 1 | 1 | 893129 |  | RR | FOT | CSYS | 8190 | GRADUAL DROPS ON MUD PUMPS PRESSURE,
481 | 03/08/2022 | SP-261 | HZEM-162202 | SDM | 08 Mar 0845 - 0345 | 19 | 19 | 893149 |  | BHA | FOT | MWD | 8209 | MWD TOOL SIGNAL FAILED - TROUBLE SHOOT WITH NO SUCCESS. POH AND CHANGE OUT MWD TOOLS.
483 | 03/08/2022 | SSA-46 | JAHM-7 | RIG | 08 Mar 1345 - 1645 | 3 | 3 | 893131 |  | RR | FOT | RWCS | 3824 | DURING DAILY CHECK OBSERVED INDICATOR OF LOWER CHOKE CLOSE LIGHT ON DRILLERS PANEL NOT ILLUMINATING.
485 | 03/08/2022 | SSA-5865 | ABJF-50 | RIG | 08 Mar 1330 - 1700 | 3.5 | 3.5 | 893130 |  | RR | FOT | DWKS | 500 | WHILE MAKING CONNECTION THE DRILLER WENT TO HOIST THE TOP DRIVE UP TO THE RACKING BOARD TO LATCH UP STAND OF HWDP. THE DRAW WORKS STOPPED ABRUPTLY. COULD NOT GET DRAW WORKS TO MOVE UP.
487 | 03/08/2022 | SSA-5964 | HRDH-1343 | WWL | 05 Mar 0900 - 2300 | 18 | 86 | 893028 |  | FISH | HERR | WLT | 8750 | WFRD WL RIH TO SET HALL 4.5" EZSV-BP @ 12,000'. GOT OBSTRUCTION @ 8,750' WITH APPLIED EXCESS IN S/O WT TO 500 LBS, ATTEMPTED TO PICK UP, WL TOOL WITH BP STUCK IN HOLE. FAILED TO FREE, CABLE RELEASED FROM WEAK POINT. DECISION TO RUN CT TO RETRIEVE STUCK RT & FISH/PUSH STUCK BP.
489 | 03/08/2022 | SSA-5970 | HWYH-1257 | SDM | 08 Mar 0500 - 0500 | 24 | 24 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
491 | 03/08/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 319 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
492 | 03/09/2022 | ADC-17 | ZULF-1211 | RIG | 09 Mar 0800 - 0830 | .5 | .5 | 893166 |  | RR | FOT | MPMP | 2539 | REPAIR OF MUD PUMPS
494 | 03/09/2022 | ADC-17 | ZULF-1211 | RIG | 09 Mar 0115 - 0230 | 1.25 | 1.25 | 893160 |  | RR | FOT | MPMP | 3435 | REPLACE PISTON AND LINER ON MUD PUMP#1.
495 | 03/09/2022 | ADC-17 | ZULF-1211 | RIG | 09 Mar 0800 - 0830 | .5 | .5 | 893166 |  | RR | FOT | MPMP | 2539 | REPAIR OF MUD PUMPS
497 | 03/09/2022 | ADC-49 | HRDH-1975 | MSD | 09 Mar 1330 - 1430 | 1 | 1 | 893207 |  | TF | FOT | CRT | 720 | TRYING TO BREAK CIRC., CRT RUBBER IS LEAKING AND NOT HOLDING PRESSURE, CHANGE IT AND TESTED, OK.
499 | 03/09/2022 | ADC-53L | HWYH-2524 | RIG | 09 Mar 2245 - 0330 | 4.75 | 4.75 | 893208 |  | RR | FOT | CSYS | 1890 | OBSERVED LEAK ON TDS UPPER IBOP WHILE DRILLING.
501 | 03/09/2022 | ADC-62L | ANDR-743 | RIG | 09 Mar 1715 - 0430 | 11.25 | 11.25 | 893161 |  | RR | FOT | TDS | 5200 | OBSERVE LEAK IN BEND X-OVER BETWEEN ROTARY HOSE & TDS "S" PIPE
502 | 03/09/2022 | ADES-173 | HRDH-2256 | ULT | 08 Mar 2345 - 1230 | 7.5 | 12.75 | 893168 |  | LROP | ETRQ | BIT | 7706 | LOW PENETRATION RATE.
504 | 03/09/2022 | ADES-173 | HRDH-2256 | RIG | 09 Mar 1945 - 2115 | 1.5 | 1.5 | 893159 |  | RR | FOT | TDS | 7985 | REPAIR ON TOP DRIVE.
505 | 03/09/2022 | ADES-173 | HRDH-2256 | ULT | 08 Mar 2345 - 1230 | 7.5 | 12.75 | 893168 |  | LROP | ETRQ | BIT | 7706 | LOW PENETRATION RATE.
507 | 03/09/2022 | ADM-262 | MRJN-122 | INW | 09 Mar 1730 - 2000 | 2.5 | 2.5 | 893163 |  | TF | FOT | PLUGT | 6866 | INTERWELL ME PLUG SETTING TOOL FAILED TO ACTIVATE.
509 | 03/09/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 22 | 30.75 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 120 BBL/HR.
511 | 03/09/2022 | ADM-339 | RBYN-50 | SCP | 19 Feb 0900 - 0900 | 4 | 430 | 892215 |  | JF | HERR | TBG | 6291 | THE WRONG CORRECTION FACTOR USED LEAD TO COMPLETION WAS SET 42FT SHALLOWER AND BOTH PACKER WERE SET ABOVE THE PERF ZONES.
512 | 03/09/2022 | ADM-511 | MRJN-799 | RIG | 07 Mar 0745 - 1800 | 10.5 | 55.75 | 893167 |  | UPRA | PPMP | NA | 0 | OBSERVED HIGH RPD READINGS ON ALL LEGS UP TO ALARM LIMITS.
514 | 03/09/2022 | ADM-511 | MRJN-799 | RIG | 09 Mar 1800 - 2130 | 3.5 | 3.5 | 893162 |  | UPRA | PPMP | NA | 0 | HAD MALFUNCTION IN JACKING SYSTEM (ENCODER FAILURE ON BOW LEG AT 0 AIR GAP
515 | 03/09/2022 | ADM-511 | MRJN-799 | RIG | 07 Mar 0745 - 1800 | 10.5 | 55.75 | 893167 |  | UPRA | PPMP | NA | 0 | OBSERVED HIGH RPD READINGS ON ALL LEGS UP TO ALARM LIMITS.
517 | 03/09/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 24 | 180 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE.
519 | 03/09/2022 | AOD-111 | MRJN-721 | RIG | 08 Mar 1515 - 0915 | .75 | 2.75 | 893134 |  | RR | FOT | PSYS | 4000 | RIG BLACKOUT DUE TO ENGINE FAILURE. TIME TO RECOVER POWER & REST DRILLING EQUIPMENT.
520 | 03/09/2022 | ARO-4001 | MRJN-533 | RIG | 09 Mar 1730 - 2000 | 2.5 | 2.5 | 893230 |  | RR | FOT | CSYS | 12419 | WHILE DRILLING 6 1/8" HOLE, OBSERVED CONNECTION LEAK BETWEEN KELLY HOSE & BHI T- PIECE ON STAND PIPE, CHANGE OUT CONNECTION SEAL, TEST, OK.
522 | 03/09/2022 | ARO-4001 | MRJN-533 | BHI | 09 Mar 2000 - 2130 | 1.5 | 1.5 | 893169 |  | BHA | FOT | RSS | 12419 | BHI HAD TOOL BAD DECODING, TROUBLESHOOTING SAME TILL TOOL WORKING OK.
523 | 03/09/2022 | ARO-4001 | MRJN-533 | BHI | 08 Mar 1730 - 1545 | 10.75 | 22.25 | 893185 |  | BHA | FOT | RSS | 12358 | BHI LOST COMMUNICATION WITH ATK TOOL, TROUBLESHOOTING, NO SUCCESS, POOH TO CHANGE FAILED 4 3/4" ATK TOOL.
524 | 03/09/2022 | ARO-4001 | MRJN-533 | RIG | 09 Mar 1730 - 2000 | 2.5 | 2.5 | 893230 |  | RR | FOT | CSYS | 12419 | WHILE DRILLING 6 1/8" HOLE, OBSERVED CONNECTION LEAK BETWEEN KELLY HOSE & BHI T- PIECE ON STAND PIPE, CHANGE OUT CONNECTION SEAL, TEST, OK.
526 | 03/09/2022 | ENSCO-54 | ABSF-45 | KSC | 07 Mar 1030 - 0500 | 24 | 66.5 | 893146 |  | TF | FOT | ESPL | 4312 | LOST COMMUNICATION WITH ESP CABLE. PHASE TO GROUND - GROUNDED TROUBLE SHOOT- NO SUCCESS.
527 | 03/09/2022 | ENSCO-76 | MRJN-2004 | WCR | 09 Mar 0000 - 0015 | .25 | .25 | 893210 |  | TF | FOT | CTRQ | 1275 | FAILURE OF 7" WFD POWER TONG DUE TO LEAKAGE IN HYDRAULIC CONNECTION.
529 | 03/09/2022 | ENSCO-76 | MRJN-2004 | WCR | 09 Mar 1900 - 1930 | .5 | .5 | 893209 |  | TF | HERR | TTRQ | 0 | DELAY IN OPERATION WHILE RU 7" WFD CASING HANDLING EQUIPMENT
530 | 03/09/2022 | ENSCO-76 | MRJN-2004 | WCR | 09 Mar 0000 - 0015 | .25 | .25 | 893210 |  | TF | FOT | CTRQ | 1275 | FAILURE OF 7" WFD POWER TONG DUE TO LEAKAGE IN HYDRAULIC CONNECTION.
532 | 03/09/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 580.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
534 | 03/09/2022 | NBR-783S | NJYN-89 | RIG | 09 Mar 1000 - 1300 | 3 | 3 | 893227 |  | JF | XTRI | BOP | 0 | N/U 13-5/8 10K BOPS
536 | 03/09/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 2100 - 0500 | 24 | 51 | 893093 |  | RR | FOT | TDS | 17743 | WHILE DRLG TDS SHOWED ERRATIC TORQUE & STOP ROTATION WHILE WORKING ON TIGHT SPOT,POOH TO FIX ERRATIC TORQUE & RELATED ISSUES.
538 | 03/09/2022 | PA-604S | HRDH-1392 | SAM | 09 Mar 2100 - 0500 | 8 | 8 | 893164 |  | TF | XTTE | WBCL | 12060 | UNABLE TO SET 9-5/8' SAMAA FSC PACKER FOR NEG TEST 4.5" X 7" LINER LAP
540 | 03/09/2022 | PA-70S | MDRK-64 | RIG | 09 Mar 1730 - 0500 | 11.5 | 11.5 | 893231 |  | RR | FOT | TDS | 6270 | TDS MALFUNCTION, TDS GIVES FAKE TORQUE VALUE, SPOT 150 HVP ON BTM AND POOH TO CSG SHOE, REPAIR TDS.
542 | 03/09/2022 | PN-9 | MRJN-92 | RIG | 09 Mar 1930 - 0400 | 8.5 | 8.5 | 893172 |  | RR | FOT | TDS | 9034 | WHILE DRILLING 6" X 7" HOLE. OBSERVED LEAK FROM TOP DRIVE WASH PIPE.
544 | 03/09/2022 | SCTD-1 | UTMN-3126 | RIG | 09 Mar 2330 - 0500 | 5.5 | 5.5 | 893171 |  | BHA | FOT | MMOT | 13754 | D&M LOSING TELEMETRY WHENEVER TAG BOTTOM.
546 | 03/09/2022 | SINO-19L | UTMN-1074 | SPS | 08 Mar 0215 - 1230 | 7.5 | 10.25 | 893138 |  | BHA | FOT | LWD | 7080 | SPS FAIL TO PERFORM SHALLOW TEST AND LOST COMMUNICATION TO THE RSS.
548 | 03/09/2022 | SND-2001 | UTMN-2329 | GOC | 09 Mar 1845 - 2130 | 2.75 | 2.75 | 893170 |  | WO | MATL | NA | 685 | ALGAITH SENT THE WRONG 30" BUSHING DESIGN FOR THE RIG.
550 | 03/09/2022 | SND-2002 | WAQR-9 | BAW | 09 Mar 1200 - 0500 | 17 | 17 | 893155 |  | TF | FOT | WLT | 16011 | BAKER FTEX TOOL FAILURE.
552 | 03/09/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 16.5 | 16.5 | 893212 |  | LCIR | FRFM | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
554 | 03/09/2022 | SND-2007 | ADHN-370100 | RIG | 08 Mar 2030 - 1930 | 14.5 | 23 | 893154 |  | RR | FOT | DWKS | 5092 | FAILURE OF TRACTION MOTOR "B" ON DRAW WORKS.
556 | 03/09/2022 | SND-3003 | HRDH-2311 | WCR | 09 Mar 1515 - 1630 | 1.25 | 1.25 | 893156 |  | TF | FOT | CTRQ | 3134 | LOST SIGNAL BETWEEN CONTROL UNIT TO MOUNTED SLIPS & CRT TOOL.
558 | 03/09/2022 | SP-106 | HRDH-3541 | RIG | 07 Mar 1630 - 0500 | 24 | 60.5 | 893145 |  | FISH | FWTS | STRG | 792 | 24" CASING GOT PARTED.
560 | 03/09/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 33 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
562 | 03/09/2022 | SSA-5820 | SDGM-1215 | RIG | 09 Mar 1000 - 0500 | 19 | 19 | 893225 |  | RR | FOT | TDS | 8377 | TDS IBOP HYDRAULIC VALVE FAILURE.
564 | 03/09/2022 | SSA-5865 | ABJF-50 | RIG | 08 Mar 1330 - 1000 | 4 | 7.5 | 893130 |  | RR | FOT | DWKS | 500 | WHILE MAKING CONNECTION THE DRILLER WENT TO HOIST THE TOP DRIVE UP TO THE RACKING BOARD TO LATCH UP STAND OF HWDP. THE DRAW WORKS STOPPED ABRUPTLY. COULD NOT GET DRAW WORKS TO MOVE UP.
566 | 03/09/2022 | SSA-5891 | HRDH-1178 | RIG | 09 Mar 1545 - 1730 | 1.75 | 1.75 | 893157 |  | RR | FOT | TDS | 0 | LEAK ON STEEL HYDRAULIC LINE.
568 | 03/09/2022 | SSA-5914 | WDYH-80 | RIG | 09 Mar 1330 - 1730 | 4 | 4 | 893206 |  | DSF | FOT | DP | 9527 | OBSERVED A DROP IN STANDPIPE PRESSURE WHILE COC FROM 9,479' TO 9,527'.
570 | 03/09/2022 | SSA-5917 | HRDH-2344 | ARM | 09 Mar 2300 - 0500 | 6 | 6 | 893213 |  | LCIR | UXDF | NA | 10600 | LOST CIRC, LOAD SYSTEM WITH LCM AND REGAIN CIRC.
572 | 03/09/2022 | SSA-5964 | HRDH-1343 | WWL | 05 Mar 0900 - 1300 | 6 | 92 | 893028 |  | FISH | HERR | WLT | 8750 | WFRD WL RIH TO SET HALL 4.5" EZSV-BP @ 12,000'. GOT OBSTRUCTION @ 8,750' WITH APPLIED EXCESS IN S/O WT TO 500 LBS, ATTEMPTED TO PICK UP, WL TOOL WITH BP STUCK IN HOLE. FAILED TO FREE, CABLE RELEASED FROM WEAK POINT. DECISION TO RUN CT TO RETRIEVE STUCK RT & FISH/PUSH STUCK BP.
574 | 03/09/2022 | SSA-5970 | HWYH-1257 | SDM | 08 Mar 0500 - 0500 | 24 | 48 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
576 | 03/09/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 343 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
578 | 03/10/2022 | ADC-31 | SDGM-1192 | RIG | 05 Mar 1330 - 2130 | 1 | 4.5 | 892999 |  | RR | FOT | TDS | 2741 | STOP OPERATION DUE TO TDS ELECTRICAL FAILURE
580 | 03/10/2022 | ADC-35 | MAQL-5 | SWL | 10 Mar 2000 - 0500 | 9 | 9 | 893307 |  | TF | FOT | WLT | 7757 | TOOLS PARTED AT ELECTRONIC CONTROL RELEASE DEVICE
582 | 03/10/2022 | ADC-42L | UTMN-2319 | SDM | 10 Mar 1200 - 0500 | 17 | 17 | 893286 |  | DD | AINC | BHA | 13570 | WHILE DRILLING 5-7/8" SECTION, THE WELL INCLINATION DROPS UNINTENTIONALY FROM 30DEG TO 27DEG & THE RSS TOOLS CAN'T CORRECT THE WELL TRAJECTORY.
584 | 03/10/2022 | ADES-144 | UTMN-3041 | SAM | 08 Mar 1000 - 1930 | 7 | 9 | 893132 |  | BHA | FOT | WBCL | 12204 | FOUND SAMAA PACKER RUBBER ELEMENT DAMAGED
586 | 03/10/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 56.25 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 120 BBL/HR.
587 | 03/10/2022 | ADM-511 | MRJN-799 | ARM | 10 Mar 0330 - 0500 | 1.5 | 1.5 | 893308 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER CONDITION TO CONTINUE PRELOAD OPERATION AT ZERO AIR GAP
589 | 03/10/2022 | ADM-511 | MRJN-799 | RIG | 07 Mar 0745 - 1745 | 12.75 | 71 | 893167 |  | UPRA | PPMP | NA | 0 | OBSERVED HIGH RPD READINGS ON ALL LEGS UP TO ALARM LIMITS.
590 | 03/10/2022 | ADM-511 | MRJN-799 | ARM | 10 Mar 0330 - 0500 | 1.5 | 1.5 | 893308 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER CONDITION TO CONTINUE PRELOAD OPERATION AT ZERO AIR GAP
592 | 03/10/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 24 | 204 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE.
594 | 03/10/2022 | ARO-2001 | BRRI-184 | WWD | 09 Mar 2115 - 0500 | 24 | 31.75 | 893285 |  | TF | FOT | WPSTK | 8215 | WHILE TRIPPING OUT OF THE HOLE WHIPSTOCK BECAME TIGHT. MAX OVERPULL APPLIED AND PACKER/ANCHOR SHEARED.
596 | 03/10/2022 | ENSCO-54 | ABSF-45 | KSC | 07 Mar 1030 - 0500 | 24 | 90.5 | 893146 |  | TF | FOT | ESPL | 4312 | LOST COMMUNICATION WITH ESP CABLE. PHASE TO GROUND - GROUNDED TROUBLE SHOOT- NO SUCCESS.
598 | 03/10/2022 | EXL-IVA | SFNY-1660 | BAW | 10 Mar 2145 - 0445 | 7 | 7 | 893305 |  | TF | FOT | WLT | 5380 | AT 5380' MREX TOOL GIVING SUSPICIOUS POROSITY READINGS.
600 | 03/10/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 604.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
602 | 03/10/2022 | NBR-783S | NJYN-89 | BHT | 05 Mar 0300 - 0500 | 15 | 33 | 893035 |  | TF | FOT | BIT | 6603 | ENCOUNTERED LOW ROP, POOH TO SURFACE FOUND TWO CONES W/ TWO LEGS LOST IN HOLE FROM BHI KEMERA BIT
604 | 03/10/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 2100 - 0500 | 24 | 75 | 893093 |  | RR | FOT | TDS | 17743 | WHILE DRLG TDS SHOWED ERRATIC TORQUE & STOP ROTATION WHILE WORKING ON TIGHT SPOT,POOH TO FIX ERRATIC TORQUE & RELATED ISSUES.
606 | 03/10/2022 | PA-604S | HRDH-1392 | SAM | 09 Mar 2100 - 1530 | 10.5 | 18.5 | 893164 |  | TF | XTTE | WBCL | 12060 | UNABLE TO SET 9-5/8' SAMAA FSC PACKER FOR NEG TEST 4.5" X 7" LINER LAP
608 | 03/10/2022 | PA-70S | MDRK-64 | RIG | 09 Mar 1730 - 1000 | 5 | 16.5 | 893231 |  | RR | FOT | TDS | 6270 | TDS MALFUNCTION, TDS GIVES FAKE TORQUE VALUE, SPOT 150 HVP ON BTM AND POOH TO CSG SHOE, REPAIR TDS.
610 | 03/10/2022 | SCTD-1 | UTMN-3126 | RIG | 09 Mar 2330 - 2000 | 15 | 20.5 | 893171 |  | BHA | FOT | MMOT | 13754 | D&M LOSING TELEMETRY WHENEVER TAG BOTTOM.
612 | 03/10/2022 | SINO21 | ABQQ-133 | SDM | 10 Mar 1300 - 1930 | 6.5 | 6.5 | 893247 |  | LROP | IDPR | BHA | 7300 | UNABLE TO DRILL WITH SLB MTR
614 | 03/10/2022 | SND-2002 | WAQR-9 | BAW | 09 Mar 1200 - 2000 | 15 | 32 | 893155 |  | TF | FOT | WLT | 16011 | BAKER FTEX TOOL FAILURE.
616 | 03/10/2022 | SND-2004 | BRRI-528 | RIG | 10 Mar 2330 - 0030 | 1 | 1 | 893248 |  | HSEI | UNKN | NA | 3085 | HEAVY SMOKE ON RIG ELECTRICAL AIR COMPRESSOR#3, SECURE THE AREA & CONDUCTED SAFETY STAND DOWN MEETING TO DISCUSS THE INCIDENT.
618 | 03/10/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 24 | 40.5 | 893212 |  | LCIR | FRFM | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
620 | 03/10/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 57 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
622 | 03/10/2022 | SP-260 | HZEM-161014 | SPS | 10 Mar 0945 - 0500 | 18 | 18 | 893306 |  | BHA | FOT | MWD | 9925 | SPS MWD FAILED
624 | 03/10/2022 | SSA-5820 | SDGM-1215 | RIG | 09 Mar 1000 - 1600 | 9 | 28 | 893225 |  | RR | FOT | TDS | 8377 | TDS IBOP HYDRAULIC VALVE FAILURE.
626 | 03/10/2022 | SSA-5917 | HRDH-2344 | ARM | 09 Mar 2300 - 0630 | 1.5 | 7.5 | 893213 |  | LCIR | UXDF | NA | 10600 | LOST CIRC, LOAD SYSTEM WITH LCM AND REGAIN CIRC.
628 | 03/10/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 72 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
630 | 03/10/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 367 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
632 | 03/11/2022 | ADC-31 | SDGM-1192 | SCM | 11 Mar 0200 - 0500 | 3 | 3 | 893348 |  | JF | FOT | SQZ | 4880 | CEMENT UNIT FAILURE DURING 13-3/8" CSG 1ST STAGE CEMENT JOB
634 | 03/11/2022 | ADC-35 | MAQL-5 | SWL | 10 Mar 2000 - 0500 | 24 | 33 | 893307 |  | TF | FOT | WLT | 7757 | ORA SAMPLING TOOLS ON WL GOT STUCK AND DISCONNECTED FROM CABLE SOCKET (ECRD).
636 | 03/11/2022 | ADC-42L | UTMN-2319 | SDM | 10 Mar 1200 - 1715 | 12.25 | 29.25 | 893286 |  | DD | AINC | BHA | 13570 | WHILE DRILLING 5-7/8" SECTION, THE WELL INCLINATION DROPS UNINTENTIONALLY FROM 30DEG TO 27DEG & THE RSS TOOLS CAN'T CORRECT THE WELL TRAJECTORY.
638 | 03/11/2022 | ADES-157 | HRDH-1204 | BAW | 11 Mar 1430 - 1600 | 1.5 | 1.5 | 893346 |  | WO | SRVC | NA | 14982 | WAIT ON BAKER TO PROCESS DATA, EXCESS TIME TO TRANSFER AND PROCESS LOGGING DATA.
640 | 03/11/2022 | ADES-173 | HRDH-2256 | ARM | 11 Mar 0545 - 0500 | 23.25 | 23.25 | 893309 |  | BHS | FRFM | NA | 9822 | DRILLSTRING STUCK ON BOTTOM
642 | 03/11/2022 | ADM-266 | ZULF-106 | ARM | 11 Mar 2000 - 0500 | 9 | 9 | 893326 |  | WON | WTHR | NA | 0 | UN-ABLE TO OFF LOAD CARGO REQUIRED FOR MILLING OPERATIONS.
644 | 03/11/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 20.5 | 76.75 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 150 BBL/HR.
646 | 03/11/2022 | ADM-511 | MRJN-799 | ARM | 10 Mar 0330 - 0500 | 24 | 25.5 | 893308 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER CONDITION TO CONTINUE PRELOAD OPERATION
648 | 03/11/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 0500 | 24 | 228 | 892805 |  | WO | SRVC | NA | 0 | WAIT ON HSU TEAM TO PERFORM SEA BED SURVEY AT BRRI-218 PF FOR SAFE RIG MOVE. RECEIVED SBS ON MAR 8 AT 15:00 HRS BARGE PROCCED TO SECURE BRRI-218.
650 | 03/11/2022 | ARO-2001 | BRRI-184 | WWD | 09 Mar 2115 - 0500 | 24 | 55.75 | 893285 |  | TF | FOT | WPSTK | 8215 | WHILE TRIPPING OUT OF THE HOLE WHIPSTOCK BECAME TIGHT. MAX OVERPULL APPLIED AND PACKER/ANCHOR SHEARED.
652 | 03/11/2022 | CG-1 | ZULF-1201 | RIG | 11 Mar 0500 - 0500 | 24 | 24 | 893269 |  | JF | HERR | NA | 0 | EXCEEDED THE PUMPING PARAMETERS & ACTIVATE WFD HANGER @ SURFACE.
654 | 03/11/2022 | DPS-4 | MDRK-54 | ARM | 11 Mar 0145 - 0445 | 3 | 3 | 893349 |  | LCIR | UVLC | NA | 5697 | LOST FULL RETURN WHILE DRILLING 16" HOLE SECTION IN SHU'AIBA FORMATION, ATTEMPT TO CURE LOSSES WITH LCM PILLS.
656 | 03/11/2022 | ENSCO-54 | ABSF-45 | KSC | 07 Mar 1030 - 0500 | 24 | 114.5 | 893146 |  | TF | FOT | ESPL | 4312 | LOST COMMUNICATION WITH ESP CABLE. PHASE TO GROUND - GROUNDED TROUBLE SHOOT- NO SUCCESS.
657 | 03/11/2022 | JACK-203 | MHWZ-823 | SWL | 11 Mar 1930 - 2300 | 3.5 | 3.5 | 893365 |  | JF | AGCB | WLT | 831 | TOOL FAILURE FOR THE ROATING SUB.
659 | 03/11/2022 | JACK-203 | MHWZ-823 | SWL | 11 Mar 0730 - 1100 | 3.5 | 3.5 | 893266 |  | JF | AGCB | WLT | 831 | WIRELINE CABLE IS LEAKING
660 | 03/11/2022 | JACK-203 | MHWZ-823 | SWL | 11 Mar 1930 - 2300 | 3.5 | 3.5 | 893365 |  | JF | AGCB | WLT | 831 | TOOL FAILURE FOR THE ROATING SUB.
662 | 03/11/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 628.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
664 | 03/11/2022 | NBR-196S | SDGM-1226 | ARM | 11 Mar 2130 - 0500 | 7.5 | 7.5 | 893347 |  | LCIR | CFFM | LCM | 377 | ENCOUNTERED COMPLETE LOSSES @ 377', UNABLE TO CURE W/LCM SLUGS.
666 | 03/11/2022 | NBR-783S | NJYN-89 | BHT | 05 Mar 0300 - 0500 | 24 | 57 | 893035 |  | TF | FOT | BIT | 6603 | ENCOUNTERED LOW ROP, POOH TO SURFACE FOUND TWO CONES W/ TWO LEGS LOST IN HOLE FROM BHI KEMERA BIT
668 | 03/11/2022 | PA-218S | QTIF-515 | RIG | 07 Mar 2100 - 0900 | 4 | 79 | 893093 |  | RR | FOT | TDS | 17743 | WHILE DRLG TDS SHOWED ERRATIC TORQUE & STOP ROTATION WHILE WORKING ON TIGHT SPOT,POOH TO FIX ERRATIC TORQUE & RELATED ISSUES.
670 | 03/11/2022 | SINO-33L | KHRS-388 | HDV | 10 Mar 1000 - 1645 | 11.75 | 30.75 | 893249 |  | TF | FOT | DV | 2619 | MANY TRIAL TO DRILL-OUT 9-5/8" DVT W/ 8-1/2" MRSS ASSY. F/ 2,616' T/ 2,619' W/ 63 PCF OBM & APPLIED OPTIMUM DRILLING PARAMETERS WITHOUT PROGRESS.
672 | 03/11/2022 | SND-2002 | WAQR-9 | BAW | 11 Mar 1200 - 0215 | 14.25 | 14.25 | 893310 |  | TF | FOT | WLT | 16011 | BAKER WL LOST COMMUNICATION WITH LOGGING TOOLS.
674 | 03/11/2022 | SND-2004 | BRRI-528 | RIG | 11 Mar 1200 - 1300 | 1 | 1 | 893345 |  | HSEI | UNKN | NA | 4400 | CONDUCT SAFETY STAND DOWN MEETING WITH RIG CREW TO REVIEW THE RIG ELECTRICAL COMPRESSOR PROPERTY DAMAGE INCIDENT AND DISCUSS THE ROOT CAUSES.
676 | 03/11/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 24 | 64.5 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
678 | 03/11/2022 | SNF036 | MRJN-901 | RIG | 11 Mar 0000 - 0200 | 2 | 2 | 893270 |  | RR | FOT | HSYS | 8189 | TEST PUMP FAILED TO OPERATE, TROUBLE SHOOTING TO FIX SAME WITH NO SUCCESS. LINE UP TO CMT UNIT AND CONTINUE PT BOPE.
680 | 03/11/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 81 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
682 | 03/11/2022 | SP-260 | HZEM-161014 | SPS | 10 Mar 0945 - 1500 | 10 | 28 | 893306 |  | BHA | FOT | MWD | 9925 | SPS MWD FAILED
684 | 03/11/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 0500 | 6.75 | 6.75 | 893267 |  | FISH | HERR | BHA | 9253 | HAD ERRATIC TORQUE 2 FT OFF BOTTOM AND OBSERVED JUNK MARKS ON BIT AND BIT SUB AT SURFACE
686 | 03/11/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 96 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
688 | 03/11/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 391 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
690 | 03/12/2022 | ADC-31 | SDGM-1192 | SCM | 11 Mar 0300 - 1000 | 5 | 7 | 893348 |  | JF | FOT | SQZ | 4880 | CEMENT UNIT FAILURE DURING 13-3/8" CSG 1ST STAGE CEMENT JOB
692 | 03/12/2022 | ADC-43L | HWYH-1226 | RIG | 11 Mar 0400 - 0630 | 1.5 | 2.5 | 893271 |  | RR | LHFL | HSYS | 13954 | LEAK FROM TDS S-PIPE CONNECTION ( GOOSENECK)
694 | 03/12/2022 | ADC-70 | SFNY-4230 | HWP | 12 Mar 1400 - 0245 | 12.25 | 12.25 | 893351 |  | TF | FOT | WLT | 5548 | HALLIBURTON LOST COMMUNICATION WITH RDT TOOL. TROUBLSHOOT SAME; NO SUCCESS. POH TO C/O RDT TOOL.
696 | 03/12/2022 | ADES-173 | HRDH-2256 | ARM | 11 Mar 0545 - 0500 | 23.5 | 46.75 | 893309 |  | BHS | FRFM | NA | 9822 | DRILLSTRING STUCK ON BOTTOM
698 | 03/12/2022 | ADES-798 | JFYN-11 | BCR | 12 Mar 0800 - 1100 | 3 | 3 | 893352 |  | JF | HERR | CTRQ | 3889 | CUMULITIVE LOST TIME TO REPAIR POWER TONG AND ADJUSTING CRT LINKS.
700 | 03/12/2022 | ADM-266 | ZULF-106 | ARM | 11 Mar 2000 - 1300 | 8 | 17 | 893326 |  | WON | WTHR | NA | 0 | UN-ABLE TO OFF LOAD CARGO REQUIRED FOR MILLING OPERATIONS.
702 | 03/12/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0215 | 21 | 97.75 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 150 BBL/HR.
704 | 03/12/2022 | ADM-339 | RBYN-55 | RIG | 12 Mar 1130 - 1445 | 3.25 | 3.25 | 893330 |  | BOP | FOT | BOP | 0 | KOOMEY UNIT NOT ABLE TO PRESSURE UP AFTER DRAWDOWN TEST IN THE TIME REQUIRED
706 | 03/12/2022 | ADM-511 | MRJN-799 | ARM | 10 Mar 0330 - 0500 | 24 | 49.5 | 893308 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER CONDITION TO CONTINUE PRELOAD OPERATION
707 | 03/12/2022 | ADM-655 | BRRI-218 | ARM | 12 Mar 1530 - 0500 | 13.5 | 13.5 | 893366 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER FOR RIG MOVE TO BRRI-218 PLATFORM.
709 | 03/12/2022 | ADM-655 | BRRI-218 | ARN | 02 Mar 1700 - 1530 | 10.5 | 238.5 | 892805 |  | WO | SRVC | NA | 0 | RECEIVED SBS ON MAR 8 AT 15:00 HRS BARGE PROCCED TO SECURE BRRI-218. WAIT ON BARGE QMS ALMARYAH TO INSTALL PLUG & MOVE OUT FROM BRRI-218.
710 | 03/12/2022 | ADM-655 | BRRI-218 | ARM | 12 Mar 1530 - 0500 | 13.5 | 13.5 | 893366 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER FOR RIG MOVE TO BRRI-218 PLATFORM.
712 | 03/12/2022 | AOD-11 | SFNY-4250 | BCR | 12 Mar 0800 - 1130 | 3.5 | 3.5 | 893368 |  | JF | XTRI | CTRQ | 321 | BAKER HUGHES POWER PACK FAILURE AFTER MAKING UP 2ND CONNECTION. NO BACK UP UNIT PROVIDED FOR OFFSHORE RIG. UNIT BECAME HOT AND STARTED LEAKING HYDRAULIC OIL DUE TO BULLHEADING AT HIGH RPM'S.
714 | 03/12/2022 | ARO-2001 | BRRI-184 | WWD | 09 Mar 2115 - 0500 | 24 | 79.75 | 893285 |  | TF | FOT | WPSTK | 8215 | WHILE TRIPPING OUT OF THE HOLE WHIPSTOCK BECAME TIGHT. MAX OVERPULL APPLIED AND PACKER/ANCHOR SHEARED.
716 | 03/12/2022 | ARO-4001 | MRJN-533 | RIG | 12 Mar 0830 - 1230 | 4 | 4 | 893332 |  | RR | FOT | DWKS | 14735 | OBSERVED DRAWWORKS BRAKE#1 NOT RELEASING PROPERLY & UNABLE TO MOVE TDS, TROUBLESHOOTING SAME, CHANGED OUT AIR SUPPLY SOLENOID ON DRAWWORKS BREAK#1, WORKING OK.
718 | 03/12/2022 | CG-1 | ZULF-1201 | RIG | 11 Mar 0500 - 0500 | 21.5 | 45.5 | 893269 |  | JF | HERR | NA | 0 | EXCEEDED THE PUMPING PARAMETERS & ACTIVATE WFD HANGER @ SURFACE.
720 | 03/12/2022 | DPS-45 | UTMN-3175 | GOC | 12 Mar 1830 - 2000 | 1.5 | 1.5 | 893333 |  | TF | FOT | PEL | 3606 | FAILURE OF AL-GHAITH SIDE DOOR ELEVATOR LATCH.
722 | 03/12/2022 | DQ-57L | KHRS-53 | ARM | 12 Mar 1100 - 1600 | 5 | 5 | 893273 |  | WON | WTHR | NA | 0 | SUSPEND CRANE LIFT OPERATION DUE TO HIGH WIND SPEED.
724 | 03/12/2022 | ENSCO-54 | ABSF-45 | KSC | 07 Mar 1030 - 0500 | 24 | 138.5 | 893146 |  | TF | FOT | ESPL | 4312 | LOST COMMUNICATION WITH ESP CABLE. PHASE TO GROUND - GROUNDED TROUBLE SHOOT- NO SUCCESS.
726 | 03/12/2022 | HI-5 | MHRH-58 | SWL | 12 Mar 1300 - 0030 | 11.5 | 11.5 | 893367 |  | TF | FOT | WLT | 7646 | SCHLUMBERGER WIRE LINE DUAL PACKER LOST SEAL EFFICIENCY WHILE PUMP OUT AT 7646.5 FT.
728 | 03/12/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 652.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
729 | 03/12/2022 | NBR-196S | SDGM-1226 | ARM | 12 Mar 1930 - 0500 | 9.5 | 9.5 | 893371 |  | LCIR | CFFM | LCM | 430 | ENCOUNTERED COMPLETE LOSSES @ 430', UNABLE TO CURE W/LCM SLUGS.
731 | 03/12/2022 | NBR-196S | SDGM-1226 | ARM | 11 Mar 2130 - 1500 | 10 | 17.5 | 893347 |  | LCIR | CFFM | LCM | 377 | ENCOUNTERED COMPLETE LOSSES @ 377', UNABLE TO CURE W/LCM SLUGS.
732 | 03/12/2022 | NBR-196S | SDGM-1226 | ARM | 12 Mar 1930 - 0500 | 9.5 | 9.5 | 893371 |  | LCIR | CFFM | LCM | 430 | ENCOUNTERED COMPLETE LOSSES @ 430', UNABLE TO CURE W/LCM SLUGS.
734 | 03/12/2022 | NBR-20S | JLMD-17 | ARM | 12 Mar 1300 - 2130 | 8.5 | 8.5 | 893372 |  | WON | WTHR | NA | 9530 | SUSPEND OPERATIONS DUE TO HIGH WINDS.
736 | 03/12/2022 | NBR-783S | NJYN-89 | BHT | 05 Mar 0300 - 0500 | 24 | 81 | 893035 |  | TF | FOT | BIT | 6603 | ENCOUNTERED LOW ROP, POOH TO SURFACE FOUND TWO CONES W/ TWO LEGS LOST IN HOLE FROM BHI KEMERA BIT
738 | 03/12/2022 | NBR-797S | UTMN-3145 | GOC | 12 Mar 2030 - 2145 | 1.25 | 1.25 | 893370 |  | TF | XTTE | CTRQ | 2990 | ALGHAITH POWER TONG/JAM UNIT NOT GIVEN THE PROPER TORQUE, CHANGED WITH BACKUP.
740 | 03/12/2022 | SINO-19L | UTMN-1074 | ARM | 12 Mar 0845 - 0945 | 1 | 1 | 893331 |  | WO | SRVC | NA | 10063 | LOST COMMUNICATION WITH GOC DUE TO VSAT SYSTEM DOWN.
742 | 03/12/2022 | SINO-32L | SHYB-385 | RIG | 12 Mar 1830 - 1930 | 1 | 1 | 893354 |  | RR | FPMP | MPMP | 3846 | LOW DRAW WORK AIR PRESSURE, TROUBLESHOOT & FIX SAME.
743 | 03/12/2022 | SINO21 | ABQQ-133 | RIG | 12 Mar 1530 - 1730 | 2 | 2 | 893369 |  | RR | FOT | DWKS | 4924 | RIG REPAIR.
745 | 03/12/2022 | SINO21 | ABQQ-133 | WUD | 12 Mar 1100 - 1400 | 3 | 3 | 893353 |  | TF | FOT | MPD | 7685 | RCD CLAMP
746 | 03/12/2022 | SINO21 | ABQQ-133 | RIG | 12 Mar 1530 - 1730 | 2 | 2 | 893369 |  | RR | FOT | DWKS | 4924 | RIG REPAIR.
748 | 03/12/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 24 | 88.5 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
750 | 03/12/2022 | SNF036 | MRJN-901 | RIG | 12 Mar 0730 - 1315 | 2 | 2 | 893350 |  | RR | FOT | RWCS | 8189 | 18-3/4" PIPE RAM CLOSING TIME EXCEED 30 SECS DURING DRAW DOWN TEST (34 SEC). TROUBLE SHOOTING AND CHECK ACCUMULATOR UNITE BOTTLES. RE-CHARGE 3 BOTTLES. PERFORM DRAW DOWN TEST - OK. ALL PIPE 18-3/4" RAMS CLOSE IN 30 SECS. RESUME NORMAL OPERATIONS.
752 | 03/12/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 105 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
754 | 03/12/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 0430 | 23.5 | 30.25 | 893267 |  | FISH | HERR | BHA | 9253 | HAD ERRATIC TORQUE 2 FT OFF BOTTOM AND OBSERVED JUNK MARKS ON BIT AND BIT SUB AT SURFACE
756 | 03/12/2022 | SSA-5964 | HRDH-1343 | RIG | 12 Mar 1000 - 1500 | 5 | 5 | 893272 |  | RR | FOT | TDS | 4030 | WHILE TOP DRIVE MOVEMENT UP, TDS HYDRAULIC SERVICE LOOP STUCK ON PAD-EYE SUPPORT ON BACK SIDE OF DERRICK, CAUSED DAMAGE TO SERVICE LOOP. REPLACED DAMAGED HYDRAULIC SERVICE LOOP WITH NEW BACKUP ONE. FUNCTION TESTED TDS, OK.
758 | 03/12/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 120 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
760 | 03/12/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 415 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
761 | 03/13/2022 | ADC-17 | ZULF-1211 | RIG | 13 Mar 2245 - 2315 | .5 | .5 | 893374 |  | JF | XTRI | NA | 0 | EXCESSIVE TIME ON RIG CREW WHILE RIG UP CMT HEAD & SURFACE LINES
763 | 03/13/2022 | ADC-17 | ZULF-1211 | HCM | 13 Mar 0030 - 0500 | 4.5 | 4.5 | 893274 |  | TF | FOT | PUMP | 4870 | MIXING PUMP COMPLETELY PLUGGED WITH CEMENT, HALLIBURTON CREW CLEANED MIXING TANK, TRY MIXING AGAIN, NO SUCCESS
764 | 03/13/2022 | ADC-17 | ZULF-1211 | RIG | 13 Mar 2245 - 2315 | .5 | .5 | 893374 |  | JF | XTRI | NA | 0 | EXCESSIVE TIME ON RIG CREW WHILE RIG UP CMT HEAD & SURFACE LINES
766 | 03/13/2022 | ADC-43L | HWYH-1226 | TK3 | 13 Mar 1330 - 0500 | 15 | 15 | 893376 |  | DD | AINC | BHA | 14710 | SLB DIRECTIONAL BHA WAS UNABLE TO BUILD INCLINATION DUE TO RSS TOOL FAILURE.
768 | 03/13/2022 | ADC-70 | SFNY-4230 | HWP | 12 Mar 1400 - 0500 | 13 | 25.25 | 893351 |  | TF | FOT | WLT | 5548 | HALLIBURTON LOST COMMUNICATION WITH RDT TOOL. TROUBLSHOOT SAME; NO SUCCESS. POH TO C/O RDT TOOL.
770 | 03/13/2022 | ADES-173 | HRDH-2256 | RIG | 11 Mar 0545 - 0500 | 21 | 67.75 | 893309 |  | BHA | ETRQ | BHA | 9822 | DRILLSTRING STUCK ON BOTTOM
772 | 03/13/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 124.75 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 150 BBL/HR.
774 | 03/13/2022 | ADM-511 | MRJN-799 | ARM | 10 Mar 0330 - 0500 | 24 | 73.5 | 893308 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER CONDITION TO CONTINUE PRELOAD OPERATION
776 | 03/13/2022 | ADM-655 | BRRI-218 | ARM | 12 Mar 1530 - 0500 | 24 | 37.5 | 893366 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER FOR RIG MOVE TO BRRI-218 PLATFORM.
778 | 03/13/2022 | ADM-656 | ABSF-169 | ARM | 13 Mar 0500 - 0500 | 24 | 24 | 893377 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER FOR BACKLOAD CEMENT,DP AND FLOWBACK EQUIPMENT TO PREPARE FOR RIG MOVE.
780 | 03/13/2022 | ARO-2001 | BRRI-184 | WWD | 09 Mar 2115 - 0500 | 24 | 103.75 | 893285 |  | TF | FOT | WPSTK | 8215 | WHILE TRIPPING OUT OF THE HOLE WHIPSTOCK BECAME TIGHT. MAX OVERPULL APPLIED AND PACKER/ANCHOR SHEARED.
782 | 03/13/2022 | ARO-3004 | MRJN-2060 | RIG | 13 Mar 0230 - 0500 | 2.5 | 2.5 | 893361 |  | RR | FPMP | MPMP | 0 | TROUBLESHOOT PUMPS POP-OFF.
784 | 03/13/2022 | ARO-4001 | MRJN-533 | RIG | 13 Mar 1730 - 0030 | 7 | 7 | 893358 |  | RR | FOT | PSYS | 15330 | OBSERVED LIMITED POWER ALARM ON DRILLING SYSTEM DUE TO TEMPORARY MEMORY ON POWER SYSTEM SBC BEING FULL, TO RESOLVE ALARM THE DRILLING SYSTEM NEED TO FULLY REBOOTED (DURING REBOOTING WILL NOT ABLE TO OPERATE ALL RIG FLOOR EQUIPMENT), REBOOTED, SYSTEM WORKING OK.
786 | 03/13/2022 | CG-1 | ZULF-1201 | RIG | 11 Mar 0500 - 0000 | 19 | 64.5 | 893269 |  | JF | HERR | NA | 0 | EXCEEDED THE PUMPING PARAMETERS & ACTIVATE WFD HANGER @ SURFACE.
788 | 03/13/2022 | DQ-57L | KHRS-53 | TK1 | 13 Mar 0745 - 0500 | 21.25 | 21.25 | 893359 |  | DRG | WNCA | NA | 4454 | UNABLE TO PASS WINDOW WITH 6-1/8" RSS/LWD ASSEMBLY.
790 | 03/13/2022 | ENSCO-54 | ABSF-45 | KSC | 07 Mar 1030 - 1130 | 6.5 | 145 | 893146 |  | TF | FOT | ESPL | 4312 | LOST COMMUNICATION WITH ESP CABLE. PHASE TO GROUND - GROUNDED TROUBLE SHOOT- NO SUCCESS.
792 | 03/13/2022 | EXL-IVA | SFNY-1660 | BAW | 13 Mar 0145 - 0500 | 3.25 | 3.25 | 893339 |  | TF | FOT | WLT | 0 | BAKER HUGHES COULD NOT GET A GOOD FUNCTION TEST ON LOGGING TOOLS FOR RUN#5 BEFORE RIH ON DRILL PIPE.
794 | 03/13/2022 | HI-5 | MHRH-58 | SWL | 12 Mar 1300 - 0500 | 20.5 | 32 | 893367 |  | TF | FOT | WLT | 7646 | SCHLUMBERGER WIRE LINE DUAL PACKER LOST SEAL EFFICIENCY WHILE PUMP OUT AT 7646.5 FT.
796 | 03/13/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0700 | 2 | 654.25 | 891345 |  | STUK | STBH | BHA | 17371 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
798 | 03/13/2022 | NBR-196S | SDGM-1226 | ARM | 12 Mar 1930 - 1200 | 7 | 16.5 | 893371 |  | LCIR | CFFM | LCM | 430 | ENCOUNTERED COMPLETE LOSSES @ 430', UNABLE TO CURE W/LCM SLUGS.
800 | 03/13/2022 | NBR-783S | NJYN-89 | BHT | 05 Mar 0300 - 0500 | 24 | 105 | 893035 |  | TF | FOT | BIT | 6603 | ENCOUNTERED LOW ROP, POOH TO SURFACE FOUND TWO CONES W/ TWO LEGS LOST IN HOLE FROM BHI KEMERA BIT
802 | 03/13/2022 | PA-861S | HRDH-1060 | BAW | 13 Mar 1200 - 1700 | 5 | 5 | 893373 |  | TF | FOT | TPCH | 12761 | POOH W/ 2.5" RCT CUTTER, CHECK TOOLS ON SURFACE AND OBSERVE MISFIRE
804 | 03/13/2022 | SINO-18 | ADHN-10 | SPS | 13 Mar 0345 - 0415 | .5 | .5 | 893363 |  | TF | XTTE | MWD | 14998 | MWD LOST SIGNAL, TROUBLE SHOOTING THREE TIMES WITH NO SUCCESS.
806 | 03/13/2022 | SL-7 | ZULF-1335 | NCS | 13 Mar 1245 - 1500 | 2.25 | 2.25 | 893275 |  | JF | FOT | SQZ | 7463 | UNABLE TO SUPPLY MIX WATER FROM BATCH MIXER TO CMT UNIT. TROUBLESHOOT WHILE CIRCULATING W/ 200 GPM, 680 PSI.
808 | 03/13/2022 | SND-2002 | WAQR-9 | BAW | 11 Mar 1200 - 0300 | 19.5 | 34 | 893310 |  | TF | FOT | WLT | 16011 | BAKER WL LOST COMMUNICATION WITH LOGGING TOOLS.
810 | 03/13/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 23.5 | 112 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
812 | 03/13/2022 | SNF036 | MRJN-901 | HWP | 13 Mar 2245 - 0500 | 6.25 | 6.25 | 893362 |  | TF | FOT | WLT | 8189 | LOST COMMUNICATION WITH HALL WL RDT TOOL, TROUBLESHOOTING ISSUE. CHANGE OUT PUMP DOWN HEAD FEMALE WET CONNECTOR WITH NO SUCCESS. POOH WITH RDT LOGGING TOOL TO C/O FAILED TOOL.
814 | 03/13/2022 | SP-105 | SHRR-818 | WWL | 13 Mar 2030 - 0000 | 3.5 | 3.5 | 893357 |  | WO | MATL | NA | 2150 | WAIT ON WEATHERFORD COMPANY FOR RECEIVING BOP
816 | 03/13/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 129 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
818 | 03/13/2022 | SSA-201 | HRDH-2176 | WCS | 13 Mar 0200 - 0500 | 3 | 3 | 893338 |  | TF | HERR | TBG | 6696 | WFD OPERATOR MADE OVER TORQUE FOR JOINT #162, AND CONTINUE RIH WITH 20 JOINTS MORE WITHOUT INFORMING RIG FOREMAN, AFTER THAT HE DISCLOSE ABOUT THE ISSUE, THE DECISION WAS POOH W/ 20 JOINTS OF TUBING TO INVESTIGATE THE CONNECTION (PIN & BOX). THIS TIME IS DOWN TIME ON WEATHERFORD RUNNING COMPANY.
820 | 03/13/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 0500 | 24 | 54.25 | 893267 |  | FISH | HERR | BHA | 9253 | ERRATIC TORQUE 2 FT OFF BOTTOM AND OBSERVED JUNK MARKS ON BIT AND BIT SUB AT SURFACE. RECOVERED WITH RCJB LOST ROLLER FROM 12 1/4" ROLLER REAMER.
822 | 03/13/2022 | SSA-5865 | ABJF-50 | ND1 | 13 Mar 1830 - 0430 | 10 | 10 | 893378 |  | BHA | FOT | MMOT | 2740 | WHILE DRILLING HAD SUDDEN SPIKE IN DRILL PIPE PRESSURE. COULD NOT CIRCULATE ANY MORE.
824 | 03/13/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 144 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
826 | 03/13/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 439 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
828 | 03/14/2022 | ADC-17 | ZULF-1211 | HCM | 13 Mar 0030 - 0645 | 1.75 | 6.25 | 893274 |  | TF | FOT | PUMP | 4870 | MIXING PUMP COMPLETELY PLUGGED WITH CEMENT, HALLIBURTON CREW CLEANED MIXING TANK, TRY MIXING AGAIN, NO SUCCESS
830 | 03/14/2022 | ADC-43L | HWYH-1226 | TK3 | 13 Mar 1330 - 2200 | 15 | 30 | 893376 |  | DD | AINC | BHA | 14710 | SLB DIRECTIONAL BHA WAS UNABLE TO BUILD INCLINATION DUE TO RSS TOOL FAILURE.
832 | 03/14/2022 | ADC-70 | SFNY-4230 | HWP | 12 Mar 1400 - 0600 | 1 | 40 | 893351 |  | TF | FOT | WLT | 5548 | HALLIBURTON LOST COMMUNICATION WITH RDT TOOL. TROUBLSHOOT SAME; NO SUCCESS. POH TO C/O RDT TOOL.
834 | 03/14/2022 | ADES-173 | HRDH-2256 | RIG | 11 Mar 0545 - 0500 | 24 | 91.75 | 893309 |  | BHA | ETRQ | BHA | 9822 | DRILLSTRING STUCK ON BOTTOM
836 | 03/14/2022 | ADES-798 | JFYN-11 | RIG | 14 Mar 1915 - 0500 | 9.75 | 9.75 | 893277 |  | JF | HERR | BHA | 3889 | ACCIDENTALLY HIT BTM W/ 120 KLBS WOB.
838 | 03/14/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 19 | 143.75 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 150 BBL/HR.
840 | 03/14/2022 | ADM-339 | RBYN-55 | RIG | 14 Mar 0300 - 0345 | .75 | .75 | 893387 |  | RR | FOT | DRRK | 5166 | UNABLE TO POSITION XY-RACKER TO WELL CENTER.
842 | 03/14/2022 | ADM-511 | MRJN-799 | ARM | 10 Mar 0330 - 0500 | 24 | 97.5 | 893308 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER CONDITION TO CONTINUE PRELOAD OPERATION
844 | 03/14/2022 | ADM-655 | BRRI-218 | ARM | 14 Mar 0500 - 0400 | 23 | 23 | 893276 |  | WO | SRVC | NA | 0 | WAIT ON BARGE QMS AL MARYAH TO MOVE OUT AND CLEAR LOCATION BRRI-218 PLATFORM TO MOVE THE RIG.
846 | 03/14/2022 | ADM-656 | ABSF-169 | ARM | 13 Mar 0500 - 0500 | 24 | 48 | 893377 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO CONTINUE BACKLOAD OPS AND TO MOVE THE RIG TO NEXT PLATFORM ABSF-162/170.
848 | 03/14/2022 | ARO-2001 | BRRI-184 | WWD | 09 Mar 2115 - 0500 | 24 | 127.75 | 893285 |  | TF | FOT | WPSTK | 8215 | WHILE TRIPPING OUT OF THE HOLE WHIPSTOCK BECAME TIGHT. MAX OVERPULL APPLIED AND PACKER/ANCHOR SHEARED.
850 | 03/14/2022 | ARO-3002 | MRJN-813 | HML | 14 Mar 0630 - 0500 | 22.5 | 22.5 | 893343 |  | TF | FOT | WPSML | 8619 | ATTEMPTED TO PASS TRANSITION JOINT WITH 7" HPH PKR & CHAMP PKR WITH NO SUCCESS . APPLIED MAXIMUM PARAMETERS AS PER MLT & HAL COMPLETIONS ENGINEER.
852 | 03/14/2022 | ARO-3004 | MRJN-2060 | RIG | 13 Mar 0230 - 0845 | .25 | 2.75 | 893361 |  | RR | FPMP | MPMP | 0 | TROUBLESHOOT PUMPS POP-OFF.
854 | 03/14/2022 | CG-1 | ZULF-1201 | ARM | 14 Mar 1330 - 0500 | 15.5 | 15.5 | 893282 |  | STUK | STCT | SCRN | 9545 | GOT RESTRICTION, ATTEMPT TO WORK HELD UP AREA. TRY TO POH THEN GOT STUCK WITH LOWER COMPLATION SCREENS.
855 | 03/14/2022 | DPS-4 | MDRK-54 | BCR | 14 Mar 1215 - 1315 | 1 | 1 | 893279 |  | JF | XTRI | CTRQ | 7075 | CRT MALFUNCTION- HAD DIFFICULTIES TO B.OUT CRT AFTER M/U EACH JOINT. BAKER TROUBLESHOOT THE PROBLEM WITHOUT SUCCESS.
857 | 03/14/2022 | DPS-4 | MDRK-54 | BCR | 14 Mar 0800 - 1000 | 2 | 2 | 893278 |  | JF | XTRI | CTRQ | 7075 | EXCCESS TIME TO R/U CRT & CSG RUNNING TOOLS
858 | 03/14/2022 | DPS-4 | MDRK-54 | BCR | 14 Mar 1215 - 1315 | 1 | 1 | 893279 |  | JF | XTRI | CTRQ | 7075 | CRT MALFUNCTION- HAD DIFFICULTIES TO B.OUT CRT AFTER M/U EACH JOINT. BAKER TROUBLESHOOT THE PROBLEM WITHOUT SUCCESS.
860 | 03/14/2022 | DQ-57L | KHRS-53 | TK1 | 13 Mar 0745 - 0915 | 4.25 | 25.5 | 893359 |  | DRG | WNCA | NA | 4454 | UNABLE TO PASS WINDOW WITH 6-1/8" RSS/LWD ASSEMBLY.
862 | 03/14/2022 | ENSCO-76 | MRJN-2004 | RIG | 14 Mar 1700 - 0500 | 12 | 12 | 893280 |  | UPRA | OTH | NA | 14660 | N/D 18-3/4" 15K BOP STACK. COULD NOT LIFT TWO SINGLE RAM UNITS WITH LIFTING DEVICE DUE TO CAPACITY LIMITATIONS.
864 | 03/14/2022 | EXL-IVA | SFNY-1660 | BAW | 13 Mar 0145 - 0600 | 1 | 4.25 | 893339 |  | TF | FOT | WLT | 0 | BAKER HUGHES COULD NOT GET A GOOD FUNCTION TEST ON LOGGING TOOLS FOR RUN#5 BEFORE RIH ON DRILL PIPE.
866 | 03/14/2022 | HI-5 | MHRH-58 | SWL | 12 Mar 1300 - 0230 | 21.5 | 53.5 | 893367 |  | TF | FOT | WLT | 7646 | SCHLUMBERGER WIRE LINE DUAL PACKER LOST SEAL EFFICIENCY WHILE PUMP OUT AT 7646.5 FT.
868 | 03/14/2022 | NBR-115S | HRDH-2140 | RIG | 14 Mar 1545 - 1700 | 1.25 | 1.25 | 893342 |  | RR | FOT | RWCS | 16102 | DURING ACCUMULATOR DRAWDOWN TEST FOUND THE MANIFOLD PRESSURE REGULATOR ON THE ACCUMULATOR UNIT LEAKING.
870 | 03/14/2022 | NBR-783S | NJYN-89 | BHT | 05 Mar 0300 - 0500 | 24 | 129 | 893035 |  | TF | FOT | BIT | 6603 | ENCOUNTERED LOW ROP, POOH TO SURFACE FOUND TWO CONES W/ TWO LEGS LOST IN HOLE FROM BHI KEMERA BIT
872 | 03/14/2022 | SINO-16 | FDHL-128 | OSL | 14 Mar 0300 - 0500 | 2 | 2 | 893405 |  | TF | FOT | SLICK | 7990 | OILSERV SLICK LINE DROP THE WIRE WHILE PULLING OUT OF HOLE WITH INTERWELL 3-1/2" PTP. { OILSERV SLICK LINE RIH TO RETRIEVE 3-1/2" INTERWELL PTP, LATCH IN & RELEASED 3-1/2" PUMP THRU PLUG, POOH 60' & SUDDENLY SLICK LINE WIRE CUT AT SURFACE +/-20F FROM SPOOLER DRUM UNIT & DROP IN HOLE (+/- 7,990FT OF 0.125" SLICK LINE PLUS 22FT OF GS PULLING TOOL BHA) }.
874 | 03/14/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 24 | 136 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
876 | 03/14/2022 | SNF036 | MRJN-901 | HWP | 13 Mar 2245 - 0330 | 22.5 | 28.75 | 893362 |  | TF | FOT | WLT | 8189 | LOST COMMUNICATION WITH HALL WL RDT TOOL, TROUBLESHOOTING ISSUE. CHANGE OUT PUMP DOWN HEAD FEMALE WET CONNECTOR WITH NO SUCCESS. POOH WITH RDT LOGGING TOOL TO C/O FAILED TOOL.
878 | 03/14/2022 | SP-105 | SHRR-818 | WWL | 14 Mar 2130 - 0430 | 7 | 7 | 893385 |  | TF | FOT | WLT | 2250 | HAD DENSITY SENSOR NOT WORKING WHILE LOGGING JOB.
880 | 03/14/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 153 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
882 | 03/14/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 0500 | 24 | 78.25 | 893267 |  | FISH | HERR | BHA | 9253 | ONE ROLLER SEGMENT WAS LOST IN THE HOLE FROM THE 12 1/4" ROLLER REAMER , BHA WAS PULLED & LAIED DOWN WITHOUT REPORTING THE MISSED ROLLER TO ARAMCO FOREMAN. AFTER RUNNING CSG & WHILE DRILL OUT THE 8 1/2" RAT HOLE. OBSERVED ERRATIC TORQUE & JUNK MARKS ON BHA. THE LOST ROLLER WAS LATER RECOVERED WITH THE RCJB.
884 | 03/14/2022 | SSA-5865 | ABJF-50 | ND1 | 13 Mar 1830 - 1230 | 7.5 | 17.5 | 893378 |  | BHA | FOT | MMOT | 2740 | WHILE DRILLING HAD SUDDEN SPIKE IN DRILL PIPE PRESSURE. COULD NOT CIRCULATE ANY MORE.
886 | 03/14/2022 | SSA-5917 | HRDH-2344 | RIG | 13 Mar 2200 - 0030 | 19.5 | 26.5 | 893364 |  | RR | FOT | PSYS | 11227 | TDS, DRAWWORKS & PUMPS TRIP OUT, TROUBLESHOOTING PCR & VFD ROOM.
888 | 03/14/2022 | SSA-5964 | HRDH-1343 | RIG | 14 Mar 1800 - 2000 | 2 | 2 | 893344 |  | RR | FOT | PSYS | 9757 | COMMUNICATION LOST BETWEEN VFD & TOP DRIVE. TROUBLESHOOTING, FIXED & FUNCTION TESTED, OK.
890 | 03/14/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 168 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
892 | 03/14/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 463 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
894 | 03/15/2022 | 910TE | DMMM-613 | BLH | 15 Mar 0600 - 1600 | 10 | 10 | 893449 |  | TF | FOT | HGRL | 2624 | WHILE CIRCULATION OBSERVED RETURN FROM DEBRIS BARRIER ABOVE LINER PBR (NO SEAL BETWEEN RUNNING TOOL AND LINER. SUSPECTED RS PACK OFF FAILED). L/D BAKER 7" LINER HANGER & REPLACE WITH NEW BAKER 7" LINER HANGER.
896 | 03/15/2022 | ADC-16 | JAHM-6 | ARM | 15 Mar 2100 - 0500 | 8 | 8 | 893463 |  | STUK | HINW | WLT | 7182 | ORA SAMPLING TOOLS ON WL GOT STUCK
898 | 03/15/2022 | ADC-36 | SDGM-1234 | SPS | 14 Mar 2330 - 2115 | 15.75 | 20.75 | 893455 |  | BHA | FOT | MWD | 4011 | STRING GOT PLUGGED, POOH & CHECKED BHA FOUND THE FLOW TUBE STUCK INSIDE MWD TOOL & ALL STRING WET ABOVE THE TOOL.
900 | 03/15/2022 | ADC-50 | SFNY-1178 | ARM | 14 Mar 2315 - 0500 | 21.25 | 26.75 | 893464 |  | LCIR | UVLC | NA | 2725 | LOST COMPLETE CIRCULATION AT 2,725', SIMILAR TO ALL OTHER WELLS IN SAME PLATFORM.
902 | 03/15/2022 | ADC-65L | HWYH-1273 | FME | 15 Mar 2000 - 0000 | 4 | 4 | 893462 |  | WH | FOT | WH | 7980 | UNABLE TO INSTALL FMC FMH PACK-OFF SEAL.
904 | 03/15/2022 | ADES-173 | HRDH-2256 | RIG | 13 Mar 0500 - 0500 | 23.5 | 68 | 893450 |  | BHA | FOT | RM | 9822 | LOST PART OF ROLLER REAMER.
906 | 03/15/2022 | ADES-798 | JFYN-11 | RIG | 14 Mar 1915 - 0600 | 1 | 10.75 | 893277 |  | JF | HERR | BHA | 3889 | ACCIDENTALLY HIT BTM W/ 120 KLBS WOB.
908 | 03/15/2022 | ADM-266 | ZULF-106 | WI3 | 15 Mar 1945 - 0500 | 9.25 | 9.25 | 893452 |  | TF | FOT | WPSTK | 5907 | UNABLE TO PASS TOW @ 5907' W/ HALL RSS ASSY.
910 | 03/15/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 167.75 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 150 BBL/HR.
912 | 03/15/2022 | ADM-339 | RBYN-55 | RIG | 14 Mar 0300 - 0900 | 3 | 3.75 | 893387 |  | RR | FOT | DRRK | 5166 | UNABLE TO POSITION XY-RACKER TO WELL CENTER.
913 | 03/15/2022 | ADM-511 | MRJN-799 | RIG | 15 Mar 0215 - 0415 | 2 | 2 | 893469 |  | RR | FOT | WATER | 0 | OBSERVED DUMP VALVE STUCK IN OPEN POSITION FOR ONE OF PORT PRELOAD TANK
915 | 03/15/2022 | ADM-511 | MRJN-799 | ARM | 10 Mar 0330 - 1300 | 8 | 105.5 | 893308 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER CONDITION TO CONTINUE PRELOAD OPERATION
916 | 03/15/2022 | ADM-511 | MRJN-799 | RIG | 15 Mar 0215 - 0415 | 2 | 2 | 893469 |  | RR | FOT | WATER | 0 | OBSERVED DUMP VALVE STUCK IN OPEN POSITION FOR ONE OF PORT PRELOAD TANK
917 | 03/15/2022 | ADM-656 | ABSF-169 | MRN | 15 Mar 1500 - 0500 | 14 | 14 | 893425 |  | WO | SRVC | NA | 0 | WAIT ON RIG MOVE MASTER AND RIG MOVE BOATS.
919 | 03/15/2022 | ADM-656 | ABSF-169 | ARM | 13 Mar 0500 - 0800 | 3 | 51 | 893377 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO CONTINUE BACKLOAD OPS AND TO MOVE THE RIG TO NEXT PLATFORM ABSF-162/170.
920 | 03/15/2022 | ADM-656 | ABSF-169 | MRN | 15 Mar 1500 - 0500 | 14 | 14 | 893425 |  | WO | SRVC | NA | 0 | WAIT ON RIG MOVE MASTER AND RIG MOVE BOATS.
922 | 03/15/2022 | ARO-3002 | MRJN-813 | HCO | 14 Mar 0630 - 0500 | 24 | 46.5 | 893343 |  | TF | FOT | PKR | 8619 | ATTEMPTED TO PASS TRANSITION JOINT WITH 7" HPH PKR & CHAMP PKR WITH NO SUCCESS . APPLIED MAXIMUM PARAMETERS AS PER MLT & HAL COMPLETIONS ENGINEER.
924 | 03/15/2022 | ARO-3003 | SFNY-1740 | ARM | 14 Mar 1000 - 0500 | 24 | 31.5 | 893453 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO MOVE RIG TO NEXT LOCATION SFNY-1740.
926 | 03/15/2022 | CG-1 | ZULF-1201 | ARM | 14 Mar 1330 - 0500 | 24 | 39.5 | 893282 |  | STUK | STCT | SCRN | 9545 | GOT RESTRICTION, ATTEMPT TO WORK HELD UP AREA. TRY TO POH THEN GOT STUCK WITH LOWER COMPLATION SCREENS.
928 | 03/15/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 13 | 667.25 | 891345 |  | STUK | STBH | BHA | 16400 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
929 | 03/15/2022 | NBR-783S | NJYN-89 | RIG | 15 Mar 1645 - 0330 | 10.75 | 10.75 | 893446 |  | RR | FOT | TDS | 6436 | FAILURE ON TDS BRAKE SYSTEM
931 | 03/15/2022 | NBR-783S | NJYN-89 | BHT | 05 Mar 0300 - 1645 | 11.75 | 140.75 | 893035 |  | TF | FOT | BIT | 6603 | ENCOUNTERED LOW ROP, POOH TO SURFACE FOUND TWO CONES W/ TWO LEGS LOST IN HOLE FROM BHI KEMERA BIT
932 | 03/15/2022 | NBR-783S | NJYN-89 | RIG | 15 Mar 1645 - 0330 | 10.75 | 10.75 | 893446 |  | RR | FOT | TDS | 6436 | FAILURE ON TDS BRAKE SYSTEM
934 | 03/15/2022 | PA-326S | SAHB-32 | FMC | 15 Mar 1700 - 0500 | 12 | 12 | 893448 |  | JF | HERR | CTRQ | 15608 | IMPROPER JAM MAKE UP CHART.
936 | 03/15/2022 | PA-529S | SHYB-45 | BC | 15 Mar 0500 - 1745 | 12.75 | 12.75 | 893457 |  | JF | HERR | TBG | 7700 | BAKER COMPLETION SUPERVISOR REPORTED WRONG DATA THAT ALL CONTROL LINES RECOVERED DURING THE FISHING OF 3RD PKR, RESULTED IN RUNNING OVERSHOT RUN.
938 | 03/15/2022 | SCTD-2 | HWYH-1193 | RIG | 14 Mar 2100 - 1430 | 9.5 | 17.5 | 893379 |  | BHA | FOT | MMOT | 14800 | LOST VIBS FROM TOOL DURING THE WIPER TRIP. POH TO CHECK BHA & FOUND 2 RINGS LOST FROM TURBINE BEND HOUSING.
940 | 03/15/2022 | SDA | MRJN-733 | FMC | 15 Mar 2245 - 2315 | .5 | .5 | 893456 |  | TF | FOT | TTRQ | 12811 | FRANKS POWER TONG FAILED - UPNABLE TO M/U 4-1/2" TBG. REPLACE TONG WITH BACK UP ONE, CONTINUE OPS.
942 | 03/15/2022 | SINO-16 | FDHL-128 | OSL | 14 Mar 0300 - 1300 | 8 | 10 | 893405 |  | TF | FOT | SLICK | 7990 | OILSERV SLICK LINE CUT & DROPPED THE WIRE WHILE PULLING OUT OF HOLE WITH INTERWELL 3.5" PTP. { OILSERV SLICK LINE RIH TO RETRIEVE 3-1/2" INTERWELL PTP, LATCH IN & RELEASED 3-1/2" PUMP THRU PLUG, POOH 60' & SUDDENLY SLICK LINE WIRE CUT AT SURFACE +/-20F FROM SPOOLER DRUM UNIT & DROP IN HOLE (+/- 7,990FT OF 0.125" SLICK LINE PLUS 22FT OF GS PULLING TOOL BHA) }.
944 | 03/15/2022 | SINO-37L | HWYH-356 | SPS | 15 Mar 2000 - 0500 | 9 | 9 | 893466 |  | BHA | FOT | LWD | 0 | ICRUISE AND LWD NOT COMMUNICATING WITH EACH OTHER WHEN CONNECTED TOGETHER ON RIG FLOOR WHILE SURFACE TESTING.
946 | 03/15/2022 | SINO-42L | HWYH-286 | SPS | 15 Mar 0630 - 0500 | 22.5 | 22.5 | 893467 |  | BHA | FOT | RSS | 0 | SPS ICRUISE HAD NO RESPONSE DURING SHALLOW TEST
948 | 03/15/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 24 | 160 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
950 | 03/15/2022 | SNT-025 | SFNY-1188 | AP2 | 15 Mar 1900 - 0500 | 10 | 10 | 893447 |  | WO | WOPF | NA | 0 | WAITING ON PRODUCING TO GIVE PERMISSION FOR FLOW BACK.
952 | 03/15/2022 | SP-229 | SFNY-4 | HCO | 15 Mar 1930 - 0500 | 9.5 | 9.5 | 893468 |  | WO | WOTO | NA | 0 | UNABLE TO SET PX PLUG IN X NIPPLE AT SURFACE
954 | 03/15/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0400 | 23 | 176 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
956 | 03/15/2022 | SP-260 | HZEM-161014 | SPS | 15 Mar 0530 - 0830 | 3 | 3 | 893465 |  | BHA | FOT | MWD | 13771 | SPS MWD LOST SIGNAL
958 | 03/15/2022 | SSA-201 | HRDH-2176 | SPL | 15 Mar 0630 - 1715 | 8.25 | 8.25 | 893470 |  | TF | FOT | SLICK | 12753 | UNABLE TO SET PR PLUG INSIDE LOWER R-NIPPLE
960 | 03/15/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 0500 | 24 | 102.25 | 893267 |  | FISH | HERR | BHA | 9253 | ONE ROLLER SEGMENT WAS LOST IN THE HOLE FROM THE 12 1/4" ROLLER REAMER , BHA WAS PULLED & LAIED DOWN WITHOUT REPORTING THE MISSED ROLLER TO ARAMCO FOREMAN. AFTER RUNNING CSG & WHILE DRILL OUT THE 8 1/2" RAT HOLE. OBSERVED ERRATIC TORQUE & JUNK MARKS ON BHA. THE LOST ROLLER WAS LATER RECOVERED WITH THE RCJB.
961 | 03/15/2022 | SSA-5970 | HWYH-1257 | NCT | 15 Mar 0000 - 0500 | 5 | 5 | 893451 |  | TF | FOT | CTBG | 19116 | NPS COILED TUBING FAILED TO TAG NO GO, FISHING BHA PARTED AND DROPED INSIDE DRILL STRING.
963 | 03/15/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0000 | 19 | 187 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
964 | 03/15/2022 | SSA-5970 | HWYH-1257 | NCT | 15 Mar 0000 - 0500 | 5 | 5 | 893451 |  | TF | FOT | CTBG | 19116 | NPS COILED TUBING FAILED TO TAG NO GO, FISHING BHA PARTED AND DROPED INSIDE DRILL STRING.
966 | 03/15/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 487 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
968 | 03/16/2022 | ADC-16 | JAHM-6 | ARM | 15 Mar 2100 - 1830 | 13.5 | 21.5 | 893463 |  | STUK | HINW | WLT | 7182 | ORA SAMPLING TOOLS ON WL GOT STUCK
970 | 03/16/2022 | ADC-17 | ZULF-1215 | RIG | 16 Mar 1700 - 1800 | 1 | 1 | 893527 |  | RR | FOT | MPMP | 3151 | CHANGE PISTON OF MUD PUMP#2
972 | 03/16/2022 | ADC-34 | UTMN-2317 | ARM | 15 Mar 2215 - 1600 | 11 | 17.75 | 893526 |  | TH | NARW | NA | 12300 | WHILE RIH WITH HALL. LNR HGR, HAD SLACK WT. @ 12680'. WASH DOWN WITH 2.8 BPM, PRESSURE INCREASED F/ 620 PSI TO 1100 PSI AND COULDN'T PASS.
974 | 03/16/2022 | ADC-50 | SFNY-1178 | ARM | 14 Mar 2315 - 0230 | 20.25 | 47 | 893464 |  | LCIR | UVLC | NA | 2725 | LOST COMPLETE CIRCULATION AT 2,725', SIMILAR TO ALL OTHER WELLS IN SAME PLATFORM.
976 | 03/16/2022 | ADC-59L | HRDH-2232 | TK3 | 16 Mar 1300 - 0315 | 14.25 | 14.25 | 893532 |  | JF | HERR | NA | 13971 | POOH TO REDUCE SHOE TRACK FROM 4 TO 3 JOINTS FOR PERFORATION SPACE-OUT
978 | 03/16/2022 | ADC-62L | ANDR-743 | SDM | 16 Mar 2045 - 2245 | 2 | 2 | 893547 |  | TF | XTTE | LWD | 8248 | TROUBLE SHOOTING RESISTIVITY DATA OF DNM TOOL.
980 | 03/16/2022 | ADES-40 | ANDR-469 | RIG | 16 Mar 1700 - 2100 | 4 | 4 | 893551 |  | JF | XTRI | BOP | 0 | EXCESS TIME TO R/U BOP.
982 | 03/16/2022 | ADM-266 | ZULF-106 | WI3 | 15 Mar 1945 - 0500 | 24 | 33.25 | 893452 |  | TF | FOT | WPSTK | 5907 | UNABLE TO PASS TOW @ 5907' W/ HALL RSS ASSY. (WI3 WHIPSTOCK SERVICES D/T,WIS)
984 | 03/16/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 191.75 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 150 BBL/HR.
986 | 03/16/2022 | ADM-339 | RBYN-55 | RIG | 16 Mar 0830 - 2130 | 8.25 | 8.25 | 893473 |  | RR | FOT | MPMP | 5899 | OBSERVED 1,000 PSI DROP IN STAND PIPE PRESSURE WHILE DRILLING. P/U OFF BOTTOM AND INVESTIGATE THE SAME.
988 | 03/16/2022 | ADM-511 | MRJN-799 | ARM | 16 Mar 0400 - 0500 | 1 | 1 | 893548 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER HIGH WIND SPEED UNABLE TO CONTINUE WORK WITH RIG AFT CRANE TO TRANSFER THE REQUIRED EQUIOMENT TO PLATFORM
990 | 03/16/2022 | ARO-2001 | BRRI-184 | RIG | 16 Mar 2100 - 2200 | 1 | 1 | 893546 |  | RR | FOT | DWKS | 9156 | DRAWWORKS SYSTEM REPAIR.
992 | 03/16/2022 | ARO-3003 | SFNY-1740 | ARM | 14 Mar 1000 - 0500 | 24 | 55.5 | 893453 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO MOVE RIG TO NEXT LOCATION SFNY-1740.
994 | 03/16/2022 | CG-1 | ZULF-1201 | ARM | 14 Mar 1330 - 0500 | 24 | 63.5 | 893282 |  | STUK | STCT | SCRN | 9545 | GOT RESTRICTION, ATTEMPT TO WORK HELD UP AREA. TRY TO POH THEN GOT STUCK WITH LOWER COMPLATION SCREENS.
996 | 03/16/2022 | CR-36A | ZULF-2038 | ARM | 14 Mar 0900 - 0500 | 12.5 | 15.5 | 893406 |  | BHS | CWEL | NA | 7784 | HOLE PACKED OFF AND COULDN'T PERFORM PRIMARY CMT JOB.
998 | 03/16/2022 | ENS-108 | SFNY-1720 | OTH | 16 Mar 1900 - 0500 | 10 | 10 | 893525 |  | WON | WTHR | NA | 0 | SUSPENDED PRE-LOAD OPS DUE TO BAD WEATHER.
999 | 03/16/2022 | JACK-203 | MHWZ-823 | ARM | 16 Mar 0100 - 0500 | 4 | 4 | 893545 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER DUE TO HIGH WIND SPEED FROM 36KM/H TO 40 KM/H. CRANE OPREATION HAS BEED SUSPENDED.
1001 | 03/16/2022 | JACK-203 | MHWZ-823 | SWL | 16 Mar 0900 - 1030 | 1.5 | 1.5 | 893528 |  | JF | AGCB | WLT | 0 | CHECK THE TOOL ON SURFACE. THE HEAD HAVE MISCONNECTION WHICH LEAD TO A TROUBLE SHOOTING ON THE TOOL.
1002 | 03/16/2022 | JACK-203 | MHWZ-823 | ARM | 16 Mar 0100 - 0500 | 4 | 4 | 893545 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER DUE TO HIGH WIND SPEED FROM 36KM/H TO 40 KM/H. CRANE OPREATION HAS BEED SUSPENDED.
1004 | 03/16/2022 | OFGRL | HSBH-23 | ARM | 16 Mar 0045 - 0500 | 4.25 | 4.25 | 893427 |  | WON | WTHR | NA | 11296 | WAIT ON WEATHER FOR CRANE OPERATIONS TO CONTINUE NIPPLE DOWN WELLHEAD
1006 | 03/16/2022 | PA-218S | QTIF-515 | MSD | 16 Mar 0000 - 0130 | 1.5 | 1.5 | 893553 |  | TF | FOT | CTRQ | 1115 | OBSERVE MALFUNCTION IN AL-MASAOOD POWER TONG AND JAM UNIT, FIX SAME.
1008 | 03/16/2022 | PA-326S | SAHB-32 | FMC | 15 Mar 1700 - 0500 | 23 | 35 | 893448 |  | JF | HERR | CTRQ | 15608 | IMPROPER JAM MAKE UP CHART.
1010 | 03/16/2022 | PA-604S | HRDH-1392 | RIG | 16 Mar 0200 - 0400 | 2 | 2 | 893549 |  | RR | FOT | CSYS | 12060 | ATTEMPT TO PRESSURE TEST LINES TO 7,000PSI, UNSUCCESSFUL, LEAKS ON SANAD HP LINE.
1012 | 03/16/2022 | PN-7 | MRJN-775 | RIG | 16 Mar 0930 - 1030 | 1 | 1 | 893529 |  | RR | FOT | DWKS | 7970 | DRAW WORK LUB OIL PRESSURE DROP
1014 | 03/16/2022 | SIN30L | KHRS-1409 | ARM | 11 Mar 0300 - 0700 | 1.5 | 7.25 | 893474 |  | LCIR | UVLC | NA | 135 | DRILL 22" HOLE F/ 135 FT TO 165 FT WITH 0% CIRC. (BLIND DRILL)
1016 | 03/16/2022 | SINO-12L | HRDH-410 | HCM | 16 Mar 1300 - 1615 | 3.25 | 3.25 | 893536 |  | WO | SRVC | NA | 5874 | WIAT ON CONFIRMATION TEST FOR KICK OFF CMT PLUG.
1018 | 03/16/2022 | SINO-16 | FDHL-128 | BAL | 16 Mar 1200 - 1300 | 1 | 1 | 893539 |  | TF | FOT | ESP | 0 | ATTEMPT TO START ESP BAKER VSD( VARIABLE SPEED DRIVE), THE VSD TRIPPED OFF EVERY TIME WHEN INCREASING THE FREQUENCY DUE TO OVERLOAD. TROUBLESHOOTING ON BAKER VSD AND COULDN'T FIX THE PROBLEM, BAKER NEEDS TO REPLACE WITH NEW VSD.
1020 | 03/16/2022 | SINO-1L | ABJF-15 | TK1 | 16 Mar 2200 - 0500 | 7 | 7 | 893552 |  | FISH | FWTS | BHA | 0 | AFTER PUNCHED 3.1/2" TBG OBSERVED JUMP AND DROP IN WEIGHT FROM 400 LBS TO 250 LBS THEN INCREASE TO 400 LBS, PULL OUT TO SURFACE WEIGHT DROPPED FROM 300 LBS TO 100 LBS, LD LUBRICATOR TO CHECK FOUND 2.78" DPU PERFORATOR DROPPED IN THE HOLE.
1022 | 03/16/2022 | SINO-32L | SHYB-385 | RIG | 16 Mar 0630 - 0900 | 2.5 | 2.5 | 893550 |  | RR | FOT | TDS | 5720 | LITTLE VIBRATION ON ADJUSTABLE PAD HYDRAULIC CYLINDER OF UPPER IBOP CONTROL SYSTEM.
1024 | 03/16/2022 | SINO-33L | KHRS-388 | BCR | 16 Mar 0500 - 0830 | 3.5 | 3.5 | 893426 |  | TF | FOT | TTRQ | 8717 | AL-MANSOORI S/L RIH W/ 3.875" HELD DOWN @ 755' (S/L DEPTH) MANY TRIAL TO PASS NO SUCESS,POOH & R/D S/L
1026 | 03/16/2022 | SINO-37L | HWYH-356 | SPS | 15 Mar 2000 - 1400 | 9 | 18 | 893466 |  | BHA | FOT | LWD | 0 | ICRUISE AND LWD NOT COMMUNICATING WITH EACH OTHER WHEN CONNECTED TOGETHER ON RIG FLOOR WHILE SURFACE TESTING.
1028 | 03/16/2022 | SINO-42L | HWYH-286 | SPS | 15 Mar 0630 - 1000 | 5 | 27.5 | 893467 |  | BHA | FOT | RSS | 0 | SPS ICRUISE HAD NO RESPONSE DURING SHALLOW TEST
1029 | 03/16/2022 | SL-7 | ZULF-1335 | SPS | 16 Mar 2230 - 0500 | 6.5 | 6.5 | 893535 |  | BHA | FOT | RSS | 7492 | SPS RSS FAILURE.
1031 | 03/16/2022 | SL-7 | ZULF-1335 | SPS | 16 Mar 2115 - 2200 | .75 | .75 | 893534 |  | BHA | FOT | LWD | 7430 | SPS DOWNLINK & TROUBLESHOOT LOGGING TOOL.
1032 | 03/16/2022 | SL-7 | ZULF-1335 | SPS | 16 Mar 2230 - 0500 | 6.5 | 6.5 | 893535 |  | BHA | FOT | RSS | 7492 | SPS RSS FAILURE.
1034 | 03/16/2022 | SND-2001 | UTMN-2329 | GOC | 16 Mar 0830 - 1030 | 2 | 2 | 893533 |  | WO | WOTO | NA | 2970 | EXCESS TIME BY ALGHAITH TO RU CSG EQUIPMENT DUE TO WAITING ON EQUIPMENT.
1036 | 03/16/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0615 | 1.25 | 161.25 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
1038 | 03/16/2022 | SNT-025 | SFNY-1188 | AP2 | 15 Mar 1900 - 1330 | 8.5 | 18.5 | 893447 |  | WO | WOPF | NA | 0 | WAITING ON PRODUCING TO GIVE PERMISSION FOR FLOW BACK.
1040 | 03/16/2022 | SP-229 | SFNY-4 | HCO | 15 Mar 1930 - 0730 | 2.5 | 12 | 893468 |  | WO | WOTO | NA | 0 | UNABLE TO SET PX PLUG IN X NIPPLE AT SURFACE
1042 | 03/16/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 200 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
1044 | 03/16/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 0500 | 24 | 126.25 | 893267 |  | FISH | HERR | BHA | 9253 | ONE ROLLER SEGMENT WAS LOST IN THE HOLE FROM THE 12 1/4" ROLLER REAMER , BHA WAS PULLED & LAIED DOWN WITHOUT REPORTING THE MISSED ROLLER TO ARAMCO FOREMAN. AFTER RUNNING CSG & WHILE DRILL OUT THE 8 1/2" RAT HOLE. OBSERVED ERRATIC TORQUE & JUNK MARKS ON BHA. THE LOST ROLLER WAS LATER RECOVERED WITH THE RCJB.
1046 | 03/16/2022 | SSA-5868 | HRDH-1946 | WCR | 16 Mar 1130 - 0100 | 13.5 | 13.5 | 893537 |  | TF | FOT | TTRQ | 4720 | HAD TBG OVER TOURQED WHILE RIH W/4 1/2" TBG BY WFD.
1048 | 03/16/2022 | SSA-5891 | HRDH-1178 | SPS | 16 Mar 1245 - 0500 | 15.5 | 15.5 | 893485 |  | BHA | FOT | GMWD | 11869 | LOST COMMUNICATION W/ MWD TOOL.
1050 | 03/16/2022 | SSA-5914 | WDYH-80 | RIG | 16 Mar 0700 - 0830 | 1.5 | 1.5 | 893505 |  | RR | FPMP | MPMP | 13755 | OBSERVED LEAK ON POP OFF VALVE WHILE DRILL 8-3/8" HOLE.
1052 | 03/16/2022 | SSA-5970 | HWYH-1257 | NCT | 15 Mar 0000 - 0500 | 24 | 29 | 893451 |  | TF | FOT | CTBG | 19116 | NPS COILED TUBING FAILED TO TAG NO GO, FISHING BHA PARTED AND DROPED INSIDE DRILL STRING.
1054 | 03/16/2022 | SSA-5971 | UTMN-2302 | WDV | 15 Mar 1730 - 0500 | 5.5 | 10 | 893472 |  | TF | FOT | DV | 11025 | DROP WFD DV OPENING BOMB. GOOD INDICATION TO SET WFD DV (10K) PACKER AT 800 PSI. INCREATE PRESSURE TO 3,500 PSI - NO PRESSURE DROP. BLEED OFF AND PRESSURE UP TO 3,300 PSI - GET SHARP PRESSURE DROP TO 1,000 PSI BUT NO RETURNS. UNABLE TO CIRCULATE WITH STATIC FLUID LEVEL IN ANNULUS. ABLE TO PUMP/SQUEEZE AT 1,400 PSI (PRESSURE REMAINS FLAT) AT 180 GPM WITHOUT RETURNS.
1056 | 03/16/2022 | SSA-5974 | HRDH-1970 | SPS | 16 Mar 1800 - 0100 | 7 | 7 | 893538 |  | BHA | FOT | MWD | 13313 | SPS WERE NOT ABLE TO DETECT MWD SIGNAL AT SURFACE WHILE DRILLING 8-3/8" HOLE SECTION
1058 | 03/16/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 511 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1060 | 03/17/2022 | ADC-16 | JAHM-6 | SWL | 15 Mar 2100 - 2030 | 4 | 25.5 | 893463 |  | WO | WOTO | NA | 7182 | WAIT ON SAMPLE CHAMBERS FROM SLB
1061 | 03/17/2022 | ADC-17 | ZULF-1215 | RIG | 17 Mar 0315 - 0345 | .5 | .5 | 893592 |  | RR | FOT | ACDC | 4572 | WHILE DRILLING @4572' STOP RECEIVING DATA, STOP DRILLING, PICK-UP OFF BTM FOUND LOOSE ON RIG CABLE FIXED CABLE AND START RECEIVING DATA
1063 | 03/17/2022 | ADC-17 | ZULF-1215 | RIG | 17 Mar 0915 - 1030 | 1.25 | 1.25 | 893568 |  | RR | FOT | MPMP | 3755 | WHILE DRILLING @3755 FT, HAD 930 PSI PRESSURE DROP OF SPP, STOP DRILLING, PICK-UP 30 FT OFF-BTM FOUND OFF BTM PRESSURE DROPPED 700 PSI, STOP PUMPING, WHILE RECIPROCATE STRING, PT MUD PUMPS & SURFACE LINES TO 3000 PSI SEPARATELY, GOOD TEST, CHECK MUD PUMP#2, FOUND PLUNGER SPRING BROKEN, CHANGE SPRING, START-UP PUMPS HAD NORMAL ON/OFF BTM SPP.
1064 | 03/17/2022 | ADC-17 | ZULF-1215 | RIG | 17 Mar 0200 - 0215 | .25 | .25 | 893591 |  | RR | FOT | MPMP | 4528 | WHILE DRILLING @4528 FT, HAD 1091 PSI PRESSURE DROP OF SPP, STOP DRILLING, PICK-UP 30 FT OFF-BTM FOUND OFF BTM PRESSURE DROPPED 437 PSI, STOP PUMPING, WHILE RECIPROCATE STRING, CHECK MUD PUMP#1, FOUND VALVE SPRING BROKEN, CHANGE SPRING, START-UP PUMPS HAD NORMAL ON/OFF BTM SPP.
1065 | 03/17/2022 | ADC-17 | ZULF-1215 | RIG | 17 Mar 0315 - 0345 | .5 | .5 | 893592 |  | RR | FOT | ACDC | 4572 | WHILE DRILLING @4572' STOP RECEIVING DATA, STOP DRILLING, PICK-UP OFF BTM FOUND LOOSE ON RIG CABLE FIXED CABLE AND START RECEIVING DATA
1067 | 03/17/2022 | ADC-34 | UTMN-2317 | ARM | 15 Mar 2215 - 0500 | 6.5 | 24.25 | 893526 |  | TH | NARW | NA | 12300 | WHILE RIH WITH HALL. LNR HGR, HAD SLACK WT. @ 12680'. WASH DOWN WITH 2.8 BPM, PRESSURE INCREASED F/ 620 PSI TO 1100 PSI AND COULDN'T PASS.
1069 | 03/17/2022 | ADC-50 | SFNY-1178 | ARM | 14 Mar 2315 - 0500 | 24 | 71 | 893464 |  | LCIR | UVLC | NA | 2725 | LOST COMPLETE CIRCULATION AT 2,725', SIMILAR TO ALL OTHER WELLS IN SAME PLATFORM.
1070 | 03/17/2022 | ADC-59L | HRDH-2232 | TK3 | 17 Mar 1400 - 0500 | 15 | 15 | 893608 | 892986 | WON | WTHR | NA | 13971 | UNABLE TO L/D BOT 4-1/2" X 7" LINER HANGER WITH CRANE. HIGH WIND SPEED 45-54 KM/HR & GUSTS UPTO 65 KM/HR.
1072 | 03/17/2022 | ADC-59L | HRDH-2232 | TK3 | 16 Mar 1300 - 1400 | 9 | 23.25 | 893532 |  | JF | HERR | NA | 13971 | POOH TO REDUCE SHOE TRACK FROM 4 TO 3 JOINTS FOR PERFORATION SPACE-OUT
1073 | 03/17/2022 | ADC-59L | HRDH-2232 | TK3 | 17 Mar 1400 - 0500 | 15 | 15 | 893608 | 892986 | WON | WTHR | NA | 13971 | UNABLE TO L/D BOT 4-1/2" X 7" LINER HANGER WITH CRANE. HIGH WIND SPEED 45-54 KM/HR & GUSTS UPTO 65 KM/HR.
1075 | 03/17/2022 | ADES-174 | GHZL-88 | RIG | 17 Mar 1300 - 1430 | 1.5 | 1.5 | 893593 |  | RR | FOT | TDS | 3090 | FIXING ELECTRICAL PROBLEM ON TOP DRIVE BLOWER MOTOR.
1077 | 03/17/2022 | ADM-266 | ZULF-106 | WI3 | 15 Mar 1945 - 1300 | 8 | 41.25 | 893452 |  | TF | FOT | WPSTK | 5907 | UNABLE TO PASS TOW @ 5907' W/ HALL RSS ASSY. (WI3 WHIPSTOCK SERVICES D/T,WIS)
1079 | 03/17/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 215.75 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 150 BBL/HR.
1081 | 03/17/2022 | ADM-511 | MRJN-799 | ARM | 16 Mar 0400 - 0500 | 7.5 | 8.5 | 893548 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER HIGH WIND SPEED UNABLE TO CONTINUE WORK WITH RIG CRANES TO TRANSFER THE REQUIRED EQUIOMENT TO PLATFORM
1083 | 03/17/2022 | ADM-655 | BRRI-218 | ARM | 17 Mar 1200 - 0500 | 17 | 17 | 893585 |  | WON | WTHR | NA | 0 | ATTEMPT TO RIG UP SLICK LINE WIND SPEED 37-40 KNTS UNABLE TO OPERATE CRANES.
1085 | 03/17/2022 | ADM-656 | ABSF-169 | ARM | 17 Mar 0300 - 0500 | 2 | 2 | 893607 |  | WON | WTHR | NA | 0 | WOW DUE TO HIGH WIND SPEED (38-42 KNOTS AND SEA SWELL 3.5 -4.0 MTRS)
1087 | 03/17/2022 | ARO-2001 | BRRI-184 | RIG | 16 Mar 2100 - 0245 | 3 | 4 | 893546 |  | RR | FOT | DWKS | 0 | B-MOTOR OF DRAWWORKS NOT WORKING.
1089 | 03/17/2022 | BCTD-3 | HRDH-1375 | RIG | 17 Mar 1930 - 0500 | 8.5 | 8.5 | 893586 |  | DSF | FOT | STRG | 13621 | BHI LOST COMMUNICATION WITH DOWNHOLE TOOL.
1091 | 03/17/2022 | DQ-50L | HRDH-1492 | TK2 | 17 Mar 2030 - 0500 | 7 | 7 | 893569 |  | WON | WTHR | NA | 207 | WAIT ON WEATHER, HIGH WIND SPEED 46-58 KM/HR
1093 | 03/17/2022 | DQ-57L | KHRS-53 | TK1 | 17 Mar 1000 - 1530 | 5.5 | 5.5 | 893556 |  | CMT | HERR | NA | 6147 | WAIT ON CEMENT CONFRIMATION TEST.
1095 | 03/17/2022 | ENS-108 | SFNY-1720 | OTH | 16 Mar 1900 - 0500 | 24 | 34 | 893525 |  | WON | WTHR | NA | 0 | SUSPENDED PRE-LOAD OPS DUE TO BAD WEATHER.
1097 | 03/17/2022 | ENS-140 | RBYN-100 | ARM | 17 Mar 1700 - 0500 | 12 | 12 | 893559 |  | WON | WTHR | NA | 722 | UNABLE TO CONTINUE OPERATIONS DUE TO HIGH WINDS SPEEDS IN EXCESS OF 35KTS AND HIGH SEA STATE
1099 | 03/17/2022 | ENSCO-54 | ABSF-179 | ARM | 17 Mar 0500 - 0500 | 24 | 24 | 893588 |  | WON | WTHR | NA | 0 | ADVERSE WEATHER CONDITION - NOT SUITABLE FOR CONDUCTING RIG MOVE OPERATIONS
1101 | 03/17/2022 | JACK-203 | MHWZ-823 | ARM | 16 Mar 0100 - 0500 | 24 | 28 | 893545 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER DUE TO HIGH WIND SPEED FROM 36KM/H TO 40 KM/H. CRANE OPREATION HAS BEED SUSPENDED.
1103 | 03/17/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0500 | 24 | 715.25 | 891345 |  | STUK | STBH | BHA | 17100 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1105 | 03/17/2022 | OFGRL | HSBH-23 | ARM | 16 Mar 0045 - 0500 | 24 | 28.25 | 893427 |  | WON | WTHR | NA | 11296 | WAIT ON WEATHER FOR CRANE OPERATIONS TO CONTINUE NIPPLE DOWN WELLHEAD
1107 | 03/17/2022 | PA-326S | SAHB-32 | FMC | 15 Mar 1700 - 0330 | 22.5 | 57.5 | 893448 |  | JF | HERR | CTRQ | 15608 | IMPROPER JAM MAKE UP CHART.
1109 | 03/17/2022 | PA-529S | SHYB-45 | BC | 15 Mar 0500 - 1330 | 8.5 | 21.25 | 893457 |  | JF | HERR | TBG | 7700 | BAKER COMPLETION SUPERVISOR REPORTED THAT ALL CONTROL LINE RECOVERED WITH 3RD PKR FISHING RUN, RIH WITH OVERSHOT TO FISH 4TH PKR, FOUND MANY CONTROL LINE EXIST ON TOF.
1111 | 03/17/2022 | RBP-50A | KARN-51 | ARM | 17 Mar 0630 - 0500 | 22.5 | 22.5 | 893554 |  | WON | WTHR | NA | 11296 | UNABLE TO CONTINUE PRE-LOAD OPERATIONS DUE TO ADVERSE WEATHER CONDITIONS (WAVES HITTING BTM OF THE HULL) SUSPEND PRE-LOADING OPS AND JACK-UP TO 20' AIR-GAP.
1113 | 03/17/2022 | RM-74A | KARN-60 | ARM | 17 Mar 0830 - 0500 | 20.5 | 20.5 | 893571 |  | WON | WTHR | NA | 0 | WOW.UNABLE TO REMOVE MOORING LINES OR PERFORM WATER TIGHT INTEGRITY TEST & RIG MOVE DUE TO ADVERSE WEATHER CONDITION
1115 | 03/17/2022 | SCTD-2 | HWYH-1193 | RIG | 17 Mar 1600 - 0500 | 13 | 13 | 893609 |  | BHA | FOT | MMOT | 14127 | LOSING COMMUNICATION WITH DOWNHOLE TOOLS. TROUBLESHOOT WITHOUT SUCCESS.
1117 | 03/17/2022 | SINO-1L | ABJF-15 | TK1 | 16 Mar 2200 - 0500 | 24 | 31 | 893552 |  | FISH | FWTS | BHA | 0 | AFTER PUNCHED 3.1/2" TBG OBSERVED JUMP AND DROP IN WEIGHT FROM 400 LBS TO 250 LBS THEN INCREASE TO 400 LBS, PULL OUT TO SURFACE WEIGHT DROPPED FROM 300 LBS TO 100 LBS, LD LUBRICATOR TO CHECK FOUND 2.78" DPU PERFORATOR DROPPED IN THE HOLE.
1119 | 03/17/2022 | SINO-22 | BRRI-381 | ARN | 17 Mar 1000 - 0200 | 11.25 | 11.25 | 893605 |  | WON | WTHR | NA | 4710 | WAIT ON WEATHER DUE TO HIGH WIND SPEED +50 KM/H.
1121 | 03/17/2022 | SINO-27N | UTMN-438 | ARM | 17 Mar 1900 - 0500 | 9 | 9 | 893572 |  | WON | WTHR | NA | 0 | HAD SAND STORM WITH LOW VISIBILTY & HIGH WIND SPEED UP TO 50 KM/HR.
1123 | 03/17/2022 | SL-7 | ZULF-1335 | SPS | 16 Mar 2230 - 2015 | 15.25 | 21.75 | 893535 |  | BHA | FOT | RSS | 7492 | SPS RSS FAILURE.
1125 | 03/17/2022 | SND-2005 | MHKK-2 | ARM | 17 Mar 0115 - 0500 | 3.75 | 3.75 | 893570 |  | WON | WTHR | NA | 5300 | BAD SAND STORM, WIND SPEED OVER 45 KM/HR.
1127 | 03/17/2022 | SNF036 | MRJN-901 | RIG | 17 Mar 1700 - 1800 | 1 | 1 | 893558 |  | RR | FOT | FL | 8189 | OBSERVED LEAK IN KFDJ DIVERTER LIP SEAL. PULL DIVERTER ASSY AND CHANGE OUT SEAL.
1129 | 03/17/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 224 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
1131 | 03/17/2022 | SSA-101 | BRRI-1145 | ARN | 17 Mar 1700 - 0400 | 10.25 | 10.25 | 893606 |  | WON | WTHR | NA | 9532 | SUSPEND OPERATIONS AND WAIT ON WEATHER DUE TO WIND SPEED OVER 55 KM/H.
1133 | 03/17/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 0500 | 24 | 150.25 | 893267 |  | FISH | HERR | BHA | 9253 | ONE ROLLER SEGMENT WAS LOST IN THE HOLE FROM THE 12 1/4" ROLLER REAMER , BHA WAS PULLED & LAIED DOWN WITHOUT REPORTING THE MISSED ROLLER TO ARAMCO FOREMAN. AFTER RUNNING CSG & WHILE DRILL OUT THE 8 1/2" RAT HOLE. OBSERVED ERRATIC TORQUE & JUNK MARKS ON BHA. THE LOST ROLLER WAS LATER RECOVERED WITH THE RCJB.
1135 | 03/17/2022 | SSA-5865 | ABJF-50 | RIG | 17 Mar 0115 - 0430 | 3.25 | 3.25 | 893589 |  | BHA | FOT | DC | 4152 | ON BOTTOM DRILLING. THERE WAS A SUDDEN DECREASE IN DRILL PIPE PRESSURE AND TORQUE. PICKED UP OFF BOTTOM AND FOUND 63K OF HOOKLOAD LOST. STRING IS TWISTED OFF.
1137 | 03/17/2022 | SSA-5891 | HRDH-1178 | SPS | 16 Mar 1245 - 0500 | 14.25 | 29.75 | 893485 |  | BHA | FOT | GMWD | 11869 | LOST COMMUNICATION W/ MWD TOOL.
1139 | 03/17/2022 | SSA-5914 | WDYH-80 | RIG | 17 Mar 1500 - 0500 | 14 | 14 | 893557 |  | JF | HERR | NA | 13985 | OBSERVED MW OF THE TRIP TANK AT TOP OF BHA CUT BY 2 PCF DUE TO CLEANING RIG FLOOR WITH WATER. TRIP TANK MW FOUND IT 103 PCF INSTEAD OF 105 PCF.
1141 | 03/17/2022 | SSA-5970 | HWYH-1257 | NCT | 15 Mar 0000 - 0500 | 24 | 53 | 893451 |  | TF | FOT | CTBG | 19116 | NPS COILED TUBING FAILED TO TAG NO GO, FISHING BHA PARTED AND DROPED INSIDE DRILL STRING.
1143 | 03/17/2022 | SSA-5971 | UTMN-2302 | WDV | 15 Mar 1730 - 0400 | 20.5 | 30.5 | 893472 |  | TF | FOT | DV | 11025 | DROP WFD DV OPENING BOMB. GOOD INDICATION TO SET WFD DV (10K) PACKER AT 800 PSI. INCREATE PRESSURE TO 3,500 PSI - NO PRESSURE DROP. BLEED OFF AND PRESSURE UP TO 3,300 PSI - GET SHARP PRESSURE DROP TO 1,000 PSI BUT NO RETURNS. UNABLE TO CIRCULATE WITH STATIC FLUID LEVEL IN ANNULUS. ABLE TO PUMP/SQUEEZE AT 1,400 PSI (PRESSURE REMAINS FLAT) AT 180 GPM WITHOUT RETURNS.
1145 | 03/17/2022 | SSA-5974 | HRDH-1970 | SPS | 17 Mar 0530 - 0500 | 23.5 | 23.5 | 893587 |  | BHA | FOT | MWD | 13357 | SPS WERE NOT ABLE TO DETECT MWD SIGNAL AT SURFACE WHILE DRILLING 8-3/8" HOLE SECTION
1147 | 03/17/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 535 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1149 | 03/17/2022 | T218 | UTMN-564 | ARM | 05 Mar 1300 - 0500 | 1.25 | 12.25 | 893050 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER
1151 | 03/18/2022 | ADC-15 | HRDH-1915 | ARM | 18 Mar 1000 - 1400 | 4 | 4 | 893688 |  | WON | WTHR | NA | 10600 | SUSPEND SLICK LINE OPERATIONS DUE TO WEATHER CONDITION.
1153 | 03/18/2022 | ADC-17 | ZULF-1215 | RIG | 17 Mar 0915 - 1030 | .5 | 2 | 893568 |  | RR | FOT | MPMP | 3755 | SPP DROP, REPAIR MUD PUMPS
1155 | 03/18/2022 | ADC-32 | SDGM-1139 | RIG | 04 Feb 0415 - 0700 | 2 | 87.75 | 890891 |  | JF | HERR | SFLN | 10570 | TAGGED ON TOC @ 10,570' [545' BELOW DV TOOL], APPROX. 1766' SHALLOWER THAN PLAN DUE TO MISS-ALIGNMENT ON SURFACE LINES DURING 9-5/8" 1ST STAGE CMT JOB
1157 | 03/18/2022 | ADC-34 | UTMN-2317 | ARM | 15 Mar 2215 - 2045 | 13.75 | 38 | 893526 |  | TH | NARW | NA | 12300 | WHILE RIH WITH HALL. LNR HGR, HAD SLACK WT. @ 12680'. WASH DOWN WITH 2.8 BPM, PRESSURE INCREASED F/ 620 PSI TO 1100 PSI AND COULDN'T PASS.
1159 | 03/18/2022 | ADC-43L | HWYH-1226 | TK3 | 18 Mar 0900 - 0500 | 20 | 20 | 893577 |  | STUK | HINW | WLT | 14895 | WHILE LOGGING UP OH WITH SLB WIRELINE LOGGING TOOLS (HLDS-QCNTHLDS-GR-CAL-XTRA-C) @ 13640 FT, THE WL TOOLSTRING GOT STUCK. UNABLE TO RELEASE.
1161 | 03/18/2022 | ADC-50 | SFNY-1178 | ARM | 14 Mar 2315 - 0500 | 24 | 95 | 893464 |  | LCIR | UVLC | NA | 2725 | LOST COMPLETE CIRCULATION AT 2,725', SIMILAR TO ALL OTHER WELLS IN SAME PLATFORM.
1163 | 03/18/2022 | ADC-52 | HRDH-2312 | ARM | 18 Mar 1000 - 1200 | 2 | 2 | 893703 |  | WON | WTHR | NA | 13287 | HIGH WIND SPEED & REDUCED VISIBLITY. UNABLE TO PERFORM CRITICAL LIFTS REQUIRED.
1164 | 03/18/2022 | ADC-59L | HRDH-2232 | TK3 | 17 Mar 1400 - 1400 | 9 | 24 | 893608 | 892986 | WON | WTHR | NA | 13971 | UNABLE TO L/D BOT 4-1/2" X 7" LINER HANGER WITH CRANE. HIGH WIND SPEED 45-54 KM/HR & GUSTS UPTO 65 KM/HR.
1166 | 03/18/2022 | ADC-59L | HRDH-2232 | TK3 | 16 Mar 1300 - 0500 | 15 | 38.25 | 893532 |  | JF | HERR | NA | 13971 | POOH TO REDUCE SHOE TRACK FROM 4 TO 3 JOINTS FOR PERFORATION SPACE-OUT
1167 | 03/18/2022 | ADC-59L | HRDH-2232 | TK3 | 17 Mar 1400 - 1400 | 9 | 24 | 893608 | 892986 | WON | WTHR | NA | 13971 | UNABLE TO L/D BOT 4-1/2" X 7" LINER HANGER WITH CRANE. HIGH WIND SPEED 45-54 KM/HR & GUSTS UPTO 65 KM/HR.
1169 | 03/18/2022 | ADES-158 | ABQQ-737 | ARM | 17 Mar 1600 - 1300 | 8 | 21 | 893573 |  | WON | WTHR | NA | 11960 | WAITING ON WEATHER DUE TO HIGH WIND SPEED 50 KM/HR.
1171 | 03/18/2022 | ADM-261 | MRJN-138 | ARM | 18 Mar 0645 - 0930 | 2.75 | 2.75 | 893707 |  | WON | WTHR | NA | 0 | WIND GUSTING 47 KTS - WAIT ON WEATHER TO RUN CRANE FOR R/D HALLIBURTON WIRELINE.
1173 | 03/18/2022 | ADM-262 | MRJN-122 | ARM | 18 Mar 2200 - 0500 | 7 | 7 | 893712 |  | WON | WTHR | NA | 7450 | WAIT ON WEATHER FOR THE DELIVERY OF WILDWELL HOT TAPPING EQUIPMENT.
1175 | 03/18/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0115 | 20.25 | 236 | 893229 |  | LCIR | FRFM | NA | 9900 | HAD AVERAGE DOWNHOLE LOSSES 150 BBL/HR.
1177 | 03/18/2022 | ADM-511 | MRJN-799 | ARM | 16 Mar 0400 - 1530 | 10.5 | 19 | 893548 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER HIGH WIND SPEED UNABLE TO CONTINUE WORK WITH RIG CRANES TO TRANSFER THE REQUIRED EQUIOMENT TO PLATFORM
1178 | 03/18/2022 | ADM-655 | BRRI-218 | ARM | 17 Mar 1200 - 1200 | 7 | 24 | 893585 |  | WON | WTHR | NA | 0 | ATTEMPT TO RIG UP SLICK LINE WIND SPEED 37-40 KNTS UNABLE TO OPERATE CRANES.
1180 | 03/18/2022 | ADM-655 | BRRI-218 | EX1 | 18 Mar 2000 - 2200 | 2 | 2 | 893576 |  | TF | FOT | SLICK | 0 | SLICKLINE WIRE PARTED AFTER RELEASING INTERWELL 4-1/2" HEX PLUG WITH NORMAL RELEASING OVERPULL.
1181 | 03/18/2022 | ADM-655 | BRRI-218 | ARM | 17 Mar 1200 - 1200 | 7 | 24 | 893585 |  | WON | WTHR | NA | 0 | ATTEMPT TO RIG UP SLICK LINE WIND SPEED 37-40 KNTS UNABLE TO OPERATE CRANES.
1183 | 03/18/2022 | ADM-656 | ABSF-169 | ARM | 18 Mar 0500 - 0500 | 24 | 24 | 893699 |  | WON | WTHR | NA | 0 | WOW TO OFFLOAD SPUD MATERIAL FROM VESSEL "CABINESS TIDE".
1185 | 03/18/2022 | ARO-2001 | BRRI-184 | HCM | 18 Mar 2000 - 2130 | 1.5 | 1.5 | 893697 |  | TF | FOT | PUMP | 0 | TRIED TO PRESSURE TEST SURFACE LINES WITH 4500 PSI, NEGATIVE, DUT TO CEMENT UNIT VALVE FAILURE.
1187 | 03/18/2022 | ARO-2003 | ZULF-299 | ARM | 18 Mar 0500 - 0500 | 24 | 24 | 893575 |  | WON | WTHR | NA | 0 | WAITING ON WEATHER FOR FIELD SERVICE TO VISIT PLATFORM FOR HANDOVER
1189 | 03/18/2022 | BB-84A | MRJN-588 | ARM | 17 Mar 1530 - 0500 | 24 | 37.5 | 893645 |  | WON | WTHR | NA | 17045 | WAIT ON WEATHER - UNABLE TO OFFLOAD VESSEL
1191 | 03/18/2022 | BCTD-3 | HRDH-1375 | RIG | 17 Mar 1930 - 1330 | 8.5 | 17 | 893586 |  | DSF | FOT | STRG | 13621 | BHI LOST COMMUNICATION WITH DOWNHOLE TOOL.
1193 | 03/18/2022 | CG-1 | ZULF-1201 | ARM | 18 Mar 1500 - 0500 | 14 | 14 | 893725 |  | WON | WTHR | NA | 6000 | WAIT ON WEATHER
1194 | 03/18/2022 | CR-36A | ZULF-2038 | HCA | 17 Mar 2030 - 1015 | 5.25 | 13.75 | 893685 |  | TF | FOT | ACP | 7517 | UNABLE TO STING BACK INTO EZSV TO PERFORM CEMENT SQUEEZE.
1196 | 03/18/2022 | CR-36A | ZULF-2038 | ARM | 14 Mar 0900 - 0500 | 15 | 33 | 893406 |  | BHS | CWEL | NA | 7784 | HOLE PACKED OFF AND COULDN'T PERFORM PRIMARY CMT JOB.
1197 | 03/18/2022 | CR-36A | ZULF-2038 | HCA | 17 Mar 2030 - 1015 | 5.25 | 13.75 | 893685 |  | TF | FOT | ACP | 7517 | UNABLE TO STING BACK INTO EZSV TO PERFORM CEMENT SQUEEZE.
1199 | 03/18/2022 | DQ-57L | KHRS-53 | ARM | 12 Mar 1100 - 0730 | 2.5 | 7.5 | 893273 |  | WON | WTHR | NA | 0 | SUSPEND CRANE LIFT OPERATION DUE TO HIGH WIND SPEED.
1201 | 03/18/2022 | ENS-108 | SFNY-1720 | OTH | 16 Mar 1900 - 0500 | 24 | 58 | 893525 |  | WON | WTHR | NA | 0 | SUSPENDED PRE-LOAD OPS DUE TO BAD WEATHER.
1203 | 03/18/2022 | ENS-140 | RBYN-100 | ARM | 17 Mar 1700 - 1300 | 8 | 20 | 893559 |  | WON | WTHR | NA | 722 | UNABLE TO CONTINUE OPERATIONS DUE TO HIGH WINDS SPEEDS IN EXCESS OF 35KTS AND HIGH SEA STATE
1205 | 03/18/2022 | ENS-141 | MRJN-758 | ARM | 18 Mar 1200 - 1830 | 6.5 | 6.5 | 893709 |  | WON | WTHR | NA | 10370 | WAITING ON N2 TANKS TO BE DELIVERED, TANKS LOADED ON RAWABI-20 BUT BOAT DELAYED IN TANAJIB DUE TO BAD WEATHER.
1207 | 03/18/2022 | ENSCO-54 | ABSF-179 | ARM | 17 Mar 0500 - 0500 | 24 | 48 | 893588 |  | WON | WTHR | NA | 0 | ADVERSE WEATHER CONDITION - NOT SUITABLE FOR CONDUCTING RIG MOVE OPERATIONS
1209 | 03/18/2022 | JACK-203 | MHWZ-823 | ARM | 16 Mar 0100 - 0500 | 24 | 52 | 893545 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER DUE TO HIGH WIND SPEED FROM 36KM/H TO 40 KM/H. CRANE OPREATION HAS BEED SUSPENDED.
1211 | 03/18/2022 | NA-18S | SDGM-442 | ARM | 17 Mar 2000 - 0900 | 4 | 13 | 893625 |  | WON | WTHR | NA | 2200 | HIGH WIND SPEED 50 - 55KM/HR WITH SAND STORM.
1213 | 03/18/2022 | NA-393S | HWYH-1087 | RIG | 18 Mar 1600 - 1800 | 2 | 2 | 893695 |  | RR | FOT | EDR | 16100 | RIG ELECTRONIC DATA RECORDER SYSTEM SHUT DOWN SUDDENLY.
1215 | 03/18/2022 | NBR-115S | HRDH-2140 | ARM | 10 Feb 0945 - 0330 | 22.5 | 737.75 | 891345 |  | STUK | STBH | BHA | 17100 | WHILE HARD BACK REAMING OUT OF HOLE THE STRING STALLED AND STUCK.
1217 | 03/18/2022 | NBR-304S | HRDH-1952 | RIG | 18 Mar 0500 - 1030 | 5.5 | 5.5 | 893711 |  | RR | FOT | TDS | 124 | FOUND QUILL STUCK IN UPPER POSITION
1219 | 03/18/2022 | OFGRL | HSBH-23 | ARM | 16 Mar 0045 - 0500 | 24 | 52.25 | 893427 |  | WON | WTHR | NA | 11296 | WAIT ON WEATHER FOR CRANE OPERATIONS TO CONTINUE NIPPLE DOWN WELLHEAD
1221 | 03/18/2022 | PA-218S | QTIF-515 | RIG | 18 Mar 0745 - 0930 | 1.75 | 1.75 | 893704 |  | RR | FOT | DRRK | 11600 | RIG REPAIR. STABBING BOARD MALFUNCTION
1223 | 03/18/2022 | RBP-50A | KARN-51 | ARM | 17 Mar 0630 - 0500 | 24 | 46.5 | 893554 |  | WON | WTHR | NA | 11296 | UNABLE TO CONTINUE PRE-LOAD OPERATIONS DUE TO ADVERSE WEATHER CONDITIONS (WAVES HITTING BTM OF THE HULL) SUSPEND PRE-LOADING OPS AND JACK-UP TO 20' AIR-GAP.
1225 | 03/18/2022 | RM-74A | KARN-60 | ARM | 17 Mar 0830 - 0500 | 24 | 44.5 | 893571 |  | WON | WTHR | NA | 0 | WOW.UNABLE TO REMOVE MOORING LINES OR PERFORM WATER TIGHT INTEGRITY TEST & RIG MOVE DUE TO ADVERSE WEATHER CONDITION
1227 | 03/18/2022 | SCTD-2 | HWYH-1193 | RIG | 17 Mar 1600 - 0930 | 4.5 | 17.5 | 893609 |  | BHA | FOT | MMOT | 14127 | LOSING COMMUNICATION WITH DOWNHOLE TOOLS. TROUBLESHOOT WITHOUT SUCCESS.
1229 | 03/18/2022 | SINO-1L | ABJF-15 | TK1 | 16 Mar 2200 - 1000 | 5 | 36 | 893552 |  | FISH | FWTS | BHA | 0 | AFTER PUNCHED 3.1/2" TBG OBSERVED JUMP AND DROP IN WEIGHT FROM 400 LBS TO 250 LBS THEN INCREASE TO 400 LBS, PULL OUT TO SURFACE WEIGHT DROPPED FROM 300 LBS TO 100 LBS, LD LUBRICATOR TO CHECK FOUND 2.78" DPU PERFORATOR DROPPED IN THE HOLE.
1231 | 03/18/2022 | SINO-27N | UTMN-438 | ARM | 17 Mar 1900 - 1430 | 9.5 | 18.5 | 893572 |  | WON | WTHR | NA | 0 | HAD SAND STORM WITH LOW VISIBILTY & HIGH WIND SPEED UP TO 50 KM/HR.
1233 | 03/18/2022 | SINO-42L | HWYH-286 | SPS | 18 Mar 2200 - 0500 | 7 | 7 | 893713 |  | BHA | FOT | MWD | 0 | SPS PULSER MALFUNCTION & BAD DETECTION TROUBLESHOOTING .
1235 | 03/18/2022 | SND-2005 | MHKK-2 | ARM | 17 Mar 0115 - 0600 | 1 | 4.75 | 893570 |  | WON | WTHR | NA | 5300 | BAD SAND STORM, WIND SPEED OVER 45 KM/HR.
1237 | 03/18/2022 | SND-3003 | HRDH-2311 | WCR | 18 Mar 1230 - 1530 | 3 | 3 | 893706 |  | TF | FOT | CTRQ | 8980 | FAILED TO ACHIEVE THE REQUIRED VAM TOP TORQUE WITH POWER TONG AND JAM UNIT, FAILED TO BREAK OUT OVERTORQUED CONNECTION , JAM UNIT SENSOR FAILURE
1239 | 03/18/2022 | SP-161 | HWYH-2558 | ARM | 18 Mar 0500 - 1530 | 10.5 | 10.5 | 893701 |  | WON | WTHR | NA | 8124 | SUSPEND OPERATIONS DUE TO HIGH WIND SPEED UP TO 55 KM/HR.
1241 | 03/18/2022 | SP-229 | SFNY-4 | ARM | 17 Mar 2130 - 0700 | 2 | 9.5 | 893666 |  | WON | WTHR | NA | 0 | SHUT DOWN OPERATIONS DUE TO HIGH WINS SPEED - >43 KM/H
1242 | 03/18/2022 | SP-258 | HZEM-160612 | ARM | 18 Mar 0630 - 1430 | 8 | 8 | 893708 |  | WON | WTHR | NA | 2196 | OPERATION SUSPENDED DUE TO SAND STORM, WIND SPEED 45-70 KM/HR.
1244 | 03/18/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 16 | 240 | 893186 |  | STUK | LCRW | STRG | 2196 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
1245 | 03/18/2022 | SP-258 | HZEM-160612 | ARM | 18 Mar 0630 - 1430 | 8 | 8 | 893708 |  | WON | WTHR | NA | 2196 | OPERATION SUSPENDED DUE TO SAND STORM, WIND SPEED 45-70 KM/HR.
1247 | 03/18/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 0500 | 24 | 174.25 | 893267 |  | FISH | HERR | BHA | 9253 | ONE ROLLER SEGMENT WAS LOST IN THE HOLE FROM THE 12 1/4" ROLLER REAMER , BHA WAS PULLED & LAIED DOWN WITHOUT REPORTING THE MISSED ROLLER TO ARAMCO FOREMAN. AFTER RUNNING CSG & WHILE DRILL OUT THE 8 1/2" RAT HOLE. OBSERVED ERRATIC TORQUE & JUNK MARKS ON BHA. THE LOST ROLLER WAS LATER RECOVERED WITH THE RCJB.
1249 | 03/18/2022 | SSA-5865 | ABJF-50 | OJR | 17 Mar 0115 - 0500 | 22.75 | 26 | 893589 |  | BHA | FOT | JARS | 4152 | ON BOTTOM DRILLING. THERE WAS A SUDDEN DECREASE IN DRILL PIPE PRESSURE AND TORQUE. PICKED UP OFF BOTTOM AND FOUND 63K OF HOOKLOAD LOST. STRING IS TWISTED OFF.
1251 | 03/18/2022 | SSA-5891 | HRDH-1178 | SPS | 16 Mar 1245 - 0945 | 4.75 | 34.5 | 893485 |  | BHA | FOT | GMWD | 11869 | LOST COMMUNICATION W/ MWD TOOL.
1253 | 03/18/2022 | SSA-5914 | WDYH-80 | RIG | 17 Mar 1500 - 0500 | 23.5 | 37.5 | 893557 |  | JF | HERR | NA | 13985 | OBSERVED MW OF THE TRIP TANK AT TOP OF BHA CUT BY 2 PCF DUE TO CLEANING RIG FLOOR WITH WATER. TRIP TANK MW FOUND IT 103 PCF INSTEAD OF 105 PCF.
1255 | 03/18/2022 | SSA-5969 | UTMN-3021 | ARM | 18 Mar 0730 - 1130 | 4 | 4 | 893702 |  | WON | WTHR | NA | 122 | WAITING ON WEATHER DUE TO HIGH WIND SPEED
1257 | 03/18/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 216.5 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1259 | 03/18/2022 | SSA-5971 | UTMN-2302 | WDV | 15 Mar 1730 - 0500 | 15 | 24.5 | 893472 |  | TF | FOT | DV | 11025 | UNABLE TO OPEN 9-5/8" WEATHERFORD 10K DV CIRCULATION PORTS TO PERFORM 2ND STAGE CMT JOB.
1261 | 03/18/2022 | SSA-5974 | HRDH-1970 | SPS | 17 Mar 0530 - 1830 | 13.5 | 37 | 893587 |  | BHA | FOT | MWD | 13357 | SPS WERE NOT ABLE TO DETECT MWD SIGNAL AT SURFACE WHILE DRILLING 8-3/8" HOLE SECTION
1263 | 03/18/2022 | T216 | ANDR-263 | ARM | 18 Mar 0845 - 1000 | 1.25 | 1.25 | 893745 |  | WON | WTHR | NA | 0 | EXPERIENCED HIGH WIND SPEED AND LOW VISIBILITY
1264 | 03/18/2022 | T217 | UTMN-488 | ARM | 18 Mar 0800 - 1230 | 4.5 | 4.5 | 893700 |  | WON | WTHR | NA | 0 | SUSPEND OPERATIONS DUE TO SAND STORM & HIGH WIND SPEED.
1266 | 03/18/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 19.5 | 554.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1267 | 03/18/2022 | T217 | UTMN-488 | ARM | 18 Mar 0800 - 1230 | 4.5 | 4.5 | 893700 |  | WON | WTHR | NA | 0 | SUSPEND OPERATIONS DUE TO SAND STORM & HIGH WIND SPEED.
1269 | 03/18/2022 | T218 | UTMN-564 | ARM | 05 Mar 1300 - 0930 | 4.5 | 16.75 | 893050 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER
1271 | 03/19/2022 | 910TE | DMMM-613 | WTC | 19 Mar 0830 - 1015 | 1.75 | 1.75 | 893760 |  | TF | FOT | PKR | 11997 | AFTER SETTING WELLTEC WAB PKR, BALL DID NOT RELEASE TO BALL CATCHER TO REGAIN CIRCULATION.
1273 | 03/19/2022 | ADC-43L | HWYH-1226 | TK3 | 18 Mar 0900 - 0430 | 23.5 | 43.5 | 893577 |  | STUK | HINW | WLT | 14895 | WHILE LOGGING UP OH WITH SLB WIRELINE LOGGING TOOLS (HLDS-QCNTHLDS-GR-CAL-XTRA-C) @ 13640 FT, THE WL TOOLSTRING GOT STUCK. UNABLE TO RELEASE.
1275 | 03/19/2022 | ADC-50 | SFNY-1178 | ARM | 14 Mar 2315 - 0500 | 24 | 119 | 893464 |  | LCIR | UVLC | NA | 2725 | LOST COMPLETE CIRCULATION AT 2,725', SIMILAR TO ALL OTHER WELLS IN SAME PLATFORM.
1277 | 03/19/2022 | ADC-52 | HRDH-2312 | SPL | 19 Mar 0115 - 0500 | 3.75 | 3.75 | 893759 |  | TF | FOT | SLICK | 10921 | TRY TO POOH WITH PR PLUG SETTING TOOL NO SUCCESS. NOT ABLE TO PASS THRU THT PACKER @ 10,921'.
1279 | 03/19/2022 | ADC-59L | HRDH-2232 | TK3 | 16 Mar 1300 - 1030 | 5.5 | 43.75 | 893532 |  | JF | HERR | NA | 13971 | POOH TO REDUCE SHOE TRACK FROM 4 TO 3 JOINTS FOR PERFORATION SPACE-OUT
1281 | 03/19/2022 | ADM-262 | MRJN-122 | ARM | 18 Mar 2200 - 2030 | 15.5 | 22.5 | 893712 |  | WON | WTHR | NA | 7450 | WAIT ON WEATHER FOR THE DELIVERY OF WILDWELL HOT TAPPING EQUIPMENT.
1283 | 03/19/2022 | ADM-656 | ABSF-169 | ARM | 19 Mar 0500 - 0500 | 24 | 24 | 893756 |  | WON | WTHR | NA | 0 | WOW TO OFFLOAD SPUD MATERIAL FROM VESSEL " CABINESS TIDE".
1285 | 03/19/2022 | AOD-1 | ZULF-695 | WWB | 19 Mar 0600 - 0700 | 1 | 1 | 893748 |  | BHA | FOT | MACS | 7225 | ATTEMPTED TO FUNCTION TEST PBL SUB. PBL SUB FUNCTIONED OPEN AND WOULD NOT FUNCTION CLOSED.
1287 | 03/19/2022 | ARO-2003 | ZULF-299 | ARM | 18 Mar 0500 - 0000 | 19 | 43 | 893575 |  | WON | WTHR | NA | 0 | WAITING ON WEATHER FOR FIELD SERVICE TO VISIT PLATFORM FOR HANDOVER
1289 | 03/19/2022 | BB-84A | MRJN-588 | ARM | 17 Mar 1530 - 1430 | 9.5 | 47 | 893645 |  | WON | WTHR | NA | 17045 | WAIT ON WEATHER - UNABLE TO OFFLOAD VESSEL
1290 | 03/19/2022 | CG-1 | ZULF-1201 | HCB | 19 Mar 1130 - 0500 | 17.5 | 17.5 | 893754 |  | WO | MATL | NA | 5800 | WAIT ON HALLIBURTON 9-5/8" RBP.
1292 | 03/19/2022 | CG-1 | ZULF-1201 | ARM | 18 Mar 1500 - 1130 | 6.5 | 20.5 | 893725 |  | WON | WTHR | NA | 6000 | WAIT ON WEATHER
1293 | 03/19/2022 | CG-1 | ZULF-1201 | HCB | 19 Mar 1130 - 0500 | 17.5 | 17.5 | 893754 |  | WO | MATL | NA | 5800 | WAIT ON HALLIBURTON 9-5/8" RBP.
1295 | 03/19/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 57 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1297 | 03/19/2022 | DPS-5 | HRDH-1909 | FMC | 19 Mar 0500 - 2200 | 16 | 16 | 893753 |  | JF | HERR | CTRQ | 8686 | OBSTRUCTION WHILE PERFORMING SL DRIFT W/ 3.795"OD & 3.7"OD DUE TO OVER TORQUE ON 4.5"TBG COLLAR BOX THREAD USING FRANKS JAM UNIT.
1299 | 03/19/2022 | DQ-48 | KHRS-1411 | WI1 | 17 Mar 0330 - 0500 | 24 | 49.5 | 893751 |  | JF | FOP | MILL | 8503 | L2 WHIPSTOCK PKR LEAKING.
1301 | 03/19/2022 | ENS-141 | MRJN-758 | ARM | 18 Mar 1200 - 1200 | 7 | 13.5 | 893709 |  | WON | WTHR | NA | 10370 | WAITING ON N2 TANKS TO BE DELIVERED, TANKS LOADED ON RAWABI-20 BUT BOAT DELAYED IN TANAJIB DUE TO BAD WEATHER.
1303 | 03/19/2022 | ENSCO-54 | ABSF-179 | ARM | 17 Mar 0500 - 0500 | 24 | 72 | 893588 |  | WON | WTHR | NA | 0 | ADVERSE WEATHER CONDITION - NOT SUITABLE FOR CONDUCTING RIG MOVE OPERATIONS
1305 | 03/19/2022 | ENSCO-76 | MRJN-851 | ARM | 19 Mar 0500 - 0500 | 24 | 24 | 893749 |  | WON | WTHR | NA | 0 | UNABLE TO MOVE RIG DUE TO ADVERSE WEATHER CONDITIONS.
1307 | 03/19/2022 | JACK-203 | MHWZ-823 | ARM | 16 Mar 0100 - 1645 | 11.75 | 63.75 | 893545 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER DUE TO HIGH WIND SPEED FROM 36KM/H TO 40 KM/H. CRANE OPREATION HAS BEED SUSPENDED.
1309 | 03/19/2022 | NBR-783S | NJYN-89 | RIG | 19 Mar 2030 - 2130 | 1 | 1 | 893757 |  | RR | FPMP | MPMP | 6340 | FAILURE ON MUD PUMP POP OFF
1311 | 03/19/2022 | OFGRL | HSBH-23 | ARM | 16 Mar 0045 - 1200 | 7 | 59.25 | 893427 |  | WON | WTHR | NA | 11296 | WAIT ON WEATHER FOR CRANE OPERATIONS TO CONTINUE NIPPLE DOWN WELLHEAD
1313 | 03/19/2022 | PA-622S | AFLJ-4 | HWP | 19 Mar 0830 - 2000 | 11.5 | 11.5 | 893579 |  | TF | FOT | WLU | 2838 | WHILE LOGGING COULD NOT PULL THE WIRE TROUBLESHOOTING DRUM GEAR FAILURE.
1315 | 03/19/2022 | RBP-50A | KARN-51 | ARM | 17 Mar 0630 - 0500 | 24 | 70.5 | 893554 |  | WON | WTHR | NA | 11296 | UNABLE TO CONTINUE PRE-LOAD OPERATIONS DUE TO ADVERSE WEATHER CONDITIONS (WAVES HITTING BTM OF THE HULL) SUSPEND PRE-LOADING OPS AND JACK-UP TO 20' AIR-GAP.
1317 | 03/19/2022 | RM-74A | KARN-60 | ARM | 17 Mar 0830 - 0500 | 24 | 68.5 | 893571 |  | WON | WTHR | NA | 0 | WOW.UNABLE TO REMOVE MOORING LINES OR PERFORM WATER TIGHT INTEGRITY TEST & RIG MOVE DUE TO ADVERSE WEATHER CONDITION
1319 | 03/19/2022 | SCTD-1 | UTMN-3126 | RIG | 19 Mar 1200 - 1400 | 2 | 2 | 893750 |  | TF | FOT | TESTT | 0 | FOUND GAS FLOW METER NOT READING WHEN START FLOW TEST OPERATION.
1321 | 03/19/2022 | SINO-42L | HWYH-286 | SPS | 19 Mar 0630 - 0500 | 22.5 | 22.5 | 893758 |  | BHA | FOT | LWD | 10819 | ALD TOOL FAILURE .
1323 | 03/19/2022 | SP-122 | ANDR-602 | INW | 19 Mar 2200 - 0500 | 7 | 7 | 893755 |  | JF | XTTE | SLICK | 0 | INTERWELL RBP DIDN'T SET
1325 | 03/19/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 0500 | 24 | 264 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
1327 | 03/19/2022 | SP-259 | HZEM-160404 | RIG | 19 Mar 0600 - 0900 | 3 | 3 | 893752 |  | BOP | FOT | BOP | 5085 | EXSESS TIME TO TEST BOP'S DUE TO SEVERAL LEAKS
1329 | 03/19/2022 | SSA-51 | MNIF-259 | RIG | 11 Mar 2215 - 1600 | 11 | 185.25 | 893267 |  | FISH | HERR | BHA | 9253 | ONE ROLLER SEGMENT WAS LOST IN THE HOLE FROM THE 12 1/4" ROLLER REAMER , BHA WAS PULLED & LAIED DOWN WITHOUT REPORTING THE MISSED ROLLER TO ARAMCO FOREMAN. AFTER RUNNING CSG & WHILE DRILL OUT THE 8 1/2" RAT HOLE. OBSERVED ERRATIC TORQUE & JUNK MARKS ON BHA. THE LOST ROLLER WAS LATER RECOVERED WITH THE RCJB.
1331 | 03/19/2022 | SSA-5865 | ABJF-50 | OJR | 17 Mar 0115 - 2045 | 7.75 | 33.75 | 893589 |  | BHA | FOT | JARS | 4152 | ON BOTTOM DRILLING. THERE WAS A SUDDEN DECREASE IN DRILL PIPE PRESSURE AND TORQUE. PICKED UP OFF BOTTOM AND FOUND 63K OF HOOKLOAD LOST. STRING IS TWISTED OFF.
1333 | 03/19/2022 | SSA-5914 | WDYH-80 | RIG | 17 Mar 1500 - 1215 | 7.25 | 44.75 | 893557 |  | JF | HERR | NA | 13985 | OBSERVED MW OF THE TRIP TANK AT TOP OF BHA CUT BY 2 PCF DUE TO CLEANING RIG FLOOR WITH WATER. TRIP TANK MW FOUND IT 103 PCF INSTEAD OF 105 PCF.
1335 | 03/19/2022 | SSA-5969 | UTMN-3021 | ARM | 19 Mar 0600 - 2230 | 16.5 | 16.5 | 893746 |  | LCIR | UVLC | NA | 262 | LOST COMPLETE RETURNS AT 262'.
1337 | 03/19/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 23.5 | 240 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1339 | 03/19/2022 | SSA-5971 | UTMN-2302 | WDV | 15 Mar 1730 - 0300 | 22 | 46.5 | 893472 |  | TF | FOT | DV | 11025 | UNABLE TO OPEN 9-5/8" WEATHERFORD 10K DV CIRCULATION PORTS TO PERFORM 2ND STAGE CMT JOB.
1341 | 03/19/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 578.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1343 | 03/20/2022 | ADC-52 | HRDH-2312 | SPL | 19 Mar 0115 - 1900 | 14 | 17.75 | 893759 |  | TF | FOT | SLICK | 10921 | TRY TO POOH WITH PR PLUG SETTING TOOL NO SUCCESS. NOT ABLE TO PASS THRU THT PACKER @ 10,921'.
1345 | 03/20/2022 | ADC-68L | KRSN-706 | SDM | 20 Mar 1700 - 0500 | 12 | 12 | 893770 |  | BHA | FOT | MMOT | 2786 | WHILE DRILLING AT 2,786 FT, OBSERVED 300 PSI DROP IN PRESSURE WHEN BIT ON-BOTTOM.
1347 | 03/20/2022 | ADES-157 | HRDH-1204 | ITS | 20 Mar 0215 - 0500 | 2.75 | 2.75 | 893771 |  | TF | FOT | CTRQ | 14982 | ITS POWER TONG DOES NOT WORK PROPERLY. PROBLEM SAFETY DOOR
1349 | 03/20/2022 | ADES-798 | JFYN-11 | BCR | 20 Mar 2100 - 2330 | 2.5 | 2.5 | 893786 |  | TF | XTTE | CTRQ | 3001 | CUMULITIVE LOST TIME DUE TO CRT STUCK INSIDE CSG & ADJUSTING CRT LINKS.
1351 | 03/20/2022 | ADM-656 | ABSF-169 | ARM | 17 Mar 0300 - 1000 | 5 | 55 | 893607 |  | WON | WTHR | NA | 0 | WOW TO OFFLOAD SPUD MATERIAL BOAT DUE TO HIGH WIND SPEED (38-45 KNOTS AND SEA SWELL 3.5 -4.0 MTRS).
1353 | 03/20/2022 | ARO-3001 | ZULF-2058 | RIG | 20 Mar 0500 - 0815 | 3.25 | 3.25 | 893785 |  | RR | FOT | TDS | 9000 | TDS WASH PIPE PACKING SEAL FAILED
1355 | 03/20/2022 | ARO-3004 | MRJN-2060 | ARM | 20 Mar 1200 - 0500 | 17 | 17 | 893788 |  | WON | WTHR | NA | 5495 | CASING ARRIVAL DELAYED DUE TO ADVERSE WEATHER.
1357 | 03/20/2022 | CG-1 | ZULF-1201 | HCB | 19 Mar 1130 - 0930 | 4.5 | 22 | 893754 |  | WO | MATL | NA | 5800 | WAIT ON HALLIBURTON 9-5/8" RBP.
1359 | 03/20/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 81 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1361 | 03/20/2022 | DQ-48 | KHRS-1411 | WI1 | 17 Mar 0330 - 2130 | 16.5 | 66 | 893751 |  | JF | FOP | MILL | 8503 | L2 WHIPSTOCK PKR LEAKING.
1363 | 03/20/2022 | ENSCO-54 | ABSF-179 | ARM | 17 Mar 0500 - 0500 | 24 | 96 | 893588 |  | WON | WTHR | NA | 0 | ADVERSE WEATHER CONDITION - NOT SUITABLE FOR CONDUCTING RIG MOVE OPERATIONS
1365 | 03/20/2022 | NBR-16S | HMYM-433314 | RIG | 20 Mar 2200 - 0130 | 3.5 | 3.5 | 893766 |  | BOP | FOT | DVRT | 0 | DIVERTER LEAKING.
1367 | 03/20/2022 | OFGRL | HSBH-23 | FME | 20 Mar 0930 - 0500 | 19.5 | 19.5 | 893765 |  | WO | WOTO | NA | 11296 | FMC UNABLE TO TIGHTEN THE 1.25" NUTS ON THE ENERGIZING LOCK MANDREL SPECIALIZED TOOL - MISSSING 2" SIZED SPANNER TORQUE WRENCHES.
1369 | 03/20/2022 | RM-74A | KARN-60 | ARM | 17 Mar 0830 - 0700 | 2 | 70.5 | 893571 |  | WON | WTHR | NA | 0 | WOW.UNABLE TO REMOVE MOORING LINES OR PERFORM WATER TIGHT INTEGRITY TEST & RIG MOVE DUE TO ADVERSE WEATHER CONDITION
1370 | 03/20/2022 | SINO-42L | HWYH-286 | SPS | 20 Mar 1030 - 1630 | 6 | 6 | 893768 |  | BHA | FOT | RSS | 8320 | ICRUISE NOT RESPOND .
1372 | 03/20/2022 | SINO-42L | HWYH-286 | SPS | 19 Mar 0630 - 1030 | 5.5 | 28 | 893758 |  | BHA | FOT | LWD | 10819 | ALD TOOL FAILURE .
1373 | 03/20/2022 | SINO-42L | HWYH-286 | SPS | 20 Mar 1030 - 1630 | 6 | 6 | 893768 |  | BHA | FOT | RSS | 8320 | ICRUISE NOT RESPOND .
1375 | 03/20/2022 | SP-257 | HZEM-141212 | SDM | 20 Mar 1030 - 0500 | 18.5 | 18.5 | 893762 |  | BHA | IBHA | MMOT | 3210 | UNABLE TO CORRECT AZM.
1377 | 03/20/2022 | SP-258 | HZEM-160612 | ARM | 08 Mar 2000 - 1530 | 10.5 | 274.5 | 893186 |  | STUK | LCRW | STRG | 3637 | WHILE POOH @ 3637' ENCOUNTERED TIGHT HOLE STOP AND WORK DOWN MADE 15' THEN NO PROGRESS CONTINUED WORKING FREE POINT AND TRYING TO ESTABLISH ROTATION. PROGRESS STOPPED BOTH UP AND DOWN. ARUMA SHALE
1379 | 03/20/2022 | SSA-51 | MNIF-259 | RIG | 20 Mar 1230 - 2300 | 10.5 | 10.5 | 893763 |  | RR | FOT | TDS | 9639 | TOP DRIVE SYSTEM ROTATION MALFUNCTION. TROUBLESHOOTING, FOUND ONE OF THE THREE TDS INVERTERS IS DOWN.
1381 | 03/20/2022 | SSA-5820 | SDGM-1215 | WCR | 20 Mar 2030 - 0030 | 4 | 4 | 893767 |  | TF | FOT | CRT | 2111 | WFD CRT FAILURE
1383 | 03/20/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 264 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1385 | 03/20/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 602.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1387 | 03/20/2022 | WCL-83 | MRJN-835 | RIG | 20 Mar 2215 - 0000 | 1.75 | 1.75 | 893787 |  | RR | FOT | DWKS | 13815 | UNABLE TO RELEASE DRAW WARKS BRAKES, TROUBLESHOOT PROBLEM.
1388 | 03/21/2022 | ADC-17 | ZULF-1217 | RIG | 21 Mar 1600 - 1645 | .75 | .75 | 893907 |  | RR | FOT | MPMP | 2609 | MUD PUMPS REPAIR
1390 | 03/21/2022 | ADC-17 | ZULF-1217 | RIG | 21 Mar 1130 - 1330 | 2 | 2 | 893865 |  | RR | FOT | EDR | 2313 | RIG PASON SYSTEM SHUT-DOWN
1391 | 03/21/2022 | ADC-17 | ZULF-1217 | RIG | 21 Mar 1600 - 1645 | .75 | .75 | 893907 |  | RR | FOT | MPMP | 2609 | MUD PUMPS REPAIR
1392 | 03/21/2022 | ADC-32 | SDGM-1139 | FMC | 21 Mar 2030 - 2230 | 2 | 2 | 893908 |  | TF | FOT | CTRQ | 144 | HYDRAULIC & MECHANICAL PROBLEMS WITH POWER TONG & POWER UNIT.
1394 | 03/21/2022 | ADC-32 | SDGM-1139 | RIG | 04 Feb 0415 - 0500 | 10 | 97.75 | 890891 |  | JF | HERR | SFLN | 10570 | TAGGED ON TOC @ 10,570' [545' BELOW DV TOOL], APPROX. 1766' SHALLOWER THAN PLAN DUE TO MISS-ALIGNMENT ON SURFACE LINES DURING 9-5/8" 1ST STAGE CMT JOB
1395 | 03/21/2022 | ADC-32 | SDGM-1139 | FMC | 21 Mar 2030 - 2230 | 2 | 2 | 893908 |  | TF | FOT | CTRQ | 144 | HYDRAULIC & MECHANICAL PROBLEMS WITH POWER TONG & POWER UNIT.
1397 | 03/21/2022 | ADC-50 | SFNY-1178 | ARM | 14 Mar 2315 - 0500 | 24 | 167 | 893464 |  | LCIR | UVLC | NA | 2725 | LOST COMPLETE CIRCULATION AT 2,725', SIMILAR TO ALL OTHER WELLS IN SAME PLATFORM.
1399 | 03/21/2022 | ADC-52 | HRDH-2312 | NSL | 21 Mar 0500 - 0430 | 23.5 | 23.5 | 893945 |  | TF | FOT | PLUGN | 10981 | FAILURE ON PLUG AND PRONG TO HOLD PRESSURE WHILE TRYING TO SET HALLIBURTON THT PACKER. HAD COMMUNICATION WITH ANNULUS.
1401 | 03/21/2022 | ADC-68L | KRSN-706 | SDM | 20 Mar 1700 - 0500 | 24 | 36 | 893770 |  | BHA | FOT | MMOT | 2786 | WHILE DRILLING AT 2,786 FT, OBSERVED 300 PSI DROP IN PRESSURE WHEN BIT ON-BOTTOM, POOH TO SURFACE, OBSERVED MUD MOTOR TWISTED-OFF.
1403 | 03/21/2022 | ADES-157 | HRDH-1204 | SAM | 21 Mar 0830 - 0215 | 17.75 | 17.75 | 893827 |  | BHA | FOT | WBCL | 14982 | LOST RUBBER OF SAMAA9 5/8'' FSC PACKER.
1404 | 03/21/2022 | ADES-158 | ABQQ-737 | RIG | 21 Mar 2300 - 0500 | 6 | 6 | 893872 |  | BOP | FOT | BOP | 11960 | ATTEMPTS TO UNSCREWE 13-5/8"-5M ANNULAR CAP, NO SUCCESS.
1406 | 03/21/2022 | ADES-158 | ABQQ-737 | SWL | 21 Mar 0800 - 1100 | 3 | 3 | 893868 |  | TF | FOT | WLT | 4990 | TRIED TO LATCH THRU-BIT SLB LOGGING TOOL W/ RETRIEVING TOOL SEVERAL ATTEMPS , NO SUCCESS.
1407 | 03/21/2022 | ADES-158 | ABQQ-737 | RIG | 21 Mar 2300 - 0500 | 6 | 6 | 893872 |  | BOP | FOT | BOP | 11960 | ATTEMPTS TO UNSCREWE 13-5/8"-5M ANNULAR CAP, NO SUCCESS.
1409 | 03/21/2022 | ADES-798 | JFYN-11 | RIG | 21 Mar 0600 - 1330 | 7.5 | 7.5 | 893825 |  | RR | FOT | TDS | 6548 | TDS TROUBLE SHOOTING. CHANGE OUT MASTER POWER STACK 2 PC BOARDS.
1411 | 03/21/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 1.5 | 237.5 | 893229 |  | LCIR | FRFM | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1413 | 03/21/2022 | ARO-3003 | SFNY-1740 | RIG | 21 Mar 1500 - 1800 | 3 | 3 | 893828 |  | RR | FOT | WATER | 0 | EXCESSIVE TIME FOR PRE-LOAD OPERATIONS
1415 | 03/21/2022 | ARO-3004 | MRJN-2060 | ARM | 20 Mar 1200 - 1400 | 9 | 26 | 893788 |  | WON | WTHR | NA | 5495 | CASING ARRIVAL DELAYED DUE TO ADVERSE WEATHER AND MAIN ENGINE FAILURE OF ORIGINAL CASING VESSEL
1417 | 03/21/2022 | BCTD-3 | HRDH-1375 | RIG | 21 Mar 1530 - 1930 | 4 | 4 | 893927 |  | RR | FOT | CHK | 10000 | WHILE INSPECTING CHOKE A, FOUND CHOKE RETAINING RING GOT LOOSE & WASHED OUT.
1419 | 03/21/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 105 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1421 | 03/21/2022 | DQ-50L | HRDH-1492 | BHI | 21 Mar 0000 - 0500 | 5 | 5 | 893928 |  | BHA | FOT | RSS | 8939 | LOST COMMUNICATION WITH RSS TOOL (ATK), TROUBLESHOOTING WITHOUT SUCCESS
1423 | 03/21/2022 | EXL-IA | SFNY-4050 | BAW | 21 Mar 1115 - 0445 | 17.5 | 17.5 | 893866 |  | TF | FOT | WLT | 6884 | UNABLE TO ENGAGE WET LATCH. PERFORM 6 ATTEMPTS WITHOUT SUCCESS.
1425 | 03/21/2022 | MP-1 | SFNY-994 | HCM | 21 Mar 1845 - 0500 | 10.25 | 10.25 | 893871 |  | JF | CEDE | NA | 2883 | WHILE RIH WITH WHIPSTOCK, OBSERVED CEMENT DEPOST ON SET-BACK. STOPPED RIH, OBSERVED THIN SLIVERS OF CEMENT DEPOSIT, CHECKED FURTHER 2 STDS, SAME. POH TO FLUSH PIPE OF CEMENT DEPOSIT.
1427 | 03/21/2022 | NBR-783S | NJYN-89 | RIG | 15 Mar 1645 - 1700 | 2.5 | 13.25 | 893446 |  | RR | FOT | TDS | 6436 | REPAIR ON TDS BRAKE SYSTEM
1429 | 03/21/2022 | OFGRL | HSBH-23 | FME | 20 Mar 0930 - 1000 | 5 | 24.5 | 893765 |  | WO | WOTO | NA | 11296 | FMC UNABLE TO TIGHTEN THE 1.25" NUTS ON THE ENERGIZING LOCK MANDREL SPECIALIZED TOOL - MISSSING 2" SIZED SPANNER TORQUE WRENCHES.
1431 | 03/21/2022 | PA-861S | HRDH-1060 | TK2 | 20 Mar 0030 - 0500 | 24 | 28.5 | 893581 |  | STUK | STBH | MILL | 11206 | STRING STUCK AT 11,211.86',WORK STRING JARRING DOWN WITH 100KLBS, WITH PUMP/WITHOUT PUMP(550-200GPM/0GPM), WITH TORQUE/WITHOUT TORQUE(16.5K-FT/LBS/0K-FT/LBS) WITHOUT SUCCESS, CANNOT SEE ANY INDICATION OF JAR WORKING AFTER @ 8 TIMES. - JAR FIRED 6-8 TIMES WITH 100K-K/LBS DOWN WEIGHT, NO INDICATION THAT JAR IS FIRING.
1433 | 03/21/2022 | RM-74A | KARN-60 | ARN | 21 Mar 0700 - 0500 | 22 | 22 | 893925 |  | WON | WTHR | NA | 0 | UNABLE TO MOVE RIG TO KARN 60, PLATFORM DEPRESSURIZING HAS BEEN DELAYED DUE TO RECENT ADVERS WEATHER CONDITIONS.
1435 | 03/21/2022 | SINO-18 | ADHN-10 | RIG | 21 Mar 0430 - 0500 | .5 | .5 | 893829 |  | RR | FOT | CSYS | 15349 | WHILE DRILL 5-7/8" TO 15349' OBSERVED LEAKE FROM SAVER SUB CONNECTION.
1437 | 03/21/2022 | SINO-19L | UTMN-1074 | HSL | 21 Mar 0630 - 0800 | 1.5 | 1.5 | 893826 |  | TF | XTTE | SLICK | 200 | PT 3-1/2'' SHALLOW MONO-LOCK PLUG NOT HOLD.
1439 | 03/21/2022 | SINO-22 | BRRI-381 | NCS | 21 Mar 0030 - 0400 | 3.5 | 3.5 | 893867 |  | CMT | HFFT | NA | 14590 | PERFORMED FIT DUE TO SOFT CEMENT WHILE DRILLING SHOE TRACK.
1441 | 03/21/2022 | SINO-43L | UTMN-4063 | TK2 | 21 Mar 1100 - 1930 | 8.5 | 8.5 | 893906 |  | TF | FOT | CSG | 719 | NO SEALING BETWIN STINGER AND 24'' STAB IN SHOE.
1443 | 03/21/2022 | SND-2006 | UTMN-3135 | ARM | 20 Mar 1630 - 0500 | 24 | 36.5 | 893947 |  | LCIR | UXGE | NA | 14939 | LOST RETURN AT 14,939 FT IN TAWIL RES WITH 95 PCF OBM.
1445 | 03/21/2022 | SND-3003 | HRDH-2311 | ULT | 21 Mar 0500 - 0330 | 22.5 | 22.5 | 893885 |  | LROP | IBSL | BIT | 10135 | VERY SLOW ROP FROM START DRILLING 8-3/8" SECTION WITH ULTERA BIT COMPARING WITH OFFSET WELLS WITH SIMILAR BIT
1447 | 03/21/2022 | SP-257 | HZEM-141212 | ARM | 20 Mar 1030 - 0800 | 3 | 21.5 | 893762 |  | BHA | IBHA | BHA | 3210 | UNABLE TO CORRECT AZM.
1449 | 03/21/2022 | SSA-5820 | SDGM-1215 | WCR | 21 Mar 0500 - 0600 | 1 | 1 | 893772 |  | JF | HERR | CTRQ | 4230 | UNABLE TO GET PROPER JAM READING W/MAKE UP CASING
1451 | 03/21/2022 | SSA-5859 | HRDH-1967 | RIG | 21 Mar 2200 - 0300 | 5 | 5 | 893929 |  | JF | XTRI | BOP | 4285 | EXCESS TIME TO N/U BOP 13 5/8" 10K
1453 | 03/21/2022 | SSA-5865 | ABJF-50 | RIG | 21 Mar 1930 - 2100 | 1.5 | 1.5 | 893869 |  | RR | FOT | DWKS | 1534 | WHILE RUNNING CASING, DRAWWORK EMERGENCY BREAK ENGAGED - UNABLE TO OPERATE DRAWWORK.
1455 | 03/21/2022 | SSA-5892 | SMNH-521700 | HDV | 21 Mar 1530 - 0500 | 13.5 | 13.5 | 893946 |  | TF | FOT | DV | 11313 | HALLIBURTON 9-5/8" DV TOOL OPENING PLUG DID NOT SEAT TO OPEN DV TOOL
1457 | 03/21/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 288 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1459 | 03/21/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 626.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1461 | 03/22/2022 | 095TE | MNIF-225 | BHI | 21 Mar 0100 - 0500 | 24 | 28 | 893948 |  | BHA | FOT | RSS | 14901 | ROTATING SLEEVE IN RSS NOT WORKING. TROUBLESHOOTING SEVERAL TIME NO SUCCESS( RSS FAILURE) . POOH TO CHANGE RSS.
1463 | 03/22/2022 | ADC-12 | ABQQ-64 | BHI | 22 Mar 0200 - 0500 | 3 | 3 | 893936 |  | BHA | FOT | MMOT | 6372 | BHI MUD MTR FAILURE
1465 | 03/22/2022 | ADC-32 | SDGM-1139 | RIG | 04 Feb 0415 - 0500 | 24 | 121.75 | 890891 |  | JF | HERR | SFLN | 10570 | TAGGED ON TOC @ 10,570' [545' BELOW DV TOOL], APPROX. 1766' SHALLOWER THAN PLAN DUE TO MISS-ALIGNMENT ON SURFACE LINES DURING 9-5/8" 1ST STAGE CMT JOB
1467 | 03/22/2022 | ADC-50 | SFNY-1178 | ARM | 14 Mar 2315 - 0000 | 19 | 189.75 | 893464 |  | LCIR | UVLC | NA | 2725 | AT 2,725', LOST COMPLETE CIRCULATION WITH 89 PCF WBM, AT A SIMILAR DEPTH TO ALL OTHER WELLS IN THE SAME PLATFORM. ATTEMPTED TO DRILL WITH SEA WATER AND 110 PCF MUD CAP - OBSERVED RETURNS TO SURFACE. ATTEMPTED TO CURE LOSSES WITH LCM PILLS & LOSS CIRCULATION CEMENT PLUGS - NO SUCCESS. RUN AND SET HAL EZSV, PERFORM TWO CEMENT SQUEEZE JOBS, CURE LOSSES. SET 200' SUSPENSION CMT PLUG ABOVE EZSV, TAG & PT TO 800 PSI - OK. SUSPEND SECTION.
1469 | 03/22/2022 | ADC-53L | HWYH-2524 | TK3 | 21 Mar 0500 - 0500 | 17.25 | 41.25 | 894029 |  | CMT | WSHO | CSG | 7115 | GOT DOWN HOLE LOSSES DURING 7" LINER CMT JOB.
1471 | 03/22/2022 | ADC-55L | UTMN-3199 | TK3 | 22 Mar 0830 - 2330 | 15 | 15 | 893934 |  | JF | HELD | CSG | 2795 | AT 2,795 OBSERVED HELD UP, WHILE WASHING DOWN OBSERVED HOLE PACK OFF. - STAGED UP FLOW RATE SLOWLY FROM 2 BPM TO 8 BPM & WASH DOWN CASING STRING TO 2,862 FT.
1473 | 03/22/2022 | ADC-59L | HRDH-2232 | TK3 | 21 Mar 1500 - 0145 | 20.75 | 34.75 | 893931 |  | JF | HERR | NA | 13082 | OVERSIZE BIT SUB (4-3/8" OD) WAS PICKED UP & INSTALLED IN WBCU ASSEMBLY. BIT SUB TAGGED UP @ 13,082' (BOTTOM OF 4-1/2" X 7" PBR) AND WAS UNABLE TO ENTER 4-1/2" LINER.
1475 | 03/22/2022 | ADC-60 | ABSF-216 | WCS | 22 Mar 0715 - 1115 | 4 | 4 | 893988 |  | TF | FOT | PDHMS | 338 | FIBER OPTICAL CABLE FOR PDMHS WAS NOT SECURED PROPERLY. OPERATION DELAYED BY WFD PDMHS CREW.
1477 | 03/22/2022 | ADC-62L | ANDR-743 | TK3 | 22 Mar 0400 - 0500 | 1 | 1 | 894030 |  | STUK | STBH | BHA | 13285 | WHILE CONNECTION AT 13285 FT TRY TO POOH WITHOUT SUCCESS, UNABLE TO FREE DOWN
1479 | 03/22/2022 | ADC-68L | KRSN-706 | SDM | 20 Mar 1700 - 0500 | 24 | 60 | 893770 |  | BHA | FOT | MMOT | 2786 | WHILE DRILLING AT 2,786 FT, OBSERVED 300 PSI DROP IN PRESSURE WHEN BIT ON-BOTTOM, POOH TO SURFACE, OBSERVED MUD MOTOR TWISTED-OFF.
1481 | 03/22/2022 | ADES-158 | ABQQ-737 | RIG | 21 Mar 2100 - 1700 | 12 | 20 | 893872 |  | BOP | FOT | BOP | 11960 | ATTEMPTS TO UNSCREWE 13-5/8"-5M ANNULAR CAP, NO SUCCESS.
1483 | 03/22/2022 | ADM-262 | MRJN-122 | RIG | 22 Mar 1700 - 2000 | 3 | 3 | 893938 |  | TF | FOT | CTRQ | 243 | UNABLE TO DRIFT UPPER COMPLETION. OBSERVE COUPLINGS INTERNALLY BELLED DUE TO EXCESSIVE TORQUE FROM ADES POWER TONG.
1485 | 03/22/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 261.5 | 893229 |  | LCIR | FRFM | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1487 | 03/22/2022 | ADM-510 | ABSF-228 | DHP | 22 Mar 1830 - 0500 | 10.5 | 10.5 | 893937 |  | TF | FOT | FC | 8013 | ATTEMPT TO BLEED OFF 9 5/8" CASING AFTER CEMENT JOB AND FLOAT NOT HOLDING. UNABLE TO DROP DV OPENING CONE TO PERFORM SECOND STAGE CEMENT JOB
1489 | 03/22/2022 | ARO-3004 | MRJN-2060 | WCR | 22 Mar 1015 - 1115 | 1 | 1 | 894006 |  | TF | HERR | TTRQ | 5495 | CASING NOT MADE UP TO BASE OF TRIANGLE
1491 | 03/22/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 129 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1493 | 03/22/2022 | DQ-50L | HRDH-1492 | BHI | 21 Mar 0000 - 0000 | 19 | 24 | 893928 |  | BHA | FOT | RSS | 8939 | LOST COMMUNICATION WITH RSS TOOL (ATK), TROUBLESHOOTING WITHOUT SUCCESS
1495 | 03/22/2022 | ENS-108 | SFNY-1720 | RIG | 22 Mar 0530 - 0730 | 2 | 2 | 893933 |  | RR | FOT | TDS | 275 | REPAIRED OIL LEAKS ON TDS.
1497 | 03/22/2022 | MP-1 | SFNY-994 | HCM | 21 Mar 1845 - 1715 | 10.25 | 20.5 | 893871 |  | JF | CEDE | NA | 2883 | WHILE RIH WITH WHIPSTOCK, OBSERVED CEMENT DEPOSIT ON SET-BACK. STOPPED RIH, OBSERVED THIN SLIVERS OF CEMENT DEPOSIT, CHECKED FURTHER 2 STDS, SAME. POH TO FLUSH PIPE OF CEMENT DEPOSIT.
1499 | 03/22/2022 | MP-4 | LWHH-20 | RIG | 22 Mar 2330 - 0200 | 2.5 | 2.5 | 893989 |  | JF | HERR | BOP | 8761 | DRILLER INADVERTENTLY CLOSED 4" UPR AGAINST 5" DP BEFORE 7" LINER TEST. POH 5" DP STD. FOUND 5" DP BODY SLIGHTLY CRUSHED.
1501 | 03/22/2022 | OFGRL | HSBH-23 | FME | 22 Mar 1830 - 0500 | 10.5 | 10.5 | 893935 |  | WH | FOT | WH | 11296 | FAILED PRESSURE TEST ON NEWLY INSTALLED 14" PACK-OFF
1503 | 03/22/2022 | PA-861S | HRDH-1060 | TK2 | 20 Mar 0030 - 0400 | 23 | 51.5 | 893581 |  | STUK | STBH | MILL | 11206 | STRING STUCK AT 11,211.86',WORK STRING JARRING DOWN WITH 100KLBS, WITH PUMP/WITHOUT PUMP(550-200GPM/0GPM), WITH TORQUE/WITHOUT TORQUE(16.5K-FT/LBS/0K-FT/LBS) WITHOUT SUCCESS, CANNOT SEE ANY INDICATION OF JAR WORKING AFTER @ 8 TIMES. - JAR FIRED 6-8 TIMES WITH 100K-K/LBS DOWN WEIGHT, NO INDICATION THAT JAR IS FIRING.
1505 | 03/22/2022 | PN-7 | MRJN-775 | BHI | 22 Mar 1145 - 1300 | 1.25 | 1.25 | 893966 |  | BHA | FOT | MWD | 12894 | LOST COMMUNICATION WITH MWD TOOLS, TROUBLESHOOT SAME - NO SUCCESS.
1507 | 03/22/2022 | RM-74A | KARN-60 | ARN | 21 Mar 0700 - 0500 | 24 | 46 | 893925 |  | WON | WTHR | NA | 0 | UNABLE TO MOVE RIG TO KARN 60, PLATFORM DEPRESSURIZING HAS BEEN DELAYED DUE TO RECENT ADVERS WEATHER CONDITIONS.
1509 | 03/22/2022 | SINO-18 | ADHN-10 | RIG | 21 Mar 0430 - 0630 | 1.5 | 2 | 893829 |  | RR | FOT | CSYS | 15349 | WHILE DRILL 5-7/8" TO 15349' OBSERVED LEAKE FROM SAVER SUB CONNECTION.
1511 | 03/22/2022 | SINO-47 | HRDH-1957 | RIG | 22 Mar 0145 - 0330 | 1.75 | 1.75 | 894028 |  | RR | FOT | MPMP | 9318 | HAD LEAKS IN SUCTION MODULES IN MUD PUMP#1 & PUMP#2
1513 | 03/22/2022 | SINO-5L | UTMN-1525 | SPS | 22 Mar 2130 - 0500 | 7.5 | 7.5 | 894007 |  | BHA | FOT | LWD | 8566 | ''ADR'' SHALLOW RISISTIVITY TOOL FAILURE
1515 | 03/22/2022 | SND-2006 | UTMN-3135 | ARM | 20 Mar 1630 - 0500 | 24 | 60.5 | 893947 |  | LCIR | UXGE | NA | 14939 | LOST RETURN AT 14,939 FT IN TAWIL RES WITH 95 PCF OBM.
1517 | 03/22/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0500 | 24 | 253.25 | 891286 |  | STUK | SCSG | LINR | 22213 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
1519 | 03/22/2022 | SP-262 | HZEM-140804 | SCM | 22 Mar 0915 - 1400 | 4.75 | 4.75 | 893986 |  | TF | FOT | PUMP | 1156 | DURING CEMENTING THE 18-5/8" CASING. THE SLB CEMENT UNIT WAS UNABLE TO PUMP OR MIX CEMENT.
1521 | 03/22/2022 | SSA-51 | MNIF-259 | ARN | 22 Mar 2230 - 0100 | 2.5 | 2.5 | 894027 |  | WO | STOP | NA | 13091 | RMD CHANGED THE WELL TRAGET ENTRY FROM LPR ZONE TO LRTR-A ZONE. REVISED DIR PLAN RESPECT TO THE NEW TARGET ENTRY.
1523 | 03/22/2022 | SSA-5892 | SMNH-521700 | HDV | 21 Mar 1530 - 0500 | 24 | 37.5 | 893946 |  | TF | FOT | DV | 11313 | HALLIBURTON 9-5/8" DV TOOL OPENING PLUG DID NOT SEAT TO OPEN DV TOOL
1525 | 03/22/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 312 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1527 | 03/22/2022 | SSA-5971 | UTMN-2302 | RIG | 22 Mar 1100 - 1300 | 2 | 2 | 893985 |  | RR | FOT | DWKS | 11310 | THE MAIN CLUTCH TO ENGAGE THE HOISTING SYSTEM FAILED TO WORK AND THE BLOCK AND STRING COULD NOT BE PICKED UP. THE DRILLSTRING WAS ROTATED AND CIRCULATION OF 300 GPM WAS MAINTAINED.
1529 | 03/22/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 650.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1531 | 03/23/2022 | 095TE | MNIF-225 | BHI | 21 Mar 0100 - 1430 | 9 | 37 | 893948 |  | BHA | FOT | RSS | 14901 | ROTATING SLEEVE IN RSS NOT WORKING. TROUBLESHOOTING SEVERAL TIME NO SUCCESS( RSS FAILURE) . POOH TO CHANGE RSS.
1533 | 03/23/2022 | ADC-12 | ABQQ-64 | BHI | 22 Mar 0200 - 1715 | 11.75 | 14.75 | 893936 |  | BHA | FOT | MMOT | 6372 | BHI MUD MTR FAILURE
1535 | 03/23/2022 | ADC-32 | SDGM-1139 | RIG | 04 Feb 0415 - 0500 | 19 | 140.75 | 890891 |  | JF | HERR | SFLN | 10570 | TAGGED ON TOC @ 10,570' [545' BELOW DV TOOL], APPROX. 1766' SHALLOWER THAN PLAN DUE TO MISS-ALIGNMENT ON SURFACE LINES DURING 9-5/8" 1ST STAGE CMT JOB
1536 | 03/23/2022 | ADC-62L | ANDR-743 | TK3 | 23 Mar 2330 - 0430 | 5 | 5 | 894106 |  | STUK | STBH | BHA | 13197 | AFTER CIRCULATE ACID OUT OF HOLE THRU CHOKE MANIFOLD AND MGS, ATTEMPT TO MOVE PIPE - STRING STUCK
1538 | 03/23/2022 | ADC-62L | ANDR-743 | TK3 | 22 Mar 0400 - 2045 | 15.25 | 16.25 | 894030 |  | STUK | STBH | BHA | 13285 | WHILE CONNECTION AT 13285 FT TRY TO POOH WITHOUT SUCCESS, UNABLE TO FREE DOWN
1539 | 03/23/2022 | ADC-62L | ANDR-743 | TK3 | 23 Mar 2330 - 0430 | 5 | 5 | 894106 |  | STUK | STBH | BHA | 13197 | AFTER CIRCULATE ACID OUT OF HOLE THRU CHOKE MANIFOLD AND MGS, ATTEMPT TO MOVE PIPE - STRING STUCK
1541 | 03/23/2022 | ADC-64L | UTMN-2310 | TK3 | 23 Mar 0730 - 0500 | 21.5 | 21.5 | 894069 |  | LCIR | FRFM | NA | 14815 | TOTAL LOSSES CIRCULATION ON KC02 FORMATION AT 14815 '
1543 | 03/23/2022 | ADES-157 | HRDH-1204 | ARM | 22 Mar 1730 - 0000 | 6.25 | 11.75 | 894031 |  | TF | FOT | TBG | 14982 | WHILE DRIFTING 4 1/2'' COMPLETION, DRIFT COULD NOT PASS. POOH AND CHECK SUSPECTED JT. DRIFT PASS WHILE DRIFTING AT SURFACE. SUSPECTED MANUFACTURER DEFECT ON CONNECTION
1545 | 03/23/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 285.5 | 893229 |  | LCIR | FRFM | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1547 | 03/23/2022 | ADM-510 | ABSF-228 | DHP | 22 Mar 1830 - 0500 | 24 | 34.5 | 893937 |  | TF | FOT | FC | 8013 | ATTEMPT TO BLEED OFF 9 5/8" CASING AFTER CEMENT JOB AND FLOAT NOT HOLDING. UNABLE TO DROP DV OPENING CONE TO PERFORM SECOND STAGE CEMENT JOB
1549 | 03/23/2022 | ARO-3002 | MRJN-813 | HCO | 23 Mar 1100 - 0500 | 18 | 18 | 894086 |  | TF | FOT | PKR | 16264 | PRESSURE UP STRING AGAINST 9-5/8" HALLIBURTON VCH & SEAL ASSEMBLY WITH NO SUCCESS.
1551 | 03/23/2022 | ARO-3003 | SFNY-1740 | RIG | 23 Mar 0600 - 0500 | 23 | 23 | 894105 |  | RR | FOT | PSYS | 0 | UNABLE TO MOVE DRAWWORKS TO PICK-UP DRILL STRING DUE TO ELECTRICAL FAILURE ON DRILL FLOOR POWER SYSTEM.
1553 | 03/23/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 153 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1555 | 03/23/2022 | MP-1 | SFNY-994 | ARM | 23 Mar 0000 - 0100 | 1 | 1 | 894068 |  | HSEI | UNKN | NA | 0 | HELD SAFETY STAND DOWN MEETING WITH BOTH CREWS AND DISCUSS ALL THE HAZARD ON PLATFORM.
1557 | 03/23/2022 | MP-4 | LWHH-20 | SPS | 23 Mar 1930 - 0500 | 9.5 | 9.5 | 894085 |  | LROP | IDPR | BHA | 8776 | WORK WITH DIFFERENT PARAMETES TO D/O L/C. NO PROGRESS.
1559 | 03/23/2022 | OFGRL | HSBH-23 | FME | 22 Mar 1830 - 0500 | 24 | 34.5 | 893935 |  | WH | FOT | WH | 11296 | FAILED PRESSURE TEST ON NEWLY INSTALLED 14" PACK-OFF
1561 | 03/23/2022 | PA-218S | QTIF-515 | RIG | 23 Mar 0500 - 1200 | 7 | 7 | 894066 |  | WH | HERR | WH | 18175 | FOUND ONE OF BOP DSA BOLTS FALLED BETWEEN CHS BOWEL & 7" CSG.
1563 | 03/23/2022 | RM-74A | KARN-60 | ARN | 21 Mar 0700 - 0500 | 24 | 70 | 893925 |  | WON | WTHR | NA | 0 | UNABLE TO MOVE RIG TO KARN 60, PLATFORM DEPRESSURIZING HAS BEEN DELAYED DUE TO RECENT ADVERS WEATHER CONDITIONS.
1565 | 03/23/2022 | SINO-5L | UTMN-1525 | SPS | 22 Mar 2130 - 1800 | 13 | 20.5 | 894007 |  | BHA | FOT | LWD | 8566 | ''ADR'' TOOL FAILURE
1567 | 03/23/2022 | SND-2006 | UTMN-3135 | ARM | 20 Mar 1630 - 0500 | 24 | 84.5 | 893947 |  | LCIR | UXGE | NA | 14939 | LOST RETURN AT 14,939 FT IN TAWIL RES WITH 95 PCF OBM.
1569 | 03/23/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0500 | 24 | 277.25 | 891286 |  | STUK | SCSG | LINR | 22213 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
1571 | 03/23/2022 | SP-258 | HZEM-160612 | RIG | 23 Mar 1900 - 0445 | 9.75 | 9.75 | 894067 |  | RR | FOT | TDS | 2780 | SPENT LONG TIME TO TORQUE UP MOST CONNECTIONS. CHECK SAVER SUB AND FOUND WORN OUT.
1573 | 03/23/2022 | SSA-202 | QTIF-500 | ARM | 23 Mar 1200 - 1230 | .5 | .5 | 894065 |  | LCIR | CFFM | MDCAP | 787 | COMPLETE LOSS OF CIRCULATION AT 787' MD.
1575 | 03/23/2022 | SSA-5892 | SMNH-521700 | HDV | 21 Mar 1530 - 0500 | 24 | 61.5 | 893946 |  | TF | FOT | DV | 11313 | HALLIBURTON 9-5/8" DV TOOL OPENING PLUG DID NOT SEAT TO OPEN DV TOOL
1577 | 03/23/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 1530 | 10.5 | 322.5 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1579 | 03/23/2022 | SSA-5971 | UTMN-2302 | RIG | 23 Mar 0730 - 0930 | 1.5 | 1.5 | 894045 |  | RR | FOT | TDS | 11643 | SAVER SUB STARTED LEAKING DURING DRILLING 8 3/8" HOLE AT 11643'.
1581 | 03/23/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 674.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1583 | 03/24/2022 | ADC-32 | SDGM-1139 | RIG | 04 Feb 0415 - 1200 | 7 | 147.75 | 890891 |  | JF | HERR | SFLN | 10570 | TAGGED ON TOC @ 10,570' [545' BELOW DV TOOL], APPROX. 1766' SHALLOWER THAN PLAN DUE TO MISS-ALIGNMENT ON SURFACE LINES DURING 9-5/8" 1ST STAGE CMT JOB
1585 | 03/24/2022 | ADC-53L | HWYH-2524 | TK3 | 21 Mar 0500 - 0200 | 21 | 86.25 | 894029 |  | CMT | WSHO | CSG | 7115 | GOT DOWN HOLE LOSSES DURING 7" LINER CMT JOB.
1586 | 03/24/2022 | ADC-62L | ANDR-743 | TK3 | 24 Mar 0315 - 0500 | 1.75 | 1.75 | 894166 |  | STUK | STBH | BHA | 12727 | STUCK WHILE CONNECTION AT 12727 FT
1588 | 03/24/2022 | ADC-62L | ANDR-743 | TK3 | 24 Mar 0500 - 2330 | 18.5 | 18.5 | 894165 |  | STUK | STBH | BHA | 13001 | STUCK WHILE CONNECTION AT 13001
1589 | 03/24/2022 | ADC-62L | ANDR-743 | TK3 | 24 Mar 0315 - 0500 | 1.75 | 1.75 | 894166 |  | STUK | STBH | BHA | 12727 | STUCK WHILE CONNECTION AT 12727 FT
1590 | 03/24/2022 | ADC-70 | SFNY-4230 | ARM | 24 Mar 1330 - 2200 | 8.5 | 8.5 | 894151 |  | LCIR | CFFM | MDCAP | 3757 | HAD TOTAL LOSSES. CIRCULATE WITH TREATED SEA WATER AND GEL SWEEPS, MEANWHILE OFFLOAD BARITE FROM SUPPLY VESSEL AND BUILD MUD CAP VOLUME AT 105 PCF.
1592 | 03/24/2022 | ADC-70 | SFNY-4230 | ARM | 23 Mar 2345 - 0700 | 2 | 7.25 | 894145 |  | WCNT | WCC1 | NA | 3591 | DRILLER OBSERVED 8 BBLS PIT GAIN. SPACE OUT AND SHUT IN THE WELL. MONITOR PRESSURE 20 PSI CSG PRESSURE/ 0 PSI SPP. SUSPECTED WATER FLOW FROM UER FOREMATION. BULLHEAD 1.5 X ANNULUS VOLUME/1.5 X STRING VOLUME WITH 85 PCF KILL MUD.
1593 | 03/24/2022 | ADC-70 | SFNY-4230 | ARM | 24 Mar 1330 - 2200 | 8.5 | 8.5 | 894151 |  | LCIR | CFFM | MDCAP | 3757 | HAD TOTAL LOSSES. CIRCULATE WITH TREATED SEA WATER AND GEL SWEEPS, MEANWHILE OFFLOAD BARITE FROM SUPPLY VESSEL AND BUILD MUD CAP VOLUME AT 105 PCF.
1595 | 03/24/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 309.5 | 893229 |  | LCIR | FRFM | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1597 | 03/24/2022 | ADM-510 | ABSF-228 | DHP | 22 Mar 1830 - 0500 | 24 | 58.5 | 893937 |  | TF | FOT | FC | 8013 | ATTEMPT TO BLEED OFF 9 5/8" CASING AFTER CEMENT JOB AND FLOAT NOT HOLDING. UNABLE TO DROP DV OPENING CONE TO PERFORM SECOND STAGE CEMENT JOB
1599 | 03/24/2022 | ARO-3002 | MRJN-813 | HCO | 23 Mar 1100 - 0500 | 24 | 42 | 894086 |  | TF | FOT | PKR | 16264 | PRESSURE UP STRING AGAINST 9-5/8" HALLIBURTON VCH & SEAL ASSEMBLY WITH NO SUCCESS.
1601 | 03/24/2022 | ARO-3003 | SFNY-1740 | RIG | 23 Mar 0600 - 1500 | 10 | 33 | 894105 |  | UPRA | OTH | NA | 0 | UNABLE TO MOVE DRAWWORKS TO PICK-UP DRILL STRING DUE TO ELECTRICAL FAILURE ON DRILL FLOOR POWER SYSTEM.
1603 | 03/24/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 177 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1604 | 03/24/2022 | DPS-4 | MDRK-54 | BCR | 24 Mar 0300 - 0400 | 1 | 1 | 894167 |  | TF | FOT | CRT | 8505 | CRT PACKER WAS FAILED WHILE FILLING UP CASING AT 160 PSI.
1606 | 03/24/2022 | DPS-4 | MDRK-54 | BCR | 24 Mar 2215 - 2345 | 1.5 | 1.5 | 894090 |  | TF | FOT | CRT | 5295 | CRT MALFUNCTION. FAINLURE OF REALESING CRT AFTER CONNECTION IS MADE.
1607 | 03/24/2022 | DPS-4 | MDRK-54 | BCR | 24 Mar 0300 - 0400 | 1 | 1 | 894167 |  | TF | FOT | CRT | 8505 | CRT PACKER WAS FAILED WHILE FILLING UP CASING AT 160 PSI.
1609 | 03/24/2022 | DPS-74 | NJYN-54 | RIG | 24 Mar 1630 - 2030 | 4 | 4 | 894148 |  | RR | FOT | TDS | 12911 | WHILE DRLG 8 3/8" DIRCTIONAL HOLE, FOUND SMALL LEAKAGE FROM WASH PIPE AFTER CONNECTION.
1610 | 03/24/2022 | NBR-16S | HMYM-433314 | RIG | 24 Mar 0700 - 0800 | 1 | 1 | 894154 |  | JF | XTRI | NA | 4864 | EXCESSIVE TIME TO L/D TOOLS
1612 | 03/24/2022 | NBR-16S | HMYM-433314 | RIG | 24 Mar 2230 - 0130 | 3 | 3 | 894153 |  | JF | XTRI | BOP | 4684 | EXCESSIVE TIME TO N/U BOP
1613 | 03/24/2022 | NBR-16S | HMYM-433314 | RIG | 24 Mar 0700 - 0800 | 1 | 1 | 894154 |  | JF | XTRI | NA | 4864 | EXCESSIVE TIME TO L/D TOOLS
1615 | 03/24/2022 | OFGRL | HSBH-23 | FME | 22 Mar 1830 - 0500 | 24 | 58.5 | 893935 |  | WH | FOT | WH | 11296 | FAILED PRESSURE TEST ON NEWLY INSTALLED 14" PACK-OFF
1617 | 03/24/2022 | PA-218S | QTIF-515 | RIG | 24 Mar 1800 - 2000 | 2 | 2 | 894109 |  | RR | FOT | HSYS | 18175 | FOUND BOP TEST UNIT WATER FEED LINE PLUGGED.
1619 | 03/24/2022 | SND-2006 | UTMN-3135 | ARM | 20 Mar 1630 - 0500 | 22.5 | 107 | 893947 |  | LCIR | UXGE | NA | 14939 | LOST RETURN AT 14,939 FT IN TAWIL RES WITH 95 PCF OBM.
1621 | 03/24/2022 | SP-258 | HZEM-160612 | RIG | 24 Mar 0530 - 1700 | 11.5 | 11.5 | 894149 |  | RR | FOT | TDS | 3500 | AFTER FILL UP & DISCONNECT TDS FOUND SAVER SUB THREAD DAMAGED WITH TOOL JOINT BOX CONNECTION.
1623 | 03/24/2022 | SSA-5892 | SMNH-521700 | HDV | 21 Mar 1530 - 0500 | 24 | 85.5 | 893946 |  | TF | FOT | DV | 11313 | HALLIBURTON 9-5/8" DV TOOL OPENING PLUG DID NOT SEAT TO OPEN DV TOOL
1625 | 03/24/2022 | SSA-5917 | HRDH-2344 | CRW | 24 Mar 1630 - 0500 | 12.5 | 12.5 | 894150 |  | BHA | FOT | WBCL | 14237 | PERFORMED NEGATIVE TEST 1 HRS, HAD COMMUNICATION, CORETRAX PKR FAILED.
1627 | 03/24/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 18.5 | 341 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1629 | 03/24/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 698.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1631 | 03/25/2022 | ADC-16 | JAHM-6 | SWL | 25 Mar 1400 - 1800 | 4 | 4 | 894205 |  | TF | FOT | WLT | 8340 | LOST COMMUNICATION WITH W/L TOOL DURING SURFACE TEST
1633 | 03/25/2022 | ADC-45 | KHRS-334 | ARM | 25 Mar 1100 - 1330 | 2.5 | 2.5 | 894228 |  | WON | WTHR | NA | 0 | HIGH WIND SPEED
1634 | 03/25/2022 | ADC-55L | UTMN-3199 | TK3 | 25 Mar 1230 - 1530 | 3 | 9.5 | 894188 |  | JF | HERR | NA | 2667 | 4" LINE FROM CHOKE MANIFOLD TO MGS NOT ALIGNED CORRECTLY DURING RIG MOVE
1636 | 03/25/2022 | ADC-55L | UTMN-3199 | TK3 | 25 Mar 1600 - 2230 | 6.5 | 6.5 | 894159 | 894188 | JF | HERR | NA | 2667 | CUTTINGS DISCHARGE LINE NOT ALIGNED WITH WASTE PIT AFTER RIG MOVE
1637 | 03/25/2022 | ADC-55L | UTMN-3199 | TK3 | 25 Mar 1230 - 1530 | 3 | 9.5 | 894188 |  | JF | HERR | NA | 2667 | 4" LINE FROM CHOKE MANIFOLD TO MGS NOT ALIGNED CORRECTLY DURING RIG MOVE
1638 | 03/25/2022 | ADC-62L | ANDR-743 | TK3 | 25 Mar 2330 - 0500 | 5 | 5 | 894226 |  | STUK | STBH | BHA | 12635 | STUCK WHILE STICKING TEST AT 30 SEC PRIOR CONNECTION.
1640 | 03/25/2022 | ADC-62L | ANDR-743 | TK3 | 24 Mar 0315 - 1715 | 12.25 | 14 | 894166 |  | STUK | STBH | BHA | 12727 | STUCK WHILE CONNECTION AT 12727 FT
1641 | 03/25/2022 | ADC-62L | ANDR-743 | TK3 | 25 Mar 2330 - 0500 | 5 | 5 | 894226 |  | STUK | STBH | BHA | 12635 | STUCK WHILE STICKING TEST AT 30 SEC PRIOR CONNECTION.
1643 | 03/25/2022 | ADC-70 | SFNY-4230 | ARM | 24 Mar 1330 - 2000 | 5.5 | 14.5 | 894151 |  | LCIR | CFFM | MDCAP | 3757 | HAD TOTAL LOSSES. CIRCULATE WITH TREATED SEA WATER AND GEL SWEEPS AT LOW GPM, MEANWHILE OFFLOAD BARITE FROM SUPPLY VESSEL AND BUILD MUD CAP VOLUME AT 105 PCF.
1645 | 03/25/2022 | ADES-14 | HRDH-178 | ARM | 25 Mar 0045 - 0500 | 4.25 | 4.25 | 894192 |  | STUK | PSSW | NA | 9750 | DRILL STRING STUCK DIFFRENTIALLY.
1647 | 03/25/2022 | ADES-173 | HRDH-2256 | RIG | 25 Mar 0330 - 0500 | 1.5 | 1.5 | 894162 |  | RR | FOT | TDS | 11670 | TDS BLOWER DOWN - TROUBLESHOOTING ONGOING
1649 | 03/25/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 23 | 332.5 | 893229 |  | LCIR | UVLC | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1651 | 03/25/2022 | ADM-510 | ABSF-228 | DHP | 22 Mar 1830 - 0315 | 22.25 | 80.75 | 893937 |  | TF | FOT | FC | 8013 | ATTEMPT TO BLEED OFF 9 5/8" CASING AFTER CEMENT JOB AND FLOAT NOT HOLDING. UNABLE TO DROP DV OPENING CONE TO PERFORM SECOND STAGE CEMENT JOB
1653 | 03/25/2022 | ADM-656 | ABSF-169 | RIG | 25 Mar 1400 - 0500 | 15 | 15 | 894206 |  | JF | HERR | BHA | 0 | MOUSE HOLE PARTED AND FALL DOWN TO PLATFORM.
1655 | 03/25/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 24 | 37 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
1657 | 03/25/2022 | ARO-2003 | ZULF-299 | ARM | 25 Mar 1000 - 0330 | 17.5 | 17.5 | 894209 |  | WON | WTHR | NA | 0 | STRONG WINDS ROUGH SEAS UNABLE TO PERFORM RIG MOVE.
1659 | 03/25/2022 | ARO-3002 | MRJN-813 | HCO | 23 Mar 1100 - 1445 | 9.75 | 51.75 | 894086 |  | TF | FOT | PKR | 16264 | PRESSURE UP STRING AGAINST 9-5/8" HALLIBURTON VCH & SEAL ASSEMBLY WITH NO SUCCESS. HALL 9-5/8 VCH PKR PARTED AT THE MIDDLE OF THE ASSY, LEAVING SBE, CERAMIC DISC & TAIL PIPE IN HOLE.
1660 | 03/25/2022 | ARO-3003 | SFNY-1740 | RIG | 25 Mar 1500 - 1715 | 2.25 | 2.25 | 894161 |  | RR | FOT | TDS | 239 | TD'S POWER DOWN, TROUBLE SHOOTING RIG FLOOR PLC SYSTEM.
1662 | 03/25/2022 | ARO-3003 | SFNY-1740 | RIG | 25 Mar 0945 - 1145 | 2 | 2 | 894160 |  | RR | FOT | TDS | 153 | RIG CHANGE OUT SWIVEL PACKING ON TDS & ADJUST IBOP ACTUATOR.
1663 | 03/25/2022 | ARO-3003 | SFNY-1740 | RIG | 25 Mar 1500 - 1715 | 2.25 | 2.25 | 894161 |  | RR | FOT | TDS | 239 | TD'S POWER DOWN, TROUBLE SHOOTING RIG FLOOR PLC SYSTEM.
1665 | 03/25/2022 | CG-1 | ZULF-1206 | SDM | 25 Mar 0200 - 0500 | 1.75 | 1.75 | 894190 |  | BHA | FOT | MWD | 7053 | TROUBLESHOOTING ON SLB MWD TOOLS
1667 | 03/25/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 21.5 | 198.5 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1669 | 03/25/2022 | DPS-44 | UTMN-3151 | ARM | 25 Mar 1600 - 1815 | 2.25 | 2.25 | 894194 |  | WO | HMWT | NA | 5525 | STOPPED DRILLING DUE TO WATER LINE PARTED & RESUMED AFTER FIXING IT.
1671 | 03/25/2022 | MP-1 | SFNY-994 | SDM | 25 Mar 1700 - 1845 | 1.75 | 1.75 | 894225 |  | DD | IDPR | RSS | 4643 | SLB DD DEVIATED FROM THE ORIGINAL PLAN WHICH LEAD TO CREATE EXCESSIVE DOG LEG AND DRILLED EXTRA FOOTAGE.
1673 | 03/25/2022 | NA-207S | SHYB-194 | RIG | 25 Mar 1400 - 2000 | 6 | 6 | 894227 |  | BOP | FOT | CTRL | 0 | WHILE FUNCTION TEST BOPE FOUND CHOKE MANIFOLD HCR CANNOT OPERATE FROM BOTH REMOTE STATIONS. RIG ELECTRICIAN FIX LOOSE WIRE & PUSH BUTTON PROBLEM.
1675 | 03/25/2022 | NBR-16S | HMYM-433314 | RIG | 25 Mar 1145 - 1345 | 2 | 2 | 894193 |  | RR | FOT | TDS | 0 | TOP DRIVE REPAIR
1677 | 03/25/2022 | NBR-783S | NJYN-89 | RIG | 25 Mar 1630 - 0145 | 9.25 | 9.25 | 894163 |  | RR | FOT | CHK | 6110 | HAD LEAK ON CHOCK MANIFOLD VALVES # 3, 4, 6 & 11 WHILE PRESSURE TEST
1679 | 03/25/2022 | OFGRL | HSBH-23 | ARM | 25 Mar 2145 - 0500 | 7.25 | 7.25 | 894187 |  | WON | WTHR | NA | 11296 | WAIT ON WEATHER FOR CRANE OPERATIONS TO PRESSURE TEST WELLHEAD
1681 | 03/25/2022 | PN-9 | MRJN-92 | RIG | 25 Mar 0300 - 0500 | 2 | 2 | 894207 |  | RR | FOT | TDS | 9350 | WHILE DRILL OUT CEMENT OBSERVED TDS WASH PIPE LEAKING.
1683 | 03/25/2022 | SINO-12L | HRDH-410 | HWP | 25 Mar 2030 - 2200 | 1.5 | 1.5 | 894208 |  | TF | FOT | WLT | 9178 | WHILE HES RECORDING IMAGE/CALIPER LOGS, ONE OUTER CABLE ARMOR STRAND GOT LOOSE AND ACCUMULATED IN BUSHING.
1685 | 03/25/2022 | SINO-33L | KHRS-1715 | ARM | 25 Mar 2200 - 0500 | 7 | 7 | 894210 |  | LCIR | UVLC | NA | 275 | HAD COMPLETE LOSSES @ 275 FT.
1687 | 03/25/2022 | SL-7 | ZULF-1335 | HML | 25 Mar 0530 - 0415 | 22.75 | 22.75 | 894191 |  | TF | FOT | WPSML | 5940 | UNABLE TO RETRIEVE HALLIBURTON WHIPSTOCK.
1689 | 03/25/2022 | SND-2001 | UTMN-2329 | RIG | 25 Mar 1530 - 0500 | 13.5 | 13.5 | 894229 |  | FISH | FWTS | BHA | 6086 | LOST 140 KLBS OF STRING WT IN HOLE.
1691 | 03/25/2022 | SND-2006 | UTMN-3135 | ARM | 20 Mar 1630 - 0500 | 14 | 121 | 893947 |  | LCIR | UXGE | NA | 14939 | LOST RETURN AT 14,939 FT IN TAWIL RES WITH 95 PCF OBM.
1693 | 03/25/2022 | SNF036 | MRJN-901 | HWP | 24 Mar 2200 - 1815 | 13.25 | 20.25 | 894156 |  | TF | FOT | WLT | 8189 | HALLIBURTON WL RDT PACKER DID NOT MAKE SEAL AFTER ATTENPTING TO INFLATE SEVERAL TIMES AT SEVERAL DEPTHS.
1695 | 03/25/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0500 | 24 | 325.25 | 891286 |  | STUK | SCSG | LINR | 22213 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
1697 | 03/25/2022 | SSA-101 | BRRI-1145 | BAW | 25 Mar 1530 - 0230 | 11 | 11 | 894158 |  | TF | FOT | WLT | 8800 | TRIP OUT TO CHANGE BAKER WL RPM TOOL (RESERVOIR PERFORMANCE MONITORING) DUE TO DATA QUALITY ISSUE.
1699 | 03/25/2022 | SSA-5820 | SDGM-1215 | ARM | 25 Mar 1030 - 1530 | 5 | 5 | 894186 |  | WON | WTHR | NA | 10550 | SHUT DOWN OPERATIONS DUE TO HIGH WIND SPEED
1701 | 03/25/2022 | SSA-5917 | HRDH-2344 | CRW | 24 Mar 1630 - 2230 | 15.5 | 28 | 894150 |  | BHA | FOT | WBCL | 14237 | PERFORMED NEGATIVE TEST 1 HRS, HAD COMMUNICATION, CORETRAX PKR FAILED.
1703 | 03/25/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 365 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1705 | 03/25/2022 | ZPEC-1 | HMYM-846 | RIG | 25 Mar 2200 - 0500 | 7 | 7 | 894189 |  | RR | FOT | RSYS | 1832 | WHILE DRILLING OBSERVED TORQUE INCREASED AND ROTARY OVERHEATED.
1707 | 03/26/2022 | ADC-14 | HRDH-694 | RIG | 26 Mar 1600 - 1630 | .5 | .5 | 894247 |  | RR | FOT | PSYS | 14902 | DOWN TIME ON ADC: UNABLE TO PRESSURE TEST X-TREE, TROUBLESHOOT ADC TESTING PUMP.
1709 | 03/26/2022 | ADC-60 | ABSF-216 | RIG | 25 Mar 1900 - 0700 | 2 | 12 | 894212 |  | JF | HERR | NA | 4936 | UNABLE TO LATCH ON INTERWELL PLUG WITH RETRIEVEING TOOL.
1711 | 03/26/2022 | ADC-62L | ANDR-743 | TK3 | 25 Mar 2330 - 1515 | 8.25 | 13.25 | 894226 |  | STUK | STBH | BHA | 12635 | STUCK WHILE STICKING TEST AT 30 SEC PRIOR CONNECTION.
1712 | 03/26/2022 | ADC-70 | SFNY-4230 | ARM | 26 Mar 0500 - 0500 | 17.25 | 17.25 | 894232 |  | DD | DFOR | MMOT | 4723 | UABLE TO SLIDE WITH SLB MM DUE TO STICKY FORMATION. ROUND TRIP TO C/O BHA.
1714 | 03/26/2022 | ADC-70 | SFNY-4230 | ARM | 26 Mar 1145 - 1830 | 6.75 | 6.75 | 894231 |  | WON | WTHR | NA | 2819 | WOW. UNABLE WORKING SUPPLY VESSEL TO OFFLOAD BARITE TO MIX NEW MUD CAP VOLUMES AT 105 PCF.
1715 | 03/26/2022 | ADC-70 | SFNY-4230 | ARM | 26 Mar 0500 - 0500 | 17.25 | 17.25 | 894232 |  | DD | DFOR | MMOT | 4723 | UABLE TO SLIDE WITH SLB MM DUE TO STICKY FORMATION. ROUND TRIP TO C/O BHA.
1717 | 03/26/2022 | ADES-14 | HRDH-178 | ARM | 25 Mar 0030 - 0600 | 1 | 5.5 | 894192 |  | STUK | PSSW | NA | 9750 | DRILL STRING STUCK DIFFRENTIALLY.
1719 | 03/26/2022 | ADES-40 | ANDR-469 | RIG | 26 Mar 1300 - 1900 | 6 | 6 | 894248 |  | RR | FPMP | MPMP | 0 | OBSERVED MUD PUMP PRESSURE DROPPED TO 50 PSI WHILE DRILLING CMT. FOUND SUCTION LINE & MUD PUMP SCREENS PLUGGED WITH CUTTINGS.
1721 | 03/26/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 23.5 | 356 | 893229 |  | LCIR | UVLC | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1723 | 03/26/2022 | ADM-656 | ABSF-169 | RIG | 26 Mar 0500 - 0500 | 24 | 24 | 894235 |  | JF | HERR | BHA | 0 | MOUSE HOLE PARTED AND FALL DOWN TO PLATFORM.
1725 | 03/26/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 24 | 61 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
1727 | 03/26/2022 | ARO-2003 | ZULF-299 | ARM | 25 Mar 1000 - 0500 | 24 | 43 | 894209 |  | WON | WTHR | NA | 0 | STRONG WINDS ROUGH SEAS UNABLE TO PERFORM RIG MOVE.
1729 | 03/26/2022 | ARO-3002 | MRJN-813 | HCO | 23 Mar 1100 - 0500 | 24 | 75.75 | 894086 |  | TF | FOT | PKR | 16264 | PRESSURE UP STRING AGAINST 9-5/8" HALLIBURTON VCH & SEAL ASSEMBLY WITH NO SUCCESS. HALL 9-5/8 VCH PKR PARTED AT THE MIDDLE OF THE ASSY, LEAVING SBE, CERAMIC DISC & TAIL PIPE IN HOLE.
1731 | 03/26/2022 | ARO-3003 | SFNY-1740 | RIG | 25 Mar 1500 - 0500 | 19.5 | 21.75 | 894161 |  | UPRA | OTH | NA | 84 | POWER DOWN ON DRILL FLOOR CONSOLE, TROUBLE SHOOTING RIG FLOOR PLC SYSTEM.
1732 | 03/26/2022 | ARO-4001 | MRJN-539 | RIG | 26 Mar 0230 - 0500 | 2.5 | 2.5 | 894250 |  | BOP | MRWL | DVRT | 8800 | WHILE FILLING DP OBSERVED DIVERTOR LEAKING.
1734 | 03/26/2022 | ARO-4001 | MRJN-539 | RIG | 26 Mar 1730 - 2130 | 4 | 4 | 894249 |  | RR | FOT | SWVL | 8800 | WASHPIPE ASSEMBLY WAS LEAKING
1735 | 03/26/2022 | ARO-4001 | MRJN-539 | RIG | 26 Mar 0230 - 0500 | 2.5 | 2.5 | 894250 |  | BOP | MRWL | DVRT | 8800 | WHILE FILLING DP OBSERVED DIVERTOR LEAKING.
1737 | 03/26/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 222.5 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1739 | 03/26/2022 | DQ-50L | HRDH-1492 | ARM | 26 Mar 0500 - 0630 | 1.5 | 1.5 | 894234 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER - HIGH WIND SPEED
1741 | 03/26/2022 | ENSCO-76 | MRJN-851 | SCD | 26 Mar 1300 - 0500 | 10 | 10 | 894195 |  | TF | FOT | GYRO | 1573 | SCIENTIFIC DRILLING UNABLE TO GET GOOD GWD DIRECTIONAL SURVEY.
1743 | 03/26/2022 | MP-1 | SFNY-994 | SDM | 25 Mar 1700 - 0500 | 21.25 | 23 | 894225 |  | DD | IDPR | RSS | 4643 | SLB DD DEVIATED FROM THE ORIGINAL PLAN WHICH LEAD TO CREATE EXCESSIVE DOG LEG AND DRILLED EXTRA FOOTAGE.
1745 | 03/26/2022 | NBR-783S | NJYN-89 | RIG | 25 Mar 1630 - 0500 | 24 | 36.5 | 894163 |  | RR | FOT | CHK | 6110 | HAD LEAK ON CHOCK MANIFOLD VALVES WHILE PRESSURE TEST
1747 | 03/26/2022 | NBR-987S | ABTL-2 | ARN | 26 Mar 1900 - 2000 | 1 | 1 | 894197 |  | WO | STOP | NA | 17934 | V-SAT WENT DOWN, NEED REALTIME DATA
1749 | 03/26/2022 | OFGRL | HSBH-23 | ARM | 25 Mar 2145 - 1500 | 10 | 17.25 | 894187 |  | WON | WTHR | NA | 11296 | WAIT ON WEATHER FOR CRANE OPERATIONS TO PRESSURE TEST WELLHEAD
1751 | 03/26/2022 | PA-218S | QTIF-515 | RIG | 26 Mar 1500 - 2100 | 6 | 6 | 894211 |  | RR | FOT | HSYS | 18175 | REPAIR IRON ROUGHNECK DUE TO FAILURE IN HYDRAULIC HOSE.
1753 | 03/26/2022 | RM-74A | KARN-60 | ARM | 26 Mar 0700 - 0500 | 22 | 22 | 894245 |  | WON | WTHR | NA | 0 | SUSPEND FINAL RIG POSITIONING DUE TO ADVERSE WEATHER CONDITON
1755 | 03/26/2022 | SCTD-1 | UTMN-3141 | RIG | 26 Mar 2030 - 0400 | 7.5 | 7.5 | 894233 |  | RR | FOT | RWCS | 12380 | AFTER UNDEPLOY BHA#1 FOUND M-SEALS ON UPPER STRIPPER ARE DAMAGED , CHANGED SAME AND HYDRO & N2 P/TEST.
1757 | 03/26/2022 | SL-7 | ZULF-1335 | HML | 25 Mar 0530 - 1115 | 5.5 | 28.25 | 894191 |  | TF | FOT | WPSML | 5940 | UNABLE TO RETRIEVE HALLIBURTON WHIPSTOCK.
1759 | 03/26/2022 | SND-2001 | UTMN-2329 | RIG | 25 Mar 1530 - 0500 | 24 | 37.5 | 894229 |  | FISH | FWTS | BHA | 6086 | 1032 FT OF FISH LEFT IN HOLE.
1761 | 03/26/2022 | SND-2006 | UTMN-3135 | ARM | 20 Mar 1630 - 1700 | 12 | 133 | 893947 |  | LCIR | UXGE | NA | 14939 | LOST RETURN AT 14,939 FT IN TAWIL RES WITH 95 PCF OBM.
1763 | 03/26/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 22 | 387 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1765 | 03/26/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 746.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1767 | 03/26/2022 | ZPEC-1 | HMYM-846 | RIG | 25 Mar 2200 - 0800 | 3 | 10 | 894189 |  | RR | FOT | RSYS | 1832 | WHILE DRILLING OBSERVED TORQUE INCREASED DUE TO ROTARY TABLE FAILURE ( BASE PLATE BOLTS OF TRUNING TABLE LOOSE).
1769 | 03/27/2022 | ADC-17 | ZULF-1212 | RIG | 27 Mar 0500 - 1045 | 1.25 | 1.25 | 894199 |  | RR | FOT | MPMP | 3463 | REPAIR RIG MUD PUMPS
1771 | 03/27/2022 | ADC-31 | SDGM-1192 | RIG | 27 Mar 0830 - 0930 | 1 | 1 | 894240 |  | RR | FOT | DWKS | 10590 | DRAW WORKS LOW CLUTCH FAILURE.
1773 | 03/27/2022 | ADC-70 | SFNY-4230 | ARM | 26 Mar 0500 - 2200 | 17 | 34.25 | 894232 |  | DD | DFOR | MMOT | 4723 | UABLE TO SLIDE WITH SLB MM DUE TO STICKY FORMATION. ROUND TRIP TO C/O BHA.
1775 | 03/27/2022 | ADM-261 | MRJN-137 | RIG | 27 Mar 1330 - 1530 | 2 | 2 | 894239 |  | JF | HERR | MPMP | 7754 | TROUBLESHOOT VALVE ON MUD MIXING SYSTEM, ALLOWING THE FLUID TO BACKFLOW TO THE MIXING HOPPER CONTAMINATING SPACER.
1777 | 03/27/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0500 | 24 | 380 | 893229 |  | LCIR | UVLC | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1779 | 03/27/2022 | ADM-655 | BRRI-218 | EX1 | 18 Mar 2000 - 0500 | 18 | 20 | 893576 |  | TF | FOT | SLICK | 0 | SLICKLINE WIRE PARTED AFTER RELEASING INTERWELL 4-1/2" HEX PLUG WITH NORMAL RELEASING OVERPULL.
1781 | 03/27/2022 | ADM-656 | ABSF-169 | RIG | 25 Mar 1400 - 1200 | 7 | 46 | 894206 |  | JF | HERR | BHA | 0 | MOUSE HOLE PARTED AND FALL DOWN TO PLATFORM.
1783 | 03/27/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 24 | 85 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
1785 | 03/27/2022 | ARO-2003 | ZULF-299 | ARM | 25 Mar 1000 - 0500 | 24 | 67 | 894209 |  | WON | WTHR | NA | 0 | STRONG WINDS ROUGH SEAS UNABLE TO PERFORM RIG MOVE.
1787 | 03/27/2022 | ARO-3002 | MRJN-813 | HCO | 23 Mar 1100 - 0500 | 24 | 99.75 | 894086 |  | TF | FOT | PKR | 16264 | PRESSURE UP STRING AGAINST 9-5/8" HALLIBURTON VCH & SEAL ASSEMBLY WITH NO SUCCESS. HALL 9-5/8 VCH PKR PARTED AT THE MIDDLE OF THE ASSY, LEAVING SBE, CERAMIC DISC & TAIL PIPE IN HOLE.
1789 | 03/27/2022 | ARO-3003 | SFNY-1740 | RIG | 25 Mar 1500 - 0715 | 2.25 | 24 | 894161 |  | UPRA | OTH | NA | 84 | POWER DOWN ON DRILL FLOOR CONSOLE, TROUBLE SHOOTING RIG FLOOR PLC SYSTEM.
1791 | 03/27/2022 | ARO-3004 | MRJN-2060 | RIG | 27 Mar 2330 - 0500 | 5.5 | 5.5 | 894274 |  | RR | FOT | RWCS | 2030 | FOUND ONE OF THE ELECTRICAL MOTOR ON BOP KOOMEY UNIT NOT WORKING, REPLACED SAME WITH NEW ONE.
1793 | 03/27/2022 | ARO-4001 | MRJN-539 | RIG | 26 Mar 0230 - 0630 | 1.5 | 4 | 894250 |  | BOP | MRWL | DVRT | 8800 | WHILE FILLING DP OBSERVED DIVERTOR LEAKING.
1795 | 03/27/2022 | BCTD-3 | HRDH-1375 | ARM | 26 Mar 1300 - 0500 | 24 | 40 | 894236 |  | STUK | STBH | BHA | 13600 | BHA STUCK AT SIDETRACK POINT.
1797 | 03/27/2022 | BCTD-4 | SHDN-12 | RIG | 27 Mar 1500 - 0200 | 11 | 11 | 894266 |  | BHA | FOT | CTAC | 14751 | EDS FAULT WHILE PERFORMING CORRELATION, TROUBLESHOOT WITHOUT SUCCESS. POH TO CHANGE BHA.
1799 | 03/27/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 246.5 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1801 | 03/27/2022 | DQ-47 | KHRS-1707 | WWD | 27 Mar 0500 - 2300 | 18 | 18 | 894271 |  | TF | FOT | WPSTK | 1475 | WHILE RIH W/ 7" WFD WSTK/MILL ASSY, HANGED UP @ 1,475' WITH STEERING MILL IN 7" LINER TOP PKR, MANY TRIALS TO PASS BUT NO SUCCESS.
1803 | 03/27/2022 | ENS-108 | SFNY-1720 | RIG | 27 Mar 1645 - 1915 | 2.5 | 2.5 | 894252 |  | RR | FOT | DWKS | 1137 | OBSERVED E-STOP FAULT ON AMPHEON SYSTEM ENGAGING EMERGENCY DRAWWORKS BRAKE.
1804 | 03/27/2022 | ENSCO-76 | MRJN-851 | RIG | 27 Mar 0400 - 0500 | 1 | 1 | 894275 |  | RR | FOT | CSYS | 2363 | HAD LEAKAGE IN WASHPIPE OF TDS
1806 | 03/27/2022 | ENSCO-76 | MRJN-851 | SCD | 26 Mar 1300 - 1715 | 11.75 | 21.75 | 894195 |  | TF | FOT | GYRO | 1846 | SCIENTIFIC DRILLING UNABLE TO GET GOOD GWD DIRECTIONAL SURVEY.
1807 | 03/27/2022 | ENSCO-76 | MRJN-851 | RIG | 27 Mar 0400 - 0500 | 1 | 1 | 894275 |  | RR | FOT | CSYS | 2363 | HAD LEAKAGE IN WASHPIPE OF TDS
1809 | 03/27/2022 | MP-1 | SFNY-994 | SDM | 25 Mar 1700 - 1215 | 7.25 | 30.25 | 894225 |  | DD | IDPR | RSS | 4643 | SLB DD DEVIATED FROM THE ORIGINAL PLAN WHICH LEAD TO CREATE EXCESSIVE DOG LEG AND DRILLED EXTRA FOOTAGE.
1811 | 03/27/2022 | NA-128S | ZMLH-5 | ARM | 27 Mar 0345 - 0500 | 1.25 | 1.25 | 894277 |  | TF | MAOS | TBG | 16601 | WHILE DRIFTING 4 1/2'' COMPLETION, DRIFT COULD NOT PASS @ 2387 FT.
1813 | 03/27/2022 | NA-18S | SDGM-442 | SDM | 27 Mar 1530 - 0500 | 13.5 | 13.5 | 894241 |  | BHA | FOT | MWD | 11574 | LOST MWD SIGNAL FROM SLB TOOLS. SENT DOWNLINK & TROUBLESHOOTING TOOLS; NO SUCCESS.
1815 | 03/27/2022 | NBR-115S | HRDH-2140 | RIG | 27 Mar 0530 - 0930 | 4 | 4 | 894198 |  | RR | FOT | DWKS | 17320 | BLOCKS WOULD NOT LOWER AT AN ACCEPTABLE SPEED. FOUND ONE RETENTION SPRING BROKE ON THE BRAKE BANDS.
1817 | 03/27/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 0500 | 22.5 | 22.5 | 894237 |  | LCIR | CFFM | LCM | 8416 | FULL MUD LOSSES ENCOUNTERED @ 8,416' IN FADHILI FORMATION.
1819 | 03/27/2022 | NBR-591S | HRDH-1921 | RIG | 27 Mar 1830 - 0500 | 10.5 | 10.5 | 894269 |  | RR | FOT | TDS | 581 | LOST COMMUNICATION AND FUNCTION WITH TOP DIVE SYSTEM
1821 | 03/27/2022 | NBR-783S | NJYN-89 | RIG | 25 Mar 1630 - 0430 | 23.5 | 60 | 894163 |  | RR | FOT | CHK | 6110 | HAD LEAK ON CHOCK MANIFOLD VALVES WHILE PRESSURE TEST
1823 | 03/27/2022 | OFGRL | HSBH-23 | ARM | 27 Mar 0930 - 2145 | 10.5 | 10.5 | 894268 |  | WON | WTHR | NA | 11296 | WAIT ON WEATHER FOR CRANE OPERATIONS
1825 | 03/27/2022 | PA-218S | QTIF-515 | RIG | 27 Mar 2200 - 0000 | 2 | 2 | 894273 |  | RR | FPMP | MPMP | 18175 | NOTICED PRESSURE LOSS WHILE P/T SURFACE LINE.
1827 | 03/27/2022 | PA-861S | HRDH-1060 | BFW | 27 Mar 0730 - 1400 | 6.5 | 6.5 | 894267 |  | JF | UITE | MILL | 11235 | WHILE MILLING AT BOTTOM, STRING GOT STUCK.
1829 | 03/27/2022 | PN-7 | MRJN-775 | RIG | 27 Mar 0645 - 0745 | 1 | 1 | 894238 |  | RR | LHFL | HSYS | 12901 | PIPE HANDLING RACKER HYDRULIC HOSE BURST.
1831 | 03/27/2022 | RM-74A | KARN-60 | ARM | 26 Mar 0700 - 0500 | 24 | 46 | 894245 |  | WON | WTHR | NA | 0 | UNABLE TO FINAL RIG POSITIONING DUE TO ADVERSE WEATHER CONDITON.WOW.
1833 | 03/27/2022 | SND-2001 | UTMN-2329 | RIG | 25 Mar 1530 - 0500 | 23.5 | 61 | 894229 |  | FISH | FWTS | BHA | 6086 | 1032 FT OF FISH LEFT IN HOLE.
1835 | 03/27/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 14.25 | 175.5 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
1837 | 03/27/2022 | SP-110 | BRRI-562 | RIG | 27 Mar 1630 - 1830 | 2 | 2 | 894251 |  | RR | FOT | TDS | 1375 | REPAIR ON TDS- TROUBLESHOOT AND FIX THE SIGNAL CABLE CONNECTOR.
1839 | 03/27/2022 | SP-122 | ANDR-602 | BTT | 27 Mar 1730 - 0500 | 11.5 | 11.5 | 894270 |  | TF | FOT | DRFT | 11876 | BAKER THRU-TUBING CUTTER TOOLS PLUGGED. UNABLE TO CUT 4-1/2" FISH TUBING WITH SAME.
1841 | 03/27/2022 | SP-260 | HZEM-161002 | IP | 27 Mar 2130 - 2345 | 2.25 | 2.25 | 894276 |  | JF | FOI | CSG | 5073 | IPS FAILURE ON CSG INSPECTION.
1843 | 03/27/2022 | SSA-5820 | SDGM-1215 | RIG | 27 Mar 1400 - 1730 | 3.5 | 3.5 | 894242 |  | RR | FOT | CSYS | 9515 | WHILE DRILLING CEMENT TO TOP OF LANDING COLLAR, THE TDS IBOP WASHED OUT AND STARTED TO LEAK.
1845 | 03/27/2022 | SSA-5914 | WDYH-80 | RIG | 27 Mar 1145 - 1245 | 1 | 1 | 894265 |  | RR | FOT | CSYS | 14076 | TROUBLESHOOT & SERVICED MUD PUMPS WHILE CIRCULATING HOLE WITH ONE MUD PUMP.
1847 | 03/27/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 411 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1849 | 03/27/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 770.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1850 | 03/28/2022 | ADC-35 | MAQL-5 | RIG | 28 Mar 2100 - 0130 | 4.5 | 4.5 | 894351 |  | RR | FOT | MPMP | 8350 | RIG TEST PUMP NOT HOLDING PRESSURE.
1852 | 03/28/2022 | ADC-35 | MAQL-5 | SWL | 27 Mar 2230 - 1830 | 13.5 | 20 | 894345 |  | TF | FOT | WLT | 8350 | SLB W/L MINI FRAC 10K PKR NOT SEALING .
1853 | 03/28/2022 | ADC-35 | MAQL-5 | RIG | 28 Mar 2100 - 0130 | 4.5 | 4.5 | 894351 |  | RR | FOT | MPMP | 8350 | RIG TEST PUMP NOT HOLDING PRESSURE.
1855 | 03/28/2022 | ADC-43L | HWYH-1226 | TK3 | 27 Mar 2030 - 0500 | 23.5 | 32 | 894200 |  | DD | IDPR | HTMTR | 15269 | 5-7/8" DOWNHOLE DIRECTIONAL BHA (VORTEX) FAILURE
1857 | 03/28/2022 | ADC-50 | SFNY-1177 | ARM | 28 Mar 1230 - 0500 | 16.5 | 16.5 | 894353 |  | LCIR | UVLC | NA | 4190 | AFTER DISPLACING 72 PCF WBM WITH 88 PCF OBM, WE OBSERVED TOTAL MUD LOSSES OF 150 BPH
1859 | 03/28/2022 | ADC-57L | FDHL-158 | SWL | 27 Mar 1900 - 0215 | 21.25 | 31.25 | 894305 |  | TF | FOT | WLT | 10217 | WL DUAL PACKER NOT SEAL.
1861 | 03/28/2022 | ADC-68L | KRSN-706 | TK3 | 28 Mar 1130 - 2030 | 9 | 9 | 894357 |  | LROP | IBSL | BIT | 539 | UNABLE TO DRILL HAL. 13-3/8" DV W/ 12-1/4" PDC BIT.
1863 | 03/28/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0445 | 22.75 | 402.75 | 893229 |  | LCIR | UVLC | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1865 | 03/28/2022 | ADM-510 | ABSF-224 | RIG | 28 Mar 2030 - 0315 | 6.75 | 6.75 | 894355 |  | RR | FOT | FL | 3700 | OVERBOARD DITCH LINE AT SHAKERS PLUGGED WITH CUTTINGS
1867 | 03/28/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 24 | 109 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
1869 | 03/28/2022 | ARO-2003 | ZULF-299 | ARM | 25 Mar 1000 - 0500 | 24 | 91 | 894209 |  | WON | WTHR | NA | 0 | STRONG WINDS ROUGH SEAS UNABLE TO PERFORM RIG MOVE.
1871 | 03/28/2022 | ARO-3002 | MRJN-813 | HCO | 23 Mar 1100 - 0500 | 23.5 | 123.25 | 894086 |  | TF | FOT | PKR | 16264 | PRESSURE UP STRING AGAINST 9-5/8" HALLIBURTON VCH & SEAL ASSEMBLY WITH NO SUCCESS. HALL 9-5/8 VCH PKR PARTED AT THE MIDDLE OF THE ASSY, LEAVING SBE, CERAMIC DISC & TAIL PIPE IN HOLE.
1873 | 03/28/2022 | ARO-3003 | SFNY-1740 | RIG | 28 Mar 0830 - 0915 | .75 | .75 | 894356 |  | HSEI | UNKN | NA | 0 | HELD SAFETY STAND DOWN WITH ALL RIG CREWS, DISCUSSED BODY POSITION AND BEING AWARE OF YOUR SURROUNDINGS WHILE NIPPLE UP OPERATIONS.
1874 | 03/28/2022 | ARO-3004 | MRJN-2060 | RIG | 28 Mar 0230 - 0430 | 2 | 2 | 894354 |  | RR | FOT | SWVL | 5467 | TDS SWIVEL PACKING LEAKING
1876 | 03/28/2022 | ARO-3004 | MRJN-2060 | RIG | 27 Mar 2330 - 0700 | 2 | 7.5 | 894274 |  | RR | FOT | RWCS | 2030 | FOUND ONE OF THE ELECTRICAL MOTOR ON BOP KOOMEY UNIT NOT WORKING, REPLACED SAME WITH NEW ONE.
1877 | 03/28/2022 | ARO-3004 | MRJN-2060 | RIG | 28 Mar 0230 - 0430 | 2 | 2 | 894354 |  | RR | FOT | SWVL | 5467 | TDS SWIVEL PACKING LEAKING
1879 | 03/28/2022 | BCTD-3 | HRDH-1375 | ARM | 26 Mar 1300 - 0500 | 24 | 64 | 894236 |  | STUK | STBH | BHA | 13600 | BHA STUCK AT SIDETRACK POINT.
1881 | 03/28/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 270.5 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1883 | 03/28/2022 | DPS-44 | UTMN-3151 | ARM | 28 Mar 0500 - 0500 | 22.25 | 22.25 | 894325 |  | TH | NARW | NA | 3032 | OBSERVED TIGHT SPOT AND CASING DID NOT PASS THROUGH. TRIED SEVERAL TIMES NO SUCCESS.
1885 | 03/28/2022 | ENSCO-76 | MRJN-851 | RIG | 27 Mar 0400 - 0630 | 1.5 | 2.5 | 894275 |  | RR | FOT | CSYS | 2363 | HAD LEAKAGE IN WASHPIPE OF TDS
1887 | 03/28/2022 | NA-128S | ZMLH-5 | ITS | 27 Mar 0345 - 1700 | 12 | 13.25 | 894277 |  | TF | HERR | TTRQ | 16601 | WHILE DRIFTING 4 1/2'' COMPLETION, DRIFT COULD NOT PASS @ 2387 FT. JT# 84 OVER TORQUED
1889 | 03/28/2022 | NA-18S | SDGM-442 | SDM | 27 Mar 1530 - 0300 | 11.5 | 25 | 894241 |  | BHA | FOT | MWD | 11574 | LOST MWD SIGNAL FROM SLB TOOLS. SENT DOWNLINK & TROUBLESHOOTING TOOLS; NO SUCCESS.
1891 | 03/28/2022 | NBR-210S | HRDH-1491 | ARM | 28 Mar 0500 - 0500 | 24 | 24 | 894350 |  | STUK | PSSW | NA | 9087 | WHILE REAMING WFD 6.1/8" DIR BHA FROM 9171' TO 9087', STRING STALLED, UNABLE TO MOVE STRING. PIPE STUCK.
1893 | 03/28/2022 | NBR-591S | HRDH-1921 | RIG | 27 Mar 1830 - 0445 | 23.75 | 34.25 | 894269 |  | RR | FOT | TDS | 581 | LOST COMMUNICATION AND FUNCTION WITH TOP DIVE SYSTEM
1894 | 03/28/2022 | PA-604S | HRDH-1953 | RIG | 28 Mar 0230 - 0500 | 2.5 | 2.5 | 894359 |  | RR | FOT | TDS | 356 | TDS LINK TILT CYLINDER MALFUNCTION: CHANGE TILT LINK EYE.
1896 | 03/28/2022 | PA-604S | HRDH-1953 | RIG | 28 Mar 0000 - 0230 | 2.5 | 2.5 | 894326 |  | RR | FOT | TDS | 356 | REPAIR / REPLACE TDS WASHPIPE.
1897 | 03/28/2022 | PA-604S | HRDH-1953 | RIG | 28 Mar 0230 - 0500 | 2.5 | 2.5 | 894359 |  | RR | FOT | TDS | 356 | TDS LINK TILT CYLINDER MALFUNCTION: CHANGE TILT LINK EYE.
1899 | 03/28/2022 | PA-861S | HRDH-1060 | RIG | 28 Mar 0500 - 1030 | 5.5 | 5.5 | 894346 |  | RR | FOT | TDS | 2600 | TOP DRIVE LINK TILT HAS MULFUNCTION DUE TO NO PRESURE COMING FROM HPU. WORK & FIX SAME
1901 | 03/28/2022 | RM-74A | KARN-60 | ARM | 26 Mar 0700 - 0500 | 24 | 70 | 894245 |  | WON | WTHR | NA | 0 | UNABLE TO FINAL RIG POSITIONING DUE TO ADVERSE WEATHER CONDITON.WOW.
1903 | 03/28/2022 | SDA | MRJN-735 | BHI | 28 Mar 1015 - 1045 | .5 | .5 | 894347 |  | TF | FOT | COMP | 10415 | BAD SIGNAL DECODING FOR MWD/LWD/PWD. INSPECT MUD PUMP STROKE COUNTER AND TIGHTEN UP THE SAME, CONTINUE OPERATION.
1905 | 03/28/2022 | SND-2001 | UTMN-2329 | RIG | 25 Mar 1530 - 2100 | 16 | 76.5 | 894229 |  | FISH | FWTS | BHA | 6086 | 1032 FT OF FISH LEFT IN HOLE.
1907 | 03/28/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 24 | 199.5 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
1909 | 03/28/2022 | SND-3003 | HRDH-2311 | SJC | 28 Mar 2300 - 0500 | 6 | 6 | 894352 |  | CMT | IFCS | NA | 12345 | LEAD CEMENT GOT GELLED UP INSIDE THE BATCH MIXER DURING WEIGHTING UP TO TARGET WEIGHT AT 127 PCF.
1911 | 03/28/2022 | SP-103 | KRSN-70 | BHI | 28 Mar 0500 - 2300 | 18 | 18 | 894349 |  | BHA | FOT | PWD | 8454 | BHI TESTTRACK TOOL NOT SEAL
1913 | 03/28/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0500 | 24 | 397.25 | 891286 |  | STUK | SCSG | LINR | 22213 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
1915 | 03/28/2022 | SP-122 | ANDR-602 | BTT | 27 Mar 1730 - 0230 | 20.5 | 32 | 894270 |  | TF | FOT | PCPD | 11876 | BAKER THRU-TUBING 2-7/8" MOTOR PLUGGED & MALFUNCTIONED. UNABLE TO CUT 4-1/2" FISH TUBING WITH SAME.
1917 | 03/28/2022 | SSA-51 | MNIF-259 | SWL | 28 Mar 2130 - 0030 | 3 | 3 | 894348 |  | TF | FOT | WLT | 9087 | W/L CABLE SLIPPING FROM ITS CLAMP WHILE PERFORMING PULL TEST.
1919 | 03/28/2022 | SSA-5914 | WDYH-80 | RIG | 27 Mar 1145 - 1845 | 1.5 | 2.5 | 894265 |  | RR | FOT | CSYS | 14076 | TROUBLESHOOT & SERVICED MUD PUMPS WHILE CIRCULATING HOLE.
1921 | 03/28/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 22 | 433 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1922 | 03/28/2022 | T217 | UTMN-488 | RIG | 28 Mar 0330 - 0430 | 1 | 1 | 894358 |  | RR | FPMP | MPMP | 7318 | FAILURE ON RIG PUMP & REPAIR SAME.
1924 | 03/28/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 23 | 793.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1925 | 03/28/2022 | T217 | UTMN-488 | RIG | 28 Mar 0330 - 0430 | 1 | 1 | 894358 |  | RR | FPMP | MPMP | 7318 | FAILURE ON RIG PUMP & REPAIR SAME.
1927 | 03/29/2022 | ADC-43L | HWYH-1226 | TK3 | 27 Mar 2030 - 0630 | 1.5 | 33.5 | 894200 |  | DD | IDPR | HTMTR | 15269 | 5-7/8" DOWNHOLE DIRECTIONAL BHA (VORTEX) FAILURE
1929 | 03/29/2022 | ADC-50 | SFNY-1177 | ARM | 28 Mar 1230 - 0500 | 24 | 40.5 | 894353 |  | LCIR | UVLC | NA | 4190 | AFTER DISPLACING 72 PCF WBM WITH 88 PCF OBM, WE OBSERVED TOTAL MUD LOSSES.
1931 | 03/29/2022 | ADC-55L | UTMN-3199 | TK3 | 29 Mar 1000 - 1200 | 2 | 2 | 894431 |  | WO | ORDS | NA | 6330 | NO CERTIFIED SLINGER ONBOARD TO SAFELY PEFORM LIFTING OPERATIONS
1933 | 03/29/2022 | ADC-57L | FDHL-158 | SWL | 27 Mar 1900 - 0500 | .5 | 31.75 | 894305 |  | TF | FOT | WLT | 10217 | WL DUAL PACKER NOT SEAL.
1935 | 03/29/2022 | ADC-59L | HRDH-2232 | TSC | 29 Mar 1315 - 0500 | 15.75 | 15.75 | 894367 |  | TF | FOT | CTRQ | 13061 | PERFORM TCA TEST TO 6000 PSI, OK. ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS
1937 | 03/29/2022 | ADES-173 | HRDH-2256 | SEC | 25 Mar 0330 - 1630 | 10 | 28.5 | 894162 |  | TF | XBTR | BIT | 11670 | LOW PERFORMANCE
1939 | 03/29/2022 | ADM-337 | MRJN-900 | ARM | 08 Mar 2015 - 0815 | 3.25 | 406 | 893229 |  | LCIR | UVLC | NA | 9900 | LOST CIRCULATION @ 9769, UNABLE TO CURE, SET EZSV, SQUEEZE CMT, CURE LOSSES.
1941 | 03/29/2022 | ADM-655 | BRRI-218 | EX1 | 18 Mar 2000 - 0500 | 5 | 25 | 893576 |  | TF | FOT | SLICK | 0 | SLICKLINE WIRE PARTED AFTER RELEASING INTERWELL 4-1/2" HEX PLUG WITH NORMAL RELEASING OVERPULL.
1943 | 03/29/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 24 | 113.5 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
1945 | 03/29/2022 | ARO-2003 | ZULF-299 | ARM | 25 Mar 1000 - 0500 | 24 | 115 | 894209 |  | WON | WTHR | NA | 0 | STRONG WINDS ROUGH SEAS UNABLE TO PERFORM RIG MOVE.
1947 | 03/29/2022 | ARO-3002 | MRJN-813 | HCO | 23 Mar 1100 - 0815 | 3.25 | 126.5 | 894086 |  | TF | FOT | PKR | 16264 | PRESSURE UP STRING AGAINST 9-5/8" HALLIBURTON VCH & SEAL ASSEMBLY WITH NO SUCCESS. HALL 9-5/8 VCH PKR PARTED AT THE MIDDLE OF THE ASSY, LEAVING SBE, CERAMIC DISC & TAIL PIPE IN HOLE.
1949 | 03/29/2022 | ARO-3003 | SFNY-1740 | SPS | 29 Mar 1530 - 1600 | .5 | .5 | 894428 |  | WO | SRVC | NA | 282 | EXCESSIVE TIME FOR HALLIBURTON TO INSTALL ROP SENSOR ON DRAWWORK & PRESSURE SENSOR ON STD PIPE.
1950 | 03/29/2022 | ARO-4001 | MRJN-539 | RIG | 29 Mar 1500 - 1600 | 1 | 1 | 894446 |  | RR | FOT | DWKS | 9635 | DRAWWORKS LOST COMMUNICATION, ET RESET JAVA SCRIPT AND PERFORM BLOCK CALIBRATION AND RESET HOOKLOAD TARE.
1952 | 03/29/2022 | ARO-4001 | MRJN-539 | RIG | 29 Mar 1800 - 0500 | 11 | 11 | 894366 |  | RR | FPMP | MPMP | 9733 | WHILE DRILLING MUD PUMP #1 & #2 POP OFF VALVES OPENED DUE TO LOW AIR PRESSURE ALARM, TROUBLESHOOTING SAME TO RE-SET.
1953 | 03/29/2022 | ARO-4001 | MRJN-539 | RIG | 29 Mar 1500 - 1600 | 1 | 1 | 894446 |  | RR | FOT | DWKS | 9635 | DRAWWORKS LOST COMMUNICATION, ET RESET JAVA SCRIPT AND PERFORM BLOCK CALIBRATION AND RESET HOOKLOAD TARE.
1955 | 03/29/2022 | BCTD-3 | HRDH-1375 | ARM | 26 Mar 1300 - 1000 | 5 | 69 | 894236 |  | STUK | STBH | BHA | 13600 | BHA STUCK AT SIDETRACK POINT.
1957 | 03/29/2022 | CR-36A | ZULF-2038 | WLH | 14 Mar 0900 - 0500 | 24 | 294.5 | 893406 |  | JF | DSFT | LLAP | 7784 | PAKER SET AND COULDN'T PERFORM PRIMARY CMT JOB.
1958 | 03/29/2022 | DPS-44 | UTMN-3151 | SJS | 29 Mar 1600 - 0500 | 12.5 | 12.5 | 894429 |  | TF | TOWC | JARS | 4460 | SUDDEN DROP IN SPP, P/U AND FOUND 69 KLBS LOST IN HOOK LOAD, POOH AND FOUND OUT JAR HAD PARTED.
1960 | 03/29/2022 | DPS-44 | UTMN-3151 | ARM | 28 Mar 0500 - 1600 | 11 | 33.25 | 894325 |  | TH | NARW | NA | 3032 | OBSERVED TIGHT SPOT AND CASING DID NOT PASS THROUGH. TRIED SEVERAL TIMES NO SUCCESS.
1961 | 03/29/2022 | DPS-44 | UTMN-3151 | SJS | 29 Mar 1600 - 0500 | 12.5 | 12.5 | 894429 |  | TF | TOWC | JARS | 4460 | SUDDEN DROP IN SPP, P/U AND FOUND 69 KLBS LOST IN HOOK LOAD, POOH AND FOUND OUT JAR HAD PARTED.
1963 | 03/29/2022 | DQ-47 | KHRS-1707 | TK2 | 29 Mar 0815 - 0345 | 19.5 | 19.5 | 894426 |  | DD | ACDI | BHA | 9620 | DUE TO UNAVAILABLE MODULAR MOTOR, BAKER LSTK RUN 6 1/8" RSS/MWD STAND ALONE BHA WITHOUT SDN & R/A SOURCE AS A SEPARATION RUN.
1965 | 03/29/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 0500 | 24 | 70.5 | 894425 |  | LCIR | UVLC | NA | 8416 | ENCOUNTERED TOTAL LOSSES AT 8,416' WHILE ROTARY DRILLING 12" HOLE SECTION (BASE LOWER FADHILI RESERVOIR) FRACTURE /28' FORMATION CAVERN/VOID.
1967 | 03/29/2022 | NBR-210S | HRDH-1491 | ARM | 28 Mar 0500 - 1500 | 10 | 34 | 894350 |  | STUK | PSSW | NA | 9087 | WHILE REAMING WFD 6.1/8" DIR BHA FROM 9171' TO 9087', STRING STALLED, UNABLE TO MOVE STRING. PIPE STUCK.
1969 | 03/29/2022 | RM-74A | KARN-60 | ARM | 26 Mar 0700 - 0500 | 24 | 94 | 894245 |  | WON | WTHR | NA | 0 | UNABLE TO FINAL RIG POSITIONING DUE TO ADVERSE WEATHER CONDITON.WOW.
1971 | 03/29/2022 | RPKU-2 | HWYH-58 | OCT | 29 Mar 2100 - 0500 | 8 | 8 | 894445 |  | CMT | CFST | NA | 0 | OILSERVE CTU CMT JOB FAILURE
1973 | 03/29/2022 | SINO-42L | HWYH-286 | ITS | 29 Mar 0400 - 0500 | 1 | 1 | 894447 |  | TF | FOT | TTRQ | 0 | MALFUNCTION OF ITS POWER TONG .
1975 | 03/29/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 24 | 223.5 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
1977 | 03/29/2022 | SND-2009 | NJYN-81 | RIG | 29 Mar 1830 - 2000 | 1.5 | 1.5 | 894427 |  | RR | FOT | TDS | 15360 | TDS MALFUNCTIONING, STOP RESPONDING AFTER CONNECTION.
1979 | 03/29/2022 | SND-3001 | MHWZ-167102 | BHI | 29 Mar 0800 - 0500 | 20.75 | 20.75 | 894385 |  | BHA | FOT | MWD | 18309 | BAKER MWD TOOL LOST SIGNAL
1981 | 03/29/2022 | SND-3002 | DMMM-602 | BLH | 29 Mar 2200 - 0500 | 7 | 7 | 894430 |  | TF | FOT | HGRL | 12000 | P/UP LINER & ATTEMPT TO RUN HAD SLACK OFF, L/D BAKER LINER FOUND HANGER SLIPS SET.
1983 | 03/29/2022 | SND-3003 | HRDH-2311 | SJC | 28 Mar 2300 - 2300 | 18 | 24 | 894352 |  | CMT | IFCS | NA | 12345 | LEAD CEMENT GOT GELLED UP INSIDE THE BATCH MIXER DURING WEIGHTING UP TO TARGET WEIGHT AT 127 PCF.
1985 | 03/29/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0800 | 3 | 400.25 | 891286 |  | STUK | SCSG | LINR | 22213 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
1987 | 03/29/2022 | SSA-5859 | HRDH-1967 | OES | 29 Mar 0300 - 0400 | 1 | 1 | 894368 |  | MUD | IPDF | NA | 9510 | EXCESS TIME TO MAINTAIN CSG-GO PILL REHOLOGY
1989 | 03/29/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 457 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
1991 | 03/29/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 817.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
1993 | 03/30/2022 | ADC-32 | SDGM-1139 | RIG | 30 Mar 0300 - 0500 | 2 | 2 | 894394 |  | RR | FPMP | MPMP | 12040 | LEAK IN SURFACE LINES
1995 | 03/30/2022 | ADC-55L | UTMN-3199 | SCM | 30 Mar 1300 - 1600 | 3 | 3 | 894493 |  | TF | FOT | PUMP | 6330 | HOOK UP LINES TO CEMENT HEAD AND P/T. - OBSERVED LEAK AT LO - TORQ VALVE.
1997 | 03/30/2022 | ADC-57L | FDHL-158 | SWL | 27 Mar 1900 - 0330 | 22.5 | 54.25 | 894305 |  | TF | FOT | WLT | 10217 | WL DUAL PACKER NOT SEAL.
1999 | 03/30/2022 | ADC-59L | HRDH-2232 | TK3 | 29 Mar 1315 - 0445 | 23.75 | 39.5 | 894371 |  | TF | FCLK | CSG | 13061 | PERFORM TCA TEST TO 6000 PSI (OK), ATTEMPT TO TEST TBG TO 5000 PSI WITHOUT SUCCESS.
2001 | 03/30/2022 | ADC-67L | UTMN-3156 | TK3 | 29 Mar 1315 - 0500 | 24 | 39.75 | 894387 |  | LCIR | CFFM | MDCAP | 6652 | WHILE DRILLING 12" HOLE ENCOUNTERED LOSSES
2003 | 03/30/2022 | ADM-339 | RBYN-55 | RIG | 30 Mar 2045 - 2130 | .75 | .75 | 894495 |  | RR | FOT | CSYS | 6795 | DURING REVERSE CIRCULATION AFTER 7" LINER CEMENT JOB OBSERVED LEAK FROM CEMENT HOSE.
2005 | 03/30/2022 | ADM-655 | BRRI-218 | EX1 | 18 Mar 2000 - 1830 | 13.5 | 38.5 | 893576 |  | TF | FOT | SLICK | 0 | SLICKLINE WIRE PARTED AFTER RELEASING INTERWELL 4-1/2" HEX PLUG WITH NORMAL RELEASING OVERPULL.
2007 | 03/30/2022 | ARO-2001 | BRRI-184 | ARM | 24 Mar 1600 - 0500 | 24 | 137 | 894185 |  | TF | HERR | TBG | 6430 | AFTER LANDING THE TUBING HANGER TO THE PRE DETERMINED MARKED POSITION MADE ON THE DUMMY LANDING, IT WAS FOUND THAT THE MARK WAS WRONG AND THE HANGER WAS NOT FULLY LANDED. DURING DISPLACEMENT HANGER LOST SEAL INTEGRITY. WHEN PULLED THE SHOULDER OD WAS ALSO SHOWING SCRAPE MARKS FROM LOCKDOWN PINS.
2009 | 03/30/2022 | ARO-2003 | ZULF-299 | ARM | 25 Mar 1000 - 0500 | 24 | 139 | 894209 |  | WON | WTHR | NA | 0 | STRONG WINDS ROUGH SEAS UNABLE TO PERFORM RIG MOVE.
2011 | 03/30/2022 | ARO-4001 | MRJN-539 | RIG | 29 Mar 1800 - 0500 | 24 | 35 | 894366 |  | UPRA | GRF | MPMP | 9733 | WHILE DRILLING MUD PUMP #1 & #2 POP OFF VALVES OPENED DUE TO LOW AIR PRESSURE ALARM, TROUBLESHOOTING SAME TO RE-SET.
2013 | 03/30/2022 | CR-36A | ZULF-2038 | HCA | 17 Mar 2030 - 0500 | 17.75 | 31.5 | 893685 |  | TF | FOT | ACP | 7517 | UNABLE TO STING BACK INTO EZSV TO PERFORM CEMENT SQUEEZE.
2014 | 03/30/2022 | DPS-4 | MDRK-54 | RIG | 30 Mar 2030 - 2300 | 2.5 | 2.5 | 894392 |  | RR | FOT | DWKS | 12190 | REPAIR ON DRAWWORKS AUXILIARY BRAKE, CHANGED PCB (PRINTED CIRCUIT BOARD) IN SCR ROOM.
2016 | 03/30/2022 | DPS-4 | MDRK-54 | ARM | 30 Mar 1345 - 0500 | 12.75 | 12.75 | 894391 |  | FISH | FWTS | STRG | 12190 | OBSERVED JUNK TRACES ON THE BIT & BROKEN BLADE. DECISION MADE TO RIH W/MILL ASSY
2017 | 03/30/2022 | DPS-4 | MDRK-54 | RIG | 30 Mar 2030 - 2300 | 2.5 | 2.5 | 894392 |  | RR | FOT | DWKS | 12190 | REPAIR ON DRAWWORKS AUXILIARY BRAKE, CHANGED PCB (PRINTED CIRCUIT BOARD) IN SCR ROOM.
2018 | 03/30/2022 | DPS-44 | UTMN-3151 | SJS | 29 Mar 1600 - 2145 | 16.25 | 28.75 | 894429 |  | TF | TOWC | JARS | 4460 | SUDDEN DROP IN SPP, P/U AND FOUND 69 KLBS LOST IN HOOK LOAD, POOH AND FOUND OUT JAR HAD PARTED.
2020 | 03/30/2022 | DPS-44 | UTMN-3151 | ARM | 28 Mar 0500 - 0500 | 7.25 | 40.5 | 894325 |  | TH | NARW | NA | 3032 | OBSERVED TIGHT SPOT AND CASING DID NOT PASS THROUGH. TRIED SEVERAL TIMES NO SUCCESS.
2021 | 03/30/2022 | DPS-44 | UTMN-3151 | SJS | 29 Mar 1600 - 2145 | 16.25 | 28.75 | 894429 |  | TF | TOWC | JARS | 4460 | SUDDEN DROP IN SPP, P/U AND FOUND 69 KLBS LOST IN HOOK LOAD, POOH AND FOUND OUT JAR HAD PARTED.
2023 | 03/30/2022 | ENSCO-54 | ABSF-179 | ARM | 30 Mar 1300 - 0000 | 11 | 11 | 894510 |  | WON | WTHR | NA | 0 | WAIT ON WEATHER TO OFFLOAD MBP ZERO FLARING EQUIPMENT.
2025 | 03/30/2022 | NBR-115S | HRDH-2140 | FMC | 30 Mar 2145 - 2245 | 1 | 1 | 894393 |  | TF | FOT | CRT | 2100 | FRANKS PU/LD MACHINE ENGINE FAILURE.
2027 | 03/30/2022 | NBR-196S | SDGM-1226 | ARM | 27 Mar 0630 - 0500 | 24 | 94.5 | 894425 |  | LCIR | UVLC | NA | 8416 | ENCOUNTERED TOTAL LOSSES AT 8,416' WHILE ROTARY DRILLING 12" HOLE SECTION (BASE LOWER FADHILI RESERVOIR) FRACTURE /28' FORMATION CAVERN/VOID.
2029 | 03/30/2022 | PA-785S | QTIF-641 | WWD | 30 Mar 2200 - 0500 | 7 | 7 | 894494 |  | TF | FOT | WPSTK | 5643 | ENABLE TO GET RETURN WHILE CIRCULATION PRIOR TO SET WHIPSTOCK
2031 | 03/30/2022 | RM-74A | KARN-60 | ARM | 26 Mar 0700 - 0500 | 24 | 118 | 894245 |  | WON | WTHR | NA | 0 | UNABLE TO FINAL RIG POSITIONING DUE TO ADVERSE WEATHER CONDITON.WOW.
2033 | 03/30/2022 | RPKU-2 | HWYH-58 | OCT | 29 Mar 2100 - 2000 | 15 | 23 | 894445 |  | CMT | CFST | NA | 0 | OILSERVE CEMENTING JOB FAILURE.
2035 | 03/30/2022 | SINO-22 | BRRI-381 | ARM | 30 Mar 1200 - 1500 | 3 | 3 | 894525 |  | WON | WTHR | NA | 12920 | WAIT ON WEATHER & SUSPEND CRANE OPERATION TO LD MWD & TRI-MILL ASSY DUE TO HIGH WIND SPEED.
2037 | 03/30/2022 | SINO-42L | HWYH-286 | ITS | 29 Mar 0400 - 0900 | 4 | 5 | 894447 |  | TF | FOT | TTRQ | 0 | MALFUNCTION OF ITS POWER TONG .
2039 | 03/30/2022 | SINO-45L | UTMN-243 | BC | 30 Mar 1530 - 2030 | 5 | 5 | 894527 |  | TF | FOT | EQLZR | 1000 | BAKER MTV SCREEN FAILURE
2041 | 03/30/2022 | SND-2005 | MHKK-2 | ARM | 09 Mar 1230 - 0500 | 23.25 | 246.75 | 893212 |  | LCIR | UVLC | NA | 4435 | OBSERVED 80 BPH LOSSES, PUMPED LCM PILLS TO CURE SAME PARTIALLY.
2043 | 03/30/2022 | SND-3001 | MHWZ-167102 | BHI | 29 Mar 0800 - 0500 | 13 | 33.75 | 894385 |  | BHA | FOT | MWD | 18309 | BAKER MWD TOOL LOST SIGNAL
2045 | 03/30/2022 | SND-3002 | DMMM-602 | BLH | 29 Mar 2200 - 1630 | 11 | 18 | 894430 |  | TF | FOT | HGRL | 12000 | P/UP LINER & ATTEMPT TO RUN HAD SLACK OFF, L/D BAKER LINER FOUND HANGER SLIPS SET.
2047 | 03/30/2022 | SP-120 | MNIF-189 | ARM | 08 Feb 0115 - 0430 | 23.5 | 444.75 | 891286 |  | STUK | SCSG | LINR | 22213 | DIFFERENTIAL STUCK OF 7" LINER WHILE RIH ON 5" DP STANDS AFTER CONNECTION.
2049 | 03/30/2022 | SP-124 | ABHD-111 | WCR | 30 Mar 1830 - 2230 | 4 | 4 | 894526 |  | TF | FOT | PEL | 9000 | UNPROPER GRIPPJNG OF TUBING SLIPS
2051 | 03/30/2022 | SSA-29 | QTIF-348 | HWP | 30 Mar 0845 - 1030 | 1.75 | 1.75 | 894389 |  | TF | FOT | WLTT | 1700 | HALL E-LINE TOOLS WITH MISS-COMMUNICATION DUE TO PROBLEM IN TOOL FLEX JOINT, POOH.
2053 | 03/30/2022 | SSA-5970 | HWYH-1257 | ARM | 08 Mar 0500 - 0500 | 24 | 481 | 893136 |  | STUK | SDIR | RSS | 18680 | STRING GOT STUCK WHILE BACK REAMING TIGHT SPOT @ 18,680 FT.
2055 | 03/30/2022 | SSA-5972 | JFYN-10 | RIG | 30 Mar 1430 - 1500 | .5 | .5 | 894486 |  | RR | FOT | DWKS | 6655 | DRAWWORKS COOLING FAN TRIPPING OFF CAUSING DRAWWORKS TO SHUT DOWN
2057 | 03/30/2022 | T217 | UTMN-488 | ARM | 22 Feb 0300 - 0500 | 24 | 841.5 | 892373 |  | STUK | SCSG | LINR | 6865 | 4-1/2" OBL GOT STUCK
2059 | 03/30/2022 | ZPEC-1 | HMYM-846 | ARM | 30 Mar 1000 - 1300 | 3 | 3 | 894508 |  | WON | WTHR | NA | 2450 | FOR SAFETY SUSPENDED OPERATIONAL DOU TO SANDSTORM,WIND SPEED:44 KM.