## Sheet1
seq | Report Date | Rig Name | Well No | Date and Time | Time in Hrs | Cummulative Hrs | LT ID | Parent LT ID | LT Type | Cause | Object | Company Name | Depth | LT Summary
118 | 01/01/2022 | ADC-16 | JAHM-6 | 01 Jan 1900 - 0500 | 10 | 10 | 886676 |  | RR | FOT | TDS | RIG | 0 | TDS TRIPPED DUE TO GROUND FAULT. TROUBLESHOOT & FOUND TDS STATOR MOTOR INSULATION GROUNDED.
120 | 01/01/2022 | ADC-32 | SDGM-1139 | 01 Jan 2100 - 0000 | 3 | 3 | 886710 |  | RR | FOT | EDR | RIG | 5530 | WATER OF THE RAINS LEAKED THROUGH THE ROOF OF DRILLER'S CABIN INTO THE MAIN ELECTRIC BOX CAUSING ALL MONITORING SCREENS TO SHUT-DOWN.
122 | 01/01/2022 | ADC-34 | UTMN-2317 | 27 Dec 1930 - 0500 | 4.5 | 12 | 886267 |  | TF | FOT | CTRQ | FMC | 320 | JAM UNITS (MAIN & BACK UP ) FAILED
124 | 01/01/2022 | ADC-60 | ABSF-215 | 01 Jan 0800 - 0330 | 18 | 18 | 886686 |  | BHA | FOT | MWD | SDM | 6365 | FAILED TO COMMUNICATE WITH SLB MWD TOOLS.
125 | 01/01/2022 | ADC-65L | HRDH-1980 | 01 Jan 1930 - 0500 | 9.5 | 9.5 | 886706 |  | STUK | STBH | BHA | TK3 | 6395 | STRING GET STUCK IN OPEN HOLE AFTER MAKING THE PUMP IN SUB ASSEMBLY WHILE PREPAREATION FOR PUMP CEMENT PLUG. ATTEMPT TO WORK STRING UP & DOWN AT MAX LOADS - NO SUCCESS
127 | 01/01/2022 | ADC-65L | HRDH-1980 | 26 Dec 1800 - 1930 | 3.5 | 127.5 | 886385 |  | LCIR | UVLC | NA | TK3 | 6230 | DURING DRILLING THROUGH ARAB D BASE RESORVAR WITH 72 PCF KCL POLIMER MUD TOTAL LOSSES WERE ENCOUNTERED AT 6,230' TVD 6,231' MD. 50' MORE WERE DRILLED TO 6,280' PRIOR CURE LOSS PROCEDURES ACCORDING ARAMCO MANUAL WERE FOLLOWED UP.
128 | 01/01/2022 | ADC-65L | HRDH-1980 | 01 Jan 1930 - 0500 | 9.5 | 9.5 | 886706 |  | STUK | STBH | BHA | TK3 | 6395 | STRING GET STUCK IN OPEN HOLE AFTER MAKING THE PUMP IN SUB ASSEMBLY WHILE PREPAREATION FOR PUMP CEMENT PLUG. ATTEMPT TO WORK STRING UP & DOWN AT MAX LOADS - NO SUCCESS
130 | 01/01/2022 | ADES-173 | NJYN-90 | 31 Dec 1200 - 0500 | 24 | 41 | 886561 |  | UPRA | GRF | MPMP | RIG | 12978 | NOTICED UNUSUAL NOISE AT MP AND MUD PUMPS OVERHEATING. TROUBLE-SHOOT MUD PUMP #2, FOUND BAD PINION BEARING. MP #3 FOUND DAMAGED CROSS-HEAD BEARING AND SLIDES.
132 | 01/01/2022 | ADES-174 | HRDH-2184 | 31 Dec 2230 - 0500 | 24 | 30.5 | 886670 | 886167 | LROP | XBTR | BIT | ARM | 5619 | ATTEMPTED TO DRILL 12" HOLE IN NEW FORMATION, OBSERVED ERRATIC TQ ONCE TOUCH BTM, SUSPECT JUNK ON BTM REMAINING FROM 16" BIT.
134 | 01/01/2022 | ARO-3001 | ZULF-2054 | 01 Jan 0030 - 0315 | 2.75 | 2.75 | 886678 |  | BHA | FOT | MWD | SPS | 4417 | MWD TOOL FAILURE TO SEND PULSE.
136 | 01/01/2022 | DPS-4 | SAHB-34 | 01 Jan 1630 - 0500 | 12.5 | 12.5 | 886685 |  | TH | NARW | NA | ARM | 4983 | TAKE SLACK OFF WEIGHT AT 4190' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS.
137 | 01/01/2022 | DPS-45 | UTMN-3015 | 01 Jan 1115 - 1630 | 5.25 | 5.25 | 886709 |  | TF | FOT | CORRL | SWL | 13228 | SLB E-LINE LOST COMMUNICATION WITH CCL, TROUBLESHOOT WITHOUT SUCCESS.
139 | 01/01/2022 | DPS-45 | UTMN-3015 | 30 Dec 1500 - 0500 | 18.75 | 21.75 | 886683 |  | WCNT | WC20 | NA | ARM | 13228 | OBSERVED 80 PSI DROPPED IN SPP, FLOW CHECK AND NOTICED WELL IS FLOWING. SHUT IN WELL
140 | 01/01/2022 | DPS-45 | UTMN-3015 | 01 Jan 1115 - 1630 | 5.25 | 5.25 | 886709 |  | TF | FOT | CORRL | SWL | 13228 | SLB E-LINE LOST COMMUNICATION WITH CCL, TROUBLESHOOT WITHOUT SUCCESS.
142 | 01/01/2022 | DQ-50L | HRDH-1497 | 30 Dec 0230 - 1300 | 8 | 34.5 | 886632 |  | UPRA | IRES | RSSS | RIG | 4150 | WHILE DISCUSSING WITH DQ & BAKER WHY THEY WANT TO REPLACE SUPER SACK HOIST, FOUND OUT THAT THERE WAS A HIDDEN INCIDENT (EQUIPMENT DAMAGE) 9 MONTHS AGO. SHUT DOWN RIG FOR INVESTIGATION.
144 | 01/01/2022 | ENSCO-54 | ABSF-168 | 30 Dec 0700 - 0800 | 3 | 28 | 886585 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER
146 | 01/01/2022 | HI-2 | BRRI-462 | 13 Dec 1000 - 0500 | 24 | 426.5 | 884683 |  | TF | FOT | HVLV | BC | 5239 | BAKER UPPER SMART COMPLETION STINGER UNABLE TO ESTABLISH COMMUNICATION WITH LOWER SMART COMPLETION RESULT IN WELL DE-COMPLETION.
148 | 01/01/2022 | HI-4 | BRRI-780 | 01 Jan 2000 - 0100 | 5 | 5 | 886677 |  | RR | FOT | RWCS | RIG | 5543 | DURING BOP TESTING, OBSERVE TEST LEAKING, INVESTIGATE FOUND TAGET BLOCK ON EMRGENCY KILL LEAKING, BLEED OFF PRESSURE.
150 | 01/01/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0500 | 24 | 62.5 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
152 | 01/01/2022 | NBR-304S | HRDH-2260 | 25 Dec 1045 - 2200 | 15 | 174.75 | 886085 |  | BHA | FOT | SKSUB | OJR | 5503 | WHILE DRILLING 16" HOLE SECTION. 12" SHOCK SUB WASHED AND PARTED 2.81" ABOVE CONNECTION. LEAVING 13.81 FEET OF BHA IN HOLE.
153 | 01/01/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 740.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
155 | 01/01/2022 | NBR-783S | MDRK-55 | 07 Nov 0500 - 0500 | 12 | 519 | 881591 |  | STUK | IPDF | BHA | BAR | 16256 | PIPE STUCK WHILE POOH DUE TO SUSPECTED MUD CONDITION.
156 | 01/01/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 740.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
157 | 01/01/2022 | PN-9 | MRJN-91 | 01 Jan 1130 - 0500 | 17.5 | 17.5 | 886674 |  | WO | SRVC | NA | ARN | 0 | WAIT ON HSU TO PERFORM SEA BED SURVEY AT MRJN-89/94 PF FOR SAFE RIG APPROACH.
159 | 01/01/2022 | PN-9 | MRJN-91 | 25 Dec 0500 - 1130 | 6.5 | 102.5 | 886105 |  | WO | WPD3 | NA | AP2 | 0 | WAIT ON MRJN FIELD SERVICE TO DEPRESSURIZE MRJN-89/94, 307 PF.
160 | 01/01/2022 | PN-9 | MRJN-91 | 01 Jan 1130 - 0500 | 17.5 | 17.5 | 886674 |  | WO | SRVC | NA | ARN | 0 | WAIT ON HSU TO PERFORM SEA BED SURVEY AT MRJN-89/94 PF FOR SAFE RIG APPROACH.
162 | 01/01/2022 | RM-74A | HSBH-23 | 03 Dec 2045 - 0500 | 24 | 622.5 | 883682 |  | WH | FOT | WH | FME | 11296 | FMC 14" PACK OFF LOCKING MANDREL OUT OF POSITION
164 | 01/01/2022 | SCTD-1 | SDGM-1188 | 01 Jan 2300 - 0230 | 3.5 | 3.5 | 886679 |  | RR | FOT | EDR | RIG | 13572 | LOAD CELL READING ABNORMAL STRING WEIGHTS.
166 | 01/01/2022 | SDA | MRJN-737 | 01 Jan 1100 - 0500 | 18 | 18 | 886675 |  | UPRA | OTH | NA | RIG | 9280 | RIG SHUT DOWN WAITING FOR INVESTIGATION FOR THE HAND INJURY OF THE BARGE CAPTAIN.
168 | 01/01/2022 | SINO-12L | HRDH-447 | 13 Dec 0500 - 0500 | 24 | 477.75 | 884690 |  | STUK | HINW | WLT | TK1 | 7110 | WL TRIPLE COMBO WITH DIELECTRIC LOGGING TOOL STRING GOT STUCK.
170 | 01/01/2022 | SINO-32L | SHYB-535 | 29 Dec 0245 - 0500 | 24 | 74.25 | 886665 |  | CMT | CPNF | NA | BCM | 5950 | SOFT CMT WHILE DRILLING KICK OFF CMT PLUG.
172 | 01/01/2022 | SND-2006 | UTMN-3135 | 31 Dec 0000 - 0730 | 2.5 | 7.5 | 886668 |  | BB | VPFM | BIT | ARM | 2304 | TRIP OUT OF HOLE DUE TO LOW ROP AND BIT BALLING REASONS.
174 | 01/01/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 93.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
176 | 01/01/2022 | SNT-025 | SFNY-1007 | 30 Dec 1130 - 0500 | 24 | 65.5 | 886625 |  | WO | WOPF | NA | AP2 | 0 | RIG WAITING ON APPROVAL FROM SFNY ONSHORE PRODUCTION ENGINEERING TO COMMENCE FLOW BACK OPERATIONS.
178 | 01/01/2022 | SP-120 | MNIF-189 | 25 Dec 0500 - 0500 | 24 | 175.5 | 886030 |  | STUK | STBH | BHA | ARM | 6040 | STUCK PIPE DUE TO HOLE PACK-OFF AT SHALE FORMATION.
180 | 01/01/2022 | SP-229 | ABHD-873 | 01 Jan 0400 - 0500 | 1 | 1 | 886725 |  | JF | HERR | ESPL | KSC | 6819 | CANNOT GET READINGS FROM ZEINETH SENSOR
182 | 01/01/2022 | SP-306 | ABHD-843 | 27 Dec 1515 - 0500 | 24 | 133.75 | 886286 |  | TF | FOT | ESP | SBA | 6430 | SAWAFI-BORETS ESP FAILED TO WORK DURING ESP FUNCTION TEST.
184 | 01/01/2022 | SSA-51 | MNIF-254 | 01 Jan 1445 - 1545 | 1 | 1 | 886672 |  | RR | FPMP | MPMP | RIG | 1575 | CIRE WHILE CHANGE OUT VALVE SEAT ON MP#3 AND WEAR PLATE ON MP#1
186 | 01/01/2022 | SSA-5891 | HRDH-695 | 01 Jan 1245 - 1700 | 4.25 | 4.25 | 886673 |  | RR | FOT | TDS | RIG | 11697 | FAULTY AIR PRESSURE SWITCH IN TDS.
188 | 01/01/2022 | SSA-5917 | HRDH-2304 | 01 Jan 0500 - 0700 | 2 | 2 | 886708 |  | RR | FOT | TDS | RIG | 4811 | TDS LOST POWER, TROUBLESHOOTING, CHANGE POWER AUXILIARY PLUG FOR TDS SERVICE LOOP.
190 | 01/01/2022 | SSA-5969 | UTMN-3195 | 26 Dec 0930 - 0500 | 21.5 | 159 | 886037 |  | LCIR | UVLC | NA | ARM | 8624 | HAD COMPLETE LOSSES AT 8,624' (BLFR).
192 | 01/02/2022 | ADC-14 | HRDH-1804 | 02 Jan 0130 - 0500 | 3.5 | 3.5 | 886771 |  | RR | FOT | DWKS | RIG | 10734 | ATTEMPTS TO START DRAWWORK AFTER SLIP AND CUT DRILLING LINE WITH NO SUCCESS., DRAWWORK IS NOT WORKING DUE TO ELECTICAL PROBLEM, TROUBLESHOOT DRAWWORKS FAILURE
194 | 01/02/2022 | ADC-16 | JAHM-6 | 01 Jan 1900 - 0500 | 24 | 34 | 886676 |  | RR | FOT | TDS | RIG | 0 | TDS TRIPPED DUE TO GROUND FAULT. TROUBLESHOOT & FOUND TDS STATOR MOTOR INSULATION GROUNDED.
196 | 01/02/2022 | ADC-21 | MHWZ-125104 | 02 Jan 1830 - 2330 | 5 | 5 | 886770 |  | JF | XTRI | BOP | RIG | 0 | EXCESS TIME TO RIG UP 26 3/4" BOP'S
197 | 01/02/2022 | ADC-58L | ABHD-170 | 02 Jan 2330 - 0500 | 5.5 | 5.5 | 886773 |  | WON | WTHR | NA | TK3 | 16437 | WAIT ON WEATHER DUE TO HEAVY RAIN, UNABLE TO MIX CEMENT.
199 | 01/02/2022 | ADC-58L | ABHD-170 | 27 Dec 1200 - 2330 | 18.5 | 38.5 | 886713 |  | TF | FOT | DV | TOD | 11802 | WHILE P/T 4-1/2" OFF BTM LINER BELOW HYDROSEAL CEMENTING VALVE TO 1450 PSI, OBSERVED PRESSURE DROP CONTINUOUSLY, RATE OF DROPPING 180 PSI /15 MIN'S.
200 | 01/02/2022 | ADC-58L | ABHD-170 | 02 Jan 2330 - 0500 | 5.5 | 5.5 | 886773 |  | WON | WTHR | NA | TK3 | 16437 | WAIT ON WEATHER DUE TO HEAVY RAIN, UNABLE TO MIX CEMENT.
201 | 01/02/2022 | ADC-65L | HRDH-1980 | 01 Jan 1930 - 1900 | 14 | 23.5 | 886706 |  | STUK | STBH | BHA | TK3 | 6395 | STRING GET STUCK IN OPEN HOLE AFTER MAKING THE PUMP IN SUB ASSEMBLY WHILE PREPAREATION FOR PUMP CEMENT PLUG. ATTEMPT TO WORK STRING UP & DOWN AT MAX LOADS - NO SUCCESS
203 | 01/02/2022 | ADC-65L | HRDH-1980 | 26 Dec 1800 - 0500 | 2.5 | 130 | 886385 |  | LCIR | UVLC | NA | TK3 | 6230 | DURING DRILLING THROUGH ARAB D BASE RESORVAR WITH 72 PCF KCL POLIMER MUD TOTAL LOSSES WERE ENCOUNTERED AT 6,230' TVD 6,231' MD. 50' MORE WERE DRILLED TO 6,280' PRIOR CURE LOSS PROCEDURES ACCORDING ARAMCO MANUAL WERE FOLLOWED UP.
204 | 01/02/2022 | ADC-65L | HRDH-1980 | 01 Jan 1930 - 1900 | 14 | 23.5 | 886706 |  | STUK | STBH | BHA | TK3 | 6395 | STRING GET STUCK IN OPEN HOLE AFTER MAKING THE PUMP IN SUB ASSEMBLY WHILE PREPAREATION FOR PUMP CEMENT PLUG. ATTEMPT TO WORK STRING UP & DOWN AT MAX LOADS - NO SUCCESS
206 | 01/02/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 1800 | 12.5 | 12.5 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
208 | 01/02/2022 | ADES-173 | NJYN-90 | 31 Dec 1200 - 0430 | 23.5 | 64.5 | 886561 |  | UPRA | GRF | MPMP | RIG | 12978 | NOTICED UNUSUAL NOISE AT MP AND MUD PUMPS OVERHEATING. TROUBLE-SHOOT MUD PUMP #2, FOUND BAD PINION BEARING. MP #3 FOUND DAMAGED CROSS-HEAD BEARING AND SLIDES.
210 | 01/02/2022 | ADES-174 | HRDH-2184 | 31 Dec 2230 - 0500 | 24 | 54.5 | 886670 | 886167 | LROP | XBTR | BIT | ARM | 5619 | ATTEMPTED TO DRILL 12" HOLE IN NEW FORMATION, OBSERVED ERRATIC TQ ONCE TOUCH BTM, SUSPECT JUNK ON BTM REMAINING FROM 16" BIT.
212 | 01/02/2022 | DPS-4 | SAHB-34 | 01 Jan 1630 - 0500 | 24 | 36.5 | 886685 |  | TH | NARW | NA | ARM | 4983 | TAKE SLACK OFF WEIGHT AT 4190' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS.
214 | 01/02/2022 | DPS-45 | UTMN-3015 | 30 Dec 0130 - 0500 | 23.5 | 70.25 | 886767 |  | MUD | IPDF | NA | SMI | 13228 | UNABLE TO ESTABLISH CIRCULATION DUE TO PLUGGED STRING CAUSED BY SETTLED BARITE.
215 | 01/02/2022 | HI-2 | BRRI-462 | 02 Jan 1445 - 1645 | 2 | 2 | 886720 | 884683 | TF | HERR | TBG | SCP | 1405 | SLB COMPLETION EXCESS TIME TO CONNECT CONTROL LINES AT ICV#2 & MP-PKR #2.
217 | 01/02/2022 | HI-2 | BRRI-462 | 13 Dec 1000 - 0500 | 22 | 450.5 | 884683 |  | TF | FOT | HVLV | BC | 5239 | BAKER UPPER SMART COMPLETION STINGER UNABLE TO ESTABLISH COMMUNICATION WITH LOWER SMART COMPLETION RESULT IN WELL DE-COMPLETION.
218 | 01/02/2022 | HI-2 | BRRI-462 | 02 Jan 1445 - 1645 | 2 | 2 | 886720 | 884683 | TF | HERR | TBG | SCP | 1405 | SLB COMPLETION EXCESS TIME TO CONNECT CONTROL LINES AT ICV#2 & MP-PKR #2.
220 | 01/02/2022 | HI-9 | MRJN-228 | 02 Jan 1530 - 0330 | 12 | 12 | 886723 |  | RR | FOT | CSYS | RIG | 10724 | WHILE WASH UP AND REAM DOWN,TDS KELLY HOSE STARTED LEAKING FROM ABOVE THE CLAMP ON TDS SIDE.
222 | 01/02/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0500 | 24 | 86.5 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
224 | 01/02/2022 | NBR-20S | UMWL-17 | 02 Jan 0900 - 1630 | 7.5 | 7.5 | 886772 |  | RR | FOT | DWKS | RIG | 9380 | EMERGENCY BRAKE DON'T RELEASE.
226 | 01/02/2022 | PN-9 | MRJN-91 | 01 Jan 1130 - 0500 | 24 | 41.5 | 886674 |  | WO | SRVC | NA | ARN | 0 | WAIT ON HSU TO PERFORM SEA BED SURVEY AT MRJN-89/94 PF FOR SAFE RIG APPROACH.
228 | 01/02/2022 | SCTD-2 | UTMN-1876 | 02 Jan 1800 - 0500 | 11 | 11 | 886785 |  | BHA | FOT | MWD | SDM | 12500 | UNABLE TO RESTORE COMMUNICATIONS WITH DOWNHOLE TOOLS
230 | 01/02/2022 | SDA | MRJN-737 | 01 Jan 1100 - 0500 | 24 | 42 | 886675 |  | UPRA | OTH | NA | RIG | 9280 | RIG SHUT DOWN WAITING FOR INVESTIGATION FOR THE HAND INJURY.
232 | 01/02/2022 | SINO-12L | HRDH-447 | 13 Dec 0500 - 1500 | 10 | 487.75 | 884690 |  | STUK | HINW | WLT | TK1 | 7110 | WL TRIPLE COMBO WITH DIELECTRIC LOGGING TOOL STRING GOT STUCK.
234 | 01/02/2022 | SINO-1L | KHRS-340 | 02 Jan 1400 - 2200 | 8 | 8 | 886745 |  | JF | HERR | NA | TK1 | 4228 | UNABLE TO RETREIVE 3-1/2" PX PLUG BELLOW PKR DUE TO SAND FILL.
236 | 01/02/2022 | SINO-32L | SHYB-535 | 29 Dec 0245 - 0700 | 2 | 76.25 | 886665 |  | CMT | CPNF | NA | BCM | 5950 | SOFT CMT WHILE DRILLING KICK OFF CMT PLUG.
238 | 01/02/2022 | SINO-36L | SDGM-490 | 02 Jan 0800 - 0500 | 21 | 21 | 886766 |  | STUK | STBG | TBG | TK1 | 10075 | LOWER COMPLETION DIFFERENTIALLY STUCK.
239 | 01/02/2022 | SL-7 | ZULF-1337 | 02 Jan 2115 - 0115 | 4 | 4 | 886769 |  | BHA | FOT | RM | NRT | 9709 | NOV ANDERREAM BLADE DIDN'T CLOSE FULLY WHEN PUMP OFF.
241 | 01/02/2022 | SL-7 | ZULF-1337 | 02 Jan 1630 - 0500 | 8.5 | 8.5 | 886768 |  | RR | FOT | TDS | RIG | 9709 | TOP DRIVE STOPPED TURNING DUE TO BRAKES ENGAGED.
242 | 01/02/2022 | SL-7 | ZULF-1337 | 02 Jan 2115 - 0115 | 4 | 4 | 886769 |  | BHA | FOT | RM | NRT | 9709 | NOV ANDERREAM BLADE DIDN'T CLOSE FULLY WHEN PUMP OFF.
244 | 01/02/2022 | SND-2004 | BRRI-556 | 02 Jan 0900 - 1500 | 6 | 6 | 886722 |  | RR | FOT | PSYS | RIG | 18367 | RIG POWER SHUT-DOWN DUE TO RAIN WATER INFILTRATION IN VFD UNIT. REPAIR AND REGAIN POWER SUPPLY
246 | 01/02/2022 | SND-2006 | UTMN-3135 | 02 Jan 1315 - 0500 | 15.75 | 15.75 | 886787 |  | BHA | FOT | BIT | RTC | 3069 | WHILE DRILLING 22" H.S, A 450 PSI SUDDEN DROP IN PRESSURE RESULTING IN 22" REED BIT LOST IN HOLE.
248 | 01/02/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 117.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
250 | 01/02/2022 | SNT-025 | SFNY-1007 | 30 Dec 1130 - 0500 | 24 | 89.5 | 886625 |  | WO | WOPF | NA | AP2 | 0 | RIG WAITING ON APPROVAL FROM SFNY ONSHORE PRODUCTION ENGINEERING TO COMMENCE FLOW BACK OPERATIONS.
252 | 01/02/2022 | SP-120 | MNIF-189 | 25 Dec 0500 - 0500 | 23.5 | 199 | 886030 |  | STUK | STBH | BHA | ARM | 6040 | STUCK PIPE DUE TO HOLE PACK-OFF AT SHALE FORMATION.
254 | 01/02/2022 | SP-229 | ABHD-873 | 01 Jan 0400 - 1130 | 6.5 | 7.5 | 886725 |  | JF | HERR | ESPL | KSC | 6819 | CANNOT GET READINGS FROM ZEINETH SENSOR, CHECKED & FOUND SURFACE EQUIPMENT ISSUES. (CABLE CONNECTOR AT SURFACE IS DAMAGED)
256 | 01/02/2022 | SP-306 | ABHD-843 | 27 Dec 1515 - 2200 | 17 | 150.75 | 886286 |  | TF | FOT | ESP | SBA | 6430 | SAWAFI-BORETS ESP FAILED TO WORK DURING ESP FUNCTION TEST.
258 | 01/02/2022 | SSA-302 | HRDH-1945 | 02 Jan 2130 - 2300 | 1.5 | 1.5 | 886765 |  | RR | FOT | HSYS | RIG | 9000 | RIG IRON ROUGHNICK HYD. HOSE LEAKING, CHANHING TO RIG PIPE SPINNER AND RIG TONGS.
260 | 01/02/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0500 | 23 | 46 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
262 | 01/02/2022 | SSA-5969 | UTMN-3195 | 26 Dec 0930 - 0430 | 23 | 182 | 886037 |  | LCIR | UVLC | NA | ARM | 8624 | HAD COMPLETE LOSSES AT 8,624' (BLFR).
264 | 01/02/2022 | STY-038 | ZULF-2084 | 02 Jan 1715 - 0500 | 11.75 | 11.75 | 886786 |  | DD | UDWL | RSS | SDM | 6111 | INSUFFICIENT BUILD UP RATE TO CATCH DIRECTIONAL PLAN
266 | 01/03/2022 | 088TE | QTIF-279 | 03 Jan 1815 - 1945 | 1.5 | 1.5 | 886781 |  | RR | FOT | HSYS | RIG | 14500 | REPAIR RIG CSG STABBING BOARD.
268 | 01/03/2022 | ADC-17 | ZULF-1259 | 30 Dec 1530 - 1700 | 10.75 | 12 | 886552 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER
269 | 01/03/2022 | ADC-31 | SDGM-1163 | 03 Jan 2130 - 0500 | 7.5 | 7.5 | 886896 |  | DSF | FOT | STRG | RIG | 12976 | PLUGGED DRL STRING.
271 | 01/03/2022 | ADC-31 | SDGM-1163 | 03 Jan 1815 - 2130 | 3.25 | 3.25 | 886779 |  | RR | FOT | PSYS | RIG | 12976 | POWER FAILURE OF SCR DUE TO HEAVY RAIN.
272 | 01/03/2022 | ADC-31 | SDGM-1163 | 03 Jan 2130 - 0500 | 7.5 | 7.5 | 886896 |  | DSF | FOT | STRG | RIG | 12976 | PLUGGED DRL STRING.
274 | 01/03/2022 | ADC-36 | SDGM-1186 | 03 Jan 0300 - 0500 | 2 | 2 | 886893 |  | JF | XTRI | CTRQ | WCR | 12384 | EXCESSIVE TIME FOR RUNNING CSG DUE TO POWER TONG & JAM UNIT FAILURE
276 | 01/03/2022 | ADC-50 | SFNY-1174 | 03 Jan 2145 - 2330 | 1.75 | 1.75 | 886898 |  | TF | FOT | WLT | SWL | 0 | SURFACE TEST WIRELINE BHA, DATA WAS NOT CLEAR, CHECKED BHA, CHANGED WIRELINE JAR AND HAD GOOD SHALLOW TEST.
278 | 01/03/2022 | ADC-57L | ABHD-620 | 02 Jan 1200 - 0100 | 18 | 22 | 886866 |  | WON | WTHR | NA | OTH | 0 | HEAVY RAIN LOCATION & SKID ROAD IN SLIPPERY CONDITION
279 | 01/03/2022 | ADC-58L | ABHD-170 | 02 Jan 2330 - 1230 | 7.5 | 13 | 886773 |  | WON | WTHR | NA | OTH | 16437 | WAIT ON WEATHER DUE TO HEAVY RAIN, UNABLE TO MIX CEMENT.
281 | 01/03/2022 | ADC-58L | ABHD-170 | 27 Dec 1200 - 0500 | 16.5 | 55 | 886713 |  | TF | FOT | HGRL | TOT | 11802 | WHILE P/T 4-1/2" OFF BTM LINER BELOW HYDROSEAL CEMENTING VALVE TO 1450 PSI, OBSERVED PRESSURE DROP CONTINUOUSLY, RATE OF DROPPING 180 PSI /15 MIN'S.
282 | 01/03/2022 | ADC-58L | ABHD-170 | 02 Jan 2330 - 1230 | 7.5 | 13 | 886773 |  | WON | WTHR | NA | OTH | 16437 | WAIT ON WEATHER DUE TO HEAVY RAIN, UNABLE TO MIX CEMENT.
284 | 01/03/2022 | ADC-62L | ANDR-764 | 03 Jan 1745 - 0500 | 11.25 | 11.25 | 886899 |  | RR | FOT | TDS | RIG | 2115 | AFTER HEAVY RAIN, OBSERVED RIG POWER SYSTEM SHUT DOWN WITH GROUND FAULT ALARM IN THE VFD ROOM, FOUND GROUND FAULT ON THE TDS,TRIED TO POWER UP THE TDS, GROUND FAULT ALARM FOR TDS REMAINS, NOT ABLE TO POWER UP THE TDS MOTOR
286 | 01/03/2022 | ADC-65L | HRDH-1980 | 26 Dec 1800 - 0500 | 23.5 | 153.5 | 886385 |  | LCIR | UVLC | NA | TK3 | 6230 | DURING DRILLING THROUGH ARAB D BASE RESORVAR WITH 72 PCF KCL POLIMER MUD TOTAL LOSSES WERE ENCOUNTERED AT 6,230' TVD 6,231' MD. 50' MORE WERE DRILLED TO 6,280' PRIOR CURE LOSS PROCEDURES ACCORDING ARAMCO MANUAL WERE FOLLOWED UP.
288 | 01/03/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 1100 | 5.5 | 18 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
290 | 01/03/2022 | ADES-173 | NJYN-90 | 03 Jan 0530 - 1000 | 2.75 | 2.75 | 886825 |  | RR | FOT | CSYS | RIG | 12983 | NOTICED A LOSS IN PUMP PRESSURE.
292 | 01/03/2022 | ADES-174 | HRDH-2184 | 31 Dec 2230 - 0500 | 24 | 78.5 | 886670 | 886167 | LROP | XBTR | BIT | RTC | 5619 | ATTEMPTED TO DRILL 12" HOLE IN NEW FORMATION, OBSERVED ERRATIC TQ ONCE TOUCH BTM, SUSPECT JUNK ON BTM REMAINING FROM 16" BIT.
294 | 01/03/2022 | ADM-656 | ABSF-179 | 03 Jan 0930 - 0500 | 19.5 | 19.5 | 886845 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR RIG MOVE
296 | 01/03/2022 | ARO-2001 | BRRI-184 | 03 Jan 0245 - 0500 | 2.25 | 2.25 | 886780 |  | TF | FOT | CTBG | SJT | 0 | SANJEL CTU INJECTOR HEAD MALFUNCTIONED
298 | 01/03/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 17.25 | 17.25 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
299 | 01/03/2022 | ARO-3004 | KARN-46 | 03 Jan 1845 - 2315 | 4.5 | 4.5 | 886895 |  | TF | FOT | PBR | BC | 10193 | UNABLE TO RELEASE BAKER RUNNING TOOL FROM MIDDLE COMPLETION
301 | 01/03/2022 | ARO-3004 | KARN-46 | 03 Jan 0845 - 1330 | 2.25 | 2.25 | 886894 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER
302 | 01/03/2022 | ARO-3004 | KARN-46 | 03 Jan 1845 - 2315 | 4.5 | 4.5 | 886895 |  | TF | FOT | PBR | BC | 10193 | UNABLE TO RELEASE BAKER RUNNING TOOL FROM MIDDLE COMPLETION
304 | 01/03/2022 | DPS-4 | SAHB-34 | 01 Jan 1630 - 0500 | 24 | 60.5 | 886685 |  | TH | NARW | NA | ARM | 4983 | TAKE SLACK OFF WEIGHT AT 4190' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS.
306 | 01/03/2022 | DPS-45 | UTMN-3015 | 30 Dec 0130 - 0500 | 24 | 94.25 | 886767 |  | MUD | IPDF | NA | SMI | 13228 | UNABLE TO ESTABLISH CIRCULATION DUE TO PLUGGED STRING CAUSED BY SETTLED BARITE.
308 | 01/03/2022 | HI-2 | BRRI-462 | 13 Dec 1000 - 0500 | 24 | 474.5 | 884683 |  | TF | FOT | HVLV | BC | 5239 | BAKER UPPER SMART COMPLETION STINGER UNABLE TO ESTABLISH COMMUNICATION WITH LOWER SMART COMPLETION RESULT IN WELL DE-COMPLETION.
309 | 01/03/2022 | NA-207S | ABMK-701 | 03 Jan 0800 - 1000 | 2 | 2 | 886891 |  | RR | FOT | TDS | RIG | 0 | WASH PIPE LEAKING
311 | 01/03/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0800 | 3 | 89.5 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
312 | 01/03/2022 | NA-207S | ABMK-701 | 03 Jan 1000 - 0500 | 19 | 19 | 886783 |  | JF | HERR | SLIPS | RIG | 0 | 3EA SLIPS DIES LOST IN THE WELL
313 | 01/03/2022 | NA-207S | ABMK-701 | 03 Jan 0800 - 1000 | 2 | 2 | 886891 |  | RR | FOT | TDS | RIG | 0 | WASH PIPE LEAKING
315 | 01/03/2022 | NBR-196S | SDGM-1174 | 03 Jan 1830 - 0500 | 10.5 | 10.5 | 886778 |  | TF | FOT | HGRL | SLH | 13034 | SCHLUMBERGER 7" BALANCED PISTON HYD. SET LH FAILED TO SET.
316 | 01/03/2022 | NBR-654S | HRDH-1935 | 03 Jan 0415 - 0500 | .75 | .75 | 886901 |  | RR | FOT | TDS | RIG | 10960 | EXCESSIVE TIME FOR TDS SERVICE.
318 | 01/03/2022 | NBR-654S | HRDH-1935 | 03 Jan 0115 - 0315 | 2 | 2 | 886900 |  | DSF | FOT | DP | RIG | 10960 | VERY TIGHT DP CONNECTION.
319 | 01/03/2022 | NBR-654S | HRDH-1935 | 03 Jan 0415 - 0500 | .75 | .75 | 886901 |  | RR | FOT | TDS | RIG | 10960 | EXCESSIVE TIME FOR TDS SERVICE.
320 | 01/03/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 764.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
322 | 01/03/2022 | NBR-783S | MDRK-55 | 07 Nov 0500 - 0500 | 12 | 543 | 881591 |  | STUK | IPDF | BHA | BAR | 16256 | PIPE STUCK WHILE POOH DUE TO SUSPECTED MUD CONDITION.
323 | 01/03/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 764.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
324 | 01/03/2022 | PN-9 | MRJN-91 | 03 Jan 1100 - 0500 | 18 | 18 | 886906 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR RIG MOVE TO MRJN-89/94 PF.
326 | 01/03/2022 | PN-9 | MRJN-91 | 01 Jan 1130 - 1100 | 6 | 47.5 | 886674 |  | WO | SRVC | NA | ARN | 0 | WAIT ON HSU TO PERFORM SEA BED SURVEY AT MRJN-89/94 PF FOR SAFE RIG APPROACH.
327 | 01/03/2022 | PN-9 | MRJN-91 | 03 Jan 1100 - 0500 | 18 | 18 | 886906 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR RIG MOVE TO MRJN-89/94 PF.
329 | 01/03/2022 | SCTD-2 | UTMN-1876 | 02 Jan 1800 - 1100 | 6 | 17 | 886785 |  | BHA | FOT | MWD | SDM | 12500 | UNABLE TO RESTORE COMMUNICATIONS WITH DOWNHOLE TOOLS
331 | 01/03/2022 | SDA | MRJN-737 | 01 Jan 1100 - 1000 | 5 | 47 | 886675 |  | UPRA | OTH | NA | RIG | 9280 | RIG SHUT DOWN WAITING FOR INVESTIGATION FOR THE HAND INJURY.
333 | 01/03/2022 | SINO-12L | HRDH-447 | 03 Jan 0500 - 0245 | 21.75 | 21.75 | 886782 |  | TF | FOT | WLT | SWL | 5050 | AFTER SLB LATCHED TO WET CONNECTOR. OBSERVED RESISTIVITY TOOL SIGNAL LOST.
335 | 01/03/2022 | SINO-32L | SHYB-535 | 03 Jan 0145 - 0500 | 3.25 | 3.25 | 886890 |  | BHA | FOT | MACS | DSI | 4645 | ATTEMPT TO CIRCULATE FOUND STRG PLUGGED PBL SUB MALFUNCTION.
337 | 01/03/2022 | SINO-36L | SDGM-490 | 02 Jan 0800 - 0500 | 21.5 | 42.5 | 886766 |  | STUK | STBG | TBG | TK1 | 10075 | DIFFERENTIALLY STUCK +/- 1409 FEET OFF PLANNED SETTING DEPTH
339 | 01/03/2022 | SL-7 | ZULF-1337 | 02 Jan 1630 - 2045 | 15.75 | 24.25 | 886768 |  | RR | FOT | TDS | RIG | 9709 | TOP DRIVE STOPPED TURNING DUE TO BRAKES ENGAGED.
341 | 01/03/2022 | SND-1502 | HWYH-32 | 03 Jan 1930 - 0500 | 9.5 | 9.5 | 886887 |  | RR | FOT | TDS | RIG | 4947 | REPAIR TDS
343 | 01/03/2022 | SND-2006 | UTMN-3135 | 02 Jan 1315 - 0500 | 24 | 39.75 | 886787 |  | BHA | FOT | BIT | RTC | 3069 | WHILE DRILLING 22" H.S, A 450 PSI SUDDEN DROP IN PRESSURE RESULTING IN 22" REED BIT LOST IN HOLE.
345 | 01/03/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 141.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
347 | 01/03/2022 | SND-3001 | HZEM-161004 | 03 Jan 1530 - 1630 | 1 | 1 | 886888 |  | TF | FOT | TTRQ | ITS | 11450 | ITC HYDRAULIC UNIT FOR POWER TONG STOPPED WORKING AND SUPPLYING AIR TO POWER TONG
349 | 01/03/2022 | SNF036 | MRJN-901 | 03 Jan 0500 - 0500 | 24 | 24 | 886776 |  | WON | WTHR | NA | ARN | 0 | WAIT ON WEATHER TO START RIG MOVE.
351 | 01/03/2022 | SNT-025 | SFNY-1007 | 30 Dec 1100 - 0500 | 24 | 114 | 886625 |  | WO | WOPF | NA | AP2 | 0 | RIG WAITING ON APPROVAL FROM SFNY ONSHORE PRODUCTION ENGINEERING TO COMMENCE FLOW BACK OPERATIONS.
353 | 01/03/2022 | SP-120 | MNIF-189 | 25 Dec 0500 - 0500 | 24 | 223 | 886030 |  | STUK | STBH | BHA | ARM | 6040 | STUCK PIPE DUE TO HOLE PACK-OFF AT SHALE FORMATION.
355 | 01/03/2022 | SP-262 | HZEM-141404 | 03 Jan 1200 - 1445 | 2.75 | 2.75 | 886897 |  | RR | FOT | TDS | RIG | 12249 | LOST ROTATION ON TDS DUE TO BAD COMMUNICATION BETWEEN ENCODER AND TDS MOTOR.
357 | 01/03/2022 | SSA-51 | MNIF-254 | 03 Jan 1630 - 1915 | 2.75 | 2.75 | 886889 |  | STUK | STBH | BHA | ARM | 4073 | AT 4073 FT, STRING GOT STUCK. WORK STRING TILL GOT CIRCUALTION. SPOT 50 BBLS LUBRICANT PILL AND WORK STRING WITH JAR UP TILL STRING GOT FREE.
359 | 01/03/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0500 | 23.5 | 69.5 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
361 | 01/03/2022 | SSA-5969 | UTMN-3195 | 03 Jan 0800 - 2130 | 13.5 | 13.5 | 886777 |  | BHA | FOT | MWD | SDM | 8868 | LOST SIGNAL FROM SLB MWD/GR TOOL
363 | 01/03/2022 | STY-038 | ZULF-2084 | 02 Jan 1715 - 1300 | 8 | 19.75 | 886786 |  | DD | UDWL | RSS | SDM | 6111 | INSUFFICIENT BUILD UP RATE TO CATCH DIRECTIONAL PLAN
365 | 01/04/2022 | ADC-31 | SDGM-1163 | 03 Jan 2130 - 0400 | 22.25 | 29.75 | 886896 |  | DSF | FOT | STRG | RIG | 12976 | PLUGGED DRL STRING.
367 | 01/04/2022 | ADC-50 | SFNY-1174 | 04 Jan 1330 - 1500 | 1.5 | 1.5 | 887086 |  | TF | FOT | WLT | SWL | 0 | TROUBLESHOOTING FOUND THE ELECTRIC ISSUE WAS COMING FROM ADAPTER BETWEEN SLB TOOLS AND TGT TOOLS
369 | 01/04/2022 | ADC-57L | ABHD-620 | 02 Jan 1200 - 0500 | 20.5 | 42.5 | 886866 |  | WON | WTHR | NA | OTH | 0 | HEAVY RAIN LOCATION & SKID ROAD IN SLIPPERY CONDITION
371 | 01/04/2022 | ADC-58L | ABHD-170 | 27 Dec 1200 - 0500 | 24 | 79 | 886713 |  | TF | FOT | HGRL | TOT | 11802 | WHILE P/T 4-1/2" OFF BTM LINER BELOW HYDROSEAL CEMENTING VALVE TO 1450 PSI, OBSERVED PRESSURE DROP CONTINUOUSLY, RATE OF DROPPING 180 PSI /15 MIN'S.
373 | 01/04/2022 | ADC-62L | ANDR-764 | 03 Jan 1745 - 0500 | 24 | 35.25 | 886899 |  | RR | FOT | TDS | RIG | 2115 | AFTER HEAVY RAIN, OBSERVED RIG POWER SYSTEM SHUT DOWN WITH GROUND FAULT ALARM IN THE VFD ROOM, FOUND GROUND FAULT ON THE TDS,TRIED TO POWER UP THE TDS, GROUND FAULT ALARM FOR TDS REMAINS, NOT ABLE TO POWER UP THE TDS MOTOR
375 | 01/04/2022 | ADC-65L | HRDH-1980 | 26 Dec 1800 - 1200 | 7 | 160.5 | 886385 |  | LCIR | UVLC | NA | TK3 | 6230 | DURING DRILLING THROUGH ARAB D BASE RESORVAR WITH 72 PCF KCL POLIMER MUD TOTAL LOSSES WERE ENCOUNTERED AT 6,230' TVD 6,231' MD. 50' MORE WERE DRILLED TO 6,280' PRIOR CURE LOSS PROCEDURES ACCORDING ARAMCO MANUAL WERE FOLLOWED UP.
377 | 01/04/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 0500 | 24 | 42 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
379 | 01/04/2022 | ADES-174 | HRDH-2184 | 31 Dec 2230 - 0500 | 24 | 102.5 | 886670 | 886167 | LROP | XBTR | BIT | RTC | 5619 | ATTEMPTED TO DRILL 12" HOLE IN NEW FORMATION, OBSERVED ERRATIC TQ ONCE TOUCH BTM, SUSPECT JUNK ON BTM REMAINING FROM 16" BIT.
381 | 01/04/2022 | ADES-798 | JFYN-13 | 03 Jan 0500 - 0500 | 24 | 48 | 886985 |  | CMT | CPNF | NA | SCM | 16255 | CEMENT PLUG WAS NOT FOUND AFTER WOC FOR 1000 PSI UCA.
383 | 01/04/2022 | ADM-261 | MRJN-134 | 04 Jan 0945 - 1045 | 1 | 1 | 887025 |  | RR | FPMP | MPMP | RIG | 8145 | MUD PUMP FAILURE (LINER GASKET) WHILST OTHER MUD PUMP ALREADY UNDER REPAIR (LINER GASKET). WORK STRING. REPAIR MUD PUMP.
385 | 01/04/2022 | ADM-266 | SFNY-489 | 04 Jan 0500 - 0500 | 24 | 24 | 886969 |  | WON | WTHR | NA | ARN | 0 | W.O.W TO MAKE CREW CHANGE AND RECEIVE SERVICE HAND BY CHOPPER.
387 | 01/04/2022 | ADM-339 | RBYN-54 | 04 Jan 0245 - 0445 | 2 | 2 | 886972 |  | BHA | FOT | WBCL | SSW | 5166 | DURING M/U SYNERGY VAX TOOL OBSERVED KELLY BUSHING X KELLY SLEEVE CONNECTION DAMAGED,
389 | 01/04/2022 | ADM-656 | ABSF-179 | 03 Jan 0930 - 0500 | 24 | 43.5 | 886845 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR RIG MOVE
391 | 01/04/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 24 | 41.25 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
393 | 01/04/2022 | BB-84A | MRJN-587 | 04 Jan 2000 - 2230 | 2.5 | 2.5 | 886970 |  | RR | FOT | TDS | RIG | 2000 | EXCESSIVE TIME WHILE CHANGE-OUT TDS SAVER SUB DUE TO OVER TOURQED, AND CHANGED-OUT RIG TONG DIES
395 | 01/04/2022 | BCTD-4 | HRDH-2016 | 04 Jan 1430 - 0500 | 14.5 | 14.5 | 886966 |  | BHA | FOT | CTAC | RIG | 14450 | FAILED DGS TOOL; POH FOR NEW BHA
397 | 01/04/2022 | DPS-4 | SAHB-34 | 01 Jan 1630 - 0500 | 24 | 84.5 | 886685 |  | TH | IPDF | NA | OES | 4983 | TAKE SLACK OFF WEIGHT AT 4190' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS.
399 | 01/04/2022 | EXL-IVA | SFNY-4010 | 04 Jan 0630 - 0745 | 1.25 | 1.25 | 887085 |  | JF | XTRI | CTRQ | MSD | 903 | ALMASOOD FLUSH MOUNT SLIPS NOT SETTING,
401 | 01/04/2022 | HI-2 | BRRI-462 | 13 Dec 1000 - 0500 | 24 | 498.5 | 884683 |  | TF | FOT | HVLV | BC | 5239 | BAKER UPPER SMART COMPLETION STINGER UNABLE TO ESTABLISH COMMUNICATION WITH LOWER SMART COMPLETION RESULT IN WELL DE-COMPLETION.
403 | 01/04/2022 | HI-5 | MHRH-59 | 04 Jan 0900 - 1400 | 5 | 5 | 886968 |  | WO | MATL | NA | ARM | 8200 | WAIT ON BAKER P& A ISOLATION KIT TO BE SHIPPED DUE TO CHANGE OF PLAN.
405 | 01/04/2022 | NA-128S | HRDH-2225 | 04 Jan 0315 - 0500 | 1.75 | 1.75 | 887067 |  | RR | FOT | TDS | RIG | 12130 | TROUBLE SHOOTING ON TDS LINKS, LINKS DON'T OPERATE.
406 | 01/04/2022 | NA-207S | ABMK-701 | 03 Jan 1000 - 0530 | .5 | 19.5 | 886783 |  | JF | HERR | SLIPS | RIG | 0 | 3EA SLIPS DIES LOST IN THE WELL
408 | 01/04/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0500 | 23.5 | 113 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
409 | 01/04/2022 | NA-207S | ABMK-701 | 03 Jan 1000 - 0530 | .5 | 19.5 | 886783 |  | JF | HERR | SLIPS | RIG | 0 | 3EA SLIPS DIES LOST IN THE WELL
411 | 01/04/2022 | NBR-196S | SDGM-1174 | 03 Jan 1830 - 0500 | 24 | 34.5 | 886778 |  | TF | FOT | HGRL | SLH | 13034 | SCHLUMBERGER 7" BALANCED PISTON HYD. SET LH FAILED TO SET.
412 | 01/04/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 776.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
414 | 01/04/2022 | NBR-783S | MDRK-55 | 07 Nov 0500 - 0500 | 12 | 555 | 881591 |  | STUK | IPDF | BHA | BAR | 16256 | PIPE STUCK WHILE POOH DUE TO SUSPECTED MUD CONDITION.
415 | 01/04/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 776.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
417 | 01/04/2022 | PN-9 | MRJN-91 | 03 Jan 1100 - 0500 | 24 | 42 | 886906 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR RIG MOVE TO MRJN-89/94 PF.
419 | 01/04/2022 | SINO-1L | KHRS-340 | 04 Jan 1430 - 0100 | 10.5 | 10.5 | 886974 |  | BB | LFVS | BIT | TK1 | 3550 | FAILURE OF FLOAT VALVE DURING RIH W/9-5/8" SCRAPER BHA.
420 | 01/04/2022 | SINO-32L | SHYB-535 | 03 Jan 0200 - 1100 | 6 | 9 | 886890 |  | BHA | FOT | MACS | DSI | 5900 | ATTEMPT TO CIRCULATE FOUND STRG PLUGGED PBL SUB MALFUNCTION.
422 | 01/04/2022 | SINO-32L | SHYB-535 | 03 Jan 1800 - 0500 | 18 | 26 | 886784 |  | LCIR | FRFM | NA | ARN | 5900 | SEVER LOSS OF CIRCULATION 200 BPH
423 | 01/04/2022 | SINO-32L | SHYB-535 | 03 Jan 0200 - 1100 | 6 | 9 | 886890 |  | BHA | FOT | MACS | DSI | 5900 | ATTEMPT TO CIRCULATE FOUND STRG PLUGGED PBL SUB MALFUNCTION.
425 | 01/04/2022 | SINO-36L | SDGM-490 | 02 Jan 0800 - 0500 | 24 | 66.5 | 886766 |  | STUK | STBG | TBG | TK1 | 10075 | DIFFERENTIALLY STUCK +/- 1409 FEET OFF PLANNED SETTING DEPTH
426 | 01/04/2022 | SL-7 | ZULF-1337 | 04 Jan 0700 - 1845 | 1.5 | 1.5 | 886986 |  | RR | FOT | SLIPS | RIG | 10028 | HYDR ELEVATORS NOT CLOSING FULLY ON STAND 5-1/2" DP.
428 | 01/04/2022 | SL-7 | ZULF-1337 | 04 Jan 1400 - 0400 | 13 | 13 | 886967 |  | BHA | FOT | MWD | SPS | 10215 | SPERRY SUN MWD FAILURE
429 | 01/04/2022 | SL-7 | ZULF-1337 | 04 Jan 0700 - 1845 | 1.5 | 1.5 | 886986 |  | RR | FOT | SLIPS | RIG | 10028 | HYDR ELEVATORS NOT CLOSING FULLY ON STAND 5-1/2" DP.
431 | 01/04/2022 | SND-1502 | HWYH-32 | 03 Jan 1930 - 0500 | 24 | 33.5 | 886887 |  | RR | FOT | TDS | RIG | 4947 | REPAIR TDS
433 | 01/04/2022 | SND-2001 | SDGM-1240 | 04 Jan 0500 - 0230 | 21.5 | 21.5 | 886987 |  | TF | FOT | WLT | HWP | 14696 | WHILE ATTEMPTING TO SET DUAL PACKER AT STATION FOR PUMPING SESSION THE PUMPS QUIT WORKING. BOTH PUMPS FAILED.
435 | 01/04/2022 | SND-2006 | UTMN-3135 | 02 Jan 1315 - 0500 | 23.5 | 63.25 | 886787 |  | BHA | FOT | BIT | RTC | 3069 | WHILE DRILLING 22" H.S, A 450 PSI SUDDEN DROP IN PRESSURE RESULTING IN 22" REED BIT LOST IN HOLE.
437 | 01/04/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 165.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
439 | 01/04/2022 | SNT-025 | SFNY-1007 | 30 Dec 1100 - 0730 | 2.5 | 116.5 | 886625 |  | WO | WOPF | NA | AP2 | 0 | RIG WAITING ON APPROVAL FROM SFNY ONSHORE PRODUCTION ENGINEERING TO COMMENCE FLOW BACK OPERATIONS.
440 | 01/04/2022 | SP-120 | MNIF-189 | 04 Jan 1400 - 1930 | 5.5 | 5.5 | 886988 |  | RR | FOT | DWKS | RIG | 1430 | RETIGHT DRAWWORK LUBRICANT PLATE.
442 | 01/04/2022 | SP-120 | MNIF-189 | 25 Dec 0500 - 0500 | 18 | 241 | 886030 |  | STUK | STBH | BHA | ARM | 6040 | STUCK PIPE DUE TO HOLE PACK-OFF AT SHALE FORMATION.
443 | 01/04/2022 | SP-120 | MNIF-189 | 04 Jan 1400 - 1930 | 5.5 | 5.5 | 886988 |  | RR | FOT | DWKS | RIG | 1430 | RETIGHT DRAWWORK LUBRICANT PLATE.
445 | 01/04/2022 | SP-276 | MHKK-802 | 04 Jan 0130 - 0500 | 3.5 | 3.5 | 886971 |  | JF | CCAJ | NA | SJC | 620 | C PUMP MIXING STUCK AND PACKED THE MIXING SYSTEM OF UNIT
447 | 01/04/2022 | SSA-102 | QTIF-699 | 04 Jan 1330 - 1345 | .25 | .25 | 886989 |  | LCIR | CFFM | MDCAP | ARM | 1228 | ENCOUNTERED TOTAL LOSSES AT 1228' MD,
449 | 01/04/2022 | SSA-51 | MNIF-254 | 04 Jan 2030 - 2130 | 1 | 1 | 887066 |  | BHA | FOT | MWD | BHI | 4356 | CHECK MWD SURVEY DATA QUALITY MEANWHILE CIRCULATE AND RECIPROCATE STRING
451 | 01/04/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0500 | 24 | 93.5 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
453 | 01/04/2022 | SSA-5868 | GHZL-97 | 04 Jan 0645 - 0500 | 22.25 | 22.25 | 887065 |  | BHA | FOT | RSS | BHI | 11955 | RSS DRILLING SYSTEM UNABLE TO BUILD INC.
455 | 01/04/2022 | SSA-5969 | UTMN-3195 | 03 Jan 0800 - 2330 | 11.5 | 25 | 886777 |  | BHA | FOT | MWD | SDM | 8868 | LOST SIGNAL FROM SLB MWD/GR TOOL
457 | 01/04/2022 | T216 | ANDR-357 | 04 Jan 0400 - 0500 | 1 | 1 | 886990 |  | RR | FOT | DWKS | RIG | 0 | DRAWWORK FAILURE
459 | 01/04/2022 | T217 | UTMN-488 | 04 Jan 0000 - 0500 | 5 | 5 | 886973 |  | DSF | HERR | STRG | RIG | 0 | BHA PLUGGED WHILE ATTEMPT TO PUMP DOWN STRING VOL.
461 | 01/05/2022 | ADC-17 | ZULF-1259 | 30 Dec 1530 - 1445 | 5.75 | 17.75 | 886552 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER
463 | 01/05/2022 | ADC-58L | ABHD-170 | 27 Dec 1200 - 1630 | 11.5 | 90.5 | 886713 |  | TF | FOT | HGRL | TOT | 11802 | WHILE P/T 4-1/2" OFF BTM LINER BELOW HYDROSEAL CEMENTING VALVE TO 1450 PSI, OBSERVED PRESSURE DROP CONTINUOUSLY, RATE OF DROPPING 180 PSI /15 MIN'S.
465 | 01/05/2022 | ADC-62L | ANDR-764 | 03 Jan 1745 - 0500 | 24 | 59.25 | 886899 |  | RR | FOT | TDS | RIG | 2115 | AFTER HEAVY RAIN, OBSERVED RIG POWER SYSTEM SHUT DOWN WITH GROUND FAULT ALARM IN THE VFD ROOM, FOUND GROUND FAULT ON THE TDS,TRIED TO POWER UP THE TDS, GROUND FAULT ALARM FOR TDS REMAINS, NOT ABLE TO POWER UP THE TDS MOTOR
467 | 01/05/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 0500 | 24 | 66 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
469 | 01/05/2022 | ADC-70 | BRRI-2230 | 05 Jan 1230 - 1430 | 2 | 2 | 887125 |  | WO | ORDS | NA | ARM | 7880 | WAITING ON APPROVED DIRECTIONAL PLAN FROM RMD.
471 | 01/05/2022 | ADES-174 | HRDH-2184 | 31 Dec 2230 - 1800 | 13 | 115.5 | 886670 | 886167 | LROP | XBTR | BIT | ARM | 5619 | ATTEMPTED TO DRILL 12" HOLE IN NEW FORMATION, OBSERVED ERRATIC TQ ONCE TOUCH BTM, SUSPECT JUNK ON BTM REMAINING FROM 16" BIT.
473 | 01/05/2022 | ADES-798 | JFYN-13 | 03 Jan 0500 - 1615 | 9 | 57 | 886985 |  | CMT | CPNF | NA | SCM | 16255 | CEMENT PLUG WAS NOT FOUND AFTER WOC FOR 1000 PSI UCA.
475 | 01/05/2022 | ADM-266 | SFNY-489 | 04 Jan 0500 - 1500 | 10 | 34 | 886969 |  | WON | WTHR | NA | ARN | 0 | W.O.W TO MAKE CREW CHANGE AND RECEIVE SERVICE HAND BY CHOPPER.
477 | 01/05/2022 | ADM-339 | RBYN-54 | 04 Jan 0245 - 1215 | 7.25 | 9.5 | 886972 |  | BHA | FOT | WBCL | SSW | 5166 | DURING M/U SYNERGY VAX TOOL OBSERVED KELLY BUSHING X KELLY SLEEVE CONNECTION DAMAGED,
479 | 01/05/2022 | ADM-511 | MRJN-2016 | 05 Jan 1600 - 1930 | 3.5 | 3.5 | 887185 |  | WON | WTHR | NA | ARM | 18040 | UNABLE TO OFFLOAD MUD CHEMICALS FROM SUPPLY VESSEL DUE TO ADVERSE WEATHER CONDITIONS.
481 | 01/05/2022 | ADM-656 | ABSF-179 | 03 Jan 0930 - 0500 | 24 | 67.5 | 886845 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR RIG MOVE
483 | 01/05/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 24 | 65.25 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
485 | 01/05/2022 | ARO-3004 | KARN-46 | 05 Jan 0700 - 0500 | 22 | 22 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
487 | 01/05/2022 | DPS-4 | SAHB-34 | 01 Jan 1630 - 0945 | 4.75 | 89.25 | 886685 |  | TH | IPDF | NA | OES | 4983 | TAKE SLACK OFF WEIGHT AT 4190' WHILE RUNNING 13-3/8"CASING, ATTEMPT TO WASH DOWN, NO SUCCESS.
489 | 01/05/2022 | ENS-108 | SFNY-1560 | 05 Jan 1000 - 1800 | 8 | 8 | 887165 |  | WON | WTHR | NA | ARM | 0 | STOP PRE-LOAD OPERATION DUE TO ROUGH WEATHER
490 | 01/05/2022 | ENS-141 | MRJN-752 | 05 Jan 2215 - 2345 | 1.5 | 1.5 | 887186 |  | DD | HERR | RSS | BHI | 5820 | EXCESSIVE TIME RE-LOGGING 8.5" WITH RSS-MWD ASSY.
492 | 01/05/2022 | ENS-141 | MRJN-752 | 05 Jan 1400 - 1500 | 1 | 1 | 886977 |  | DD | HERR | RSS | BHI | 5961 | EXCESSIVE TIME MAKING UP 8.5" RSS-MWD ASSY.
493 | 01/05/2022 | ENS-141 | MRJN-752 | 05 Jan 2215 - 2345 | 1.5 | 1.5 | 887186 |  | DD | HERR | RSS | BHI | 5820 | EXCESSIVE TIME RE-LOGGING 8.5" WITH RSS-MWD ASSY.
495 | 01/05/2022 | HI-2 | BRRI-462 | 13 Dec 1000 - 0500 | 24 | 522.5 | 884683 |  | TF | FOT | HVLV | BC | 5239 | BAKER UPPER SMART COMPLETION STINGER UNABLE TO ESTABLISH COMMUNICATION WITH LOWER SMART COMPLETION RESULT IN WELL DE-COMPLETION.
497 | 01/05/2022 | HI-4 | BRRI-780 | 05 Jan 1800 - 0500 | 11 | 11 | 887205 |  | WON | WTHR | NA | ARM | 6062 | NON-DP SUPPLY BOATS UNABLE TO WORK TO SUPPLY MUD TO DISPLACE HOLE.
499 | 01/05/2022 | MP-4 | SFNY-672 | 05 Jan 1700 - 0500 | 12 | 12 | 887226 |  | WON | WTHR | NA | ARM | 0 | ZULF FIELD SERVICES UNABLE TO VISIT ZULF-216/221 PF FOR ACCEPTANCE DUE TO BAD WEATHER
501 | 01/05/2022 | NA-128S | HRDH-2225 | 04 Jan 0315 - 0800 | 3 | 4.75 | 887067 |  | RR | FOT | TDS | RIG | 12130 | TROUBLE SHOOTING ON TDS LINKS, LINKS DON'T OPERATE.
503 | 01/05/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0500 | 24 | 137 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
505 | 01/05/2022 | NBR-196S | SDGM-1174 | 03 Jan 1830 - 0500 | 24 | 58.5 | 886778 |  | TF | FOT | HGRL | SLH | 13034 | SCHLUMBERGER 7" BALANCED PISTON HYD. SET LH FAILED TO SET.
506 | 01/05/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 788.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
508 | 01/05/2022 | NBR-783S | MDRK-55 | 07 Nov 0500 - 0500 | 12 | 567 | 881591 |  | STUK | IPDF | BHA | BAR | 16256 | PIPE STUCK WHILE POOH DUE TO SUSPECTED MUD CONDITION.
509 | 01/05/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 788.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
511 | 01/05/2022 | PA-785S | QTIF-24 | 05 Jan 2330 - 0100 | 1.5 | 1.5 | 887225 |  | RR | FOT | TDS | RIG | 250 | LEAK FROM TDS HANDLER ROTATE MOTOR HYDRAULIC HOSE.
513 | 01/05/2022 | PN-9 | MRJN-91 | 03 Jan 1100 - 0430 | 17.5 | 59.5 | 886906 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR RIG MOVE TO MRJN-89/94 PF.
515 | 01/05/2022 | SA5898 | HRDH-2101 | 05 Jan 1245 - 1745 | 5 | 5 | 887145 |  | RR | FOT | TDS | RIG | 9467 | FAILURE OF BLOWER MOTOR OF TOP DRIVE.
517 | 01/05/2022 | SINO-32L | SHYB-535 | 03 Jan 1800 - 0500 | 24 | 50 | 886784 |  | LCIR | FRFM | NA | ARN | 5900 | SEVER LOSS OF CIRCULATION 200 BPH
519 | 01/05/2022 | SINO-36L | SDGM-490 | 02 Jan 0800 - 0500 | 24 | 90.5 | 886766 |  | STUK | STBG | TBG | TK1 | 10075 | DIFFERENTIALLY STUCK +/- 1409 FEET OFF PLANNED SETTING DEPTH
521 | 01/05/2022 | SL-7 | ZULF-1337 | 04 Jan 1400 - 1200 | 7 | 21 | 886967 |  | BHA | FOT | MWD | SPS | 10215 | SPERRY SUN MWD FAILURE
523 | 01/05/2022 | SND-1502 | HWYH-32 | 03 Jan 1930 - 2215 | 17.25 | 50.75 | 886887 |  | RR | FOT | TDS | RIG | 4947 | REPAIR TDS
525 | 01/05/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 189.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
527 | 01/05/2022 | SSA-101 | BRRI-1145 | 05 Jan 1730 - 0500 | 11.5 | 11.5 | 886978 |  | TF | FOT | WLT | BAW | 9280 | BAKER GR NOT WORKING AFTER LATCH RCX (PRESSURE / SAMPLING TOOL)
529 | 01/05/2022 | SSA-201 | HRDH-1216 | 05 Jan 2130 - 0500 | 7.5 | 7.5 | 886982 |  | CMT | HERR | NA | NCS | 14717 | NESR UNABLE TO BATCH MIX TAIL SLURRY, DUE PLUG ON THE BULKER SECTION LINE.
531 | 01/05/2022 | SSA-302 | HRDH-1945 | 05 Jan 0230 - 0400 | 1.5 | 1.5 | 886983 |  | TF | FOT | WLT | HWP | 11208 | HALL W/L TRUCK SHUT DOWN SUDDENLY @ 11208' & LOST TOOLS SIGNAL, POWER UP TRUCK AGAIN WITHOUT TOOLS RESPONSE, POH HALL LOGGING TOOLS RUN#1 INSIDE 7" SHOE, HALL CREW TROUBLE SHOOTING TILL REGAIN TOOLS SIGNAL, RIH BACK & RECORD UP TO SAME DEPTH.
533 | 01/05/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0500 | 23.5 | 117 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
535 | 01/05/2022 | SSA-5868 | GHZL-97 | 04 Jan 0645 - 1000 | 5 | 27.25 | 887065 |  | BHA | FOT | RSS | BHI | 11955 | RSS DRILLING SYSTEM UNABLE TO BUILD INC.
537 | 01/05/2022 | SSA-5891 | HRDH-695 | 05 Jan 1800 - 0500 | 11 | 11 | 886979 |  | DD | UDWL | RSS | SPS | 12200 | SPERRY SUN IS NOT ABLE TO ACHIEVE REQUIRED BUILD UP AS DIRECTIONAL PLAN.
539 | 01/05/2022 | SSA-5892 | MHWZ-5 | 05 Jan 0630 - 1600 | 9.5 | 9.5 | 886976 |  | BHA | FOT | GMWD | BHI | 16897 | MWD TOOL/ISOLATION TOOL THREAD CONNECTION NOT ABLE TO APPLY RECOMMENDED MAKE UP TORQUE.
541 | 01/05/2022 | T217 | UTMN-488 | 04 Jan 0000 - 1000 | 5 | 10 | 886973 |  | DSF | HERR | STRG | RIG | 0 | BHA PLUGGED WHILE ATTEMPT TO PUMP DOWN STRING VOL.
543 | 01/05/2022 | WCL-83 | MRJN-831 | 04 Jan 0445 - 1515 | 10.25 | 10.5 | 887105 |  | WO | WOTO | NA | CRW | 6500 | CORETRAX FAILED TO DELIVER WBCO TOOLS ON TIME RESULTING IN AN ADDITIONAL RUN.
545 | 01/06/2022 | ADC-16 | JAHM-6 | 06 Jan 0100 - 0500 | 4 | 4 | 887425 |  | RR | FOT | TDS | RIG | 126 | WHILE DISCONNECTING TDS FROM HWDP CONNECTION, TDS CONNECTION OPEN AT SAVER SUB AND KELLY COCK.
547 | 01/06/2022 | ADC-62L | ANDR-764 | 03 Jan 1745 - 1645 | 11.75 | 71 | 886899 |  | RR | FOT | TDS | RIG | 2115 | AFTER HEAVY RAIN, OBSERVED RIG POWER SYSTEM SHUT DOWN WITH GROUND FAULT ALARM IN THE VFD ROOM, FOUND GROUND FAULT ON THE TDS,TRIED TO POWER UP THE TDS, GROUND FAULT ALARM FOR TDS REMAINS, NOT ABLE TO POWER UP THE TDS MOTOR
549 | 01/06/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 0500 | 24 | 90 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
551 | 01/06/2022 | ADES-889 | HRDH-1282 | 06 Jan 2230 - 0500 | 6.5 | 6.5 | 887385 |  | TF | FOT | SLICK | EX1 | 12150 | EXPRO SLICKLINE UNABLE TO POOH W/3.6" GC DUE TO ELECTRICAL PROBLEM IN UNIT. CAN RIH, BUT CAN'T POOH
553 | 01/06/2022 | ADM-261 | MRJN-134 | 06 Jan 1400 - 0500 | 15 | 15 | 887265 |  | BHA | FOT | LWD | BHI | 10252 | BAKER HUGHES BHA CONNECTIVITY MALFUNCTION.
555 | 01/06/2022 | ADM-510 | ABSF-224 | 06 Jan 0130 - 0145 | .25 | .25 | 887407 |  | LCIR | CFFM | MDCAP | ARM | 1444 | HAD TOTAL LOSSES AT 1444FT
557 | 01/06/2022 | ADM-656 | ABSF-179 | 03 Jan 0930 - 0500 | 24 | 91.5 | 886845 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR RIG MOVE
559 | 01/06/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 24 | 89.25 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
561 | 01/06/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 1945 | 14.75 | 56.25 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
563 | 01/06/2022 | HI-4 | BRRI-780 | 05 Jan 1800 - 1030 | 5.5 | 16.5 | 887205 |  | WON | WTHR | NA | ARM | 6062 | NON-DP SUPPLY BOATS UNABLE TO WORK TO SUPPLY MUD TO DISPLACE HOLE.
564 | 01/06/2022 | MP-4 | SFNY-672 | 06 Jan 2000 - 0500 | 9 | 9 | 887305 |  | WON | DAY | NA | ARM | 0 | WAIT ON DAYLIGHT TO MOVE RIG FROM ZULF-216/221 PF TO LWHH-15/20, 45 PF.
566 | 01/06/2022 | MP-4 | SFNY-672 | 05 Jan 1700 - 0800 | 3 | 15 | 887226 |  | WON | WTHR | NA | ARM | 0 | ZULF FIELD SERVICES UNABLE TO VISIT ZULF-216/221 PF FOR ACCEPTANCE DUE TO BAD WEATHER
567 | 01/06/2022 | MP-4 | SFNY-672 | 06 Jan 2000 - 0500 | 9 | 9 | 887305 |  | WON | DAY | NA | ARM | 0 | WAIT ON DAYLIGHT TO MOVE RIG FROM ZULF-216/221 PF TO LWHH-15/20, 45 PF.
569 | 01/06/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0500 | 24 | 161 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
571 | 01/06/2022 | NBR-196S | SDGM-1174 | 03 Jan 1830 - 0500 | 24 | 82.5 | 886778 |  | TF | FOT | HGRL | SLH | 13034 | SCHLUMBERGER 7" BALANCED PISTON HYD. SET LH FAILED TO SET.
572 | 01/06/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 800.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
574 | 01/06/2022 | NBR-783S | MDRK-55 | 07 Nov 0500 - 0500 | 12 | 579 | 881591 |  | STUK | IPDF | BHA | BAR | 16256 | PIPE STUCK WHILE POOH DUE TO SUSPECTED MUD CONDITION.
575 | 01/06/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 800.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
577 | 01/06/2022 | SINO-1L | KHRS-340 | 06 Jan 0500 - 0500 | 21.5 | 21.5 | 887405 |  | JF | HERR | NA | TK1 | 4650 | FAILED TO OPEN 9-5/8" HALL EZSV-CR SLIDING VALVE
578 | 01/06/2022 | SINO-32L | SHYB-535 | 06 Jan 2115 - 0500 | 7.75 | 7.75 | 887325 |  | LCIR | FRFM | NA | ARM | 6017 | HAD TOTAL LOSS OF CIRCULATION @ 6017'.
580 | 01/06/2022 | SINO-32L | SHYB-535 | 03 Jan 1800 - 1345 | 8.25 | 58.25 | 886784 |  | LCIR | FRFM | NA | ARM | 5900 | SEVER LOSS OF CIRCULATION 200 BPH
581 | 01/06/2022 | SINO-32L | SHYB-535 | 06 Jan 2115 - 0500 | 7.75 | 7.75 | 887325 |  | LCIR | FRFM | NA | ARM | 6017 | HAD TOTAL LOSS OF CIRCULATION @ 6017'.
583 | 01/06/2022 | SINO-36L | SDGM-490 | 02 Jan 0800 - 2230 | 17.5 | 108 | 886766 |  | STUK | STBG | TBG | TK1 | 10075 | DIFFERENTIALLY STUCK +/- 1409 FEET OFF PLANNED SETTING DEPTH
585 | 01/06/2022 | SND-2006 | UTMN-3135 | 02 Jan 1315 - 0500 | 24 | 111.25 | 886787 |  | BHA | FOT | BIT | RTC | 3069 | WHILE DRILLING 22" H.S, A 450 PSI SUDDEN DROP IN PRESSURE RESULTING IN 22" REED BIT LOST IN HOLE.
587 | 01/06/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 213.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
589 | 01/06/2022 | SNT-025 | SFNY-1007 | 06 Jan 2345 - 0215 | 2.5 | 2.5 | 887345 |  | TF | FOT | WLT | SWL | 0 | WIRELINE TOOL FAILED DURING PRESSURE TEST OF RISER. FOUND ADAPTOR IN LOGGING BHA 'SHORT-CIRCUITED'.
591 | 01/06/2022 | SP-257 | HZEM-141204 | 06 Jan 0900 - 2245 | 13.25 | 13.25 | 887245 |  | RR | FOT | TDS | RIG | 1729 | ALL TDS FUNCTIONS STOPPED.
593 | 01/06/2022 | SSA-101 | BRRI-1145 | 05 Jan 1730 - 2330 | 18 | 29.5 | 886978 |  | TF | FOT | WLT | BAW | 9280 | BAKER GR NOT WORKING AFTER LATCH RCX (PRESSURE / SAMPLING TOOL)
595 | 01/06/2022 | SSA-201 | HRDH-1216 | 05 Jan 2130 - 2145 | 16.75 | 24.25 | 886982 |  | CMT | HERR | NA | NCS | 14717 | NESR UNABLE TO BATCH MIX TAIL SLURRY, DUE PLUG ON THE BULKER SECTION LINE.
596 | 01/06/2022 | SSA-302 | HRDH-1945 | 06 Jan 1900 - 0130 | 6.5 | 6.5 | 887286 |  | TF | FOT | WLT | HWP | 8500 | HALL W/L 2ND RUN TOOLS LOST COMMUNICATION, POH, M/U BACK-UP TOOLS AND RIH BACK.
598 | 01/06/2022 | SSA-302 | HRDH-1945 | 06 Jan 1330 - 1730 | 4 | 4 | 887285 |  | TF | FOT | WLU | HWP | 0 | HALL W/L TRUCK SHUT DOWN @ SURFACE & MECHANIC REMOVE ITS DIESEL FILTERS & FILL TANK WITH NEW DIESEL, POWER UP THE TRUCK AGAIN.
599 | 01/06/2022 | SSA-302 | HRDH-1945 | 06 Jan 1900 - 0130 | 6.5 | 6.5 | 887286 |  | TF | FOT | WLT | HWP | 8500 | HALL W/L 2ND RUN TOOLS LOST COMMUNICATION, POH, M/U BACK-UP TOOLS AND RIH BACK.
601 | 01/06/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0500 | 23 | 140 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
603 | 01/06/2022 | SSA-5891 | HRDH-695 | 05 Jan 1800 - 0500 | 12 | 23 | 886979 |  | DD | UDWL | RSS | SPS | 12200 | SPERRY SUN IS NOT ABLE TO ACHIEVE REQUIRED BUILD UP AS DIRECTIONAL PLAN.
605 | 01/06/2022 | SSA-5970 | HWYH-1257 | 06 Jan 2000 - 0130 | 5.5 | 5.5 | 887365 |  | RR | FOT | PSYS | RIG | 5690 | ROUGHNECK AND EZY TORQUE NOT WORKING.
607 | 01/06/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0500 | 24 | 36.5 | 886984 |  | STUK | STBH | BIT | ARM | 5560 | AT 5,152 FT HOLE PACKED OFF. STRING STALLED AND AND PRUSSRE INCREASE FROM 2000 UP TO 2400 PSI.
609 | 01/06/2022 | T907 | DILM-2 | 06 Jan 2345 - 0415 | 4.5 | 4.5 | 887406 |  | JF | HERR | BHA | RIG | 6339 | DID NOT TAG BOTTOM AS PER RATHOLE DEPTH,REVIEW PIPE TALLYS AND FOUND DISCREPENCIE BETWEEN WHIPSTOCK TALLY AND DRILLING TALLY.
611 | 01/07/2022 | ADC-16 | JAHM-6 | 06 Jan 0100 - 1100 | 6 | 10 | 887425 |  | RR | FOT | TDS | RIG | 126 | WHILE DISCONNECTING TDS FROM HWDP CONNECTION, TDS UPPER IBOP STARTED GETTING LOOSE FROM THE MAIN SHAFT, TIGHTENED, CHANGE GRABBER MOTOR & CALIBRATED TDS TORQUE WITH RIG TONG.
613 | 01/07/2022 | ADC-55L | UTMN-3076 | 07 Jan 0200 - 0500 | 3 | 3 | 887357 |  | STUK | STBH | BHA | TK3 | 10973 | AFTER RACK BACK STAND & WHILE M/UP TDS, FOUND STRING STUCK AFTER CONNECTION.
615 | 01/07/2022 | ADC-56L | UTMN-3011 | 07 Jan 1900 - 0500 | 10 | 10 | 887515 |  | HSEI | UNKN | NA | TK3 | 6210 | WHILE PICKING UP DRILLING JARS THE DRILLING JARS SLIPPED FROM ELEVATORS AND FELL TO THE GROUND
617 | 01/07/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 0500 | 24 | 114 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
619 | 01/07/2022 | ADES-798 | JFYN-13 | 03 Jan 0500 - 0500 | 24 | 102 | 886985 |  | CMT | CPNF | NA | SCM | 16255 | CEMENT PLUG WAS NOT FOUND AFTER WOC FOR 1000 PSI UCA.
621 | 01/07/2022 | ADM-261 | MRJN-134 | 06 Jan 1400 - 0345 | 22.75 | 37.75 | 887265 |  | BHA | FOT | LWD | BHI | 10252 | BAKER HUGHES BHA CONNECTIVITY MALFUNCTION.
623 | 01/07/2022 | ADM-339 | RBYN-54 | 07 Jan 1515 - 0500 | 13.75 | 13.75 | 887546 |  | TF | FOT | ESP | SBA | 3241 | PUMP DISCHARGE MODULE PRESSURE SENSOR READING NOT CORRECT
625 | 01/07/2022 | ADM-656 | ABSF-179 | 07 Jan 0500 - 0500 | 24 | 24 | 887347 |  | UPRA | OTH | NA | RIG | 0 | RIG UNDER UNPLANNED MAINTENANCE TO RENEW 5 YEARS CERTIFICATION FOR DRILLING EQUIPMENT AND RIG CRANES.
627 | 01/07/2022 | AOD-1 | ZULF-693 | 07 Jan 0845 - 0500 | 20.25 | 20.25 | 887514 |  | UPRA | OTH | NA | RIG | 7595 | KOOMEY PUMPS CONTINOUSLY RUNNING TO SUPPLY PRESSURE.
629 | 01/07/2022 | ARO-2001 | BRRI-184 | 07 Jan 1100 - 0500 | 18 | 18 | 887487 |  | TF | FOT | PLUGN | INW | 5881 | INTERWEL ME PLUG MISS SET AT 5881'
631 | 01/07/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 1930 | 14.5 | 103.75 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
633 | 01/07/2022 | DPS-5 | HRDH-2202 | 07 Jan 0830 - 1245 | 4.25 | 4.25 | 887465 |  | WCNT | WCC5 | NA | ARM | 12118 | HAD 4 BBL PIT GAIN WHILE DRLG. , KILL THE WELL.
635 | 01/07/2022 | DQ-50L | HRDH-1497 | 07 Jan 1930 - 0500 | 9.5 | 9.5 | 887547 |  | WCNT | WCC5 | NA | TK2 | 8015 | WELL FLOWING, SUSPECTED A/R "D" FM PENTRATED ACCIDENTALLY.
637 | 01/07/2022 | ENSCO-54 | ABSF-168 | 07 Jan 1900 - 2300 | 4 | 4 | 887516 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER TO OFFLOAD ZERO FLARING EQUIPMENTS.
639 | 01/07/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 21 | 105 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
641 | 01/07/2022 | MP-4 | SFNY-672 | 07 Jan 0500 - 0500 | 24 | 24 | 887545 |  | WO | SRVC | NA | ARM | 0 | WAIT ON SIGNED RIG MOVE MEETING MINUTES TO MOVE RIG FROM ZULF 216/ 221 PF TO LWHH-15/20, 45 PF.
643 | 01/07/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0500 | 24 | 185 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
645 | 01/07/2022 | NA-393S | HWYH-997 | 07 Jan 0000 - 0500 | 5 | 5 | 887358 |  | FISH | FWTS | BHA | ARM | 11915 | AFTER POOH, INSPECT BIT, OBSERVE PART OF 2 ADJACENT BLADES BROKEN.
647 | 01/07/2022 | NBR-196S | SDGM-1174 | 03 Jan 1830 - 1700 | 12 | 94.5 | 886778 |  | TF | FOT | HGRL | SLH | 13034 | SCHLUMBERGER 7" BALANCED PISTON HYD. SET LH FAILED TO SET.
648 | 01/07/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 812.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
650 | 01/07/2022 | NBR-783S | MDRK-55 | 07 Nov 0500 - 0500 | 12 | 591 | 881591 |  | STUK | IPDF | BHA | BAR | 16256 | PIPE STUCK WHILE POOH DUE TO SUSPECTED MUD CONDITION.
651 | 01/07/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 812.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
653 | 01/07/2022 | SCTD-2 | UTMN-1876 | 07 Jan 0000 - 0500 | 5 | 5 | 887517 |  | BHA | FOT | MMOT | SDM | 13100 | MOTOR STALLED ON BOTTOM & SEIZED.
655 | 01/07/2022 | SINO-1L | KHRS-340 | 06 Jan 0500 - 2030 | 15.5 | 37 | 887405 |  | JF | HERR | NA | TK1 | 4650 | FAILED TO OPEN 9-5/8" HALL EZSV-CR SLIDING VALVE
656 | 01/07/2022 | SINO-22 | BRRI-1220 | 07 Jan 0030 - 0145 | 1.25 | 1.25 | 887354 |  | RR | FOT | TDS | RIG | 19681 | TDS ROTATION STOPPED DUE TO MOTOR FAILED.
658 | 01/07/2022 | SINO-22 | BRRI-1220 | 07 Jan 1630 - 0500 | 9.5 | 9.5 | 887348 |  | BHA | FOT | RSS | SDM | 19724 | SDM RSS BHA FAIL TO DROP INCLINATION AS PER GOC INSTRUCTION.
659 | 01/07/2022 | SINO-22 | BRRI-1220 | 07 Jan 0030 - 0145 | 1.25 | 1.25 | 887354 |  | RR | FOT | TDS | RIG | 19681 | TDS ROTATION STOPPED DUE TO MOTOR FAILED.
661 | 01/07/2022 | SINO-32L | SHYB-535 | 06 Jan 2115 - 0500 | 23.5 | 31.25 | 887325 |  | LCIR | FRFM | NA | ARM | 6017 | HAD TOTAL LOSS OF CIRCULATION @ 6017'.
663 | 01/07/2022 | SINO-47 | HRDH-2206 | 07 Jan 0945 - 0500 | 19.25 | 19.25 | 887506 |  | BHA | FOT | LWD | SPS | 15808 | LWD RESISTIVITY TOOL FAILED. POOH TO CHANGE SAME.
665 | 01/07/2022 | SINO-7N | FDHL-608 | 07 Jan 0500 - 0500 | 11 | 11 | 887526 |  | FISH | HERR | WLT | WWL | 5507 | WFD E-LINE RIH 3.5" DRIFT, HELD @ 5507 AT 7" X 4 1/2" X-OVER, ATTEMPTED TO P/U, HAD OVERPULL 2 KLBS ON E-LINE CABLE, LOST ALL BHA IN HOLE.
667 | 01/07/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 237.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
669 | 01/07/2022 | SP-120 | MNIF-189 | 06 Jan 0400 - 0400 | 22.5 | 23.5 | 887507 |  | LCIR | CFFM | MDCAP | ARM | 7355 | ENCOUNTERED SEVERE LOSSES WHILE DRLG 12 1/4" HOLE AT 7355' ( ACROSS SHUAIBAH FM)
671 | 01/07/2022 | SP-257 | HZEM-141204 | 07 Jan 0800 - 0900 | 1 | 1 | 887485 |  | RR | FOT | HSYS | RIG | 3155 | UNABLE TO TORQUE CONNECTION DUE TO IRON ROUGHNECK POWER LOSS.
673 | 01/07/2022 | SSA-51 | MNIF-254 | 07 Jan 0300 - 0400 | 1 | 1 | 887355 |  | CMT | HERR | NA | HCM | 4908 | LATE ON MIXING CEMENT DUE TO BAD ARRANGEMENT FROM HALL ( CHANGE ON RECIPE OF CEMENT PROGRAM ) .
675 | 01/07/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0500 | 22 | 162 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
677 | 01/07/2022 | SSA-5891 | HRDH-695 | 05 Jan 1800 - 1400 | 9 | 31 | 886979 |  | DD | UDWL | RSS | SPS | 12200 | SPERRY SUN IS NOT ABLE TO ACHIEVE REQUIRED BUILD UP AS DIRECTIONAL PLAN.
679 | 01/07/2022 | SSA-5969 | UTMN-3195 | 07 Jan 1830 - 2030 | 2 | 2 | 887486 |  | LROP | IDPR | BHA | SDM | 9937 | CUMULATIVE TIME ON SLB TO DRILL OFF, PICK UP OFF BTM DUE TO HIGHT CHOCKS ON MWD TOOLS.
681 | 01/07/2022 | SSA-5970 | HWYH-1257 | 07 Jan 0900 - 1200 | 3 | 3 | 887349 |  | RR | FOT | CSYS | RIG | 5690 | REPAIR ON MUD SYSTEM, FIXED RUBBER LINE.
683 | 01/08/2022 | ADC-12 | ABQQ-308 | 08 Jan 2300 - 0500 | 6 | 6 | 887586 |  | BHA | FOT | MWD | BHI | 6372 | BHI MWD TOOLS FAILURE
685 | 01/08/2022 | ADC-21 | MHWZ-125104 | 08 Jan 0300 - 0500 | 2 | 2 | 887570 |  | RR | FOT | DWKS | RIG | 2116 | ELECTRONIC CROWN/ FLOOR SAVER ISN'T WORKING
687 | 01/08/2022 | ADC-55L | UTMN-3076 | 07 Jan 0200 - 0500 | 24 | 27 | 887357 |  | STUK | STBH | BHA | TK3 | 10973 | AFTER RACK BACK STAND & WHILE M/UP TDS, FOUND STRING STUCK AFTER CONNECTION.
689 | 01/08/2022 | ADC-56L | UTMN-3011 | 07 Jan 1900 - 0500 | 24 | 34 | 887515 |  | HSEI | UNKN | NA | TK3 | 6210 | WHILE PICKING UP DRILLING JARS THE DRILLING JARS SLIPPED FROM ELEVATORS AND FELL TO THE GROUND
691 | 01/08/2022 | ADC-64L | UTMN-2333 | 08 Jan 1715 - 1745 | .5 | .5 | 887359 |  | TF | FOT | HGRL | BLH | 14390 | UNABLE TO CIRCULATE EXCESS CEMENT AT TOL DUE TO STRING BEING PLUGGED BY WIPER DART WHICH WAS STUCK IN RUNNING TOOL.
693 | 01/08/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 0500 | 24 | 138 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
695 | 01/08/2022 | ADES-174 | HRDH-2184 | 07 Jan 1130 - 0500 | 24 | 41.5 | 887585 |  | FISH | HERR | BHA | RIG | 6100 | DIES OF ADES DRILL COLLAR SLIPS LOST IN HOLE.
697 | 01/08/2022 | ADES-798 | JFYN-13 | 03 Jan 0500 - 0500 | 24 | 126 | 886985 |  | CMT | CPNF | NA | SCM | 16255 | FAILED 2 SIDETRACK CMT PLUGS DUE TO BAD DESIGN. DIRECTIONAL COMPANY COULDN'T TO SIDETRACK IN THE 2ND PLUG DUE TO VERY SOFT CMT.
699 | 01/08/2022 | ADM-339 | RBYN-54 | 07 Jan 1515 - 0500 | 24 | 37.75 | 887546 |  | TF | FOT | ESP | SBA | 3241 | PUMP DISCHARGE MODULE PRESSURE SENSOR READING NOT CORRECT
701 | 01/08/2022 | ADM-656 | ABSF-179 | 07 Jan 0500 - 0500 | 24 | 48 | 887347 |  | UPRA | OTH | NA | RIG | 0 | RIG UNDER UNPLANNED MAINTENANCE TO RENEW 5 YEARS CERTIFICATION FOR DRILLING EQUIPMENT AND RIG CRANES.
703 | 01/08/2022 | AOD-1 | ZULF-693 | 07 Jan 0845 - 0330 | 22.5 | 42.75 | 887514 |  | UPRA | OTH | NA | RIG | 7595 | KOOMEY PUMPS CONTINOUSLY RUNNING TO SUPPLY PRESSURE.
705 | 01/08/2022 | ARO-2001 | BRRI-184 | 07 Jan 1100 - 0930 | 4.5 | 22.5 | 887487 |  | TF | FOT | PLUGN | INW | 5881 | INTERWEL ME PLUG MISS SET AT 5881'
707 | 01/08/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 13.25 | 117 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
709 | 01/08/2022 | DQ-50L | HRDH-1497 | 07 Jan 1930 - 2230 | 17.5 | 27 | 887547 |  | WCNT | WCC5 | NA | TK2 | 8015 | WELL FLOWING, SUSPECTED A/R "D" FM PENTRATED ACCIDENTALLY.
711 | 01/08/2022 | ENS-141 | MRJN-752 | 08 Jan 0045 - 0145 | 1 | 1 | 887569 |  | RR | FOT | DRRK | RIG | 8830 | MALFUNCTION IN PIPE RACKING SYSTEM DUE TO FAILURE IN LOWER DRIVE GEAR BOX .
712 | 01/08/2022 | ENSCO-76 | MRJN-2004 | 08 Jan 1900 - 1915 | .25 | .25 | 887590 |  | RR | FOT | DRRK | RIG | 6195 | BOTH AIR TUGGERS AT MONKEY BOARD WERE NOT WORKING
714 | 01/08/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 20 | 125 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
715 | 01/08/2022 | ENSCO-76 | MRJN-2004 | 08 Jan 0800 - 0815 | .25 | .25 | 887589 |  | RR | FOT | TDS | RIG | 6195 | TOP DRIVE SYSTEM KICKED OUT BREAKER - RE-OCCURING TDS ISSUE
716 | 01/08/2022 | ENSCO-76 | MRJN-2004 | 08 Jan 1900 - 1915 | .25 | .25 | 887590 |  | RR | FOT | DRRK | RIG | 6195 | BOTH AIR TUGGERS AT MONKEY BOARD WERE NOT WORKING
718 | 01/08/2022 | MP-4 | SFNY-672 | 07 Jan 0500 - 0500 | 24 | 48 | 887545 |  | WO | SRVC | NA | ARM | 0 | WAIT ON SIGNED RIG MOVE MEETING MINUTES TO MOVE RIG FROM ZULF 216/ 221 PF TO LWHH-15/20, 45 PF.
720 | 01/08/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0500 | 24 | 209 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
722 | 01/08/2022 | NA-393S | HWYH-997 | 07 Jan 0000 - 0130 | 20 | 25 | 887358 |  | FISH | FWTS | BHA | ARM | 11915 | AFTER POOH, INSPECT BIT, OBSERVE PART OF 2 ADJACENT BLADES BROKEN.
723 | 01/08/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 824.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
725 | 01/08/2022 | NBR-783S | MDRK-55 | 07 Nov 0500 - 0500 | 12 | 603 | 881591 |  | STUK | IPDF | BHA | BAR | 16256 | PIPE STUCK WHILE POOH DUE TO SUSPECTED MUD CONDITION.
726 | 01/08/2022 | NBR-783S | MDRK-55 | 08 Nov 2045 - 1700 | 12 | 824.75 | 881720 |  | BHA | FOT | JARS | SJS | 2000 | OBSERVED LOSS OF STRING WEIGHT WHILE POOH AFTER FREEING STUCK PIPE. FOUND SLB DRILLING JAR PARTED
727 | 01/08/2022 | SA5898 | HRDH-2101 | 08 Jan 1300 - 0500 | 16 | 16 | 887361 |  | WCNT | WCC5 | NA | ARM | 10047 | WHILE DRILLING & TROUBLESHOOTING MWD SIGNAL HAD KICK.
729 | 01/08/2022 | SA5898 | HRDH-2101 | 08 Jan 0500 - 1300 | 8 | 8 | 887360 |  | WCNT | WCC5 | NA | ARM | 10043 | WHILE MAKING CONNECTION HAD KICK.
730 | 01/08/2022 | SA5898 | HRDH-2101 | 08 Jan 1300 - 0500 | 16 | 16 | 887361 |  | WCNT | WCC5 | NA | ARM | 10047 | WHILE DRILLING & TROUBLESHOOTING MWD SIGNAL HAD KICK.
731 | 01/08/2022 | SCTD-2 | UTMN-1876 | 08 Jan 2330 - 0500 | 5.5 | 5.5 | 887588 |  | BHA | FOT | MMOT | RIG | 13198 | LOST COMMUNICATION WITH TOOL
733 | 01/08/2022 | SCTD-2 | UTMN-1876 | 07 Jan 0000 - 1500 | 10 | 15 | 887517 |  | BHA | FOT | MMOT | SDM | 13100 | MOTOR STALLED ON BOTTOM & SEIZED.
734 | 01/08/2022 | SCTD-2 | UTMN-1876 | 08 Jan 2330 - 0500 | 5.5 | 5.5 | 887588 |  | BHA | FOT | MMOT | RIG | 13198 | LOST COMMUNICATION WITH TOOL
736 | 01/08/2022 | SINO-22 | BRRI-1220 | 07 Jan 1630 - 0530 | .5 | 10 | 887348 |  | BHA | FOT | RSS | SDM | 19724 | SDM RSS BHA FAIL TO DROP INCLINATION AS PER GOC INSTRUCTION.
738 | 01/08/2022 | SINO-32L | SHYB-535 | 06 Jan 2115 - 0500 | 24 | 55.25 | 887325 |  | LCIR | FRFM | NA | ARM | 6017 | HAD TOTAL LOSS OF CIRCULATION @ 6017'.
740 | 01/08/2022 | SINO-47 | HRDH-2206 | 07 Jan 0945 - 1500 | 10 | 29.25 | 887506 |  | BHA | FOT | LWD | SPS | 15808 | LWD RESISTIVITY TOOL FAILED. POOH TO CHANGE SAME.
742 | 01/08/2022 | SINO-7N | FDHL-608 | 07 Jan 0500 - 0500 | 24 | 35 | 887526 |  | FISH | HERR | WLT | WWL | 5507 | WFD E-LINE RIH 3.5" DRIFT, HELD @ 5507 AT 7" X 4 1/2" X-OVER, ATTEMPTED TO P/U, HAD OVERPULL 2 KLBS ON E-LINE CABLE, LOST ALL BHA IN HOLE.
744 | 01/08/2022 | SND-2006 | UTMN-3135 | 02 Jan 1315 - 0500 | 24 | 148.75 | 886787 |  | BHA | FOT | BIT | RTC | 3069 | WHILE DRILLING 22" H.S, A 450 PSI SUDDEN DROP IN PRESSURE RESULTING IN 22" REED BIT LOST IN HOLE.
746 | 01/08/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 261.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
748 | 01/08/2022 | SP-120 | MNIF-189 | 08 Jan 0230 - 0500 | 2.5 | 2.5 | 887568 |  | RR | FOT | DWKS | RIG | 7768 | MALFUNCTION IN DRAWWORK ASSIST BRAKE.
749 | 01/08/2022 | SP-257 | HZEM-141204 | 08 Jan 0245 - 0415 | 1.5 | 1.5 | 887587 |  | TF | HERR | TTRQ | FMC | 0 | EXCESS TIME TO RU CASING RUNNING EQUIPMENT.
751 | 01/08/2022 | SP-257 | HZEM-141204 | 08 Jan 1315 - 1415 | 1 | 1 | 887548 |  | RR | FOT | HSYS | RIG | 1858 | EXCESS TIME DUE TO IRON ROUGHNECK SLOW FUNCTION ON BRAKE OUT.
752 | 01/08/2022 | SP-257 | HZEM-141204 | 08 Jan 1545 - 1745 | 2 | 2 | 887565 |  | RR | FOT | HSYS | RIG | 477 | EXCESS TIME TO BREAK OVER TORQUED DRILL COLLAR CONNECTIONS.
753 | 01/08/2022 | SP-257 | HZEM-141204 | 08 Jan 2015 - 2345 | 3.5 | 3.5 | 887566 |  | RR | FOT | TDS | RIG | 0 | ADJUST MISALIGNED TDS TRACK.
754 | 01/08/2022 | SP-257 | HZEM-141204 | 08 Jan 0245 - 0415 | 1.5 | 1.5 | 887587 |  | TF | HERR | TTRQ | FMC | 0 | EXCESS TIME TO RU CASING RUNNING EQUIPMENT.
756 | 01/08/2022 | SP-261 | HZEM-162102 | 08 Jan 0830 - 1100 | 2.5 | 2.5 | 887549 |  | RR | FOT | EDR | RIG | 6553 | IDS DRILLING RECORDER SHUT DOWN - UNABLE TO TRANSMIT REAL TIME DATA TO IOC. CIRCULATE HOLE WHILE RE-BOOTING DRILLING RECORDER AND TROUBLESHOOT DATA TRANSMITION.
758 | 01/08/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0500 | 23.5 | 185.5 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
760 | 01/08/2022 | SSA-5969 | UTMN-3195 | 08 Jan 0500 - 0430 | 23 | 23 | 887362 |  | FISH | FWTS | BHA | RIG | 10062 | LOST 15 KLB FROM STRING WEIGHT WHILE DRILLING 12" HOLE SECTION
762 | 01/08/2022 | SSA-5970 | HWYH-1257 | 08 Jan 1800 - 1900 | 1 | 1 | 887363 |  | RR | FOT | HSYS | RIG | 5690 | REPAIR ON RIG AIR COMPRESSOR, FOUND FUSE BLOWN IN TRANSFORMER.
764 | 01/08/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 4 | 4 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED WHILE CIRCULATE OUT CMT.
766 | 01/09/2022 | ADC-12 | ABQQ-308 | 08 Jan 2300 - 1330 | 8.5 | 14.5 | 887586 |  | BHA | FOT | MWD | BHI | 6372 | BHI MWD TOOLS FAILURE
768 | 01/09/2022 | ADC-21 | MHWZ-125104 | 08 Jan 0300 - 0500 | 6.75 | 8.75 | 887570 |  | RR | FOT | DWKS | RIG | 2116 | ELECTRONIC CROWN/ FLOOR SAVER ISN'T WORKING
770 | 01/09/2022 | ADC-46L | UTMN-3101 | 09 Jan 1730 - 2100 | 3.5 | 3.5 | 887649 |  | WO | WOTO | NA | RIG | 2465 | REQUESTED NEW UPR 5 1/2" PACKER ELEMENT & TOP SEAL REPLACEMENT DELIVERY
772 | 01/09/2022 | ADC-51 | SDGM-1168 | 09 Jan 1230 - 0500 | 16.5 | 16.5 | 887611 |  | BHA | FOT | LWD | SPS | 17315 | LOST COMMUNICATION WITH LWD
774 | 01/09/2022 | ADC-55L | UTMN-3076 | 07 Jan 0200 - 0500 | 24 | 51 | 887357 |  | STUK | STBH | BHA | TK3 | 10415 | AFTER RACK BACK STAND & WHILE M/UP TDS, FOUND STRING STUCK AFTER CONNECTION.
776 | 01/09/2022 | ADC-56L | UTMN-3011 | 07 Jan 1900 - 0500 | 24 | 58 | 887515 |  | HSEI | UNKN | NA | TK3 | 6210 | WHILE PICKING UP DRILLING JARS THE DRILLING JARS SLIPPED FROM ELEVATORS AND FELL TO THE GROUND
778 | 01/09/2022 | ADC-62L | ANDR-764 | 09 Jan 0730 - 1030 | 3 | 3 | 887591 |  | WO | SRVC | NA | SCM | 3009 | SCM CEMENT UNIT CIRCULATING SYSTEM NOT WORKING EFFICIENTLY & COULDN'T PERFORM SECOND STAGE CEMENT JOB. WAIT ON ARRIVAL OF SECOND SCM CMT UNIT.
779 | 01/09/2022 | ADES-174 | HRDH-2184 | 09 Jan 1100 - 1645 | 5.75 | 5.75 | 887626 |  | RR | FOT | TDS | RIG | 6172 | ATTEMPTED TO DRILL 12" HOLE IN SLIDING MODE, UNABLE TO HOLD MOTOR TOOL FACE DUE TO FAILURE IN TDS BRAKE SYSTEM.
781 | 01/09/2022 | ADES-174 | HRDH-2184 | 07 Jan 1130 - 0930 | 4.5 | 46 | 887585 |  | FISH | HERR | BHA | RIG | 6100 | DIES OF ADES DRILL COLLAR SLIPS LOST IN HOLE.
782 | 01/09/2022 | ADES-174 | HRDH-2184 | 09 Jan 1100 - 1645 | 5.75 | 5.75 | 887626 |  | RR | FOT | TDS | RIG | 6172 | ATTEMPTED TO DRILL 12" HOLE IN SLIDING MODE, UNABLE TO HOLD MOTOR TOOL FACE DUE TO FAILURE IN TDS BRAKE SYSTEM.
784 | 01/09/2022 | ADES-798 | JFYN-13 | 03 Jan 0500 - 0500 | 23.5 | 149.5 | 886985 |  | CMT | CPNF | NA | SCM | 16255 | FAILED 2 SIDETRACK CMT PLUGS DUE TO BAD DESIGN. DIRECTIONAL COMPANY COULDN'T TO SIDETRACK IN THE 2ND PLUG DUE TO VERY SOFT CMT.
786 | 01/09/2022 | ADM-261 | MRJN-134 | 09 Jan 1945 - 0000 | 4.25 | 4.25 | 887665 |  | RR | FOT | TDS | RIG | 2315 | WHILE PERFORMING RIG SERVICE ON TDS, NOTICED TDS DOLLY ROLLER HAD FAILED.
788 | 01/09/2022 | ADM-339 | RBYN-54 | 07 Jan 1515 - 0930 | 4.5 | 42.25 | 887546 |  | TF | FOT | ESP | SBA | 3241 | PUMP DISCHARGE MODULE PRESSURE SENSOR READING NOT CORRECT
790 | 01/09/2022 | ADM-656 | ABSF-179 | 07 Jan 0500 - 0500 | 24 | 72 | 887347 |  | UPRA | OTH | NA | RIG | 0 | RIG UNDER UNPLANNED MAINTENANCE TO RENEW 5 YEARS CERTIFICATION FOR DRILLING EQUIPMENT AND RIG CRANES.
792 | 01/09/2022 | ARO-2003 | MNIF-732 | 09 Jan 2045 - 0500 | 8.25 | 8.25 | 887609 |  | RR | FOT | SLIPS | RIG | 20000 | WHILE SERVICE SPINNING WRENCH, DROPPED SCREW DRIVER, WICH BOUNCED INTO WELL.
794 | 01/09/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 24 | 141 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
796 | 01/09/2022 | CG-1 | ZULF-1206 | 09 Jan 0845 - 1030 | 1.75 | 1.75 | 887606 |  | RR | FOT | SWVL | RIG | 4600 | WASH PIPE LEAKING, PUMP HI-VIS, RACK BACK STAND, CIR WITH PUMPING SUB AND RT, CHANGE SEALS
798 | 01/09/2022 | DPS-5 | HRDH-2202 | 09 Jan 0600 - 0900 | 3 | 3 | 887625 |  | WO | SRVC | NA | HWP | 0 | EXCESS TIME FROM HALL. TO M/U W/L LOGGING 1ST RUN.
800 | 01/09/2022 | DQ-50L | HRDH-1497 | 08 Jan 2330 - 1100 | 6 | 11.5 | 887605 |  | STUK | SDIR | RSS | BHI | 7255 | WHILE POOH WIPER TRIP WITH 8-1/2" BHI MRSS BHA GOT STRG STUCK @ 7,255'.
802 | 01/09/2022 | ENS-108 | SFNY-1560 | 09 Jan 1915 - 2330 | 4.25 | 4.25 | 887627 |  | RR | FOT | TDS | RIG | 306 | TOP DRIVE GEAR BOX OIL COOLER LEAKING.
804 | 01/09/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 22.5 | 147.5 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
806 | 01/09/2022 | MP-4 | SFNY-672 | 07 Jan 0500 - 0500 | 24 | 72 | 887545 |  | WO | SRVC | NA | ARM | 0 | WAIT ON SIGNED RIG MOVE MEETING MINUTES TO MOVE RIG FROM ZULF 216/ 221 PF TO LWHH-15/20, 45 PF.
808 | 01/09/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 0500 | 24 | 233 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
810 | 01/09/2022 | NBR-591S | HRDH-1933 | 09 Jan 2330 - 0230 | 2.5 | 2.5 | 887628 |  | RR | FOT | DWKS | RIG | 12075 | OBSERVE KINK ON DRILLINE LINE ON 2ND WRAP LAYER ON DRAWWORKS BY DRILLER SIDE. POOH W/PUMP 2 STD. CIRC WHILE PERFORM SLIP & CUT DRILLING LINE. RIH TO BTM.
812 | 01/09/2022 | PA-785S | QTIF-24 | 09 Jan 0030 - 0200 | 1.5 | 1.5 | 887629 |  | RR | FOT | TDS | RIG | 0 | LEAK FROM TDS TELESCOPIC HYDRAULIC HOSE.
814 | 01/09/2022 | SA5898 | HRDH-2101 | 08 Jan 1300 - 0745 | 2.75 | 18.75 | 887361 |  | WCNT | WCC5 | NA | ARM | 10047 | WHILE DRILLING, HAD SECOND KICK IN JELH REFLECTOR WITH UNEXPECTED HIGH SHUT IN PRESSURES,
816 | 01/09/2022 | SCTD-2 | UTMN-1876 | 08 Jan 2330 - 0500 | 24 | 29.5 | 887588 |  | BHA | FOT | MMOT | RIG | 13198 | LOST COMMUNICATION WITH TOOL
818 | 01/09/2022 | SINO-22 | BRRI-1220 | 07 Jan 1630 - 0500 | 17.5 | 27.5 | 887348 |  | BHA | FOT | RSS | SDM | 19724 | SDM RSS BHA FAIL TO DROP INCLINATION AS PER GOC INSTRUCTION.
820 | 01/09/2022 | SINO-32L | SHYB-535 | 06 Jan 2115 - 0500 | 24 | 79.25 | 887325 |  | LCIR | FRFM | NA | ARM | 6017 | HAD TOTAL LOSS OF CIRCULATION @ 6017'.
822 | 01/09/2022 | SINO-42L | HWYH-537 | 09 Jan 1100 - 0430 | 17.5 | 17.5 | 887666 |  | STUK | HINW | WLT | TK1 | 6596 | RDT STUCK AT SAMPLE POINT# 3 @ 6596' & HOLE CONDITION TRIP .
824 | 01/09/2022 | SINO-43L | HRDH-353 | 09 Jan 1915 - 0330 | 8.25 | 8.25 | 887648 |  | TF | ISEQ | SLICK | MSL | 791 | FAILURE OF SLICK LINE UNIT BREAK.
826 | 01/09/2022 | SINO-7N | FDHL-608 | 07 Jan 0500 - 0200 | 21 | 56 | 887526 |  | FISH | HERR | WLT | WWL | 5507 | WFD E-LINE RIH 3.5" DRIFT, HELD @ 5507 AT 7" X 4 1/2" X-OVER, ATTEMPTED TO P/U, HAD OVERPULL 2 KLBS ON E-LINE CABLE, LOST ALL BHA IN HOLE.
828 | 01/09/2022 | SL-7 | ZULF-1337 | 09 Jan 1615 - 1645 | .5 | .5 | 887650 |  | RR | FPMP | MPMP | RIG | 10918 | MUD PUMPS NOT GETTING FLUID.
830 | 01/09/2022 | SND-2006 | UTMN-3135 | 02 Jan 1315 - 0730 | 2.5 | 151.25 | 886787 |  | BHA | FOT | BIT | RTC | 3069 | WHILE DRILLING 22" H.S, A 450 PSI SUDDEN DROP IN PRESSURE RESULTING IN 22" REED BIT LOST IN HOLE.
832 | 01/09/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 285.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | PRESSURE TEST OF TUBING & TCA FAILED
834 | 01/09/2022 | SP-120 | MNIF-189 | 08 Jan 0230 - 1130 | 6.5 | 9 | 887568 |  | RR | FOT | DWKS | RIG | 7768 | MALFUNCTION IN DRAWWORK ASSIST BRAKE.
836 | 01/09/2022 | SP-257 | HZEM-141204 | 09 Jan 0630 - 0800 | 1.5 | 1.5 | 887607 |  | JF | XTRI | CTRQ | RIG | 209 | EXCESS TIME TAKEN TO MAKE UP SHOE TRACK DUE TO IMPROPER SNUB LINE PLACEMENT.
838 | 01/09/2022 | SP-261 | HZEM-162102 | 09 Jan 0330 - 0430 | 1 | 1 | 887651 |  | JF | XTRI | NA | RIG | 7128 | EXCESSIVE TIME SPENT INSTALLING CEMENT HEAD - CREW NOT PREPARED FOR TASK AT HAND.
840 | 01/09/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0130 | 20 | 205.5 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
841 | 01/09/2022 | SSA-5969 | UTMN-3195 | 09 Jan 2100 - 0500 | 7.5 | 7.5 | 887646 |  | BHA | FOT | MWD | SDM | 9990 | LOST SIGNAL FROM SLB MWD/GR TOOL
843 | 01/09/2022 | SSA-5969 | UTMN-3195 | 08 Jan 0500 - 2000 | 15 | 38 | 887362 |  | FISH | FWTS | BHA | RIG | 10062 | LOST 15 KLB FROM STRING WEIGHT WHILE DRILLING 12" HOLE SECTION
844 | 01/09/2022 | SSA-5969 | UTMN-3195 | 09 Jan 2100 - 0500 | 7.5 | 7.5 | 887646 |  | BHA | FOT | MWD | SDM | 9990 | LOST SIGNAL FROM SLB MWD/GR TOOL
846 | 01/09/2022 | SSA-5970 | HWYH-1257 | 09 Jan 2000 - 2100 | 1 | 1 | 887647 |  | RR | FOT | PSYS | RIG | 5690 | REPAIR ON RIG HPU, ROUGHNECK AND EZY TORQUE NOT WORKING.
848 | 01/09/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 28 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED WHILE CIRCULATE OUT CMT.
850 | 01/10/2022 | ADC-21 | MHWZ-125104 | 08 Jan 0300 - 1300 | 8 | 16.75 | 887570 |  | RR | FOT | DWKS | RIG | 2116 | ELECTRONIC CROWN/ FLOOR SAVER ISN'T WORKING
852 | 01/10/2022 | ADC-51 | SDGM-1168 | 09 Jan 1230 - 0500 | 20.75 | 37.25 | 887611 |  | BHA | FOT | LWD | SPS | 17315 | LOST COMMUNICATION WITH LWD
854 | 01/10/2022 | ADC-56L | UTMN-3011 | 07 Jan 1900 - 0130 | 20.5 | 78.5 | 887515 |  | HSEI | UNKN | NA | TK3 | 6210 | WHILE PICKING UP DRILLING JARS THE DRILLING JARS SLIPPED FROM ELEVATORS AND FELL TO THE GROUND
856 | 01/10/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 0500 | 24 | 186 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
858 | 01/10/2022 | ADES-14 | UTMN-585 | 10 Jan 0500 - 1815 | 13.25 | 13.25 | 887668 |  | TF | FOT | CTRQ | FMC | 5313 | WHILE RUNNING DRIFT FOUND OBSTRUCTION IN TUBING
860 | 01/10/2022 | ADES-798 | JFYN-13 | 03 Jan 0500 - 0500 | 24 | 173.5 | 886985 |  | CMT | CPNF | NA | SCM | 16255 | FAILED 3 SIDETRACK CMT PLUGS DUE TO BAD DESIGN. DIRECTIONAL COMPANY COULDN'T TO SIDETRACK IN THE 2ND PLUG DUE TO VERY SOFT CMT.
862 | 01/10/2022 | ADM-261 | MRJN-134 | 10 Jan 0045 - 0500 | 4.25 | 4.25 | 887653 |  | RR | FOT | SWVL | RIG | 8441 | NOTICED SWIVEL PACKING LEAKING.
863 | 01/10/2022 | ADM-266 | SFNY-489 | 10 Jan 2000 - 0015 | 4.25 | 4.25 | 887617 |  | BHA | FOT | FISHT | NFM | 0 | GS TOOL FAILED TO RETRIEVE WRSSSV, ONCE ON SURFACE GS TOOL DOGS' OBSERVED STUCK SEMI RETRACTED.
865 | 01/10/2022 | ADM-266 | SFNY-489 | 10 Jan 0600 - 1000 | 4 | 4 | 887616 |  | BHA | HERR | MILL | NFM | 55 | NESR THRU TBS DEVIATE APPROVED PLAN & RUN 2.5" MILL INSTEAD OF 2.8" MILL.
866 | 01/10/2022 | ADM-266 | SFNY-489 | 10 Jan 2000 - 0015 | 4.25 | 4.25 | 887617 |  | BHA | FOT | FISHT | NFM | 0 | GS TOOL FAILED TO RETRIEVE WRSSSV, ONCE ON SURFACE GS TOOL DOGS' OBSERVED STUCK SEMI RETRACTED.
868 | 01/10/2022 | ADM-510 | ABSF-226 | 10 Jan 0145 - 0200 | .25 | .25 | 887725 |  | LCIR | CFFM | MDCAP | ARM | 1763 | HAD TOTAL LOSSES @1763FT, SWITCH TO SEA WATER & CONTINUE DRILL PUMPING 85 PCF MUD CUP AT 1BPM
870 | 01/10/2022 | ADM-511 | MRJN-2016 | 09 Jan 0300 - 0500 | 24 | 26 | 887707 |  | JF | DSFT | PKR | WCS | 19244 | DROPPED 1.5'' SETTING BALL TO SET 4-1/2'' ISOLATION PACKERS.FAILED TO SET AS REQUIRED.
872 | 01/10/2022 | ADM-656 | ABSF-179 | 07 Jan 0500 - 0500 | 24 | 96 | 887347 |  | UPRA | OTH | NA | RIG | 0 | RIG UNDER UNPLANNED MAINTENANCE TO RENEW 5 YEARS CERTIFICATION FOR DRILLING EQUIPMENT AND RIG CRANES.
874 | 01/10/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 24 | 165 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
876 | 01/10/2022 | CR-36A | ZULF-2030 | 10 Jan 2045 - 0000 | 3.25 | 3.25 | 887618 |  | RR | FOT | TDS | RIG | 256 | TROUBLE SHOOT ISSUE WITH GRAB ASSY ON TDS.
878 | 01/10/2022 | DPS-43 | SDGM-1187 | 10 Jan 0000 - 0300 | 3 | 3 | 887685 |  | TF | FOT | CRT | WCR | 4785 | WHILE SPACING OUT FOR CIW FMH. CRT CSG INTERNAL SLIPS FAILED TO GRIP THE CASING AND CARRY ITS WT.
880 | 01/10/2022 | DPS-45 | UTMN-3015 | 10 Jan 1200 - 0300 | 15 | 15 | 887619 |  | TF | FOT | HGRL | BLH | 14068 | UNABLE TO PUMP CMT WITH HIGH PRESSURE FLUCTUATIONS RESULTED FROM FAILURE ON BAKER LINER HANGER
881 | 01/10/2022 | ENSCO-54 | ABSF-125 | 10 Jan 1800 - 0500 | 11 | 11 | 887730 |  | WON | DAY | NA | ARM | 0 | WAITING FOR DAY LIGHT TO MOVE RIG.
883 | 01/10/2022 | ENSCO-54 | ABSF-125 | 10 Jan 0500 - 1800 | 13 | 13 | 887729 |  | WON | DAY | NA | ARM | 0 | WAITING FOR RIG MOVE BOATS
884 | 01/10/2022 | ENSCO-54 | ABSF-125 | 10 Jan 1800 - 0500 | 11 | 11 | 887730 |  | WON | DAY | NA | ARM | 0 | WAITING FOR DAY LIGHT TO MOVE RIG.
886 | 01/10/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 24 | 171.5 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
888 | 01/10/2022 | NA-207S | ABMK-701 | 30 Dec 1430 - 1930 | 14.5 | 247.5 | 886564 |  | TF | FOT | CSG | ARM | 11500 | TAGGED OBSTRUCTION INSIDE 7" CSG WHILE RIH WITH 4-1/2" LOWER COMPLETION.
890 | 01/10/2022 | PA-785S | QTIF-24 | 10 Jan 0745 - 0845 | 1 | 1 | 887613 |  | JF | HERR | STRG | RIG | 4785 | LOST TIME ON RIG FOR WRONG TALLY AND DEPTH CONFUSION.
892 | 01/10/2022 | PA-866S | RMYD-1 | 10 Jan 1900 - 0500 | 10 | 10 | 887669 |  | TF | FOT | WLT | SWL | 15046 | FAULTY READINGS WHILE ATTEMPTING TO TAKE PRESSURE POINT# 1 - NOT ABLE TO TAKE PRESSURE POINT.
894 | 01/10/2022 | SCTD-2 | UTMN-1876 | 08 Jan 2330 - 0830 | 3.5 | 33 | 887588 |  | BHA | FOT | MMOT | RIG | 13198 | LOST COMMUNICATION WITH TOOL
896 | 01/10/2022 | SDA | MRJN-737 | 10 Jan 1115 - 1215 | 1 | 1 | 887614 |  | RR | FOT | DRRK | RIG | 13200 | PRS NOT FUNCTIONAL WHILE POOH.
898 | 01/10/2022 | SINO-22 | BRRI-1220 | 07 Jan 1630 - 2330 | 15.5 | 43 | 887348 |  | BHA | FOT | RSS | SDM | 19724 | SDM RSS BHA FAIL TO DROP INCLINATION AS PER GOC INSTRUCTION.
900 | 01/10/2022 | SINO-28L | SHYB-243 | 10 Jan 1730 - 0500 | 11.5 | 11.5 | 887630 |  | JF | CEDE | NA | BCM | 1590 | OBSERVED CEMENT UNIT SUCTION LINES PLUGGED WHILE 18-5/"CSG CMT JOB.
902 | 01/10/2022 | SINO-32L | SHYB-535 | 06 Jan 2115 - 0500 | 24 | 103.25 | 887325 |  | LCIR | FRFM | NA | ARM | 6017 | HAD TOTAL LOSS OF CIRCULATION @ 6017'.
904 | 01/10/2022 | SINO-36L | SDGM-490 | 10 Jan 1830 - 0500 | 10.5 | 10.5 | 887726 |  | RR | FOT | DWKS | RIG | 8400 | SUSPENDED DUE TO ABNORMAL NOISE FROM THE DRAWWORKS.
906 | 01/10/2022 | SINO-42L | HWYH-537 | 09 Jan 1100 - 0230 | 21.5 | 39.5 | 887666 |  | STUK | HINW | WLT | TK1 | 6596 | RDT STUCK AT SAMPLE POINT# 3 @ 6596' & HOLE CONDITION TRIP .
908 | 01/10/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 309.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
909 | 01/10/2022 | SP-257 | HZEM-141204 | 10 Jan 0130 - 0500 | 3.5 | 3.5 | 887655 |  | RR | FOT | HSYS | RIG | 4950 | TROUBLE SHOOT JCC IRON ROUGHNECK PER SP SENIOR ELECTRCIAN.
911 | 01/10/2022 | SP-257 | HZEM-141204 | 10 Jan 1515 - 1800 | 2.75 | 2.75 | 887652 |  | JF | XTRI | BOP | RIG | 4950 | EXCESS TIME TO NU 13-5/8" 10K BOPE.
912 | 01/10/2022 | SP-257 | HZEM-141204 | 10 Jan 0130 - 0500 | 3.5 | 3.5 | 887655 |  | RR | FOT | HSYS | RIG | 4950 | TROUBLE SHOOT JCC IRON ROUGHNECK PER SP SENIOR ELECTRCIAN.
914 | 01/10/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 0500 | 22 | 227.5 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
916 | 01/10/2022 | SSA-5962 | KHRS-1314 | 10 Jan 1900 - 0500 | 10 | 10 | 887654 |  | BHA | FOT | MWD | WDS | 12173 | WFD SURVEY TOOL ( IDS ) LOST COMMUNICATION WHILE DRILLING.
918 | 01/10/2022 | SSA-5971 | UTMN-2302 | 10 Jan 1030 - 1430 | 4 | 4 | 887705 |  | RR | FOT | TDS | RIG | 0 | TOP DRIVE NOT WORKING DUE TO GROUND FAULT & TROUBLESHOOT TDS
920 | 01/10/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 52 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
922 | 01/11/2022 | ADC-14 | HRDH-1804 | 11 Jan 0800 - 0945 | 1.75 | 1.75 | 887731 |  | TF | FOT | WLT | BAW | 200 | AFTER RUN IN HOLE HAD TOOLS FAILURE POOH AND CHANGE TOOLS.
924 | 01/11/2022 | ADC-34 | UTMN-2317 | 11 Jan 0030 - 0500 | 4.5 | 4.5 | 887826 |  | TF | FOT | WLT | BAW | 13107 | BAKER TLC LOGGING TOOL MALFUNCTION
926 | 01/11/2022 | ADC-51 | SDGM-1168 | 09 Jan 1230 - 0230 | 21.5 | 58.75 | 887611 |  | BHA | FOT | LWD | SPS | 17315 | LOST COMMUNICATION WITH LWD
928 | 01/11/2022 | ADC-62L | ANDR-764 | 11 Jan 0045 - 0500 | 4.25 | 4.25 | 887788 |  | RR | FOT | CHK | RIG | 3012 | RIG REPAIR DUE TO 02 MANUAL VLVS UPSTREAM AND BOTH REMOTE CHOKES LEAKAGE ON CHOKE MANIFOLD
930 | 01/11/2022 | ADC-68L | KRSN-705 | 02 Jan 0530 - 1200 | 7 | 193 | 886721 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER & SUSPENDED RIG MOVE OPERATIONS DUE TO HEAVY RAIN IN OLD AND NEW LOCATION. POOR VISIBILITY AND VERY SLIPPERY GROUND/ROAD CONDITIONS.
931 | 01/11/2022 | ADM-261 | MRJN-134 | 11 Jan 1745 - 0500 | 11.25 | 11.25 | 887808 |  | WO | WOTR | NA | ARM | 9125 | IN-BOUND 3RD CREW CHANGE CHOPPER WAS UNEXPECTEDLY CANCELLED, WAIT ON ESSENTIAL ADES PERSONAL TO ARRIVE & CON'T OPERATIONS.
933 | 01/11/2022 | ADM-261 | MRJN-134 | 10 Jan 0045 - 0530 | .5 | 4.75 | 887653 |  | RR | FOT | SWVL | RIG | 8441 | NOTICED SWIVEL PACKING LEAKING.
934 | 01/11/2022 | ADM-261 | MRJN-134 | 11 Jan 1745 - 0500 | 11.25 | 11.25 | 887808 |  | WO | WOTR | NA | ARM | 9125 | IN-BOUND 3RD CREW CHANGE CHOPPER WAS UNEXPECTEDLY CANCELLED, WAIT ON ESSENTIAL ADES PERSONAL TO ARRIVE & CON'T OPERATIONS.
936 | 01/11/2022 | ADM-511 | MRJN-2016 | 09 Jan 0300 - 0500 | 24 | 50 | 887707 |  | JF | DSFT | PKR | WCS | 19244 | DROPPED 1.5'' SETTING BALL TO SET 4-1/2'' ISOLATION PACKERS.FAILED TO SET AS REQUIRED.
938 | 01/11/2022 | ARO-2001 | BRRI-184 | 11 Jan 1100 - 2300 | 6 | 6 | 887811 |  | TF | FOT | WLU | BAW | 0 | BAKER DEPTH ENCODER ARE NOT CONSTANT.
940 | 01/11/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 24 | 189 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
942 | 01/11/2022 | DPS-44 | UTMN-2335 | 11 Jan 2030 - 0030 | 4 | 4 | 887810 |  | RR | FOT | TDS | RIG | 6932 | TDS BLOWER QUIT WORKING. REPLACE & FIX SAME.
944 | 01/11/2022 | ENSCO-54 | ABSF-125 | 11 Jan 1600 - 0500 | 13 | 13 | 887809 |  | WO | SRVC | NA | ARM | 0 | WAIT ON FEILD SERVICESS TO DE-PRESSURE PLATFORM AND SECURE ABSF-124 WELL.
946 | 01/11/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 24 | 195.5 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
948 | 01/11/2022 | EXL-IA | SFNY-4020 | 11 Jan 0030 - 0500 | 4.5 | 4.5 | 887786 |  | UPRA | GRF | RWCS | RIG | 5140 | ATTEMPTED TO FUNCTION BOP TO PRESSURE TEST CEMENT PLUGS. ANNULAR FAILED TO FUNCTION FROM REMOTE PANNEL IN DOG HOUSE. BOTH REMOTE PANNELS NOT FUNCTIONING
950 | 01/11/2022 | MP-1 | LWHH-24 | 11 Jan 0830 - 0930 | 1 | 1 | 887768 |  | JF | DSFT | PKR | BC | 6279 | OBSERVED EXCESSIVE SOW (20 KLBS) WHILE STINGING IN SEAL ASS'Y INTO PBR. PU, OBSERVED OP (25 KLBS). INCREASED SOW LIMIT TO 30 KLBS, NO PROGRESS. INCREASED OP TO 30 KLBS, FREE. RIH & ATTEMPT TO STING IN WITH 20 KLBS SOW LIMIT, LANDED SUCCESSFULLY.
952 | 01/11/2022 | NA-393S | HWYH-997 | 11 Jan 1630 - 0500 | 12.5 | 12.5 | 887827 |  | TF | FOT | FC | BCA | 11757 | MORE IME TO DRILL LC
954 | 01/11/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 23.5 | 23.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
956 | 01/11/2022 | PA-326S | SAHB-32 | 11 Jan 1600 - 1900 | 3 | 3 | 887770 |  | RR | FOT | TDS | RIG | 2575 | HAD OIL LEAKAGE ON TDS .CHANGE MAIN ROTARY SHAFT TOP SEAL ON TDS
958 | 01/11/2022 | PA-866S | RMYD-1 | 10 Jan 1900 - 0500 | 24 | 34 | 887669 |  | TF | FOT | WLT | SWL | 15046 | FAULTY READINGS WHILE ATTEMPTING TO TAKE PRESSURE POINT# 1 - NOT ABLE TO TAKE PRESSURE POINT.
960 | 01/11/2022 | SINO-28L | SHYB-243 | 10 Jan 1730 - 1300 | 8 | 19.5 | 887630 |  | JF | CEDE | NA | BCM | 1590 | OBSERVED CEMENT UNIT SUCTION LINES PLUGGED WHILE 18-5/"CSG CMT JOB.
962 | 01/11/2022 | SINO-36L | SDGM-490 | 10 Jan 1830 - 0500 | 24 | 34.5 | 887726 |  | RR | FOT | DWKS | RIG | 8400 | ABNORMAL NOISE FROM THE DRAWWORKS.
964 | 01/11/2022 | SND-1502 | HWYH-32 | 11 Jan 1000 - 1400 | 4 | 4 | 887805 |  | RR | FOT | TDS | RIG | 4804 | REPAIR TDS.
966 | 01/11/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 333.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
968 | 01/11/2022 | SND-3003 | HRDH-2345 | 11 Jan 1700 - 0500 | 12 | 12 | 887807 |  | BHA | FOT | RSS | SPS | 11882 | SPERRY SUN UNABLE TO ACHIEVE REQUIRED BUILD UP RATE.
970 | 01/11/2022 | SP-257 | HZEM-141204 | 10 Jan 0130 - 0500 | 24 | 27.5 | 887655 |  | RR | FOT | HSYS | RIG | 4950 | TROUBLE SHOOT JCC IRON ROUGHNECK PER SP MANAGEMENT.
972 | 01/11/2022 | SP-261 | HZEM-162102 | 11 Jan 0500 - 0745 | 2.75 | 2.75 | 887769 |  | JF | XTRI | BOP | RIG | 7128 | EXCESSIVE TIME SPENT P/T BOP & INSTALL WEAR BUSHING.
974 | 01/11/2022 | SSA-51 | MNIF-254 | 11 Jan 1130 - 1500 | 3.5 | 3.5 | 887806 |  | RR | ITRP | DWKS | RIG | 5070 | FIX LEAK IN TOP DRIVE GEAR BOX HYDRAULIC OIL TANK .
976 | 01/11/2022 | SSA-5859 | HWYH-1265 | 01 Jan 0600 - 1200 | 7 | 234.5 | 886719 |  | LCIR | UVLC | NA | ARM | 1925 | LOST RETURNS WHEN C/O RATE HOLE DUE TO WET SHOE
978 | 01/11/2022 | SSA-5962 | KHRS-1314 | 10 Jan 1900 - 2300 | 17.5 | 27.5 | 887654 |  | BHA | FOT | MWD | WDS | 12173 | WFD SURVEY TOOL ( IDS ) LOST COMMUNICATION WHILE DRILLING.
980 | 01/11/2022 | SSA-5970 | HWYH-1257 | 11 Jan 1930 - 2100 | 1.5 | 1.5 | 887825 |  | RR | FOT | HSYS | RIG | 5690 | RIG REPAIR ON EZY TORQUE.
982 | 01/11/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0330 | 22.5 | 74.5 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
984 | 01/12/2022 | 088TE | QTIF-279 | 11 Jan 0000 - 0545 | .75 | 5.75 | 887772 |  | TF | FOT | HGRL | BLH | 11708 | LOST TIME ON BAKER LINER HANGER DUE TO 7" WIPER PLUG DID NOT FULLY WIPED CMT AHEAD OF IT & LEFT CMT SHEET ON THE LOW SIDE OF 7" CSG WHICH RESULTED TO TAG CMT LEDGES SHALLOWER & REAM DOWN.
986 | 01/12/2022 | ADC-14 | HRDH-1804 | 12 Jan 0745 - 1915 | 11.5 | 11.5 | 887790 |  | WO | MATL | NA | BAW | 0 | CHECK LOOGING TOOLS AT TD , FLEX LOG TOOL IS NOT WOKING. DECIDED TO RE-RUN WITH FLEX LOG TOOL.
988 | 01/12/2022 | ADC-34 | UTMN-2317 | 11 Jan 0030 - 1500 | 10 | 14.5 | 887826 |  | TF | FOT | WLT | BAW | 13107 | BAKER TLC LOGGING TOOL MALFUNCTION
990 | 01/12/2022 | ADC-52 | HRDH-2312 | 12 Jan 2300 - 0030 | 1.5 | 1.5 | 887906 |  | RR | FOT | DWKS | RIG | 3480 | NOT ABLE TO PICK UP STRING FOR CONNECTION. DRAWWORKS FAILURE DUE TO POWER PROBLEM.
992 | 01/12/2022 | ADC-60 | ABSF-198 | 12 Jan 1800 - 2100 | 3 | 3 | 887888 |  | BHA | FOT | RSS | SDM | 7134 | SDM POWER DRIVE (RSS) UNABLE TO BUILD.
994 | 01/12/2022 | ADC-62L | ANDR-764 | 11 Jan 0045 - 1900 | 14 | 18.25 | 887788 |  | RR | FOT | CHK | RIG | 3012 | RIG REPAIR DUE TO MANUAL VLVS UPSTREAM, BOTH REMOTE CHOKES & MANUAL CHOKE LEAKAGE ON CHOKE MANIFOLD.
996 | 01/12/2022 | ADES-173 | NJYN-90 | 12 Jan 0945 - 1100 | 1.25 | 1.25 | 887846 |  | RR | FOT | CSYS | RIG | 15316 | NOTICED A LOSS IN PUMP PRESSURE.
998 | 01/12/2022 | ADM-261 | MRJN-134 | 11 Jan 1745 - 0845 | 3.75 | 15 | 887808 |  | WO | WOTR | NA | ARN | 9125 | IN-BOUND 3RD CREW CHANGE CHOPPER WAS UNEXPECTEDLY CANCELLED, WAIT ON ESSENTIAL ADES PERSONAL TO ARRIVE & CON'T OPERATIONS.
1000 | 01/12/2022 | ADM-337 | MRJN-900 | 12 Jan 0300 - 0400 | 1 | 1 | 887778 |  | RR | LHFL | HSYS | RIG | 8163 | WHILE RTREIVING DIVERTER OPERATION, OBSERVED J LOCK CONTROL HOSE LEAKING
1002 | 01/12/2022 | ADM-339 | RBYN-54 | 12 Jan 2100 - 0500 | 8 | 8 | 887945 |  | TF | FOT | SLICK | EX1 | 4910 | ATTEMPT TO DISCONNECT FROM THE PX-NIPPLE PRONG WITH JARRING DOWN W/ 3" SB TOOL. UNABLE TO DISCONNECT FROM PRONG.
1004 | 01/12/2022 | ADM-511 | MRJN-2016 | 09 Jan 0300 - 1330 | 8.5 | 58.5 | 887707 |  | JF | DSFT | PKR | WCS | 19244 | DROPPED 1.5'' SETTING BALL TO SET 4-1/2'' ISOLATION PACKERS.FAILED TO SET AS REQUIRED.
1006 | 01/12/2022 | AOD-111 | MRJN-724 | 12 Jan 1030 - 2330 | 13 | 13 | 887907 |  | BHA | FOT | MWD | BHI | 2875 | WHILE DRILLING LOST MWD SIGNAL. TROUBLE SHOOT FAILURE. CHECKED ALL SURFACE EQUIPMENT.
1008 | 01/12/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 24 | 213 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
1010 | 01/12/2022 | DPS-46 | SDGM-1177 | 11 Jan 0400 - 1400 | 9 | 10 | 887774 |  | WO | MATL | NA | SWL | 0 | CAN'T RIH WITH SLB CCL & 4-1/2" EZSV-BP, DUE TO NOT ENOUGH WEIGHT ON SLB TOOL STRING. WAIT ON SLB WIRELINE TO BRING WEIGHT BARS FOR E-LINE OPERATION.
1012 | 01/12/2022 | ENS-108 | SFNY-1560 | 12 Jan 0030 - 0500 | 4.5 | 4.5 | 887887 |  | RR | FOT | TDS | RIG | 0 | RIG REPAIRE ON TOP DRIVE GEAR BOX OIL COOLER DUE TO LEAKING.
1014 | 01/12/2022 | ENSCO-54 | ABSF-125 | 11 Jan 1600 - 0500 | 24 | 37 | 887809 |  | WO | SRVC | NA | ARM | 0 | WAIT ON FEILD SERVICESS TO DE-PRESSURE PLATFORM AND SECURE ABSF-124 WELL.
1016 | 01/12/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 21 | 216.5 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
1018 | 01/12/2022 | EXL-IA | SFNY-4020 | 11 Jan 0030 - 0500 | 24 | 28.5 | 887786 |  | UPRA | GRF | RWCS | RIG | 5140 | ATTEMPTED TO FUNCTION BOP TO PRESSURE TEST CEMENT PLUGS. ANNULAR FAILED TO FUNCTION FROM REMOTE PANNEL IN DOG HOUSE. BOTH REMOTE PANNELS NOT FUNCTIONING
1020 | 01/12/2022 | HI-4 | BRRI-780 | 12 Jan 1400 - 0500 | 15 | 15 | 887845 |  | RR | FOT | TDS | RIG | 8680 | OBSERVE TDS SHOWING GROUND FAULT, ELECTRICIAN INVESTIGATE AND FOUND MALFUNCTIONING TDS MOTOR.
1022 | 01/12/2022 | MP-1 | LWHH-24 | 12 Jan 0700 - 1000 | 3 | 3 | 887927 |  | WH | HERR | TREE | RIG | 0 | OBSERVED X-TREE FLANGED CONNECTIONS LEAKING. TIGHTEN DOWN SAME & PT TO 300 / 2500 PSI, OK.
1024 | 01/12/2022 | NA-393S | HWYH-997 | 11 Jan 1630 - 1930 | 14.5 | 27 | 887827 |  | TF | FOT | FC | BCA | 11757 | MORE TIME TO DRILL LC
1026 | 01/12/2022 | NBR-115S | HRDH-2140 | 12 Jan 0730 - 1000 | 2.5 | 2.5 | 887773 |  | TF | FOT | CTRQ | ZPC | 11311 | WHILE P/U FIRST JOINT OF 9 5/8" LINER THE P/U MACHINE WOULD NOT HOLD THE JOINT IN PLACE.
1028 | 01/12/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 47.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1030 | 01/12/2022 | PA-866S | RMYD-1 | 10 Jan 1900 - 0315 | 22.25 | 56.25 | 887669 |  | TF | FOT | WLT | SWL | 15046 | FAULTY READINGS WHILE ATTEMPTING TO TAKE PRESSURE POINT# 1 - NOT ABLE TO TAKE PRESSURE POINT.
1032 | 01/12/2022 | RBP-50A | HSBH-19 | 12 Jan 0600 - 1730 | 11.5 | 11.5 | 887885 |  | WON | WTHR | NA | ARM | 12400 | UNABLE TO FLOW-BACK WELL DUE TO UNFAVORABLE WIND DIRECTION/SPEED.
1034 | 01/12/2022 | SINO-36L | SDGM-490 | 10 Jan 1830 - 0500 | 24 | 58.5 | 887726 |  | RR | FOT | DWKS | RIG | 8400 | ABNORMAL NOISE FROM THE DRAWWORKS.
1036 | 01/12/2022 | SND-2003 | MNIF-900 | 12 Jan 1415 - 0500 | 14.75 | 14.75 | 887908 |  | BOP | FOT | BOP | RIG | 10854 | ATTEMPT MANY TIMES TO TEST BOP FOUND SBR BONNET LEAK VISUALLY & REPLACED BNT SEALS W/O SUCCESS ( PLAN TO REPLACE BOP DOUBLE RAMS).
1038 | 01/12/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 357.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
1040 | 01/12/2022 | SND-3003 | HRDH-2345 | 11 Jan 1700 - 1600 | 10.5 | 22.5 | 887807 |  | BHA | FOT | RSS | SPS | 11882 | SPERRY SUN UNABLE TO ACHIEVE REQUIRED BUILD UP RATE.
1042 | 01/12/2022 | SP-124 | ABHD-17 | 12 Jan 0300 - 0500 | 2 | 2 | 887779 |  | DSF | FOT | DP | RIG | 2078 | STRING PLUGGED, UNABLE TO CIRCULATE
1044 | 01/12/2022 | SP-229 | ABHD-890 | 10 Jan 2130 - 0130 | 20.5 | 52 | 887905 |  | TF | FOT | BP | INW | 6150 | INTERWELL 9-5/8" RBP FAILED TO PRESSUTRE TEST
1046 | 01/12/2022 | SP-257 | HZEM-141204 | 12 Jan 0500 - 0900 | 4 | 4 | 887865 |  | RR | FOT | HSYS | RIG | 4950 | TROUBLE SHOOT & REPAIR RIG FLOOR HPU.
1048 | 01/12/2022 | SSA-5964 | SDGM-1158 | 12 Jan 0630 - 0500 | 22.5 | 22.5 | 887775 |  | JF | UITE | CORL | WWL | 17503 | STAND BY ON SLB LOGGING CREW AND EQUIPMENT. QUALITY OF LOGS SUPPLIED FROM WFD DID NOT MEET ARAMCO RDD REQUIREMENT.
1050 | 01/12/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0500 | 24 | 158.5 | 887889 |  | BHS | CWEL | NA | ARM | 5560 | HARD BACK-REAMING DUE TO HOLE COLLAPSED
1052 | 01/12/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 19.5 | 94 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1054 | 01/13/2022 | ADC-34 | UTMN-2317 | 11 Jan 0030 - 0500 | 12.5 | 27 | 887826 |  | TF | FOT | WLT | BAW | 13107 | BAKER TLC LOGGING TOOL MALFUNCTION
1056 | 01/13/2022 | ADC-58L | ABHD-170 | 13 Jan 0315 - 0500 | 1.75 | 1.75 | 888045 |  | WON | WTHR | NA | ARM | 16437 | UNABLE TO CONT. SPLICE ESP CABLES DUE TO WATER MOISTURE CAUSED BY HEAVY FOG.
1058 | 01/13/2022 | ADES-889 | HRDH-1282 | 13 Jan 1630 - 1830 | 2 | 2 | 887989 |  | WO | SRVC | NA | RIG | 10351 | OBSERVED LEAK ON STANDPIPE HAMMER UNION CLOSE TO GOOSE NECK WHILE MILLING, ATTEMPT TO FIX SAME, NO SUCCESS.
1060 | 01/13/2022 | ADM-656 | ZULF-106 | 07 Jan 0500 - 0500 | 12 | 108 | 887347 |  | WON | DAY | NA | ARM | 0 | WAIT ON DAY LIGHT TO MOVE RIG FROM ZULF-104/109 TO ABSF- 90/97.
1062 | 01/13/2022 | ARO-2001 | BRRI-184 | 11 Jan 1100 - 0400 | 8.75 | 14.75 | 887811 |  | TF | FOT | WLU | BAW | 0 | BAKER DEPTH ENCODER ARE NOT CONSTANT.
1064 | 01/13/2022 | ARO-3004 | KARN-46 | 13 Jan 1400 - 0500 | 15 | 15 | 887986 |  | WH | HERR | WH | GEP | 10710 | INCORRECT SIZE OF BAKER/GE ENERGIZING RING / SEAL ASSY FOR CURRENT 10-3/4" CASING STUMP TO INSTALL NEW GE 11'' TUBING SPOOL
1066 | 01/13/2022 | CR-36A | ZULF-2030 | 13 Jan 1800 - 1900 | 1 | 1 | 888005 |  | TF | FOT | PUMP | HCM | 235 | CMT HEAD 13 3/8" LEAKING.
1068 | 01/13/2022 | DPS-45 | UTMN-3015 | 10 Jan 1200 - 0500 | 17 | 47.75 | 887619 |  | TF | FOT | HGRL | BLH | 14068 | UNABLE TO PUMP CMT WITH HIGH PRESSURE FLUCTUATIONS RESULTED FROM FAILURE ON BAKER LINER HANGER
1070 | 01/13/2022 | DQ-50L | HRDH-1497 | 13 Jan 1730 - 2100 | 3.5 | 3.5 | 887990 |  | CMT | HFFT | NA | BCM | 8015 | FOUND SOFT CMT WHILE DRLG SHOE TRACK, WOC.
1072 | 01/13/2022 | ENS-108 | SFNY-1560 | 12 Jan 0030 - 0530 | .5 | 5 | 887887 |  | RR | FOT | TDS | RIG | 0 | RIG REPAIRE ON TOP DRIVE GEAR BOX OIL COOLER DUE TO LEAKING.
1074 | 01/13/2022 | ENSCO-54 | ABSF-125 | 11 Jan 1600 - 0500 | 24 | 61 | 887809 |  | WO | SRVC | NA | ARM | 0 | WAIT ON FEILD SERVICESS TO DE-PRESSURE PLATFORM AND SECURE ABSF-124 WELL.
1075 | 01/13/2022 | ENSCO-76 | MRJN-2004 | 13 Jan 0730 - 0800 | .5 | .5 | 887780 |  | RR | FOT | TDS | RIG | 5570 | FOUND TDS PIPE HANDLER DIE BLOCKS LOOSE.
1077 | 01/13/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 20.5 | 237 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
1078 | 01/13/2022 | ENSCO-76 | MRJN-2004 | 13 Jan 0730 - 0800 | .5 | .5 | 887780 |  | RR | FOT | TDS | RIG | 5570 | FOUND TDS PIPE HANDLER DIE BLOCKS LOOSE.
1080 | 01/13/2022 | EXL-IA | SFNY-4020 | 11 Jan 0030 - 0500 | 24 | 52.5 | 887786 |  | UPRA | GRF | RWCS | RIG | 5140 | ATTEMPTED TO FUNCTION BOP TO PRESSURE TEST CEMENT PLUGS. ANNULAR FAILED TO FUNCTION FROM REMOTE PANNEL IN DOG HOUSE. BOTH REMOTE PANNELS NOT FUNCTIONING
1082 | 01/13/2022 | HI-4 | BRRI-780 | 12 Jan 1400 - 0500 | 24 | 39 | 887845 |  | UPRA | GRF | TDS | RIG | 8680 | OBSERVE TDS SHOWING GROUND FAULT, ELECTRICIAN INVESTIGATE AND FOUND MALFUNCTIONING TDS MOTOR.
1084 | 01/13/2022 | NA-18S | SDGM-1030 | 13 Jan 1730 - 1930 | 2 | 2 | 888065 |  | RR | FOT | TDS | RIG | 0 | WHILE DRILLING OBSERVED A LEAK IN TDS SAVER SUB.
1086 | 01/13/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 71.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1088 | 01/13/2022 | RBP-50A | HSBH-19 | 12 Jan 0600 - 1730 | 11.5 | 23 | 887885 |  | WON | WTHR | NA | ARM | 12400 | UNABLE TO FLOW-BACK WELL DUE TO UNFAVORABLE WIND DIRECTION/SPEED.
1090 | 01/13/2022 | SA5898 | HRDH-2101 | 13 Jan 0915 - 0500 | 19.75 | 19.75 | 888006 |  | STUK | STBH | BHA | ARM | 11364 | AFTER MAKING A CONNECTION GOT STRING STUCK DIFFERENTIALLY.
1092 | 01/13/2022 | SDA | MRJN-737 | 13 Jan 0515 - 0545 | .5 | .5 | 888025 |  | RR | FOT | DRRK | RIG | 8696 | TROUBLSHOOT LOWER ARM OF PRS, NOT ABLE TO MOVE IN SINCRONISATION WITH UPPER ARM OF PRS.
1094 | 01/13/2022 | SINO-36L | SDGM-490 | 10 Jan 1830 - 2230 | 17.5 | 76 | 887726 |  | UPRA | GRF | DWKS | RIG | 8400 | ABNORMAL NOISE FROM THE DRAWWORKS.
1096 | 01/13/2022 | SND-2003 | MNIF-900 | 13 Jan 0900 - 2100 | 12 | 12 | 887965 |  | BOP | FOT | BOP | RIG | 10853 | REPLACED 13-5/8"-10M BOP DOUBLE RAMS DUE TO SBR BNT LEAKS.
1098 | 01/13/2022 | SND-2007 | AWTD-100921 | 13 Jan 2100 - 0500 | 8 | 8 | 888105 |  | TF | FOT | WLT | SWL | 20140 | SLB WIRELINE TOOL FAILURE ON TLC LOGGING RUN # 1.
1100 | 01/13/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 381.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
1102 | 01/13/2022 | SP-124 | ABHD-17 | 12 Jan 0300 - 0800 | 3 | 5 | 887779 |  | DSF | FOT | DP | RIG | 2078 | STRING PLUGGED, UNABLE TO CIRCULATE
1104 | 01/13/2022 | SP-58 | BRRI-508 | 13 Jan 2100 - 0500 | 8 | 8 | 887985 |  | JF | HERR | CTAC | SJT | 0 | SUSPEND RIG UP OF 2-7/8" TAQA COIL TUBING EQUIPMENT. WAIT FOR THE HEAVY/OVERSIZED 2-7/8" COIL REEL BE TRANSFERRED ON SPECIAL GOVERNMENT ROAD PERMIT AND CONVEYED THRU ACCEPTED ROAD.
1106 | 01/13/2022 | SSA-202 | QTIF-674 | 13 Jan 2200 - 0500 | 7 | 7 | 887991 |  | BHA | FOT | RSS | SPS | 4150 | SPS 4-3/4" RSS FAILED WHILE RIH AT 4150' MD.
1108 | 01/13/2022 | SSA-5964 | SDGM-1158 | 12 Jan 0630 - 2215 | 17.25 | 39.75 | 887775 |  | JF | UITE | CORL | WWL | 17503 | QUALITY OF LOGS SUPPLIED FROM WFD DID NOT MEET ARAMCO RDD REQUIREMENT.
1110 | 01/13/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0500 | 23.5 | 182 | 887889 |  | BHS | CWEL | NA | ARM | 5560 | HARD BACK-REAMING DUE TO HOLE COLLAPSED.
1112 | 01/13/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 118 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1114 | 01/14/2022 | ADC-58L | ABHD-170 | 13 Jan 0315 - 0715 | 2.25 | 4 | 888045 |  | WON | WTHR | NA | TK3 | 16437 | UNABLE TO CONT. SPLICE ESP CABLES DUE TO WATER MOISTURE CAUSED BY HEAVY FOG.
1116 | 01/14/2022 | ADES-173 | NJYN-90 | 14 Jan 1000 - 1100 | 1 | 1 | 888225 |  | JF | XTRI | CTRQ | WCR | 15620 | EXCESS TIME RIGGING UP P/U MACHINE
1118 | 01/14/2022 | ADM-261 | MRJN-134 | 14 Jan 1300 - 1530 | 2.5 | 2.5 | 888226 |  | RR | FOT | RSSS | RIG | 0 | ELECTRONIC CROWN SAVER NOT WORKING. SUCCESSFULLY TEST CROWN-O-MATIC AND PRODUCE MOC AND RISK ASSESSMENT TO SAFELY CONTINUE OPERATIONS. WAIT FOR APPROVAL FROM ADES OFFICE.
1120 | 01/14/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 0500 | 13.5 | 249 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
1122 | 01/14/2022 | ARO-3004 | KARN-46 | 13 Jan 1400 - 1400 | 9 | 24 | 887986 |  | WH | HERR | WH | GEP | 10710 | INCORRECT SIZE OF BAKER/GE ENERGIZING RING / SEAL ASSY FOR CURRENT 10-3/4" CASING STUMP TO INSTALL NEW GE 11'' TUBING SPOOL
1124 | 01/14/2022 | BCTD-3 | HWYH-1250 | 14 Jan 1230 - 1700 | 4.5 | 4.5 | 888206 |  | BHA | ISEQ | BHA | RIG | 3800 | FAILURE OF MWD TOOLS.
1126 | 01/14/2022 | DPS-45 | UTMN-3015 | 10 Jan 1200 - 1230 | 7.5 | 42.25 | 887619 |  | TF | FOT | HGRL | BLH | 14068 | UNABLE TO PUMP CMT WITH HIGH PRESSURE FLUCTUATIONS RESULTED FROM FAILURE ON BAKER LINER HANGER
1128 | 01/14/2022 | ENS-141 | MRJN-752 | 14 Jan 0845 - 1130 | 2.75 | 2.75 | 888205 |  | RR | FOT | TDS | RIG | 9681 | OBSERVED BROKEN BOLT FROM IBOP ACTUATOR CRANK IN TDS.
1129 | 01/14/2022 | ENSCO-54 | ABSF-142 | 14 Jan 1800 - 0500 | 11 | 11 | 888245 |  | WON | DAY | NA | ARM | 0 | WAITING FOR DAY LIGHT TO MOVE RIG TO ABSF-10/15-142
1131 | 01/14/2022 | ENSCO-54 | ABSF-142 | 13 Jan 0500 - 1800 | 13 | 37 | 888165 |  | WO | ORDS | NA | ARM | 0 | WAITING ON NEW LOCATION ABSF-10/15-142
1132 | 01/14/2022 | ENSCO-54 | ABSF-142 | 14 Jan 1800 - 0500 | 11 | 11 | 888245 |  | WON | DAY | NA | ARM | 0 | WAITING FOR DAY LIGHT TO MOVE RIG TO ABSF-10/15-142
1134 | 01/14/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 24 | 261 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
1136 | 01/14/2022 | EXL-IA | SFNY-4020 | 11 Jan 0030 - 1230 | 7.5 | 60 | 887786 |  | UPRA | GRF | RWCS | RIG | 5140 | ATTEMPTED TO FUNCTION BOP TO PRESSURE TEST CEMENT PLUGS. ANNULAR FAILED TO FUNCTION FROM REMOTE PANNEL IN DOG HOUSE. BOTH REMOTE PANNELS NOT FUNCTIONING
1138 | 01/14/2022 | HI-4 | BRRI-780 | 12 Jan 1400 - 0900 | 4 | 43 | 887845 |  | UPRA | GRF | TDS | RIG | 8680 | OBSERVE TDS SHOWING GROUND FAULT, ELECTRICIAN INVESTIGATE AND FOUND MALFUNCTIONING TDS MOTOR.
1140 | 01/14/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 95.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1142 | 01/14/2022 | PA-70S | TINT-87 | 14 Jan 1900 - 2130 | 2.5 | 2.5 | 888265 |  | WO | MATL | NA | RIG | 14627 | AFTER REPLACING THE DRILLING LINE SPOOL, THE DRILLING LINE SIZE WAS OBSERVED TO BE BIGGER BY 2 MM, INSTEAD OF 38 MM IT IS 40 MM. THIS CAUSE THE DRILLING LINE CLAMP FOR DRAWWORKS NOT TO FIT.
1144 | 01/14/2022 | RBP-50A | HSBH-19 | 12 Jan 0600 - 1730 | 11 | 34 | 887885 |  | WON | WTHR | NA | ARM | 12400 | UNABLE TO FLOW-BACK WELL DUE TO UNFAVORABLE WIND DIRECTION/SPEED.
1146 | 01/14/2022 | SA5898 | HRDH-2101 | 13 Jan 0915 - 1215 | 7.25 | 27 | 888006 |  | DD | HERR | RSS | SPS | 11364 | AFTER MAKING A CONNECTION GOT STRING STUCK DIFFERENTIALLY.
1148 | 01/14/2022 | SCTD-1 | UTMN-1800 | 14 Jan 0200 - 0500 | 3 | 3 | 888305 |  | BHA | FOT | FV | SDM | 280 | AFTER DEPLOY BHA # 2 OBSERVED INCREASE IN INTERNAL PRESSURE AT 280 FT.
1150 | 01/14/2022 | SINO-1L | KHRS-340 | 14 Jan 0230 - 0500 | 2.5 | 2.5 | 888286 |  | JF | HERR | CHK | RIG | 4938 | FAILURE TO TEST RIG SURFACE LINE.
1152 | 01/14/2022 | SND-1502 | HWYH-32 | 14 Jan 1000 - 0500 | 19 | 19 | 888207 |  | BHA | FOT | LWD | WDS | 8392 | WFD LWD TOOLS FAILURE.
1154 | 01/14/2022 | SND-2007 | AWTD-100921 | 13 Jan 2100 - 2030 | 15.5 | 23.5 | 888105 |  | TF | FOT | WLT | SWL | 20140 | SLB WIRELINE TOOL FAILURE ON TLC LOGGING RUN # 1.
1156 | 01/14/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 405.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
1158 | 01/14/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 24 | 24 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | ATTEMPT TO CURE LOSSES WITH LCM PILLS.
1160 | 01/14/2022 | SP-261 | HZEM-162102 | 11 Jan 0500 - 0500 | 6.5 | 9.25 | 887769 |  | DD | UDWL | RSS | SDM | 10100 | RSS NOT BUILDING REQUIRED ANGLE.
1162 | 01/14/2022 | SP-58 | BRRI-508 | 13 Jan 2100 - 1400 | 9 | 17 | 887985 |  | JF | HERR | CTAC | SJT | 0 | SUSPEND RIG UP OF 2-7/8" TAQA COIL TUBING EQUIPMENT. WAIT FOR THE HEAVY/OVERSIZED 2-7/8" COIL REEL BE TRANSFERRED ON SPECIAL GOVERNMENT ROAD PERMIT AND CONVEYED THRU ACCEPTED ROAD.
1164 | 01/14/2022 | SSA-202 | QTIF-674 | 13 Jan 2200 - 1100 | 6 | 13 | 887991 |  | BHA | FOT | RSS | SPS | 4150 | SPS 4-3/4" RSS FAILED WHILE RIH AT 4150' MD.
1166 | 01/14/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0500 | 23.5 | 206.5 | 887889 |  | BHS | CWEL | NA | ARM | 5560 | HARD BACK-REAMING DUE TO HOLE COLLAPSED.
1168 | 01/14/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 23.5 | 141.5 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1170 | 01/15/2022 | 910TE | DMMM-524 | 15 Jan 1400 - 1700 | 3 | 3 | 888369 |  | STUK | STDP | DP | ARM | 11473 | STRING GOT STUCK WHILE DRILL OUT EZSV JUNK INSIDE 7" LINER.
1172 | 01/15/2022 | ADC-17 | ZULF-1257 | 15 Jan 0615 - 1700 | 10.75 | 10.75 | 888307 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER, HIGH WIND SPEED
1174 | 01/15/2022 | ADC-45 | KHRS-82 | 14 Jan 1300 - 0500 | 24 | 40 | 888372 |  | STUK | STBH | BHA | ARM | 7890 | GOT STRING STUCK WHILE WASHING UP STRING AFTER DRILLING @ 7890'.
1176 | 01/15/2022 | ADC-51 | SDGM-1168 | 15 Jan 1315 - 1445 | 1.5 | 1.5 | 888370 |  | RR | FOT | TDS | RIG | 18803 | CHANGE TDS WASH PIPE
1177 | 01/15/2022 | ADC-62L | ANDR-764 | 15 Jan 0300 - 0500 | 2 | 2 | 888371 |  | RR | FOT | FL | RIG | 0 | RIG WORK TO FIX THE CONNECTION BETWEEN BELL NIPPLE & FLOW LINE.
1179 | 01/15/2022 | ADC-62L | ANDR-764 | 15 Jan 1630 - 0300 | 10.5 | 10.5 | 888367 |  | FISH | FWTS | STRG | TK3 | 2249 | WHILE FILLING THE PIPE OBSERVED HOOKLOAD DROPPED F/150 KLBS TO 88 KLBS, DECISION MADE TO POOH 9-5/8" CASING TO SURFACE
1180 | 01/15/2022 | ADC-62L | ANDR-764 | 15 Jan 0300 - 0500 | 2 | 2 | 888371 |  | RR | FOT | FL | RIG | 0 | RIG WORK TO FIX THE CONNECTION BETWEEN BELL NIPPLE & FLOW LINE.
1182 | 01/15/2022 | ADC-68L | KRSN-705 | 15 Jan 1500 - 0100 | 10 | 10 | 888330 |  | WON | WTHR | NA | OTH | 0 | WAIT ON WEATHER DUE TO CONTINOUS HEAVEY RAIN AND HAD MUDDY AND SLIPPRY GROUND.
1184 | 01/15/2022 | ADES-157 | HRDH-698 | 15 Jan 2045 - 0315 | 6.5 | 6.5 | 888365 |  | TF | FOT | WLT | BAW | 0 | WHILE RIH WITH BAKER W/L TOOLS, CCL READ NOISE AT 7,000 FT. POOH AND CHANGE TOOLS.
1186 | 01/15/2022 | ADES-889 | HRDH-1282 | 15 Jan 1030 - 1200 | 1.5 | 1.5 | 888329 |  | BHA | FOT | RSS | BHI | 10371 | RSS NOT RESPONDING TO DOWNLINK
1188 | 01/15/2022 | ADM-656 | ZULF-106 | 07 Jan 0500 - 0500 | 20 | 128 | 887347 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER TO ARRIVE ABSF FIELD SERVICES FOR PLATFORM DEPRESSURIZATION AND FINAL POSITION RIG.
1190 | 01/15/2022 | ARO-3002 | MRJN-818 | 03 Jan 1145 - 2030 | 15.5 | 264.5 | 886886 |  | CMT | CFST | NA | BCM | 7094 | CEMENT PREMATURED VERY EARLY WHICH CAUSE THE STRING TO STUCK JUST AFTER THE STRING GOT RELEASED FORM THE TRANSITION JOINT.
1192 | 01/15/2022 | ARO-3004 | KARN-46 | 15 Jan 0745 - 1430 | 6.75 | 6.75 | 888306 |  | WH | FOT | WH | FME | 0 | MULTIPLE ATTEMPTS TO BAKER/GE PRESSURE TEST 11'' X 13 5/8'' TUBING SPOOL SEAL ASSY ELASTOMER SEAL TO 300/6250 PSI - OK
1194 | 01/15/2022 | DQ-57L | KHRS-581 | 15 Jan 2330 - 0500 | 5.5 | 5.5 | 888331 |  | BHA | FOT | LWD | SPS | 9654 | - HAD UNREASONABLE READINGS FROM RESISTIVITY TOOLS.
1195 | 01/15/2022 | ENSCO-54 | ABSF-142 | 15 Jan 1800 - 0500 | 11 | 11 | 888327 |  | WON | DAY | NA | ARM | 0 | WAIT ON DAY LIGHT TO MOVE & APPROACH PLATFORM.
1197 | 01/15/2022 | ENSCO-54 | ABSF-142 | 15 Jan 1200 - 1800 | 6 | 6 | 888326 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER
1198 | 01/15/2022 | ENSCO-54 | ABSF-142 | 15 Jan 1800 - 0500 | 11 | 11 | 888327 |  | WON | DAY | NA | ARM | 0 | WAIT ON DAY LIGHT TO MOVE & APPROACH PLATFORM.
1200 | 01/15/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 23.5 | 284.5 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
1202 | 01/15/2022 | HI-2 | BRRI-462 | 15 Jan 0615 - 0700 | .75 | .75 | 888325 |  | WON | WTHR | NA | ARM | 16964 | UNFAVORABLE WEATHER CONDITIONS TO COMMENCE FLARING.
1204 | 01/15/2022 | NBR-654S | HRDH-1935 | 15 Jan 1230 - 1330 | 1 | 1 | 888328 |  | DD | HERR | AVDS | SDM | 13432 | SLB REPLACED SENSOR ON STD PIPE GOOSE NECK, NO PRE-PLAN WAS IN PLACE, SHALL BE CHANGED WHILE NEGATIVE TEST TO AVOID RIG ACTIVITY EFFECT.
1206 | 01/15/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 119.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1208 | 01/15/2022 | RBP-50A | HSBH-19 | 12 Jan 0600 - 1730 | 11.5 | 45.5 | 887885 |  | WON | WTHR | NA | ARM | 12400 | UNABLE TO FLOW-BACK WELL DUE TO UNFAVORABLE WIND DIRECTION/SPEED.
1210 | 01/15/2022 | RPKU-2 | UTMN-438 | 15 Jan 1600 - 0500 | 13 | 13 | 888309 |  | TF | FOT | WLT | SWL | 0 | SLB IBC CORROSION LOG DATA NOT ACCURATE
1212 | 01/15/2022 | SCTD-1 | UTMN-1800 | 14 Jan 0200 - 0600 | 1 | 4 | 888305 |  | BHA | FOT | FV | SDM | 280 | AFTER DEPLOY BHA # 2 OBSERVED INCREASE IN INTERNAL PRESSURE AT 280 FT.
1214 | 01/15/2022 | SINO-1L | KHRS-340 | 14 Jan 0230 - 0500 | 24 | 26.5 | 888286 |  | CMT | CPNF | NA | TK1 | 4938 | P/T ON-BTM LINER AFTER DRILL FLOAT EQUIPMENTS FAILED
1216 | 01/15/2022 | SND-1201 | ABJF-1003 | 15 Jan 1745 - 0030 | 6.75 | 6.75 | 888346 |  | RR | FOT | DWKS | RIG | 0 | REPLACE MALFUNCTION BAND BRAKE ON DRAWWORK.
1218 | 01/15/2022 | SND-1502 | HWYH-32 | 14 Jan 1000 - 0145 | 19.75 | 36.75 | 888207 |  | BHA | FOT | LWD | WDS | 8392 | WFD LWD TOOLS FAILURE.
1220 | 01/15/2022 | SND-2007 | AWTD-100921 | 13 Jan 2100 - 1900 | 13 | 36.5 | 888105 |  | TF | FOT | WLT | SWL | 20140 | SLB WIRELINE TOOL FAILURE ON TLC LOGGING RUN # 1.
1222 | 01/15/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 429.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
1224 | 01/15/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 24 | 48 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | ATTEMPT TO CURE LOSSES WITH LCM PILLS.
1226 | 01/15/2022 | SP-261 | HZEM-162102 | 11 Jan 0500 - 0045 | 17.75 | 27 | 887769 |  | DD | UDWL | RSS | SDM | 10100 | RSS NOT BUILDING REQUIRED ANGLE.
1228 | 01/15/2022 | SP-306 | MNIF-865 | 15 Jan 1900 - 0500 | 10 | 10 | 888310 |  | LCIR | FRFM | NA | ARM | 250 | WHILE DRILLING 22" ECOUNTERED TOTAL LOSSES AT 250 FT
1230 | 01/15/2022 | SSA-51 | MNIF-254 | 15 Jan 0400 - 0500 | 1 | 1 | 888366 |  | JF | HERR | CTRQ | GOC | 8486 | LOW KPI FROM AL-GAITH POWER TONG DUE TO FAUILER ON LOW SPEED GEAR .
1232 | 01/15/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 4.5 | 4.5 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1234 | 01/15/2022 | SSA-5892 | MHWZ-5 | 15 Jan 0930 - 0500 | 19.5 | 19.5 | 888368 |  | BHA | FOT | MWD | BHI | 14248 | MALFUNCTION IN MWD TOOL.
1236 | 01/15/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0500 | 23.5 | 230 | 887889 |  | BHS | CWEL | NA | ARM | 5560 | HARD BACK-REAMING DUE TO HOLE COLLAPSED.
1238 | 01/15/2022 | SSA-5972 | NJYN-102 | 15 Jan 1700 - 2015 | 3.25 | 3.25 | 888308 |  | BOP | FOT | BOP | RIG | 6730 | FOUND ANNULAR OPENING CHAMBER SEALS LEAKING DURING FUNCTION TEST.
1240 | 01/15/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 165.5 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1242 | 01/16/2022 | 088TE | QTIF-279 | 16 Jan 0645 - 0500 | 22.25 | 22.25 | 888387 |  | BHA | FOT | RSS | SPS | 15547 | SPS LOST COMMUNICATION BETWEEN RSS & LWD, TROUBLE SHOOT, NO SUCCESS,CHC, POOH TO CHANGE THE FAILED BHA.
1244 | 01/16/2022 | 095TE | MNIF-221 | 16 Jan 1130 - 0500 | 17.5 | 17.5 | 888392 |  | TF | FOT | CTAC | BCT | 24085 | A ISSUE WAS NOTICED IN THE WEIGHT INDICATOR READING ON CT CONTROL , CONT TO RIH MEANWHILE CHECKING THE SOURCE OF PROBLEM. MALFUNCTION HAS BEEN OBSERVED IN INJECTOR LOAD CELL, CHECKED AND FOUND SUPPORT PLATE WAS BROKEN AND BAKER IS UNABLE TO MAKE REPAIR , POOH WITH BAKER 2 3/8" COIL TUBING FROM 24085 FT TO 23990 FT EXPERIENCED OVER PULL AND COIL TUBING GET STUCK.
1246 | 01/16/2022 | ADC-32 | SDGM-1139 | 16 Jan 2330 - 0500 | 5.5 | 5.5 | 888425 |  | RR | FOT | ACDC | RIG | 9150 | DRILLER OBSERVED THAT HE CAN NOT RETOTATE TDS. HE CALL RIG ELECTRITION HE CHECK. HE GOT SLOW ROTATION WITHOUT TORQUE. STOP RUNNING CASING. RIG ELECTITION KEEP TROUBLE SHOOTING.
1248 | 01/16/2022 | ADC-45 | KHRS-82 | 14 Jan 1300 - 0500 | 24 | 64 | 888372 |  | STUK | STBH | BHA | ARM | 7890 | GOT STRING STUCK WHILE WASHING UP STRING AFTER DRILLING @ 7890'.
1249 | 01/16/2022 | ADC-62L | ANDR-764 | 16 Jan 2245 - 0045 | 2 | 2 | 888426 |  | RR | FOT | DWKS | RIG | 45 | RIG REPAIR ON DRAWWORKS, WHILE MAKING UP THE 12-1/4" C/O BHA, MOVED TDS UP TO PICK UP ONE STAND DC, DRAWOWRKS STOP WORKING
1251 | 01/16/2022 | ADC-62L | ANDR-764 | 15 Jan 1630 - 0500 | 22 | 32.5 | 888367 |  | FISH | FWTS | STRG | TK3 | 2249 | WHILE FILLING THE PIPE OBSERVED HOOKLOAD DROPPED F/150 KLBS TO 88 KLBS, DECISION MADE TO POOH 9-5/8" CASING TO SURFACE
1252 | 01/16/2022 | ADC-62L | ANDR-764 | 16 Jan 2245 - 0045 | 2 | 2 | 888426 |  | RR | FOT | DWKS | RIG | 45 | RIG REPAIR ON DRAWWORKS, WHILE MAKING UP THE 12-1/4" C/O BHA, MOVED TDS UP TO PICK UP ONE STAND DC, DRAWOWRKS STOP WORKING
1254 | 01/16/2022 | ADC-70 | BRRI-2230 | 16 Jan 0830 - 0500 | 20.5 | 20.5 | 888385 |  | BHA | FOT | LWD | SDM | 14204 | LWD FAILURE.
1256 | 01/16/2022 | ADM-656 | ZULF-106 | 07 Jan 0500 - 0500 | 24 | 152 | 887347 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER TO ARRIVE ABSF FIELD SERVICES FOR PLATFORM DEPRESSURIZATION AND FINAL POSITION RIG.
1258 | 01/16/2022 | ARO-2001 | BRRI-184 | 14 Jan 2000 - 1530 | 10.5 | 35.5 | 888389 |  | TF | FOT | WLT | BAW | 6829 | BAKER WL UNABLE TO CUT WITH MPC CUTTER.
1260 | 01/16/2022 | ARO-3004 | KARN-46 | 16 Jan 1130 - 1330 | 2 | 2 | 888332 |  | HSEI | UNKN | NA | RIG | 0 | HELD SAFETY STAND DOWN WITH ALL CREW MEMBERS ON INCIDENT WITH IP PINCHING HIS FINGER WHILE USING PIPE WRENCH W/O CORRECT PPE. REVIEW SWA, PPE POLICIES, NEAR-MISS REPORTING AND S/A AND ARO EXPECTATIONS FOR SAFE WORK FROM ALL PAX
1262 | 01/16/2022 | DQ-57L | KHRS-581 | 15 Jan 2330 - 0500 | 22 | 27.5 | 888331 |  | BHA | FOT | LWD | SPS | 9654 | - HAD UNREASONABLE READINGS FROM RESISTIVITY TOOLS.
1263 | 01/16/2022 | ENSCO-54 | ABSF-142 | 16 Jan 1800 - 0500 | 11 | 11 | 888391 |  | WON | DAY | NA | ARM | 0 | WAIT ON DAY LIGHT TO MOVE & APPROACH PLATFORM
1265 | 01/16/2022 | ENSCO-54 | ABSF-142 | 16 Jan 0500 - 1800 | 13 | 13 | 888390 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FEILD SERVICE COULD NOT ABLE TO COME AND DE-PRESSURE PLATFORM ABSF-10/15-142
1266 | 01/16/2022 | ENSCO-54 | ABSF-142 | 16 Jan 1800 - 0500 | 11 | 11 | 888391 |  | WON | DAY | NA | ARM | 0 | WAIT ON DAY LIGHT TO MOVE & APPROACH PLATFORM
1267 | 01/16/2022 | ENSCO-76 | MRJN-2004 | 16 Jan 0230 - 0500 | 2.5 | 2.5 | 888427 |  | TF | FOT | WLU | HWP | 0 | RU HALLIBURTON LOGGING EQUIPMENT, HAD COMMUNICATION ISSUE BETWEEN POWER PACK & LOGGING UNIT, TROUBLESHOOTING SAME, NO SUCCESS.
1269 | 01/16/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0230 | 21.5 | 306 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
1270 | 01/16/2022 | ENSCO-76 | MRJN-2004 | 16 Jan 0230 - 0500 | 2.5 | 2.5 | 888427 |  | TF | FOT | WLU | HWP | 0 | RU HALLIBURTON LOGGING EQUIPMENT, HAD COMMUNICATION ISSUE BETWEEN POWER PACK & LOGGING UNIT, TROUBLESHOOTING SAME, NO SUCCESS.
1272 | 01/16/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 22 | 141.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1274 | 01/16/2022 | RBP-50A | HSBH-19 | 12 Jan 0600 - 1730 | 11 | 56.5 | 887885 |  | WON | WTHR | NA | ARM | 12400 | UNABLE TO FLOW-BACK WELL DUE TO UNFAVORABLE WIND DIRECTION/SPEED.
1276 | 01/16/2022 | SINO-10 | UMTW-1 | 16 Jan 0500 - 1030 | 5.5 | 5.5 | 888388 |  | RR | FOT | HSYS | RIG | 100 | HYROLIC CAT HEAD NOT WORKING UN ABLE TO BRAKE DRILL COLLAES
1278 | 01/16/2022 | SINO-1L | KHRS-340 | 14 Jan 0230 - 0500 | 24 | 50.5 | 888286 |  | CMT | CPNF | NA | TK1 | 4938 | P/T ON-BTM LINER AFTER DRILL FLOAT EQUIPMENTS FAILED
1280 | 01/16/2022 | SND-2003 | MNIF-900 | 16 Jan 0730 - 0500 | 21.5 | 21.5 | 888386 |  | BHA | HERR | WBCL | CRW | 10864 | BHA DROP IN HOLE DUE TO PBL CATCHER SUB BACKED OFF FROM PBL.
1282 | 01/16/2022 | SND-2007 | AWTD-100921 | 13 Jan 2100 - 0500 | 24 | 69.5 | 888105 |  | TF | FOT | WLT | SWL | 20140 | SLB WIRELINE TOOL FAILURE ON TLC LOGGING RUN # 1.
1284 | 01/16/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 453.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
1286 | 01/16/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 24 | 72 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | ATTEMPT TO CURE LOSSES WITH LCM PILLS.
1288 | 01/16/2022 | SP-110 | HWYH-127 | 16 Jan 1430 - 0500 | 14.5 | 14.5 | 888333 |  | WO | STOP | NA | ARM | 0 | WAIT ON RMD TO SHUT IN NEARBY PIW AFFECTING BTM HOLE PRESSURE IN CURRENT WELL.
1290 | 01/16/2022 | SP-261 | HZEM-162102 | 11 Jan 0500 - 0500 | 20.5 | 47.5 | 887769 |  | DD | UDWL | RSS | SDM | 10100 | RSS NOT BUILDING REQUIRED ANGLE.
1292 | 01/16/2022 | SP-306 | MNIF-865 | 15 Jan 1900 - 0500 | 24 | 34 | 888310 |  | LCIR | FRFM | NA | ARM | 250 | WHILE DRILLING 22" HOLE ECOUNTERED TOTAL LOSSES AT 250 FT
1294 | 01/16/2022 | SSA-202 | QTIF-674 | 16 Jan 1915 - 2045 | 1.5 | 1.5 | 888334 |  | BHA | FOT | MWD | SPS | 17975 | TROUBLESHOOT MWD SIGNAL.
1296 | 01/16/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 28 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1298 | 01/16/2022 | SSA-5892 | MHWZ-5 | 15 Jan 0930 - 2000 | 15 | 34 | 888368 |  | BHA | FOT | MWD | BHI | 14248 | MALFUNCTION IN MWD TOOL.
1299 | 01/16/2022 | SSA-5914 | SAHB-360900 | 16 Jan 0300 - 0500 | 2 | 2 | 888466 |  | JF | XTTE | SLICK | INW | 21200 | UNABLE TO REACH PLUG SETTING DEPTH DUE TO SLOW RUNNING SPEED.
1301 | 01/16/2022 | SSA-5914 | SAHB-360900 | 16 Jan 0645 - 2045 | 3.25 | 3.25 | 888445 |  | TF | FOT | CTRQ | MID | 21200 | ITS CASING RUNNING EQUIPMENT FAILURE.
1302 | 01/16/2022 | SSA-5914 | SAHB-360900 | 16 Jan 0300 - 0500 | 2 | 2 | 888466 |  | JF | XTTE | SLICK | INW | 21200 | UNABLE TO REACH PLUG SETTING DEPTH DUE TO SLOW RUNNING SPEED.
1304 | 01/16/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0500 | 23.5 | 253.5 | 887889 |  | BHS | CWEL | NA | ARM | 5560 | HARD BACK-REAMING DUE TO HOLE COLLAPSED.
1306 | 01/16/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 189.5 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1308 | 01/16/2022 | T218 | UTMN-471 | 16 Jan 1500 - 0500 | 14 | 14 | 888465 |  | RR | FOT | TDS | RIG | 7121 | TDS FAILURE.
1309 | 01/17/2022 | 088TE | QTIF-279 | 17 Jan 0245 - 0500 | 2.25 | 2.25 | 888646 |  | BHA | FOT | RSS | SPS | 15555 | SPS RSS NOT RESPONDING TO COMMAND, TROUBLE SHOOT, NO SUCCESS, POOH.
1311 | 01/17/2022 | 088TE | QTIF-279 | 16 Jan 0645 - 0230 | 21 | 43.25 | 888387 |  | BHA | FOT | RSS | SPS | 15547 | SPS LOST COMMUNICATION BETWEEN RSS & LWD, TROUBLE SHOOT, NO SUCCESS,CHC, POOH TO CHANGE THE FAILED BHA.
1312 | 01/17/2022 | 088TE | QTIF-279 | 17 Jan 0245 - 0500 | 2.25 | 2.25 | 888646 |  | BHA | FOT | RSS | SPS | 15555 | SPS RSS NOT RESPONDING TO COMMAND, TROUBLE SHOOT, NO SUCCESS, POOH.
1314 | 01/17/2022 | 095TE | MNIF-221 | 16 Jan 1130 - 0500 | 24 | 41.5 | 888392 |  | TF | FOT | CTAC | BCT | 24085 | A ISSUE WAS NOTICED IN THE WEIGHT INDICATOR READING ON CT CONTROL , CONT TO RIH MEANWHILE CHECKING THE SOURCE OF PROBLEM. MALFUNCTION HAS BEEN OBSERVED IN INJECTOR LOAD CELL, CHECKED AND FOUND SUPPORT PLATE WAS BROKEN AND BAKER IS UNABLE TO MAKE REPAIR , POOH WITH BAKER 2 3/8" COIL TUBING FROM 24085 FT TO 23990 FT EXPERIENCED OVER PULL AND COIL TUBING GET STUCK.
1316 | 01/17/2022 | ADC-32 | SDGM-1139 | 17 Jan 0500 - 0945 | 4.75 | 4.75 | 888470 |  | RR | FOT | TDS | RIG | 9150 | DUE TO HEAVY RAINS TDS MALFUNCTION ( A/C TRACTION MOTOR ( MAIN MOTOR) GROUND FAULT)
1318 | 01/17/2022 | ADC-62L | ANDR-764 | 15 Jan 1630 - 0500 | 24 | 56.5 | 888367 |  | FISH | FWTS | STRG | TK3 | 2249 | WHILE FILLING THE PIPE OBSERVED HOOKLOAD DROPPED F/150 KLBS TO 88 KLBS, DECISION MADE TO POOH 9-5/8" CASING TO SURFACE
1320 | 01/17/2022 | ADC-68L | KRSN-705 | 17 Jan 0530 - 2000 | 14.5 | 14.5 | 888586 |  | WO | STOP | NA | ARM | 0 | WAIT ON REPAIR THE LOCATION PAD DUE TO HEAVY RAIN, ENTRANCE ROAD AND EMRG EXIT ROAD KRSN-705.
1322 | 01/17/2022 | ADC-70 | BRRI-2230 | 16 Jan 0830 - 1000 | 5 | 25.5 | 888385 |  | BHA | FOT | LWD | SDM | 14204 | LWD FAILURE.
1324 | 01/17/2022 | ADM-656 | ABSF-95 | 15 Jan 0900 - 0845 | 3.75 | 47.75 | 888485 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER FOR FIELD SERVICES TO DEPRESSURIZE THE PLATFORM.
1326 | 01/17/2022 | DQ-57L | KHRS-581 | 15 Jan 2330 - 0630 | 1.5 | 29 | 888331 |  | BHA | FOT | LWD | SPS | 9654 | - HAD UNREASONABLE READINGS FROM RESISTIVITY TOOLS.
1328 | 01/17/2022 | ED-85A | SFNY-4060 | 17 Jan 1345 - 1800 | 4.25 | 4.25 | 888545 |  | BHA | ISEQ | MWD | BHI | 0 | EXPIRING BAKER T-PIECE.
1329 | 01/17/2022 | ENSCO-76 | MRJN-2004 | 16 Jan 0230 - 1100 | 6 | 8.5 | 888427 |  | TF | FOT | WLU | HWP | 0 | RU HALLIBURTON LOGGING EQUIPMENT, HAD COMMUNICATION ISSUE BETWEEN POWER PACK & LOGGING UNIT, TROUBLESHOOTING SAME, NO SUCCESS. RESOLVED WITH ELECTRICAL DRAWINGS.
1331 | 01/17/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 18 | 324 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
1332 | 01/17/2022 | ENSCO-76 | MRJN-2004 | 16 Jan 0230 - 1100 | 6 | 8.5 | 888427 |  | TF | FOT | WLU | HWP | 0 | RU HALLIBURTON LOGGING EQUIPMENT, HAD COMMUNICATION ISSUE BETWEEN POWER PACK & LOGGING UNIT, TROUBLESHOOTING SAME, NO SUCCESS. RESOLVED WITH ELECTRICAL DRAWINGS.
1334 | 01/17/2022 | HI-4 | BRRI-780 | 16 Jan 1130 - 0915 | 4.25 | 21.75 | 888469 |  | DRG | PCPF | NA | ARM | 5091 | ATTEMPT TO PASS 5197 FT BIT DEPTH WITH NO SUCCESS. MAGNETS SUSPECTED HANGING UP AT DV PROFILE.
1336 | 01/17/2022 | MP-1 | LWHH-28 | 17 Jan 0800 - 0500 | 21 | 21 | 888546 |  | HSEI | UNKN | NA | BAW | 0 | BAKER WIRELINE DROPPED OBJECT INCIDENT, WIRELINE WEAK LINK TENSION EXCEEDED, TOOLSTRING DROPPED TO RIG FLOOR AND PLATFORM. SHUT-DOWN OPERATIONS FOR INVESTIGATION AND CORRECTIVE ACTION, SLS #3242269. .
1338 | 01/17/2022 | NA-393S | HWYH-997 | 17 Jan 2045 - 2300 | 2.25 | 2.25 | 888645 |  | TF | FOT | CRT | WCR | 10681 | WFD ELEVATOR NOT WORKING PROPERLY
1340 | 01/17/2022 | NBR-783S | MDRK-55 | 17 Jan 2115 - 2330 | 2.25 | 2.25 | 888627 |  | RR | FOT | DWKS | RIG | 10670 | DRAWWORKS BREAK OUT OFF SERVICE
1342 | 01/17/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 165.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1344 | 01/17/2022 | SINO-16 | FDHL-139 | 17 Jan 2130 - 0300 | 5.5 | 5.5 | 888567 |  | TF | FOT | PDHMS | HCO | 0 | CHECK READING AFTER CONNECT PDHMS CABLE FROM SPOOLER TO THE MANDREL, FOUND NO PRESSURE OR TEMPERTURE READING.
1346 | 01/17/2022 | SINO-1L | KHRS-340 | 14 Jan 0230 - 0500 | 24 | 74.5 | 888286 |  | CMT | CPNF | NA | TK1 | 4938 | P/T ON-BTM LINER AFTER DRILL FLOAT EQUIPMENTS FAILED
1348 | 01/17/2022 | SND-1501 | HRDH-431 | 16 Jan 0500 - 0500 | 24 | 48 | 888505 |  | UPRA | OTH | NA | RIG | 10984 | TDS SHOWING OIL LEAKS
1349 | 01/17/2022 | SND-2003 | MNIF-900 | 17 Jan 2300 - 0215 | 3.25 | 3.25 | 888628 |  | RR | FPMP | MPMP | RIG | 10864 | PUMP PRESSURE DROPPING
1351 | 01/17/2022 | SND-2003 | MNIF-900 | 16 Jan 0730 - 1130 | 6.5 | 28 | 888386 |  | BHA | HERR | WBCL | CRW | 10864 | BHA DROP IN HOLE DUE TO PBL CATCHER SUB BACKED OFF FROM PBL.
1352 | 01/17/2022 | SND-2003 | MNIF-900 | 17 Jan 2300 - 0215 | 3.25 | 3.25 | 888628 |  | RR | FPMP | MPMP | RIG | 10864 | PUMP PRESSURE DROPPING
1354 | 01/17/2022 | SND-2007 | AWTD-100921 | 13 Jan 2100 - 0500 | 24 | 93.5 | 888105 |  | TF | FOT | WLT | SWL | 20140 | SLB WIRELINE TOOL FAILURE ON TLC LOGGING RUN # 1.
1356 | 01/17/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 477.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
1358 | 01/17/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 24 | 96 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | ATTEMPT TO CURE LOSSES WITH LCM PILLS.
1360 | 01/17/2022 | SP-258 | HZEM-160614 | 17 Jan 2100 - 0300 | 6 | 6 | 888626 |  | BOP | FOT | BOP | RIG | 5100 | LEAKS IN BONNET SEALS, FLANGES ON CHOKE LINE, AND HYDRAULIC LINE SWIVEL.
1362 | 01/17/2022 | SP-262 | HZEM-141414 | 17 Jan 0115 - 0315 | 2 | 2 | 888605 |  | WO | SRVC | NA | FME | 4933 | FMC TECHNICIAN LEFT LOCATION DURING THE NIGHT AND DID NOT LOG OUT OF RIG LOG BOOK OR NOTIFY FOREMAN THAT HE WAS LEAVING LOCATION.
1364 | 01/17/2022 | SP-306 | MNIF-865 | 15 Jan 1900 - 1630 | 11.5 | 45.5 | 888310 |  | LCIR | FRFM | NA | ARM | 250 | WHILE DRILLING 22" HOLE ECOUNTERED TOTAL LOSSES AT 250 FT
1366 | 01/17/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0430 | 23.5 | 51.5 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1368 | 01/17/2022 | SSA-5891 | HRDH-695 | 17 Jan 2130 - 2345 | 2.25 | 2.25 | 888566 |  | RR | FOT | TDS | RIG | 13607 | HRDRAULIC RAM FOR STAND JUMP ON TDS FAILED
1370 | 01/17/2022 | SSA-5914 | SAHB-360900 | 16 Jan 0300 - 0745 | 2.75 | 4.75 | 888466 |  | JF | XTTE | SLICK | INW | 21200 | UNABLE TO REACH PLUG SETTING DEPTH DUE TO SETTING TIME.
1372 | 01/17/2022 | SSA-5969 | UTMN-3195 | 17 Jan 1330 - 1630 | 3 | 3 | 888585 |  | RR | FOT | TDS | RIG | 10081 | TDS UNABLE TO DISCONNECT FROM HWDP .
1374 | 01/17/2022 | SSA-5970 | HWYH-1257 | 17 Jan 1100 - 1245 | 1.75 | 1.75 | 888525 |  | RR | FOT | HSYS | RIG | 8665 | REPAIR ON STAND PIPE NOV PRESSURE GAUGE, CHANGED SAME.
1376 | 01/17/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0500 | 22 | 275.5 | 887889 |  | BHS | CWEL | NA | ARM | 5560 | HARD BACK-REAMING DUE TO HOLE COLLAPSED.
1378 | 01/17/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 213.5 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1380 | 01/17/2022 | T218 | UTMN-471 | 16 Jan 1500 - 1000 | 3 | 17 | 888465 |  | RR | FOT | TDS | RIG | 7121 | TDS FAILURE.
1382 | 01/18/2022 | 088TE | QTIF-279 | 17 Jan 0245 - 2100 | 16 | 18.25 | 888646 |  | BHA | FOT | RSS | SPS | 15555 | SPS RSS NOT RESPONDING TO COMMAND, TROUBLE SHOOT, NO SUCCESS, POOH.
1384 | 01/18/2022 | 095TE | MNIF-221 | 16 Jan 1130 - 0500 | 24 | 65.5 | 888392 |  | TF | FOT | CTAC | BCT | 24085 | A ISSUE WAS NOTICED IN THE WEIGHT INDICATOR READING ON CT CONTROL , CONT TO RIH MEANWHILE CHECKING THE SOURCE OF PROBLEM. MALFUNCTION HAS BEEN OBSERVED IN INJECTOR LOAD CELL, CHECKED AND FOUND SUPPORT PLATE WAS BROKEN AND BAKER IS UNABLE TO MAKE REPAIR , POOH WITH BAKER 2 3/8" COIL TUBING FROM 24085 FT TO 23990 FT EXPERIENCED OVER PULL AND COIL TUBING GET STUCK.
1386 | 01/18/2022 | ADC-41L | UTMN-3105 | 18 Jan 1530 - 0500 | 12 | 12 | 888669 |  | BOP | ISEQ | BOP | RIG | 2805 | AFTER NIPPLE UP THE 26-3/4" CIW TEST PLUG ASSEMBLY WAS MADE UP AND RAN IN THE HOLE. TEST PLUG WOULD NOT PASS THROUGH TOP OF 26-3/4" 3M 10 FT SPACER SPOOL BELOW BTM RAMS. MULTIPLE ATTEMPTS WERE MADE WITH ORIGINAL TEST PLUG ON LOCATION AND AND ALSO WITH A SECOND TEST PLUG AQUIRED FROM ANOTHER RIG.
1388 | 01/18/2022 | ADC-62L | ANDR-764 | 15 Jan 1630 - 0500 | 24 | 80.5 | 888367 |  | FISH | FWTS | STRG | TK3 | 2249 | WHILE FILLING THE PIPE OBSERVED HOOKLOAD DROPPED F/150 KLBS TO 88 KLBS, DECISION MADE TO POOH 9-5/8" CASING TO SURFACE
1389 | 01/18/2022 | ADES-13 | HRDH-1448 | 18 Jan 1400 - 1630 | 2.5 | 2.5 | 888725 |  | RR | FOT | CSYS | RIG | 8185 | RIG FLOOR STAND PIPE LEAKING FROM CONN.
1391 | 01/18/2022 | ADES-13 | HRDH-1448 | 18 Jan 1630 - 2330 | 6 | 6 | 888634 |  | RR | FOT | DWKS | RIG | 5700 | DRAW WORKS BREAK FAILURE.
1392 | 01/18/2022 | ADES-13 | HRDH-1448 | 18 Jan 1400 - 1630 | 2.5 | 2.5 | 888725 |  | RR | FOT | CSYS | RIG | 8185 | RIG FLOOR STAND PIPE LEAKING FROM CONN.
1394 | 01/18/2022 | ADM-339 | RBYN-57 | 18 Jan 1200 - 1345 | 1.75 | 1.75 | 888632 |  | RR | FOT | TDS | RIG | 7530 | OBSERVED PIPE HANDLER DIE PLATE LOOSE.
1396 | 01/18/2022 | ADM-510 | ABSF-229 | 18 Jan 1145 - 1200 | .25 | .25 | 888666 |  | LCIR | CFFM | MDCAP | ARM | 1767 | WELL IN TOTAL LOSSES @ 1767FT
1398 | 01/18/2022 | ARO-3002 | MRJN-813 | 18 Jan 1800 - 0500 | 11 | 11 | 888706 |  | BOP | FOT | BOP | RIG | 9550 | ATTEMPT TO PRESSURE TEST 13-5/8" ANNULAR, OBSERVE LEAK ON WHIP HOLE.
1400 | 01/18/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 24 | 170.5 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1401 | 01/18/2022 | DQ-57L | KHRS-581 | 18 Jan 0030 - 0100 | .5 | .5 | 888671 |  | WO | SRVC | NA | RIG | 10220 | - ELECTRICAL POWER FAILURE.
1403 | 01/18/2022 | DQ-57L | KHRS-581 | 18 Jan 2330 - 0030 | 1 | 1 | 888670 |  | RR | FOT | SLIPS | RIG | 10220 | - CUMULATIVE POWER TONG FAILURE DUE TO JAWS DIES SLIPPAGE.
1404 | 01/18/2022 | DQ-57L | KHRS-581 | 18 Jan 0030 - 0100 | .5 | .5 | 888671 |  | WO | SRVC | NA | RIG | 10220 | - ELECTRICAL POWER FAILURE.
1406 | 01/18/2022 | ENSCO-76 | MRJN-2004 | 26 Dec 1600 - 0500 | 24 | 348 | 886225 |  | BHA | FOT | BIT | SEC | 6195 | OBSERVE BIT STALLING, HIGH TORQUE, ATTEMPT TO DRILL, UNSUCCESSFUL
1408 | 01/18/2022 | MP-1 | LWHH-28 | 17 Jan 0800 - 1445 | 9.75 | 30.75 | 888546 |  | HSEI | UNKN | NA | BAW | 0 | BAKER WIRELINE DROPPED OBJECT INCIDENT, WIRELINE WEAK LINK TENSION EXCEEDED, TOOLSTRING DROPPED TO RIG FLOOR AND PLATFORM. SHUT-DOWN OPERATIONS FOR INVESTIGATION AND CORRECTIVE ACTION, SLS #3242269. .
1410 | 01/18/2022 | NBR-783S | MDRK-55 | 17 Jan 2115 - 1715 | 1.75 | 4 | 888627 |  | RR | FOT | DWKS | RIG | 10670 | DRAWWORKS BREAK OUT OFF SERVICE
1412 | 01/18/2022 | PA-604S | HRDH-1392 | 18 Jan 2300 - 0415 | 3 | 3 | 888707 |  | RR | LHFL | HSYS | RIG | 475 | OBSERVED LEAK ON HYDRAULIC HOUSE ON TOP DRIVE.
1414 | 01/18/2022 | RBP-50A | HSBH-19 | 12 Jan 0600 - 1730 | 9.25 | 65.75 | 887885 |  | WON | WTHR | NA | ARM | 12400 | UNABLE TO FLOW-BACK WELL DUE TO UNFAVORABLE WIND DIRECTION/SPEED.
1416 | 01/18/2022 | RTC-1 | RMTN-18 | 17 Jan 0100 - 1530 | 10.5 | 14.5 | 888630 |  | TF | FOT | CTAC | NCT | 0 | TARGET TOOLS HAD HYD-OIL LEAKAGE FAILURE.
1418 | 01/18/2022 | SINO-1L | KHRS-340 | 14 Jan 0230 - 0500 | 24 | 98.5 | 888286 |  | CMT | CPNF | NA | TK1 | 4938 | P/T ON-BTM LINER AFTER DRILL FLOAT EQUIPMENTS FAILED
1420 | 01/18/2022 | SINO-22 | BRRI-1220 | 18 Jan 0200 - 0315 | 1.25 | 1.25 | 888727 |  | TF | FOT | CTRQ | MSD | 2750 | JAM UNIT MALFNCTION, TROUBLE SHOOT SAME, OK.
1422 | 01/18/2022 | SINO-32L | SHYB-535 | 18 Jan 0915 - 1600 | 6.75 | 6.75 | 888668 |  | MUD | SLCR | NA | TK2 | 3950 | BHA PLUGGED WITH SALT CREEP .
1424 | 01/18/2022 | SINO-46L | SHYB-223 | 18 Jan 1830 - 0500 | 10.5 | 10.5 | 888726 |  | BHA | FOT | WBCL | SAM | 0 | WHILE L/D SAMAA CLEAN OUT BHA , RECOVERED ONE PIECE OF MAGNET BAR ( 3 CM LONG X 2 CM OD) AND LOST IN HOLE 3 PIECE OF MAGNET BAR SAME DIMENSION 3 CM LONG X 2 CM OD + 2 COVERED CLAMP, ALL ON LOWER MAGNET IN BHA.
1426 | 01/18/2022 | SINO-7N | FDHL-608 | 18 Jan 1900 - 2200 | 3 | 3 | 888635 |  | WO | MATL | NA | RIG | 0 | PERFORMED BOP HOIST LOAD TEST (CAPACITY = 25T), STATIC LOAD TEST WITH 110% LOAD (27.5 T) FAILED, DYNAMIC LOAD TEST WITH 100% LOAD FAILED, OBSERVED HYDRAULIC OIL LEAK FROM HOIST HOLD VALVE, CHANGED HOLD VALVE BY A NEW ONE, LOAD TEST FAILED AGAIN.
1428 | 01/18/2022 | SND-1201 | ABJF-1003 | 18 Jan 0615 - 0715 | 1 | 1 | 888665 |  | WON | WTHR | NA | ARM | 467 | FOGGY WEATHER AND POOR VISIBILITY.
1430 | 01/18/2022 | SND-1501 | HRDH-431 | 16 Jan 0500 - 2000 | 15 | 63 | 888505 |  | UPRA | OTH | NA | RIG | 10984 | TDS SHOWING OIL LEAKS
1432 | 01/18/2022 | SND-1502 | HWYH-32 | 18 Jan 1630 - 0500 | 12.5 | 12.5 | 888636 |  | DD | IDPR | HTMTR | NNN | 10384 | SHOCK SUB BODY WASHED OUT.
1434 | 01/18/2022 | SND-2007 | AWTD-100921 | 13 Jan 2100 - 1700 | 12 | 105.5 | 888105 |  | TF | FOT | WLT | SWL | 20140 | SLB WIRELINE TOOL FAILURE ON TLC LOGGING RUN # 1.
1436 | 01/18/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 0500 | 24 | 501.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
1438 | 01/18/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 24 | 120 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | ATTEMPT TO CURE LOSSES WITH LCM PILLS.
1440 | 01/18/2022 | SSA-101 | BRRI-1145 | 18 Jan 1030 - 0500 | 18.5 | 18.5 | 888685 |  | TF | FOT | WLT | BAW | 9148 | ATTEMPT TROUBLE SHOOT FLUID ID TOOL ON RCX WITHOUT SUCCESS. POOH TO CHANGE THE TOOL.
1442 | 01/18/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 75 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1444 | 01/18/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0500 | 23.5 | 299 | 887889 |  | BHS | CWEL | NA | ARM | 5560 | HARD BACK-REAMING DUE TO HOLE COLLAPSED.
1446 | 01/18/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 237.5 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1448 | 01/18/2022 | T901 | HMYM-433104 | 18 Jan 0630 - 0330 | 21 | 21 | 888728 |  | STUK | PSSW | NA | ARM | 16092 | WHEN POH FOR CONNECTION, STRING BECAME STUCK
1450 | 01/19/2022 | 088TE | QTIF-279 | 17 Jan 0245 - 0430 | 19.5 | 37.75 | 888646 |  | BHA | FOT | RSS | SPS | 15555 | SPS RSS NOT RESPONDING TO COMMAND, TROUBLE SHOOT, NO SUCCESS (BACK TO BACK FAILURE), POOH AND CHANGE COMPANY.
1452 | 01/19/2022 | 095TE | MNIF-221 | 16 Jan 1130 - 0500 | 24 | 89.5 | 888392 |  | TF | FOT | CTAC | BCT | 24085 | A ISSUE WAS NOTICED IN THE WEIGHT INDICATOR READING ON CT CONTROL , CONT TO RIH MEANWHILE CHECKING THE SOURCE OF PROBLEM. MALFUNCTION HAS BEEN OBSERVED IN INJECTOR LOAD CELL, CHECKED AND FOUND SUPPORT PLATE WAS BROKEN AND BAKER IS UNABLE TO MAKE REPAIR , POOH WITH BAKER 2 3/8" COIL TUBING FROM 24085 FT TO 23990 FT EXPERIENCED OVER PULL AND COIL TUBING GET STUCK.
1454 | 01/19/2022 | ADC-50 | SFNY-1174 | 18 Jan 0300 - 0545 | .75 | 2.75 | 888747 |  | WON | WTHR | NA | ARM | 422 | WOW DUE TO HIGH WIND AND RAIN
1456 | 01/19/2022 | ADC-52 | HRDH-2312 | 19 Jan 1430 - 1930 | 4.5 | 4.5 | 888785 |  | RR | FOT | TDS | RIG | 5780 | OBSERVED LEAKING ON "S PIPE" WHICH PLACED BETWEEN TDS WASH PIPE TO KELLY HOSE.
1458 | 01/19/2022 | ADC-62L | ANDR-764 | 15 Jan 1630 - 2230 | 17.5 | 98 | 888367 |  | FISH | FWTS | STRG | TK3 | 2249 | WHILE FILLING THE PIPE OBSERVED HOOKLOAD DROPPED F/150 KLBS TO 88 KLBS, DECISION MADE TO POOH 9-5/8" CASING TO SURFACE
1460 | 01/19/2022 | ADC-66L | HWYH-1223 | 19 Jan 0700 - 0930 | 2.5 | 2.5 | 888814 |  | RR | FOT | CSYS | RIG | 16358 | OBSERVED KELLY HOSE DAMAGED/ WORN.
1462 | 01/19/2022 | ADES-174 | HRDH-2184 | 19 Jan 1630 - 2000 | 3.5 | 3.5 | 888809 |  | TF | FOT | CTRQ | ZPC | 10678 | SUDDEN FAILURE OF ZAMIL PICK UP MACHINE WHILE PICKING UP FIRST 9-5/8" JOINT. RIG CRANE WAS USED TO LIFT CASING JOINTS TO RIG FLOOR UNTIL BACK UP ONE ARRIVED LOCATION WHICH AFFECTED RATE OF RIH AND BY SO EXCESS RIG TIME.
1464 | 01/19/2022 | ADES-798 | JFYN-13 | 19 Jan 0600 - 0800 | 2 | 2 | 888746 |  | JF | XTRI | BOP | RIG | 13518 | EXCESS TIME TO TEST BOP.
1466 | 01/19/2022 | ADM-656 | ABSF-95 | 19 Jan 1600 - 0500 | 13 | 13 | 888846 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER TO OFFLOAD SPUD MATERIAL FROM SPUD VESSEL"AHTS EXCELSIOR" TO COMMENCE WORKOVER OPERATIONS.
1468 | 01/19/2022 | ARO-2003 | MNIF-735 | 19 Jan 0500 - 0500 | 24 | 24 | 888766 |  | WO | SRVC | NA | ARN | 0 | WAITING TO PERFORM SEABED SURVEY.
1470 | 01/19/2022 | ARO-3002 | MRJN-813 | 18 Jan 1830 - 0630 | 1.5 | 12 | 888706 |  | BOP | FOT | BOP | RIG | 9550 | ATTEMPT TO PRESSURE TEST 13-5/8" ANNULAR, OBSERVE LEAK ON WHIP HOLE.
1472 | 01/19/2022 | ARO-3004 | KARN-46 | 19 Jan 0945 - 0500 | 19.25 | 19.25 | 888810 |  | WON | WTHR | NA | ARN | 8770 | WOW DUE TO INABILITY TO WORK BOATS FOR MUD AND CHEMICALS SUPPORT
1474 | 01/19/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 24 | 194.5 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1476 | 01/19/2022 | CR-36A | ZULF-2030 | 19 Jan 1530 - 1600 | .5 | .5 | 888813 |  | RR | FOT | TDS | RIG | 6916 | FAULTY LINK TILT PNEUMATIC DUMP VALVE.
1477 | 01/19/2022 | ENSCO-76 | MRJN-2004 | 19 Jan 1115 - 1145 | .5 | .5 | 888808 |  | RR | FOT | TDS | RIG | 6065 | TOP DRIVE AUTO-BRAKE FAILED FUNCTION PROPERLY, CAUSED TDS TO TRIP BREAKER, DRILLER COULD NOT CONTROL DRILL STRING
1479 | 01/19/2022 | ENSCO-76 | MRJN-2004 | 19 Jan 0030 - 0100 | .5 | .5 | 888772 |  | RR | FOT | PSYS | RIG | 6265 | ENGINE #2 OVERSPEED BLACKOUT WHILE ON BOTTOM
1480 | 01/19/2022 | ENSCO-76 | MRJN-2004 | 19 Jan 1115 - 1145 | .5 | .5 | 888808 |  | RR | FOT | TDS | RIG | 6065 | TOP DRIVE AUTO-BRAKE FAILED FUNCTION PROPERLY, CAUSED TDS TO TRIP BREAKER, DRILLER COULD NOT CONTROL DRILL STRING
1482 | 01/19/2022 | EXL-IA | SFNY-4050 | 19 Jan 1000 - 0500 | 18 | 18 | 888773 |  | WON | WTHR | NA | ARN | 0 | UNABLET TO DEPLOY DIVERS TO PERFORM CONDUCTOR HEIGHT CHECK AND LOCATION BOUY.
1484 | 01/19/2022 | HI-9 | MRJN-228 | 18 Jan 0500 - 0900 | 4 | 28 | 888673 |  | TF | FOT | WPSTK | WI3 | 9378 | WIS TRI-MILL ASSEMBLY UNABLE TO MILL AND DRILL RAT HOLE DUE TO NO MILLING PROGRESS.
1486 | 01/19/2022 | NA-393S | HWYH-997 | 19 Jan 2030 - 0345 | 7.25 | 7.25 | 888812 |  | TF | FOT | SLICK | SPL | 10681 | WHILE POOH W/ 3.688" BRUSH AT 1,800', SAPESCO SLICK LINE UNIT SHUT DOWN. UNIT ENGINE NOT WORKING.
1488 | 01/19/2022 | NBR-115S | HRDH-2140 | 19 Jan 2030 - 2230 | 2 | 2 | 888825 |  | BOP | HERR | BOP | RIG | 11311 | EXCESS TIME TO NIPPLE UP BOP.
1490 | 01/19/2022 | NBR-304S | HRDH-2260 | 19 Jan 1500 - 1630 | 1.5 | 1.5 | 888811 |  | TF | FOT | CTRQ | SPR | 7871 | SPIDER SLIP SEGMENT FAILURE AND CRT DIES NOT GRIPPING
1492 | 01/19/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 213.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1494 | 01/19/2022 | SCTD-2 | UTMN-1876 | 19 Jan 1430 - 2200 | 3.5 | 3.5 | 888847 |  | RR | FOT | TDS | RIG | 0 | INJECTOR DEPTH SENSORS & LOAD CELLS GIVING WRONG READINGS.
1496 | 01/19/2022 | SDA | MRJN-737 | 19 Jan 1500 - 2100 | 6 | 6 | 888770 |  | STUK | HINW | SLICK | SPL | 5350 | WHIL POOH SSD'S SHIFTING TOOL GOT STUCK AT 5350.
1498 | 01/19/2022 | SINO-10 | UMTW-1 | 18 Jan 1215 - 1130 | 3.5 | 16.25 | 888745 |  | STUK | LCRW | STRG | ARM | 340 | WHILE DRLG. 28" HOLE HAD COMPLETE LOSS OF RETURNS, PICK THE STRING 50 FT OFF BTM WHERE THE HOLE COLLAPSED AND STRING STUCK
1500 | 01/19/2022 | SINO-1L | KHRS-340 | 14 Jan 0230 - 0500 | 24 | 122.5 | 888286 |  | CMT | CPNF | NA | TK1 | 4938 | P/T ON-BTM LINER AFTER DRILL FLOAT EQUIPMENTS FAILED
1502 | 01/19/2022 | SINO-22 | BRRI-1220 | 18 Jan 0200 - 2115 | 1 | 2.25 | 888727 |  | TF | FOT | CTRQ | MSD | 2750 | JAM UNIT MALFUNCTION, TROUBLE SHOOT SAME
1504 | 01/19/2022 | SINO-46L | SHYB-223 | 18 Jan 1830 - 0500 | 24 | 34.5 | 888726 |  | BHA | FOT | WBCL | SAM | 0 | WHILE L/D SAMAA CLEAN OUT BHA , RECOVERED ONE PIECE OF MAGNET BAR ( 3 CM LONG X 2 CM OD) AND LOST IN HOLE 3 PIECE OF MAGNET BAR SAME DIMENSION 3 CM LONG X 2 CM OD + 2 COVERED CLAMP, ALL ON LOWER MAGNET IN BHA.
1506 | 01/19/2022 | SINO-7N | FDHL-608 | 18 Jan 1600 - 2200 | 3 | 9 | 888635 |  | WO | MATL | NA | RIG | 0 | PERFORMED BOP HOIST LOAD TEST (CAPACITY = 25T), STATIC LOAD TEST WITH 110% LOAD (27.5 T) FAILED, DYNAMIC LOAD TEST WITH 100% LOAD FAILED, OBSERVED HYDRAULIC OIL LEAK FROM HOIST HOLD VALVE, CHANGED HOLD VALVE BY A NEW ONE, LOAD TEST FAILED AGAIN.
1508 | 01/19/2022 | SND-2004 | BRRI-528 | 19 Jan 1100 - 1545 | 2 | 2 | 888774 |  | BB | PCPF | NA | ARM | 210 | BALLED UP BIT DUE TO STICKY FORMATION AND LOW PUMP RATE. TRIP OUT TO CLEAN THE BIT
1510 | 01/19/2022 | SND-2007 | AWTD-100921 | 19 Jan 1245 - 1400 | 1.25 | 1.25 | 888771 |  | RR | FOT | TDS | RIG | 3256 | LEAKING WASHPIPE ON TDS.
1512 | 01/19/2022 | SND-2009 | ZMLH-15 | 29 Dec 0730 - 1800 | 13 | 514.5 | 886487 |  | TF | FOT | SEAL | HCO | 14319 | HALLIBURTON ANCHOR COMPRESSION PACKER NOT HOLD PRESS WHILE PT TCA & TBG
1514 | 01/19/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 24 | 144 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | ATTEMPT TO CURE LOSSES WITH LCM PILLS.
1516 | 01/19/2022 | SNT-025 | SFNY-1007 | 19 Jan 1300 - 0500 | 16 | 16 | 888817 |  | WO | WOPF | NA | AP2 | 0 | RIG WAITING ON APPROVAL FROM SFNY PRODUCTION ENGINEERING TO COMMENCE FLOW BACK OPERATIONS
1518 | 01/19/2022 | SP-58 | BRRI-508 | 19 Jan 1145 - 0500 | 17.25 | 17.25 | 888767 |  | TF | FOT | PLUGN | INW | 13160 | INTERWELL PUMP THROUGH PLUG DIDN'T SET.
1520 | 01/19/2022 | SSA-101 | BRRI-1145 | 18 Jan 1030 - 1600 | 11 | 29.5 | 888685 |  | TF | FOT | WLT | BAW | 9148 | ATTEMPT TROUBLE SHOOT FLUID ID TOOL ON RCX WITHOUT SUCCESS. POOH TO CHANGE THE TOOL.
1522 | 01/19/2022 | SSA-102 | QTIF-699 | 19 Jan 2230 - 0500 | 6.5 | 6.5 | 888826 |  | BHA | FOT | PWD | SPS | 4320 | NO SEAL OF GEO-TAP (FPWD) TOOL PROBE WHILE FUNCTION TEST ON CSD HOLE.
1524 | 01/19/2022 | SSA-202 | QTIF-674 | 19 Jan 2345 - 0500 | 3 | 3 | 888845 |  | BHA | FOT | MWD | SPS | 21400 | TROUBLESHOOT LWD SIGNAL.
1526 | 01/19/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 98.5 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1528 | 01/19/2022 | SSA-5914 | SAHB-360900 | 19 Jan 0600 - 0730 | 1.5 | 1.5 | 888816 |  | RR | FOT | CSYS | RIG | 21200 | TROUBLESHOOT ON IBOP TO OPEN.
1530 | 01/19/2022 | SSA-5971 | UTMN-2302 | 05 Jan 1630 - 0200 | 20.5 | 319.5 | 887889 |  | BHS | CWEL | NA | ARM | 5560 | HARD BACK-REAMING DUE TO HOLE COLLAPSED.
1532 | 01/19/2022 | SSA-5972 | NJYN-102 | 19 Jan 0330 - 0400 | .5 | .5 | 888815 |  | CMT | HERR | NA | SJC | 6767 | CEMENT LINE FROM SILO TO PUMP TRUCK PLUGGED AT START OF JOB.
1534 | 01/19/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 261.5 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1536 | 01/20/2022 | 095TE | MNIF-221 | 16 Jan 1130 - 0500 | 24 | 113.5 | 888392 |  | TF | FOT | CTAC | BCT | 24085 | A ISSUE WAS NOTICED IN THE WEIGHT INDICATOR READING ON CT CONTROL , CONT TO RIH MEANWHILE CHECKING THE SOURCE OF PROBLEM. MALFUNCTION HAS BEEN OBSERVED IN INJECTOR LOAD CELL, CHECKED AND FOUND SUPPORT PLATE WAS BROKEN AND BAKER IS UNABLE TO MAKE REPAIR , POOH WITH BAKER 2 3/8" COIL TUBING FROM 24085 FT TO 23990 FT EXPERIENCED OVER PULL AND COIL TUBING GET STUCK.
1538 | 01/20/2022 | ADC-36 | SDGM-1186 | 20 Jan 0030 - 0500 | 4.5 | 4.5 | 888824 |  | TF | FOT | HGRL | WIN | 13833 | AFTER SETTING 7" X 9.5/8" INNOVEX LINER HANGER, PRESSURED UP TO 2600 PSI TO RELEASE RUNNING TOOL WITHOUT SUCCESS. PRESSURED-UP IN STAGES TO MAXIMIM OF 4800 PSI - NO SUCCESS. UNSET HANGER WITH 35K O/PULL ; POH WITH 7" LINER.
1540 | 01/20/2022 | ADC-50 | SFNY-1174 | 20 Jan 1615 - 1715 | 1 | 1 | 888965 |  | TF | FOT | SLICK | EX1 | 0 | ATTEMPT TO START UP SLICKLINE UNIT WITH NO SUCCESS.
1542 | 01/20/2022 | ADC-55L | UTMN-3076 | 20 Jan 1000 - 1800 | 8 | 8 | 889006 |  | CMT | HERR | NA | TK3 | 10973 | AFTER PUMPING THE SPACER FOR THE 13-3/8" 2ND STAGE CMT JOB, OBSERVED CONTAMINATED 108 PCF CMT/MUD IN SHAKERS. STOPPED OPERATION AND INVISTIGATE. FOUND CONTAMINATED CMT/MUD IN ACTIVE SYSTEM.
1544 | 01/20/2022 | ADM-337 | MRJN-900 | 20 Jan 0330 - 0500 | 1.5 | 1.5 | 889005 |  | TF | FOT | WLT | SWL | 8286 | WHILE SCHLUMBERGER WL RECORDING PRESSURE AT POINT #5 (8286FT) SCHLUMBERGER ENGINEER OBSERVED INDICATION FOR INTERNAL LEAK WITHIN THE DOWN HOLE TOOL OF MDT STRING
1546 | 01/20/2022 | ADM-656 | ABSF-95 | 19 Jan 1600 - 1100 | 6 | 19 | 888846 |  | WON | WTHR | NA | ARM | 0 | WAIT ON WEATHER TO OFFLOAD SPUD MATERIAL FROM SPUD VESSEL"AHTS EXCELSIOR" TO COMMENCE WORKOVER OPERATIONS.
1548 | 01/20/2022 | ARO-2003 | MNIF-735 | 19 Jan 0500 - 0500 | 24 | 48 | 888766 |  | WO | SRVC | NA | ARN | 0 | WAITING TO PERFORM SEABED SURVEY.
1550 | 01/20/2022 | ARO-3004 | KARN-46 | 19 Jan 0945 - 1015 | 5.25 | 24.5 | 888810 |  | WON | WTHR | NA | ARN | 8770 | WOW DUE TO INABILITY TO WORK BOATS FOR MUD AND CHEMICALS SUPPORT
1552 | 01/20/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 24 | 218.5 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1554 | 01/20/2022 | BB-84A | MRJN-587 | 20 Jan 0845 - 0500 | 20.25 | 20.25 | 888820 |  | HSEI | UNKN | NA | RIG | 296 | OPERATIONS SUSPENDED FOR DROPPED OBJECT INCIDENT INVESTIGATION
1556 | 01/20/2022 | DPS-5 | HRDH-2202 | 20 Jan 2200 - 0100 | 3 | 3 | 888822 |  | WCNT | WCC5 | NA | ARM | 13134 | WHILE CIRC. @ BTM HAD 7 BBL PIT GAIN & LEL ALARMS ACTIVATED, WELL WAS SHUT IN AND CONFIRM SICP=SIDP=ZERO.
1558 | 01/20/2022 | NBR-20S | UMWL-58 | 20 Jan 0545 - 0500 | 23.25 | 23.25 | 888985 |  | RR | FOT | DWKS | RIG | 5800 | DRAWWORKS GEARBOX SHAFT BEARING FAILED. WAITED ON PARTS, AND REPLACED SAME UPON ARRIVAL.
1560 | 01/20/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 237.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1562 | 01/20/2022 | PA-70S | TINT-87 | 20 Jan 1430 - 2130 | 7 | 7 | 888818 |  | TF | FOT | CTRQ | WCR | 16646 | FAILED TO M/U LOWER COMPLETION, POWER TONG IS NOT WORKING PROPELY.
1564 | 01/20/2022 | SINO-1L | KHRS-340 | 14 Jan 0230 - 0500 | 15 | 137.5 | 888286 |  | CMT | CPNF | NA | TK1 | 4938 | P/T ON-BTM LINER AFTER DRILL FLOAT EQUIPMENTS FAILED
1566 | 01/20/2022 | SINO-46L | SHYB-223 | 18 Jan 1830 - 0500 | 24 | 58.5 | 888726 |  | BHA | FOT | WBCL | SAM | 0 | WHILE L/D SAMAA CLEAN OUT BHA , RECOVERED ONE PIECE OF MAGNET BAR ( 3 CM LONG X 2 CM OD) AND LOST IN HOLE 3 PIECE OF MAGNET BAR SAME DIMENSION 3 CM LONG X 2 CM OD + 2 COVERED CLAMP, ALL ON LOWER MAGNET IN BHA.
1568 | 01/20/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 23.25 | 167.25 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | ATTEMPT TO CURE LOSSES WITH LCM PILLS.
1570 | 01/20/2022 | SNT-025 | SFNY-1007 | 19 Jan 1300 - 0800 | 3 | 19 | 888817 |  | WO | WOPF | NA | AP2 | 0 | RIG WAITING ON APPROVAL FROM SFNY PRODUCTION ENGINEERING TO COMMENCE FLOW BACK OPERATIONS
1572 | 01/20/2022 | SP-122 | SDGM-726 | 20 Jan 0600 - 1200 | 6 | 6 | 888819 |  | WO | SRVC | NA | BLH | 0 | BAKER 7" FLOAT COLLAR VALVES MALFUNCTIONED, WAIT ON NEW REPLACEMENT.
1574 | 01/20/2022 | SP-261 | HZEM-162102 | 20 Jan 0245 - 0430 | 1.75 | 1.75 | 889007 |  | RR | FOT | TDS | RIG | 13214 | DURING DRILLING TDS HAVING FAULT AND STOPPED ROTATION, REFLECTING ALL INDICATION OF STUCK PIPE, STRING . WORK ON STRING SLOWLY COMING UP.
1576 | 01/20/2022 | SSA-102 | QTIF-699 | 19 Jan 2230 - 1430 | 9.5 | 16 | 888826 |  | BHA | FOT | PWD | SPS | 4320 | NO SEAL OF GEO-TAP (FPWD) TOOL PROBE WHILE FUNCTION TEST ON CSD HOLE.
1578 | 01/20/2022 | SSA-46 | JAHM-5 | 20 Jan 2015 - 0215 | 6 | 6 | 888986 |  | RR | FOT | TDS | RIG | 0 | TDS LINK TILT MECHANISM NOT WORKING. TROUBLE SHOOT SAME. CHANGE SOLENOID SENSOR OF TDS.
1580 | 01/20/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 24 | 122.5 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1582 | 01/20/2022 | SSA-5891 | HRDH-695 | 20 Jan 1200 - 1245 | .75 | .75 | 888925 |  | JF | XTRI | NA | RIG | 13607 | DERRICKMAN DROP STAND OF DRILL PIPE ACROSS DERRICK.
1584 | 01/20/2022 | SSA-5964 | SDGM-1158 | 20 Jan 0500 - 0630 | 1.5 | 1.5 | 888848 |  | RR | FOT | TDS | RIG | 11234 | TDS CONTROL LINE DAMAGED.
1586 | 01/20/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 21.5 | 283 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1588 | 01/21/2022 | 095TE | MNIF-221 | 16 Jan 1130 - 0500 | 24 | 137.5 | 888392 |  | TF | FOT | CTAC | BCT | 24085 | A ISSUE WAS NOTICED IN THE WEIGHT INDICATOR READING ON CT CONTROL , CONT TO RIH MEANWHILE CHECKING THE SOURCE OF PROBLEM. MALFUNCTION HAS BEEN OBSERVED IN INJECTOR LOAD CELL, CHECKED AND FOUND SUPPORT PLATE WAS BROKEN AND BAKER IS UNABLE TO MAKE REPAIR , POOH WITH BAKER 2 3/8" COIL TUBING FROM 24085 FT TO 23990 FT EXPERIENCED OVER PULL AND COIL TUBING GET STUCK.
1590 | 01/21/2022 | ADC-36 | SDGM-1186 | 20 Jan 0030 - 0500 | 24 | 28.5 | 888824 |  | TF | FOT | HGRL | TOT | 13833 | AFTER SETTING 7" X 9.5/8" INNOVEX LINER HANGER, PRESSURED UP TO 2600 PSI TO RELEASE RUNNING TOOL WITHOUT SUCCESS. PRESSURED-UP IN STAGES TO MAXIMIM OF 4800 PSI - NO SUCCESS. UNSET HANGER WITH 35K O/PULL ; POH WITH 7" LINER.
1592 | 01/21/2022 | ADC-45 | KHRS-82 | 21 Jan 1800 - 2030 | 2.5 | 2.5 | 889072 |  | WON | WTHR | NA | ARM | 10894 | WAIT ON WEATHER DUE TO HIGH WIND SPEED 38 KM/HR.
1594 | 01/21/2022 | ADC-48 | HWYH-1258 | 21 Jan 2215 - 0500 | 6.75 | 6.75 | 888992 |  | CMT | CFST | NA | SJC | 6980 | FIND TOP CEMENT SHALOWER INSIDE CASING DUE TO CEMENT SET PREMATURELY
1596 | 01/21/2022 | ADC-55L | UTMN-3076 | 21 Jan 0500 - 1630 | 11.5 | 11.5 | 888991 |  | HSEI | UNKN | NA | RIG | 10973 | SUSPEND OPERATION DUE TO PTW VIOLATION.
1598 | 01/21/2022 | ADC-65L | HRDH-1980 | 21 Jan 2130 - 2230 | 1 | 1 | 889065 |  | TF | FOT | CTRQ | PM1 | 10727 | FAILURE ON PRIMADRILL CRT.
1600 | 01/21/2022 | ADM-337 | MRJN-900 | 20 Jan 0330 - 0830 | 3.5 | 5 | 889005 |  | TF | FOT | WLT | SWL | 8286 | WHILE SCHLUMBERGER WL RECORDING PRESSURE AT POINT #5 (8286FT) SCHLUMBERGER ENGINEER OBSERVED INDICATION FOR INTERNAL LEAK WITHIN THE DOWN HOLE TOOL OF MDT STRING
1602 | 01/21/2022 | AOD-111 | MRJN-726 | 21 Jan 0015 - 0130 | 1.25 | 1.25 | 889070 |  | WON | WTHR | NA | ARM | 1360 | SUSPENDE TRIPPING DUE TO HIGH WINDS OF OVER 45KNOTS
1604 | 01/21/2022 | ARO-2003 | MNIF-735 | 19 Jan 0500 - 0500 | 24 | 72 | 888766 |  | WO | SRVC | NA | ARN | 0 | WAITING TO PERFORM SEABED SURVEY.
1606 | 01/21/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 24 | 242.5 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1608 | 01/21/2022 | BB-84A | MRJN-587 | 20 Jan 0845 - 0500 | 24 | 44.25 | 888820 |  | HSEI | UNKN | NA | RIG | 296 | OPERATIONS SUSPENDED FOR DROPPED OBJECT INCIDENT INVESTIGATION
1610 | 01/21/2022 | HI-9 | MRJN-228 | 21 Jan 0500 - 0500 | 24 | 24 | 888988 |  | BHA | FOT | BIT | BHT | 9417 | DUE TO PREMATURE FAILURE OF 6-1/8" TRI-CONE BIT INITIATE SIDETRACK.
1612 | 01/21/2022 | MP-1 | LWHH-28 | 21 Jan 0600 - 1930 | 13.5 | 13.5 | 889025 |  | TF | FOT | WLT | BAW | 0 | CUT 4-1/2" TBG WITH BAKER WL RCT, ATTEMPTED TO RETRIEVE CUT STRING WITH NO SUCCESS.
1614 | 01/21/2022 | NBR-20S | UMWL-58 | 20 Jan 0545 - 0500 | 24 | 47.25 | 888985 |  | RR | FOT | DWKS | RIG | 5800 | DRAWWORKS GEARBOX SHAFT BEARING FAILED. WAITED ON PARTS, AND REPLACED SAME UPON ARRIVAL.
1616 | 01/21/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 261.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1618 | 01/21/2022 | PA-70S | TINT-87 | 21 Jan 2330 - 0300 | 3.5 | 3.5 | 888989 |  | WON | WTHR | NA | ARM | 16646 | BAD WEATHER DUE TO STRONG WIND & SAND STORM.
1619 | 01/21/2022 | SINO-1L | KHRS-340 | 21 Jan 0830 - 1030 | 2 | 2 | 889071 |  | TF | FOT | TBG | TK1 | 5696 | LWD TOOL SIGNAL BAD DETECTION WHILE RE-LOG
1621 | 01/21/2022 | SINO-1L | KHRS-340 | 14 Jan 0230 - 1500 | 8 | 145.5 | 888286 |  | CMT | CPNF | NA | TK1 | 4938 | P/T ON-BTM LINER AFTER DRILL FLOAT EQUIPMENTS FAILED
1622 | 01/21/2022 | SINO-1L | KHRS-340 | 21 Jan 0830 - 1030 | 2 | 2 | 889071 |  | TF | FOT | TBG | TK1 | 5696 | LWD TOOL SIGNAL BAD DETECTION WHILE RE-LOG
1624 | 01/21/2022 | SINO-46L | SHYB-223 | 18 Jan 1830 - 0500 | 24 | 82.5 | 888726 |  | BHA | FOT | WBCL | SAM | 0 | WHILE L/D SAMAA CLEAN OUT BHA , RECOVERED ONE PIECE OF MAGNET BAR ( 3 CM LONG X 2 CM OD) AND LOST IN HOLE 3 PIECE OF MAGNET BAR SAME DIMENSION 3 CM LONG X 2 CM OD + 2 COVERED CLAMP, ALL ON LOWER MAGNET IN BHA.
1626 | 01/21/2022 | SL-7 | ZULF-1337 | 21 Jan 0100 - 0345 | 2.75 | 2.75 | 888990 |  | WON | WTHR | NA | ARM | 5132 | WAIT ON WEATHER TO RESUME OPERATON DUE TO STRONG WIND SPEED AT 46 KNTS.
1628 | 01/21/2022 | SND-2001 | SDGM-1240 | 21 Jan 1845 - 0330 | 8.75 | 8.75 | 889067 |  | TF | FOT | WLT | HWP | 15160 | HALLIBURTON WL CAST LOG TOOL PROVIDE POOR QUALITY OF DATA AFTER CONDUCTING LOG UNDER 2100 PSI PRESSURE.
1630 | 01/21/2022 | SND-2004 | BRRI-528 | 21 Jan 1500 - 0200 | 6 | 6 | 889073 |  | BB | PCPF | NA | ARM | 215 | 28" BALLED UP BIT DUE TO STICKY FORMATION. TRIP OUT TO CLEAN THE BIT
1632 | 01/21/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 24 | 191.25 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | WHILE DRILLING 8.5" PILOT HOLE, HAD 40 BPH DYNAMIC LOSSES @ 1500'. CONTINUE DRILL 8.5" PILOT HOLE TO 1710', LOSSES INCREASED TO 170 BPH.
1634 | 01/21/2022 | SP-306 | MNIF-865 | 21 Jan 0200 - 0500 | 3 | 3 | 889045 |  | RR | FOT | TDS | RIG | 1539 | WHILE DRILLING 16'' HS @ 1,539' FOUND CONNECTION BETWEEN IBOPS (MANUAL & HYDRAULIC)
1636 | 01/21/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 146 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1638 | 01/21/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 307 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1640 | 01/22/2022 | 095TE | MNIF-221 | 16 Jan 1130 - 0500 | 24 | 161.5 | 888392 |  | TF | FOT | CTAC | BCT | 24085 | A ISSUE WAS NOTICED IN THE WEIGHT INDICATOR READING ON CT CONTROL , CONT TO RIH MEANWHILE CHECKING THE SOURCE OF PROBLEM. MALFUNCTION HAS BEEN OBSERVED IN INJECTOR LOAD CELL, CHECKED AND FOUND SUPPORT PLATE WAS BROKEN AND BAKER IS UNABLE TO MAKE REPAIR , POOH WITH BAKER 2 3/8" COIL TUBING FROM 24085 FT TO 23990 FT EXPERIENCED OVER PULL AND COIL TUBING GET STUCK.
1642 | 01/22/2022 | ADC-36 | SDGM-1186 | 20 Jan 0030 - 0500 | 23.5 | 52 | 888824 |  | TF | FOT | HGRL | TOT | 13833 | AFTER SETTING 7" X 9.5/8" INNOVEX LINER HANGER, PRESSURED UP TO 2600 PSI TO RELEASE RUNNING TOOL WITHOUT SUCCESS. PRESSURED-UP IN STAGES TO MAXIMIM OF 4800 PSI - NO SUCCESS. UNSET HANGER WITH 35K O/PULL ; POH WITH 7" LINER.
1643 | 01/22/2022 | ADC-43L | HRDH-1928 | 22 Jan 1915 - 2000 | .75 | .75 | 889151 |  | TF | FOT | CRT | WCR | 2767 | STOP OPERATION AFTER LEAK IN ONE HYDRAULIC HOSE FROM WFD
1645 | 01/22/2022 | ADC-43L | HRDH-1928 | 22 Jan 0930 - 1000 | .5 | .5 | 889149 |  | TF | FOT | CRT | WCR | 0 | ATTEMPT TO MAKE UP JOINT. OBSERVE POWER TONG JAWS MAKING A DEEP DENT ON THE TUBING BODY.
1646 | 01/22/2022 | ADC-43L | HRDH-1928 | 22 Jan 1030 - 1330 | 3 | 3 | 889150 |  | TF | FOT | CRT | WCR | 0 | TUBING TONG POWER UNIT FAILURE.
1647 | 01/22/2022 | ADC-43L | HRDH-1928 | 22 Jan 1915 - 2000 | .75 | .75 | 889151 |  | TF | FOT | CRT | WCR | 2767 | STOP OPERATION AFTER LEAK IN ONE HYDRAULIC HOSE FROM WFD
1649 | 01/22/2022 | ADC-59L | HRDH-2232 | 22 Jan 1745 - 1845 | 1 | 1 | 889166 |  | RR | FOT | TDS | RIG | 7095 | EMERGENCY STOP ACTIVATED ON ITS OWN. UNABLE TO ROTATE DRILL STRING.
1651 | 01/22/2022 | ADM-266 | ZULF-106 | 22 Jan 0500 - 0500 | 24 | 24 | 889125 |  | WON | WTHR | NA | ARN | 0 | WAIT ON SUITABLE WEATHER AND FORECAST TO COMPLETE BACKLOAD & MOVE RIG FROM SFNY-30, 488/489 PF TO ZULF-104/109 PF.
1653 | 01/22/2022 | ADM-656 | ABSF-95 | 22 Jan 1400 - 0500 | 15 | 15 | 889245 |  | WON | WTHR | NA | ARM | 5100 | WOW HIGH WIND SPEED.
1655 | 01/22/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 11 | 11 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
1656 | 01/22/2022 | ARO-3004 | KARN-46 | 22 Jan 1415 - 0315 | 12.75 | 12.75 | 888995 |  | FISH | HERR | STRG | RIG | 4104 | MISSING DIE SEGMENT FROM 5.5" DRILL PIPE SLIPS WHILE RIH SCRAPER BHA ON 5.5" DP, ASSUMED TO HAVE FALLEN DOWN HOLE.
1658 | 01/22/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 8 | 64.25 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
1659 | 01/22/2022 | ARO-3004 | KARN-46 | 22 Jan 1415 - 0315 | 12.75 | 12.75 | 888995 |  | FISH | HERR | STRG | RIG | 4104 | MISSING DIE SEGMENT FROM 5.5" DRILL PIPE SLIPS WHILE RIH SCRAPER BHA ON 5.5" DP, ASSUMED TO HAVE FALLEN DOWN HOLE.
1661 | 01/22/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 24 | 266.5 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1663 | 01/22/2022 | BB-84A | MRJN-587 | 20 Jan 0845 - 0500 | 21.25 | 65.5 | 888820 |  | HSEI | UNKN | NA | RIG | 296 | OPERATIONS SUSPENDED FOR DROPPED OBJECT INCIDENT INVESTIGATION
1665 | 01/22/2022 | EXL-IA | SFNY-4050 | 22 Jan 1100 - 0500 | 17 | 17 | 889105 |  | WON | WTHR | NA | ARN | 0 | WAITING ON WEATHER CONDITIONS TO SUBSIDE FOR RIG MOVE OPERATIONS
1667 | 01/22/2022 | HI-9 | MRJN-228 | 21 Jan 0500 - 0500 | 24 | 48 | 888988 |  | BHA | FOT | BIT | BHT | 9417 | DUE TO PREMATURE FAILURE OF 6-1/8" TRI-CONE BIT INITIATE SIDETRACK.
1669 | 01/22/2022 | MP-4 | LWHH-18 | 22 Jan 1900 - 0500 | 10 | 10 | 888994 |  | WON | WTHR | NA | ARM | 6320 | WAIT ON WEATHER TO IMPROVE TO OFFLOAD OBM, WEIGHTING MATERIAL & MUD ADDITIVES FROM BOAT
1671 | 01/22/2022 | NBR-20S | UMWL-58 | 20 Jan 0545 - 0630 | 1.5 | 48.75 | 888985 |  | RR | FOT | DWKS | RIG | 5800 | DRAWWORKS GEARBOX SHAFT BEARING FAILED. WAITED ON PARTS, AND REPLACED SAME UPON ARRIVAL.
1673 | 01/22/2022 | NBR-304S | HRDH-2260 | 22 Jan 1100 - 1400 | 3 | 3 | 889146 |  | WON | WTHR | NA | OTH | 11411 | HIGH WIND SPEEDS OF 45KMPH AT RISK OF DAMAGING SERVICE LOOP FOR TOP DRIVE DUE TO WIND SPEED AND DIRECTION
1674 | 01/22/2022 | NBR-797S | UTMN-3145 | 22 Jan 1330 - 0500 | 15.5 | 15.5 | 889106 |  | FISH | HERR | WLT | SWL | 10770 | - SLB WIRELINE ENCOUNTER SLACK OFF @ 10,770 FT MD. - SLB WORK TOOL UP/ DOWN WITH NO PUMP TO PASS RESTRICTION IN DP. NO SUCCESS. - ATTEMPT TO PUMP DOWN TOOLS PAST RESTRICTION W/300 GPM 3500 PSI. MAKE SEVERAL ATTEMPTS DURING PUMPING - SLB WIRELINE PARTED AT SIDE ENTRY SUB. WIRELINE & BAKER MPC LOST DOWN DP
1676 | 01/22/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 1330 | 8.5 | 270 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1677 | 01/22/2022 | NBR-797S | UTMN-3145 | 22 Jan 1330 - 0500 | 15.5 | 15.5 | 889106 |  | FISH | HERR | WLT | SWL | 10770 | - SLB WIRELINE ENCOUNTER SLACK OFF @ 10,770 FT MD. - SLB WORK TOOL UP/ DOWN WITH NO PUMP TO PASS RESTRICTION IN DP. NO SUCCESS. - ATTEMPT TO PUMP DOWN TOOLS PAST RESTRICTION W/300 GPM 3500 PSI. MAKE SEVERAL ATTEMPTS DURING PUMPING - SLB WIRELINE PARTED AT SIDE ENTRY SUB. WIRELINE & BAKER MPC LOST DOWN DP
1679 | 01/22/2022 | PA-70S | TINT-87 | 21 Jan 2330 - 1100 | 3.5 | 7 | 888989 |  | WON | WTHR | NA | ARM | 16646 | BAD WEATHER DUE TO STRONG WIND & SAND STORM.
1681 | 01/22/2022 | SA5898 | HRDH-2101 | 20 Jan 1830 - 1315 | 8.25 | 35.5 | 889147 |  | STUK | STDP | DP | ARM | 11780 | DIFFERENTIAL STUCK PIPE ACROSS KUFF-B WHILE WASHING UP (HAD 15 KLB O/P, TRY TO FREE DOWN HAD 10 KLB S.O.WT- ATTEMPT TO ROTATE HAD STRG STALLED AND GOT STUCK)
1682 | 01/22/2022 | SINO-12L | HRDH-447 | 22 Jan 1530 - 1630 | 1 | 1 | 889206 |  | SURV | FOT | SS | SPS | 8598 | SPERRY SUN LOST SIGNAL TO MWD TOOLS.
1684 | 01/22/2022 | SINO-12L | HRDH-447 | 22 Jan 0500 - 0700 | 2 | 2 | 889205 |  | TF | FOT | TBG | TK1 | 7955 | UNABLE TO RESUME DRILLING DUE TO FAILURE IN SCR ROOM.
1685 | 01/22/2022 | SINO-12L | HRDH-447 | 22 Jan 1530 - 1630 | 1 | 1 | 889206 |  | SURV | FOT | SS | SPS | 8598 | SPERRY SUN LOST SIGNAL TO MWD TOOLS.
1687 | 01/22/2022 | SINO-33L | KHRS-365 | 22 Jan 0500 - 1100 | 6 | 6 | 889085 |  | WO | SRVC | NA | TK2 | 300 | MIX PUMP DAMAGED (PUMP SHAFT BROKEN), NOT ABLE TO MIX AND WAIT ON ANOTHER CEMENT UNIT FOR 2ND CMT PLUG.
1689 | 01/22/2022 | SINO-46L | SHYB-223 | 18 Jan 1830 - 0500 | 24 | 106.5 | 888726 |  | BHA | FOT | WBCL | SAM | 0 | WHILE L/D SAMAA CLEAN OUT BHA , RECOVERED ONE PIECE OF MAGNET BAR ( 3 CM LONG X 2 CM OD) AND LOST IN HOLE 3 PIECE OF MAGNET BAR SAME DIMENSION 3 CM LONG X 2 CM OD + 2 COVERED CLAMP, ALL ON LOWER MAGNET IN BHA.
1691 | 01/22/2022 | SND-1201 | ABJF-1003 | 22 Jan 1630 - 1930 | 3 | 3 | 889225 |  | WON | WTHR | NA | ARM | 0 | SUSPEND CRANE ACTIVITY DUE TO HIGH WIND SPEED
1693 | 01/22/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0500 | 24 | 215.25 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | WHILE DRILLING 8.5" PILOT HOLE, HAD 40 BPH DYNAMIC LOSSES @ 1500'. CONTINUE DRILL 8.5" PILOT HOLE TO 1710', LOSSES INCREASED TO 170 BPH.
1695 | 01/22/2022 | SP-257 | HZEM-141204 | 22 Jan 0400 - 0500 | 1 | 1 | 889185 |  | RR | FOT | HSYS | RIG | 11542 | UNABLE TO BREAK DP CONNECTION DUE TO IRON ROUGHNECK FAILURE.
1697 | 01/22/2022 | SP-260 | HZEM-141612 | 22 Jan 1915 - 0500 | 5.5 | 5.5 | 889145 |  | DD | UDWL | RSS | BHI | 9500 | BAKER MWD LOST SIGNAL
1699 | 01/22/2022 | SP-306 | MNIF-865 | 21 Jan 0200 - 0930 | 4 | 7 | 889045 |  | RR | FOT | TDS | RIG | 1539 | WHILE DRILLING 16'' HOLE @ 1,539' OBSERVED LEAKAGE AT THE CONNECTION BETWEEN TDS IBOPS (MANUAL & HYDRAULIC).
1701 | 01/22/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 24 | 170 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1703 | 01/22/2022 | SSA-5970 | HWYH-1257 | 22 Jan 2330 - 0100 | 1.5 | 1.5 | 889165 |  | RR | FOT | RSYS | RIG | 11100 | RIG REPAIR ON IRON ROUGHNECK.
1705 | 01/22/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 331 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1707 | 01/23/2022 | ADC-32 | SDGM-1139 | 23 Jan 0145 - 0500 | 3.25 | 3.25 | 889427 |  | RR | FOT | CSYS | RIG | 10514 | LEAK ON STAND PIPE.
1709 | 01/23/2022 | ADC-36 | SDGM-1186 | 20 Jan 0030 - 0500 | 23.5 | 75.5 | 888824 |  | TF | FOT | HGRL | TOT | 13833 | AFTER SETTING 7" X 9.5/8" INNOVEX LINER HANGER, PRESSURED UP TO 2600 PSI TO RELEASE RUNNING TOOL WITHOUT SUCCESS. PRESSURED-UP IN STAGES TO MAXIMIM OF 4800 PSI - NO SUCCESS. UNSET HANGER WITH 35K O/PULL ; POH WITH 7" LINER.
1711 | 01/23/2022 | ADC-46L | UTMN-3101 | 23 Jan 1000 - 1600 | 6 | 6 | 889385 |  | RR | FOT | TDS | RIG | 6213 | OBSERVED LEAK ON TDS S-PIPE.
1713 | 01/23/2022 | ADM-262 | MRJN-121 | 23 Jan 0745 - 0500 | 21.25 | 21.25 | 889158 |  | DD | AINC | BHA | BHI | 12298 | BAKER RSS BHA CONSTANTLY BUILDING ANGLE, UNABLE TO FOLLOW GOC STEERING INSTRUCTIONS.
1714 | 01/23/2022 | ADM-266 | ZULF-106 | 23 Jan 2230 - 0500 | 6.5 | 6.5 | 889405 |  | WON | DAY | NA | ARN | 0 | WAIT ON DAYLIGHT FOR TO TIEBACK BOAT FOR BACKLOAD.
1716 | 01/23/2022 | ADM-266 | ZULF-106 | 22 Jan 0500 - 1930 | 14.5 | 38.5 | 889125 |  | WON | WTHR | NA | ARN | 0 | WAIT ON SUITABLE WEATHER AND FORECAST TO COMPLETE BACKLOAD & MOVE RIG FROM SFNY-30, 488/489 PF TO ZULF-104/109 PF.
1717 | 01/23/2022 | ADM-266 | ZULF-106 | 23 Jan 2230 - 0500 | 6.5 | 6.5 | 889405 |  | WON | DAY | NA | ARN | 0 | WAIT ON DAYLIGHT FOR TO TIEBACK BOAT FOR BACKLOAD.
1719 | 01/23/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 24 | 35 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
1721 | 01/23/2022 | ARO-2003 | MNIF-735 | 19 Jan 0500 - 0500 | 24 | 120 | 888766 |  | WO | SRVC | NA | ARN | 0 | WAITING TO PERFORM SEABED SURVEY.
1723 | 01/23/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 23.5 | 87.75 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
1724 | 01/23/2022 | ARO-4001 | MRJN-537 | 23 Jan 1045 - 1200 | 1.25 | 1.25 | 889365 |  | RR | FOT | MPMP | RIG | 6965 | HAD MUD PUMP # 2 & 3 VALVE AND SEAT LEAKING, REPLACED SAME, OK.
1726 | 01/23/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 21 | 287.5 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1727 | 01/23/2022 | ARO-4001 | MRJN-537 | 23 Jan 0900 - 1045 | 1.75 | 1.75 | 889345 |  | LROP | IDPR | BHA | BHI | 6965 | WHILE DRILLING 12 1/4" HOLE ROP DROPPED TO ZERO, CHANGE PARAMETERS TO RESUME DRILLING, NO SUCCESS, BHI SENT DOWN LINK FOR RIPS OFF, DRILL 10 FT, THEN CONT. DRILLING.
1728 | 01/23/2022 | ARO-4001 | MRJN-537 | 23 Jan 1045 - 1200 | 1.25 | 1.25 | 889365 |  | RR | FOT | MPMP | RIG | 6965 | HAD MUD PUMP # 2 & 3 VALVE AND SEAT LEAKING, REPLACED SAME, OK.
1730 | 01/23/2022 | EXL-IA | SFNY-4050 | 22 Jan 1100 - 1700 | 11.5 | 28.5 | 889105 |  | WON | WTHR | NA | ARN | 0 | WAITING ON WEATHER CONDITIONS TO SUBSIDE FOR RIG MOVE OPERATIONS
1732 | 01/23/2022 | HI-9 | MRJN-228 | 21 Jan 0500 - 0200 | 21 | 69 | 888988 |  | BHA | FOT | BIT | BHT | 9417 | DUE TO PREMATURE FAILURE OF 6-1/8" TRI-CONE BIT INITIATE SIDETRACK.
1734 | 01/23/2022 | MP-1 | LWHH-28 | 23 Jan 1930 - 2215 | 2.75 | 2.75 | 889285 |  | RR | FOT | CSYS | RIG | 0 | RIG BARITE SUPPLY STOPPED DUE TO LEAKING FROM SHOWING GLASS ON BARITE TANK.
1736 | 01/23/2022 | MP-4 | LWHH-18 | 22 Jan 1900 - 2000 | 15 | 25 | 888994 |  | WON | WTHR | NA | ARM | 6320 | WAIT ON WEATHER TO IMPROVE TO OFFLOAD OBM, WEIGHTING MATERIAL & MUD ADDITIVES FROM BOAT
1737 | 01/23/2022 | NBR-797S | UTMN-3145 | 22 Jan 1330 - 1500 | 10 | 25.5 | 889106 |  | FISH | HERR | WLT | SWL | 10770 | - SLB WIRELINE ENCOUNTER SLACK OFF @ 10,770 FT MD. - SLB WORK TOOL UP/ DOWN WITH NO PUMP TO PASS RESTRICTION IN DP. NO SUCCESS. - ATTEMPT TO PUMP DOWN TOOLS PAST RESTRICTION W/300 GPM 3500 PSI. MAKE SEVERAL ATTEMPTS DURING PUMPING - SLB WIRELINE PARTED AT SIDE ENTRY SUB. WIRELINE & BAKER MPC LOST DOWN DP
1739 | 01/23/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 14 | 284 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1740 | 01/23/2022 | NBR-797S | UTMN-3145 | 22 Jan 1330 - 1500 | 10 | 25.5 | 889106 |  | FISH | HERR | WLT | SWL | 10770 | - SLB WIRELINE ENCOUNTER SLACK OFF @ 10,770 FT MD. - SLB WORK TOOL UP/ DOWN WITH NO PUMP TO PASS RESTRICTION IN DP. NO SUCCESS. - ATTEMPT TO PUMP DOWN TOOLS PAST RESTRICTION W/300 GPM 3500 PSI. MAKE SEVERAL ATTEMPTS DURING PUMPING - SLB WIRELINE PARTED AT SIDE ENTRY SUB. WIRELINE & BAKER MPC LOST DOWN DP
1742 | 01/23/2022 | SCTD-1 | UTMN-1800 | 23 Jan 2130 - 0500 | 7.5 | 7.5 | 889325 |  | BHA | FOT | MWD | SDM | 12686 | FAILURE TO ORIENT BHA , POOH TO INSPECT BHA.
1744 | 01/23/2022 | SCTD-2 | UTMN-1876 | 23 Jan 0200 - 0500 | 3 | 3 | 889429 |  | BHA | FOT | MMOT | RIG | 3200 | LOST COMMUNICATION WITH BHA, TROUBLESHOOT WITH NO SUCCESS.
1746 | 01/23/2022 | SINO-12L | HRDH-447 | 23 Jan 2230 - 0430 | 6 | 6 | 889431 |  | TF | FOT | TBG | TK1 | 9200 | DELAY IN DRILLING OPERATION DUE TO SUCTION SCREEN PLUGGING, PUMP PRESSURE NOT STABLE.
1748 | 01/23/2022 | SINO-27N | HRDH-485 | 23 Jan 0530 - 1800 | 12.5 | 12.5 | 889428 |  | TH | NARW | NA | ARM | 5298 | ADDITIONAL C/O RUN TO CLEAN 7'' CSG
1750 | 01/23/2022 | SINO-46L | SHYB-223 | 18 Jan 1830 - 0800 | 3 | 109.5 | 888726 |  | BHA | FOT | WBCL | SAM | 0 | WHILE L/D SAMAA CLEAN OUT BHA , RECOVERED ONE PIECE OF MAGNET BAR ( 3 CM LONG X 2 CM OD) AND LOST IN HOLE 3 PIECE OF MAGNET BAR SAME DIMENSION 3 CM LONG X 2 CM OD + 2 COVERED CLAMP, ALL ON LOWER MAGNET IN BHA.
1752 | 01/23/2022 | SL-7 | ZULF-1337 | 23 Jan 0745 - 0945 | 2 | 2 | 889430 |  | WO | SRVC | NA | INW | 5097 | SLICKLINE COMPANY DID TWO EXTRA RUNS TO SET PX PLUG DUE TO INTERWELL COMPANY COULDN'T PROVIDE SERVICE HAND TO SET ME PLUG.
1754 | 01/23/2022 | SND-2003 | MNIF-900 | 23 Jan 0500 - 0700 | 2 | 2 | 889155 |  | RR | FOT | TDS | RIG | 11050 | REPLACED TDS HYDRAULIC IBOP DUE TO LEAKS.
1756 | 01/23/2022 | SNF036 | MRJN-901 | 14 Jan 0500 - 0530 | .5 | 215.75 | 888266 |  | LCIR | ULCM | LCM | ARM | 1500 | WHILE DRILLING 8.5" PILOT HOLE, HAD 40 BPH DYNAMIC LOSSES @ 1500'. CONTINUE DRILL 8.5" PILOT HOLE TO 1710', LOSSES INCREASED TO 170 BPH.
1757 | 01/23/2022 | SP-257 | HZEM-141204 | 23 Jan 2200 - 0500 | 7 | 7 | 889305 |  | JF | HERR | CTRQ | FMC | 0 | TROUBLE SHOOT FRANKS CRT HYDRAULLICS.
1759 | 01/23/2022 | SP-257 | HZEM-141204 | 22 Jan 0400 - 0800 | 2 | 3 | 889185 |  | RR | FOT | HSYS | RIG | 11542 | UNABLE TO BREAK DP CONNECTION DUE TO IRON ROUGHNECK FAILURE.
1760 | 01/23/2022 | SP-257 | HZEM-141204 | 23 Jan 2200 - 0500 | 7 | 7 | 889305 |  | JF | HERR | CTRQ | FMC | 0 | TROUBLE SHOOT FRANKS CRT HYDRAULLICS.
1762 | 01/23/2022 | SP-260 | HZEM-141612 | 22 Jan 1915 - 2015 | 14.75 | 20.25 | 889145 |  | DD | UDWL | RSS | BHI | 9500 | BAKER MWD LOST SIGNAL
1764 | 01/23/2022 | SP-306 | MNIF-865 | 23 Jan 1130 - 1145 | .25 | .25 | 889157 |  | LCIR | FRFM | NA | ARM | 2690 | WHILE DRILLING 16 HOLE AT 2,690 FT, PARTIAL LOSSES 120 BPH ENCOUNTERED.
1766 | 01/23/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23 | 193 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1767 | 01/23/2022 | SSA-5970 | HWYH-1257 | 23 Jan 2330 - 0100 | 1.5 | 1.5 | 889426 |  | TF | FOT | CTRQ | GOC | 11100 | AL GHAITH POWER TONG NOT WORKING PROPERLY
1769 | 01/23/2022 | SSA-5970 | HWYH-1257 | 23 Jan 1630 - 1800 | 1.5 | 1.5 | 889425 |  | WH | HERR | WBSH | CAM | 11100 | EXCESS TIME CAMERON TO PREPARE 9-5/8" FMH HANGER.
1770 | 01/23/2022 | SSA-5970 | HWYH-1257 | 23 Jan 2330 - 0100 | 1.5 | 1.5 | 889426 |  | TF | FOT | CTRQ | GOC | 11100 | AL GHAITH POWER TONG NOT WORKING PROPERLY
1772 | 01/23/2022 | T217 | UTMN-488 | 08 Jan 0100 - 0500 | 24 | 355 | 886973 |  | STUK | STDP | DP | ARM | 0 | PIPE STUCKED
1774 | 01/23/2022 | WCL-83 | MRJN-831 | 23 Jan 1130 - 1515 | 3.75 | 3.75 | 889154 |  | WON | WTHR | NA | ARM | 13192 | WAIT ON WEATHER. WIND SPEEDS GREATER THAN 35 KNOTS.
1776 | 01/24/2022 | ADC-14 | HRDH-1804 | 24 Jan 1800 - 0500 | 11 | 11 | 889585 |  | TF | FOT | TBG | ARM | 4812 | TUBING DRIFT ISSUE
1778 | 01/24/2022 | ADC-17 | ZULF-1210 | 19 Jan 0500 - 0630 | 1.5 | 121 | 889432 |  | WON | WTHR | NA | ARM | 6470 | WAIT ON WEATHER WINDOW OF 48 HOURS IN ORDER TO MOVE RIG
1780 | 01/24/2022 | ADC-21 | MHWZ-125104 | 24 Jan 0630 - 0500 | 22.5 | 22.5 | 889605 |  | JF | CEDE | NA | BCM | 10305 | SOFT CEMENT ON THE SHOE TRACK FROM 1ST STAGE CEMENT JOB
1781 | 01/24/2022 | ADC-23 | RMLH-15 | 24 Jan 1630 - 2030 | 4 | 4 | 889565 |  | TF | FOT | CTRQ | GOC | 7237 | CRT, CSG GRABBER SLIPS FAILED TO GRAB AND HOLD CSG
1783 | 01/24/2022 | ADC-23 | RMLH-15 | 24 Jan 0515 - 0730 | 2.25 | 2.25 | 889505 |  | TF | FOT | CTRQ | GOC | 4135 | CRT, CSG GRABBER SLIPS FAILED TO GRAB AND HOLD CSG
1784 | 01/24/2022 | ADC-23 | RMLH-15 | 24 Jan 1630 - 2030 | 4 | 4 | 889565 |  | TF | FOT | CTRQ | GOC | 7237 | CRT, CSG GRABBER SLIPS FAILED TO GRAB AND HOLD CSG
1786 | 01/24/2022 | ADC-31 | SDGM-1163 | 23 Jan 0030 - 2200 | 16 | 20.5 | 889465 |  | TF | FOT | WLT | SWL | 13097 | WHILE RIH THE SLB MDT DUAL PACKER OBSERVED THE MOTOR ACTIVATING OPENING/ CLOSING INTERVAL VALVE, AND INFLATE VALVE OF THE PKR TRIPPED OUT (MALFUNCTION)
1788 | 01/24/2022 | ADC-36 | SDGM-1186 | 20 Jan 0030 - 1900 | 14 | 89.5 | 888824 |  | TF | FOT | HGRL | TOT | 13833 | AFTER SETTING 7" X 9.5/8" INNOVEX LINER HANGER, PRESSURED UP TO 2600 PSI TO RELEASE RUNNING TOOL WITHOUT SUCCESS. PRESSURED-UP IN STAGES TO MAXIMIM OF 4800 PSI - NO SUCCESS. UNSET HANGER WITH 35K O/PULL ; POH WITH 7" LINER.
1790 | 01/24/2022 | ADC-68L | KRSN-705 | 22 Jan 1630 - 0930 | 4.5 | 41 | 889153 |  | JF | HELD | CSG | TK3 | 732 | ATTEMPTED TO RIH WITH 18-5/8" CASING, HAD OBSTRUCTION AT 209 FT.
1792 | 01/24/2022 | ADM-262 | MRJN-121 | 23 Jan 0745 - 0500 | 24 | 45.25 | 889158 |  | DD | AINC | BHA | BHI | 12298 | BAKER RSS BHA CONSTANTLY BUILDING ANGLE, UNABLE TO FOLLOW GOC STEERING INSTRUCTIONS.
1794 | 01/24/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 24 | 59 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
1796 | 01/24/2022 | ARO-2003 | MNIF-735 | 19 Jan 0500 - 0500 | 24 | 144 | 888766 |  | WO | SRVC | NA | ARN | 0 | WAITING TO PERFORM SEABED SURVEY.
1798 | 01/24/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 15.25 | 71.5 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
1799 | 01/24/2022 | ARO-4001 | MRJN-537 | 24 Jan 2300 - 0500 | 3 | 3 | 889527 |  | RR | FOT | TDS | RIG | 7234 | WHILE DRILLING OBSERVED HIGH TEMP ALARM FOR TDS MOTOR B NON DRIVE END BEARING & SMOKE FROM TDS MOTOR B SIDE, TROUBLESHOOTING & DISENGAGE MOTOR B GEAR FROM TDS MAIN SHAFT (PLAN TO REPAIR TDS MOTOR B WHILE INSIDE CSG SHOE).
1801 | 01/24/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0400 | 21 | 308.5 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1802 | 01/24/2022 | ARO-4001 | MRJN-537 | 24 Jan 2300 - 0500 | 3 | 3 | 889527 |  | RR | FOT | TDS | RIG | 7234 | WHILE DRILLING OBSERVED HIGH TEMP ALARM FOR TDS MOTOR B NON DRIVE END BEARING & SMOKE FROM TDS MOTOR B SIDE, TROUBLESHOOTING & DISENGAGE MOTOR B GEAR FROM TDS MAIN SHAFT (PLAN TO REPAIR TDS MOTOR B WHILE INSIDE CSG SHOE).
1804 | 01/24/2022 | DPS-4 | SAHB-34 | 24 Jan 0900 - 0500 | 20 | 20 | 889507 |  | BHA | FOT | STZRM | RIG | 14132 | FOUND ONE ROLLER SHAFT & BLOCK MISSING FROM BOTTOM ROLLER REAMER.
1806 | 01/24/2022 | EXL-IA | SFNY-4050 | 24 Jan 1230 - 1400 | 1.5 | 1.5 | 889510 |  | UPRA | OTH | NA | RIG | 0 | PERFORM SPUD CAN INSPECTIOBS WITH ROV.
1808 | 01/24/2022 | HI-9 | MRJN-228 | 21 Jan 0500 - 0500 | 17 | 86 | 888988 |  | TF | FOT | WPSTK | WI3 | 9417 | WIS PREMATURE FAILURE OF TRI MILL ASSEMBLY RESULTING IN IMPROPER 7" WINDOW CUT AND UNABLE TO CLEAN METAL JUNK FROM RAT HOLE.
1810 | 01/24/2022 | NBR-20S | UMWL-58 | 24 Jan 0030 - 0500 | 4.5 | 4.5 | 889586 |  | TF | XTTE | SLICK | GD1 | 520 | SLICKLINE PR PLUG NOT PASSING PAST 520' EVEN THOUGH 3.75" DRIFT PASSES FREELY.
1812 | 01/24/2022 | NBR-783S | MDRK-55 | 24 Jan 0900 - 1230 | 3.5 | 3.5 | 889587 |  | TF | XTTE | SLICK | SPL | 0 | MISS RUN TO SET PRONG
1813 | 01/24/2022 | NBR-797S | UTMN-3145 | 24 Jan 0245 - 0500 | 2.25 | 2.25 | 889531 |  | TF | FOT | CUT | NWL | 15163 | POWER LOST AT TOOL DOWNHOLE TO WELLTECH TRACTOR W/MPC TOOLS WHILE TRACTORING INSIDE STUCK 4" DP @ 15,163FT
1815 | 01/24/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0245 | 19.25 | 303.25 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1816 | 01/24/2022 | NBR-797S | UTMN-3145 | 24 Jan 1700 - 1930 | 2.5 | 2.5 | 889528 |  | WO | SRVC | NA | WTC | 0 | TROUBLESHOOT SOFTWARE AND COMMUNICATOIN PROBLEM WITH WELLTEC MPC TOOLS
1817 | 01/24/2022 | NBR-797S | UTMN-3145 | 24 Jan 0245 - 0500 | 2.25 | 2.25 | 889531 |  | TF | FOT | CUT | NWL | 15163 | POWER LOST AT TOOL DOWNHOLE TO WELLTECH TRACTOR W/MPC TOOLS WHILE TRACTORING INSIDE STUCK 4" DP @ 15,163FT
1819 | 01/24/2022 | PA-785S | QTIF-24 | 24 Jan 1330 - 0500 | 15.5 | 15.5 | 889536 |  | RR | FOT | TDS | RIG | 6746 | RIG TOP DRIVE FAILURE IN INVERTER, ENCODER SENSORS.
1820 | 01/24/2022 | SCTD-1 | UTMN-1800 | 24 Jan 0830 - 1730 | 9 | 9 | 889525 |  | BHA | FOT | MWD | SDM | 2490 | D&M LOST COMMUNICATION WITH DOWNHOLE TOOLS.
1822 | 01/24/2022 | SCTD-1 | UTMN-1800 | 23 Jan 2130 - 2100 | 7 | 14.5 | 889325 |  | BHA | FOT | MWD | SDM | 12686 | FAILURE TO ORIENT BHA , POOH TO INSPECT BHA.
1823 | 01/24/2022 | SCTD-1 | UTMN-1800 | 24 Jan 0830 - 1730 | 9 | 9 | 889525 |  | BHA | FOT | MWD | SDM | 2490 | D&M LOST COMMUNICATION WITH DOWNHOLE TOOLS.
1825 | 01/24/2022 | SCTD-2 | UTMN-1876 | 23 Jan 0200 - 1430 | 9.5 | 12.5 | 889429 |  | BHA | FOT | MMOT | RIG | 3200 | LOST COMMUNICATION WITH BHA, TROUBLESHOOT WITH NO SUCCESS.
1826 | 01/24/2022 | SINO-43L | UTMN-4808 | 24 Jan 0700 - 0830 | 1.5 | 1.5 | 889535 |  | RR | FOT | FL | RIG | 814 | EXCESS TIME WHILE DRILLING FOR CELLAR PUMP ISSUE.
1828 | 01/24/2022 | SINO-43L | UTMN-4808 | 24 Jan 2330 - 0500 | 5.5 | 5.5 | 889509 |  | TH | NARW | NA | TK2 | 1391 | HAD SUDDEN INCREASE IN TORQUE F/ 3 UP TO 19 KFT.LBS & STRING STALL.
1829 | 01/24/2022 | SINO-43L | UTMN-4808 | 24 Jan 0700 - 0830 | 1.5 | 1.5 | 889535 |  | RR | FOT | FL | RIG | 814 | EXCESS TIME WHILE DRILLING FOR CELLAR PUMP ISSUE.
1831 | 01/24/2022 | SP-257 | HZEM-141204 | 23 Jan 2200 - 0500 | 24 | 31 | 889305 |  | JF | HERR | CTRQ | FMC | 0 | TROUBLE SHOOT FRANKS CRT HYDRAULLICS.
1833 | 01/24/2022 | SP-260 | HZEM-141612 | 24 Jan 0545 - 0500 | 23.25 | 23.25 | 889506 |  | BHA | FOT | RSS | BHI | 10369 | BAKER RSS LUCIDA BROKEN, LOST IN THE HOLE BIT BOX OF BAKER RSS LUCIDA AND BIT.
1834 | 01/24/2022 | SP-306 | MNIF-865 | 24 Jan 2315 - 2345 | .5 | .5 | 889529 |  | LCIR | FRFM | NA | ARM | 3605 | WHILE DRLG AT 3,605' (ARUMA FM) ENCOUNTERED TOTAL LOSSES. -
1836 | 01/24/2022 | SP-306 | MNIF-865 | 24 Jan 0900 - 0915 | .25 | .25 | 889485 |  | LCIR | FRFM | NA | ARM | 3376 | WHILE DRLG AT 3,376' (ARUMA FM) ENCOUNTERED TOTAL LOSSES.
1837 | 01/24/2022 | SP-306 | MNIF-865 | 24 Jan 2315 - 2345 | .5 | .5 | 889529 |  | LCIR | FRFM | NA | ARM | 3605 | WHILE DRLG AT 3,605' (ARUMA FM) ENCOUNTERED TOTAL LOSSES. -
1838 | 01/24/2022 | SSA-51 | MNIF-254 | 24 Jan 0115 - 0400 | 2.75 | 2.75 | 889534 |  | CMT | HERR | NA | HCM | 13769 | WAIT ON HALL CONFIRMATION TEST TO START BATCH MIX CMT.
1840 | 01/24/2022 | SSA-51 | MNIF-254 | 24 Jan 0015 - 0115 | 1 | 1 | 889530 |  | RR | FOT | CSYS | RIG | 13769 | LEAK ON RIG CMT LINES.
1841 | 01/24/2022 | SSA-51 | MNIF-254 | 24 Jan 0115 - 0400 | 2.75 | 2.75 | 889534 |  | CMT | HERR | NA | HCM | 13769 | WAIT ON HALL CONFIRMATION TEST TO START BATCH MIX CMT.
1843 | 01/24/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 2230 | 17.5 | 210.5 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1845 | 01/24/2022 | SSA-5964 | SDGM-1158 | 24 Jan 1630 - 0500 | 12.5 | 12.5 | 889526 |  | BHA | FOT | RSS | SPS | 12952 | SPERRY RRS UNABLE TO BUILD INC
1847 | 01/25/2022 | ADC-14 | HRDH-1804 | 24 Jan 1800 - 1445 | 9.75 | 20.75 | 889585 |  | TF | FOT | TBG | ARM | 4812 | TUBING DRIFT ISSUE
1849 | 01/25/2022 | ADC-31 | SDGM-1163 | 23 Jan 0030 - 0500 | 19.75 | 40.25 | 889465 |  | TF | FOT | WLT | SWL | 13097 | WHILE RIH THE SLB MDT DUAL PACKER OBSERVED THE MOTOR ACTIVATING OPENING/ CLOSING INTERVAL VALVE, AND INFLATE VALVE OF THE PKR TRIPPED OUT (MALFUNCTION)
1851 | 01/25/2022 | ADC-42L | UTMN-2319 | 24 Jan 1545 - 0500 | 24 | 37.25 | 889625 |  | DRG | WNCA | NA | TK3 | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
1853 | 01/25/2022 | ADC-56L | UTMN-3011 | 25 Jan 0515 - 0500 | 23.75 | 23.75 | 889707 |  | WCNT | WC11 | NA | TK3 | 10753 | AT CASING POINT FLOW CHECK OBSERVED WELL FLOWING
1854 | 01/25/2022 | ADES-157 | HRDH-698 | 25 Jan 1415 - 2300 | 8.75 | 8.75 | 889666 |  | TF | FOT | WLT | BAW | 500 | BAKER ALTEX MOTOR STOPPED WORKING. POOH & REPLACED ALTEX ELECTRONIC MANDRILL & MOTOR. FUNCTION TEST TOOLS; NOT WORKING.
1856 | 01/25/2022 | ADES-157 | HRDH-698 | 24 Jan 1145 - 1230 | 2 | 3.75 | 889512 |  | WO | SRVC | NA | HWP | 0 | EXCESS TIME TO PROCESS DATA BY HES W/L
1857 | 01/25/2022 | ADES-157 | HRDH-698 | 25 Jan 1415 - 2300 | 8.75 | 8.75 | 889666 |  | TF | FOT | WLT | BAW | 500 | BAKER ALTEX MOTOR STOPPED WORKING. POOH & REPLACED ALTEX ELECTRONIC MANDRILL & MOTOR. FUNCTION TEST TOOLS; NOT WORKING.
1859 | 01/25/2022 | ADM-261 | MRJN-134 | 24 Jan 1615 - 0500 | 24 | 36.75 | 889537 |  | TF | FOT | STING | SCP | 6461 | UNABLE TO STING THRU TOL & PASS W/ SLB UPPER COMPLETION.
1861 | 01/25/2022 | ADM-262 | MRJN-121 | 23 Jan 0745 - 2030 | 15.5 | 60.75 | 889158 |  | DD | AINC | BHA | BHI | 12298 | BAKER RSS/BAKER BIT COMBINATION CONSTANTLY BUILDING ANGLE, UNABLE TO FOLLOW GOC STEERING INSTRUCTIONS.
1862 | 01/25/2022 | ADM-337 | MRJN-900 | 25 Jan 1530 - 0500 | 13.5 | 13.5 | 889667 |  | TF | FOT | WLT | SWL | 9275 | WHILE PERFORMING 1ST SAMPLING POINT, SCHLUMBERGER REPORT PROBLEM WITH REFERENCE TO LOSS OF POWER DUE TO LOSS OF COMMUNICATION BETWEEN PWCH AND DWCH
1864 | 01/25/2022 | ADM-337 | MRJN-900 | 25 Jan 1415 - 1530 | 1.25 | 1.25 | 889647 |  | RR | FOT | TDS | RIG | 7950 | HYDRAULIC OIL LEAK FROM THE TDS
1865 | 01/25/2022 | ADM-337 | MRJN-900 | 25 Jan 1530 - 0500 | 13.5 | 13.5 | 889667 |  | TF | FOT | WLT | SWL | 9275 | WHILE PERFORMING 1ST SAMPLING POINT, SCHLUMBERGER REPORT PROBLEM WITH REFERENCE TO LOSS OF POWER DUE TO LOSS OF COMMUNICATION BETWEEN PWCH AND DWCH
1867 | 01/25/2022 | ADM-656 | ABSF-95 | 25 Jan 0500 - 1600 | 11 | 11 | 889645 |  | TH | NARW | NA | ARM | 500 | HAD OBSTRUCTION INSIDE 7" CASING @ 500 FT LEAD TO LOST ESP CABLE READING.
1869 | 01/25/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 22.75 | 81.75 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
1870 | 01/25/2022 | ARO-3003 | SFNY-1150 | 25 Jan 0015 - 0130 | 1.25 | 1.25 | 889687 |  | JF | XTRI | CTRQ | FMC | 4105 | EXCESSIVE TIME FOR RUN 7'' LINER DUE TO FRANKS SINGLE JTS ELEVATOR NOT LATCH AROUND MOST COATED CSG WHILE PICK UP FROM CATWALK.
1872 | 01/25/2022 | ARO-3003 | SFNY-1150 | 25 Jan 0300 - 0315 | .25 | .25 | 889539 |  | TF | FOT | PEL | FMC | 4385 | FRANKS SINGLE JTS ELEVATOR DOOR LATCH JAMMED NOT RELEASED FROM CSG.
1873 | 01/25/2022 | ARO-3003 | SFNY-1150 | 25 Jan 1715 - 1745 | .5 | .5 | 889665 |  | TF | FOT | CRT | FMC | 857 | FRANKS TONGE JAM UNIT MALFUNCTION.
1874 | 01/25/2022 | ARO-3003 | SFNY-1150 | 25 Jan 0015 - 0130 | 1.25 | 1.25 | 889687 |  | JF | XTRI | CTRQ | FMC | 4105 | EXCESSIVE TIME FOR RUN 7'' LINER DUE TO FRANKS SINGLE JTS ELEVATOR NOT LATCH AROUND MOST COATED CSG WHILE PICK UP FROM CATWALK.
1876 | 01/25/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 24 | 95.5 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
1877 | 01/25/2022 | ARO-4001 | MRJN-537 | 24 Jan 2300 - 1030 | 5.5 | 8.5 | 889527 |  | RR | FOT | TDS | RIG | 7234 | WHILE DRILLING OBSERVED HIGH TEMP ALARM FOR TDS MOTOR B NON DRIVE END BEARING & SMOKE FROM TDS MOTOR B SIDE, TROUBLESHOOTING & DISENGAGE MOTOR B GEAR FROM TDS MAIN SHAFT (PLAN TO REPAIR TDS MOTOR B WHILE INSIDE CSG SHOE).
1879 | 01/25/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 18.5 | 327 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1880 | 01/25/2022 | ARO-4001 | MRJN-537 | 24 Jan 2300 - 1030 | 5.5 | 8.5 | 889527 |  | RR | FOT | TDS | RIG | 7234 | WHILE DRILLING OBSERVED HIGH TEMP ALARM FOR TDS MOTOR B NON DRIVE END BEARING & SMOKE FROM TDS MOTOR B SIDE, TROUBLESHOOTING & DISENGAGE MOTOR B GEAR FROM TDS MAIN SHAFT (PLAN TO REPAIR TDS MOTOR B WHILE INSIDE CSG SHOE).
1882 | 01/25/2022 | DPS-4 | SAHB-34 | 24 Jan 0900 - 0500 | 24 | 44 | 889507 |  | BHA | FOT | STZRM | RIG | 14132 | FOUND ONE ROLLER SHAFT & BLOCK MISSING FROM BOTTOM ROLLER REAMER.
1884 | 01/25/2022 | DPS-46 | SDGM-1177 | 25 Jan 0830 - 1200 | 3.5 | 3.5 | 889513 |  | RR | FOT | TDS | RIG | 12334 | ELECTRICAL FAULT ON TDS SERVICE LOOP CONNECTION.
1886 | 01/25/2022 | HI-9 | MRJN-228 | 21 Jan 0500 - 0500 | 24 | 110 | 888988 |  | TF | FOT | WPSTK | WI3 | 9417 | WIS PREMATURE FAILURE OF TRI MILL ASSEMBLY RESULTING IN IMPROPER 7" WINDOW CUT AND UNABLE TO CLEAN METAL JUNK FROM RAT HOLE.
1887 | 01/25/2022 | NBR-797S | UTMN-3145 | 24 Jan 0245 - 0030 | 19.5 | 21.75 | 889531 |  | TF | FOT | CUT | NWL | 15163 | POWER LOST AT TOOL DOWNHOLE TO WELLTECH TRACTOR W/MPC TOOLS WHILE TRACTORING INSIDE STUCK 4" DP @ 15,163FT
1889 | 01/25/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 4.5 | 307.75 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
1890 | 01/25/2022 | NBR-797S | UTMN-3145 | 24 Jan 0245 - 0030 | 19.5 | 21.75 | 889531 |  | TF | FOT | CUT | NWL | 15163 | POWER LOST AT TOOL DOWNHOLE TO WELLTECH TRACTOR W/MPC TOOLS WHILE TRACTORING INSIDE STUCK 4" DP @ 15,163FT
1892 | 01/25/2022 | PA-326S | SAHB-32 | 25 Jan 0015 - 0145 | 1.5 | 1.5 | 889725 |  | TF | FOT | CRT | GOC | 584 | AL-GHAITH CRT ENGAGED INSIDE CSG JT AND CAN NOT RELEASE WHILE RUN 9 5/8" CSG.
1894 | 01/25/2022 | PA-785S | QTIF-24 | 24 Jan 1330 - 1600 | 9.5 | 25 | 889536 |  | RR | FOT | TDS | RIG | 6746 | RIG TOP DRIVE FAILURE IN INVERTER, ENCODER SENSORS.
1896 | 01/25/2022 | SINO-12L | HRDH-447 | 25 Jan 0600 - 1515 | 9.25 | 9.25 | 889727 |  | TF | FOT | TBG | TK1 | 9540 | TDS SAVER SUB PIN BROKEN INSIDE DP BOX WHILE CONNECTING TDS.
1898 | 01/25/2022 | SINO-43L | UTMN-4808 | 24 Jan 2330 - 2230 | 17.5 | 23 | 889509 |  | TH | NARW | NA | TK2 | 1391 | HAD SUDDEN INCREASE IN TORQUE F/ 3 UP TO 19 KFT.LBS & STRING STALL.
1900 | 01/25/2022 | SL-7 | ZULF-1335 | 25 Jan 2345 - 0245 | 3 | 3 | 889706 |  | JF | XTRI | BOP | RIG | 0 | EXCESSIVE TIME TO RIG UP 30" DIVERTER SYSTEM.
1902 | 01/25/2022 | SND-1502 | HWYH-32 | 25 Jan 0600 - 0500 | 23 | 23 | 889511 |  | TF | FOT | HGRL | BLH | 8047 | UNABLE TO SET BAKER 4-1/2" LINER HANGER
1904 | 01/25/2022 | SND-2004 | BRRI-528 | 25 Jan 1845 - 2215 | 3.5 | 3.5 | 889685 |  | RR | FOT | HSYS | RIG | 790 | EZY TORQUE HPU MOTOR FAILED TO SUPPLY REQUIRED PRESSURE TO MAKE UP DRILL COLLARS.
1906 | 01/25/2022 | SNT-025 | SFNY-520 | 25 Jan 0500 - 0000 | 19 | 19 | 889728 |  | WON | WTHR | NA | ARM | 0 | WAIT ON SUITABLE WEATHER AND FORECAST TO COMPLETE BACKLOAD & MOVE RIG TO SFNY-520
1908 | 01/25/2022 | SP-257 | HZEM-141204 | 23 Jan 2200 - 0500 | 24 | 55 | 889305 |  | JF | HERR | CTRQ | FMC | 0 | TROUBLE SHOOT FRANKS CRT HYDRAULLICS.
1910 | 01/25/2022 | SP-260 | HZEM-141612 | 24 Jan 0545 - 0500 | 24 | 47.25 | 889506 |  | BHA | FOT | RSS | BHI | 10369 | BAKER RSS LUCIDA BROKEN, LOST IN THE HOLE BIT BOX OF BAKER RSS LUCIDA AND BIT.
1912 | 01/25/2022 | SP-306 | MNIF-865 | 25 Jan 0330 - 0500 | 1.5 | 1.5 | 889668 |  | DD | ACDI | BHA | WDS | 4309 | WHILE DRILLING 16" HOLE AT 4,309' HAD BAD DECODING AND LOST MWD SIGNAL
1914 | 01/25/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 10.5 | 221 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1916 | 01/25/2022 | SSA-5964 | SDGM-1158 | 24 Jan 1630 - 0430 | 22 | 34.5 | 889526 |  | BHA | FOT | RSS | SPS | 12952 | SPERRY RRS UNABLE TO BUILD INC
1918 | 01/25/2022 | ZPEC-2 | HZEM-838 | 25 Jan 1430 - 0500 | 14.5 | 14.5 | 889646 |  | WH | FOT | TREE | CAM | 5858 | 9"CAMERON TREE HAD SLIGHT LEAKING WHILE PRESSURE TEST
1920 | 01/26/2022 | ADC-12 | ABQQ-308 | 26 Jan 0500 - 1500 | 5 | 5 | 889845 |  | TF | FOT | CTRQ | MSD | 200 | AL-MASOOD TBG POWER TONG FAILURE
1922 | 01/26/2022 | ADC-21 | MHWZ-125104 | 24 Jan 0630 - 0500 | 24 | 70.5 | 889605 |  | JF | CEDE | NA | BCM | 10305 | SOFT CEMENT ON THE SHOE TRACK FROM 1ST STAGE CEMENT JOB
1924 | 01/26/2022 | ADC-31 | SDGM-1163 | 23 Jan 0030 - 0500 | 24 | 64.25 | 889465 |  | TF | FOT | WLT | SWL | 13097 | WHILE RIH THE SLB MDT DUAL PACKER OBSERVED THE MOTOR ACTIVATING OPENING/ CLOSING INTERVAL VALVE, AND INFLATE VALVE OF THE PKR TRIPPED OUT (MALFUNCTION)
1926 | 01/26/2022 | ADC-32 | SDGM-1139 | 26 Jan 1000 - 1300 | 3 | 3 | 889886 |  | RR | FOT | CSYS | RIG | 11300 | LEAK ON WASH PIPE & SAVER SUB
1928 | 01/26/2022 | ADC-36 | SDGM-1186 | 26 Jan 0500 - 0500 | 16.5 | 16.5 | 889805 |  | BOP | FOT | BOP | RIG | 13833 | DURING BOPE TEST, WHILE ATTEMPTING TO P/T UPPER PIPE RAM TO 300/8500 PSI - OBSERVED LEAKAGE FROM THE CONNECTION BETWEEN MUD CROSS AND UPPER DOUBLE RAMS, RUN RTTS AND CHANGE MUD CROSS.
1930 | 01/26/2022 | ADC-42L | UTMN-2319 | 24 Jan 1545 - 0500 | 24 | 61.25 | 889625 |  | DRG | WNCA | NA | TK3 | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
1932 | 01/26/2022 | ADC-55L | UTMN-3076 | 26 Jan 1130 - 1200 | .5 | .5 | 889543 |  | RR | FOT | CSYS | RIG | 11362 | PREPAIR MUD PMUP#1 AND MUD PUMP#3
1934 | 01/26/2022 | ADC-56L | UTMN-3011 | 25 Jan 0515 - 1345 | 8.75 | 32.5 | 889707 |  | WCNT | WC11 | NA | TK3 | 10753 | AT CASING POINT FLOW CHECK OBSERVED WELL FLOWING
1936 | 01/26/2022 | ADC-66L | HWYH-1223 | 26 Jan 0845 - 0045 | 7.75 | 7.75 | 889905 |  | BHA | FOT | LWD | SDM | 18900 | HAD BAD SIGNAL FOR LOGGING DATA WHILE DRILLING.
1938 | 01/26/2022 | ADM-337 | MRJN-900 | 26 Jan 2030 - 0500 | 3.75 | 3.75 | 889868 |  | RR | FOT | PSYS | RIG | 8260 | WHILE PERFORM TLC/MDT LOGGING, WIRELINE UNIT ENCOUNTERED SHUTDOWN, PULL TO SHOE, TAKE DIESEL SAMPLE FROM RIG SUPPLY TO SCHLUMBERGER UNIT & OBSERVE TRACES OF H2O MIXED WITH FUEL SUPPLY
1940 | 01/26/2022 | ADM-656 | ABSF-95 | 25 Jan 0500 - 0430 | 13 | 24 | 889645 |  | TH | NARW | NA | ARM | 500 | HAD OBSTRUCTION INSIDE 7" CASING @ 500 FT LEAD TO LOST ESP CABLE READING.
1942 | 01/26/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 24 | 105.75 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
1943 | 01/26/2022 | ARO-2003 | MNIF-735 | 26 Jan 1100 - 0500 | 18 | 18 | 889785 |  | RR | FOT | HSYS | RIG | 0 | BEARING IN JACKING SYSTEM STARBOARD AFT LEG BROKE
1945 | 01/26/2022 | ARO-2003 | MNIF-735 | 19 Jan 0500 - 1100 | 6 | 150 | 888766 |  | WO | SRVC | NA | ARN | 0 | WAITING TO PERFORM SEABED SURVEY.
1946 | 01/26/2022 | ARO-2003 | MNIF-735 | 26 Jan 1100 - 0500 | 18 | 18 | 889785 |  | RR | FOT | HSYS | RIG | 0 | BEARING IN JACKING SYSTEM STARBOARD AFT LEG BROKE
1948 | 01/26/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 24 | 119.5 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
1949 | 01/26/2022 | ARO-4001 | MRJN-537 | 24 Jan 2300 - 1300 | 3.25 | 11.75 | 889527 |  | RR | FOT | TDS | RIG | 7234 | WHILE DRILLING OBSERVED HIGH TEMP ALARM FOR TDS MOTOR B NON DRIVE END BEARING & SMOKE FROM TDS MOTOR B SIDE, TROUBLESHOOTING & DISENGAGE MOTOR B GEAR FROM TDS MAIN SHAFT (PLAN TO REPAIR TDS MOTOR B WHILE INSIDE CSG SHOE).
1951 | 01/26/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 20.75 | 347.75 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
1952 | 01/26/2022 | ARO-4001 | MRJN-537 | 24 Jan 2300 - 1300 | 3.25 | 11.75 | 889527 |  | RR | FOT | TDS | RIG | 7234 | WHILE DRILLING OBSERVED HIGH TEMP ALARM FOR TDS MOTOR B NON DRIVE END BEARING & SMOKE FROM TDS MOTOR B SIDE, TROUBLESHOOTING & DISENGAGE MOTOR B GEAR FROM TDS MAIN SHAFT (PLAN TO REPAIR TDS MOTOR B WHILE INSIDE CSG SHOE).
1954 | 01/26/2022 | BB-84A | MRJN-588 | 26 Jan 0215 - 0500 | 2.75 | 2.75 | 889869 |  | RR | FOT | TDS | RIG | 0 | TDS SWIVEL PACKING LEAKING WHILE ATTEMPTING TO PRESSURE TEST STANDPIPE MANIFOLD
1956 | 01/26/2022 | CG-1 | ZULF-1201 | 26 Jan 2145 - 0500 | 7.25 | 7.25 | 889867 |  | UPRA | GRF | CSYS | RIG | 7660 | RIG SUPPLY CEMENT HOSE GOT BLOCKED. UNABLE TO SUPPLY CEMENT TO CEMENT UNIT. CIRCULATE OUT CEMENT & UNPLUG CEMENT HOSE. MIX NEW BHI SPACER & MIX WATER MEANWHILE INVESTIGATE WHY HOSE BECAME BLOCKED.
1958 | 01/26/2022 | DPS-4 | SAHB-34 | 24 Jan 0900 - 1300 | 8 | 52 | 889507 |  | BHA | FOT | STZRM | RIG | 14132 | FOUND ONE ROLLER SHAFT & BLOCK MISSING FROM BOTTOM ROLLER REAMER.
1960 | 01/26/2022 | EXL-IVA | SFNY-4010 | 25 Jan 1700 - 0500 | 11.25 | 23.25 | 889746 |  | TF | FOT | WLT | BAW | 5334 | BH WIRELINE DID NOT GET REQUIRED SAMPLE DUE TO FAILURE OF TOOL
1962 | 01/26/2022 | HI-4 | BRRI-780 | 25 Jan 0200 - 0530 | .5 | 3.5 | 889729 |  | LROP | ETRQ | BHA | SDM | 8800 | SCHLUMBERGER RE-LOGGING HOLE @ 100 FT / HOUR, TOOK ESCESS TIME RE-LOGGING. DUE TO POOR LOG QUAILITY.
1964 | 01/26/2022 | HI-5 | MHRH-60 | 26 Jan 1030 - 0500 | 18.5 | 18.5 | 889907 |  | TF | TOMD | STRG | RIG | 6822 | DOUBLE PIN X-OVER 4-1/2" REG CONNECTION TWISTED OFF WHILE MILLING 8-1/2" CSG WINDOW
1966 | 01/26/2022 | HI-9 | MRJN-228 | 21 Jan 0500 - 0500 | 24 | 134 | 888988 |  | TF | FOT | WPSTK | WI3 | 9417 | WIS PREMATURE FAILURE OF TRI MILL ASSEMBLY RESULTING IN IMPROPER 7" WINDOW CUT AND UNABLE TO CLEAN METAL JUNK FROM RAT HOLE.
1967 | 01/26/2022 | PA-326S | SAHB-32 | 26 Jan 1215 - 1500 | 2.75 | 2.75 | 889826 |  | TF | FOT | CRT | GOC | 5748 | TRIED TO REMOVE CRT PACKER CUP AT SEVERAL TIMES NO SUCCESS THEN LAID DOWN CRT TOOL & REPLACED BY NEW ONE.
1969 | 01/26/2022 | PA-326S | SAHB-32 | 26 Jan 0845 - 1030 | 1.75 | 1.75 | 889542 |  | TF | FOT | CRT | GOC | 5140 | GOT CRT LEAKING JUST WHEN START CIRCULATE PRIOR ENTERING INTO OPEN HOLE SO REMOVED & REPLACED BY NEW ONE.
1970 | 01/26/2022 | PA-326S | SAHB-32 | 26 Jan 1215 - 1500 | 2.75 | 2.75 | 889826 |  | TF | FOT | CRT | GOC | 5748 | TRIED TO REMOVE CRT PACKER CUP AT SEVERAL TIMES NO SUCCESS THEN LAID DOWN CRT TOOL & REPLACED BY NEW ONE.
1972 | 01/26/2022 | RBP-50A | HSBH-58 | 25 Jan 0100 - 1700 | 12 | 16 | 889765 |  | UPRA | OTH | NA | RIG | 13243 | WHILE JACKING RIG DOWN FOR WATER INTEGRITY TEST OBSERVED PORT LEG BOW GEAR BOX FAILURE, BULL GEAR DAMAGED AND 2 TEETH MISSING FROM CHORD/JACKING COLUMN.
1974 | 01/26/2022 | SINO-33L | KHRS-365 | 25 Jan 0300 - 0045 | 12.25 | 14.25 | 889669 |  | TH | NARW | NA | TK2 | 2020 | POOH FREE W/16" ROTARY DRLG ASSY WIPER TRIP T/ 2,003', HAD 20 KLB OVER PULL GO DOWN TO 2,020' HAD STRG STUCK , WORK ON SAME WITH TQ. AND JAR DOWN STRG. TILL GET STRG. FREE
1976 | 01/26/2022 | SINO-46L | SHYB-223 | 26 Jan 1500 - 0500 | 14 | 14 | 889866 |  | BHA | FOT | MWD | BHI | 13105 | LOST COMMUNICATION WITH MWD TOOL
1978 | 01/26/2022 | SND-1502 | HWYH-32 | 25 Jan 0600 - 0500 | 22 | 45 | 889511 |  | TF | FOT | HGRL | BLH | 8047 | UNABLE TO SET BAKER 4-1/2" LINER HANGER
1980 | 01/26/2022 | SND-2001 | SDGM-1240 | 24 Jan 2300 - 0500 | 24 | 54 | 889825 |  | JF | CEDE | NA | SJC | 14832 | BAD CEMENT QUALITY (FREE PIPE) FOR 4-1/2" LINER. SIDE TRACK FOR NEW HOLE.
1981 | 01/26/2022 | SP-257 | HZEM-141204 | 26 Jan 1415 - 0030 | 2.5 | 2.5 | 889827 |  | TF | FOT | CTRQ | FMC | 2200 | UNABLE TO FILL OR BREAK CIRCULATION DUE TO CRT PACKER FAILURE.
1983 | 01/26/2022 | SP-257 | HZEM-141204 | 23 Jan 2200 - 1030 | 5.5 | 60.5 | 889305 |  | JF | HERR | CTRQ | FMC | 0 | TROUBLE SHOOT FRANKS CRT HYDRAULLICS.
1984 | 01/26/2022 | SP-257 | HZEM-141204 | 26 Jan 1415 - 0030 | 2.5 | 2.5 | 889827 |  | TF | FOT | CTRQ | FMC | 2200 | UNABLE TO FILL OR BREAK CIRCULATION DUE TO CRT PACKER FAILURE.
1986 | 01/26/2022 | SP-260 | HZEM-141612 | 24 Jan 0545 - 0500 | 24 | 71.25 | 889506 |  | BHA | FOT | RSS | BHI | 10369 | BAKER RSS LUCIDA BROKEN, LOST IN THE HOLE BIT BOX OF BAKER RSS LUCIDA AND BIT.
1987 | 01/26/2022 | SP-306 | MNIF-865 | 26 Jan 1530 - 0500 | 13.5 | 13.5 | 889885 |  | BHA | FOT | DC | RIG | 100 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY.
1989 | 01/26/2022 | SP-306 | MNIF-865 | 25 Jan 0330 - 1530 | 10.5 | 12 | 889668 |  | DD | ACDI | BHA | WDS | 4309 | WHILE DRILLING 16" HOLE AT 4,309' HAD BAD DECODING AND LOST MWD SIGNAL,
1990 | 01/26/2022 | SP-306 | MNIF-865 | 26 Jan 1530 - 0500 | 13.5 | 13.5 | 889885 |  | BHA | FOT | DC | RIG | 100 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY.
1992 | 01/26/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 24 | 245 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
1994 | 01/26/2022 | T914 | HWYH-512 | 26 Jan 1015 - 1145 | 1.5 | 1.5 | 889865 |  | HC | IPDF | NA | GDF | 6579 | MUD PROPERTIES NOT IN COMPLIANCE WITH PROGRAM
1996 | 01/26/2022 | WCL-83 | MRJN-831 | 26 Jan 0015 - 0500 | 4.75 | 4.75 | 889906 |  | LCIR | UVLC | NA | ARM | 13192 | AFTER RETRIEVING HLB RBP, OBSERVED 360 BPH LOSSES, ATTEMPTED TO CURE LOSSES WITH NO SUCCESS, SET HLB RBP TO MIX & BUILD 81 PCF CACL2 BRINE.
1998 | 01/26/2022 | ZPEC-2 | HZEM-838 | 25 Jan 1430 - 0500 | 24 | 38.5 | 889646 |  | WH | FOT | TREE | CAM | 5858 | 9"CAMERON TREE HAD SLIGHT LEAKING WHILE PRESSURE TEST
1999 | 01/27/2022 | ADC-31 | SDGM-1163 | 27 Jan 1900 - 0500 | 10 | 10 | 890025 |  | TF | FOT | WLT | SWL | 13170 | AFTER MOVING TO THE SECOND SAMPLE POINT, ATTEMPTED TO INFLATE THE DUAL PACKER BUT FOUND THAT THE INFLATE VALVE WAS JAMMED CLOSED (MALFUNCTIONING) NOT ABLE TO OPERATE.
2001 | 01/27/2022 | ADC-31 | SDGM-1163 | 23 Jan 0030 - 0800 | 3 | 67.25 | 889465 |  | TF | FOT | WLT | SWL | 13097 | WHILE RIH THE SLB MDT DUAL PACKER OBSERVED THE MOTOR ACTIVATING OPENING/ CLOSING INTERVAL VALVE, AND INFLATE VALVE OF THE PKR TRIPPED OUT (MALFUNCTION)
2002 | 01/27/2022 | ADC-31 | SDGM-1163 | 27 Jan 1900 - 0500 | 10 | 10 | 890025 |  | TF | FOT | WLT | SWL | 13170 | AFTER MOVING TO THE SECOND SAMPLE POINT, ATTEMPTED TO INFLATE THE DUAL PACKER BUT FOUND THAT THE INFLATE VALVE WAS JAMMED CLOSED (MALFUNCTIONING) NOT ABLE TO OPERATE.
2004 | 01/27/2022 | ADC-36 | SDGM-1186 | 26 Jan 0500 - 0030 | 8.75 | 25.25 | 889805 |  | BOP | FOT | BOP | RIG | 13833 | DURING BOPE TEST, WHILE ATTEMPTING TO P/T UPPER PIPE RAM TO 300/8500 PSI - OBSERVED LEAKAGE FROM THE CONNECTION BETWEEN MUD CROSS AND UPPER DOUBLE RAMS, RUN RTTS AND CHANGE MUD CROSS.
2006 | 01/27/2022 | ADC-42L | UTMN-2319 | 24 Jan 1545 - 0500 | 24 | 85.25 | 889625 |  | DRG | WNCA | NA | TK3 | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
2007 | 01/27/2022 | ADC-45 | KHRS-82 | 27 Jan 2230 - 0500 | 6.5 | 6.5 | 890066 |  | TF | FOT | PKR | BAL | 3982 | WHILE PT 3-1/2" PX PLUG TO 500 PSI - HAD PRAXIS PKR ACCEDINTLY SET.
2009 | 01/27/2022 | ADC-45 | KHRS-82 | 27 Jan 2030 - 2230 | 2 | 2 | 890065 |  | TF | FOT | PLUGT | GD1 | 4011 | TRIED TO RETRIVE PRONG OF 3-1/2" PX-PLUG WITHOUT SUCCESS.
2010 | 01/27/2022 | ADC-45 | KHRS-82 | 27 Jan 2230 - 0500 | 6.5 | 6.5 | 890066 |  | TF | FOT | PKR | BAL | 3982 | WHILE PT 3-1/2" PX PLUG TO 500 PSI - HAD PRAXIS PKR ACCEDINTLY SET.
2012 | 01/27/2022 | ADC-66L | HWYH-1223 | 26 Jan 0845 - 0130 | 15.25 | 23 | 889905 |  | BHA | FOT | LWD | SDM | 18900 | HAD BAD SIGNAL FOR LOGGING DATA WHILE DRILLING.
2014 | 01/27/2022 | ADC-68L | KRSN-705 | 27 Jan 2345 - 0500 | 5.25 | 5.25 | 889972 |  | BHA | FOT | MMOT | SDM | 3199 | OBSEREVD DROP IN ROP FROM AVG. 30 FPH TO 5 FPH AND NO DIFFERENTIAL PRESSURE WITH 30 KLBS WOB.
2016 | 01/27/2022 | ADM-337 | MRJN-900 | 26 Jan 2030 - 1000 | 5 | 8.75 | 889868 |  | RR | FOT | PSYS | RIG | 8260 | WHILE PERFORM TLC/MDT LOGGING, WIRELINE UNIT ENCOUNTERED SHUTDOWN, PULL TO SHOE, TAKE DIESEL SAMPLE FROM RIG SUPPLY TO SCHLUMBERGER UNIT & OBSERVE TRACES OF H2O MIXED WITH FUEL SUPPLY
2018 | 01/27/2022 | ADM-655 | BRRI-150 | 27 Jan 1830 - 0045 | 6.25 | 6.25 | 889968 |  | WON | WTHR | NA | ARM | 0 | -UNABLE TO CONT. OFFLOAD FLOW BACK EQUIPMENT FROM BOAT DUE TO HIGH WIND SPEED 22-25 KNTS AND CURRENT.
2020 | 01/27/2022 | AOD-11 | SFNY-1506 | 26 Jan 1915 - 0500 | 24 | 33.75 | 889970 |  | TF | XTTE | SLICK | ARM | 4573 | ATTEMPT TO LATCH INTO ENTERWELL PLUG. UNABLE TO GET DOWN. ADD ADDITIONAL SINKER BAR & RIH. UNABLE TO ENGAGE
2022 | 01/27/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 24 | 129.75 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
2024 | 01/27/2022 | ARO-2003 | MNIF-735 | 26 Jan 1100 - 0500 | 24 | 42 | 889785 |  | RR | FOT | HSYS | RIG | 0 | BEARING IN JACKING SYSTEM STARBOARD AFT LEG BROKE
2026 | 01/27/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 23.5 | 143 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
2028 | 01/27/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 0500 | 24 | 371.75 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
2030 | 01/27/2022 | BB-84A | MRJN-588 | 26 Jan 0215 - 0700 | 2 | 4.75 | 889869 |  | RR | FOT | TDS | RIG | 0 | TDS SWIVEL PACKING LEAKING WHILE ATTEMPTING TO PRESSURE TEST STANDPIPE MANIFOLD
2032 | 01/27/2022 | CG-1 | ZULF-1201 | 26 Jan 2145 - 0730 | 2.5 | 9.75 | 889867 |  | UPRA | GRF | CSYS | RIG | 7660 | RIG SUPPLY CEMENT HOSE GOT BLOCKED. UNABLE TO SUPPLY CEMENT TO CEMENT UNIT. CIRCULATE OUT CEMENT & UNPLUG CEMENT HOSE. MIX NEW BHI SPACER & MIX WATER MEANWHILE INVESTIGATE WHY HOSE BECAME BLOCKED.
2034 | 01/27/2022 | DQ-47 | KHRS-270 | 26 Jan 0200 - 1330 | 8.5 | 11.5 | 890005 |  | CELR | UNSF | NA | ARM | 344 | DRILLED 22" HOLE WITH SPUD MUD & FULL RETURN TO 299' THEN HAD TOTAL LOSSES, CONT. BLIND DRILLED 22" HOLE TO 344' THEN OBSERVED CELLAR COLLAPSE HALF MOON SHAPE AROUND 24" CSG FALL +/-5' FROM CELLAR BTM.
2036 | 01/27/2022 | EXL-IVA | SFNY-4010 | 25 Jan 1700 - 1700 | 12 | 35.25 | 889746 |  | TF | FOT | WLT | BAW | 5334 | BH WIRELINE DID NOT GET REQUIRED SAMPLE DUE TO FAILURE OF TOOL
2038 | 01/27/2022 | HI-5 | MHRH-60 | 26 Jan 1030 - 0130 | 20.5 | 39 | 889907 |  | TF | TOMD | STRG | RIG | 6822 | DOUBLE PIN X-OVER 4-1/2" REG CONNECTION TWISTED OFF WHILE MILLING 8-1/2" CSG WINDOW
2040 | 01/27/2022 | HI-9 | MRJN-228 | 21 Jan 0500 - 0500 | 24 | 158 | 888988 |  | TF | FOT | WPSTK | WI3 | 9417 | WIS PREMATURE FAILURE OF TRI MILL ASSEMBLY RESULTING IN IMPROPER 7" WINDOW CUT AND UNABLE TO CLEAN METAL JUNK FROM RAT HOLE.
2042 | 01/27/2022 | NBR-115S | HRDH-2140 | 27 Jan 1330 - 1500 | 1.5 | 1.5 | 889965 |  | RR | LHFL | HSYS | RIG | 12395 | HYDRAULIC FEED LINE FOR ADJUSTING THE PIPE HANDLER LEAKING HYDRAULIC FLUID
2044 | 01/27/2022 | NBR-196S | SDGM-1174 | 27 Jan 0100 - 0500 | 4 | 4 | 890026 |  | STUK | HINW | WLT | SWL | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
2046 | 01/27/2022 | NBR-575S | HRDH-2323 | 27 Jan 1545 - 1945 | 4 | 4 | 889967 |  | STUK | LCRW | STRG | ARM | 2018 | STRING BECAME STUCK AFTER CONNECTION DURING BLIND DRILLING WITH INHIBITED PHPA MUD
2048 | 01/27/2022 | NBR-987S | ABTL-2 | 27 Jan 1745 - 0100 | 7.25 | 7.25 | 890027 |  | TF | FOT | BP | HWP | 13725 | ATTEMPT TO SET 4.5" EZSV BRIDGE PLUG WITHOUT SUCCESS. TROUBLE SHOOTING ON COMMUNICATION BETWEEN RUNNING TOOL AND BRIDGE PLUG.
2050 | 01/27/2022 | PA-70S | TINT-87 | 27 Jan 1515 - 2015 | 5 | 5 | 889969 |  | RR | FOT | DWKS | RIG | 16646 | DRAW-WORKS DOWN DUE TO ONE TRACTION MOTOR FAILURE.
2052 | 01/27/2022 | RBP-50A | HSBH-58 | 25 Jan 0100 - 0500 | 13 | 41 | 889765 |  | UPRA | OTH | NA | RIG | 13243 | WHILE JACKING RIG DOWN FOR WATER INTEGRITY TEST OBSERVED PORT LEG BOW GEAR BOX FAILURE, BULL GEAR DAMAGED AND 2 TEETH MISSING FROM CHORD/JACKING COLUMN.
2054 | 01/27/2022 | SINO-12L | HRDH-447 | 27 Jan 0100 - 0130 | .5 | .5 | 890046 |  | TF | FOT | TBG | TK1 | 1965 | OBSERVED LEAKS ON POWER TONG HYDRAULIC HOSE
2056 | 01/27/2022 | SINO-46L | SHYB-223 | 26 Jan 1500 - 2115 | 16.25 | 30.25 | 889866 |  | BHA | FOT | MWD | BHI | 13105 | LOST COMMUNICATION WITH MWD TOOL
2058 | 01/27/2022 | SND-2001 | SDGM-1240 | 24 Jan 2300 - 0500 | 24 | 78 | 889825 |  | JF | CEDE | NA | SJC | 14832 | BAD CEMENT QUALITY (FREE PIPE) FOR 4-1/2" LINER. SIDE TRACK FOR NEW HOLE.
2060 | 01/27/2022 | SND-3001 | MHWZ-167102 | 27 Jan 1215 - 0500 | 16.75 | 16.75 | 890029 |  | TF | FOT | CSG | ARM | 1557 | WHILE MAKING JOINT OF 18-5/8" CSG ON RIG FLOOR NOTICED STRING JUMP IN SLIPS. PICKED UP AND HOOKLOAD GONE, OBSERVED THE CASING THREADS PARTED OFF JOINT IN CELLAR
2062 | 01/27/2022 | SP-260 | HZEM-141612 | 24 Jan 0545 - 0500 | 24 | 95.25 | 889506 |  | BHA | FOT | RSS | BHI | 10369 | BAKER RSS LUCIDA BROKEN, LOST IN THE HOLE BIT BOX OF BAKER RSS LUCIDA AND BIT.
2063 | 01/27/2022 | SP-306 | MNIF-865 | 27 Jan 1400 - 0445 | 14.75 | 14.75 | 889985 |  | DSF | COPS | STRG | ARM | 4309 | WHILE WORKING ON STRING STUCK, STRING PARTED AND FALLED DOWN TO BTM.
2065 | 01/27/2022 | SP-306 | MNIF-865 | 25 Jan 0330 - 0500 | 7 | 19 | 889668 |  | DD | ACDI | BHA | WDS | 4309 | WHILE DRILLING 16" HOLE AT 4,309' HAD BAD DECODING AND LOST MWD SIGNAL,
2066 | 01/27/2022 | SP-306 | MNIF-865 | 26 Jan 1530 - 0715 | 2.25 | 15.75 | 889885 |  | BHA | FOT | DC | RIG | 100 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY.
2067 | 01/27/2022 | SP-306 | MNIF-865 | 27 Jan 1400 - 0445 | 14.75 | 14.75 | 889985 |  | DSF | COPS | STRG | ARM | 4309 | WHILE WORKING ON STRING STUCK, STRING PARTED AND FALLED DOWN TO BTM.
2069 | 01/27/2022 | SSA-102 | QTIF-699 | 27 Jan 1730 - 1830 | 1 | 1 | 890028 |  | TF | FOT | CTRQ | MSD | 2800 | FAILURE OF AL MASAOOD POWER TONG WHILE M/U CSG. CHANGE SSNE WITH BACK UP ONE.
2071 | 01/27/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 268.5 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
2073 | 01/27/2022 | WCL-83 | MRJN-831 | 26 Jan 0015 - 0500 | 24 | 28.75 | 889906 |  | LCIR | UVLC | NA | ARM | 13192 | AFTER RETRIEVING HLB RBP, OBSERVED 360 BPH LOSSES, ATTEMPTED TO CURE LOSSES WITH NO SUCCESS, SET HLB RBP TO MIX & BUILD 81 PCF CACL2 BRINE.
2075 | 01/27/2022 | ZPEC-2 | HZEM-838 | 25 Jan 1430 - 1200 | 7 | 45.5 | 889646 |  | WH | FOT | TREE | CAM | 5858 | 9"CAMERON TREE HAD SLIGHT LEAKING WHILE PRESSURE TEST
2077 | 01/28/2022 | ADC-31 | SDGM-1163 | 27 Jan 1900 - 0500 | 23.5 | 33.5 | 890025 |  | TF | FOT | WLT | SWL | 13170 | AFTER MOVING TO THE SECOND SAMPLE POINT, ATTEMPTED TO INFLATE THE DUAL PACKER BUT FOUND THAT THE INFLATE VALVE WAS JAMMED CLOSED (MALFUNCTIONING) NOT ABLE TO OPERATE.
2079 | 01/28/2022 | ADC-45 | KHRS-82 | 27 Jan 2030 - 0500 | 24 | 32.5 | 890066 |  | TF | FOT | PKR | BAL | 3982 | HAD PRAXIS PKR ACCEDINTLY SET.
2081 | 01/28/2022 | ADC-66L | HWYH-1223 | 28 Jan 2230 - 0100 | 2.5 | 2.5 | 890134 |  | STUK | KSFM | STRG | TK3 | 17930 | BACK REAM F/ 17,875 FT TO 17,830 FT. OBSERVE STRING STUCK WHILE BACKREAMING AT 17,830 FT.
2083 | 01/28/2022 | ADC-68L | KRSN-705 | 27 Jan 2345 - 1345 | 8.25 | 13.5 | 889972 |  | DSF | FOT | STRG | TK3 | 3199 | OBSEREVD DROP IN ROP FROM AVG. 30 FPH TO 5 FPH AND NO DIFFERENTIAL PRESSURE WITH 30 KLBS WOB.
2085 | 01/28/2022 | ADES-174 | HRDH-2184 | 28 Jan 1330 - 0500 | 15.5 | 15.5 | 890185 |  | BHA | FOT | MWD | WDS | 13698 | OST SIGNAL FROM LWD/MWD SENSORS DOWNHOLE. ATTEMPT TO TAKE SURVEY - NO SUCCESS
2087 | 01/28/2022 | ADES-798 | JFYN-13 | 28 Jan 1800 - 0500 | 11 | 11 | 890127 |  | BHA | FOT | MWD | SPS | 15622 | MWD LOST COMMUNICATION WITH RSS. MANY TRIALS TO REGAIN SIGNAL, NO SUCCESS.
2089 | 01/28/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 24 | 153.75 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
2091 | 01/28/2022 | ARO-2003 | MNIF-735 | 26 Jan 1100 - 0500 | 24 | 66 | 889785 |  | RR | FOT | HSYS | RIG | 0 | BEARING IN JACKING SYSTEM STARBOARD AFT LEG BROKE
2092 | 01/28/2022 | ARO-3004 | KARN-46 | 28 Jan 0600 - 0645 | .75 | .75 | 890125 |  | RR | FOT | HSYS | RIG | 0 | ARO LT: TROUBLE-SHOOT TW61 IRON ROUGHNECK - NO SUCCESS. REPLACE WITH SPARE TW61
2094 | 01/28/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 23.25 | 166.75 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
2095 | 01/28/2022 | ARO-3004 | KARN-46 | 28 Jan 0600 - 0645 | .75 | .75 | 890125 |  | RR | FOT | HSYS | RIG | 0 | ARO LT: TROUBLE-SHOOT TW61 IRON ROUGHNECK - NO SUCCESS. REPLACE WITH SPARE TW61
2097 | 01/28/2022 | ARO-4001 | MRJN-537 | 11 Jan 0500 - 2315 | 18.25 | 390 | 888705 |  | LCIR | CFFM | SQZ | ARM | 7057 | HAD TOTAL LOSSES WHILE DRILLING 12 1/4" HOLE, STOP DRILLING @ 7057 FT, TRYING TO CURE LOSSES WITH LCM PILLS AND CMT PLUGS.
2099 | 01/28/2022 | BCTD-3 | HRDH-101001 | 28 Jan 1430 - 2000 | 5.5 | 5.5 | 890165 |  | RR | FOT | CHK | RIG | 0 | VALVE C-1 ON DRILLING CHOKE DOES NOT CLOSE FULLY.
2101 | 01/28/2022 | DQ-48 | KHRS-384 | 28 Jan 0215 - 0500 | 2.75 | 2.75 | 890132 |  | STUK | STBH | BHA | ARM | 7560 | WHILE POOH 8-1/2" MRSS DRILL STRING @ 7560' GOT STRING STUCK, WORK ON STUCK
2103 | 01/28/2022 | HWU-1 | HZEM-142814 | 28 Jan 1800 - 0500 | 11 | 11 | 890128 |  | WON | WTHR | NA | ARM | 0 | -SUSPEND CRANE OPERATIONS DUE TO HIGH WIND
2105 | 01/28/2022 | NBR-196S | SDGM-1174 | 27 Jan 0100 - 0500 | 24 | 28 | 890026 |  | STUK | HINW | WLT | SWL | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
2107 | 01/28/2022 | NBR-20S | JLMS-13 | 28 Jan 0500 - 0500 | 24 | 24 | 890131 |  | WON | WTHR | NA | ARM | 0 | WAITED ON HIGH WINDS TO SUBSIDE. UNABLE TO USE CRANES, POOR VISIBILITY.
2109 | 01/28/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 355.75 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
2111 | 01/28/2022 | RBP-50A | HSBH-58 | 25 Jan 0100 - 0500 | 24 | 65 | 889765 |  | UPRA | OTH | NA | RIG | 13243 | WHILE JACKING RIG DOWN FOR WATER INTEGRITY TEST OBSERVED PORT LEG BOW GEAR BOX FAILURE, BULL GEAR DAMAGED AND 2 TEETH MISSING FROM CHORD/JACKING COLUMN.
2113 | 01/28/2022 | RM-74A | KARN-61 | 28 Jan 0830 - 1045 | 2.25 | 2.25 | 890145 |  | WO | SRVC | NA | RIG | 14220 | RIG LOST MAIN POWER IN ENGINE ROOM DUE TO ACTIVATION OF 2 SMOKE DETECTORS. MAINTENANCE TEAM INVESTIGATED AND REPORTED THAT THE #5 ENGINE TO GENERATOR COUPLING WAS DAMAGED. THIS IS WHAT CAUSED THE SMOKE IN THE ENGINE ROOM AND INITIATED THE ESD
2115 | 01/28/2022 | SINO-12L | HRDH-447 | 28 Jan 1545 - 0015 | 8.5 | 8.5 | 890135 |  | STUK | PSSW | NA | TK1 | 10450 | STUCK WHILE RIH WITH IMAGE/CALIPER LOGGING TOOLS.
2117 | 01/28/2022 | SINO-25 | MNIF-144 | 27 Jan 2230 - 0900 | 4 | 10.5 | 890206 |  | TF | FOT | ESP | KSC | 0 | L/D NEW APC ESP, DEFECTED MOTOR I-LEAD V-2 CABLE CONNECTION PORT. APC ATTEMPT TO CONNECT I-LEAD V-2 W/ ESP MOTOR POT HEAD CONNECTION PORT W/ NO SUCCESS.
2119 | 01/28/2022 | SINO-43L | UTMN-4808 | 24 Jan 0700 - 2000 | 3.5 | 5 | 889535 |  | RR | FOT | FL | RIG | 814 | SECTION LINE OF CELLAR PUMP PLEGGUED.
2121 | 01/28/2022 | SND-2001 | SDGM-1240 | 24 Jan 2300 - 0500 | 24 | 102 | 889825 |  | JF | CEDE | NA | SJC | 14832 | BAD CEMENT QUALITY (FREE PIPE) FOR 4-1/2" LINER. SIDE TRACK FOR NEW HOLE.
2123 | 01/28/2022 | SND-2002 | WAQR-9 | 28 Jan 2045 - 2200 | 1.25 | 1.25 | 890129 |  | TF | FOT | DV | WDV | 0 | LOST RETURNS WHILE DISPLACING CLOSING PLUG, SUSPECT DV LEAK
2125 | 01/28/2022 | SND-3001 | MHWZ-167102 | 27 Jan 1215 - 0500 | 24 | 40.75 | 890029 |  | TF | FOT | CTRQ | ITS | 1557 | WHILE MAKING JOINT OF 18-5/8" CSG ON RIG FLOOR NOTICED STRING JUMP IN SLIPS. PICKED UP AND HOOKLOAD GONE, OBSERVED THE CASING THREADS PARTED OFF JOINT IN CELLAR
2127 | 01/28/2022 | SP-306 | MNIF-865 | 25 Jan 0330 - 0500 | 24 | 73.5 | 889885 |  | BHA | FOT | DC | RIG | 100 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
2129 | 01/28/2022 | SSA-51 | MNIF-254 | 28 Jan 0345 - 0500 | 1.25 | 1.25 | 890207 |  | DD | UDWL | HTMTR | BHI | 14403 | MISCOMMUNICATION BETWEEN BAKER DD & GOC, LED TO EXCESS TIME FOR SURVEY AND DOWN LINK .
2131 | 01/28/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 292 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
2133 | 01/29/2022 | ADC-31 | SDGM-1163 | 27 Jan 1900 - 0500 | 23.5 | 57 | 890025 |  | TF | FOT | WLT | SWL | 13170 | AFTER MOVING TO THE SECOND SAMPLE POINT, ATTEMPTED TO INFLATE THE DUAL PACKER BUT FOUND THAT THE INFLATE VALVE WAS JAMMED CLOSED (MALFUNCTIONING) NOT ABLE TO OPERATE.
2135 | 01/29/2022 | ADC-42L | UTMN-2319 | 24 Jan 1545 - 0500 | 24 | 126.75 | 889625 |  | DRG | WNCA | NA | TK3 | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
2137 | 01/29/2022 | ADC-45 | KHRS-82 | 27 Jan 2230 - 0500 | 24 | 54.5 | 890066 |  | TF | FOT | PKR | BAL | 3982 | HAD 9-5/8" PRAXIS PKR ACCEDINTLY SET.
2139 | 01/29/2022 | ADC-68L | KRSN-705 | 29 Jan 1845 - 2030 | 1.75 | 1.75 | 890142 |  | TF | FOT | WATER | ARN | 3789 | STOPPED DRILLING DUE TO PROBLEM IN THE WATER WELL ENGINE WHICH LEADS TO SHORTAGE IN DRILL WATER SUPPLY TO THE RIG
2141 | 01/29/2022 | ADES-174 | HRDH-2184 | 28 Jan 1330 - 1830 | 13.5 | 29 | 890185 |  | BHA | FOT | MWD | WDS | 13698 | OST SIGNAL FROM LWD/MWD SENSORS DOWNHOLE. ATTEMPT TO TAKE SURVEY - NO SUCCESS
2143 | 01/29/2022 | ADES-798 | JFYN-13 | 28 Jan 1800 - 0500 | 21.5 | 32.5 | 890127 |  | BHA | FOT | MWD | SPS | 15622 | MWD LOST COMMUNICATION WITH RSS. MANY TRIALS TO REGAIN SIGNAL, NO SUCCESS.
2145 | 01/29/2022 | ADM-510 | ABSF-223 | 29 Jan 0300 - 0500 | 2 | 2 | 890213 |  | RR | FOT | TDS | RIG | 509 | WHILE DRILLING CEMENT AT 509', GOT AN OIL PRESSURE ALARM ON TDS
2147 | 01/29/2022 | ADM-511 | MRJN-2011 | 29 Jan 1145 - 1200 | .25 | .25 | 890209 |  | BHA | FOT | LWD | BHI | 17995 | STOP DRILLING AND BHI DOWNLINK TO ACTIVATE NBGR SENSOR NUMBER 2
2149 | 01/29/2022 | AOD-1 | ZULF-695 | 29 Jan 1600 - 0500 | 12.75 | 12.75 | 890247 |  | JF | XTRI | BOP | RIG | 7952 | WHILE TESTING BOPE OBSERVED LEAK BETWEEN 11" 3M X 18-3/4" 15M DSA AND 18-3/4" 15K RISER. N/D AND INSPECT RING GROOVES AND RING GASKET. FOUND WASH IN RING GASKET AND RING GROVES.
2151 | 01/29/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 24 | 177.75 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
2153 | 01/29/2022 | ARO-2003 | MNIF-735 | 29 Jan 0500 - 0500 | 24 | 24 | 890136 |  | WON | WTHR | NA | OTH | 0 | WAITING ON WEATHER TO START RIG MOVE OPERATION. LOW VISIBILITY, HIGH SEAS AND WIND.
2155 | 01/29/2022 | ARO-3003 | SFNY-1150 | 29 Jan 1000 - 0500 | 19 | 19 | 890246 |  | UPRA | OTH | NA | RIG | 7314 | HSE INCIDENT SUSPEND OPERATIONS FOR INVESTIGATION.
2157 | 01/29/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 24 | 190.75 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
2159 | 01/29/2022 | ARO-4001 | MRJN-533 | 29 Jan 0200 - 0500 | 3 | 3 | 890212 |  | UPRA | GRF | TDS | RIG | 5543 | REPAIR & MAINTENANCE ON TDS MOTORS.
2161 | 01/29/2022 | BB-84A | MRJN-588 | 29 Jan 1715 - 0230 | 3.75 | 3.75 | 890140 |  | RR | FPMP | MPMP | RIG | 6245 | PRESSURE LOSS MP-3 MP-1
2163 | 01/29/2022 | DQ-48 | KHRS-384 | 28 Jan 0215 - 1415 | 9.25 | 12 | 890132 |  | STUK | STBH | BHA | TK2 | 7560 | WHILE POOH 8-1/2" MRSS DRILL STRING @ 7560' GOT STRING STUCK, WORK ON STUCK
2165 | 01/29/2022 | ENS-108 | SFNY-1560 | 29 Jan 0930 - 1015 | .75 | .75 | 890137 |  | RR | FOT | MPMP | RIG | 4881 | CHANGE MECHANICAL SEAL FOR SUPERCHARGE PUMP OF MP#1.
2167 | 01/29/2022 | ENSCO-54 | ABSF-13 | 29 Jan 1900 - 0500 | 10 | 10 | 890211 |  | WO | WOTO | NA | KSC | 0 | ALKHORAYEF SENT WRONG SIZE OF ESP PACKER TO RIG.
2169 | 01/29/2022 | HWU-1 | HZEM-142814 | 28 Jan 1800 - 0100 | 20 | 31 | 890128 |  | WON | WTHR | NA | ARM | 0 | -SUSPEND CRANE OPERATIONS DUE TO HIGH WIND
2171 | 01/29/2022 | NBR-654S | HRDH-1935 | 29 Jan 0000 - 0030 | .5 | .5 | 890306 |  | TF | FOT | PEL | SPR | 13951 | TROUBLESHOOTING ON SAPESCO JAM UNIT
2172 | 01/29/2022 | NBR-797S | UTMN-3145 | 29 Jan 1245 - 0400 | 15.25 | 15.25 | 890139 |  | TF | FOT | FISHT | BFW | 17000 | NPS W/L RIH TO FREE FALL DEPTH 13,700FT. CHECK TOOL TEMP = 300F. TEMP IN RANGE FOR BAKER AND ALTUS TOOLS. BAKER MPC/CCL TOOLS OK. - NPS W/L SWITCH POWER FROM BAKER MPC/CCL TOOLS TO ALTUS TRACTOR - TRACTOR IN HOLE TO 17,000 FT. - NPS W/L SWITCH POWER FROM ALTUS TRACTOR TO BAKER MPC/CCL TOOLS. COMMUNICATION FAILURE AT BAKER MPC/CCL TOOL.
2174 | 01/29/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 8.75 | 364.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
2175 | 01/29/2022 | NBR-797S | UTMN-3145 | 29 Jan 1245 - 0400 | 15.25 | 15.25 | 890139 |  | TF | FOT | FISHT | BFW | 17000 | NPS W/L RIH TO FREE FALL DEPTH 13,700FT. CHECK TOOL TEMP = 300F. TEMP IN RANGE FOR BAKER AND ALTUS TOOLS. BAKER MPC/CCL TOOLS OK. - NPS W/L SWITCH POWER FROM BAKER MPC/CCL TOOLS TO ALTUS TRACTOR - TRACTOR IN HOLE TO 17,000 FT. - NPS W/L SWITCH POWER FROM ALTUS TRACTOR TO BAKER MPC/CCL TOOLS. COMMUNICATION FAILURE AT BAKER MPC/CCL TOOL.
2176 | 01/29/2022 | PA-785S | QTIF-24 | 29 Jan 1200 - 1400 | 2 | 2 | 890285 |  | RR | FOT | MPMP | RIG | 9770 | RIG PUMP#1&2 FAILURE
2178 | 01/29/2022 | PA-785S | QTIF-24 | 29 Jan 0700 - 0900 | 2 | 2 | 890208 |  | RR | FOT | TDS | RIG | 9675 | TOP DRIVE SAVER SUB PIN BROKEN WHILE M/U CONNECTION.
2179 | 01/29/2022 | PA-785S | QTIF-24 | 29 Jan 1200 - 1400 | 2 | 2 | 890285 |  | RR | FOT | MPMP | RIG | 9770 | RIG PUMP#1&2 FAILURE
2181 | 01/29/2022 | RBP-50A | HSBH-58 | 25 Jan 0100 - 0500 | 24 | 89 | 889765 |  | UPRA | OTH | NA | RIG | 13243 | WHILE JACKING RIG DOWN FOR WATER INTEGRITY TEST OBSERVED PORT LEG BOW GEAR BOX FAILURE, BULL GEAR DAMAGED AND 2 TEETH MISSING FROM CHORD/JACKING COLUMN.
2183 | 01/29/2022 | SINO-12L | HRDH-447 | 28 Jan 1545 - 0500 | 24 | 37.25 | 890135 |  | STUK | PSSW | NA | TK1 | 10450 | STUCK WHILE RIH WITH IMAGE/CALIPER LOGGING TOOLS.
2185 | 01/29/2022 | SINO21 | ABQQ-551 | 29 Jan 0415 - 0500 | .75 | .75 | 890325 |  | STUK | STBH | BHA | ARM | 5274 | STUCK STRING.
2187 | 01/29/2022 | SND-3001 | MHWZ-167102 | 27 Jan 1215 - 2300 | 18 | 58.75 | 890029 |  | TF | FOT | CTRQ | ITS | 1557 | WHILE MAKING JOINT OF 18-5/8" CSG ON RIG FLOOR NOTICED STRING JUMP IN SLIPS. PICKED UP AND HOOKLOAD GONE, OBSERVED THE CASING THREADS PARTED OFF JOINT IN CELLAR
2189 | 01/29/2022 | SP-120 | MNIF-189 | 29 Jan 2215 - 0245 | 4.5 | 4.5 | 890141 |  | RR | FOT | TDS | RIG | 20190 | AFTER CIRC AND WHILE RIH TO MAKE CONNECTION WITH TDS LINKS TILTED TOWARDS STANDPIPE MANIFOLD SIDE AT HIEGHT 72 FT ABOVE ROTARY. OBSERVED SOME SOUND. P/U 12 FT, CHANGED TDS LINKS POSITION AND RIH TDS TO ROTARY FOUND BOTH TDS LINKS HYDRAULIC CYLINDERS ARE BENT. CHANGED BOTH CYLINDERS WHILE CIRCULATE AND ROTATE STRING. * CHECKED TDS CABLES AND ANTI COLLECTION SYSTEM FOUND ALL GOOD.
2191 | 01/29/2022 | SP-260 | HZEM-141612 | 24 Jan 0545 - 0500 | 24 | 143.25 | 889506 |  | BHA | FOT | RSS | BHI | 10369 | BAKER RSS LUCIDA BROKEN, LOST IN THE HOLE BIT BOX OF BAKER RSS LUCIDA AND BIT.
2193 | 01/29/2022 | SP-306 | MNIF-865 | 25 Jan 0330 - 0500 | 24 | 97.5 | 889885 |  | BHA | FOT | DC | RIG | 100 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
2195 | 01/29/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 315.5 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
2197 | 01/30/2022 | ADC-31 | SDGM-1163 | 27 Jan 1900 - 1130 | 6.5 | 63.5 | 890025 |  | TF | FOT | WLT | SWL | 13170 | AFTER MOVING TO THE SECOND SAMPLE POINT, ATTEMPTED TO INFLATE THE DUAL PACKER BUT FOUND THAT THE INFLATE VALVE WAS JAMMED CLOSED (MALFUNCTIONING) NOT ABLE TO OPERATE.
2199 | 01/30/2022 | ADC-42L | UTMN-2319 | 24 Jan 1545 - 0500 | 24 | 150.75 | 889625 |  | DRG | WNCA | NA | TK3 | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
2200 | 01/30/2022 | ADC-45 | KHRS-82 | 30 Jan 1000 - 1330 | 3.5 | 3.5 | 890412 |  | TF | FOT | TTRQ | MSD | 10894 | PKR TOP PUP JT COLLABSED WHILE MU BY ALMASOOD POWER TONG
2202 | 01/30/2022 | ADC-45 | KHRS-82 | 27 Jan 2230 - 0500 | 20.5 | 75 | 890066 |  | TF | FOT | PKR | BAL | 3982 | HAD 9-5/8" PRAXIS PKR ACCEDINTLY SET.
2203 | 01/30/2022 | ADC-45 | KHRS-82 | 30 Jan 1000 - 1330 | 3.5 | 3.5 | 890412 |  | TF | FOT | TTRQ | MSD | 10894 | PKR TOP PUP JT COLLABSED WHILE MU BY ALMASOOD POWER TONG
2205 | 01/30/2022 | ADC-58L | ABHD-172 | 30 Jan 2300 - 0330 | 4.5 | 4.5 | 890450 |  | TF | FOT | PEL | TSC | 744 | DOWN TIME ON TESCO COMPANY DUE TO DIFFICULTY OF USING SIDE DOOR ELEVATOR TO RUN 18 5/8" CSG, PRIMARY & BACK UP BJ 18-5/8" SDE UNABLE TO LATCH ONTO CASING
2207 | 01/30/2022 | ADC-66L | HWYH-1223 | 30 Jan 1200 - 0500 | 16.5 | 16.5 | 890222 |  | STUK | STBH | BHA | TK3 | 17660 | BACK REAM WITH 5-7/8" BHA F/ 17,680 FT TO 17,660 FT, OBSERVE STRING STUCK.
2209 | 01/30/2022 | ADES-157 | HRDH-698 | 30 Jan 1800 - 2230 | 4.5 | 4.5 | 890408 |  | WO | WOTO | NA | SAM | 0 | WAIT ON SAMAA WBCO TOOLS
2210 | 01/30/2022 | ADES-798 | JFYN-13 | 30 Jan 2300 - 0500 | 6 | 6 | 890223 |  | BHA | FOT | RSS | SPS | 15773 | SPS RSS FAILED TO ACHIEVE REQUIRED BUILDING RATE.
2212 | 01/30/2022 | ADES-798 | JFYN-13 | 28 Jan 1800 - 0600 | 1 | 33.5 | 890127 |  | BHA | FOT | MWD | SPS | 15622 | MWD LOST COMMUNICATION WITH RSS. MANY TRIALS TO REGAIN SIGNAL, NO SUCCESS.
2213 | 01/30/2022 | ADES-798 | JFYN-13 | 30 Jan 2300 - 0500 | 6 | 6 | 890223 |  | BHA | FOT | RSS | SPS | 15773 | SPS RSS FAILED TO ACHIEVE REQUIRED BUILDING RATE.
2214 | 01/30/2022 | ADM-510 | ABSF-223 | 30 Jan 1215 - 1715 | 5 | 5 | 890425 |  | RR | FOT | FL | RIG | 674 | FLOWLINE PLUGGED UP WITH RUBBER FROM THE WIPER PLUGS
2216 | 01/30/2022 | ADM-510 | ABSF-223 | 30 Jan 1715 - 2330 | 6.25 | 6.25 | 890217 |  | BHA | FOT | MWD | SCD | 674 | GYRO TOOL NOT WORKING
2217 | 01/30/2022 | ADM-510 | ABSF-223 | 30 Jan 1215 - 1715 | 5 | 5 | 890425 |  | RR | FOT | FL | RIG | 674 | FLOWLINE PLUGGED UP WITH RUBBER FROM THE WIPER PLUGS
2218 | 01/30/2022 | AOD-1 | ZULF-695 | 30 Jan 0145 - 0500 | 3.25 | 3.25 | 890448 |  | BOP | FOT | RAMS | RIG | 7952 | WHILE PT 18-3/4" BLIND RAMS OBSERVED LEAK ON AFT MPR SIDE.
2220 | 01/30/2022 | AOD-1 | ZULF-695 | 29 Jan 1600 - 0145 | 17.25 | 30 | 890247 |  | JF | XTRI | BOP | RIG | 7952 | WHILE TESTING BOPE OBSERVED LEAK BETWEEN 11" 3M X 18-3/4" 15M DSA AND 18-3/4" 15K RISER. N/D AND INSPECT RING GROOVES AND RING GASKET. FOUND WASH IN RING GASKET AND RING GROVES.
2221 | 01/30/2022 | AOD-1 | ZULF-695 | 30 Jan 0145 - 0500 | 3.25 | 3.25 | 890448 |  | BOP | FOT | RAMS | RIG | 7952 | WHILE PT 18-3/4" BLIND RAMS OBSERVED LEAK ON AFT MPR SIDE.
2223 | 01/30/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 24 | 201.75 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
2225 | 01/30/2022 | ARO-2003 | MNIF-735 | 28 Jan 1800 - 0700 | 2 | 13 | 890345 |  | WON | DAY | NA | ARM | 0 | WAIT ON DAYLIGHT
2227 | 01/30/2022 | ARO-3003 | SFNY-1150 | 29 Jan 1000 - 0500 | 24 | 43 | 890246 |  | UPRA | OTH | NA | RIG | 7314 | HSE INCIDENT SUSPEND OPERATIONS FOR INVESTIGATION.
2229 | 01/30/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 0500 | 24 | 214.75 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
2231 | 01/30/2022 | ARO-4001 | MRJN-533 | 29 Jan 0200 - 0500 | 24 | 27 | 890212 |  | UPRA | GRF | TDS | RIG | 5543 | REPAIR & MAINTENANCE ON TDS MOTORS.
2233 | 01/30/2022 | ENSCO-54 | ABSF-13 | 29 Jan 1900 - 2130 | 16.5 | 26.5 | 890211 |  | WO | WOTO | NA | KSC | 0 | ALKHORAYEF SENT WRONG SIZE OF ESP PACKER TO RIG.
2235 | 01/30/2022 | NA-128S | ZMLH-5 | 30 Jan 0500 - 0500 | 24 | 24 | 890446 |  | TF | FOT | CUT | SWL | 13011 | SLB RCT FAILED TO CUT 4.5'' TUBING.
2237 | 01/30/2022 | NBR-196S | SDGM-1174 | 27 Jan 0100 - 0500 | 24 | 76 | 890026 |  | STUK | HINW | WLT | SWL | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
2238 | 01/30/2022 | NBR-575S | HRDH-2323 | 30 Jan 2030 - 0345 | 2.5 | 2.5 | 890221 |  | TF | XTTE | CTRQ | ITS | 963 | EXCESSIVE TIME TO TORQUE CASING AND DAMAGE THEREAD
2240 | 01/30/2022 | NBR-575S | HRDH-2323 | 30 Jan 1500 - 1600 | 1 | 1 | 890218 |  | RR | FOT | TDS | RIG | 586 | LOST SIGNAL BETWEEN CONSAL PANAL AND SRC
2241 | 01/30/2022 | NBR-575S | HRDH-2323 | 30 Jan 1700 - 1745 | .75 | .75 | 890219 |  | RR | FOT | TDS | RIG | 586 | TOP DRIVE NOT GOOD CENTRALIZED
2242 | 01/30/2022 | NBR-575S | HRDH-2323 | 30 Jan 1745 - 1845 | 1 | 1 | 890220 |  | TF | XTTE | CTRQ | ITS | 586 | EXCESS TIME TO TORQUE CSG
2243 | 01/30/2022 | NBR-575S | HRDH-2323 | 30 Jan 2030 - 0345 | 2.5 | 2.5 | 890221 |  | TF | XTTE | CTRQ | ITS | 963 | EXCESSIVE TIME TO TORQUE CASING AND DAMAGE THEREAD
2245 | 01/30/2022 | NBR-591S | HRDH-1933 | 30 Jan 2130 - 0500 | 7.5 | 7.5 | 890411 |  | STUK | STBH | BHA | ARM | 17660 | OBSERVED HIGHT TORQUE WHILE DRILLING, THE STRING GOT STALLED AND BECAME STUCK
2247 | 01/30/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 24 | 388.5 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
2249 | 01/30/2022 | PA-861S | HRDH-1332 | 30 Jan 1045 - 1145 | 1 | 1 | 890406 |  | JF | XTRI | CTRQ | FMC | 1780 | 1HR LOST DUE TO JAM UNIT FAILURE AND SWITCH OUT JAM UNIT.
2251 | 01/30/2022 | RBP-50A | HSBH-58 | 25 Jan 0100 - 0500 | 24 | 113 | 889765 |  | UPRA | OTH | NA | RIG | 13243 | WHILE JACKING RIG DOWN FOR WATER INTEGRITY TEST OBSERVED PORT LEG BOW GEAR BOX FAILURE, BULL GEAR DAMAGED AND 2 TEETH MISSING FROM CHORD/JACKING COLUMN.
2253 | 01/30/2022 | SA5898 | HRDH-2101 | 30 Jan 1400 - 1700 | 3 | 3 | 890447 |  | TF | FOT | HGRL | BLH | 12032 | 4-1/2" BAKER LINER HANGER NOT SET.
2255 | 01/30/2022 | SINO-12L | HRDH-447 | 28 Jan 1545 - 0500 | 24 | 61.25 | 890135 |  | STUK | PSSW | NA | TK1 | 10450 | STUCK WHILE RIH WITH IMAGE/CALIPER LOGGING TOOLS.
2257 | 01/30/2022 | SINO21 | ABQQ-551 | 29 Jan 0415 - 0500 | 24 | 24.75 | 890325 |  | STUK | STBH | BHA | ARM | 5274 | STUCK STRING.
2259 | 01/30/2022 | SND-3001 | MHWZ-167102 | 30 Jan 0615 - 1000 | 3.75 | 3.75 | 890385 |  | JF | HERR | CSYS | RIG | 1557 | DURING 18-5/8" CEMENT JOB DURING THE SWITCH FROM MIX WATER FOR LEAD TO TAIL, THE TAIL MIX WATER WAS LOST AND CONTAMINATED UNABLE TO COMPLETE PUMPING TAIL.
2261 | 01/30/2022 | SP-259 | HZEM-160802 | 28 Jan 1345 - 1330 | 8.5 | 47.25 | 890409 |  | WCNT | WC11 | NA | ARM | 18456 | OBSERVED CUT IN MW WHILE CHC AT 9110 FT.
2263 | 01/30/2022 | SP-260 | HZEM-141612 | 24 Jan 0545 - 0500 | 24 | 143.25 | 889506 |  | BHA | FOT | RSS | BHI | 10369 | BAKER RSS LUCIDA BROKEN, LOST IN THE HOLE BIT BOX OF BAKER RSS LUCIDA AND BIT.
2265 | 01/30/2022 | SP-306 | MNIF-865 | 25 Jan 0330 - 0500 | 24 | 121.5 | 889885 |  | BHA | FOT | DC | RIG | 4309 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
2267 | 01/30/2022 | SSA-46 | JAHM-5 | 29 Jan 1845 - 0500 | 24 | 34.25 | 890215 |  | WO | STOP | NA | ARM | 3790 | RIG SHUT DOWN BY GOVT ENVIRONMENTAL GUARDS DUE TO OPERATION PERMISSION IN THE NATURE RESERVE NOT BEING ISSUED.
2269 | 01/30/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 339 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
2271 | 01/30/2022 | SSA-5964 | SDGM-1158 | 29 Jan 0000 - 1600 | 2.5 | 7.5 | 890407 |  | TF | XTTE | RSS | SPS | 14300 | CIRCULATION TIME TAKEN TO COOL DOWN SPERRY RSS EQUIPMENT DUE TO INCORRECT TOOL TEMPERATURE RANGE SELECTION BY HALLIBURTON. CURRENT TOOL LIMITED TO 302 DEG F.
2273 | 01/30/2022 | SSA-5971 | UTMN-2302 | 30 Jan 0500 - 0500 | 24 | 24 | 890426 |  | BHA | FOT | MWD | SPS | 7240 | DURING DRILLING 16" HOLE WITH 800GPM THE CIRCULATION PRESSURE OF 2500PSI RAISED UP TO 3500PSI. NO MORE CIRCULATION COULD BE ESTABLISCHED AFTER THAT. THE DRILL STRING WAS PLUGGED. POOH AND MWD WAS FOUND PLUGGED WITH MUD AND FINE SOLIDS ABOVE THE PULSER. THE DOWNHOLE SCREEN SUB WAS NOT FOUND PLUGGED.
2275 | 01/30/2022 | SSA-5972 | NJYN-102 | 30 Jan 0500 - 1800 | 13 | 13 | 890410 |  | CMT | IFCS | NA | SJC | 11420 | MIX FLUID SAMPLES DID NOT PASS LAB TEST RESULTS, DUMP MIX FLUID & PREPARED NEW MIX FLUID WITH NEW RECIPE, WAIT ON LAB TEST RESULTS.
2277 | 01/30/2022 | T914 | HWYH-512 | 30 Jan 0530 - 0500 | 23.5 | 23.5 | 890216 |  | JF | FOP | CORL | BAW | 4565 | UNABLE TO COMMUNICATE WITH BAKER LOGGING TOOLS THROUGH WET CONNECT.
2279 | 01/31/2022 | ADC-42L | UTMN-2319 | 24 Jan 1545 - 0500 | 24 | 174.75 | 889625 |  | DRG | WNCA | NA | TK3 | 4889 | ENCOUNTER OBSTRUCTION AT 4,880 FT. TRY TO CLEAR BY WASHING DOWN . WASH DOWN FROM 4,880 - 4,889 KLBS - NO FURTHER PROGRESS.
2281 | 01/31/2022 | ADC-45 | KHRS-82 | 27 Jan 2230 - 1930 | 14.5 | 89.5 | 890066 |  | TF | FOT | PKR | BAL | 3982 | HAD 9-5/8" PRAXIS PKR ACCEDINTLY SET.
2283 | 01/31/2022 | ADC-55L | UTMN-3076 | 31 Jan 0615 - 1715 | 11 | 11 | 890545 |  | RR | FOT | CSYS | RIG | 12956 | OBSERVED LEAK IN THE UPPER IBOP CRANK MECHANISM
2285 | 01/31/2022 | ADC-59L | HRDH-2232 | 31 Jan 0600 - 1030 | 4.5 | 4.5 | 890489 |  | RR | FOT | CSYS | RIG | 10494 | LOWER SAFETY VALVE ON TOP DRIVE IS LEAKING AT MANUAL ACTUATOR (CANISTER)
2287 | 01/31/2022 | ADC-65L | HRDH-1980 | 31 Jan 1415 - 0500 | 14.75 | 14.75 | 890488 |  | TF | FOT | WLT | SWL | 11760 | THE RESISTIVITY DATA SENT FOR THIS WELL WAS NOT ACCEPTED.
2289 | 01/31/2022 | ADC-66L | HWYH-1223 | 30 Jan 1200 - 0430 | 23 | 39.5 | 890222 |  | STUK | STBH | BHA | TK3 | 17660 | BACK REAM WITH 5-7/8" BHA F/ 17,680 FT TO 17,660 FT, OBSERVE STRING STUCK.
2291 | 01/31/2022 | ADES-14 | HRDH-476 | 31 Jan 1600 - 0500 | 13 | 13 | 890546 |  | BHA | FOT | MWD | BHI | 5200 | MWD FAILURE (INTERMITTENT PULSER FAILURE).
2293 | 01/31/2022 | ADES-144 | UTMN-3041 | 31 Jan 0500 - 1300 | 8 | 8 | 890485 |  | RR | FOT | CHK | RIG | 2390 | WORK ON DAMMAGED MANUAL VALVLE ON KILL LINE.
2295 | 01/31/2022 | ADM-266 | ZULF-106 | 29 Jan 1200 - 1500 | 2 | 8 | 890405 |  | WON | WTHR | NA | ARN | 0 | HIGH SEA SWELL.
2297 | 01/31/2022 | AOD-1 | ZULF-695 | 30 Jan 0145 - 0545 | .75 | 4 | 890448 |  | BOP | FOT | RAMS | RIG | 7952 | WHILE PT 18-3/4" BOP OBSERVED LEAK ON AFT MPR SIDE.
2299 | 01/31/2022 | AOD-111 | MRJN-726 | 22 Jan 1800 - 0500 | 24 | 225.75 | 889152 |  | TH | NARW | NA | ARM | 4940 | HELD UP WITH 13-3/8" CASING AT 4940'. ATTEMPT WASH THROUGH OBSTRUCTION WITHOUT SUCCESS
2301 | 01/31/2022 | ARO-3003 | SFNY-1150 | 29 Jan 1000 - 0500 | 24 | 67 | 890246 |  | UPRA | OTH | NA | RIG | 7314 | HSE INCIDENT SUSPEND OPERATIONS FOR INVESTIGATION.
2303 | 01/31/2022 | ARO-3004 | KARN-46 | 04 Jan 1130 - 1215 | 7.25 | 222 | 886981 |  | TF | FOT | PKR | BC | 10193 | UNABLE TO IN-FLOW TEST BAKER MIDDLE COMPLETION
2305 | 01/31/2022 | ARO-4001 | MRJN-533 | 29 Jan 0200 - 0000 | 19 | 46 | 890212 |  | UPRA | GRF | TDS | RIG | 5543 | REPAIR & MAINTENANCE ON TDS MOTORS.
2307 | 01/31/2022 | BCTD-4 | MNJR-7 | 31 Jan 1730 - 2200 | 4.5 | 4.5 | 890550 |  | BHA | FOT | MWD | BHI | 6485 | LOST COMMUNICATION WITH DHT, POH AND TROUBLESHOOT FOUND ISSUE WITH E-LINE CONDUCTOR.
2309 | 01/31/2022 | CG-1 | ZULF-1203 | 31 Jan 0145 - 0300 | 1.25 | 1.25 | 890548 |  | RR | FOT | TDS | RIG | 6698 | RIG REPAIR- TDS WASH PIPE LEAKING
2311 | 01/31/2022 | EXL-IA | SFNY-4050 | 31 Jan 0230 - 0500 | 2.5 | 2.5 | 890526 |  | TF | FOT | PEL | RIG | 457 | OBSERVE DAMAGE TO FRANKS 30" CASING ELEVATOR EAR LINK CONNECTION DUE TO TDS LINK TILT.
2313 | 01/31/2022 | NA-128S | ZMLH-5 | 30 Jan 0500 - 0500 | 24 | 48 | 890446 |  | TF | FOT | CUT | SWL | 13011 | SLB RCT FAILED TO CUT 4.5'' TUBING.
2315 | 01/31/2022 | NBR-196S | SDGM-1174 | 27 Jan 0100 - 0500 | 13.5 | 89.5 | 890026 |  | STUK | HINW | WLT | SWL | 13264 | SCHLUMBERGER WIRELINE TOOL STUCK WHILE RECORDING RUN#2 AT 13,264'
2317 | 01/31/2022 | NBR-591S | HRDH-1933 | 30 Jan 2130 - 0900 | 4 | 11.5 | 890411 |  | STUK | STBH | BHA | ARM | 17660 | OBSERVED HIGHT TORQUE WHILE DRILLING, THE STRING GOT STALLED AND BECAME STUCK
2319 | 01/31/2022 | NBR-797S | UTMN-3145 | 11 Jan 0530 - 0500 | 7.5 | 420 | 887787 |  | STUK | STDP | DP | ARM | 18272 | RACK BACK STAND @ 18,272', M/U TDS TO STRING, BREAK CIRCULATION 100% CIRC, ATTEMPT ROTATION, STRING IMMEDIATELY STUCK AFTER CONNECTION.
2321 | 01/31/2022 | NBR-987S | ABTL-2 | 31 Jan 1600 - 0500 | 13 | 13 | 890527 |  | TF | FOT | WLT | HWP | 10995 | UNABLE TO WORK FREE THE CSG AFTER CASING CUTTER RUN @ 10,995' POSSIBLY DUE TO PARTIAL CUTTING.
2323 | 01/31/2022 | PA-218S | QTIF-515 | 31 Jan 2030 - 0130 | 5 | 5 | 890547 |  | RR | FOT | RWCS | RIG | 1063 | FIX LEAKS ON DIVERTER LINES BY RE-TIGHTNING ALL CONNECTIONS.
2325 | 01/31/2022 | PA-785S | QTIF-24 | 31 Jan 1145 - 1330 | 1.75 | 1.75 | 890466 |  | RR | FOT | TDS | RIG | 10996 | AFTER M/U CONNECTION, STRING SLIPT FROM TOP DRIVE & DROPPED ON ELEVATOR, SAVER SUB PIN THREADS DAMAGED
2327 | 01/31/2022 | RBP-50A | HSBH-58 | 25 Jan 0100 - 0500 | 24 | 137 | 889765 |  | UPRA | OTH | NA | RIG | 13243 | WHILE JACKING RIG DOWN FOR WATER INTEGRITY TEST OBSERVED PORT LEG BOW GEAR BOX FAILURE, BULL GEAR DAMAGED AND 2 TEETH MISSING FROM CHORD/JACKING COLUMN.
2329 | 01/31/2022 | SND-2003 | MNIF-900 | 31 Jan 0200 - 0500 | 3 | 3 | 890551 |  | TF | FOT | MLOG | SGR | 13990 | GEOSERVICE GAS DETECTION SYSTEM MALFUNCTION.
2331 | 01/31/2022 | SP-110 | HWYH-127 | 31 Jan 0030 - 0500 | 4.5 | 4.5 | 890486 |  | BHA | FOT | RSS | WDS | 8570 | WFD MAGNUS RSS TOOL UNABLE TO BUILD INCLINATION AS PER PLAN
2333 | 01/31/2022 | SP-260 | HZEM-141612 | 24 Jan 0545 - 0500 | 24 | 167.25 | 889506 |  | BHA | FOT | RSS | BHI | 10369 | BAKER RSS LUCIDA BROKEN, LOST IN THE HOLE BIT BOX OF BAKER RSS LUCIDA AND BIT.
2335 | 01/31/2022 | SP-306 | MNIF-865 | 25 Jan 0330 - 0500 | 24 | 145.5 | 889885 |  | BHA | FOT | DC | RIG | 4309 | WHILE WORKING ON STRING STUCK, 5" DP PARTED AT 100 FT BELOW ROTARY. - AFTER CHECKING BHA OBSERVED RAGS PARTICLES AT TOP OF WFD FLOAT VALVE AND MWD PLUGGED.
2337 | 01/31/2022 | SP-58 | BRRI-508 | 31 Jan 1030 - 1800 | 7.5 | 7.5 | 890505 |  | TF | XTTE | CTRQ | SPR | 4772 | WHILE RIH HLB SMART COMPLETION, 2.867" DRIFT COULDN'T PASS THRU 3-1/2" TBG. LD TBG, FOUND 3-1/2 COUPLING ID BETWEEN JOINT 110 & 111 RESTRICTED. RE-DRIFT AND RUN TUBING.
2339 | 01/31/2022 | SSA-202 | QTIF-674 | 31 Jan 0945 - 1115 | 1.5 | 1.5 | 890549 |  | BHA | FOT | MWD | SPS | 16838 | SPERRY SUN TROUBLESHOOT MWD SIGNAL.
2341 | 01/31/2022 | SSA-46 | JAHM-5 | 29 Jan 1845 - 0500 | 24 | 58.25 | 890215 |  | WO | STOP | NA | ARM | 3790 | RIG SHUT DOWN BY GOVT ENVIRONMENTAL GUARDS DUE TO OPERATION PERMISSION IN THE NATURE RESERVE NOT BEING ISSUED.
2343 | 01/31/2022 | SSA-51 | MNIF-254 | 31 Jan 0815 - 0930 | 1.25 | 1.25 | 890525 |  | RR | FOT | DWKS | RIG | 17948 | DRAWWORKS SUDDENLY STOPPED WORKING. REAPAIRED SAME, CHANGED BLOWN COMMAND FUSE IN SCR ROOM.
2345 | 01/31/2022 | SSA-5859 | HWYH-1265 | 15 Jan 0030 - 0500 | 23.5 | 362.5 | 888311 |  | STUK | STBH | BHA | ARM | 3180 | STRING STALLED OUT WHILE BLIND ROTARY DRILLING 22", STUCK ON BOTTOM
2347 | 01/31/2022 | SSA-5971 | UTMN-2302 | 30 Jan 0500 - 1230 | 7 | 31 | 890426 |  | RR | FOT | CSYS | RIG | 7240 | DURING DRILLING 16" HOLE WITH 800GPM THE CIRCULATION PRESSURE OF 2500PSI RAISED UP TO 3500PSI. NO MORE CIRCULATION COULD BE ESTABLISCHED AFTER THAT. THE DRILL STRING WAS PLUGGED. POOH AND MWD WAS FOUND PLUGGED WITH CUTTINGS AND LCM ABOVE THE PULSER. THE DOWNHOLE SCREEN SUB WAS NOT FOUND PLUGGED.
2349 | 01/31/2022 | STY-038 | ZULF-2083 | 31 Jan 0500 - 0500 | 24 | 24 | 890528 |  | BHA | FOT | STZRM | SRT | 6070 | WHILE TRYING TO FREE PIPE SMITH STABILIZER PARTED AND LEAVING NO FISH NICK.