## Sheet1
| Cause | Company Name | Cummulative Hrs | Date and Time | Depth | LT ID | LT Summary | LT Type | Object | Parent LT ID | Report Date | Rig Name | Time in Hrs | Well No
0 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | 095TE | Hrs | MNIF-220
1 | FOT | BHI | 1 | 01 May 0330 - 0430 | 9430 | 896148 | LOST SIGNAL OF LWD , TROUBLESHOOTING NO SUCCESS, CONSULT WITH GOC AND DECISION WAS MADE TO CONTINUE DRILL WITHOUT LWD TO TOP OF LRTR ,POH AND CHANGE SAME. | BHA | LWD |  | 05/01/2022 | 095TE | 1 | MNIF-220
2 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | ADC-14 | Hrs | HRDH-986
3 | FOT | SAM | 27.75 | 30 Apr 1945 - 2330 | 10338 | 896110 | SAMAA SET 9-5/8" FSC PACKER WITH 60 KLBS S/O WT, CLOSE BOP, ATTEMPTS TO PRESSURE TEST SAMAA PACKER BACK SIDE TO 1,000 PSI, PACKER CANNOT HOLD PRESSURE. UNSET PACKER. | BHA | WBCL |  | 05/01/2022 | ADC-14 | 18.5 | HRDH-986
4 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | ADC-57L | Hrs | FDHL-158
5 | WSHO | TK3 | 86.5 | 27 Apr 2230 - 0500 | 13135 | 896041 | DRILL OUT 7" LNR SHOE TRACK 20 FT ABOVE FLOAT SHOE. P/T 7" CSG LNR TO 650 PSI PRESSURE DROP NOT HOLDING | CMT | CSG |  | 05/01/2022 | ADC-57L | 24 | FDHL-158
6 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | ADC-58L | Hrs | ABHD-178
7 | PCPF | TK3 | 195.75 | 23 Apr 0045 - 0500 | 6966 | 895847 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS. | TH | NA |  | 05/01/2022 | ADC-58L | 24 | ABHD-178
8 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | ADM-266 | Hrs | SFNY-934
9 | FOT | RIG | 48 | 29 Apr 2300 - 2300 | 5262 | 896141 | TOP DRIVE IBOP ACTUATOR NOT FUNCTION. | RR | TDS |  | 05/01/2022 | ADM-266 | 18 | SFNY-934
10 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | ARO-3001 | Hrs | ZULF-2058
11 | STCT | ARM | 569.75 | 05 Apr 1030 - 0845 | 10340 | 894792 | EXCESS DRAG ACROSS 10340', NO MOVEMENT UP OR DOWN | STUK | SCRN |  | 05/01/2022 | ARO-3001 | 3.75 | ZULF-2058
12 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | CR-36A | Hrs | ZULF-2030
13 | FOT | NCT | 16 | 01 May 1100 - 0300 | 6300 | 896168 | NESR CT TROUBLE SHOOT & ATTEMPT TO REPAIR NITROGEN PUMP. | TF | CTBG |  | 05/01/2022 | CR-36A | 16 | ZULF-2030
14 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | DPS-74 | Hrs | NJYN-54
15 | SCSG | ARM | 437.25 | 13 Apr 0730 - 0500 | 14010 | 895421 | WHILE WASHING DOWN 7" LINER @ 14010, HOLE PACKED OFF CREATING STUCK 7" LINER 2489' OFF BOTTOM WITH NO CIRCULATION. | STUK | LINR |  | 05/01/2022 | DPS-74 | 23.5 | NJYN-54
16 | 7550 | 7250 | LOG | E | 2564 | WLT | CONT. BHI E/L LOGGING TOOLS RUN # 2 (GR/MREX/ADEX/MLL).LOGGED UP AS FOLLOWS:- CONTINUE RELOG MAIN PASS TOP INTERVAL (5900'-5550') PP GAS ACQUISITION MODE.- RIH & RELOG BTM INTERVAL (7550'-7250') PP GAS ACQUISITION MODE.- HOLE IN GOOD CONDITION.- TOOL LENGTH: 104.6', MAX OD: 6.3".- MONITOR WELL THROUGH TRIP TANK, WELL STATIC. | 7550 | 7550 | BAW | 05/01/2022 | DQ-47 | LOG | KHRS-1416
17 | 7550 |  | OTH | E | 2564 | NA | POOH TO SURFACE & R/D BKR LOGGING SHEAVES AND TOOLS. | 7550 |  | BAW | 05/01/2022 | DQ-47 | LOG | KHRS-1416
18 | 7550 |  | SET | N | 2564 | WBSH | PJSM, INSTALL 13-5/8" CIW WEAR BUSHING. | 7550 |  | RIG | 05/01/2022 | DQ-47 | WH | KHRS-1416
19 | 7550 |  | HT | E | 2564 | BHA | HPJSM, M/U & RIH W/ 8-1/2" CONDITION TRIP REAMING BHA FOR LOGGING T/ 1260'.BHA: - 8 1/2" TCI BIT + NBRR (W/ FLOAT VALVE) + 1X 6 1/4" DC + STRR +1X 6 1/4" DC + STRR + 6X 6 1/4" DCS, X/O, JAR, X/O, 2X 6 1/4" DCS, X/O, 30X 5" HWDP. | 7550 |  | RIG | 05/01/2022 | DQ-47 | CT | KHRS-1416
20 | 7550 | 3514 | TI | E | 2564 | STDP | RIH WITH 8 1/2'' CONDITION TRIP BHA TO 13 3/8" CSG SHOE @ 3514 FT. | 7550 | 1260 | RIG | 05/01/2022 | DQ-47 | CT | KHRS-1416
21 | 7550 | 7550 | ST | E | 2564 | STDP | RIH WITH 8 1/2" CONDITION TRIP BHA TO BTM AT 7550 FT. - HOLE IN GOOD CONDITION.- FILL STRING EVERY 20 STD'S. | 7550 | 3514 | RIG | 05/01/2022 | DQ-47 | CT | KHRS-1416
22 | 7550 |  | CIRC | E | 2564 | MPMP | SWEEP HOLE WITH 2X50 BBLS HVP & CHC.- DISPLACE HOLE TO 69 PCF OBM, CIRC AND CONDITION MUD IN/OUT = 69 PCF. | 7550 |  | RIG | 05/01/2022 | DQ-47 | CT | KHRS-1416
23 | 7550 |  | WCNT | E | 2564 | NA | FLOW CHECK, WELL STATIC. | 7550 |  | RIG | 05/01/2022 | DQ-47 | CT | KHRS-1416
24 | 7550 | 3514 | ST | E | 2564 | STDP | POOH W/ 8 1/2'' CONDITION TRIP BHA FOR RCX LOG TO 13-3/8" CS @ 3,514'.- HOLE IN GOOD CONDITION.- FLOW CHECK AFTER 5 STD'S, WELL STATIC. | 7550 | 7550 | RIG | 05/01/2022 | DQ-47 | CT | KHRS-1416
25 | 45.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | BAKER W/L LOG FOR 8 1/2" PILOT HOLE. | 24 | 2564 | 30 Apr 0730 | 05/01/2022 | DQ-47 | Type | KHRS-1416
26
27
28 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | HI-4 | Hrs | SFNY-918
29 | IDPR | SDM | 14 | 01 May 1000 - 0030 | 2885 | 896115 | DUE TO LOW ROP, STRING HANGING SLB UNABLE TO ACHIEVE DIRECTIONAL PLAN W/ MUD MOTOR ASSY. | LROP | BHA |  | 05/01/2022 | HI-4 | 14 | SFNY-918
30 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | PA-622S | Hrs | AFLJ-4
31 | PSSW | ARM | 173.5 | 24 Apr 1000 - 0000 | 6896 | 895875 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION. | STUK | NA |  | 05/01/2022 | PA-622S | 17.5 | AFLJ-4
32 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | PN-9 | Hrs | MRJN-91
33 | FOT | RIG | 7.5 | 01 May 1500 - 2230 | 9573 | 896177 | TOP DRIVE WASH PIPE LEAKING, REPLACE WITH NEW DEUBLIN TYPE WASHPIPE. | RR | TDS |  | 05/01/2022 | PN-9 | 7.5 | MRJN-91
34 | 17315 | 460 | TO | N |  | SPDP | POOH WITH L-2 8-1/2" MRSS BHA F/ 2,673' T/ 460' WHILE L/D 5'' DP TO CLEAR DRILLER SIDE RACK FOR COIL TUBING OPERATION ACCESSABILITY. | 17315 | 2673 | RIG | 05/01/2022 | SIN30L | DRLG | KHRS-1409
35 | 17315 |  | CIRC | N |  | MPMP | FLOW CHECK, STATIC LOSSES RATE = 4 BPH. | 17315 |  | RIG | 05/01/2022 | SIN30L | DRLG | KHRS-1409
36 | 17315 | 0 | LDP | N |  | BHA | HPJSM, POOH & L/D 8.5" MRSS BHA. - UNLOAD RA SOURCE.- DUMP TOOLS MEMORY.- BIT DULL: 1-1-WT-A-X-I-NO-TD.- 04 BPH STATIC LOSSES | 17315 | 460 | RIG | 05/01/2022 | SIN30L | DRLG | KHRS-1409
37 | 17315 |  | RTRV | N |  | WBSH | RETRIEVE WEAR-BUSHING. | 17315 |  | RIG | 05/01/2022 | SIN30L | WH | KHRS-1409
38 | 17315 |  | BOPT | N |  | BOP | HPJSM. PERFORM FULL BOP TEST AS PER ARAMCO STANDARDS. | 17315 |  | RIG | 05/01/2022 | SIN30L | BOP | KHRS-1409
39 | 17315 |  | STIM | E | 2545 | CTU | HPJSM. N/D BELL NIPPLE & FLOW LINE, RU TRIP TANK LINE TO THS WING VALVE. | 17315 |  | BCT | 05/01/2022 | SIN30L | STIM | KHRS-1409
40 | 17315 |  | STIM | E | 2545 | CTU | HPJSM WITH ALL RIG CREW & ALL PERSONNEL INVOLVED W/ BKR CT R/U. | 17315 |  | BCT | 05/01/2022 | SIN30L | STIM | KHRS-1409
41 | 17315 |  | STIM | E | 2545 | CTU | HPJSM, R/U & CONNECT RISER, X/O'S, FLANGES & GATE VALVE TO RIG BOP.- MONITOR WELL THROUGH TRIP TANK, 4 BPH STATIC LOSSES. | 17315 |  | BCT | 05/01/2022 | SIN30L | STIM | KHRS-1409
42 | 17315 |  | STIM | E | 2545 | CTU | HPJSM, R/U CT QUAD BOP ON TOP OF RISER, CONNECT CONTROL HOSES & HI PRESSURE LINES TO CT BOP.- FUNCTION TEST CT BOP RAMS, OK.- MONITOR WELL THROUGH TRIP TANK, 7 BPH STATIC LOSSES. | 17315 |  | BCT | 05/01/2022 | SIN30L | STIM | KHRS-1409
43 | 11 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS. | 11 | 2545 | 01 May 1800 | 05/01/2022 | SIN30L | Type | KHRS-1409
44
45
46 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SINO-11 | Hrs | HWTH-827
47 | FOT | HCO | 6.5 | 01 May 1400 - 2030 | 3400 | 896169 | ATTEMPT TO SET HALLIBURTON 9-5/8" RTTS ASSY @ 3400' , NO SUCCESS. | TF | RTTS |  | 05/01/2022 | SINO-11 | 6.5 | HWTH-827
48 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SINO-12L | Hrs | HRDH-1454
49 | STBG | TK1 | 72.5 | 28 Apr 2130 - 0500 | 8710 | 896069 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION | STUK | TBG |  | 05/01/2022 | SINO-12L | 24 | HRDH-1454
50 | 6598 | 180 | SET | N |  | RBP | HPJSM, M/U 9-5/8" RTTS PKR W/ STORM VALVE, SET SAME @ 180'. PT ANNULUS TO 1300 PSI, HOLD. RELEASED SETTING TOOL & PT CSG TO 1300 PSI, HOLD. | 6598 | 180 | HCB | 05/01/2022 | SINO-19L | WH | UTMN-1587
51 | 6598 |  | OTH | N |  | NA | HPJSM, PERFORMED GAS TEST CELLAR FREE FROM GASES.- CHECKED 9-5/8" X 13-3/8" CCA IS ZERO PRESSURE.- PT 9-5/8'' X1 3-3/8'' CCA WITH INH WTR TO 500, DROPPED TO 300 PSI THEN HOLD, GOOD.- PT 13-5/8" TBG SPOOL CAVETY SEAL AGAINST 9-5/8" SLIPS TO 1000 PSI, HOLD-OK | 6598 |  | RIG | 05/01/2022 | SINO-19L | WH | UTMN-1587
52 | 6598 |  | OTH | N |  | NA | ISSUED PTW AND REVISED JSA TO PERFORM WH WORK, DIG-OUT CELLAR 6' BELOW LANDING BASE FLANGE, FOUND 18-5/8" CSG IS SEAL WELDED TO DOUT PLATE OF LANDING BASE, PERFORMED UT INSPECTION FOR LANDING BASE AND 18-5/8" CASINGS, GOOD CONDITION.> KEEP MONITOR 13-3/8'' X 9-5/8'' CCA, ZERO READING | 6598 |  | RIG | 05/01/2022 | SINO-19L | WH | UTMN-1587
53 | 6598 |  | OTH | N | 2565 | NA | (OOS) HPJSM , WELDED 1-1/2" NIPPLE ON 18-5/8" CSG , MANSOORI PERFORM MPI FOR WELDINGS , BOOTS & COOTS R/U & P/T MPHT FOR 500 PSI / 1500 PSI- OK , BOOTS & COOTS PERFORMED HOT TAPPING ON 18-5/8" CSG , NO PRESSURE OR GAS ON 18-5/8" X 13-3/8" CCA , R/D MPHT . | 6598 |  | RIG | 05/01/2022 | SINO-19L | WH | UTMN-1587
54 | 6598 |  | OTH | N |  | NA | HOT-HED CUT WINDOW ON 18-5/8" CSG , REMOVE CMT , ALMANSOORI PERFORMED UT INSPECTION ON 13-3/8" CSG ( GOOD CONDITION ), BACK FILL 18-5/8" X 13-3/8" CCA W/ CMT, HOT-HED WELD BACK WINDOW, MANSOORI PERFORM MPI FOR WELDING AREA, OK , BACK FILL CELLAR W/ SWEET SAND.- PAINTED EXPOSED CASING WITH COATED PAINT.- INSTALLED NEW 2-1/16" CIW 3M SIDE OUTLET VALVE TO OLD FMC THS. P/T VALVE TO 300/2550 PSI, HOLD. | 6598 |  | RIG | 05/01/2022 | SINO-19L | WH | UTMN-1587
55 | 6598 |  | OTH | N |  | NA | HPJSM, M/U AND RIH WITH HALLIBURTON RETRIEVING TOOL, LATCHED & RETRIVED 9-5/8" RTTS PKR. | 6598 |  | HCB | 05/01/2022 | SINO-19L | PA | UTMN-1587
56 | 6598 | 0 | TO | N |  | STDP | POH W/ EZSV-CR MST ON 4'' HWDP TO SURFACE.> KEEP FILLING HOLE AND MONITOR - STATIC | 6598 | 3000 | RIG | 05/01/2022 | SINO-19L | PA | UTMN-1587
57 | 6598 |  | HT | N |  | STRG | L/D HALLIBURTON CEMENT STINGER. | 6598 |  | RIG | 05/01/2022 | SINO-19L | PA | UTMN-1587
58 | 6598 |  | HT | N |  | BHA | HPJSM, P/U & M/U 7'' WFD QC RHN HYD WHIPSTOCK W/ MILLING BHA, SCRIBE LINE WITH UBHO.> BHA: 7" QC RHN WHIPSTOCK, 6" QUICK CUT LEAD MILL, 6-1/8" FLEX MILL, 1 X 3-1/2" HWDP, F/S WITH FLOAT VALVE, UBHO, FLOAT SUB, X/O, 45 X 4"HWDP, 4" DP> KEEP FILLING HOLE AND MONITOR - STATIC | 6598 |  | RIG | 05/01/2022 | SINO-19L | TINL | UTMN-1587
59 | 6598 | 5331 | ST | N |  | STDP | RIH W/ 7'' WFD QC RHN HYD WHIPSTOCK ASSY. ON DRIFTED 4" HWDP/DP STD'S AT CONTROLLED SPEED TO SETTING DEPTH 5331'.> KEEP MONITOR WELL ON TRIP TANK - STATIC | 6598 | 0 | RIG | 05/01/2022 | SINO-19L | TINL | UTMN-1587
60 | 6598 |  | SURV | N |  | GYRO | HPJSM, R/U GYRO SHEAVES & M/U GYRO TOOL, RIH WHILE RECORDING MULTI-SHOT SURVEYS EVERY 100' TILL LANDED IN UBHO, ORIENT WHIPSTOCK TO 45 RIGHT HIGH SIDE AZIMUTH, POH TO SURFACE. R/D GYRO TOOLS & SHEAVES.- CONFIRMED WHIPSTOCK ORIENTATION WITH THREE GYRO SHOTS. | 6598 |  | GCD | 05/01/2022 | SINO-19L | TINL | UTMN-1587
61 | 6598 | 5331 | SET | N |  | WPSTK | HPJSM, SET 7" WFD WHIPSTOCK BY PUMPING 420 GPM, CONFIRMED SET W/ 15 KLBS S/OFF AND SHEARED-OFF BOLT W/ 32 KLB S/O WT & ENERGIZED ANCHOR W/ 40 KLBS S/OFF.- TOW @ 5315', BOW @ 5324', BOTTOM OF WHIPSTOCK @ 5331'. | 6598 | 5331 | WWD | 05/01/2022 | SINO-19L | TINL | UTMN-1587
62 | 6598 |  | CIRC | N |  | MPMP | SWEPT HOLE W/ 20 BBL HI VIS AND DISPLACED HOLE TO 82 PCF POLYMER MUD. MW IN / MW OUT = 82 PCF. FLOW CHECK, WELL STATIC. | 6598 |  | RIG | 05/01/2022 | SINO-19L | TINL | UTMN-1587
63 | 6598 | 5324 | MILL | N |  | MILL | SET MILLING PARAMETERS, MILL & CUT WINDOW IN 7" CSG F/ 5315 FT (TOW) T/ 5324 FT (BOW) W/ 82 PCF POLYMER MUD & 100% RETURNS. | 6598 | 5315 | WFS | 05/01/2022 | SINO-19L | TINL | UTMN-1587
64 | 5324 |  | TINL | S |  | NA | TIE-IN NEW LATERAL L-0-1. | 5324 |  | RIG | 05/01/2022 | SINO-19L | OT | UTMN-1587
65 | 5324 | 5329 | DO | N |  | MMOT | DRILL RAT HOLE F/ 5324 FT (BOW) T/ 5332 FT (KOP) W/ 82 PCF POLYMER MUD & HI-VIS PILLS, 100% CIRC.........INC@RPT. | 5324 | 5324 | RIG | 05/01/2022 | SINO-19L | TINL | UTMN-1587
66 | 1.5 | OOSS | Category | DOOS ID | HTAP | Out of Scope Summary | PERFORMED HOT TAPPING ON SEAL WELDED 18-5/8" CSG. | 1.5 | 2565 | 01 May 0830 | 05/01/2022 | SINO-19L | Type | UTMN-1587
67
68
69 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SINO-27N | Hrs | UTMN-432
70 | FOT | SCB | 37.25 | 30 Apr 1545 - 0500 | 1500 | 896010 | SLB COULD'T RETREIVE RBP 4.5" SIMPLUS PLUG. | TF | BP |  | 05/01/2022 | SINO-27N | 24 | UTMN-432
71 |  | 896105 | BCM | WOC |  | 903 | WOC, MEANWHILE MONITOR 30" X 24" CCA PRESSURE.- CCA PRESSURE INCREASED GRADUALLY TO 80 PSI IN 5 HOURS THEN STABILIZED.- SURFACE SAMPLE HARD. |  | CMT | 903 | 05/01/2022 | SINO-32L | CSG | SHYB-570
72 |  | 896105 | BCM | TOP |  | 903 | PERFORMED 2ND SQUEEZE TOP JOB AS FOLLOW:- FLUSH CEMENT LINES. - PUMP AND SQUEEZE 6 BBL,118 PCF SILICATE GAS BLOCK CMT SLURRY AT 0.4 BPM (30 SXS CMT G, 0.01 GPS FP-12L, 1% BWOC BA-10, 0.3%BWOC CD-32, 0.2%BWOC A-2(SMS)). PRESSURE LOCK UP AT 120 PSI MAXIMUM PRESSURE, HOLD PRESSURE FOR 15 MINUTES. BLEED OFF PRESSURE TO ZERO PSI, GOT 1.0 BBLS RETURN.- FLUSH CEMENTING LINES AND CONDUCTOR GATE VALVE. |  | CMT | 903 | 05/01/2022 | SINO-32L | CSG | SHYB-570
73 |  | 896105 | BCM | WOC |  | 903 | WOC MEANWHILE MONITORING 30" X 24" CCA PRESSURE ZERO PSI, SURFACE SAMPLE -HARD.- TOTAL WOC 6.0 HRS. |  | CMT | 903 | 05/01/2022 | SINO-32L | CSG | SHYB-570
74 |  | 896105 | RIG | WCNT |  | 903 | OPEN CELLAR GATE VALVE, F/C, NO FLOW THEN OPEN 30" DIVERTER, FLOW CHECK FOR ONE HOUR, WELL STATIC. NO FLOW, NO BUBBLES.** CHECK CMT LEVEL FOUND AT 41 FT (BTM OF CELLAR). |  | CMT | 903 | 05/01/2022 | SINO-32L | NA | SHYB-570
75 |  |  | RIG | OTH | 2504 | 903 | HPJSM, HANG UP 30" DIVERTER USING TWO SYSTEMS (RIG BOP HOISTING SYSTEM & TWO 20T SLINGS TO TRAVELLING BLOCK AS SECONDARY RETENTION).- DISCONNECT 8" DIVERTER VENT LINES & FLOW LINE. |  |  | 903 | 05/01/2022 | SINO-32L | DVRT | SHYB-570
76 |  |  | RIG | OTH | 2504 | 903 | HPSJM, RIG WELDER CUT 30" CONDUCTOR PIPE, LIFT DIVERTER & WELD 2 X HALF-MOON PLATES WITH THREE COMPLETE WELDING PASSES TO SEAL & ISOLATE 30" X 24" CCA. - PRESSURE TEST TO 100 PSI & CHECK WITH SOAP, NO PIN HOLES. |  |  | 903 | 05/01/2022 | SINO-32L | NA | SHYB-570
77 |  |  | RIG | OTH | 2504 | 903 | ROUGH CUT 24" CSG LANDING JT & L/D CUT-OFF JT. N/D 30" DIVERTER, DISCONNECT 30" X 30" WELD NECK FLANGE... IN PROGRESS. |  |  | 903 | 05/01/2022 | SINO-32L | NA | SHYB-570
78 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SINO-32L | Hrs | SHYB-570
79 | HFFT | BCM | 35 | 29 Apr 2300 - 2300 | 902 | 896105 | WHILE 24" CSG CMT JOB, CMT WEIGHT NOT MAINTAINED 122 PCF AS PG, FLUCTUATED BETWEEN 105-122, SWITCHED TO THE BACKUP CEMENT UNIT BUT HAD SAME PROBLEM, CIRCULATED OUT CMT SLURRY, REPEATED 24" CMT JOB, AFTER WOC, HAD 90 PSI CCA PRESSURE DUE TO CHANNELLING THRU CEMENT. PERFORMED 2 SQUEEZE TOP JOB. | CMT | NA |  | 05/01/2022 | SINO-32L | 18 | SHYB-570
80 | 35 | OOS | Category | DOOS ID | DRLG | Out of Scope Summary | DRILL 28" SECTION & RUN ADDITIONAL 24" CSG TO COVER SHALLOW GAS ZONE. | 6 | 2504 | 29 Apr 0700 | 05/01/2022 | SINO-32L | Type | SHYB-570
81
82
83 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SND-1501 | Hrs | UTMN-567
84 | FOT | BC | 135.25 | 26 Apr 1115 - 0500 | 0 | 895984 | AFTER DISPLACED WELL TO DIESEL OBERVED WELL NOT STATIC W/ STEADY RETURNS | TF | PKR |  | 05/01/2022 | SND-1501 | 24 | UTMN-567
85 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SND-2005 | Hrs | MHKK-2
86 | FOT | ARM | 7.5 | 01 May 2130 - 0500 | 10000 | 896178 | UNABLE TO RETRIEVE WEAR BUSHING F/ WH PROFILE. | WH | WBSH |  | 05/01/2022 | SND-2005 | 7.5 | MHKK-2
87 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SP-101 | Hrs | ABQQ-710
88 | FOT | WI1 | 108.5 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/01/2022 | SP-101 | 18.5 | ABQQ-710
89 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SP-120 | Hrs | MNIF-188
90 | FOT | BHI | 1.5 | 01 May 0330 - 0500 | 3480 | 896015 | MWD STOP PULSING | BHA | MWD |  | 05/01/2022 | SP-120 | 1.5 | MNIF-188
91 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SP-161 | Hrs | HWYH-680
92 | STBH | ARM | 24.5 | 30 Apr 2300 - 2330 | 7185 | 896146 | CORING BHA STRING GOT STUCK AFTER BREAKING THE CORE. | STUK | CORC |  | 05/01/2022 | SP-161 | 18.5 | HWYH-680
93 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SP-259 | Hrs | HZEM-160402
94 | ETRQ | RIG | 24.5 | 30 Apr 0430 - 0500 | 6708 | 896166 | ROLLER REAMER PINS LOST IN HOLE | BHA | BHA |  | 05/01/2022 | SP-259 | 24 | HZEM-160402
95 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SP-260 | Hrs | HZEM-161012
96 | FOT | BHI | 1.25 | 01 May 1045 - 1200 | 17374 | 896167 | BAKER RSS DIRECTIONAL SENSOR SIGNAL IS LOST. | BHA | RSS |  | 05/01/2022 | SP-260 | 1.25 | HZEM-161012
97 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SSA-201 | Hrs | HRDH-1818
98 | HINW | ARM | 339.5 | 17 Apr 1500 - 0500 | 14502 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/01/2022 | SSA-201 | 24 | HRDH-1818
99 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SSA-303 | Hrs | HRDH-2306
100 | FOT | RIG | 1 | 01 May 0300 - 0400 | 2550 | 896173 | OBSERVE LEAK IN FLOW LINE HAMMER UNION | RR | FL |  | 05/01/2022 | SSA-303 | 1 | HRDH-2306
101 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SSA-5969 | Hrs | UTMN-3021
102 | UVLC | ARM | 1.5 | 01 May 0330 - 0500 | 8892 | 896172 | HAD PARTIAL LOSSES | LCIR | NA |  | 05/01/2022 | SSA-5969 | 1.5 | UTMN-3021
103 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | SSA-5974 | Hrs | HRDH-1970
104 | CWEL | ARM | 227.5 | 22 Apr 0500 - 0500 | 14884 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/01/2022 | SSA-5974 | 24 | HRDH-1970
105 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | STY-038 | Hrs | ZULF-2083
106 | FOT | HCO | 20.5 | 30 Apr 0300 - 2330 | 5497 | 896011 | HALLIBURTON UNSUCCESSFULLY ATTEMPT TO LATCH INTO VHR PKR WITH RATCH-LATCH TOOL | TF | SEAL |  | 05/01/2022 | STY-038 | 18.5 | ZULF-2083
107 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | T216 | Hrs | ANDR-95
108 | HINW | SWL | 3 | 01 May 0200 - 0500 | 0 | 896171 | WHILE RIH 7'' EZSV-CR GOT STUCK @ 1700'. | STUK | WLT |  | 05/01/2022 | T216 | 3 | ANDR-95
109 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/01/2022 | T914 | Hrs | HWYH-135
110 | FPMP | RIG | 4 | 01 May 1930 - 2330 | 9500 | 896014 | EXTRA CIRC TIME TO CONDITION MUD DUE TO PUMP EFFICIENCY & STROKE-COUNTER MALFUNCTION | RR | MPMP |  | 05/01/2022 | T914 | 4 | HWYH-135
111 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | 095TE | Hrs | MNIF-220
112 | FOT | BHI | 20.5 | 01 May 0330 - 0500 | 9430 | 896148 | LOST SIGNAL OF LWD , POOH TO CHANGE SAME. | BHA | LWD |  | 05/02/2022 | 095TE | 19.5 | MNIF-220
113 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | ADC-57L | Hrs | FDHL-158
114 | WSHO | TK3 | 104.75 | 27 Apr 2230 - 0500 | 13135 | 896041 | DRILL OUT 7" LNR SHOE TRACK 20 FT ABOVE FLOAT SHOE. P/T 7" CSG LNR TO 650 PSI PRESSURE DROP NOT HOLDING | CMT | CSG |  | 05/02/2022 | ADC-57L | 18.25 | FDHL-158
115 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | ADC-58L | Hrs | ABHD-178
116 | PCPF | TK3 | 201.5 | 23 Apr 0045 - 1045 | 6966 | 895847 | RIH WITH 13-3/8" CSG HARD WASH DOWN WITH CRT, HAD OBS @ 5222 FT. ATTEMPTED TO PASS MANY TIMES WITH DIFFERENT PARAMETERS WITHOUT SUCCESS. | TH | NA |  | 05/02/2022 | ADC-58L | 5.75 | ABHD-178
117 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | ADM-266 | Hrs | SFNY-934
118 | ORDS | ARM | 3.75 | 02 May 0115 - 0500 | 6404 | 896238 | WAIT ON RMD & GOC TO PROVIDE US WITH NEW TARGET ENTRY COORDINATES. | WO | NA |  | 05/02/2022 | ADM-266 | 3.75 | SFNY-934
119 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | AOD-1 | Hrs | ZULF-696
120 | FOT | RIG | .75 | 02 May 1345 - 1430 | 0 | 896152 | ATTEMPTED TO M/U TDS TO KELLY STAND, B/U GRIPPER WOULD NOT ENGAGE | RR | TDS |  | 05/02/2022 | AOD-1 | .75 | ZULF-696
121 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | AOD-11 | Hrs | SFNY-4280
122 | FOT | HSS | 1 | 02 May 1730 - 1830 | 287 | 896237 | HALLIBURTON AUGER TRIP. REPLACE POWER CABLE. | TF | SCS |  | 05/02/2022 | AOD-11 | 1 | SFNY-4280
123 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | CR-36A | Hrs | ZULF-2030
124 | FOT | NCT | 23.75 | 01 May 1100 - 1045 | 6300 | 896168 | NESR CT TROUBLE SHOOT & ATTEMPT TO REPAIR NITROGEN PUMP. | TF | CTBG |  | 05/02/2022 | CR-36A | 5.75 | ZULF-2030
125 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | DPS-74 | Hrs | NJYN-54
126 | FOT | BLH | 460.75 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/02/2022 | DPS-74 | 23.5 | NJYN-54
127 | 7550 |  | WCNT | E | 2564 | NA | FLOW CHECK AT CSG SHOE, WELL STATIC. | 7550 |  | RIG | 05/02/2022 | DQ-47 | CT | KHRS-1416
128 | 7550 | 350 | TO | N | 2564 | STDP | POOH W/ 8 1/2'' CONDITION TRIP BHA FOR LOGGING TO TOP BHA AT 350 FT. | 7550 | 3514 | RIG | 05/02/2022 | DQ-47 | CT | KHRS-1416
129 | 7550 |  | WCNT | E | 2564 | NA | FLOW CHECK, WELL STATIC - OK. | 7550 |  | RIG | 05/02/2022 | DQ-47 | CT | KHRS-1416
130 | 7550 |  | HT | E | 2564 | BHA | R/B 8 1/2" REAMING BHA & L/D 8 1/2" BIT. | 7550 |  | RIG | 05/02/2022 | DQ-47 | CT | KHRS-1416
131 | 7550 |  | OTH | E | 2564 | NA | HPJSM, P/U & M/U BKR RUN # 3 (RCX-GR) LOGGING TOOLS.- TOTAL LENGTH: 175.81' & MAX OD: 7.46''.- TESTED TOOLS & FUNCTIONS AT SURFACE - OK. | 7550 |  | BAW | 05/02/2022 | DQ-47 | LOG | KHRS-1416
132 | 7550 | 4200 | ST | E | 2564 | STDP | RIH W/ BKR RUN # 3 RCX/GR/PCL ON DRIFTED 5" DP T/ 4200'.- DRIFTED STRG. W/ 2.625" DRIFT EVERY STD.- BREAK CIRC. W/ 71 PCF OBM EVERY 10 STD.- MONITORED WELL THRU TRIP TANK, STATIC. | 7550 | 0 | RIG | 05/02/2022 | DQ-47 | LOG | KHRS-1416
133 | 7550 |  | CIRC | E | 2564 | MPMP | CIRC 2 STRING CAPACITY W/ 69 PCF OBM @ 250 GPM T/ 230 PSI, MEANWHILE R/U W/L SHEAVES. | 7550 |  | RIG | 05/02/2022 | DQ-47 | LOG | KHRS-1416
134 | 7550 |  | OTH | E | 2564 | NA | HPJSM, P/U & M/U BKR SIDE ENTRY SUB.- BKR RIH WITH W/L CONNECTOR HEAD BUMPED SAME.- LATCHED LOGGING TOOLS.- CHECKED TOOLS SIGNALS -OK.- SECURED CABLE ON SES WITH CLAMP & PULL TEST TO 5000 LB, OK.- MONITORED WELL THRU TRIP TANK, STATIC. | 7550 |  | BAW | 05/02/2022 | DQ-47 | LOG | KHRS-1416
135 | 7550 | 5605 | LOG | E | 2564 | WLT | RIH AT CONTROLLED SPEED W/ BHI LOGGING TOOLS RUN#3 (RCX-GR) ON DRIFTED 5" DP T/ 5605'.- BREAK CIRC W/ 69 PCF OBM MUD EVERY 10 STDS.- MONITORED WELL THRU TRIP TANK, STATIC. | 7550 | 4200 | BAW | 05/02/2022 | DQ-47 | LOG | KHRS-1416
136 | 7550 | 5822 | LOG | E | 2564 | WLT | BHI W/L LOGGING RECORDED PP WHILE LOG-DOWN.- PERFORM STICKY TEST FOR 15 MINS, OK.- RECORDED 12 OUT OF 23 PRESSURE POINTS F/ 5605' T/ 5822'. - PRESSURE POINTS @ 5605.5', 5650', 5655.5', 5666', 5673', 5690', 5705', 5731', 5749', 5775', 5793', 5822'.- PRESSURE POINTS ACROSS ARAB FM.- MONITORED WELL THRU TRIP TANK, STATIC. | 7550 | 5605 | BAW | 05/02/2022 | DQ-47 | LOG | KHRS-1416
137 | 69.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | BAKER W/L LOG FOR 8 1/2" PILOT HOLE. | 24 | 2564 | 30 Apr 0730 | 05/02/2022 | DQ-47 | Type | KHRS-1416
138
139
140 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | DQ-57L | Hrs | KHRS-227
141 | FOT | RIG | 1 | 02 May 2130 - 2230 | 4670 | 896198 | PRESSURE DROPPED DUE TO RIG MUD PUMPS FAILURE. | RR | MPMP |  | 05/02/2022 | DQ-57L | 1 | KHRS-227
142 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | HI-9 | Hrs | QTIF-557
143 | WTHR | ARM | 12 | 02 May 1700 - 0500 | 0 | 896153 | DUE TO HIGH CURRENT FIELD SERVICE BOAT UNABLE TO PROCEED TO PLATFROM TO CONFIRM DEPRESSURIZATION. | WON | NA |  | 05/02/2022 | HI-9 | 12 | QTIF-557
144 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | JACK-202 | Hrs | HMYM-844
145 | FOT | RIG | 2.75 | 02 May 0100 - 0345 | 1516 | 896236 | DRAWWORK COOLANT SYSTEM MOTOR DOWN. | RR | DWKS |  | 05/02/2022 | JACK-202 | 2.75 | HMYM-844
146 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | NBR-654S | Hrs | HRDH-2210
147 | FOT | RIG | 1 | 02 May 2130 - 2230 | 14431 | 896183 | CHIKSAN LINES LEAK. | TF | SFLN |  | 05/02/2022 | NBR-654S | 1 | HRDH-2210
148 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | PA-622S | Hrs | AFLJ-4
149 | PSSW | ARM | 180 | 24 Apr 1000 - 0500 | 6896 | 895875 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION. | STUK | NA |  | 05/02/2022 | PA-622S | 6.5 | AFLJ-4
150 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | RM-74A | Hrs | KARN-60
151 | FOT | SCT | 1.25 | 02 May 0230 - 0345 | 0 | 896197 | LOSS PRIME ON N2 TRIPLEX PUMP, AFTER N2 TRANSFER | TF | CTPMP |  | 05/02/2022 | RM-74A | 1.25 | KARN-60
152 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SCTD-2 | Hrs | HRDH-1853
153 | FOT | RIG | 16 | 02 May 0930 - 0130 | 15100 | 896174 | LOST COMMUNICATION WITH BHA, TROUBLESHOOT WITH NO SUCCESS | BHA | MMOT |  | 05/02/2022 | SCTD-2 | 16 | HRDH-1853
154 | 17315 |  | STIM | E | 2545 | CTU | CONT. R/U CT EQUIPMENT.- CONTINUE CONNECTING REQUIRED RISER SECTIONS.- CONNECT HIGH PRESSUER LINE.- CONNECT 2" GROUND LINES.- PERFORM 30 KLB PULL TEST ON COIL CONNECTOR - OK .- SPOT 130T CRANE, HANG COIL TBG INJECTOR HEAD/RISERS.- FLUSH CT LINE AND P/T CT CONNECTOR @ 500/8500PSI.- P/T CT BOP BLIND RAM AGAINST GATE VALVE TO 500/2500 PSI.- DRIFT CT WITH 1" BALL & CHASE SAME W/ WTR, RETRIEVED BALL - OK .- MONITOR THE WELL THROUGH TRIP TANK WHILE, +/- 3 BBL/HR STATIC LOSSES. | 17315 |  | BCT | 05/02/2022 | SIN30L | STIM | KHRS-1409
155 | 17315 |  | STIM | E | 2545 | CTU | HPJSM, M/U BHA AS PER BKR AND NOV REPRESENTATIVE. - FUNCTION TEST THE SAME AS PER NOV: - WITHOUT AGITATOR : 1 BPM = 350 PSI, 1.5 BPM = 690 PSI, 2 BPM = 960 PSI, 2.5 BPM = 1200 PSI, 3 BPM = 1600 PSI.- WITH AGITATOR : 1.5 BPM = 950 PSI, 2 BPM = 1427 PSI, 2.5 BPM = 980 PSI, 3 BPM = 2600 PSI.- P/T 13-5/8" BLIND RAMS AGAINST CTU GATE VALVE TO 300/ 1500 PSI, OK. - P/T GATE VALVE AGAINST CT STRIPPER TO 500/2500 PSI.- MONITOR THE WELL THROUGH TRIP TANK WHILE, +/- 3 BBL/HR STATIC LOSSES. | 17315 |  | BCT | 05/02/2022 | SIN30L | STIM | KHRS-1409
156 | 17315 |  | STIM | E | 2545 | CTU | RIH W/ BHI 2-3/8" CT AS PER BHI STANDARD PROCEDURES TO 7000'- CT RIH SPEED: 30-40 FT/MIN.- PUMP 66 PCF BRINE @ 0.5 BPM.- START TO DISPLACE CT W/ 140 BBLS EASY REACH @ 3500' TO BE OUT OF CT AT 7000'.- PERFORM PULL TEST EVERY 1000'-1500'. | 17315 |  | BCT | 05/02/2022 | SIN30L | STIM | KHRS-1409
157 | 35 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 24 | 2545 | 01 May 1800 | 05/02/2022 | SIN30L | Type | KHRS-1409
158
159
160 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SINO-15L | Hrs | ANDR-478
161 | FOT | NGS | 3 | 02 May 1700 - 2000 | 0 | 896184 | TOOL MISCOMMUNICATION, TROUBLE SHOOTING GYRO. | TF | GYRO |  | 05/02/2022 | SINO-15L | 3 | ANDR-478
162 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SINO-27N | Hrs | UTMN-432
163 | FOT | SCB | 61.25 | 30 Apr 1545 - 0500 | 1500 | 896010 | SLB COULD'T RETREIVE RBP 4.5" SIMPLUS PLUG. | TF | BP |  | 05/02/2022 | SINO-27N | 24 | UTMN-432
164 | 903 |  | OTH | N | 2504 | DVRT | CONT N/D 30" DIVERTER, DISCONNECT 30" X 30" WELD NECK FLANGE. | 903 |  | RIG | 05/02/2022 | SINO-32L | BOP | SHYB-570
165 | 903 |  | OTH | N | 2504 | NA | FINAL CUT 24" CSG. INSTALL & WELD 24" X 30" - 1K WELD NECK FLANGE ON 24" CSG.- WELD 2" NIPPLE ON 24" CSG, INSTALL 2-1/16''-3M GATE VALVE. | 903 |  | RIG | 05/02/2022 | SINO-32L | WH | SHYB-570
166 | 903 |  | OTH | N | 2504 | DVRT | HPJSM, N/U 30"-1M MUD CROSS + 30"-1M ANNULAR DIVERTER + 2 X 7-1/16"-2M HCR VALVES. | 903 |  | RIG | 05/02/2022 | SINO-32L | BOP | SHYB-570
167 | 903 |  | NU | N | 2504 | BNIP | N/U BELL NIPPLE. CONNECT FLOW LINE, KILL LINE, AND 2 X 8" DIVERTER VENT LINES. | 903 |  | RIG | 05/02/2022 | SINO-32L | BOP | SHYB-570
168 | 903 |  | BOPT | N | 2504 | DVRT | FUNCTION TEST 30" DIVERTER & HCR'S FROM ALL CONTROL UNITS.- FLUSH DIVERTER & VENT LINES WITH WATER.- HYDRO TEST DIVERTER VENT LINES, CHECK INTEGRITY FOR LEAKAGE- OK.- P/T 30" DIVERTER AGAINST 24" CSG TO 200 PSI, OK.- P/T KILL LINE TO 1500 PSI, OK. | 903 |  | RIG | 05/02/2022 | SINO-32L | BOP | SHYB-570
169 | 903 |  | HT | N | 2504 | BHA | HPJSM, P/U & M/U 22" ROTARY BHA. | 903 |  | RIG | 05/02/2022 | SINO-32L | DRLG | SHYB-570
170 | 903 |  | HT | N | 2504 | BHA | RIH 22" BHA TO 875', WASHED DOWN LAST STAND & TAG CMT AT 900'. | 903 |  | RIG | 05/02/2022 | SINO-32L | DRLG | SHYB-570
171 | 903 |  | CIRC | N | 2504 | MPMP | DISPLACED HOLE TO 70 PCF POLYMER MUD AS PER DRILLING MUD PROGRAM. MW IN =MW OUT = 70 PCF. | 903 |  | RIG | 05/02/2022 | SINO-32L | DRLG | SHYB-570
172 | 903 | 903 | DFS | N | 2504 | TDS | HPJSM, DRILL OUT CMT & 24" FLOAT SHOE TO 902' & C/O RAT HOLE TO BTM @ 903'. | 903 | 900 | RIG | 05/02/2022 | SINO-32L | DRLG | SHYB-570
173 | 913 |  | D | N |  | TDS | ROTARY DRILLED 10 FT NEW FM 22" HOLE VERTICAL HOLE W/70 PCF POLYMER MUD & 100% CIRC. | 903 |  | RIG | 05/02/2022 | SINO-32L | DRLG | SHYB-570
174 | 913 |  | WCNT | N |  | NA | FLOW CHECK- WELL STATIC. | 913 |  | RIG | 05/02/2022 | SINO-32L | DRLG | SHYB-570
175 | 1475 |  | D | N |  | TDS | ROTARY DRILL 22" VERTICAL HOLE W/70 PCF POLYMER MUD AT CONTROLLED ROP & 99% CIRC. * SWEEP HOLE W/30 BBLS HI-VIS IN EVERY 45 FT DRILLED. * WASH UP & REAM DOWN EACH STAND.* LOADED SYSTEM WITH 35 PPB LCM.* QUICK FLOW CHECK EVERY CONNECTION.* CONTROLLED DRILLING PARAMETER TILL PASS ROLLER REAMERS THROUGH 24" CASING SHOE. | 913 |  | RIG | 05/02/2022 | SINO-32L | DRLG | SHYB-570
176 | 46.5 | OOS | Category | DOOS ID | DRLG | Out of Scope Summary | DRILL 28" SECTION & RUN ADDITIONAL 24" CSG TO COVER SHALLOW GAS ZONE. | 11.5 | 2504 | 29 Apr 0700 | 05/02/2022 | SINO-32L | Type | SHYB-570
177
178
179 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SND-1501 | Hrs | UTMN-567
180 | FOT | BC | 159.25 | 26 Apr 1115 - 0500 | 0 | 895984 | AFTER DISPLACED WELL TO DIESEL OBERVED WELL NOT STATIC W/ STEADY RETURNS | TF | PKR |  | 05/02/2022 | SND-1501 | 24 | UTMN-567
181 | HERR | MSD | 2 | 02 May 0645 - 0845 | 567 | 896175 | AL MASAOOD PERFORMED IMPROER MAKE UP LEADING TO CONNECTION THREAD DAMAGE, POOH & REPLACED THREE 9-5/8"CASING JOINTS. | JF | CTRQ |  | 05/02/2022 | SND-2004 | 2 | BRRI-1148
182 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SND-2004 | Hrs | BRRI-1148
183 | XTRI | MSD | 1.25 | 02 May 1045 - 1200 | 1769 | 896154 | EXCESSIVE TIME FOR 9 5/8 CSG MAKE UP DUE TO POWER TONG DIES WORN OUT, CHANGED POWER TONG. | JF | CTRQ |  | 05/02/2022 | SND-2004 | 1.25 | BRRI-1148
184 | HERR | MSD | 2 | 02 May 0645 - 0845 | 567 | 896175 | AL MASAOOD PERFORMED IMPROER MAKE UP LEADING TO CONNECTION THREAD DAMAGE, POOH & REPLACED THREE 9-5/8"CASING JOINTS. | JF | CTRQ |  | 05/02/2022 | SND-2004 | 2 | BRRI-1148
185 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SND-2005 | Hrs | MHKK-2
186 | FOT | DEL | 23.25 | 01 May 2130 - 0500 | 10000 | 896178 | UNABLE TO RETRIEVE WEAR BUSHING F/ WH PROFILE. | WH | WBSH |  | 05/02/2022 | SND-2005 | 15.75 | MHKK-2
187 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SP-101 | Hrs | ABQQ-710
188 | FOT | WI1 | 132.5 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/02/2022 | SP-101 | 24 | ABQQ-710
189 | FRFM | ARM | 1 | 02 May 2100 - 2200 | 4343 | 896155 | TOTAL LOSSES WHILE DRLG ARUMA FM. | LCIR | NA |  | 05/02/2022 | SP-120 | 1 | MNIF-188
190 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SP-120 | Hrs | MNIF-188
191 | FOT | BHI | 4.5 | 01 May 0330 - 0800 | 3480 | 896015 | MWD LOST SIGNAL | BHA | MWD |  | 05/02/2022 | SP-120 | 3 | MNIF-188
192 | FRFM | ARM | 1 | 02 May 2100 - 2200 | 4343 | 896155 | TOTAL LOSSES WHILE DRLG ARUMA FM. | LCIR | NA |  | 05/02/2022 | SP-120 | 1 | MNIF-188
193 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SP-124 | Hrs | ABHD-111
194 | HERR | HCO | 2 | 02 May 1500 - 1700 | 620 | 896182 | EXCESS TIME TO MAKE UP CABLE TO UPPER PDHMS ASSY | TF | TBG |  | 05/02/2022 | SP-124 | 2 | ABHD-111
195 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SP-160 | Hrs | HWTH-72
196 | FWTS | RIG | 17.25 | 02 May 1145 - 0500 | 8444 | 896181 | WHILE BACK REAM, STRING STALLED, LOST ROTATION AND CIRCULATION. ATTEMPT TO GET ROTATION WHILE JARING DOWN SUCCESSFULLY. REESTABLISH CIRCULATION GRADUALLY TO 90 GPM , DISPLACE HOLE TO 75 PCF OBM. KEEP STRING IN ROTATION. POOH, FOUND SHEARED OFF PIN BETWEEN THE TWO LAST 4" HWDP ABOVE DOG LEG REAMER. | FISH | BHA |  | 05/02/2022 | SP-160 | 17.25 | HWTH-72
197 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SP-259 | Hrs | HZEM-160402
198 | ETRQ | RIG | 29.5 | 30 Apr 0430 - 1000 | 6708 | 896166 | ROLLER REAMER PINS LOST IN HOLE | BHA | BHA |  | 05/02/2022 | SP-259 | 5 | HZEM-160402
199 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SP-260 | Hrs | HZEM-161012
200 | FOT | BHI | 2.25 | 01 May 1045 - 1030 | 17374 | 896167 | BAKER RSS DIRECTIONAL SENSOR SIGNAL IS LOST. | BHA | RSS |  | 05/02/2022 | SP-260 | 1 | HZEM-161012
201 | FOT | RIG | 1.5 | 02 May 1030 - 1200 | 18491 | 896180 | FOUND DAMAGE ON DRILLING LINE, RE-SLIP & CUT DRILLING LINE. | RR | DWKS |  | 05/02/2022 | SP-262 | 1.5 | HZEM-140814
202 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SP-262 | Hrs | HZEM-140814
203 | FOT | SPR | 3 | 02 May 0500 - 1330 | 18491 | 896179 | LEAKAGE ON CRT HYDRAULIC SERVICE LOOP, RUN CASING WITH SIDE DOOR ELEVATOR UNTIL RECEIVED NEW SERVICE LOOP THEN USED CRT. | TF | CRT |  | 05/02/2022 | SP-262 | 3 | HZEM-140814
204 | FOT | RIG | 1.5 | 02 May 1030 - 1200 | 18491 | 896180 | FOUND DAMAGE ON DRILLING LINE, RE-SLIP & CUT DRILLING LINE. | RR | DWKS |  | 05/02/2022 | SP-262 | 1.5 | HZEM-140814
205 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SSA-201 | Hrs | HRDH-1818
206 | HINW | ARM | 363.5 | 17 Apr 1500 - 0500 | 14502 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/02/2022 | SSA-201 | 24 | HRDH-1818
207 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | SSA-5969 | Hrs | UTMN-3021
208 | UVLC | ARM | 23.5 | 01 May 0330 - 0300 | 8892 | 896172 | HAD PARTIAL LOSSES | LCIR | NA |  | 05/02/2022 | SSA-5969 | 22 | UTMN-3021
209 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | STY-038 | Hrs | ZULF-2083
210 | FOT | HCO | 36.5 | 30 Apr 0300 - 0500 | 5497 | 896011 | HALLIBURTON UNSUCCESSFULLY ATTEMPT TO LATCH INTO VHR PKR WITH RATCH-LATCH TOOL | TF | SEAL |  | 05/02/2022 | STY-038 | 16 | ZULF-2083
211 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/02/2022 | V140A | Hrs | SFNY-1760
212 | FOT | RIG | 3 | 02 May 1230 - 1530 | 269 | 896196 | TDS BLOWER MOTOR OVERHEAT & SHUTING DOWN WHILE DRILLING. | RR | TDS |  | 05/02/2022 | V140A | 3 | SFNY-1760
213 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | 095TE | Hrs | MNIF-220
214 | FOT | BHI | 26.25 | 01 May 0330 - 1045 | 9430 | 896148 | LOST SIGNAL OF LWD , POOH TO CHANGE SAME. | BHA | LWD |  | 05/03/2022 | 095TE | 5.75 | MNIF-220
215 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | ADC-12 | Hrs | ABQQ-84
216 | SDIR | SPS | 1 | 03 May 1215 - 1315 | 7318 | 896217 | STRG STUCK @ BTM WHILE SLIDING. | STUK | MMOT |  | 05/03/2022 | ADC-12 | 1 | ABQQ-84
217 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | ADC-21 | Hrs | MZLJ-155201
218 | PSSW | ARM | 21 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/03/2022 | ADC-21 | 21 | MZLJ-155201
219 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | ADC-42L | Hrs | UTMN-2327
220 | FOT | SDM | 10.25 | 03 May 1430 - 0500 | 10952 | 896242 | SEVERAL TIMES TO SEND DOWN LINK TO CHECK TOOLS. NO RESPONSE FROM TOOLS. | BHA | MWD |  | 05/03/2022 | ADC-42L | 10.25 | UTMN-2327
221 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | ADC-68L | Hrs | KRSN-168
222 | HMWT | ARM | 5.75 | 03 May 1730 - 2315 | 2038 | 896243 | WATER WELL PUMP NOT WORKING AND WATER LINE WAS PARTED. | WO | NA |  | 05/03/2022 | ADC-68L | 5.75 | KRSN-168
223 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | ADM-262 | Hrs | MRJN-123
224 | FOT | BHI | 4 | 03 May 0100 - 0500 | 9013 | 896186 | LOST RESPONSE FROM BAKER RESISTIVITY SENSOR IN AZI-TRACK. TROUBLESHOOT SAME WITH NO SUCCESS. | BHA | LWD |  | 05/03/2022 | ADM-262 | 4 | MRJN-123
225 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | ADM-266 | Hrs | SFNY-934
226 | ORDS | ARM | 8 | 02 May 0115 - 0915 | 6404 | 896238 | WAIT ON RMD & GOC TO PROVIDE US WITH NEW TARGET ENTRY COORDINATES. | WO | NA |  | 05/03/2022 | ADM-266 | 4.25 | SFNY-934
227 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | ARO-3001 | Hrs | ZULF-2058
228 | XTRI | BCR | .5 | 03 May 0930 - 1000 | 0 | 896219 | EXCESS TIME LAYING DOWN 2 3/8" INNER STRING. | JF | CTRQ |  | 05/03/2022 | ARO-3001 | .5 | ZULF-2058
229 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | DPS-4 | Hrs | MDRK-54
230 | STBH | ARM | 243.75 | 15 Apr 1900 - 0500 | 16058 | 895547 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. | STUK | BHA | 895515 | 05/03/2022 | DPS-4 | 7 | MDRK-54
231 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | DPS-74 | Hrs | NJYN-54
232 | FOT | BLH | 484.75 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/03/2022 | DPS-74 | 24 | NJYN-54
233 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | DQ-57L | Hrs | KHRS-227
234 | FOT | RIG | 3.5 | 03 May 0845 - 1430 | 5112 | 896220 | NOTICED DRILLING LINE ON THE DRAWWORKS SLIGHTLY FLATTENED. | RR | DWKS |  | 05/03/2022 | DQ-57L | 3.5 | KHRS-227
235 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | HI-9 | Hrs | QTIF-557
236 | WTHR | ARM | 19 | 02 May 1700 - 1600 | 0 | 896153 | DUE TO HIGH CURRENT FIELD SERVICE BOAT UNABLE TO PROCEED TO PLATFROM TO CONFIRM DEPRESSURIZATION. | WON | NA |  | 05/03/2022 | HI-9 | 7 | QTIF-557
237 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | NBR-591S | Hrs | HRDH-1921
238 | FOT | RIG | 1.5 | 03 May 0030 - 0200 | 10265 | 896199 | OBSERVE DROP IN PRESSSURE DUE TO O-RING SEAL FAILURE ON MP#3 HARD LINE WHILE REPAIRING MP#1 WEAR PLATE. | RR | MPMP |  | 05/03/2022 | NBR-591S | 1.5 | HRDH-1921
239 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | PA-622S | Hrs | AFLJ-4
240 | PSSW | ARM | 204 | 24 Apr 1000 - 0500 | 6896 | 895875 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION. | STUK | NA |  | 05/03/2022 | PA-622S | 24 | AFLJ-4
241 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SINO-12L | Hrs | HRDH-1454
242 | STBG | TK1 | 110 | 28 Apr 2130 - 1830 | 8710 | 896069 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION | STUK | TBG |  | 05/03/2022 | SINO-12L | 13.5 | HRDH-1454
243 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SINO-27N | Hrs | UTMN-432
244 | FOT | SCB | 66.25 | 30 Apr 1545 - 1000 | 1500 | 896010 | SLB COULD'T RETREIVE RBP 4.5" SIMPLUS PLUG. | TF | BP |  | 05/03/2022 | SINO-27N | 5 | UTMN-432
245 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SINO-43L | Hrs | HWYH-2528
246 | FOT | RIG | 8 | 03 May 1130 - 1930 | 329 | 896240 | FOUND LEAKAGE ON UPPER IBOP, DUE TO CRACK ON UPPER IBOP BODDY. | RR | TDS |  | 05/03/2022 | SINO-43L | 8 | HWYH-2528
247 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SND-1501 | Hrs | UTMN-567
248 | FOT | BC | 183.25 | 26 Apr 1115 - 0500 | 0 | 895984 | AFTER DISPLACED WELL TO DIESEL OBERVED WELL NOT STATIC W/ STEADY RETURNS | TF | PKR |  | 05/03/2022 | SND-1501 | 24 | UTMN-567
249 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SND-2005 | Hrs | MHKK-2
250 | FOT | DEL | 36.75 | 01 May 2130 - 1830 | 10000 | 896178 | UNABLE TO RETRIEVE WEAR BUSHING F/ WH PROFILE. | WH | WBSH |  | 05/03/2022 | SND-2005 | 13.5 | MHKK-2
251 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SND-2006 | Hrs | UTMN-3165
252 | FOT | RIG | 4.5 | 02 May 0330 - 0800 | 580 | 896241 | WHILE CIRCULATING PRIOR TO PERFORM THE CEMENT JOB, THE SUBMERSIBLE PUMP AND JAEGER PUMP AT CALLER NOT WORKING DUE NOT EQUIP WITH FOOT VALUE, BREAK AND CIRCULATE EVERY 30 MIN MEANWHILE TROUBLE SHOOTING. | RR | CSYS |  | 05/03/2022 | SND-2006 | 3 | UTMN-3165
253 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SP-101 | Hrs | ABQQ-710
254 | FOT | WI1 | 156.5 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/03/2022 | SP-101 | 24 | ABQQ-710
255 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SP-124 | Hrs | ABHD-111
256 | HERR | ODJ | 17.5 | 03 May 0500 - 2230 | 944 | 896239 | UNABLE TO DRIFT 4-1/2" COMPLETION. POH AND FOUND JOINT OVERTORQUED AND COLLAR SQUASHED | TF | TTRQ |  | 05/03/2022 | SP-124 | 17.5 | ABHD-111
257 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SSA-201 | Hrs | HRDH-1818
258 | HINW | ARM | 387.5 | 17 Apr 1500 - 0500 | 14502 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/03/2022 | SSA-201 | 24 | HRDH-1818
259 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | SSA-5969 | Hrs | UTMN-3021
260 | UVLC | ARM | 29.5 | 01 May 0330 - 1100 | 8892 | 896172 | HAD PARTIAL LOSSES | LCIR | NA |  | 05/03/2022 | SSA-5969 | 6 | UTMN-3021
261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/03/2022 | STY-038 | Hrs | ZULF-2083
262 | FOT | HCO | 56.75 | 30 Apr 0300 - 0115 | 5497 | 896011 | HALLIBURTON UNSUCCESSFULLY ATTEMPT TO LATCH INTO VHR PKR WITH RATCH-LATCH TOOL | TF | SEAL |  | 05/03/2022 | STY-038 | 20.25 | ZULF-2083
263 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | ADC-21 | Hrs | MZLJ-155201
264 | PSSW | ARM | 45 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/04/2022 | ADC-21 | 24 | MZLJ-155201
265 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | ADC-49 | Hrs | HRDH-2128
266 | FOT | MSD | 2 | 28 Apr 0130 - 0330 | 1400 | 896096 | AFTER P/U CSG JT FROM RACK WITH CRT LINKS AND STAB IN WITH JT FOR M/U, CRT LINKS DIDN'T RETRACT COMPLETELY TO CENTER THE JOINT WHILE M/U | TF | CRT |  | 05/04/2022 | ADC-49 | 1 | HRDH-2128
267 | 7109 | 4620 | TO | N |  | STDP | CONT'D POOH WITH 8-1/2" MOTORIZED BHA TO 9-5/8" SHOE @ 4620'. OPEN HOLE IN GOOD CONDITION.- MONITORED WELL ON TRIP TANK. | 7109 | 5200 | RIG | 05/04/2022 | ADC-53L | DRLG | UTMN-4069
268 | 7109 |  | OTH | N |  | NA | FLOW CHECK @ CSG SHOE- WELL STATIC. | 7109 |  | RIG | 05/04/2022 | ADC-53L | DRLG | UTMN-4069
269 | 7109 | 1220 | TO | N |  | STDP | CONT'D POOH WITH 8-1/2" MOTORIZED BHA TO 5 STDS BEFORE BHA @ 1220 FT.- MONITORED WELL ON TRIP TANK. | 7109 | 4620 | RIG | 05/04/2022 | ADC-53L | DRLG | UTMN-4069
270 | 7109 |  | OTH | N |  | NA | FLOW CHECK @ 5 STDS BEFORE BHA TOP- WELL STATIC. | 7109 |  | RIG | 05/04/2022 | ADC-53L | DRLG | UTMN-4069
271 | 7109 | 774 | TO | N |  | STDP | CONT'D POOH WITH 8-1/2" MOTORIZED BHA TO TOP OF BHA @ 774 FT.- MONITORED WELL ON TRIP TANK. | 7109 | 1220 | RIG | 05/04/2022 | ADC-53L | DRLG | UTMN-4069
272 | 7109 |  | OTH | N |  | NA | FLOW CHECK @ BHA TOP- WELL STATIC. | 7109 |  | RIG | 05/04/2022 | ADC-53L | DRLG | UTMN-4069
273 | 7109 | 0 | TO | N |  | BHA | CONT'D POOH WITH 8-1/2" MOTORIZED BHA TO SURFACE.- MONITORED WELL ON TRIP TANK. | 7109 | 774 | RIG | 05/04/2022 | ADC-53L | DRLG | UTMN-4069
274 | 7109 |  | HT | N |  | BHA | HPJSM, L/D 8-1/2" MOTORIZED BHA, L/D MWD & PDC BIT.- DULL BIT GRADING: 0 - 1 - CT - G - X- I - NO - TD- MONITORED WELL ON TRIP TANK. | 7109 |  | RIG | 05/04/2022 | ADC-53L | DRLG | UTMN-4069
275 | 7109 |  | OTH | E | 2584 | NA | HELD PRE JOB SAFETY MEETING PRIOR TO R/U SLB LOGGING TOOL, DISCUSS THE HAZARD AND RISKS RELATED TO R/U & RUN WL TOOL WITH ALL INVOLVED CREW. | 7109 |  | SWL | 05/04/2022 | ADC-53L | LOG | UTMN-4069
276 | 7109 |  | OTH | E | 2584 | NA | SLB WL PU AND MU WL TOOL STRING RUN #1 (AIT-M/HDRS-H/HGNS-B/EDTC). LOAD RADIO ACTIVE SOURCE.- MONITORED WELL ON TRIP TANK. | 7109 |  | SWL | 05/04/2022 | ADC-53L | LOG | UTMN-4069
277 | 7109 |  | OTH | E | 2584 | NA | RIH SLB WL RUN #1 (AIT-M/HDRS-H/HGNS-B/EDTC) TO BTM @ 7,109 FT.- MONITOR THE WELL WITH TRIP TANK. | 7109 |  | SWL | 05/04/2022 | ADC-53L | LOG | UTMN-4069
278 | 7109 | 4620 | LOG | E | 2584 | WLT | SLB WL LOGGING UP RUN #1 ( AIT-M/HDRS-H/HGNS-B/EDTC ) FROM 7109 FT TO 9-5/8" CSG POINT @ 4,620 FT. - MONITOR THE WELL WITH TRIP TANK. | 7109 | 7109 | SWL | 05/04/2022 | ADC-53L | LOG | UTMN-4069
279 | 7109 | 6600 | LOG | E | 2584 | WLT | SLB WL RIH W/ RUN#1 TO 6,900 FT & RECORD REPEAT PASS LOGGING FROM 6,900 FT TO 6,600 FT. - POOH WL TOOLS TO 9-5/8" CSG SHOE @ 4620 FT.- MONITOR THE WELL WITH TRIP TANK. | 7109 | 6900 | SWL | 05/04/2022 | ADC-53L | LOG | UTMN-4069
280 | 7109 | 0 | LOG | E | 2584 | WLT | SLB WL LOGGING UP (CNL-GR) FROM 9-5/8" CSG POINT @ 4,620 FT TO SURFACE.- MONITOR THE WELL WITH TRIP TANK. | 7109 | 4620 | SWL | 05/04/2022 | ADC-53L | LOG | UTMN-4069
281 | 7109 |  | OTH | E | 2584 | NA | HPJSM, L/D SLB WL RUN #1 ASSY. & RELATED EQUIPMENT. UNLOADED WL R/A SOURCE.- MONITOR THE WELL WITH TRIP TANK. | 7109 |  | RIG | 05/04/2022 | ADC-53L | LOG | UTMN-4069
282 | 7109 |  | OTH | E | 2584 | NA | HPJSM, SLB WL PU AND MU WL TOOL STRING RUN #2 (XPT - EDTC). - MONITORED WELL ON TRIP TANK. | 7109 |  | SWL | 05/04/2022 | ADC-53L | LOG | UTMN-4069
283 | 7109 |  | OTH | E | 2584 | NA | RIH SLB WL RUN #2 (XPT - EDTC) TO 1ST POINT @ 4,764 FT (SULY FM). PERFORMED CORRELATION & STICKY TEST.- MONITOR THE WELL WITH TRIP TANK.** TIME SINCE LAST CIRCULATION = 26.25 HOURS. | 7109 |  | SWL | 05/04/2022 | ADC-53L | LOG | UTMN-4069
284 | 17 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 17 | 2584 | 04 May 0100 | 05/04/2022 | ADC-53L | Type | UTMN-4069
285
286
287 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | ADC-56L | Hrs | UTMN-2330
288 | PCPF | TK3 | 6.75 | 04 May 2215 - 0500 | 14193 | 896245 | RIH WITH LOGGING TOOLS TO 13,412 FT. UNABLE TO PASS OBSTRUCTION. | BHS | NA |  | 05/04/2022 | ADC-56L | 6.75 | UTMN-2330
289 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | ADC-57L | Hrs | FDHL-158
290 | WSHO | TK3 | 145.25 | 27 Apr 2230 - 2130 | 13135 | 896041 | DRILL OUT 7" LNR SHOE TRACK 20 FT ABOVE FLOAT SHOE. P/T 7" CSG LNR TO 650 PSI PRESSURE DROP NOT HOLDING | CMT | CSG |  | 05/04/2022 | ADC-57L | 16.5 | FDHL-158
291 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | ADM-262 | Hrs | MRJN-123
292 | FOT | BHI | 19.5 | 03 May 0100 - 0500 | 9013 | 896186 | LOST RESPONSE FROM BAKER RESISTIVITY SENSOR IN AZI-TRACK. TROUBLESHOOT SAME WITH NO SUCCESS. | BHA | LWD |  | 05/04/2022 | ADM-262 | 15.5 | MRJN-123
293 | FOT | RIG | 2.25 | 04 May 0230 - 0445 | 0 | 896190 | EZY-TORQUE CATHEAD HYDRAULICS UNIT MALFUNCTION. | RR | HSYS |  | 05/04/2022 | AOD-11 | 2.25 | SFNY-4280
294 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | AOD-11 | Hrs | SFNY-4280
295 | FOT | RIG | 3 | 04 May 1615 - 1915 | 150 | 896188 | UNABLE TO FUNCTION TDS HAVE FAULT ON TDS CONTROL MODULE IN DERRICK. | RR | TDS |  | 05/04/2022 | AOD-11 | 3 | SFNY-4280
296 | FOT | RIG | 2.25 | 04 May 0230 - 0445 | 0 | 896190 | EZY-TORQUE CATHEAD HYDRAULICS UNIT MALFUNCTION. | RR | HSYS |  | 05/04/2022 | AOD-11 | 2.25 | SFNY-4280
297 | STBH | ARM | 10 | 04 May 1900 - 0500 | 13938 | 896247 | SIDETRACK WELL DUE TO STUCK OF 5-7/8" ROT DRLG BHA. | STUK | BHA | 895547 | 05/04/2022 | DPS-4 | 10 | MDRK-54
298 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | DPS-4 | Hrs | MDRK-54
299 | STBH | ARM | 260.25 | 15 Apr 1900 - 1230 | 16058 | 895547 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. | STUK | BHA | 895515 | 05/04/2022 | DPS-4 | 6.5 | MDRK-54
300 | STBH | ARM | 10 | 04 May 1900 - 0500 | 13938 | 896247 | SIDETRACK WELL DUE TO STUCK OF 5-7/8" ROT DRLG BHA. | STUK | BHA | 895547 | 05/04/2022 | DPS-4 | 10 | MDRK-54
301 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | DPS-74 | Hrs | NJYN-54
302 | FOT | BLH | 504.75 | 13 Apr 0730 - 0100 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/04/2022 | DPS-74 | 20 | NJYN-54
303 | 7550 | 7297 | LOG | E | 2564 | WLT | CONT. PERFORM BHI LOGGING TOOLS RUN # 3 (RCX ON GR) 3RD CYCLE & COLLECTED 1ST SAMPLE AT 7297' (1 OF 12 FM SAMPLES).- SAMPLE #1 @ 7,297' (LFDR): TOTAL DUMPING IN ANN. = 1.55 BBL / WATER IN 3 CYCLES & COLLECTED SAMPLE.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 7297 | BAW | 05/04/2022 | DQ-47 | LOG | KHRS-1416
304 | 7550 | 7312 | LOG | E | 2564 | WLT | POSITION BHI LOGGING TOOLS RUN # 3 (RCX ON GR), INFLATE STRADDLE PKR & COLLECTED 2ND SAMPLE AT 7312' (2 OF 12 FM SAMPLES).- SAMPLE #2 @ 7,312' (LFDR): TOTAL DUMPING IN ANN. = 1.16 BBL / WATER IN 2 CYCLES & COLLECTED SAMPLE.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK.- RDD CANCELLED TWO REMAINING SAMPLE POINTS IN LFDR AT 7324' & 7355'. | 7550 | 7312 | BAW | 05/04/2022 | DQ-47 | LOG | KHRS-1416
305 | 7550 |  | CIRC | E | 2564 | MPMP | CIRC. 1.5 BOTTOM /UP W/ 175 GPM, 310 PSI & CONDITION MUD WT = 69 PCF IN/OUT & 100 % RETURN. | 7550 |  | RIG | 05/04/2022 | DQ-47 | LOG | KHRS-1416
306 | 7550 |  | WCNT | E | 2564 | NA | FLOW CHECK, WELL STATIC. | 7550 |  | RIG | 05/04/2022 | DQ-47 | LOG | KHRS-1416
307 | 7550 | 5650 | ST | E | 2564 | STDP | POOH W/ CONTROLED SPEED W/ BHI LOGGING TOOLS RUN#3 (RCX-GR) F/ 7312' T/ 5650'. | 7550 | 7312 | RIG | 05/04/2022 | DQ-47 | LOG | KHRS-1416
308 | 7550 | 5650 | LOG | E | 2564 | WLT | PERFORM STICKY TEST @ 5650' FOR ONE HR - OK, NO OVERPULL OBSERVED. | 7550 | 5650 | BAW | 05/04/2022 | DQ-47 | LOG | KHRS-1416
309 | 7550 | 5651 | LOG | E | 2564 | WLT | POSITION STRING, ACTIVATE MAGNA PROBE & COLLECT 2ND SAMPLE AT 5651' (3 OF 10 FM SAMPLES) 2ND CYCLE - ONGOING.- ATTEMPTED TO PUMP OUT WITH MAGNA PROBE @ 5,650', ABORTED DUE TO LOW MOBILITY.- SAMPLE #3 @ 5,651' (ABD1): TOTAL DUMPING IN ANN. = 1.25 BBL / WATER & OIL & ONGOING.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5651 | BAW | 05/04/2022 | DQ-47 | LOG | KHRS-1416
310 | 117.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | BAKER W/L LOG FOR 8 1/2" PILOT HOLE. | 24 | 2564 | 30 Apr 0730 | 05/04/2022 | DQ-47 | Type | KHRS-1416
311
312
313 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | NBR-591S | Hrs | HRDH-1921
314 | FOT | RIG | 1 | 04 May 0745 - 0845 | 10430 | 896222 | OBSERVE LEAK ON MP#3 SWAB. | RR | MPMP |  | 05/04/2022 | NBR-591S | 1 | HRDH-1921
315 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | PA-622S | Hrs | AFLJ-4
316 | PSSW | ARM | 228 | 24 Apr 1000 - 0500 | 6896 | 895875 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION. | STUK | NA |  | 05/04/2022 | PA-622S | 24 | AFLJ-4
317 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | PA-866S | Hrs | SHHB-2
318 | FPMP | RIG | 4 | 04 May 1300 - 1700 | 4523 | 896200 | OBSERVED LEAK ON STAND PIPE | RR | MPMP |  | 05/04/2022 | PA-866S | 4 | SHHB-2
319 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | SCTD-1 | Hrs | SDGM-1240
320 | FOT | RIG | 7 | 04 May 2200 - 0500 | 15435 | 896224 | LOSS OF TELMETRY FROM DOWNHOLE TOOLS | DSF | STRG |  | 05/04/2022 | SCTD-1 | 7 | SDGM-1240
321 | 17315 |  | STIM | E | 2545 | CTU | PERFORM L-2 ACID MATRIX STIMULATION WITH BHI CT AS PER PROGRAM WHILE POOH FROM 11,650 FT TO AT 9,667 FT.- TOTAL VOLUME PUMPED ( 15% HCL: 1821 BBLS; 15% EMULSIFIED ACID: 546 BBLS).- PUMP RATE: 2.5-2.9 BPM.- CTU PUMPING PRESS: 3500-4300 PSI.- CTU SPEED: 2-12 FT/MIN.- WHP : 500-10 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/04/2022 | SIN30L | STIM | KHRS-1409
322 | 17315 |  | STIM | E | 2545 | CTU | RIH W/ 2-3/8" CT F/ 9,667 FT T/ TO TD @ 17315 FT.(L-2 TD) WHILE PUMPING POST FLUSH.- PUMP RATE: 2-2.9 BPM.- CTU PUMPING PRESS: 3200-3600 PSI.- CTU SPEED: 20-25 FT/MIN.- WHP :0-20 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/04/2022 | SIN30L | STIM | KHRS-1409
323 | 17315 |  | STIM | E | 2545 | CTU | POOH W/ 2-3/8" CT F/ 17,315 FT T/ TO L-2 TOW@ 9,669 FT. WHILE PUMPING POST FLUSH.- PUMP RATE:2 BPM.- CTU PUMPING PRESS: 1900-3300 PSI.- CTU SPEED: 20-30 FT/MIN.- WHP : 0-20 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/04/2022 | SIN30L | STIM | KHRS-1409
324 | 17315 |  | STIM | E | 2545 | CTU | LINE UP AND BULLHEAD 1.2X CSG CAPACITY W/ 66 PCF VISCOUS BRINE THROUGHT CT KILL LINE AT TOW 9667'.- WHP : 0-15 PSI. | 17315 |  | BCT | 05/04/2022 | SIN30L | STIM | KHRS-1409
325 | 17315 |  | STIM | E | 2545 | CTU | EXTENDED FLOW CHECK, TOTAL LOSSES. | 17315 |  | BCT | 05/04/2022 | SIN30L | STIM | KHRS-1409
326 | 17315 |  | STIM | E | 2545 | CTU | POOH W/ 2-3/8" CT F/ L-2 TOW@ 9,667' TO 500' WHILE PUMPING 66 PCF VISCOUS BEINE AT MINIMUM RATE 0.25 BPM.- KEEP PUMPING 2-3 BPM OF 66 PCF VISCUS BRINE FROM THE BACK SIDE. | 17315 |  | BCT | 05/04/2022 | SIN30L | STIM | KHRS-1409
327 | 83 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 24 | 2545 | 01 May 1800 | 05/04/2022 | SIN30L | Type | KHRS-1409
328
329
330 | FOT | RIG | 8.25 | 04 May 0545 - 1400 | 10600 | 896225 | TROUBLESHOOTING VFD COMMUTATORS | RR | PSYS |  | 05/04/2022 | SINO-12L | 8.25 | HRDH-1454
331 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | SINO-12L | Hrs | HRDH-1454
332 | STBG | TK1 | 13 | 04 May 1600 - 0500 | 10600 | 896189 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION. | STUK | TBG |  | 05/04/2022 | SINO-12L | 13 | HRDH-1454
333 | FOT | RIG | 8.25 | 04 May 0545 - 1400 | 10600 | 896225 | TROUBLESHOOTING VFD COMMUTATORS | RR | PSYS |  | 05/04/2022 | SINO-12L | 8.25 | HRDH-1454
334 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | SINO-47 | Hrs | HRDH-1957
335 | FOT | SPS | 24 | 04 May 0500 - 0500 | 14005 | 896223 | RSS TOOL LOST COMMUNICATION WITH MWD TOOL. | BHA | RSS |  | 05/04/2022 | SINO-47 | 24 | HRDH-1957
336 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | SND-1501 | Hrs | UTMN-567
337 | FOT | BC | 188.25 | 26 Apr 1115 - 1000 | 0 | 895984 | AFTER DISPLACED WELL TO DIESEL OBERVED WELL NOT STATIC W/ STEADY RETURNS | TF | PKR |  | 05/04/2022 | SND-1501 | 5 | UTMN-567
338 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | SND-2008 | Hrs | HRDH-1052
339 | FOT | SWL | 12.5 | 03 May 0300 - 1530 | 11368 | 896221 | TRIED TO SET HALL 3.68" BP WITH SLB SETTING TOOL SEVERAL TIMES WITHOUT SUCCESS | TF | WLT |  | 05/04/2022 | SND-2008 | 10.5 | HRDH-1052
340 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | SP-160 | Hrs | HWTH-72
341 | FWTS | RIG | 59.75 | 02 May 1145 - 0500 | 8444 | 896181 | WHILE BACK REAM, STRING STALLED, LOST ROTATION AND CIRCULATION. ATTEMPT TO GET ROTATION WHILE JARING DOWN SUCCESSFULLY. REESTABLISH CIRCULATION GRADUALLY TO 90 GPM , DISPLACE HOLE TO 75 PCF OBM. KEEP STRING IN ROTATION. POOH, FOUND SHEARED OFF PIN BETWEEN THE TWO LAST 4" HWDP ABOVE DOG LEG REAMER. | FISH | BHA |  | 05/04/2022 | SP-160 | 18.5 | HWTH-72
342 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | SSA-201 | Hrs | HRDH-1818
343 | HINW | ARM | 411.5 | 17 Apr 1500 - 0500 | 14502 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/04/2022 | SSA-201 | 24 | HRDH-1818
344 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | SSA-5891 | Hrs | HRDH-2016
345 | XTTE | WCR | 1 | 04 May 0815 - 0915 | 15244 | 896244 | WFD 4-1/2" TBG SLIPS NOT HOLDING TBG. | TF | TTRQ |  | 05/04/2022 | SSA-5891 | 1 | HRDH-2016
346 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/04/2022 | STY-038 | Hrs | ZULF-2083
347 | FOT | HCO | 74.5 | 30 Apr 0300 - 1900 | 5497 | 896011 | HALLIBURTON UNSUCCESSFULLY ATTEMPT TO LATCH INTO VHR PKR WITH RATCH-LATCH TOOL | TF | SEAL |  | 05/04/2022 | STY-038 | 14 | ZULF-2083
348 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | ADC-17 | Hrs | ZULF-1212
349 | FOT | HCM | 2.75 | 05 May 1945 - 2230 | 6983 | 896194 | WHILE MIXING CEMENT, HAD FAILURE ON CEMENTER MIXING PUMP, MALFUNCTION DUE TO BROKEN CLUTCH ON MIXING PUMP | TF | PUMP |  | 05/05/2022 | ADC-17 | 2.75 | ZULF-1212
350 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | ADC-21 | Hrs | MZLJ-155201
351 | PSSW | ARM | 69 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/05/2022 | ADC-21 | 24 | MZLJ-155201
352 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | ADC-31 | Hrs | SDGM-1181
353 | FOT | GOC | 7 | 05 May 1730 - 0030 | 4230 | 896255 | EXCESS TIME RUNNING CASING DUE TO LOW PRESSURE ON POWER UNIT. USED 3 UNITS DURING JOB. | TF | CTRQ |  | 05/05/2022 | ADC-31 | 7 | SDGM-1181
354 | 7109 | 6946 | LOG | E | 2584 | WLT | CONT'D SLB WL RECORDED TOTAL 27 PRESSURE POINTS AS PER RDD REQUEST. FROM 4,765 FT TO 6,964 FT.- RECORDED TOTAL 27 POINTS: 03 POINTS IN SULY, 01 IN HITH, 04 IN ABAR, 03 IN ABCR, 01 IN PADS, 01 IN ABD1, 03 IN AD2A, 11 IN ARAB-D.- MIN. OVERBALANCE RECORDED AT 6,524' = 221 PSI IN ARAB-C RESERVOIR.- MAX. OVERBALANCE RECORDED AT 6,946' = 937 PSI IN ARAB-D RESERVOIR.- CORRELATION AS REQUIRED PRIOR TAKING PRESSURE.- MONITOR WELL ON TRIP TANK. | 7109 | 4764 | SWL | 05/05/2022 | ADC-53L | LOG | UTMN-4069
355 | 7109 |  | OTH | E | 2584 | NA | SLB WL POOH WITH 2ND RUN (XPT-GR) TO SURFACE.- MONITOR THE WELL WITH TRIP TANK. | 7109 |  | SWL | 05/05/2022 | ADC-53L | LOG | UTMN-4069
356 | 7109 |  | OTH | E | 2584 | NA | HPJSM, L/D SLB WL RUN #2 ASSY. & SURFACE EQUIPMENT.- MONITOR THE WELL WITH TRIP TANK.** TIME SINCE LAST CIRCULATION = 41.25 HOURS. | 7109 |  | RIG | 05/05/2022 | ADC-53L | LOG | UTMN-4069
357 | 7109 |  | HT | E | 2584 | BHA | HPJSM, P/U & M/U 8-1/2" REAMING BHA AND RIH TO 1137 FT. SMITH XS616-C SN/ SM0536 W/ 6 X 13" NOZZLES.- MONITOR WELL ON TRIP TANK-FILL STRING AFTER BHA. | 7109 |  | RIG | 05/05/2022 | ADC-53L | CT | UTMN-4069
358 | 7109 | 4620 | TI | E | 2584 | STDP | CONTINUE RIH WITH 8-1/2" REAMING BHA IN CH FROM 1137' TO 9-5/8" CSG SHOE AT 4620 FT.- MONITOR WELL ON TRIP TANK-FILL STRING EVERY 20 STD. | 7109 | 1137 | RIG | 05/05/2022 | ADC-53L | CT | UTMN-4069
359 | 7109 | 6550 | TI | E | 2584 | STDP | CONTINUE RIH WITH 8-1/2" REAMING BHA IN OH FROM 4,620 TO 6,550 FT.- MONITOR WELL ON TRIP TANK | 7109 | 4620 | RIG | 05/05/2022 | ADC-53L | CT | UTMN-4069
360 | 7109 | 7109 | RW | E | 2584 | BIT | REAM DOWN SAMPLING INTERVAL WITH 8-1/2" REAMING BHA FROM 6,550 FT TO 7,109 FT.- FR 600 GPM, SPP 2700 PSI, 100 RPM , TQ 1.5-2.5 KFT.LBS | 7109 | 6550 | RIG | 05/05/2022 | ADC-53L | CT | UTMN-4069
361 | 7109 |  | CIRC | E | 2584 | MPMP | SWEPT HOLE WITH 50 BBLS HI-VIS & CIRCULATE TILL SHAKERS CLEAN... INCT @ RT.- FR: 600 GPM, SPP: 2700 PSI. | 7109 |  | RIG | 05/05/2022 | ADC-53L | CT | UTMN-4069
362 | 41 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/05/2022 | ADC-53L | Type | UTMN-4069
363
364
365 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | ADC-56L | Hrs | UTMN-2330
366 | PCPF | TK3 | 11.25 | 04 May 2215 - 0930 | 14193 | 896245 | RIH WITH LOGGING TOOLS TO 13,412 FT. UNABLE TO PASS OBSTRUCTION. | BHS | NA |  | 05/05/2022 | ADC-56L | 4.5 | UTMN-2330
367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | ADC-62L | Hrs | ANDR-745
368 | FOT | BHI | 3.25 | 05 May 0045 - 0500 | 5512 | 896254 | BHI MAGTRAK TOOL STOP WORKING @ 5,512 FT WHILE DRILLING. | BHA | LWD |  | 05/05/2022 | ADC-62L | 3.25 | ANDR-745
369 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | ADM-262 | Hrs | MRJN-123
370 | FOT | BHI | 27 | 03 May 0100 - 1230 | 9013 | 896186 | LOST RESPONSE FROM BAKER RESISTIVITY SENSOR IN AZI-TRACK. TROUBLESHOOT SAME WITH NO SUCCESS. | BHA | LWD |  | 05/05/2022 | ADM-262 | 7.5 | MRJN-123
371 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | ARO-3001 | Hrs | ZULF-2058
372 | HERR | RIG | 2.75 | 05 May 0045 - 0330 | 0 | 896195 | EXCESS TIME N/D BOP | JF | BOP |  | 05/05/2022 | ARO-3001 | 2.75 | ZULF-2058
373 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | DPS-4 | Hrs | MDRK-54
374 | STBH | ARM | 33.5 | 04 May 1900 - 0500 | 13938 | 896247 | SIDETRACK WELL DUE TO STUCK OF 5-7/8" ROT DRLG BHA. | STUK | BHA | 895547 | 05/05/2022 | DPS-4 | 23.5 | MDRK-54
375 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | DPS-74 | Hrs | NJYN-54
376 | FOT | BLH | 521.75 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/05/2022 | DPS-74 | 17 | NJYN-54
377 | 7550 | 5651 | LOG | E | 2564 | WLT | CONT. BHI LOGGING TOOLS RUN # 3 (RCX ON GR) & COLLECT SAMPLE #3 @ 5651' (3 OF 9 FM SAMPLES) .- COLLECT ONE BOTTLE OF OIL SAMPLE WITH STANDARD PROBE.- COLLECT ONE BOTTLE OF MIX (OIL & WATER) SAMPLE WITH STANDARD PROBE.- SAMPLE #3 @ 5,651' (ABD1): TOTAL DUMPING IN ANN. = 3.72 BBL / OIL & WATER - TOTAL 3 CYCLES.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5651 | BAW | 05/05/2022 | DQ-47 | LOG | KHRS-1416
378 | 7550 | 5673 | LOG | E | 2564 | WLT | POSITION STRING, INFLATE STRADDLE PKR & COLLECT SAMPLE # 4 @ 5675' (4 OF 9 FM SAMPLES).- ATTEMPTED TO PUMP OUT WITH MAGNA PROBE @ 5,673', ABORTED DUE TO LOW MOBILITY.- SAMPLE #4 @ 5,675' (ABD1): TOTAL DUMPING IN ANN. = 1.92 BBL / WATER - TOTAL 2 CYCLES.- COLLECTED ONE BOTTLE OF WATER SAMPLE WITH STRADDLE PKR.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5673 | BAW | 05/05/2022 | DQ-47 | LOG | KHRS-1416
379 | 7550 | 5705 | LOG | E | 2564 | WLT | POSITION STRING, ACTIVATE STANDARD PROBE & COLLECT SAMPLE # 5 @ 5705' (5 OF 9 FM SAMPLES) - 2ND CYCLE IN PROGRESS.- ATTEMPT TO COLECT SAMPLE @ 5704' WITH MAGNA PROBE, NO SEAL, MOVE STRING & SWITCH TO STRADDLE PKR.- MOVE STRING FREE AFTER 1ST CYCLE & SWITCH TO STANDARD PROBE AS PER RDD - ONGOING.- SAMPLE #5 @ 5,705' (ABD1): TOTAL DUMPING IN ANN. = 1.89 BBL / WATER - 2ND CYCLE - ONGOING.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5705 | BAW | 05/05/2022 | DQ-47 | LOG | KHRS-1416
380 | 141.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | BAKER W/L LOG FOR 8 1/2" PILOT HOLE. | 24 | 2564 | 30 Apr 0730 | 05/05/2022 | DQ-47 | Type | KHRS-1416
381
382
383 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | MP-1 | Hrs | MRJN-305
384 | FOT | RIG | 1 | 05 May 0600 - 0700 | 8720 | 896249 | WHILE DRILLING, OBSERVED REDUCTION IN ELECTRICAL POWER. POH 1 STD OF DP. CHC, INVESTIGATED, SINGLE POWER GENERATOR TRIPPED, BROUGHT BACK ONLINE. CONTINUED OPS. | RR | PSYS |  | 05/05/2022 | MP-1 | 1 | MRJN-305
385 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | NA-128S | Hrs | SAHB-28
386 | FOT | RIG | 1 | 05 May 0830 - 0930 | 8748 | 896191 | WHILE POOH W/ 9-5/8" SAMAA WBCO BHA HAD MALFUNCTION IN DRAWWOK BRAKE EQUILIZER BAR. | RR | DWKS |  | 05/05/2022 | NA-128S | 1 | SAHB-28
387 | FOT | ITS | 1.5 | 05 May 1130 - 1300 | 19250 | 896253 | TROUBLE SHOOT ITS POWER TONG NOT ABLE TO APPLY REQUIRED MAKE UP TORQUE & POWER UNIT. REPLACED BOTH. | TF | CTRQ |  | 05/05/2022 | NBR-16S | 1.5 | HMYM-433302
388 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | NBR-16S | Hrs | HMYM-433302
389 | XTTE | RIG | 2 | 05 May 0615 - 0815 | 19250 | 896252 | TROUBLESHOOTING TEST PUMP, ARRANGED SPEAR . | TF | BOP |  | 05/05/2022 | NBR-16S | 2 | HMYM-433302
390 | FOT | ITS | 1.5 | 05 May 1130 - 1300 | 19250 | 896253 | TROUBLE SHOOT ITS POWER TONG NOT ABLE TO APPLY REQUIRED MAKE UP TORQUE & POWER UNIT. REPLACED BOTH. | TF | CTRQ |  | 05/05/2022 | NBR-16S | 1.5 | HMYM-433302
391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | PA-622S | Hrs | AFLJ-4
392 | PSSW | ARM | 238.75 | 24 Apr 1000 - 1545 | 6896 | 895875 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION. | STUK | NA |  | 05/05/2022 | PA-622S | 10.75 | AFLJ-4
393 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | PA-861S | Hrs | HRDH-1060
394 | FOT | WI3 | 135 | 29 Apr 1700 - 2200 | 11784 | 896139 | WHILE RIH W/ REAMING BHA STRING GOT STUCK AT THE OPEN HOLE WHIPSTOCK | TF | WPSTK |  | 05/05/2022 | PA-861S | 17 | HRDH-1060
395 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SCTD-1 | Hrs | SDGM-1240
396 | FOT | RIG | 15 | 04 May 2200 - 1300 | 15435 | 896224 | LOSS OF TELMETRY FROM DOWNHOLE TOOLS | DSF | STRG |  | 05/05/2022 | SCTD-1 | 8 | SDGM-1240
397 | 17315 |  | STIM | E | 2545 | CTU | CONT. POOH W/2-3/8" CT TO SURFACE WHILE PUMPING 66 PCF VISCOUS BRINE AT MINIMUM RATE 0.25 BPM.-KEEP PUMPING 2-3 BPM OF 66 PCF VISCUS BRINE FROM THE BACK SIDE. | 17315 |  | BCT | 05/05/2022 | SIN30L | STIM | KHRS-1409
398 | 17315 |  | STIM | E | 2545 | CTU | HPJSM, DISCONNECT RISER, R/D BAKER CTU INJECTOR HEAD, RISER, QUAD BOP, HCR GATE VALVE AND ALL RELATED LINES.-DISPLACED CTU TO WATER.-L/D CTU BHA.-MONITOR WELL ON TRIP TANK. PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM . | 17315 |  | BCT | 05/05/2022 | SIN30L | STIM | KHRS-1409
399 | 17315 |  | STIM | E | 2545 | CTU | HPJSM, N/D CT RISER, ISO-GATE VALVE WITH 13-5/8,- 5 K X 4-1/16" -10K ADAPTOR FLANGE. - N/U BELL NIPPLE & FLOW LINE.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. | 17315 |  | BCT | 05/05/2022 | SIN30L | STIM | KHRS-1409
400 | 17315 |  | HT | N |  | FISHT | HPJSM. P/U & M/U WIS WPS RETRIEVAL HOOK & BKR MWD BHA T/ 550.RETRIEVING HOOK +1 JT X 5" DP + INTEQ FLOAT SUB + MWD + FILTER SUB +1 STD X 5" HWDP +3X9-5/8* MAGNETS 9-5/8" SCRAPER+ BRUSH+2 X 5/8" MAGNETS + JUNK BASKET+5" PJ+1 STDX HWDP+D/J+2X JT 5" HWDP+1 STD X 5" HWDP.-SCRIBE LINE HOOK JETTING NOZZLE WITH MWD HS.-SHALLOW TEST MWD @ 400 GPM & 1200 PSI.-MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. | 17315 |  | WI1 | 05/05/2022 | SIN30L | FISH | KHRS-1409
401 | 17315 | 2070 | TI | N |  | STDP | RIH W/ WIS WPS RETRIEVAL HOOK BHA F/ 550' T/ 2070'.-MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BAINE W/ 2-3 BPM. | 17315 | 550 | RIG | 05/05/2022 | SIN30L | FISH | KHRS-1409
402 | 17315 |  | RR | N |  | DWKS | HPJSM. SLIP DRILL LINE.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. | 17315 |  | RIG | 05/05/2022 | SIN30L | DRLG | KHRS-1409
403 | 17315 | 9660 | TI | N |  | STDP | RIH W/ WIS WPS RETRIEVAL HOOK BHA F/ 2070' T/ 9660'.- WORK SCRAPER ACROSS DV TOOL.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM.- SCRAP L-3 WHIPSTOCK SETTING DEPTH FROM 9,334' TO 9450' . | 17315 | 2070 | RIG | 05/05/2022 | SIN30L | FISH | KHRS-1409
404 | 17315 | 9681 | RTRV | N |  | WPSTK | ORIENTED HOOK NOZZLE TO 134 DEG & CLEAN HOOK SLOT BY WASHING ACROSS WPS FACE F/ 9660' T/ 9681' W/ 400 GPM @ 1100 PSI.- ORIENT NOZZLE TO 3O7 DEG , NO SUCCESS TO ENGAGE AND RELEASE WPS.- ORIENT NOZZLE TO 312 DEG , NO SUCCESS TO ENGAGE AND RELEASE WPS.- ORIENT NOZZLE TO 316 DEG, ENGAGED 9-5/8" WPS & RELEASED SAME W/ 90 KLBS OVER PULL OBSERVED A DROP IN MUD COLUM AND DRAG INCREASED BY+-5KLB.- CONDUCT TQ TEST AS PER WIS ENGINEER TO ENSURE HOOK ENGAGEMENT.- DYNAMIC LOSSES, +-180 BPH. | 17315 | 9660 | WI3 | 05/05/2022 | SIN30L | FISH | KHRS-1409
405 | 17315 |  | WCNT | N |  | NA | PICK UP 5' & FLOW CHECK MEANWHILE ALLOW PACKER ELEMENT TO RETRACT.-HPJSM PRIOR TO POOH W/ WPS-STATIC LOSSES +-130 BPH. | 17315 |  | RIG | 05/05/2022 | SIN30L | FISH | KHRS-1409
406 | 17315 | 9200 | TO | N |  | STDP | PUMP OUT W/ L-2 WPS RETRIVAL BHA @ CONTROLLED SPEED F/ 9681' T/9200'.(5 STD).- DYNAMIC LOSSES, +-200 BPH. | 17315 | 9681 | RIG | 05/05/2022 | SIN30L | FISH | KHRS-1409
407 | 17315 | 7800 | TO | N |  | STDP | POOH W/ L-2 WPS RETRIVAL BHA @ CONTROLLED SPEED F/9200' T/7800'.-PUMPING 66 PCF VISCOUS BRINE W/2-3 BPM FROM BACKSIDE. | 17315 | 9200 | RIG | 05/05/2022 | SIN30L | FISH | KHRS-1409
408 | 91 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 8 | 2545 | 01 May 1800 | 05/05/2022 | SIN30L | Type | KHRS-1409
409
410
411 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SINO-12L | Hrs | HRDH-1454
412 | STBG | TK1 | 37 | 04 May 1600 - 0500 | 10600 | 896189 | GOT STUCK WITH LOWER COMPLETION DRUING CONNECTION. | STUK | TBG |  | 05/05/2022 | SINO-12L | 24 | HRDH-1454
413 | 7455 | 7455 | ST | N |  | STDP | CONT. PERFORMED WIPER TRIP W/ 6 1/8" SPS MTR/LWD BHA TO 5315' (TOW) ON ELEVATOR, RIH BACK TO TD @ 7455'. HOLE IN GOOD CONDITION. | 7455 | 7455 | RIG | 05/05/2022 | SINO-19L | DRLG | UTMN-1587
414 | 7455 |  | CIRC | N |  | MPMP | SWEPT HOLE & CHC W/ 82 PCF MUD, SPOT 100 BBLS LUBRICANT PILL. FLOW CHECK - WELL STATIC. | 7455 |  | RIG | 05/05/2022 | SINO-19L | DRLG | UTMN-1587
415 | 7455 | 5315 | ST | N |  | STDP | HPJSM, POH W/ 6-1/8" SPS MTR/MWD ASSY. T/ 5315 FT (TOW).> FLOW CHECK AFTER 5 STDS - WELL STATIC> KEEP FILLING HOLE AND MONITOR - STATIC> OPEN HOLE IN GOOD CONDITION | 7455 | 7455 | RIG | 05/05/2022 | SINO-19L | DRLG | UTMN-1587
416 | 7455 |  | CIRC | N |  | MPMP | FLOW CHECK - WELL STATIC, PUMPED SLUG. | 7455 |  | RIG | 05/05/2022 | SINO-19L | DRLG | UTMN-1587
417 | 7455 | 150 | TO | N |  | STDP | HPJSM, POOH W/ 6-1/8" SPS MTR/MWD ASSY. TO BHA TOP.> KEEP FILLING HOLE AND MONITOR - STATIC. | 7455 | 5315 | RIG | 05/05/2022 | SINO-19L | DRLG | UTMN-1587
418 | 7455 |  | CIRC | N |  | MPMP | FLOW CHECK, WELL STATIC. | 7455 |  | RIG | 05/05/2022 | SINO-19L | DRLG | UTMN-1587
419 | 7455 |  | HT | N |  | BHA | HPJSM, POH & L/D 6-1/8" MTR/LWD BHA.- BIT DULL: 1-1-WT-A-X-I-NO-TD. | 7455 |  | SPS | 05/05/2022 | SINO-19L | DRLG | UTMN-1587
420 | 7455 |  | OTH | E | 2604 | NA | (OOS) HPJSM. P/U & M/U HES WIRELINE DIELECTRIC/MSFL LOGGING TOOLS STRING + XO FOR 4"DP.- FUNCTION TEST TOOLS, OK. | 7455 |  | HWP | 05/05/2022 | SINO-19L | LOG | UTMN-1587
421 | 7455 | 5090 | ST | E | 2604 | STDP | (OOS) RIH W/ HES DIELECTRIC/MSFL LOGGING TOOLS AT CONTROLLED SPEED ON 4" DP/HWDP TO 5090'.- DRIFTED 4" DP/HWDP WITH 2.25" SIZE WHILE RIH. - PASSED FREELY 7" TOL AT 2107'.- FILLED STRING EVERY 10 STANDS W/ 82 PCF MUD USING W/L CIRC SUB & SCREEN. | 7455 | 150 | RIG | 05/05/2022 | SINO-19L | LOG | UTMN-1587
422 | 7455 |  | OTH | E | 2604 | NA | (OOS) M/U HES WL SIDE ENTRY SUB & CIRC SUB WITH MUD SCREEN. - RIH WITH W/L CABLE 300 FT ABOVE TOOL-HEAD - LATCHED ON WET CONNECTOR. CHECKED SIGNAL, OK. | 7455 |  | HWP | 05/05/2022 | SINO-19L | LOG | UTMN-1587
423 | 7455 |  | OTH | E | 2604 | NA | (OOS) INSTALLED CABLE CLAMP & PERFORMED PULL TEST, OK. | 7455 |  | HWP | 05/05/2022 | SINO-19L | LOG | UTMN-1587
424 | 7455 | 7440 | ST | E | 2604 | STDP | (OOS) CON.T RIH W/ HES MSFL / DIELECTRIC LOGGING TOOLS ON DRIFTED 4" DPS F/ 5090 T/ 7440' (15' OFF BOTTOM).- FILL STRING EVERY 15 STANDS. | 7455 | 5090 | RIG | 05/05/2022 | SINO-19L | LOG | UTMN-1587
425 | 13 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | MSFL WITH DIELECTRIC PILOT HOLE LOGS. | 13 | 2604 | 05 May 0100 | 05/05/2022 | SINO-19L | Type | UTMN-1587
426
427
428 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SINO-47 | Hrs | HRDH-1957
429 | FOT | SPS | 27.25 | 04 May 0500 - 0815 | 14005 | 896223 | RSS TOOL LOST COMMUNICATION WITH MWD TOOL. | BHA | RSS |  | 05/05/2022 | SINO-47 | 3.25 | HRDH-1957
430 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SND-2001 | Hrs | UTMN-2329
431 | SCSG | ARM | 3 | 05 May 1500 - 1800 | 6196 | 896226 | CASING STUCK AFTER CONNECTION AT 9196' (BASE LOWER FADHILI). | STUK | CSG |  | 05/05/2022 | SND-2001 | 3 | UTMN-2329
432 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SND-2007 | Hrs | ADHN-370100
433 | FOT | MSD | 12.25 | 05 May 1645 - 0500 | 16029 | 896250 | UNABLE TO ACHEIVE OPTIMAL MAKE UP TORQUE DUE TO HYDRAULIC LEAK ON PRIMARY & BACK UP POWER PACKS. | TF | CTRQ |  | 05/05/2022 | SND-2007 | 12.25 | ADHN-370100
434 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SP-101 | Hrs | ABQQ-710
435 | FOT | WI1 | 204.5 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/05/2022 | SP-101 | 24 | ABQQ-710
436 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SP-160 | Hrs | HWTH-72
437 | FWTS | RIG | 83.75 | 02 May 1145 - 0500 | 8444 | 896181 | WHILE BACK REAM, STRING STALLED, LOST ROTATION AND CIRCULATION. ATTEMPT TO GET ROTATION WHILE JARING DOWN SUCCESSFULLY. REESTABLISH CIRCULATION GRADUALLY TO 90 GPM , DISPLACE HOLE TO 75 PCF OBM. KEEP STRING IN ROTATION. POOH, FOUND SHEARED OFF PIN BETWEEN THE TWO LAST 4" HWDP ABOVE DOG LEG REAMER. | FISH | BHA |  | 05/05/2022 | SP-160 | 24 | HWTH-72
438 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SP-259 | Hrs | HZEM-160402
439 | ETRQ | RIG | 116.75 | 30 Apr 0430 - 0115 | 6708 | 896166 | ROLLER REAMER PINS LOST IN HOLE | BHA | BHA |  | 05/05/2022 | SP-259 | 20.25 | HZEM-160402
440 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SP-260 | Hrs | HZEM-161012
441 | HERR | ARN | 4 | 05 May 1615 - 2015 | 18426 | 896251 | ARAMCO BPV TEAM UNABLE TO SET BPV DUE TO INCOMPETENT PERSONNEL. | WH | BPV |  | 05/05/2022 | SP-260 | 4 | HZEM-161012
442 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SSA-5820 | Hrs | SDGM-1215
443 | FOT | RIG | 2 | 05 May 1430 - 1630 | 11405 | 896201 | TDS LOST HYDRAULIC FUNCTIONS AND WAS LEAKING OIL. | RR | TDS |  | 05/05/2022 | SSA-5820 | 2 | SDGM-1215
444 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SSA-5891 | Hrs | HRDH-2016
445 | FOT | BLH | 27 | 04 May 0200 - 0500 | 15227 | 896202 | BAKER RUNNING TOOL FAILED TO RELEASE OFF PBR. | TF | HGRL |  | 05/05/2022 | SSA-5891 | 24 | HRDH-2016
446 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | SSA-5974 | Hrs | HRDH-1970
447 | CWEL | ARM | 323.5 | 22 Apr 0500 - 0500 | 14884 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/05/2022 | SSA-5974 | 24 | HRDH-1970
448 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/05/2022 | T901 | Hrs | JLMN-79
449 | STOP | ARM | 2.75 | 05 May 0745 - 1030 | 3540 | 896227 | SHUT DOWN OPERATION DUE TO STRONG WIND. | WO | NA |  | 05/05/2022 | T901 | 2.75 | JLMN-79
450 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | ADC-21 | Hrs | MZLJ-155201
451 | PSSW | ARM | 93 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/06/2022 | ADC-21 | 24 | MZLJ-155201
452 | 7109 |  | CIRC | E | 2584 | MPMP | CONTINUE CIRCULATED THREE COMPLETE CYCLES TILL SHAKERS CLEAN. FLOW CHECK - WELL STATIC- FR: 600 GPM, SPP: 2700 PSI. | 7109 |  | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
453 | 7109 | 6645 | ST | E | 2584 | STDP | HPJSM, WIPER TRIP POOH WITH 8 1/2" REAMING BHA FIRST 05 STDS TO 6,645 FT. OPEN HOLE IN GOOD CONDITION.- MONITORED WELL ON TRIP TANK. | 7109 | 7109 | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
454 | 7109 |  | OTH | E | 2584 | NA | FLOW CHECK - WELL STATIC. | 7109 |  | RIG | 05/06/2022 | ADC-53L | DRLG | UTMN-4069
455 | 7109 | 4620 | ST | E | 2584 | STDP | CONT'D WIPER TRIP POOH WITH 8-1/2" REAMING BHA FROM 6645 FT TO 9-5/8" SHOE @ 4620'.- MONITORED WELL ON TRIP TANK. | 7109 | 6645 | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
456 | 7109 | 7109 | ST | E | 2584 | STDP | HPJSM, RIH BACK 8-1/2" REAMING BHA TO BTM @ 7109 FT. PRECAUTIONARY WASH DOWN LAST STD.-OPEN HOLE IN GOOD CONDITION.- MONITORED WELL ON TRIP TANK & TRIP SHEET. | 7109 | 4620 | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
457 | 7109 |  | CIRC | E | 2584 | MPMP | SWEPT HOLE WITH 50 BBLS HI VIS PILL & CIRCULATED TWO COMPLETE CYCLES TILL SHAKERS CLEAN. FLOW CHECK - WELL STATIC.- FR: 600 GPM, SPP: 2800 PSI. | 7109 |  | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
458 | 7109 | 6645 | TO | E | 2584 | STDP | HPJSM, POOH WITH 8 1/2" REAMING BHA FOR LOGGING FIRST 05 STDS TO 6,645 FT.-OPEN HOLE IN GOOD CONDITION.- MONITORED WELL ON TRIP TANK. | 7109 | 7109 | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
459 | 7109 |  | OTH | E | 2584 | NA | FLOW CHECK - WELL STATIC. | 7109 |  | RIG | 05/06/2022 | ADC-53L | DRLG | UTMN-4069
460 | 7109 | 4620 | TO | E | 2584 | STDP | CONT'D POOH WITH 8 1/2" REAMING BHA FOR LOGGING FROM 6,645 FT TO 4620 FT-OPEN HOLE IN GOOD CONDITION.- MONITORED WELL ON TRIP TANK. | 7109 | 6645 | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
461 | 7109 |  | OTH | E | 2584 | NA | FLOW CHECK - WELL STATIC. | 7109 |  | RIG | 05/06/2022 | ADC-53L | DRLG | UTMN-4069
462 | 7109 | 1137 | TO | E | 2584 | STDP | CONT'D POOH WITH 8 1/2" REAMING BHA FOR LOGGING FROM 4620 FT TO BHA DEPTH @ 1137 FT- MONITORED WELL ON TRIP TANK. | 7109 | 4620 | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
463 | 7109 |  | OTH | E | 2584 | NA | FLOW CHECK @ BHA TOP- WELL STATIC. | 7109 |  | RIG | 05/06/2022 | ADC-53L | DRLG | UTMN-4069
464 | 7109 | 0 | TO | E | 2584 | BHA | CONT'D POOH WITH 8-1/2" REAMING BHA FOR LOGGING TO SURFACE.- MONITORED WELL ON TRIP TANK. | 7109 | 1137 | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
465 | 7109 |  | HT | E | 2584 | BHA | HPJSM, L/D 8-1/2" REAMING BHA & PDC BIT.- DULL BIT GRADING: 0 - 1 - CT - G - X- I - NO - LOG- MONITORED WELL ON TRIP TANK. | 7109 |  | RIG | 05/06/2022 | ADC-53L | CT | UTMN-4069
466 | 7109 |  | PJSM | E | 2584 | NA | HPJSM, BEFORE PICKING UP TLC BHA. DISCUSS THE PROCEDURE. REVIEW THE JSA & OPERATIONAL ASPECT OF THE JOB. | 7109 |  | RIG | 05/06/2022 | ADC-53L | LOG | UTMN-4069
467 | 7109 |  | OTH | E | 2584 | NA | P/U & M/U TLC LOGGING TOOLS 3RD RUN (MDT-GR) & RIH TO 157 FT. -CHECK TLC TOOLS ON SURFACE, OK.- TOOL LENGTH: 157.48 FT. MAX TOOL OD: 5.284 INCHES.- MONITOR WELL ON TRIP TANK. | 7109 |  | SWL | 05/06/2022 | ADC-53L | LOG | UTMN-4069
468 | 7109 | 4292 | TI | E | 2584 | STDP | RIH TLC 3RD RUN LOGGING TOOLS ON 4" DP F/ 157 FT TO LATCHING DEPTH @ 4292 FT W/ CONTROL SPEED. - FILL UP STRING & BREAK CIRC. EVERY 10 STANDS. DRIFT ALL STANDS RIH WITH 2.25" DRIFT.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- MONITOR WELL ON TRIP TANK - OK. | 7109 | 157 | RIG | 05/06/2022 | ADC-53L | LOG | UTMN-4069
469 | 7109 |  | CIRC | E | 2584 | MPMP | CIRC 1.5 STRING VOLUME W/ OBM. MEANWHILE HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW.-FR: 300 GPM & P.P.: 450 PSI. | 7109 |  | RIG | 05/06/2022 | ADC-53L | LOG | UTMN-4069
470 | 65 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/06/2022 | ADC-53L | Type | UTMN-4069
471
472
473 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | ADC-56L | Hrs | UTMN-2330
474 | PCPF | TK3 | 13.25 | 06 May 1215 - 0130 | 14193 | 896262 | WHILE RIH WITH TLC AT 12239 FT OBSERVED OBSTRUCTION. | BHS | NA |  | 05/06/2022 | ADC-56L | 13.25 | UTMN-2330
475 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | ADC-60 | Hrs | ABSF-218
476 | FOT | ALC | 2 | 06 May 0300 - 0500 | 718 | 896284 | BAKER ESP CREW CHECK THE CABLE INTIGRITY PRIOR TO QCI FEED MLE SHIELD CABLE THRU ESP PKR, FOUND THE CABLE LOST INTEGRITY. | TF | ESPL |  | 05/06/2022 | ADC-60 | 2 | ABSF-218
477 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | ADC-62L | Hrs | ANDR-745
478 | FOT | BHI | 20.5 | 05 May 0045 - 2115 | 5512 | 896254 | BHI MAGTRAK TOOL STOP WORKING @ 5,512 FT WHILE DRILLING. | BHA | LWD |  | 05/06/2022 | ADC-62L | 16.25 | ANDR-745
479 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | ADES-40 | Hrs | ANDR-469
480 | FOT | MSD | 1 | 06 May 0145 - 0245 | 0 | 896285 | AL-MASAOOD POWER TONG HYDRAULIC UNIT MALFUNCTION. | TF | CRT |  | 05/06/2022 | ADES-40 | 1 | ANDR-469
481 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | ARO-4001 | Hrs | MRJN-539
482 | FOT | RIG | 1.25 | 06 May 0015 - 0130 | 8140 | 896283 | DRAW WORKS WAS GIVING STOP ALARM, TROUBLESHOOT SAME, FOUND LOAD SENSOR LOST COMMUNICATION WITH LOAD CELL. RESET LOAD CELL, FUNCTION TEST DRAWWORK | RR | DWKS |  | 05/06/2022 | ARO-4001 | 1.25 | MRJN-539
483 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | DPS-4 | Hrs | MDRK-54
484 | STBH | ARM | 55.5 | 04 May 1900 - 0330 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. | STUK | BHA | 895547 | 05/06/2022 | DPS-4 | 22 | MDRK-54
485 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | DPS-74 | Hrs | NJYN-54
486 | FOT | RAC | 41 | 05 May 1030 - 0500 | 10695 | 896234 | POOH W/ SPEAR, AT SURFACE FOUND GRAPPLE MISSING. | TF | FISHT |  | 05/06/2022 | DPS-74 | 24 | NJYN-54
487 | 7550 | 5704 | LOG | E | 2564 | WLT | CONT. BHI LOGGING TOOLS RUN # 3 (RCX ON GR) & COLLECT SAMPLE #5 @ 5704' (5 OF 9 FM SAMPLES) - TOTAL 2 CYCLES.- ATTEMPT TO COLECT SAMPLE @ 5705' WITH MAGNA PROBE, NO SEAL, MOVE STRING & SWITCH TO STRADDLE PKR.- MOVE STRING FREE AFTER 1ST CYCLE & SWITCH TO STANDARD PROBE AS PER RDD.- SAMPLE #5 @ 5,704' (ABD1): TOTAL DUMPING IN ANN. = 2.78 BBL / WATER - IN 2 CYCLES.- COLLECTED ONE BOTTLE OF WATER SAMPLE WITH STANDARD PROBE.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5704 | BAW | 05/06/2022 | DQ-47 | LOG | KHRS-1416
488 | 7550 |  | CIRC | E | 2564 | MPMP | RIH TO 6012', CIRC. 1.2 BOTTOM /UP AT 170 GPM, 250 PSI W/ 100% RETURN & CONDITION MUD WT = 69 PCF IN/OUT. | 7550 |  | RIG | 05/06/2022 | DQ-47 | LOG | KHRS-1416
489 | 7550 |  | WCNT | E | 2564 | NA | FLOW CHECK, WELL STATIC. | 7550 |  | RIG | 05/06/2022 | DQ-47 | LOG | KHRS-1416
490 | 7550 | 5732 | LOG | E | 2564 | WLT | CONT. BKR RUN # 3 (RCX-GR) POSITION STRING , ACTIVATE MAGNA PROBE AND COLLECTED SAMPLE #6 AT 5732' (6 OF 9 FM SAMPLES).- SAMPLE #6 @ 5,732' (ABD1): TOTAL DUMPING IN ANN. = 1.57 BBL / WATER - IN 1 CYCLE.- NO SAMPLES COLLECTED AT THIS POINT.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5732 | BAW | 05/06/2022 | DQ-47 | LOG | KHRS-1416
491 | 7550 | 5749 | LOG | E | 2564 | WLT | POSITION STRING , ACTIVATE STRADDLE PKR AND COLLECTED SAMPLE #7 AT 5749' (7 OF 9 FM SAMPLES).- SAMPLE #7 @ 5,749' (ABD2): TOTAL DUMPING IN ANN. = 2.28 BBL / WATER - IN 2 CYCLES.- COLLECTED ONE BOTTLE OF WATER SAMPLE WITH STRADDLE PKR.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5749 | BAW | 05/06/2022 | DQ-47 | LOG | KHRS-1416
492 | 7550 | 5774 | LOG | E | 2564 | WLT | POSITION STRING , ACTIVATE MAGNA PROBE AND COLLECT SAMPLE #8 AT 5774' (8 OF 9 FM SAMPLES) - ON GOING.- MOVE STRG. FREE, SCAN W/ MAGNA PROBE FOR GOOD MOBILITY POINT (AS PER ARAMCO RDD) AT 5,775', 5,776', 5,774'.- SAMPLE #8 @ 5,774' (ABD2): TOTAL DUMPING IN ANN. = 0.88 BBL / WATER - IN 1ST CYCLE -ONGOING.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5774 | BAW | 05/06/2022 | DQ-47 | LOG | KHRS-1416
493 | 165.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | BAKER W/L LOG FOR 8 1/2" PILOT HOLE. | 24 | 2564 | 30 Apr 0730 | 05/06/2022 | DQ-47 | Type | KHRS-1416
494
495
496 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | JACK-202 | Hrs | HMYM-844
497 | FOT | RIG | 12.5 | 06 May 1630 - 0500 | 1772 | 896281 | WHILE PULLING OUT DRILL STRING TO CHANGE BHA DUE TO TOTAL LOSS. DRILLING LINE SLIPPED OUT OF DRAWWORKS CLAMB AND TRAVELLING BLOC FALL DOWN ON RIG FLOOR. | RR | DWKS |  | 05/06/2022 | JACK-202 | 12.5 | HMYM-844
498 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | MP-4 | Hrs | LWHH-45
499 | FOT | SDM | 5 | 06 May 0000 - 0500 | 8100 | 896282 | LOST SIGNAL FROM MWD WHILE DRILLING AT 8100', TROUBLESHOOTING MWD TOOL, NO SUCCESS. | BHA | MWD |  | 05/06/2022 | MP-4 | 5 | LWHH-45
500 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | PA-622S | Hrs | AFLJ-4
501 | PSSW | ARM | 253.25 | 24 Apr 1000 - 0645 | 6860 | 895875 | WHILE PUMPING-OUT OF HOLE PRIOR TO POOH TO CHANGE BIT OBSERVED PRESSURE SUDDENLY INCREASED TO 4,000 PSI. STOP PUMP AND TRIED TO RUN BACK TO BOTTOM UNSUCCESSFULLY: STRING GOT STUCK @ 6,896' MD (5,395.0' TVD, ABOUT 30' OFF BOTTOM), WITH NO AVAILABLE ROTATION OR CIRCULATION. | STUK | NA |  | 05/06/2022 | PA-622S | 1.75 | AFLJ-4
502 | FOT | RIG | 9.5 | 06 May 1200 - 2130 | 6166 | 896258 | OBSERVED LEAK ON STAND PIPE | RR | CSYS |  | 05/06/2022 | PA-866S | 9.5 | SHHB-2
503 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | PA-866S | Hrs | SHHB-2
504 | FOT | RIG | 2.5 | 06 May 0230 - 0500 | 6326 | 896235 | OBSERVED LEAK ON SECONDARY STANDPIPE. | RR | CSYS |  | 05/06/2022 | PA-866S | 2.5 | SHHB-2
505 | FOT | RIG | 9.5 | 06 May 1200 - 2130 | 6166 | 896258 | OBSERVED LEAK ON STAND PIPE | RR | CSYS |  | 05/06/2022 | PA-866S | 9.5 | SHHB-2
506 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | PN-9 | Hrs | MRJN-91
507 | FOT | RIG | 1.5 | 06 May 1900 - 2030 | 5605 | 896264 | OBSERVED LEAK IN THE TOP DRIVE WASHPIPE. | RR | TDS |  | 05/06/2022 | PN-9 | 1.5 | MRJN-91
508 | 17315 | 500 | TO | N |  | STDP | POOH W/ L-2 WPS RETRIVAL BHA @ CONTROLLED SPEED F/7800' T/500'.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/2-3 BPM FROM BACKSIDE. | 17315 | 7800 | RIG | 05/06/2022 | SIN30L | FISH | KHRS-1409
509 | 17315 |  | CIRC | N |  | MPMP | FLOW CHECK, 120 BPH STATIC LOSSES. | 17315 |  | RIG | 05/06/2022 | SIN30L | FISH | KHRS-1409
510 | 17315 | 0 | RTRV | N |  | WPSTK | POOH TO SURFACE, L/D WIS WSTK (100% RECOVERY) & L/D C/O TOOL, RETRIEVAL HOOK & MWD.- COLLECT 4 KG FINE DEBRIS F/ STRING MAGNETS. | 17315 | 500 | WI3 | 05/06/2022 | SIN30L | FISH | KHRS-1409
511 | 17315 |  | STIM | E | 2545 | CTU | HPJSM. N/D BELL NIPPLE & FLOW LINE.-MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/2-3 BPM. | 17315 |  | BCT | 05/06/2022 | SIN30L | STIM | KHRS-1409
512 | 17315 |  | STIM | E | 2545 | CTU | HPJSM WITH ALL RIG CREW & ALL PERSONNEL INVOLVED W/ BKR CT R/U .- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/2-3 BPM. | 17315 |  | BCT | 05/06/2022 | SIN30L | STIM | KHRS-1409
513 | 17315 |  | STIM | E | 2545 | CTU | HPJSM. SPOT 130T CRANE, R/U & CONNECT RISER, X/O'S, FLANGES & GATE VALVE TO RIG BOP.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/2-3 BPM. | 17315 |  | BCT | 05/06/2022 | SIN30L | STIM | KHRS-1409
514 | 17315 |  | STIM | E | 2545 | CTU | HPJSM, R/U CT QUAD BOP ON TOP OF RISER, CONNECT CONTROL HOSES & HI PRESSURE LINES TO CT BOP.- FUNCTION TEST CT BOP RAMS, OK.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/2-3 BPM. | 17315 |  | BCT | 05/06/2022 | SIN30L | STIM | KHRS-1409
515 | 17315 |  | STIM | E | 2545 | CTU | LIFT CT INJECTOR HEAD & MADE UP TWO RISERS & P/U SAME TO RIG FLOOR.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/2-3 BPM. | 17315 |  | BCT | 05/06/2022 | SIN30L | STIM | KHRS-1409
516 | 17315 |  | STIM | E | 2545 | CTU | M/U BHA AS PER BKR CT AND FUNCTION TEST SAME.W/OUT NOV AGITATOR 1 BPM= 420 PSI, 1.5 BPM=670 PSI, 2 BPM=14OO PSI, 2.BPM=1950 PSI, 3 BPM=2150 PSI. W/ NOV AGITATOR 1 BPM= 550 PSI, 1.5 BPM=1,000 PSI, 2 BPM=1,625 PSI, 2.BPM= 2,375 PSI, 3 BPM=3,300 PSI.-CONNECTED CTU INJECTOR TO CTU QUAD BOP.-P/T STRIPPER AGAINST CTU STACK TO 300/2500 PSI, OK-INFLOW TEST DFCV TO 1500 PSI FOR 10 MINS, OK. BLEED OFF PRESSURE.-P/T RIG BOP SR AGAINST CT GATE VALVE TO 300/1500 PSI, OK.-MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. | 17315 |  | BCT | 05/06/2022 | SIN30L | STIM | KHRS-1409
517 | 17315 |  | STIM | E | 2545 | CTU | RIH W/ BHI 2-3/8" CT AS PER BHI STANDARD PROCEDURES TO 6820'.-CT RIH SPEED 30-40 FT/MIN.-PUMP 66 PCF BRINE @ 0.5 BPM.-START PUMPING 140 BBLS EASY REACH @4000', TO BE DISPLACED AT 7000'.-PERFORM PULL TEST EVERY 1OOO'-15OO'.-MONITOR WELL THROUGH TRIP TANK. | 17315 |  | BCT | 05/06/2022 | SIN30L | STIM | KHRS-1409
518 | 104.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 13.25 | 2545 | 01 May 1800 | 05/06/2022 | SIN30L | Type | KHRS-1409
519
520
521 | 7455 | 6440 | LOG | E | 2604 | WLT | (OOS) HES ACTIVATED TOOLS & LOGGED UP MAIN PASS WITH MSFL / DIELECTRIC OH LOGGING TOOLS ON 4" DP F/ 7440' T/ 6440'. | 7455 | 7440 | HWP | 05/06/2022 | SINO-19L | LOG | UTMN-1587
522 | 7455 | 6800 | LOG | E | 2604 | WLT | (OOS) HES RIH BACK TO 7000' & ACTIVATED TOOLS & LOGGED UP REPEAT PASS WITH MSFL / DIELECTRIC OH LOGGING TOOLS ON 4" DP F/ 7000' T/ 6800'. | 7455 | 7000 | HWP | 05/06/2022 | SINO-19L | LOG | UTMN-1587
523 | 7455 | 5090 | ST | E | 2604 | STDP | (OOS) POOH HES MSFL / DIELECTRIC LOGGING TOOLS ON 4" DP F/ 6800' T/ 5090'.- PROCCESSED LOGS & SENT DATA TO RDD | 7455 | 6800 | RIG | 05/06/2022 | SINO-19L | LOG | UTMN-1587
524 | 7455 |  | OTH | E | 2604 | NA | (OOS) HES WL UNLATCHED FROM WET CONNECTOR.- POOH WITH W/L CABLE TO SURFACE.- RIG DOWN HES WL SHEAVES & SPLIT BUSHING. | 7455 |  | HWP | 05/06/2022 | SINO-19L | LOG | UTMN-1587
525 | 7455 | 110 | TO | E | 2604 | STDP | (OOS) POOH HES MSFL / DIELECTRIC LOGGING TOOLS ON 4" DP TO SURFACE. > KEEP FILLING HOLE AND MONITOR - STATIC. | 7455 | 5090 | RIG | 05/06/2022 | SINO-19L | LOG | UTMN-1587
526 | 7455 |  | OTH | E | 2604 | NA | (OOS) L/D HES WIRELINE LOOGING TOOLS. | 7455 |  | HWP | 05/06/2022 | SINO-19L | LOG | UTMN-1587
527 | 7455 |  | HT | N |  | BHA | HPJSM, P/U & M/U 6-1/8" STIFF REAMING BHA AS FOLLOWS:> 6-1/8" WELDED TRI-CONE BIT + 6-1/8" NEAR BIT REAMER WITH FLOAT VALVE + 1 JT X 4-3/4" D/C + 6-1/8" STRING REAMER + 1 JT 4-3/4" D/C + 6-1/8" STRING REAMER +1 JTS 4-3/4" D/C + XO + 3 JTS 4" HWDP + 4-3/4" JAR + 2 JTS 4'' HWDP | 7455 |  | RIG | 05/06/2022 | SINO-19L | CT | UTMN-1587
528 | 7455 | 5315 | TI | N |  | STDP | RIH W/ 6-1/8" STIFF REAMING ASSY. ON 4" HWDP/DP T/ 5315' (TOW).> KEEP MONITOR WELL ON TRIP TANK - STATIC | 7455 | 270 | RIG | 05/06/2022 | SINO-19L | CT | UTMN-1587
529 | 7455 |  | RR | N |  | TDS | HPJSM, SERVICE TDS & CHANGED SAVER SUB. | 7455 |  | RIG | 05/06/2022 | SINO-19L | CT | UTMN-1587
530 | 7455 | 7455 | ST | N |  | STDP | PASS THROUGH WINDOW FREELY. RIH WITH 6-1/8" STIFF REAMING BHA ACROSS 6-1/8" OPEN HOLE FREELY ON ELEVATOR TO TD @ 7455'. - FILL STRING EVERY 15 STANDS WITH 82 PCF WBM. | 7455 | 5315 | RIG | 05/06/2022 | SINO-19L | CT | UTMN-1587
531 | 7455 |  | CIRC | N |  | MPMP | DISPLACE HOLE TO 82 PCF OBM. CIRCULATE AND CONDITION OBM PROPERTIES WHILE RECIPROCATING AND ROTATING THE STRING. FLOW CHECK, WELL STATIC. | 7455 |  | RIG | 05/06/2022 | SINO-19L | CT | UTMN-1587
532 | 7455 |  | CIRC | N |  | MPMP | PERFORMED STIKY TEST FOR 10 MIN AND 30 MIN, OK. | 7455 |  | RIG | 05/06/2022 | SINO-19L | CT | UTMN-1587
533 | 24 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | MSFL WITH DIELECTRIC PILOT HOLE LOGS. | 11 | 2604 | 05 May 0100 | 05/06/2022 | SINO-19L | Type | UTMN-1587
534
535
536 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | SND-1501 | Hrs | UTMN-567
537 | WTHR | ARM | 1.75 | 06 May 1000 - 1145 | 0 | 896263 | OBSERVED HIGH WIND 39-40 KPH CANNOT SAFELY L/D DP | WON | NA |  | 05/06/2022 | SND-1501 | 1.75 | UTMN-567
538 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | SND-2007 | Hrs | ADHN-370100
539 | FOT | MSD | 19 | 05 May 1645 - 1145 | 16029 | 896250 | UNABLE TO ACHEIVE OPTIMAL MAKE UP TORQUE DUE TO HYDRAULIC LEAK ON PRIMARY & BACK UP POWER PACKS. | TF | CTRQ |  | 05/06/2022 | SND-2007 | 6.75 | ADHN-370100
540 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | SP-120 | Hrs | MNIF-188
541 | XTRI | RIG | 3.5 | 06 May 0030 - 0400 | 4943 | 896296 | EXCESSIVE TIME TO FIX MULTIPLE LEAKS WHILE TESTING 13 5/8" BOP STACK. | JF | BOP |  | 05/06/2022 | SP-120 | 3.5 | MNIF-188
542 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | SP-160 | Hrs | HWTH-72
543 | FWTS | RIG | 107.75 | 02 May 1145 - 0500 | 8444 | 896181 | WHILE BACK REAM, STRING STALLED, LOST ROTATION AND CIRCULATION. ATTEMPT TO GET ROTATION WHILE JARING DOWN SUCCESSFULLY. REESTABLISH CIRCULATION GRADUALLY TO 90 GPM , DISPLACE HOLE TO 75 PCF OBM. KEEP STRING IN ROTATION. POOH, FOUND SHEARED OFF PIN BETWEEN THE TWO LAST 4" HWDP ABOVE DOG LEG REAMER. | FISH | BHA |  | 05/06/2022 | SP-160 | 24 | HWTH-72
544 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | SSA-201 | Hrs | HRDH-1818
545 | HINW | ARM | 459.5 | 17 Apr 1500 - 0500 | 14502 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/06/2022 | SSA-201 | 24 | HRDH-1818
546 | FOT | RIG | 2.25 | 06 May 1045 - 1300 | 15244 | 896257 | ACS (ANTICOLLISION FOR TDS) NOT FUNCTIONING. | RR | RSSS |  | 05/06/2022 | SSA-5891 | 2.25 | HRDH-2016
547 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | SSA-5891 | Hrs | HRDH-2016
548 | FOT | BLH | 48.25 | 04 May 0200 - 0500 | 15227 | 896202 | BAKER RUNNING TOOL FAILED TO RELEASE OFF PBR. | TF | HGRL |  | 05/06/2022 | SSA-5891 | 21.25 | HRDH-2016
549 | FOT | RIG | 2.25 | 06 May 1045 - 1300 | 15244 | 896257 | ACS (ANTICOLLISION FOR TDS) NOT FUNCTIONING. | RR | RSSS |  | 05/06/2022 | SSA-5891 | 2.25 | HRDH-2016
550 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | SSA-5974 | Hrs | HRDH-1970
551 | CWEL | ARM | 347.5 | 22 Apr 0500 - 0500 | 14884 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/06/2022 | SSA-5974 | 24 | HRDH-1970
552 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/06/2022 | V140A | Hrs | SFNY-1760
553 | UVLC | ARM | 38 | 05 May 1430 - 0430 | 313 | 896256 | LOSS OF RETURNS TO SURFACE AFTER DRILLING OUT 30" CONDUCTOR SHOE. | LCIR | NA |  | 05/06/2022 | V140A | 23.5 | SFNY-1760
554 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ADC-21 | Hrs | MZLJ-155201
555 | PSSW | ARM | 113.5 | 03 May 0800 - 0130 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/07/2022 | ADC-21 | 20.5 | MZLJ-155201
556 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ADC-35 | Hrs | MAQL-5
557 | FOT | RIG | 1 | 07 May 1900 - 2000 | 0 | 896290 | TEST UNIT WAS LEAKING | RR | RWCS |  | 05/07/2022 | ADC-35 | 1 | MAQL-5
558 |  |  | SWL | OTH | 2584 | 7109 | R/U SLB WIRE LINE SHEAVES & M/U SLB W/L CABLE S.E.S. & FEED THROUGH WIRE LINE CABLE.- MONITORED WELL ON TRIP TANK, WELL STATIC. |  |  | 7109 | 05/07/2022 | ADC-53L | NA | UTMN-4069
559 |  |  | SWL | OTH | 2584 | 7109 | RIH W/ WIRE LINE CABLE, LATCH INTO CONNECTOR AS PER MDT ENGINEER INSTRUCTION.- APPLY 150 PSI PUMP PRESS TO ASSIST IN LATCHING PROCESS AS PER SLB MDT ENG.- LATCH INTO WET CONNECTOR PROFILE, FUNCTION TEST SLB TOOLS, OK.- PERFORM PULL TENSION TEST TO 3,100 LBS, OK.- MONITORED WELL ON TRIP TANK, WELL STATIC. |  |  | 7109 | 05/07/2022 | ADC-53L | NA | UTMN-4069
560 |  |  | SWL | OTH | 2584 | 7109 | HELD PRE JOB SAFETY MEETING DISCUSSED RUNNING PRECAUTIONS, WELL CONTROL & STICKY TEST PROCEDURES. |  |  | 7109 | 05/07/2022 | ADC-53L | NA | UTMN-4069
561 | 6946 |  | RIG | TI | 2584 | 7109 | CONT'D RIH TLC 3RD RUN LOGGING TOOLS ON 4" DP FROM 4,292 FT TO 1ST SAMPLE POINT DEPTH @ 6,946 FT W/ CONTROL SPEED. - FILL UP STRING & BREAK CIRC. EVERY 10 STANDS. DRIFT ALL STANDS RIH WITH 2.25" DRIFT.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 4292 |  | 7109 | 05/07/2022 | ADC-53L | STDP | UTMN-4069
562 |  |  | SWL | OTH | 2584 | 7109 | PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE. |  |  | 7109 | 05/07/2022 | ADC-53L | NA | UTMN-4069
563 | 6946 |  | SWL | LOG | 2584 | 7109 | SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 1/12 AT 6,946 FT, (ARAB-D RESERVOIR FM).- PERFORMED SCANNING WITH LD PROBE AT 6,946 FT.- COLLECTED SAMPLE IN 01 SESSION.- MAX. STATIONARY TIME IS 4 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 1/12.- PUMP OUT COMPLETED: 1/12.- PUMP OUT INTO WELLBORE 1.07 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 1.07 BBLS, (FLUID TYPE: OIL).- HYDROSTATIC DROP= 02 PSI, OVERBALANCE, AS PER SLB MDT 972 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 6946 |  | 7109 | 05/07/2022 | ADC-53L | WLT | UTMN-4069
564 | 6892 |  | SWL | LOG | 2584 | 7109 | SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 2/12 AT 6,892 FT, (ARAB-D RESERVOIR FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH LD PROBE AT 6,892 FT.- COLLECTED SAMPLE IN 01 SESSIONS.- MAX. STATIONARY TIME IS 4 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 2/12.- PUMP OUT COMPLETED: 2/12.- PUMP OUT INTO WELLBORE 1.01 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 2.08 BBLS, (FLUID TYPE: OIL).- HYDROSTATIC DROP= 01 PSI, OVERBALANCE, AS PER SLB MDT 951 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 6892 |  | 7109 | 05/07/2022 | ADC-53L | WLT | UTMN-4069
565 |  | 896300 | SWL | OTH | 2584 | 7109 | OBSERVED AFTER SAMPLE #2, WHILE MOVE UP STRING HAD LOST COMMUNICATION WITH WL DH TOOLS. SLB WL TROUBLESHOOTING SAME WITHOUT SUCCESS.- MEANWHILE MOVE UP & DOWN THE STRING, FREE TO MOVE.- MONITORED WELL ON TRIP TANK, WELL STATIC.** DECIDED TO POOH TILL CSES DEPTH @ 4,292' TO UNLATCH CABLE, LATCH AGAIN AND TROUBLESHOUTING TRIALS. |  | TF | 7109 | 05/07/2022 | ADC-53L | NA | UTMN-4069
566 |  | 896300 | RIG | CIRC | 2584 | 7109 | RIH TO ONE STD BELOW BTM POINT @ 7,093 FT& CIRC. HOLE CLEAN ONE COMPLETE CYCLE, 100% CIRC. MW IN/ OUT 80 PCF. PERCAUTIONARY CLOSE BOP AT FINAL 200 BBLS AND CONT. CIRC. THRU CHOCK. FLOW CHECK THRU CHOCK FOR 15 MIN- WELL STATIC.- OPENED BOP & PERFORM NORMAL FLOW CHECK- WELL STATIC. |  | TF | 7109 | 05/07/2022 | ADC-53L | MPMP | UTMN-4069
567 | 6637 | 896300 | RIG | TO | 2584 | 7109 | HPJSM, POOH W/ TLC RUN #3 (MDT SAMPLING) FIRST 05 STDS TO 6,637 FT.- MONITOR WELL ON TRIP TANK. | 7093 | TF | 7109 | 05/07/2022 | ADC-53L | STDP | UTMN-4069
568 |  | 896300 | RIG | OTH | 2584 | 7109 | FLOW CHECK - WELL STATIC. |  | TF | 7109 | 05/07/2022 | ADC-53L | NA | UTMN-4069
569 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ADC-53L | Hrs | UTMN-4069
570 | FOT | SWL | 6 | 07 May 2300 - 0500 | 6869 | 896300 | OBSERVED LOST COMMUNICATION WITH WL DH TOOLS WHILE SAMPLING OPERATION. | TF | WLT |  | 05/07/2022 | ADC-53L | 6 | UTMN-4069
571 | 89 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/07/2022 | ADC-53L | Type | UTMN-4069
572
573
574 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ADC-60 | Hrs | ABSF-218
575 | FOT | ALC | 13 | 06 May 0300 - 1600 | 718 | 896284 | BAKER ESP CREW CHECK THE CABLE INTIGRITY PRIOR TO QCI FEED MLE SHIELD CABLE THRU ESP PKR, FOUND THE CABLE LOST INTEGRITY. | TF | ESPL |  | 05/07/2022 | ADC-60 | 11 | ABSF-218
576 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ADES-174 | Hrs | GHZL-88
577 | FOT | WDS | 2.25 | 07 May 1330 - 0200 | 14250 | 896297 | DOWN HOLE MWD SENSOR FAILED WHILE DRILLING AT 14,250'. ATTEMPTED SURVEYS EACH CONNECTION TO TD BUT NOT SUCCESSFUL AND NO MEMORY SURVEYS AVAILABLE. | BHA | MWD |  | 05/07/2022 | ADES-174 | 2.25 | GHZL-88
578 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ADM-655 | Hrs | SFNY-1095
579 | WTHR | ARM | 15.5 | 07 May 1330 - 0500 | 0 | 896302 | WAIT ON WEATHER TO IMPROVE TO MOVE THE RIG SFNY 1090/1099 PF. | WON | NA |  | 05/07/2022 | ADM-655 | 15.5 | SFNY-1095
580 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ADM-656 | Hrs | SFNY-397
581 | FOT | ARN | 1 | 07 May 0400 - 0500 | 7992 | 896303 | WELLLINK STOPPED TRANSMITTING SIGNAL/DATA. UNABLE TO CONTINUE DRILLING. | TF | VSAT |  | 05/07/2022 | ADM-656 | 1 | SFNY-397
582 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ARO-3003 | Hrs | SFNY-1740
583 | FOT | RIG | 3.5 | 07 May 1400 - 1730 | 4650 | 896287 | AFTER FILL-UP, BREAKING OUT TDS F/ STRING, EXCESSIVE BREAK-OUT TORQUE RESULTED IN GRABBER DIES TO BREAK AND COME OUT OF GRABBER BLOCK | RR | TDS |  | 05/07/2022 | ARO-3003 | 3.5 | SFNY-1740
584 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ARO-3004 | Hrs | MRJN-2060
585 | FOT | RIG | 5.5 | 07 May 1330 - 1900 | 0 | 896306 | ARO LT: TROUBLE SHOOT DRAW WORKS LOW CLUTCH LOSS OF AIR CONTROL; REPLACED AIR RELAY VALVE ON LOW CLUTCH SIDE & RECOVER NORMAL AIR PRESSURE | RR | DWKS |  | 05/07/2022 | ARO-3004 | 5.5 | MRJN-2060
586 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | ARO-4001 | Hrs | MRJN-539
587 | OTH | RIG | 5 | 07 May 1930 - 0030 | 2175 | 896298 | HAD MALFUNCTION IN IRON ROUGHNECH, TROUBLESHOOTING SAME. | UPRA | NA |  | 05/07/2022 | ARO-4001 | 5 | MRJN-539
588 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | DPS-4 | Hrs | MDRK-54
589 | STBH | ARM | 69.25 | 04 May 1900 - 0500 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. | STUK | BHA | 895547 | 05/07/2022 | DPS-4 | 13.75 | MDRK-54
590 | FOT | RAC | 53 | 05 May 1030 - 1700 | 10695 | 896234 | POOH W/ SPEAR, AT SURFACE FOUND GRAPPLE MISSING. | TF | FISHT |  | 05/07/2022 | DPS-74 | 12 | NJYN-54
591 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | DPS-74 | Hrs | NJYN-54
592 | FOT | BLH | 516.75 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/07/2022 | DPS-74 | 12 | NJYN-54
593 | FOT | RAC | 53 | 05 May 1030 - 1700 | 10695 | 896234 | POOH W/ SPEAR, AT SURFACE FOUND GRAPPLE MISSING. | TF | FISHT |  | 05/07/2022 | DPS-74 | 12 | NJYN-54
594 | 7550 | 5774 | LOG | E | 2564 | WLT | CONT. BHI LOGGING TOOLS RUN # 3 (RCX ON GR) & COLLECT SAMPLE #8 AT 5774' (8 OF 9 FM SAMPLES).- SAMPLE #8 @ 5,774' (ABD2): TOTAL DUMPING IN ANN. = 1.0 BBL / WATER - IN 1 CYCLE.- COLLECTED ONE BOTTLE OF WATER SAMPLE WITH MAGNA PROBE.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5774 | BAW | 05/07/2022 | DQ-47 | LOG | KHRS-1416
595 | 7550 | 5605 | LOG | E | 2564 | WLT | POSITION STRING, ACTIVATE MAGNA PROBE AND COLLECT SAMPLE #9 AT 5605.5' (9 OF 9 FM SAMPLES).- MOVE STRG. FREE, SCAN W/ MAGNA PROBE FOR GOOD MOBILITY POINT (AS PER ARAMCO RDD) AT 5605.5', 5606.5' & 5605'.- SAMPLE #9 @ 5,605.5' (PADS): TOTAL DUMPING IN ANN. = 0.1 BBL / WATER - IN 1 CYCLE.- RDD CANCELLED TIGHT POINT.- MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 7550 | 5605 | BAW | 05/07/2022 | DQ-47 | LOG | KHRS-1416
596 | 7550 |  | CIRC | E | 2564 | MPMP | RIH TO 6090', CIRC. 1.2 BOTTOM /UP AT 170 GPM, 250 PSI W/ 100% RETURN & CONDITION MUD WT = 69 PCF IN/OUT. | 7550 |  | RIG | 05/07/2022 | DQ-47 | LOG | KHRS-1416
597 | 7550 |  | WCNT | E | 2564 | NA | FLOW CHECK, WELL STATIC. | 7550 |  | RIG | 05/07/2022 | DQ-47 | LOG | KHRS-1416
598 | 7550 | 4183 | ST | E | 2564 | STDP | POOH W/ BHI (RCX-GR) WL LOG RUN #3 ON 5" DP @ CONTROLLED SPEED F/ 6090 ' T/ 4183' - SES DEPTH. | 7550 | 6090 | RIG | 05/07/2022 | DQ-47 | LOG | KHRS-1416
599 | 7550 |  | OTH | E | 2564 | NA | BHI UNLATCH CABLE HEAD & POOH T/ SURFACE. L/D SES & R/D SHEAVES. | 7550 |  | BAW | 05/07/2022 | DQ-47 | LOG | KHRS-1416
600 | 7550 | 3514 | ST | E | 2564 | STDP | POOH W/ BHI (RCX-GR) LOG RUN #3 ON 5" DP F/ 4183' T/ 13-3/8" CSG SHOE @ 3514'. | 7550 | 4183 | RIG | 05/07/2022 | DQ-47 | LOG | KHRS-1416
601 | 7550 |  | WCNT | E | 2564 | NA | FLOW CHECK, WELL STATIC. | 7550 |  | RIG | 05/07/2022 | DQ-47 | LOG | KHRS-1416
602 | 7550 | 350 | TO | E | 2564 | STDP | POOH W/ BHI (RCX-GR) LOG RUN #3 ON 5" DP F/ 3514' T/ 350' TOP OF BHA. | 7550 | 3514 | RIG | 05/07/2022 | DQ-47 | LOG | KHRS-1416
603 | 7550 |  | WCNT | E | 2564 | NA | FLOW CHECK, WELL STATIC. | 7550 |  | RIG | 05/07/2022 | DQ-47 | LOG | KHRS-1416
604 | 7550 |  | OTH | E | 2564 | NA | POOH W/ BHI RUN # 3 (RCX-GR) LOGGING TOOL ON 5" DP TO SURFACE & L/D LOGGING TOOLS. | 7550 |  | BAW | 05/07/2022 | DQ-47 | LOG | KHRS-1416
605 | 7550 |  | HT | N |  | STRG | HPJSM, R/U 4" DP HANDLING TOOLS. | 7550 |  | RIG | 05/07/2022 | DQ-47 | PA | KHRS-1416
606 | 7550 |  | HT | N |  | STRG | P/U, M/U & RIH W/ 4" DP AS CMT STINGER 32 JTS DRIFTED SINGLE BY SINGLE FROM RACK T/ 1,028'. | 7550 |  | RIG | 05/07/2022 | DQ-47 | PA | KHRS-1416
607 | 7550 |  | HT | N |  | STRG | HPJSM, R/D 4" DP HANDLING TOOLS & R/U 5'' DP HANDLING TOOLS. | 7550 |  | RIG | 05/07/2022 | DQ-47 | PA | KHRS-1416
608 | 7550 | 3514 | TI | N |  | STDP | RIH W/ 4" DP CMT STINGER ON 5" DP TO 13-3/8" CSG SHOE @ 3,514'. | 7550 | 1028 | RIG | 05/07/2022 | DQ-47 | PA | KHRS-1416
609 | 7550 | 7550 | ST | N |  | STDP | RIH W/ 4" DP CMT STINGER ON 5'' DP F/ 3,514' TO BTM @ 7,550' - AT RT. | 7550 | 3514 | RIG | 05/07/2022 | DQ-47 | PA | KHRS-1416
610 | 184.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | BAKER W/L LOG FOR 8 1/2" PILOT HOLE. | 18.75 | 2564 | 30 Apr 0730 | 05/07/2022 | DQ-47 | Type | KHRS-1416
611
612
613 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | HI-2 | Hrs | BRRI-464
614 | WTHR | ARN | 2.5 | 07 May 1400 - 1630 | 2681 | 896267 | WHILE PU / MU 9 5/8" WBCO ASSY, OBSERVED VERY HIGH WIND SPEED & ROUGH WEATHER. SUSPEND CRANE OPERATION. | WON | NA |  | 05/07/2022 | HI-2 | 2.5 | BRRI-464
615 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | HI-4 | Hrs | SFNY-918
616 | FOT | FMC | 1.25 | 07 May 1515 - 1630 | 3368 | 896289 | CRT SPEAR TAKING HIGH TORQUE AND HANGING UP DURING RELEASE. | TF | CRT |  | 05/07/2022 | HI-4 | 1.25 | SFNY-918
617 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | JACK-202 | Hrs | HMYM-844
618 | FOT | RIG | 36.5 | 06 May 1630 - 0500 | 1772 | 896281 | WHILE PULLING OUT DRILL STRING TO CHANGE BHA DUE TO TOTAL LOSS. DRILLING LINE SLIPPED OUT OF DRAWWORKS CLAMB AND TRAVELLING BLOC FALL DOWN ON RIG FLOOR. | RR | DWKS |  | 05/07/2022 | JACK-202 | 24 | HMYM-844
619 | UNKN | RIG | 1 | 07 May 2230 - 2330 | 10875 | 896269 | IP WAS MOVING A LOAD SUSPENDED WITH A CHAIN HOIST, AS THE ITEM WAS LOWERED, THE LOAD SHIFTED AND CAUGHT THE IP INDEX FINGER BETWEEN A ROLLER ON THE LOAD. THE IP WAS TAKEN TO THE MEDIC AND A SMALL PRESSURE CUT WAS DRESSED. SAFETY STAND-DOWN WAS HELD. | HSEI | NA |  | 05/07/2022 | MP-1 | 1 | MRJN-305
620 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | MP-1 | Hrs | MRJN-305
621 | FOT | RIG | .5 | 07 May 1115 - 1145 | 10395 | 896209 | LOSS OF PRESSURE OBSERVED DURING DRILLING. MUD PUMP PISTON SWAB WAS LEAKING. ISOLATED PUMP AND REPLACED SWAB. CONTINUED DRILLING. | RR | MPMP |  | 05/07/2022 | MP-1 | .5 | MRJN-305
622 | FOT | RIG | 1.25 | 07 May 1800 - 1915 | 10780 | 896210 | LOSS OF PRESSURE OBSERVED DURING DRILLING. MUD PUMP PISTON SWAB WAS LEAKING. ISOLATED PUMP AND REPLACED SWAB, LINER AND SEAL. CONTINUED DRILLING. | RR | MPMP |  | 05/07/2022 | MP-1 | 1.25 | MRJN-305
623 | UNKN | RIG | 1 | 07 May 2230 - 2330 | 10875 | 896269 | IP WAS MOVING A LOAD SUSPENDED WITH A CHAIN HOIST, AS THE ITEM WAS LOWERED, THE LOAD SHIFTED AND CAUGHT THE IP INDEX FINGER BETWEEN A ROLLER ON THE LOAD. THE IP WAS TAKEN TO THE MEDIC AND A SMALL PRESSURE CUT WAS DRESSED. SAFETY STAND-DOWN WAS HELD. | HSEI | NA |  | 05/07/2022 | MP-1 | 1 | MRJN-305
624 | FOT | SDM | 26.5 | 06 May 0000 - 0300 | 8100 | 896282 | LOST SIGNAL FROM MWD WHILE DRILLING AT 8100', TROUBLESHOOTING MWD TOOL, NO SUCCESS. | BHA | MWD |  | 05/07/2022 | MP-4 | 21.5 | LWHH-45
625 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | MP-4 | Hrs | LWHH-45
626 | SRVC | ARM | 1 | 07 May 0400 - 0500 | 8100 | 896268 | ARAMCO CDC MAIN SERVER NOT WORKING, GOC INSTRUCTION NOT TO START DRILLING UNTIL SERVER BACK TO NORMAL. | WO | NA |  | 05/07/2022 | MP-4 | 1 | LWHH-45
627 | FOT | SDM | 26.5 | 06 May 0000 - 0300 | 8100 | 896282 | LOST SIGNAL FROM MWD WHILE DRILLING AT 8100', TROUBLESHOOTING MWD TOOL, NO SUCCESS. | BHA | MWD |  | 05/07/2022 | MP-4 | 21.5 | LWHH-45
628 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | NBR-591S | Hrs | HRDH-1921
629 | FOT | GOC | 7.25 | 07 May 1615 - 2330 | 10436 | 896266 | AL-GHAITH SPIDER ELEVATOR & SPIDER SLIPS STUCK ON CASING JT# 254. | TF | CTRQ |  | 05/07/2022 | NBR-591S | 7.25 | HRDH-1921
630 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | PA-866S | Hrs | SHHB-2
631 | FOT | RIG | 17.5 | 06 May 0230 - 2000 | 6326 | 896235 | OBSERVED LEAK ON SECONDARY STANDPIPE. | RR | CSYS |  | 05/07/2022 | PA-866S | 15 | SHHB-2
632 | FOT | BHI | 1.5 | 07 May 0200 - 0330 | 7815 | 896271 | BHI LOST COMMUNICATION WITH THEIR TOOLS. | BHA | LWD |  | 05/07/2022 | PN-7 | 1.5 | MRJN-773
633 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | PN-7 | Hrs | MRJN-773
634 | FOT | ARN | 1 | 07 May 0400 - 0500 | 7830 | 896270 | GOC LOST WELLLINK REAL TIME DATA | TF | VSAT |  | 05/07/2022 | PN-7 | 1 | MRJN-773
635 | FOT | BHI | 1.5 | 07 May 0200 - 0330 | 7815 | 896271 | BHI LOST COMMUNICATION WITH THEIR TOOLS. | BHA | LWD |  | 05/07/2022 | PN-7 | 1.5 | MRJN-773
636 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | RM-74A | Hrs | KARN-60
637 | WTHR | ARM | 3 | 07 May 1015 - 1315 | 0 | 896286 | WOW. UNABLE TO OPEN WELL DUE TO UNFAVORABLE WIND CONDITION | WON | NA |  | 05/07/2022 | RM-74A | 3 | KARN-60
638 | 17315 |  | STIM | E | 2545 | CTU | RIH W/ BHI 2-3/8" CT AS PER BHI STANDARD PROCEDURES F/ 6,850' TO 9-5/8" CSG SHOE AT 9,983'.- CT RIH SPEED: 30-40 FT/MIN.- START PUMPING 140 BBLS EASY REACH @ 3500' TO BE OUT OF CT AT 7000'.- PERFORM PULL TEST EVERY 1000'-1500'. | 17315 |  | BCT | 05/07/2022 | SIN30L | STIM | KHRS-1409
639 | 17315 |  | STIM | E | 2545 | CTU | CONT. RIH W/ 2-3/8" CT F/ 9,983' T/ TARGETED DEPTH 17,226 '.(L-1 TD)- STARTED PUMPING PRE-FLUSH F/ 9983 FT.- PUMP RATE: 2-3 BPM.- CTU PUMPING PRESS:1700-3600 PSI.- CTU SPEED: 10-15 FT/MIN.- WHP : 25-120 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/07/2022 | SIN30L | STIM | KHRS-1409
640 | 17315 |  | STIM | E | 2545 | CTU | PERFORM L-1 ACID MATRIX STIMULATION WITH BHI CT AS PER PROGRAM WHILE POOH F/ 17,226 FT T/ 1,0350' FT.- TOTAL VOLUME PUMPED ( 15% HCL: 1725 BBLS; 15% EMULSIFIED ACID: 517 BBLS).- PUMP RATE: 2.4-3 BPM.- CTU PUMPING PRESS: 3500-4400 PSI.- CTU SPEED: 2-12 FT/MIN.- WHP : 70-140 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/07/2022 | SIN30L | STIM | KHRS-1409
641 | 128.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 24 | 2545 | 01 May 1800 | 05/07/2022 | SIN30L | Type | KHRS-1409
642
643
644 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | SINO-43L | Hrs | HWYH-2528
645 | SCSG | TK2 | 23.5 | 07 May 0530 - 0500 | 1960 | 896265 | WHILE RIH W/ 18-5/8"CSG HAD OBSTRUCTION @ 1600 FT ,ATTEMPT TO P/U CSG & WASH DOWN, CSG GOT STUCK. CONTINUE WORK ON STUCK . STRG NOT MOVE UP OR DOWN. | STUK | CSG |  | 05/07/2022 | SINO-43L | 23.5 | HWYH-2528
646 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | SP-101 | Hrs | ABQQ-710
647 | FOT | WI1 | 250.5 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/07/2022 | SP-101 | 22 | ABQQ-710
648 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | SP-160 | Hrs | HWTH-72
649 | FWTS | RIG | 129.75 | 02 May 1145 - 0500 | 8444 | 896181 | WHILE BACK REAM, STRING STALLED, LOST ROTATION AND CIRCULATION. ATTEMPT TO GET ROTATION WHILE JARING DOWN SUCCESSFULLY. REESTABLISH CIRCULATION GRADUALLY TO 90 GPM , DISPLACE HOLE TO 75 PCF OBM. KEEP STRING IN ROTATION. POOH, FOUND SHEARED OFF PIN BETWEEN THE TWO LAST 4" HWDP ABOVE DOG LEG REAMER. | FISH | BHA |  | 05/07/2022 | SP-160 | 23.5 | HWTH-72
650 | ACDI | SDM | 14.5 | 07 May 1430 - 0500 | 14121 | 896301 | HAD PRESSURE DROP, LOST MWD SIGNAL AND UNABLE TO REGAIN SIGNAL TO THE TOOL. | DD | BHA |  | 05/07/2022 | SSA-201 | 14.5 | HRDH-1818
651 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | SSA-201 | Hrs | HRDH-1818
652 | HINW | ARM | 469 | 17 Apr 1500 - 1430 | 14502 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/07/2022 | SSA-201 | 9.5 | HRDH-1818
653 | ACDI | SDM | 14.5 | 07 May 1430 - 0500 | 14121 | 896301 | HAD PRESSURE DROP, LOST MWD SIGNAL AND UNABLE TO REGAIN SIGNAL TO THE TOOL. | DD | BHA |  | 05/07/2022 | SSA-201 | 14.5 | HRDH-1818
654 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | SSA-303 | Hrs | HRDH-2306
655 | FOT | CAM | 2.75 | 07 May 0100 - 0345 | 5115 | 896305 | UNABLE TO PRESSURE TEST PACK OFF SEALS ON 13-5/8" FLUTED MANDREL HANGER | TF | FMH |  | 05/07/2022 | SSA-303 | 2.75 | HRDH-2306
656 | XTTE | WCR | 2.5 | 07 May 0145 - 0415 | 15244 | 896208 | WFD 4-1/2" TBG SLIPS NOT HOLDING TBG. | TF | TTRQ |  | 05/07/2022 | SSA-5891 | 2.5 | HRDH-2016
657 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | SSA-5891 | Hrs | HRDH-2016
658 | FOT | BLH | 67.75 | 04 May 0200 - 0500 | 15227 | 896202 | BAKER RUNNING TOOL FAILED TO RELEASE OFF PBR. | TF | HGRL |  | 05/07/2022 | SSA-5891 | 19.5 | HRDH-2016
659 | XTTE | WCR | 2.5 | 07 May 0145 - 0415 | 15244 | 896208 | WFD 4-1/2" TBG SLIPS NOT HOLDING TBG. | TF | TTRQ |  | 05/07/2022 | SSA-5891 | 2.5 | HRDH-2016
660 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | T216 | Hrs | ANDR-95
661 | FOT | RIG | 5 | 07 May 0000 - 0500 | 0 | 896299 | STRING PLUG WHILE ATTAMPT TO FILL UP & CIRC. | DSF | STRG |  | 05/07/2022 | T216 | 5 | ANDR-95
662 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/07/2022 | WCL-83 | Hrs | MRJN-837
663 | WOTO | ARM | .5 | 07 May 0430 - 0500 | 12669 | 896304 | LOST REAL TIME DATA TRANSMISSION WHILE DRILLING DUE TO V-SAT WAS DOWN. | WO | NA |  | 05/07/2022 | WCL-83 | .5 | MRJN-837
664 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | 095TE | Hrs | MNIF-220
665 | FOT | BHI | 24.25 | 07 May 0345 - 0500 | 9948 | 896294 | BHI TESTRAK TOOL FAILURE WHILE TAKING PRESSURE POINTS REQUESTED BY RDD, POOH AND P/U NEW BHI FPWD + MWD (GR) TOOLS WITH 8.5" REAMING ASSY. | BHA | LWD |  | 05/08/2022 | 095TE | 23 | MNIF-220
666 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADC-21 | Hrs | MZLJ-155201
667 | PSSW | ARM | 131 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/08/2022 | ADC-21 | 17.5 | MZLJ-155201
668 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADC-52 | Hrs | SDGM-1254
669 | FOT | SPS | 22 | 08 May 0700 - 0500 | 11704 | 896272 | DURING 5-7/8" SECTION DRILLING W/ SPERRY RSS/MWD/GR BHA, FOUND SPP SPIKES FROM THE BEGINNING. BUT SIGNAL QUALITY WAS GOOD AND ABLE TO CONTINUE DRILLING. BUT AFTER REACH TO 11, 524' SPP INCREASED +/- 500 PSI AND MWD TOOLS LOST SIGNAL. | BHA | MWD |  | 05/08/2022 | ADC-52 | 22 | SDGM-1254
670 | 4292 | 896300 | RIG | TO | 2584 | 7109 | CONT'D POOH CONTROLLED SPEED W/ TLC RUN #3 (MDT SAMPLING) FROM 6,637 FT TO CSES (LATCHING) DEPTH @ 4.292 FT.- MONITOR WELL ON TRIP TANK. | 6637 | TF | 7109 | 05/08/2022 | ADC-53L | STDP | UTMN-4069
671 |  | 896300 | SWL | OTH | 2584 | 7109 | SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE, RE-LATCH AGAIN & TROUBLESHOOTING TRIALS - WITHOUT SUCCESS.- DECIDED TO POOH WITH CABLE HEAD TO SURFACE TO CHECK SAME. |  | TF | 7109 | 05/08/2022 | ADC-53L | NA | UTMN-4069
672 |  | 896300 | SWL | OTH | 2584 | 7109 | HPJSM, SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE & POOH SAME TO SURFACE, TROUBLESHOOTING- FOUND CABLE HEAD MALFUNCTION. |  | TF | 7109 | 05/08/2022 | ADC-53L | NA | UTMN-4069
673 |  | 896300 | SWL | OTH | 2584 | 7109 | SLB WL CHANGED CABLE HEAD TO NEW ONE AND FUNCTION TEST SAME ON SURFACE- OK. |  | TF | 7109 | 05/08/2022 | ADC-53L | NA | UTMN-4069
674 |  | 896300 | SCP | OTH | 2584 | 7109 | RIH W/ WIRE LINE CABLE, LATCH INTO CONNECTOR AS PER MDT ENGINEER INSTRUCTION. LATCH INTO WET CONNECTOR PROFILE, FUNCTION TEST SLB TOOLS- FAILED TO HAVE GOOD COMMUNICATION WITH DH TOOLS. DECIDED TO POOH TO CHANGE DOWN HOLE SAMPLING TOOLS. |  | TF | 7109 | 05/08/2022 | ADC-53L | NA | UTMN-4069
675 |  | 896300 | SWL | OTH | 2584 | 7109 | SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE & POOH SAME TO SURFACE. R/D CSES & SHEAVES. |  | TF | 7109 | 05/08/2022 | ADC-53L | NA | UTMN-4069
676 |  | 896300 | SWL | OTH | 2584 | 7109 | POOH CONTROLLED SPEED W/ TLC RUN #3 (MDT SAMPLING) FROM 4,292 FT TO SURFACE.- MONITOR WELL ON TRIP TANK. |  | TF | 7109 | 05/08/2022 | ADC-53L | NA | UTMN-4069
677 |  | 896300 | SWL | OTH | 2584 | 7109 | HPJSM, L/D SLB MDT-GR LOGGING TOOL.- MONITOR WELL ON TRIP TANK. |  | TF | 7109 | 05/08/2022 | ADC-53L | NA | UTMN-4069
678 |  | 896300 | RIG | HT | 2584 | 7109 | HPJSM, P/U & M/U 8-1/2" COND. TRIP BHA AND RIH TO 1,137 FT.SMITH XS616-C SN/ SM0536 W/ 6 X 13" NOZZLES.- MONITOR WELL ON TRIP TANK- FILL STRING AFTER BHA. |  | TF | 7109 | 05/08/2022 | ADC-53L | BHA | UTMN-4069
679 | 4620 | 896300 | RIG | TI | 2584 | 7109 | CONTINUE RIH WITH 8-1/2" COND. TRIP FROM 1137' TO 9-5/8" CSG SHOE AT 4620 FT.- MONITOR WELL ON TRIP TANK-FILL STRING EVERY 20 STD. | 1137 | TF | 7109 | 05/08/2022 | ADC-53L | STDP | UTMN-4069
680 | 5900 | 896300 | RIG | TI | 2584 | 7109 | CONTINUE RIH WITH 8-1/2" COND. TRIP IN OH FROM 4,620 TO 5,900 FT... IN PROGRESS.- MONITOR WELL ON TRIP TANK.- FILL STRING EVERY 20 STD. | 4620 | TF | 7109 | 05/08/2022 | ADC-53L | STDP | UTMN-4069
681 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADC-53L | Hrs | UTMN-4069
682 | FOT | SWL | 30 | 07 May 2300 - 0500 | 6869 | 896300 | CABLE HEAD MALFUNCTION & LEADS TO LOST COMMUNICATION WITH WL DH TOOLS WHILE SAMPLING OPERATION. | TF | WLT |  | 05/08/2022 | ADC-53L | 24 | UTMN-4069
683 | 113 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/08/2022 | ADC-53L | Type | UTMN-4069
684
685
686 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADC-56L | Hrs | UTMN-2330
687 | WTHR | TK3 | 2 | 08 May 1830 - 2030 | 14193 | 896322 | WAIT ON WEATHER HIGH WINDS ABOVE 14 M/S | WON | NA |  | 05/08/2022 | ADC-56L | 2 | UTMN-2330
688 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADC-60 | Hrs | ABSF-218
689 | FOT | ALC | 30.5 | 06 May 0300 - 0500 | 718 | 896284 | BAKER ESP CREW CHECK THE CABLE INTEGRITY, FOUND THE CABLE LOST INTEGRITY. | TF | ESPL |  | 05/08/2022 | ADC-60 | 17.5 | ABSF-218
690 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADC-65L | Hrs | HWYH-1280
691 | HERR | RIG | 14.25 | 08 May 1445 - 0500 | 3050 | 896273 | DURING N/U OF SPACER SPOOL, ONE 3-1/8" OD NUT SLIPPED FROM BOLT INTO THE WELL. | FISH | STRG |  | 05/08/2022 | ADC-65L | 14.25 | HWYH-1280
692 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADES-174 | Hrs | GHZL-88
693 | FOT | RIG | .75 | 08 May 0815 - 0900 | 14698 | 896316 | DRAWWORKS OIL PUMP ELECTRIC MOTOR FAILED. | RR | DWKS |  | 05/08/2022 | ADES-174 | .75 | GHZL-88
694 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADM-262 | Hrs | MRJN-123
695 | FOT | RIG | 1 | 08 May 0800 - 0900 | 11372 | 896211 | WASHPIPE STARTED LEAKING AFTER ONLY 384 CIRCULATING HOURS, CHANGE OUT SAME. | RR | RSYS |  | 05/08/2022 | ADM-262 | 1 | MRJN-123
696 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ADM-655 | Hrs | SFNY-1095
697 | WTHR | ARM | 39.5 | 07 May 1330 - 0500 | 0 | 896302 | WAIT ON WEATHER TO IMPROVE TO MOVE THE RIG SFNY 1090/1099 PF. | WON | NA |  | 05/08/2022 | ADM-655 | 24 | SFNY-1095
698 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | AOD-1 | Hrs | ZULF-694
699 | FOT | SCD | 6.5 | 08 May 2230 - 0500 | 1516 | 896319 | GWD TOOL, POOR DECODING & INTERMITTENT PULSING. | TF | GYRO |  | 05/08/2022 | AOD-1 | 6.5 | ZULF-694
700 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | ARO-2001 | Hrs | BRRI-91
701 | FOT | SJT | 13.75 | 08 May 0915 - 2300 | 0 | 896317 | SANJIL CTU BOP SHEAR RAM FAIL TO FULL OPEN/CLOSE, CREATING OBSTRUCTION TO PASS. | BOP | RAMS |  | 05/08/2022 | ARO-2001 | 13.75 | BRRI-91
702 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | DPS-4 | Hrs | MDRK-54
703 | STBH | ARM | 92.75 | 04 May 1900 - 0500 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. | STUK | BHA | 895547 | 05/08/2022 | DPS-4 | 23.5 | MDRK-54
704 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | DPS-46 | Hrs | SDGM-1106
705 | FOT | CRW | 12.75 | 08 May 1615 - 0500 | 12595 | 896318 | AFTER COMPLETING NEG. TEST ATTEMPTED TO CIRC W/ NO SUCCESS, | BHA | WBCL |  | 05/08/2022 | DPS-46 | 12.75 | SDGM-1106
706 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | DPS-74 | Hrs | NJYN-54
707 | FOT | BLH | 593 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/08/2022 | DPS-74 | 24 | NJYN-54
708 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | JACK-202 | Hrs | HMYM-844
709 | FOT | RIG | 60.5 | 06 May 1630 - 0500 | 1772 | 896281 | WHILE PULLING OUT DRILL STRING TO CHANGE BHA DUE TO TOTAL LOSS. DRILLING LINE SLIPPED OUT OF DRAWWORKS CLAMB AND TRAVELLING BLOC FALL DOWN ON RIG FLOOR. | RR | DWKS |  | 05/08/2022 | JACK-202 | 24 | HMYM-844
710 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | MP-1 | Hrs | MRJN-305
711 | FOT | RIG | 10.5 | 08 May 1830 - 0500 | 10875 | 896307 | WHILE POH AND L/D DIRECTIONAL RSS/MWD ASSY, COLLAR SLIPS WERE USED, WHEN PULLED FROM THE ROATARY IT WAS NOTICED THAT 2 BUTTON DYES WERE MISSING. CHECKED IMMEDIATE AREA, NOT FOUND. ASSUMED TO HAVE FALLEN DOWNHOLE. RIH WITH MILL ASSY TO RETRIEVE OR PUSH TO BOTTOM/ OPEN HOLE. | TF | SLIPS |  | 05/08/2022 | MP-1 | 10.5 | MRJN-305
712 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | NBR-633S | Hrs | HRDH-2234
713 | HERR | RIG | 4 | 25 Apr 0000 - 2330 | 5100 | 895944 | EXCESS TIME WHILE N/U & P/T BOPE. | BOP | BOP |  | 05/08/2022 | NBR-633S | 2 | HRDH-2234
714 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | PA-866S | Hrs | SHHB-2
715 | FOT | RIG | 12.5 | 08 May 1630 - 0500 | 6982 | 896213 | LEAK ON MUD PUMP GROUND MANIFOLD - ISOLATION VALVE LEAK. | RR | CHK |  | 05/08/2022 | PA-866S | 12.5 | SHHB-2
716 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | RBP-50A | Hrs | KARN-46
717 | FOT | HTS | 14 | 08 May 0500 - 2030 | 11911 | 896293 | MULTIPLE LEAKS ON HWT LINES. NOT ENOUGH 1502 GASKETS, HWT BORROW FROM HCT AND THE RIG TO BE ABLE TO GET SURFACE LINE TEST. | TF | WTSE |  | 05/08/2022 | RBP-50A | 14 | KARN-46
718 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | RM-74A | Hrs | KARN-60
719 | WTHR | ARM | 4 | 07 May 1015 - 0700 | 0 | 896286 | WOW. UNABLE TO OPEN WELL DUE TO UNFAVORABLE WIND CONDITION | WON | NA |  | 05/08/2022 | RM-74A | 1 | KARN-60
720 | 17315 |  | STIM | E | 2545 | CTU | PERFORM L-1 ACID MATRIX STIMULATION WITH BHI CT AS PER PROGRAM WHILE POOH F/ 10,350 FT T/ 9,983' FT.- TOTAL VOLUME PUMPED ( 15% HCL: 1725 BBLS; 15% EMULSIFIED ACID: 517 BBLS).- PUMP RATE: 2.4 BPM.- CTU PUMPING PRESS: 2500-2700 PSI.- CTU SPEED: 2-12 FT/MIN.- WHP : 100-125 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/08/2022 | SIN30L | STIM | KHRS-1409
721 | 17315 |  | STIM | E | 2545 | CTU | RIH W/ 2-3/8" CT F/ 9,983 FT T/ TO LOCK UP DEPTH @ 14.668 FT.(L-1) WHILE PUMPING POST FLUSH.- PUMP RATE: 1.3-3 BPM.- CTU PUMPING PRESS: 3600-5500 PSI. CT PUMPING PRESSURE INCREASED.- CTU SPEED: 5-25 FT/MIN.- WHP :50-120 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/08/2022 | SIN30L | STIM | KHRS-1409
722 | 17315 |  | STIM | E | 2545 | CTU | POOH W/ 2-3/8" CT F/ 14,688 FT T/ TO 9-5/8"CSG SHOE @ 9,983 FT. WHILE PUMPING POST FLUSH.- PUMP RATE: 1.3-1.5 BPM.- CTU PUMPING PRESS: 4000-5500 PSI.- CTU SPEED: 5-10 FT/MIN.- WHP : 55-120 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/08/2022 | SIN30L | STIM | KHRS-1409
723 | 17315 |  | STIM | E | 2545 | CTU | CONT PUMPING POST FLUSH AT 9-5/8" CSG SHOE TILL PLANED AMOUNT (1,390 BBL) PUMPED.- PUMP RATE: 1.3 BPM.- CTU PUMPING PRESS: 4800-5500 PSI.- WHP : 50-65 PSI, CHOKE CLOSED. | 17315 |  | BCT | 05/08/2022 | SIN30L | STIM | KHRS-1409
724 | 17315 |  | STIM | E | 2545 | CTU | LINE UP AND BULLHEAD 1.2X CSG CAPACITY W/ 66 PCF VISCOUS BRINE AT 9-5/8" CSG SHOE.- WHP : 100-170 PSI. | 17315 |  | BCT | 05/08/2022 | SIN30L | STIM | KHRS-1409
725 | 17315 |  | STIM | E | 2545 | CTU | EXTENDED FLOW CHECK, STATIC LOSSES 100 BPH. | 17315 |  | BCT | 05/08/2022 | SIN30L | STIM | KHRS-1409
726 | 17315 |  | STIM | E | 2545 | CTU | POOH W/ 2-3/8" CT F/ 9-5/8"CSG SHOE @ 9,983' TO 5000' WHILE PUMPING 66 PCF VISCOUS BRINE AT MINIMUM RATE 0.25 BPM.- MONITOR WELL ON TRIP TANK, STATIC LOSSES 100 BPH. | 17315 |  | BCT | 05/08/2022 | SIN30L | STIM | KHRS-1409
727 | 152.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 24 | 2545 | 01 May 1800 | 05/08/2022 | SIN30L | Type | KHRS-1409
728
729
730 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | SINO-12L | Hrs | HRDH-1454
731 | HERR | TK1 | 3.5 | 08 May 0130 - 0500 | 7965 | 896274 | HAD LEAK DURING PRESSURE TEST CMT VALVE. | TF | CSG |  | 05/08/2022 | SINO-12L | 3.5 | HRDH-1454
732 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | SINO-43L | Hrs | HWYH-2528
733 | SCSG | TK2 | 33.5 | 07 May 0530 - 1500 | 1960 | 896265 | WHILE RIH W/ 18-5/8"CSG HAD OBSTRUCTION @ 1600 FT ,ATTEMPT TO P/U CSG & WASH DOWN, CSG GOT STUCK. CONTINUE WORK ON STUCK . STRG NOT MOVE UP OR DOWN. | STUK | CSG |  | 05/08/2022 | SINO-43L | 10 | HWYH-2528
734 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | SNT-025 | Hrs | SFNY-956
735 | WTHR | ARM | 17 | 08 May 1200 - 0500 | 4650 | 896295 | ALL CHOPPERS HAVE BEEN CANCELLED DUE TO BAD WEATHER. | WON | NA |  | 05/08/2022 | SNT-025 | 17 | SFNY-956
736 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | SP-101 | Hrs | ABQQ-710
737 | FOT | WI1 | 272 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/08/2022 | SP-101 | 21.5 | ABQQ-710
738 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | SP-160 | Hrs | HWTH-72
739 | FWTS | RIG | 152.75 | 02 May 1145 - 0500 | 8444 | 896181 | WHILE BACK REAM, STRING STALLED, LOST ROTATION AND CIRCULATION. ATTEMPT TO GET ROTATION WHILE JARING DOWN SUCCESSFULLY. REESTABLISH CIRCULATION GRADUALLY TO 90 GPM , DISPLACE HOLE TO 75 PCF OBM. KEEP STRING IN ROTATION. POOH, FOUND SHEARED OFF PIN BETWEEN THE TWO LAST 4" HWDP ABOVE DOG LEG REAMER. | FISH | BHA |  | 05/08/2022 | SP-160 | 23 | HWTH-72
740 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | SSA-201 | Hrs | HRDH-1818
741 | ACDI | SDM | 31.5 | 07 May 1430 - 0500 | 14121 | 896301 | HAD PRESSURE DROP, LOST MWD SIGNAL AND UNABLE TO REGAIN SIGNAL TO THE TOOL. | DD | BHA |  | 05/08/2022 | SSA-201 | 17 | HRDH-1818
742 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | SSA-5891 | Hrs | HRDH-2016
743 | FOT | BLH | 91.75 | 04 May 0200 - 0500 | 15227 | 896202 | BAKER RUNNING TOOL FAILED TO RELEASE OFF PBR. | TF | HGRL |  | 05/08/2022 | SSA-5891 | 24 | HRDH-2016
744 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | SSA-5974 | Hrs | HRDH-1970
745 | CWEL | ARM | 395.5 | 22 Apr 0500 - 0500 | 14140 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/08/2022 | SSA-5974 | 24 | HRDH-1970
746 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/08/2022 | T216 | Hrs | ANDR-95
747 | LRFL | SMI | 29 | 07 May 0000 - 0500 | 0 | 896299 | STRING PLUG WHILE ATTAMPT TO FILL UP & CIRC DUE TO CHEMICAL SETTLING | HC | NA |  | 05/08/2022 | T216 | 24 | ANDR-95
748 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | 095TE | Hrs | MNIF-220
749 | FOT | BHI | 47.75 | 07 May 0345 - 0500 | 9948 | 896294 | BHI TESTRAK TOOL FAILURE WHILE TAKING PRESSURE POINTS REQUESTED BY RDD, POOH AND P/U NEW BHI FPWD + MWD (GR) TOOLS WITH 8.5" REAMING ASSY. | BHA | LWD |  | 05/09/2022 | 095TE | 23.5 | MNIF-220
750 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-21 | Hrs | MZLJ-155201
751 | PSSW | ARM | 155 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/09/2022 | ADC-21 | 24 | MZLJ-155201
752 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-31 | Hrs | SDGM-1181
753 | FOT | RIG | 2.25 | 09 May 0245 - 0500 | 4247 | 896313 | REPAIRE LEAK IN STAND PIP VALVE | RR | CSYS |  | 05/09/2022 | ADC-31 | 2.25 | SDGM-1181
754 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-46L | Hrs | UTMN-3153
755 | CFFM | TK3 | 20.75 | 09 May 0815 - 0500 | 13570 | 896378 | RUN IN OPEN HOLE SLB WIRELINE LOGGING TO 13570 FT, OBSERVED HOLD UP, PICKED UP WITH NO OVER PULL MADE 2 FURTHER ATTEMPTS WITH DIFFERENT RUNNING SPEED - COULD NOT PASS. | BHS | NA |  | 05/09/2022 | ADC-46L | 20.75 | UTMN-3153
756 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-52 | Hrs | SDGM-1254
757 | FOT | SPS | 27.25 | 08 May 0700 - 1015 | 11704 | 896272 | DURING 5-7/8" SECTION DRILLING W/ SPERRY RSS/MWD/GR BHA, FOUND SPP SPIKES FROM THE BEGINNING. BUT SIGNAL QUALITY WAS GOOD AND ABLE TO CONTINUE DRILLING. BUT AFTER REACH TO 11, 524' SPP INCREASED +/- 500 PSI AND MWD TOOLS LOST SIGNAL. | BHA | MWD |  | 05/09/2022 | ADC-52 | 5.25 | SDGM-1254
758 | 7109 | 896300 | RIG | TI | 2584 | 7109 | CONTINUE RIH WITH 8-1/2" COND. TRIP IN OH FROM 5,900 TO BTM @ 7,109 FT, PRECAUTIONARY WASH DOWN LAST STD.- MONITOR WELL ON TRIP TANK. FILL STRING EVERY 20 STD. | 5900 | TF | 7109 | 05/09/2022 | ADC-53L | STDP | UTMN-4069
759 |  | 896300 | RIG | CIRC | 2584 | 7109 | SWEPT HOLE WITH 50 BBLS HI VIS PILL & CIRCULATED THREE COMPLETE CYCLES TILL SHAKERS CLEAN. FLOW CHECK - WELL STATIC.- FR: 600 GPM, SPP: 2750 PSI. |  | TF | 7109 | 05/09/2022 | ADC-53L | MPMP | UTMN-4069
760 | 6645 | 896300 | RIG | TO | 2584 | 7109 | HPJSM, POOH WITH 8 1/2" COND. TRIP FOR LOGGING FIRST 05 STDS TO 6,645 FT.-OPEN HOLE IN GOOD CONDITION.- MONITORED WELL ON TRIP TANK | 7109 | TF | 7109 | 05/09/2022 | ADC-53L | STDP | UTMN-4069
761 |  | 896300 | RIG | OTH | 2584 | 7109 | FLOW CHECK - WELL STATIC. |  | TF | 7109 | 05/09/2022 | ADC-53L | NA | UTMN-4069
762 | 4620 | 896300 | RIG | TO | 2584 | 7109 | CONT'D POOH WITH 8 1/2" COND. TRIP FOR LOGGING FROM 6,645 FT TO 9-5/8" CSG SHOE @ 4,620 FT-OPEN HOLE IN GOOD CONDITION.- MONITORED WELL ON TRIP TANK. | 6645 | TF | 7109 | 05/09/2022 | ADC-53L | STDP | UTMN-4069
763 |  | 896300 | RIG | OTH | 2584 | 7109 | FLOW CHECK AT CSG SHOE - WELL STATIC |  | TF | 7109 | 05/09/2022 | ADC-53L | NA | UTMN-4069
764 | 1137 | 896300 | RIG | TO | 2584 | 7109 | CONT'D POOH WITH 8 1/2" COND. TRIP FOR LOGGING FROM 4620 FT TO BHA DEPTH @ 1137 FT- MONITORED WELL ON TRIP TANK. | 4620 | TF | 7109 | 05/09/2022 | ADC-53L | STDP | UTMN-4069
765 |  | 896300 | RIG | OTH | 2584 | 7109 | FLOW CHECK @ BHA TOP- WELL STATIC. |  | TF | 7109 | 05/09/2022 | ADC-53L | NA | UTMN-4069
766 | 0 | 896300 | RIG | TO | 2584 | 7109 | CONT'D POOH WITH 8-1/2" COND. TRIP FOR LOGGING TO SURFACE.- MONITORED WELL ON TRIP TANK. | 1137 | TF | 7109 | 05/09/2022 | ADC-53L | BHA | UTMN-4069
767 |  | 896300 | RIG | HT | 2584 | 7109 | HPJSM, L/D 8-1/2" BHA & PDC BIT.- DULL BIT GRADING: 0 - 1 - CT - G - X- I - NO - LOG- MONITORED WELL ON TRIP TANK. |  | TF | 7109 | 05/09/2022 | ADC-53L | BHA | UTMN-4069
768 |  | 896300 | SWL | OTH | 2584 | 7109 | L/D SHEAVES, CHANGE WL UNIT, PREPARE NEW RWCH CABLE HEAD. |  | TF | 7109 | 05/09/2022 | ADC-53L | NA | UTMN-4069
769 |  | 896300 | RIG | PJSM | 2584 | 7109 | HPJSM, BEFORE PICKING UP TLC BHA. DISCUSS THE PROCEDURE. REVIEW THE JSA & OPERATIONAL ASPECT OF THE JOB. |  | TF | 7109 | 05/09/2022 | ADC-53L | NA | UTMN-4069
770 |  | 896300 | SWL | OTH | 2584 | 7109 | P/U & M/U TLC LOGGING TOOLS 3RD RUN (MDT-GR) & RIH TO 157 FT. - R/U WL SHEAVES- CHECK TLC TOOLS ON SURFACE, OK.- TOOL LENGTH: 157.48 FT. MAX TOOL OD: 5.284 INCHES.- MONITOR WELL ON TRIP TANK. |  | TF | 7109 | 05/09/2022 | ADC-53L | NA | UTMN-4069
771 | 4292 | 896300 | RIG | TI | 2584 | 7109 | RIH TLC 3RD RUN LOGGING TOOLS ON 4" DP F/ 157 FT TO LATCHING DEPTH @ 4,292 FT W/ CONTROL SPEED.- FILL UP STRING & BREAK CIRC. USING W/L SCREEN EVERY 10 STANDS.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- MONITOR WELL ON TRIP TANK - OK. | 157 | TF | 7109 | 05/09/2022 | ADC-53L | STDP | UTMN-4069
772 |  | 896300 | RIG | CIRC | 2584 | 7109 | CIRC 1.5 STRING VOLUME. MEANWHILE HELD PJSM FOR TLC LOGGING OPERATION. REVIEWED JSA & PTW.-FR: 300 GPM & P.P.: 450 PSI. OUT OF SCOPE DETAILS |  | TF | 7109 | 05/09/2022 | ADC-53L | MPMP | UTMN-4069
773 |  | 896300 | SWL | OTH | 2584 | 7109 | M/U SLB W/L CABLE S.E.S. & FEED THROUGH WIRE LINE CABLE.- MONITORED WELL ON TRIP TANK, WELL STATIC. |  | TF | 7109 | 05/09/2022 | ADC-53L | NA | UTMN-4069
774 |  | 896300 | SWL | OTH | 2584 | 7109 | RIH W/ WIRE LINE CABLE, LATCH INTO CONNECTOR AS PER MDT ENGINEER INSTRUCTION... INCT @ RT.- APPLY 150 PSI PUMP PRESS TO ASSIST IN LATCHING PROCESS AS PER SLB MDT ENG.- MONITORED WELL ON TRIP TANK, WELL STATIC. |  | TF | 7109 | 05/09/2022 | ADC-53L | NA | UTMN-4069
775 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-53L | Hrs | UTMN-4069
776 | FOT | SWL | 54 | 07 May 2300 - 0500 | 6869 | 896300 | LOST COMMUNICATION WITH WL DH TOOLS WHILE SAMPLING OPERATION, DUE TO FAILURE IN CABLE HEAD AND WET CONNECTOR TELEMETRY/POWER UNIT. | TF | WLT |  | 05/09/2022 | ADC-53L | 24 | UTMN-4069
777 | 137 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/09/2022 | ADC-53L | Type | UTMN-4069
778
779
780 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-56L | Hrs | UTMN-2330
781 | FOT | TSC | 1.5 | 09 May 0500 - 0630 | 14193 | 896397 | WHILE MAKING JOINT POWER TONG HYDRAULIC COUPLING START LEAKING. | TF | CTRQ |  | 05/09/2022 | ADC-56L | 1.5 | UTMN-2330
782 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-60 | Hrs | ABSF-218
783 | FOT | ALC | 54.5 | 06 May 0300 - 0500 | 718 | 896284 | BAKER ESP CREW CHECK THE CABLE INTEGRITY, FOUND THE CABLE LOST INTEGRITY. | TF | ESPL |  | 05/09/2022 | ADC-60 | 24 | ABSF-218
784 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-62L | Hrs | ANDR-745
785 | FOT | BHI | 9 | 09 May 1215 - 2115 | 7406 | 896406 | BHI REQUEST A NEW LOG (POOR QUALITY PREVIOUSLY LOG).NEED RE-LOG AGAIN INTERVAL F/7,110 FT TO 7,406 FT AND 6660 FT TO 6703 FT. | TF | COMP |  | 05/09/2022 | ADC-62L | 9 | ANDR-745
786 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADC-65L | Hrs | HWYH-1280
787 | HERR | RIG | 27.75 | 08 May 1445 - 1930 | 3050 | 896273 | DURING N/U OF SPACER SPOOL, ONE 3-1/8" OD NUT SLIPPED FROM BOLT INTO THE WELL. | FISH | STRG |  | 05/09/2022 | ADC-65L | 13.5 | HWYH-1280
788 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ADM-655 | Hrs | SFNY-1095
789 | WTHR | ARM | 63.5 | 07 May 1330 - 0500 | 0 | 896302 | WAIT ON WEATHER TO IMPROVE TO MOVE THE RIG SFNY 1090/1099 PF. | WON | NA |  | 05/09/2022 | ADM-655 | 24 | SFNY-1095
790 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | AOD-1 | Hrs | ZULF-694
791 | FOT | RIG | 13.5 | 08 May 2230 - 1200 | 1516 | 896319 | GWD TOOL, POOR DECODING & INTERMITTENT PULSING, TROUBLE SHOOT SCEINTIFIC GWD. | BHA | DC |  | 05/09/2022 | AOD-1 | 7 | ZULF-694
792 | FOT | SJT | 2.5 | 09 May 0000 - 0230 | 0 | 896377 | SANJEL ACID PUMP WOULD NOT START AFTER ARRIVING AT RIG | TF | CTPMP |  | 05/09/2022 | ARO-2001 | 2.5 | BRRI-91
793 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ARO-2001 | Hrs | BRRI-91
794 | WTHR | ARM | 2.75 | 09 May 1945 - 2230 | 0 | 896315 | HIGH WINDS DIDNT ALLOW FOR ACID TANK AND PUMP TO BE UNLOADED FROM VESSEL | WON | NA |  | 05/09/2022 | ARO-2001 | 2.75 | BRRI-91
795 | FOT | SJT | 2.5 | 09 May 0000 - 0230 | 0 | 896377 | SANJEL ACID PUMP WOULD NOT START AFTER ARRIVING AT RIG | TF | CTPMP |  | 05/09/2022 | ARO-2001 | 2.5 | BRRI-91
796 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ARO-2003 | Hrs | ZULF-10
797 | WTHR | ARN | 14.75 | 09 May 1415 - 0500 | 0 | 896308 | WAIT ON WEATHER. ( ALL CHOPPERS CANCELLED SINCE LAST FRIDAY). | WON | NA |  | 05/09/2022 | ARO-2003 | 14.75 | ZULF-10
798 | FOT | RIG | 1 | 09 May 2300 - 0000 | 1980 | 896398 | ARO LT; LINK/TILT NOT FUNCTIONING OBSERVED (AIR DUMP VALVE OF TDS LINK/TILT CONTROLS REPLACED SAME) | RR | TDS |  | 05/09/2022 | ARO-3004 | 1 | MRJN-2060
799 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ARO-3004 | Hrs | MRJN-2060
800 | XTTE | WCR | 2 | 09 May 0000 - 0200 | 1980 | 896311 | WFRD CRS LT; TROUBLE-SHOT & CORRECT WFRD CRT | TF | CRT |  | 05/09/2022 | ARO-3004 | 2 | MRJN-2060
801 | FOT | RIG | 1 | 09 May 2300 - 0000 | 1980 | 896398 | ARO LT; LINK/TILT NOT FUNCTIONING OBSERVED (AIR DUMP VALVE OF TDS LINK/TILT CONTROLS REPLACED SAME) | RR | TDS |  | 05/09/2022 | ARO-3004 | 1 | MRJN-2060
802 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | CG-1 | Hrs | ZULF-1207
803 | FOT | RIG | 3.5 | 09 May 0130 - 0500 | 7220 | 896402 | PIPE GRABER ON TDS FAILED TO FUNCTION. | RR | TDS |  | 05/09/2022 | CG-1 | 3.5 | ZULF-1207
804 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | DPS-4 | Hrs | MDRK-54
805 | STBH | ARM | 116.25 | 04 May 1900 - 0500 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. CONSEQUENCE LOST TIME TO LT ID:895515 | STUK | BHA | 895547 | 05/09/2022 | DPS-4 | 23.5 | MDRK-54
806 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | DPS-46 | Hrs | SDGM-1106
807 | FOT | CRW | 36.75 | 08 May 1615 - 0500 | 12595 | 896318 | AFTER COMPLETING NEG. TEST, HAD DIFFICULTY TO RELEASE CORETRAX PKR & OPEN CIRC VALVE, ATTEMPTED TO CIRC W/ NO SUCCESS. | BHA | WBCL |  | 05/09/2022 | DPS-46 | 24 | SDGM-1106
808 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | DPS-74 | Hrs | NJYN-54
809 | FOT | BLH | 617 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/09/2022 | DPS-74 | 24 | NJYN-54
810 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | DQ-47 | Hrs | KHRS-1416
811 | TCPD | TK2 | 2.5 | 09 May 0000 - 0230 | 4738 | 896404 | RIH W/ CMT STINGER TO 4738' WITHOUT TAG ON TOC, POOH & CONT. WOC MORE THAN THICKENING TIME PERIOD. | CMT | NA |  | 05/09/2022 | DQ-47 | 2.5 | KHRS-1416
812 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | ED-85A | Hrs | ZULF-2062
813 | LHFL | RIG | 6.5 | 09 May 2230 - 0500 | 5394 | 896407 | ATTEMPT TO DRAW DOWN TEST, NOTICE A LEAK IN WEEP HOLE ON ANNULAR PREVENTER | BOP | RWCS |  | 05/09/2022 | ED-85A | 6.5 | ZULF-2062
814 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | NBR-115S | Hrs | HWYH-1220
815 | UNKN | RIG | 2 | 09 May 1230 - 1430 | 5878 | 896396 | PINCH FINGER INCIDENT WHILE P/U 8 1/2" DC'S | HSEI | NA |  | 05/09/2022 | NBR-115S | 2 | HWYH-1220
816 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | NBR-783S | Hrs | NJYN-89
817 | XTTE | MSD | 1 | 09 May 1200 - 1300 | 0 | 896310 | EXXESSIVE TIME TO FIX & CALIBRATE AL-MASAOOD POWER TONG AND JAM UNIT. | TF | TTRQ |  | 05/09/2022 | NBR-783S | 1 | NJYN-89
818 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | PA-866S | Hrs | SHHB-2
819 | FOT | RIG | 36.5 | 08 May 1630 - 0500 | 6982 | 896213 | LEAK ON MUD PUMP GROUND MANIFOLD - ISOLATION VALVE LEAK. | RR | CHK |  | 05/09/2022 | PA-866S | 24 | SHHB-2
820 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | RBP-50A | Hrs | KARN-46
821 | FOT | HTS | 2.75 | 09 May 2215 - 0100 | 11911 | 896314 | HALLIBURTON WELL TEST CONNECTION AND LOW TORQUE VALVES LEAKING. REPAIR AND CHANGE SAME. | TF | WTSE |  | 05/09/2022 | RBP-50A | 2.75 | KARN-46
822 |  |  | BCT | STIM | 2545 | 17315 | CONT POOH W/ 2-3/8" CT F/ 5000' TO SURFACE WHILE PUMPING 66 PCF VISCOUS BRINE AT MINIMUM RATE 0.25 BPM.-CLOSE GATE VALVE & FLUSH CTU W/ FRESH WATER.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. |  |  | 17315 | 05/09/2022 | SIN30L | CTU | KHRS-1409
823 |  |  | BCT | STIM | 2545 | 17315 | HPJSM. DISCONNECT & R/D BKR CT INJECTOR HEAD, QUAD BOP, RISER AND ALL RELATED LINES & ISO-GATE VALVE WITH ADAPTOR FLANGE. - L/D CT BHA.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. |  |  | 17315 | 05/09/2022 | SIN30L | CTU | KHRS-1409
824 |  |  | RIG | NU | 2545 | 17315 | HPJSM. N/U BELL NIPPLE, FLOW LINE & R/U 5" DP HANDLING TOOLS.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. |  |  | 17315 | 05/09/2022 | SIN30L | BNIP | KHRS-1409
825 |  |  | RIG | SET |  | 17315 | HPJSM, INSTALL 11" CIW WEAR BUSHING.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. |  |  | 17315 | 05/09/2022 | SIN30L | WBSH | KHRS-1409
826 |  | 896403 | RIG | HT |  | 17315 | M/U BKR FLOAT SUB, MWD, FILTER SUB & WIS HI-FLOW VALVE. RIH 3 X STDS 5" DP FOR MWD SHALLOW TEST.WHILE TRYING TO TEST MWD TOOL, HI-FLOW VALVE CLOSED, POOH TO SURFACE, LD SAME. |  | TF | 17315 | 05/09/2022 | SIN30L | BHA | KHRS-1409
827 |  |  | RIG | HT |  | 17315 | M/U BKR FLOAT SUB, MWD, FILTER SUB & WIS HI-FLOW VALVE. RIH 5 X STDS 5" DP FOR MWD SHALLOW TEST.- SHALLOW TESTED MWD TOOLS W/ 280 GPM / 275 PSI, OK.-L/D MWD.- DYNAMIC LOSS RATE @ 280 GPM IS 110 BPH. (74% RETURN) |  |  | 17315 | 05/09/2022 | SIN30L | BHA | KHRS-1409
828 |  |  | RIG | HT |  | 17315 | HPJSM. P/U & M/U & RIH W/ WIS 9-5/8" L-3 WPS / MILLING ASSY T/ 375'.- CHECK MILLS GAUGES.- SCRIBE WPS HS WITH MWD HS.- P/U & M/U 4 X 9-5/8" MAGNETS WHILE RIH.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. |  |  | 17315 | 05/09/2022 | SIN30L | BHA | KHRS-1409
829 | 7500 |  | RIG | TI |  | 17315 | RIH W/WIS L-3 WPS AT CONTROLLED SPEED (3MIN/SLIP TO SLIP) F/375' TO 7500'.(SETTING DEPTH 9,414')- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM.- FILL STRING EVERY 5 STD'S W/HOSE. | 375 |  | 17315 | 05/09/2022 | SIN30L | STDP | KHRS-1409
830 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SIN30L | Hrs | KHRS-1409
831 | FOT | WI3 | 2 | 09 May 1345 - 1545 | 327 | 896403 | WHILE SHALLOW TESTING MWD TOOL, WIS HIGH FLOW VALVE CLOSED. | TF | WPSTK |  | 05/09/2022 | SIN30L | 2 | KHRS-1409
832 | 160.5 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 8.25 | 2545 | 01 May 1800 | 05/09/2022 | SIN30L | Type | KHRS-1409
833
834
835 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SINO-12L | Hrs | HRDH-1454
836 | HERR | TK1 | 27.5 | 08 May 0130 - 0500 | 7965 | 896274 | HAD LEAK DURING PRESSURE TEST CMT VALVE. | TF | CSG |  | 05/09/2022 | SINO-12L | 24 | HRDH-1454
837 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SINO-18 | Hrs | SRYN-14
838 | STBH | ARM | 41 | 08 May 1200 - 0500 | 840 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/09/2022 | SINO-18 | 24 | SRYN-14
839 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SND-2008 | Hrs | HRDH-1052
840 | WOTO | WDS | .5 | 09 May 0430 - 0500 | 0 | 896357 | WAIT ON WFD 6 3/4" MWD TOOL ARRIVAL | WO | NA |  | 05/09/2022 | SND-2008 | .5 | HRDH-1052
841 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SNF036 | Hrs | MRJN-901
842 | FOT | SWL | 10 | 09 May 0730 - 1730 | 9368 | 896356 | SCHLUMBERGER-WL LOST POWER ON MDT TOOLS DUE TO CABLE HEAD CONNECTOR FAILURE | TF | WLT |  | 05/09/2022 | SNF036 | 10 | MRJN-901
843 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SNT-025 | Hrs | SFNY-956
844 | WTHR | ARM | 25 | 08 May 1200 - 1300 | 4650 | 896295 | ALL CHOPPERS HAVE BEEN CANCELLED DUE TO BAD WEATHER. | WON | NA |  | 05/09/2022 | SNT-025 | 8 | SFNY-956
845 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SP-101 | Hrs | ABQQ-710
846 | FOT | WI1 | 296 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/09/2022 | SP-101 | 24 | ABQQ-710
847 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SP-160 | Hrs | HWTH-72
848 | FWTS | RIG | 176.25 | 02 May 1145 - 0500 | 8444 | 896181 | WHILE BACK REAM, STRING STALLED, LOST ROTATION AND CIRCULATION. ATTEMPT TO GET ROTATION WHILE JARING DOWN SUCCESSFULLY. REESTABLISH CIRCULATION GRADUALLY TO 90 GPM , DISPLACE HOLE TO 75 PCF OBM. KEEP STRING IN ROTATION. POOH, FOUND SHEARED OFF PIN BETWEEN THE TWO LAST 4" HWDP ABOVE DOG LEG REAMER. | FISH | BHA |  | 05/09/2022 | SP-160 | 23.5 | HWTH-72
849 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SP-262 | Hrs | HZEM-140802
850 | FOT | RIG | 1.25 | 09 May 1430 - 1545 | 1114 | 896399 | TOP DRIVE WOULD NOT BREAK OUT OF CONNECTION. | RR | TDS |  | 05/09/2022 | SP-262 | 1.25 | HZEM-140802
851 | ACDI | SDM | 36.5 | 07 May 1430 - 1100 | 14121 | 896301 | HAD PRESSURE DROP, LOST MWD SIGNAL AND UNABLE TO REGAIN SIGNAL TO THE TOOL. | DD | BHA |  | 05/09/2022 | SSA-201 | 5 | HRDH-1818
852 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SSA-201 | Hrs | HRDH-1818
853 | HINW | ARM | 487 | 17 Apr 1500 - 0500 | 14240 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/09/2022 | SSA-201 | 18 | HRDH-1818
854 | ACDI | SDM | 36.5 | 07 May 1430 - 1100 | 14121 | 896301 | HAD PRESSURE DROP, LOST MWD SIGNAL AND UNABLE TO REGAIN SIGNAL TO THE TOOL. | DD | BHA |  | 05/09/2022 | SSA-201 | 5 | HRDH-1818
855 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SSA-202 | Hrs | QTIF-500
856 | SFHS | ARM | 2 | 09 May 0130 - 0330 | 5520 | 896379 | DURING POOH 7" WEATHERFORD WHIPSTOCK HAD OBSTRUTION AT 5520' (TIE BACK DEPTH) . | STUK | FISHT |  | 05/09/2022 | SSA-202 | 2 | QTIF-500
857 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SSA-5891 | Hrs | HRDH-2016
858 | FOT | BLH | 115.75 | 04 May 0200 - 0500 | 15227 | 896202 | BAKER RUNNING TOOL FAILED TO RELEASE OFF PBR. | TF | HGRL |  | 05/09/2022 | SSA-5891 | 24 | HRDH-2016
859 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | SSA-5974 | Hrs | HRDH-1970
860 | CWEL | ARM | 419.5 | 22 Apr 0500 - 0500 | 14140 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/09/2022 | SSA-5974 | 24 | HRDH-1970
861 | FOT | SDM | 4.75 | 09 May 0500 - 0500 | 11981 | 896381 | SLB LWD ECOSCOPE UNABLE TO SEND POROSITY READINGS. POOH & CHANGE THE SAME | BHA | LWD |  | 05/09/2022 | STY-038 | 4.75 | ZULF-2085
862 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | STY-038 | Hrs | ZULF-2085
863 | FOT | RIG | 4 | 09 May 0730 - 1130 | 11300 | 896380 | TDS WASH PIPE WAS LEAKING. POOH AND REPLACE THE SAME. | RR | TDS |  | 05/09/2022 | STY-038 | 4 | ZULF-2085
864 | FOT | SDM | 4.75 | 09 May 0500 - 0500 | 11981 | 896381 | SLB LWD ECOSCOPE UNABLE TO SEND POROSITY READINGS. POOH & CHANGE THE SAME | BHA | LWD |  | 05/09/2022 | STY-038 | 4.75 | ZULF-2085
865 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/09/2022 | T216 | Hrs | ANDR-95
866 | LRFL | GDF | 49 | 07 May 0000 - 0400 | 0 | 896299 | STRING PLUG WHILE ATTAMPT TO FILL UP & CIRC DUE TO CHEMICAL SETTLING | HC | NA |  | 05/09/2022 | T216 | 20 | ANDR-95
867 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | 095TE | Hrs | MNIF-220
868 | FOT | BHI | 55.25 | 07 May 0345 - 0500 | 9948 | 896294 | BHI TESTRAK TOOL FAILURE WHILE TAKING PRESSURE POINTS REQUESTED BY RDD, POOH AND P/U NEW BHI FPWD + MWD (GR) TOOLS WITH 8.5" REAMING ASSY. | BHA | LWD |  | 05/10/2022 | 095TE | 7.5 | MNIF-220
869 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ADC-21 | Hrs | MZLJ-155201
870 | PSSW | ARM | 179 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/10/2022 | ADC-21 | 24 | MZLJ-155201
871 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ADC-42L | Hrs | UTMN-2327
872 | AINC | SBT | 28 | 09 May 1200 - 1600 | 13392 | 896416 | OBSERVE POOR ROP & FLAT TORQUE. | LROP | BIT |  | 05/10/2022 | ADC-42L | 11 | UTMN-2327
873 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ADC-46L | Hrs | UTMN-3153
874 | CFFM | TK3 | 43.75 | 09 May 0815 - 0500 | 13570 | 896378 | RUN IN OPEN HOLE SLB WIRELINE LOGGING TO 13570 FT, OBSERVED HOLD UP, PICKED UP WITH NO OVER PULL MADE 2 FURTHER ATTEMPTS WITH DIFFERENT RUNNING SPEED - COULD NOT PASS. | BHS | NA |  | 05/10/2022 | ADC-46L | 23 | UTMN-3153
875 |  | 896300 | SWL | OTH | 2584 | 7109 | CONT'D RIH W/ WIRE LINE CABLE, LATCH INTO CONNECTOR AS PER MDT ENGINEER INSTRUCTION.- APPLY 150 PSI PUMP PRESS TO ASSIST IN LATCHING PROCESS AS PER SLB MDT ENG.- LATCH INTO WET CONNECTOR PROFILE, FUNCTION TEST SLB TOOLS, OK.- PERFORM PULL TENSION TEST TO 3,100 LBS, OK.- MONITORED WELL ON TRIP TANK, WELL STATIC. |  | TF | 7109 | 05/10/2022 | ADC-53L | NA | UTMN-4069
876 |  | 896300 | RIG | PJSM | 2584 | 7109 | HELD PRE JOB SAFETY MEETING DISCUSSED RUNNING PRECAUTIONS, WELL CONTROL & STICKY TEST PROCEDURES. |  | TF | 7109 | 05/10/2022 | ADC-53L | NA | UTMN-4069
877 | 6820 | 896300 | RIG | ST | 2584 | 7109 | RIH TLC MDT LOGGING TOOLS ON 4" DP FROM 4,292 FT TO 3RD SAMPLE POINT DEPTH @ 6,820 FT W/ CONTROL SPEED. - FILL UP STRING & BREAK CIRC. EVERY 10 STANDS. CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 4292 | TF | 7109 | 05/10/2022 | ADC-53L | STDP | UTMN-4069
878 |  |  | SWL | OTH | 2584 | 7109 | PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE. |  |  | 7109 | 05/10/2022 | ADC-53L | NA | UTMN-4069
879 | 3820 |  | SWL | LOG | 2584 | 7109 | SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 3/12 AT 6,820 FT, (ARAB-D RESERVOIR FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH PROBE AT 6,820 FT.- COLLECTED SAMPLE IN 4 SESSIONS.- MAX. STATIONARY TIME IS 04 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 3/12.- PUMP OUT COMPLETED: 3/12.- PUMP OUT INTO WELLBORE 2.54 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 2.54 BBLS, (FLUID TYPE: WATER).- HYDROSTATIC DROP= 2 PSI, OVERBALANCE, AS PER SLB MDT 938 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 6820 |  | 7109 | 05/10/2022 | ADC-53L | WLT | UTMN-4069
880 | 6810 |  | SWL | LOG | 2584 | 7109 | SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 4/12 AT 6,810 FT, (ARAB-D RESERVOIR FM). ON GOING AT REPORT TIME.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH PROBE AT 6,810 FT.- MONITORED WELL ON TRIP TANK, WELL STATIC.** TIME SINCE LAST CIRCULATION = 44.75 HOURS. | 6810 |  | 7109 | 05/10/2022 | ADC-53L | WLT | UTMN-4069
881 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ADC-53L | Hrs | UTMN-4069
882 | FOT | SWL | 57.25 | 07 May 2300 - 0815 | 6869 | 896300 | LOST COMMUNICATION WITH WL DH TOOLS WHILE SAMPLING OPERATION, DUE TO FAILURE IN CABLE HEAD AND WET CONNECTOR TELEMETRY/POWER UNIT. | TF | WLT |  | 05/10/2022 | ADC-53L | 3.25 | UTMN-4069
883 | 161 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/10/2022 | ADC-53L | Type | UTMN-4069
884
885
886 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ADC-55L | Hrs | UTMN-3199
887 | FOT | TK3 | 48 | 09 May 0500 - 0500 | 13620 | 896359 | UNABLE TO DRILL OUT LC WITH 3 5/8" PDC BIT | TF | LINR |  | 05/10/2022 | ADC-55L | 24 | UTMN-3199
888 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ADC-60 | Hrs | ABSF-218
889 | FOT | ALC | 78.5 | 06 May 0300 - 0500 | 718 | 896284 | BAKER ESP CREW CHECK THE CABLE INTEGRITY, FOUND THE CABLE LOST INTEGRITY. | TF | ESPL |  | 05/10/2022 | ADC-60 | 24 | ABSF-218
890 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ADM-261 | Hrs | MRJN-138
891 | MATL | RMD | 12 | 10 May 1700 - 0500 | 0 | 896410 | UNPLANNED CHANGE OF PROGRAM, MOBILIZE & SHIP REQUIRED CHEMICALS FOR RESERVOIR STIMULATION OPERATIONS. | WO | NA |  | 05/10/2022 | ADM-261 | 12 | MRJN-138
892 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | AOD-11 | Hrs | SFNY-4280
893 | FOT | SDM | .25 | 10 May 0445 - 0500 | 4218 | 896389 | SCHLUMBERGER RE-LOG LAST 100 FT DRILLED DUE TO SIGNAL MISSING WHILE DRILLING. | BHA | MWD |  | 05/10/2022 | AOD-11 | .25 | SFNY-4280
894 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ARO-3003 | Hrs | SFNY-1740
895 | FOT | SPS | 2.5 | 10 May 0730 - 1000 | 0 | 896419 | OBSERVED EXCESSIVE TORQUE WHILE BREAK-OUT & BACK-OFF LWD F/ MWD. NOTED GALLED THREADS (VERY DAMAGED). L/D LWD. | BHA | MWD |  | 05/10/2022 | ARO-3003 | 2.5 | SFNY-1740
896 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ARO-3004 | Hrs | MRJN-2060
897 | FOT | WCR | 1.5 | 10 May 0830 - 1000 | 3720 | 896436 | WFRD CRS LT: DROPPED PIN FR/ SINGLE JOINTS; PULL FMS AND FIND STRIPPED STUD AND BOLT (MISSING SAFETY PIN) ON THE MAIN CARRIER OF THE SLIP BODIES - REPLACE FMS W/ 500T SPIDE SLIPS | TF | CTRQ |  | 05/10/2022 | ARO-3004 | 1.5 | MRJN-2060
898 | FOT | SDM | 1.5 | 10 May 0330 - 0500 | 14767 | 896420 | SLB MUD MOTOR FAILURE. | BHA | MMOT |  | 05/10/2022 | DPS-4 | 1.5 | MDRK-54
899 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | DPS-4 | Hrs | MDRK-54
900 | STBH | ARM | 138.25 | 04 May 1900 - 0330 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. CONSEQUENCE LOST TIME TO LT ID:895515 | STUK | BHA | 895547 | 05/10/2022 | DPS-4 | 22 | MDRK-54
901 | FOT | SDM | 1.5 | 10 May 0330 - 0500 | 14767 | 896420 | SLB MUD MOTOR FAILURE. | BHA | MMOT |  | 05/10/2022 | DPS-4 | 1.5 | MDRK-54
902 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | DPS-46 | Hrs | SDGM-1106
903 | FOT | CRW | 43.75 | 08 May 1615 - 1200 | 12595 | 896318 | AFTER COMPLETING NEG. TEST, HAD DIFFICULTY TO RELEASE CORETRAX PKR & OPEN CIRC VALVE, ATTEMPTED TO CIRC W/ NO SUCCESS. | BHA | WBCL |  | 05/10/2022 | DPS-46 | 7 | SDGM-1106
904 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | DPS-74 | Hrs | NJYN-54
905 | FOT | BLH | 641 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/10/2022 | DPS-74 | 24 | NJYN-54
906 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | ED-85A | Hrs | ZULF-2062
907 | LHFL | RIG | 21 | 09 May 2230 - 2115 | 5394 | 896407 | ATTEMPT TO DRAW DOWN TEST, NOTICE A LEAK IN WEEP HOLE ON ANNULAR PREVENTER | BOP | RWCS |  | 05/10/2022 | ED-85A | 14.5 | ZULF-2062
908 | FOT | BC | 5.5 | 10 May 1300 - 1830 | 5643 | 896438 | ATTEMPT TO RETRIEVE BAKER PBR BY OVERPULL W/5,10,20 KIPS AND TRANSMIT TOURQUE TO RELEASE THE QUICK DISCCONECT BY RIGHT HAND TURNS, AFTER 3-4 TURNS THE LATCH SLIPPED OUT FROM PBR. DECIDED TO RIH WITH 3-1/4" FBM WITH 2 X 2-3/8" DP PUP JTS (30 FT) INSIDE THE PBR AND CLEAN DEBRIS. | TF | PBR | 896412 | 05/10/2022 | HI-9 | 5.5 | QTIF-557
909 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | HI-9 | Hrs | QTIF-557
910 | FOT | BC | 14.5 | 10 May 0700 - 2130 | 5643 | 896412 | OBSERVE BAKER PBR RETRIEVING TOOL WITHOUT FISH, DECIDED TO RIH SECOND ATTEMPT TO RECOVER PBR ASSY. | TF | PBR |  | 05/10/2022 | HI-9 | 9 | QTIF-557
911 | FOT | BC | 5.5 | 10 May 1300 - 1830 | 5643 | 896438 | ATTEMPT TO RETRIEVE BAKER PBR BY OVERPULL W/5,10,20 KIPS AND TRANSMIT TOURQUE TO RELEASE THE QUICK DISCCONECT BY RIGHT HAND TURNS, AFTER 3-4 TURNS THE LATCH SLIPPED OUT FROM PBR. DECIDED TO RIH WITH 3-1/4" FBM WITH 2 X 2-3/8" DP PUP JTS (30 FT) INSIDE THE PBR AND CLEAN DEBRIS. | TF | PBR | 896412 | 05/10/2022 | HI-9 | 5.5 | QTIF-557
912 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | NBR-304S | Hrs | HRDH-1952
913 | FOT | RIG | 1.5 | 10 May 1000 - 1130 | 16515 | 896411 | WASH PIPE PACKING LEAKING | RR | TDS |  | 05/10/2022 | NBR-304S | 1.5 | HRDH-1952
914 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | PA-866S | Hrs | SHHB-2
915 | FOT | RIG | 38 | 08 May 1630 - 0630 | 6982 | 896213 | LEAK ON MUD PUMP GROUND MANIFOLD - ISOLATION VALVE LEAK. | RR | CHK |  | 05/10/2022 | PA-866S | 1.5 | SHHB-2
916 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SINO-12L | Hrs | HRDH-1454
917 | FOT | TOD | 50.75 | 08 May 0215 - 0500 | 7965 | 896274 | HAD LEAK DURING PRESSURE TEST CMT VALVE. | TF | DV |  | 05/10/2022 | SINO-12L | 24 | HRDH-1454
918 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SINO-18 | Hrs | SRYN-14
919 | STBH | ARM | 65 | 08 May 1200 - 0500 | 840 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/10/2022 | SINO-18 | 24 | SRYN-14
920 | 9737 |  | CIRC | N |  | MPMP | SPOT 40 BBL INHIBITED BRINE ( 152 SEC ) ON TOP OF FAST DRILL-CR , FLOW CHECK-WELL STATIC . | 9737 |  | RIG | 05/10/2022 | SINO-42L | PA | HWYH-485
921 | 9737 |  | OTH | N |  | NA | R/D CEMENT SURFACE LINES & CIRC HEAD . | 9737 |  | RIG | 05/10/2022 | SINO-42L | PA | HWYH-485
922 | 9737 | 3000 | ST | N |  | STDP | POOH W/ FAST DRILL STINGER ON 4" DP TO 3000' .>> MONITOR WELL ON TRIP TANK - WELL STATIC . | 9737 | 4590 | RIG | 05/10/2022 | SINO-42L | PA | HWYH-485
923 | 9737 |  | OTH | N |  | NA | HPJSM , M/U & RIH W/ HCO 9-5/8" RTTS PKR W/ STORM VALVE ON 4" DP , SET 9-5/8" RTTS @ 208' , RELEASE SETTING TOOL , POOH & L/D RTTS SETTING TOOL , CLOSE BSR & P/T SAME TO 1000 PSI-OK . | 9737 |  | HCO | 05/10/2022 | SINO-42L | WH | HWYH-485
924 | 9737 |  | OTH | N |  | BOP | HPJSM , DISCONNECT EMERGENCY KILL LINES , HANG UP & SECURE BOP STACK . | 9737 |  | RIG | 05/10/2022 | SINO-42L | BOP | HWYH-485
925 | 9737 |  | OTH | N |  | NA | HPJSM ,CHECK WH & CSG INTEGRITY :>> ISSUE REQUIRED PTW & DISCUSSED JSA .>> CHECK 9" X 13" CCA IS ZERO PRESSURE .>> P/T 9" X 13" CCA TO 500 PSI W/INHIBITED WATER- HOLD .>> P/T 9-5/8'' CSG SEALS AND SLIPS TO 1000 PSI -OK .>> DIG CELLAR 6 FT BELOW LANDING BASE..>>MANSOORI PERFORM UT INSPECTION FOR LANDING BASE ( GOOD CONDITION ) ,18-5/8" CSG , 87.5# ( SEAL WELDED TO DONUT PLATE ) , RECORD 1.8 % MAX ML ( GOOD CONDITION ). | 9737 |  | RIG | 05/10/2022 | SINO-42L | WH | HWYH-485
926 | 9737 |  | OTH | N | 2644 | NA | ( OOSS) HPJSM , WELD 1-1/2" NIPPLE ON 18-5/8" CSG , MANSOORI PERFORM MPI FOR WELDINGS , WILD WELL R/U & P/T MPHT FOR 500 PSI / 1200 PSI- OK , WILD WELL PERFORM HOT TAPPING ON 18-5/8" CSG , NO PRESSURE OR GAS ON 18-5/8" X 13-3/8" CCA , R/D MPHT . | 9737 |  | WWC | 05/10/2022 | SINO-42L | WH | HWYH-485
927 | 9737 |  | OTH | N |  | NA | HOTHED CUT WINDOW ON 18-5/8" CSG , ALMANSOORI PERFORM UT INSPECTION ON 13-3/8" CSG , RECORD 0.698 % MAX ML ( GOOD CONDITION ) , BACK FILL 18-5/8" X 13-3/8" CCA W/ CMT , HOT HEAD WELD BACK WINDOW , MANSOORI PERFORM MPI FOR WELDINGS-OK , BACK FILL CELLAR W/ SWEET SAND . | 9737 |  | HTD | 05/10/2022 | SINO-42L | WH | HWYH-485
928 | 9737 |  | NU | N |  | BOP | HPJSM , N/U CLASS "A" 13-5/8" 5M BOPE & RELATED EQUIPMENT . | 9737 |  | RIG | 05/10/2022 | SINO-42L | BOP | HWYH-485
929 | 9737 |  | BOPT | N |  | BOP | HPJSM , F/T BOPE , M/U 9-5/8" CUP TESTER ASSY, P/T THS GATE VALVES , BOP CONNECTIONS , E-KILL LINE TO 300/ 2550 PSI-OK , L/D TEST ASSY . | 9737 |  | RIG | 05/10/2022 | SINO-42L | BOP | HWYH-485
930 | 9737 |  | OTH | N |  | NA | HPJSM , RIH & RETRIEVE 9-5/8" RTTS . | 9737 |  | HCO | 05/10/2022 | SINO-42L | WH | HWYH-485
931 | 9737 | 0 | TO | N |  | STDP | POOH W/ FAST DRILL STINGER ON 4" DP TO SURFACE , L/D 7" FAST DRILL STINGER .>> MONITOR WELL ON TRIP TANK , STATIC . | 9737 | 3000 | RIG | 05/10/2022 | SINO-42L | PA | HWYH-485
932 | 9737 |  | HT | N |  | BHA | HPJSM , M/U & RIH W/ WFD 7'' WHIPSTOCK & MILLING BHA .>> 7" WHIPSTOCK BHA: 5-1/2" QC RHS WHIPSTOCK ( W/ PACKER ) + 6-1/8" LEAD MILL + 6-1/8" FLEX MILL + 3-1/2" HWDP + FLOAT SUB+ UBHO+ X/O .>> GAUGE LEAD & FLEX MILLS-OK .>> ALIGN UBHO W/WHIPSTOCK .>> ATTACH LEAD MILL TO WHIP FACE W/ 43 KLB SHEAR BOLT . | 9737 |  | RIG | 05/10/2022 | SINO-42L | TINL | HWYH-485
933 | 9737 |  | HT | N |  | STRG | RIH W/ 7" WFD WHIPSTOCK & MILLING BHA WHILE P/U 39 JTS HWDP FROM PIPE RACK TO 1242' .>> DRIFT 4" HWDP WHILE RIH .>> CONTROL RIH SPEED . >> BREAK CIRC EVERY 20 JTS . | 9737 |  | RIG | 05/10/2022 | SINO-42L | TINL | HWYH-485
934 | 3 | OOSS | Category | DOOS ID | HTAP | Out of Scope Summary | WILD WELL PERFORM HOT TAPPING ON 18-5/8" CSG . | 3 | 2644 | 10 May 1300 | 05/10/2022 | SINO-42L | Type | HWYH-485
935
936
937 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SND-2004 | Hrs | BRRI-1148
938 | FOT | RIG | 1.5 | 10 May 0730 - 0900 | 5800 | 896387 | DRAWWORKS BREAKING SYSTEM MALFUNCTION, TROUBLESHOOT AND FIX IT. | RR | DWKS |  | 05/10/2022 | SND-2004 | 1.5 | BRRI-1148
939 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SP-101 | Hrs | ABQQ-710
940 | FOT | WI1 | 320 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/10/2022 | SP-101 | 24 | ABQQ-710
941 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SP-120 | Hrs | MNIF-188
942 | FRFM | ARM | 23.5 | 10 May 0500 - 0500 | 6225 | 896360 | CURE LOSSES WITH LCM PILL AND CMT PLUG | LCIR | NA |  | 05/10/2022 | SP-120 | 23.5 | MNIF-188
943 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SP-160 | Hrs | HWTH-72
944 | FWTS | RIG | 193.25 | 02 May 1145 - 2230 | 8444 | 896181 | WHILE BACK REAM, STRING STALLED, LOST ROTATION AND CIRCULATION. ATTEMPT TO GET ROTATION WHILE JARING DOWN SUCCESSFULLY. REESTABLISH CIRCULATION GRADUALLY TO 90 GPM , DISPLACE HOLE TO 75 PCF OBM. KEEP STRING IN ROTATION. POOH, FOUND SHEARED OFF PIN BETWEEN THE TWO LAST 4" HWDP ABOVE DOG LEG REAMER. | FISH | BHA |  | 05/10/2022 | SP-160 | 17 | HWTH-72
945 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SP-261 | Hrs | HZEM-160204
946 | FOT | SDM | 15 | 10 May 1400 - 0500 | 10050 | 896390 | SLB MWD TOOLS STOPPED SENDING GAMA SIGNAL. | BHA | MWD |  | 05/10/2022 | SP-261 | 15 | HZEM-160204
947 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SSA-201 | Hrs | HRDH-1818
948 | HINW | ARM | 510.5 | 17 Apr 1500 - 0500 | 14240 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/10/2022 | SSA-201 | 23.5 | HRDH-1818
949 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SSA-5891 | Hrs | HRDH-2016
950 | FOT | BLH | 127.5 | 04 May 0200 - 1645 | 15227 | 896202 | BAKER RUNNING TOOL FAILED TO RELEASE OFF PBR. | TF | HGRL |  | 05/10/2022 | SSA-5891 | 11.75 | HRDH-2016
951 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | SSA-5974 | Hrs | HRDH-1970
952 | CWEL | ARM | 443.5 | 22 Apr 0500 - 0500 | 14140 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/10/2022 | SSA-5974 | 24 | HRDH-1970
953 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/10/2022 | STY-038 | Hrs | ZULF-2085
954 | FOT | SDM | 23.5 | 09 May 2230 - 2200 | 11981 | 896381 | SLB LWD ECOSCOPE UNABLE TO SEND POROSITY READINGS. POOH & CHANGE THE SAME | BHA | LWD |  | 05/10/2022 | STY-038 | 17 | ZULF-2085
955 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | 095TE | Hrs | MNIF-220
956 | FOT | BHI | 78.25 | 07 May 0345 - 0500 | 9948 | 896294 | BHI TESTRAK TOOL FAILURE WHILE TAKING PRESSURE POINTS REQUESTED BY RDD, POOH AND P/U NEW BHI FPWD + MWD (GR) TOOLS WITH 8.5" REAMING ASSY. | BHA | LWD |  | 05/11/2022 | 095TE | 23 | MNIF-220
957 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | ADC-21 | Hrs | MZLJ-155201
958 | PSSW | ARM | 203 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/11/2022 | ADC-21 | 24 | MZLJ-155201
959 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | ADC-34 | Hrs | UTMN-2316
960 | ULCM | ARM | 16 | 11 May 0500 - 2100 | 8005 | 896391 | AFTER CIRCULATING 13-3/8" ON BOTTOM WITH 100% RETURNS, PERFORMED SPACE OUT OPERATIONS, STAGE PUMP RATE SLOWLY 1 BPM TO 9 BPM 350 PSI, 100% CIRC FULL RETURN. SUDDENLY LOST RETURNS. NO RETURNS WHILE CIRC. MIX SLB SHIELD BOND LCM SPACER FOR CEMENT JOB. | LCIR | LCM |  | 05/11/2022 | ADC-34 | 16 | UTMN-2316
961 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | ADC-46L | Hrs | UTMN-3153
962 | CFFM | TK3 | 62.75 | 09 May 0815 - 0130 | 13570 | 896378 | RUN IN OPEN HOLE SLB WIRELINE LOGGING TO 13570 FT, OBSERVED HOLD UP, PICKED UP WITH NO OVER PULL MADE 2 FURTHER ATTEMPTS WITH DIFFERENT RUNNING SPEED - COULD NOT PASS. | BHS | NA |  | 05/11/2022 | ADC-46L | 19 | UTMN-3153
963 | 7109 | 6810 | LOG | E | 2584 | WLT | CONT'D SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 4/12 AT 6,810 FT, (ARAB-D RESERVOIR FM). ON GOING AT REPORT TIME.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH PROBE AT 6,810 FT.- COLLECTED SAMPLE IN 01 SESSION.- MAX. STATIONARY TIME IS 04 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 4/12.- PUMP OUT COMPLETED: 4/12.- PUMP OUT INTO WELLBORE 0.87 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 3.41 BBLS, (FLUID TYPE: WATER+ OIL).- HYDROSTATIC DROP= 3 PSI, OVERBALANCE, AS PER SLB MDT 937 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC.** TIME SINCE LAST CIRCULATION = 47.5 HOURS. | 7109 | 6810 | SWL | 05/11/2022 | ADC-53L | LOG | UTMN-4069
964 | 7109 |  | CIRC | E | 2584 | MPMP | RIH TO ONE STD BELOW 03RD POINT @ 6,880 FT & CIRC. HOLE CLEAN ONE COMPLETE CYCLE, 100% CIRC. MW IN/ OUT 80 PCF. PERCAUTIONARY CLOSE BOP AT FINAL 200 BBLS AND CONT. CIRC. THRU CHOCK. FLOW CHECK THRU CHOCK FOR 15 MIN- WELL STATIC.- OPENED BOP & PERFORM NORMAL FLOW CHECK- WELL STATIC. | 7109 |  | RIG | 05/11/2022 | ADC-53L | LOG | UTMN-4069
965 | 7109 | 6799 | LOG | E | 2584 | WLT | CONT'D SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 5/12 AT 6,799 FT, (ARAB-D RESERVOIR FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH LD PROBE AT 6,799 FT.- COLLECTED SAMPLE IN 2 SESSIONS.- MAX. STATIONARY TIME IS 04 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 5/12.- PUMP OUT COMPLETED: 5/12.- PUMP OUT INTO WELLBORE 1.58 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 1.58 BBLS, (FLUID TYPE: OIL).- HYDROSTATIC DROP= 3.54 PSI, OVERBALANCE, AS PER SLB MDT 949.7 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7109 | 6799 | SWL | 05/11/2022 | ADC-53L | LOG | UTMN-4069
966 | 7109 | 6780 | LOG | E | 2584 | WLT | CONT'D SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 6/12 AT 6,780 FT, (ARAB-D RESERVOIR FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH LD PROBE AT 6,780 FT.- COLLECTED SAMPLE IN 2 SESSIONS.- MAX. STATIONARY TIME IS 04 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 6/12.- PUMP OUT COMPLETED: 6/12.- PUMP OUT INTO WELLBORE 1.59 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 3.17 BBLS, (FLUID TYPE: OIL & WATER ).- HYDROSTATIC DROP= 5.54 PSI, OVERBALANCE, AS PER SLB MDT 941 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC.** TIME SINCE LAST CIRCULATION = 18 HOURS. | 7109 | 6780 | SWL | 05/11/2022 | ADC-53L | LOG | UTMN-4069
967 | 185 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/11/2022 | ADC-53L | Type | UTMN-4069
968
969
970 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | ADC-55L | Hrs | UTMN-3199
971 | FOT | TK3 | 53 | 09 May 0500 - 1000 | 13620 | 896359 | UNABLE TO DRILL OUT LC WITH 3 5/8" PDC BIT | TF | LINR |  | 05/11/2022 | ADC-55L | 5 | UTMN-3199
972 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | ADC-60 | Hrs | ABSF-218
973 | FOT | ALC | 84.5 | 06 May 0300 - 1100 | 718 | 896284 | BAKER ESP CREW CHECK THE CABLE INTEGRITY, FOUND THE CABLE LOST INTEGRITY. | TF | ESPL |  | 05/11/2022 | ADC-60 | 6 | ABSF-218
974 | 7406 |  | RR | E |  | DWKS | SLIP & CUT 100 FT OF DRILLING LINE. SECURED WELL WITH 5" FOSV, HANGED TRAVELLING BLOCK, CALIBERATED DEPTH SENSOR, RESET CHECK AND VERIFIED CROWN AND FLOOR SAVER DEVICES.- PUMPED 30 BBLS SLUG. | 7406 |  | RIG | 05/11/2022 | ADC-62L | CT | ANDR-745
975 | 7406 | 632 | TO | E | 2665 | STDP | (OOS): POOH 8-1/2" CONDITION BHA IN CH FROM 5,032 FT TO TOP BHA @ 632 FT.- FLOW CHECK ATA TOP BHA- WELL STATIC- MONITOR THE WELL WITH TRIP TANK. | 7406 | 5032 | RIG | 05/11/2022 | ADC-62L | CT | ANDR-745
976 | 7406 |  | HT | E | 2665 | BHA | (OOS): POOH & L/D 8-1/2" CONDITION BHA- L/D D.JAR (ARAMCO JAR), L/D 02 X 6-1/4'' DC + 01 NBSTB + 01 STR STB.- B/O & L/D BIT, BIT DULL GRADING: 1-1-WT-A-X-I-NO-LOG- MONITOR THE WELL WITH TRIP TANK. | 7406 |  | RIG | 05/11/2022 | ADC-62L | CT | ANDR-745
977 | 7406 |  | PJSM | E | 2684 | NA | (OOS): PJSM PRIOR TO TLC WIRELINE OPERATIONS.- DISCUSSED R/U, JOB PROCEDURE, TRIPPING SPEED & MAX S/O IF ANY OBSTRUCTION, MAX CIR RATE & PRESSURE.- HIGHLIGHTED WELL CONTROL ASPECTS. | 7406 |  | RIG | 05/11/2022 | ADC-62L | LOG | ANDR-745
978 | 7406 |  | OTH | E | 2684 | NA | (OOS): P/U, M/U & RIH SLB WIRELINE MDT TLC TOOL STRING TO 483 FT:- M/U MDT & GR TOOL.- PERFORMED SURFACE TESTS -OK.- MU 3-1/2" IF X XT39 + XT39 X 4-1/2" IF XO'S + 3 X 5'' HWDP STD.- ALL HWDP/ X-OVER DRIFTED TO 2.5''.- MONITORED WELL ON TRIP TANK | 7406 |  | SWL | 05/11/2022 | ADC-62L | LOG | ANDR-745
979 | 7406 |  | OTH | E | 2684 | NA | (OOS): RIH SLB MDT LOGGING TOOLS ON 5'' STD'S D.P'S CONTROLLED SPEED 3 MIN/STD TO 4,814 FT- FILL STRING EVERY 10 STDS & BREAK CIRC. FOR 5-10 MIN.- USE WL DP SCREEN TO FILL STRING.- ALL DP DRIFTED TO 2.5''.- MONITORED WELL ON TRIP TANK & TRIP SHEET.- NO DOWN HOLE LOSSES | 7406 |  | RIG | 05/11/2022 | ADC-62L | LOG | ANDR-745
980 | 7406 |  | CIRC | E | 2684 | MPMP | (OOS): CIRCULATE 1.5 STRING VOLUMES PRIOR TO P/U SIDE ENTRY SUB (SES) USING 84 PCF OBM MUD FOR W/L CABLE LATCH PURPOSE- FR = 250 GPM; SPP = 325 PSI.- MEANWHILE HPJSM, R/U SHEAVES. | 7406 |  | RIG | 05/11/2022 | ADC-62L | LOG | ANDR-745
981 | 7406 |  | OTH | E | 2684 | NA | (OOS): M/U WL CSES & FEED THROUGH WIRE LINE CABLE.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 |  | SWL | 05/11/2022 | ADC-62L | LOG | ANDR-745
982 | 7406 |  | OTH | E | 2684 | NA | (OOS): RIH CABLE HEAD WHILE PUMPING INSIDE STRING 170 GPM , PRESSURE 350 PSI & LATCH PWCH INTO DWCH.- LATCHED SUCCESSFULLY. RECEIVED GOOD COMMUNICATION WITH LOGGING TOOLS, INSTALLED CLAMP ON SES & PERFORMED TENSION TEST ON CLAMP. OK.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 |  | SWL | 05/11/2022 | ADC-62L | LOG | ANDR-745
983 | 7406 |  | PJSM | E | 2684 | NA | (OOS): HELD PJSM PRIOR TO RIH WL ON TLC IN OPEN HOLE.- DISCUSS RUNNING PROCEDURES IN OPEN HOLE. | 7406 |  | RIG | 05/11/2022 | ADC-62L | LOG | ANDR-745
984 | 7406 |  | OTH | E | 2684 | NA | (OOS): RIH SLB MDT LOGGING TOOLS ON 5" STD 5" D.P'S CONTROLLED SPEED 3 MIN/STD TO 5,610 FT.FILLED STRING EVERY 15 STANDS.- USED WL DP SCREEN TO FILL STRING- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 |  | RIG | 05/11/2022 | ADC-62L | LOG | ANDR-745
985 | 18.25 | OOS | HCRM | 2665 | LOG | RUN 8-1/2'' CONDITION BHA TO DISPLACE WELL TO 84 PCF OBM PRIORE MDT LOGGING OPERATION UNDER OOS AS PER DP | PERFORM PRESSURE POINTS AND SAMPLING UNDER OOS AS PER DP. | 18.25 | 2684 | 11 May 0300 | 05/11/2022 | ADC-62L | OOS | ANDR-745
986
987
988
989 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | ADM-339 | Hrs | RBYN-53
990 | WTHR | ARM | 2.75 | 11 May 1415 - 1700 | 11512 | 896456 | WIND SPEED DROP BELOW 2 KTS. SUSPEND FLARING OPERATIONS DUE TO NO WIND. WOW. | WON | NA |  | 05/11/2022 | ADM-339 | 2.75 | RBYN-53
991 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | AOD-11 | Hrs | SFNY-4280
992 | FOT | SDM | 4.75 | 10 May 0445 - 1245 | 4218 | 896389 | SCHLUMBERGER MWD HAD SIGNAL DEMODULATION ISSUE CAUSED BY ELECTRICAL NOISES LEAD TO POOR QUALITY OF SIGNAL DEMODULATION , TROUBLESHOOTING WITH DIFFERENT SURFACE PARAMETER. | BHA | MWD |  | 05/11/2022 | AOD-11 | 4.5 | SFNY-4280
993 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | ARO-3001 | Hrs | ZULF-2053
994 | HELD | ARM | 41.5 | 10 May 1130 - 0500 | 7524 | 896413 | 9 5/8" CSG GOT HELD OFF BTM | JF | CSG |  | 05/11/2022 | ARO-3001 | 24 | ZULF-2053
995 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | DPS-4 | Hrs | MDRK-54
996 | FOT | SDM | 25 | 10 May 0330 - 0500 | 14767 | 896420 | SLB MUD MOTOR FAILURE. | BHA | MMOT |  | 05/11/2022 | DPS-4 | 23.5 | MDRK-54
997 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | DPS-74 | Hrs | NJYN-54
998 | FOT | BLH | 663 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/11/2022 | DPS-74 | 22 | NJYN-54
999 | 7579 |  | HT | N |  | BHA | POOH TO SURFACE WHILE L/D 8 1/2" BAKER MRRS DIR ASSY.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- 8 1/2" BIT DULL: 1-1-WT-A-X-I-NO-TD. | 7579 |  | RIG | 05/11/2022 | DQ-48 | DRLG | KHRS-1420
1000 | 7579 |  | RTRV | N |  | WBSH | RETRIEVE 13 5/8" CIW WEAR BUSHING. | 7579 |  | RIG | 05/11/2022 | DQ-48 | WH | KHRS-1420
1001 | 7579 | 0 | LOG | E |  | WLT | HPJSM, R/U BKR E/L LOGGING EQUIPMENT, M/U BHI W/L LOGGING TOOLS RUN #1 [ HDIL-WGI-ZDL-CN-GR ] TO 111 FT.- TOTAL LOGGING TOOL LENGTH: 110.98' & MAX OD: 4.88".- FUNCTION TESTED LOGGING TOOLS STRING @ SURFACE.- PERFORM TOOL CALIBRATION @ SURFACE BEFORE RIH.- MONITOR HOLE ON TRIP TANK, STATIC.- LOADED RADIO ACTIVE SOURCE. | 7579 | 0 | BAW | 05/11/2022 | DQ-48 | LOG | KHRS-1420
1002 | 7579 | 7579 | LOG | E |  | WLT | RIH BHI E/L LOGGING TOOLS RUN# 1 (HDIL-WGI-ZDL-CN-GR) TO BTM AT 7579', POOH WHILE LOG UP F/ BTM TO 5100'. - RECORDED REPEAT LOG SECTION 200 FT [ F/ 7579' TO 7379' ], LOG GR FROM BTM @ 7579' TILL SURFACE.- LOG CN / NEUTRON, ZDL / DENSITY & HDIL / RESISTIVITY IN 8 1/2" HOLE FROM BTM TILL 5100'.- WGI WELL GEOMETERY / CALIPER ALL OPEN HOLE FROM BTM TILL 13 3/8" CSG SHOE @ 3485'.- HELD PJSM, RETRIEVE R/A SOURCE & L/D BAKER RUN #1 LOGGING TOOL.- AVERAGE HOLE SIZE 8 1/2" HOLE: 8.61", 12 1/4" HOLE: 12.47".- MAX STATIC TEMP: 166 DEGF. | 7579 | 0 | BAW | 05/11/2022 | DQ-48 | LOG | KHRS-1420
1003 | 7579 | 5900 | LOG | E | 2664 | WLT | HPJSM, P/U, M/U & RIH W/ BHI W/L RUN # 2 (MLL_MREX_GR_ADEX_JAR_MRCH) FREE TO BTM @ 7579', POOH WHILE LOGGING UP, START LOG UP 2ND INTERVAL FROM 5900'.> FUNCTION TESTED LOGGING TOOLS STRING @ SURFACE BEFORE RIH.> TOTAL LENGTH: 104.62' & MAX OD: 6.4".- MONITOR HOLE ON TRIP TANK, STATIC.> LOGGED UP AS FOLLOW:-- LOG UP 1ST INTERVAL MLL-MREX-ADEX-GR: MAIN PASS F/ 7579' T/ 7250', PP GAS ACQUISITION MODE.- POOH TO 2ND INTERVAL F/ 7250' TO 5900 FT.- START LOG 2ND MLL-MREX-ADEX-GR ZONE F/ 5900 TO 5500' PP GAS ACQUISITION MODE, IN PROGRESS @ RT. | 7579 | 7560 | BAW | 05/11/2022 | DQ-48 | LOG | KHRS-1420
1004 | 9.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 9.5 | 2664 | 11 May 1930 | 05/11/2022 | DQ-48 | Type | KHRS-1420
1005
1006
1007 | 473 |  | D | N |  | TDS | CONT. ROTARY DRILLING 28" VERTICAL HOLE FROM 430 FT TO 24" CSG PT @ 473 FT W/ 64 PCF SPUD MUD & 100% RETURN. - SWEPT HOLE W/ 30 BBL HVP EACH SINGLE DRILLED. | 430 |  | RIG | 05/11/2022 | DQ-50L | DRLG | HRDH-582
1008 | 473 |  | CIRC | N |  | MPMP | SWEEP HOLE W/ 100 BBLS 64 PCF HVP & CHC W/100% RETURN. | 473 |  | RIG | 05/11/2022 | DQ-50L | DRLG | HRDH-582
1009 | 473 | 473 | ST | N |  | STDP | PERFORM WIPER TRIP TO SURFACE & RIH BACK TO BTM, HOLE IN GOOD CONDITION.- KEEP HOLE FULL W/ 64 PCF SPUD MUD FROM BACKSIDE. | 473 | 473 | RIG | 05/11/2022 | DQ-50L | DRLG | HRDH-582
1010 | 473 |  | CIRC | N |  | MPMP | SWEEP HOLE W/ 100 BBL 64 PCF HVP & CHC, SPOT 150 BBL 64 PCF HVP ON BTM & DROP TOTCO. | 473 |  | RIG | 05/11/2022 | DQ-50L | DRLG | HRDH-582
1011 | 473 |  | HT | N |  | BHA | POOH W/ 28" DRLG BHA F/ 473 FT T/ SURFACE & L/D BHA. - HOLE IN GOOD CONDITION.- BIT DULL: 1-1-WT-A-E-I-NO-TD. | 473 |  | RIG | 05/11/2022 | DQ-50L | DRLG | HRDH-582
1012 | 473 |  | HT | N |  | PEL | HPJSM, R/D DP HANDLING EQUIP & R/U 24" BAKER CSG RUNNING EQUIPMENT.- CHANGE TDS BAILS TO LONG BAILS. | 473 |  | BCR | 05/11/2022 | DQ-50L | CSG | HRDH-582
1013 | 473 | 473 | RCSG | N |  | CTRQ | HPJSM, P/U & RIH W/ 24" CSG (176 #, X-42, RL-4S, FPE-EPC) TO BTM @ 473 FT.- P/U 24" STAB-IN SHOE W/ JV-LW/RL-4S X/O + 11 X 24" CSG JTS TOTAL.- TEST FLOAT - OK.- FILLING EVERY JT. | 473 | 0 | BCR | 05/11/2022 | DQ-50L | CSG | HRDH-582
1014 | 473 |  | CIRC | N |  | MPMP | CIRC.1.5 CSG VOLUME W/100 % RETURN. | 473 |  | RIG | 05/11/2022 | DQ-50L | CSG | HRDH-582
1015 | 473 |  | HT | N |  | PEL | R/D 24" CSG HANDLING TOOLS & R/U 5" DP HANDLING EQUIP. | 473 |  | RIG | 05/11/2022 | DQ-50L | CSG | HRDH-582
1016 | 473 |  | OTH | N |  | CSG | P/U & M/U 5" STAB-IN STINGER & RIH ON DRIFTED 5" DP STDS, STING INTO 24" STAB IN FLOAT SHOE.- FILL ANNULUS BETWEEN 5" DP & CSG W/ MUD TILL FULL & MUD LEVEL STABLE INSIDE 24" CSG.- CIRCULATE THROUGH CMT STINGER - FULL RETURN & LEVEL INSIDE 24" CSG STABLE. | 473 |  | TK2 | 05/11/2022 | DQ-50L | CSG | HRDH-582
1017 | 473 |  | CMC | N |  | CSG | HPJSM, R/U CMT LINES & P/T SAME T/3000 PSI, OK.>> PERFORM 24" CSG CMT JOB AS FOLLOW: - RIG PUMP 100 BBL FRESH WATER AS SPACER.- FLY MIX & PUMP 150 BBL 118 PCF CMT.- DROP DART PLUG, DISPLACE WITH 2 BBLS CMT + 8 BBL MUD.- BUMP PLUG WITH 600 PSI - BLEED OFF PRESSURE - OK.- CHECK FLOW - NO BACK FLOW.- APPLY 300 PSI AND STING OUT - CIRCULATE ONE STRING VOLUME.- LEVEL STATIC AT CELLAR & CIP : 16:30 HRS. | 473 |  | BCM | 05/11/2022 | DQ-50L | CSG | HRDH-582
1018 | 473 |  | WOC | N |  | CSG | WOC MEANWHILE:- FLUSH DP STRG & R/D CMT SURFACE LINE.- POOH W/ CMT STINGER TO SURFACE & L/D SAME.- CLEAN CELLAR AREA FROM CMT (CEMENT LEVEL STATIC).- CHANGE TDS LINKS.- P/U, M/U & RB 25 STD 4" DP. | 473 |  | RIG | 05/11/2022 | DQ-50L | CSG | HRDH-582
1019 | 473 |  | OTH | N |  | NA | HPJSM, ROUGH CUT & L/D 24" CUT OFF JOINT. | 473 |  | RIG | 05/11/2022 | DQ-50L | WH | HRDH-582
1020 | 473 |  | OTH | N | 2666 | NA | OOS - INSTALL & WELD 24" X 30" BASE FLANGE (1 K WELD NECK FLANGE).- WAIT ON WELD TO COOL DOWN.- SECURED 24" CSG WITH METAL SUPPORT. | 473 |  | RIG | 05/11/2022 | DQ-50L | WH | HRDH-582
1021 | 473 |  | NU | N | 2666 | DVRT | OOS - HPJSM, N/U 30" 1M MUD CROSS, 2 X 7-1/16" 2M HCR VALVES & 30" 1M DIVERTER.- N/U BELL NIPPLE, CONNECT FLOW LINE, KILL LINE & 8" VENT LINES. | 473 |  | RIG | 05/11/2022 | DQ-50L | BOP | HRDH-582
1022 | 473 |  | BOPT | N | 2666 | DVRT | OOS - FUNCTION TEST 30" DIVERTER & VENT LINES HCRS FROM ALL CONTROL UNITS...ONGOING @ RPT. | 473 |  | RIG | 05/11/2022 | DQ-50L | BOP | HRDH-582
1023 | 8 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | N/U 30" 1M DIVERTER. | 8 | 2666 | 11 May 0000 | 05/11/2022 | DQ-50L | Type | HRDH-582
1024
1025
1026 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | NA-393S | Hrs | HWYH-1138
1027 | ISEQ | WI1 | 13.75 | 11 May 1500 - 0445 | 11720 | 896461 | TRIED TO PASS WITH 5-7/8" MM DIR BHA THRU WIS WHIPSTOCK WINDOW. | BHA | FISHT |  | 05/11/2022 | NA-393S | 13.75 | HWYH-1138
1028 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | NBR-115S | Hrs | HWYH-1220
1029 | FOT | RIG | 2 | 11 May 0700 - 0900 | 6354 | 896415 | WHILE DRILLING AHEAD THE TOP DRIVE ROTATION WOULD STOP. | RR | TDS |  | 05/11/2022 | NBR-115S | 2 | HWYH-1220
1030 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | NBR-797S | Hrs | UTMN-3130
1031 | FOT | NRC | 1 | 11 May 2030 - 2130 | 7630 | 896458 | SPIDER SLIPS STUCK ON JOINT WHILE SPACE OUT. HPJSM. TRYING TO OPEN SLIPS WITHOUT SUCCESS, USED BACK-UP SLIPS, SECURED SLIPS WITH SECONDARY RETENTION AND L/D JOINT WITH SPIDER SLIPS ON. | TF | PEL |  | 05/11/2022 | NBR-797S | 1 | UTMN-3130
1032 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | NBR-987S | Hrs | UMKR-1
1033 | EDIS | RIG | 2.75 | 11 May 1445 - 1730 | 11595 | 896457 | TROUBLE SHOOT LINK TILT ON TDS. | RR | RSYS |  | 05/11/2022 | NBR-987S | 2.75 | UMKR-1
1034 | 9409 | 0 | LDP | N |  | BHA | CONT L/D MILLING BHA AT SURFACE.- 8 1/2" LEAD MILL: 1/8'' UNDER GAUGED.- 8 1/2" FOLLOW MILL: 1/16'' UNDER GAUGED.- 8 1/2" UPPER DRESS MILL: FULLY GAUGED.- RECOVERED 80 KG OF METAL JUNK FROM 4X STRING MAGNETS.- RECOVERED 15 KG OF METAL JUNK FROM 3X DITCH MAGNETS. | 9409 | 0 | RIG | 05/11/2022 | SIN30L | MILL | KHRS-1409
1035 | 9409 | 490 | TI | N |  | BHA | HPJSM. P/U, M/U & RIH 8 1/2" MRSS WITH MWD/ LWD BHA T/ 490'.- 8-1/2" RR PDC BIT: TD506X - SN 7913618, 6X14 NOZZLES.- 8-1/2" BHA: 8-1/2" PDC BIT, ATK, MMTR, MOD STAB, ONTRAK, MOD STAB, BCPM, ORD, CCN, STOP SUB, FLOAT SUB, FILTER SUB, 6-3/4" PBL, 6 X 5" HWDP, 8-7/16" DLR, 3 X 5" HWDP, 6-1/2" D.JAR, 2X 5" HWDP.- 6-3/4" ULTRA XL/RS MOTOR: 5/6 LOBE, 4.0 STAGE & 0.21 REV/GAL, FLOW RANGE 580-600- MWD FLOW RANGE: 360-600 GPM- SENSOR OFFSET (FROM BIT): NBI: 6.83', PRESS: 50.34', GR: 51.23', RESISETIVITY: 55.26', DIR: 61.07', DENSITY: 90.33', NEUTRON:99.37', CALIPER: 92.64'- PERFORM TOOL VERIFICATION, OK.- HPJSM & LOAD RADIOACTIVE SOURCE.- SHALLOW TEST @ 550 GPM & 1050 PSI, OK. | 9409 | 0 | RIG | 05/11/2022 | SIN30L | DRLG | KHRS-1409
1036 | 9409 | 7406 | TI | N | 2704 | STDP | P/U,M/U 5"DP FROM RACK(73 STD)WHILE RIH W/ 8.5" MRSS BHA F/490' T/7406'.- FILL STRING EVERY 20 STDS. | 9409 | 490 | RIG | 05/11/2022 | SIN30L | DRLG | KHRS-1409
1037 | 9409 | 9250 | TI | N |  | STDP | CONT RIH W/ 8-1/2" MRSS WITH MWD/LWD BHA F/7406' T/9250'.- FILL STRING EVERY 20 STDS. | 9409 | 7406 | RIG | 05/11/2022 | SIN30L | DRLG | KHRS-1409
1038 | 9409 | 9353 | CIRC | N |  | MPMP | SEND DOWN LINK & START RE- LOG F/ 9250' TO 9353' AS PER GOC INSTRUCTIONS. | 9409 | 9250 | RIG | 05/11/2022 | SIN30L | DRLG | KHRS-1409
1039 | 9409 | 9408 | TI | N |  | STDP | PASS THRU WINDOW SMOOTHLY W/OUT ROTATION NOR CIRC T/ 9408'. - AT 9408' SWEPT HOLE W/ 15/20 BBL LO-VIS/WT PILL AND CHC. | 9409 | 9353 | RIG | 05/11/2022 | SIN30L | DRLG | KHRS-1409
1040 | 17490 |  | DMR | N |  | HMRSS | DRILL IN SLIDING MODE 8 1/2" L-3 HOLE F/ 9409' T/ 9459' W/ 64 PCF OBM & 100% RETURN- SWEEP HOLE W/ 15/20 BBL LO-VIS/WT PILL.- PARAM: WOB: 5-30 KLB, FLOW RATE: 500 GPM, PRESS OFF/ON : 1640 / 1800 PSI.- PROJECTION TO BIT:9460' MD, 7273.43 TVD, 91DEG INC | 9409 |  | BHI | 05/11/2022 | SIN30L | DRLG | KHRS-1409
1041 | 9 | OOS | Category | DOOS ID | DRLG | Out of Scope Summary | P/U,M/U 5"DP FROM RACK(73 STD)WHILE RIH W/ 8.5" MRSS BHA F/490' T/7406'. - FILL STRING EVERY 20 STDS. | 9 | 2704 | 11 May 1100 | 05/11/2022 | SIN30L | Type | KHRS-1409
1042
1043
1044 | ITRP | RIG | 16 | 09 May 0715 - 1645 | 2503 | 896479 | EXECES TIME TO P/U & L/D 2-3/8" DP DUE TO BELLY BOARD NOT INSTALLED. | RR | DRRK |  | 05/11/2022 | SINO-12L | 6.25 | HRDH-1454
1045 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SINO-12L | Hrs | HRDH-1454
1046 | FOT | TOT | 58.75 | 08 May 0215 - 0500 | 7965 | 896274 | HAD LEAK DURING PRESSURE TEST CMT VALVE. | TF | LLAP |  | 05/11/2022 | SINO-12L | 17.75 | HRDH-1454
1047 | ITRP | RIG | 16 | 09 May 0715 - 1645 | 2503 | 896479 | EXECES TIME TO P/U & L/D 2-3/8" DP DUE TO BELLY BOARD NOT INSTALLED. | RR | DRRK |  | 05/11/2022 | SINO-12L | 6.25 | HRDH-1454
1048 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SINO-18 | Hrs | SRYN-14
1049 | STBH | ARM | 89 | 08 May 1200 - 0500 | 840 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/11/2022 | SINO-18 | 24 | SRYN-14
1050 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SINO-42L | Hrs | HWYH-485
1051 | FOT | WWD | 12 | 11 May 1200 - 0500 | 4564 | 896478 | UNABLE TO SET 7" WFD WHIPSTOCK . | TF | WPSTK |  | 05/11/2022 | SINO-42L | 12 | HWYH-485
1052 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SINO-47 | Hrs | HRDH-1957
1053 | FOT | RIG | 2 | 11 May 2000 - 2200 | 18234 | 896476 | TDS UPPER IBOP LEAK | RR | TDS |  | 05/11/2022 | SINO-47 | 2 | HRDH-1957
1054 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SL-7 | Hrs | ZULF-1332
1055 | FOT | SPS | 2 | 11 May 0530 - 0730 | 2238 | 896423 | EXCESS TIME SHALLOW TESTING MWD. | BHA | MWD |  | 05/11/2022 | SL-7 | 2 | ZULF-1332
1056 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SP-101 | Hrs | ABQQ-710
1057 | FOT | WI1 | 344 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/11/2022 | SP-101 | 24 | ABQQ-710
1058 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SP-120 | Hrs | MNIF-188
1059 | FRFM | ARM | 47.5 | 10 May 0500 - 0500 | 6225 | 896360 | CURE LOSSES WITH LCM PILL AND CMT PLUG | LCIR | NA |  | 05/11/2022 | SP-120 | 24 | MNIF-188
1060 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SP-124 | Hrs | FDHL-141
1061 | FOT | OSL | 6 | 11 May 2300 - 0500 | 7705 | 896460 | OILSERV SL PARTED WHILE ATTEMPTED TO PUNCH 3-1/2" TBG AT 7705' | TF | SLICK |  | 05/11/2022 | SP-124 | 6 | FDHL-141
1062 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SP-261 | Hrs | HZEM-160204
1063 | FOT | SDM | 26 | 10 May 1400 - 1600 | 5070 | 896390 | SLB MWD TOOLS STOPPED SENDING GAMA SIGNAL. | BHA | MWD |  | 05/11/2022 | SP-261 | 11 | HZEM-160204
1064 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SSA-201 | Hrs | HRDH-1818
1065 | HINW | ARM | 534 | 17 Apr 1500 - 0500 | 14240 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/11/2022 | SSA-201 | 23.5 | HRDH-1818
1066 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SSA-303 | Hrs | HRDH-2306
1067 | FOT | RIG | 13.75 | 11 May 1430 - 0415 | 5562 | 896422 | CHANGED SAVER SUB. WHILE CHANGING SAVER SUB GRAPPER HYD HARD LINE GOT BENT. | RR | TDS |  | 05/11/2022 | SSA-303 | 13.75 | HRDH-2306
1068 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | SSA-5974 | Hrs | HRDH-1970
1069 | CWEL | ARM | 445.25 | 22 Apr 0500 - 1900 | 14140 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/11/2022 | SSA-5974 | 1.75 | HRDH-1970
1070 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/11/2022 | V140A | Hrs | SFNY-1760
1071 | FOT | GEP | 11 | 11 May 1800 - 0500 | 156 | 896459 | AFTER CEMENTING 18 5/8" CASING AND CLEANING 18 5/8" MLC PORTS, ATTEMPTED TO CLOSE WITHOUT SUCCESS. MANY TRIALS VARYING PARAMETERS PORTS STUCK IN OPEN POSITION. | WH | WH |  | 05/11/2022 | V140A | 11 | SFNY-1760
1072 | HERR | MSD | 1 | 12 May 2030 - 2130 | 3525 | 896538 | AL MASAOOD OPERATOR CROSS THREAD CONNECTION WHILE MAKE UP CASING THREE TIMES. REPLACE ONE JOINT DUE TO DAMAGED THREAD ON PIN. | JF | CTRQ |  | 05/12/2022 | 095TE | 1 | MNIF-220
1073 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | 095TE | Hrs | MNIF-220
1074 | FOT | BHI | 84.25 | 07 May 0345 - 1100 | 9948 | 896294 | BHI TESTRAK TOOL FAILURE WHILE TAKING PRESSURE POINTS REQUESTED BY RDD, POOH AND P/U NEW BHI FPWD + MWD (GR) TOOLS WITH 8.5" REAMING ASSY. | BHA | LWD |  | 05/12/2022 | 095TE | 6 | MNIF-220
1075 | HERR | MSD | 1 | 12 May 2030 - 2130 | 3525 | 896538 | AL MASAOOD OPERATOR CROSS THREAD CONNECTION WHILE MAKE UP CASING THREE TIMES. REPLACE ONE JOINT DUE TO DAMAGED THREAD ON PIN. | JF | CTRQ |  | 05/12/2022 | 095TE | 1 | MNIF-220
1076 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | ADC-21 | Hrs | MZLJ-155201
1077 | PSSW | ARM | 227 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/12/2022 | ADC-21 | 24 | MZLJ-155201
1078 | 2386 |  | ND | N | 2705 | BNIP | N/D FLOW LINE. LIFTED BELL NIPPLE. DE-ATTACHED 30" DIVERTER FROM DRILLING SPOOL. LIFTED DIVERTER WITH BOP WINCHES. CENTERED 24" CSG TO 30" CONDUCTOR. ROUGH CUT AND L/D 24" LANDING JT EXCESS. | 2386 |  | RIG | 05/12/2022 | ADC-43L | BOP | UTMN-3118
1079 | 2386 |  | HT | N |  | PEL | R/D CRT (NABORS) & CASING RUNNING TOOLS. CLEARED RIG FLOOR | 2386 |  | TSC | 05/12/2022 | ADC-43L | CSG | UTMN-3118
1080 | 2386 |  | PJSM | N |  | DVRT | PERFORMED PSJM | 2386 |  | RIG | 05/12/2022 | ADC-43L | BOP | UTMN-3118
1081 | 2386 |  | ND | N | 2705 | DVRT | N/D 30" DIVERTER + 2 X 2 7/16" HCR SOV'S + 3 1/8" HCR TO KILL/FILL LINE + 10" VENT LINES. CUT 30" FLANGE FROM 30" CSG STUB.* OBSERVED CMT LEVEL DROP SEVERAL FEET AND THEN STATIC. | 2386 |  | RIG | 05/12/2022 | ADC-43L | BOP | UTMN-3118
1082 | 2386 |  | TOP | N |  | CSG | PERFORMED PSJM.* MEAHWHILE: PERFORMED TOP JOB (20 BBL) IN 24" X 30" CCA, WITH GOOD CMT AT SURFACE AND STATIC LEVEL. | 2386 |  | SCM | 05/12/2022 | ADC-43L | CSG | UTMN-3118
1083 | 2386 |  | NU | N |  | WH | FINAL CUT OF 36" & 30" CSG (144.00" BGL) & 24" CSG (127.75" BGL) AND DRESS (HOT-HED). REMOVED EXCESS AND CENTER BEAM.-* FINAL CUTS AS PER K2 WELL DESIGN & PROGRAM AND GE VETCO OPERATOR SUPERVISION. INSTALLED AND TAG WELDED BASE PLATES OVER 36" & 30" CSG STUBS. | 2386 |  | HTD | 05/12/2022 | ADC-43L | WH | UTMN-3118
1084 | 2386 |  | NU | N |  | WH | N/U WELLHEAD.- INSTALLED 24" X 26 3/4" 3M SLIP-ON-WELD CSG HEAD (SOW; GE-VETCO; S/N: DJ4739435; P/N: R640068-1) ON 24" CSG STUB. HEATED-UP WELLHEAD. PERFORMED FINAL WELDING ON 24" CSG STUB. P/T WELLHEAD WELDING (620 PSI X 10 MIN WITH N2: OK). WELDED VERTICAL SUPPORTS BETWEEN BASE PLATES. WAITED ON WELLHEAD TO COOL DOWN.- MEANWHILE: POSITIONED CHOKE MANIFOLD AND CONNECTED LINES. INSTALLED & P/T 2 X 3 1/8" 3M SIDE OUTLET VALVES ON CH (3000 PSI X 10 MIN EACH).-* CAMERON (S/N: 113083604-03; P/N: 141523-21-10-12 REV-03).* CAMERON (S/N: 121184220-12; P/N: 141523-21-13-10 REV-07). | 2386 |  | GEP | 05/12/2022 | ADC-43L | WH | UTMN-3118
1085 | 2386 |  | PJSM | N |  | BOP | PERFORMED PSJM. | 2386 |  | RIG | 05/12/2022 | ADC-43L | BOP | UTMN-3118
1086 | 2386 |  | NU | N |  | BOP | N/U 26 3/4" 3M BOP.- FLANGES & SPACER SPOOL + STACK + HYDRAULIC HOSES + LINES (MAIN KILL, CHOKE & SECONDARIES). CONNECTED BELL NIPPLE TO FLOW LINE, ON GOING. | 2386 |  | RIG | 05/12/2022 | ADC-43L | BOP | UTMN-3118
1087 | 8.75 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | INSTALLED DIVERTER FOR SHALLOW GAS PRECAUTIONS | 5.5 | 2705 | 06 May 0500 | 05/12/2022 | ADC-43L | Type | UTMN-3118
1088
1089
1090 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | ADC-51 | Hrs | SDGM-1245
1091 | HERR | RIG | 8.5 | 11 May 2230 - 0700 | 2713 | 896427 | OBSERVED HIGH CIRCULATING PRESSURE AFTER P/TEST CASING. | JF | BIT |  | 05/12/2022 | ADC-51 | 2 | SDGM-1245
1092 | 7109 | 6759 | LOG | E | 2584 | WLT | SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 7/12 AT 6,759 FT, (ARAB-D RESERVOIR FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH LD PROBE AT 6,759 FT.- COLLECTED SAMPLE IN 2 SESSIONS.- MAX. STATIONARY TIME IS 04 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 7/12.- PUMP OUT COMPLETED: 7/12.- PUMP OUT INTO WELLBORE 1.52 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 4.69 BBLS, (FLUID TYPE: WATER ).- HYDROSTATIC DROP= 6.54 PSI, OVERBALANCE, AS PER SLB MDT 937 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7109 | 6759 | SWL | 05/12/2022 | ADC-53L | LOG | UTMN-4069
1093 | 7109 | 6744 | LOG | E | 2584 | WLT | SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 8/12 AT 6,744 FT, (ARAB-D RESERVOIR FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH LD PROBE AT 6,744 FT.- COLLECTED SAMPLE IN 2 SESSIONS.- MAX. STATIONARY TIME IS 04 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: ARAB-D.- SAMPLES COMPLETED: 8/12.- PUMP OUT COMPLETED: 8/12.- PUMP OUT INTO WELLBORE 1.26 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 5.95 BBLS, (FLUID TYPE: OIL ).- HYDROSTATIC DROP= 8.54 PSI, OVERBALANCE, AS PER SLB MDT 935 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7109 | 6744 | SWL | 05/12/2022 | ADC-53L | LOG | UTMN-4069
1094 | 7109 |  | CIRC | E | 2584 | MPMP | RIH TO ONE STD BELOW 5TH POINT @ 6,820 FT & CIRC HOLE CLEAN ONE COMPLETE CYCLE AT 150 GPM WITH 290 PSI, 100% CIRC. MW IN/ OUT 80 PCF. PERCAUTIONARY CLOSE BOP AT FINAL 200 BBLS AND CONT. CIRC. THRU CHOCK. FLOW CHECK THRU CHOCK FOR 15 MIN- WELL STATIC.- OPENED BOP & PERFORM NORMAL FLOW CHECK- WELL STATIC. | 7109 |  | RIG | 05/12/2022 | ADC-53L | LOG | UTMN-4069
1095 | 7109 | 6733 | LOG | E | 2584 | WLT | CONT'D SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 9/12 AT 6,733 FT, (ARAB-D RESERVOIR FM)...ON GOING AT REPORT TIME.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH LD PROBE AT 6,733 FT.- MONITORED WELL ON TRIP TANK, WELL STATIC.** TIME SINCE LAST CIRCULATION = 4.75 HOURS. | 7109 | 6733 | SWL | 05/12/2022 | ADC-53L | LOG | UTMN-4069
1096 | 209 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/12/2022 | ADC-53L | Type | UTMN-4069
1097
1098
1099 | 7406 |  | OTH | E | 2684 | NA | (OOS): RIH SLB MDT LOGGING TOOLS ON 5" STD 5" D.P'S CONTROLLED SPEED 3 MIN/STD F/ 5,610 FT TO 6,850 FT.- FILLED STRING EVERY 15 STANDS.- USED WL DP SCREEN TO FILL STRING- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 |  | RIG | 05/12/2022 | ADC-62L | LOG | ANDR-745
1100 | 7406 | 7120 | LOG | E | 2684 | WLT | (OOS) RECORDED TOTAL 13 PRESSURE POINTS AS PER RDD REQUEST FROM 6,850 FT TO 7,120FT. - RECORDED 2 POINTS IN ARBC, 2 IN PADS, 1 IN ABD1, 5 IN AD2A, AND 3 IN AD2B.- MIN. OVERBALANCE RECORDED AT 6989' = 348 PSI IN ABD1.- MAX. OVERBALANCE RECORDED AT 6850' = 577 PSI IN ARBC.- PERFORM STICK TESTS 5,10 & 15 MINS BEFORE PRESSURE POINT.- CORRELATION AS REQUIRED PRIOR TAKING PRESSURE. - MONITOR WELL ON TRIP TANK, WELL STATIC. | 7406 | 6850 | SWL | 05/12/2022 | ADC-62L | LOG | ANDR-745
1101 | 7406 | 7085 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 1/7 AT 7,085 FT, (AD2B FM)...INC @ RPT- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING WITH XLD PROBE AT 7,085 FT AND DECIDE TO PERFORM SAMPLING WITH XLD PROBE.- MAX. STATIONARY TIME IS 4 HRS. AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- MONITORED WELL ON TRIP TANK, WELL STATIC.** LAST CIRCULATION ON 10TH MAY @ 01:45 HR, TIME FROM LAST CIRCULATION: 51.25 HRS.** MUD AGING TEST: SAG FACTOR IN ACCEPTED RANGE (0.506 / 0.507) AFTER 24/48 HRS OF STATIC AGING AS PER MI SWACO LAB TEST. | 7406 | 7085 | SWL | 05/12/2022 | ADC-62L | LOG | ANDR-745
1102 | 42.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORM PRESSURE POINTS AND SAMPLING UNDER OOS AS PER DP. | 24 | 2684 | 11 May 0300 | 05/12/2022 | ADC-62L | Type | ANDR-745
1103
1104
1105 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | ADC-65L | Hrs | HWYH-1280
1106 | FWTS | SDM | 7 | 12 May 1600 - 0500 | 5432 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/12/2022 | ADC-65L | 7 | HWYH-1280
1107 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | ADES-157 | Hrs | HRDH-1260
1108 | FOT | RIG | 2 | 12 May 2315 - 0115 | 12604 | 896523 | MALFUNCTION OF ELMAGO AUXILIARY BRAKE. | RR | DWKS |  | 05/12/2022 | ADES-157 | 2 | HRDH-1260
1109 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | ADM-337 | Hrs | MRJN-900
1110 | FOT | SAM | 1.25 | 12 May 0030 - 0145 | 78 | 896525 | ATTEMPT TO TEST PBL SUB, UNABLE TO FUNCTION, LAY DOWN SAME | BHA | MACS |  | 05/12/2022 | ADM-337 | 1.25 | MRJN-900
1111 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | AOD-11 | Hrs | SFNY-4280
1112 | XTRI | BCR | 1 | 12 May 2030 - 2130 | 0 | 896522 | BAKER CASING SIDE DOOR ELEVATORS NOT COMPATIBLE WITH BAKER EXTENSION BAILS. | JF | CTRQ |  | 05/12/2022 | AOD-11 | 1 | SFNY-4280
1113 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | ARO-3001 | Hrs | ZULF-2053
1114 | HELD | ARM | 65.5 | 10 May 1130 - 0500 | 7524 | 896413 | 9 5/8" CSG GOT HELD OFF BTM | JF | CSG |  | 05/12/2022 | ARO-3001 | 24 | ZULF-2053
1115 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | BCTD-4 | Hrs | GHZL-89
1116 | FOT | RIG | 11 | 12 May 1800 - 0500 | 14265 | 896524 | WHILE STAGING UP PR TO 88 GPM, OBSERVED A SUDDEN INCREASE IN DIFFERATIAL PRESSURE. BLED OFF CT PRESSURE, TRAPPED PRESSURE INTO THE BHA. | BHA | CTAC |  | 05/12/2022 | BCTD-4 | 11 | GHZL-89
1117 | FOT | SDM | 29 | 10 May 0330 - 0900 | 14767 | 896420 | SLB MUD MOTOR FAILURE. | BHA | MMOT |  | 05/12/2022 | DPS-4 | 4 | MDRK-54
1118 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | DPS-4 | Hrs | MDRK-54
1119 | STBH | ARM | 155.25 | 04 May 1900 - 0500 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. CONSEQUENCE LOST TIME TO LT ID:895515 | STUK | BHA | 895547 | 05/12/2022 | DPS-4 | 17 | MDRK-54
1120 | FOT | SDM | 29 | 10 May 0330 - 0900 | 14767 | 896420 | SLB MUD MOTOR FAILURE. | BHA | MMOT |  | 05/12/2022 | DPS-4 | 4 | MDRK-54
1121 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | DPS-74 | Hrs | NJYN-54
1122 | FOT | BLH | 687 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/12/2022 | DPS-74 | 24 | NJYN-54
1123 | 7579 | 0 | LOG | E | 2664 | WLT | POOH BHI W/L RUN # 2 [ MLL_MREX_GR_ADEX_JAR_MRCH ] FREE WHILE LOG UP FROM 5900' TO 5500'.- TOTAL LENGTH: 104.62' & MAX OD: 6.4".- MONITOR HOLE ON TRIP TANK, STATIC.> LOGGED UP AS FOLLOW:-- LOG MLL-MREX-ADEX-GR 2ND ZONE MAIN PASS SECTION F/ 5900 TO 5500' PP GAS ACQUISITION MODE,- LOG MLL-MREX-ADEX-GR 2ND ZONE REPEAT SECTION F/ 5900 TO 5500' PP LIGHT OIL ACQUISITION MODE,- POOH W/ W/L LOGGING TOOLS TILL 13 3/8" CSG SHOE @ 3485' & CONFIRM DATA W/ RDD.- POOH TO SURFACE & R/D ALL BAKER LOGGING TOOL & EQUIPMENT. | 7579 | 5900 | BAW | 05/12/2022 | DQ-48 | LOG | KHRS-1420
1124 | 7579 |  | SET | N | 2664 | WBSH | INSTALL 13-5/8" X 3M (CIW) WEAR BUSHING | 7579 |  | RIG | 05/12/2022 | DQ-48 | WH | KHRS-1420
1125 | 7579 |  | HT | E | 2664 | BHA | HPJSM, P/U, M/U & RIH 8 1/2" CONDITION TRIP REAMING ASSY ON 5" D/P & HWDP TO 370 FT.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 |  | RIG | 05/12/2022 | DQ-48 | CT | KHRS-1420
1126 | 7579 | 3485 | TI | E | 2664 | STDP | RIH 8 1/2" CONDITION TRIP REAMING ASSY ON 5" D/P & HWDP TILL 13 3/8" CSG SHOE @ 3485 FT.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 370 | RIG | 05/12/2022 | DQ-48 | CT | KHRS-1420
1127 | 7579 | 7579 | TI | E | 2664 | STDP | RIH 8 1/2" CONDITION TRIP REAMING ASSY TO BTM @ 7579'.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7579 | 3485 | RIG | 05/12/2022 | DQ-48 | CT | KHRS-1420
1128 | 7579 |  | CIRC | E |  | MPMP | SWEEP HOLE W/ 2 X 80 BBL HI-VIS PILL, CHC, DISPLACED HOLE TO 72 PCF OBM & CIRCULATE CONDITION MUD IN PROGRESS @ RT. | 7579 |  | RIG | 05/12/2022 | DQ-48 | CT | KHRS-1420
1129 | 28 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 18.5 | 2664 | 11 May 1930 | 05/12/2022 | DQ-48 | Type | KHRS-1420
1130
1131
1132 | 473 |  | BOPT | N | 2666 | DVRT | OOS - FUNCTION TEST 30" DIVERTER & DIVERTER LINE HCR'S FROM ALL CONTROL UNITS.- FLUSH DIVERTER LINES WITH WATER, HYDRO TEST DIVERTER AND DIVERTER LINE - OK.- PRESSURE TEST KILL LINE TO 1500 PSI - OK.- PRESSURE TEST 24" CONDUCTOR, 30" DIVERTER & HCR VALVES TO 200 PSI - OK. | 473 |  | RIG | 05/12/2022 | DQ-50L | BOP | HRDH-582
1133 | 473 |  | HT | N |  | BHA | HPJSM-P/U, M/U & RIH 17" ROTARY DRLG BHA, WASH DOWN LAST STD & TAG CMT @ 464'. | 473 |  | RIG | 05/12/2022 | DQ-50L | DRLG | HRDH-582
1134 | 473 |  | PTST | N |  | MPMP | HYDRO TEST 24" CSG, 15 MIN - OK. | 473 |  | RIG | 05/12/2022 | DQ-50L | DRLG | HRDH-582
1135 | 473 | 473 | DC | N |  | TDS | DRILL OUT CMT, 24" STAB IN SHOE & RAT HOLE F/ 464 FT T/ 473 FT MEANWHILE DISPLACE TO 64 PCF INHIBITED POLYMER MUD WITH FULL RETURN. | 473 | 464 | RIG | 05/12/2022 | DQ-50L | DRLG | HRDH-582
1136 | 793 |  | D | N |  | TDS | ROTARY DRILL 17" VERTICAL HOLE F/ 473 FT T/ 793 FT W/ 64 PCF INHIBITED POLYMER MUD & 100% RETURN.- SWEEP HOLE W/50 BBL HVP EVERY JT & SPOT 50 BBL HVP ACROSS BHA BEFORE CONNECTION.- WASH UP & REAM DOWN LAST JT EVERY STD. | 473 |  | RIG | 05/12/2022 | DQ-50L | DRLG | HRDH-582
1137 | 793 |  | CIRC | N |  | MPMP | HAD COMPLETE LOSS @ 793 FT, P/U OFF BTM WHILE KEEPING CIRC, ROTATION & RECIPROCATION, CONFIRM STRG IS FREE, SWEPT HOLE W/ 50 BBL HVP.- PUMP 2 BPM 64 PCF INHIBITED POLYMER MUD FROM BACKSIDE. | 793 |  | RIG | 05/12/2022 | DQ-50L | DRLG | HRDH-582
1138 | 2122 |  | D | N |  | TDS | CONT. ROTARY DRILL 17" VERTICAL HOLE F/ 793 FT TO CSG PT @ 2,122 FT W/ 64 PCF INHIBTED POLY MUD ON FLY MIX / GEL SWEEPS & NO RETURN.- WOB: 30-60 KLBS, GPM: :800 @ 260 PSI, RPM: 80:100, OFF BTM/ON BTM TQ: 4-5/11-16 KLB.FT. - SWEEP HOLE W/50 BBL HVP EVERY JT & SPOT 50 BBL HVP ACROSS BHA BEFORE CONNECTION.- CONTROLED ROP @ 50 FPH FOR 50' BELOW LZ.- WASH UP & REAM DOWN LAST JT EVERY STD.- KEEP PUMPING 2 BPM 64 PCF INHIBITED POLYMER MUD FROM BACKSIDE. | 793 |  | RIG | 05/12/2022 | DQ-50L | DRLG | HRDH-582
1139 | 2122 |  | CIRC | N |  | MPMP | SWEEP HOLE W/ 2 X 100 BBL HVP & CIRCULATE UP TO LOSS ZONE @ 793 FT WITH NO RETURN.- SPOT 500 BBL 90 PCF INHIBETED HVP ON BTM.- KEEP PUMPING 2 BPM OF 64 PCF POLYMER MUD IN ANNULUS ALL THE TIME. | 2122 |  | RIG | 05/12/2022 | DQ-50L | DRLG | HRDH-582
1140 | 2122 | 1600 | ST | N |  | STDP | POOH W/ 17" DRLG BHA FOR 13-3/8" CSG TO 1,600' ... ONGOING @ RPT.- KEEP PUMPING 2 BPM OF 64 PCF POLYMER MUD IN ANNULUS. | 2122 | 2122 | RIG | 05/12/2022 | DQ-50L | DRLG | HRDH-582
1141 | 11 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | N/U 30" 1M DIVERTER. | 3 | 2666 | 11 May 0000 | 05/12/2022 | DQ-50L | Type | HRDH-582
1142
1143
1144 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | DQ-57L | Hrs | KHRS-227
1145 | FOT | HCB | 1.5 | 12 May 0330 - 0500 | 200 | 896526 | PRESSURE TEST HALLIBURTON MONOLOCK PLUG NOT HOLD. | TF | BP |  | 05/12/2022 | DQ-57L | 1.5 | KHRS-227
1146 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | ENS-108 | Hrs | SFNY-1720
1147 | UXDF | ARM | 30 | 11 May 2300 - 0500 | 8182 | 896393 | ENCOUNTERED TOTAL LOSSES. | LCIR | NA |  | 05/12/2022 | ENS-108 | 24 | SFNY-1720
1148 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | HI-4 | Hrs | SFNY-918
1149 | FOT | RIG | 3.25 | 12 May 1800 - 2115 | 5269 | 896519 | ENCOUNTERED 2 EACH MODULE SEAL FAILURES BETWEEN DISCHARGE AND SUCTION MODULES ON MUD PUMP # 2. POOH TO SHOE AND REPAIR SAME. | RR | MPMP |  | 05/12/2022 | HI-4 | 3.25 | SFNY-918
1150 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | NA-128S | Hrs | SAHB-28
1151 | FOT | SPS | 13.25 | 12 May 1545 - 0500 | 12216 | 896517 | LOST COMMUNICATION WITH RSS | BHA | RSS |  | 05/12/2022 | NA-128S | 13.25 | SAHB-28
1152 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | NA-393S | Hrs | HWYH-1138
1153 | FOT | WI3 | 32.5 | 11 May 1500 - 2345 | 11720 | 896461 | AFTER SETTING 7" WHIPSTOCTRIED TO PASS WITH 5-7/8" MM DIR BHA THRU WIS WHIPSTOCK WINDOW. | TF | WPSTK |  | 05/12/2022 | NA-393S | 18.75 | HWYH-1138
1154 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | RM-74A | Hrs | KARN-60
1155 | WOTO | GEP | 1.5 | 12 May 2030 - 2200 | 0 | 896537 | BPV LUBRICATOR WAS LEAKING @ PRESSURE TEST. | WO | NA |  | 05/12/2022 | RM-74A | 1.5 | KARN-60
1156 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | SINO-12L | Hrs | HRDH-1454
1157 | FOT | TOT | 98.75 | 08 May 0215 - 0500 | 7965 | 896274 | HAD LEAK DURING PRESSURE TEST CMT VALVE. | TF | LLAP |  | 05/12/2022 | SINO-12L | 24 | HRDH-1454
1158 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | SINO-18 | Hrs | SRYN-14
1159 | STBH | ARM | 113 | 08 May 1200 - 0500 | 840 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/12/2022 | SINO-18 | 24 | SRYN-14
1160 | FOT | NGS | 4.5 | 12 May 0730 - 1200 | 4564 | 896521 | NO COMMUNICATION WITH NAPESCO GYRO TOOL . | SURV | GYRO |  | 05/12/2022 | SINO-42L | 4.5 | HWYH-485
1161 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | SINO-42L | Hrs | HWYH-485
1162 | FOT | WWD | 14.5 | 11 May 1200 - 0730 | 4564 | 896478 | UNABLE TO SET 7" WFD WHIPSTOCK . | TF | WPSTK |  | 05/12/2022 | SINO-42L | 2.5 | HWYH-485
1163 | FOT | NGS | 4.5 | 12 May 0730 - 1200 | 4564 | 896521 | NO COMMUNICATION WITH NAPESCO GYRO TOOL . | SURV | GYRO |  | 05/12/2022 | SINO-42L | 4.5 | HWYH-485
1164 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | SP-101 | Hrs | ABQQ-710
1165 | FOT | WI1 | 368 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/12/2022 | SP-101 | 24 | ABQQ-710
1166 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | SP-120 | Hrs | MNIF-188
1167 | FRFM | ARM | 54.5 | 10 May 0500 - 1200 | 6225 | 896360 | CURE LOSSES WITH LCM PILL AND CMT PLUG | LCIR | NA |  | 05/12/2022 | SP-120 | 7 | MNIF-188
1168 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | SP-124 | Hrs | FDHL-141
1169 | FOT | OSL | 16.5 | 11 May 2300 - 1530 | 7705 | 896460 | OILSERV SL PARTED WHILE POH AFTER ATTEMPTING TO PUNCH 3-1/2" TBG AT 7705' | TF | SLICK |  | 05/12/2022 | SP-124 | 10.5 | FDHL-141
1170 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | SP-257 | Hrs | HZEM-141014
1171 | WOTO | ARM | 2.75 | 12 May 0215 - 0500 | 1175 | 896432 | WAIT ON SLB TOOLS DUE TO TRUCK STUCK ON DAMAGED SKID ROAD. | WO | NA |  | 05/12/2022 | SP-257 | 2.75 | HZEM-141014
1172 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | SSA-201 | Hrs | HRDH-1818
1173 | HINW | ARM | 557.5 | 17 Apr 1500 - 0500 | 14240 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/12/2022 | SSA-201 | 23.5 | HRDH-1818
1174 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | T217 | Hrs | UTMN-375
1175 | ISEQ | RIG | 3 | 12 May 1800 - 2100 | 0 | 896431 | OBSERVE SINGLE ELEVATOR WITH OVER CLEARANCE CATCH AND CHANGED SAME. | TF | TBG |  | 05/12/2022 | T217 | 3 | UTMN-375
1176 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/12/2022 | V140A | Hrs | SFNY-1760
1177 | FOT | GEP | 19.25 | 11 May 1800 - 1315 | 156 | 896459 | AFTER CEMENTING 18 5/8" CASING AND CLEANING 18 5/8" MLC PORTS, ATTEMPTED TO CLOSE WITHOUT SUCCESS. MANY TRIALS VARYING PARAMETERS PORTS STUCK IN OPEN POSITION. | WH | WH |  | 05/12/2022 | V140A | 8.25 | SFNY-1760
1178 | FOT | FMC | 1 | 13 May 1330 - 1430 | 4704 | 896503 | FRANKS P/U MACHINE MALFUNCTION. | TF | TTRQ |  | 05/13/2022 | 088TE | 1 | QTIF-176
1179 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | 088TE | Hrs | QTIF-176
1180 | FOT | FMC | 1 | 13 May 0900 - 1000 | 3515 | 896502 | FRANKS POWER TONG MALFUNCTION. | TF | TTRQ |  | 05/13/2022 | 088TE | 1 | QTIF-176
1181 | FOT | FMC | 1 | 13 May 1330 - 1430 | 4704 | 896503 | FRANKS P/U MACHINE MALFUNCTION. | TF | TTRQ |  | 05/13/2022 | 088TE | 1 | QTIF-176
1182 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | ADC-17 | Hrs | ZULF-1218
1183 | FOT | RIG | 1.75 | 13 May 0245 - 0430 | 4615 | 896557 | RIG REPLACE LEAKING PISTON OF TDS PIPE GRAP | RR | TDS |  | 05/13/2022 | ADC-17 | 1.75 | ZULF-1218
1184 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | ADC-21 | Hrs | MZLJ-155201
1185 | PSSW | ARM | 251 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/13/2022 | ADC-21 | 24 | MZLJ-155201
1186 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | ADC-60 | Hrs | ABSF-218
1187 | FOT | SCB | 13 | 13 May 1100 - 0000 | 4920 | 896504 | S/L RIH WTIH PULLING TOOL TO RETRIEVE SLB PLUS PLUG, LATCHED ON. JAR UP TO RETRIEVE THE PLUG, NEGATIVE. | TF | BP |  | 05/13/2022 | ADC-60 | 13 | ABSF-218
1188 | 7406 | 7085 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 1 OUT OF 7 AT 7,085 FT, (AD2B FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING AT 7,085 FT AND DECIDE TO PERFORM SAMPLING WITH XLD PROBE.- PUMP OUT INTO WELLBORE 1.46 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 1.46 BBLS, (FLUID TYPE: WATER). - HYDROSTATIC DROP= 8 PSI, OVERBALANCE, AS PER SLB MDT 342 PSI. - MAX. STATIONARY TIME IS 4 HRS. AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 | 7085 | SWL | 05/13/2022 | ADC-62L | LOG | ANDR-745
1189 | 7406 | 7065 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 2 OUT OF 7 AT 7,065 FT, (AD2B FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING WITH XLD PROBE AT 7,065 FT AND DECIDE TO PERFORM SAMPLING WITH SATURN PACKER.- PUMP OUT INTO WELLBORE 1.52 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 2.98 BBLS, (FLUID TYPE: OIL+WATER). - HYDROSTATIC DROP= 15 PSI, OVERBALANCE, AS PER MDT 334 PSI. - PERFORM THE SAMPLE IN 2 SESSIONS. AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.* RDD DECIDED TO PERFORM 2 EXTRA PRESSURE POINTS IN AD2B FORMATION.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 | 7065 | SWL | 05/13/2022 | ADC-62L | LOG | ANDR-745
1190 | 7406 | 7062 | LOG | E | 2684 | WLT | (OOS) RECORDED 2 PRESSURE POINTS AS PER RDD REQUEST AT 7,070 FT AND 7,062 FT ( AD2B FM)(COMPLETED TOTAL 15).- PERFORM STICK TESTS 5,10 & 15 MINS BEFORE PRESSURE POINT.- CORRELATION AS REQUIRED PRIOR TAKING PRESSURE. - MONITOR WELL ON TRIP TANK, WELL STATIC. | 7406 | 7070 | SWL | 05/13/2022 | ADC-62L | LOG | ANDR-745
1191 | 7406 | 7030 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 3 OUT OF 7 AT 7,030 FT, (AD2A FM)...INC @ RPT.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING AT 7,065 FT AND DECIDE TO PERFORM SAMPLING WITH XLD PROBE.- PUMP OUT INTO WELLBORE 0.82 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 3.8 BBLS, (FLUID TYPE: WATER).- AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- MONITORED WELL ON TRIP TANK, WELL STATIC.** LAST CIRCULATION ON 10TH MAY @ 01:45 HR, TIME FROM LAST CIRCULATION: 75.25 HRS.** MUD AGING TEST: SAG FACTOR IN ACCEPTED RANGE (0.506 / 0.507 / 0.510) AFTER 24/48/72 HRS OF STATIC AGING AS PER MI SWACO LAB TEST.. | 7406 | 7030 | SWL | 05/13/2022 | ADC-62L | LOG | ANDR-745
1192 | 66.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORM PRESSURE POINTS AND SAMPLING UNDER OOS AS PER DP. | 24 | 2684 | 11 May 0300 | 05/13/2022 | ADC-62L | Type | ANDR-745
1193
1194
1195 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | ADC-65L | Hrs | HWYH-1280
1196 | FWTS | SDM | 31 | 12 May 1600 - 0500 | 5432 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/13/2022 | ADC-65L | 24 | HWYH-1280
1197 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | ARO-3002 | Hrs | MRJN-815
1198 | HERR | BCM | 1 | 13 May 1900 - 2000 | 16603 | 896507 | EXCESSIVE TIME TO PREPARE FOR ACID JOB. | CMT | NA |  | 05/13/2022 | ARO-3002 | 1 | MRJN-815
1199 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | BCTD-4 | Hrs | GHZL-89
1200 | FOT | RIG | 12.5 | 12 May 1800 - 0630 | 14265 | 896524 | TURBINE FAILURE, OBSERVED A SUDDEN INCREASE IN SURFACE & INNER STRING PRESSURE & CIRCULATIONAL MINIMAL, POH TO CHECK BHA & TURBINE. | BHA | CTAC |  | 05/13/2022 | BCTD-4 | 1.5 | GHZL-89
1201 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | DPS-4 | Hrs | MDRK-54
1202 | STBH | ARM | 178.75 | 04 May 1900 - 0500 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. CONSEQUENCE LOST TIME TO LT ID:895515 | STUK | BHA | 895547 | 05/13/2022 | DPS-4 | 23.5 | MDRK-54
1203 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | DPS-74 | Hrs | NJYN-54
1204 | FOT | BLH | 710.5 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/13/2022 | DPS-74 | 23.5 | NJYN-54
1205 | 7579 |  | CIRC | E | 2664 | MPMP | CON'T CHC & CONDITION 72 PCF OBM, COFIRM MUD WT IN & OUT = 72 PCF. | 7579 |  | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1206 | 7579 |  | SDR1 | E | 2664 | NA | FLOW CHECK, HOLE STATIC.- TAKE SLOW PUMP RATE & UPDATE KILL SHEET. | 7579 |  | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1207 | 7579 | 3485 | TO | E | 2664 | STDP | POOH 8 1/2" CONDITION TRIP REAMING ASSY WIPER TRIP TILL 13 3/8" CSG SHOE @ 3485 FT.- FLOW CHECK AFTER 5 STD POOH, HOLE STATIC.- MONITORE HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7579 | 7579 | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1208 | 7579 |  | SDR1 | E | 2664 | NA | FLOW CHECK, HOLE STATIC. | 7579 |  | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1209 | 7579 | 7579 | TI | E | 2664 | STDP | RIH 8 1/2" CONDITION TRIP REAMING ASSY WIPER TRIP BACK TO BTM.- MONITORE HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7579 | 3485 | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1210 | 7579 |  | CIRC | E | 2664 | MPMP | SWEEP HOLE W/ 2 X 30 BBL HVP & CHC. | 7579 |  | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1211 | 7579 |  | SDR1 | E | 2664 | NA | FLOW CHECK, HOLE STATIC. | 7579 |  | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1212 | 7579 | 3485 | TO | E | 2664 | STDP | POOH 8 1/2" CONDITION TRIP REAMING ASSY TILL 13 3/8" CSG SHOE @ 3485 FT.- FLOW CHECK AFTER 10 STD POOH, HOLE STATIC.- MONITORE HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7579 | 7579 | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1213 | 7579 |  | SDR1 | E | 2664 | NA | FLOW CHECK, HOLE STATIC. | 7579 |  | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1214 | 7579 | 370 | TO | E | 2664 | STDP | POOH 8 1/2" CONDITION TRIP REAMING ASSY TILL TOP OF BHA @ 370 FT.- MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 3485 | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1215 | 7579 |  | SDR1 | E | 2664 | NA | FLOW CHECK, HOLE STATIC. | 7579 |  | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1216 | 7579 |  | HT | E | 2664 | BHA | POOH TO SURFACE WHILE L/D 8 1/2" CONDITION TRIP REAMING ASSY.- MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7579 |  | RIG | 05/13/2022 | DQ-48 | CT | KHRS-1420
1217 | 7579 | 183 | LOG | E | 2664 | WLT | HPJSM, R/U BKR E/L EQUIPMENT, P/U & M/U BHI W/L LOGGING TOOLS RUN#3 [ RCX ON GR ] IN PROGRESS @ RT.- TOTAL LOGGING TOOL LENGTH: 183.13', WT: 5517 IB & MAX OD: 7.8".- MONITOR HOLE ON TRIP TANK, STATIC. | 7579 | 0 | BAW | 05/13/2022 | DQ-48 | LOG | KHRS-1420
1218 | 56 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2664 | 11 May 1930 | 05/13/2022 | DQ-48 | Type | KHRS-1420
1219
1220
1221 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | ENS-108 | Hrs | SFNY-1720
1222 | UXDF | ARM | 54 | 11 May 2300 - 0500 | 8182 | 896393 | ENCOUNTERED TOTAL LOSSES. | LCIR | NA |  | 05/13/2022 | ENS-108 | 24 | SFNY-1720
1223 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | EXL-IVA | Hrs | SFNY-1800
1224 | FOT | BAW | 15 | 13 May 1330 - 0500 | 7597 | 896543 | FAILURE OF WIRELINE PROBE USED TO TAKE VIT'S. | TF | WLT |  | 05/13/2022 | EXL-IVA | 15 | SFNY-1800
1225 | ORDS | ARM | 1.25 | 13 May 1045 - 1200 | 6021 | 896541 | DIRECTIONAL PLAN CHANGE BY GOC. WAIT ON APPROVED PLAN 6.5 TO BE ISSUED. | WO | NA |  | 05/13/2022 | HI-4 | 1.25 | SFNY-918
1226 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | HI-4 | Hrs | SFNY-918
1227 | SRVC | OTH | 2 | 13 May 0800 - 1045 | 3550 | 896530 | LOSS OF REAL TIME COMMUNICATION BETWEEN RIG DIRECTIONAL CO. / GOC DUE TO V-SAT OUTAGE. | WO | NA |  | 05/13/2022 | HI-4 | 2 | SFNY-918
1228 | ORDS | ARM | 1.25 | 13 May 1045 - 1200 | 6021 | 896541 | DIRECTIONAL PLAN CHANGE BY GOC. WAIT ON APPROVED PLAN 6.5 TO BE ISSUED. | WO | NA |  | 05/13/2022 | HI-4 | 1.25 | SFNY-918
1229 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | MP-1 | Hrs | MRJN-305
1230 | HERR | BHI | .75 | 13 May 0215 - 0300 | 127 | 896542 | REMOVED BAKER FILTER SUB FROM BHA DUE TO 1 CM GAP BETWEEN 3-1/2" IF FILTER SUB BOX AND RIG 3-1/2" IF X.O PIN. | DD | RSS |  | 05/13/2022 | MP-1 | .75 | MRJN-305
1231 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | NA-128S | Hrs | SAHB-28
1232 | FOT | SPS | 24.25 | 12 May 1545 - 1600 | 12216 | 896517 | LOST COMMUNICATION WITH RSS | BHA | RSS |  | 05/13/2022 | NA-128S | 11 | SAHB-28
1233 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | NA-393S | Hrs | HWYH-1138
1234 | FOT | WI3 | 56.5 | 11 May 1500 - 0500 | 11720 | 896461 | AFTER SETTING 7" WHIPSTOCTRIED TO PASS WITH 5-7/8" MM DIR BHA THRU WIS WHIPSTOCK WINDOW. | TF | WPSTK |  | 05/13/2022 | NA-393S | 24 | HWYH-1138
1235 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | NBR-783S | Hrs | NJYN-89
1236 | FOT | CRT | 33.75 | 12 May 1015 - 0500 | 14935 | 896433 | LEAK ON LTTT PACKER DURING NEGATIVE TST | BHA | WBCL |  | 05/13/2022 | NBR-783S | 20.5 | NJYN-89
1237 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | PA-785S | Hrs | QTIF-269
1238 | SRVC | SCD | 2.5 | 13 May 0500 - 0730 | 0 | 896527 | HH | WO | NA |  | 05/13/2022 | PA-785S | 2.5 | QTIF-269
1239 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SINO-12L | Hrs | HRDH-1454
1240 | FOT | TOT | 102.75 | 08 May 0215 - 0900 | 7965 | 896274 | HAD LEAK DURING PRESSURE TEST CMT VALVE. | TF | LLAP |  | 05/13/2022 | SINO-12L | 4 | HRDH-1454
1241 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SINO-18 | Hrs | SRYN-14
1242 | STBH | ARM | 137 | 08 May 1200 - 0500 | 840 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/13/2022 | SINO-18 | 24 | SRYN-14
1243 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SND-2003 | Hrs | RMTN-17
1244 | FOT | GOC | 1.5 | 13 May 0330 - 0500 | 3400 | 896506 | CRT DIES SLIPPING WHILE ATTEPMTED TO LIFT THE SLIPS. | TF | CTRQ |  | 05/13/2022 | SND-2003 | 1.5 | RMTN-17
1245 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SND-2004 | Hrs | BRRI-1148
1246 | FOT | RIG | 14 | 13 May 1200 - 0500 | 7657 | 896529 | RIG POWER ISSUE DUE TO FREQUENT SHUT DOWN & TROUBLESHOOTING WHILE MONITORING THE WELL AT SHOE. | RR | PSYS |  | 05/13/2022 | SND-2004 | 14 | BRRI-1148
1247 | FOT | RIG | 1 | 13 May 0030 - 0130 | 10058 | 896435 | RIG MUD PUMPS # 1 & 2 HAD LEAKING CAP SEAL & WASHED VALVE/SEAT | RR | MPMP |  | 05/13/2022 | SND-2005 | 1 | MHKK-2
1248 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SND-2005 | Hrs | MHKK-2
1249 | FOT | RIG | 9 | 13 May 1215 - 2315 | 10031 | 896434 | DRILL SMART EATON BRAKE SYSTEM FOR AUTO DRILLER NOT FUNCTIONING CORRECTLY | RR | DWKS |  | 05/13/2022 | SND-2005 | 9 | MHKK-2
1250 | FOT | RIG | 1 | 13 May 0030 - 0130 | 10058 | 896435 | RIG MUD PUMPS # 1 & 2 HAD LEAKING CAP SEAL & WASHED VALVE/SEAT | RR | MPMP |  | 05/13/2022 | SND-2005 | 1 | MHKK-2
1251 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SNT-025 | Hrs | SFNY-956
1252 | FOT | RIG | 3 | 13 May 0800 - 1100 | 4568 | 896500 | TOP DRIVE GOOSE NECK LEAKING AROUND CONNECTION. | RR | TDS |  | 05/13/2022 | SNT-025 | 3 | SFNY-956
1253 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SP-101 | Hrs | ABQQ-710
1254 | FOT | WI1 | 392 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/13/2022 | SP-101 | 24 | ABQQ-710
1255 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SP-257 | Hrs | HZEM-141014
1256 | WOTO | SDM | 9.5 | 12 May 0215 - 1145 | 1175 | 896432 | WAIT ON SLB DIRECTIONAL TOOLS, REQUESTED FOR 5/10/22. | WO | NA |  | 05/13/2022 | SP-257 | 6.75 | HZEM-141014
1257 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SSA-201 | Hrs | HRDH-1818
1258 | HINW | ARM | 581 | 17 Apr 1500 - 0500 | 14240 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/13/2022 | SSA-201 | 23.5 | HRDH-1818
1259 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SSA-303 | Hrs | HRDH-2306
1260 | FOT | RIG | 11.5 | 13 May 1215 - 0500 | 8210 | 896501 | OBSERVED WASH PIPE LEAKING, CHANGED SAME. | RR | TDS |  | 05/13/2022 | SSA-303 | 11.5 | HRDH-2306
1261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/13/2022 | SSA-5859 | Hrs | HWYH-1222
1262 | FOT | RIG | 4.5 | 13 May 2330 - 0400 | 314 | 896558 | TDS GOOSNEK FRAME SUPPORT BOLTS SHEARED . | RR | TDS |  | 05/13/2022 | SSA-5859 | 4.5 | HWYH-1222
1263 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | ADC-21 | Hrs | MZLJ-155201
1264 | PSSW | ARM | 275 | 03 May 0800 - 0500 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/14/2022 | ADC-21 | 24 | MZLJ-155201
1265 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | ADC-45 | Hrs | KHRS-564
1266 | WTHR | ARM | 2 | 14 May 1130 - 1330 | 0 | 896564 | SUSPEND CRANE LIFT DUE TO HIGH WIND SPEED. | WON | NA |  | 05/14/2022 | ADC-45 | 2 | KHRS-564
1267 | 7109 | 6696 | LOG | E | 2584 | WLT | CONT'D SLB MDT-TLC PUMPING OUT AND COLLECT SAMPLE 12/12 AT 6,696 FT, (ABD1 RESERVOIR FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10 & 15 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- PERFORMED SCANNING WITH LD PROBE AT 6,696 FT.- COLLECTED SAMPLE IN 3 SESSIONS.- MAX. STATIONARY TIME IS 04 HOURS.- AFTER EVERY SESSION 04 HOURS MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- FORMATION: TOP ARAB-D ZONE 1.- SAMPLES COMPLETED: 12/12.- PUMP OUT COMPLETED: 12/12.- PUMP OUT INTO WELLBORE 0.68 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 4.41 BBLS, (FLUID TYPE: OIL).- HYDROSTATIC DROP= 8.3 PSI, OVERBALANCE, AS PER SLB MDT 871 PSI.- MONITORED WELL ON TRIP TANK, WELL STATIC.** TIME SINCE LAST CIRCULATION = 41.25 HOURS. | 7109 | 6696 | SWL | 05/14/2022 | ADC-53L | LOG | UTMN-4069
1268 | 7109 |  | CIRC | E | 2584 | MPMP | RIH BELOW 1ST SAMPLING POINT TO 7090 FT & CIRC HOLE ONE COMPLETE CYCLE AT 150 GPM WITH 310 PSI, 100% CIRC. MW IN/ OUT 80 PCF. PERCAUTIONARY CLOSE BOP AT FINAL 200 BBLS AND CONT. CIRC. THRU CHOCK. FLOW CHECK THRU CHOCK FOR 15 MIN- WELL STATIC.- OPENED BOP & PERFORM NORMAL FLOW CHECK- WELL STATIC. | 7109 |  | RIG | 05/14/2022 | ADC-53L | LOG | UTMN-4069
1269 | 7109 | 6664 | ST | E | 2584 | STDP | HPJSM, POOH CONTROLLED SPEED W/MDT - TLC STRING AS PER SLB PROCEDURE FIRST 5 STDS TO 6,664 FT. FLOW CHECK FOR 15 MINS - WELL STATIC.- MONITOR WELL ON TRIP TANK. | 7109 | 7090 | RIG | 05/14/2022 | ADC-53L | LOG | UTMN-4069
1270 | 7109 | 4447 | ST | E | 2584 | STDP | CONT'D POOH CONTROLLED SPEED W/MDT - TLC STRING TO WIRELINE SES DEPTH @ 4,447 FT. FLOW CHECK - WELL STATIC. | 7109 | 6664 | RIG | 05/14/2022 | ADC-53L | LOG | UTMN-4069
1271 | 7109 |  | OTH | E | 2584 | NA | HPJSM, SLB WL UNLATCHED CABLE HEAD FROM WET CONNECTOR PROFILE & POOH WITH WL CABLE TO SURFACE. R/D SES AND WIRE LINE SHEAVES. | 7109 |  | SWL | 05/14/2022 | ADC-53L | LOG | UTMN-4069
1272 | 257 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE. | 24 | 2584 | 04 May 0100 | 05/14/2022 | ADC-53L | Type | UTMN-4069
1273
1274
1275 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | ADC-58L | Hrs | ABHD-178
1276 | WTHR | OTH | 3.25 | 14 May 0945 - 1300 | 10258 | 896545 | WOW DUE TO HIGH SAND STORM SPEED 50 KM/HR | WON | NA |  | 05/14/2022 | ADC-58L | 3.25 | ABHD-178
1277 | 7406 | 7030 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 3 OUT OF 7 AT 7,030 FT, (AD2A FM)- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING AT 7,030 FT AND DECIDE TO PERFORM SAMPLING WITH XLD PROBE.- PUMP OUT INTO WELLBORE 1.35 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 4.34 BBLS, (FLUID TYPE: WATER).- HYDROSTATIC DROP= 22 PSI, OVERBALANCE, AS PER MDT 327 PSI.- PERFORM THE SAMPLE IN 2 SESSIONS. AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- MONITORED WELL ON TRIP TANK, WELL STATIC.** LAST CIRCULATION ON 10TH MAY @ 01:45 HR. TIME FROM LAST CIRCULATION: 76.75 HRS. | 7406 | 7030 | SWL | 05/14/2022 | ADC-62L | LOG | ANDR-745
1278 | 7406 |  | OTH | E | 2684 | NA | (OOS) RIH WIRELINE MDT-GR TLC STRING F/ 7,030 FT TO 7,295 FT.- TRIPPING SPEED: 3 MIN SLIP-TO-SLIP AS PER SLB WL ENGINEER.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 |  | RIG | 05/14/2022 | ADC-62L | LOG | ANDR-745
1279 | 7406 |  | CIRC | E | 2684 | MPMP | (OOS) CIRCULATED OH ANNULAR VOLUME TO 9-5/8" CSG. FR: 100 GPM, SPP: 250 PSI.- INCREASED FR GRADUALLY IN STEPS TO 100 GPM.- RECIPROCATE THE STRING WHILE CIRC.- NO DOWN HOLE DYNAMIC LOSSES.- PERFORM FLOW CHECK, WELL STATIC. | 7406 |  | RIG | 05/14/2022 | ADC-62L | LOG | ANDR-745
1280 | 7406 |  | OTH | E | 2684 | NA | (OOS) POOH WIRELINE MDT-GR TLC STRING F/ 7,295 FT TO 4,814 FT (INSIDE 9-5/8" CSG).- POOH AT CONTROLLED SPEED: 3 MIN/STD.- OH IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK, OK.- PERFORM FLOW CHECK AT 9-5/8" CSG SHOE, WELL STATIC. | 7406 |  | RIG | 05/14/2022 | ADC-62L | LOG | ANDR-745
1281 | 7406 |  | CIRC | E | 2684 | MPMP | (OOS) CIRCULATE 1.2 BTM UP. FR: 100 GPM, SPP: 250 PSI. MW IN/OUT: 84 PCF.- PRECAUTIONARY CIRC THROUGH CHOKE & POOR BOY DEGASSER.- NO CUT IN MW.* PERFORM FLOW CHECK FOR 30 MIN, WELL STATIC. | 7406 |  | RIG | 05/14/2022 | ADC-62L | LOG | ANDR-745
1282 | 7406 |  | OTH | E | 2684 | NA | (OOS) RIH SLB WL MDT TLC STRING F/ 4,814 FT TO 7,003 FT- FILLED STRING EVERY 15 STANDS.- USED WL DP SCREEN TO FILL STRING.- CONTROLLED TRIPPING SPEED: 3 MIN SLIP-TO-SLIP.- OPEN HOLE IN GOOD CONDITION.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 |  | RIG | 05/14/2022 | ADC-62L | LOG | ANDR-745
1283 | 7406 | 7003 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 4 OUT OF 7 AT 7,003 FT, (AD2A FM)- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING AT 7,003 FT AND DECIDE TO PERFORM SAMPLING WITH XLD PROBE.- PUMP OUT INTO WELLBORE 2.84 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 2.84 BBLS, (FLUID TYPE: WATER).- HYDROSTATIC DROP= 15 PSI, OVERBALANCE, AS PER MDT 342 PSI.- PERFORM THE SAMPLE IN 2 SESSIONS. AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 | 7003 | SWL | 05/14/2022 | ADC-62L | LOG | ANDR-745
1284 | 7406 | 6993 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 5 OUT OF 7 AT 6,993 FT, (AD2A FM)...INC @ RPT.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP ONGOING.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 | 6993 | SWL | 05/14/2022 | ADC-62L | LOG | ANDR-745
1285 | 90.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORM PRESSURE POINTS AND SAMPLING UNDER OOS AS PER DP. | 24 | 2684 | 11 May 0300 | 05/14/2022 | ADC-62L | Type | ANDR-745
1286
1287
1288 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | ADM-510 | Hrs | ABSF-230
1289 | FOT | SWL | 4.75 | 14 May 1030 - 1515 | 6786 | 896511 | ATTEMPT TO OPEN CALIPER AND FOUND WIRE GROUNDED IN LATCH HEAD/ROPE SOCKET | TF | WLT |  | 05/14/2022 | ADM-510 | 4.75 | ABSF-230
1290 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | DPS-4 | Hrs | MDRK-54
1291 | STBH | ARM | 202.25 | 04 May 1900 - 0500 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. CONSEQUENCE LOST TIME TO LT ID:895515 | STUK | BHA | 895547 | 05/14/2022 | DPS-4 | 23.5 | MDRK-54
1292 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | DPS-74 | Hrs | NJYN-54
1293 | FOT | BLH | 734.5 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/14/2022 | DPS-74 | 24 | NJYN-54
1294 | 7579 | 183 | OTH | E | 2664 | NA | FINISH R/U BKR E/L EQUIPMENT & RIH BHI W/L LOGGING TOOLS RUN#3 MDT [ RCX ON GR ] TO 183 FT.- TOTAL LOGGING TOOL LENGTH: 183.13', WT: 5517 IB & MAX OD: 7.8".- TESTED TOOLS & FUNCTIONS AT SURFACE.- MONITOR HOLE ON TRIP TANK, STATIC. | 7579 | 0 | BAW | 05/14/2022 | DQ-48 | LOG | KHRS-1420
1295 | 7579 | 4790 | LOG | E | 2664 | WLT | RIH BHI LOGGING TOOLS ON 5" D/P RUN# 3 MDT LOG [ RCX ON GR ] WITH CONTROLLED SPEED TO LATCH POINT @ 4790'.- FILL STRING & BREAK CIRCULATION 72 PCF OBM MUD EVERY 10 STD.- CONTROLLED RUNNING SPEED TO 2 MIN / STD.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- DRIFT ALL STD'S WITH 3.1". | 7579 | 0 | BAW | 05/14/2022 | DQ-48 | LOG | KHRS-1420
1296 | 7579 |  | CIRC | E | 2664 | MPMP | CIRCULATE TWICE STRING VOLUME [ 170 BBL ] W/ 72 PCF MUD [ 210 GPM - 140 PSI ], MEANWHILE R/U W/L SHEAVES. | 7579 |  | RIG | 05/14/2022 | DQ-48 | LOG | KHRS-1420
1297 | 7579 | 4790 | LOG | E | 2664 | WLT | HPJSM, P/U & M/U BKR SIDE ENTRY SUB, RIH WITH SINKER BAR INSIDE D/P, LATCH CABLE WITH LOGGING TOOLS [ 200 GPM - 150 PSI ].- TEST LOGGING TOOL COMMUNICATION, GOOD RESPONCE.- CHECK TOOLS SIGNAL & PERFORM PULL UP TEST, OK.- INSTALL W/L CLAMP ON SES & SECURE SAME.- INSTALL SPLIT WIRELINE ROTARY BUSHING.- MONITOR HOLE ON TRIP TANK, STATIC. | 7579 | 4790 | BAW | 05/14/2022 | DQ-48 | LOG | KHRS-1420
1298 | 7579 | 5537 | LOG | E | 2664 | WLT | RIH BHI LOGGING TOOLS ON 5" D/P RUN # 3 MDT LOG [ RCX ON GR ] TO 1ST PRESS POINT @ 5537'.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- TAKE CORRELATION PATH F/ 5800' TO 5670'- OPEN HOLE IN GOOD CONDITION. | 7579 | 4790 | BAW | 05/14/2022 | DQ-48 | LOG | KHRS-1420
1299 | 7579 | 5850 | LOG | E | 2664 | WLT | RIH BHI LOGGING TOOLS ON 5" D/P RUN#3 MDT LOG [ RCX ON GR ] MEANWHILE EVALUATED 12 OUT OF 23 P.POINTS AS PER RDD PROGRAM F/ 5537' TO 5850'.- RECORED 1 POINT @ PADS [ TIGHT ], 7 PRESS POPINT IN ARAB-D ZONE-1, 2 P.POINT @ ARAB-D ZONE 2 & 2 P.POINT @ ARAB-D ZONE 3 [ ONE TIGHT ].- PERFORMED STICK TENDENCY TESTS @ 5631' FOR 15 MIN, NO STICKING TENDENCY.- REPEAT POINT NO: 9, 10 & 11 TWO TIMES TILL HAVE VALID DATA.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION.> HAD ARAB-D ZONE-1 OVER BALANCE BELOW 200 PSI, DECISION MADE TO INCREASE MUD WT 1 PCF [ TO 73 PCF OBM ] TO HAVE OVERBALANCE > 200 PSI. | 7579 | 5537 | BAW | 05/14/2022 | DQ-48 | LOG | KHRS-1420
1300 | 7579 | 6500 | LOG | E | 2664 | WLT | RIH BHI LOGGING TOOLS ON 5" D/P RUN # 3 MDT LOG [ RCX ON GR ] TO 6500 FT.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7579 | 5850 | BAW | 05/14/2022 | DQ-48 | LOG | KHRS-1420
1301 | 81.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2664 | 11 May 1930 | 05/14/2022 | DQ-48 | Type | KHRS-1420
1302
1303
1304 | 2122 |  | ND | N | 2670 | DVRT | OOS - COMPLETE N/D 30" 1M DIVERTER & 24" X 30" WELD NECK FLANGE. | 2122 |  | RIG | 05/14/2022 | DQ-50L | BOP | HRDH-582
1305 | 2122 |  | OTH | N |  | NA | FINAL CUT 24" CSG & DRESS 13-3/8" CSG, WELD C PLATE & SEAL OFF 13-3/8"- 24" ANNULUS. | 2122 |  | RIG | 05/14/2022 | DQ-50L | WH | HRDH-582
1306 | 2122 |  | NU | N |  | WH | HOT-HED WELD CIW 13-3/8" X 13-5/8" 3K CHH, P/T VOIDS W/ N2 TO 1200 PSI FOR 15 MIN, OK. | 2122 |  | RIG | 05/14/2022 | DQ-50L | WH | HRDH-582
1307 | 2122 |  | OTH | N |  | NA | WAIT ON CSG HEAD TO COOL DOWN MEANWHILE:- INSTALL 2 X 2 1/16'' - 3K CWI WING VALVES. | 2122 |  | RIG | 05/14/2022 | DQ-50L | WH | HRDH-582
1308 | 2122 |  | NU | N |  | BOP | HPJSM, N/U 13-5/8" 5M CLASS "A" BOP & ALL RELATED EQUIPMENT. | 2122 |  | RIG | 05/14/2022 | DQ-50L | BOP | HRDH-582
1309 | 2122 |  | BOPT | N |  | BOP | HPJSM, P/T 13-5/8" 5M CLASS "A" BOPE AS PER ARAMCO STANDARD (300/3000 PSI, INITIAL TEST):- FLUSHED 13-5/8" 5M CLASS "A" BOPE & RELATED EQUIPMENT.- P/T ANNULAR, RAMS, VALVES & LINES TO 300/3000 PSI FOR 10 MIN EACH TEST WITH 13-5/8" TEST PLUG.- P/T WELLHEAD, SIDE OUTLET VALVES , EMERGENCY KILL LINE TO 300 /2550 PSI FOR 10 MIN EACH TEST WITH CUP TESTER.- PERFORMED ACCUMULATOR DRAW DOWN TEST.- FUNCTION TESTED DRILLER PANEL & RIG MANAGER PANEL.- FUNCTION TESTED IGNITION SYSTEM - OK.- P/T FLARE LINES TO 1,200 PSI (OFFLINE).- P/T CHOKE MANIFOLD VALVES TO 300/3000 (OFFLINE). | 2122 |  | RIG | 05/14/2022 | DQ-50L | BOP | HRDH-582
1310 | 2122 |  | SET | N |  | WBSH | INSTALLED 13-5/8" CAMERON WEAR BUSHING. | 2122 |  | RIG | 05/14/2022 | DQ-50L | WH | HRDH-582
1311 | 2122 | 0 | LDP | N |  | BHA | L/D 3 X 9 1/2" DC'S & 9 1/2" DRLG JAR. | 2122 | 0 | RIG | 05/14/2022 | DQ-50L | DRLG | HRDH-582
1312 | 2122 |  | HT | N |  | BHA | HPJSM, P/U & M/U 12-1/4" ROTARY DRLG BHA, RIH ON 5" DP, WASH DOWN LAST STD & TAG TOC @ 1,925 FT. | 2122 |  | RIG | 05/14/2022 | DQ-50L | DRLG | HRDH-582
1313 | 2122 | 2090 | DC | N |  | TDS | DRILL OUT HARD CMT, TOP CMT PLUG, F/C @ 2,035' & CMT T/ 2,090 FT - (30 FT ABOVE CSG SHOE). | 2122 | 1925 | RIG | 05/14/2022 | DQ-50L | DRLG | HRDH-582
1314 | 2122 |  | CIRC | N |  | MPMP | CHC & P/T 13-3/8" CSG TO 1500 PSI WATER EQUIVALENT- OK. | 2122 |  | RIG | 05/14/2022 | DQ-50L | DRLG | HRDH-582
1315 | 2122 | 2122 | DC | N |  | TDS | CONT. DRILL OUT CMT & 13-3/8" F/S @ 2,122' MEANWHILE DISPLACE HOLE TO FRESH 65 PCF INHIBTED POLYMER MUD. | 2122 | 2090 | RIG | 05/14/2022 | DQ-50L | DRLG | HRDH-582
1316 | 2132 |  | D | N |  | TDS | ROTARY DRILL 10' NEW FORMATION TO 2,132', 100% RETURN. | 2122 |  | RIG | 05/14/2022 | DQ-50L | DRLG | HRDH-582
1317 | 2132 |  | WCNT | N |  | NA | POOH INSIDE 13-3/8" CSG SHOE, FLOW CHECK - WELL STATIC, RECORD SCR @ RPT. | 2132 |  | RIG | 05/14/2022 | DQ-50L | DRLG | HRDH-582
1318 | 6 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | N/D 30" DIVERTER. | 1 | 2670 | 13 May 0000 | 05/14/2022 | DQ-50L | Type | HRDH-582
1319
1320
1321 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | ED-85A | Hrs | ZULF-2062
1322 | FPMP | RIG | 1 | 14 May 0400 - 0500 | 6157 | 896550 | MUD JUMPER HOSE LEAKED WHILE DRILLING. | RR | MPMP |  | 05/14/2022 | ED-85A | 1 | ZULF-2062
1323 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | ENS-108 | Hrs | SFNY-1720
1324 | UXDF | ARM | 78 | 11 May 2300 - 0500 | 8182 | 896393 | ENCOUNTERED TOTAL LOSSES. | LCIR | NA |  | 05/14/2022 | ENS-108 | 24 | SFNY-1720
1325 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | NA-393S | Hrs | HWYH-1138
1326 | FOT | WI3 | 80.5 | 11 May 1500 - 0500 | 11720 | 896461 | AFTER SETTING 7" WHIPSTOCTRIED TO PASS WITH 5-7/8" MM DIR BHA THRU WIS WHIPSTOCK WINDOW. | TF | WPSTK |  | 05/14/2022 | NA-393S | 24 | HWYH-1138
1327 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | NBR-304S | Hrs | HRDH-1952
1328 | STBH | ARM | 8 | 14 May 1015 - 1815 | 13495 | 896514 | AFETR CIRC. CYCLES 600' FROM SHOE PIPE STUCK WHILE PULLING ON ELEVATORS | STUK | BHA |  | 05/14/2022 | NBR-304S | 8 | HRDH-1952
1329 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | NBR-783S | Hrs | NJYN-89
1330 | FOT | CRW | 24 | 14 May 0500 - 0500 | 14930 | 896508 | UNABLE TO NEGATIVE TEST, PKR NOT HOLDING | BHA | WBCL |  | 05/14/2022 | NBR-783S | 24 | NJYN-89
1331 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SINO-18 | Hrs | SRYN-14
1332 | STBH | ARM | 161 | 08 May 1200 - 0500 | 840 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/14/2022 | SINO-18 | 24 | SRYN-14
1333 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SINO-1L | Hrs | KHRS-348
1334 | FOT | RIG | 7 | 14 May 1000 - 1700 | 3750 | 896547 | ATTEMPTED TO POOH WITH WFD 8 5/8" MILLING ASSY. OBSERVED POWER TONG NOT WORKING DUE TO HPU RELEIF VLV FAILURE, TROUBLSHOOT & FIXED SAME. | RR | HSYS |  | 05/14/2022 | SINO-1L | 7 | KHRS-348
1335 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SINO21 | Hrs | ABQQ-494
1336 | WTHR | ARM | 1.75 | 14 May 1415 - 1600 | 0 | 896562 | BAD WEATHER CONDITION HIGH WIND SPEED & BAD VISIBILITY | WON | NA |  | 05/14/2022 | SINO21 | 1.75 | ABQQ-494
1337 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SND-2003 | Hrs | RMTN-17
1338 | FOT | GOC | 2.5 | 13 May 0330 - 0600 | 3400 | 896506 | CRT DIES SLIPPING WHILE ATTEPMTED TO LIFT THE SLIPS. | TF | CTRQ |  | 05/14/2022 | SND-2003 | 1 | RMTN-17
1339 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SND-2004 | Hrs | BRRI-1148
1340 | FOT | RIG | 38 | 13 May 1200 - 0500 | 7657 | 896529 | RIG POWER ISSUE DUE TO FREQUENT SHUT DOWN. TROUBLESHOOT WHILE MONITORING THE WELL AT SHOE. CHANGE LOAD SHARING & SPEED CONTROL BOARD AT ENGINE#1 & REPLACE TDS SERVICE LOOP. | RR | PSYS |  | 05/14/2022 | SND-2004 | 24 | BRRI-1148
1341 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SND-2005 | Hrs | MHKK-2
1342 | FOT | RIG | 18.5 | 14 May 0700 - 0130 | 10117 | 896509 | KEEP LOSING PUMP PRESSURE ON MUD PUMPS. | RR | MPMP |  | 05/14/2022 | SND-2005 | 18.5 | MHKK-2
1343 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SND-2008 | Hrs | HRDH-1052
1344 | FOT | WDS | 17.75 | 14 May 0745 - 0500 | 11559 | 896510 | UN ABLE TO BUILD THE ANGLE DUE TO WFD RSS TOOL NOT ABLE TO ACHIEVE BUILD RATE | BHA | RSS |  | 05/14/2022 | SND-2008 | 17.75 | HRDH-1052
1345 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SP-101 | Hrs | ABQQ-710
1346 | FOT | WI1 | 416 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/14/2022 | SP-101 | 24 | ABQQ-710
1347 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SP-110 | Hrs | BRRI-562
1348 | UNKN | RIG | 4.75 | 14 May 0015 - 0500 | 8510 | 896549 | SHUT DOWN THE OPERATION TO INVESTIGATE THE DROP OBJECT INCIDENT (NAPPY PIN) WHILE PREPARING FOR SLIP & CUT DRILLING LINE. | HSEI | NA |  | 05/14/2022 | SP-110 | 4.75 | BRRI-562
1349 | XTTE | NST | 1.5 | 14 May 0330 - 0500 | 6000 | 896532 | PUMPING UNIT DIDN'T HOLD THE PRESSURE (CONT DROP SLOWLY) | TF | PUMP |  | 05/14/2022 | SP-122 | 1.5 | UTMN-2087
1350 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SP-122 | Hrs | UTMN-2087
1351 | XTTE | RIG | 2 | 14 May 0130 - 0330 | 6000 | 896531 | CHICKSAN LINE WERE NOT HOLDING THE PRESSURE | TF | STRG |  | 05/14/2022 | SP-122 | 2 | UTMN-2087
1352 | XTTE | NST | 1.5 | 14 May 0330 - 0500 | 6000 | 896532 | PUMPING UNIT DIDN'T HOLD THE PRESSURE (CONT DROP SLOWLY) | TF | PUMP |  | 05/14/2022 | SP-122 | 1.5 | UTMN-2087
1353 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SP-306 | Hrs | MNIF-196
1354 | FOT | WCR | 1 | 14 May 0330 - 0430 | 1000 | 896548 | WFD CSG POWER TONG FAILURE | TF | CTRQ |  | 05/14/2022 | SP-306 | 1 | MNIF-196
1355 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SSA-201 | Hrs | HRDH-1818
1356 | HINW | ARM | 586.25 | 17 Apr 1500 - 1015 | 14240 | 895529 | SLB RECORDING MAIN PASS (MSIP/HNGS/AIT/CAL/GR) FROM WELL TD @ 14,849 FT TO 14,502 FT, TOOL STUCK AT THIS DEPTH. | STUK | WLT |  | 05/14/2022 | SSA-201 | 5.25 | HRDH-1818
1357 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SSA-303 | Hrs | HRDH-2306
1358 | FOT | RIG | 26 | 13 May 1215 - 1930 | 8210 | 896501 | OBSERVED WASH PIPE LEAKING, CHANGED SAME. | RR | TDS |  | 05/14/2022 | SSA-303 | 14.5 | HRDH-2306
1359 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SSA-46 | Hrs | JAHM-7
1360 | FOT | SWL | 7.75 | 14 May 2115 - 0500 | 5395 | 896563 | WHILE TAKING FORMATION SAMPLE AT 5395 FT BY SLB ORA/GR ASSY. PUMP OF TOOL ASSY STOP WORKING. POOH ASSY. RIH NEW ASSY. TAKE SAMPLE AT 5395 FT. POOH. | TF | WLT |  | 05/14/2022 | SSA-46 | 7.75 | JAHM-7
1361 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SSA-51 | Hrs | MNIF-253
1362 | FPMP | RIG | 1 | 14 May 1045 - 1145 | 3244 | 896561 | FIX RIG PUMP RELIEF VALVE | RR | MPMP |  | 05/14/2022 | SSA-51 | 1 | MNIF-253
1363 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | SSA-5974 | Hrs | HRDH-1970
1364 | CWEL | ARM | 461.25 | 22 Apr 0500 - 0500 | 0 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/14/2022 | SSA-5974 | 16 | HRDH-1970
1365 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | T218 | Hrs | UTMN-1281
1366 | SRVC | HWP | 4 | 14 May 0100 - 0500 | 0 | 896515 | EXCESSIVE TIME FOR RIG UP W/L TOOLS. | WO | NA |  | 05/14/2022 | T218 | 4 | UTMN-1281
1367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/14/2022 | V140A | Hrs | SFNY-1760
1368 | FPMP | RIG | 1 | 14 May 0845 - 0945 | 1073 | 896546 | HAD MALFUNCTION IN RIG PUMPS. UNABLE TO MAKE PRESSURE #2 MUD PUMP DUE TO CAVITATION | RR | MPMP |  | 05/14/2022 | V140A | 1 | SFNY-1760
1369 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADC-21 | Hrs | MZLJ-155201
1370 | PSSW | ARM | 282.5 | 03 May 0800 - 1230 | 12600 | 896187 | WHILE BACK REAMING TO MAKE CONNECTION STRING BECAME STUCK | STUK | NA |  | 05/15/2022 | ADC-21 | 7.5 | MZLJ-155201
1371 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADC-36 | Hrs | SDGM-1234
1372 | WTHR | ARM | 5 | 15 May 0800 - 1300 | 16080 | 896596 | WAIT ON WEATHER DUE TO SAND STORM & HIGH WIND SPEED UP TO 55-60 KM/HR. | WON | NA |  | 05/15/2022 | ADC-36 | 5 | SDGM-1234
1373 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADC-45 | Hrs | KHRS-564
1374 | WTHR | ARM | 4 | 14 May 1130 - 1300 | 0 | 896564 | SUSPEND CRANE LIFT DUE TO HIGH WIND SPEED. | WON | NA |  | 05/15/2022 | ADC-45 | 2 | KHRS-564
1375 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADC-50 | Hrs | SFNY-1177
1376 | MRWL | RIG | 35 | 14 May 1800 - 0500 | 0 | 896533 | WHILE LIFTING 13-5/8" BOP AFTER N/D, BOP STACK MOVED AND BENT ESP CABLE. PERFORMED VARIOUS TESTS ON ESP CABLE: PHASE-TO-PHASE, PHASE-TO-GROUND, AND 5 KV VOLTAGE TEST - ALL OKAY. DISCUSSION WITH TOWN DETERMINED THAT DAMAGE TO CABLE COULD RESULT IN REDUCED LIFESPAN OF THE ESP. DECISION MADE TO RECOMPLETE. | BOP | BOP |  | 05/15/2022 | ADC-50 | 24 | SFNY-1177
1377 | 157 |  | RIG | TO | 2584 | 7109 | CONT'D POOH CONTROLLED SPEED W/MDT - TLC STRING ON 4" DP FFROM 4,447 FT TO TOP OF LOGGING TOOLS.- CONTROLLED SPEED 3 MIN FROM SLIPS TO SLIPS.- MONITOR WELL ON TRIP TANK - OK. | 4447 |  | 7109 | 05/15/2022 | ADC-53L | STDP | UTMN-4069
1378 |  |  | RIG | OTH | 2584 | 7109 | FLOW CHECK - WELL STATIC. |  |  | 7109 | 05/15/2022 | ADC-53L | NA | UTMN-4069
1379 |  | 896567 | RIG | WO | 2584 | 7109 | WAIT ON WEATHER DUE TO SAND STORM, POOR VISIBILITY & HIGH WIND SPEED ABOVE 50 KM/HR. SUSPENDED CRANE OPERATION FOR L/D LOGGING TOOLS.- INSTALLED SAFETY VALVE TO STRING & CLOSED SAME- KEEP MONITRING WELL ON TRIP TANK. |  | WON | 7109 | 05/15/2022 | ADC-53L | NA | UTMN-4069
1380 |  |  | SWL | OTH | 2584 | 7109 | HPJSM, L/D SLB MDT-GR LOGGING TOOL.- MONITOR WELL ON TRIP TANK. |  |  | 7109 | 05/15/2022 | ADC-53L | NA | UTMN-4069
1381 | 4620 |  | RIG | TI |  | 7109 | HPJSM, M/U & RIH 4" OEDP STRING TO 4620 FT (SHOE)- MONITOR WELL ON TRIP TANK. | 0 |  | 7109 | 05/15/2022 | ADC-53L | STDP | UTMN-4069
1382 |  |  | RIG | CIRC |  | 7109 | M/U TDS AND BREAK CIRC AT SHOE AT 300 GPM. |  |  | 7109 | 05/15/2022 | ADC-53L | MPMP | UTMN-4069
1383 | 7000 |  | RIG | TI |  | 7109 | CONTD RIH 4" OEDP STRING TO 7000 FT. BREAK CIRC EVERY 1000 FT RAN.- MONITOR WELL ON TRIP TANK. | 4620 |  | 7109 | 05/15/2022 | ADC-53L | STDP | UTMN-4069
1384 |  |  | RIG | CIRC |  | 7109 | M/U TDS AND WASHED LAST STAND TO BTM AT 7109 FT. CIRC HOLE AT 250 GPM W/ 460 PSI. 100% CIRCULATION WITH 80 PCF MW IN/OUT. |  |  | 7109 | 05/15/2022 | ADC-53L | MPMP | UTMN-4069
1385 |  |  | RIG | OTH |  | 7109 | PJSM. M/U FOSV, SES AND CMTG LINES. FLUSHED LINES AND PRESSURE TESTED LINES TO 500/3000 PSI FOR 5/10 MINS.- MONITOR WELL ON TRIP TANK. |  |  | 7109 | 05/15/2022 | ADC-53L | NA | UTMN-4069
1386 | 6609 |  | SCM | CMP |  | 7109 | PJSM. SLB PERFORM P&A CEMENT PLUG#1 (7,109' - 6,609') AS FOLLOWS:- SLB PUMPED 60 BBLS X 90 PCF SLB MUD PUSH AHEAD- SLB PUMPED 53 BBLS OF BATCH MIXED 125 PCF CEMENT- SLB PUMPED 12 BBLS X 90 PCF MUD PUSH BEHIND- SLB DISPLACED WITH 50.3 BBLS OF 80 PCF MUD (SLOW DOWN PUMP RATE TO 3 BPM FOR LAST 10 BBLS). 100% CIRCULATION.- CIP AT 0345 HRS. | 7109 |  | 7109 | 05/15/2022 | ADC-53L | OEDP | UTMN-4069
1387 | 5800 |  | RIG | ST |  | 7109 | POOH FIRST 7 STANDS AT CONTROLLED SPEED (5 MIN/STD) AND NORMAL SPEED ON LAST 7 STANDS (WITH DRY PIPE) TO 5,800 FT.- MONITOR WELL ON TRIP TANK. | 7100 |  | 7109 | 05/15/2022 | ADC-53L | STDP | UTMN-4069
1388 |  |  | RIG | CIRC |  | 7109 | M/U CIRC HEAD, FOSV & X/O'S. CLOSED ANNULAR AND REVERSE CIRCULATE 1.5 X STRING VOLUME (94 BBLS)...ON GOING AT REPORT TIME. |  |  | 7109 | 05/15/2022 | ADC-53L | MPMP | UTMN-4069
1389 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADC-53L | Hrs | UTMN-4069
1390 | WTHR | OTH | 9.5 | 15 May 0845 - 1815 | 7109 | 896567 | BAD WEATHER DUE TO SAND STORM, POOR VISIBILITY & HIGH WIND SPEED ABOVE 50 KM/HR. SUSPENDED CRANE OPERATION FOR L/D LOGGING TOOLS. | WON | NA |  | 05/15/2022 | ADC-53L | 9.5 | UTMN-4069
1391 | 271.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | E-LOGGING FOR 8-1/2" PILOT HOLE, P&A PILOT HOLE. | 14.75 | 2584 | 04 May 0100 | 05/15/2022 | ADC-53L | Type | UTMN-4069
1392
1393
1394 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADC-58L | Hrs | ABHD-178
1395 | HERR | TK3 | 4 | 15 May 0500 - 1315 | 10258 | 896570 | OBSERVED CSG JTS HAD MAXIMUM TQ WHILE MOST OF THE THREAD STILL NOT CONNECTED, THREAD FAILED. | JF | NA |  | 05/15/2022 | ADC-58L | 4 | ABHD-178
1396 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADC-60 | Hrs | ABSF-213
1397 | MRWL | RIG | 6 | 15 May 0700 - 1300 | 0 | 896575 | ATTEMPT TO ENGAGE KFDJ DIVERTER + OVERSHOT ASSY ONTO MANDREL WITHOUT SUCCESS. | BOP | DVRT |  | 05/15/2022 | ADC-60 | 6 | ABSF-213
1398 | 7406 | 6993 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 5 OUT OF 7 AT 6,993 FT (AD2A FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING AT 6,993 FT AND DECIDE TO PERFORM SAMPLING WITH XLD PROBE.- PUMP OUT INTO WELLBORE 1.65 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 4.48 BBLS, (FLUID TYPE: OIL).- HYDROSTATIC DROP= 23 PSI, OVERBALANCE, AS PER MDT 332 PSI.- AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 | 6993 | SWL | 05/15/2022 | ADC-62L | LOG | ANDR-745
1399 | 7406 | 6699 | LOG | E | 2684 | WLT | (OOS) RECORDED PRESSURE POINTS AT 6,695 FT, 6,697 FT & 6,699 FT.- RECORDED (3) PRESSURE POINTS SUCCESSFULLY (COMPLETED TOTAL 18/21).- PERFORM STICK TESTS: 5,10 & 15 MINS BEFORE PRESSURE POINT.- RECORDED PRESSURE POINTS IN ARBC FORMATION.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 | 6695 | SWL | 05/15/2022 | ADC-62L | LOG | ANDR-745
1400 | 7406 | 6989 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 6 OUT OF 7 AT 6,989 FT (ABD1 FM).- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING AT 6,989 FT AND DECIDE TO PERFORM SAMPLING WITH XLD PROBE.- PUMP OUT INTO WELLBORE 0.97 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 5.45 BBLS, (FLUID TYPE: OIL).- HYDROSTATIC DROP= 28 PSI, OVERBALANCE, AS PER MDT 329 PSI.- AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 | 6989 | SWL | 05/15/2022 | ADC-62L | LOG | ANDR-745
1401 | 7406 | 7001 | LOG | E | 2684 | WLT | (OOS) RECORDED PRESSURE POINTS AT 6,995 FT, 6,997 FT & 7,001 FT.- RECORDED (3) PRESSURE POINTS SUCCESSFULLY (COMPLETED TOTAL 21/21).- PERFORM STICK TESTS: 5,10 & 15 MINS BEFORE PRESSURE POINT.- RECORDED PRESSURE POINTS IN ARBC FORMATION.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 | 6995 | SWL | 05/15/2022 | ADC-62L | LOG | ANDR-745
1402 | 7406 | 6969 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 7 OUT OF 7 AT 6,969 FT (PADS FM)...INC @ RPT.- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP ONGOING.- MONITORED WELL ON TRIP TANK, WELL STATIC.** LAST CIRCULATION ON 10TH MAY @ 08:30 HR. TIME FROM LAST CIRCULATION: 44.50 HRS. | 7406 | 6969 | SWL | 05/15/2022 | ADC-62L | LOG | ANDR-745
1403 | 114.25 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORM PRESSURE POINTS AND SAMPLING UNDER OOS AS PER DP. | 24 | 2684 | 11 May 0300 | 05/15/2022 | ADC-62L | Type | ANDR-745
1404
1405
1406 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADC-65L | Hrs | HWYH-1280
1407 | FWTS | SDM | 79 | 12 May 1600 - 0500 | 5432 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/15/2022 | ADC-65L | 24 | HWYH-1280
1408 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADES-14 | Hrs | HWYH-530
1409 | WTHR | ARM | 4.5 | 15 May 1300 - 1730 | 0 | 896584 | WAIT ON WEATHER | WON | NA |  | 05/15/2022 | ADES-14 | 4.5 | HWYH-530
1410 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADES-144 | Hrs | UTMN-3099
1411 | WTHR | ARM | 3 | 15 May 1200 - 1500 | 11909 | 896555 | WAIT ON WEATHER, HIGH WIND SPEED WITH SAND AND LOW VISIBILTY. UNABLE TO WORK CRANE AND HANDLE TOOLS. WIND SPEED @ 45 - 60 KPH. | WON | NA |  | 05/15/2022 | ADES-144 | 3 | UTMN-3099
1412 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADES-157 | Hrs | HRDH-1260
1413 | FOT | ITS | .5 | 15 May 0130 - 0200 | 16204 | 896619 | ITS POWER TONG DIDN'T WORK, PROBLEM ON BRAKE SYSTEM AND DIES. | TF | TTRQ |  | 05/15/2022 | ADES-157 | .5 | HRDH-1260
1414 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADES-889 | Hrs | HRDH-1858
1415 | FOT | RIG | 4 | 15 May 1200 - 1600 | 13927 | 896569 | COMMUNICATION LOST BETWEEN VFD & TOP DRIVE. CHANGE AND FIX VFD RECTIFIER. FUNCTION TEST - OK. | RR | PSYS |  | 05/15/2022 | ADES-889 | 4 | HRDH-1858
1416 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ADM-656 | Hrs | SFNY-397
1417 | SRVC | SBA | 15 | 15 May 1400 - 0500 | 0 | 896585 | WAITNG ON BORETS ESP SUPERVISOR TO RUN UPPER ESP COMPLETION. > BORETS ESP SUPERVISOR DID'NT ATTEND THE CHOPPER BOOKING TWICE SINCE 13TH MAY. > BORETS SUPERVISOR BOOKED ON 13TH MAY MORNING/AFTERNOON FLIGHT - NOT ABLE TO CHECK IN. | WO | NA |  | 05/15/2022 | ADM-656 | 15 | SFNY-397
1418 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ARO-3001 | Hrs | ZULF-2053
1419 | FOT | RIG | 1.5 | 15 May 2030 - 2200 | 8059 | 896618 | HAD LEAKAGE FROM SWIVEL WHILE DRILLING. | RR | SWVL |  | 05/15/2022 | ARO-3001 | 1.5 | ZULF-2053
1420 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ARO-4001 | Hrs | MRJN-539
1421 | HERR | HCO | 6.5 | 15 May 2230 - 0500 | 7696 | 896598 | OBSERVED PIECE OF MATERIAL BELOW TUBING HANGER & BLOCK ONE SIDE OUTLET OF TUBING SPOOL, INVESTIGATE THE MATTER. | TF | TBG |  | 05/15/2022 | ARO-4001 | 6.5 | MRJN-539
1422 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | DPS-4 | Hrs | MDRK-54
1423 | FOT | BCR | .5 | 15 May 1130 - 1200 | 15700 | 896568 | PRIMARY 7" CASING ELEVATOR UNABLE TO LATCH 7" CSG. | TF | CTRQ |  | 05/15/2022 | DPS-4 | .5 | MDRK-54
1424 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | DPS-74 | Hrs | NJYN-54
1425 | FOT | BLH | 758 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/15/2022 | DPS-74 | 23.5 | NJYN-54
1426 | 7579 | 7549 | LOG | E | 2664 | WLT | RIH BHI LOGGING TOOLS MDT LOG [ RCX ON GR ] ON 5" D/P RUN# 3 FROM 6500' TO 7549 FT.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7579 | 6500 | BAW | 05/15/2022 | DQ-48 | LOG | KHRS-1420
1427 | 7579 |  | CIRC | E | 2664 | MPMP | SWEPT HOLE & CHC WHILE INCREASE MUD WT FROM 72 TO 73 PCF OBM [ 200 GPM / 300 PSI ] TO INCREASE OVER BALANCE ACROSS ARAB-D ZONE-1.- AFTER DISPLACE HOLE TO 73 PCF, OB INCREASE FROM 186 PSI TO +/- 223 PSI AGAINST ARAB-D ZONE-1. | 7579 |  | RIG | 05/15/2022 | DQ-48 | LOG | KHRS-1420
1428 | 7579 | 7305 | LOG | E | 2664 | WLT | POOH BHI LOGGING TOOLS RUN# 3 MDT [ RCX ON GR ] ON 5" D/P MEANWHILE EVALUATED REMAINING 10 P.POINTS AS PER RDD PROGRAM F/ 7413' T0 7305'.- TOTAL 22 / 23 POINT'S: 1 POINT @ PADS [ TIGHT ], 11 IN ARAB-D ZONE-1, 2 & 3 [ 1 TIGHT & 10 VALIED ] & 10 POINT @ LFDR [ 4 TIGHT & 6 VALIED ].- REPEAT POINT NO: 16, 19 & 22 ONE FT UP OR DOWN DUE TO POOR MOBILITY TILL GOT VALID DATA.- PERFORMED STICK TENDENCY TESTS @ 7355' FOR 15 MIN, NO STICKING TENDENCY.- RECIPROCATE STRING EVERY 30 MIN, NO OVERPULL OBSERVED.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7579 | 7413 | BAW | 05/15/2022 | DQ-48 | LOG | KHRS-1420
1429 | 7579 | 7305 | LOG | E | 2664 | WLT | PERFORMED STICK TENDENCY TESTS @ 7305' [ 1ST SAMPLE POINT DEPTH ] FOR 60 MIN, NO STICKING TENDENCY. | 7579 | 7305 | BAW | 05/15/2022 | DQ-48 | LOG | KHRS-1420
1430 | 7579 | 7305 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 1ST SAMPLE [ 1 OUT OF 9 SAMPLE ] @ 7305'.- ATTEMPTED TO PUMP OUT WITH RCI XL PKR @ 7305' & 7304', ABORTED DUE TO LOW MOBILITY.- WITH RCI XL PKR @ 7306', START 1ST CYCLE FOR 2.5 HRS WITH LOW MOBILITY, 4 HRS WITH STRADDLE PKR, LOW MOBILITY,- 3RD CYCLE WITH STRADDLE IN PROGRESS @ RT, NO SAMPLE COLLECT TILL THE MOMENT.- SAMPLE# 1 [ LFDR FM ] @ 7306': TOTAL DUMPING IN ANNUL: 1.03 BBL / WATER.- MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.- NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- TOTAL HRS SINCE LAST CIRCULATION : 20 HRS. | 7579 | 7305 | BAW | 05/15/2022 | DQ-48 | LOG | KHRS-1420
1431 | 105.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2664 | 11 May 1930 | 05/15/2022 | DQ-48 | Type | KHRS-1420
1432
1433
1434 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ED-85A | Hrs | ZULF-2062
1435 | FOT | RIG | 7.5 | 14 May 0430 - 1200 | 6157 | 896550 | MUD JUMPER HOSE LEAKED WHILE DRILLING. | RR | CSYS |  | 05/15/2022 | ED-85A | 7 | ZULF-2062
1436 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | ENS-108 | Hrs | SFNY-1720
1437 | UXDF | ARM | 95.5 | 11 May 2300 - 2230 | 8182 | 896393 | ENCOUNTERED TOTAL LOSSES. | LCIR | NA |  | 05/15/2022 | ENS-108 | 17.5 | SFNY-1720
1438 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | HI-2 | Hrs | BRRI-464
1439 | WTHR | ARM | 12 | 15 May 1700 - 0500 | 14802 | 896551 | UNABLE TO WORK WITH SUPPLY VESSELS DUE TO UNFAVORABLE WEATHER CONDITIONS. | WON | NA |  | 05/15/2022 | HI-2 | 12 | BRRI-464
1440 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | HWU-1 | Hrs | HZEM-162802
1441 | WTHR | ARM | 17.25 | 14 May 1100 - 2015 | 2000 | 896566 | CRANE AND MANLIFT OPERATIONS SUSPENDED DUE TO WINDS 80+KPH. MONITOR WINDS AND REPORT EVERY 30 MIN | WON | NA |  | 05/15/2022 | HWU-1 | 9.25 | HZEM-162802
1442 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | MP-1 | Hrs | MRJN-305
1443 | UDWL | BHI | 1.75 | 15 May 0715 - 0900 | 10965 | 896578 | TROUBLE SHOOTING ISSUES WITH BAKER RSS, INCOMPLETE SIGNAL. | DD | RSS |  | 05/15/2022 | MP-1 | 1.75 | MRJN-305
1444 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | NA-128S | Hrs | SAHB-28
1445 | FOT | SPS | 10 | 15 May 1900 - 0500 | 13476 | 896583 | MWD TOOLS FAILED TO TRANSMIT SURVEYS. | BHA | MWD |  | 05/15/2022 | NA-128S | 10 | SAHB-28
1446 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | NA-18S | Hrs | UTMN-2334
1447 | STBH | ARM | 88 | 12 May 1300 - 0500 | 14361 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/15/2022 | NA-18S | 24 | UTMN-2334
1448 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | NA-393S | Hrs | HWYH-1138
1449 | FOT | WI3 | 99 | 11 May 1500 - 0500 | 11720 | 896461 | AFTER SETTING 7" WHIPSTOCTRIED TO PASS WITH 5-7/8" MM DIR BHA THRU WIS WHIPSTOCK WINDOW. | TF | WPSTK |  | 05/15/2022 | NA-393S | 18.5 | HWYH-1138
1450 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | NBR-304S | Hrs | HRDH-1952
1451 | WTHR | OTH | 8 | 15 May 0945 - 1745 | 4571 | 896579 | SUSPEND TRIP DUE TO HIGH WINDS | WON | NA |  | 05/15/2022 | NBR-304S | 8 | HRDH-1952
1452 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | NBR-783S | Hrs | NJYN-89
1453 | FOT | CRW | 45.75 | 14 May 0500 - 0500 | 14930 | 896508 | UNABLE TO NEGATIVE TEST, PKR NOT HOLDING | BHA | WBCL |  | 05/15/2022 | NBR-783S | 21.75 | NJYN-89
1454 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SINO-12L | Hrs | HRDH-1454
1455 | WTHR | ARM | 6 | 15 May 1300 - 1900 | 0 | 896597 | SUSPEND OPERATION DUE TO HIGH WIND SPEED AND STONG SAND STORM. | WON | NA |  | 05/15/2022 | SINO-12L | 6 | HRDH-1454
1456 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SINO-18 | Hrs | SRYN-14
1457 | STBH | ARM | 185 | 08 May 1200 - 0500 | 840 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/15/2022 | SINO-18 | 24 | SRYN-14
1458 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SINO21 | Hrs | ABQQ-494
1459 | WTHR | ARM | 2.75 | 14 May 1415 - 1245 | 0 | 896562 | BAD WEATHER CONDITION, HIGH WIND SPEED & BAD VISIBILITY. | WON | NA |  | 05/15/2022 | SINO21 | 1 | ABQQ-494
1460 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SND-1502 | Hrs | HRDH-121
1461 | WTHR | ARM | 5.5 | 15 May 1200 - 1730 | 0 | 896553 | BAD WEATHER CONDITION, HIGH WIND SPEED & BAD VISIBILITY. | WON | NA |  | 05/15/2022 | SND-1502 | 5.5 | HRDH-121
1462 | SROP | NOC | .5 | 15 May 2100 - 2130 | 9663 | 896616 | NO PROGRESS DUE TO 8-1/2" CORE JAMMED. | JF | CORC |  | 05/15/2022 | SND-2004 | .5 | BRRI-1148
1463 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SND-2004 | Hrs | BRRI-1148
1464 | FOT | RIG | 46 | 13 May 1200 - 1300 | 7657 | 896529 | RIG POWER ISSUE DUE TO FREQUENT SHUT DOWN. TROUBLESHOOT WHILE MONITORING THE WELL AT SHOE. CHANGE LOAD SHARING & SPEED CONTROL BOARD AT ENGINE#1 & REPLACE TDS SERVICE LOOP. | RR | PSYS |  | 05/15/2022 | SND-2004 | 8 | BRRI-1148
1465 | SROP | NOC | .5 | 15 May 2100 - 2130 | 9663 | 896616 | NO PROGRESS DUE TO 8-1/2" CORE JAMMED. | JF | CORC |  | 05/15/2022 | SND-2004 | .5 | BRRI-1148
1466 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SND-2007 | Hrs | ADHN-370100
1467 | FOT | BHI | 15 | 15 May 1400 - 0500 | 16323 | 896573 | OBSERVED FAILURE ON BAKER ATK RIP #3, NO PRESSURE ON IT, TROUBLESHOOTING THE TOOL-NO SUCCESS | BHA | RSS |  | 05/15/2022 | SND-2007 | 15 | ADHN-370100
1468 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SND-2008 | Hrs | HRDH-1052
1469 | FOT | WDS | 29.25 | 14 May 0745 - 1630 | 11559 | 896510 | UN ABLE TO BUILD THE ANGLE DUE TO WFD RSS TOOL NOT ABLE TO ACHIEVE BUILD RATE | BHA | RSS |  | 05/15/2022 | SND-2008 | 11.5 | HRDH-1052
1470 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SP-101 | Hrs | ABQQ-710
1471 | FOT | WI1 | 440 | 27 Apr 1100 - 0500 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/15/2022 | SP-101 | 24 | ABQQ-710
1472 | FOT | RIG | 7 | 15 May 2200 - 0500 | 11857 | 896552 | REPLACE HARPOON COONECTION PART . | RR | TDS |  | 05/15/2022 | SP-110 | 7 | BRRI-562
1473 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SP-110 | Hrs | BRRI-562
1474 | UNKN | RIG | 21.75 | 14 May 0015 - 2200 | 8510 | 896549 | SHUT DOWN THE OPERATION TO INVESTIGATE THE DROP OBJECT INCIDENT (NAPPY PIN) WHILE PREPARING FOR SLIP & CUT DRILLING LINE. | HSEI | NA |  | 05/15/2022 | SP-110 | 17 | BRRI-562
1475 | FOT | RIG | 7 | 15 May 2200 - 0500 | 11857 | 896552 | REPLACE HARPOON COONECTION PART . | RR | TDS |  | 05/15/2022 | SP-110 | 7 | BRRI-562
1476 | GRF | RIG | .5 | 15 May 1900 - 1930 | 6000 | 896617 | RIG POWER SUDDENLY DISCONNECTED DUE TO ELECTRIC PROBLEM IN SCR ROOM. | UPRA | PSYS |  | 05/15/2022 | SP-122 | .5 | UTMN-2087
1477 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SP-122 | Hrs | UTMN-2087
1478 | XTTE | NST | 13.75 | 14 May 0300 - 0500 | 6000 | 896532 | NESR PUMPING UNIT NOT HOLDING PRESSURE. | TF | PUMP |  | 05/15/2022 | SP-122 | 11.75 | UTMN-2087
1479 | GRF | RIG | .5 | 15 May 1900 - 1930 | 6000 | 896617 | RIG POWER SUDDENLY DISCONNECTED DUE TO ELECTRIC PROBLEM IN SCR ROOM. | UPRA | PSYS |  | 05/15/2022 | SP-122 | .5 | UTMN-2087
1480 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SP-161 | Hrs | HWYH-680
1481 | WTHR | ARM | 3.5 | 15 May 1130 - 1500 | 7285 | 896636 | WAIT ON BAD WEATHER ( HIGH WIND SPEED AND HEAVY SAND STORM ). | WON | NA |  | 05/15/2022 | SP-161 | 3.5 | HWYH-680
1482 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SP-259 | Hrs | HZEM-160402
1483 | FOT | ITS | 6.5 | 15 May 2230 - 0500 | 17307 | 896586 | CRT FILL UP SPEAR SEALS BROKEN | TF | CTRQ |  | 05/15/2022 | SP-259 | 6.5 | HZEM-160402
1484 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SP-262 | Hrs | HZEM-140802
1485 | WTHR | ARM | 4 | 15 May 1000 - 1400 | 7690 | 896581 | SHUT DOWN RUNNING 9-5/8" CSG OPERATIONS DUE TO SANDSTORM BLOWING HIGH WINDS. | WON | NA |  | 05/15/2022 | SP-262 | 4 | HZEM-140802
1486 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SSA-102 | Hrs | QTIF-696
1487 | UNKN | RIG | 4.5 | 15 May 0700 - 1730 | 19720 | 896535 | ELMAGO BRAKE FAILED & TDS W/STRING DESCENDED WHILE CIRCULATION & RECIPROCATION ON BTM; WHICH CAUSED THE STAND ABOVE ROTARY TO BEND & TWIST AROUND TDS RAIL BEAM. | HSEI | NA |  | 05/15/2022 | SSA-102 | 4.5 | QTIF-696
1488 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SSA-51 | Hrs | MNIF-253
1489 | CFFM | ARM | .75 | 15 May 1400 - 1445 | 4244 | 896571 | TOTAL LOSSES AT 4244 FT (ARUMA FM) | LCIR | MDCAP |  | 05/15/2022 | SSA-51 | .75 | MNIF-253
1490 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SSA-5971 | Hrs | HRDH-2247
1491 | FOT | RIG | 2 | 15 May 1300 - 1500 | 200 | 896574 | TDS STOPPED WORKING SEVERAL TIMES AND LOST ALL CONTROLS. | RR | TDS |  | 05/15/2022 | SSA-5971 | 2 | HRDH-2247
1492 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SSA-5972 | Hrs | JFYN-10
1493 | WTHR | ARM | 3.5 | 15 May 1100 - 1430 | 9500 | 896554 | OBSERVED HIGH WIND DURING TRIPPING OPERATIONS. | WON | NA |  | 05/15/2022 | SSA-5972 | 3.5 | JFYN-10
1494 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | SSA-5974 | Hrs | HRDH-1970
1495 | CWEL | ARM | 485.25 | 22 Apr 0500 - 0500 | 0 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/15/2022 | SSA-5974 | 24 | HRDH-1970
1496 | WTHR | ARM | 2.5 | 15 May 1600 - 1830 | 0 | 896582 | WAIT ON WEATHER | WON | NA |  | 05/15/2022 | T218 | 2.5 | UTMN-1281
1497 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/15/2022 | T218 | Hrs | UTMN-1281
1498 | FOT | SCP | 5 | 15 May 1830 - 2330 | 0 | 896580 | FAILED TO SET SLB 4-1/2" PTP. | TF | PLUGT |  | 05/15/2022 | T218 | 5 | UTMN-1281
1499 | WTHR | ARM | 2.5 | 15 May 1600 - 1830 | 0 | 896582 | WAIT ON WEATHER | WON | NA |  | 05/15/2022 | T218 | 2.5 | UTMN-1281
1500 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | ADC-50 | Hrs | SFNY-1177
1501 | MRWL | RIG | 59 | 14 May 1800 - 0500 | 0 | 896533 | WHILE LIFTING 13-5/8" BOP AFTER N/D, BOP STACK MOVED AND BENT ESP CABLE. PERFORMED VARIOUS TESTS ON ESP CABLE: PHASE-TO-PHASE, PHASE-TO-GROUND, AND 5 KV VOLTAGE TEST - ALL OKAY. DISCUSSION WITH TOWN DETERMINED THAT DAMAGE TO CABLE COULD RESULT IN REDUCED LIFESPAN OF THE ESP. DECISION MADE TO RECOMPLETE. | BOP | BOP |  | 05/16/2022 | ADC-50 | 24 | SFNY-1177
1502 | 7406 | 6969 | LOG | E | 2684 | WLT | (OOS) SLB MDT-TLC COLLECT SAMPLE 7 OUT OF 7 AT 6,969 FT (PADS FM)- PERFORMED CORRELATION & STICKY TEST FOR 5, 10, 15, 20 & 40 MIN AND CHECKED STRING AFTER EACH STEP- STRING FREE.- ENG PERFORMED SCANNING AT 6,969 FT AND DECIDE TO PERFORM SAMPLING WITH SATURN PACKER.- PUMP OUT INTO WELLBORE 1.28 BBLS, TOTAL FLUID PUMPED OUT INTO WELLBORE: 6.73 BBLS, (FLUID TYPE: OIL).- HYDROSTATIC DROP= 35 PSI, OVERBALANCE, AS PER MDT 474 PSI.- AFTER EVERY SESSION (4 HRS) MOVE STRING & CONFIRM STRING FREE, NO OVERPUL.- MONITORED WELL ON TRIP TANK, WELL STATIC.** LAST CIRCULATION ON 13TH MAY @ 15:00 HR. TIME FROM LAST CIRCULATION: 45.5 HRS. | 7406 | 6969 | SWL | 05/16/2022 | ADC-62L | LOG | ANDR-745
1503 | 7406 |  | OTH | E | 2684 | NA | (OOS) RIH WIRELINE MDT-GR TLC STRING F/ 6,969 FT TO 7,295 FT.- TRIPPING SPEED: 3 MIN SLIP-TO-SLIP AS PER SLB WL ENGINEER.- MONITORED WELL ON TRIP TANK, WELL STATIC. | 7406 |  | RIG | 05/16/2022 | ADC-62L | LOG | ANDR-745
1504 | 7406 |  | CIRC | E | 2684 | MPMP | (OOS) CIRCULATED OH ANNULAR VOLUME TO UNLATCH DEPTH (INSIDE 9-5/8" CSG). FR: 100 GPM, SPP: 250 PSI.- INCREASED FR GRADUALLY IN STEPS TO 100 GPM.- RECIPROCATE THE STRING WHILE CIRC.- NO DOWN HOLE DYNAMIC LOSSES.** PERFORMED FLOW CHECK, WELL STATIC. | 7406 |  | RIG | 05/16/2022 | ADC-62L | LOG | ANDR-745
1505 | 7406 |  | OTH | E | 2684 | NA | (OOS) POOH WIRELINE MDT-GR TLC STRING F/ 7,295 FT TO 4,814 FT UNLATCH DEPTH (INSIDE 9-5/8" CSG).- POOH AT CONTROLLED SPEED: 3 MIN/STD.- OH IN GOOD CONDITION.- MONITOR WELL ON TRIP TANK.** PERFORM FLOW CHECK @ 9-5/8" CSG SHOE, WELL STATIC. | 7406 |  | RIG | 05/16/2022 | ADC-62L | LOG | ANDR-745
1506 | 7406 |  | SDR1 | E | 2684 | NA | (OOS) PERFORMED FIRE DRILL WITH MAN DOWN.- HELD CRITIQUE MEETING AND DISCUSSED FEEBLE POINT WITH THE CREW. | 7406 |  | RIG | 05/16/2022 | ADC-62L | LOG | ANDR-745
1507 | 7406 |  | OTH | E | 2684 | NA | (OOS) UNLATCH THE WL CABLE.- POOH WL CABLE TO SURFACE, L/D WL SES.- PJSM, R/D WL SHEAVES. | 7406 |  | SWL | 05/16/2022 | ADC-62L | LOG | ANDR-745
1508 | 7406 |  | CIRC | E | 2684 | MPMP | (OOS) CIRCULATE 1.2 BTM UP. FR: 200 GPM, SPP: 320 PSI. MW IN/OUT: 84 PCF.- PRECAUTIONARY CIRC. THROUGH CHOKE & POOR BOY DEGASSER.- NO CUT IN MW.** PERFORM 30 MIN FLOW CHECK, WELL STATIC. | 7406 |  | RIG | 05/16/2022 | ADC-62L | LOG | ANDR-745
1509 | 7406 |  | OTH | E | 2684 | NA | (OOS) POOH WIRELINE MDT-GR TLC STRING F/ 4,814 FT TO 483 FT.- POOH AT CONTROLLED SPEED: 3 MIN/STD.- MONITOR WELL ON TRIP TANK.** PERFORM FLOW CHECK, WELL STATIC. | 7406 |  | RIG | 05/16/2022 | ADC-62L | LOG | ANDR-745
1510 | 7406 |  | OTH | E | 2684 | NA | (OOS) POOH WL TLC MDT-GR STRING TO SURFACE & L/D SAME.- L/D 3-1/2" IF X XT39 + XT39 X 4-1/2" IF XO'S.- R/B 3 X 5'' HWDP STD.- L/D WIRELINE MDT TOOL STRING.- MONITOR WELL ON TRIPTANK, OK. | 7406 |  | SWL | 05/16/2022 | ADC-62L | LOG | ANDR-745
1511 | 7406 |  | HT | E |  | STRG | HELD PRE JOB SAFETY MEETING PRIOR TO M/U 4" OEDP CMT STINGER.- R/U 4" DP LIFTING GEAR. | 7406 |  | RIG | 05/16/2022 | ADC-62L | PA | ANDR-745
1512 | 138 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORM PRESSURE POINTS AND SAMPLING UNDER OOS AS PER DP. | 23.75 | 2684 | 11 May 0300 | 05/16/2022 | ADC-62L | Type | ANDR-745
1513
1514
1515 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | ADC-65L | Hrs | HWYH-1280
1516 | FWTS | SDM | 103 | 12 May 1600 - 0500 | 5432 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/16/2022 | ADC-65L | 24 | HWYH-1280
1517 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | ADM-266 | Hrs | SFNY-934
1518 | FOT | ARM | 19.75 | 15 May 2115 - 1700 | 5731 | 896601 | BREAK CIRCULATION PUMPED 4 BBL OBM OBSERVE PRESSURE INDICATING 3-1/4" CSH TBG DRIFT STRING PLUGGED. | DSF | STRG |  | 05/16/2022 | ADM-266 | 12 | SFNY-934
1519 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | ADM-337 | Hrs | MRJN-900
1520 | FOT | SAM | 2 | 16 May 0030 - 0230 | 0 | 896604 | WHILE FUNCTION TEST PBL SUB ON SURFACE, OBSERVED TOOL IS NOT CLOSING PROBABLY, LD PBL SUB. | BHA | MACS |  | 05/16/2022 | ADM-337 | 2 | MRJN-900
1521 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | ADM-656 | Hrs | SFNY-397
1522 | SRVC | SBA | 6 | 16 May 0500 - 1100 | 0 | 896603 | WAITNG ON BORETS ESP SUPERVISOR TO RUN UPPER ESP COMPLETION. > BORETS ESP SUPERVISOR DID'NT ATTEND THE CHOPPER BOOKING TWICE SINCE 13TH MAY AND NOT ABLE TO CHECK IN. | WO | NA |  | 05/16/2022 | ADM-656 | 6 | SFNY-397
1523 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | ARO-4001 | Hrs | MRJN-539
1524 | HERR | HCO | 16 | 15 May 2230 - 1430 | 7696 | 896598 | OBSERVED PIECE OF FABRIC (RAG) BELOW TUBING HANGER & BLOCK ONE SIDE OUTLET OF TUBING SPOOL, INVESTIGATE THE MATTER. | TF | TBG |  | 05/16/2022 | ARO-4001 | 9.5 | MRJN-539
1525 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | BCTD-3 | Hrs | HWYH-1029
1526 | ORDS | ARN | 10.5 | 15 May 0130 - 1200 | 12105 | 896625 | WAIT ON GRMD TO APPROVE 2ND LATERAL PLAN. | WO | NA |  | 05/16/2022 | BCTD-3 | 7 | HWYH-1029
1527 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | DPS-74 | Hrs | NJYN-54
1528 | FOT | BLH | 781.5 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/16/2022 | DPS-74 | 23.5 | NJYN-54
1529 | 7579 | 7305 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], CON'T WORK TO COLLECT 1ST SAMPLE [ 1 OUT OF 9 SAMPLE ] @ 7305'.- FINISH 3RD CYCLE WITH STRADDLE PKR @ 7306', COLLECT SAMPLE @ 7306 FT.- SAMPLE# 1 [ LFDR FM ] @ 7306': TOTAL DUMPING IN ANNUL: 1.9 BBL / WATER.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 7305 | BAW | 05/16/2022 | DQ-48 | LOG | KHRS-1420
1530 | 7579 | 7314 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 2ND SAMPLE [ 2 OUT OF 9 SAMPLE ] @ 7314'.- ATTEMPTED TO PUMP OUT WITH RCI XL PKR, ABORTED DUE TO LOW MOBILITY, INFLATE STRADDLE PKR & TAKE 2 CYCLE FOR 8 HRS WITH LOW MOBILITY, - MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE [ NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN ].- SAMPLE# 2 [ LFDR FM ] @ 7314': TOTAL DUMPING IN ANNUL: 1.2 BBL / WATER, [ ONE SAMPLE COLLECTED ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 7314 | BAW | 05/16/2022 | DQ-48 | LOG | KHRS-1420
1531 | 7579 | 7320 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 3RD SAMPLE [ 3 OUT OF 9 SAMPLE ] @ 7320' IN PROGRESS @ RT.- ATTEMPTED TO PUMP OUT WITH RCI XL PKR, ABORTED DUE TO LOW MOBILITY,- INFLATE STRADDLE PKR @ 7320', FININSH 2 CYCLE FOR 8 HRS WITH LOW MOBILITY & 3RD CYCLE IN PROGRESS @ REPORT TIME,- MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE [ NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN ].- SAMPLE# 3 [ LFDR FM ] @ 7320': TOTAL DUMPING IN ANNUL: 1.7 BBL / WATER, [ NO SAMPLE COLLECT TILL THE MOMENT ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- TOTAL HRS SINCE LAST CIRCULATION : 44 HRS. | 7579 | 7320 | BAW | 05/16/2022 | DQ-48 | LOG | KHRS-1420
1532 | 129.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2664 | 11 May 1930 | 05/16/2022 | DQ-48 | Type | KHRS-1420
1533
1534
1535 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | DQ-50L | Hrs | HRDH-582
1536 | FOT | HDV | 5.75 | 16 May 1900 - 0045 | 1902 | 896607 | FAILED TO CLOSE 9-5/8" DV PORTS. | TF | DV |  | 05/16/2022 | DQ-50L | 5.75 | HRDH-582
1537 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | ED-85A | Hrs | ZULF-2062
1538 | FOT | RIG | 5.75 | 16 May 1515 - 2100 | 6721 | 896639 | SWIVEL PACKING LEAKED. | RR | SWVL |  | 05/16/2022 | ED-85A | 5.75 | ZULF-2062
1539 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | HI-2 | Hrs | BRRI-464
1540 | WTHR | ARM | 22 | 15 May 1700 - 1500 | 14802 | 896551 | UNABLE TO WORK WITH SUPPLY VESSELS DUE TO UNFAVORABLE WEATHER CONDITIONS. | WON | NA |  | 05/16/2022 | HI-2 | 10 | BRRI-464
1541 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | MP-4 | Hrs | LWHH-45
1542 | SRVC | ARM | 1 | 16 May 0800 - 0900 | 10436 | 896632 | LOST VSAT SIGNAL WHILE DRILLING 6-1/8" HORIZONTAL HOLE WITH GEOSTEERING. | WO | NA |  | 05/16/2022 | MP-4 | 1 | LWHH-45
1543 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | NA-128S | Hrs | SAHB-28
1544 | FOT | SPS | 21 | 15 May 1900 - 0045 | 13476 | 896583 | MWD TOOLS FAILED TO TRANSMIT SURVEYS. | BHA | MWD |  | 05/16/2022 | NA-128S | 11 | SAHB-28
1545 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | NA-18S | Hrs | UTMN-2334
1546 | STBH | ARM | 112 | 12 May 1300 - 0500 | 14361 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/16/2022 | NA-18S | 24 | UTMN-2334
1547 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | NA-393S | Hrs | HWYH-1138
1548 | FOT | WI3 | 123 | 11 May 1500 - 0500 | 11720 | 896461 | AFTER SETTING 7" WHIPSTOCTRIED TO PASS WITH 5-7/8" MM DIR BHA THRU WIS WHIPSTOCK WINDOW. | TF | WPSTK |  | 05/16/2022 | NA-393S | 24 | HWYH-1138
1549 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | NBR-783S | Hrs | NJYN-89
1550 | FOT | CRT | 98 | 12 May 1015 - 0500 | 14935 | 896433 | LEAK ON LTTT PACKER DURING NEGATIVE TST | BHA | WBCL |  | 05/16/2022 | NBR-783S | 18.5 | NJYN-89
1551 | XWSW | SRT | 5.5 | 16 May 2330 - 0500 | 7300 | 896591 | CALIPER LOG SHOWING 0.8 MM LESS THAN 6.9" (APPROVED HOLE SIZE FOR RUNNING EXPANDABLE LINER), ENGINEERING ASK TO ENLARGE HOLE AGAIN TO GET 6.9" HOLE DIAMETER OR ABOVE. LOST TIME ON SLB RHINO REAMER AS IT DOESN'T ENLARGE THE HOLE AS PER PLAN TO 7 3/8". | TF | STZRM |  | 05/16/2022 | PA-529S | 5.5 | SHYB-108
1552 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | PA-529S | Hrs | SHYB-108
1553 | LHFL | RIG | 4 | 16 May 1930 - 2330 | 5540 | 896590 | OBSERVED LEAK IN TDS WASH PIPE, POOH WITH SLB RSS/LWD/RHINO-REAMER ASSEMBLY TO CSG WINDOW @5,440', REPLACE WASH PIPE, RIH. | RR | HSYS |  | 05/16/2022 | PA-529S | 4 | SHYB-108
1554 | XWSW | SRT | 5.5 | 16 May 2330 - 0500 | 7300 | 896591 | CALIPER LOG SHOWING 0.8 MM LESS THAN 6.9" (APPROVED HOLE SIZE FOR RUNNING EXPANDABLE LINER), ENGINEERING ASK TO ENLARGE HOLE AGAIN TO GET 6.9" HOLE DIAMETER OR ABOVE. LOST TIME ON SLB RHINO REAMER AS IT DOESN'T ENLARGE THE HOLE AS PER PLAN TO 7 3/8". | TF | STZRM |  | 05/16/2022 | PA-529S | 5.5 | SHYB-108
1555 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | RBP-50A | Hrs | KARN-46
1556 | FOT | WI2 | 4 | 16 May 0500 - 0900 | 11911 | 896599 | WIS COILED TUBING CONNECTOR FAILED TWICE WHILE FILLING UP REEL WITH WATER (WITHOUT PRESSURE). 3RD WIS CONNECTOR GOOD PUL-TEST AND GOOD P/TEST. | BHA | CTAC |  | 05/16/2022 | RBP-50A | 4 | KARN-46
1557 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SINO-12L | Hrs | HRDH-1454
1558 | FOT | TK1 | 7 | 16 May 1630 - 2330 | 2955 | 896606 | HES SL RE-RUN WITH 3.875" DRIFT TO 880' JT # 48 ( 9' ABOVE COLLAR) ATTEMPT TO PASS NO SUCCESS. | DSF | STRG |  | 05/16/2022 | SINO-12L | 7 | HRDH-1454
1559 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SINO-18 | Hrs | SRYN-14
1560 | STBH | ARM | 209 | 08 May 1200 - 0500 | 803 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/16/2022 | SINO-18 | 24 | SRYN-14
1561 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SND-2005 | Hrs | MHKK-2
1562 | FOT | RIG | 3 | 16 May 2130 - 0030 | 10636 | 896602 | NOTICED LEAKING FLANGE CONNECTION AT 2" GATE VALVE AT STAND PIPE | RR | CSYS |  | 05/16/2022 | SND-2005 | 3 | MHKK-2
1563 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SND-2006 | Hrs | UTMN-3165
1564 | FOT | RIG | 2.5 | 16 May 0630 - 0900 | 3640 | 896624 | TROUBLESHOOT/ REPLACE TDS TORQUE ENCODER. | RR | TDS |  | 05/16/2022 | SND-2006 | 2.5 | UTMN-3165
1565 | LHFL | RIG | 1.75 | 16 May 0945 - 1130 | 264 | 896627 | OBSERVED HYDRAULIC OIL LEAK FROM TOP DRIVE SERVICE LOOP. | RR | HSYS |  | 05/16/2022 | SND-2007 | 1.75 | ADHN-370100
1566 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SND-2007 | Hrs | ADHN-370100
1567 | FOT | BHI | 31 | 15 May 1400 - 2315 | 16323 | 896573 | OBSERVED FAILURE ON BAKER ATK RIP #3, NO PRESSURE ON IT, TROUBLESHOOTING THE TOOL-NO SUCCESS | BHA | RSS |  | 05/16/2022 | SND-2007 | 16 | ADHN-370100
1568 | LHFL | RIG | 1.75 | 16 May 0945 - 1130 | 264 | 896627 | OBSERVED HYDRAULIC OIL LEAK FROM TOP DRIVE SERVICE LOOP. | RR | HSYS |  | 05/16/2022 | SND-2007 | 1.75 | ADHN-370100
1569 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SND-2008 | Hrs | HRDH-1052
1570 | FOT | WDS | 50.75 | 14 May 0745 - 0500 | 11559 | 896510 | UN ABLE TO BUILD THE ANGLE DUE TO WFD RSS TOOL NOT ABLE TO ACHIEVE BUILD RATE | BHA | RSS |  | 05/16/2022 | SND-2008 | 21.5 | HRDH-1052
1571 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SP-101 | Hrs | ABQQ-710
1572 | FOT | WI1 | 446 | 27 Apr 1100 - 1100 | 2398 | 896019 | STRING STUCK WHILE WIS SECTION MILLING 9-5/8" CSG. | TF | FISHT |  | 05/16/2022 | SP-101 | 6 | ABQQ-710
1573 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SP-110 | Hrs | BRRI-562
1574 | FOT | RIG | 31 | 15 May 2200 - 0500 | 11857 | 896629 | REPLACE TDS HARPOON CONNECTION. | RR | TDS |  | 05/16/2022 | SP-110 | 24 | BRRI-562
1575 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SP-122 | Hrs | UTMN-2087
1576 | XTTE | NST | 14.5 | 14 May 0300 - 0545 | 6000 | 896532 | NESR PUMPING UNIT NOT HOLDING PRESSURE. | TF | PUMP |  | 05/16/2022 | SP-122 | .75 | UTMN-2087
1577 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SP-259 | Hrs | HZEM-160402
1578 | FOT | ITS | 16.5 | 15 May 2230 - 0130 | 17307 | 896586 | CRT FILL UP SPEAR SEALS BROKEN | TF | CTRQ |  | 05/16/2022 | SP-259 | 10 | HZEM-160402
1579 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SP-261 | Hrs | HZEM-160204
1580 | FOT | ITS | 2.25 | 16 May 1800 - 2015 | 10848 | 896631 | GRT STINGER PACKER RUBBER FAILED, CHANGED PACKER SEVERAL TIMES. | TF | CRT |  | 05/16/2022 | SP-261 | 2.25 | HZEM-160204
1581 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SSA-102 | Hrs | QTIF-696
1582 | UNKN | RIG | 17 | 15 May 0700 - 0030 | 19720 | 896535 | ELMAGO BRAKE FAILED & TDS W/STRING DESCENDED WHILE CIRCULATION & RECIPROCATION ON BTM; WHICH CAUSED THE STAND ABOVE ROTARY TO BEND & TWIST AROUND TDS RAIL BEAM. | HSEI | NA |  | 05/16/2022 | SSA-102 | 5 | QTIF-696
1583 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | SSA-46 | Hrs | JAHM-7
1584 | FOT | SWL | 48.25 | 14 May 2115 - 0030 | 5395 | 896563 | WHILE TAKING FORMATION SAMPLE AT 5395 FT BY SLB ORA/GR ASSY. PUMP OF TOOL ASSY STOP WORKING. POOH ASSY. RIH NEW ASSY. TAKE SAMPLE AT 5395 FT. POOH. | TF | WLT |  | 05/16/2022 | SSA-46 | 16.5 | JAHM-7
1585 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | T914 | Hrs | UTMN-1272
1586 | FOT | GD1 | 2.5 | 16 May 1545 - 1815 | 0 | 896605 | FAILED TO SET THE MECHANICAL PUNCHER. | TF | SLICK |  | 05/16/2022 | T914 | 2.5 | UTMN-1272
1587 | UVLC | ARM | 10 | 16 May 1900 - 0500 | 3673 | 896641 | OBSERVE TOTAL LOSSES IN ARUMA FORMATION | LCIR | NA |  | 05/16/2022 | V140A | 10 | SFNY-1760
1588 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/16/2022 | V140A | Hrs | SFNY-1760
1589 | WTHR | ARM | 15.25 | 15 May 0115 - 1630 | 3501 | 896587 | TANAJIB UNABLE TO LOAD AND SUPPLY MUD SKIPS FOR OPERATIONS DUE TO ADVERSE WEATHER AND CRANES UNABLE TO WORK - ALL AVAILABLE SKIPS ON FIELD BOAT UTILIZED. STOP DRILLING CIRCULATE CLEAN AND POOH TO SHOE | WON | NA |  | 05/16/2022 | V140A | 11.5 | SFNY-1760
1590 | UVLC | ARM | 10 | 16 May 1900 - 0500 | 3673 | 896641 | OBSERVE TOTAL LOSSES IN ARUMA FORMATION | LCIR | NA |  | 05/16/2022 | V140A | 10 | SFNY-1760
1591 | DSFT | SCP | 16 | 17 May 1000 - 0500 | 4080 | 896679 | UNABLE TO RETRIEVE SLB RETRIEVABLE BRIDGE PLUG USING ALMANSOORI SL | JF | PKR |  | 05/17/2022 | ADC-50 | 16 | SFNY-1177
1592 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | ADC-50 | Hrs | SFNY-1177
1593 | MRWL | RIG | 67 | 14 May 1800 - 2030 | 0 | 896533 | WHILE LIFTING 13-5/8" BOP AFTER N/D, BOP STACK MOVED AND BENT ESP CABLE. PERFORMED VARIOUS TESTS ON ESP CABLE: PHASE-TO-PHASE, PHASE-TO-GROUND, AND 5 KV VOLTAGE TEST - ALL OKAY. DISCUSSION WITH TOWN DETERMINED THAT DAMAGE TO CABLE COULD RESULT IN REDUCED LIFESPAN OF THE ESP. DECISION MADE TO RECOMPLETE. | BOP | BOP |  | 05/17/2022 | ADC-50 | 8 | SFNY-1177
1594 | DSFT | SCP | 16 | 17 May 1000 - 0500 | 4080 | 896679 | UNABLE TO RETRIEVE SLB RETRIEVABLE BRIDGE PLUG USING ALMANSOORI SL | JF | PKR |  | 05/17/2022 | ADC-50 | 16 | SFNY-1177
1595 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | ADC-56L | Hrs | UTMN-2330
1596 | FOT | SDM | 16 | 17 May 1300 - 0500 | 15784 | 896676 | POWER DRIVE JAMMING. | BHA | RSS |  | 05/17/2022 | ADC-56L | 16 | UTMN-2330
1597 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | ADC-65L | Hrs | HWYH-1280
1598 | FWTS | SDM | 124.75 | 12 May 1600 - 0500 | 5432 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/17/2022 | ADC-65L | 21.75 | HWYH-1280
1599 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | ADC-67L | Hrs | SDGM-1265
1600 | OTH | RIG | 14 | 17 May 1500 - 0500 | 0 | 896608 | UPGRADE ON DRILL-OPS / ONTRAK SYSTEM | UPRA | NA |  | 05/17/2022 | ADC-67L | 14 | SDGM-1265
1601 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | ADES-144 | Hrs | UTMN-3099
1602 | XTRI | RIG | 1.5 | 17 May 1800 - 1930 | 0 | 896595 | EXCESS TIME TAKEN TO PREPARE AND HANDLE TOOLS. | JF | NA |  | 05/17/2022 | ADES-144 | 1.5 | UTMN-3099
1603 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | ADM-339 | Hrs | RBYN-52
1604 | FOT | RIG | 5 | 17 May 0900 - 1400 | 11146 | 896657 | ADES TROUBLESHOOT AIR SUPPLY TO STBD FLARE BOOM - UNABLE TO GET EFFICIENT BURNING. | RR | FLR |  | 05/17/2022 | ADM-339 | 5 | RBYN-52
1605 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | DPS-74 | Hrs | NJYN-54
1606 | FOT | BLH | 803.5 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/17/2022 | DPS-74 | 22 | NJYN-54
1607 | 7579 | 7320 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], CON'T WORK TO COLLECT 3RD SAMPLE [ 3 OUT OF 9 SAMPLE ] @ 7320'.- FINISH 3RD CYCLE WITH STRADDLE PKR @ 7320', ONE SAMPLE COLLECTED @ 7320 FT.- SAMPLE# 3 [ LFDR FM ] @ 7320': TOTAL DUMPING IN ANNUL: 1.9 BBL / OIL.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 7320 | BAW | 05/17/2022 | DQ-48 | LOG | KHRS-1420
1608 | 7579 | 7328 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 4TH SAMPLE [ 4 OUT OF 9 SAMPLE ] @ 7328'.- ATTEMPTED TO PUMP OUT WITH RCI XL PKR, ABORTED DUE TO LOW MOBILITY, INFLATE STRADDLE PKR & TAKE 2 CYCLE FOR 8 HRS WITH LOW MOBILITY, - MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE [ NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN ].- SAMPLE# 4 [ LFDR FM ] @ 7328': TOTAL DUMPING IN ANNUL: 1.3 BBL / OIL, [ ONE SAMPLE COLLECT ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 7328 | BAW | 05/17/2022 | DQ-48 | LOG | KHRS-1420
1609 | 7579 | 7335 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 5TH SAMPLE [ 5 OUT OF 9 SAMPLE ] @ 7335'.- ATTEMPTED TO PUMP OUT WITH RCI XL PKR, ABORTED DUE TO LOW MOBILITY, INFLATE STRADDLE PKR, FINISH 3 CYCLE & 4TH CYCLE IN PROGRESS @ R.TIME. - MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE [ NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN ].- SAMPLE# 5 [ LFDR FM ] @ 7335': TOTAL DUMPING IN ANNUL: 1.5 BBL / OIL-WATER, [ NO SAMPLE COLLECTED TILL THE MOMENT ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC.> TOTAL HRS SINCE LAST CIRCULATION : 68 HRS. | 7579 | 7335 | BAW | 05/17/2022 | DQ-48 | LOG | KHRS-1420
1610 | 153.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2664 | 11 May 1930 | 05/17/2022 | DQ-48 | Type | KHRS-1420
1611
1612
1613 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | DQ-50L | Hrs | HRDH-582
1614 | FOT | HDV | 7.75 | 16 May 1900 - 1630 | 1902 | 896607 | FAILED TO CLOSE 9-5/8" DV PORTS. | TF | DV |  | 05/17/2022 | DQ-50L | 2 | HRDH-582
1615 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | ED-85A | Hrs | ZULF-2062
1616 | FOT | RIG | 11.25 | 17 May 1600 - 0315 | 7258 | 896678 | TDS STOP ROTATION, TROUBLE SHOOTING FOUND FAILURE IN TDS LUBE OIL PUMP | RR | TDS |  | 05/17/2022 | ED-85A | 11.25 | ZULF-2062
1617 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | EXL-IA | Hrs | SFNY-4240
1618 | DRIG | RIG | 2 | 17 May 1600 - 1800 | 4687 | 896611 | TEST PLUG HANGING UP IN BOP CAVITIES, ATTEMPTED TO GET PRESSURE TEST FLUID BYPASING TEST PLUG, PULLED PLUG REPLACE DAMAGED SEALS, CENTERED DRILL STRING LANDED TEST PLUG. TESTED OK. | BOP | BOP |  | 05/17/2022 | EXL-IA | 2 | SFNY-4240
1619 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | NA-128S | Hrs | SAHB-28
1620 | FOT | SPS | 30 | 15 May 1900 - 0945 | 13476 | 896583 | MWD TOOLS FAILED TO TRANSMIT SURVEYS. | BHA | MWD |  | 05/17/2022 | NA-128S | 4.75 | SAHB-28
1621 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | NA-18S | Hrs | UTMN-2334
1622 | STBH | ARM | 124.5 | 12 May 1300 - 0500 | 14361 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/17/2022 | NA-18S | 12.5 | UTMN-2334
1623 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | NA-393S | Hrs | HWYH-1138
1624 | FOT | WI3 | 147 | 11 May 1500 - 0500 | 11720 | 896461 | AFTER SETTING 7" WHIPSTOCK TRIED TO PASS WITH 5-7/8" MM DIR BHA THRU WIS WHIPSTOCK WINDOW. | TF | WPSTK |  | 05/17/2022 | NA-393S | 24 | HWYH-1138
1625 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | NBR-304S | Hrs | HRDH-1952
1626 | XCIR | ARM | 11.25 | 17 May 1615 - 0330 | 17822 | 896681 | EXCESSWIVE CIRC. NEEDED DUE TO PACK OFF TENDENCIES | BHS | NA |  | 05/17/2022 | NBR-304S | 11.25 | HRDH-1952
1627 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | NBR-783S | Hrs | NJYN-89
1628 | FOT | CRT | 105 | 12 May 1015 - 1200 | 14935 | 896433 | LEAK ON LTTT PACKER DURING NEGATIVE TST | BHA | WBCL |  | 05/17/2022 | NBR-783S | 7 | NJYN-89
1629 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | PA-529S | Hrs | SHYB-108
1630 | XWSW | SRT | 10 | 16 May 2330 - 0930 | 7300 | 896591 | CALIPER LOG SHOWING 0.8 MM LESS THAN 6.9" (APPROVED HOLE SIZE FOR RUNNING EXPANDABLE LINER), ENGINEERING ASK TO ENLARGE HOLE AGAIN TO GET 6.9" HOLE DIAMETER OR ABOVE. LOST TIME ON SLB RHINO REAMER AS IT DOESN'T ENLARGE THE HOLE AS PER PLAN TO 7 3/8". | TF | STZRM |  | 05/17/2022 | PA-529S | 4.5 | SHYB-108
1631 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SDA | Hrs | MRJN-733
1632 | XTRI | HTS | 2 | 17 May 0500 - 0700 | 0 | 896594 | EXTRA TIME TAKEN TO IMPROVE BS&W IN TANK # 3 (WATER WAS NOT SEPARATED SINCE WELL WAS SHUT AT 6 PM). BS&W REPORTED "0" AND RE-CHECKED PRIOR TO FLARING - BS&W -10%. REMOVE WATER FROM SURGE TANK, ADD EXTRA DIESEL TO IMPROVE BS&W. | JF | SEPR |  | 05/17/2022 | SDA | 2 | MRJN-733
1633 | 17491 | 9382 | TO | N |  | STDP | POOH WITH L-3 8-1/2" MRSS BHA F/ 10,800' T/TOW @9,382'. - KEEP FILLING WELL THROUGH TRIP TANK WITH 66PCF BRINE, +/- 10 BBL/HR STATIC LOSSES.- HOLE IN GOOD CONDITION. | 17491 | 10800 | RIG | 05/17/2022 | SIN30L | DRLG | KHRS-1409
1634 | 17491 |  | WCNT | N |  | NA | FLOW CHECK, WELL +/- 8 BBL/HR STATIC LOSSES. | 17491 |  | RIG | 05/17/2022 | SIN30L | DRLG | KHRS-1409
1635 | 17491 | 7406 | TO | N |  | STDP | POOH WITH L-3 8-1/2" MRSS BHA F/ /9,382' TO 7,406'. - KEEP FILLING WELL THROUGH TRIP TANK WITH 66PCF BRINE, +/- 8 BBL/HR STATIC LOSSES.- HOLE IN GOOD CONDITION. | 17491 | 9382 | RIG | 05/17/2022 | SIN30L | DRLG | KHRS-1409
1636 | 17491 | 496 | TO | N |  | STDP | POOH W/8-1/2" MRSS DRILL BHA FROM 7,406' TO 496' MEANWHILE L/D 5" DPS.- L/D 2 STDS 5" DP FROM DERRICK TO ACCOMMODATE RF FOR CT.- MONITOR THE WELL THROUGH TRIP TANK, 8 BBL/HR STATIC LOSSES. | 17491 | 7406 | RIG | 05/17/2022 | SIN30L | DRLG | KHRS-1409
1637 | 17491 |  | WCNT | N |  | NA | FLOW CHECK AT TOP OF BHA , 7 BBL/HR STATIC LOSSES. | 17491 |  | RIG | 05/17/2022 | SIN30L | DRLG | KHRS-1409
1638 | 17491 |  | OTH | N |  | NA | PERFORM H2S DRILL WITH ALL RELATED PERSONNEL. | 17491 |  | OTH | 05/17/2022 | SIN30L | DRLG | KHRS-1409
1639 | 17491 | 0 | TO | N |  | BHA | CONT POOH WITH 8-1/2" MRSS DRLG BHA TO SURFACE.- HPJSM, UNLOAD RADIOACTIVE SOURCE.- DUMP MEMORY DATA.- L/D MRSS BHA & 8-1/2" PDC BIT.- BIT DULL GRADING: 1-1-WT-A-X-I-NO-TD.- MONITOR THE WELL THROUGH TRIP TANK, 7 BBL/HR STATIC LOSSES. | 17491 | 496 | RIG | 05/17/2022 | SIN30L | DRLG | KHRS-1409
1640 | 17491 |  | RTRV | N |  | WBSH | RETRIVE WEAR BUSHING. | 17491 |  | RIG | 05/17/2022 | SIN30L | WH | KHRS-1409
1641 | 17491 |  | BOPT | N |  | BOP | PERFORM FULL BOP TEST AS PER ARAMCO STANDARDS. | 17491 |  | RIG | 05/17/2022 | SIN30L | BOP | KHRS-1409
1642 | 17491 |  | ND | N | 2545 | BNIP | HPJSM, R/D POWER TONG & N/D BELL NIPPLE & FLOW LINE. | 17491 |  | RIG | 05/17/2022 | SIN30L | BOP | KHRS-1409
1643 | 17491 |  | PJSM | C | 2545 | NA | HPJSM WITH ALL RIG CREW & ALL PERSONNEL INVOLVED W/ BKR CT R/U. | 17491 |  | TK2 | 05/17/2022 | SIN30L | STIM | KHRS-1409
1644 | 17491 |  | STIM | C | 2545 | CTU | R/U & CONNECT RISER, X/O'S, FLANGES & GATE VALVE TO RIG BOP.MONITOR THE WELL THROUGH TRIP TANK, 7 BBL/HR STATIC LOSSES | 17491 |  | BCT | 05/17/2022 | SIN30L | STIM | KHRS-1409
1645 | 17491 |  | STIM | C | 2545 | CTU | HPJSM, R/U CT QUAD BOP ON TOP OF RISER . ON GOING.MONITOR THE WELL THROUGH TRIP TANK, 7 BBL/HR STATIC LOSSES. | 17491 |  | BCT | 05/17/2022 | SIN30L | STIM | KHRS-1409
1646 | 163.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 2.75 | 2545 | 01 May 1800 | 05/17/2022 | SIN30L | Type | KHRS-1409
1647
1648
1649 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SINO-18 | Hrs | SRYN-14
1650 | STBH | ARM | 233 | 08 May 1200 - 0500 | 803 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/17/2022 | SINO-18 | 24 | SRYN-14
1651 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SINO-42L | Hrs | HWYH-485
1652 | FOT | SPS | 11.5 | 17 May 1730 - 0500 | 7134 | 896716 | MWD TOOL STOPPED PUSLING . | BHA | MWD |  | 05/17/2022 | SINO-42L | 11.5 | HWYH-485
1653 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SND-2001 | Hrs | UTMN-2329
1654 | WCC5 | ARM | 9.5 | 17 May 1930 - 0500 | 11660 | 896696 | OBSERVED WELL FLLOWING AFTER MAKING SURVEY | WCNT | NA |  | 05/17/2022 | SND-2001 | 9.5 | UTMN-2329
1655 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SND-2005 | Hrs | MHKK-2
1656 | FOT | RIG | 4.25 | 17 May 1630 - 2045 | 10636 | 896656 | 2-1/16" 10M BLEED OFF GATE VALVE AT STAND PIPE WASHED OUT. | RR | CSYS |  | 05/17/2022 | SND-2005 | 4.25 | MHKK-2
1657 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SND-2008 | Hrs | HRDH-1052
1658 | FOT | WDS | 23.25 | 16 May 0700 - 0645 | 11880 | 896593 | WFD RSS/MWD/GR DIR DRILL 5 7/8" HOLE W/102 PCF OBM, 100% CIRC, HAD NO SIGNAL FROM WFD RSS/MWD, | BHA | RSS |  | 05/17/2022 | SND-2008 | 1.75 | HRDH-1052
1659 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SSA-102 | Hrs | QTIF-696
1660 | UNKN | RIG | 23 | 15 May 0700 - 2300 | 19720 | 896535 | ELMAGO BRAKE FAILED & TDS W/STRING DESCENDED WHILE CIRCULATION & RECIPROCATION; WHICH CAUSED THE STAND ABOVE ROTARY TO BEND & TWIST AROUND TDS RAIL BEAM. | HSEI | NA |  | 05/17/2022 | SSA-102 | 6 | QTIF-696
1661 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SSA-303 | Hrs | HRDH-2306
1662 | SRVC | RIG | 2 | 17 May 1800 - 2000 | 10270 | 896697 | EXCESS TIME TO MAKE UP TEST PLUG ASSY DUE TO LEAKING CONNECTION | WO | NA |  | 05/17/2022 | SSA-303 | 2 | HRDH-2306
1663 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SSA-5917 | Hrs | HRDH-2261
1664 | FOT | TK3 | 24 | 16 May 0400 - 0500 | 8600 | 896610 | OBESERVED DROP ON STAND PIPE PRESSURE | DSF | DP |  | 05/17/2022 | SSA-5917 | 23 | HRDH-2261
1665 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | SSA-5974 | Hrs | HRDH-1970
1666 | CWEL | ARM | 533.25 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/17/2022 | SSA-5974 | 24 | HRDH-1970
1667 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | T216 | Hrs | ANDR-95
1668 | IDPR | NPC | 21 | 17 May 0800 - 0500 | 9936 | 896680 | NOISY SIGNAL, TROUBLESHOTING, DOWNHOLE WASH OUT. | BHA | JARS |  | 05/17/2022 | T216 | 21 | ANDR-95
1669 | FOT | RIG | 8.25 | 17 May 1415 - 2230 | 4000 | 896677 | ENGINE HEAT UP DUE TO MALFUNCTIONED FAN IN ENGINE COOLING MODULE. PARTIAL BLACKOUT HAVING TWO GENERATORS UP WITH NO SUFFICIENT POWER TO OPERATE DRILLING MODULE IN FULL CAPACITY. | RR | PSYS |  | 05/17/2022 | V140A | 8.25 | SFNY-1760
1670 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/17/2022 | V140A | Hrs | SFNY-1760
1671 | FOT | SDM | 6.5 | 17 May 2230 - 0500 | 4161 | 896635 | LOST COMMUNICATION WITH MWD-GR DOWNHOLE TOOLS. ALL TROUBLESHOOTING TRIALS FAILED. | BHA | MWD |  | 05/17/2022 | V140A | 6.5 | SFNY-1760
1672 | FOT | RIG | 8.25 | 17 May 1415 - 2230 | 4000 | 896677 | ENGINE HEAT UP DUE TO MALFUNCTIONED FAN IN ENGINE COOLING MODULE. PARTIAL BLACKOUT HAVING TWO GENERATORS UP WITH NO SUFFICIENT POWER TO OPERATE DRILLING MODULE IN FULL CAPACITY. | RR | PSYS |  | 05/17/2022 | V140A | 8.25 | SFNY-1760
1673 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADC-32 | Hrs | SDGM-1228
1674 | UVLC | ARM | 8 | 18 May 2100 - 0500 | 11088 | 896689 | OBSERVED 220 BPH LOSSES @ 480 GPM WHILE DRLG | LCIR | NA |  | 05/18/2022 | ADC-32 | 8 | SDGM-1228
1675 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADC-41L | Hrs | UTMN-3142
1676 | SRVC | TSC | 1 | 18 May 0600 - 0700 | 10681 | 896706 | WHILE RUNNING 9-5/8" CASING AT 3,595 FT TESCO HYDRAULIC CAT WALK STOPPED OPERATING DUE TO THE LOW OIL SAFETY SHUT DOWN SWITCH MALFUNCTIONING. CATWALK OIL RESERVOIR WAS AT PROPER LEVEL BUT SAFETY SWITCH WAS READING LOW CAUSING IT TO SHUT DOWN. | WO | NA |  | 05/18/2022 | ADC-41L | 1 | UTMN-3142
1677 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADC-50 | Hrs | SFNY-1177
1678 | MRWL | RIG | 91 | 14 May 1800 - 0500 | 0 | 896533 | WHILE LIFTING 13-5/8" BOP AFTER N/D, BOP STACK MOVED AND BENT ESP CABLE. PERFORMED VARIOUS TESTS ON ESP CABLE: PHASE-TO-PHASE, PHASE-TO-GROUND, AND 5 KV VOLTAGE TEST - ALL OKAY. DISCUSSION WITH TOWN DETERMINED THAT DAMAGE TO CABLE COULD RESULT IN REDUCED LIFESPAN OF THE ESP. DECISION MADE TO RECOMPLETE. | BOP | BOP |  | 05/18/2022 | ADC-50 | 24 | SFNY-1177
1679 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADC-56L | Hrs | UTMN-2330
1680 | FOT | SDM | 40 | 17 May 1300 - 0500 | 15784 | 896676 | POWER DRIVE JAMMING. | BHA | RSS |  | 05/18/2022 | ADC-56L | 24 | UTMN-2330
1681 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADC-65L | Hrs | HWYH-1280
1682 | FWTS | SDM | 148.25 | 12 May 1600 - 0500 | 5432 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/18/2022 | ADC-65L | 23.5 | HWYH-1280
1683 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADC-70 | Hrs | SFNY-1820
1684 | FOT | HWP | 3.5 | 18 May 2200 - 0500 | 5410 | 896722 | HALL OBSERVED SUDDEN MOVEMENT AND HIGH TENSION ON WIRELINE CABLE. POH TO SES, FOUND THE CABLE CALMP UNSEATED, INSTALL SHEAR PINS. CHANGE OUT POWER PACK MEANWHILE CIRCULATE BTTMS UP THROUGH CHOKE. | TF | WLT |  | 05/18/2022 | ADC-70 | 3.5 | SFNY-1820
1685 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADES-14 | Hrs | HWYH-530
1686 | WTHR | ARM | 3 | 18 May 0800 - 1100 | 0 | 896695 | WAIT ON WEATHER | WON | NA |  | 05/18/2022 | ADES-14 | 3 | HWYH-530
1687 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADES-144 | Hrs | UTMN-3099
1688 | FOT | SAM | 11.5 | 18 May 1730 - 0500 | 11872 | 896688 | SAMAA FCS NEGATIVE TEST PACKER FAILURE. | BHA | WBCL |  | 05/18/2022 | ADES-144 | 11.5 | UTMN-3099
1689 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADM-261 | Hrs | LWHH-9
1690 | DAY | ARM | 8.5 | 18 May 2030 - 0500 | 0 | 896723 | WAIT ON DAY LIGHT TO COMMENCE RIG MOVE | WON | NA |  | 05/18/2022 | ADM-261 | 8.5 | LWHH-9
1691 | FOT | SWL | 1.25 | 18 May 0345 - 0500 | 0 | 896693 | SCHLUMBERGER TROUBLE SHOOT MRPO-PUMP, CHANGE OUT PUMP. | TF | WLT |  | 05/18/2022 | ADM-337 | 1.25 | MRJN-900
1692 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ADM-337 | Hrs | MRJN-900
1693 | ITRP | RIG | .75 | 18 May 1945 - 2030 | 1450 | 896690 | WHILE POOH WITH 5-7/8" BHA @ A DEPTH OF 1450', THE A.D RACKED BACK A STAND OF 4" DRILL PIPE IN AUTO SEQUENCE. AFTER GOING THROUGH THE STEPS AND SETTING THE PIPE DOWN. HE BEGAN THE AUTO SEQUENCE FOR THE HYDRO-RACKER TO GO TO WELL CENTER TO RETRIEVE THE STAND. WHILE THE HYDRO-RACKER WAS MOVING TOWARDS WELL CENTER THE STAND HE HAD JUST RACKED BACK CAME FROM BEHIND THE HYDRO-RACKER TRACK AND FELL ACROSS TO THE BEAM ON THE ADJACENT SIDE OF THE DERRICK. NO DAMAGE TO EQUIPMENT AND NO INJURY'S. | RR | DRRK |  | 05/18/2022 | ADM-337 | .75 | MRJN-900
1694 | FOT | SWL | 1.25 | 18 May 0345 - 0500 | 0 | 896693 | SCHLUMBERGER TROUBLE SHOOT MRPO-PUMP, CHANGE OUT PUMP. | TF | WLT |  | 05/18/2022 | ADM-337 | 1.25 | MRJN-900
1695 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | ARO-3004 | Hrs | MRJN-2060
1696 | FOT | RIG | 2.5 | 18 May 0530 - 0800 | 8155 | 896684 | ARO LT: TDS UNABLE TO ROTATE; POOH UP INTO SHOE, TROUBLE-SHOT TDS; CLEAN AIR LOUVERS OF EXCESSIVE SAND & REPLACE AIR FILTERS; SECURE ALL AS PER DROPS - OK | RR | TDS |  | 05/18/2022 | ARO-3004 | 2.5 | MRJN-2060
1697 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | DPS-74 | Hrs | NJYN-54
1698 | FOT | BLH | 826.75 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/18/2022 | DPS-74 | 23.25 | NJYN-54
1699 | 7579 | 7335 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], CON'T WORK TO COLLECT 5TH SAMPLE [ 5 OUT OF 9 SAMPLE ] @ 7335'.- FINISH 4TH CYCLE WITH STRADDLE PKR @ 7335', ONE SAMPLE COLLECTED @ 7335 FT.- SAMPLE# 5 [ LFDR FM ] @ 7335': TOTAL DUMPING IN ANNUL: 2 BBL / OIL, [ ONE SAMPLE COLLECT ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 7335 | BAW | 05/18/2022 | DQ-48 | LOG | KHRS-1420
1700 | 7579 | 7360 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 6TH SAMPLE [ 6 OUT OF 9 SAMPLE ] @ 7360'.- ATTEMPTED TO PUMP OUT WITH RCI XL PKR, ABORTED DUE TO LOW MOBILITY, INFLATE STRADDLE PKR & TAKE 2 CYCLE FOR 8 HRS WITH LOW MOBILITY, - MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE [ NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN ].- SAMPLE# 6 [ LFDR FM ] @ 7360': TOTAL DUMPING IN ANNUL: 1.4 BBL / OIL, [ ONE SAMPLE COLLECT ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 7360 | BAW | 05/18/2022 | DQ-48 | LOG | KHRS-1420
1701 | 7579 | 7343 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 7TH SAMPLE [ 7 OUT OF 9 SAMPLE ] @ 7343'.- ATTEMPTED TO PUMP OUT WITH RCI XL PKR, ABORTED DUE TO LOW MOBILITY, INFLATE STRADDLE PKR & TAKE 2 CYCLE FOR 8 HRS WITH LOW MOBILITY, - MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE [ NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN ].- POINT# 7 [ LFDR FM ] @ 7343': TOTAL DUMPING IN ANNUL: 1.4 BBL / OIL, [ PUMP OUT, NO SAMPLE COLLECT ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 7343 | BAW | 05/18/2022 | DQ-48 | LOG | KHRS-1420
1702 | 7579 |  | CIRC | E | 2664 | MPMP | RIH BACK TO BTM @ 7560', CIRC TWO BOTTOM UP WITH 73 PCF OBM IN PROGRESS @ RT. | 7579 |  | RIG | 05/18/2022 | DQ-48 | LOG | KHRS-1420
1703 | 177.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2664 | 11 May 1930 | 05/18/2022 | DQ-48 | Type | KHRS-1420
1704
1705
1706 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | EXL-IA | Hrs | SFNY-4240
1707 | FOT | RIG | 20.75 | 18 May 0815 - 0500 | 6335 | 896612 | WHEN ON BOTTOM NOTICED DRILLERS BOP REMOTE PANNEL DIGITAL PRESSURES FLUCTUATING & LIGHTS NOT ILUMINATING. FOUND A COMUNICATION ISSUE WITHIN THE FIBER OPTIC SYSTEM | RR | RWCS |  | 05/18/2022 | EXL-IA | 20.75 | SFNY-4240
1708 | SRVC | BAW | 2 | 18 May 2100 - 2300 | 2 | 896691 | BAKER ENG HAD LATE TO ARRIVE THE LOCATION, UNIT AND TOOLS WERE NOT READY FOR THE JOB. | WO | NA |  | 05/18/2022 | NA-18S | 2 | UTMN-2334
1709 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | NA-18S | Hrs | UTMN-2334
1710 | STBH | ARM | 146.5 | 12 May 1300 - 0500 | 14361 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/18/2022 | NA-18S | 22 | UTMN-2334
1711 | SRVC | BAW | 2 | 18 May 2100 - 2300 | 2 | 896691 | BAKER ENG HAD LATE TO ARRIVE THE LOCATION, UNIT AND TOOLS WERE NOT READY FOR THE JOB. | WO | NA |  | 05/18/2022 | NA-18S | 2 | UTMN-2334
1712 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | PA-529S | Hrs | SHYB-108
1713 | IHFL | RIG | .5 | 18 May 1545 - 1615 | 0 | 896686 | DRAWWORK BREAK WAS NOT FUCTIONING. | RR | HSYS |  | 05/18/2022 | PA-529S | .5 | SHYB-108
1714 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SDA | Hrs | MRJN-733
1715 | FOT | BCT | 14.75 | 18 May 1415 - 0500 | 0 | 896721 | BAKER HYDRAULIC PUMP ON CTU POWER PACK FAILED. STOP PUMPING N2, CLOSE CTU SLIPS AND PIPE RAMS, STRIPPERS. SERURE REEL. WAITING TO RECEIVE REPLACMENT COIL TUBING POWER PACK. | TF | CTBG |  | 05/18/2022 | SDA | 14.75 | MRJN-733
1716 | 17491 |  | STIM | E | 2545 | CTU | R/U CT QUAD BOP ON TOP OF RISER. CONNECT CONTROL HOSES TO CTU BOP. FUNCTION TEST CTU BOP 'S RAMS. CONNECT HIGH PRESSUER LINE. | 17491 |  | BCT | 05/18/2022 | SIN30L | STIM | KHRS-1409
1717 | 17491 |  | STIM | E | 2545 | CTU | CONT. R/U CT EQUIPMENT.- CONTINUE CONNECTING REQUIRED RISER SECTIONS.- CONNECT HIGH PRESSUER LINE.- CONNECT 2" GROUND LINES.- PERFORM 30 KLB PULL TEST ON COIL CONNECTOR - OK .- SPOT 130T CRANE, HANG COIL TBG INJECTOR HEAD/RISERS.- FLUSH CT LINE AND P/T CT CONNECTOR @ 500/8500PSI.- P/T CT BOP BLIND RAM AGAINST GATE VALVE TO 500/5000 PSI.- P/T 13-5/8" BLIND RAMS AGAINST CTU GATE VALVE TO 300/ 1500 PSI, OK. - DRIFT CT WITH 1" BALL & CHASE SAME W/ WTR, RETRIEVED BALL - OK .- MONITOR THE WELL THROUGH TRIP TANK WHILE, +/- 7 BBL/HR STATIC LOSSES. | 17491 |  | BCT | 05/18/2022 | SIN30L | STIM | KHRS-1409
1718 | 17491 |  | STIM | E | 2545 | CTU | HPJSM, M/U BHA AS PER BKR AND NOV REPRESENTATIVE. - FUNCTION TEST THE SAME AS PER NOV: - WITHOUT AGITATOR : 1.5 BPM = 930 PSI, 2 BPM = 1560 PSI, 2.5 BPM = 2200 PSI, 3 BPM = 2950 PSI.- WITH AGITATOR : 1.5 BPM = 1030 PSI, 2 BPM = 1800 PSI, 2.5 BPM = 2650 PSI, 3 BPM = 3750 PSI.. - MONITOR THE WELL THROUGH TRIP TANK WHILE, +/- 7 BBL/HR STATIC LOSSES. | 17491 |  | BCT | 05/18/2022 | SIN30L | STIM | KHRS-1409
1719 | 17491 |  | STIM | E | 2545 | CTU | CONNECTED CTU INJECTOR TO CTU QUAD BOP. - P/T CTU STACK AGAINST STRIPPER TO 500/ 2500 PSI FOR 5/15 MINS, OK. - INFLOW TEST DFCV TO 1500 PSI FOR 10 MINS, OK. BLEED OFF PRESSURE.- MONITOR THE WELL THROUGH TRIP TANK WHILE, +/-7 BBL/HR STATIC LOSSES. | 17491 |  | BCT | 05/18/2022 | SIN30L | STIM | KHRS-1409
1720 | 17491 |  | STIM | E | 2545 | CTU | DISPLACE CT WITH 87 BBLS OF 66 PCF BRINE.- MONITOR THE WELL THROUGH TRIP TANK WHILE, +/- 7 BBL/HR STATIC LOSSES. | 17491 |  | BCT | 05/18/2022 | SIN30L | STIM | KHRS-1409
1721 | 17491 |  | STIM | E | 2545 | CTU | RIH W/ BHI 2-3/8" CT AS PER BHI STANDARD PROCEDURES TO TOW @ 9382'.- CT RIH SPEED: 30-35 FT/MIN.- PUMP 66 PCF BRINE @ 0.5 BPM.- START TO DISPLACE CT W/ 140 BBLS EASY REACH @ 1400'.- PERFORM PULL TEST EVERY 1000'.- MONITOR THE WELL THROUGH TRIP TANK WHILE, +/- 7 BBL/HR STATIC LOSSES. | 17491 |  | BCT | 05/18/2022 | SIN30L | STIM | KHRS-1409
1722 | 17491 |  | STIM | E | 2545 | CTU | CLOSE THE CHOKE, CONT RIH W/ BHI 2-3/8'' CTU IN L-3 OPEN HOLE WHILE PUMPING PRE-FLUSH FROM 9,382' TO 14,679 FT ON GOING.- PRE-FLUSH PUMPED 1215 BBLS.- PUMP RATE: 2.5-3 BPM, CTU PUMPING PRESS: 2700-3800 PSI, WHP: 550-80 PSI, CTU SPEED: 17-2 FT/MIN. | 17491 |  | BCT | 05/18/2022 | SIN30L | STIM | KHRS-1409
1723 | 187.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 24 | 2545 | 01 May 1800 | 05/18/2022 | SIN30L | Type | KHRS-1409
1724
1725
1726 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SINO-18 | Hrs | SRYN-14
1727 | STBH | ARM | 257 | 08 May 1200 - 0500 | 803 | 896336 | AFTER REAMING DOWN A STAND DURING THE CONDITIONING TRIP. WORKED THE STAND UP AND DOWN WITH NO PROBLEMS. THEN LATCHED ONTO AND MADE UP THE NEXT STAND. THE STRING IMMEDIATELY TOOK WT. MADE UP THE TDS AND COULD NOT PUMP OR ROTATE. RACK BACK THE STAND AND PICKED UP SINGLE JT DRILL PIPE AND M/U THE TDS. | STUK | BIT |  | 05/18/2022 | SINO-18 | 24 | SRYN-14
1728 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SINO-19L | Hrs | UTMN-1587
1729 | HERR | TK1 | 8 | 18 May 1100 - 1900 | 9399 | 896702 | WAIT TO GET ENOUGH WATER ON LOCATION AND BUILD SUFFICIENT MUD VOLUME. | JF | NA |  | 05/18/2022 | SINO-19L | 8 | UTMN-1587
1730 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SINO-42L | Hrs | HWYH-485
1731 | FOT | SPS | 25.5 | 17 May 1730 - 1900 | 7134 | 896716 | MWD TOOL STOPPED PULSING . | BHA | MWD |  | 05/18/2022 | SINO-42L | 14 | HWYH-485
1732 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SINO21 | Hrs | ABQQ-494
1733 | FOT | ARN | 4 | 18 May 1200 - 1600 | 7656 | 896703 | V-SAT ISSUE. | TF | VSAT |  | 05/18/2022 | SINO21 | 4 | ABQQ-494
1734 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SND-2001 | Hrs | UTMN-2329
1735 | WCC5 | ARM | 33.5 | 17 May 1930 - 0500 | 11660 | 896696 | OBSERVED WELL FLLOWING AFTER MAKING SURVEY | WCNT | NA |  | 05/18/2022 | SND-2001 | 24 | UTMN-2329
1736 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SND-2002 | Hrs | WAQR-23
1737 | UVLC | ARM | 192 | 11 May 0500 - 0500 | 10207 | 896698 | ENCOUNTERED COMPLETE LOSS OF CIRCULATION @ 10207' WHILE DRILLING. | LCIR | NA |  | 05/18/2022 | SND-2002 | 24 | WAQR-23
1738 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SND-2003 | Hrs | RMTN-17
1739 | HERR | RIG | 18 | 18 May 1100 - 0500 | 10558 | 896720 | AFTER DOWNLINKING PRIOR TO CONNECTION, SPP INCREASED FROM 1950 PSI TO 2700 PSI. DECISION MADE TO POOH, AT SURFACE BREAK OUT BAKER FILTER SUB AND FOUND DP SCALING ACCUMULATED AROUND FILTER SUB AND FILTER SUB PLUGGED. | DSF | STRG |  | 05/18/2022 | SND-2003 | 18 | RMTN-17
1740 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SND-2004 | Hrs | BRRI-1148
1741 | SROP | NOC | 1.5 | 18 May 0330 - 0500 | 9803 | 896694 | NO PROGRESS WITH NOV 8-1/2" CORING BHA & CORE JAMMED. | JF | CORC |  | 05/18/2022 | SND-2004 | 1.5 | BRRI-1148
1742 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SND-2005 | Hrs | MHKK-2
1743 | FOT | RIG | 2.75 | 18 May 1615 - 1900 | 10852 | 896704 | MUD PUMP #3 WEAR PLATE WASHED | RR | MPMP |  | 05/18/2022 | SND-2005 | 2.75 | MHKK-2
1744 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SND-2008 | Hrs | HRDH-1052
1745 | FOT | WDS | 18.5 | 18 May 1030 - 0500 | 12400 | 896719 | WHILE DRILLING, HAD WFD MWD FAILURE DUE TO NO SIGNAL | BHA | MWD |  | 05/18/2022 | SND-2008 | 18.5 | HRDH-1052
1746 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SND-3003 | Hrs | HRDH-2303
1747 | FOT | WCR | .5 | 18 May 0115 - 0145 | 1350 | 896692 | JAM UNIT SENSOR NOT WORKING | TF | CTRQ |  | 05/18/2022 | SND-3003 | .5 | HRDH-2303
1748 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SNF036 | Hrs | MRJN-901
1749 | FOT | SWL | 5 | 18 May 1800 - 2300 | 7882 | 896685 | SCHLUMBERGER-WL LOST POWER ON MDT TOOLS DUE TO CABLE HEAD CONNECTOR FAILURE | TF | WLT |  | 05/18/2022 | SNF036 | 5 | MRJN-901
1750 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SSA-5969 | Hrs | UTMN-3021
1751 | HSCM | RIG | 9 | 18 May 0800 - 1700 | 10805 | 896700 | WHILE DRILLING OBSERVED HIGH NOISE READINGS ON SLB TOOLS SIGNAL & PRESSURE INCREASED ,CHECKED SURFACE LINES , FOUND SUCTION TANKS FILLED WITH BARITE SETTLEMENTS. | MUD | NA |  | 05/18/2022 | SSA-5969 | 9 | UTMN-3021
1752 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | SSA-5974 | Hrs | HRDH-1970
1753 | CWEL | ARM | 557.25 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/18/2022 | SSA-5974 | 24 | HRDH-1970
1754 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | T216 | Hrs | ANDR-95
1755 | IDPR | NPC | 35.25 | 17 May 0800 - 1915 | 9936 | 896680 | NOISY SIGNAL, TROUBLESHOTING, DOWNHOLE WASH OUT. | BHA | JARS |  | 05/18/2022 | T216 | 14.25 | ANDR-95
1756 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | T902 | Hrs | HZEM-162404
1757 | XTRI | ITS | 4 | 18 May 0500 - 0900 | 7605 | 896613 | ITS BACK UP BELT TONG DIES ARE WORN OUT. | JF | CTRQ |  | 05/18/2022 | T902 | 4 | HZEM-162404
1758 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/18/2022 | V140A | Hrs | SFNY-1760
1759 | FOT | RIG | 22 | 17 May 2230 - 2100 | 4161 | 896635 | LOST COMMUNICATION WITH MWD-GR DOWNHOLE TOOLS. ALL TROUBLESHOOTING TRIALS FAILED. CAUSE ASSUMED TO BE LOW FLOW RATE AND RPM DUE TO POWER LIMITATIONS | RR | PSYS |  | 05/18/2022 | V140A | 15.5 | SFNY-1760
1760 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | 095TE | Hrs | MNIF-220
1761 | FOT | BHI | 3.75 | 19 May 1630 - 2100 | 16949 | 896816 | BHI TESTRAK TOOL FAILURE WHILE TAKING PRESSURE POINTS, RDD REQUEST TO CANCEL FPT. | BHA | LWD |  | 05/19/2022 | 095TE | 3.75 | MNIF-220
1762 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | ADC-32 | Hrs | SDGM-1228
1763 | UVLC | ARM | 32 | 18 May 2100 - 0500 | 11088 | 896689 | OBSERVED 220 BPH LOSSES @ 480 GPM WHILE DRLG | LCIR | NA |  | 05/19/2022 | ADC-32 | 24 | SDGM-1228
1764 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | ADC-34 | Hrs | UTMN-2316
1765 | MATL | ARM | 6.5 | 19 May 2230 - 0500 | 10892 | 896615 | XO'S INCORRECT FOR 9-5/8" 58.4# CASING. | WO | NA |  | 05/19/2022 | ADC-34 | 6.5 | UTMN-2316
1766 | WTHR | ARM | 9 | 18 May 0030 - 0930 | 4021 | 896776 | REPEATED ATTEMPTS TO UNSET ESP PACKER UNSUCCESFUL. DECISION MADE TO PUNCH TUBING TO EQUALIZE ACROSS PACKER AND UNSET. RIGGING UP WL UNIT WHICH WAS DELAYED DUE TO BAD WEATHER. | WON | NA |  | 05/19/2022 | ADC-50 | 4.5 | SFNY-1177
1767 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | ADC-50 | Hrs | SFNY-1177
1768 | MRWL | RIG | 90 | 14 May 1800 - 0500 | 0 | 896533 | WHILE LIFTING 13-5/8" BOP AFTER N/D, BOP STACK MOVED AND BENT ESP CABLE. PERFORMED VARIOUS TESTS ON ESP CABLE: PHASE-TO-PHASE, PHASE-TO-GROUND, AND 5 KV VOLTAGE TEST - ALL OKAY. DISCUSSION WITH TOWN DETERMINED THAT DAMAGE TO CABLE COULD RESULT IN REDUCED LIFESPAN OF THE ESP. DECISION MADE TO RECOMPLETE. | BOP | BOP |  | 05/19/2022 | ADC-50 | 19.5 | SFNY-1177
1769 | WTHR | ARM | 9 | 18 May 0030 - 0930 | 4021 | 896776 | REPEATED ATTEMPTS TO UNSET ESP PACKER UNSUCCESFUL. DECISION MADE TO PUNCH TUBING TO EQUALIZE ACROSS PACKER AND UNSET. RIGGING UP WL UNIT WHICH WAS DELAYED DUE TO BAD WEATHER. | WON | NA |  | 05/19/2022 | ADC-50 | 4.5 | SFNY-1177
1770 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | ADC-56L | Hrs | UTMN-2330
1771 | FOT | SDM | 62.5 | 17 May 1300 - 0330 | 15784 | 896676 | POWER DRIVE JAMMING. | BHA | RSS |  | 05/19/2022 | ADC-56L | 22.5 | UTMN-2330
1772 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | ADC-57L | Hrs | FDHL-158
1773 | PSSW | TK3 | 3 | 19 May 0200 - 0500 | 15534 | 896797 | R/B ONE STDP, ATTEMPT TO POOH OBSERVE 15-20 K O/P AT 15,534 FT. M/U ONE STD, ATTEMPT TO RIH W/ TQ, OBSERVE TDS STALLE. | STUK | NA |  | 05/19/2022 | ADC-57L | 3 | FDHL-158
1774 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | ADC-65L | Hrs | HWYH-1280
1775 | FWTS | SDM | 152 | 12 May 1600 - 0915 | 5432 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/19/2022 | ADC-65L | 3.75 | HWYH-1280
1776 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | ADES-144 | Hrs | UTMN-3099
1777 | FOT | SAM | 33.25 | 18 May 1730 - 0315 | 11872 | 896688 | SAMAA FCS NEGATIVE TEST PACKER FAILURE. | BHA | WBCL |  | 05/19/2022 | ADES-144 | 21.75 | UTMN-3099
1778 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | DPS-74 | Hrs | NJYN-54
1779 | FOT | BLH | 850.75 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/19/2022 | DPS-74 | 24 | NJYN-54
1780 | 7579 |  | CIRC | E | 2664 | MPMP | CIRC TWO BOTTOM UP & CONFIRM MUD WT IN & OUT = 73 PCF [ 200 GPM & 350 PSI ]. | 7579 |  | RIG | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1781 | 7579 |  | OTH | E | 2664 | NA | FLOW CHECK, HOLE STATIC. | 7579 |  | RIG | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1782 | 7579 | 7350 | LOG | E | 2664 | WLT | POOH BHI LOGGING TOOL RUN # 3 [ RCX ON GR ] TO NEXT SAMPLE POINT# 8 WITH CONTROL SPEED @ 7350'. | 7579 | 7560 | BAW | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1783 | 7579 | 7350 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 8TH SAMPLE POINT [ COLLECT 6 OUT OF 10 SAMPLE ] @ 7350'.- ATTEMPTED TO PUMP OUT WITH RCI XL PKR, ABORTED DUE TO LOW MOBILITY, INFLATE STRADDLE PKR & TAKE 2 CYCLE FOR 8 HRS WITH LOW MOBILITY, - MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE [ NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN ].- POINT# 8 [ LFDR FM ] @ 7350': TOTAL DUMPING IN ANNUL: 1.2 BBL / WATER & OIL, [ PUMP OUT, NO SAMPLE COLLECT ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 7350 | BAW | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1784 | 7579 | 6119 | LOG | E | 2664 | WLT | POOH BHI LOGGING TOOL RUN # 3 [ RCX ON GR ] ON 5" D/P INSIDE HNIF FM @ 6119'. | 7579 | 7350 | BAW | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1785 | 7579 | 6119 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN# 3 MDT [ RCX ON GR ] ON 5" D/P EVALUATED LAST P.POINTS AS PER RDD PROGRAM @ 6119'.- PERFORMED STICK TENDENCY TESTS @ 6119' FOR 15 MIN, NO STICKING TENDENCY.- RECIPROCATE STRING EVERY 30 MIN, NO OVERPULL OBSERVED.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- TOTAL P.POINT RECORDED 23 POINTS.- OPEN HOLE IN GOOD CONDITION. | 7579 | 6119 | BAW | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1786 | 7579 | 5660 | LOG | E | 2664 | WLT | POOH BHI LOGGING TOOL RUN # 3 [ RCX ON GR ] ON 5" D/P TO ARAB-D ZONE-1 WITH CONTROL SPEED @ 5660'. | 7579 | 6119 | BAW | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1787 | 7579 | 5660 | LOG | E | 2664 | WLT | PERFORMED STICK TENDENCY TESTS @ 5660' FOR 60 MIN, NO STICKING TENDENCY. | 7579 | 5660 | BAW | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1788 | 7579 | 5616 | LOG | E | 2664 | WLT | BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ], POSITION STRING & WORK TO COLLECT 9TH SAMPLE POINT [ COLLECT 7 OUT OF 10 SAMPLE ] @ 5616'.- ATTEMPTED TO PUMP OUT WITH STANDERED PKR, ABORTED DUE TO LOW RATE, SWITCH TO RCI XL PKR & TAKE 2 CYCLE FOR 2.5 +4 HRS, - MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE [ NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN ].- POINT# 9 [ ARAD-D ZONE-1 FM ] @ 5616': TOTAL DUMPING IN ANNUL: 2 BBL / WATER, [ COLLECT SAMPLE COLLECT ].- MONITOR HOLE ON TRIP TANK, HOLE STATIC.> TOTAL HRS SINCE LAST CIRCULATION : 21 HRS. | 7579 | 5616 | BAW | 05/19/2022 | DQ-48 | LOG | KHRS-1420
1789 | 201.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2664 | 11 May 1930 | 05/19/2022 | DQ-48 | Type | KHRS-1420
1790
1791
1792 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | EXL-IA | Hrs | SFNY-4240
1793 | FOT | RIG | 32.25 | 18 May 0815 - 1630 | 6335 | 896612 | WHEN ON BOTTOM NOTICED DRILLERS BOP REMOTE PANNEL DIGITAL PRESSURES FLUCTUATING & LIGHTS NOT ILUMINATING. FOUND A COMUNICATION ISSUE WITHIN THE FIBER OPTIC SYSTEM | RR | RWCS |  | 05/19/2022 | EXL-IA | 11.5 | SFNY-4240
1794 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | NA-18S | Hrs | UTMN-2334
1795 | STBH | ARM | 170.5 | 12 May 1300 - 0500 | 14361 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/19/2022 | NA-18S | 24 | UTMN-2334
1796 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | PA-785S | Hrs | QTIF-269
1797 | HINW | BAW | 8.5 | 19 May 2030 - 0500 | 0 | 896796 | WHILE POOH W/L MPC CUTTER GOT HELD. | STUK | WLT |  | 05/19/2022 | PA-785S | 8.5 | QTIF-269
1798 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SDA | Hrs | MRJN-733
1799 | FOT | BCT | 20.5 | 18 May 1415 - 1045 | 0 | 896721 | BAKER HYDRAULIC PUMP ON CTU POWER PACK FAILED. STOP PUMPING N2, CLOSE CTU SLIPS AND PIPE RAMS, STRIPPERS. SERURE REEL. REPAIR HYDRAULIC PUMP. WAITING TO RECEIVE REPLACMENT COIL TUBING POWER PACK. | TF | CTBG |  | 05/19/2022 | SDA | 5.75 | MRJN-733
1800 | 17491 |  | STIM | E | 2545 | CTU | CONT RIH W/ BHI 2-3/8'' CTU IN L-3 OPEN HOLE WHILE PUMPING PRE-FLUSH TO FINAL REACH DEPTH @ 15,640 FT.- PRE-FLUSH PUMPED 3200 BBLS.- PUMP RATE: 3 BPM, CTU PUMPING PRESS: 3000 PSI, WHP: 60 PSI, CTU FINAL SPEED: 1-1.5 FT/MIN.- CHOKE CLOSED. | 17491 |  | BCT | 05/19/2022 | SIN30L | STIM | KHRS-1409
1801 | 17491 |  | STIM | E | 2545 | CTU | PERFORM L-3 ACID MATRIX STIMULATION W/ BAKER CTU AS PER PROGRAM WHILE POOH F/ 15,640' FT TO 10,900 FT . ON GOING - CHOKE CLOSED.- PUMP RATE: 2.3-2.4 BPM, CTU PUMPING PRESS: 3100 PSI, WHP: 130 PSI, CTU SPEED: 1-10 FT/MIN.- VOLUME PUMPED: 15 % HCL= 1550 BBLS, EMULSIFIED ACID: 475 BBLS. | 17491 |  | BCT | 05/19/2022 | SIN30L | STIM | KHRS-1409
1802 | 211.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 24 | 2545 | 01 May 1800 | 05/19/2022 | SIN30L | Type | KHRS-1409
1803
1804
1805 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SND-2001 | Hrs | UTMN-2329
1806 | WCC5 | ARM | 57.5 | 17 May 1930 - 0500 | 11660 | 896696 | OBSERVED WELL FLLOWING AFTER MAKING SURVEY | WCNT | NA |  | 05/19/2022 | SND-2001 | 24 | UTMN-2329
1807 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SND-2002 | Hrs | WAQR-23
1808 | UVLC | ARM | 216 | 11 May 0500 - 0500 | 10207 | 896698 | ENCOUNTERED COMPLETE LOSS OF CIRCULATION @ 10207' WHILE DRILLING. | LCIR | NA |  | 05/19/2022 | SND-2002 | 24 | WAQR-23
1809 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SND-2003 | Hrs | RMTN-17
1810 | HERR | RIG | 29.5 | 18 May 1100 - 1630 | 10558 | 896720 | AFTER DOWNLINKING PRIOR TO CONNECTION, SPP INCREASED FROM 1950 PSI TO 2700 PSI. DECISION MADE TO POOH, AT SURFACE BREAK OUT BAKER FILTER SUB AND FOUND DP SCALING ACCUMULATED AROUND FILTER SUB AND FILTER SUB PLUGGED. | DSF | STRG |  | 05/19/2022 | SND-2003 | 11.5 | RMTN-17
1811 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SND-2004 | Hrs | BRRI-1148
1812 | SROP | NOC | 25.5 | 18 May 0330 - 0500 | 9803 | 896694 | NO PROGRESS WITH NOV 8-1/2" CORING BHA & CORE JAMMED. | JF | CORC |  | 05/19/2022 | SND-2004 | 24 | BRRI-1148
1813 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SND-2008 | Hrs | HRDH-1052
1814 | FOT | WDS | 25.25 | 18 May 1030 - 1145 | 12400 | 896719 | WHILE DRILLING, HAD WFD MWD FAILURE DUE TO NO SIGNAL | BHA | MWD |  | 05/19/2022 | SND-2008 | 6.75 | HRDH-1052
1815 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SND-3003 | Hrs | HRDH-2303
1816 | FOT | WCR | 5.5 | 19 May 1000 - 1530 | 5663 | 896614 | FAILED 3 POWER TONG TO ACHIEVE THE OPTIMUM MAKE UP TORQUE WITH JAM UNIT FOR JPC-4 53.5# CSG . | TF | CTRQ |  | 05/19/2022 | SND-3003 | 5.5 | HRDH-2303
1817 | FOT | RIG | 1 | 19 May 1130 - 1230 | 8575 | 896736 | REPAIR DP POWER TONG. | TF | SLIPS |  | 05/19/2022 | SP-120 | 1 | MNIF-188
1818 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SP-120 | Hrs | MNIF-188
1819 | HERR | RIG | 2 | 19 May 0800 - 1000 | 8575 | 896707 | RIG SHUT-DOWN TO REPLACE THE DRILLER FOR LACK OF COMPETENCY. TOTCO RING WAS NOT INSTALLED IN THE CLEAN OUT BHA. | TF | FV |  | 05/19/2022 | SP-120 | 2 | MNIF-188
1820 | FOT | RIG | 1 | 19 May 1130 - 1230 | 8575 | 896736 | REPAIR DP POWER TONG. | TF | SLIPS |  | 05/19/2022 | SP-120 | 1 | MNIF-188
1821 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | SSA-5974 | Hrs | HRDH-1970
1822 | CWEL | ARM | 580.25 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/19/2022 | SSA-5974 | 23.5 | HRDH-1970
1823 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/19/2022 | T218 | Hrs | UTMN-1281
1824 | FOT | HWP | 4.5 | 19 May 0500 - 0930 | 0 | 896798 | HALL W/L MPET LOGGING TOOL FAILURE . | TF | WLT |  | 05/19/2022 | T218 | 4.5 | UTMN-1281
1825 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADC-17 | Hrs | ZULF-1211
1826 | FOT | SPS | .5 | 21 May 1430 - 1500 | 6802 | 896804 | EXCESS TIME ON SPERRY SUN WHILE SENDING DOWNLINK FOR RELOG | TF | COMP |  | 05/21/2022 | ADC-17 | .5 | ZULF-1211
1827 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADC-31 | Hrs | SDGM-1181
1828 | FOT | GOC | 1.5 | 21 May 0100 - 0230 | 0 | 896850 | EXCESS TIME TO RIG UP ALGAITH LINKS AND CRT TOOL. | TF | CRT |  | 05/21/2022 | ADC-31 | 1.5 | SDGM-1181
1829 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADC-42L | Hrs | UTMN-2327
1830 | FOT | SDM | 30.25 | 20 May 2245 - 0500 | 14388 | 896819 | OBSERVED HIGH DIFFERENTIL PRESSURE AND RUBBER ON SHALE SHAKER. | BHA | MMOT |  | 05/21/2022 | ADC-42L | 24 | UTMN-2327
1831 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADC-50 | Hrs | SFNY-1177
1832 | MRWL | RIG | 138 | 14 May 1800 - 0500 | 0 | 896533 | WHILE LIFTING 13-5/8" BOP AFTER N/D, BOP STACK MOVED AND BENT ESP CABLE. PERFORMED VARIOUS TESTS ON ESP CABLE: PHASE-TO-PHASE, PHASE-TO-GROUND, AND 5 KV VOLTAGE TEST - ALL OKAY. DISCUSSION WITH TOWN DETERMINED THAT DAMAGE TO CABLE COULD RESULT IN REDUCED LIFESPAN OF THE ESP. DECISION MADE TO RECOMPLETE. | BOP | BOP |  | 05/21/2022 | ADC-50 | 24 | SFNY-1177
1833 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADC-57L | Hrs | FDHL-158
1834 | PSSW | TK3 | 40.25 | 19 May 0200 - 1815 | 15534 | 896797 | R/B ONE STDP, ATTEMPT TO POOH OBSERVE 15-20 K O/P AT 15,534 FT. M/U ONE STD, ATTEMPT TO RIH W/ TQ, OBSERVE TDS STALLE. | STUK | NA |  | 05/21/2022 | ADC-57L | 13.25 | FDHL-158
1835 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADES-174 | Hrs | GHZL-88
1836 | FOT | SDM | 27.5 | 20 May 2230 - 0200 | 12280 | 896711 | WHILE WASH DOWN LAST STAND TO BOTTOM LOST COMMUNICATION WITH SLB RSS. ATTEMPTED TROUBLESHOOT AND MADE ANTIJAMMING PROCEDURE TO SLB RSS WITHOUT SUCCESS. DECIDE TO POOH TO CHANGE SLB RSS. PUMPED HI-VIS PILL & CHC. | BHA | RSS |  | 05/21/2022 | ADES-174 | 21 | GHZL-88
1837 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADES-40 | Hrs | ANDR-29
1838 | FOT | BC | 46 | 20 May 0700 - 0500 | 6549 | 896818 | BAKER S-3 PACKER SEAL ASSY. FAILURE TO PRESSURE TEST. | TF | SEAL |  | 05/21/2022 | ADES-40 | 24 | ANDR-29
1839 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADES-889 | Hrs | HRDH-1858
1840 | HERR | RIG | 22.25 | 21 May 0600 - 0415 | 13350 | 896713 | SLB ATTEMPT TO LATCH IN WITHOUT SUCCESS. OBSERVED DEBRIS INSIDE WET CONNECTOR. | JF | WLT |  | 05/21/2022 | ADES-889 | 22.25 | HRDH-1858
1841 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ADM-656 | Hrs | SFNY-396
1842 | WOTO | ARM | 4 | 21 May 1000 - 1400 | 0 | 896802 | DUE TO NEW REQUIREMENTS FROM RDD FOR PLT LOG , WAITING ON EQUIPMENT PREPARATION. | WO | NA |  | 05/21/2022 | ADM-656 | 4 | SFNY-396
1843 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | ARO-3002 | Hrs | MRJN-815
1844 | FOT | HML | 38.75 | 20 May 0545 - 2330 | 8870 | 896759 | HALLIBURTON MLT UNABLE TO WASH OVER WHIPSTOCK. | TF | WPSTK |  | 05/21/2022 | ARO-3002 | 18.5 | MRJN-815
1845 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | DPS-4 | Hrs | MDRK-54
1846 | STBH | ARM | 149.5 | 04 May 1900 - 0215 | 13938 | 896247 | STRING GOT DIFFERENTIAL STUCK AFTER KILLING THE WELL. CONSEQUENCE LOST TIME TO LT ID:895515 | STUK | BHA | 895547 | 05/21/2022 | DPS-4 | 11.25 | MDRK-54
1847 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | DPS-74 | Hrs | NJYN-54
1848 | FOT | BLH | 887.75 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/21/2022 | DPS-74 | 23.5 | NJYN-54
1849 | 7579 | 4790 | LOG | E | 2664 | WLT | POOH BHI LOGGING TOOLS RUN # 3 [ RCX ON GR ] ON 5" D/P WITH CONTROLLED SPEED TILL SES DEPTH T 4790'.- MONITORE HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7579 | 6600 | BAW | 05/21/2022 | DQ-48 | LOG | KHRS-1420
1850 | 7579 |  | OTH | E | 2664 | NA | BHI UNLATCH CABLE HEAD & POOH T/ SURFACE. L/D SES & R/D SHEAVES.- MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7579 |  | BAW | 05/21/2022 | DQ-48 | LOG | KHRS-1420
1851 | 7579 | 3485 | LOG | E | 2664 | WLT | POOH BHI [ RCX-GR ] LOGGING TOOL RUN# 3 ON 5" D/P TILL 13 3/8" CSG SHOE @ 3485'. - MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 4790 | BAW | 05/21/2022 | DQ-48 | LOG | KHRS-1420
1852 | 7579 |  | OTH | E | 2664 | NA | FLOW CHECK, HOLE STATIC. | 7579 |  | RIG | 05/21/2022 | DQ-48 | LOG | KHRS-1420
1853 | 7579 | 183 | TO | E | 2664 | STDP | POOH BHI [ RCX-GR ] LOGGING TOOL RUN# 3 ON 5" D/P TO 183'. - MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 3485 | RIG | 05/21/2022 | DQ-48 | LOG | KHRS-1420
1854 | 7579 |  | OTH | E | 2664 | NA | FLOW CHECK, HOLE STATIC. | 7579 |  | RIG | 05/21/2022 | DQ-48 | LOG | KHRS-1420
1855 | 7579 |  | OTH | E | 2664 | NA | HPJSM, POOH TO SURFACE WHILE L/D ALL BHI RUN # 3 [ RCX-GR ] LOGGING TOOL. - L/D 8 X 6 1/4" DCS & JAR [ CONDITION TRIP BHA ] F/ DRK. - MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7579 |  | BAW | 05/21/2022 | DQ-48 | LOG | KHRS-1420
1856 | 7579 |  | OTH | N |  | NA | HPJSM, R/U 4" D/P HANDLING TOOLS. | 7579 |  | RIG | 05/21/2022 | DQ-48 | PA | KHRS-1420
1857 | 7579 |  | HT | N |  | STRG | P/U, M/U & RIH 4" D/P AS CMT STINGER TOTAL 32 JTS DRIFTED SINGLE BY SINGLE FROM PIPE RACK TO 1026'.- MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7579 |  | RIG | 05/21/2022 | DQ-48 | PA | KHRS-1420
1858 | 7579 |  | OTH | N |  | NA | HPJSM, R/D 4" D/P HANDLING TOOLS & R/U 5'' D/P HANDLING TOOLS. | 7579 |  | RIG | 05/21/2022 | DQ-48 | PA | KHRS-1420
1859 | 7579 | 3485 | TI | N |  | STDP | RIH W/ 4" D/P CMT STINGER ON 5" D/P TILL 13 3/8" CSG SHOE @ 3485'.- MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7579 | 1026 | RIG | 05/21/2022 | DQ-48 | PA | KHRS-1420
1860 | 7579 | 7579 | TI | N |  | STDP | RIH WITH CMT STINGER ASSY ON 5'' D/P TO BOTTOM @ 7579'.- MONITORE HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION.- TAG BTM WITH 5 KLB. | 7579 | 3485 | RIG | 05/21/2022 | DQ-48 | PA | KHRS-1420
1861 | 7579 |  | CIRC | N |  | MPMP | POOH TO 7570', CIRC 2 TIMES BTM UP & CONDITION MUD, [ CONFIRM MW IN & OUT = 73 PCF OBM ].- CIRC WITH 7 BPM, 800 PSI & 10 RPM. | 7579 |  | RIG | 05/21/2022 | DQ-48 | CSG | KHRS-1420
1862 | 7579 |  | OTH | N |  | NA | HPJSM, R/U BKR CEMENT SURFACE LINES & P/T SAME TO 3000 PSI. | 7579 |  | BCM | 05/21/2022 | DQ-48 | PA | KHRS-1420
1863 | 7579 | 7570 | CMP | N |  | OEDP | HPJSM, PERFORMED 1ST P&A CEMENT PLUG [ 7570' - 6970' ] 600 FT AS FOLLOW :-- CEMENT UNIT PUMPED 50 BBLS (95 PCF ) SPACER AHEAD.- 47 BBLS ( 118 PCF ) BATCH MIXED CEMENT SLURRY & 15.6 BBLS ( 95 PCF ) SPACER BEHIND. - DISPLACE SAME WITH 98 BBBLS 73 PCF OBM, [ 6 BBL UNDERDISPLACEMENT ].- CHECK FOR BACK FLOW, NO FLOW BACK, PLUG BALANCED.- NO LOSSES DURING CEMENT JOB. | 7579 | 7570 | BCM | 05/21/2022 | DQ-48 | PA | KHRS-1420
1864 | 7579 | 6870 | TO | N |  | STDP | POOH TO 6870 FT [ BTM DEPTH OF 2ND PLUG ] @ CONTROLLED SPEED. | 7579 | 7570 | RIG | 05/21/2022 | DQ-48 | PA | KHRS-1420
1865 | 237.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 12 | 2664 | 11 May 1930 | 05/21/2022 | DQ-48 | Type | KHRS-1420
1866
1867
1868 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | HI-4 | Hrs | SFNY-918
1869 | SRVC | ARM | 15.75 | 20 May 1415 - 1200 | 7353 | 896842 | V-SAT IS DOWN. GOC UNABLE TO MONITOR DRILLING AND STEERING OPERATION. STOPPED DRILLING OPERATION. V-SAT TECHNICIAN ONBOARD WORKING ON THE ISSUE. | WO | NA |  | 05/21/2022 | HI-4 | 7 | SFNY-918
1870 | FOT | WWD | 27.5 | 20 May 0600 - 0930 | 13126 | 896839 | TRYING TO SET WHIPSTOCK AND ESTABLISH CIRCULATION, STG PLUGGED. | TF | WPSTK |  | 05/21/2022 | NA-18S | 4.5 | UTMN-2334
1871 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | NA-18S | Hrs | UTMN-2334
1872 | STBH | ARM | 191 | 12 May 1300 - 0500 | 13129 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/21/2022 | NA-18S | 19.5 | UTMN-2334
1873 | FOT | WWD | 27.5 | 20 May 0600 - 0930 | 13126 | 896839 | TRYING TO SET WHIPSTOCK AND ESTABLISH CIRCULATION, STG PLUGGED. | TF | WPSTK |  | 05/21/2022 | NA-18S | 4.5 | UTMN-2334
1874 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | NBR-263S | Hrs | QTIF-736
1875 | FOT | RIG | 2.75 | 21 May 0215 - 0500 | 124 | 896821 | FAILURE OF TOP DRIVE ROTATION WHILE CIRC DUE TO ELEC PROBLEM. | RR | TDS |  | 05/21/2022 | NBR-263S | 2.75 | QTIF-736
1876 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | NBR-797S | Hrs | UTMN-3130
1877 | FOT | GOC | 4.5 | 21 May 1930 - 0000 | 382 | 896846 | OBSERVE CRT RUBBER DAMAGED & GUIDE NOSE LOOSE. | TF | CRT |  | 05/21/2022 | NBR-797S | 4.5 | UTMN-3130
1878 | FOT | WWW | 4 | 21 May 0100 - 0500 | 0 | 896849 | EXCESSIVE TIME TO P/TEST WEATHERFORD CO-FLEX HOSE DUE TO MULTIPLE LEAKS FOUND. | TF | DSTT |  | 05/21/2022 | PA-622S | 4 | AFLJ-4
1879 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | PA-622S | Hrs | AFLJ-4
1880 | UNKN | RIG | 2 | 21 May 2130 - 2330 | 0 | 896848 | STOPPED OPERATION & HELD STAND DOWN SAFETY MEETING WITH RIG CREW TO DISCUSS THE FAILURE TO REPORT THE INCIDENT ON TIME. | HSEI | NA |  | 05/21/2022 | PA-622S | 2 | AFLJ-4
1881 | FOT | WWW | 4 | 21 May 0100 - 0500 | 0 | 896849 | EXCESSIVE TIME TO P/TEST WEATHERFORD CO-FLEX HOSE DUE TO MULTIPLE LEAKS FOUND. | TF | DSTT |  | 05/21/2022 | PA-622S | 4 | AFLJ-4
1882 | 17491 |  | STIM | E | 2545 | CTU | CONT. POOH W/ 2-3/8" CT F/ 1,400 FT TO SURFACE, WHILE PUMPING 66 PCF VISCOUS BRINE AT MINIMUM RATE 0.25 BPM.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM . | 17491 |  | BCT | 05/21/2022 | SIN30L | STIM | KHRS-1409
1883 | 17491 |  | STIM | E | 2545 | CTU | HPJSM, DISCONNECT RISER, R/D BAKER CTU INJECTOR HEAD, RISER, QUAD BOP, HCR GATE VALVE AND ALL RELATED LINES. N/D CT RISER, ISO-GATE VALVE WITH 13-5/8" - 5 K X 4-1/16"-10K ADAPTOR FLANGE- DISPLACED CTU TO WATER.- L/D CTU BHA.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. | 17491 |  | BCT | 05/21/2022 | SIN30L | STIM | KHRS-1409
1884 | 17491 |  | STIM | E | 2545 | CTU | HPJSM, N/U BELL NIPPLE & FLOW LINE. - MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. | 17491 |  | BCT | 05/21/2022 | SIN30L | STIM | KHRS-1409
1885 | 17491 |  | SET | N |  | WBSH | INSTALL 11'' WEAR BUSHING.- MONITOR WELL ON TRIP TANK, PUMPING 66 PCF VISCOUS BRINE W/ 2-3 BPM. | 17491 |  | RIG | 05/21/2022 | SIN30L | WH | KHRS-1409
1886 | 17491 |  | HT | N |  | FISHT | HPJSM, P/U & M/U WIS WHIPSTOCK RETRIEVAL HOOK ASSY TO 509 FT.- RETRIEVAL HOOK + 1 JT X 5" DP + FLOAT SUB + MWD + FILTER SUB + 3 JT X 5" HWDP + 4 X 9-5/8" MAGNET + 3 JT X 5" HWDP + 6-1/2" DRLG JAR + 5 JT X 5" HWDP. - SCRIB HOOK WITH MWD & SHALLOW TESTED MWD TOOLS W/ 350 GPM / 700 PSI, OK.- MONITOR THE WELL THROUGH TRIP TANK WHILE PUMPING 66 PCF VISCOUS BRINE- +/- 150 BPH LOSSES. | 17491 |  | WI1 | 05/21/2022 | SIN30L | FISH | KHRS-1409
1887 | 17491 | 9376 | TI | N |  | STDP | RIH W/ WSTK RETRIEVAL ASSY ON 5" DP F/ 403 FT TO 9376 FT.- FILL STRING WHILE RIH EVERY 20 STDS.- MONITOR THE WELL THROUGH TRIP TANK WHILE PUMPING 66 PCF VISCOUS BRINE, +/-150 BPH LOSSES. | 17491 | 403 | RIG | 05/21/2022 | SIN30L | FISH | KHRS-1409
1888 | 17491 | 9690 | RTRV | N |  | WPSTK | ORIENTED HOOK NOZZLE TO 130DEG & CLEAN HOOK SLOT BY WASHING ACROSS WPS FACE F/ 9376' T/ 9690' W/ 360 GPM @ 900 PSI.-ORIENT NOZZLE TO 310DEG, NO SUCCESS TO ENGAGE AND RELEASE WPS.-ORIENT NOZZLE TO 305DEG, NO SUCCESS TO ENGAGE AND RELEASE WPS.- ORIENT NOZZLE TO 290DEG, ENGAGED 9-5/8" WPS & RELEASED SAME W/ 120 KLBS OVERPULL. OBSERVED DRAG INCREASED BY +-5KIB.- CONDUCT TQ TEST AS PER WIS ENGINEER TO ENSURE HOOK ENGAGEMENT .- DYNAMIC LOSSES, +- 250 BPH. | 17491 | 9376 | WI3 | 05/21/2022 | SIN30L | FISH | KHRS-1409
1889 | 17491 |  | WCNT | N |  | NA | PICK UP 5' & FLOW CHECK MEANWHILE ALLOW PACKER ELEMENT TO RETRACT.- HPJSM PRIOR TO POOH W/ WPS.- STATIC LOSSES: +- 120 BPH. | 17491 |  | RIG | 05/21/2022 | SIN30L | FISH | KHRS-1409
1890 | 17491 | 8919 | TO | N |  | STDP | PUMP OUT W/ L-3 WPS RETRIVAL BHA @ CONTROLLED SPEED F/ 9376' T/ 8919' (5 STD)- DYNAMIC LOSSES, +- 250 BPH. | 17491 | 9376 | RIG | 05/21/2022 | SIN30L | FISH | KHRS-1409
1891 | 17491 | 4500 | TO | N |  | STDP | POOH W/ L-3 WPS RETRIVAL BHA @ CONTROLLED SPEED F/ 8919' T/ 4500'. ON GOING.- MONITOR THE WELL THROUGH TRIP TANK WHILE PUMPING 66 PCF VISCOUS BRINE- +/- 100 BPH LOSSES. | 17491 | 8919 | RIG | 05/21/2022 | SIN30L | FISH | KHRS-1409
1892 | 242.75 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | COIL TUBING OPERATIONS TO PERFORM ACID STIMULATION JOB. | 7.5 | 2545 | 01 May 1800 | 05/21/2022 | SIN30L | Type | KHRS-1409
1893
1894
1895 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SINO-10 | Hrs | JLDI-37
1896 | FOT | HCO | 23.5 | 20 May 1500 - 1430 | 9300 | 896840 | 7" RTT PKR NOT SEALING, BACK SIDE PRESSURE NOT HOLDING WITH RETURN FROM DP'S, CONFIRMED PKR. DAMAGED | TF | CHAMP |  | 05/21/2022 | SINO-10 | 9.5 | JLDI-37
1897 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SINO-27N | Hrs | HWYH-466
1898 | STBH | ARM | 13.5 | 21 May 1530 - 0500 | 7515 | 896822 | STRING GOT STUCK. | STUK | RBHA |  | 05/21/2022 | SINO-27N | 13.5 | HWYH-466
1899 | 6717 |  | CIRC | E | 2824 | MPMP | SWEEP HOLE WITH 2 X 50 BBL HI-VIS PILL AND CIRCULATE TILL SHALE SHAKERS CLEAN. | 6717 |  | RIG | 05/21/2022 | SINO-43L | CT | HWYH-2528
1900 | 6717 |  | WCNT | E | 2824 | NA | FLOW CHECK, WELL STATIC | 6717 |  | RIG | 05/21/2022 | SINO-43L | CT | HWYH-2528
1901 | 6717 | 6276 | ST | E | 2824 | SPDP | POOH W/ 8-1/2" ROTARY BHA T/ 6,276' (9-5/8" CSG SHOE), HOLE IN GOOD CONDITION. | 6717 | 6717 | RIG | 05/21/2022 | SINO-43L | CT | HWYH-2528
1902 | 6717 |  | WCNT | E | 2824 | NA | FLOW CHECK, WELL STATIC. | 6717 |  | RIG | 05/21/2022 | SINO-43L | CT | HWYH-2528
1903 | 6717 | 108 | TO | E | 2824 | STDP | POOH W/ 8-1/2" CONDITION TRIP REAMING ASSY F/ 6,276' TO TOP OF BHA @ 108'.> ARAMCO KPI 19 STD/HR, ACHIEVED 19.7 STD/HR. | 6717 | 6276 | RIG | 05/21/2022 | SINO-43L | CT | HWYH-2528
1904 | 6717 |  | WCNT | E | 2824 | NA | FLOW CHECK , WELL STATIC. | 6717 | 6276 | RIG | 05/21/2022 | SINO-43L | CT | HWYH-2528
1905 | 6717 |  | HT | E | 2824 | BHA | POOH W/ 8-1/2" CONDITION TRIP REAMING ASSY TO SURFACE & R/B BHA.->MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6717 |  | RIG | 05/21/2022 | SINO-43L | CT | HWYH-2528
1906 | 6717 |  | OTH | E | 2824 | NA | HPJSM, R/U E/L TOOLS & SHEAVES.,P/U & M/U BHI W/L LOGGING TOOLS RUN #3 GR - FTEX (PRESSURE TESTING).& RIH TO 6276.> TOTAL LOGGING TOOL LENGTH: 71.25', MAX OD: 4.25".> TESTED TOOLS & FUNCTIONS AT SURFACE.> PEFRORM CORRELATION LOG.> MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6717 |  | BAW | 05/21/2022 | SINO-43L | LOG | HWYH-2528
1907 | 6717 | 6717 | LOG | E | 2824 | WLT | CONT'D RIH W/ BHI LOGGING TOOLS RUN #3 ON W/L WHILE LOG-DOWN.F/ 6300' T/ 6528'. > PERFORM STICKY TEST @ 6,290' FOR 20 MIN - OK, NO OVERPULL OBSERVED.> RECORDED 20 OUT OF 20 PRESSURE POINTS F/ 6290' T/ 6528'. > PRESSURE POINTS @ 6,290', 6,300', 6,304', 6,310', 6,316', 6,320', 6,329.5', 6,336', 6,342.5', 6,352', 6,366', 6,376', 6,386', 6,396', 6,402', 6,417', 6,452', 6,476', 6,488', 6,528'> MONITORED WELL THRU TRIP TANK, STATIC. | 6717 | 6300 | BAW | 05/21/2022 | SINO-43L | LOG | HWYH-2528
1908 | 6717 |  | OTH | E | 2824 | NA | POOH WITH BHI RUN #3 TO SURFACE & L/D SAME.> MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6717 |  | BAW | 05/21/2022 | SINO-43L | LOG | HWYH-2528
1909 | 6717 |  | PJSM | E | 2824 | NA | HPJSM WITH ARAMCO, BAKER DSV, RIG CREW, & BAKER E/L TEAM & DISSCUS OPEN HOLE [ SAMPLE ] LOG JOB & RELATED RISK, | 6717 |  | TK2 | 05/21/2022 | SINO-43L | LOG | HWYH-2528
1910 | 6717 | 183 | LOG | E | 2824 | WLT | R/U BKR E/L EQUIPMENT & RIH BHI W/L LOGGING TOOLS RUN#4 MDT [ RCX ON GR ] TO 204FT.> TOTAL LOGGING TOOL LENGTH: 204.2', MAX OD: 7.46".> TESTED TOOLS & FUNCTIONS AT SURFACE.> MONITOR HOLE ON TRIP TANK, STATIC. | 6717 | 0 | BAW | 05/21/2022 | SINO-43L | LOG | HWYH-2528
1911 | 43.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2"VERTICAL EVALUATION HOLE LOGGING. | 24 | 2824 | 20 May 0030 | 05/21/2022 | SINO-43L | Type | HWYH-2528
1912
1913
1914 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SND-2001 | Hrs | UTMN-2329
1915 | WCC5 | ARM | 90 | 17 May 1930 - 1330 | 11660 | 896696 | OBSERVED WELL FLLOWING AFTER MAKING SURVEY | WCNT | NA |  | 05/21/2022 | SND-2001 | 8.5 | UTMN-2329
1916 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SND-2002 | Hrs | WAQR-23
1917 | UVLC | ARM | 264 | 11 May 0500 - 0500 | 10207 | 896698 | ENCOUNTERED COMPLETE LOSS OF CIRCULATION @ 10207' WHILE DRILLING. | LCIR | NA |  | 05/21/2022 | SND-2002 | 24 | WAQR-23
1918 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SND-2004 | Hrs | BRRI-1148
1919 | FOT | RIG | 3.25 | 10 May 0730 - 0330 | 5800 | 896387 | DRAWWORKS BRAKING SYSTEM MALFUNCTION, TROUBLESHOOT AND FIX IT. | RR | DWKS |  | 05/21/2022 | SND-2004 | 1.75 | BRRI-1148
1920 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SP-103 | Hrs | KRSN-71
1921 | FOT | RIG | 2.5 | 21 May 2300 - 0130 | 6925 | 896847 | OBSERVED LEAK ON TDS, WASHOUT BETWEEN SAVER SUB AND 4" DP | RR | TDS |  | 05/21/2022 | SP-103 | 2.5 | KRSN-71
1922 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SP-110 | Hrs | BRRI-562
1923 | HERR | RIG | 29 | 20 May 1200 - 1945 | 6055 | 896799 | RIG MUD PUMPS SUCTION & DISCHARGE SCREENS IMPROPERLY CLEAN & PULSATION DAMPENER'S RUBBER PIECES ACCUMULATE AT MWD FILTER SUB, WHICH AFFECT GETTING SIGNAL WHILE ORIENTING THE WHIPSTOCK | JF | CSYS |  | 05/21/2022 | SP-110 | 14.75 | BRRI-562
1924 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SSA-29 | Hrs | QTIF-348
1925 | XTTE | BHI | 13 | 20 May 1500 - 0315 | 18400 | 896820 | BAKER LOST SIGNAL FROM DOWNHOLE TOOLS. CYCLED PUMPS AND CHANGED PUMPS SEVERALS TIMES UNTIL SIGNAL REGAINED | TF | MWD |  | 05/21/2022 | SSA-29 | 10 | QTIF-348
1926 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SSA-46 | Hrs | JAHM-7
1927 | FOT | SWL | 47 | 19 May 2015 - 0500 | 3615 | 896757 | WHILE TESTING SLB MDT/GR TOOL IN 9-5/8" CSG TO 6000 PSI. FOUND LOST COMMUNICATION FROM TOOL. POOH WL. FOUND TOOL BROKEN/SHEARED FROM BETWEEN THE PKR. | TF | WLT |  | 05/21/2022 | SSA-46 | 24 | JAHM-7
1928 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | SSA-5974 | Hrs | HRDH-1970
1929 | CWEL | ARM | 627.25 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/21/2022 | SSA-5974 | 23.5 | HRDH-1970
1930 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/21/2022 | T907 | Hrs | RGHB-703
1931 | ACDI | SPS | 13.75 | 21 May 1515 - 0500 | 7350 | 896803 | DEVIATE FROM ORIGINAL DIRECTION PLAN BY AROUND 180 DEGREE AZIMUTH | DD | BHA |  | 05/21/2022 | T907 | 13.75 | RGHB-703
1932 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ADC-31 | Hrs | SDGM-1181
1933 | FOT | WCM | 5 | 23 May 0000 - 0500 | 9902 | 896940 | TRY TO CLOSE WFD DV TOOL WITHOUT SUCCESS. | TF | ACCSS |  | 05/23/2022 | ADC-31 | 5 | SDGM-1181
1934 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ADC-48 | Hrs | HWYH-1256
1935 | FOT | BHI | 34.5 | 22 May 1430 - 0500 | 17098 | 896879 | DEEP RESISTIVITY TOOL NOT WORKING | BHA | LWD |  | 05/23/2022 | ADC-48 | 23.5 | HWYH-1256
1936 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ADC-50 | Hrs | SFNY-1177
1937 | MRWL | RIG | 186 | 14 May 1800 - 0500 | 0 | 896533 | WHILE LIFTING 13-5/8" BOP AFTER N/D, BOP STACK MOVED AND BENT ESP CABLE. PERFORMED VARIOUS TESTS ON ESP CABLE: PHASE-TO-PHASE, PHASE-TO-GROUND, AND 5 KV VOLTAGE TEST - ALL OKAY. DISCUSSION WITH TOWN DETERMINED THAT DAMAGE TO CABLE COULD RESULT IN REDUCED LIFESPAN OF THE ESP. DECISION MADE TO RECOMPLETE. | BOP | BOP |  | 05/23/2022 | ADC-50 | 24 | SFNY-1177
1938 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ADC-65L | Hrs | HWYH-1280
1939 | FWTS | SDM | 163 | 12 May 1600 - 0500 | 5432 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/23/2022 | ADC-65L | 11 | HWYH-1280
1940 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ADES-158 | Hrs | ABQQ-736
1941 | HERR | RIG | 6.5 | 23 May 1300 - 1930 | 117 | 896956 | EXCEESIVE TIME WHILE N/U BELL NIPPLE DUE TO WRONG FLANGE SIZE | JF | FLR |  | 05/23/2022 | ADES-158 | 6.5 | ABQQ-736
1942 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ADM-655 | Hrs | SFNY-144
1943 | WPDH | AP3 | 14 | 23 May 1500 - 0500 | 0 | 896896 | WAIT ON SFNY FIELD SERVICE TO DE-PRESSURIZE SFNY-143/146 PLATFORM FOR SAFE RIG APPROACH. | WO | NA |  | 05/23/2022 | ADM-655 | 14 | SFNY-144
1944 | HERR | NCT | 7 | 22 May 0000 - 0700 | 0 | 896957 | NESR CTU WT NOT MATCHING WFD CONNECTOR DUE TO MISS DATA SHARED BY NESR. | JF | CTAC |  | 05/23/2022 | ADM-656 | 2 | SFNY-396
1945 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ADM-656 | Hrs | SFNY-396
1946 | HERR | WTS | 7 | 22 May 1900 - 0900 | 0 | 896877 | WFD CONNECTOR NOT MATCHING WITH 1.5" NESR E-CT. | JF | CTAC |  | 05/23/2022 | ADM-656 | 2 | SFNY-396
1947 | HERR | NCT | 7 | 22 May 0000 - 0700 | 0 | 896957 | NESR CTU WT NOT MATCHING WFD CONNECTOR DUE TO MISS DATA SHARED BY NESR. | JF | CTAC |  | 05/23/2022 | ADM-656 | 2 | SFNY-396
1948 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | BCTD-4 | Hrs | GHZL-94
1949 | FOT | RIG | 11.5 | 23 May 1400 - 0130 | 14013 | 896937 | DPS FAILED WHILE DRILLING, BHI TROUBLESHOOT WITHOUT SUCCESS. POH TO C/O BHA. | BHA | CTAC |  | 05/23/2022 | BCTD-4 | 11.5 | GHZL-94
1950 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | DPS-43 | Hrs | SDGM-1196
1951 | FOT | SPS | 29.75 | 21 May 0400 - 1115 | 15475 | 896714 | LOSS COMMUNICATION WITH RSS SYSTEM. | BHA | RSS |  | 05/23/2022 | DPS-43 | 4.75 | SDGM-1196
1952 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | DPS-74 | Hrs | NJYN-54
1953 | FOT | BLH | 933.25 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/23/2022 | DPS-74 | 23.5 | NJYN-54
1954 | 7153 | 0 | LOG | E | 2844 | WLT | POOH W/ W/ BHI W/L RUN # 2 (MREX_GR) T/ SURFACE, R/D SAME.- MONITOR HOLE ON TRIP TANK, STATIC. | 7153 | 0 | BAW | 05/23/2022 | DQ-50L | LOG | HRDH-582
1955 | 7153 |  | HT | E | 2844 | BHA | HPJSM, P/U, M/U & RIH 8 1/2" CONDITION TRIP REAMING ASSY TO 370 FT.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7153 |  | RIG | 05/23/2022 | DQ-50L | CT | HRDH-582
1956 | 7153 | 3845 | TI | E | 2844 | STDP | RIH 8 1/2" CONDITION TRIP REAMING ASSY TILL 9-5/8" CSG SHOE @ 3,845 FT.- MONITOR HOLE ON TRIP TANK, HOLE STATIC | 7153 | 620 | RIG | 05/23/2022 | DQ-50L | CT | HRDH-582
1957 | 7153 |  | CIRC | E | 2844 | MPMP | CUMULATIVE TIME TO FILL THE STRING & BREAK CIRC. | 7153 |  | RIG | 05/23/2022 | DQ-50L | LOG | HRDH-582
1958 | 7153 | 7153 | ST | E | 2844 | STDP | RIH 8 1/2" CONDITION TRIP REAMING ASSY TO BTM @ 7,153'.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7153 | 3845 | RIG | 05/23/2022 | DQ-50L | LOG | HRDH-582
1959 | 7153 |  | CIRC | E | 2844 | MPMP | CUMULATIVE TIME TO FILL THE STRING & BREAK CIRC. | 7153 |  | RIG | 05/23/2022 | DQ-50L | LOG | HRDH-582
1960 | 7153 |  | CIRC | E | 2844 | MPMP | SWEEP HOLE W/ 2 X 50 BBL HI-VIS PILL, CHC & CONDITION MUD.- MUD WT IN & OUT = 81 PCF. | 7153 |  | RIG | 05/23/2022 | DQ-50L | CT | HRDH-582
1961 | 7153 |  | OTH | E | 2844 | NA | FLOW CHECK - WELL STATIC. | 7153 |  | RIG | 05/23/2022 | DQ-50L | LOG | HRDH-582
1962 | 7153 | 3845 | ST | E | 2844 | STDP | POOH 8 1/2" CONDITION TRIP REAMING ASSY F/ 7,153 FT TO 9-5/8" CSG SHOE @ 3,845 FT.- MONITOR WELL THRU TRIP TANK & TRIP SHEET - WELL STATIC.- GOOD HOLE CONDITION. | 7153 | 7153 | RIG | 05/23/2022 | DQ-50L | CT | HRDH-582
1963 | 7153 |  | OTH | E | 2844 | NA | FLOW CHECK - WELL STATIC, PUMP SLUG. | 7153 |  | RIG | 05/23/2022 | DQ-50L | LOG | HRDH-582
1964 | 7153 | 620 | TO | E | 2844 | STDP | CONT. POOH W/ 8-1/2" CONDITION TRIP BHA F/ 9-5/8" CSG SHOE @ 3,845 FT TO TOP OF BHA @ 620 FT.- MONITOR WELL THRU TRIP TANK & TRIP SHEET - WELL STATIC.- ARAMCO KPI/ACTUAL: 19/21 STD/HR. | 7153 | 3845 | RIG | 05/23/2022 | DQ-50L | CT | HRDH-582
1965 | 7153 |  | OTH | E | 2844 | NA | FLOW CHECK-WELL STATIC.- CHANGE ELEVATOR FROM 4" TO 5" | 7153 |  | RIG | 05/23/2022 | DQ-50L | LOG | HRDH-582
1966 | 7153 |  | HT | E | 2844 | BHA | CONT. POOH 8-1/2" CONDITION TRIP BHA FROM 620 FT TO SURFACE.- L/D 8-1/2" BIT, RB 8-1/2" NBR & STRRS.- MONITOR WELL THRU TRIP TANK - WELL STATIC. | 7153 |  | RIG | 05/23/2022 | DQ-50L | CT | HRDH-582
1967 | 7153 |  | OTH | E | 2844 | NA | HPJSM. R/U W/L TOOLS & SHEAVES.P/U & M/U BHI W/L LOGGING TOOLS RUN # 3 SLIM FORMATION TESTER (GR-FTEX).- PERFORM SURFACE CHECKS AND TOOL CALIBRATION ON SURFACE BEFORE RIH.- TOOL LENGTH: 68.69', MAX OD: 4.13" (WITH TOOL CLOSED).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7153 |  | BAW | 05/23/2022 | DQ-50L | LOG | HRDH-582
1968 | 7153 | 6500 | LOG | E | 2844 | WLT | RIH WITH BHI RUN # 3 SLIM FORMATION TESTER (GR-FTEX) ON W/L TO 6,908'.- PEFRORM CORRELATION LOG PASS F/ 6,908 FT TO 6,551 FT.- PERFORM STICKY TEST @ 6,551 FT FOR 15 MIN - OK, NO OVERPULL OBSERVED.- RECORD 1/20 PRESSURE POINT...ONGOING.- POINT #1 @ 6,551 FT, FM PRESS = 3,068 PSI, EQ.M.WT = 67 PCF, CURRENT OVERBALANCE= 646 PSI. | 7153 | 6900 | BAW | 05/23/2022 | DQ-50L | LOG | HRDH-582
1969 | 44 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2844 | 22 May 0900 | 05/23/2022 | DQ-50L | Type | HRDH-582
1970
1971
1972 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ENSCO-54 | Hrs | ABSF-28
1973 | WTHR | ARM | 23 | 23 May 0600 - 0500 | 0 | 896944 | WAIT ON WEATHER TO MOVE RIG TO PLATFORM ABSF-23/28 | WON | NA |  | 05/23/2022 | ENSCO-54 | 23 | ABSF-28
1974 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | ENSCO-76 | Hrs | MRJN-851
1975 | FOT | BHI | 5.75 | 23 May 1730 - 2315 | 6090 | 896978 | OBSTRUCTION WHILE PULLING INSIDE 13-3/8" CASING DUE TO BAKER RSS PADS WERE NOT FULLY CLOSED. | BHA | RSS |  | 05/23/2022 | ENSCO-76 | 5.75 | MRJN-851
1976 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | NA-18S | Hrs | UTMN-2334
1977 | STBH | ARM | 239 | 12 May 1300 - 0500 | 13129 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/23/2022 | NA-18S | 24 | UTMN-2334
1978 | FOT | RIG | 2 | 23 May 1900 - 2100 | 129 | 896943 | WHILE CONNECTION. OBSERVED B/O OF CONNECTION BETWEEN MANUAL & HYD IBOP OF TDS. | DSF | DP |  | 05/23/2022 | NBR-263S | 2 | QTIF-736
1979 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | NBR-263S | Hrs | QTIF-736
1980 | FOT | RIG | 12.75 | 21 May 0215 - 1330 | 124 | 896821 | FAILURE OF TOP DRIVE ROTATION WHILE CIRC DUE TO ELEC PROBLEM. | RR | TDS |  | 05/23/2022 | NBR-263S | 5.5 | QTIF-736
1981 | FOT | RIG | 1 | 23 May 0230 - 0330 | 157 | 896942 | DELAY IN DISCONNECTION FROM TDS. | DSF | DP |  | 05/23/2022 | NBR-263S | 1 | QTIF-736
1982 | FOT | RIG | 2 | 23 May 1900 - 2100 | 129 | 896943 | WHILE CONNECTION. OBSERVED B/O OF CONNECTION BETWEEN MANUAL & HYD IBOP OF TDS. | DSF | DP |  | 05/23/2022 | NBR-263S | 2 | QTIF-736
1983 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | NBR-987S | Hrs | UMKR-1
1984 | FOT | SDM | 23 | 22 May 0330 - 0430 | 12754 | 896854 | TOOL UNABLE TO BUILD INCLINATION AS PER PROGRAM | BHA | RSS |  | 05/23/2022 | NBR-987S | 21.5 | UMKR-1
1985 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | PA-861S | Hrs | HRDH-1060
1986 | FOT | RIG | 6.5 | 23 May 2230 - 0500 | 10660 | 896979 | RIG REPAIR . HPU TOP DRIVE SYSTEM DOWN | RR | TDS |  | 05/23/2022 | PA-861S | 6.5 | HRDH-1060
1987 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SINO-19L | Hrs | UTMN-1587
1988 | FOT | SPS | 20.5 | 22 May 1930 - 1600 | 10500 | 896715 | FAILURE ON PULSER TOOL (NO RESPONSE, DIED). TROUBLESHOTTING SEVERAL TIMES, NO PROGRESS. | BHA | LWD |  | 05/23/2022 | SINO-19L | 11 | UTMN-1587
1989 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SINO-27N | Hrs | HWYH-466
1990 | STBH | ARM | 60.5 | 21 May 1630 - 0500 | 7515 | 896822 | STRING GOT STUCK. | STUK | RBHA |  | 05/23/2022 | SINO-27N | 24 | HWYH-466
1991 | 6717 | 6528 | LOG | E | 2824 | WLT | CONT. BHI LOGGING TOOLS RUN # 4 (RCX ON GR) & COLLECT 1ST SAMPLE AT 6,528' (1 OF 14 FM SAMPLES) .2 CYCLES.> SAMPLE #1 @ 6,528, TOTAL DUMPING IN ANN. =334 LITERS / WATER COLLECT ONE BOTTLE OF WATER SAMPLE > MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> NO O/PULL OBBSERVED WHILE MOVE & SCAN UP & DOWN.> MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 6717 | 6528 | BAW | 05/23/2022 | SINO-43L | LOG | HWYH-2528
1992 | 6717 | 6487 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED XL PKR & COLLECT SAMPLE # 2 @ 6,487' (2 OF 14 FM SAMPLES) ONE CYCLES.> ATTEMPTED TO PUMP OUT WITH STRADDLE PKR, ABORTED DUE TO HIGH MOBILITY> SAMPLE #2 @ 6,487(3B21 FM): TOTAL DUMPING IN ANN. = 235 LITERS / WATER - TOTAL 569 LITERS.> COLLECTED ONE BOTTLE OF WATER SAMPLE WITH XL PKR.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6487 | BAW | 05/23/2022 | SINO-43L | LOG | HWYH-2528
1993 | 6717 | 6452 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED XL PKR & COLLECT SAMPLE # 3 @ 6,452' (3 OF 14 FM SAMPLES) ONE CYCLES.- SAMPLE #3 @ 6,452' (3A17 FM): TOTAL DUMPING IN ANN. = 237 LITERS / WATER - TOTAL 806 LITERS- NO SAMPLE COLLECTED - MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.- MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6452 | BAW | 05/23/2022 | SINO-43L | LOG | HWYH-2528
1994 | 6717 | 6402 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED STANDARD PROBE & COLLECTED SAMPLE # 4 @ 6,402' (4 OF 14 FM SAMPLES) TWO CYCLES.> SAMPLE #4 @ 6,402' (ARBD): TOTAL DUMPING IN ANN. = 327 LITERS / WATER - TOTAL 1,133 LITERS> COLLECTED ONE BOTTLE OF WATER SAMPLE WITH STANDARD PROBE.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6402 | BAW | 05/23/2022 | SINO-43L | LOG | HWYH-2528
1995 | 6717 | 6397 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED XL PKR & COLLECTING SAMPLE # 5 @ 6,397' (5 OF 14 FM SAMPLES) ONE CYCLE. ONGOING...> SAMPLE #5 @ 6,937' (ARBD): NO SAMPLE COLLECT TILL THE MOMENT.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MONITORED WELL THRU TRIP TANK, STATIC - OK.> TOTAL HRS SINCE LAST CIRCULATION : 34 HRS. | 6717 | 6397 | BAW | 05/23/2022 | SINO-43L | LOG | HWYH-2528
1996 | 91.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2"VERTICAL EVALUATION HOLE LOGGING. | 24 | 2824 | 20 May 0030 | 05/23/2022 | SINO-43L | Type | HWYH-2528
1997
1998
1999 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SND-2002 | Hrs | WAQR-23
2000 | UVLC | ARM | 312 | 11 May 0500 - 0500 | 10207 | 896698 | ENCOUNTERED COMPLETE LOSS OF CIRCULATION @ 10207' WHILE DRILLING. | LCIR | NA |  | 05/23/2022 | SND-2002 | 24 | WAQR-23
2001 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SND-2005 | Hrs | MHKK-2
2002 | FOT | SDM | 17.5 | 23 May 1130 - 0500 | 11387 | 896916 | LOST SIGNAL TO SLB MWD/LWD TOOLS WHILE DRILLING AT 11,387'. TROUBLESHOOT W/ NO SUCCESS. | BHA | LWD |  | 05/23/2022 | SND-2005 | 17.5 | MHKK-2
2003 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SP-124 | Hrs | FDHL-141
2004 | FOT | WWB | 3 | 23 May 2300 - 0200 | 9532 | 896941 | AT 9532 FT WFD ENGINEER DROP THE FIRST BALL TO ACTIVATE THE PBL SUB BUT NO SUCCESS,BECOUSE THE BALL NOT SEATED ON THE BPL SUB. | BHA | WBCL |  | 05/23/2022 | SP-124 | 3 | FDHL-141
2005 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SP-257 | Hrs | HZEM-141014
2006 | FOT | BHI | 10.75 | 23 May 1815 - 0500 | 10205 | 896939 | PER BAKER DD COMMUNICATION FAILURE TO BAKER TOOLS. | BHA | MWD |  | 05/23/2022 | SP-257 | 10.75 | HZEM-141014
2007 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SSA-303 | Hrs | HRDH-2306
2008 | FOT | BHI | 2 | 23 May 1415 - 1615 | 10990 | 896938 | LOST SIGNAL WITH BAKER MWD TOOL @ 10,990' | BHA | MWD |  | 05/23/2022 | SSA-303 | 2 | HRDH-2306
2009 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SSA-46 | Hrs | JAHM-7
2010 | FOT | SWL | 73.75 | 19 May 2015 - 0745 | 3615 | 896757 | WHILE TESTING SLB MDT/GR TOOL IN 9-5/8" CSG TO 6000 PSI. FOUND LOST COMMUNICATION FROM TOOL. POOH WL. FOUND TOOL BROKEN/SHEARED FROM BETWEEN THE PKR. | TF | WLT |  | 05/23/2022 | SSA-46 | 2.75 | JAHM-7
2011 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SSA-5914 | Hrs | WDYH-80
2012 | FOT | RIG | 3.5 | 23 May 2345 - 0500 | 9400 | 896959 | INADEQUATE TDS LINK CLAMPS FIXATION. | RR | TDS |  | 05/23/2022 | SSA-5914 | 3.5 | WDYH-80
2013 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | SSA-5974 | Hrs | HRDH-1970
2014 | CWEL | ARM | 675.25 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/23/2022 | SSA-5974 | 24 | HRDH-1970
2015 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | STY-038 | Hrs | ZULF-2085
2016 | DSFT | BLH | 3 | 23 May 0815 - 1115 | 16323 | 896976 | UNSUCCESSFUL ATTEMPT TO RELEASE RUNNING TOOL. | JF | HGRL |  | 05/23/2022 | STY-038 | 3 | ZULF-2085
2017 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/23/2022 | T907 | Hrs | RGHB-703
2018 | ACDI | SPS | 61.75 | 21 May 1515 - 0500 | 7350 | 896803 | DEVIATE FROM ORIGINAL DIRECTION PLAN BY AROUND 180 DEGREE AZIMUTH | DD | BHA |  | 05/23/2022 | T907 | 24 | RGHB-703
2019 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADC-31 | Hrs | SDGM-1181
2020 | FOT | WCM | 4.5 | 23 May 0100 - 0530 | 9902 | 896940 | TRY TO CLOSE WFD DV TOOL WITHOUT SUCCESS. | TF | ACCSS |  | 05/24/2022 | ADC-31 | .5 | SDGM-1181
2021 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADC-35 | Hrs | MAQL-5
2022 | WTHR | ARM | 5 | 24 May 1630 - 2130 | 11403 | 896950 | SUSPEND OPERATION DUE TO HIGH WIND SPEED ( 61 KM/HR ) & LOW VISIBILITY . | WON | NA |  | 05/24/2022 | ADC-35 | 5 | MAQL-5
2023 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADC-43L | Hrs | UTMN-3118
2024 | FRFM | TK3 | 23.75 | 24 May 0515 - 0500 | 6420 | 896951 | WHILE DRILLING LOST COMPLETE RETURNS IN POST ARAB-D STRINGERS. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES | LCIR | NA |  | 05/24/2022 | ADC-43L | 23.75 | UTMN-3118
2025 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADC-48 | Hrs | HWYH-1256
2026 | FOT | BHI | 45.5 | 22 May 1430 - 1900 | 17098 | 896879 | DEEP RESISTIVITY TOOL NOT WORKING | BHA | LWD |  | 05/24/2022 | ADC-48 | 11 | HWYH-1256
2027 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADC-50 | Hrs | SFNY-1177
2028 | MRWL | RIG | 194.75 | 14 May 1800 - 1345 | 0 | 896533 | WHILE LIFTING 13-5/8" BOP AFTER N/D, BOP STACK MOVED AND BENT ESP CABLE. PERFORMED VARIOUS TESTS ON ESP CABLE: PHASE-TO-PHASE, PHASE-TO-GROUND, AND 5 KV VOLTAGE TEST - ALL OKAY. DISCUSSION WITH TOWN DETERMINED THAT DAMAGE TO CABLE COULD RESULT IN REDUCED LIFESPAN OF THE ESP. DECISION MADE TO RECOMPLETE. | BOP | BOP |  | 05/24/2022 | ADC-50 | 8.75 | SFNY-1177
2029 | 16463 |  | CIRC | N |  | MPMP | CONTINUE SWEEP HOLE W/ 1 X TANDEM PILL (15 BBL LO-VIS + 15 BBL HI-WT), CHC W/ 1 CYCLE. - MW IN/OUT = 68 PCF, DYNAMIC LOSSES 18 BPH. | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2030 | 16463 |  | CIRC | N |  | MPMP | DISPLACE 1500 FT OF 6-1/8" OH TO VISCOUS BRINE. | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2031 | 16463 |  | CIRC | N |  | MPMP | FLOW CHECK, LOSSES 2 BPH | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2032 | 16463 | 12815 | ST | N |  | STDP | POOH 6 1/8" CO BHA FROM 16463 FT TO 12815 FT W/ PUMP OUT WITH VISCOUS BRINE 70 PCF ALL STANDS- AFTER REACHING 15300 FT OBSERVED BRINE AT THE SURFACE | 16463 | 16463 | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2033 | 16463 | 12675 | TO | N |  | STDP | POOH W/6 1/8" CO BHA FROM 12815 FT TO 12675 FT ON ELEVATOR | 16463 | 12815 | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2034 | 16463 |  | CIRC | N |  | MPMP | CIRCULATE WITH BRINE ABOVE THE WHIPSTOCK | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2035 | 16463 |  | CIRC | N |  | MPMP | EXTENDED FLOW CHECK - STATIC LOSSES 5 BPH | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2036 | 16463 | 11002 | TO | N |  | STDP | POOH W/6 1/8" CO BHA FROM 12675 FT TO 11002 FT ON ELEVATOR | 16463 | 12675 | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2037 | 16463 |  | HT | N |  | PEL | CHANGED HANDLING EQUIPMENT TO 4" DP HANDLING EQUIPMENT.- R/U 4" MUD BUCKET. | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2038 | 16463 | 1127 | TO | N |  | STDP | POOH W/6 1/8" CO BHA FROM 11002 FT TO 1127 FT. | 16463 | 11002 | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2039 | 16463 |  | CIRC | N |  | MPMP | FLOW CHECK - STATIC LOSSES AT 4 BBL/HR. | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2040 | 16463 | 654 | TO | N |  | STDP | POOH W/6 1/8" CO BHA FROM 1127 FT TO 654 FT. | 16463 | 1127 | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2041 | 16463 |  | CIRC | N |  | MPMP | FLOW CHECK - STATIC LOSSES AT 4 BBL/HR. | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2042 | 16463 |  | HT | N |  | BHA | POOH & L/D 6-1/8" CO BHA TO SURFACE. | 16463 |  | RIG | 05/24/2022 | ADC-57L | CT | FDHL-158
2043 | 16463 |  | HT | N | 2864 | STRG | RETRIEVE WEAR BUSHING. | 16463 |  | RIG | 05/24/2022 | ADC-57L | SIMOPS | FDHL-158
2044 | 16463 |  | HT | N | 2864 | BHA | RIG DOWN BELL NIPPLE. | 16463 |  | RIG | 05/24/2022 | ADC-57L | SIMOPS | FDHL-158
2045 | 16463 |  | PJSM | N | 2864 | STRG | HPJSM PRIOR TO RIG UP SLB COIL TUBING. DISCUSS THE RISK AND HAZARD. REVIEW THE JSA. | 16463 |  | RIG | 05/24/2022 | ADC-57L | SIMOPS | FDHL-158
2046 | 16463 |  | HT | N | 2864 | BHA | R/U ADAPTOR FLANGE & RISER PIPE ABOVE RIG BOP TO INSTALL PRESSURE CONTROL EQUIPMENT & INJECTOR HEAD. ON GOING AT RT. - MONITOR WELL ON TRIP TANK VIA CHOKE. | 16463 |  | RIG | 05/24/2022 | ADC-57L | SIMOPS | FDHL-158
2047 | 2.5 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | STIMULATION JON FOR L-2, L-1. | 2.5 | 2864 | 24 May 0230 | 05/24/2022 | ADC-57L | Type | FDHL-158
2048
2049
2050 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADC-65L | Hrs | HWYH-1280
2051 | FWTS | SDM | 186.5 | 12 May 1600 - 0500 | 4900 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/24/2022 | ADC-65L | 23.5 | HWYH-1280
2052 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADES-173 | Hrs | HRDH-1277
2053 | FOT | HCB | 6.25 | 24 May 2245 - 0500 | 10500 | 896953 | RTTS PACKER LEAK DURING POSITIVE TEST. | TF | BP |  | 05/24/2022 | ADES-173 | 6.25 | HRDH-1277
2054 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADM-262 | Hrs | MRJN-123
2055 | WOPF | AP2 | 17.25 | 24 May 0745 - 0500 | 0 | 897000 | GOSP LINE PRESSURE STARTED TO INCREASE. SHUT WELL IN AND WAIT ON MRJN FIELD SERVICES TO RESOLVE THE ISSUE. | WO | NA |  | 05/24/2022 | ADM-262 | 17.25 | MRJN-123
2056 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADM-337 | Hrs | MRJN-900
2057 | FOHL | ARM | 20.75 | 24 May 0815 - 0500 | 12935 | 897001 | UNABLE TO PASS SCRAPER DEPTH @ 11555 FT BIT DEPTH, 12935 FT. | BHS | NA |  | 05/24/2022 | ADM-337 | 20.75 | MRJN-900
2058 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ADM-655 | Hrs | SFNY-144
2059 | WPDH | AP3 | 38 | 23 May 1500 - 0500 | 0 | 896896 | WAIT ON SFNY FIELD SERVICE TO DE-PRESSURIZE SFNY-143/146 PLATFORM FOR SAFE RIG APPROACH. | WO | NA |  | 05/24/2022 | ADM-655 | 24 | SFNY-144
2060 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ARO-4001 | Hrs | MRJN-538
2061 | GRF | RIG | 12 | 24 May 1400 - 0500 | 10842 | 896919 | OBSERVED TDS OVERHEATING AND ROTATION DISABLED, POOH INSIDE SHOE & TROUBLESHOOTNG TDS. | UPRA | TDS |  | 05/24/2022 | ARO-4001 | 12 | MRJN-538
2062 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | DPS-74 | Hrs | NJYN-54
2063 | FOT | BLH | 957.25 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/24/2022 | DPS-74 | 24 | NJYN-54
2064 | 7153 | 6500 | LOG | E | 2844 | WLT | CONT' RIH WITH BHI RUN # 3 SLIM FORMATION TESTER (GR-FTEX) ON W/L .- RECORD 3/20 PRESSURE POINT.- POINT #2(ABD1) @ 6,722 FT, FM PRESS = 3,249 PSI, CURRENT OVERBALANCE= 562 PSI, NO OVERPULL.- POINT #3(AD2A) @ 6,738 FT, FM PRESS = 2,957 PSI, CURRENT OVERBALANCE= 863 PSI, HAD 1,900 LB OVERPULL.- PERFORM 15 MINS STICKY TEST AT POINT#4, HAD 1,400 LB OVERPULL.- DECIDED TO POOH & RUN CONDITION TRIP TO ADJUST MUD WT BASED ON NEW FORMATION PRESSURE. | 7153 | 6900 | BAW | 05/24/2022 | DQ-50L | LOG | HRDH-582
2065 | 7153 |  | HT | E | 2844 | BHA | HPJSM, P/U, M/U & RIH 8 1/2" CONDITION TRIP REAMING ASSY TO 370 FT.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7153 |  | RIG | 05/24/2022 | DQ-50L | CT | HRDH-582
2066 | 7153 | 3845 | TI | E | 2844 | STDP | RIH 8 1/2" CONDITION TRIP REAMING ASSY TILL 9-5/8" CSG SHOE @ 3,845 FT.- MONITOR HOLE ON TRIP TANK, HOLE STATIC | 7153 | 620 | RIG | 05/24/2022 | DQ-50L | CT | HRDH-582
2067 | 7153 |  | CIRC | E | 2844 | MPMP | CUMULATIVE TIME TO FILL THE STRING. | 7153 |  | RIG | 05/24/2022 | DQ-50L | LOG | HRDH-582
2068 | 7153 | 7153 | ST | E | 2844 | STDP | RIH 8 1/2" CONDITION TRIP REAMING ASSY TO BTM @ 7,153'.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7153 | 3845 | RIG | 05/24/2022 | DQ-50L | CT | HRDH-582
2069 | 7153 |  | CIRC | E | 2844 | MPMP | CUMULATIVE TIME TO FILL THE STRING & BREAK CIRC. | 7153 |  | RIG | 05/24/2022 | DQ-50L | LOG | HRDH-582
2070 | 7153 |  | CIRC | E | 2844 | MPMP | SWEEP & CHC, MEANWHILE CUT MUT WT F/81 PCF T/79 PCF.- NO GASES WITH BTM UP. | 7153 |  | RIG | 05/24/2022 | DQ-50L | CT | HRDH-582
2071 | 7153 |  | CIRC | E | 2844 | MPMP | FLOW CHECK, WELL STATIC.RPM=10, TRQ=1500 | 7153 |  | RIG | 05/24/2022 | DQ-50L | CT | HRDH-582
2072 | 7153 |  | CIRC | E | 2844 | MPMP | CONT' CIRC & CUT MUD WT F/ 79 PCF T/ 77 PCF.- NO GASES WITH BTM UP. | 7153 |  | RIG | 05/24/2022 | DQ-50L | CT | HRDH-582
2073 | 7153 |  | OTH | E | 2844 | NA | FLOW CHECK, WELL STATIC.RPM=10, TRQ=1500 | 7153 |  | RIG | 05/24/2022 | DQ-50L | LOG | HRDH-582
2074 | 7153 |  | CIRC | E | 2844 | MPMP | CONT' CIRC & CUT MUD WT F/ 77 PCF T/ 75 PCF.- CONFIRMED MWT IN = M WT OUT=75 PCF. | 7153 |  | RIG | 05/24/2022 | DQ-50L | CT | HRDH-582
2075 | 7153 |  | WCNT | E | 2844 | MPMP | FLOW CHECK, WELL IS TRICKLING 1.2 BBL/HR.SHUT IN THE WELL, SIDPP=0 PSI, SICP=30 PSI.PREPARE AND MIX 81 PCF KILL MUD. | 7153 |  | RIG | 05/24/2022 | DQ-50L | LOG | HRDH-582
2076 | 7153 |  | WCNT | E | 2844 | MPMP | HPJSM, KILL WELL WITH W&W METHOD BY 81 PCF KMWT, MWT IN = OUT = 81 PCF & NO GASES. -NO CUT IN MUD WT WITH BTM UP | 7153 |  | RIG | 05/24/2022 | DQ-50L | LOG | HRDH-582
2077 | 7153 |  | WCNT | E | 2844 | MPMP | SHUT DOWN PUMP & SHUT-IN WELL, SICP = SIDPP = ZERO. | 7153 |  | RIG | 05/24/2022 | DQ-50L | LOG | HRDH-582
2078 | 7153 |  | CIRC | E | 2844 | MPMP | ROTATE STRING & MOVE DOWN, STRING IS FREE, CIRCULATE & CONDITIONING MUD...ONGOING. | 7153 |  | RIG | 05/24/2022 | DQ-50L | LOG | HRDH-582
2079 | 68 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2844 | 22 May 0900 | 05/24/2022 | DQ-50L | Type | HRDH-582
2080
2081
2082 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ED-85A | Hrs | ZULF-2062
2083 | CEDE | BCM | 5.25 | 24 May 2345 - 0500 | 0 | 896961 | CAN NOT MIX CEMENT DUE TO MIX FLUID PROBLEM, TO MATCH FOAM AND MIXING PUMP LOST SUCTION MANY TIMES DUE TO FOAM. | JF | NA |  | 05/24/2022 | ED-85A | 5.25 | ZULF-2062
2084 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | ENSCO-54 | Hrs | ABSF-28
2085 | WOPF | AP2 | 4 | 24 May 0900 - 1300 | 0 | 897002 | WAIT ON FIELD SERVICES TO DEPRESSURIZE PLATFORM. | WO | NA |  | 05/24/2022 | ENSCO-54 | 4 | ABSF-28
2086 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | HI-4 | Hrs | SFNY-918
2087 | ULCM | ARM | 4.75 | 24 May 0600 - 1045 | 6825 | 896923 | WHILE BACKREAMING AT 6886' STRING GOT STALLED AND PACKED-OFF AND LOST COMPLETE CIRCULATION. | LCIR | LCM |  | 05/24/2022 | HI-4 | 4.75 | SFNY-918
2088 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | NA-18S | Hrs | UTMN-2334
2089 | STBH | ARM | 263 | 12 May 1300 - 0500 | 13129 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/24/2022 | NA-18S | 24 | UTMN-2334
2090 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | NBR-20S | Hrs | HMYM-433504
2091 | HERR | RIG | 3 | 24 May 0200 - 0500 | 4832 | 897003 | TEST PLUG SEALS LEAKING DUE TO IMPROPER RUNNING. BOP FLANGES LEAKING. | BOP | BOP |  | 05/24/2022 | NBR-20S | 3 | HMYM-433504
2092 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | NBR-263S | Hrs | QTIF-736
2093 | FOT | RIG | 3.5 | 24 May 1730 - 2100 | 283 | 896920 | HAD TO REPLACE TDS BACK UP TONG DIES ELEMENT. | RR | TDS |  | 05/24/2022 | NBR-263S | 3.5 | QTIF-736
2094 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | NBR-987S | Hrs | UMKR-1
2095 | FOT | SDM | 26 | 22 May 0330 - 0900 | 12754 | 896854 | TOOL UNABLE TO BUILD INCLINATION AS PER PROGRAM | BHA | RSS |  | 05/24/2022 | NBR-987S | 3 | UMKR-1
2096 | FOT | RIG | 7 | 23 May 2230 - 0530 | 10660 | 896979 | RIG REPAIR . HPU TOP DRIVE SYSTEM DOWN | RR | TDS |  | 05/24/2022 | PA-861S | .5 | HRDH-1060
2097 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | PA-861S | Hrs | HRDH-1060
2098 | FOT | HCM | 2.25 | 24 May 1645 - 1900 | 14590 | 896954 | HALLIBURTON CEMENT PUMP UNIT FAILED PRESSURE TEST | TF | PUMP |  | 05/24/2022 | PA-861S | 2.25 | HRDH-1060
2099 | FOT | RIG | 7 | 23 May 2230 - 0530 | 10660 | 896979 | RIG REPAIR . HPU TOP DRIVE SYSTEM DOWN | RR | TDS |  | 05/24/2022 | PA-861S | .5 | HRDH-1060
2100 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SA5898 | Hrs | MDRK-57
2101 | PCPF | ARM | 2 | 24 May 1745 - 1945 | 2710 | 896921 | UNABLE TO RUN 18-5/8" CSG DUE TO TIGHT HOLE. | TH | NA |  | 05/24/2022 | SA5898 | 2 | MDRK-57
2102 | FOT | BAW | 4 | 24 May 1630 - 2030 | 7444 | 896999 | HAD WL MISS-COMMUNICATION WITH MPC CUTTER. | TF | WLT |  | 05/24/2022 | SINO-27N | 4 | HWYH-466
2103 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SINO-27N | Hrs | HWYH-466
2104 | STBH | ARM | 80.5 | 21 May 1630 - 0500 | 7515 | 896822 | STRING GOT STUCK. | STUK | RBHA |  | 05/24/2022 | SINO-27N | 20 | HWYH-466
2105 | FOT | BAW | 4 | 24 May 1630 - 2030 | 7444 | 896999 | HAD WL MISS-COMMUNICATION WITH MPC CUTTER. | TF | WLT |  | 05/24/2022 | SINO-27N | 4 | HWYH-466
2106 | 6717 | 6397 | LOG | E | 2824 | WLT | CONT. COLLECTING SAMPLE # 5 @ 6,397' (5 OF 13 FM SAMPLES) ONE CYCLE. ............(OOS).> SAMPLE #5 @ 6,937' (AD2B): DUMPING IN ANN. = 227 LITERS / WATER - TOTAL 1,360 LITERS NO SAMPLE COLLECTED .> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MONITORED WELL THRU TRIP TANK, STATIC - OK.> TOTAL HRS SINCE LAST CIRCULATION : 34 HRS. | 6717 | 6397 | BAW | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2107 | 6717 | 6376 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED STD-PKR & COLLECTED SAMPLE # 6 @ 6,376' (6 OF 13 FM SAMPLES) ONE CYCLES. ............(OOS).> SAMPLE #6 @ 6,376' (AD2B): TOTAL DUMPING IN ANN. = 225 LITERS / WATER - TOTAL 1,585 LITERS> COLLECTED ONE BOTTLE OF WATER SAMPLE WITH STANDARD PROBE.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6376 | BAW | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2108 | 6717 | 6351 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED XL-PKR & COLLECTED SAMPLE # 7 @ 6,351.5' (7 OF 13 FM SAMPLES) ONE CYCLES. ............(OOS).> SAMPLE #7 @ 6,351.5' (AD2B): TOTAL DUMPING IN ANN. = 200 LITERS / WATER - TOTAL 1,785 LITERS> COLLECTED ONE BOTTLE OF WATER SAMPLE WITH STANDARD PROBE.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MOVED & CONFIRMED STRG FREE EVERY 4 HRS WHILE SAMPLING.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6351 | BAW | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2109 | 6717 | 6717 | ST | E | 2824 | STDP | RIH BACK W/MDT TOOLS ON D/P W/CONTROLLED SPEED F/6,351 FT TO BTM @ 6,717 FT ............(OOS). | 6717 | 6351 | RIG | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2110 | 6717 |  | CIRC | E | 2824 | MPMP | CIRC TWO BOTTOM UP & CONDITIONMUD WT IN & OUT = 72 PCF [ 200 GPM & 350 PSI ]. ............(OOS).> PRECAUTIONARY CIRCULATE THROUGH FULL OPEN CHOKE TO MGS W/ ANNULAR PREVENTER CLOSED. | 6717 |  | RIG | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2111 | 6717 |  | WCNT | E | 2824 | NA | FLOW CHECK, HOLE STATIC ............(OOS). | 6717 |  | RIG | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2112 | 6717 | 6336 | ST | E | 2824 | STDP | POOH BHI LOGGING RUN # 5 [ RCX ON GR ] TO NEXT SAMPLE POINT# 8 WITH CONTROL SPEED @ 6336'. ............(OOS). | 6717 | 6717 | RIG | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2113 | 6717 | 6336 | LOG | E | 2824 | WLT | PERFORMED STICK TENDENCY TESTS @ 6336' [ SAMPLE POINT DEPTH ] FOR 30 MIN, NO STICKING TENDENCY. ............(OOS). | 6717 | 6336 | BAW | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2114 | 6717 | 6336 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED XL-PKR & COLLECTED SAMPLE # 8 @ 6,336' (8 OF 13 FM SAMPLES) ONE CYCLES. ............(OOS).> SAMPLE #8 @ 6,336' (AD2A): TOTAL DUMPING IN ANN. = 82 LITERS / WATER - TOTAL 82 LITERS> NO SAMPLE COLLECTED.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6336 | BAW | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2115 | 6717 | 6336 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED STD-PKR & COLLECTED SAMPLE # 9 @ 6,320' (9 OF 13 FM SAMPLES) ONE CYCLE. ...ONGOING ............(OOS).> SAMPLE #9 @ 6,320' (AD2A): IN PROGRESS.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6336 | BAW | 05/24/2022 | SINO-43L | LOG | HWYH-2528
2116 | 115.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2"VERTICAL EVALUATION HOLE LOGGING. | 24 | 2824 | 20 May 0030 | 05/24/2022 | SINO-43L | Type | HWYH-2528
2117
2118
2119 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SND-2003 | Hrs | RMTN-17
2120 | FOT | HWP | 22 | 24 May 0700 - 0500 | 12534 | 896997 | WHILE ATTEMPTING TO INCREASE WIRELINE TENSION TO 19.5 KLBS, THE WIRELINE TRUCKS AIR BRAKES FAILED. | TF | WLU |  | 05/24/2022 | SND-2003 | 22 | RMTN-17
2121 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SND-2005 | Hrs | MHKK-2
2122 | FOT | SDM | 32 | 23 May 1130 - 1930 | 11387 | 896916 | LOST SIGNAL TO SLB MWD/LWD TOOLS WHILE DRILLING AT 11,387'. TROUBLESHOOT W/ NO SUCCESS. | BHA | LWD |  | 05/24/2022 | SND-2005 | 14.5 | MHKK-2
2123 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SND-2008 | Hrs | HRDH-1052
2124 | FOT | GEP | 2.5 | 24 May 0230 - 0500 | 0 | 896998 | WOOD GROUP EBS SECONDARY SEAL FAILED, REPLACE W/NEW ONE. | WH | WH |  | 05/24/2022 | SND-2008 | 2.5 | HRDH-1052
2125 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SP-257 | Hrs | HZEM-141014
2126 | FOT | BHI | 11.25 | 23 May 1815 - 0530 | 10205 | 896939 | PER BAKER DD COMMUNICATION FAILURE TO BAKER TOOLS. | BHA | MWD |  | 05/24/2022 | SP-257 | .5 | HZEM-141014
2127 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SSA-102 | Hrs | QTIF-696
2128 | FOT | SPS | 2 | 24 May 0800 - 1000 | 50 | 896948 | HAD BAD SIGNAL ON MWD TOOL, | BHA | MWD |  | 05/24/2022 | SSA-102 | 2 | QTIF-696
2129 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SSA-303 | Hrs | HRDH-2306
2130 | FOT | BHI | 9 | 23 May 1415 - 0500 | 10990 | 896938 | LOST SIGNAL WITH BAKER MWD TOOL @ 10,990' | BHA | MWD |  | 05/24/2022 | SSA-303 | 7 | HRDH-2306
2131 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SSA-5859 | Hrs | HWYH-1222
2132 | XTRI | RIG | 2 | 24 May 1200 - 1400 | 3153 | 896952 | LOST TIME WHILE N/U 26"3/4 3M BOP STACK | JF | BOP |  | 05/24/2022 | SSA-5859 | 2 | HWYH-1222
2133 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SSA-5914 | Hrs | WDYH-80
2134 | FOT | RIG | 4.25 | 23 May 2345 - 0545 | 9400 | 896959 | INADEQUATE TDS LINK CLAMPS FIXATION. | RR | TDS |  | 05/24/2022 | SSA-5914 | .75 | WDYH-80
2135 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | SSA-5974 | Hrs | HRDH-1970
2136 | CWEL | ARM | 698.75 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/24/2022 | SSA-5974 | 23.5 | HRDH-1970
2137 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | T907 | Hrs | RGHB-703
2138 | ACDI | SPS | 85.25 | 21 May 1515 - 0500 | 7060 | 896803 | DEVIATE FROM ORIGINAL DIRECTION PLAN BY AROUND 180 DEGREE AZIMUTH | DD | BHA |  | 05/24/2022 | T907 | 23.5 | RGHB-703
2139 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/24/2022 | WCL-83 | Hrs | MRJN-837
2140 | STCT | ARM | 10.5 | 24 May 0730 - 1800 | 5064 | 896949 | UNABLE TO PULL THE HALLIBURTON RBP PLUG DUE TO SAND, SCALE AND FINE DEBRIS ABOVE PLUG. | STUK | PLUGT |  | 05/24/2022 | WCL-83 | 10.5 | MRJN-837
2141 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | 095TE | Hrs | MNIF-220
2142 | FOP | SCB | 2.5 | 25 May 1545 - 0330 | 19101 | 896926 | REPAIR BOP WINCH SYSTEM. | JF | RBP |  | 05/25/2022 | 095TE | 2.5 | MNIF-220
2143 | WTHR | ARM | 1.75 | 25 May 1015 - 1200 | 6420 | 896964 | SUSPEND ALL CRANE AND WORKING AT HIGHT OPERATIONS DUE TO HIGH WIND SPEED (ABOVE 40 KM/HOUR) AND LOW VISIBILITY. | WON | NA |  | 05/25/2022 | ADC-43L | 1.75 | UTMN-3118
2144 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | ADC-43L | Hrs | UTMN-3118
2145 | FRFM | TK3 | 40.5 | 24 May 0715 - 0500 | 6420 | 896955 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 05/25/2022 | ADC-43L | 21.75 | UTMN-3118
2146 | WTHR | ARM | 1.75 | 25 May 1015 - 1200 | 6420 | 896964 | SUSPEND ALL CRANE AND WORKING AT HIGHT OPERATIONS DUE TO HIGH WIND SPEED (ABOVE 40 KM/HOUR) AND LOW VISIBILITY. | WON | NA |  | 05/25/2022 | ADC-43L | 1.75 | UTMN-3118
2147 | 16463 |  | STIM | E | 2864 | CTU | CONTINUE R/U ADAPTOR FLANGE, GATE VALVE & RISER PIPE ABOVE RIG BOP TO INSTALL PRESSURE CONTROL EQUIPMENT & INJECTOR HEAD. R/U CT BOP & FUNCTION TEST BOP.- MONITOR WELL ON TRIP TANK VIA CHOKE.- STATIC LOSSES 3 BPH | 16463 |  | SCT | 05/25/2022 | ADC-57L | STIM | FDHL-158
2148 | 16463 |  | STIM | E | 2864 | CTU | PT THE TREATING LINE AGAINST REEL AND LT VALVE ON THE RIG FLOOR TO 300/7500 PSI - 15 MIN; PT BLIND RAMS AGAINST MASTER VALVE 300/2500 PSI - 15 MIN. | 16463 |  | SCT | 05/25/2022 | ADC-57L | STIM | FDHL-158
2149 | 16463 |  | STIM | E | 2864 | CTU | PREFORMED MINOR GENERAL RIG UP MEANWILE WATTING ON WEATHER DUE TO STRON WIND - WIND SPEED FROM 42 KM/HR TO 55 KM/HR- MONITOR WELL ON THE TRIP TANK THROUGH THE CHOKE MANIFOLD - STATIC LOSSES 3 BPH. | 16463 |  | SCT | 05/25/2022 | ADC-57L | STIM | FDHL-158
2150 | 16463 |  | STIM | E | 2864 | CTU | HPJSM, DISCUSSED RISK ASSESSMENT. LIFT CT INJECTOR & HANG IT WITH TOP DRIVE. | 16463 |  | SCT | 05/25/2022 | ADC-57L | STIM | FDHL-158
2151 | 16463 |  | STIM | E | 2864 | CTU | PERFORMED H2S DRILL. | 16463 |  | SCT | 05/25/2022 | ADC-57L | STIM | FDHL-158
2152 | 16463 |  | STIM | E | 2864 | CTU | FILL UP COIL TBG REEL WITH WATER AND P/T CT REEL TO 7500 PSI FOR 15 MINS - OK. | 16463 |  | SCT | 05/25/2022 | ADC-57L | STIM | FDHL-158
2153 | 16463 |  | STIM | E | 2864 | CTU | RIG UP RISER PIPE BELOW COIL TBG INJECTOR & STAB CT INJECTOR ON HYDRA CONN. | 16463 |  | SCT | 05/25/2022 | ADC-57L | STIM | FDHL-158
2154 | 16463 |  | STIM | E | 2864 | CTU | PT BOP PIPE RAM TO 300/2500 PSI. | 16463 |  | SCT | 05/25/2022 | ADC-57L | STIM | FDHL-158
2155 | 26.5 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | STIMULATION JON FOR L-2, L-1. | 24 | 2864 | 24 May 0230 | 05/25/2022 | ADC-57L | Type | FDHL-158
2156
2157
2158 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | ADC-65L | Hrs | HWYH-1280
2159 | FWTS | SDM | 188 | 12 May 1600 - 0630 | 4900 | 896539 | WHILE L/D BHA OBSERVED MOTOR HOUSING SHEARED OF AT 24.5 FT FROM TOP. | FISH | BHA |  | 05/25/2022 | ADC-65L | 1.5 | HWYH-1280
2160 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | ADM-262 | Hrs | MRJN-123
2161 | WOPF | AP2 | 38.25 | 24 May 0745 - 0200 | 0 | 897000 | GOSP LINE PRESSURE STARTED TO INCREASE. SHUT WELL IN AND WAIT ON MRJN FIELD SERVICES TO RESOLVE THE ISSUE. | WO | NA |  | 05/25/2022 | ADM-262 | 21 | MRJN-123
2162 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | ADM-337 | Hrs | MRJN-900
2163 | FOHL | ARM | 24.5 | 24 May 0815 - 0845 | 12935 | 897001 | UNABLE TO PASS SCRAPER DEPTH @ 11555 FT BIT DEPTH, 12935 FT. | BHS | NA |  | 05/25/2022 | ADM-337 | 3.75 | MRJN-900
2164 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | ADM-655 | Hrs | SFNY-144
2165 | WPDH | AP3 | 62 | 23 May 1500 - 0500 | 0 | 896896 | WAIT ON SFNY FIELD SERVICE TO DE-PRESSURIZE SFNY-143/146 PLATFORM FOR SAFE RIG APPROACH. | WO | NA |  | 05/25/2022 | ADM-655 | 24 | SFNY-144
2166 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | ARO-4001 | Hrs | MRJN-538
2167 | GRF | RIG | 13.75 | 24 May 1400 - 0900 | 10842 | 896919 | OBSERVED TDS OVERHEATING AND ROTATION DISABLED, POOH INSIDE SHOE & TROUBLESHOOTNG TDS. | UPRA | TDS |  | 05/25/2022 | ARO-4001 | 2.75 | MRJN-538
2168 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | DPS-4 | Hrs | MDRK-54
2169 | ORDS | ARM | 3.5 | 25 May 0600 - 0930 | 16111 | 896962 | WAIT ON RDD TO PREPARE FORWARD LOGGING PLAN. | WO | NA |  | 05/25/2022 | DPS-4 | 3.5 | MDRK-54
2170 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | DPS-44 | Hrs | UTMN-3174
2171 | FOT | RIG | 6.5 | 25 May 0800 - 1515 | 2310 | 897037 | OBSERVED ABNORMAL HIGH PRESSURE RIGHT AFTER M/U CONNECTION, PRESSURE IS 2000 PSI MORE THAN NORMAL CIRCULATION PRESSURE. TROUBLE SHOOTING ON SURFACE WITHOUT SUCCESS. POH AND CHECK BHA. 4 BIT NOZZLES COMPLETED PLUGGED BY CMT AND FORMATION CUTTINGS, 2 BIT NOZZLES ARE PARTIALLY PLUGGED BY CMT AND FORMATION CUTTINGS. FOUND SLIGHTLY DAMAGE OF FLOAT VALVE SEAL AND WASH MARK ON FLAPPER. | TF | FV |  | 05/25/2022 | DPS-44 | 6.5 | UTMN-3174
2172 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | DPS-5 | Hrs | HRDH-2318
2173 | HERR | FMC | 19 | 25 May 1000 - 0500 | 3415 | 896925 | OBSTRUCTION WHILE PERFORMING SL DRIFT W/ 3.75"OD DUE TO OVER TORQUE ON 4.5" TBG COLLAR BOX THREAD USING FRANKS JAM UNIT. | JF | CTRQ |  | 05/25/2022 | DPS-5 | 19 | HRDH-2318
2174 | 7153 |  | CIRC | E | 2844 | MPMP | CONT, CIRC & CONDITION MUD PARAMETERS. | 7153 |  | RIG | 05/25/2022 | DQ-50L | LOG | HRDH-582
2175 | 7153 |  | OTH | E | 2844 | NA | EXTENDED FLOW CHECK, WELL STATIC.- RPM=10, TRQ = 1800 FT.LB.- RECORD SCR. | 7153 |  | RIG | 05/25/2022 | DQ-50L | LOG | HRDH-582
2176 | 7153 | 3845 | ST | E | 2844 | STDP | POOH 8-1/2" CONDITION TRIP BHA F/ 7,153 FT TO 9-5/8" CSG SHOE @ 3,845 FT.- MONITOR WELL THRU TRIP TANK & TRIP SHEET - WELL STATIC.- FLOW CHECK AFTER 10 STD'S - WELL STATIC. | 7153 | 7153 | RIG | 05/25/2022 | DQ-50L | CT | HRDH-582
2177 | 7153 |  | CIRC | E | 2844 | MPMP | FLOW CHECK - WELL STATIC, PUMP SLUG. | 7153 |  | RIG | 05/25/2022 | DQ-50L | CT | HRDH-582
2178 | 7153 | 620 | TO | E | 2844 | STDP | CONT. POOH W/ 8-1/2" CONDITION TRIP BHA F/ 9-5/8" CSG SHOE @ 3,845 FT TO TOP OF BHA @ 620 FT.- MONITOR WELL THRU TRIP TANK & TRIP SHEET - WELL STATIC.- ARAMCO KPI/ACTUAL: 19/21 STD/HR. | 7153 | 3845 | RIG | 05/25/2022 | DQ-50L | CT | HRDH-582
2179 | 7153 |  | WCNT | E | 2844 | NA | FLOW CHECK-WELL STATIC.- CHANGE ELEVATOR FROM 4" TO 5". | 7153 |  | RIG | 05/25/2022 | DQ-50L | CT | HRDH-582
2180 | 7153 |  | HT | E | 2844 | BHA | CONT. POOH 8-1/2" CONDITION TRIP BHA FROM 620 FT TO SURFACE.- L/D 8-1/2" BIT, RB 8-1/2" NBR & STRRS.- SWAP 10 STD'S X 5" HWDP FROM DS TO ODS.- MONITOR WELL THRU TRIP TANK - WELL STATIC. | 7153 |  | RIG | 05/25/2022 | DQ-50L | CT | HRDH-582
2181 | 7153 | 0 | LOG | E | 2844 | WLT | HPJSM, P/U & M/U BHI W/L LOGGING TOOLS RUN # 4 SLIM FORMATION TESTER & SAMPLING TOOLS (GR-FTEX-RCX).- PERFORM SURFACE CHECKS AND TOOL CALIBRATION ON SURFACE BEFORE RIH.- TOTAL LOGGING TOOL LENGTH: 175', WT: 5400 IB & MAX OD: 7.8".- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7153 | 0 | BAW | 05/25/2022 | DQ-50L | LOG | HRDH-582
2182 | 7153 | 3694 | ST | E | 2844 | STDP | HPJSM, RIH WL RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DRIFTED DP STDS TO 3,694 FT (LATCHING DEPTH) WITH CONTROL SPEED.- FILL STRING EVERY 15 STDS.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7153 | 0 | RIG | 05/25/2022 | DQ-50L | LOG | HRDH-582
2183 | 7153 |  | CIRC | E | 2844 | MPMP | CIRCULATE TWICE STRING CAPACITY 90 BBLS (GPM: 250 & SPP: 320 PSI).- MW IN / OUT 81 PCF | 7153 |  | RIG | 05/25/2022 | DQ-50L | LOG | HRDH-582
2184 | 7153 |  | OTH | E | 2844 | NA | HPJSM. R/U BH W/L SHEAVES AND INSTALL SES.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7153 |  | BAW | 05/25/2022 | DQ-50L | LOG | HRDH-582
2185 | 7153 | 3694 | LOG | E | 2844 | WLT | RIH WITH LATCH HEAD AND LATCH DOWN HOLE TOOL. TEST COMMUNICATION - OK. MAKE PULL TEST ON SES CABLE CLAMP W/ 5000 LB LINE PULL - OK.- PUMP 50 BBL LATCHING PILL PRIOR TO LATCH.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC | 7153 | 3694 | BAW | 05/25/2022 | DQ-50L | LOG | HRDH-582
2186 | 7153 | 3900 | ST | E | 2844 | STDP | CONT. RIH WL RUN#4 LOGGING TOOLS (GR-FTEX-RCX) F/ 3,700 FT TO 3,900'..ONGOING. | 7153 | 3700 | RIG | 05/25/2022 | DQ-50L | LOG | HRDH-582
2187 | 92 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2844 | 22 May 0900 | 05/25/2022 | DQ-50L | Type | HRDH-582
2188
2189
2190 | OTH | RIG | 9.5 | 25 May 1930 - 0500 | 0 | 897038 | (CONTINUATION TO LT ID 894547 ON ZULF-2060 - BONNET PISTON LEAK). REPLACE CAMERON DOUBLE RAM WITH REPAIRED NOV DOUBLE RAM. | UPRA | NA |  | 05/25/2022 | ED-85A | 9.5 | ZULF-2062
2191 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | ED-85A | Hrs | ZULF-2062
2192 | CEDE | BCM | 7.75 | 24 May 2345 - 0730 | 0 | 896961 | CAN NOT MIX CEMENT DUE TO MIX FLUID PROBLEM, TO MATCH FOAM AND MIXING PUMP LOST SUCTION MANY TIMES DUE TO FOAM. | JF | NA |  | 05/25/2022 | ED-85A | 2.5 | ZULF-2062
2193 | OTH | RIG | 9.5 | 25 May 1930 - 0500 | 0 | 897038 | (CONTINUATION TO LT ID 894547 ON ZULF-2060 - BONNET PISTON LEAK). REPLACE CAMERON DOUBLE RAM WITH REPAIRED NOV DOUBLE RAM. | UPRA | NA |  | 05/25/2022 | ED-85A | 9.5 | ZULF-2062
2194 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | NA-18S | Hrs | UTMN-2334
2195 | STBH | ARM | 287 | 12 May 1300 - 0500 | 13129 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/25/2022 | NA-18S | 24 | UTMN-2334
2196 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | NBR-20S | Hrs | HMYM-433504
2197 | HERR | RIG | 7 | 24 May 0200 - 0900 | 4832 | 897003 | TEST PLUG SEALS LEAKING DUE TO IMPROPER RUNNING. BOP FLANGES LEAKING. | BOP | BOP |  | 05/25/2022 | NBR-20S | 4 | HMYM-433504
2198 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | NBR-263S | Hrs | QTIF-736
2199 | HERR | RIG | .5 | 25 May 0430 - 0500 | 412 | 896928 | DRILLER NON-INTENTIONALLY FUNCTIONED THE ESD INSTEAD OF BREAK. MAINTENANCE TEAM REGAIN THE POWER, AND RESTARTED VFD. BACK TO NORMAL. OK | JF | DWKS |  | 05/25/2022 | NBR-263S | .5 | QTIF-736
2200 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | SINO-27N | Hrs | HWYH-466
2201 | STBH | ARM | 104.5 | 21 May 1630 - 0500 | 7515 | 896822 | STRING GOT STUCK. | STUK | RBHA |  | 05/25/2022 | SINO-27N | 24 | HWYH-466
2202 | 6717 | 6320 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED STANDARD PROBE & COLLECTED SAMPLE #9 @ 6,320' (9 OF 13 FM SAMPLES) ONE CYCLE. . ............(OOS).> SAMPLE #9 @ 6,320' (AD2A): TOTAL DUMPING IN ANN. = 234 LITERS / WATER - TOTAL 316 LITERS.> COLLECTED ONE BOTTLE OF WATER SAMPLE WITH STANDARD PROBE.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6320 | BAW | 05/25/2022 | SINO-43L | LOG | HWYH-2528
2203 | 6717 | 6310 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED STANDARD PROBE & COLLECTED SAMPLE #10 @ 6,310' (10 OF 13 FM SAMPLES) ONE CYCLE. ............(OOS).> SAMPLE #10 @ 6,310' (AD2A): TOTAL DUMPING IN ANN.= 243 LITERS / WATER - TOTAL 559 LITERS.> NO SAMPLE COLLECTED.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6310 | BAW | 05/25/2022 | SINO-43L | LOG | HWYH-2528
2204 | 6717 | 6303 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED XL PKR FOR SAMPLE # 11 @ 6,303' (11 OF 13 FM SAMPLES) TWO CYCLES. ............(OOS).MOVED AND REPOSITIONED STRING. INFLATED STRADDLE PACKER. SAMPLING IN PROGRESS.> TOTAL DUMPING IN ANN.= 316 LITERS / WATER & OIL - TOTAL 924 LITERS.> MAX STATIONARY TIME 4 HRS FOR EACH CYCLE, MOVE & CONFIRMED STRG FREE.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6303 | BAW | 05/25/2022 | SINO-43L | LOG | HWYH-2528
2205 | 139.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2"VERTICAL EVALUATION HOLE LOGGING. | 24 | 2824 | 20 May 0030 | 05/25/2022 | SINO-43L | Type | HWYH-2528
2206
2207
2208 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | SND-2002 | Hrs | WAQR-23
2209 | UVLC | ARM | 337 | 11 May 0500 - 0600 | 10207 | 896698 | ENCOUNTERED COMPLETE LOSS OF CIRCULATION @ 10207' WHILE DRILLING. | LCIR | NA |  | 05/25/2022 | SND-2002 | 1 | WAQR-23
2210 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | SND-2003 | Hrs | RMTN-17
2211 | FOT | HWP | 41.75 | 24 May 0700 - 0045 | 12534 | 896997 | WHILE ATTEMPTING TO INCREASE WIRELINE TENSION TO 19.5 KLBS, THE WIRELINE TRUCKS AIR BRAKES FAILED. | TF | WLU |  | 05/25/2022 | SND-2003 | 19.75 | RMTN-17
2212 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | SND-2008 | Hrs | HRDH-1052
2213 | FOT | GEP | 5 | 24 May 0230 - 0730 | 0 | 896998 | WOOD GROUP EBS SECONDARY SEAL FAILED, REPLACE W/NEW ONE. | WH | WH |  | 05/25/2022 | SND-2008 | 2.5 | HRDH-1052
2214 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | SSA-303 | Hrs | HRDH-2306
2215 | FOT | BHI | 32.5 | 23 May 1415 - 0430 | 10990 | 896938 | LOST SIGNAL WITH BAKER MWD TOOL @ 10,990' | BHA | MWD |  | 05/25/2022 | SSA-303 | 23.5 | HRDH-2306
2216 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | SSA-5969 | Hrs | UTMN-3021
2217 | FOT | HLH | 11 | 25 May 0530 - 1630 | 12564 | 896963 | HALLIBURTON 9-5/8" XTREMEGRIP LINER HANGER FAILED TO SET | TF | HGRL |  | 05/25/2022 | SSA-5969 | 11 | UTMN-3021
2218 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | SSA-5974 | Hrs | HRDH-1970
2219 | CWEL | ARM | 710.25 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/25/2022 | SSA-5974 | 21.5 | HRDH-1970
2220 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/25/2022 | T907 | Hrs | RGHB-703
2221 | ACDI | SPS | 92.75 | 21 May 1515 - 1230 | 7060 | 896803 | DEVIATE FROM ORIGINAL DIRECTION PLAN BY AROUND 180 DEGREE AZIMUTH | DD | BHA |  | 05/25/2022 | T907 | 7.5 | RGHB-703
2222 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | 095TE | Hrs | MNIF-220
2223 | FOT | NSL | 2 | 26 May 0730 - 0930 | 19101 | 896929 | SLICKLINE UNIT NON OPERATIONAL . | TF | SLICK |  | 05/26/2022 | 095TE | 2 | MNIF-220
2224 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | ADC-43L | Hrs | UTMN-3118
2225 | FRFM | TK3 | 62.5 | 24 May 0715 - 0500 | 6420 | 896955 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 05/26/2022 | ADC-43L | 22 | UTMN-3118
2226 | 16463 |  | STIM | E | 2864 | CTU | P/T CT EQUIPMENT AS BELOW:- P/T ALL RISERS, PCE CONNECTIONS, STRIPPERS AGAINST GATE VALVE TO 300/2500 PSI.- P/T ALL RISERS, PCE CONNECTIONS, ADAPTOR FLANGE CONNECTION TO RIG BOP AGAINST RIG BOP BLIND RAM VALVE TO 300/1500 PSI. | 16463 |  | SCT | 05/26/2022 | ADC-57L | STIM | FDHL-158
2227 | 16463 |  | STIM | E | 2864 | CTU | M/U CT BHA (MHA + STRAIGHT BAR + NOZZ). P/T DOUBLE FLAPPER CHECK VALVE, RISER STACK AGAINST GATE VALVE TO 2500 PSI. | 16463 |  | SCT | 05/26/2022 | ADC-57L | STIM | FDHL-158
2228 | 16463 |  | STIM | E | 2864 | CTU | PICKLE CT WITH 10 BBLS OF HCL ACID & DISPLACE THE COILED TUBING FROM FRESH WATER TO LUBRICATED BRINE (82 BBLS). | 16463 |  | SCT | 05/26/2022 | ADC-57L | STIM | FDHL-158
2229 | 16463 |  | STIM | E | 2864 | CTU | RIH COILED TUBING FROM SURFACE TO 12778 FT. - CIRCULATING LUBRICATED BRINE AT 0.5 BPM WITH CHOKE OPEN. - TAKE CARE PASSING THROUGH BOP, WELL HEAD & TOP OF LINER. - RIH SPEED: 40 FPM. | 16463 |  | SCT | 05/26/2022 | ADC-57L | STIM | FDHL-158
2230 | 16463 |  | STIM | E | 2864 | CTU | RIH COILED TUBING FROM 12778 FT TO 15358 FT. - CIRCULATING LUBRICATED BRINE AT 1 BPM WITH CHOKE OPEN. | 16463 |  | SCT | 05/26/2022 | ADC-57L | STIM | FDHL-158
2231 | 16463 |  | STIM | E | 2864 | CTU | RIH COILED TUBING IN OPEN HOLE FROM 15358 FT TO 15400 FT. - PUMP 134 BBL PRE-FLUSH AT 3 BPM WITH CHOKE OPEN. | 16463 |  | SCT | 05/26/2022 | ADC-57L | STIM | FDHL-158
2232 | 16463 |  | STIM | E | 2864 | CTU | RIH COILED TUBING IN OPEN HOLE FROM 15358 FT TO 16463 FT. - PUMPING PREFLUSH AT 3 BPM, CIRCULATING PRESSURE 2000 PSI WITH CHOKE CLOSED, 800 PSI WELL HEAD PRESSURE. | 16463 |  | SCT | 05/26/2022 | ADC-57L | STIM | FDHL-158
2233 | 16463 |  | STIM | E | 2864 | CTU | POOH FROM 16463 FT TO 13160 FT WITH PUMPING 15% HCL ACID FOLLOWING MATRIX ACID STIMULATION TREATMENT PUMPING SCHEDULE. ON GOING AT RT. - CIRCULATING PRESSURE: 800 PSI, WHP: 0 PSI - POOH SPEED: 8 FPM | 16463 |  | SCT | 05/26/2022 | ADC-57L | STIM | FDHL-158
2234 | 50.5 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | STIMULATION JON FOR L-2, L-1. | 24 | 2864 | 24 May 0230 | 05/26/2022 | ADC-57L | Type | FDHL-158
2235
2236
2237 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | ADM-655 | Hrs | SFNY-144
2238 | WPDH | AP3 | 86 | 23 May 1500 - 0500 | 0 | 896896 | WAIT ON SFNY FIELD SERVICE TO DE-PRESSURIZE SFNY-143/146 PLATFORM FOR SAFE RIG APPROACH. | WO | NA |  | 05/26/2022 | ADM-655 | 24 | SFNY-144
2239 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | DPS-5 | Hrs | HRDH-2318
2240 | HERR | FMC | 25.25 | 25 May 1000 - 1115 | 3415 | 896925 | OBSTRUCTION WHILE PERFORMING SL DRIFT W/ 3.75"OD ON 4.5" TBG USING FRANKS JAM UNIT. | JF | CTRQ |  | 05/26/2022 | DPS-5 | 6.25 | HRDH-2318
2241 | WC16 | ARM | 22 | 25 May 0800 - 0600 | 6400 | 896931 | WHILE RIH, NOTICED DISCREPANCY ON TRIP SHEET. FLOW CHECKED, OBSERVED WELL FLOWING, SHUT IN WELL. KILL WELL W/137 PCF KILL MUD | WCNT | NA |  | 05/26/2022 | DPS-74 | 1 | NJYN-54
2242 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | DPS-74 | Hrs | NJYN-54
2243 | FOT | BLH | 983.25 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/26/2022 | DPS-74 | 23 | NJYN-54
2244 | WC16 | ARM | 22 | 25 May 0800 - 0600 | 6400 | 896931 | WHILE RIH, NOTICED DISCREPANCY ON TRIP SHEET. FLOW CHECKED, OBSERVED WELL FLOWING, SHUT IN WELL. KILL WELL W/137 PCF KILL MUD | WCNT | NA |  | 05/26/2022 | DPS-74 | 1 | NJYN-54
2245 | 7153 | 6700 | ST | E | 2844 | STDP | CONT. RIH WL LOG RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DRIFTED D/P F/3,900 FT T/ 6,700 FT. - MONITOR HOLE ON TRIP TANK, HOLE STATIC.- LOG CORRELATION PATH F/ 6,700' TO 6,500'- OPEN HOLE IN GOOD CONDITION. | 7153 | 3900 | RIG | 05/26/2022 | DQ-50L | LOG | HRDH-582
2246 | 7153 | 6908 | LOG | E | 2844 | WLT | CONT. RIH WL LOG RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DRIFTED D/P WHILE LOG DOWN F/6,557' T/ 6,908'.- PERFORMED STICK TENDENCY TESTS @ 6,598' FOR 20 MIN, NO STICKING TENDENCY.- RECORDED18/22 VALID PRESSURE POINTS AT 6,745', 6,750', 6,762', 6,765', 6,772', 6,779', 6,787', 6,795', 6,800', 6,815, 6,826', 6,831, 6,846, 6,858,, 6,908'.- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7153 | 6557 | BAW | 05/26/2022 | DQ-50L | LOG | HRDH-582
2247 | 7153 | 6908 | LOG | E | 2844 | WLT | POSITION WL RUN#4 LOGGING TOOLS (GR-FTEX-RCX) TO 6,908 FT SAMPLE POINT, & PERFORM STICKY TENDENCY TEST @ 6,908 FT FOR 15 MIN, 30 MIN, 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7153 | 6908 | BAW | 05/26/2022 | DQ-50L | LOG | HRDH-582
2248 | 7153 | 6738 | LOG | E | 2844 | WLT | POOH W/ WL RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DP STDS F/ 6,908 FT & POSITION STRING @ 6,738 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL AFTRER 3 TRIALS.- PUMP OUT STATION #1 @ 6,738 FT (AD2A) .- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 0.7 BBLS (WATER: 0.07 BBLS - OIL: 0.63 BBLS)- OPEN HOLE IN GOOD CONDITION.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7153 | 6738 | BAW | 05/26/2022 | DQ-50L | LOG | HRDH-582
2249 | 7153 | 6745 | LOG | E | 2844 | WLT | POSITION STRING @ 6,745 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL. AS PER RDD PROGRAM.- PUMP OUT STATION #2 @ 6,745 FT (2A05) (WATER: 0.076 BBLS - OIL: 0.24 BBLS). ... ONGOING.- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 1 BBLS (WATER: 0.14 BBLS - OIL: 0.87 BBLS). | 7153 | 6745 | BAW | 05/26/2022 | DQ-50L | LOG | HRDH-582
2250 | 116 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2844 | 22 May 0900 | 05/26/2022 | DQ-50L | Type | HRDH-582
2251
2252
2253 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | ED-85A | Hrs | ZULF-2062
2254 | OTH | RIG | 11.75 | 25 May 1930 - 0715 | 0 | 897038 | (CONTINUATION TO LT ID 894547 ON ZULF-2060 - BONNET PISTON LEAK). REPLACE CAMERON DOUBLE RAM WITH REPAIRED NOV DOUBLE RAM. | UPRA | NA |  | 05/26/2022 | ED-85A | 2.25 | ZULF-2062
2255 | FOT | BCR | 2.5 | 26 May 0100 - 0330 | 10450 | 897077 | TROUBLE SHOOT BAKER CRT, UNABLE TO ENGAGE CRT TO THE CSG JOINT DUE MECHANICAL FAILURE | TF | CRT |  | 05/26/2022 | ENSCO-76 | 2.5 | MRJN-851
2256 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | ENSCO-76 | Hrs | MRJN-851
2257 | FOT | DEP | 2 | 26 May 2130 - 2330 | 10450 | 896933 | DEEP CASING TOOLS 9-5/8" TURBOCASER FAILED WHILE FUNCTION TEST. | TF | RESH |  | 05/26/2022 | ENSCO-76 | 2 | MRJN-851
2258 | FOT | BCR | 2.5 | 26 May 0100 - 0330 | 10450 | 897077 | TROUBLE SHOOT BAKER CRT, UNABLE TO ENGAGE CRT TO THE CSG JOINT DUE MECHANICAL FAILURE | TF | CRT |  | 05/26/2022 | ENSCO-76 | 2.5 | MRJN-851
2259 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | NBR-797S | Hrs | UTMN-3130
2260 | FOT | SDM | 4.5 | 26 May 0030 - 0500 | 53 | 896934 | P/U MWD COLLAR, TRY TO INSTALL MWD TOOL INSIDE ITS COLLAR, MWD TOOL WOULD NOT FIT INSIDE ITS COLLAR | BHA | MWD |  | 05/26/2022 | NBR-797S | 4.5 | UTMN-3130
2261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | PA-529S | Hrs | SHYB-108
2262 | FOT | ENV | 42.25 | 25 May 1045 - 0500 | 0 | 896965 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY. | TF | EXPND |  | 05/26/2022 | PA-529S | 24 | SHYB-108
2263 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | PA-866S | Hrs | SHHB-2
2264 | FOT | RIG | 4.75 | 26 May 0015 - 0500 | 9870 | 897078 | OBSERVED VFD FAULT ON CONSOLE & FROM DRAWWORKS B MOTOR. 3 GENERATORS KNOCKED OFFLINE. ELECTRICIAN CHECKED TRACTION MOTOR AND CONFIRMS GROUND FAULT AND BURN OUT OF DRAWWORKS B MOTOR. ATTEMPT TO PULL OUT OF HOLE WITH DRAWWORKS A MOTOR AND OBSERVE OVERHEATING FROM DYNAMIC BREAKER MODULES #2 & #3 IN VFD HOUSE. | RR | DWKS |  | 05/26/2022 | PA-866S | 4.75 | SHHB-2
2265 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | SINO-19L | Hrs | UTMN-1587
2266 | FOT | HWP | 11 | 26 May 1800 - 0500 | 11496 | 896932 | WHILE LOG IMAGE/CALIPER LOG UP, SUDDENLY LOST COMMUNICATION TO THE TOOL AFTER ONLY 03 STDS. | TF | WLT |  | 05/26/2022 | SINO-19L | 11 | UTMN-1587
2267 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | SINO-27N | Hrs | HWYH-466
2268 | STBH | ARM | 128.5 | 21 May 1630 - 0500 | 7515 | 896822 | STRING GOT STUCK. | STUK | RBHA |  | 05/26/2022 | SINO-27N | 24 | HWYH-466
2269 | 6717 | 6303 | LOG | E | 2824 | WLT | COLLECTED SAMPLE # 11 USING STRADDLE PACKER @ 6,303' (11 OF 13 FM SAMPLES) ONE CYCLE. ............(OOS).> TOTAL DUMPING IN ANN.= 209 LITERS / WATER & OIL - TOTAL 1,133 LITERS.> MAX STATIONARY TIME 4 HRS FOR EACH CYCLE, MOVE & CONFIRMED STRG FREE.> MONITORED WELL THRU TRIP TANK, STATIC - OK | 6717 | 6303 | BAW | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2270 | 6717 | 6303 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED XL-PACKER & COLLECTED SAMPLE #12 @ 6,300' (12 OF 13 FM SAMPLES) ONE CYCLE. ............(OOS).> SAMPLE #12 @ 6,300' (AD2A): TOTAL DUMPING IN ANN.= 131 LITERS - TOTAL 1,264 LITERS.> COLLECTED OIL SAMPLE.> MAX STATIONARY 4 HRS FOR EVERY POINT, MOVE & CONFIRMED STRG FREE.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6303 | BAW | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2271 | 6717 | 6303 | LOG | E | 2824 | WLT | POSITIONED STRING, INFLATED XL-PACKER & COLLECTED SAMPLE #13 @ 6,290' (13 OF 13 FM SAMPLES) ONE CYCLE. ............(OOS).> SAMPLE #13 @ 6,290' (ABD1): TOTAL DUMPING IN ANN.= 145 LITERS - TOTAL 1,409 LITERS.> COLLECTED OIL SAMPLE.> MONITORED WELL THRU TRIP TANK, STATIC - OK. | 6717 | 6303 | BAW | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2272 | 6717 |  | WCNT | E | 2824 | NA | FLOW CHECK, WELL STATIC. ............(OOS). | 6717 |  | RIG | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2273 | 6717 | 6090 | ST | E | 2824 | STDP | POOH WITH LOGGING TO SES DEPTH @ 6,090 FT.............(OOS). | 6717 | 6290 | RIG | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2274 | 6717 |  | OTH | E | 2824 | NA | HELD PJSM. UNLATCH CABLE, POOH SAME TO SURFACE AND L/D CABLE SHEAVES AND SES.............(OOS). | 6717 |  | BAW | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2275 | 6717 | 6520 | ST | E | 2824 | STDP | RIH TO BTM. HOLE IN GOOD CONDITION.............(OOS). | 6717 | 6090 | RIG | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2276 | 6717 |  | CIRC | E | 2824 | MPMP | CHC WITH 3 BPM AND 250 PSI. CONDITION MUD IN-OUT 72 PCF.............(OOS). | 6717 |  | RIG | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2277 | 6717 |  | WCNT | E | 2824 | NA | FLOW CHECK, WELL STATIC.............(OOS). | 6717 |  | RIG | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2278 | 6717 | 204 | ST | E | 2824 | STDP | POOH WITH 5" DP STDS TO TOP OF LOGGING TOOL.............(OOS). | 6717 | 6250 | RIG | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2279 | 6717 |  | WCNT | E | 2824 | NA | FLOW CHECK, WELL STATIC.............(OOS). | 6717 |  | RIG | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2280 | 6717 | 0 | LOG | E | 2824 | WLT | HPJSM, L/D BAKER LOGGING TOOLS.............(OOS). | 6717 | 204 | BAW | 05/26/2022 | SINO-43L | LOG | HWYH-2528
2281 | 6717 |  | HT | N |  | BHA | HPJSM. P/U, M/U & RIH COMBIND 8-1/2" REAMING WITH 9-5/8'' CLEAN OUT BHA ON 5" HWDP TO 660 FT. | 6717 |  | RIG | 05/26/2022 | SINO-43L | CT | HWYH-2528
2282 | 6717 | 1670 | TI | N |  | STDP | RIH C/O BHA ON 5" DP T/ 1670'.- FILL UP STRING EVERY 20 STD. | 6717 | 660 | RIG | 05/26/2022 | SINO-43L | CT | HWYH-2528
2283 | 6717 |  | HT | N |  | BHA | P/U & M/U STRING MILL, SCRAPER & MAGNETS ASSY, RIH T/ 1774'. | 6717 |  | RIG | 05/26/2022 | SINO-43L | CT | HWYH-2528
2284 | 161.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2"VERTICAL EVALUATION HOLE LOGGING. | 22 | 2824 | 20 May 0030 | 05/26/2022 | SINO-43L | Type | HWYH-2528
2285
2286
2287 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | SND-3002 | Hrs | DMMM-601
2288 | FOT | WDV | 14 | 26 May 1500 - 0500 | 3880 | 897076 | WFD DV OPENING PLUG NOT BUMPED AFTER DISPLACMENT. | TF | DV |  | 05/26/2022 | SND-3002 | 14 | DMMM-601
2289 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | SP-58 | Hrs | MDRK-53
2290 | FOT | RIG | 4 | 26 May 1730 - 2130 | 13225 | 896968 | AFTER CONNECTION, OBSERVED LEAK IN TDS SAVER SUB. | RR | CSYS |  | 05/26/2022 | SP-58 | 4 | MDRK-53
2291 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | SSA-5974 | Hrs | HRDH-1970
2292 | CWEL | ARM | 733.75 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/26/2022 | SSA-5974 | 23.5 | HRDH-1970
2293 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/26/2022 | T914 | Hrs | UTMN-1272
2294 | WCC8 | RIG | 24 | 26 May 0500 - 0500 | 7386 | 897079 | KILLING OPERATION | WCNT | NA |  | 05/26/2022 | T914 | 24 | UTMN-1272
2295 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | ADC-34 | Hrs | UTMN-2316
2296 | FOT | RIG | 5 | 27 May 1600 - 2230 | 11400 | 897060 | TOP DRIVE WILL NOT TURN ON | RR | TDS |  | 05/27/2022 | ADC-34 | 5 | UTMN-2316
2297 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | ADC-43L | Hrs | UTMN-3118
2298 | FRFM | TK3 | 86.5 | 24 May 0715 - 0500 | 6420 | 896955 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 05/27/2022 | ADC-43L | 24 | UTMN-3118
2299 | 16463 |  | STIM | E | 2864 | CTU | POOH FROM 13160 FT TO 12878 FT WITH PUMPING 15% HCL ACID FOLLOWING MATRIX ACID STIMULATION TREATMENT PUMPING SCHEDULE. - PUMPED 854 BBLS OF 15%HCL + 256 SXE WITH 3 BPM - CIRCULATING PRESSURE 800 PSI, WHP: 0 PSI - POOH SPEED: 10 FPM | 16463 |  | SCT | 05/27/2022 | ADC-57L | STIM | FDHL-158
2300 | 16463 |  | STIM | E | 2864 | CTU | POOH 2-3/8" CT FROM 12878 FT TO 12778 FT PUMPING POST FLUSH FLUID. - PUMPED 702 BBLS OF POSTFLUSH WITH 3 BPM. | 16463 |  | SCT | 05/27/2022 | ADC-57L | STIM | FDHL-158
2301 | 16463 |  | STIM | E | 2864 | CTU | POOH 2-3/8" CT IN CASED HOLE FROM 12778 FT TO SURFACE PUMPING BRINE AT 2 BPM. - CIRCULATING PRESSURE 250 PSI, WHP: 0 PSI. - POOH SPEED: 50 FPM. - RIG PRECAUTIONARY PUMPED 750 BBL OF 70 PCF VISCOUS BRINE AT 12778 FT, 500 BBL OF 70 PCF VISCOUS BRINE AT 6000 FT.- PUMP BACKSIDE MUD CAP 70 PCF BRINE @ 2 BPM CONTINUOUSLY. | 16463 |  | SCT | 05/27/2022 | ADC-57L | STIM | FDHL-158
2302 | 16463 |  | STIM | E | 2864 | CTU | HPJSM, DISCUSSED RISK ASSESSMENT. TRANSFER CT INJECTOR FROM TOP DRIVE TO CRANE & L/D. | 16463 |  | SCT | 05/27/2022 | ADC-57L | STIM | FDHL-158
2303 | 16463 |  | STIM | E | 2864 | CTU | R/D COILED TUBING EQUIPMENT:- - DISCONNECTED RISER& BHA. - REMOVED RISERS FROM THE BOTTOM OF INJECTOR HEAD ASSEMBLY ON RIG FLOOR. - LAY DOWN INJECTOR HEAD FROM RIG FLOOR TO TRUCK - DISCONNECT CT BOP HYDRAULIC HOSES. - NIPPLE DOWN CT BOP FROM RISER AND LAY DOWN. - DISCONNECT RISER ASSEMBLY FROM RIG BOP. - RIG PRECAUTIONARY PUMPED 300 BBL OF 70 PCF VISCOUS BRINE.- PUMP BACKSIDE MUD CAP 70 PCF BRINE @ 2 BPM CONTINUOUSLY, WELL UNDER TOTAL LOSSES. | 16463 |  | SCT | 05/27/2022 | ADC-57L | STIM | FDHL-158
2304 | 16463 |  | HT | E | 2864 | PEL | R/U BELL NIPPLE AND FLOW LINE. - PUMP BACKSIDE MUD CAP 70 PCF BRINE @ 2 BPM CONTINUOUSLY. | 16463 |  | RIG | 05/27/2022 | ADC-57L | DRLG | FDHL-158
2305 | 16463 |  | SET | N | 2864 | WBSH | INSTALL 11" WEAR BUSHING | 16463 |  | RIG | 05/27/2022 | ADC-57L | WH | FDHL-158
2306 | 16463 |  | PJSM | N |  | STRG | HELD PJSM PRIOR TO M/U WHIPSTOCK RETRIEVING BHA. | 16463 |  | RIG | 05/27/2022 | ADC-57L | CT | FDHL-158
2307 | 16463 |  | HT | N |  | BHA | P/U, M/U AND RIH WITH WHIPSTOCK RETRIEVAL BHA TO 622 FT: - WS RETRIEVING HOOK - CROSS OVER - 1 JNT X 4" HWDP - FLOAT SUB WITH FV - MWD TOOL - FILTER SUB - CROSS OVER - 1 STD X 4" HWDP - 2 X 7" MAGNOSTAR - 1 JNT X 4" HWDP - 1 X 7" MAGNOSTAR - 3 JNTS X 4" HWDP - 4-3/4" JAR - 8 JNST X 4" HWDP- RIG PRECAUTIONARY PUMPED 100 BBLS OF 70 PCF VISOUS BRINE INTO ANNULUS. | 16463 |  | RIG | 05/27/2022 | ADC-57L | CT | FDHL-158
2308 | 16463 | 2413 | TI | N |  | STDP | RIH WHIPSTOCK RETRIEVING BHA ON 4" DP FROM 622 FT TO 2413 FT. ON GOING AT RT. - PUMP BACKSIDE MUD CAP 70 PCF BRINE @ 1.5 BPM CONTINUOUSLY. WELL IN TOTAL LOSSES. | 16463 | 622 | RIG | 05/27/2022 | ADC-57L | CT | FDHL-158
2309 | 70.25 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | STIMULATION JON FOR L-2, L-1. | 19.75 | 2864 | 24 May 0230 | 05/27/2022 | ADC-57L | Type | FDHL-158
2310
2311
2312 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | ADC-65L | Hrs | HWYH-1280
2313 | AINC | SDM | 11.5 | 27 May 1730 - 0500 | 6370 | 897097 | SIDETRACK DIR. BHA TENDS TO BUILD UP IN ROTARY MODE ALL THE TIME. | DD | BHA |  | 05/27/2022 | ADC-65L | 11.5 | HWYH-1280
2314 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | ADM-655 | Hrs | SFNY-144
2315 | WPDH | AP3 | 110 | 23 May 1500 - 0500 | 0 | 896896 | WAIT ON SFNY FIELD SERVICE TO DE-PRESSURIZE SFNY-143/146 PLATFORM FOR SAFE RIG APPROACH. | WO | NA |  | 05/27/2022 | ADM-655 | 24 | SFNY-144
2316 | FOT | RIG | 6 | 27 May 2300 - 0500 | 11650 | 896975 | REPAIR ON TDS. PROBLEM ON TDS AUXILIARY MOTOR CABLES. CHANGE CABLES | RR | TDS |  | 05/27/2022 | DPS-74 | 6 | NJYN-54
2317 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | DPS-74 | Hrs | NJYN-54
2318 | FOT | BLH | 1001.25 | 13 Apr 0730 - 2300 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/27/2022 | DPS-74 | 18 | NJYN-54
2319 | FOT | RIG | 6 | 27 May 2300 - 0500 | 11650 | 896975 | REPAIR ON TDS. PROBLEM ON TDS AUXILIARY MOTOR CABLES. CHANGE CABLES | RR | TDS |  | 05/27/2022 | DPS-74 | 6 | NJYN-54
2320 | 7153 | 6745 | LOG | E | 2844 | WLT | CONT' POSITION STRING @ 6,745 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL. - PUMP OUT STATION #2 @ 6,745 FT (2A05) (WATER: 0.07 BBLS - OIL: 1.16BBLS). - MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 2 BBLS (WATER: 0.14 BBLS - OIL: 1.87BBLS). | 7153 | 6745 | BAW | 05/27/2022 | DQ-50L | LOG | HRDH-582
2321 | 7153 | 6762 | LOG | E | 2844 | WLT | POSITION STRING @ 6,762 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL. - PUMP OUT STATION #3 @ 6,762 FT (2A06) (WATER: 0.06BBLS - OIL: 0.59 BBLS). - MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE-2.11BBLS (WATER: 1.19 BBLS - OIL: 2.46 BBLS).- NO SMAPLES COLLECTED TILL MOMENT | 7153 | 6762 | BAW | 05/27/2022 | DQ-50L | LOG | HRDH-582
2322 | 7153 | 6765 | LOG | E | 2844 | WLT | POSITION STRING @ 6,765 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL. - PUMP OUT STATION #4 @ 6,765 FT (2A06) (WATER: 0.99BBLS ). - MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 3.65 BBLS (WATER: 1.19 BBLS - OIL: 2.46 BBLS).- COLLECTED ONE WATER SAMPLE (500 CC). | 7153 | 6765 | BAW | 05/27/2022 | DQ-50L | LOG | HRDH-582
2323 | 7153 | 6772 | LOG | E | 2844 | WLT | POSITION STRING @ 6,772 FT, ACTIVATE STD PROBE & CONFIRM GOOD SEAL. - PUMP OUT STATION #5 @ 6,772 FT (2A06) (WATER: 1.3 BBLS ). - MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 4.95 BBLS (WATER: 2.49 BBLS - OIL: 2.46 BBLS).- COLLECTED ONE WATER SAMPLE (500 CC).- MAX STATITIONARY TIME IS 4 HRS.- TIME FROM LAST CIRCULATION IS 57.75 HRS. | 7153 | 6772 | BAW | 05/27/2022 | DQ-50L | LOG | HRDH-582
2324 | 7153 |  | CIRC | E | 2844 | MPMP | DEACTIVATE STANDARD PROBE, MOVED FREELY, NO OVERPULL OBSERVED.RIH WITH WL SAMPLING TOOLS & POSITION CIRCULATION PORTS BELOW DEEPEST SAMPLE POINT @ 7,080 FT. | 7153 |  | RIG | 05/27/2022 | DQ-50L | LOG | HRDH-582
2325 | 7153 |  | CIRC | E | 2844 | MPMP | HPJSM & CIRCULATE FORMATION FLUIDS (2.49 BBLS WATER + 2.46 BBLS OIL) TO 3,000 FT INSIDE 9-5/8" CSG .- CIRC. FR 80:140 GPM, CIRC. PRESSURE 400 PSI.- RECIPROCATE THE STRG | 7153 |  | RIG | 05/27/2022 | DQ-50L | LOG | HRDH-582
2326 | 7153 |  | OTH | E | 2844 | NA | FLOW CHECK - WELL STATIC. | 7153 |  | RIG | 05/27/2022 | DQ-50L | LOG | HRDH-582
2327 | 7153 | 3690 | ST | E | 2844 | STDP | POOH W/ WL RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DP STDS F/ 7,080 FT TO 3,690 FT INSIDE 9-5/8" CSG AT CONTROLLED SPEED (3 MIN SLIPS TO SLIPS) - CSES ON SURFACE.- MONITOR WELL ON TRIP TANK & TRIP SHEET- WELL STATIC.- HOLE IN GOOD CONDITION. | 7153 | 7080 | RIG | 05/27/2022 | DQ-50L | LOG | HRDH-582
2328 | 7153 |  | CIRC | E | 2844 | MPMP | HPJSM & DISCUSS JSA W/ ALL PARTIES INVOLVED PRIOR TO PERFORM CIRCULATION OPERATIONS.CIRCULATE BTMS UP FORMATION FLUIDS (2.49 BBLS WATER + 2.46 BBLS OIL) & CONDITION MUD IN & OUT 81 PCF THROUGH FULLY OPEN CHOKE TO MGS W/ ANNULAR PREVENTER CLOSED.- CIRC. FR 170 GPM, CIRC. PRESSURE 330 PSI. | 7153 |  | RIG | 05/27/2022 | DQ-50L | LOG | HRDH-582
2329 | 7153 | 6230 | ST | E | 2844 | STDP | RIH W/ WL RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DP STDS F/ 3,690 FT AT CONTROLLED SPEED (3 MIN SLIPS TO SLIPS) TO 6,230 FT.- MONITOR WELL ON TRIP TANK & TRIP SHEET- WELL STATIC.- HOLE IN GOOD CONDITION. | 7153 | 3690 | RIG | 05/27/2022 | DQ-50L | LOG | HRDH-582
2330 | 140 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2844 | 22 May 0900 | 05/27/2022 | DQ-50L | Type | HRDH-582
2331
2332
2333 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | ED-85A | Hrs | ZULF-2062
2334 | FOT | RIG | 4 | 27 May 0630 - 1030 | 0 | 897063 | PROBLEM IN 4 WAY 3 POSITION VALVE ON CAD UNIT. | BOP | CTRL |  | 05/27/2022 | ED-85A | 4 | ZULF-2062
2335 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | NA-18S | Hrs | UTMN-2334
2336 | STBH | ARM | 335 | 12 May 1300 - 0500 | 13129 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/27/2022 | NA-18S | 24 | UTMN-2334
2337 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | PA-529S | Hrs | SHYB-108
2338 | FOT | ENV | 60.75 | 25 May 1045 - 2330 | 0 | 896965 | DURING EXPAND 5 1/2" ENVENTURE LINER GOT PRESSURE LOSS AT 5,742 FT, CONT. EXPAND LINER MECHANICALY. | TF | EXPND |  | 05/27/2022 | PA-529S | 18.5 | SHYB-108
2339 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | PA-866S | Hrs | SHHB-2
2340 | FOT | RIG | 28.75 | 26 May 0015 - 0500 | 9870 | 897078 | OBSERVED VFD FAULT ON CONSOLE & FROM DRAWWORKS B MOTOR. 3 GENERATORS KNOCKED OFFLINE. ELECTRICIAN CHECKED TRACTION MOTOR AND CONFIRMS GROUND FAULT AND BURN OUT OF DRAWWORKS B MOTOR. ATTEMPT TO PULL OUT OF HOLE WITH DRAWWORKS A MOTOR AND OBSERVE OVERHEATING FROM DYNAMIC BREAKER MODULES #2 & #3 IN VFD HOUSE. | RR | DWKS |  | 05/27/2022 | PA-866S | 24 | SHHB-2
2341 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SINO-12L | Hrs | HRDH-400
2342 | GRF | RIG | 128 | 22 May 1600 - 0500 | 0 | 896973 | UNPLANNED RIG MAINTENANCE ON THE MAST | UPRA | DRRK |  | 05/27/2022 | SINO-12L | 24 | HRDH-400
2343 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SINO-19L | Hrs | UTMN-1587
2344 | FOT | HWP | 27 | 26 May 1800 - 2100 | 11496 | 896932 | WHILE RECORDING IMAGE/CALIPER LOG, SUDDENLY LOST COMMUNICATION TO THE TOOL AFTER ONLY 03 STDS. | TF | WLT |  | 05/27/2022 | SINO-19L | 16 | UTMN-1587
2345 | 6705 |  | STIM | E | 2884 | CTU | CONTINUE R/U HALL. CT UNIT & EQUIPMENT .(OOS)- P/T QUAD BOP'S BLIND RAM TO 300/7500 PSI AGAINST 4 1/6''-10K GATE VALVE, OK.- CHANGE STRIPPER RUBBER- LIFT 10 FT RISER TO RIG FLOOR- LIFT INJECTOR TO RIG FLOOR & MAKE UP SAME WITH 10 FT RISER THEN LIFT & HANG UP INJECTOR WITH TOP DRIVE.- M/U CT CONNECTOR THEN PERFORM PULL TEST TO 25 KLBS,)- FLUSH & P/T CT UP TO CONNECTOR & SURFACE LINE UP TO CT BOP @ 300/7500 PSI , HOLD,OK- P/T QUAD BOP'S PIPE RAM TO 300/2500 PSI AGAINST 4 1/6''-10K GATE VALVE.- FLUSH & DRIFT CT WITH 7/8" BALL, OK- M/U CT BHA:- CT CONNECTOR + X.O + 2-7/8'' MOTOR HEAD ASSY. 7/8'' DISCONNECT BALL + 3/4'' CIRC. BALL 4 X STEEL SHEAR PINS + 7,500 PSI BURST DISC + STARIGHT BAR +X-O+ PULSONIX TF 2-1/8'' TOTAL BHA LEGTH: 7.6 FT.- P/T STRIPPER#2 & RISERS TO 300/2500 PSI AGAINST 4 1/6''-10K GATE VALVE, OK.- P/T STRIPPER#1 & RISERS TO 300/2500 PSI AGAINST 4 1/6''-10K GATE VALVE, OK.- P/T BHA CHECK VALVE TO 1500 PSI, OK [INFLOW TEST].** KEEP TRIP TANK RUNNING, THROUGH TUBING SPOOL OUTLET ALL TIMES. | 6705 |  | HCT | 05/27/2022 | SINO-1L | STIM | KHRS-348
2346 | 6705 |  | STIM | E | 2884 | CTU | OPEN 4 1/16"-10K GATE VALVE & RIH WITH HALL. 2'' C.T TO 5880 FT (OOS)- RECORDED ZERO WHP.- PERFORMRD PULL TEST EVERY 1000 FT, OK.- BREAK CIRCULATION 2 BBLS EVERY 1000 FT.- MONITOR WHSP WHILE RIH WITH MAX. PRESSURE UP TO 1000 PSI.- MEANWHILE PREPARED & MIXED ACID AS PER PROGRAM.* PRE FLUSH : 157 BBLS.* ACID MATRIX (20% HCL): 196 BBLS.* EMULSIFIED ACID (20% HCL): 59 BBLS.* POST FLUSH : 157 BBLS.* DISPLACEMENT : 157 BBLS WITH 66 PCF VISCOUS BRINE. | 6705 |  | HCT | 05/27/2022 | SINO-1L | STIM | KHRS-348
2347 | 6705 |  | STIM | E | 2884 | CTU | HPJSM , PERFORM ACID STIMULATION JOB : (OOS)- SHUT IN THE WELL , CT AT 5880 FT, DISPLACE WELL WITH 157 BBL. OF PRE-FLUSH .INC@RT | 6705 |  | HCT | 05/27/2022 | SINO-1L | STIM | KHRS-348
2348 | 49 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | ACID STIMULATION JOB. | 24 | 2884 | 23 May 2230 | 05/27/2022 | SINO-1L | Type | KHRS-348
2349
2350
2351 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SINO-27N | Hrs | HWYH-466
2352 | STBH | ARM | 152.5 | 21 May 1630 - 0500 | 7515 | 896822 | STRING GOT STUCK. | STUK | RBHA |  | 05/27/2022 | SINO-27N | 24 | HWYH-466
2353 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SND-2001 | Hrs | UTMN-2329
2354 | FOT | WUD | 6 | 27 May 0600 - 1200 | 12283 | 897062 | RCD BEARING FAILED | TF | MPD |  | 05/27/2022 | SND-2001 | 6 | UTMN-2329
2355 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SND-2002 | Hrs | WAQR-23
2356 | FOT | HLH | 32.5 | 26 May 2000 - 0500 | 10330 | 897098 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES. | TF | HGRL |  | 05/27/2022 | SND-2002 | 23.5 | WAQR-23
2357 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SND-3002 | Hrs | DMMM-601
2358 | FOT | WDV | 38 | 26 May 1500 - 0500 | 3880 | 897076 | WFD DV OPENING PLUG NOT BUMPED AFTER DISPLACMENT. | TF | DV |  | 05/27/2022 | SND-3002 | 24 | DMMM-601
2359 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SND-3003 | Hrs | HRDH-2303
2360 | HERR | SAM | 2 | 27 May 0730 - 0930 | 10697 | 896974 | SAMAA FCS PACKER FAILED TO HOLE PRESSURE TO 1000 PSI, LEAK AT 600 PSI. | JF | WBCL |  | 05/27/2022 | SND-3003 | 2 | HRDH-2303
2361 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SNF036 | Hrs | MRJN-901
2362 | FOT | RIG | 4 | 27 May 0645 - 1045 | 9368 | 897059 | AFTER OPERATING ANNULAR BOP OBSERVED LEAK ON ACCUMULATOR FROM THE"MANIFOLD" LINE. | RR | RWCS |  | 05/27/2022 | SNF036 | 4 | MRJN-901
2363 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SP-120 | Hrs | MNIF-188
2364 | FPMP | RIG | 2.5 | 27 May 1730 - 2000 | 16218 | 897061 | CIRC WITH MP#1 WHILE REPAIR MP#2 & 3 ( CHANGE OUT DAMAGED VALVES AND SEALS) | RR | MPMP |  | 05/27/2022 | SP-120 | 2.5 | MNIF-188
2365 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SSA-5917 | Hrs | HRDH-2261
2366 | FOT | RIG | 32.5 | 16 May 0400 - 0130 | 11200 | 896610 | TROUBLESHOOTING -ABNORMAL SOUND IN TDS - TRYING TO REPAIR | RR | TDS |  | 05/27/2022 | SSA-5917 | 8.5 | HRDH-2261
2367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SSA-5969 | Hrs | UTMN-3021
2368 | FOT | HLH | 32 | 25 May 0530 - 0500 | 12564 | 896963 | HALLIBURTON 9-5/8" XTREMEGRIP LINER HANGER FAILED TO SET | TF | HGRL |  | 05/27/2022 | SSA-5969 | 21 | UTMN-3021
2369 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | SSA-5974 | Hrs | HRDH-1970
2370 | CWEL | ARM | 835 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/27/2022 | SSA-5974 | 23 | HRDH-1970
2371 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | T914 | Hrs | UTMN-1272
2372 | WCC8 | RIG | 40.5 | 26 May 0500 - 2130 | 7386 | 897079 | KILLING OPERATION | WCNT | NA |  | 05/27/2022 | T914 | 16.5 | UTMN-1272
2373 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/27/2022 | ZPEC-1 | Hrs | GZLN-801
2374 | HYFM | ARM | 1.5 | 27 May 0900 - 1030 | 1887 | 897058 | ATTEPTED TO CIRCULATE HOLE WITH ICS PRESSURE BULD UP FORMATION BRIDGING. | HC | NA |  | 05/27/2022 | ZPEC-1 | 1.5 | GZLN-801
2375 | FOT | WUD | 1.5 | 28 May 0200 - 0330 | 10520 | 897118 | WFD RCD BOWL SEAL LEAKS | TF | MPD |  | 05/28/2022 | ADC-31 | 1.5 | SDGM-1181
2376 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | ADC-31 | Hrs | SDGM-1181
2377 | FOT | RIG | 2 | 28 May 0000 - 0200 | 10520 | 897117 | STAND PIPE JUMPER HOUSE LEAKS. | TF | SFLN |  | 05/28/2022 | ADC-31 | 2 | SDGM-1181
2378 | FOT | WUD | 1.5 | 28 May 0200 - 0330 | 10520 | 897118 | WFD RCD BOWL SEAL LEAKS | TF | MPD |  | 05/28/2022 | ADC-31 | 1.5 | SDGM-1181
2379 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | ADC-43L | Hrs | UTMN-3118
2380 | FRFM | TK3 | 110.5 | 24 May 0715 - 0500 | 6420 | 896955 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 05/28/2022 | ADC-43L | 24 | UTMN-3118
2381 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | ADC-57L | Hrs | FDHL-158
2382 | IBHA | TK3 | 18.25 | 28 May 1030 - 0445 | 9138 | 897073 | MWD TOOL NOT RECEIVING SIGNAL AT SURFACE | BHA | BHA |  | 05/28/2022 | ADC-57L | 18.25 | FDHL-158
2383 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | ADC-65L | Hrs | HWYH-1280
2384 | AINC | SDM | 28.5 | 27 May 1730 - 2230 | 6371 | 897097 | SIDETRACK DIR. BHA TENDS TO BUILD UP IN ROTARY MODE ALL THE TIME. | DD | BHA |  | 05/28/2022 | ADC-65L | 17 | HWYH-1280
2385 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | ADES-13 | Hrs | HRDH-157
2386 | FOT | BHI | 23.5 | 27 May 2000 - 0500 | 6321 | 897074 | LOW ROP BECAUSE OF BAKER RSS FAILING TO BUILD UP AS PER PLAN. | BHA | RSS |  | 05/28/2022 | ADES-13 | 14.5 | HRDH-157
2387 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | ADM-655 | Hrs | SFNY-144
2388 | WPDH | AP3 | 134 | 23 May 1500 - 0500 | 0 | 896896 | WAIT ON SFNY FIELD SERVICE TO DE-PRESSURIZE SFNY-143/146 PLATFORM FOR SAFE RIG APPROACH. | WO | NA |  | 05/28/2022 | ADM-655 | 24 | SFNY-144
2389 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | DPS-43 | Hrs | SDGM-1196
2390 | ULCM | ARM | 11.75 | 28 May 0515 - 1700 | 15885 | 897071 | WHILE DIRC DRILLING AT 15,885' GOT PARTIAL LOSSES | LCIR | LCM |  | 05/28/2022 | DPS-43 | 11.75 | SDGM-1196
2391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | DPS-74 | Hrs | NJYN-54
2392 | FOT | BLH | 1025.25 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/28/2022 | DPS-74 | 24 | NJYN-54
2393 | 7153 | 6800 | ST | E | 2844 | STDP | RIH W/ WL RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DP STDS F/ 6,230 FT AT CONTROLLED SPEED (3 MIN SLIPS TO SLIPS) TO 6,800 FT.- MONITOR WELL ON TRIP TANK & TRIP SHEET- WELL STATIC.- HOLE IN GOOD CONDITION. | 7153 | 6230 | RIG | 05/28/2022 | DQ-50L | LOG | HRDH-582
2394 | 7153 | 6787 | LOG | E | 2844 | WLT | POSITION STRING @ 6,787 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL.- PUMP OUT STATION #6 @ 6,787 FT (2B08) TOT 1.16 BBL ( OIL: 0.81 WATER: 0.35 BBLS ).- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- TOT 1.16 BBL ( OIL: 0.81 WATER: 0.35 BBLS ).- COLLECTED ONE WATER/OIL SAMPLE (500 CC).- MAX STATIONARY TIME IS 4 HRS.- 6,787', 2B08,FM.PRESS = 3,167 PSI, EQ.MW=67PCF, O.P=686PSI | 7153 | 6787 | BAW | 05/28/2022 | DQ-50L | LOG | HRDH-582
2395 | 7153 | 6795 | LOG | E | 2844 | WLT | POSITION STRING @ 6,795FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL.- PUMP OUT STATION #7 @ 6,795 FT (2B09) TOT 1.26 BBL ( OIL: 0 WATER: 1.26 BBLS ).- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- TOT 2.42 BBL ( OIL: 0.81 WATER: 1.61BBLS ).- COLLECTED ONE WATERSAMPLE (500 CC).- MAX STATIONARY TIME IS 4 HRS.- 6,795', 2B09,FM.PRESS = 3,171 PSI, EQ.MW=67PCF, O.P=697PSI | 7153 | 6795 | BAW | 05/28/2022 | DQ-50L | LOG | HRDH-582
2396 | 7153 | 6815 | LOG | E | 2844 | WLT | POSITION STRING @ 6,815FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL.- PUMP OUT STATION #8 @ 6,815 FT (2B11) TOT 1.17BBL ( OIL: 0.05 WATER: 1.12 BBLS ).- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- TOT 3.59 BBL ( OIL: 0.86 WATER: 2.73BBLS ).- COLLECTED ONE WATER SAMPLE (500 CC).- MAX STATIONARY TIME IS 4 HRS.- 6,815', 2B11,FM.PRESS = 3,177 PSI, EQ.MW=67PCF, O.P=690PSI | 7153 | 6815 | BAW | 05/28/2022 | DQ-50L | LOG | HRDH-582
2397 | 7153 | 6826 | LOG | E | 2844 | WLT | POSITION STRING @ 6,826FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL.- PUMP OUT STATION #9 @ 6,826 FT (2B12) TOT 1.34BBL ( OIL: 0 WATER: 1.34 BBLS ).- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- TOT 4.93 BBL ( OIL: 0.86 WATER: 4.07BBLS ).- COLLECTED ONE WATER SAMPLE (500 CC).- MAX STATIONARY TIME IS 4 HRS.- 6,826', 2B12,FM.PRESS = 3,181 PSI, EQ.MW=67PCF, O.P=706 PSI | 7153 | 6826 | BAW | 05/28/2022 | DQ-50L | LOG | HRDH-582
2398 | 7153 | 6841 | LOG | E | 2844 | WLT | POSITION STRING @ 6,840 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL.- TRY TO PUMP OUT STATION #10 @ 6,840 FT (AD3A), FOUND DRY, REPOSITION AT 6,841 FT, ACTIVATE XL PROBE.- PUMP OUT STATION #10 @ 6,841 FT (AD3A) TOT 0.7BBL ( OIL: 0 WATER: 0.7 BBLS ).- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- TOT 5.63 BBL ( OIL: 0.86 WATER: 4.77 BBLS ).- NO SAMPLE COLLECTED, RDD DECIDED TO GO FOR CYCLE #2.- MAX STATIONARY TIME IS 4 HRS. | 7153 | 6841 | BAW | 05/28/2022 | DQ-50L | LOG | HRDH-582
2399 | 7153 | 6841 | LOG | E | 2844 | WLT | POSITION STRING @ 6,841 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL....ONGOING- PUMP OUT STATION #10 CYCLE #2 @ 6,841 FT (AD3A) ...ONGOING- MONITORING WELL ON TRIP TANK- WELL STATIC. | 7153 | 6841 | BAW | 05/28/2022 | DQ-50L | LOG | HRDH-582
2400 | 164 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2844 | 22 May 0900 | 05/28/2022 | DQ-50L | Type | HRDH-582
2401
2402
2403 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | HI-9 | Hrs | QTIF-557
2404 | UNKN | RIG | 14.5 | 28 May 1430 - 0500 | 17717 | 897099 | SUSPEND RIG OPERATIONS TILL INVESTIGATION COMPLETE. | HSEI | NA |  | 05/28/2022 | HI-9 | 14.5 | QTIF-557
2405 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | NA-18S | Hrs | UTMN-2334
2406 | STBH | ARM | 359 | 12 May 1300 - 0500 | 13129 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/28/2022 | NA-18S | 24 | UTMN-2334
2407 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | NBR-115S | Hrs | HWYH-1220
2408 | FOT | RIG | 1.5 | 28 May 0600 - 0830 | 13938 | 897067 | TDS LOWER CONTROL VALVE CONNECTION WASHOUT. | RR | TDS |  | 05/28/2022 | NBR-115S | 1.5 | HWYH-1220
2409 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | NBR-263S | Hrs | QTIF-736
2410 | HERR | RIG | 1.5 | 28 May 0115 - 0245 | 927 | 897116 | WHILE FLUSH OF CEMENT LINE, FOUND RIG CHIKSAN, SWIVEL & MANIFOLD PLUGGED WITH CEMENT FROM PREVIOUS JOB. REPLACED SAME | JF | SFLN |  | 05/28/2022 | NBR-263S | 1.5 | QTIF-736
2411 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | PA-622S | Hrs | AFLJ-4
2412 | FOT | HCO | .75 | 28 May 1000 - 1045 | 7478 | 897068 | CYCLE HAL PROPHASE VALVE TO LOCK OPEN, AND ATTEMPTED TO PASS WITH COILED TBG BUT FOUND IT CLOSE. | TF | HVLV |  | 05/28/2022 | PA-622S | .75 | AFLJ-4
2413 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | PA-866S | Hrs | SHHB-2
2414 | FOT | RIG | 50 | 26 May 0015 - 0500 | 9870 | 897078 | OBSERVED VFD FAULT ON CONSOLE & FROM DRAWWORKS B MOTOR. 3 GENERATORS KNOCKED OFFLINE. ELECTRICIAN CHECKED TRACTION MOTOR AND CONFIRMS GROUND FAULT AND BURN OUT OF DRAWWORKS B MOTOR. ATTEMPT TO PULL OUT OF HOLE WITH DRAWWORKS A MOTOR AND OBSERVE OVERHEATING FROM DYNAMIC BREAKER MODULES #2 & #3 IN VFD HOUSE. | RR | DWKS |  | 05/28/2022 | PA-866S | 21.25 | SHHB-2
2415 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | PN-9 | Hrs | ABSF-16
2416 | FOT | BAW | 3 | 28 May 2100 - 0000 | 0 | 897072 | BAKER PNL LOGGING ASSY UNALBE TO BE RELEASED FROM TOOL CATCHER. MADE SEVERAL ATTEMPTS TO RELEASE TOOL, NO SUCCESS. DISCONNECT LUBRICATOR. INSPECT TOOL CATCHER. RECONNECT HYDRAULIC HOSE. FUNCTION TOOL CATCHER, OK. MU LUBRICATOR. PT. | TF | WLT |  | 05/28/2022 | PN-9 | 3 | ABSF-16
2417 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SINO-12L | Hrs | HRDH-400
2418 | GRF | RIG | 135 | 22 May 1600 - 1200 | 0 | 896973 | UNPLANNED RIG MAINTENANCE ON THE MAST | UPRA | DRRK |  | 05/28/2022 | SINO-12L | 7 | HRDH-400
2419 | 6705 |  | STIM | E | 2884 | CTU | HPJSM , PERFORM ACID STIMULATION JOB : (OOS)- SHUT IN THE WELL , RIH CT FROM 5880 FT TO 6705 FT, DISPLACE WELL WITH 157 BBL. OF PRE-FLUSH.- POOH CT TO CSG SHOE @ 5880 FT , MEANWHILE SQUEEZE ACID PILL & EMULSIFIED ACID @ 2 BPM WITH MAX. SHUT IN PRESSURE 1000 PSI THEN PRESSURE GRADUALLY DROP, GOOD INDICATION FOR ACID EFFECT .- WITH WELL SHUT IN , RIH CT T/6705 FT WITH RUNNING SPEED 11 FPM MEAN WHILE PUMPING POST-FLUSH @ 2 BPM & WELL HEAD SHUT IN PRESSURE 0 TO 1000 PSI ,TOTAL POST-FLUSH VOLUME 157 BBLS. | 6705 |  | HCT | 05/28/2022 | SINO-1L | STIM | KHRS-348
2420 | 6705 |  | STIM | E | 2884 | CTU | - WITH WELL SHUT IN , START POOH CT FROM 6705 FT TO 5880 FT WITH PULLING SPEED 11 FPM MEANWHILE PUMPING DISPLACEMENT 157 BBLS WITH 66 PCF VISCOUS BRINE. AS PER PUMPING SCHEDULE @ 2 BPM , WELL HEAD SHUT IN PRESSURE NOT EXCEED 1000 PSI, ONCE DISPLACEMENT GET OUT FROM CT.(OOS) | 6705 |  | HCT | 05/28/2022 | SINO-1L | STIM | KHRS-348
2421 | 6705 |  | STIM | E | 2884 | CTU | CONT POOH COILED TUBING FROM 5880 FT TO SURFACE, MEANWHILE LINE-UP TO RIG PUMP & BULLHEADED WELL WITH 600 BBLS OF 66 PCF VISCOUS BRINE @ 6-8 BPM & 300-500 PSI. (OOS)- FLOW CHECK, WELL IN COMPLETE LOSS. | 6705 |  | HCT | 05/28/2022 | SINO-1L | STIM | KHRS-348
2422 | 6705 |  | STIM | E | 2884 | CTU | FLUSH & R/D CT INJECTIOR AND ACID STIMULATION TANKS & SURFACE EQUIP. (OOS)- KEEP TRIP TANK RUNNING WITH 60 BPH, 66 PCF VISCOUS BRINE. | 6705 |  | HCT | 05/28/2022 | SINO-1L | STIM | KHRS-348
2423 | 6705 |  | NU | C |  | BNIP | NU BELL NIPPLE & FLOW LINE.- KEPT RUNNING TRIP TANK WITH 60 BPH, WELL IN COMPLETE LOSS. | 6705 |  | RIG | 05/28/2022 | SINO-1L | BOP | KHRS-348
2424 | 6705 |  | HT | C |  | PEL | HPJSM, RIG DOWN RIG POWER TONG & HANDLING EQPT. RU NABORS POWER TONG & TBG RUNNING/HANDLING TOOLS.- KEPT RUNNING TRIP TANK WITH 60 BPH, WELL IN COMPLETE LOSS. | 6705 |  | SPR | 05/28/2022 | SINO-1L | COMP | KHRS-348
2425 | 6705 |  | PJSM | C |  | ESPL | HPJSM, DISCUSS WITH RIG CREW AND KEY PERSONNEL, REVIEWED COMBINED LSTK/BK JSA & PROCEDURES IN DETAILS PRIOR TO RUN ESP COMPLETION. | 6705 |  | BAL | 05/28/2022 | SINO-1L | COMP | KHRS-348
2426 | 6705 |  | HT | C |  | ESP | CONT. P/U & M/U ESP PUMP ASSY AS BELOW:- PUMP HEAD, BO 3-1/2 8RD EUE 4SS.- SUB,TRANSFER DISCHARGE PRESSURE 3-1/2 8RD EUE- PUMP, 538PMSXD, FLEX47 - 39 STG S/N:15639023- INTAKE GPARCINT FER 6CRC S/N:15716741- SEAL 513SL_B/B/L FER H18 AB CU SLV TL S/N:15672792- SEAL 513SL_B/B/L FER H18 AB CU SLV TLS/N:15672793- MOTOR, 562XP 125/1890/41 S/N:15561635- SENSOR,ZENITH E7 SERIES ESP DOWNHOLE S/N:15443292- CENTRALIZER, MOTOR 6.00 OD STL- TOTAL PUMP ASSY LENGTH: 41.33 FT.- KEPT TRIP TANK RUNNING WITH 66 PCF VICOUS BRINE - WELL IN COMPLETE LOSS. | 6705 |  | BAL | 05/28/2022 | SINO-1L | COMP | KHRS-348
2427 | 6705 |  | HT | C |  | ESP | CONNECTED AND FEED MLE FLAT CABLE TO PUMP DISCHARGE HEAD (INTAKE & DISCHARGE). - PRESSURE TEST SENSOR TO 2500 PSI; OK.- TAKE CABLE READING P-P=2.0 OHMS (BALANCED), P-G= 53.0 G OHMS @ 5 MINS & 70.0 G OHMS @ 10 MIN.- KEPT TRIP TANK RUNNING WITH 66 PCF VICOUS BRINE - WELL IN COMPLETE LOSS. | 6705 |  | BAL | 05/28/2022 | SINO-1L | COMP | KHRS-348
2428 | 6705 |  | HT | C |  | PKR | P/U & M/U 7" PRAXIS ISOPAX ESP PACKER ASSY AS FOLLOW ..INC@RT.-PJ, 2-7/8", 6.4#, J-55 NVAM PRAXIS,ISOPAX ESP PACKER (7" X 2.875" X 1.9")S/N:PRX-PO-21905259-002PJ, 2-7/8", 6.4#, J-55 NVAM XOVR, 2-7/8" NVAM BOX X 2-7/8" 8RD EUE PINPJ, 2-7/8", 6.5#, J-55 8RD EUE (9.94+2.99+2.06)PJ, 2-7/8", 6.5#, J-55 8RD EUEXN-NIPPLE, 2-7/8" 8RD EUE (NO-GO ID: 2.205") - W/COUPLINGPJ, 2-7/8", 6.5#, J-55 8RD EUEXOVR, 2-7/8" 8RD EUE BOX X 3-1/2" 8RD EUE PINTBG, 3-1/2", 9.3#, J-55 8RD EUE- KEPT TRIP TANK RUNNING WITH 66 PCF VICOUS BRINE - WELL IN COMPLETE LOSS. | 6705 |  | BAL | 05/28/2022 | SINO-1L | COMP | KHRS-348
2429 | 67 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | ACID STIMULATION JOB. | 18 | 2884 | 23 May 2230 | 05/28/2022 | SINO-1L | Type | KHRS-348
2430
2431
2432 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SINO-27N | Hrs | HWYH-466
2433 | STBH | ARM | 176.5 | 21 May 1630 - 0500 | 7515 | 896822 | STRING GOT STUCK. | STUK | RBHA |  | 05/28/2022 | SINO-27N | 24 | HWYH-466
2434 | 9892 | 9892 | TI | N |  | STDP | RUN BACK WASH DOWN TO BOTTOM @ 9891 TO CLEAN HOLE FOR MPASS PACKER RUN. | 9892 | 7139 | RIG | 05/28/2022 | SINO-32L | DRLG | SHYB-570
2435 | 9892 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH 2 X 20 BBL LOW-VIS / 30 BBL. HI-WEIGHT PILLS , CHC , 70 BPH DYNAMIC LOSSES.* FLOW CHECK, 20 BPH STATIC LOSSES.* DECISION TAKEN TO CALL EARLY TD AND SET MPAS PKR. | 9892 |  | RIG | 05/28/2022 | SINO-32L | DRLG | SHYB-570
2436 | 9892 | 9300 | TO | N |  | STDP | POOH WITH PUMP OUT 5 STDS TO 9300 FT*FLOW CHECK, 20 BPH STATIC LOSSES. | 9892 | 9892 | RIG | 05/28/2022 | SINO-32L | DRLG | SHYB-570
2437 | 9892 | 7139 | TO | N |  | STDP | CONTINUE POOH WITH MB RSS BHA TO 7" LINER SHOE @ 7139 FT.*FLOW CHECK, 20 BPH STATIC LOSSES. | 9892 | 9300 | RIG | 05/28/2022 | SINO-32L | DRLG | SHYB-570
2438 | 9892 | 0 | TO | N |  | STDP | CONTINUE POOH WITH 6-1/8" RSS MB BHA TO SURFACE* FLOW CHECK @TOL, @ TOP OF BHA - 30 BBLS STATIC LOSSES | 9892 | 7139 | RIG | 05/28/2022 | SINO-32L | DRLG | SHYB-570
2439 | 9892 |  | HT | N |  | BHA | HPJSM ,RETRIEVE AND L/D RADIO ACTIVE SOURCE.DUMP MWD MEMORY & RACK BACK BHA.** CHECK FLOAT SUB AND FILTER SUB.** RACK BACK BHA | 9892 |  | BHI | 05/28/2022 | SINO-32L | DRLG | SHYB-570
2440 | 9892 |  | HT | N | 2904 | PEL | P/U 4 1/2" TUBING HANDLING TOOLS. | 9892 |  | RIG | 05/28/2022 | SINO-32L | DRLG | SHYB-570
2441 | 9892 |  | HT | N | 2904 | STRG | P/U & M/U 4 1/2" P&A KIT AS BELOW:*4.5" BAKER GPV SHOE W/ PUP JOINT, 2X PUP JOINT 4 1/2", 4 1/2" WELLBORE ISOLATION VALVE W/ PJ, TBG JOINT 4 1/2", BAKER MPAS MECH. EXTERNAL CSG PACKER, BAKER LIFT NIPPLE, TBG JOINT 4-1/2", BAKER MPAS MECH. EXTERNAL CSG PACKER, BAKER LIFT NIPPLE, TBG JOINT 4-1/2", PUP JOINT 4-1/2", 2X 4 1/2" C2 SETTING SLEEVE W/ EXTENTION. ** CIRCULATE WITH 4 BPM, PRESSURE 50 PSI** PUW=60 KLBS , SOW =60 KLBSMONITOR THE WELL ON TRIP TANK | 9892 |  | RIG | 05/28/2022 | SINO-32L | PA | SHYB-570
2442 | 9892 | 2500 | OTH | N | 2904 | NA | RIH WITH MPAS PACKERS ASSEMBLY ON 4" DP AT CONTROLLED SPEEDMONITOR THE WELL ON TRIP TANK | 9892 | 217 | RIG | 05/28/2022 | SINO-32L | PA | SHYB-570
2443 | 4.5 | OOS | Category | DOOS ID | RZIT | Out of Scope Summary | MPAS PLUG AND ABANDONMENT JOB | 4.5 | 2904 | 28 May 0030 | 05/28/2022 | SINO-32L | Type | SHYB-570
2444
2445
2446 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SND-2001 | Hrs | UTMN-2329
2447 | FOT | RIG | 6.5 | 28 May 0700 - 1330 | 12518 | 897065 | STAND PIPE MANIFOLD ISOLATION VALVE WASHED OUT | TF | SFLN |  | 05/28/2022 | SND-2001 | 6.5 | UTMN-2329
2448 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SND-2002 | Hrs | WAQR-23
2449 | FOT | HLH | 56.5 | 26 May 2000 - 0500 | 10330 | 897098 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES. | TF | HGRL |  | 05/28/2022 | SND-2002 | 24 | WAQR-23
2450 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SND-3002 | Hrs | DMMM-601
2451 | FOT | WDV | 62 | 26 May 1500 - 0500 | 3880 | 897076 | WFD DV OPENING PLUG NOT BUMPED AFTER DISPLACMENT. | TF | DV |  | 05/28/2022 | SND-3002 | 24 | DMMM-601
2452 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SSA-101 | Hrs | QTIF-785
2453 | FOT | SPS | 1 | 28 May 1500 - 1600 | 14885 | 897069 | SPS TROUBLE SHOOT WITH MWD TOOLS. | BHA | MWD |  | 05/28/2022 | SSA-101 | 1 | QTIF-785
2454 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SSA-5859 | Hrs | HWYH-1222
2455 | GRF | RIG | 5 | 28 May 1630 - 2130 | 3857 | 897075 | WHILE BREAK OUT CONNECTION HAD ONE DIES FROM TDS GRABBER DROPPED DOWN. | UPRA | TDS |  | 05/28/2022 | SSA-5859 | 5 | HWYH-1222
2456 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SSA-5969 | Hrs | UTMN-3021
2457 | FOT | HLH | 39 | 25 May 0530 - 1200 | 12564 | 896963 | HALLIBURTON 9-5/8" XTREMEGRIP LINER HANGER FAILED TO SET | TF | HGRL |  | 05/28/2022 | SSA-5969 | 7 | UTMN-3021
2458 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/28/2022 | SSA-5974 | Hrs | HRDH-1970
2459 | CWEL | ARM | 858.5 | 22 Apr 0500 - 0500 | 11685 | 895858 | BOREHOLE STABILITY PROBLEM BELOW SHOE, RIH W/ CMT STINGER AND CMT PLUG PROBLEMATIC INTERVAL TO STABILIZE THE HOLE- NOT ABLE TO CMT PLUG. DECISION MADE TO MILL 7" TOL AND SIDE TRACK THE WELL. | BHS | NA |  | 05/28/2022 | SSA-5974 | 23.5 | HRDH-1970
2460 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADC-31 | Hrs | SDGM-1181
2461 | FOT | RIG | 5 | 28 May 0030 - 2100 | 10520 | 897117 | STAND PIPE JUMPER HOUSE LEAKS. | TF | SFLN |  | 05/29/2022 | ADC-31 | 3 | SDGM-1181
2462 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADC-43L | Hrs | UTMN-3118
2463 | FRFM | TK3 | 134.5 | 24 May 0715 - 0500 | 6420 | 896955 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 05/29/2022 | ADC-43L | 24 | UTMN-3118
2464 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADC-56L | Hrs | UTMN-2330
2465 | FOT | SDM | 14.5 | 29 May 1200 - 0500 | 19362 | 897107 | LOST LWD-ADN POROSITY SIGNAL. | BHA | LWD |  | 05/29/2022 | ADC-56L | 14.5 | UTMN-2330
2466 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADC-62L | Hrs | ANDR-745
2467 | UNKN | RIG | 15 | 29 May 1400 - 0500 | 9094 | 897160 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS. | HSEI | NA |  | 05/29/2022 | ADC-62L | 15 | ANDR-745
2468 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADES-13 | Hrs | HRDH-157
2469 | FOT | BHI | 47.5 | 27 May 2000 - 0500 | 6321 | 897074 | LOW ROP BECAUSE OF BAKER RSS FAILING TO BUILD UP AS PER PLAN. | BHA | RSS |  | 05/29/2022 | ADES-13 | 24 | HRDH-157
2470 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADES-174 | Hrs | GHZL-88
2471 | XTTE | BCR | 3 | 20 May 2100 - 0115 | 12280 | 896710 | OBSERVED HYDRAULIC FAILURE OF BH POWER TONGUE. | TF | CTRQ |  | 05/29/2022 | ADES-174 | 2 | GHZL-88
2472 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADM-337 | Hrs | MRJN-900
2473 | FOT | RIG | 1 | 29 May 0400 - 0500 | 13019 | 897157 | C/OUT IBOP ON TOP DRIVE ( FAILED PRIOR ON BOP TEST) | RR | TDS |  | 05/29/2022 | ADM-337 | 1 | MRJN-900
2474 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADM-510 | Hrs | ABSF-230
2475 | OTH | RIG | 11 | 29 May 1800 - 0500 | 0 | 897109 | SET RTTS AND CHANGE LOWER PIPE RAMS DUE TO EXPIRING COC | UPRA | NA |  | 05/29/2022 | ADM-510 | 11 | ABSF-230
2476 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADM-511 | Hrs | MRJN-799
2477 | FOT | BAW | 7.5 | 29 May 0600 - 1330 | 12375 | 897123 | BAKER WL LATCH INTO LOGGING TOOL STRING, TRY TO PERFORM SURFACE TEST, HAD BAD COMMUNICATION, TROUBLE SHOOTING BY CHANGING OUT EACH TOOL WITH THE BACKUP TOOL TILL CHANGE OUT THE SAMPLE VIEW TOOL, HAD GOOD COMMUNICATION. | TF | WLT |  | 05/29/2022 | ADM-511 | 7.5 | MRJN-799
2478 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ADM-657 | Hrs | ZULF-72
2479 | LHFL | RIG | 4 | 29 May 0100 - 0500 | 0 | 897128 | DIVERTER SYSTEM FLOW LINE SEAL LEAKING. | RR | HSYS |  | 05/29/2022 | ADM-657 | 4 | ZULF-72
2480 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ARO-4001 | Hrs | MRJN-538
2481 | FOT | RIG | .5 | 29 May 2200 - 2230 | 3105 | 897126 | TROUBLE SHOOT CAT WALK MACHINE DUE TO ELECTRICAL ISSUES. | RR | CATW |  | 05/29/2022 | ARO-4001 | .5 | MRJN-538
2482 | STBH | ARM | 1.5 | 29 May 1000 - 1130 | 12791 | 897124 | WORK ON STUCK- CTC STUCK AT THE HIGH GR INTERVAL (12,786'-12,791' MD) | STUK | BHA |  | 05/29/2022 | BCTD-3 | 1.5 | HWYH-1029
2483 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | BCTD-3 | Hrs | HWYH-1029
2484 | STOP | ARM | 4.5 | 29 May 1130 - 1600 | 12870 | 897122 | WAITING ON APPROVED DIRECTIONAL PLAN FOR L-0-1-1-2-1 FROM GRMD. | WO | NA |  | 05/29/2022 | BCTD-3 | 4.5 | HWYH-1029
2485 | STBH | ARM | 1.5 | 29 May 1000 - 1130 | 12791 | 897124 | WORK ON STUCK- CTC STUCK AT THE HIGH GR INTERVAL (12,786'-12,791' MD) | STUK | BHA |  | 05/29/2022 | BCTD-3 | 1.5 | HWYH-1029
2486 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | CG-1 | Hrs | ZULF-1208
2487 | FOT | RIG | .75 | 29 May 2115 - 2200 | 10219 | 897159 | RIG ENGINE GENERATOR #5 SHUT DOWN DUE TO COUPLING FAILURE BETWEEN GENERATORS CAUSING OVERLOAD TRIPPING BREAKERS. | RR | PSYS |  | 05/29/2022 | CG-1 | .75 | ZULF-1208
2488 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | DPS-74 | Hrs | NJYN-54
2489 | FOT | BLH | 1049.25 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/29/2022 | DPS-74 | 24 | NJYN-54
2490 | 7153 | 6841 | LOG | E | 2844 | WLT | POSITION STRING @ 6,841 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL.- PUMP OUT STATION #10 @ 6,841 FT (AD3A) TOT 1.47 BBL ( OIL: 0 WATER: 1.47 BBLS ).- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- TOT 7.1 BBL ( OIL: 0.86 WATER: 6.24 BBLS ).- COLLECTED ONE WATER SAMPLE (500 CC) IN CYCLE#2.- MAX STATIONARY TIME IS 4 HRS.- TOT MEASURED HYDROSTATIC REDUCTION = 14 PSI. | 7153 | 6841 | BAW | 05/29/2022 | DQ-50L | LOG | HRDH-582
2491 | 7153 | 6908 | LOG | E | 2844 | WLT | POSITION STRING @ 6,908 FT, ACTIVATE XL PROBE & CONFIRM GOOD SEAL.- PUMP OUT STATION #11 @ 6,908 FT (3B21) TOT 1.26 BBL ( OIL: 0.13 WATER: 1.13 BBLS ).- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- TOT 7.66 BBL ( OIL: 0.99 WATER: 6.67 BBLS ).- COLLECTED ONE OIL/WATER SAMPLE (500 CC) .- MAX STATIONARY TIME IS 4 HRS.- TOT MEASURED HYDROSTATIC REDUCTION = 17 PSI.- 6,908', 3B21,FM.PRESS = 3,451 PSI, EQ.MW=72PCF, O.P=472 PSI. | 7153 | 6908 | BAW | 05/29/2022 | DQ-50L | LOG | HRDH-582
2492 | 7153 | 6723 | LOG | E | 2844 | WLT | POSITION STRING @ 6,723 FT, ACTIVATE STRADDLE PKR- TRY PUMP OUT STATION #12 @ 6,723 FT (ABD1), FOUND LOW MOBILITY ( 0.066 MD/CP), SCAN UP/DOWN FOR GOOD MOBILITY, NEGATIVE.- STATION ABORTED DUE TO LOW MOBILITY.- MONITORING WELL ON TRIP TANK- WELL STATIC.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- TOT 7.66 BBL ( OIL: 0.99 WATER: 6.67 BBLS ).- MAX STATIONARY TIME IS 4 HRS.- TOT MEASURED HYDROSTATIC REDUCTION = 17 PSI.- 6,723', ABD1,FM.PRESS = 3,249 PSI, EQ.MW=70PCF, O.P=566 PSI.- TIME SINCE LAST CIRC = 42 HRS. | 7153 | 6723 | BAW | 05/29/2022 | DQ-50L | LOG | HRDH-582
2493 | 7153 | 7080 | ST | E | 2844 | STDP | RIH WITH WL SAMPLING TOOLS & POSITION CIRCULATION PORTS BELOW DEEPEST SAMPLE POINT @ 7,080 FT.- MONITORING WELL ON TRIP TANK- WELL STATIC. | 7153 | 6723 | RIG | 05/29/2022 | DQ-50L | LOG | HRDH-582
2494 | 7153 |  | CIRC | E | 2844 | MPMP | HPJSM & CIRCULATE FORMATION FLUIDS ( OIL: 0.99 WATER: 6.67 BBLS ). TO 3,000 FT INSIDE 9-5/8" CSG .- CIRC. FR 80:140 GPM, CIRC. PRESSURE 400 PSI.- RECIPROCATE THE STRG | 7153 |  | RIG | 05/29/2022 | DQ-50L | LOG | HRDH-582
2495 | 7153 |  | OTH | E | 2844 | NA | FLOW CHECK - WELL STATIC. | 7153 |  | RIG | 05/29/2022 | DQ-50L | LOG | HRDH-582
2496 | 7153 | 3690 | ST | E | 2844 | STDP | POOH W/ WL RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DP STDS F/ 7,080 FT TO 3,690 FT INSIDE 9-5/8" CSG AT CONTROLLED SPEED (3 MIN SLIPS TO SLIPS) - CSES ON SURFACE.- MONITOR WELL ON TRIP TANK & TRIP SHEET- WELL STATIC.- HOLE IN GOOD CONDITION. | 7153 | 7080 | RIG | 05/29/2022 | DQ-50L | LOG | HRDH-582
2497 | 7153 |  | OTH | E | 2844 | NA | BHI UNLATCH CABLE HEAD & POOH T/ SURFACE. L/D SES & R/D SHEAVES.- MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7153 |  | BAW | 05/29/2022 | DQ-50L | LOG | HRDH-582
2498 | 7153 |  | CIRC | E | 2844 | MPMP | HPJSM & DISCUSS JSA W/ ALL PARTIES INVOLVED PRIOR TO PERFORM CIRCULATION OPERATIONS.CIRCULATE BTMS UP FORMATION FLUIDS (OIL: 0.99 WATER: 6.67 BBLS ) & CONDITION MUD IN & OUT 81 PCF THROUGH FULLY OPEN CHOKE TO MGS W/ ANNULAR PREVENTER CLOSED.- CIRC. FR 250 GPM, CIRC. PRESSURE 330 PSI. | 7153 |  | RIG | 05/29/2022 | DQ-50L | LOG | HRDH-582
2499 | 7153 |  | OTH | E | 2844 | NA | FLOW CHECK, WELL STATIC. | 7153 |  | RIG | 05/29/2022 | DQ-50L | LOG | HRDH-582
2500 | 7153 | 180 | ST | E | 2844 | STDP | POOH WITH BHI RUN#4 LOGGING TOOLS (GR-FTEX-RCX) ON 4" DP STDS F/ 3,690 FT TO SURFACE.- POOH @ CONTROLLED SPEED (1:2 MIN SLIP TO SLIPS).- FLOW CHECK AT TOP OF BHA, WELL STATIC. | 7153 | 3690 | RIG | 05/29/2022 | DQ-50L | LOG | HRDH-582
2501 | 7153 |  | OTH | E | 2844 | NA | HPJSM, L/D BHI RUN#4 LOGGING TOOLS (GR-FTEX-RCX).. ONGOING.- MONITOR WELL THRU TRIP TANK, STATIC. | 7153 |  | BAW | 05/29/2022 | DQ-50L | LOG | HRDH-582
2502 | 188 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 24 | 2844 | 22 May 0900 | 05/29/2022 | DQ-50L | Type | HRDH-582
2503
2504
2505 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ENSCO-76 | Hrs | MRJN-851
2506 | HERR | RIG | 7.75 | 26 May 2130 - 1330 | 10450 | 896933 | WHILE PERFORMING 2ND STAGE CEMENT JOB CENTIFUGAL PUMP LOST PRIME. UN ABLE TO DELIVER MIX WATER TO CEMENT UNIT. | JF | CSYS |  | 05/29/2022 | ENSCO-76 | 5.75 | MRJN-851
2507 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | HI-9 | Hrs | QTIF-557
2508 | UNKN | RIG | 19.5 | 28 May 1430 - 1000 | 17717 | 897099 | SUSPEND RIG OPERATIONS FOR CRANE INCIDENT INVESTIGATION | HSEI | NA |  | 05/29/2022 | HI-9 | 5 | QTIF-557
2509 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | NA-18S | Hrs | UTMN-2334
2510 | STBH | ARM | 383 | 12 May 1300 - 0500 | 13129 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/29/2022 | NA-18S | 24 | UTMN-2334
2511 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | NBR-20S | Hrs | HMYM-433504
2512 | HERR | RIG | 4 | 29 May 1700 - 2100 | 7160 | 897158 | EXCESSIVE TIME TO NIPPLE UP BOP. | BOP | BOP |  | 05/29/2022 | NBR-20S | 4 | HMYM-433504
2513 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | PA-866S | Hrs | SHHB-2
2514 | FOT | RIG | 59 | 26 May 0015 - 1400 | 9870 | 897078 | OBSERVED VFD FAULT ON CONSOLE & FROM DRAWWORKS B MOTOR. 3 GENERATORS KNOCKED OFFLINE. ELECTRICIAN CHECKED TRACTION MOTOR AND CONFIRMS GROUND FAULT AND BURN OUT OF DRAWWORKS B MOTOR. ATTEMPT TO PULL OUT OF HOLE WITH DRAWWORKS A MOTOR AND OBSERVE OVERHEATING FROM DYNAMIC BREAKER MODULES #2 & #3 IN VFD HOUSE. | RR | DWKS |  | 05/29/2022 | PA-866S | 9 | SHHB-2
2515 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SINO-27N | Hrs | HWYH-466
2516 | STBH | ARM | 200.5 | 21 May 1630 - 0500 | 7515 | 896822 | STRING GOT STUCK. | STUK | RBHA |  | 05/29/2022 | SINO-27N | 24 | HWYH-466
2517 | 9892 | 5610 | TI | N | 2904 | STDP | CONTINUE RIH WITH MPAS PACKERS ASSEMBLY ON 4" DP AT CONTROLLED SPEED 2200 FT TO 5610 FT MD. ** DRIFT EVERY STAND .** FILL UP STRING EVERY 10 STDS | 9892 | 2200 | RIG | 05/29/2022 | SINO-32L | PA | SHYB-570
2518 | 9892 |  | OTH | N | 2904 | NA | GOT OBSTRUCTION 10 KBLS @ 5610 FT CIRCULATE 160 GPM 265 PSI WORKSTRING UP / DOWN TO CLEAN HOLE.WASHDOWN TO 5616 FT UNABLE TO GO DOWN WITH 10 KLBS SLACKOFF. | 9892 |  | RIG | 05/29/2022 | SINO-32L | PA | SHYB-570
2519 | 9892 |  | CIRC | N | 2904 | MPMP | PUMP 30 BBLS LO VIS / HI VIS EACH CIRCULATE OUT *FLOW CHECK WELL STATIC | 9892 |  | RIG | 05/29/2022 | SINO-32L | PA | SHYB-570
2520 | 9892 | 3721 | TO | N | 2904 | STDP | POOH MPAS PACKERS ASSEMBLY WITH PUMP OUT 150 GPM TO TOL@3721 FT. *FLOW CHECK WELL STATIC | 9892 | 5610 | RIG | 05/29/2022 | SINO-32L | PA | SHYB-570
2521 | 9892 | 217 | TO | N | 2904 | SPDP | CONTINUE POOH MPAS PACKERS ASSEMBLY TO SURFACEMONITOR THE WELL ON TRIP TANK WELL STATICFLOW CHECK WELL STATIC | 9892 | 3721 | RIG | 05/29/2022 | SINO-32L | PA | SHYB-570
2522 | 9892 |  | HT | N | 2904 | BHA | HPJSM, L/D MPAS PACKERS ASSEMBLY | 9892 |  | RIG | 05/29/2022 | SINO-32L | PA | SHYB-570
2523 | 9892 |  | HT | N |  | BHA | P/U & M/U CLEAN OUT ASSEMBLY6 1/8'' WELDED TCI ( OPEN NOZZLES), 6 1/8'' NB RMR ( W/ FLOAT) , 1JT DC 4 3/4'', 6 1/8'' ST.RMR; 1STD DP, 1STD HWDP, 4 3/4'' JAR, 2 JTS HWDP, 64 JTS 4" DP ; ST MILL , 3 STDS DP; JUNK BASKET , DP, HWDP , DP . | 9892 |  | RIG | 05/29/2022 | SINO-32L | CT | SHYB-570
2524 | 9892 | 5300 | TI | N |  | STDP | RIH WITH CLEAN OUT ASSEMBLY ON 4" DPS TO 5300 FTMONITOR THE WELL ON TRIP TANK WELL STATIC | 9892 | 0 | RIG | 05/29/2022 | SINO-32L | CT | SHYB-570
2525 | 9892 | 8640 | RW | N |  | BIT | WASH DOWN FROM 5300 TO 8640 FT WITH 220 GPM ,450PSI** WORK STRING UP / DOWN THROUGH OBSTRUCTION AT 5613 FT , CONTINUE WASH DOWN ** DYNAMIC LOSSES INCREASE GRADUALLY TO 70 BPH AFTER CLEANING 5613 FT.** GOT LCM ON SHALE SHAKERS WHILE WASH DOWN FROM 5600 FT | 9892 | 5300 | RIG | 05/29/2022 | SINO-32L | CT | SHYB-570
2526 | 18.25 | OOS | Category | DOOS ID | RZIT | Out of Scope Summary | MPAS PLUG AND ABANDONMENT JOB | 13.75 | 2904 | 28 May 0030 | 05/29/2022 | SINO-32L | Type | SHYB-570
2527
2528
2529 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SINO-7N | Hrs | FDHL-3
2530 | FOT | HWP | 8 | 29 May 2100 - 0500 | 9870 | 897139 | AFTER HALL W/L SET STRADDLE PKR AT SAMPLE POINT#1 @9870' (STRADDLE PKR DEPTH), FOUND THAT THE DOWN HOLE SENSOR (FLID) WHICH RESPONSIBLE FOR FLUID IDENTIFICATION IS NOT RESPONDING AND FAILED, HALL TROUBLE SHOOTING TO GET RESPONSE FROM SENSOR BUT NO SUCCESS. | TF | WLT |  | 05/29/2022 | SINO-7N | 8 | FDHL-3
2531 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SND-2001 | Hrs | UTMN-2329
2532 | FOT | WUD | 2.75 | 29 May 1900 - 2145 | 12903 | 897108 | RCD ELEMENT FAILURE | TF | MPD |  | 05/29/2022 | SND-2001 | 2.75 | UTMN-2329
2533 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SND-2002 | Hrs | WAQR-23
2534 | FOT | HLH | 70.5 | 26 May 2000 - 0500 | 10330 | 897098 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES. | TF | HGRL |  | 05/29/2022 | SND-2002 | 14 | WAQR-23
2535 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SND-2006 | Hrs | UTMN-3165
2536 | FOT | SPS | 11 | 29 May 1800 - 0500 | 7955 | 897138 | RSS ICRUISE FAILURE | BHA | RSS |  | 05/29/2022 | SND-2006 | 11 | UTMN-3165
2537 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SND-3002 | Hrs | DMMM-601
2538 | FOT | WDV | 86 | 26 May 1500 - 0500 | 3880 | 897076 | WFD DV OPENING PLUG NOT BUMPED AFTER DISPLACMENT. | TF | DV |  | 05/29/2022 | SND-3002 | 24 | DMMM-601
2539 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SP-110 | Hrs | BRRI-562
2540 | FOT | RIG | 5 | 29 May 1930 - 0030 | 13921 | 897125 | REPLACED KELLY HOSE, DUE TO PIN HOLE LEAK - 15.5 INCHES FROM TOP CONNECTION , JUST BELOW FACTORY CRIMP. | RR | CSYS |  | 05/29/2022 | SP-110 | 5 | BRRI-562
2541 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SP-120 | Hrs | MNIF-188
2542 | FOT | RIG | 16 | 29 May 1300 - 0500 | 17775 | 897105 | POOH TO CASING SHOE TO FIX CONNECTION LEAK IN THE STAND PIPE MANIFOLD. | RR | CSYS |  | 05/29/2022 | SP-120 | 16 | MNIF-188
2543 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SP-306 | Hrs | MNIF-196
2544 | CFFM | ARM | 135.75 | 24 May 0800 - 2345 | 7520 | 897104 | WHILE RIH 9 5/8" CSG W/ TOTAL LOSS SITUATION, OBSERVED LOSSES STOPPED. FLOW CHECK-WELL STATIC. EXPECTED FORMATION PACKED OFF ABOVE LOSS ZONE. | BHS | NA |  | 05/29/2022 | SP-306 | 18.75 | MNIF-196
2545 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SSA-202 | Hrs | QTIF-500
2546 | FOT | SCT | 10.5 | 29 May 1830 - 0500 | 2600 | 897106 | SLB 2-7/8" COILED TUBING PTC-G MLT ASSY PLUGGED WHILE RIH AT 2600' MD. | BHA | CTAC |  | 05/29/2022 | SSA-202 | 10.5 | QTIF-500
2547 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SSA-5859 | Hrs | HWYH-1222
2548 | XTTE | FMC | 1 | 29 May 0200 - 0300 | 5620 | 897140 | EXTRA TIME IN MAKE UP LANING JOINT WITH HGR ASSY. | TF | CTRQ |  | 05/29/2022 | SSA-5859 | 1 | HWYH-1222
2549 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | SSA-5962 | Hrs | HRDH-2230
2550 | WCC5 | ARM | 24 | 29 May 0500 - 0500 | 14186 | 897156 | WELL FLOWING WHILE DRILLING | WCNT | NA |  | 05/29/2022 | SSA-5962 | 24 | HRDH-2230
2551 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/29/2022 | ZPEC-1 | Hrs | GZLN-801
2552 | FOT | RIG | 3.5 | 29 May 1130 - 1500 | 90 | 897137 | PWOER TONG MALFUNCTION HYDROLIC OIL LEAK. | RR | HSYS |  | 05/29/2022 | ZPEC-1 | 3.5 | GZLN-801
2553 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADC-17 | Hrs | ZULF-1215
2554 | FOT | RIG | .75 | 30 May 1015 - 1100 | 0 | 897130 | HAD LEAK ON TEST PUMP WHILE TESTING STANDPIPE | RR | HSYS |  | 05/30/2022 | ADC-17 | .75 | ZULF-1215
2555 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADC-31 | Hrs | SDGM-1181
2556 | IDPR | SPS | 1 | 30 May 2330 - 0030 | 10600 | 897179 | ECCESSIVE DIRECTIONAL TOOL NOISE | DD | RSS |  | 05/30/2022 | ADC-31 | 1 | SDGM-1181
2557 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADC-34 | Hrs | UTMN-2316
2558 | FOT | RIG | 9.5 | 30 May 0900 - 2000 | 12416 | 897129 | KELLY HOSE LEAKING, | RR | CSYS |  | 05/30/2022 | ADC-34 | 9.5 | UTMN-2316
2559 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADC-43L | Hrs | UTMN-3118
2560 | FRFM | TK3 | 157.75 | 24 May 0715 - 0500 | 6420 | 896955 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 05/30/2022 | ADC-43L | 23.25 | UTMN-3118
2561 | 10376 | 398 | TO | N |  | STDP | POOH 7" CLEAN OUT ASSY F/6428 FT TO TOP OF BHA @ 398 FT.- MONITORED WELL ON TRIP TANK & TRIP SHEET. | 10376 | 6428 | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2562 | 10376 |  | HT | N |  | BHA | FLOW CHECK - WELL STATIC. CONT POOH AND L/D 7" CLEAN OUT BHA.- 6 1/8" PDC BIT (1-1-WT-A-X-I-NO-TD).- WELL MONITORED ON TRIP TANK.- RECOVERED 5 KG OF FINE METAL SHAVINGS FROM MAGNETS. | 10376 |  | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2563 | 10376 |  | RR | N |  | TDS | SERVICED TDS. CLEANED AND CLEARED RIG FLOOR | 10376 |  | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2564 | 10376 |  | HT | N | 2924 | BHA | P/U AND M/U 6-1/8" REAMING BHA AND RIH TO 390 FT.- MONITORED WELL ON TRIP TANK. | 10376 |  | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2565 | 10376 | 1715 | TI | N | 2924 | STDP | CONTD RIH 6-1/8" REAMING BHA ON 4" DP STDS F/390 FT T/1,715 FT. | 10376 | 390 | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2566 | 10376 |  | SDR1 | N |  | NA | CONDUCTED STAND DOWN MEETING WITH ALL RIG CREWS AND DISCUSSED ADC-62 INCIDENT. RISK ASSESSMENT FOR CRITICAL JOBS, LINE OF FIRE AND IMPORTANCE OF SWA. | 10376 |  | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2567 | 10376 | 7443 | TI | N | 2924 | STDP | CONT RIH 6-1/8" REAMING BHA ON 4" DP STDS F/1,715 FT TO 7" LINER SHOE @ 7,443 FT.- FILL UP STRING EVERY 20 STD.- SLOW DOWN AT 7" TOL- WELL MONITORED ON TRIP TANK. | 10376 | 1715 | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2568 | 10376 | 10376 | RW | N | 2924 | BIT | REAM DOWN OPEN HOLE F/ 7443 FT TO TD @ 10,376 FT- WOB: 0-1 KLBS, RPM: 120, TQ: 3-8 K.FT-LBS, FLOW RATE: 300 GPM & PRESS: 1650 PSI. | 10376 | 7443 | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2569 | 10376 |  | CIRC | N | 2924 | MPMP | SWEPT HOLE WITH TANDEM 30/30 BBLS LO/HI VIS WEIGHTED PILL & CIRC HOLE UNTIL SHAKERS CLEAN.- FR 300 GPM, SPP 1550 PSI.- FLOW CHECK , WELL STATIC. | 10376 |  | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2570 | 10376 | 9466 | ST | N | 2924 | STDP | POOH & WIPER TRIP 6-1/8" REAMING BHA ON ELEVATOR F/ 10,376 FT TO 9,466 FT. ON GOING ART.- FLOW CHECK AFTER 10 STDS PULLED - WELL STATIC. | 10376 | 10376 | RIG | 05/30/2022 | ADC-53L | CT | UTMN-4069
2571 | 18.25 | OOS | Category | DOOS ID | HCRM | Out of Scope Summary | REAM 6-1/8" OPEN HOLE SECTION F/7443 FT TO 10,376 FT (TD) PRIOR RUNNING LOWER COMPLETION. | 18.25 | 2924 | 30 May 0145 | 05/30/2022 | ADC-53L | Type | UTMN-4069
2572
2573
2574 | STBH | TK3 | 19.5 | 30 May 0715 - 0245 | 14549 | 897177 | STRING STUCK AT 14,549'. | STUK | BHA |  | 05/30/2022 | ADC-56L | 19.5 | UTMN-2330
2575 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADC-56L | Hrs | UTMN-2330
2576 | FOT | SDM | 19 | 29 May 1200 - 0500 | 19362 | 897107 | LOST LWD-ADN POROSITY SIGNAL. | BHA | LWD |  | 05/30/2022 | ADC-56L | 4.5 | UTMN-2330
2577 | STBH | TK3 | 19.5 | 30 May 0715 - 0245 | 14549 | 897177 | STRING STUCK AT 14,549'. | STUK | BHA |  | 05/30/2022 | ADC-56L | 19.5 | UTMN-2330
2578 | 16580 |  | PJSM | N |  | BOP | HPJSM PRIOR TO P/T BOP. CLEAR RIG FLOOR. | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2579 | 16580 |  | RTRV | N |  | WBSH | RETRIEVED WEAR BUSHING. | 16580 |  | RIG | 05/30/2022 | ADC-57L | WH | FDHL-158
2580 | 16580 |  | OTH | N |  | BOP | P/U & M/U 11" TEST ASSY. RIH & LANDED TEST PLUG ONTO THS. | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2581 | 16580 |  | OTH | N |  | BOP | FUNCTION TESTED BOP ELEMENTS AND FLUSHED BOP, CHOKE LINE, CHOKE MANIFOLD & MGS W/ WATER. | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2582 | 16580 |  | BOPT | N |  | BOP | P/T 13-5/8'' 5K BOP: TEST #1: ANNULAR (ON 4" DP), 4" FOSV, MUD PUMP KILL LINE MV, CMT UNIT KILL LINE MV, CHOKE LINE MANUAL 300/3500 PSI 10 MIN EACH. TEST #2: VBR(ON 4" DP), TDS MANUAL IBOP, CHOKE LINE HCR, EKL MANUAL #1, KL MANUAL 300/4250 PSI 10 MIN EACH. TEST #3: VBR(ON 4" DP), TDS HYD IBOP, KL HCR, EKL HCR, CHOKE LINE MASTER VALVE 300/4250 PSI 10 MIN EACH. TEST #4: 5MASTER RAM, 5" FOSV, EKL MANUAL #2 300/4250 PSI 10 MIN EACH. UNSCREW FROM TP AND CONNECTED TEST UNIT TO CHOKE MANIFOLD. TEST #5: BLIND/SHEAR RAMS, NRV 1&2, CHOKE MANIFOLD VALVES NO. 13, 14 & 15 300/4250 PSI 10 MIN EACH | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2583 | 16580 |  | OTH | N |  | BOP | RETRIEVE TEST PLUG ASSEMBLY AND RIH W/ CUP TESTER ASSEMBLY | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2584 | 16580 |  | BOPT | N |  | BOP | P/T 13-5/8'' 5K BOP. TEST #6: ANNULAR(ON 5" DP), SOV, KL HCR, EKL HCR 300/3500 PSI 10 MIN EACH. TEST #7: VBR(ON 5" DP), SOV, KL HCR, EKL HCR 300/4250 PSI 10 MIN EACH | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2585 | 16580 |  | BOP | N |  | BOP | PERFORMED ACCUMULATOR DRAW DOWN TEST: - RECORD FINAL PRESSURE: ACCUM 2450 PSI. - RECHARGED PRESSURE FROM 1200 PSI TO 3000 PSI IN 3 MIN 54 SEC | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2586 | 16580 |  | BOPT | N |  | BOP | P/T PRIMARY KILL LINE AND EMERGENCY KILL LINE @ 300/ 4250 PSI 10 MIN | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2587 | 16580 |  | OTH | N |  | BOP | POOH & L/D CUP TESTER ASSEMBLY. | 16580 |  | RIG | 05/30/2022 | ADC-57L | BOP | FDHL-158
2588 | 16580 |  | STIM | E | 2864 | CTU | N/D BELL NIPPLE | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2589 | 16580 |  | STIM | E | 2864 | CTU | HPJSM PRIOR TO RIG UP SLB COIL TUBING. DISCUSS THE RISK AND HAZARD. REVIEW THE JSA. | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2590 | 16580 |  | STIM | E | 2864 | CTU | R/U ADAPTOR FLANGE, GATE VALVE & RISER ABOVE RIG BOP TO INSTALL PRESSURE CONTROL EQUIPMENT. R/U CT BOP & FUNCTION TEST.- CONTINUOSLY FILL UP HOLE FROM TRIP TANK 2.0 BPM. | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2591 | 16580 |  | STIM | E | 2864 | CTU | HPJSM, DISCUSSED RISK ASSESSMENT. LIFT CT INJECTOR & HANG IT WITH TOP DRIVE. | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2592 | 16580 |  | STIM | E | 2864 | CTU | LIFT CT INJECTOR & HANG IT WITH TOP DRIVE. RIG UP RISER PIPE BELOW COIL TBG INJECTOR.- CONTINUOUSLY PUMP 70 PCF VISCOUS BRINE INTO ANNULUS AT 2 BPM FROM TRIP TANK, WELL ON TOTAL LOSSES. | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2593 | 16580 |  | STIM | E | 2864 | CTU | M/U CT BHA (MHA + STRAIGHT BAR + NOZZ). STAB THE COIL TBG INJECTOR ON TOP OF HYDRA CONN. | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2594 | 16580 |  | STIM | E | 2864 | CTU | P/T CT EQUIPMENT AS BELOW: - P/T ALL RISERS, PCE CONNECTIONS, STRIPPERS AGAINST GATE VALVE TO 300/2500 PSI. P/T DOUBLE FLAPPER CHECK VALVE, RISER STACK AGAINST GATE VALVE TO 2500 PSI. - P/T ALL RISERS, PCE CONNECTIONS, ADAPTOR FLANGE CONNECTION TO RIG BOP AGAINST RIG BOP BLIND RAM VALVE TO 300/1500 PSI. | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2595 | 16580 |  | STIM | E | 2864 | CTU | DISPLACE THE COILED TUBING FROM FRESH WATER TO LUBRICATED BRINE (82 BBLS).- CONTINUOUSLY PUMP 70 PCF VISCOUS BRINE INTO ANNULUS AT 2 BPM FROM TRIP TANK, WELL ON TOTAL LOSSES | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2596 | 16580 |  | STIM | E | 2864 | CTU | RIH COILED TUBING FROM SURFACE TO 6760 FT. - CIRCULATING LUBRICATED BRINE AT 0.5 BPM WITH CHOKE OPEN. - TAKE CARE PASSING THROUGH BOP & WELL HEAD- RIH SPEED: 40 FPM.- CONTINUOUSLY PUMP 70 PCF VISCOUS BRINE INTO ANNULUS AT 2 BPM, WELL ON TOTAL LOSSES. | 16580 |  | SCT | 05/30/2022 | ADC-57L | STIM | FDHL-158
2597 | 84.75 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | STIMULATION JON FOR L-2, L-1. | 14.5 | 2864 | 24 May 0230 | 05/30/2022 | ADC-57L | Type | FDHL-158
2598
2599
2600 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADC-62L | Hrs | ANDR-745
2601 | UNKN | RIG | 39 | 29 May 1400 - 0500 | 9094 | 897160 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS. | HSEI | NA |  | 05/30/2022 | ADC-62L | 24 | ANDR-745
2602 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADES-13 | Hrs | HRDH-157
2603 | FOT | BHI | 62 | 27 May 2000 - 1930 | 6321 | 897074 | LOW ROP BECAUSE OF BAKER RSS FAILING TO BUILD UP AS PER PLAN. | BHA | RSS |  | 05/30/2022 | ADES-13 | 14.5 | HRDH-157
2604 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADM-337 | Hrs | MRJN-900
2605 | FOT | RIG | 6.25 | 29 May 0400 - 1015 | 13019 | 897157 | C/OUT IBOP ON TOP DRIVE ( FAILED PRIOR ON BOP TEST) | RR | TDS |  | 05/30/2022 | ADM-337 | 5.25 | MRJN-900
2606 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADM-510 | Hrs | ABSF-230
2607 | XTTE | RIG | 16 | 29 May 1800 - 1000 | 0 | 897109 | SET RTTS AND CHANGE LOWER PIPE RAMS DUE TO EXPIRING COC | TF | BOP |  | 05/30/2022 | ADM-510 | 5 | ABSF-230
2608 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ADM-657 | Hrs | ZULF-72
2609 | LHFL | RIG | 7.5 | 29 May 0100 - 0830 | 0 | 897128 | DIVERTER SYSTEM FLOW LINE SEAL LEAKING. | RR | HSYS |  | 05/30/2022 | ADM-657 | 3.5 | ZULF-72
2610 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | DPS-74 | Hrs | NJYN-54
2611 | FOT | BLH | 1073.25 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/30/2022 | DPS-74 | 24 | NJYN-54
2612 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | DQ-48 | Hrs | KHRS-1420
2613 | STBH | TK2 | 10.75 | 30 May 1730 - 0415 | 9377 | 897178 | POOH W/ 12-1/4"MRSS BHA FOR WIPER TRIP F/ 9400' T/ 9377', GOT STRING STUCK. WORK ON STUCK BY TRYING TO JARRING UP/DOWN WITHOUT SUCCESS, PUMP ACID PILL - GOT FREE | STUK | BHA |  | 05/30/2022 | DQ-48 | 10.75 | KHRS-1420
2614 | 7153 |  | OTH | E | 2844 | NA | CONT' L/D BHI RUN#4 LOGGING TOOLS (GR-FTEX-RCX).- MONITOR WELL THRU TRIP TANK, STATIC. | 7153 |  | BAW | 05/30/2022 | DQ-50L | LOG | HRDH-582
2615 | 7153 | 3845 | TI | N |  | STDP | RIH W/ 4" OEDP STRING TILL 9-5/8" CSG SHOE @ 3,845'.- MONITORE HOLE ON TRIP TANK, HOLE STATIC. | 7153 | 0 | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2616 | 7153 |  | CIRC | N |  | MPMP | BREAK CIRC AT 9-5/8" SHOE | 7153 |  | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2617 | 7153 | 7153 | ST | N |  | STDP | RIH WITH 4" OEDP STRING T/ BOTTOM @7,153'.- MONITORE HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION.- TAG BTM WITH 5 KLB. | 7153 | 3845 | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2618 | 7153 |  | CIRC | N |  | MPMP | POOH TO 7,143', CIRC 2 TIMES BTM UP & CONDITION MUD, [ CONFIRM MW IN & OUT = 81 PCF ].- CIRC WITH 500 GPM, 1600 PSI. | 7153 |  | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2619 | 7153 |  | OTH | N |  | NA | HPJSM, R/U BKR CEMENT SURFACE LINES & P/T SAME TO 3,000 PSI. | 7153 |  | BCM | 05/30/2022 | DQ-50L | PA | HRDH-582
2620 | 7153 | 6493 | CMP | N |  | OEDP | HPJSM, PERFORMED 1ST P&A CEMENT PLUG [ 7,143' - 6,493' ] 650 FT TO ISOLATE ARAB D FORMATION AS FOLLOW :-- CEMENT UNIT PUMPED 50 BBLS (99 PCF ) SPACER AHEAD.- 52 BBLS ( 118 PCF ) BATCH MIXED CEMENT SLURRY & 9.5 BBLS ( 99 PCF ) SPACER BEHIND. - DISPLACE SAME WITH 54 BBBLS 81 PCF WBM, [ 6 BBL UNDERDISPLACEMENT ].- CHECK FOR BACK FLOW, NO FLOW BACK, PLUG BALANCED.- NO LOSSES DURING CEMENT JOB. | 7153 | 7143 | BCM | 05/30/2022 | DQ-50L | PA | HRDH-582
2621 | 7153 | 6393 | ST | N |  | STDP | POOH TO 6,393 FT [ BTM DEPTH OF 2ND PLUG ] @ CONTROLLED SPEED, [ 6 MIN'S PER STD ]. | 7153 | 7143 | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2622 | 7153 |  | CIRC | N |  | MPMP | CIRC. 2 X BTMS-UP & CONDITION MUD (MW IN = MW OUT = 81 PCF)- CIRC @7 BPM, 650 PSI & 10 RPM.- HAD 70 BBL OF CONTAMINATED SPACER. | 7153 |  | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2623 | 7153 | 5743 | CMP | N |  | OEDP | PERFORMED 2ND P & A CMT PLUG (6,393'-5,743') AGAINST ARAB C,B,A & HITH AS FOLLOW:- BH CMT PUMP 50 BBLS 99 PCF SPACER AHEAD @ 5 BPM .- BH CMT BATCH MIXED & PUMPED 55 BBLS 118 PCF CEMENT SLURRY.- BH CMT PUMP 9.5 BBLS 99 PCF SPACER BEHIND.- BH CMT PUMP AND DISPLACED ALL W/ 46 BBLS 81 PCF WBM MUD.- NO LOSSES RECORDED DURING CMT JOB.- NO BACK FLOW. | 7153 | 6393 | BCM | 05/30/2022 | DQ-50L | PA | HRDH-582
2624 | 7153 | 5643 | ST | N |  | STDP | POOH TO 5,643 FT [ BTM DEPTH OF 3RD PLUG ] @ CONTROLLED SPEED, [ 6 MIN'S PER STD ]. | 7153 | 6393 | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2625 | 7153 |  | CIRC | N |  | MPMP | CIRC. 2 X BTMS-UP & CONDITION MUD (MW IN = MW OUT = 81 PCF)- CIRC @7 BPM, 650 PSI & 10 RPM.- HAD 80 BBL OF CONTAMINATED SPACER. | 7153 |  | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2626 | 7153 | 4993 | CMP | N |  | OEDP | PERFORMED 3RD P & A CMT PLUG (5,643'-4,993') AGAINST SULAY AS FOLLOW:- BH CMT PUMP 50 BBLS 99 PCF SPACER AHEAD @ 5 BPM .- BH CMT BATCH MIXED & PUMPED 60 BBLS 118 PCF CEMENT SLURRY.- BH CMT PUMP 9.5 BBLS 99 PCF SPACER BEHIND.- BH CMT PUMP AND DISPLACED ALL W/ 36 BBLS 81 PCF WBM MUD.- NO LOSSES RECORDED DURING CMT JOB.- NO BACK FLOW.- CIP AT 20:15 HRS. | 7153 | 5643 | BCM | 05/30/2022 | DQ-50L | PA | HRDH-582
2627 | 7153 | 4340 | ST | N |  | STDP | WOC:1000 PSI CS AS PER UCA TEST BEFORE TAGGING THE PLUG.POOH W/ 4" OEDP @ CONTROLLED SPEED 9 STDS (6 MINS/STD) F/5,643 FT T/4,800 FT THEN 5 STDS TO 4,340 FT @ NORMAL SPEED. | 7153 | 5643 | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2628 | 7153 |  | CIRC | N |  | MPMP | WOC:DROP FOAM BALL & CIRC. 2 X BTMS-UP & CONDITION MUD (MW IN = MW OUT = 81 PCF)- CIRC @7 BPM, 540 PSI & 10 RPM.- HAD 80 BBL OF CONTAMINATED SPACER. | 7153 |  | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2629 | 7153 | 3770 | ST | N |  | STDP | WOC:POOH W/ 4" OEDP F/4,340 FT T/3,770 FT INSIDE 9-5/8" CSG SHOE. | 7153 | 4340 | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2630 | 7153 |  | WOC | N |  | SQZ | WOC:- L/D 8-1/2" NBRR, 2X 8-1/2" STRR.- L/D 19X 6-1/2" DC JTS.- P/U, M/U & RB 25X 4" STDS.- MONITOR WELL THRU TRIP TANK - WELL STATIC | 7153 |  | RIG | 05/30/2022 | DQ-50L | PA | HRDH-582
2631 | 189.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | PERFORMED 8 1/2" PILOT HOLE LOGGING. | 1.75 | 2844 | 22 May 0900 | 05/30/2022 | DQ-50L | Type | HRDH-582
2632
2633
2634 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | ENSCO-54 | Hrs | ABSF-28
2635 | FOT | BAW | 2 | 30 May 1800 - 2000 | -200 | 897184 | HAD NO RESPONSE FROM BAKER E/L LOGGING TOOL, TROUBLESHOOT (NO SUCCESS ) ,POH & CHANGE SAME . | TF | WLT |  | 05/30/2022 | ENSCO-54 | 2 | ABSF-28
2636 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | NA-18S | Hrs | UTMN-2334
2637 | STBH | ARM | 401 | 12 May 1300 - 2300 | 13129 | 896559 | RACK BACK FIRST STAND, ATTEMPT TO PULL 2ND STAND - HAD OVERPULL - HAD STUCK. | STUK | BHA |  | 05/30/2022 | NA-18S | 18 | UTMN-2334
2638 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | NBR-16S | Hrs | HMYM-433312
2639 | FOT | ITS | 3 | 30 May 0000 - 0300 | 18210 | 897186 | CUMULATIVE EXCESSIVE TIME TO RUN CASING FOR TROUBLESHOOTING AND REPLACING EQUIPMENT (JAM UNIT, HYDRAULIC SPIDER, POWER TONG AND POWER UNIT) | TF | CTRQ |  | 05/30/2022 | NBR-16S | 3 | HMYM-433312
2640 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | PA-70S | Hrs | MDRK-64
2641 | FOT | WLH | 10.5 | 30 May 1800 - 0430 | 15492 | 897183 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK. | TF | LLAP |  | 05/30/2022 | PA-70S | 10.5 | MDRK-64
2642 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SCTD-2 | Hrs | HRDH-1898
2643 | UDWL | SDM | 17 | 29 May 1800 - 1100 | 14750 | 897131 | WHILE ENTERING L 0-1-2 BY WASHING DOWN, PREMATURELY INITIATED SIDETRACK 10' ABOVE & LANDED. | DD | MMOT |  | 05/30/2022 | SCTD-2 | 6 | HRDH-1898
2644 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SINO-16 | Hrs | FDHL-606
2645 | FOT | WCT | 15 | 30 May 1330 - 0500 | 9510 | 897181 | WFD TT MECHANICAL CUTTER FAILED TO CUT TBG AT DESIRED DEPTH AT 9510' | TF | CTBG |  | 05/30/2022 | SINO-16 | 15 | FDHL-606
2646 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SINO-27N | Hrs | HWYH-466
2647 | FOT | WCS | 17.75 | 30 May 0500 - 0500 | 7515 | 897182 | WFD 7" HDL PKR GOT STUCK WHILE POOH. | TF | CHAMP |  | 05/30/2022 | SINO-27N | 17.75 | HWYH-466
2648 | 9550 | 897161 | RIG | RW |  | 9892 | CONTINUE WASH DOWN FROM 8640 TO 9550FT WITH 220 GPM ,450PSI** DYNAMIC LOSSES INCREASE GRADUALLY TO 70 BPH AFTER CLEANING 5613 FT.** GOT LCM ON SHALE SHAKERS WHILE WASH DOWN | 8640 | DRG | 9892 | 05/30/2022 | SINO-32L | BIT | SHYB-570
2649 |  | 897161 | RIG | CIRC |  | 9892 | PUMP LO/ HI VIS PILL CIRCULATE OUT 250 GPM, 750 PSI; GOT SIGNIFICANT LCM AMOUNT ON SHALE SHAKERS .* DYNAMIC LOSSES 90 BPH* FLOW CHECK STATIC LOSSES 35 BPH |  | DRG | 9892 | 05/30/2022 | SINO-32L | MPMP | SHYB-570
2650 | 5000 | 897161 | RIG | TO |  | 9892 | POOH WITH PUMP OUT TO REMOVE ANY LCM CUTTING BEDS TO 5000 FT; 250 GPM, 750- 500 PSI, 30 RPM, TQ 2-3 KFT.LBS | 9550 | DRG | 9892 | 05/30/2022 | SINO-32L | STDP | SHYB-570
2651 |  | 897161 | RIG | CIRC |  | 9892 | PUMP LO/ HI VIS PILL CIRCULATE OUT 250 GPM, 350 PSI; SHALE SHAKERS CLEAN. .* DYNAMIC LOSSES 75 BPH* FLOW CHECK STATIC LOSSES 35 BPH |  | DRG | 9892 | 05/30/2022 | SINO-32L | MPMP | SHYB-570
2652 | 0 | 897161 | RIG | TO |  | 9892 | DROP DP DRIFT & CONTINUE POOH CLEAN OUT BHA TO SURFACE * FLOW CHECK 35 BPH | 5000 | DRG | 9892 | 05/30/2022 | SINO-32L | STDP | SHYB-570
2653 |  | 897161 | RIG | HT |  | 9892 | CONTINUE POOH CLEAN OUT BHA TO SURFACE , LAY DOWN BHA.** RECOVER 02 KG OF NON MAGNETIC METAL SHAVINGS FROM JUNK BASKET |  | DRG | 9892 | 05/30/2022 | SINO-32L | BHA | SHYB-570
2654 |  |  | RIG | HT |  | 9892 | HPJSM , P/U 4 1/2" TUBING HANDLING TOOLS |  |  | 9892 | 05/30/2022 | SINO-32L | STRG | SHYB-570
2655 |  |  | RIG | HT |  | 9892 | P/U & M/U 4 1/2" P&A KIT AS BELOW:*4.5" BAKER GPV SHOE W/ PUP JOINT, 2X PUP JOINT 4 1/2", 4 1/2" WELLBORE ISOLATION VALVE W/ PJ, CSG JOINT 4 1/2", NEW BAKER MPAS MECH. EXTERNAL CSG PACKER, BAKER LIFT NIPPLE, CSG JOINT 4-1/2", NEW BAKER MPAS MECH. EXTERNAL CSG PACKER, BAKER LIFT NIPPLE, CASING JOINT 4-1/2", PUP JOINT 4-1/2", 2X 4 1/2" C2 SETTING SLEEVE W/ EXTENTION. ** CIRCULATE WITH 04 BPM , PRESSURE 50 PSI** PUW=60 KLBS , SOW =60 KLBS |  |  | 9892 | 05/30/2022 | SINO-32L | STRG | SHYB-570
2656 |  |  | RIG | OTH |  | 9892 | RIH WITH MPAS PACKERS ASSEMBLY ON 4" DP AT CONTROLLED SPEED TO 1925 FT MD. ** FILL UP STRING EVERY 10 STDSMONITOR THE WELL ON TRIP TANK |  |  | 9892 | 05/30/2022 | SINO-32L | NA | SHYB-570
2657 |  |  | RIG | RR |  | 9892 | CHANGE OUT TDS SAVER SUB WITH NEW ONE XT-39 .(4" DP). RIG SERVICE TDS. |  |  | 9892 | 05/30/2022 | SINO-32L | TDS | SHYB-570
2658 |  |  | RIG | OTH |  | 9892 | RIH WITH MPAS PACKERS ASSEMBLY ON 4" DP AT CONTROLLED SPEED FROM 1925 FT TO 5616 FT* FILL UP STRING EVERY 10 STDS* MONITOR THE WELL ON TRIP TANK |  |  | 9892 | 05/30/2022 | SINO-32L | NA | SHYB-570
2659 |  |  | RIG | OTH | 2904 | 9892 | CONTINUE RIH WITH MPAS PACKERS ASSEMBLY ON 4" DP AT CONTROLLED SPEED FROM 5616 FT TO 6400 FT* FILL UP STRING EVERY 10 STDS* MONITOR THE WELL ON TRIP TANK |  |  | 9892 | 05/30/2022 | SINO-32L | NA | SHYB-570
2660 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SINO-32L | Hrs | SHYB-570
2661 | WNCA | TK2 | 24.75 | 29 May 1900 - 1945 | 5616 | 897161 | UNABLE TO PASS WITH MPAS PKR ASSY OBSTRUCTION AT 5616 FT INSIDE 7" LINER, SLACK OFF 10 KLB. | DRG | NA |  | 05/30/2022 | SINO-32L | 14.75 | SHYB-570
2662 | 19.25 | OOS | Category | DOOS ID | RZIT | Out of Scope Summary | MPAS PLUG AND ABANDONMENT JOB | 1 | 2904 | 28 May 0045 | 05/30/2022 | SINO-32L | Type | SHYB-570
2663
2664
2665 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SINO-7N | Hrs | FDHL-3
2666 | FOT | HWP | 31.5 | 29 May 2100 - 0500 | 9870 | 897139 | AFTER HALL W/L SET STRADDLE PKR AT SAMPLE POINT#1 @9870' (STRADDLE PKR DEPTH), FOUND THAT THE DOWN HOLE SENSOR (FLID) WHICH RESPONSIBLE FOR FLUID IDENTIFICATION IS NOT RESPONDING AND FAILED, HALL TROUBLE SHOOTING TO GET RESPONSE FROM SENSOR BUT NO SUCCESS. | TF | WLT |  | 05/30/2022 | SINO-7N | 23.5 | FDHL-3
2667 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SL-7 | Hrs | ZULF-1333
2668 | FOT | RIG | 2 | 30 May 1930 - 2130 | 6404 | 897185 | ABNORMALITY OBSERVED ON DRILL LINE | RR | DRRK |  | 05/30/2022 | SL-7 | 2 | ZULF-1333
2669 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SND-2002 | Hrs | WAQR-23
2670 | FOT | HLH | 91.5 | 26 May 2000 - 0500 | 10330 | 897098 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES. | TF | HGRL |  | 05/30/2022 | SND-2002 | 21 | WAQR-23
2671 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SND-2006 | Hrs | UTMN-3165
2672 | FOT | SPS | 35 | 29 May 1800 - 0500 | 7955 | 897138 | RSS ICRUISE FAILURE | BHA | RSS |  | 05/30/2022 | SND-2006 | 24 | UTMN-3165
2673 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SND-3002 | Hrs | DMMM-601
2674 | FOT | WDV | 110 | 26 May 1500 - 0500 | 3880 | 897076 | WFD DV OPENING PLUG NOT BUMPED AFTER DISPLACMENT. | TF | DV |  | 05/30/2022 | SND-3002 | 24 | DMMM-601
2675 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SP-120 | Hrs | MNIF-188
2676 | FOT | RIG | 17.5 | 29 May 1300 - 0630 | 17775 | 897105 | POOH TO CASING SHOE TO FIX CONNECTION LEAK IN THE STAND PIPE MANIFOLD. | RR | CSYS |  | 05/30/2022 | SP-120 | 1.5 | MNIF-188
2677 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SSA-102 | Hrs | QTIF-696
2678 | FOT | RIG | 8.5 | 30 May 0730 - 1600 | 9050 | 897133 | REPLACED FAULTY ELMAGCO EDDY CURRENT BRAKE DUE TO WEAR & AIR GAP CLEARANCE. | RR | DWKS |  | 05/30/2022 | SSA-102 | 8.5 | QTIF-696
2679 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SSA-5859 | Hrs | HWYH-1222
2680 | FOT | MSD | .5 | 30 May 1830 - 1900 | 3580 | 897180 | HAD FAILURE IN WORKING PISTONG OF PICK UP MACHINE | TF | CTRQ |  | 05/30/2022 | SSA-5859 | .5 | HWYH-1222
2681 | FOT | RIG | 1.25 | 30 May 2200 - 2315 | 8558 | 897187 | CUMULATIVE TIME FOR TRIP OUT SPEED BELOW KPI DUE TO DRAWWORKS HIGH SPEED MODE NOT FUNCTION. | RR | DWKS |  | 05/30/2022 | SSA-5865 | 1.25 | ABJF-50
2682 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SSA-5865 | Hrs | ABJF-50
2683 | FOT | RIG | 1.25 | 30 May 1630 - 1745 | 8558 | 897176 | RIG REPAIR ON DRWWORKS. NO MOVEMENT. RIG CHANGE DRAWWAORKS SENSOR, MOVE ON LOW SPEED MODE ONLY. NO HIGH SPEED ACTION. WAITING FOR SAIPEM TECHNICIAN. | RR | DWKS |  | 05/30/2022 | SSA-5865 | 1.25 | ABJF-50
2684 | FOT | RIG | 1.25 | 30 May 2200 - 2315 | 8558 | 897187 | CUMULATIVE TIME FOR TRIP OUT SPEED BELOW KPI DUE TO DRAWWORKS HIGH SPEED MODE NOT FUNCTION. | RR | DWKS |  | 05/30/2022 | SSA-5865 | 1.25 | ABJF-50
2685 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | SSA-5962 | Hrs | HRDH-2230
2686 | WCC5 | ARM | 43.5 | 29 May 0500 - 0030 | 14186 | 897156 | WELL FLOWING WHILE DRILLING | WCNT | NA |  | 05/30/2022 | SSA-5962 | 19.5 | HRDH-2230
2687 | FOT | RIG | 2.5 | 30 May 1330 - 1600 | 11700 | 897135 | ATTEMPTED TO CIRCULATE FOUND KELLY HOSE DAMMAGE. | RR | CSYS |  | 05/30/2022 | T902 | 2.5 | HZEM-162404
2688 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/30/2022 | T902 | Hrs | HZEM-162404
2689 | UDWL | SDM | 20 | 30 May 0630 - 0500 | 13416 | 897134 | SLB NEO STEER COULDEN'T HOLD REQIURED INCLINATION. | DD | RSS |  | 05/30/2022 | T902 | 20 | HZEM-162404
2690 | FOT | RIG | 2.5 | 30 May 1330 - 1600 | 11700 | 897135 | ATTEMPTED TO CIRCULATE FOUND KELLY HOSE DAMMAGE. | RR | CSYS |  | 05/30/2022 | T902 | 2.5 | HZEM-162404
2691 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-14 | Hrs | HRDH-612
2692 | FOT | RIG | 2 | 31 May 1400 - 1600 | 0 | 897260 | EXCESS TIME TO PRESSURE TEST BOP DUE TO HOSE OF TEST UNIT LEAK AND WAIT FOR REPLACEMENT. | TF | TESTT |  | 05/31/2022 | ADC-14 | 2 | HRDH-612
2693 | FOT | ARM | 1.75 | 31 May 1645 - 1830 | 6971 | 897259 | LOST V-SAT CONNECTION WHILE DRILLING AT 6971' | TF | COMP |  | 05/31/2022 | ADC-17 | 1.75 | ZULF-1215
2694 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-17 | Hrs | ZULF-1215
2695 | FOT | RIG | .75 | 31 May 2045 - 2130 | 7064 | 897258 | OBSERVED WASH OUT ON MUD PUMP LINER SEAL | RR | MPMP |  | 05/31/2022 | ADC-17 | .75 | ZULF-1215
2696 | FOT | ARM | 1.75 | 31 May 1645 - 1830 | 6971 | 897259 | LOST V-SAT CONNECTION WHILE DRILLING AT 6971' | TF | COMP |  | 05/31/2022 | ADC-17 | 1.75 | ZULF-1215
2697 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-29 | Hrs | NYYM-102
2698 | FOT | BHI | 9 | 31 May 0800 - 1700 | 7892 | 897252 | BHI DIR DRILLING UNABLE TO CATCH THE PLAN WHILE DRILLING 8-1/2" HOLE WITH MOTOR. | BHA | MMOT |  | 05/31/2022 | ADC-29 | 9 | NYYM-102
2699 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-31 | Hrs | SDGM-1181
2700 | LHFL | RIG | 5 | 31 May 1000 - 1500 | 10730 | 897255 | REPETITIVE MUD PUMP FAILURE. | RR | HSYS |  | 05/31/2022 | ADC-31 | 5 | SDGM-1181
2701 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-43L | Hrs | UTMN-3118
2702 | FRFM | TK3 | 180.5 | 24 May 0715 - 0500 | 6420 | 896955 | WHILE DRILLING LOST COMPLETE RETURNS IN ARAB-D RESERVOIR. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 05/31/2022 | ADC-43L | 22.75 | UTMN-3118
2703 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-48 | Hrs | HWYH-1256
2704 | FOT | OJR | 14.75 | 31 May 0945 - 0030 | 18916 | 897250 | WHILE RIH WITH 5 7/8" RSS/LWD ASSY , OBSERVED PREMATURE JAR FIRING @ 4000 FT & 6000 FT . | BHA | JARS |  | 05/31/2022 | ADC-48 | 14.75 | HWYH-1256
2705 | 10376 | 7443 | ST | N | 2924 | STDP | POOH & WIPER TRIP 6-1/8" REAMING BHA ON ELEVATOR F/ 9,446 FT TO SHOE @ 7,443 FT.- HOLE IN GOOD CONDITION.- FLOW CHECK @ SHOE - WELL STATIC.- MONITORED WELL ON TRIP TANK. | 10376 | 9466 | RIG | 05/31/2022 | ADC-53L | CT | UTMN-4069
2706 | 10376 | 10376 | ST | N | 2924 | STDP | SIMULATION RUN - RIH 6-1/8" REAMING BHA ON ELEVATOR IN OH F/ 7,443 FT TO BTM @ 10,376 FT (TD).- HOLE IN GOOD CONDITION.- WASH DOWN LAST STD. | 10376 | 7443 | RIG | 05/31/2022 | ADC-53L | CT | UTMN-4069
2707 | 10376 |  | CIRC | N | 2924 | MPMP | SWEEP HOLE WITH 30/30 BBL LO-VIS/HI-WT PILLS & CIRCULATE UNTIL SHAKERS CLEAN. 100% CIRCULATION.- FR: 300 GPM, SPP: 1650 PSI | 10376 |  | RIG | 05/31/2022 | ADC-53L | CT | UTMN-4069
2708 | 10376 |  | CIRC | N | 2924 | MPMP | DISPLACE WELL TO 68 PCF OBM & CIRCULATED TO CONDITION MUD. 100% CIRCULATIONS. FLOW CHECK - WELL STATIC.- FR: 300 GPM, SPP: 1,850 PSI. | 10376 |  | RIG | 05/31/2022 | ADC-53L | CT | UTMN-4069
2709 | 10376 | 7443 | ST | N | 2924 | STDP | POOH 6-1/8" REAMING BHA ON ELEVATOR F/ 10,376 FT TO SHOE @ 7,443 FT.- HOLE IN GOOD CONDITION.- FLOW CHECK AFTER 10 STANDS PULLED AND @ SHOE - WELL STATIC.- PUMPED SLUG & DROPPED 2.4" DRIFT- MONITORED WELL ON TRIP TANK. | 10376 | 10376 | RIG | 05/31/2022 | ADC-53L | CT | UTMN-4069
2710 | 10376 | 394 | TO | N | 2924 | STDP | CONTD POOH 6-1/8" REAMING BHA ON 4" DP STANDS TO BHA @ 394 FT.- FLOW CHECK AT BHA - WELL STATIC.- MONITORED WELL ON TRIP TANK. | 10376 | 7443 | RIG | 05/31/2022 | ADC-53L | CT | UTMN-4069
2711 | 10376 |  | HT | N | 2924 | BHA | CONTD POOH & L/D 6-1/8" REAMING BHA & BIT.- MONITOR WELL ON TRIP TANK.- RECOVERED 2.4" DRIFT - DULL BIT GRADE: 1-1-WT-A-X-I-NO-BHA. | 10376 |  | RIG | 05/31/2022 | ADC-53L | CT | UTMN-4069
2712 | 10376 |  | RTRV | N |  | WBSH | RETRIEVED 11" WEAR BUSHING. | 10376 |  | RIG | 05/31/2022 | ADC-53L | WH | UTMN-4069
2713 | 10376 |  | OTH | N |  | NA | M/U AND RIH WITH BOP JETTING ASSEMBLY. FLUSHED THE BOP AND WELLHEAD AND L/D JETTING ASSEMBLY. | 10376 |  | RIG | 05/31/2022 | ADC-53L | WH | UTMN-4069
2714 | 10376 |  | HT | C | 2925 | PEL | HPJSM, R/U TESCO 4-1/2" TBG RUNNING EQUIPMENT. ON GOING AT REPORT TIME.- MONITOR WELL ON TRIP TANK. | 10376 |  | TSC | 05/31/2022 | ADC-53L | COMP | UTMN-4069
2715 | 0.5 | OOS | HCRM | 2924 | OHCM | REAM 6-1/8" OPEN HOLE SECTION F/7443 FT TO 10,376 FT (TD) PRIOR RUNNING LOWER COMPLETION. | RUN BAKER OPEN HOLE LOWER COMPLETION. | 0.5 | 2925 | 31 May 0430 | 05/31/2022 | ADC-53L | OOS | UTMN-4069
2716
2717
2718
2719 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-56L | Hrs | UTMN-2330
2720 | FOT | SDM | 33.5 | 29 May 1200 - 1615 | 19362 | 897107 | LOST LWD-ADN POROSITY SIGNAL. | BHA | LWD |  | 05/31/2022 | ADC-56L | 9.75 | UTMN-2330
2721 | 16580 |  | STIM | E | 2864 | CTU | CONTINUE RIH WITH 2 3/8" COIL TBG FROM 6760 FT TO 13133 FT (7" LINER SHOE) WHILE CONTINUOUSLY PUMPING LUBRICATED BRINE AT 0.5 BPM.- KEPT THE CHOKE OPEN | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2722 | 16580 |  | STIM | E | 2864 | CTU | RIH WITH 2-3/8" COIL TBG IN OH FROM 13133 FT TO 13506 FT WHILE CIRCULATING WITH LUBRICATING BRINE AT 1 BPM & OPEN CHOKE. | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2723 | 16580 |  | STIM | E | 2864 | CTU | RIH COIL TBG IN OPEN HOLE FROM 13506FT TO 15479 FT WHILE PUMPED 127 BBLS OF PRE FLUSH THROUGH NOZZLE INTO OPEN HOLE WITH OPEN CHOKE CONTINUOSLY FILLING UP 2.0 BPM IN ANNULUS | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2724 | 16580 |  | STIM | E | 2864 | CTU | RIH COIL TBG IN OPEN HOLE FROM 15479FT TO 16453 FT WHILE PUMPING PRE FLUSH INTO OPEN HOLE WITH OPEN CHOKE AT 3 BPM.- PUMPED TOTAL 650 BBLS OF PRE FLUSH.- MAX CIRC. PRESSURE: 2430 PSI, WELL HEAD PRESSURE: 0 PSI. | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2725 | 16580 |  | STIM | E | 2864 | CTU | POOH COIL TBG FROM 16450 FT TO 13236 FT WITH PUMPING 15 % HCL ACID FOLLOWING ACID STIMULATION TREATMENT PUMPING SCHEDULE.- PUMPING 796 BBLS OF 15% HCL + 239 BBLS SXE- PUMPING RATE: 2 BPM, CIRC. PRESSURE: 2500 PSI, WHP: 0 PSI. | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2726 | 16580 |  | STIM | E | 2864 | CTU | STATION COIL TBG AT 13413 FT AND PUMP 650 BBL POST FLUSH AT 3.0 BPM- CIRCULATING PRESS 1900 PSI; WHP 0 PSI | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2727 | 16580 |  | STIM | E | 2864 | CTU | POOH 2 3/8" CT IN CASED HOLE FROM 13236 FT TO SURFACE WHILE PUMPING BRINE- CIRCULATING PRESSURE: 250 PSI, WHP 0 PSI- POOH SPEED 40 - 50 FPM- RIG PRECAUTIONARY PUMPED 750 BBL OF 70 PCF VISCOUS BRINE AT 13133 FT THROUGH KILL LINE- RIG PRECAUTIONARY PUMPED 500 BBL OF 70 PCF VISCOUS BRINE AT 6000 FT & 300 BBLS PRIOR TO R/D INJECTOR HEAD- CONTINUOUSLY PUMPED 2 BPM 70 PCF VISCOUS BRINE INTO ANNULUS THROUGH TRIP TANK, WELL ON TOTAL LOSSES.- FLUSHED COIL WITH FRESH WATER ONCE CT AT SURFACE. | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2728 | 16580 |  | STIM | E | 2864 | CTU | HPJSM, DISCUSSED RISK ASSESSMENT. TRANSFER CT INJECTOR FROM TOP DRIVE TO CRANE & L/D. | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2729 | 16580 |  | STIM | E | 2864 | CTU | R/D COILED TUBING EQUIPMENT:- - DISCONNECTED RISER& BHA. - REMOVED RISERS FROM THE BOTTOM OF INJECTOR HEAD ASSEMBLY ON RIG FLOOR. - LAY DOWN INJECTOR HEAD - DISCONNECT CT BOP HYDRAULIC HOSES. ON GOING AT RT. | 16580 |  | SCT | 05/31/2022 | ADC-57L | STIM | FDHL-158
2730 | 108.75 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | STIMULATION JON FOR L-2, L-1. | 24 | 2864 | 24 May 0230 | 05/31/2022 | ADC-57L | Type | FDHL-158
2731
2732
2733 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-62L | Hrs | ANDR-745
2734 | UNKN | RIG | 63 | 29 May 1400 - 0500 | 9094 | 897160 | AFTER KELLY DOWN, SUSPECTED A LEAK BETWEEN SAVER SUB & MANUAL IBOP. SLB/ADC DECIDED TO REMOVE TDS GRABBER TO CHECK LEAK WHILE KEEPING STRING ROTATING AT 43 RPM. GRABBER WAS THEN LIFTED USING AIR TUGGER. WHILE LIFTING GRABBER, ROLLER OF IBOP BECAME ENGAGED WITH ITS SHELTER. AS THE GRABBER BECAME ENGAGED WITH STRING ROTATING, THE ENTIRE ASSEMBLY ROTATED. TDS LINK ROTATED ALONG STRING & HIT THREE PERSONS. | HSEI | NA |  | 05/31/2022 | ADC-62L | 24 | ANDR-745
2735 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADC-66L | Hrs | UTMN-2361
2736 | FOT | RIG | 4 | 31 May 0100 - 0500 | 12311 | 897264 | OBSERVE ABNORMAL SOUND FROM TDS AFTER KELLY DOWN. | RR | TDS |  | 05/31/2022 | ADC-66L | 4 | UTMN-2361
2737 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ADM-262 | Hrs | MRJN-125
2738 | HINW | SLL | 35 | 30 May 0730 - 0100 | 7600 | 897208 | SLB SLICK LINE 4-1/2" PXN PLUG STUCK AFTER RETRIEVING SAME FROM XN-NIPPLE. | STUK | SLICK |  | 05/31/2022 | ADM-262 | 20 | MRJN-125
2739 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | ARO-3003 | Hrs | SFNY-4290
2740 | FOT | RIG | 2.5 | 31 May 1530 - 1800 | 265 | 897257 | TOP DRIVE WENT WENT OFFLINE. ISSUE WITH OVER HEATING IN TDS CONTROL PANEL IN LOCAL ELECTRICAL ROOM. | RR | TDS |  | 05/31/2022 | ARO-3003 | 2.5 | SFNY-4290
2741 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | BB-84A | Hrs | MRJN-586
2742 | DSFT | HCO | 13.25 | 31 May 1545 - 0500 | 7566 | 897253 | MULE SHOE HUNG UP ON TOP OF WHIP STOCK AT 7,566' | JF | PKR |  | 05/31/2022 | BB-84A | 13.25 | MRJN-586
2743 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | DPS-74 | Hrs | NJYN-54
2744 | FOT | BLH | 1097.25 | 13 Apr 0730 - 0500 | 14010 | 895421 | BAKER 7" LINER HANGER PREMATURE SET WHILE WASHING DOWN @ 14,010' CREATING STUCK 7" LINER 2,489' OFF BOTTOM WITH NO CIRCULATION. | TF | HGRL |  | 05/31/2022 | DPS-74 | 24 | NJYN-54
2745 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | JACK-202 | Hrs | HMYM-844
2746 | FOT | RIG | 2 | 31 May 0030 - 0230 | 2450 | 897261 | CAT ENGINE #1 DRAWWORKS ENGINE BROKE DOWN (BOLTS OF THE COUPLING GEAR BOX BROKENED) | RR | PSYS |  | 05/31/2022 | JACK-202 | 2 | HMYM-844
2747 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | NA-207S | Hrs | SHYB-132
2748 | SRVC | SWL | 46 | 30 May 0700 - 0500 | 15000 | 897256 | SLB E.LINE ASSIGNED COMPANY UNABLE TO PROVIDE REQUIRED SERVICES (MPC). | WO | NA |  | 05/31/2022 | NA-207S | 24 | SHYB-132
2749 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | PA-70S | Hrs | MDRK-64
2750 | FOT | WLH | 35 | 30 May 1800 - 0500 | 15492 | 897183 | WFD LOWER COMPLETION FAILED WHILE DISPLACE WITH WTR TO PICKLE UPPER COMPLETION , EITHER LINER HGR PKR OR CERAMIC DISK, HOWEVER THE NEGATIVE TEST WAS PERFORMED TO TOL HGR & CERAMIC DISK FOR 4 HR'S ON 26TH MAY-2022 WITH OUT LEAK. | TF | LLAP |  | 05/31/2022 | PA-70S | 24 | MDRK-64
2751 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | RM-74A | Hrs | HSBH-68
2752 | FOT | RIG | 6 | 31 May 1830 - 0030 | 500 | 897267 | BIG BORE DIVERTER LEAKS DURING HYDRO TEST | RR | FL |  | 05/31/2022 | RM-74A | 6 | HSBH-68
2753 | 0 | 5380 | LOG | E |  | WLT | HALL WL RECORD MAIN CORROSION LOG (MPET - GR - CCL) FROM 1440' TO SURFACE.- REPEAT RECORDED SECTION F/ 5680 FT T/ 5380 FT, POH TO SURFACE & L/D LOOGING TOOL.- R/D WL PCE & SHEAVES. | 0 | 5680 | HWP | 05/31/2022 | SINO-15L | LOG | ANDR-482
2754 | 0 |  | ND | N |  | BNIP | N/D SHOOTING BPL & N/U BELL NPL. | 0 |  | RIG | 05/31/2022 | SINO-15L | BOP | ANDR-482
2755 | 0 |  | OTH | N |  | NA | M/U & RIH 18 STDS 4" HWDP, M/U HALLIBURTON 7" RTTS PACKER & STORM VALVE AND RIH ON 2 STDS X 4" DP TO 210 FT. | 0 |  | RIG | 05/31/2022 | SINO-15L | WH | ANDR-482
2756 | 0 |  | OTH | N |  | NA | SET 7" RTTS @ 210 FT. PT 7" RTTS PKR TO 1000 PSI, OK, RELEASE RTTS RUNNING TOOL, POH & RACK BACK 2 STDS 4" DP, L/D SETTING TOOL.- P/T 7" RTTS & STORM VALVE TO 1000 PSI, HOLD. | 0 |  | RIG | 05/31/2022 | SINO-15L | WH | ANDR-482
2757 | 0 |  | ND | N |  | BOP | HPJSM. HANG FLOW LINE, N/D BELL NIPPLE, REMOVE MOUSE HOLE, DISCONNECT EM. K.LINE & HANG BOP. | 0 |  | RIG | 05/31/2022 | SINO-15L | BOP | ANDR-482
2758 | 0 |  | OTH | N |  | NA | HPJSM, DIG OUT CELLAR 6 FT BELOW LANDING BASE.- ISSUE REQUIRED PTW & DISCUSSED JSA .CHECK 9" X 13" & 7" X 9" CCA'S ARE ZERO PRESSURE - PT 9-5/8" X 13-3/8" CCA TO 500 PSI WITH INHIBITED WATER, PRESSURE HOLD.- PT 7" X 9-5/8" CCA TO 500 PSI WITH INHIBITED WATER, PRESSURE HOLD.- PT 7" CSG SLIPS TO 1500 PSI, OK- MANSOORI PERFORM INSPECTION FOR LANDING BASE ( GOOD CONDITION ) & UT FOR 18-5/8" CSG (SEAL WELDED TO DONUT PLATE). | 0 |  | RIG | 05/31/2022 | SINO-15L | WH | ANDR-482
2759 | 0 |  | OTH | N | 2927 | NA | ( OOS) HPJSM, WELD 1-1/2" NIPPLE ON 18-5/8" CSG, MANSOORI PERFORM MPI FOR WELDING, WILD WELL PERFORM HOT TAPPING ON 18-5/8" CSG, NO PRESSURE OR GAS ON 18-5/8" X 13-3/8" CCA. | 0 |  | WWC | 05/31/2022 | SINO-15L | WH | ANDR-482
2760 | 0 |  | OTH | N |  | NA | HOTHED CUT WINDOW ON 18-5/8" CSG, REMOVE CMT, ALMANSOORI PERFORM UT INSPECTION ON 13-3/8" CSG ... INC @ RPT. | 0 |  | HTD | 05/31/2022 | SINO-15L | WH | ANDR-482
2761 | 2.5 | OOSS | Category | DOOS ID | HTAP | Out of Scope Summary | WILD WELL PERFORM HOT TAPPING ON 18-5/8" CSG . | 2.5 | 2927 | 31 May 0130 | 05/31/2022 | SINO-15L | Type | ANDR-482
2762
2763
2764 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SINO-16 | Hrs | FDHL-606
2765 | FOT | WTS | 36 | 30 May 1330 - 0500 | 9510 | 897181 | WFD TT MECHANICAL CUTTER FAILED TO CUT TBG AT DESIRED DEPTH AT 9510' & WORK TO FREE TBG, NO SUCCESS. | TF | CTAC |  | 05/31/2022 | SINO-16 | 24 | FDHL-606
2766 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SINO-27N | Hrs | HWYH-466
2767 | FOT | WCS | 181.75 | 24 May 0500 - 0500 | 7515 | 897182 | WFD 7" HDL PKR GOT STUCK WHILE POOH. | TF | CHAMP |  | 05/31/2022 | SINO-27N | 24 | HWYH-466
2768 | 9892 | 9536 | OTH | N | 2904 | NA | CONTINUE RIH WITH MPAS PACKERS ASSEMBLY ON 4" DP AT CONTROLLED SPEED FROM 6400 FT TO 9536 FT * FILL UP STRING EVERY 10 STDS* MONITOR THE WELL ON TRIP TANK | 9892 | 6400 | RIG | 05/31/2022 | SINO-32L | PA | SHYB-570
2769 | 9892 |  | CIRC | N | 2904 | MPMP | CIRCULATE; PUMP 10 BBLS HI VIS PILL, DROP 1.5'' SETTING BALL , PUMP 20 BBLS HI VIS PILL BEHIND, CIRCULATE 3 BPH INCREASE PRESSURE TO 2500 PSI HOLD FOR 10 MINUTES, MPAS SET CONFIRMED BY 5 KLBS S/O WEIGHT.** RELEASE SETTING TOOL 15 TUNRS RIGHT- OK ** BOTTOM OF GPV SHOE: 9536 FT** MPAS PACKER #1 : SETTING DEPTH 9453 FT** MPAS PACKER #2: SETTING DEPTH 9390 FT ** TOP OF SETTING SLEEVE: 9328 FT | 9892 |  | RIG | 05/31/2022 | SINO-32L | PA | SHYB-570
2770 | 9892 |  | CIRC | N | 2904 | MPMP | CIRCULATE - NO DYNAMIC LOSSES. FLOW CHECK - NO STATIC LOSSES.DISPLACE HOLE TO 74 PCF VISCOUS BRINE ** NO DYNAMIC LOSSES | 9892 |  | RIG | 05/31/2022 | SINO-32L | PA | SHYB-570
2771 | 9892 |  | OTH | N | 2904 | NA | PERFORM EXTENDED FLOW CHECK - WELL STATIC. | 9892 |  | RIG | 05/31/2022 | SINO-32L | PA | SHYB-570
2772 | 9892 | 7139 | TO | N | 2904 | STDP | POOH WITH MPAS PACKER SETTING TOOL TO 7'' LINER SHOE @7139FT* PUMP OUT FIRST 5 STDS , FLOW CHECK WELL STATIC | 9892 | 9327 | RIG | 05/31/2022 | SINO-32L | PA | SHYB-570
2773 | 9892 |  | OTH | N | 2904 | NA | FLOW CHECK - WELL STATIC. PUMP SLUG. | 9892 |  | RIG | 05/31/2022 | SINO-32L | PA | SHYB-570
2774 | 9892 | 0 | TO | N | 2904 | STDP | CONTINUE POOH WITH MPAS PACKER SETTING TOOL TO SURFACE** FLOW CHECK AT TOP OF LINER , TOP OF BHA : WELL STATIC | 9892 | 7139 | RIG | 05/31/2022 | SINO-32L | PA | SHYB-570
2775 | 9892 |  | WBCO | N |  | WBCL | HPJSM, P/U & M/U 7" BWC WB CLEAN OUT ASSY.-FLUSH & JET BOP & WH AREA.-BHA: (5 3/4"RCJB+ XO +2 X 5 3/4 " JUNK BASKET + FLOAT SUB + XO + 01 DP 4" + 6X 4" HWDP + XO +2 X 7"STRING MILL + 4 3/4 DC + XO+ 7" SCRAPER + 7" BRUSH + 4 X MAGNETS +FILTER JUNK TRAPPER + PUP JT + 9 X 4" HWDP + JAR +08 X 4" HWDP-MONITOR WELL THRU TRIP TANK | 9892 |  | BWC | 05/31/2022 | SINO-32L | CT | SHYB-570
2776 | 9892 | 5500 | TI | N |  | STDP | RIH 7" BWC WB CLEAN OUT ASSY TO 5500 FT * WASH DOWN 7" TOL @ 3721 FT PASSED THRU SMOOTHLY WITHOUT OBSTRUCTIONS WITH 380 GPM - 730 PSI -MONITOR WELL ON TRIP TANK AND TRIP SHEET | 9892 | 901 | RIG | 05/31/2022 | SINO-32L | CT | SHYB-570
2777 | 9892 | 7130 | RW | N |  | BIT | WASH DOWN FROM 5500 FT TO 7130 FT.* SCRAPE & BRUSH +/- 100 FT FOR L-2 & L-1 WPSK SETTING DEPTHS : 6440 FT AND 6735 FT. * GPM: 450 1600 PSI RPM : 40 TRQ: 1-2 KFT-LB | 9892 | 5500 | BHT | 05/31/2022 | SINO-32L | CT | SHYB-570
2778 | 9892 |  | CIRC | N |  | MPMP | PUMP 20 BBL LO-VIS / 30 BBL. HI-VIS PILL AND CHC. | 9892 |  | RIG | 05/31/2022 | SINO-32L | CT | SHYB-570
2779 | 34.5 | OOS | Category | DOOS ID | RZIT | Out of Scope Summary | MPAS PLUG AND ABANDONMENT JOB | 15.25 | 2904 | 28 May 0045 | 05/31/2022 | SINO-32L | Type | SHYB-570
2780
2781
2782 | 0 |  | HT | N |  | STRG | HPJSM, P/U & M/U MST TOOL. | 0 |  | RIG | 05/31/2022 | SINO-36L | PA | SDGM-458
2783 | 0 | 5645 | TI | N |  | STDP | RIH W/MST TOOL TO 5645' (15' ABOVE EZSV-CR). | 0 | 0 | RIG | 05/31/2022 | SINO-36L | PA | SDGM-458
2784 | 0 |  | HT | N |  | STRG | CIRC BTMS UP, STING INTO EZSV-CR, CLOSE BOP, PT ANNULUS TO 1450 PSI, HOLD. PERFORM INJECTIVITY TEST W/77 PCF VIS BRINE (3 BPM, 250 PSI). STING OUT, R/U SURFACE LINES, PT SAME TO 3000 PSI, HOLD. PERFORM CMT JOB: PUMP 25 BBLS OF 81 PCF TUNED SPACER, PUMP 55 BBLS OF 118 PCF CMT, STING INTO EZSV-CR, PUMP 98 BBLS OF 118 PCF CMT, DISPLACE W/5 BBLS OF 81 PCF TUNED SPACER, DISPLACE W/40 BBLS OF 77 PCF VIS BRINE. | 0 |  | RIG | 05/31/2022 | SINO-36L | PA | SDGM-458
2785 | 0 |  | CIRC | N |  | MPMP | STING OUT, REV CIRC 3 X STRG CAP W/77 PCF BRINE -RECOVERED 15 BBL PURE CMT AT SURFACE. | 0 |  | RIG | 05/31/2022 | SINO-36L | PA | SDGM-458
2786 | 0 |  | PBA | S |  | NA | P&A MB WITH 7" EZSV-CR @ 5660' & SQUEEZED CMT | 0 |  | RIG | 05/31/2022 | SINO-36L | OT | SDGM-458
2787 | 0 |  | CIRC | N |  | MPMP | P/T 7" EZSV-CR W/ 77 PCF BRINE TO 1450 PSI- OK, CHC, SPOT 40 BBL INHIBITED BRINE ON TOP OF EZSV-CR, FLOW CHECK-WELL STATIC. | 0 |  | RIG | 05/31/2022 | SINO-36L | PA | SDGM-458
2788 | 0 |  | OTH | N |  | NA | R/D CEMENT SURFACE LINES. | 0 |  | RIG | 05/31/2022 | SINO-36L | PA | SDGM-458
2789 | 0 | 3800 | TO | N |  | STDP | POOH W/MST TOOL TO 3800'. | 0 | 5660 | RIG | 05/31/2022 | SINO-36L | PA | SDGM-458
2790 | 0 | 200 | SET | N |  | RBP | HPJSM , M/U & RIH W/ HCB 9-5/8" RTTS PKR W/ STORM VALVE ON 4" DP , SET 9-5/8" RTTS @ 200', PT ANNULUS TO 1000 PSI, HOLD, PT BELOW RTTS TO 1000 PSI, HOLD. POOH W/RTTS STORM VALVE & L/D. CLOSE BSR, PT RTTS PKR TO 1000 PSI, HOLD. | 0 | 200 | HCB | 05/31/2022 | SINO-36L | PA | SDGM-458
2791 | 0 |  | ND | N |  | BOP | HPJSM , DISCONNECT EMERGENCY KILL LINES , HANG UP & SECURE BOP STACK. | 0 |  | RIG | 05/31/2022 | SINO-36L | BOP | SDGM-458
2792 | 0 |  | OTH | N |  | NA | HPJSM ,CHECK WH & CSG INTEGRITY.- DIG CELLAR 6 FT BELOW LANDING BASE FLANGE.- 18-5/8" CSG IS SEAL WELDED TO DONUT PLATE. - PERFORM UT INSPECTION ON 18-5/8" CSG. | 0 |  | RIG | 05/31/2022 | SINO-36L | WH | SDGM-458
2793 | 0 |  | OTH | N | 2926 | NA | WILD WELL PERFORM HOT-TAPPING TO 18-5/8" CSG. NO PRESSURE & NO GASSES. | 0 |  | RIG | 05/31/2022 | SINO-36L | WH | SDGM-458
2794 | 0 |  | OTH | N |  | NA | - HOT HED CUT 18 5/8" CASING WINDOW, HAVE GOOD CMT. - ALMANSORI PERFORM UT INSPECTION FOR 13 3/8" CASING, ACCEPTED. (NO ACTION REQUIRED).- FILL ANNULUS BACK WITH CEMENT.- HOT HED SEAL WELD 18 5/8" NEW CASING WINDOW.- ALMANSORI PERFORM MPI INSPECTION FOR WELDED AREAS. | 0 |  | RIG | 05/31/2022 | SINO-36L | WH | SDGM-458
2795 | 0 |  | NU | N |  | WH | WELL HEAD REMOVAL AND ISTALATION.- N/D OLD 13-5/8" X 11" 3M " CIW" THS.- HOT HED RE-DRESS 9-5/8" CSG T/ 5".- N/U NEW 13-5/8" X 11" 3M "CIW" THS.- P/T 9-5/8" SEALS TO 1000 PS-OK.- INSTALL NEW 2 X 2-1/16", 3M "CIW"GATE VALVE. | 0 |  | RIG | 05/31/2022 | SINO-36L | WH | SDGM-458
2796 | 0 |  | NU | N |  | BOP | HPJSM, N/U BOP & RELATED EQUIPMENT. | 0 |  | RIG | 05/31/2022 | SINO-36L | BOP | SDGM-458
2797 | 3 | OOSS | Category | DOOS ID | HTAP | Out of Scope Summary | WILD WELL PERFORM HOT-TAPPING TO 18-5/8" CSG. | 3 | 2926 | 31 May 2030 | 05/31/2022 | SINO-36L | Type | SDGM-458
2798
2799
2800 | FOT | HWP | 19 | 31 May 1000 - 0500 | 9870 | 897248 | AFTER HALL W/L SET STRADDLE PKR AT SAMPLE POINT#1 @9870' (STRADDLE PKR DEPTH), AFTER 20 MIN LOST SIGNAL FROM STRADDLE PKR TOOL (TOTAL PUMP-OUT 15 LTRS WATER), TROUBLESHOOTING TRYING TO RECOVER THE SIGNAL BUT NO SUCCESS. | TF | WLT |  | 05/31/2022 | SINO-7N | 19 | FDHL-3
2801 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SINO-7N | Hrs | FDHL-3
2802 | FOT | HWP | 36 | 29 May 2100 - 1000 | 9870 | 897139 | AFTER HALL W/L SET STRADDLE PKR AT SAMPLE POINT#1 @9870' (STRADDLE PKR DEPTH), FOUND THAT THE DOWN HOLE SENSOR (FLID) WHICH RESPONSIBLE FOR FLUID IDENTIFICATION IS NOT RESPONDING AND FAILED, HALL TROUBLE SHOOTING TO GET RESPONSE FROM SENSOR BUT NO SUCCESS. | TF | WLT |  | 05/31/2022 | SINO-7N | 4.5 | FDHL-3
2803 | FOT | HWP | 19 | 31 May 1000 - 0500 | 9870 | 897248 | AFTER HALL W/L SET STRADDLE PKR AT SAMPLE POINT#1 @9870' (STRADDLE PKR DEPTH), AFTER 20 MIN LOST SIGNAL FROM STRADDLE PKR TOOL (TOTAL PUMP-OUT 15 LTRS WATER), TROUBLESHOOTING TRYING TO RECOVER THE SIGNAL BUT NO SUCCESS. | TF | WLT |  | 05/31/2022 | SINO-7N | 19 | FDHL-3
2804 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SND-1201 | Hrs | KHRS-383
2805 | FOT | RIG | 9.5 | 31 May 1100 - 2030 | 0 | 897262 | BOP HOIST MALFUNCTIONED | RR | HSYS |  | 05/31/2022 | SND-1201 | 9.5 | KHRS-383
2806 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SND-2001 | Hrs | UTMN-2329
2807 | FOT | WUD | 2 | 31 May 1200 - 1400 | 13293 | 897251 | RCD BEARING LEAKING | TF | UBDO |  | 05/31/2022 | SND-2001 | 2 | UTMN-2329
2808 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SND-2002 | Hrs | WAQR-23
2809 | FOT | HLH | 118.5 | 26 May 2000 - 0500 | 10330 | 897098 | NO INDICATION OF DART LATCH INTO WIPER PLUG & NO BUMP PLUG WHICH LEAD TO LOSSES. | TF | HGRL |  | 05/31/2022 | SND-2002 | 24 | WAQR-23
2810 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SND-2006 | Hrs | UTMN-3165
2811 | FOT | SPS | 41.5 | 29 May 1800 - 1130 | 7955 | 897138 | RSS ICRUISE FAILURE | BHA | RSS |  | 05/31/2022 | SND-2006 | 6.5 | UTMN-3165
2812 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SND-3002 | Hrs | DMMM-601
2813 | FOT | WDV | 122 | 26 May 1500 - 1700 | 3880 | 897076 | WFD DV OPENING PLUG NOT BUMPED AFTER DISPLACMENT. | TF | DV |  | 05/31/2022 | SND-3002 | 12 | DMMM-601
2814 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SP-110 | Hrs | BRRI-562
2815 | FOT | BHI | 17.5 | 31 May 1130 - 0500 | 15089 | 897188 | BAKER GR TOOL NOT WORKING DURING DRLG 8-1/2" L 0-1, RUN A DEDICATED TRIP TO LOG THE MISSED INTERVAL (2,699'). | BHA | MWD |  | 05/31/2022 | SP-110 | 17.5 | BRRI-562
2816 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SP-259 | Hrs | HZEM-160412
2817 | UDWL | SDM | 14 | 31 May 0730 - 2130 | 8700 | 897229 | SLB MWD LOST SIGNAL | DD | RSS |  | 05/31/2022 | SP-259 | 14 | HZEM-160412
2818 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | SSA-5859 | Hrs | HWYH-1222
2819 | FOT | FMC | 3 | 31 May 0530 - 0830 | 5620 | 897263 | CRT STUCK INSIDE CSG 13 3/8" | TF | CTRQ |  | 05/31/2022 | SSA-5859 | 3 | HWYH-1222
2820 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | T218 | Hrs | UTMN-1281
2821 | IPDF | EMC | 19.25 | 31 May 0945 - 0500 | 7294 | 897268 | STUCK PIPE WHILE WASH-UP | STUK | DC |  | 05/31/2022 | T218 | 19.25 | UTMN-1281
2822 | PSSW | ARM | 21.25 | 31 May 0715 - 0500 | 8708 | 897254 | WHILE BACK REAMING OOH STRING BECAME STUCK | STUK | NA |  | 05/31/2022 | T902 | 21.25 | HZEM-162404
2823 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 05/31/2022 | T902 | Hrs | HZEM-162404
2824 | UDWL | SDM | 22.25 | 30 May 0630 - 0715 | 13416 | 897134 | SLB NEO STEER COULDEN'T HOLD REQIURED INCLINATION. | DD | RSS |  | 05/31/2022 | T902 | 2.25 | HZEM-162404
2825 | PSSW | ARM | 21.25 | 31 May 0715 - 0500 | 8708 | 897254 | WHILE BACK REAMING OOH STRING BECAME STUCK | STUK | NA |  | 05/31/2022 | T902 | 21.25 | HZEM-162404