## Sheet1
| Cause | Company Name | Cummulative Hrs | Date and Time | Depth | LT ID | LT Summary | LT Type | Object | Parent LT ID | Report Date | Rig Name | Time in Hrs | Well No
0 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | 088TE | Hrs | QTIF-330
1 | FOT | WEP | 33.5 | 31 Jul 1930 - 0500 | 5926 | 900302 | UNABLE TO RUN 4-1/2" HALLIBURTON COMPLETION SEAL THROUGH WFD MCL (7" CASING PATCH). | TF | CPCH |  | 08/01/2022 | 088TE | 24 | QTIF-330
2 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADC-29 | Hrs | NYYM-100
3 | FPMP | RIG | 2 | 01 Aug 0900 - 1100 | 9336 | 900331 | WHILE DRILLING OBSERVE PRESSURE DROP, FOUND LEAK ON MP#1 | RR | MPMP |  | 08/01/2022 | ADC-29 | 2 | NYYM-100
4 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADC-31 | Hrs | SDGM-1181
5 | STDP | RIG | 444.5 | 12 Jul 1930 - 0500 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/01/2022 | ADC-31 | 24 | SDGM-1181
6 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADC-41L | Hrs | SDGM-1244
7 | UVLC | ARM | 289.5 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 08/01/2022 | ADC-41L | 24 | SDGM-1244
8 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADC-43L | Hrs | UTMN-3118
9 | FRFM | TK3 | 50.5 | 30 Jul 0115 - 0500 | 12637 | 900352 | WHILE DRILLING LOST COMPLETE RETURNS IN KHUFF B CARBONATE. PUMPING LCM TO CURE THE LOSSES. | LCIR | NA |  | 08/01/2022 | ADC-43L | 22.75 | UTMN-3118
10 | FOT | RIG | 4.5 | 01 Aug 1915 - 2345 | 2400 | 900346 | UNABLE TO BREAK CONNECTION BETWEEN TDS AND DP | RR | RSYS |  | 08/01/2022 | ADC-50 | 4.5 | SFNY-1176
11 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADC-50 | Hrs | SFNY-1176
12 | LCRW | ARM | 255.25 | 19 Jul 1830 - 0500 | 0 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 08/01/2022 | ADC-50 | 19.5 | SFNY-1176
13 | FOT | RIG | 4.5 | 01 Aug 1915 - 2345 | 2400 | 900346 | UNABLE TO BREAK CONNECTION BETWEEN TDS AND DP | RR | RSYS |  | 08/01/2022 | ADC-50 | 4.5 | SFNY-1176
14 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADC-52 | Hrs | SDGM-1185
15 | HINW | BAW | 88 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/01/2022 | ADC-52 | 24 | SDGM-1185
16 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADC-55L | Hrs | UTMN-3171
17 | STBH | TK3 | 66.5 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/01/2022 | ADC-55L | 24 | UTMN-3171
18 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADC-66L | Hrs | UTMN-3155
19 | FOT | RIG | 3.75 | 01 Aug 2245 - 0230 | 11057 | 900350 | OBSERVE TWO MUD PUMPS BROKE DOWN WHILE DRILLING AT 11057 FT. DECIDE TO POOH TO CSG SHOE WHILE WORK ON MUD PUMPS. | RR | MPMP |  | 08/01/2022 | ADC-66L | 3.75 | UTMN-3155
20 | WTHR | OTH | 2 | 01 Aug 0300 - 0500 | 0 | 900344 | STOPPED TRIPPING DUE TO HIGH WIND SPEED. | WON | NA |  | 08/01/2022 | ADES-14 | 2 | HWYH-536
21 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADES-14 | Hrs | HWYH-536
22 | FOT | RIG | 3 | 01 Aug 2030 - 2330 | 1565 | 900343 | SCRAPPER COULD NOT PASS 7" TOL | DSF | STRG |  | 08/01/2022 | ADES-14 | 3 | HWYH-536
23 | WTHR | OTH | 2 | 01 Aug 0300 - 0500 | 0 | 900344 | STOPPED TRIPPING DUE TO HIGH WIND SPEED. | WON | NA |  | 08/01/2022 | ADES-14 | 2 | HWYH-536
24 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADES-889 | Hrs | HRDH-2122
25 | FOT | RIG | 7.5 | 01 Aug 2030 - 0400 | 6780 | 900395 | DAMAGE OF DRAW WORKS HIGH GEAR CHAIN & HIGH CLATCH CHAIN. | RR | DWKS |  | 08/01/2022 | ADES-889 | 7.5 | HRDH-2122
26 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ADM-337 | Hrs | MRJN-900
27 | SRVC | BCT | 17.75 | 31 Jul 1115 - 2300 | 13019 | 900306 | ATTEMPTED TO P/T CT LINES, SEVERAL LOW-TORQUE VALVES LEAKING. REPLACE AND RE-GREASE VALVES. | WO | NA |  | 08/01/2022 | ADM-337 | 4 | MRJN-900
28 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ARO-2001 | Hrs | BRRI-90
29 | FOT | ITS | 3 | 01 Aug 1630 - 1930 | 198 | 900342 | ITS CREW USED WRONG SIZED ELEVATOR (3-1/2") TO RUN 2-7/8" TBG. | TF | PEL |  | 08/01/2022 | ARO-2001 | 3 | BRRI-90
30 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | DQ-49L | Hrs | HRDH-575
31 | STBH | TK2 | 153 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 08/01/2022 | DQ-49L | 24 | HRDH-575
32 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | DQ-57L | Hrs | KHRS-68
33 | WOTO | TK1 | 10.5 | 01 Aug 0500 - 1530 | 4600 | 900347 | WORK ON STUCK 2.34"G.C WITH JARRING UP & 820 LB MAX O/P WHILE WAITING ON GO-DEVIL CUTTER & HALL S/L FISHING EQUIPMENTS | WO | NA |  | 08/01/2022 | DQ-57L | 10.5 | KHRS-68
34 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ED-85A | Hrs | ZULF-2063
35 | CFST | BCM | 75 | 26 Jul 0145 - 0500 | 11328 | 900111 | CEMENT SET WHILE DISPLACING DV OPENNING PLUG. | CMT | NA |  | 08/01/2022 | ED-85A | 22 | ZULF-2063
36 | FOT | SRT | 2.75 | 01 Aug 0215 - 0500 | 0 | 900362 | ATTEMPTED TO FUNCTION TEST RHINO REAMER, TEST FAILED. | BHA | RM |  | 08/01/2022 | ENS-108 | 2.75 | ZULF-2014
37 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ENS-108 | Hrs | ZULF-2014
38 | FOT | ENV | 189.25 | 25 Jul 0500 - 0215 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/01/2022 | ENS-108 | 21.25 | ZULF-2014
39 | FOT | SRT | 2.75 | 01 Aug 0215 - 0500 | 0 | 900362 | ATTEMPTED TO FUNCTION TEST RHINO REAMER, TEST FAILED. | BHA | RM |  | 08/01/2022 | ENS-108 | 2.75 | ZULF-2014
40 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ENSCO-54 | Hrs | ABSF-17
41 | FOT | SPS | 1 | 01 Aug 1830 - 1930 | 7975 | 900375 | STOPPED DRILLING - CIRCULATE WHILE SPERRY TROUBLE SHOOT PC PROBLEMS. | BHA | LWD |  | 08/01/2022 | ENSCO-54 | 1 | ABSF-17
42 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | ENSCO-76 | Hrs | MRJN-853
43 | FOT | RIG | 3 | 01 Aug 0815 - 1115 | 8405 | 900372 | SWIVEL PACKING FAILED. | RR | SWVL |  | 08/01/2022 | ENSCO-76 | 3 | MRJN-853
44 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | HI-2 | Hrs | BRRI-435
45 | HERR | RIG | 2.5 | 01 Aug 0230 - 0500 | 1015 | 900393 | DURING HOUSEKEEPING OBSERVED MOUSE HOLE COVER MISSING, SUSPECTED THAT IT FELL IN HOLE. | FISH | BHA |  | 08/01/2022 | HI-2 | 2.5 | BRRI-435
46 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | MP-1 | Hrs | MRJN-78
47 | FOT | NRT | 26.25 | 31 Jul 0245 - 0500 | 9345 | 900303 | DURING THE REAMING TRIP, LOST +/- 500 PSI DPP WHILE REAMING DOWN. AFTER POH FOUND NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE. | BHA | UNDR |  | 08/01/2022 | MP-1 | 24 | MRJN-78
48 | WC20 | ARM | 1 | 01 Aug 0400 - 0500 | 13970 | 900349 | FLOW CHECK WHILE R/U WL HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 08/01/2022 | NBR-263S | 1 | QTIF-736
49 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | NBR-263S | Hrs | QTIF-736
50 | STBH | ARM | 44.75 | 29 Jul 0230 - 0400 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 08/01/2022 | NBR-263S | 13.75 | QTIF-736
51 | WC20 | ARM | 8.75 | 01 Aug 0600 - 1445 | 13970 | 900348 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 08/01/2022 | NBR-263S | 8.75 | QTIF-736
52 | WC20 | ARM | 1 | 01 Aug 0400 - 0500 | 13970 | 900349 | FLOW CHECK WHILE R/U WL HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 08/01/2022 | NBR-263S | 1 | QTIF-736
53 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | NBR-304S | Hrs | HRDH-1958
54 | FOT | SPS | 14.5 | 01 Aug 1230 - 0500 | 17692 | 900376 | SPERRY SUN I-CRUISE FAILURE | BHA | RSS |  | 08/01/2022 | NBR-304S | 14.5 | HRDH-1958
55 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | NBR-591S | Hrs | HRDH-2259
56 | FOT | GOC | 1.5 | 01 Aug 0330 - 0500 | 9910 | 900394 | AL-GHAITH CASING RUNNING EQUIPMENT STOP WORKING | TF | PEL |  | 08/01/2022 | NBR-591S | 1.5 | HRDH-2259
57 | FOT | HCM | 1.5 | 01 Aug 0015 - 0145 | 5380 | 900377 | HALLIBURTON CEMENT UNIT MALFUNCTION, RESET SOFTWARE TILL WORKING OK. | TF | PUMP | 899983 | 08/01/2022 | PN-9 | 1.5 | MRJN-673
58 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | PN-9 | Hrs | MRJN-673
59 | CFST | HCM | 222 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/01/2022 | PN-9 | 22.5 | MRJN-673
60 | FOT | HCM | 1.5 | 01 Aug 0015 - 0145 | 5380 | 900377 | HALLIBURTON CEMENT UNIT MALFUNCTION, RESET SOFTWARE TILL WORKING OK. | TF | PUMP | 899983 | 08/01/2022 | PN-9 | 1.5 | MRJN-673
61 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SINO-18 | Hrs | HDYF-4
62 | WTHR | ARM | 2 | 01 Aug 2300 - 0100 | 7508 | 900363 | WAIT ON BAD WEATHER (HIGH WIND & HEAVY RAIN) | WON | NA |  | 08/01/2022 | SINO-18 | 2 | HDYF-4
63 | 12127 |  | DTU | C |  | DRFT | CONT. HES SLICK LINE OPERATIONS:-- SET PXN PLUG IN XN-NIPPLE @ 5212', RUN CHECK SET & PRONG (3 RUNS) & PRESSURE TEST WITH 300 PSI, HOLD OK, POH.- RIH WITH JUNK CATCHER & SET SAME @ 5212', POH & R/D S/L.- KEEP PUMPING 60 BPH OF 77 PCF VISCOUS BRINE INTO ANNULUS. | 12127 |  | HSL | 08/01/2022 | SINO-36L | COMP | SDGM-458
64 | 12127 |  | CIRC | C |  | MPMP | BULLHEAD TCA WITH 330 BBL'S OF 77 PCF BRINE {2 BPM @ 50 PSI) | 12127 |  | RIG | 08/01/2022 | SINO-36L | COMP | SDGM-458
65 | 12127 | 5101 | SET | C |  | PKR | HPJSM, CONNECT TDS, PT SURFACE LINES TO 4000 PSI, OK, SPACE OUT 7 FT INSIDE TBR. PRESSURE UP T/2200 PSI & SET HALLIBURTON 7" 'VHR' PACKER @ 5101 FT, S/O 35 KLB, PRESSURE UP T/ 3500 PSI, 10 MIN - OK, CONFIRM SET W/10 KLB O/P, PT TCA W/ TBG OPEN T/ 1000 PSI - OK, PRESSURE UP T/ 2000 PSI, APPLY 40 KLB O/P & SHEAR SEAL ASSY FROM PBR. SPACE OUT SEAL ASSY, PT TCA T/1000 PSI - OK. | 12127 | 5101 | HCO | 08/01/2022 | SINO-36L | COMP | SDGM-458
66 | 12127 |  | HT | C |  | PEL | HPJSM, POH & L/D 7 EA JTS 4-1/2" TBG FOR SPACE OUT. | 12127 |  | RIG | 08/01/2022 | SINO-36L | COMP | SDGM-458
67 | 12127 |  | OTH | C | 3906 | SSSV | HPJSM, P/U & MU BAKER TRSSSV, CONNECTED CONTROL LINE & PT TO 6000 PSI, OK. | 12127 |  | BC | 08/01/2022 | SINO-36L | COMP | SDGM-458
68 | 12127 |  | HT | C |  | PEL | RIH WITH 4 JTS 4-1/2" TBG & 4 PUP JTS SPACE OUT, P/U TBG HANGER. | 12127 |  | RIG | 08/01/2022 | SINO-36L | COMP | SDGM-458
69 | 12127 |  | DTU | C |  | DRFT | HPJSM, R/U HSL PCE, PT TO 1500 PSI-OK, RUN 3.875" DRIFT & TAG TRSSSV, OK, R/D SLICK LINE. | 12127 |  | HSL | 08/01/2022 | SINO-36L | COMP | SDGM-458
70 | 12127 |  | OTH | C | 3906 | SSSV | P/U & M/U 4.5'' BHI TR-SSSV, CONNECT CONTROL LINE & P/T SAME TO 6500 PSI FOR 30 MIN, OK. | 12127 |  | BC | 08/01/2022 | SINO-36L | COMP | SDGM-458
71 | 12127 |  | OTH | C |  | TBG | M/U 4 1/2" TBG LANDING JOINT, FOSV, M/U CIRC HEAD, LOWER STRING TO 5' ABOVE PBR. | 12127 |  | RIG | 08/01/2022 | SINO-36L | COMP | SDGM-458
72 | 12127 |  | CIRC | C |  | MPMP | DISPLACE TBG TO DIESEL & TCA W/ 1% COAT-415 INHIBITED DIESEL. FLOW CHECK - WELL STATIC. | 12127 |  | RIG | 08/01/2022 | SINO-36L | COMP | SDGM-458
73 | 12127 |  | PTST | C |  | PKR | HPJSM. LAND TBG HANGER & LOCK TIE-DOWN SCREWS. PT TBG & TCA SEPARATELY TO 1500 PSI, OK. | 12127 |  | RIG | 08/01/2022 | SINO-36L | COMP | SDGM-458
74 | 12127 | 180 | SET | C |  | PLUGT | CLOSE TRSSSV, R/U HSL & PT PCE T/ 1500 PSI - OK, HSL RUN AND SET 4-1/2" MONO-LOCK AT 180', P/T TO 1000 PSI, OK. R/D HSL & L/D LANDING JOINT & FOSV. | 12127 | 180 | HSL | 08/01/2022 | SINO-36L | COMP | SDGM-458
75 | 12127 |  | ND | C |  | BOP | N/D CLASS "A" 13-5/8" 5M BOPE & RELATED EQUIPMENT. | 12127 |  | RIG | 08/01/2022 | SINO-36L | BOP | SDGM-458
76 | 12127 |  | NU | C |  | WH | HPJSM, N/U 11" X 4" NEW CIW TBG BONNET, HPJSM. N/U 4-1/16" 3M CIW OFFSHORE TREE, ORIENT VALVES TO ORIGINAL DIRECTION.- P/T BONNET SEALS TO 2500 PSI, OK.- P/T TREE TO 2500 PSI, OK. | 12127 |  | RIG | 08/01/2022 | SINO-36L | WH | SDGM-458
77 | 12127 |  | OTH | C | 3906 | SSSV | HPJSM, TERMINATE BAKER TR-SSSV C/L THROUGH TBG BONNET ,FUNCTION TEST TR-SSSV, OK & P/T CONTROL LINE INTEGRITY TO 5000 PSI FOR 10 MIN, HOLD OK. | 12127 |  | BC | 08/01/2022 | SINO-36L | COMP | SDGM-458
78 | 12127 |  | DTU | C |  | DRFT | HPJSM, R/U HSL & PT PCE T/ 1500 PSI-.......INC@RPT. | 12127 |  | HSL | 08/01/2022 | SINO-36L | COMP | SDGM-458
79 | 4 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | INSTALL BAKER TRSSSV. | 4 | 3906 | 01 Aug 0330 | 08/01/2022 | SINO-36L | Type | SDGM-458
80
81
82 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SND-1501 | Hrs | HWYH-413
83 | WTHR | ARN | 2.25 | 01 Aug 0215 - 0430 | 0 | 900392 | WAIT ON WEATHER | WON | NA |  | 08/01/2022 | SND-1501 | 2.25 | HWYH-413
84 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SND-1502 | Hrs | HRDH-124
85 | SDIR | WDS | 8 | 31 Jul 2315 - 0930 | 8168 | 900358 | STUCK PIPE DUE TO HOLE GEOMETRY | STUK | RSS |  | 08/01/2022 | SND-1502 | 4.5 | HRDH-124
86 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SND-2007 | Hrs | AWTD-104001
87 | FOT | RIG | 6.5 | 01 Aug 1815 - 0115 | 15522 | 900311 | WASH PIPE ON TDS LEAKS. | RR | TDS |  | 08/01/2022 | SND-2007 | 6.5 | AWTD-104001
88 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SND-2008 | Hrs | HRDH-1812
89 | STDP | RIG | 474 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/01/2022 | SND-2008 | 24 | HRDH-1812
90 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SP-120 | Hrs | MNIF-187
91 | FRFM | ARM | 81.5 | 29 Jul 1730 - 0500 | 6340 | 900228 | CURE LOSSES AT WARA FORMATION WITH LCM PILL AND CEMENT PLUG. | LCIR | NA |  | 08/01/2022 | SP-120 | 24 | MNIF-187
92 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SP-122 | Hrs | HWYH-1178
93 | HERR | RIG | 22 | 31 Jul 1530 - 1330 | 11862 | 900339 | WHILE RIH W/ WBCO BHA INSIDE 7" LINER DRILLER PUT 50KLBS S/O WT. | DSF | DP |  | 08/01/2022 | SP-122 | 8.5 | HWYH-1178
94 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SP-257 | Hrs | HZEM-162412
95 | LCRW | ARM | 39.5 | 31 Jul 1330 - 0500 | 445 | 900304 | 22" BHA STUCK WHILE TOOH WITH TOTAL LOSSES. | STUK | STRG |  | 08/01/2022 | SP-257 | 24 | HZEM-162412
96 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SP-258 | Hrs | JNAB-872212
97 | FOT | SDM | 57.25 | 30 Jul 1945 - 0500 | 10515 | 900327 | GR IS READING FINE IN THE BEAGGING THEN START GIVING ERRATIC GR. | BHA | LWD |  | 08/01/2022 | SP-258 | 24 | JNAB-872212
98 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SSA-303 | Hrs | HRDH-2411
99 | FOT | RIG | 1 | 01 Aug 0045 - 0145 | 5200 | 900364 | DRAW WORKS STOPPED WORKING -TROUBLESHOOTING PROBLEM AND FIXED SAME BY CHANGING CARD IN VFD CONTROLLER. | RR | DWKS |  | 08/01/2022 | SSA-303 | 1 | HRDH-2411
100 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SSA-51 | Hrs | MNIF-257
101 | FOT | OGS | 9 | 01 Aug 2000 - 0500 | 8536 | 900341 | GYRO TOOL FAILURE | TF | GYRO |  | 08/01/2022 | SSA-51 | 9 | MNIF-257
102 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SSA-5962 | Hrs | HRDH-2513
103 | WTHR | ARM | 2.5 | 01 Aug 0230 - 0500 | 4300 | 900345 | SUSPENDED OPERATION DUE BAD WEATHER (HIGH WIND & HEAVEY RAIN). | WON | NA |  | 08/01/2022 | SSA-5962 | 2.5 | HRDH-2513
104 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SSA-5970 | Hrs | UTMN-2340
105 | XTRI | RIG | 2 | 01 Aug 0100 - 0300 | 0 | 900361 | EXCESS TIME FOR INSTALLING MODIFIED BELL NIPPLE AND FITTING WITH FLOW LINE. | JF | NA |  | 08/01/2022 | SSA-5970 | 2 | UTMN-2340
106 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/01/2022 | SSA-5974 | Hrs | HRDH-2187
107 | FOT | RIG | 2 | 01 Aug 2300 - 0100 | 5519 | 900373 | TOP DRIVE TROLLY BEAM PIN BROKEN. | RR | TDS |  | 08/01/2022 | SSA-5974 | 2 | HRDH-2187
108 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-17 | Hrs | ZULF-1210
109 | HINW | ARM | 24 | 02 Aug 0500 - 0500 | 5490 | 900413 | MANSOORI SLICKLINE 3.5" SHIFTING TOOL STUCK WHILE POH @5490 FT DUE TO SAND PRODUCTION AFTER FLOW BACK TWO ZONES | STUK | SLICK |  | 08/02/2022 | ADC-17 | 24 | ZULF-1210
110 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-23 | Hrs | KIDN-23
111 | FOT | HCO | 2.5 | 02 Aug 0500 - 0730 | 0 | 900351 | CONNECTION FROM THE CIRCULATION VALVE TO THE RTTS WOULD NOT CORRECTLY MAKE UP. LAID OUT RTTS. | TF | RTTS |  | 08/02/2022 | ADC-23 | 2.5 | KIDN-23
112 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-31 | Hrs | SDGM-1181
113 | STDP | RIG | 468.5 | 12 Jul 1930 - 0500 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/02/2022 | ADC-31 | 24 | SDGM-1181
114 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-35 | Hrs | MAQL-5
115 | WTHR | ARM | 1 | 02 Aug 1700 - 1800 | 7880 | 900418 | SUSPEND OPERATION DUE TO HEAVEY SAND STORM & LOW VISIBILITY. | WON | NA |  | 08/02/2022 | ADC-35 | 1 | MAQL-5
116 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-43L | Hrs | UTMN-3118
117 | FRFM | TK3 | 74.5 | 30 Jul 0115 - 0500 | 12637 | 900352 | WHILE DRILLING LOST COMPLETE RETURNS IN KHUFF B CARBONATE. PUMPING LCM TO CURE THE LOSSES. | LCIR | NA |  | 08/02/2022 | ADC-43L | 24 | UTMN-3118
118 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-48 | Hrs | HRDH-2316
119 | FOT | RIG | 5 | 02 Aug 1530 - 2030 | 7613 | 900384 | ELECTRICIAN INSTALL NEW TDS SERVICE LOOP CABLE, FUNCTION TEST-OK - WHILE MONITORING WELL THRU TT AT SHOE | RR | TDS |  | 08/02/2022 | ADC-48 | 5 | HRDH-2316
120 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-50 | Hrs | SFNY-1176
121 | LCRW | ARM | 279.25 | 19 Jul 1830 - 0500 | 0 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 08/02/2022 | ADC-50 | 24 | SFNY-1176
122 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-52 | Hrs | SDGM-1185
123 | HINW | BAW | 112 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/02/2022 | ADC-52 | 24 | SDGM-1185
124 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-55L | Hrs | UTMN-3171
125 | STBH | TK3 | 90.5 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/02/2022 | ADC-55L | 24 | UTMN-3171
126 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-56L | Hrs | UTMN-3069
127 | FOT | RIG | 1.5 | 02 Aug 2330 - 0100 | 3665 | 900367 | WHILE RIH 13-3/8CASING JT #89, THE SINGLE JOINT ELEVATOR CAME IN CONTACT WITH SPIDER SLIPS. | RR | TDS |  | 08/02/2022 | ADC-56L | 1.5 | UTMN-3069
128 | 7019 |  | OTH | E | 3885 | NA | POOH & L/D SLB WL NMR TOOLS FROM 51 FT TO SURFACE.- MONITOR THE WELL WITH TRIP TANK | 7019 |  | SWL | 08/02/2022 | ADC-57L | LOG | KRSN-175
129 | 7019 | 959 | LDP | E | 3885 | STRG | HPJSM, P/U, M/U 8-1/2" CO BHA # 2 & RIH TO 959 FT. | 7019 | 0 | RIG | 08/02/2022 | ADC-57L | CT | KRSN-175
130 | 7019 | 6954 | TI | E | 3885 | STDP | RIH 8-1/2" CO RUN #2 FROM 959 FT TO 6,954 FT- FILL THE STRING EVERY 20 STANDS.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 959 | RIG | 08/02/2022 | ADC-57L | CT | KRSN-175
131 | 7019 | 7019 | RW | E | 3885 | BIT | REAM DN PRECAUTIONALY FROM 6,954 FT TO 7,019 FT. | 7019 | 6954 | RIG | 08/02/2022 | ADC-57L | CT | KRSN-175
132 | 7019 |  | CIRC | E | 3885 | MPMP | SWEEP THE HOLE WITH TWO TIMES 30 BBLS HI-VIS AND CIRCULATE TILL SHAKERS CLEAN. | 7019 |  | RIG | 08/02/2022 | ADC-57L | CT | KRSN-175
133 | 7019 |  | CIRC | E | 3885 | MPMP | DISPLACE WELL BORE FLUID FROM 78 PCF LOW CHLORIDE WBM TO 79 PCF OBM.- CIRCULATE AND CONDITION MUD IN/OT 79 PCF.- FLOW CHECK WELL- STATIC. | 7019 |  | RIG | 08/02/2022 | ADC-57L | CT | KRSN-175
134 | 7019 | 4819 | TO | E | 3885 | BHA | HPJSM, POOH 8-1/2" CO BHA #2 ON ELEVATOR FROM 7,019 FT TO 9-5/8" SHOE AT 4,819 FT.- HOLE IN GOOD CONDITION.- MONITOR THE WELL WITH TRIP TANK.- FLOW CHECK AT 9-5/8" FS- WELL STATIC. | 7019 | 7019 | RIG | 08/02/2022 | ADC-57L | CT | KRSN-175
135 | 7019 | 959 | TO | E | 3885 | STDP | POOH 8-1/2" CO BHA # 2 FROM 4,819 FT TO TOP BHA AT 959 FT.- MONITOR THE WELL WITH TRIP TANK- FLOW CHECK AT TOP BHA - WELL STATIC. | 7019 | 4819 | RIG | 08/02/2022 | ADC-57L | CT | KRSN-175
136 | 7019 | 0 | LDP | E | 3885 | STRG | POOH 8-1/2" CO BHA # 2 FROM 959 FT TO SURFACE AND L/D JAR & BIT.- MONITOR THE WELL WITH TRIP TANK | 7019 | 959 | RIG | 08/02/2022 | ADC-57L | CT | KRSN-175
137 | 7019 |  | OTH | E | 3885 | NA | HPJSM, TLC RUN # 3: P/U & M/U SLB TLC MDT LOGGING TOOLS TO 177 FT.- CHECK MDT TOOLS ON SURFACE. OK.- MONITOR WELL ON TRIP TANK. | 7019 |  | SWL | 08/02/2022 | ADC-57L | LOG | KRSN-175
138 | 7019 | 747 | TI | E | 3885 | STDP | RIH W/MDT LOGGING TOOLS ON 1 X 5" HWDP AND 5" DP F/ 177 FT TO 747 FT AT CONTROLLED SPEED. - FILL UP STRING EVERY 10 STANDS.- DRIFT ALL STANDS RIH WITH 2.625" DRIFT.- MONITOR WELL ON TRIP TANK | 7019 | 177 | RIG | 08/02/2022 | ADC-57L | LOG | KRSN-175
139 | 73.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | NMR LOGGING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH LOW CHLORIDE. | 24 | 3885 | 30 Jul 0315 | 08/02/2022 | ADC-57L | Type | KRSN-175
140
141
142 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADC-60 | Hrs | ABSF-218
143 | FOT | SCB | 18 | 02 Aug 1100 - 0500 | 4920 | 900422 | S/L RIH WTIH PULLING TOOL TO RETRIEVE SLB PLUS PLUG, LATCHED ON. JAR UP TO RETRIEVE THE PLUG, NEGATIVE. | TF | BP |  | 08/02/2022 | ADC-60 | 18 | ABSF-218
144 | FOT | BCT | 1.5 | 02 Aug 1915 - 2045 | 0 | 900405 | WORN RUBBER IN STRIPPER #1 | TF | CTAC |  | 08/02/2022 | ADM-337 | 1.5 | MRJN-900
145 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ADM-337 | Hrs | MRJN-900
146 | FOT | BCT | 1.5 | 02 Aug 1500 - 1630 | 0 | 900386 | COIL TUBING CONNECTOR PUSHED OUT OF THE COIL 3/4 IN, WHEN CRIMPING CONNECTOR | TF | CTBG |  | 08/02/2022 | ADM-337 | 1.5 | MRJN-900
147 | FOT | BCT | 1.5 | 02 Aug 1915 - 2045 | 0 | 900405 | WORN RUBBER IN STRIPPER #1 | TF | CTAC |  | 08/02/2022 | ADM-337 | 1.5 | MRJN-900
148 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | AOD-1 | Hrs | ZULF-694
149 | FOT | SWL | 7.5 | 01 Aug 2330 - 0700 | 5303 | 900396 | ENCOUNTERED OBSTRUCTION @TOL 5303'. MADE SEVERAL ATTEMPTS TO ENTER TOL, UNSUCCESSFUL. RECONFIGURED TOOLS STRING WITH VARIOUS CENTRALIZATION & KNUCKLE JOINTS PLACEMENT, UNSUCCESSFUL. | TF | WLT |  | 08/02/2022 | AOD-1 | 2 | ZULF-694
150 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ARO-2001 | Hrs | BRRI-90
151 | HERR | BAL | 5.5 | 02 Aug 1045 - 1615 | 3050 | 900380 | BAKER ESP CABLE DAMAGED WHILE SETTING 3 1/2" TUBING SLIPS | JF | ESPL |  | 08/02/2022 | ARO-2001 | 5.5 | BRRI-90
152 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ARO-4001 | Hrs | MRJN-532
153 | STBH | ARM | 16.5 | 02 Aug 1145 - 0500 | 6642 | 900419 | GOT SUDDEN HOLE PACK OFF, STRING STALL AND STUCK. | STUK | BHA |  | 08/02/2022 | ARO-4001 | 16.5 | MRJN-532
154 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | DQ-49L | Hrs | HRDH-575
155 | STBH | TK2 | 177 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 08/02/2022 | DQ-49L | 24 | HRDH-575
156 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ED-85A | Hrs | ZULF-2063
157 | CFST | BCM | 99 | 26 Jul 0145 - 0500 | 11328 | 900111 | CEMENT SET WHILE DISPLACING DV OPENNING PLUG. | CMT | NA |  | 08/02/2022 | ED-85A | 24 | ZULF-2063
158 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | ENS-108 | Hrs | ZULF-2014
159 | FOT | ENV | 213.25 | 25 Jul 0500 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/02/2022 | ENS-108 | 24 | ZULF-2014
160 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | HI-2 | Hrs | BRRI-435
161 | HERR | RIG | 4.5 | 01 Aug 0230 - 0700 | 1015 | 900393 | DURING HOUSEKEEPING OBSERVED MOUSE HOLE COVER MISSING, SUSPECTED THAT IT FELL IN HOLE. | FISH | BHA |  | 08/02/2022 | HI-2 | 2 | BRRI-435
162 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | HI-9 | Hrs | BRRI-155
163 | IDPR | SDM | 25 | 01 Aug 2300 - 0000 | 9127 | 900412 | POH TO CHANGE SCHLUMBERGER 6-1/8" MM BHA TO RSS BHA DUE TO SLOW ROP. | LROP | BHA |  | 08/02/2022 | HI-9 | 19 | BRRI-155
164 | GRF | RIG | 5 | 02 Aug 0900 - 1400 | 0 | 900381 | BLADDER ON THE HI CLUTCH LEAKING AIR. | UPRA | DWKS |  | 08/02/2022 | MP-1 | 5 | MRJN-78
165 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | MP-1 | Hrs | MRJN-78
166 | FOT | NRT | 45.25 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/02/2022 | MP-1 | 19 | MRJN-78
167 | GRF | RIG | 5 | 02 Aug 0900 - 1400 | 0 | 900381 | BLADDER ON THE HI CLUTCH LEAKING AIR. | UPRA | DWKS |  | 08/02/2022 | MP-1 | 5 | MRJN-78
168 | WC20 | ARM | 3.75 | 01 Aug 0400 - 0400 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 08/02/2022 | NBR-263S | 2.75 | QTIF-736
169 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | NBR-263S | Hrs | QTIF-736
170 | STBH | ARM | 66 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 08/02/2022 | NBR-263S | 21.25 | QTIF-736
171 | WC20 | ARM | 3.75 | 01 Aug 0400 - 0400 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 08/02/2022 | NBR-263S | 2.75 | QTIF-736
172 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | NBR-304S | Hrs | HRDH-1958
173 | FOT | SPS | 38.5 | 01 Aug 1230 - 0500 | 17692 | 900376 | SPERRY SUN I-CRUISE FAILURE | BHA | RSS |  | 08/02/2022 | NBR-304S | 24 | HRDH-1958
174 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | PA-218S | Hrs | HRDH-1941
175 | FOT | RIG | 17.75 | 02 Aug 0500 - 0500 | 14320 | 900397 | TROUBLE SHOOTING DRAWWORKS: CHANGE OUT TRACTION MOTOR. | RR | DWKS |  | 08/02/2022 | PA-218S | 17.75 | HRDH-1941
176 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | PN-9 | Hrs | MRJN-673
177 | CFST | HCM | 246 | 23 Jul 2300 - 0500 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/02/2022 | PN-9 | 24 | MRJN-673
178 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | RM-74A | Hrs | HSBH-68
179 | IFCS | HCM | 11.75 | 02 Aug 1715 - 0500 | 4300 | 900414 | WHILE PREPARING TO MIX THE TAIL SLURRY, OBSERVE TAIL MIX FLUID EXCESSIVELY FOAMING. | CMT | NA |  | 08/02/2022 | RM-74A | 11.75 | HSBH-68
180 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SINO-1L | Hrs | ABJF-20
181 | HERR | SPR | 7.5 | 02 Aug 0530 - 1300 | 576 | 900385 | HAD OBSTRUCTION WHILE RIH W/ SL DRIFT COULD NOT PASS @576 FT. | JF | CTRQ |  | 08/02/2022 | SINO-1L | 7.5 | ABJF-20
182 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SINO-26 | Hrs | UTMN-1231
183 | WTHR | ARM | 2 | 02 Aug 0500 - 0700 | 5500 | 900416 | HAD HEAVY RAINS & LIGHTING. | WON | NA |  | 08/02/2022 | SINO-26 | 2 | UTMN-1231
184 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SINO-33L | Hrs | HRDH-1539
185 | SRVC | ARM | 8 | 02 Aug 1600 - 0045 | 10173 | 900370 | CIRC HOLE CLEAN WAITING ARAMCO V-SAT TO REGAIN COMMUNICATION AS PER GOC REQUIREMENT. - PUMP 1-2 BPM 96 PCF MUD CAP FROM BACKSIDE. | WO | NA |  | 08/02/2022 | SINO-33L | 8 | HRDH-1539
186 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SINO-37L | Hrs | HWYH-639
187 | FOT | RIG | 3 | 02 Aug 0200 - 0500 | 0 | 900421 | TROUBLESHOOTING TOP DRIVE PROBLEM (TDS STOP ROTATION). | RR | TDS |  | 08/02/2022 | SINO-37L | 3 | HWYH-639
188 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SND-2008 | Hrs | HRDH-1812
189 | STDP | RIG | 498 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/02/2022 | SND-2008 | 24 | HRDH-1812
190 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SND-2010 | Hrs | MNIF-869
191 | FOT | RIG | 1 | 02 Aug 1100 - 1200 | 7072 | 900402 | WHILE TESTING THE BOPE WITH TEST UNIT, FOUND CHART PIN IS BROKEN AND BACK PRESSURE VALVE IS LEAKING. | TF | BPV |  | 08/02/2022 | SND-2010 | 1 | MNIF-869
192 | FOT | RIG | 2 | 30 Jul 1600 - 1430 | 6439 | 900333 | RIG TROUBLESHOOT AND REPAIR DP HYDRAULIC POWER TONG. | TF | PEL |  | 08/02/2022 | SP-120 | .5 | MNIF-187
193 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SP-120 | Hrs | MNIF-187
194 | FRFM | ARM | 105 | 29 Jul 1730 - 0500 | 6340 | 900228 | CURE LOSSES AT WARA FORMATION WITH LCM PILL AND CEMENT PLUG. | LCIR | NA |  | 08/02/2022 | SP-120 | 23.5 | MNIF-187
195 | FOT | RIG | 2 | 30 Jul 1600 - 1430 | 6439 | 900333 | RIG TROUBLESHOOT AND REPAIR DP HYDRAULIC POWER TONG. | TF | PEL |  | 08/02/2022 | SP-120 | .5 | MNIF-187
196 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SP-122 | Hrs | HWYH-1178
197 | WTHR | ARM | 4 | 01 Aug 0300 - 0700 | 7515 | 900404 | SUSPEND OPERATION DUE TO SAND STORM AND HEAVY RAINING. | WON | NA |  | 08/02/2022 | SP-122 | 2 | HWYH-1178
198 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SP-154 | Hrs | SDGM-353
199 | IBHA | SDM | 23.5 | 02 Aug 0530 - 0500 | 7545 | 900383 | SLB RSS DD BHA UNABLE TO PASS TROUGH WINDOW. | BHA | MMOT |  | 08/02/2022 | SP-154 | 23.5 | SDGM-353
200 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SP-257 | Hrs | HZEM-162412
201 | LCRW | ARM | 63.5 | 31 Jul 1330 - 0500 | 445 | 900304 | 22" BHA STUCK WHILE TOOH WITH TOTAL LOSSES. | STUK | STRG |  | 08/02/2022 | SP-257 | 24 | HZEM-162412
202 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SP-260 | Hrs | HMYM-531812
203 | STBH | ARM | 35 | 01 Aug 1800 - 0500 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/02/2022 | SP-260 | 24 | HMYM-531812
204 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SSA-102 | Hrs | QTIF-693
205 | FOT | SPS | 7.25 | 02 Aug 2145 - 0500 | 16519 | 900417 | LOST SIGNAL, TROUBLE SHOOTING WITH TOOLS, NO SUCCESS | BHA | LWD |  | 08/02/2022 | SSA-102 | 7.25 | QTIF-693
206 | LHFL | RIG | 2.5 | 02 Aug 1030 - 1300 | 0 | 900400 | FIXING OBM LEAK FROM RIG FLOOR TO BOPE AREA&GROUND AND HOUSEKEEPING THE AROUND AREA. | RR | HSYS |  | 08/02/2022 | SSA-51 | 2.5 | MNIF-257
207 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SSA-51 | Hrs | MNIF-257
208 | FOT | OGS | 13.5 | 01 Aug 2000 - 0930 | 8536 | 900341 | GYRO TOOL FAILURE | TF | GYRO |  | 08/02/2022 | SSA-51 | 4.5 | MNIF-257
209 | LHFL | RIG | 2.5 | 02 Aug 1030 - 1300 | 0 | 900400 | FIXING OBM LEAK FROM RIG FLOOR TO BOPE AREA&GROUND AND HOUSEKEEPING THE AROUND AREA. | RR | HSYS |  | 08/02/2022 | SSA-51 | 2.5 | MNIF-257
210 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/02/2022 | SSA-5962 | Hrs | HRDH-2513
211 | WTHR | ARM | 3.5 | 01 Aug 0230 - 0600 | 4300 | 900345 | SUSPENDED OPERATION DUE BAD WEATHER (HIGH WIND & HEAVEY RAIN). | WON | NA |  | 08/02/2022 | SSA-5962 | 1 | HRDH-2513
212 | FOT | FMC | 1.5 | 03 Aug 1145 - 1315 | 5436 | 900433 | TROUBLESHOOTING FRANKS POWER TONG. | TF | CTRQ |  | 08/03/2022 | 088TE | 1.5 | QTIF-330
213 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | 088TE | Hrs | QTIF-330
214 | FOT | WEP | 65.75 | 31 Jul 1930 - 1445 | 5926 | 900302 | UNABLE TO RUN 4-1/2" HALLIBURTON COMPLETION SEAL THROUGH WFD MCL (7" CASING PATCH). | TF | CPCH |  | 08/03/2022 | 088TE | 8.25 | QTIF-330
215 | FOT | FMC | 1.5 | 03 Aug 1145 - 1315 | 5436 | 900433 | TROUBLESHOOTING FRANKS POWER TONG. | TF | CTRQ |  | 08/03/2022 | 088TE | 1.5 | QTIF-330
216 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-17 | Hrs | ZULF-1210
217 | HINW | ARM | 48 | 02 Aug 0500 - 0500 | 5490 | 900413 | MANSOORI SLICKLINE 3.5" SHIFTING TOOL STUCK WHILE POH @5490 FT DUE TO SAND PRODUCTION AFTER FLOW BACK TWO ZONES | STUK | SLICK |  | 08/03/2022 | ADC-17 | 24 | ZULF-1210
218 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-31 | Hrs | SDGM-1181
219 | STDP | RIG | 492.5 | 12 Jul 1930 - 0500 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/03/2022 | ADC-31 | 24 | SDGM-1181
220 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-41L | Hrs | SDGM-1244
221 | UVLC | ARM | 337.5 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 08/03/2022 | ADC-41L | 24 | SDGM-1244
222 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-42L | Hrs | SDGM-1258
223 | FOT | RIG | 5.25 | 03 Aug 2345 - 0500 | 10422 | 900473 | TROUBLESHOOT ON DYNAMIC BRAKE CHOPPER. DRAWWORKS UNABLE TO OPERATE WITH FULL SPEED. | RR | DWKS |  | 08/03/2022 | ADC-42L | 5.25 | SDGM-1258
224 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-43L | Hrs | UTMN-3118
225 | FRFM | TK3 | 98.5 | 30 Jul 0115 - 0500 | 12637 | 900352 | WHILE DRILLING LOST COMPLETE RETURNS IN KHUFF B CARBONATE. PUMPING LCM TO CURE THE LOSSES. | LCIR | NA |  | 08/03/2022 | ADC-43L | 24 | UTMN-3118
226 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-50 | Hrs | SFNY-1176
227 | LCRW | ARM | 303.25 | 19 Jul 1830 - 0500 | 0 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 08/03/2022 | ADC-50 | 24 | SFNY-1176
228 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-52 | Hrs | SDGM-1185
229 | HINW | BAW | 136 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/03/2022 | ADC-52 | 24 | SDGM-1185
230 | 12705 | 5315 | TO | N |  | BHA | POOH W/ 6-1/8" VORTEX BHA ON ELEVATOR F/ 11,558 FT TO TOW @ 5,315 FT.- CLEAR TIGHT SPOTS @11,558 FT, 10,885 FT & 10,690 FT. RUN BACK, PUMP SWEEP & CHC, POOH FREE.- MONITOR WELL ON TRIP TANK.- FLOW CHECK - WELL STATIC. PUMP SLUG. | 12705 | 11588 | RIG | 08/03/2022 | ADC-53L | DRLG | HRDH-530
231 | 12705 | 385 | TO | N |  | STDP | POOH W/ 6-1/8" VORTEX BHA FROM 5,315 FT TO TOP OF BHA @385 FT.- MONITOR WELL ON TRIP TANK.- FLOW CHECK AT TOP OF BHA - WELL STATIC. | 12705 | 5315 | RIG | 08/03/2022 | ADC-53L | DRLG | HRDH-530
232 | 12705 |  | HT | N |  | BHA | POOH AND L/D 6-1/8" VORTEX BHA.- HELD PJSM BEFORE REMOVE R/A SOURCE.- BIT DULL: 1-1-WT-A-X-I-BT-TD.- MONITOR WELL ON TRIP TANK- WELL STATIC | 12705 |  | SDM | 08/03/2022 | ADC-53L | DRLG | HRDH-530
233 | 12705 |  | HT | N | 3947 | BHA | HPJSM, P/U, M/U THRUBIT LOGGING ASSY & RIH TO 330 FT.- M/U WL- BIT S/N: JV1942, BIT SUB, FLOAT SUB ,XO, 1 X 4" HWDP, 6-1/8" DLR, 2 X 4" HWDP, 6-1/8" DLR, 7 X 4" HWDP.- MONITORED WELL ON TRIP TANK, STATIC. | 12705 |  | RIG | 08/03/2022 | ADC-53L | CT | HRDH-530
234 | 12705 | 5325 | TI | N | 3947 | STDP | RIH W/THRUBIT LOGGING ASSY ON DRIFTED 4" DP STDS F/330 FT TO 5,325 FT- WASH DOWN LAST STD WHILE ENTRING WINDOW (TOW 5,315 FT, BOW 5,325 FT).- FILL STRING AND BREAK CIRC EVERY 20 STD.- DRIFT EVERY STAND W/ 2.4" WL DRIFT WHILE RIH.- WELL MONITORED ON TRIP TANK. | 12705 | 330 | RIG | 08/03/2022 | ADC-53L | CT | HRDH-530
235 | 12705 | 7050 | RW | N | 3947 | BIT | REAM DOWN OPEN HOLE F/5,325 FT TO 6,949 FT SMOOTHLY.- WOB: 0-3 KLBS, RPM: 120 & TQ: 1-2 KFT-LBS, FR: 300 GPM, SPP: 1000 PSI.- CONTROL RPM TO 50 TILL SECOND REAMER OUT OF THE BOW@5325 FT.- DRIFT EVERY STAND W/ 2.4" WL DRIFT. | 12705 | 5325 | RIG | 08/03/2022 | ADC-53L | CT | HRDH-530
236 | 11 | OOS | Category | DOOS ID | HCRM | Out of Scope Summary | REAMING W/ THRU BIT | 11 | 3947 | 03 Aug 1800 | 08/03/2022 | ADC-53L | Type | HRDH-530
237
238
239 | FOT | RIG | 3.25 | 03 Aug 1930 - 2245 | 0 | 900429 | OBSERVED MANUAL TONG TORQUE LOAD CELL NOT FUNCTIONING PROPERLY, TROUBLESHOOT LOAD CELL & FIXED SAME, CORSSCHECK TORQUE VALUE W/ TDS, OK | RR | HSYS |  | 08/03/2022 | ADC-55L | 3.25 | UTMN-3171
240 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-55L | Hrs | UTMN-3171
241 | STBH | TK3 | 111.25 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/03/2022 | ADC-55L | 20.75 | UTMN-3171
242 | FOT | RIG | 3.25 | 03 Aug 1930 - 2245 | 0 | 900429 | OBSERVED MANUAL TONG TORQUE LOAD CELL NOT FUNCTIONING PROPERLY, TROUBLESHOOT LOAD CELL & FIXED SAME, CORSSCHECK TORQUE VALUE W/ TDS, OK | RR | HSYS |  | 08/03/2022 | ADC-55L | 3.25 | UTMN-3171
243 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-56L | Hrs | UTMN-3069
244 | FOT | RIG | 5 | 03 Aug 0630 - 1130 | 5920 | 900391 | OBSERVED DRILLING LINE ENTANGLED AND DAMAGE ON DRAWORKS DRUM. | RR | DWKS |  | 08/03/2022 | ADC-56L | 5 | UTMN-3069
245 | 7019 | 4660 | TI | E | 3965 | STDP | RIH TLC MDT-GR LOGGING TOOLS ON 5" DP FROM 747 FT TO 4,660 FT AT CONTROLLED SPEED.- FILL UP STRING EVERY 10 STANDS.- DRIFTED ALL STANDS RIH WITH 2.625" DRIFT.- MONITOR THE WELL WITH TRIP TANK | 7019 | 747 | RIG | 08/03/2022 | ADC-57L | LOG | KRSN-175
246 | 7019 |  | CIRC | E | 3965 | MPMP | CIRCULATE 1.5 STRING VOLUME W/ 79 PCF OBM.- MEANWHILE HPJSM & R/U WL SHEAVES. | 7019 |  | RIG | 08/03/2022 | ADC-57L | LOG | KRSN-175
247 | 7019 |  | OTH | E | 3965 | NA | LATCH WIRELINE CABLE PWCH INTO DWCH @ 4,482 FT AS PER WIRELINE ENGINEER INSTRUCTION.- M/U WL SES WITH FEED THRU WIRE LINE CABLE.- RIH SLB WL CABLE- PUMP DOWN @ 100 GPM, 40 PSI TO ASSIST TO LATCH.- FUNCTION TEST SLB TOOLS- PERFORM PULL TEST TO 3,300 LBS.- MONITORE WELL THROUGH TRIP TANK. | 7019 |  | SWL | 08/03/2022 | ADC-57L | LOG | KRSN-175
248 | 7019 | 6340 | TI | E | 3965 | STDP | RIH TLC MDT-GR LOGGING TOOLS ON 5" DP FROM 4,660 FT TO 6,340 FT AT CONTROLLED SPEED.- FILL UP STRING EVERY 10 STANDS.- DRIFTED ALL STANDS RIH WITH 2.625" DRIFT.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 4660 | RIG | 08/03/2022 | ADC-57L | LOG | KRSN-175
249 | 7019 | 6430 | LOG | E | 3965 | WLT | SLB WL TAKING PRESSURE POINTS, RECORD 12 POINTS OUT OF 50 POINTS AS PER ARAMCO RMD SCHEDULE.- PERFORM STICK TEST 3, 5, 8, 15 MIN BEFORE EVERY NEW FORMATION AND PERFORM 3, 8 MIN STICKING TEST BETWEEN PRESSURE POINTS.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 6340 | SWL | 08/03/2022 | ADC-57L | LOG | KRSN-175
250 | 45.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/03/2022 | ADC-57L | Type | KRSN-175
251
252
253 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-60 | Hrs | ABSF-218
254 | FOT | SCB | 40.5 | 02 Aug 1230 - 0500 | 4920 | 900422 | S/L RIH WTIH PULLING TOOL TO RETRIEVE SLB PLUS PLUG, LATCHED ON. JAR UP TO RETRIEVE THE PLUG, NEGATIVE. | TF | BP |  | 08/03/2022 | ADC-60 | 24 | ABSF-218
255 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADC-66L | Hrs | UTMN-3155
256 | WC20 | ARM | 24 | 03 Aug 0500 - 0500 | 11790 | 900430 | WHILE DRLG OBSERVED LEL 25% - PERFORMED KILLING OPERATION IN JILH FORMATION USING W&W METHOD. | WCNT | NA |  | 08/03/2022 | ADC-66L | 24 | UTMN-3155
257 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ADM-510 | Hrs | ABSF-229
258 | FOT | SDM | 22.5 | 03 Aug 0630 - 0500 | 6022 | 900435 | WHILE DRLG AT DEPTH 6022 FT, LOST COMMUNICATION WITH SDM MWD TOOL. | BHA | MWD |  | 08/03/2022 | ADM-510 | 22.5 | ABSF-229
259 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ARO-4001 | Hrs | MRJN-532
260 | STBH | ARM | 39.5 | 02 Aug 1145 - 0500 | 6642 | 900419 | GOT SUDDEN HOLE PACK OFF, STRING STALL AND STUCK. | STUK | BHA |  | 08/03/2022 | ARO-4001 | 23 | MRJN-532
261 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | DQ-49L | Hrs | HRDH-575
262 | STBH | TK2 | 201 | 26 Jul 2000 - 0500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 08/03/2022 | DQ-49L | 24 | HRDH-575
263 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ED-85A | Hrs | ZULF-2063
264 | CFST | BCM | 123 | 26 Jul 0145 - 0500 | 11328 | 900111 | CEMENT SET WHILE DISPLACING DV OPENNING PLUG. | CMT | NA |  | 08/03/2022 | ED-85A | 24 | ZULF-2063
265 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | ENS-108 | Hrs | ZULF-2014
266 | FOT | ENV | 310.75 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/03/2022 | ENS-108 | 24 | ZULF-2014
267 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | EXL-IA | Hrs | SFNY-1790
268 | FOT | RIG | 4.5 | 03 Aug 1230 - 1700 | 4692 | 900454 | DW DISC BRAKE MALFUNCTION DURING RIH. | RR | DWKS |  | 08/03/2022 | EXL-IA | 4.5 | SFNY-1790
269 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | HI-2 | Hrs | BRRI-436
270 | UVLC | ARM | .25 | 03 Aug 1730 - 1745 | 995 | 900439 | LOST TOTAL RETURNS @ 995'. | LCIR | NA |  | 08/03/2022 | HI-2 | .25 | BRRI-436
271 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | MP-1 | Hrs | MRJN-78
272 | FOT | NRT | 66.75 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/03/2022 | MP-1 | 24 | MRJN-78
273 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | NBR-210S | Hrs | DILM-100
274 | FOT | WDS | 3.25 | 03 Aug 0145 - 0500 | 6930 | 900438 | MWD TOOL FAILURE, SURVEY REAL QUALITY OUT OF RANGE. | BHA | MWD |  | 08/03/2022 | NBR-210S | 3.25 | DILM-100
275 | FOT | BAW | 2.25 | 03 Aug 0145 - 0400 | 6000 | 900455 | LOST COMMUNICATION W/ BAKER MPC TOOL WHILE RIH. TROUBLESHOOT, NO SUCCESS, POOH TO CHECK, FOUND TOOL WORKED AGAIN AT DEPTH 4000' | TF | WLT |  | 08/03/2022 | NBR-263S | 2.25 | QTIF-736
276 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | NBR-263S | Hrs | QTIF-736
277 | STBH | ARM | 86 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 08/03/2022 | NBR-263S | 20 | QTIF-736
278 | WC20 | ARM | 5 | 01 Aug 0400 - 0115 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 08/03/2022 | NBR-263S | 1.25 | QTIF-736
279 | FOT | BAW | 2.25 | 03 Aug 0145 - 0400 | 6000 | 900455 | LOST COMMUNICATION W/ BAKER MPC TOOL WHILE RIH. TROUBLESHOOT, NO SUCCESS, POOH TO CHECK, FOUND TOOL WORKED AGAIN AT DEPTH 4000' | TF | WLT |  | 08/03/2022 | NBR-263S | 2.25 | QTIF-736
280 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | NBR-304S | Hrs | HRDH-1958
281 | FOT | SPS | 33 | 01 Aug 1230 - 0130 | 17692 | 900376 | SPERRY SUN I-CRUISE FAILURE | BHA | RSS |  | 08/03/2022 | NBR-304S | 20 | HRDH-1958
282 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | NBR-654S | Hrs | HRDH-1150
283 | FOT | PKP | 18 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAILURE OF PACKER PLUS EQUIPMENTS ( FLOAT EQUIPMETS OR RUNNING TOOL TOP SEALS) | TF | HGRL |  | 08/03/2022 | NBR-654S | 16.25 | HRDH-1150
284 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | PA-218S | Hrs | HRDH-1941
285 | FOT | RIG | 19.25 | 02 Aug 0500 - 0630 | 14320 | 900397 | TROUBLE SHOOTING DRAWWORKS: CHANGE OUT TRACTION MOTOR. | RR | DWKS |  | 08/03/2022 | PA-218S | 1.5 | HRDH-1941
286 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | PN-9 | Hrs | MRJN-673
287 | CFST | HCM | 260.5 | 23 Jul 2300 - 1930 | 0 | 899983 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/03/2022 | PN-9 | 14.5 | MRJN-673
288 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | RM-74A | Hrs | HSBH-68
289 | IFCS | HCM | 31.25 | 02 Aug 1715 - 0030 | 4300 | 900414 | WHILE PREPARING TO MIX THE TAIL SLURRY, OBSERVE TAIL MIX FLUID EXCESSIVELY FOAMING. | CMT | NA |  | 08/03/2022 | RM-74A | 19.5 | HSBH-68
290 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SCTD-1 | Hrs | SDGM-1034
291 | FOT | RIG | 24 | 03 Aug 0500 - 0500 | 13090 | 900434 | D&M FAILED TO INTIATE SIDE TRACK. | BHA | MMOT |  | 08/03/2022 | SCTD-1 | 24 | SDGM-1034
292 | 10423 | 3029 | SET | C |  | PLUGN | S/L RIH & SET 2-7/8" PXN PLUG IN 2-7/8" XN-NIPPLE BELOW PACKER (3 RUNS) AT 3029 FT. - RIH & SET JUNCK CATCHER ABOVE PXN PLUG, POOH. | 10423 | 3029 | HSL | 08/03/2022 | SINO-1L | COMP | ABJF-20
293 | 10423 | 2989 | SET | C |  | PKR | HPJSM, R/U SURFACE LINES & PT SAME TO 3,500 PSI, SET BAKER PRAXIS ISOPAX PACKER @ 2,989 FT.- GRADUALLY PRESSURE UP TBG IN 500 PSI STEPS TO 3500 PSI.- HOLD 3500 PSI FOR 15 MIN, BLEED OFF SLOWLY TO ZERO.- OBSERVE TCA WHILE SETTING PACKER, NO RETURN. | 10423 | 2998 | BAL | 08/03/2022 | SINO-1L | COMP | ABJF-20
294 | 10423 |  | PTST | C |  | PKR | P/T BOTH TCA & TUBING TO 1000 PSI FOR 10 MIN WITH 70 PCF INHIBITED BRINE, HOLD.- TBG IS OPEN WHILE P/T TCA & TCA IS OPEN WHILE P/T TBG. | 10423 |  | RIG | 08/03/2022 | SINO-1L | COMP | ABJF-20
295 | 10423 |  | HT | C |  | ESP | BHGE PERFORMED CABLE INTEGRITY TEST & RECORD ELECTRICAL INTEGRITY & ZENITH READINGS. | 10423 |  | BAL | 08/03/2022 | SINO-1L | COMP | ABJF-20
296 | 10423 | 200 | SET | C |  | PLUGT | HPJSM, RU HAL SLICKLINE EQPT & LUBRICATOR, P/T SAME TO 2500 PSI, OK.- S/L RIH & SET 3-1/2" MONOLOCK PLUG AT 200 FT (TWO RUNS).- P/T PLUG TO 2500 PSI. - R/D SLICKLINE. | 10423 | 200 | HSL | 08/03/2022 | SINO-1L | COMP | ABJF-20
297 | 10423 |  | HT | C |  | TBG | BIW DISCONNECT PENETRATOR TEST LEADS FROM THE MAIN POWER CABLE ABOVE TBG HGR AND L/D 3-1/2" N.VAM LANDING JOINT. | 10423 |  | RIG | 08/03/2022 | SINO-1L | COMP | ABJF-20
298 | 10423 |  | ND | C |  | BNIP | HPJSM, N/D BELL NIPPLE & FLOWLINE. N/D V-DOOR & CAT WALK | 10423 |  | RIG | 08/03/2022 | SINO-1L | BOP | ABJF-20
299 | 10423 |  | ND | C |  | BOP | N/D BOP STACK & RELATED EQUIPMENT. | 10423 |  | RIG | 08/03/2022 | SINO-1L | BOP | ABJF-20
300 | 10423 |  | NU | C |  | TREE | HPJSM, N/U NEW 11" X 3-1/8'', 3M WG TUBING BONNET.- OILSERV R/U FLOW BACK CHOKE MANIFOLD, LINES & EQUIPMENTS OFFLINE. | 10423 |  | RIG | 08/03/2022 | SINO-1L | WH | ABJF-20
301 | 10423 |  | HT | C |  | ESP | BIW FEED CABLE THROUGH THE BONNET, TERMINATE WIRES, CHECK INTEGRITY & RECORD ZENITH READINGS. - P/T BONNET SEAL TO 2,500 PSI, HOLD. | 10423 |  | BAL | 08/03/2022 | SINO-1L | COMP | ABJF-20
302 | 10423 |  | NU | C |  | TREE | HPJSM, N/U NEW CIW 3-1/8'', 3M PRODUCTION TREE AND R/U SURFACE LINES & P/T PROD TREE TO 2,500 PSI AGAINST 3-1/2" MONOLOCK, HOLD. | 10423 |  | RIG | 08/03/2022 | SINO-1L | WH | ABJF-20
303 | 10423 |  | OTH | C |  | NA | OILSERV CONNECTED 3-1/8" 3K X 4-1/16" 10K ADAPTER, COFLEX HOSE TO X-MASS TREE WING VALVE & TEST MANIFOLD. | 10423 |  | OWT | 08/03/2022 | SINO-1L | LIFT | ABJF-20
304 | 10423 |  | RTRV | C |  | PLUGN | HPJSM, R/U HALL SLICKLINE EQPT & P/T LUBRICATOR TO 2500 PSI, OK.- RIH & RETRIEVE 3-1/2" MONOLOCK PLUG FROM 200 FT (2-RUNS).- RIH & RETRIEVED JUNK CATCHER ABOVE 2-7/8" PXN-PLUG.- RIH & RETRIEVE PXN PLUG FROM 2-7/8" XN-NIPPLE BELOW PACKER (2-RUN). | 10423 |  | HSL | 08/03/2022 | SINO-1L | COMP | ABJF-20
305 | 10423 |  | OTH | E |  | NA | HPJSM, SPOT BAKER GENERATOR & CONNECTED CABLE TO WELLHEAD JUNCTION BOX. | 10423 |  | RIG | 08/03/2022 | SINO-1L | TEST | ABJF-20
306 | 10423 |  | OTH | C | 3986 | NA | FLUSH ALL SURFACE OILSERV FLOWBACK EQUIPMENT WITH WATER.- R/U OILSERV SURFACE LINES, P/T OILSERV FLOWBACK PACKAGE AS PER STANDARD.- PT DOWNSTREAM TO 300 AND 1200 PSI (OIL AND GAS FLARE LINES AT SOUTH FLARE PITS, OIL MANIFOLD, SEPARATOR VALVES). - PT CHOKE MANIFOLD AND SURFACE SAFETY VALVE TO 300 PSI AND 2500 PSI.- M/U 4 1/16'' 3K X 3 1/8'' 3K ADAPTER TO WING VALVE, CONNECT COFLEX TO OILSERV CHOKE MANIFOLD, P/T SAME TO 300 / 2550 PSI. | 10423 |  | OWT | 08/03/2022 | SINO-1L | LIFT | ABJF-20
307 | 4 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | FUNCTION TEST ESP THROU OILSERV SMOKELESS BURNER PACKAGE. | 4 | 3986 | 03 Aug 0100 | 08/03/2022 | SINO-1L | Type | ABJF-20
308
309
310 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SINO-37L | Hrs | HWYH-639
311 | FOT | RIG | 12.5 | 02 Aug 0200 - 1430 | 0 | 900421 | TROUBLESHOOTING TOP DRIVE PROBLEM (TDS STOP ROTATION). | RR | TDS |  | 08/03/2022 | SINO-37L | 9.5 | HWYH-639
312 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SND-2008 | Hrs | HRDH-1812
313 | STDP | RIG | 521 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/03/2022 | SND-2008 | 23 | HRDH-1812
314 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SND-2010 | Hrs | MNIF-869
315 | HERR | RIG | 4.5 | 31 Jul 1500 - 1545 | 7072 | 900299 | FOUND CONVENTIONAL DV TOOL PLUGS MISSING, AFTER INVESTIGATION FOUND SANAD FORKLIFT OPERATOR MISTAKENLY LOADED FRIDAY NIGHT 7:00 PM IN THE GARBAGE TRUCK. | TF | FV |  | 08/03/2022 | SND-2010 | 2.5 | MNIF-869
316 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SP-110 | Hrs | MNIF-142
317 | UNKN | RIG | 21.5 | 03 Aug 0730 - 0500 | 0 | 900424 | SHUT DOWN ALL OPERATION & INVESTIGATE CONTRACTOR EMPLOYEE FALL INCIDENT | HSEI | NA |  | 08/03/2022 | SP-110 | 21.5 | MNIF-142
318 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SP-120 | Hrs | MNIF-187
319 | FRFM | ARM | 113.5 | 29 Jul 1730 - 1330 | 6340 | 900228 | CURE LOSSES AT WARA FORMATION WITH LCM PILL AND CEMENT PLUG. | LCIR | NA |  | 08/03/2022 | SP-120 | 8.5 | MNIF-187
320 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SP-154 | Hrs | SDGM-353
321 | IBHA | SDM | 31.5 | 02 Aug 0530 - 1300 | 7545 | 900383 | SLB RSS DD BHA UNABLE TO PASS TROUGH WINDOW. | BHA | MMOT |  | 08/03/2022 | SP-154 | 8 | SDGM-353
322 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SP-165 | Hrs | FDHL-146
323 | ULCM | ARM | 5.25 | 03 Aug 2345 - 0500 | 5725 | 900437 | CURE PARTIAL LOSSES WITH LCM PILL. | LCIR | LCM |  | 08/03/2022 | SP-165 | 5.25 | FDHL-146
324 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SP-260 | Hrs | HMYM-531812
325 | STBH | ARM | 59 | 01 Aug 1800 - 0500 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/03/2022 | SP-260 | 24 | HMYM-531812
326 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SP-306 | Hrs | MNIF-193
327 | FOT | RIG | 3 | 03 Aug 2100 - 0000 | 19728 | 900428 | OBSERVED ANNULAR ELEMENT NOT RETRACTING COMPLETELY. | BOP | BOP |  | 08/03/2022 | SP-306 | 3 | MNIF-193
328 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SSA-102 | Hrs | QTIF-693
329 | FOT | SPS | 25.75 | 02 Aug 2000 - 2215 | 16519 | 900417 | LOST SIGNAL, TROUBLE SHOOTING WITH TOOLS, NO SUCCESS. CALL 16519' TD DUE TO FAILURE | BHA | LWD |  | 08/03/2022 | SSA-102 | 16.75 | QTIF-693
330 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SSA-303 | Hrs | HRDH-2411
331 | FOT | RIG | 3 | 03 Aug 0200 - 0500 | 10240 | 900453 | WHILE BREAKING OUT TEST ASSEMBLY HPU UNIT STOPPED FUNCTIONING | RR | HSYS |  | 08/03/2022 | SSA-303 | 3 | HRDH-2411
332 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SSA-5891 | Hrs | HRDH-1205
333 | FOT | RIG | 6.5 | 03 Aug 2230 - 0500 | 11526 | 900472 | TOP DRIVE OVER HEATED. | RR | TDS |  | 08/03/2022 | SSA-5891 | 6.5 | HRDH-1205
334 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SSA-5962 | Hrs | HRDH-2513
335 | FOT | WDS | 15.5 | 03 Aug 1030 - 0400 | 4350 | 900432 | WFD DIR TOOLS LOST COMMUNICATION BETWEEN RSS AND MWD. | BHA | MWD |  | 08/03/2022 | SSA-5962 | 15.5 | HRDH-2513
336 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | SSA-5974 | Hrs | HRDH-2187
337 | FOT | RIG | 10 | 03 Aug 1900 - 0500 | 7547 | 900452 | LOST COMMUNICATION WITH TOP DRIVE SYSTEM. | RR | TDS |  | 08/03/2022 | SSA-5974 | 10 | HRDH-2187
338 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/03/2022 | T902 | Hrs | MHWZ-906
339 | DRSR | RIG | 7.25 | 03 Aug 1500 - 2215 | 1782 | 900440 | BELL NIPPLE SPACE OUT IS INCORRECT. | RR | CSYS |  | 08/03/2022 | T902 | 7.25 | MHWZ-906
340 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | 088TE | Hrs | QTIF-330
341 | FOT | HCO | 3.75 | 04 Aug 0945 - 1330 | 7464 | 900516 | WHILE LANDING THE TBG HANGER , HAD 5KLB SLACK AT TOP OF PBR. | TF | PKR |  | 08/04/2022 | 088TE | 3.75 | QTIF-330
342 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-17 | Hrs | ZULF-1210
343 | HINW | ARM | 72 | 02 Aug 0500 - 0500 | 5490 | 900413 | MANSOORI SLICKLINE 3.5" SHIFTING TOOL STUCK WHILE POH @5490 FT DUE TO SAND PRODUCTION AFTER FLOW BACK TWO ZONES | STUK | SLICK |  | 08/04/2022 | ADC-17 | 24 | ZULF-1210
344 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-31 | Hrs | SDGM-1181
345 | STDP | RIG | 506 | 12 Jul 1930 - 1830 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/04/2022 | ADC-31 | 13.5 | SDGM-1181
346 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-41L | Hrs | SDGM-1244
347 | UVLC | ARM | 361.5 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 08/04/2022 | ADC-41L | 24 | SDGM-1244
348 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-43L | Hrs | UTMN-3118
349 | FRFM | TK3 | 118.75 | 30 Jul 0115 - 0130 | 12637 | 900352 | WHILE DRILLING LOST COMPLETE RETURNS IN KHUFF B CARBONATE. PUMPING LCM TO CURE THE LOSSES. | LCIR | NA |  | 08/04/2022 | ADC-43L | 20.25 | UTMN-3118
350 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-50 | Hrs | SFNY-1176
351 | LCRW | ARM | 327.25 | 19 Jul 1830 - 0500 | 0 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 08/04/2022 | ADC-50 | 24 | SFNY-1176
352 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-52 | Hrs | SDGM-1185
353 | HINW | BAW | 155.5 | 29 Jul 1300 - 0030 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/04/2022 | ADC-52 | 19.5 | SDGM-1185
354 | 12705 | 12705 | RW | N | 3947 | BIT | REAM DOWN 6-1/8" OH F/6,949 FT TO 12,705 FT SMOOTHLY.- WOB: 0-4 KLBS, RPM: 120 & TQ: 2-6 KFT-LBS, FR: 300 GPM, SPP: 1850 PSI.- DRIFT EVERY STD W/ 2.4" WL DRIFT. | 12705 | 6949 | RIG | 08/04/2022 | ADC-53L | CT | HRDH-530
355 | 12705 |  | CIRC | N | 3947 | MPMP | SWEPT HOLE WITH 20/20 BBLS LOW VIS / HI WT PILL THREE TIMES & CHC UNTIL SHAKERS CLEAN.- FR: 320 GPM, SPP: 1,850 PSI- RECIPROCATE STRING UP & DOWN WHILE CIRCULATION.- MEANWHILE HPJSM AND PREPARED FOR THRU-BIT LOGGING OPERATIONS & R/U SHEAVES.- DISCUSSED W/L R/U PROCEDURE, HAZARDS & RISK MITIGATION. | 12705 |  | RIG | 08/04/2022 | ADC-53L | CT | HRDH-530
356 | 12705 |  | OTH | E | 3947 | NA | SPACED OUT FOR SES : P/U TWO STDS, TRY TO SLACK OF 50 FT , NOT MOVING DOWN.REAM UP DOWN 4 TIME THEN TRY TO SLACK OFF WITH CIRCULATION SEVERAL TIMES WITHOUT SUCCESS.DISCUSS WITH ENGINEERING AND DECIDE TO DISPLACE TO OBM TO REDUCE FRICTION FACTOR. BACK TO BTM W/REAMING DOWN. | 12705 |  | SWL | 08/04/2022 | ADC-53L | LOG | HRDH-530
357 | 12705 | 12000 | CIRC | N | 3947 | MPMP | DISPLACE WELL TO 79 PCF OBM...ON GOING ART.. | 12705 | 12675 | RIG | 08/04/2022 | ADC-53L | CT | HRDH-530
358 | 35 | OOS | Category | DOOS ID | HCRM | Out of Scope Summary | REAMING W/ THRU BIT | 24 | 3947 | 03 Aug 1800 | 08/04/2022 | ADC-53L | Type | HRDH-530
359
360
361 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-55L | Hrs | UTMN-3171
362 | STBH | TK3 | 135.25 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/04/2022 | ADC-55L | 24 | UTMN-3171
363 | 7019 | 6820 | LOG | E | 3965 | WLT | SLB WL TAKING PRESSURE POINTS, RECORD 39 POINTS OUT OF 50 POINTS AS PER ARAMCO RMD SCHEDULE.- PERFORM STICK TEST 3, 5, 8, 15 MIN BEFORE EVERY NEW FORMATION AND PERFORM 3, 8 MIN STICKING TEST BETWEEN PRESSURE POINTS.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 6430 | SWL | 08/04/2022 | ADC-57L | LOG | KRSN-175
364 | 69.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/04/2022 | ADC-57L | Type | KRSN-175
365
366
367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-60 | Hrs | ABSF-218
368 | FOT | SCB | 48.5 | 02 Aug 1230 - 1300 | 4920 | 900422 | S/L RIH WTIH PULLING TOOL TO RETRIEVE SLB PLUS PLUG, LATCHED ON. JAR UP TO RETRIEVE THE PLUG, NEGATIVE. | TF | BP |  | 08/04/2022 | ADC-60 | 8 | ABSF-218
369 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADC-66L | Hrs | UTMN-3155
370 | WC20 | ARM | 25.5 | 03 Aug 0500 - 0630 | 11790 | 900430 | WHILE DRLG OBSERVED LEL 25% - PERFORMED KILLING OPERATION IN JILH FORMATION USING W&W METHOD. | WCNT | NA |  | 08/04/2022 | ADC-66L | 1.5 | UTMN-3155
371 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADM-337 | Hrs | MRJN-900
372 | XTTE | BCT | 10.25 | 04 Aug 1845 - 0500 | 13019 | 900462 | LEAK IN CHICKSAN LINE, BAD SEAL. | TF | CTU |  | 08/04/2022 | ADM-337 | 10.25 | MRJN-900
373 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ADM-510 | Hrs | ABSF-229
374 | FOT | SDM | 29 | 03 Aug 0630 - 1130 | 6022 | 900435 | WHILE DRLG AT DEPTH 6022 FT, LOST COMMUNICATION WITH SDM MWD TOOL. | BHA | MWD |  | 08/04/2022 | ADM-510 | 6.5 | ABSF-229
375 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ARO-4001 | Hrs | MRJN-532
376 | STBH | ARM | 63.5 | 02 Aug 1145 - 0500 | 6642 | 900419 | GOT SUDDEN HOLE PACK OFF, STRING STALL AND STUCK. | STUK | BHA |  | 08/04/2022 | ARO-4001 | 24 | MRJN-532
377 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | DQ-49L | Hrs | HRDH-575
378 | STBH | TK2 | 211 | 26 Jul 2000 - 1500 | 3232 | 900195 | WHILE BACKRAMING @ 3232 FT, SUDDENTLY LOST ROTARY, ATTEMPT TO MOVE PIPE DOWN WITH NO SUCCESS. OBSERVE PIPE STUCK | STUK | BHA |  | 08/04/2022 | DQ-49L | 10 | HRDH-575
379 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ED-85A | Hrs | ZULF-2063
380 | CFST | BCM | 147 | 26 Jul 0145 - 0500 | 11328 | 900111 | CEMENT SET WHILE DISPLACING DV OPENNING PLUG. | CMT | NA |  | 08/04/2022 | ED-85A | 24 | ZULF-2063
381 | FPMP | RIG | 1.5 | 04 Aug 1000 - 1130 | 10020 | 900513 | UNABLE TO REACH DESIRED GPM FROM MUD PUMP. | RR | MPMP |  | 08/04/2022 | ENS-108 | 1.5 | ZULF-2014
382 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | ENS-108 | Hrs | ZULF-2014
383 | FOT | ENV | 333.25 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/04/2022 | ENS-108 | 22.5 | ZULF-2014
384 | FPMP | RIG | 1.5 | 04 Aug 1000 - 1130 | 10020 | 900513 | UNABLE TO REACH DESIRED GPM FROM MUD PUMP. | RR | MPMP |  | 08/04/2022 | ENS-108 | 1.5 | ZULF-2014
385 | MATL | BDF | 5.5 | 04 Aug 2330 - 0500 | 5205 | 900496 | MUD ENGINEERS DID NOT HAVE ENOUGH CHEMICALS ON THE RIG TO WEIGHT UP THE RESERVE PITS | WO | NA |  | 08/04/2022 | EXL-IA | 5.5 | SFNY-1790
386 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | EXL-IA | Hrs | SFNY-1790
387 | FOT | RIG | 4.5 | 04 Aug 0930 - 1400 | 4702 | 900493 | ROTARY TABLE NOT FUCTIONING | RR | RSYS |  | 08/04/2022 | EXL-IA | 4.5 | SFNY-1790
388 | MATL | BDF | 5.5 | 04 Aug 2330 - 0500 | 5205 | 900496 | MUD ENGINEERS DID NOT HAVE ENOUGH CHEMICALS ON THE RIG TO WEIGHT UP THE RESERVE PITS | WO | NA |  | 08/04/2022 | EXL-IA | 5.5 | SFNY-1790
389 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | JACK-202 | Hrs | THRY-829
390 | FOT | RIG | 6.5 | 04 Aug 1830 - 0100 | 122 | 900495 | AFTER POOH TO CASING SHOE DURING WIPER TRIP MAST LIGHT SHUT DOWN | RR | PSYS |  | 08/04/2022 | JACK-202 | 6.5 | THRY-829
391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | MP-1 | Hrs | MRJN-78
392 | FOT | NRT | 90.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/04/2022 | MP-1 | 24 | MRJN-78
393 | FOT | SPS | 6 | 04 Aug 2300 - 0500 | 0 | 900519 | HAD MWD TOOLS FAILURE WHILE SURFACE TEST AFTER PICK UP. SPERRY SUN NOT ABLE TO LOAD DATA TO MWD TOOLS AFTER PICK UP. | BHA | MWD |  | 08/04/2022 | NBR-196S | 6 | SDGM-1235
394 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | NBR-196S | Hrs | SDGM-1235
395 | FOT | SPS | 2.5 | 04 Aug 2030 - 2300 | 0 | 900476 | LOST TIME TO SPERRY SUN AS WE HAVE TO RE-RUN SPERRY BHA TO RECOVER LOST DATA FROM PREVIOUS DRILLING RUN. | BHA | MWD |  | 08/04/2022 | NBR-196S | 2.5 | SDGM-1235
396 | FOT | SPS | 6 | 04 Aug 2300 - 0500 | 0 | 900519 | HAD MWD TOOLS FAILURE WHILE SURFACE TEST AFTER PICK UP. SPERRY SUN NOT ABLE TO LOAD DATA TO MWD TOOLS AFTER PICK UP. | BHA | MWD |  | 08/04/2022 | NBR-196S | 6 | SDGM-1235
397 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | NBR-210S | Hrs | DILM-100
398 | FOT | WDS | 13.75 | 03 Aug 0145 - 1530 | 6930 | 900438 | MWD TOOL FAILURE, SURVEY REAL QUALITY OUT OF RANGE. | BHA | MWD |  | 08/04/2022 | NBR-210S | 10.5 | DILM-100
399 | FOT | BAW | 22.25 | 03 Aug 0145 - 0300 | 6000 | 900455 | LOST COMMUNICATION W/ BAKER MPC TOOL WHILE RIH, TROUBLESHOOT, NO SUCCESS, POOH TO CHECK & RIH AGAIN. | TF | WLT |  | 08/04/2022 | NBR-263S | 20 | QTIF-736
400 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | NBR-263S | Hrs | QTIF-736
401 | WC20 | ARM | 9.75 | 01 Aug 0600 - 2100 | 13970 | 900348 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, | WCNT | NA |  | 08/04/2022 | NBR-263S | 1 | QTIF-736
402 | WC20 | ARM | 6 | 01 Aug 0400 - 0600 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, SUSPECT BALLOONING EFFECT, BULLHEAD 102 PCF MUD ON ANNULAS TILL WELL STATIC. | WCNT | NA |  | 08/04/2022 | NBR-263S | 1 | QTIF-736
403 | FOT | BAW | 22.25 | 03 Aug 0145 - 0300 | 6000 | 900455 | LOST COMMUNICATION W/ BAKER MPC TOOL WHILE RIH, TROUBLESHOOT, NO SUCCESS, POOH TO CHECK & RIH AGAIN. | TF | WLT |  | 08/04/2022 | NBR-263S | 20 | QTIF-736
404 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | NBR-654S | Hrs | HRDH-1150
405 | FOT | PKP | 29 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. | TF | HGRL |  | 08/04/2022 | NBR-654S | 11 | HRDH-1150
406 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | NBR-797S | Hrs | UTMN-3119
407 | FOT | GOC | 1 | 04 Aug 2345 - 0045 | 838 | 900461 | EXCESS TIME DUE TO ALGAITH CREW POOR EXPERIENCE LEADING TO MULTIPLE CASING CROSS THREADS. SPIDER SLIPS NOT WORKING | TF | CTRQ |  | 08/04/2022 | NBR-797S | 1 | UTMN-3119
408 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | RM-74A | Hrs | HSBH-68
409 | IFCS | HCM | 55.25 | 02 Aug 1715 - 0500 | 4300 | 900414 | WHILE PREPARING TO MIX THE TAIL SLURRY FOR 2ND STAGE, OBSERVE TAIL MIX FLUID EXCESSIVELY FOAMING. | CMT | NA |  | 08/04/2022 | RM-74A | 24 | HSBH-68
410 | FOT | RIG | 14 | 04 Aug 0930 - 2330 | 12792 | 900512 | MWD FAILURE | BHA | MMOT |  | 08/04/2022 | SCTD-1 | 14 | SDGM-1034
411 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SCTD-1 | Hrs | SDGM-1034
412 | FOT | RIG | 34 | 03 Aug 0500 - 0500 | 12790 | 900434 | D&M FAILED TO INTIATE SIDE TRACK. | BHA | MMOT |  | 08/04/2022 | SCTD-1 | 10 | SDGM-1034
413 | FOT | RIG | 14 | 04 Aug 0930 - 2330 | 12792 | 900512 | MWD FAILURE | BHA | MMOT |  | 08/04/2022 | SCTD-1 | 14 | SDGM-1034
414 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SCTD-2 | Hrs | HRDH-2148
415 | FOT | RIG | 19.5 | 04 Aug 0600 - 0130 | 13055 | 900514 | MUD MOTOR IS JAMMED. POH TO SURFACE TO CHANGE BHA | BHA | MMOT |  | 08/04/2022 | SCTD-2 | 19.5 | HRDH-2148
416 | 10423 |  | PJSM | E |  | NA | HPJSM WITH ESP CREW, RIG CREW AND OILSERV TEAM, EXPLAINED ESP FUNCTION TEST PROCEDURE AND FLARING FLOWBACK & HIGHLIGHTED RISKS & HAZARD. | 10423 |  | TK2 | 08/04/2022 | SINO-1L | TEST | ABJF-20
417 | 10423 |  | OTH | E |  | NA | BAKER START UP ESP PUMP ON FORWARD DIRC , CHANGED TO RIGHT DIRC & START ESP FUNCTION TEST, OPEN & FLOW WELL TO WASTE PIT THROUGH ADJUSTABLE CHOKE UNTIL GOT TRACE OF OIL. | 10423 |  | BAL | 08/04/2022 | SINO-1L | TEST | ABJF-20
418 | 10423 |  | OTH | E |  | NA | LINED UP TO OILSERV SEPARATOR & CONT'D ESP FUNCTION TEST BY FLOWING WELL TO OILSERV SMOKELESS BURNER.- UPSTREAM PRESSURE: 860 PSI, DOWNSTREAM PRESSURE: 100 PSI & FERQUENCY: 45 HZ, 31 AMP.- OIL: 15%. | 10423 |  | OWT | 08/04/2022 | SINO-1L | TEST | ABJF-20
419 | 10423 |  | OTH | E |  | NA | SUSPENDED OPERATION DUE TO WIND DIRECTION. | 10423 |  | OWT | 08/04/2022 | SINO-1L | SUSP | ABJF-20
420 | 10423 |  | OTH | E | 4009 | NA | SUSPENDED OPERATION DUE TO WIND DIRECTION. (O.O.S). | 10423 |  | OWT | 08/04/2022 | SINO-1L | SUSP | ABJF-20
421 | 11 | OOSS | Category | DOOS ID | WTST | Out of Scope Summary | WAIT ON WIND DIRECTION | 11 | 4009 | 04 Aug 1800 | 08/04/2022 | SINO-1L | Type | ABJF-20
422
423
424 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SINO-26 | Hrs | UTMN-1231
425 | FOT | RIG | 1 | 04 Aug 0000 - 0100 | 8570 | 900497 | FOUND LEAK IN TDS SAVER SUB. | RR | TDS |  | 08/04/2022 | SINO-26 | 1 | UTMN-1231
426 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SND-2008 | Hrs | HRDH-1812
427 | STDP | RIG | 545 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/04/2022 | SND-2008 | 24 | HRDH-1812
428 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SNF036 | Hrs | MRJN-901
429 | FOT | GEP | 8.5 | 04 Aug 0730 - 1600 | 296 | 900458 | UNABLE TO INSTALL 13-3/8" CORROSION CAP | WH | WH |  | 08/04/2022 | SNF036 | 8.5 | MRJN-901
430 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SP-110 | Hrs | MNIF-142
431 | UNKN | RIG | 45.5 | 03 Aug 0730 - 0500 | 0 | 900424 | SHUT DOWN ALL OPERATION & INVESTIGATE CONTRACTOR EMPLOYEE FALL INCIDENT | HSEI | NA |  | 08/04/2022 | SP-110 | 24 | MNIF-142
432 | FOT | WDS | 21 | 04 Aug 0600 - 0500 | 4305 | 900518 | ATTEMPTS TO CLOSE WFD PBL, NO SUCCESS - TRIP OUT TO CHECK THE TOOL. | TF | DDNRV |  | 08/04/2022 | SP-165 | 21 | FDHL-146
433 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SP-165 | Hrs | FDHL-146
434 | ULCM | ARM | 6.25 | 03 Aug 2345 - 0600 | 5725 | 900437 | CURE PARTIAL LOSSES WITH LCM PILL. | LCIR | LCM |  | 08/04/2022 | SP-165 | 1 | FDHL-146
435 | FOT | WDS | 21 | 04 Aug 0600 - 0500 | 4305 | 900518 | ATTEMPTS TO CLOSE WFD PBL, NO SUCCESS - TRIP OUT TO CHECK THE TOOL. | TF | DDNRV |  | 08/04/2022 | SP-165 | 21 | FDHL-146
436 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SP-257 | Hrs | HZEM-162412
437 | LCRW | ARM | 98.75 | 31 Jul 1330 - 0500 | 445 | 900304 | 22" BHA STUCK WHILE TOOH WITH TOTAL LOSSES. | STUK | STRG |  | 08/04/2022 | SP-257 | 11.25 | HZEM-162412
438 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SP-260 | Hrs | HMYM-531812
439 | STBH | ARM | 83 | 01 Aug 1800 - 0500 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/04/2022 | SP-260 | 24 | HMYM-531812
440 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SSA-202 | Hrs | QTIF-191
441 | FOT | ARN | 20.5 | 04 Aug 0830 - 0500 | 18300 | 900457 | V-SAT TECHNICIAN REPLACE MODEM AND TROUBLE SHOOT W/ V-SAT DUE LOST COMMUNICATION BETWEEN SPS AND GOC. | TF | VSAT |  | 08/04/2022 | SSA-202 | 20.5 | QTIF-191
442 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SSA-303 | Hrs | HRDH-2411
443 | FOT | RIG | 11 | 03 Aug 0200 - 1300 | 10240 | 900453 | WHILE BREAKING OUT TEST ASSEMBLY HPU UNIT STOPPED FUNCTIONING | RR | HSYS |  | 08/04/2022 | SSA-303 | 8 | HRDH-2411
444 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SSA-5891 | Hrs | HRDH-1205
445 | FOT | RIG | 21.75 | 03 Aug 2230 - 0500 | 11526 | 900472 | TOP DRIVE OVER HEATED. | RR | TDS |  | 08/04/2022 | SSA-5891 | 15.25 | HRDH-1205
446 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/04/2022 | SSA-5969 | Hrs | UTMN-3148
447 | UVLC | ARM | 24 | 03 Aug 2330 - 0500 | 2737 | 900494 | COMPLETE LOSS DURING DRILLING SFNY FORMATION | LCIR | NA |  | 08/04/2022 | SSA-5969 | 18.5 | UTMN-3148
448 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADC-17 | Hrs | ZULF-1210
449 | HINW | ARM | 96 | 02 Aug 0500 - 0500 | 5490 | 900413 | MANSOORI SLICKLINE 3.5" SHIFTING TOOL STUCK WHILE POH @5490 FT DUE TO SAND PRODUCTION AFTER FLOW BACK TWO ZONES | STUK | SLICK |  | 08/05/2022 | ADC-17 | 24 | ZULF-1210
450 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADC-31 | Hrs | SDGM-1181
451 | STDP | RIG | 540.5 | 12 Jul 1930 - 0500 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/05/2022 | ADC-31 | 24 | SDGM-1181
452 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADC-32 | Hrs | ANDR-1010
453 | FOT | RIG | 3.5 | 05 Aug 2300 - 0230 | 2567 | 900541 | TOP DRIVE TILT PISTON IS NOT WORKING PROPERLY. | RR | TDS |  | 08/05/2022 | ADC-32 | 3.5 | ANDR-1010
454 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADC-34 | Hrs | UTMN-2309
455 | IBSL | SEC | 11 | 04 Aug 0000 - 1100 | 2481 | 900500 | LOW ROP | LROP | BIT |  | 08/05/2022 | ADC-34 | 6 | UTMN-2309
456 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADC-41L | Hrs | SDGM-1244
457 | UVLC | ARM | 385.5 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 08/05/2022 | ADC-41L | 24 | SDGM-1244
458 | FOT | SBT | 2.5 | 05 Aug 2345 - 0215 | 1994 | 900545 | OBSERVED INCREASE IN SPP 1275 PSI TO 1675 PSI, SLB CONFIREMED UR DE-ACTIVATED, SLB TROUBLESHOOT WITH NO SUCCESS TO ACTIVATED | TF | BIT |  | 08/05/2022 | ADC-50 | 2.5 | SFNY-1176
459 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADC-50 | Hrs | SFNY-1176
460 | LCRW | ARM | 348.75 | 19 Jul 1830 - 0500 | 0 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 08/05/2022 | ADC-50 | 21.5 | SFNY-1176
461 | FOT | SBT | 2.5 | 05 Aug 2345 - 0215 | 1994 | 900545 | OBSERVED INCREASE IN SPP 1275 PSI TO 1675 PSI, SLB CONFIREMED UR DE-ACTIVATED, SLB TROUBLESHOOT WITH NO SUCCESS TO ACTIVATED | TF | BIT |  | 08/05/2022 | ADC-50 | 2.5 | SFNY-1176
462 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADC-52 | Hrs | SDGM-1185
463 | HINW | BAW | 176 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/05/2022 | ADC-52 | 20.5 | SDGM-1185
464 | 12705 |  | CIRC | N | 3947 | MPMP | CONT. TO DISPLACE WELL TO 79 PCF OBM, CIRCULATED TO CONDITION THE MUD.- FR: 300 GPM, SPP: 2,200 PSI.- FLOW CHECK - WELL STATIC.- CHECK P/U WT ( 165 - 175 KLB ) & S/O WT ( 105 - 115 KLB) - OK | 12705 |  | RIG | 08/05/2022 | ADC-53L | CT | HRDH-530
465 | 12705 |  | OTH | E | 3947 | NA | SPACED OUT FOR SES & LOGGING TOOL, M/U LOGGING TOOLS.- P/U SES AND WL TOOLS ONE BY ONE, M/U CABLE SES, - RIH W/ LOGGING TOOLS, PUMP DOWN THE TOOLS, CONFIRMED THE LATCH, ACTIVATE TOOL & RELEASE CABLE HEAD, POOH & L/D SES. | 12705 |  | SWL | 08/05/2022 | ADC-53L | LOG | HRDH-530
466 | 12705 | 5060 | LOG | E | 3947 | WLT | LOG UP OH WHILE POOH W/THRUBIT ASSY F/12,673 FT TO 5,060 FT POOH WITH THRUBIT BHA & L/D, .- TRIPPING SPEED 30 FT/MIN AS PER SLB WL.- MONITORING WELL ON TRIP TANK & TRIP SHEET, WELL STATIC.- FLOW CHECK : WELL STATIC | 12705 | 12673 | SWL | 08/05/2022 | ADC-53L | LOG | HRDH-530
467 | 12705 |  | OTH | E | 3947 | NA | HPJSM, M/U SES, RUN CABLE HEAD, RETRIEVED W/L LOGGING TOOLS & L/D SAME. | 12705 |  | SWL | 08/05/2022 | ADC-53L | LOG | HRDH-530
468 | 12705 | 861 | TO | E | 3947 | STDP | POOH W/THRU-BIT ASSY F/ 5,060 FT TO 861 FT...ON GOING ART.- MONITOR WELL ON TRIP TANK | 12705 | 5060 | RIG | 08/05/2022 | ADC-53L | LOG | HRDH-530
469 | 59 | OOS | Category | DOOS ID | HCRM | Out of Scope Summary | REAMING W/ THRU BIT | 24 | 3947 | 03 Aug 1800 | 08/05/2022 | ADC-53L | Type | HRDH-530
470
471
472 | 7019 | 6980 | LOG | E | 3965 | WLT | SLB WL TAKING PRESSURE POINTS, RECORD 50 POINTS OUT OF 50 POINTS AS PER ARAMCO RMD SCHEDULE.- PERFORM STICK TEST 3, 5, 8, 15 MIN BEFORE EVERY NEW FORMATION AND PERFORM 3, 8 MIN STICKING TEST BETWEEN PRESSURE POINTS.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 6820 | SWL | 08/05/2022 | ADC-57L | LOG | KRSN-175
473 | 7019 |  | CIRC | E | 3965 | MPMP | CIRC HOLE CLEAN AND CONDITION MUD IN/OUT 79 PCF PRIOR TO SAMPLING.- FLOW CHECK WELL STATIC. | 7019 |  | RIG | 08/05/2022 | ADC-57L | LOG | KRSN-175
474 | 7019 | 6979 | LOG | E | 3965 | WLT | SLB WL TAKING SAMPLING WHILE POOH AS PER RMD REQUEST.- SCANNING AROUND 6,980 FT FOR BEST MOBILITY.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. - MAX STATIONARY TIME: 4 HRS.- SAMPLE #1 @ 6,979 FT, SECOND SESSION IN PROGRESS.- TOTAL 0 SAMPLE OUT OF 18.- TOTAL PUMP OUT 180L AT RPT, OVERBALANCE AFTER PUMP OUT 588 PSI.- MONITOR WELL ON TRIP TANK. | 7019 | 6980 | SWL | 08/05/2022 | ADC-57L | LOG | KRSN-175
475 | 93.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/05/2022 | ADC-57L | Type | KRSN-175
476
477
478 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADES-13 | Hrs | HWYH-163
479 | FOT | RIG | 2 | 05 Aug 1400 - 1600 | 5810 | 900537 | DRILLER'S CONTROL CONSOLE NO RESPOND. | RR | MPMP |  | 08/05/2022 | ADES-13 | 2 | HWYH-163
480 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADES-157 | Hrs | HRDH-642
481 | STOP | ARN | 5.5 | 05 Aug 1630 - 2200 | 12690 | 900539 | UNABLE TO SEND REAL TIME DRILLING PARAMETERS TO GOC DUE TO V-SAT COMMUNICATION DOWN. | WO | NA |  | 08/05/2022 | ADES-157 | 5.5 | HRDH-642
482 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADM-266 | Hrs | MRJN-309
483 | WOTO | HCB | 10.25 | 05 Aug 1015 - 2030 | 3000 | 900464 | HALLIBURTON STORM VALVE FOR 9-5/8" RTTS STUCK IN OPEN POSITION. | WO | NA |  | 08/05/2022 | ADM-266 | 10.25 | MRJN-309
484 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADM-337 | Hrs | MRJN-900
485 | XTTE | BCT | 34.25 | 04 Aug 1845 - 0500 | 13019 | 900462 | LEAK IN CHICKSAN LINE, BAD SEAL. | TF | CTU |  | 08/05/2022 | ADM-337 | 24 | MRJN-900
486 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ADM-339 | Hrs | MRJN-3012
487 | FOT | RIG | 3 | 05 Aug 2200 - 0100 | 5415 | 900546 | RIG CREW TROUBLESHOOT ISSUE WITH RIG AIR COMPRESSORS AFFECTING THE RIG AIR SYSTEM. REPLACE COUPLINGS ON AIR COMPRESORS #2, 3. | RR | HSYS |  | 08/05/2022 | ADM-339 | 3 | MRJN-3012
488 | FOT | RIG | .25 | 05 Aug 2215 - 2230 | 6991 | 900538 | CHANGE STANDPIPE TO ENABLE WORK ON MP #1 SEAT AND VALVES | RR | MPMP |  | 08/05/2022 | AOD-1 | .25 | ZULF-694
489 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | AOD-1 | Hrs | ZULF-694
490 | FOT | RIG | .75 | 05 Aug 1430 - 1515 | 6800 | 900466 | TROUBLESHOOT EXCESSIVE NOISE ON MWD TOOL. UNABLE TO ACQUIRE MWD PULSE. SWITCH PUMPS & RECYCLE PUMPS NUMEROUS TIMES. | RR | MPMP |  | 08/05/2022 | AOD-1 | .75 | ZULF-694
491 | FOT | RIG | .25 | 05 Aug 2215 - 2230 | 6991 | 900538 | CHANGE STANDPIPE TO ENABLE WORK ON MP #1 SEAT AND VALVES | RR | MPMP |  | 08/05/2022 | AOD-1 | .25 | ZULF-694
492 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ARO-4001 | Hrs | MRJN-532
493 | STBH | ARM | 87.5 | 02 Aug 1145 - 0500 | 6642 | 900419 | GOT SUDDEN HOLE PACK OFF, STRING STALL AND STUCK. | STUK | BHA |  | 08/05/2022 | ARO-4001 | 24 | MRJN-532
494 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | BCTD-4 | Hrs | GHZL-58
495 | FOT | BHI | 12.5 | 05 Aug 0600 - 2130 | 14928 | 900534 | DTF, ORIENTOR HPC FAILED POH TO CHANGE BHA. | BHA | MWD |  | 08/05/2022 | BCTD-4 | 12.5 | GHZL-58
496 | FOT | RIG | 3.5 | 05 Aug 0130 - 0500 | 2906 | 900543 | WHILE DRILL 12-1/4" HOLE, TDS STOPPED ROTATION, TRIED TO ROTATE MANY TIMES UNSUCCESSFULLY, TDS ENGINEER IS TROUBLE SHOOTING TDS. | RR | TDS |  | 08/05/2022 | DQ-47 | 3.5 | KHRS-280
497 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | DQ-47 | Hrs | KHRS-280
498 | FOT | BHI | 4.5 | 05 Aug 1830 - 2300 | 2878 | 900533 | DROPPED GYRO SURVEY DATA TOOL, DATA MISSING, GYRO TOOL NOT READING SURVEYS. | TF | GYRO |  | 08/05/2022 | DQ-47 | 4.5 | KHRS-280
499 | FOT | RIG | 3.5 | 05 Aug 0130 - 0500 | 2906 | 900543 | WHILE DRILL 12-1/4" HOLE, TDS STOPPED ROTATION, TRIED TO ROTATE MANY TIMES UNSUCCESSFULLY, TDS ENGINEER IS TROUBLE SHOOTING TDS. | RR | TDS |  | 08/05/2022 | DQ-47 | 3.5 | KHRS-280
500 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ENS-108 | Hrs | ZULF-2014
501 | FOT | ENV | 357.25 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/05/2022 | ENS-108 | 24 | ZULF-2014
502 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ENSCO-54 | Hrs | ABSF-17
503 | FOT | RIG | 1 | 05 Aug 1800 - 1900 | 11871 | 900548 | TDS WASH PIPE LEAK, TROUBLESHOOT, POH TO WINDOW TO CHANGE. | RR | RSYS |  | 08/05/2022 | ENSCO-54 | 1 | ABSF-17
504 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | ENSCO-76 | Hrs | MRJN-853
505 | XTTE | BHI | 1 | 05 Aug 2215 - 2315 | 120 | 900549 | EXCESSIVE TIME TO DOWNLOAD MEMORY DATA F/ MWD/LWD/VISITRAK ASSY (2 HRS) | TF | MWD |  | 08/05/2022 | ENSCO-76 | 1 | MRJN-853
506 | MATL | BDF | 8.25 | 04 Aug 2330 - 1030 | 5205 | 900496 | MUD ENGINEERS DID NOT HAVE ENOUGH CHEMICALS ON THE RIG TO WEIGHT UP THE RESERVE PITS | WO | NA |  | 08/05/2022 | EXL-IA | 5.5 | SFNY-1790
507 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | EXL-IA | Hrs | SFNY-1790
508 | MATL | ARM | 8.25 | 04 Aug 0145 - 1600 | 5205 | 900478 | RAN OUT OF MATERIALS | WO | NA |  | 08/05/2022 | EXL-IA | 5.5 | SFNY-1790
509 | MATL | BDF | 8.25 | 04 Aug 2330 - 1030 | 5205 | 900496 | MUD ENGINEERS DID NOT HAVE ENOUGH CHEMICALS ON THE RIG TO WEIGHT UP THE RESERVE PITS | WO | NA |  | 08/05/2022 | EXL-IA | 5.5 | SFNY-1790
510 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | HI-2 | Hrs | BRRI-433
511 | UVLC | ARM | .5 | 05 Aug 2200 - 2230 | 2020 | 900540 | DRILL 16" HOLE WITH SW , GEL SWEEP & MUD CAP DUE TO TOTAL LOSSES. | LCIR | NA |  | 08/05/2022 | HI-2 | .5 | BRRI-433
512 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | MP-1 | Hrs | MRJN-78
513 | FOT | NRT | 114.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/05/2022 | MP-1 | 24 | MRJN-78
514 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | NA-207S | Hrs | SHYB-132
515 | WTHR | ARM | .75 | 05 Aug 1815 - 1900 | 2994 | 900532 | STORM AND HEAVY RAINS INTERRUPTED SAFE OPERATIONS. | WON | NA |  | 08/05/2022 | NA-207S | .75 | SHYB-132
516 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | NBR-196S | Hrs | SDGM-1235
517 | FOT | SPS | 13.5 | 04 Aug 2300 - 0000 | 0 | 900519 | HAD MWD TOOLS FAILURE WHILE SURFACE TEST AFTER PICK UP. SPERRY SUN NOT ABLE TO LOAD DATA TO MWD TOOLS AFTER PICK UP. | BHA | MWD |  | 08/05/2022 | NBR-196S | 7.5 | SDGM-1235
518 | FOT | BAW | 13.5 | 05 Aug 0700 - 2030 | 8380 | 900542 | CUT 5 1/2" D/P W/ BAKER MPC & TRIED TO POOH HAD TOOL STUCK ON D/P, TRIED TO FREE TOOL, NO SUCCESS & SHEARED WL FROM WEAK POINT ABOVE HEAD. | TF | WLT |  | 08/05/2022 | NBR-263S | 13.5 | QTIF-736
519 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | NBR-263S | Hrs | QTIF-736
520 | STBH | ARM | 95 | 29 Jul 0230 - 0330 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK. | STUK | BHA |  | 08/05/2022 | NBR-263S | 9 | QTIF-736
521 | WC20 | ARM | 7.5 | 01 Aug 0400 - 0500 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, SUSPECT BALLOONING EFFECT, BULLHEAD 102 PCF MUD ON ANNULAS TILL WELL STATIC. | WCNT | NA |  | 08/05/2022 | NBR-263S | 1.5 | QTIF-736
522 | FOT | BAW | 13.5 | 05 Aug 0700 - 2030 | 8380 | 900542 | CUT 5 1/2" D/P W/ BAKER MPC & TRIED TO POOH HAD TOOL STUCK ON D/P, TRIED TO FREE TOOL, NO SUCCESS & SHEARED WL FROM WEAK POINT ABOVE HEAD. | TF | WLT |  | 08/05/2022 | NBR-263S | 13.5 | QTIF-736
523 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | NBR-654S | Hrs | HRDH-1150
524 | FOT | PKP | 52.5 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. | TF | HGRL |  | 08/05/2022 | NBR-654S | 23.5 | HRDH-1150
525 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | PA-622S | Hrs | UTMN-3600
526 | FPMP | RIG | 4.25 | 05 Aug 0615 - 0315 | 12655 | 900470 | WHILE DRILLING 8-3/8" HOLE SECTION, OBSERVED SUDDEN DROP IN PUMP PRESSURE. | RR | MPMP |  | 08/05/2022 | PA-622S | 4.25 | UTMN-3600
527 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | RM-74A | Hrs | HSBH-68
528 | IFCS | HCM | 62 | 02 Aug 1715 - 1145 | 4300 | 900414 | WHILE PREPARING TO MIX THE TAIL SLURRY FOR 2ND STAGE, OBSERVE TAIL MIX FLUID EXCESSIVELY FOAMING. | CMT | NA |  | 08/05/2022 | RM-74A | 6.75 | HSBH-68
529 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SCTD-1 | Hrs | SDGM-1034
530 | FOT | RIG | 44.5 | 03 Aug 0500 - 1530 | 12790 | 900434 | D&M FAILED TO INTIATE SIDE TRACK. | BHA | MMOT |  | 08/05/2022 | SCTD-1 | 10.5 | SDGM-1034
531 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SINO-18 | Hrs | HDYF-4
532 | FOT | RIG | 2 | 05 Aug 1300 - 1500 | 9890 | 900463 | DRAW WORK LOW GEAR AIR BAR BROKEN. | RR | DWKS |  | 08/05/2022 | SINO-18 | 2 | HDYF-4
533 |  |  | BAL | OTH | 4009 | 10423 | HPJSM WITH ESP CREW, RIG CREW AND OILSERV TEAM, EXPLAINED ESP FUNCTION TEST PROCEDURE AND FLARING FLOWBACK & HIGHLIGHTED RISKS & HAZARD, (OOS). |  |  | 10423 | 08/05/2022 | SINO-1L | NA | ABJF-20
534 |  |  | BAL | OTH | 4009 | 10423 | BAKER START UP ESP PUMP ON FORWARD DIRC , CHANGED TO RIGHT DIRC & START ESP FUNCTION TEST, OPEN & FLOW WELL TO WASTE PIT THROUGH ADJUSTABLE CHOKE UNTIL GOT TRACE OF OIL, (OOS). |  |  | 10423 | 08/05/2022 | SINO-1L | NA | ABJF-20
535 |  |  | OWT | OTH | 4009 | 10423 | LINED UP TO OILSERV SEPARATOR & CONT'D ESP FUNCTION TEST BY FLOWING WELL TO OILSERV SMOKELESS BURNER.- UPSTREAM PRESSURE: 860 PSI, DOWNSTREAM PRESSURE: 100 PSI & FERQUENCY: 45 HZ, 31 AMP.- OIL: 15%, (OOS). |  |  | 10423 | 08/05/2022 | SINO-1L | NA | ABJF-20
536 |  | 900471 | OWT | OTH | 4009 | 10423 | SUSPEND OPERATION DUE TO WIND DIRECTION, (OOS). |  | WON | 10423 | 08/05/2022 | SINO-1L | NA | ABJF-20
537 |  |  | BAL | OTH | 4009 | 10423 | BAKER RESTART UP ESP PUMP ON FORWARD DIRC , CHANGED TO RIGHT DIRC & START ESP FUNCTION TEST, OPEN & FLOW WELL TO WASTE PIT THROUGH ADJUSTABLE CHOKE UNTIL GOT TRACE OF OIL, (OOS). |  |  | 10423 | 08/05/2022 | SINO-1L | NA | ABJF-20
538 |  |  | OWT | OTH | 4009 | 10423 | FLOWBACK OPERATION LATERAL [ L-0-3 ] THROUGH OILSERV CHOKE AS PER PROGRAM, (OOS).- TOTAL FLOWING HOURS FOR LATERAL = 16.5 / 48 HRS.- CHOKE SIZE : 24 /64"- WHP : 903 PSI-SEP. PRESS. : 190 PSI- OIL % : 95 %- WATER CUT 5%- H2S : 2 %- CO2 : 1.5 %- OIL API : 32.3- WTR CHLORIDE : 81810 PPM |  |  | 10423 | 08/05/2022 | SINO-1L | NA | ABJF-20
539 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SINO-1L | Hrs | ABJF-20
540 | WTHR | ARM | 6 | 05 Aug 0730 - 1330 | 0 | 900471 | SUSPEND OPERATION DUE TO WIND DIRECTION. | WON | NA |  | 08/05/2022 | SINO-1L | 6 | ABJF-20
541 | 35 | OOSS | Category | DOOS ID | WTST | Out of Scope Summary | WAIT ON WIND DIRECTION | 24 | 4009 | 04 Aug 1800 | 08/05/2022 | SINO-1L | Type | ABJF-20
542
543
544 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SINO-37L | Hrs | HWYH-639
545 | FOT | RIG | 1 | 05 Aug 1330 - 1430 | 5987 | 900547 | WHILE SWITCHING FROM SLIDING TO ROTARY, FOUND TDS NOT ROTATING. | RR | TDS |  | 08/05/2022 | SINO-37L | 1 | HWYH-639
546 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SND-2008 | Hrs | HRDH-1812
547 | STDP | RIG | 569 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/05/2022 | SND-2008 | 24 | HRDH-1812
548 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SNF036 | Hrs | MRJN-901
549 | FOT | GEP | 3 | 05 Aug 2000 - 2300 | 294 | 900552 | UNABLE TO INSTALL 18 5/8" CORROSION CAP. | WH | WH |  | 08/05/2022 | SNF036 | 3 | MRJN-901
550 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SP-110 | Hrs | MNIF-142
551 | UNKN | RIG | 69.5 | 03 Aug 0730 - 0500 | 0 | 900424 | SHUT DOWN ALL OPERATION & INVESTIGATE CONTRACTOR EMPLOYEE FALL INCIDENT | HSEI | NA |  | 08/05/2022 | SP-110 | 24 | MNIF-142
552 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SP-121 | Hrs | BRRI-522
553 | FOT | RIG | 1 | 05 Aug 2200 - 2300 | 8180 | 900550 | REPAIR MP# 1 & MP# 3 MEANWHILE CIRC WITH MP #2 AND RECIPROCATING STRING. | RR | MPMP |  | 08/05/2022 | SP-121 | 1 | BRRI-522
554 | FOT | WDS | 25 | 04 Aug 0600 - 0900 | 4305 | 900518 | ATTEMPTS TO CLOSE WFD PBL, NO SUCCESS - TRIP OUT TO CHECK THE TOOL. | TF | DDNRV |  | 08/05/2022 | SP-165 | 4 | FDHL-146
555 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SP-165 | Hrs | FDHL-146
556 | ULCM | ARM | 11.75 | 03 Aug 2345 - 1500 | 5725 | 900437 | CURE PARTIAL LOSSES WITH LCM PILL. | LCIR | LCM |  | 08/05/2022 | SP-165 | 5.5 | FDHL-146
557 | FOT | WDS | 25 | 04 Aug 0600 - 0900 | 4305 | 900518 | ATTEMPTS TO CLOSE WFD PBL, NO SUCCESS - TRIP OUT TO CHECK THE TOOL. | TF | DDNRV |  | 08/05/2022 | SP-165 | 4 | FDHL-146
558 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SP-257 | Hrs | HZEM-162412
559 | LCRW | ARM | 113.25 | 31 Jul 1330 - 0500 | 445 | 900304 | 22" BHA STUCK WHILE TOOH WITH TOTAL LOSSES. | STUK | STRG |  | 08/05/2022 | SP-257 | 24 | HZEM-162412
560 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SP-260 | Hrs | HMYM-531812
561 | STBH | ARM | 107 | 01 Aug 1800 - 0500 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/05/2022 | SP-260 | 24 | HMYM-531812
562 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SSA-202 | Hrs | QTIF-191
563 | FOT | ARN | 27.75 | 04 Aug 0830 - 1215 | 18300 | 900457 | V-SAT TECHNICIAN REPLACE MODEM AND TROUBLE SHOOT W/ V-SAT DUE LOST COMMUNICATION BETWEEN SPS AND GOC. | TF | VSAT |  | 08/05/2022 | SSA-202 | 7.25 | QTIF-191
564 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SSA-5891 | Hrs | HRDH-1205
565 | FOT | RIG | 45.75 | 03 Aug 2230 - 0500 | 11526 | 900472 | TOP DRIVE OVER HEATED. | RR | TDS |  | 08/05/2022 | SSA-5891 | 24 | HRDH-1205
566 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SSA-5962 | Hrs | HRDH-2513
567 | FOT | WDS | 24 | 05 Aug 0500 - 0500 | 5140 | 900465 | WFD RSS MAGNUS FAILLURE. | BHA | RSS |  | 08/05/2022 | SSA-5962 | 24 | HRDH-2513
568 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/05/2022 | SSA-5969 | Hrs | UTMN-3148
569 | UVLC | ARM | 46.5 | 03 Aug 2330 - 0500 | 2737 | 900494 | COMPLETE LOSS DURING DRILLING SFNY FORMATION | LCIR | NA |  | 08/05/2022 | SSA-5969 | 22.5 | UTMN-3148
570 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADC-17 | Hrs | ZULF-1210
571 | HINW | ARM | 120 | 02 Aug 0500 - 0500 | 5490 | 900413 | MANSOORI SLICKLINE 3.5" SHIFTING TOOL STUCK WHILE POH @5490 FT DUE TO SAND PRODUCTION AFTER FLOW BACK TWO ZONES | STUK | SLICK |  | 08/06/2022 | ADC-17 | 24 | ZULF-1210
572 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADC-31 | Hrs | SDGM-1181
573 | STDP | RIG | 564.5 | 12 Jul 1930 - 0500 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/06/2022 | ADC-31 | 24 | SDGM-1181
574 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADC-41L | Hrs | SDGM-1244
575 | UVLC | ARM | 409.5 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 08/06/2022 | ADC-41L | 24 | SDGM-1244
576 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADC-50 | Hrs | SFNY-1176
577 | LCRW | ARM | 372.75 | 19 Jul 1830 - 0500 | 0 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 08/06/2022 | ADC-50 | 24 | SFNY-1176
578 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADC-52 | Hrs | SDGM-1185
579 | HINW | BAW | 200 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/06/2022 | ADC-52 | 24 | SDGM-1185
580 | 12705 | 330 | TO | E | 3947 | BHA | POOH W/THRU-BIT ASSY F/ 861 FT TO 330 FT ( TOP BHA)- MONITOR WELL ON TRIP TANK- FLOW CHECK : WELL STATIC | 12705 | 861 | RIG | 08/06/2022 | ADC-53L | LOG | HRDH-530
581 | 12705 |  | OTH | E | 3947 | NA | POOH THRU-BIT BHA TO SURFACE & L/D TOOLS.- MONITOR WELL ON TRIP TANK | 12705 |  | SWL | 08/06/2022 | ADC-53L | LOG | HRDH-530
582 | 12705 |  | HT | C | 3947 | BHA | HPJSM, P/U, M/U 6-1/8" REAMING BHA & RIH TO 306 FT.- WELL MONITORED ON TRIP TANK. | 12705 |  | RIG | 08/06/2022 | ADC-53L | CT | HRDH-530
583 | 12705 | 5315 | TI | C | 3947 | STDP | RIH W/6-1/8" REAMING BHA ON 4" DP STDS F/306 FT TO TOW @ 5,315 FT.- FILL UP STRING EVERY 20 STD.- WELL MONITORED ON TRIP TANK. | 12705 | 306 | RIG | 08/06/2022 | ADC-53L | CT | HRDH-530
584 | 12705 | 12705 | RW | C | 3947 | BIT | RIH W/6-1/8" REAMING BHA ON ELEVATOR AS SIMULATION RUN ON 4" DP F/5,315 FT TO 12,705 FT.- HOLE IN GOOD CONDITION.- FILL UP STRING EVERY 20 STD.- MONITORED ON TRIP TANK - WELL STATIC. | 12705 | 5315 | RIG | 08/06/2022 | ADC-53L | CT | HRDH-530
585 | 12705 |  | CIRC | C | 3947 | MPMP | SWEPT HOLE WITH 20/20 BBLS LOW VIS/HI WT PILL 2 TIMES & CIRCULATED TILL SHAKERS CLEAN.- FR: 280 GPM, SPP: 3,450 PSI- RECIPROCATE STRING UP & DOWN WHILE CIRCULATION.- RECORD SCR. FLOW CHECK - WELL STATIC. | 12705 |  | RIG | 08/06/2022 | ADC-53L | CT | HRDH-530
586 | 12705 |  | CIRC | C | 3947 | MPMP | SPOT 300 BBLS OBM LOADED WITH 2 PPB OF LUBRAGLIDE. | 12705 |  | RIG | 08/06/2022 | ADC-53L | CT | HRDH-530
587 | 12705 | 12500 | TO | C | 3947 | BHA | POOH WITH 6-1/8" REAMING BHA F/12,705 FT TO 12,500 FT.- OBSERVED TIGHT SPOT AT 12,654 FT, SOFT REAM AND PASS.- PULL 2 STDS OFF BOTTOM AT 12,500 FT, CHECK PUW: 170 KLBS, SOW: 110 KLBS - PERFORM STICK TEST FOR 5 MIN :OK THEN FOR 10 MIN : HAD OVER PULL WHILE CHECKING FREE UP, RIH DOWN,STRING WAS FREE DOWN. | 12705 | 12705 | RIG | 08/06/2022 | ADC-53L | CT | HRDH-530
588 | 12705 | 12428 | BR | C | 3947 | STRG | HARD BACK REAM WITH 6-1/8" REAMING BHA F/12,500 FT TO 12,428 FT.- TIGHT SPOT: 12,500 FT, 12,494 FT, 12,460 FT, 12,454 FT.12,428 FT. - DISCUSSED WITH ENGINEERING DECIDE TO POOH TO WINDOW THEN PLAN FORWARD. | 12705 | 12500 | RIG | 08/06/2022 | ADC-53L | CT | HRDH-530
589 | 12705 | 10806 | TO | C | 3947 | BHA | POOH WITH 6-1/8" REAMING BHA ON ELEVATOR F/12,428 FT TO 10,806 FT.- HELD UP @ 12,324 FT , 12,229 FT & 11,396 FT. | 12705 | 12428 | RIG | 08/06/2022 | ADC-53L | CT | HRDH-530
590 | 83 | OOS | Category | DOOS ID | HCRM | Out of Scope Summary | REAMING W/ THRU BIT THEN WITH REAMING BHA ASSY | 24 | 3947 | 03 Aug 1800 | 08/06/2022 | ADC-53L | Type | HRDH-530
591
592
593 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADC-55L | Hrs | UTMN-3171
594 | STBH | TK3 | 183.25 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/06/2022 | ADC-55L | 24 | UTMN-3171
595 | 7019 | 6928 | LOG | E | 3965 | WLT | SLB WL TAKING SAMPLING WHILE POOH AS PER RMD REQUEST, SCANNING AROUND 6,810 FT FOR 3RD SAMPLE ........ AT RPT.- SCAN AROUND 6,905 FT FOR 2ND SAMPLE BEST MOBILITY.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. - MAX STATIONARY TIME: 4 HRS.- SAMPLE #1 @ 6,979 FT , TOT. 3 SESSION.- SAMPLE #2 @ 6,905 FT, TOT. 3 SESSION.- TOTAL 2 SAMPLE OUT OF 18.- REPEATED PRESSURE POINTS WHILE POOH AT 6845 FT, 6830 FT & 6820 FT AS PER RMD.- TOTAL PUMP OUT 800 L AT RPT, OVERBALANCE AFTER PUMP OUT 583 PSI.- MONITOR WELL ON TRIP TANK. | 7019 | 6976 | SWL | 08/06/2022 | ADC-57L | LOG | KRSN-175
596 | 117.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/06/2022 | ADC-57L | Type | KRSN-175
597
598
599 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADC-60 | Hrs | ABSF-216
600 | FOT | INW | 62 | 04 Aug 1500 - 0500 | 4936 | 900594 | UNABLE TO RETRIEVE INTERWELL PLUG. | TF | PLUGT |  | 08/06/2022 | ADC-60 | 24 | ABSF-216
601 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADC-62L | Hrs | ANDR-589
602 | GRF | RIG | 96 | 03 Aug 0500 - 0500 | 0 | 900578 | UNPLANNED MAINTENANCE FOR DRAWWORKS | UPRA | DWKS |  | 08/06/2022 | ADC-62L | 24 | ANDR-589
603 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ADM-337 | Hrs | MRJN-900
604 | XTTE | BCT | 58.25 | 04 Aug 1845 - 0500 | 13019 | 900462 | LEAK IN CHICKSAN LINE, BAD SEAL. | TF | CTU |  | 08/06/2022 | ADM-337 | 24 | MRJN-900
605 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ARO-4001 | Hrs | MRJN-532
606 | STBH | ARM | 98.5 | 02 Aug 1145 - 0500 | 6642 | 900419 | GOT SUDDEN HOLE PACK OFF, STRING STALL AND STUCK. | STUK | BHA |  | 08/06/2022 | ARO-4001 | 11 | MRJN-532
607 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | DPS-5 | Hrs | HRDH-2319
608 | HERR | BC | 6 | 06 Aug 2300 - 0500 | 1598 | 900595 | ONCE PU & MU 4.5" BKR LNR HGR ON MSF STRING & TRY TO CIRCULATE SUDDENLY STRING PLUGGED. | JF | TBG |  | 08/06/2022 | DPS-5 | 6 | HRDH-2319
609 | FOT | RIG | 15.25 | 05 Aug 0130 - 1645 | 2906 | 900543 | WHILE DRILL 12-1/4" HOLE, TDS STOPPED ROTATION, TRIED TO ROTATE MANY TIMES UNSUCCESSFULLY, TDS ENGINEER IS TROUBLE SHOOTING TDS. | RR | TDS |  | 08/06/2022 | DQ-47 | 11.75 | KHRS-280
610 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | DQ-47 | Hrs | KHRS-280
611 | FOT | BHI | 3 | 06 Aug 0200 - 0500 | 3260 | 900491 | ATTEMPTED TO TAKE SURVEY WITH NO SUCESS, TROUBLE SHOOT THE PROBLEM NO SUCESS | SURV | MS |  | 08/06/2022 | DQ-47 | 3 | KHRS-280
612 | FOT | RIG | 15.25 | 05 Aug 0130 - 1645 | 2906 | 900543 | WHILE DRILL 12-1/4" HOLE, TDS STOPPED ROTATION, TRIED TO ROTATE MANY TIMES UNSUCCESSFULLY, TDS ENGINEER IS TROUBLE SHOOTING TDS. | RR | TDS |  | 08/06/2022 | DQ-47 | 11.75 | KHRS-280
613 | 7943 | 0 | LOG | E |  | WLT | HPJSM,HALL W/L RECORDED (CAST-CBL-GR-CCL):- CONT RECORDING MAIN PASS IN 7" CASING FROM 500 FT TO SURFACE.- APPLIED 1000 PSI IN WELL WHILE LOGGING- POOH TO SURFACE. | 7943 | 500 | HWP | 08/06/2022 | DQ-57L | LOG | KHRS-68
614 | 7943 |  | OTH | E |  | NA | HPJSM, L/D HALL LOGGING TOOL & R/D WIRELINE EQUIPMENT. | 7943 |  | HWP | 08/06/2022 | DQ-57L | LOG | KHRS-68
615 | 7943 |  | NU | N |  | BNIP | N/D SHOOTING NIPPLE & N/U BELL NIPPLE & FLOW LINE | 7943 |  | RIG | 08/06/2022 | DQ-57L | BOP | KHRS-68
616 | 7943 |  | OTH | N |  | NA | HPJSM, P/T CSG SEALS & CCA'S AS FOLLOW:- P/T 7" CSG SLIPS TO 1000 PSI -HOLD OK.- P/T 13-3/8" X 9-5/8" CCA & 9 5/8" CSG SLIPS TO 400 PSI HOLD ,OK.- P/T 9-5/8" X 7" CCA TO 400 PSI HOLD ,OK. | 7943 |  | RIG | 08/06/2022 | DQ-57L | WH | KHRS-68
617 | 7943 |  | OTH | N |  | NA | HPJSM, DIG OUT CELLAR 6 FT BELOW LANDING BASE FLANGE. | 7943 |  | RIG | 08/06/2022 | DQ-57L | WH | KHRS-68
618 | 7943 |  | OTH | N |  | NA | HPJSM, AL-MANSOORI PERFORMED UT INSPECTION FOR 13-3/8" SURFACE CSG & LANDING BASE:- INSPECTED 13-3/8" SURFACE CSG FOUND SAME ACCEPTED.- LANDING BASE IN GOOD CONDITION. | 7943 |  | MSI | 08/06/2022 | DQ-57L | WH | KHRS-68
619 | 7943 |  | OTH | N | 4065 | NA | HPJSM,WELD 1 EA NIPPLE IN 18-5/8" CSG. AL-MANSOORI INSPECTED WELDING AREA. BOOTS & COOTS PERFORM HOT TAPPING ON 18-5/8" CSG, INSTALL 1" VALVE ON NIPPLE & P/T SAME TO 1000 PSI-OK, DRILLED 1/2" HOLE IN 18-5/8" CSG THRU THE VALVE, MONITOR 18-5/8'' X 13-5/8" CCA NO PRESSURE & NO GAS READINGS (OOS).-18 5/8" CONDUCTOR CSG IS SEAL WELDED. | 7943 |  | HCT | 08/06/2022 | DQ-57L | WH | KHRS-68
620 | 7943 |  | OTH | N |  | NA | HPJSM,CUT WINDOW IN 18-5/8" CSG , EXPOSING 13-3/8" CSG, REMOVED CEMENT AND AL-MANSOORI PERFORMED UT INSPECTION FOR 13-3/8" CSG - GOOD READING. FILL WINDOWS WITH CEMENT AND CLOSE BOTH WINDOWS | 7943 |  | RIG | 08/06/2022 | DQ-57L | WH | KHRS-68
621 | 7943 |  | HT | N |  | BHA | HPJSM. M/U & RIH W/ WFD WHIPSTOCK & MILLING ASSY WITH UBHO SUB AS FOLLOWS: 5.5" WHIPSTOCK RHN QC , 6-1/8" LEAD MILL, 6-1/8" FLEX MILL, 1 JT X 3-1/2" HWDP, FLOAT SUB, UBHO SUB, X/O. | 7943 |  | RIG | 08/06/2022 | DQ-57L | TINL | KHRS-68
622 | 7943 |  | HT | N |  | STRG | HPJSM, RIH, AT CONTROLLED SPEED, W/ WFD 5.1/2" WHIPSTOCK ON 4" HWDP/DP TO SETTING DEPTH AT 4241 FT (BOTTOM OF WHIPSTOCK).- FILL STRING WITH 63 PCF VISCOUS WATER WITH HOSE EVERY 10 STD.- DRIFT ALL HWDP & DP STD.- CONTINUOUSLY MONITOR WELL THROUGH TRIP TANK, WELL STATIC | 7943 |  | RIG | 08/06/2022 | DQ-57L | TINL | KHRS-68
623 | 7943 |  | SURV | N |  | GYRO | HPJSM, R/U GYRO TOOL & HANG GYRO SHEAVE IN THE DERICK.- RIH W/ GYRO TOOLS INSIDE THE DP TO UBHO AND ORIENT WHIPSTOCK FACE TO58 DEG AZIMUTH. CONFIRM WHIPSTOCK ORIENTATION WITH THREE GYRO READING | 7943 |  | GCD | 08/06/2022 | DQ-57L | TINL | KHRS-68
624 | 7943 | 4241 | SET | N |  | WPSTK | HPJSM. SET 7" WFD WHIPSTOCK, CONFRIM ANCHOR SET & SHEAR BOLT AT 35 KLBS S/O WT.- TOW AT 4225 FT.- BOW AT 4234 FT | 7943 | 4241 | WWD | 08/06/2022 | DQ-57L | TINL | KHRS-68
625 | 7943 | 4234 | MILL | N |  | MILL | HPJSM, RECORDED MILLING PARAMETERS AND MILL 7" CSG & CUT WINDOW WITH 63 PCF VISCOUS WATER FROM 4225' TO 4234'..IN PROGRESS.- PARAMETERS: WOM: 6 -17 KLB, GPM: 280, PRESSURE: 550 PSI, RPM: 100, TORQUE 2000 FT.LB, 100% CIRC.- SWEEP HOLE WITH 15 BBLS HI-VIS EVERY 1 FT MILLED.- INSTALLED 3 MAGNETS AT POSUME BELLY & DITCH LINE, CLEAN SAME EVERY 30 MIN'S | 7943 | 4225 | RIG | 08/06/2022 | DQ-57L | TINL | KHRS-68
626 | 1 | OOSS | Category | DOOS ID | HTAP | Out of Scope Summary | PREFORM HOT TAPPING ON 18-5/8" CSG TO OPEN WINDOW AND INSPECT 13-3/8" CSG. | 1 | 4065 | 06 Aug 1400 | 08/06/2022 | DQ-57L | Type | KHRS-68
627
628
629 | FOT | RIG | 2 | 06 Aug 0300 - 0500 | 11466 | 900596 | WASH PIPE LEAKED. | RR | TDS |  | 08/06/2022 | ED-85A | 2 | ZULF-2063
630 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ED-85A | Hrs | ZULF-2063
631 | FOT | SRT | 1.25 | 06 Aug 0500 - 0615 | 0 | 900483 | SMITH RHINO-REAMER FAILED DURING SURFACE TEST. | BHA | UNDR |  | 08/06/2022 | ED-85A | 1.25 | ZULF-2063
632 | FOT | RIG | 2 | 06 Aug 0300 - 0500 | 11466 | 900596 | WASH PIPE LEAKED. | RR | TDS |  | 08/06/2022 | ED-85A | 2 | ZULF-2063
633 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ENS-108 | Hrs | ZULF-2014
634 | FOT | ENV | 381.25 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/06/2022 | ENS-108 | 24 | ZULF-2014
635 | IRES | RIG | .25 | 06 Aug 0115 - 0130 | 6340 | 900612 | TRIP TANK PUMP PUMPING LESS THAN 10 BBLS/MIN | UPRA | CSYS |  | 08/06/2022 | ENSCO-76 | .25 | MRJN-853
636 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | ENSCO-76 | Hrs | MRJN-853
637 | OTH | RIG | .5 | 06 Aug 0430 - 0500 | 9970 | 900600 | RIG CREW DID NOT FOLLOW INSTRUCTIONS AND DID NOT REAM TIGHT AREAS WHILE RUNNING HOLE | UPRA | NA |  | 08/06/2022 | ENSCO-76 | .5 | MRJN-853
638 | IRES | RIG | .25 | 06 Aug 0115 - 0130 | 6340 | 900612 | TRIP TANK PUMP PUMPING LESS THAN 10 BBLS/MIN | UPRA | CSYS |  | 08/06/2022 | ENSCO-76 | .25 | MRJN-853
639 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | HI-4 | Hrs | BRRI-1001
640 | FOT | FMC | 1 | 06 Aug 0215 - 0315 | 288 | 900489 | TRIED TO FILL-UP CSG USING FILL-UP TOOL, FOUND SAME PLUGGED | TF | FUT |  | 08/06/2022 | HI-4 | 1 | BRRI-1001
641 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | MP-1 | Hrs | MRJN-78
642 | FOT | NRT | 138.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/06/2022 | MP-1 | 24 | MRJN-78
643 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | NBR-196S | Hrs | SDGM-1235
644 | FOT | SPS | 16.5 | 04 Aug 2300 - 1900 | 0 | 900519 | HAD MWD TOOLS FAILURE WHILE SURFACE TEST AFTER PICK UP. SPERRY SUN NOT ABLE TO LOAD DATA TO MWD TOOLS AFTER PICK UP. | BHA | MWD |  | 08/06/2022 | NBR-196S | 3 | SDGM-1235
645 | FOT | BAW | 14.75 | 05 Aug 0700 - 0315 | 8380 | 900542 | CUT 5 1/2" D/P W/ BAKER MPC & TRIED TO POOH HAD TOOL STUCK ON D/P, TRIED TO FREE TOOL, NO SUCCESS & SHEARED WL FROM WEAK POINT ABOVE HEAD. | TF | WLT |  | 08/06/2022 | NBR-263S | 1.25 | QTIF-736
646 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | NBR-263S | Hrs | QTIF-736
647 | STBH | ARM | 114.25 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE. | STUK | BHA |  | 08/06/2022 | NBR-263S | 19.25 | QTIF-736
648 | WC20 | ARM | 11 | 01 Aug 0400 - 2230 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, SUSPECT BALLOONING EFFECT, BULLHEAD 102 PCF MUD ON ANNULAS TILL WELL STATIC. | WCNT | NA |  | 08/06/2022 | NBR-263S | 3.5 | QTIF-736
649 | FOT | BAW | 14.75 | 05 Aug 0700 - 0315 | 8380 | 900542 | CUT 5 1/2" D/P W/ BAKER MPC & TRIED TO POOH HAD TOOL STUCK ON D/P, TRIED TO FREE TOOL, NO SUCCESS & SHEARED WL FROM WEAK POINT ABOVE HEAD. | TF | WLT |  | 08/06/2022 | NBR-263S | 1.25 | QTIF-736
650 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SINO-12L | Hrs | HWYH-220
651 | FOT | HCM | 4 | 06 Aug 1600 - 2000 | 5090 | 900579 | CEMENT PUMP, SLURRY MIXING TANK MALFUNCTION ( DRY CMT SUCTION LINE PLUGGED) | JF | SQZ |  | 08/06/2022 | SINO-12L | 4 | HWYH-220
652 | 10423 |  | OTH | E | 4009 | NA | FLOWBACK OPERATION LATERAL [ L-0-3 ] THROUGH OILSERV CHOKE AS PER PROGRAM, (OOS).- TOTAL FLOWING HOURS FOR LATERAL 23 HRS.- WATER CUT 2%, WTR CHLORIDE : 81810 PPM | 10423 |  | OWT | 08/06/2022 | SINO-1L | TEST | ABJF-20
653 | 10423 |  | OTH | E |  | NA | CLOSED WELLHEAD VALVES, FLUSHED SURFACE LINES TO WASTE PIT WITH WATER AND R/D OILSERV WELL TESTING EQUIPMENT.OFFLINE: OILSERV START RD FLOWBACK EQUIPMENTS. | 10423 |  | OWT | 08/06/2022 | SINO-1L | TEST | ABJF-20
654 | 10423 | 200 | SET | C |  | PLUGT | HPJSM, P/T HALL S/L LUBRICATOR & BOP TO 2000 PSI, - HALL S/L RUN & SET SHALLOW 3-1/2" MONOLOCK AT 200 FT.- P/T SHALLOW MONOLOCK WITH 70 PCF INHIBITED BRINE TO 1,000 PSI, OK & POOH.- R/D HAL SLICKLINE EQPT. | 10423 | 200 | HSL | 08/06/2022 | SINO-1L | COMP | ABJF-20
655 | 10423 |  | OTH | C |  | NA | SECURE WELL, INSTALLED BLIND FLANGES & WELL MARKER, CLEAN & FILL CELLAR WITH SWEET SAND, WELLHEAD TO ORIGINAL ORIENTATIONS & HEIGHTS, OPERATING VALVES TO NORTH & WING VALVE TO EAST.- DISTANCE FROM MID CROWN VALVE TO GROUND = 8.82 FT.- DISTANCE FROM WING VALVE TO GROUND = 7.7 FT.- DISTANCE FROM MID MASTER VALVE TO GROUND = 6.55 FT. | 10423 |  | RIG | 08/06/2022 | SINO-1L | WH | ABJF-20
656 | 10423 |  | RELS | S |  | NA | RELEASE RIG FROM ABJF-20 TO ABJF-260 ON AUGUST 05, 2022 @19:00 HRS. | 10423 |  | RIG | 08/06/2022 | SINO-1L | OT | ABJF-20
657 | 42.75 | OOSS | Category | DOOS ID | WTST | Out of Scope Summary | WELL BACK FLOW. | 7.75 | 4009 | 04 Aug 1800 | 08/06/2022 | SINO-1L | Type | ABJF-20
658
659
660 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SND-1502 | Hrs | HRDH-124
661 | FOT | RIG | 13 | 05 Aug 0430 - 1730 | 7500 | 900597 | STRING PLUG | DSF | STRG |  | 08/06/2022 | SND-1502 | 12.5 | HRDH-124
662 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SND-2002 | Hrs | WAQR-23
663 | FOT | BAW | 11 | 06 Aug 1730 - 0430 | 11600 | 900490 | AT LATCHING DEPTH, BKR WL TOOL COMMUNICATION FAILED. | TF | WLT |  | 08/06/2022 | SND-2002 | 11 | WAQR-23
664 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SND-2008 | Hrs | HRDH-1812
665 | STDP | RIG | 593 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/06/2022 | SND-2008 | 24 | HRDH-1812
666 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SP-110 | Hrs | MNIF-142
667 | UNKN | RIG | 93.5 | 03 Aug 0730 - 0500 | 0 | 900424 | SHUT DOWN ALL OPERATION & INVESTIGATE CONTRACTOR EMPLOYEE FALL INCIDENT | HSEI | NA |  | 08/06/2022 | SP-110 | 24 | MNIF-142
668 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SP-257 | Hrs | HZEM-162412
669 | LCRW | ARM | 136.75 | 31 Jul 1330 - 0500 | 445 | 900304 | 22" BHA STUCK WHILE TOOH WITH TOTAL LOSSES. | STUK | STRG |  | 08/06/2022 | SP-257 | 23.5 | HZEM-162412
670 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SSA-102 | Hrs | QTIF-693
671 | FOT | WI3 | 13.5 | 06 Aug 1500 - 0500 | 9617 | 900488 | WHILE RIH 7" WHIPSTOCK HAD OBSTRUCTION AT 9617' TRY TO PASS WITHOUT SUCCESS. | TF | WPSTK |  | 08/06/2022 | SSA-102 | 13.5 | QTIF-693
672 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SSA-51 | Hrs | MNIF-257
673 | FOT | BHI | 17.25 | 06 Aug 0945 - 0500 | 14230 | 900554 | BHI NOT ABLE TO STEER THE TRAJECTORY. TOOL FAILLURE HAD TO POH TO CHANGE SAME. | BHA | MWD |  | 08/06/2022 | SSA-51 | 17.25 | MNIF-257
674 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SSA-5891 | Hrs | HRDH-1205
675 | FOT | RIG | 57.25 | 03 Aug 2230 - 1630 | 11526 | 900472 | TOP DRIVE OVER HEATED. | RR | TDS |  | 08/06/2022 | SSA-5891 | 11.5 | HRDH-1205
676 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SSA-5962 | Hrs | HRDH-2513
677 | FOT | WDS | 32 | 05 Aug 0500 - 1300 | 5140 | 900465 | WFD RSS MAGNUS FAILLURE. | BHA | RSS |  | 08/06/2022 | SSA-5962 | 8 | HRDH-2513
678 | LCRW | ARM | 15.75 | 06 Aug 1315 - 0500 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | STRG |  | 08/06/2022 | SSA-5969 | 15.75 | UTMN-3148
679 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/06/2022 | SSA-5969 | Hrs | UTMN-3148
680 | UVLC | ARM | 51.5 | 03 Aug 2330 - 1315 | 2737 | 900494 | COMPLETE LOSS DURING DRILLING SFNY FORMATION | LCIR | NA |  | 08/06/2022 | SSA-5969 | 5 | UTMN-3148
681 | LCRW | ARM | 15.75 | 06 Aug 1315 - 0500 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | STRG |  | 08/06/2022 | SSA-5969 | 15.75 | UTMN-3148
682 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADC-17 | Hrs | ZULF-1210
683 | HINW | ARM | 133.5 | 02 Aug 0500 - 1830 | 5490 | 900413 | MANSOORI SLICKLINE 3.5" SHIFTING TOOL STUCK WHILE POH @5490 FT DUE TO SAND PRODUCTION AFTER FLOW BACK TWO ZONES | STUK | SLICK |  | 08/07/2022 | ADC-17 | 13.5 | ZULF-1210
684 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADC-31 | Hrs | SDGM-1181
685 | STDP | RIG | 588.5 | 12 Jul 1930 - 0500 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/07/2022 | ADC-31 | 24 | SDGM-1181
686 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADC-41L | Hrs | SDGM-1244
687 | UVLC | ARM | 433.5 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 08/07/2022 | ADC-41L | 24 | SDGM-1244
688 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADC-50 | Hrs | SFNY-1176
689 | LCRW | ARM | 396.75 | 19 Jul 1830 - 0500 | 0 | 899874 | PIPE STUCK. NO SUCCESS TO FREE PIPE. CUT PIPE AT 3260' WITH MPC . SPOTTED SIDETRACK CMT PLUG FOR SIDETRACK. | STUK | STRG |  | 08/07/2022 | ADC-50 | 24 | SFNY-1176
690 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADC-52 | Hrs | SDGM-1185
691 | HINW | BAW | 224 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/07/2022 | ADC-52 | 24 | SDGM-1185
692 | 12705 | 5315 | TO | C | 3947 | BHA | POOH WITH 6-1/8" REAMING BHA ON ELEVATOR F/10,806 FT TO TOW @ 5,315 FT.- CLEAR TIGHT SPOTS @ 10,789 FT, 10,693 FT, 7,141 FT, 6,180 FT & 5,975 FT. | 12705 | 10806 | RIG | 08/07/2022 | ADC-53L | CT | HRDH-530
693 | 12705 |  | HT | C | 3947 | STRG | M/U & RACK BACK 13 STAND 4" HWDP FOR LOWER COMPLETION | 12705 |  | RIG | 08/07/2022 | ADC-53L | CT | HRDH-530
694 | 12705 | 10045 | RW | C | 3947 | BIT | REAM DOWN OPEN HOLE F/5,325 FT TO 10,045 FT - WOB: 0-4 KLBS, RPM: 120 & TQ: 2-4 KFT-LBS, FR: 300 GPM, SPP: 2,000 - 2700 PSI.- CLEAR TIGHT SPOTS @ 7235 FT, 7292 FT, 7304FT , 7381FT , 9460 FT & 9936 FT | 12705 | 5325 | RIG | 08/07/2022 | ADC-53L | CT | HRDH-530
695 | 107 | OOS | Category | DOOS ID | HCRM | Out of Scope Summary | REAMING W/ THRU BIT THEN WITH REAMING BHA ASSY | 24 | 3947 | 03 Aug 1800 | 08/07/2022 | ADC-53L | Type | HRDH-530
696
697
698 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADC-55L | Hrs | UTMN-3171
699 | STBH | TK3 | 207.25 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/07/2022 | ADC-55L | 24 | UTMN-3171
700 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADC-56L | Hrs | UTMN-3069
701 | FOT | RIG | 4.75 | 07 Aug 2100 - 0145 | 10608 | 900589 | OBSERVED LEAK IN CONNECTION AT SAVE SUB. BROKE OUT CONNECTION AND OBSERVED MARK ON FACE OF SAVER SUB. | RR | CSYS |  | 08/07/2022 | ADC-56L | 4.75 | UTMN-3069
702 | 7019 | 6715 | LOG | E | 3965 | WLT | SLB WL TAKING SAMPLING WHILE POOH AS PER RMD REQUEST.- SCAN AROUND 6,810 FT FOR 3RD SAMPLE .- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. - MAX STATIONARY TIME: 4 HRS.- SAMPLE #3 @ 6,810 FT , TOT. 2 SESSION.- PUMP OUT SESSION @ 6,715 FT.- TOTAL 3 + 1 SAMPLE/PUMP OUT, OUT OF 12 + 6 SAMPLE/PUMP OUT .- REPEATED PRESSURE POINTS WHILE POOH AT 6,811 FT ; 6,810 FT ; 6,809 FT ; 6,765 FT ; 6,750 FT 6,749 FT; 6,740 FT & 6,725 FT AS PER RMD.- TOTAL PUMP OUT 1310 L AT RPT, OVERBALANCE AFTER PUMP OUT 555 PSI.- MONITOR WELL ON TRIP TANK. | 7019 | 6810 | SWL | 08/07/2022 | ADC-57L | LOG | KRSN-175
703 | 7019 |  | CIRC | E | 3965 | MPMP | CIRC BTM UP, CIRCULATED PRECAUTIONARY LAST 50 BBL THRUGH CHOKE, CONT. CIRCULATE UNTILL HOLE CLEAN AND CONDITION MUD IN/OUT 79 PCF.- FLOW CHECK WELL STATIC. | 7019 |  | RIG | 08/07/2022 | ADC-57L | LOG | KRSN-175
704 | 7019 | 6670 | LOG | E | 3965 | WLT | SLB WL TAKING SAMPLING WHILE POOH AS PER RMD REQUEST, SCANNING AROUND 6,670 FT FOR SAMPLE #4 .......AT RPT.- SCANNING AROUND 6,670 FT FOR BEST MOBILITY.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. - MAX STATIONARY TIME: 4 HRS.- TOTAL 3 + 1 SAMPLE/PUMP OUT, OUT OF 12 + 6 SAMPLE/PUMP OUT .- TOTAL PUMP OUT "ZERO" L AT RPT, OVERBALANCE 556 PSI.- MONITOR WELL ON TRIP TANK. | 7019 | 6715 | SWL | 08/07/2022 | ADC-57L | LOG | KRSN-175
705 | 141.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/07/2022 | ADC-57L | Type | KRSN-175
706
707
708 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADC-62L | Hrs | ANDR-589
709 | GRF | RIG | 120 | 03 Aug 0500 - 0500 | 0 | 900578 | UNPLANNED MAINTENANCE FOR DRAWWORKS | UPRA | DWKS |  | 08/07/2022 | ADC-62L | 24 | ANDR-589
710 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADES-14 | Hrs | HWYH-536
711 | FOT | BAW | 7 | 07 Aug 2200 - 0500 | 10294 | 900585 | IMAGE LOG READING NOT CLEAR | TF | WLT |  | 08/07/2022 | ADES-14 | 7 | HWYH-536
712 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ADM-337 | Hrs | MRJN-900
713 | XTTE | BCT | 59.25 | 04 Aug 1845 - 0600 | 13019 | 900462 | LEAK IN CHICKSAN LINE, BAD SEAL. | TF | CTU |  | 08/07/2022 | ADM-337 | 1 | MRJN-900
714 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | AOD-111 | Hrs | MRJN-726
715 | FOT | HCO | 1.25 | 07 Aug 0345 - 0500 | 8605 | 900557 | LOST SIGNAL ON HALLIBURTON LOWER PDHMS GAUGE. | TF | PDHMS |  | 08/07/2022 | AOD-111 | 1.25 | MRJN-726
716 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ARO-3004 | Hrs | MRJN-2060
717 | SRVC | SWL | 1.5 | 07 Aug 0830 - 1000 | 9578 | 900588 | SWL DID NOT HAVE TEST PUMP AVAILABLE FOR P/TESTING QTS. RIG SUPPLIED FITTINGS AND PUMP. | WO | NA |  | 08/07/2022 | ARO-3004 | 1.5 | MRJN-2060
718 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ARO-4001 | Hrs | MRJN-532
719 | STBH | ARM | 122.5 | 02 Aug 1145 - 0500 | 6642 | 900419 | GOT SUDDEN HOLE PACK OFF, STRING STALL AND STUCK. | STUK | BHA |  | 08/07/2022 | ARO-4001 | 24 | MRJN-532
720 | FOT | SCP | 7 | 07 Aug 0500 - 1230 | 1568 | 900617 | ONCE PU & MU 4.5" BKR LNR HGR ON MSF STRING & TRY TO CIRCULATE SUDDENLY STRING PLUGGED, POOH & FOUND RUBBER STUCK INSIDE PKR PLUS TOE CIRCULATION SUB (TCS). | TF | PLUGT |  | 08/07/2022 | DPS-5 | 7 | HRDH-2319
721 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | DPS-5 | Hrs | HRDH-2319
722 | HERR | BC | 7 | 06 Aug 2300 - 1900 | 1598 | 900595 | ONCE PU & MU 4.5" BKR LNR HGR ON MSF STRING & TRY TO CIRCULATE SUDDENLY STRING PLUGGED, POOH & FOUND RUBBER STUCK INSIDE PKR PLUS TOE CIRCULATION SUB (TCS). | JF | TBG |  | 08/07/2022 | DPS-5 | 1 | HRDH-2319
723 | FOT | RIG | 5.5 | 07 Aug 1230 - 1800 | 1568 | 900605 | ONCE PU & MU 4.5" BKR LNR HGR ON MSF STRING & TRY TO CIRCULATE SUDDENLY STRING PLUGGED, POOH & FOUND RUBBER STUCK INSIDE PKR PLUS TOE CIRCULATION SUB (TCS). | TF | TBG |  | 08/07/2022 | DPS-5 | 5.5 | HRDH-2319
724 | FOT | SCP | 7 | 07 Aug 0500 - 1230 | 1568 | 900617 | ONCE PU & MU 4.5" BKR LNR HGR ON MSF STRING & TRY TO CIRCULATE SUDDENLY STRING PLUGGED, POOH & FOUND RUBBER STUCK INSIDE PKR PLUS TOE CIRCULATION SUB (TCS). | TF | PLUGT |  | 08/07/2022 | DPS-5 | 7 | HRDH-2319
725 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | DQ-47 | Hrs | KHRS-280
726 | FOT | BHI | 9 | 06 Aug 0200 - 1100 | 3260 | 900491 | ATTEMPTED TO TAKE SURVEY WITH NO SUCESS, TROUBLE SHOOT THE PROBLEM NO SUCESS | SURV | MS |  | 08/07/2022 | DQ-47 | 6 | KHRS-280
727 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ED-85A | Hrs | ZULF-2063
728 | FOT | RIG | 3 | 06 Aug 0300 - 0600 | 11466 | 900596 | WASH PIPE LEAKED. | RR | TDS |  | 08/07/2022 | ED-85A | 1 | ZULF-2063
729 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ENS-108 | Hrs | ZULF-2014
730 | FOT | ENV | 405.25 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/07/2022 | ENS-108 | 24 | ZULF-2014
731 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | ENSCO-76 | Hrs | MRJN-853
732 | OTH | RIG | 1.5 | 06 Aug 0430 - 0600 | 9970 | 900600 | RIG CREW DID NOT FOLLOW INSTRUCTIONS AND DID NOT REAM TIGHT AREAS WHILE RUNNING HOLE | UPRA | NA |  | 08/07/2022 | ENSCO-76 | 1 | MRJN-853
733 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | HI-2 | Hrs | BRRI-433
734 | FOT | BCR | 1 | 07 Aug 0715 - 0815 | 450 | 900586 | R/D BAKER CASING RUNNING TOOL DUE TO TOOL MALFUNCTION. | TF | CRT |  | 08/07/2022 | HI-2 | 1 | BRRI-433
735 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | HI-4 | Hrs | BRRI-1001
736 | FOT | RIG | 2 | 07 Aug 0045 - 0245 | 0 | 900606 | TRIED TO LIFT DIVERTER, FOUND ONE OF THE BOP HANDLING HOISTS NOT WORKING. ISOLATE HOIST AND USE OTHER 3 HOISTS. | RR | DRRK |  | 08/07/2022 | HI-4 | 2 | BRRI-1001
737 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | MP-1 | Hrs | MRJN-78
738 | FOT | NRT | 160 | 31 Jul 0245 - 0230 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/07/2022 | MP-1 | 21.5 | MRJN-78
739 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | MP-4 | Hrs | LWHH-20
740 | FOT | EX1 | 7 | 07 Aug 0500 - 1200 | 0 | 900616 | WHILE M/U EXPRO SLICK LINE PRONG HAD SLICK LINE UNIT SHUTDOWN DUE TO FAILURE OF HYDRAULIC PUMP WAIT TILL REPLACE WITH NEW SLICK LINE UNIT | TF | SLICK |  | 08/07/2022 | MP-4 | 7 | LWHH-20
741 | WC20 | ARM | 17.25 | 01 Aug 0400 - 2130 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, SUSPECT BALLOONING EFFECT, BULLHEAD 102 PCF MUD ON ANNULAS TILL WELL STATIC. | WCNT | NA |  | 08/07/2022 | NBR-263S | 6.25 | QTIF-736
742 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | NBR-263S | Hrs | QTIF-736
743 | STBH | ARM | 129.75 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE. | STUK | BHA |  | 08/07/2022 | NBR-263S | 15.5 | QTIF-736
744 | WC20 | ARM | 17.25 | 01 Aug 0400 - 2130 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, SUSPECT BALLOONING EFFECT, BULLHEAD 102 PCF MUD ON ANNULAS TILL WELL STATIC. | WCNT | NA |  | 08/07/2022 | NBR-263S | 6.25 | QTIF-736
745 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | NBR-654S | Hrs | HRDH-1150
746 | FOT | PKP | 100 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/07/2022 | NBR-654S | 24 | HRDH-1150
747 | FOT | RIG | 2 | 07 Aug 0000 - 0200 | 336 | 900618 | BELL HOUSING OF TDS LUBE PUMP ASSY DISCONNECTED. | RR | TDS |  | 08/07/2022 | PA-70S | 2 | HRDH-1939
748 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | PA-70S | Hrs | HRDH-1939
749 | HERR | SEC | 16.25 | 06 Aug 1500 - 1415 | 90 | 900614 | DUE TO VERY LOW ROP, SECURITY FAILED TO SELECT THE CORRECT TYPE OF BIT TO DRILL 28" SECTION | BHA | BIT |  | 08/07/2022 | PA-70S | 2.25 | HRDH-1939
750 | FOT | RIG | 2 | 07 Aug 0000 - 0200 | 336 | 900618 | BELL HOUSING OF TDS LUBE PUMP ASSY DISCONNECTED. | RR | TDS |  | 08/07/2022 | PA-70S | 2 | HRDH-1939
751 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SA5898 | Hrs | MDRK-66
752 | GRF | RIG | 22 | 07 Aug 0700 - 0500 | 0 | 900613 | UNPLANNED RIG MAINTANENCE (DRAWWORKS BRAKE BANDS CONDITION IS BAD). | UPRA | DWKS |  | 08/07/2022 | SA5898 | 22 | MDRK-66
753 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SCTD-2 | Hrs | HRDH-2148
754 | FOT | RIG | 2 | 07 Aug 2130 - 2330 | 14096 | 900607 | SSV VALVES TRIGGERED DUE TO FAULTY MODULE. REBOOT MODULE AND OPEN THE VALVES. | RR | RWCS |  | 08/07/2022 | SCTD-2 | 2 | HRDH-2148
755 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SINO-29N | Hrs | SFNY-2005
756 | PCPF | ARM | 72 | 05 Aug 0500 - 0500 | 6825 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/07/2022 | SINO-29N | 24 | SFNY-2005
757 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SINO21 | Hrs | ABQQ-512
758 | FOT | RIG | 4 | 07 Aug 1730 - 2130 | 11455 | 900587 | TDS FAILURE. | RR | TDS |  | 08/07/2022 | SINO21 | 4 | ABQQ-512
759 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SND-2002 | Hrs | WAQR-23
760 | FOT | BAW | 29.5 | 06 Aug 1730 - 0500 | 11600 | 900490 | AT LATCHING DEPTH AND WHILE TAKING PRESSURE POINTS, BKR WL TOOL COMMUNICATION FAILED. | TF | WLT |  | 08/07/2022 | SND-2002 | 18 | WAQR-23
761 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SND-2008 | Hrs | HRDH-1812
762 | STDP | RIG | 617 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/07/2022 | SND-2008 | 24 | HRDH-1812
763 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SP-110 | Hrs | MNIF-142
764 | UNKN | RIG | 117.5 | 03 Aug 0730 - 0500 | 0 | 900424 | SHUT DOWN ALL OPERATION & INVESTIGATE CONTRACTOR EMPLOYEE FALL INCIDENT | HSEI | NA |  | 08/07/2022 | SP-110 | 24 | MNIF-142
765 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SP-120 | Hrs | MNIF-187
766 | PCPF | ARM | 17 | 07 Aug 1200 - 0500 | 5758 | 900604 | UNABLE TO PASS TIGHT HOLE W/ 9-5/8" CSG AT 5758', POOH & L/D CSG, RIH REAMING BHA. | TH | NA |  | 08/07/2022 | SP-120 | 17 | MNIF-187
767 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SP-121 | Hrs | BRRI-522
768 | FOT | RIG | 1.25 | 07 Aug 1530 - 1645 | 9033 | 900556 | REPAIR MP# 2 & MP# 3 MEANWHILE CIRC WITH MP# 1 AND RECIPROCATING STRING. | RR | MPMP |  | 08/07/2022 | SP-121 | 1.25 | BRRI-522
769 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SP-124 | Hrs | FDHL-106
770 | FOT | TIL | 25.25 | 06 Aug 0345 - 0500 | 10321 | 900615 | PERFORMD CEMENT JOB FOR 7" LINER , HAD NO PUMP PLUG , HAD RETRUN AND CEMENT U-TUBE AFTRE FINISHED THE JOB DUE TO FLOAT EQUIPMENT FAILEUR . | TF | HGRL |  | 08/07/2022 | SP-124 | 24 | FDHL-106
771 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SP-167 | Hrs | HRDH-218
772 | FPMP | RIG | 2 | 07 Aug 0600 - 0800 | 6340 | 900584 | RIG REPAIR ON MUD PUMP. | RR | MPMP |  | 08/07/2022 | SP-167 | 2 | HRDH-218
773 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SP-260 | Hrs | HMYM-531812
774 | STBH | ARM | 155 | 01 Aug 1800 - 0500 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/07/2022 | SP-260 | 24 | HMYM-531812
775 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SSA-102 | Hrs | QTIF-693
776 | FOT | WI3 | 37 | 06 Aug 1500 - 0500 | 9617 | 900488 | WHILE RIH 7" WHIPSTOCK HAD OBSTRUCTION AT 9617' TRY TO PASS WITHOUT SUCCESS. | TF | WPSTK |  | 08/07/2022 | SSA-102 | 23.5 | QTIF-693
777 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SSA-201 | Hrs | WDYH-13
778 | FOT | HLH | 3 | 07 Aug 1400 - 1700 | 12528 | 900603 | AFTER SET HALL XTREMEGRIP LH, AND RELEASE RUNNING TOOL. START RVERSE CIRC., PREESURE WAS STABLE FOR 10 MIN THEN INCREASED SUDDENLY TO 3,300 PSI, SUSPECTED AN ISSUE WITH LH RUNNING TOOL. | TF | HGRL |  | 08/07/2022 | SSA-201 | 3 | WDYH-13
779 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SSA-51 | Hrs | MNIF-257
780 | FOT | BHI | 36 | 06 Aug 0945 - 2345 | 14230 | 900554 | BHI NOT ABLE TO STEER THE TRAJECTORY. TOOL FAILLURE HAD TO POH TO CHANGE SAME. | BHA | MWD |  | 08/07/2022 | SSA-51 | 18.75 | MNIF-257
781 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/07/2022 | SSA-5969 | Hrs | UTMN-3148
782 | LCRW | ARM | 35.75 | 06 Aug 1315 - 0400 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | STRG |  | 08/07/2022 | SSA-5969 | 20 | UTMN-3148
783 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-31 | Hrs | SDGM-1181
784 | STDP | RIG | 612.5 | 12 Jul 1930 - 0500 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/08/2022 | ADC-31 | 24 | SDGM-1181
785 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-41L | Hrs | SDGM-1244
786 | UVLC | ARM | 457.5 | 19 Jul 0500 - 0500 | 9010 | 900095 | TOTAL LOSSES AT DEPTH OF 9,010 FT - UNCURABLE WITH CONVENTIONAL LCM PILLS | LCIR | NA |  | 08/08/2022 | ADC-41L | 24 | SDGM-1244
787 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-48 | Hrs | HRDH-2316
788 | FOT | RIG | 3.5 | 08 Aug 2230 - 0200 | 10810 | 900568 | EXTRA TIME TO PRESSURE TEST BOP: TEST UNIT PUMP NOT WORKING, NOT DEVELOPING PRESSURE, REPLACED CHECK VALVES IN MANIFOLD, FUNCTION TEST-OK. | TF | TESTT |  | 08/08/2022 | ADC-48 | 3.5 | HRDH-2316
789 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-49 | Hrs | HWYH-1104
790 | FOT | RIG | 6 | 08 Aug 1700 - 2300 | 12567 | 900570 | WHILE RIH 5-7/8" BHA, SUDDENLY DRAWWORK STOP, FOUND CHOPPER FAIL IN VFD HOUSE. | TF | ACDC |  | 08/08/2022 | ADC-49 | 6 | HWYH-1104
791 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-52 | Hrs | SDGM-1185
792 | HINW | BAW | 248 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/08/2022 | ADC-52 | 24 | SDGM-1185
793 | 12705 | 12705 | RW | C | 4046 | BIT | REAM DOWN 6-1/8" OPEN HOLE F/ 10,045 FT TO BTM : 12705 FT SMOOTHLY.- WOB: 0-4 KLBS, RPM: 120 & TQ: 3-4 KFT-LBS, FR: 300 GPM, SPP: 3,450PSI | 12705 | 10045 | RIG | 08/08/2022 | ADC-53L | CT | HRDH-530
794 | 12705 |  | CIRC | C | 4046 | MPMP | SWEPT HOLE WITH 20/20 BBLS LOW VIS/HI WT PILL & CIRCULATED TILL SHAKERS CLEAN.- SYSTEM LOADED WITH 2 PPB LUBRIGLADE- FR: 300 GPM, SPP: 3,450 PSI- RECIPROCATE STRING UP & DOWN WHILE CIRCULATION.- RECORD SCR- FLOW CHECK - WELL STATIC. | 12705 |  | RIG | 08/08/2022 | ADC-53L | CT | HRDH-530
795 | 12705 | 5315 | TO | C | 4046 | BHA | POOH WITH 6-1/8" REAMING BHA ON ELEVATOR F/12,705 FT TO TOW @ 5,315 FT. | 12705 | 12705 | RIG | 08/08/2022 | ADC-53L | CT | HRDH-530
796 | 12705 |  | CIRC | C | 4046 | MPMP | FLOW CHECK - WELL STATIC. | 12705 |  | RIG | 08/08/2022 | ADC-53L | CT | HRDH-530
797 | 12705 | 11720 | RW | C | 4046 | BIT | RIH W/6-1/8" REAMING BHA ON ELEVATOR AS SIMULATION RUN F/5,315 FT TO 11,720 FT.- HOLE IN GOOD CONDITION.- FILL UP STRING EVERY 20 STD.- MONITORED ON TRIP TANK | 12705 | 5315 | RIG | 08/08/2022 | ADC-53L | CT | HRDH-530
798 | 37.75 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | REAMING TRIP FOR LWR COMPL | 24 | 4046 | 07 Aug 1515 | 08/08/2022 | ADC-53L | Type | HRDH-530
799
800
801 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-55L | Hrs | UTMN-3171
802 | STBH | TK3 | 231.25 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/08/2022 | ADC-55L | 24 | UTMN-3171
803 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-56L | Hrs | UTMN-3069
804 | FOT | RIG | 10.5 | 08 Aug 1130 - 2200 | 10608 | 900635 | WHILE DRILLING LOST OWNERSHIP OF ROTARY, STRING STALLED. | RR | ACDC |  | 08/08/2022 | ADC-56L | 10.5 | UTMN-3069
805 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-60 | Hrs | ABSF-216
806 | FOT | BAL | 24 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/08/2022 | ADC-60 | 24 | ABSF-216
807 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADC-62L | Hrs | ANDR-589
808 | GRF | RIG | 144 | 03 Aug 0500 - 0500 | 0 | 900578 | UNPLANNED MAINTENANCE FOR DRAWWORKS | UPRA | DWKS |  | 08/08/2022 | ADC-62L | 24 | ANDR-589
809 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADES-14 | Hrs | HWYH-536
810 | FOT | BAW | 31 | 07 Aug 2200 - 0500 | 10294 | 900585 | IMAGE LOG READING NOT CLEAR (BAKER WL TOOL FAILURE). | TF | WLT |  | 08/08/2022 | ADES-14 | 24 | HWYH-536
811 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADM-262 | Hrs | MRJN-121
812 | FOT | SWL | 14.75 | 07 Aug 1815 - 0900 | 11000 | 900608 | SLB FSI TOOL FAILED WHILE RECORDING SHUTIN CONDITION | TF | PLT |  | 08/08/2022 | ADM-262 | 4 | MRJN-121
813 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ADM-337 | Hrs | MRJN-900
814 | WTHR | ARM | 2.75 | 08 Aug 0600 - 0845 | 0 | 900571 | UNFAVOURABLE WEATHER FOR FLOWBACK AND FLARING | WON | NA |  | 08/08/2022 | ADM-337 | 2.75 | MRJN-900
815 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | AOD-111 | Hrs | MRJN-726
816 | FOT | HCO | 25.25 | 07 Aug 0345 - 0500 | 8605 | 900557 | LOST SIGNAL ON HALLIBURTON LOWER PDHMS GAUGE. | TF | PDHMS |  | 08/08/2022 | AOD-111 | 24 | MRJN-726
817 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ARO-3002 | Hrs | MRJN-813
818 | FOT | BC | 2 | 08 Aug 0000 - 0200 | 16264 | 900569 | UNABLE TO OPEN TRSSSV. | TF | SSSV |  | 08/08/2022 | ARO-3002 | 2 | MRJN-813
819 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ARO-4001 | Hrs | MRJN-532
820 | STBH | ARM | 137.5 | 02 Aug 1145 - 2030 | 6642 | 900419 | GOT SUDDEN HOLE PACK OFF, STRING STALL AND STUCK. | STUK | BHA |  | 08/08/2022 | ARO-4001 | 15.5 | MRJN-532
821 | FOT | SDM | 3 | 08 Aug 2100 - 0000 | 15966 | 900611 | RSS FAILED TO BUILD UP | BHA | RSS |  | 08/08/2022 | DPS-4 | 3 | MDRK-63
822 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | DPS-4 | Hrs | MDRK-63
823 | FOT | SDM | 2 | 08 Aug 1500 - 1700 | 15948 | 900563 | LOST SIGNAL FROM MWD TOOL. | BHA | MWD |  | 08/08/2022 | DPS-4 | 2 | MDRK-63
824 | FOT | SDM | 3 | 08 Aug 2100 - 0000 | 15966 | 900611 | RSS FAILED TO BUILD UP | BHA | RSS |  | 08/08/2022 | DPS-4 | 3 | MDRK-63
825 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | DPS-5 | Hrs | HRDH-2319
826 | FOT | BLH | 18 | 08 Aug 1100 - 0500 | 14118 | 900565 | UNABLE TO GO DOWN W/ MSF LOWER COMPLETION ON 4.5" BKR LNR/HGR, POOH TO SURFACE & FOUND BKR LINER HGR SLIPS PREMATURE MECHANICAL SET. | TF | HGRL |  | 08/08/2022 | DPS-5 | 18 | HRDH-2319
827 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | ENS-108 | Hrs | ZULF-2014
828 | FOT | ENV | 429.25 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/08/2022 | ENS-108 | 24 | ZULF-2014
829 | CEDE | BCM | 3.75 | 08 Aug 1815 - 2200 | 6687 | 900567 | BAKER SLURRY PUMP HOSE LEAKING. | JF | NA |  | 08/08/2022 | EXL-IVA | 3.75 | ZULF-2040
830 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | EXL-IVA | Hrs | ZULF-2040
831 | FOT | GEP | 6.25 | 08 Aug 1130 - 1745 | 6687 | 900566 | UNABLE TO TEST MLH WASH PORTS. | WH | WH |  | 08/08/2022 | EXL-IVA | 6.25 | ZULF-2040
832 | CEDE | BCM | 3.75 | 08 Aug 1815 - 2200 | 6687 | 900567 | BAKER SLURRY PUMP HOSE LEAKING. | JF | NA |  | 08/08/2022 | EXL-IVA | 3.75 | ZULF-2040
833 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | MP-1 | Hrs | MRJN-78
834 | FOT | NRT | 173.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/08/2022 | MP-1 | 13.5 | MRJN-78
835 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | NBR-263S | Hrs | QTIF-736
836 | STBH | ARM | 153.75 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE. | STUK | BHA |  | 08/08/2022 | NBR-263S | 24 | QTIF-736
837 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | NBR-654S | Hrs | HRDH-1150
838 | FOT | PKP | 124 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/08/2022 | NBR-654S | 24 | HRDH-1150
839 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | PA-604S | Hrs | HRDH-1955
840 | FOT | FMC | 1 | 08 Aug 2245 - 2345 | 7441 | 900627 | LAY DOWN #192,193JTS DUE TO OVER TORQUE VIA FRANK'S POWER TONG OIL LEAKING. | TF | TTRQ |  | 08/08/2022 | PA-604S | 1 | HRDH-1955
841 | 9500 | 0 | LOG | E |  | WLT | CORRELATE DEPTH , PERFORM LOG UP MAIN PASS F/ 300' TO SURFACE, RIH TO 5150' PERFORMED REPEAT SECTION F/5150' T/4850' & F/500' T/400', POOH & R/D W/L TOOLS. | 9500 | 300 | HWP | 08/08/2022 | SINO-19L | LOG | HWYH-332
842 | 9500 |  | OTH | E |  | NA | HPJSM, R/D HALLIBURTON W/L MULTI CASING CORROSION LOGGING TOOLS, SHEAVES & BOP. | 9500 |  | HWP | 08/08/2022 | SINO-19L | LOG | HWYH-332
843 | 9500 |  | NU | N |  | BNIP | N/D SHOOTING NIPPLE, N/U BEL NIPPLE. | 9500 |  | RIG | 08/08/2022 | SINO-19L | BOP | HWYH-332
844 | 9500 |  | OTH | N |  | NA | HPJSM, RIH WITH 15 STANDS HWDP, P/U & M/U 9-5/8" RTTS PKR W/STORM VALVE, RIH & SET SAME @ 180', P/T RTTS TO 1000 PSI- HOLD. POH & LD RTTS RUNNING TOOL. PT RTTS & STORM VALVE TO 1000 PSI, HOLD- OK. | 9500 |  | RIG | 08/08/2022 | SINO-19L | WH | HWYH-332
845 | 9500 |  | ND | N |  | BOP | HPJSM, DISCONNECTED EMERGENCY KILL LINE, BELL NIPPLE & FLOW LINE, HUNG & MOVED BOP STACK AWAY FROM WH. | 9500 |  | RIG | 08/08/2022 | SINO-19L | BOP | HWYH-332
846 | 9500 |  | OTH | N |  | NA | HPJSM, ISSUE PTW & REVIEW JSA, GAS TEST CELLAR; NO H2S/LEL, DIG OUT CELLAR 6 FT BELOW LANDING BASE.>> PRESSURE TEST 9 5/8" X 13 3/8" CCA TO 500 PSI WITH INHIBITED WATER, PRESSURE HOLD AT 300 PSI (NO INJECTIVITY).>> MANSOORI PERFORM UT INSPECTION FOR LANDING BASE ( GOOD CONDITION ) ,18-5/8" CSG , 87.5# ( SEAL WELDED TO DONUT PLATE ) , RECORD 3.678 % MAX ML ( GOOD CONDITION ).>> PRESSURE TEST 9 5/8" CSG SLIP TO 1000 PSI, OK. | 9500 |  | RIG | 08/08/2022 | SINO-19L | WH | HWYH-332
847 | 9500 |  | OTH | N | 4049 | NA | (OOS) HPJSM , WELDED 1-1/2" NIPPLE ON 18-5/8" CSG , MANSOORI PERFORM MPI FOR WELDINGS , HOT HEAD R/U & P/T MPHT FOR 1200 PSI- OK , HOT HEAD PERFORMED HOT TAPPING ON 18-5/8" CSG , NO PRESSURE OR GAS ON 18-5/8" X 13-3/8" CCA , R/D MPHT . | 9500 |  | HTD | 08/08/2022 | SINO-19L | WH | HWYH-332
848 | 9500 |  | OTH | N |  | NA | HOT-HED CUT WINDOW ON 18-5/8" CSG , REMOVE CMT , ALMANSOORI PERFORMED UT INSPECTION ON 13-3/8" CSG ( GOOD CONDITION ), BACK FILL 18-5/8" X 13-3/8" CCA W/ CMT, HOT-HED WELD BACK WINDOW, MANSOORI PERFORM MPI FOR WELDING AREA, OK , BACK FILL CELLAR W/ SWEET SAND.> INSTALLED NEEDLE VALVE ON 18-5/8'' CSG FOR FUTURE WORKOVER OPERATIONS. | 9500 |  | HTD | 08/08/2022 | SINO-19L | WH | HWYH-332
849 | 9500 |  | NU | N |  | WH | HPJSM , N/D OLD 13-5/8" X 11" 3M "GRAY" THS , N/U NEW 13-5/8" X 11" 3M "FMC" THS WITH 9-5/8" INTERFERENCE SEAL , P/T 9-5/8" SEALS TO 1000 PS-OK , INSTALL NEW 2 X 2-1/16", 3M "CIW" GATE VALVES. | 9500 |  | RIG | 08/08/2022 | SINO-19L | WH | HWYH-332
850 | 9500 |  | NU | N |  | BOP | HPJSM , N/U CLASS "A" 13-5/8" 5M BOPE & RELATED EQUIPMENT | 9500 |  | RIG | 08/08/2022 | SINO-19L | BOP | HWYH-332
851 | 9500 |  | BOPT | N |  | BOP | HPJSM , F/T BOPE , M/U 9-5/8" CUP TESTER ASSY, P/T THS GATE VALVES , BOP CONNECTIONS , E-KILL LINE TO 300/ 2550 PSI-OK , L/D TEST ASSY . | 9500 |  | RIG | 08/08/2022 | SINO-19L | BOP | HWYH-332
852 | 9500 |  | OTH | N |  | NA | HPJSM, M/U AND RIH WITH HALLIBURTON RETRIEVING TOOL, LATCHED & RETRIVED 9-5/8" RTTS PKR, POOH TO SURFACE, L/D HALLIBURTON 9-5/8" RTTS, POOH & RACK BACK 15 STANDS 4'' HWDP. | 9500 |  | RIG | 08/08/2022 | SINO-19L | WH | HWYH-332
853 | 9500 |  | HT | N |  | BHA | M/U & RIH W/ WFD 7'' WHIPSTOCK & MILLING BHA .>> 7" WHIPSTOCK BHA: 5-1/2" RHN WHIPSTOCK + 6" LEAD MILL + 6-1/8" FLEX MILL + 3-1/2" HWDP + MWD TOOLS+ FLOAT SUB+ X/O .>> ALIGN WHIPSTOCK FACE WITH MWD.>> GAUGE LEAD & FLEX MILLS-OK .>> ATTACH LEAD MILL TO WHIP FACE W/ 43 KLB SHEAR BOLT . | 9500 |  | RIG | 08/08/2022 | SINO-19L | TINL | HWYH-332
854 | 9500 | 1200 | ST | N |  | SPDP | RIH W/ 7'' WFD QC RHN HYD WHIPSTOCK ASSY. ON DRIFTED 4" HWDP/DP STD'S @ CONTROLLED SPEED TO 1200'...INC@RPT.> KEEP MONITOR WELL ON TRIP TANK - STATIC. | 9500 | 60 | RIG | 08/08/2022 | SINO-19L | TINL | HWYH-332
855 | 1.5 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | HOT-HED PERFORM HOT TAPPING ON 18-5/8" CSG . | 1.5 | 4049 | 08 Aug 1700 | 08/08/2022 | SINO-19L | Type | HWYH-332
856
857
858 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SINO-29N | Hrs | SFNY-2005
859 | PCPF | ARM | 96 | 05 Aug 0500 - 0500 | 6825 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/08/2022 | SINO-29N | 24 | SFNY-2005
860 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SND-2002 | Hrs | WAQR-23
861 | FOT | BAW | 51.75 | 06 Aug 1730 - 0315 | 11600 | 900490 | AT LATCHING DEPTH AND WHILE TAKING PRESSURE POINTS, BKR WL TOOL COMMUNICATION FAILED. | TF | WLT |  | 08/08/2022 | SND-2002 | 22.25 | WAQR-23
862 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SND-2008 | Hrs | HRDH-1812
863 | STDP | RIG | 641 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/08/2022 | SND-2008 | 24 | HRDH-1812
864 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SP-110 | Hrs | MNIF-142
865 | UNKN | RIG | 120.5 | 03 Aug 0730 - 0800 | 0 | 900424 | SHUT DOWN ALL OPERATION & INVESTIGATE CONTRACTOR EMPLOYEE FALL INCIDENT | HSEI | NA |  | 08/08/2022 | SP-110 | 3 | MNIF-142
866 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SP-120 | Hrs | MNIF-187
867 | PCPF | ARM | 41 | 07 Aug 1200 - 0500 | 5758 | 900604 | UNABLE TO PASS TIGHT HOLE W/ 9-5/8" CSG AT 5758', POOH & L/D CSG, RIH REAMING BHA. | TH | NA |  | 08/08/2022 | SP-120 | 24 | MNIF-187
868 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SP-124 | Hrs | FDHL-106
869 | FOT | TIL | 49.25 | 06 Aug 0345 - 0500 | 10321 | 900615 | PERFORMD CEMENT JOB FOR 7" LINER , HAD NO BUMP PLUG , HAD RETRUN AND CEMENT U-TUBE AFTRE FINISHED THE JOB DUE TO FLOAT EQUIPMENT FAILEUR . | TF | HGRL |  | 08/08/2022 | SP-124 | 24 | FDHL-106
870 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SP-258 | Hrs | JNAB-872212
871 | FOT | HWP | 9.5 | 08 Aug 1900 - 0430 | 11028 | 900626 | FAILURE OF CAST-XRMI LOGGING TOOL. | TF | WLT |  | 08/08/2022 | SP-258 | 9.5 | JNAB-872212
872 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SP-260 | Hrs | HMYM-531812
873 | STBH | ARM | 179 | 01 Aug 1800 - 0500 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/08/2022 | SP-260 | 24 | HMYM-531812
874 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SSA-102 | Hrs | QTIF-693
875 | FOT | WI3 | 51.25 | 06 Aug 1500 - 0500 | 9617 | 900488 | WHILE RIH 7" WHIPSTOCK HAD OBSTRUCTION AT 9617' TRY TO PASS WITHOUT SUCCESS. | TF | WPSTK |  | 08/08/2022 | SSA-102 | 14.25 | QTIF-693
876 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/08/2022 | SSA-5969 | Hrs | UTMN-3148
877 | STBH | ARM | 59.75 | 06 Aug 1315 - 0500 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | BHA |  | 08/08/2022 | SSA-5969 | 24 | UTMN-3148
878 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-16 | Hrs | JAHM-6
879 | FOT | SWL | 10 | 09 Aug 1900 - 0500 | 11910 | 900676 | SPINNER PLT FAILURE. | TF | PLT |  | 08/09/2022 | ADC-16 | 10 | JAHM-6
880 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-31 | Hrs | SDGM-1181
881 | STDP | RIG | 626.5 | 12 Jul 1930 - 1900 | 14234 | 899623 | TDS TRIPPED AND LOST RPM CAUSING STUCK PIPE. | STUK | DP |  | 08/09/2022 | ADC-31 | 14 | SDGM-1181
882 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-32 | Hrs | ANDR-1010
883 | FOT | RIG | 23 | 09 Aug 0600 - 0500 | 8932 | 900677 | WHILE DRILLING 16" SECTION OBSERVED TDS MOTOR GROUNDED, DECISION MADE TO POOH TO 18-5/8" CSG SHOE TO L/D TDS AND REPLACE TDS MOTOR. | RR | TDS |  | 08/09/2022 | ADC-32 | 23 | ANDR-1010
884 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-42L | Hrs | SDGM-1258
885 | FOT | RIG | 2 | 09 Aug 1000 - 1200 | 10916 | 900689 | REPAIR ON MIXING MUD SYSTEM. | RR | MPMP |  | 08/09/2022 | ADC-42L | 2 | SDGM-1258
886 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-52 | Hrs | SDGM-1185
887 | HINW | BAW | 272 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/09/2022 | ADC-52 | 24 | SDGM-1185
888 | 12705 | 12705 | TI | C | 4046 | BHA | RIH WITH 6-1/8" REAMING BHA ON ELEVATOR AS SIMULATION RUN ON 4" DP F/ 11,720 FT TO 12,705 FT.- HOLE IN GOOD CONDITION.- FILL UP STRING EVERY 20 STD.- MONITORED ON TRIP TANK - WELL STATIC | 12705 | 11720 | RIG | 08/09/2022 | ADC-53L | CT | HRDH-530
889 | 12705 |  | CIRC | C | 4046 | MPMP | SWEPT HOLE WITH 20/20 BBLS LOW VIS/HI WT PILL & CIRCULATED TILL SHAKERS CLEAN.- FR: 300 GPM, SPP: 3,950 PSI.- RECIPROCATE STRING UP & DOWN WHILE CIRCULATION.- MUD LOADED WITH 2 PPB OF LUBRAGLIDE.- RECORD SCR. FLOW CHECK - WELL STATIC. | 12705 |  | RIG | 08/09/2022 | ADC-53L | CT | HRDH-530
890 | 12705 | 5315 | TO | C | 4046 | BHA | POOH WITH 6-1/8" REAMING BHA ON ELEVATOR F/12,705 FT TO TOW @ 5,315 FT.- HOLE IN GOOD CONDITION.- FLOW CHECK - WELL STATIC. | 12705 | 12705 | RIG | 08/09/2022 | ADC-53L | CT | HRDH-530
891 | 12705 | 306 | TO | C | 4046 | STDP | POOH W/6-1/8" REAMING BHA ON ELEVATOR F/TOW @5,315 FT TO TOP OF BHA AT 306 FT.- MONITOR WELL ON TRIP TANK. | 12705 | 5315 | RIG | 08/09/2022 | ADC-53L | CT | HRDH-530
892 | 12705 |  | HT | C | 4046 | BHA | L/D 6 1/8" REAMING BHA.- MONITOR WELL ON TRIP TANK- WELL STATIC | 12705 |  | RIG | 08/09/2022 | ADC-53L | CT | HRDH-530
893 | 12705 |  | HT | C | 4046 | PEL | HPJSM, R/U TESCO TBG HANDLING EQUIPMENT & FUNCTION TESTED SAME.- CLEAN MOUSE HOLE. & HOUSEKEEPING AT RIG FLOOR. | 12705 |  | TSC | 08/09/2022 | ADC-53L | COMP | HRDH-530
894 | 12705 |  | PJSM | C | 4046 | EQLZR | CONDUCTED PJSM WITH ALL INVOLVED PARTIES IN JOB. DISCUSSED ALL HAZARDS ASSOCIATED WITH RUNNING LOWER COMPLETION. | 12705 |  | BC | 08/09/2022 | ADC-53L | COMP | HRDH-530
895 | 12705 | 3292 | RPCS | C | 4046 | LWSCO | P/U, M/U & RIH BAKER LOWER COMPLETION ON 4-1/2" TBG (11.6#, J-55, NEW VAM ) TO 3,292 FT (TOT 72 JTS).- LOWER COMPLETION: 4-1/2" GPV SHOE, 4-1/2" WELLBORE ISOLATION VALVE, 09 X 4.5'' BAKER CF PLUS EQ SCREENS, 4 X 4.5'' MPAS PACKERS & 3 REFLEX PACKERS.- PASS SMOOTHLY AT 7" TOL @ 1,614 FT.- FILL LC STRING WITH 79 PCF OBM.- M/U RUPTURE DISC + X-OVER + 1 STD 4" DP.. | 12705 | 0 | BCR | 08/09/2022 | ADC-53L | COMP | HRDH-530
896 | 61.75 | OOS | Category | DOOS ID | COM | Out of Scope Summary | OH LOWER COMPLETION | 24 | 4046 | 07 Aug 1515 | 08/09/2022 | ADC-53L | Type | HRDH-530
897
898
899 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-55L | Hrs | UTMN-3171
900 | STBH | TK3 | 254 | 30 Jul 0830 - 0345 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/09/2022 | ADC-55L | 22.75 | UTMN-3171
901 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-56L | Hrs | UTMN-3069
902 | FOT | RIG | 5 | 09 Aug 2015 - 0115 | 10684 | 900686 | WHILE MAKING CONNECTION SAVER SUB BREAKING OUT FROM IBOP SIDE. | RR | TDS |  | 08/09/2022 | ADC-56L | 5 | UTMN-3069
903 | 13523 |  | OTH | C |  | NA | HELD PJSM, R/D NABORS HYDRAULIC CATWALK, LOADED TO TRUCK PRIOR TO MOVE TO RIG ADC-62. | 13523 |  | RIG | 08/09/2022 | ADC-58L | STIM | ABHD-169
904 | 13523 |  | PJSM | C | 4125 | NA | HELD PJSM PRIOR TO START R/U SLB CTU EQUIPMENTS, REVIEWED RISK ASSESSMENT OF CTU OPERATIONS, VERIFIED CRITICAL LIFTING OPERATION & THE CREW RESPONSIBILITIES. | 13523 |  | RIG | 08/09/2022 | ADC-58L | STIM | ABHD-169
905 | 13523 |  | OTH | C | 4125 | NA | RD BELL NIPPLE, FLOW LINE, NU FOLLOWING ADAPTER ASSY FOR CTU ON 13-5/8" -5 M BOP ANNULAR PREVENTER: DSA 13 5/8" 5M X 5-1/8" 10M, 5-1/8" X 4-1/16" 10M, 4 1/16-10M SLB GATE VALVE, 4-1/16" 10M RISER LONG 10FT, 4-1/16" 10M RISER LONG 8 FT & 4-1/16" COMBI BOP.- CONNECTED BOP HYD HOSES, FUNCTION TEST SAME & CONNECTED KILL LINE TO CT PUMPING UNIT.- MEANWHILE WORKING ON RIGGING UP & SPOT COILED TUBING UNIT, DID, REEL & EQUIPMENTS.- CONNECTED ALL SURFACE LINES TO FRAC TANKS & PERFORMED HYDRO TEST TO 40 PSI- OK.- TRANSFERE 850 BBL'S FRESH WTR & 800 BBLS OF 77 PCF CACL2 BRINE TO FRAC TANK'S. - CONNECTED DIESEL LINE & PREPARE TO TRANFERE DIESEL TO FRAC TANK. | 13523 |  | SCT | 08/09/2022 | ADC-58L | STIM | ABHD-169
906 | 13523 |  | OTH | C | 4125 | NA | SPOT INJECTOR HEAD, CONNECTED GOSENECK, STAB IN 2 3/8" COIL TBG INSIDE INJECTOR HEAD, M/U INJECTOR HEAD ON STRIPPER, M/U 2 3/8" CONNECTOR, CHANGED STRIPPER ELEMENT & PERFORMED PULL TEST T/45 KLBS-OK.- FLUSHED REEL, P/T TREATING LINE AGAINST REEL ISOLATION VALVE TO 300/7,500-PSI USING WATER FOR 15-MINS HOLD-OK.- P/T KILLL LINE AGAINST VALVES TO 300/2,500 PSI FOR 15-MINS HOLD OK. (2 TESTS).- P/T BETWEEN RIG BOP BSR AND CT BSR TO 500 PSI FOR 15-MINS HOLD-OK.- P/T CT BSR AGAINST GATE VALVE TO 300/2,500 PSI FOR 15-MINS HOLD OK. | 13523 |  | SCT | 08/09/2022 | ADC-58L | STIM | ABHD-169
907 | 13523 |  | OTH | C | 4125 | NA | HELD PJSM. LIFTED CT INJECTOR HEAD TO RIG FLOOR BY CRANE, TRANSFERED TO TOP DRIVE LINKS, CONNECTED 4-1/16" 10M RISER (10FT LONG) & R/U INJECTOR ABOVE CT BOP.----INCT@RPT.- MONITORED WELL THRU CHOKE & T.T ALL TIME FOR PAST OPERATION. | 13523 |  | SCT | 08/09/2022 | ADC-58L | STIM | ABHD-169
908 | 20 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | STIMULATION JOB FOR L-1. | 20 | 4125 | 09 Aug 0030 | 08/09/2022 | ADC-58L | Type | ABHD-169
909
910
911 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-60 | Hrs | ABSF-216
912 | FOT | BAL | 48 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/09/2022 | ADC-60 | 24 | ABSF-216
913 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADC-62L | Hrs | ANDR-589
914 | GRF | RIG | 168 | 03 Aug 0500 - 0500 | 0 | 900578 | UNPLANNED MAINTENANCE FOR DRAWWORKS | UPRA | DWKS |  | 08/09/2022 | ADC-62L | 24 | ANDR-589
915 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ADES-14 | Hrs | HWYH-536
916 | FOT | BAW | 36 | 07 Aug 2200 - 1000 | 10294 | 900585 | IMAGE LOG READING NOT CLEAR (BAKER WL TOOL FAILURE). | TF | WLT |  | 08/09/2022 | ADES-14 | 5 | HWYH-536
917 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | AOD-111 | Hrs | MRJN-726
918 | FOT | HCO | 38.5 | 07 Aug 0345 - 1815 | 8605 | 900557 | LOST SIGNAL ON HALLIBURTON LOWER PDHMS GAUGE. | TF | PDHMS |  | 08/09/2022 | AOD-111 | 13.25 | MRJN-726
919 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | BB-84A | Hrs | MRJN-587
920 | GRF | RIG | 3.75 | 09 Aug 0115 - 0500 | 6753 | 900684 | RIG LOST DRILLER CONTROL POWER | UPRA | PSYS |  | 08/09/2022 | BB-84A | 3.75 | MRJN-587
921 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | DPS-44 | Hrs | UTMN-2342
922 | FOT | HDV | 15.5 | 09 Aug 0700 - 0500 | 6325 | 900681 | AFTER DROPPING HAL FREE FALL DV OPENING PLUG, ATTEMPTED TO PRESSURE UP TO OPEN DV WITHOUT SUCCESS. | TF | DV |  | 08/09/2022 | DPS-44 | 15.5 | UTMN-2342
923 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | DPS-5 | Hrs | HRDH-2319
924 | FOT | BLH | 40.75 | 08 Aug 1100 - 0500 | 14118 | 900565 | UNABLE TO GO DOWN W/ MSF LOWER COMPLETION ON 4.5" BKR LNR/HGR, POOH TO SURFACE & FOUND BKR LINER HGR SLIPS PREMATURE MECHANICAL SET. | TF | HGRL |  | 08/09/2022 | DPS-5 | 22.75 | HRDH-2319
925 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ENS-108 | Hrs | ZULF-2014
926 | FOT | ENV | 453.25 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/09/2022 | ENS-108 | 24 | ZULF-2014
927 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | ENSCO-76 | Hrs | MRJN-853
928 | HERR | BCR | .5 | 09 Aug 0630 - 0700 | 0 | 900674 | BAKER CASING INCORRECTLY INSTALLED TUBING TONGS ON PBR/FLOAT SHOE ASSY CAUSING DAMAGE TO TUBE. | JF | CTRQ |  | 08/09/2022 | ENSCO-76 | .5 | MRJN-853
929 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | HI-2 | Hrs | BRRI-435
930 | CFFM | ARM | .75 | 09 Aug 1630 - 1715 | 2560 | 900683 | CONVERT TO DRILLING WITH SEA WATER, GEL SWEEP & MUD CAP DUE TO TOTAL LOSSES. | LCIR | MDCAP |  | 08/09/2022 | HI-2 | .75 | BRRI-435
931 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | MP-1 | Hrs | MRJN-78
932 | FOT | NRT | 197.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/09/2022 | MP-1 | 24 | MRJN-78
933 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | NBR-115S | Hrs | SDGM-1221
934 | FOT | RIG | 4 | 09 Aug 0100 - 0500 | 1958 | 900682 | PIPE GRAPPLE MALFUNCTIONING. | RR | TDS |  | 08/09/2022 | NBR-115S | 4 | SDGM-1221
935 | XTRI | ITS | 3 | 09 Aug 0200 - 0500 | 317 | 900696 | UNABLE TO MAKE UP CONNECTION, ALL ITS EQUIPMENT IN POOR CONDITION (CRT, POWER TONG, BELT TONG). | JF | CTRQ |  | 08/09/2022 | NBR-16S | 3 | HMYM-433112
936 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | NBR-16S | Hrs | HMYM-433112
937 | XTRI | ITS | 2 | 09 Aug 2130 - 2330 | 0 | 900695 | TROUBLESHOOTING CRT AFTER RIGGED UP. | JF | CTRQ |  | 08/09/2022 | NBR-16S | 2 | HMYM-433112
938 | XTRI | ITS | 3 | 09 Aug 0200 - 0500 | 317 | 900696 | UNABLE TO MAKE UP CONNECTION, ALL ITS EQUIPMENT IN POOR CONDITION (CRT, POWER TONG, BELT TONG). | JF | CTRQ |  | 08/09/2022 | NBR-16S | 3 | HMYM-433112
939 | WC20 | ARM | 22.25 | 01 Aug 0400 - 0400 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, SUSPECT BALLOONING EFFECT, BULLHEAD 102 PCF MUD ON ANNULAS TILL WELL STATIC. | WCNT | NA |  | 08/09/2022 | NBR-263S | 5 | QTIF-736
940 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | NBR-263S | Hrs | QTIF-736
941 | WC20 | ARM | 18.75 | 24 Jul 0500 - 0330 | 14034 | 900030 | FLOW CHECK AFTER CIRC HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=160 PSI, PUMP OPEN FLOAT VALVE AND OBSERVE SIDPP=160 PSI. | WCNT | NA |  | 08/09/2022 | NBR-263S | 2.5 | QTIF-736
942 | STBH | ARM | 170.25 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE. | STUK | BHA |  | 08/09/2022 | NBR-263S | 16.5 | QTIF-736
943 | WC20 | ARM | 22.25 | 01 Aug 0400 - 0400 | 13970 | 900349 | FLOW CHECK , HAD A SLIGHT FLOW, SHUT IN WELL AND OBSERVE PRESS FOUND SICP=0 PSI, SUSPECT BALLOONING EFFECT, BULLHEAD 102 PCF MUD ON ANNULAS TILL WELL STATIC. | WCNT | NA |  | 08/09/2022 | NBR-263S | 5 | QTIF-736
944 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | NBR-591S | Hrs | HRDH-2259
945 | FOT | SDM | 10.5 | 09 Aug 1830 - 0500 | 10776 | 900675 | WHILE DRLG. @ 10,776' COMPLETELY LOST SIGNAL/COMMUNICATION WITH SLB MWD @ SURFACE | BHA | MWD |  | 08/09/2022 | NBR-591S | 10.5 | HRDH-2259
946 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | NBR-633S | Hrs | HRDH-1911
947 | FOT | RIG | 3.5 | 09 Aug 1400 - 1730 | 50 | 900678 | EXCESS TIME TO CUT 24" CASING BY RIG WELDER. | RR | CSYS |  | 08/09/2022 | NBR-633S | 3.5 | HRDH-1911
948 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | NBR-654S | Hrs | HRDH-1150
949 | FOT | PKP | 148 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/09/2022 | NBR-654S | 24 | HRDH-1150
950 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | PA-218S | Hrs | HRDH-1941
951 | FOT | MSD | 3.5 | 09 Aug 0130 - 0500 | 14320 | 900655 | CUMULITIVE LOST TIME FOR TROUBLESHOOTING ALMASOOD TUBING RUNNING EQUIPMENT. | TF | CTRQ |  | 08/09/2022 | PA-218S | 3.5 | HRDH-1941
952 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SDA | Hrs | MRJN-737
953 | FOT | BCT | 1 | 09 Aug 1100 - 1200 | 13280 | 900672 | CHANGING OUT MALFUNCTIONING BUSTER PUMP FROM NITROGEN PUMP. | TF | CTPMP |  | 08/09/2022 | SDA | 1 | MRJN-737
954 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SINO-15L | Hrs | ANDR-566
955 | FOT | SPS | 6.5 | 09 Aug 2230 - 0500 | 7881 | 900691 | LWD FAILURE, TROUBLESHOOT TOOLS, NO SUCCESS. | BHA | LWD |  | 08/09/2022 | SINO-15L | 6.5 | ANDR-566
956 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SINO-22 | Hrs | BRRI-579
957 | IPDF | STO | 9 | 09 Aug 0600 - 1500 | 16099 | 900679 | SLB CT COULD NOT PASS 4-1/2'' ISOLATION KIT SHOE DUE TO CT EXTERNAL CONNECTOR SIZE CLEARANCE (0.125"). | STUK | CTAC |  | 08/09/2022 | SINO-22 | 9 | BRRI-579
958 | FOT | RIG | 1.25 | 09 Aug 0700 - 0815 | 165 | 900698 | LEAKS ON DIVERTER LINES, AFTER INISTAL REPAIR ATTEMPT | RR | RWCS |  | 08/09/2022 | SINO-28L | 1.25 | SHYB-255
959 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SINO-28L | Hrs | SHYB-255
960 | FOT | RIG | 7 | 08 Aug 0000 - 0700 | 165 | 900694 | RIG REPAIR ON ANNULAR REGULATOR | RR | RWCS |  | 08/09/2022 | SINO-28L | 2 | SHYB-255
961 | FOT | RIG | 1.25 | 09 Aug 0700 - 0815 | 165 | 900698 | LEAKS ON DIVERTER LINES, AFTER INISTAL REPAIR ATTEMPT | RR | RWCS |  | 08/09/2022 | SINO-28L | 1.25 | SHYB-255
962 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SINO-29N | Hrs | SFNY-2005
963 | PCPF | ARM | 120 | 05 Aug 0500 - 0500 | 6825 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/09/2022 | SINO-29N | 24 | SFNY-2005
964 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SINO-46L | Hrs | SHYB-270
965 | SRVC | TK2 | 8.5 | 09 Aug 1900 - 0330 | 0 | 900687 | ATTEMPTED TROUPLESHOOTING 2 CMT UNITS WITHOUT SUCCESS, WAIT TO MOBILIZE ANOTHER CMT UNIT FROM SINO-28L. ** FIRST CMT UNIT HAD INSTRUMENTATION PROBLEM & SECOND ONE SLURRY PUMP MALFUNCTION. | WO | NA |  | 08/09/2022 | SINO-46L | 8.5 | SHYB-270
966 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SND-1502 | Hrs | HRDH-124
967 | FOT | BLH | 7 | 09 Aug 1300 - 2000 | 5374 | 900688 | LINER HANGER PARTIALLY SET. | TF | HGRL |  | 08/09/2022 | SND-1502 | 7 | HRDH-124
968 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SND-2008 | Hrs | HRDH-1812
969 | STDP | RIG | 665 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/09/2022 | SND-2008 | 24 | HRDH-1812
970 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SP-120 | Hrs | MNIF-187
971 | PCPF | ARM | 64.75 | 07 Aug 1200 - 0445 | 5758 | 900604 | UNABLE TO PASS TIGHT HOLE W/ 9-5/8" CSG AT 5758', POOH & L/D CSG, RIH REAMING BHA. | TH | NA |  | 08/09/2022 | SP-120 | 23.75 | MNIF-187
972 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SP-154 | Hrs | SDGM-353
973 | XTRI | RIG | 2 | 09 Aug 0300 - 0500 | 9000 | 900697 | EXCESSIVE TIME WHILE MAKING CONNECTIONS. | JF | NA |  | 08/09/2022 | SP-154 | 2 | SDGM-353
974 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SP-260 | Hrs | HMYM-531812
975 | STBH | ARM | 203 | 01 Aug 1800 - 0500 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/09/2022 | SP-260 | 24 | HMYM-531812
976 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SSA-102 | Hrs | QTIF-693
977 | TOST | RIG | 21.5 | 09 Aug 0500 - 0500 | 9617 | 900628 | 7" WHIPSTOCK DROPPED IN HOLE WHILE RIH DUE SHEARED BOLT BY EXCESSIVE SLACKOFF WEIGHT | JF | STRG |  | 08/09/2022 | SSA-102 | 21.5 | QTIF-693
978 | EXPL | HWP | 13.5 | 09 Aug 1500 - 0500 | 3220 | 900680 | WORK ON STRING WITH OVERPULL AND SLACK OFF WHILE WAITING ON BAKER WIRELINE SINCE HALLIBURTON WIRELINE ( ASSIGNED COMPANY) NOT HAVING ENOUGH 9-1/2" DC DCST ( ONLY ONE ). | WO | NA |  | 08/09/2022 | SSA-5969 | 13.5 | UTMN-3148
979 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/09/2022 | SSA-5969 | Hrs | UTMN-3148
980 | STBH | ARM | 69.25 | 06 Aug 1315 - 1430 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | BHA |  | 08/09/2022 | SSA-5969 | 9.5 | UTMN-3148
981 | EXPL | HWP | 13.5 | 09 Aug 1500 - 0500 | 3220 | 900680 | WORK ON STRING WITH OVERPULL AND SLACK OFF WHILE WAITING ON BAKER WIRELINE SINCE HALLIBURTON WIRELINE ( ASSIGNED COMPANY) NOT HAVING ENOUGH 9-1/2" DC DCST ( ONLY ONE ). | WO | NA |  | 08/09/2022 | SSA-5969 | 13.5 | UTMN-3148
982 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ADC-32 | Hrs | ANDR-1010
983 | FOT | RIG | 47 | 09 Aug 0600 - 0500 | 8932 | 900677 | WHILE DRILLING 16" SECTION OBSERVED TDS MOTOR GROUNDED, DECISION MADE TO POOH TO 18-5/8" CSG SHOE TO L/D TDS AND REPLACE TDS MOTOR. | RR | TDS |  | 08/10/2022 | ADC-32 | 24 | ANDR-1010
984 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ADC-43L | Hrs | UTMN-3118
985 | FOT | RIG | 5 | 10 Aug 1330 - 1830 | 12647 | 900740 | LEAK ON UPPER IBOP ON TDS (WHILE TESTING, PRESSURE NOT HOLDING) | RR | RWCS |  | 08/10/2022 | ADC-43L | 5 | UTMN-3118
986 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ADC-52 | Hrs | SDGM-1185
987 | HINW | BAW | 281 | 29 Jul 1300 - 1400 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/10/2022 | ADC-52 | 9 | SDGM-1185
988 | 12705 |  | CIRC | C | 4046 | MPMP | CIRCULATED 1.5 STRING CAPACITY (75 BBL).- CHECK LINER HANGER ON SURFACE - OK, RIH W/ LINER PASS SLOWLY THROUGH BOP & WELL HEAD.- FR: 4.6 BPM, SPP: 750 PSI.- RECORD P/U WT: 89 KLBS, S/O WT: 88 KLBS.- MONITOR WELL ON TRIP TANK | 12705 |  | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
989 | 12705 | 5300 | TI | C | 4046 | STDP | RIH W/4-1/2" LOWER COMPLETION ASSY ON DRIFTED 4" DP FROM 3,410 FT TO 5,300 FT (ABOVE TOW @5315 FT).- FILL STRING EVERY 20 STANDS | 12705 | 3410 | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
990 | 12705 |  | CIRC | C | 4046 | MPMP | CIRCULATED 1.2 STRING VOLIME (85 BBL ). FR: 3.6 BPM, SPP:880 PSI- HPJSM WITH ALL PARTIES FOR RUNNING INSIDE OH.- P/U WT: 115 KLB & S/O WT: 114 KLB | 12705 |  | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
991 | 12705 | 12615 | TI | C | 4046 | STDP | RIH W/4-1/2" LOWER COMPLETION ASSY ON DRIFTED 4" DP & 4" HWDP FROM 5,315 FT (OH) TO SETTING DEPTH 12,615 FT.- FILL UP STRING ON FLY | 12705 | 5315 | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
992 | 12705 |  | CIRC | C | 4046 | MPMP | CIRCULATED W/ OBM- RECIPROCATE STRING UP & DOWN 10 FT WHILE CIRCULATION.- FR: 2.7 BPM, SPP: 1450 PSI.- P/U WT 172 KLB & S/O WT 140 KLB. | 12705 |  | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
993 | 12705 |  | CIRC | C | 4046 | MPMP | SPOT MUDZYME (PETROLIZE HTA PILL )AS BELOW:- PUMP 40 BBLS HI VIS SPACER 85 PCF.- PUMP 40 BBLS SURFACTANT 80 PCF.- PUMP 40 BBLS SOLVENT 80 PCF.- PUMP 60 BBL HI-VIS BRINE SPACER 85 PCF.- PUMP 20 BBL HI-VIS BRINE PRE-SPACER 80 PCF.- 80 BBL MUDZYME PILL 80 PCF.- PUMP 5 BBLS HVP- DROP 1" SETTING BALL.- PUMP 40 BBL HI-VIS BRINE POST-SPACER 80 PCF.- CHASED THE BALL TILL SEATED WITH 79 PCF OBM.- RECIPROCATE STRING UP & DOWN 10 FT DURINGDISPLACEMENT. | 12705 |  | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
994 | 12705 | 9000 | SET | C | 4046 | PKR | SET LOWER COMPLETION PACKERS AS FOLLOW (4-1/2" TBR@ 9,308 FT):- INCREASE PRESSURE TO 3,200 PSI FOR 10 MIN TO SET THE PACKERS.- BLEED OFF PRSSURE TO 600 PSI.- SLACK TO NEUTRAL WT. ROTATE STRING 15 TURN TO RIGHT. CHECKD RT FREE. PRESSURE DROPPED TO 0 PSI. | 12705 | 12000 | BC | 08/10/2022 | ADC-53L | COMP | HRDH-530
995 | 12705 |  | CIRC | C | 4046 | MPMP | CIRCULATE AND CONDITION OBM MWT IN-OUT 79 PCF.- RECIPROCATE STRING UP & DOWN WHILE CIRCULATION- FLOW CHECK : WELL STATIC | 12705 |  | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
996 | 12705 | 5300 | TO | C | 4046 | STDP | POOH WITH BKR LOWER COMP. SETTING TOOL ON 4" HWDP & DP'S TO TOW @ 5315 FTFLOW CHECK : WELL STATIC- MONITORED WELL ON TT & TRIP SHEET, -WELL STATIC-. | 12705 | 9000 | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
997 | 12705 | 0 | TO | C | 4046 | STDP | POOH WITH BKR LOWER COMP. SETTING TOOL ON 4" HWDP & DP'S TO SURFACE.- L/D & INSPECT FOR RUNNING TOOL, NO DAMAGE.- MONITORED WELL ON TT & TRIP SHEET, -WELL STATIC-. | 12705 | 5300 | RIG | 08/10/2022 | ADC-53L | COMP | HRDH-530
998 | 12705 |  | OTH | C | 4046 | LINR | HPJSM, R/U TESCO TBG HANDLING EQUIPMENT & FUNCTION TESTED SAME.- CLEAN MOUSE HOLE. & HOUSEKEEPING AT RIG FLOOR. | 12705 |  | ARM | 08/10/2022 | ADC-53L | CSG | HRDH-530
999 | 12705 |  | PJSM | C | 4046 | LINR | HPJSM | 12705 |  | RIG | 08/10/2022 | ADC-53L | CSG | HRDH-530
1000 | 12705 |  | OTH | C | 4046 | LINR | P/U & M/U 4 1/2" TIW OFF BOTTOM LINER ASSY. AND RIH TO320 FT AS FOLLOWING :- BKR SEAL ASSY + 1 PJ + FC + 1 JT- ASSY 1 : 1 PJ+ TOT I-CIRC SUB + 1 PJ- ASSY 2 : 1 PJ + TOT I-PACK#1 +1 PJ 1 + JT + 2 PJ + 1 JT- ASSY 3 : 1 PJ + + TOT I-PACK#2 + 1 PJ + 1 JT- ASSY 4 : 1 PJ + TOT HYDRO SEAL CEMENT. VALVE + 1 PJ + IJT- CHECK FLOAT, OK- APPLY THREAD LOCK ON ALL CONNECTIONS | 12705 |  | ARM | 08/10/2022 | ADC-53L | CSG | HRDH-530
1001 | 85.75 | OOS | Category | DOOS ID | COM | Out of Scope Summary | OH LOWER COMPLETION | 24 | 4046 | 07 Aug 1515 | 08/10/2022 | ADC-53L | Type | HRDH-530
1002
1003
1004 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ADC-55L | Hrs | UTMN-3171
1005 | STBH | TK3 | 262 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/10/2022 | ADC-55L | 8 | UTMN-3171
1006 | FOT | RIG | 10.5 | 10 Aug 1500 - 0200 | 10910 | 900734 | WHILE CIRCULATION W/420 GPM, OBSERVED LEAK IN TDS WASHPIPE. | RR | CSYS |  | 08/10/2022 | ADC-56L | 10.5 | UTMN-3069
1007 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ADC-56L | Hrs | UTMN-3069
1008 | FOT | RIG | .75 | 10 Aug 1415 - 1500 | 10910 | 900733 | OBSERVED 2 ENGINES (#1 & #5) TRIPPED OUT FROM 5 ENGINES RUNNING WHILE DRILLING | RR | CSYS |  | 08/10/2022 | ADC-56L | .75 | UTMN-3069
1009 | FOT | RIG | 10.5 | 10 Aug 1500 - 0200 | 10910 | 900734 | WHILE CIRCULATION W/420 GPM, OBSERVED LEAK IN TDS WASHPIPE. | RR | CSYS |  | 08/10/2022 | ADC-56L | 10.5 | UTMN-3069
1010 | 7019 | 6420 | LOG | E | 3965 | WLT | SLB WL TAKING SAMPLING WHILE POOH AS PER RMD REQUEST.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. - MAX STATIONARY TIME: 4 HRS.- SAMPLE #8 @ 6,450 FT , TOTAL 2 SESSION.- PUMP OUT SESSION @ 6,440 FT.- PUMP OUT SESSION @ 6,420 FT.- TOTAL 8 SAMPLES OUT OF 12 TOTAL & 6 PUMP OUT ONE OUT OF 6 .- TOTAL PUMP OUT 1910 L AT 21 HRS., OVERBALANCE AFTER PUMP OUT 572 PSI.- MONITOR WELL ON TRIP TANK. | 7019 | 6450 | SWL | 08/10/2022 | ADC-57L | LOG | KRSN-175
1011 | 7019 | 6980 | TI | E | 3965 | STDP | RIH WITH 3# RUN MDT ON TLC MDT FROM 6420 FT TO 6980 FT. | 7019 | 6420 | RIG | 08/10/2022 | ADC-57L | LOG | KRSN-175
1012 | 7019 |  | CIRC | E | 3965 | MPMP | CIRC BTM UP, CIRCULATED PRECAUTIONARY LAST 50 BBL THRUGH CHOKE, CONT. CIRCULATE UNTILL HOLE CLEAN AND CONDITION MUD IN/OUT 79 PCF.- FLOW CHECK WELL STATIC. | 7019 |  | RIG | 08/10/2022 | ADC-57L | LOG | KRSN-175
1013 | 7019 | 6395 | TO | E | 3965 | STDP | POOH WITH 3# RUN MDT ON TLC MDT FROM 6980 FT TO 6395 FT. | 7019 | 6980 | RIG | 08/10/2022 | ADC-57L | LOG | KRSN-175
1014 | 7019 | 6395 | LOG | E | 3965 | WLT | SLB WL TAKING SAMPLING WHILE POOH AS PER RMD REQUEST. PERFORMING STICK TEST PRIOR SAMPLE #9 IN PROGRESS............. AT RPT.- SCAN AROUND 6,395 FT FOR SAMPLE #9.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. - MAX STATIONARY TIME: 4 HRS.- TOTAL 8 SAMPLES OUT OF 12 TOTAL & 6 PUMP OUT ONE OUT OF 6 .- TOTAL PUMP OUT " ZERO" L AT RPT, OVERBALANCE AFTER PUMP OUT 534 PSI.- MONITOR WELL ON TRIP TANK. | 7019 | 6395 | SWL | 08/10/2022 | ADC-57L | LOG | KRSN-175
1015 | 213.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/10/2022 | ADC-57L | Type | KRSN-175
1016
1017
1018 | 13523 |  | OTH | C | 4125 | NA | LIFTED CT INJECTOR HEAD TO RIG FLOOR BY CRANE, TRANSFERED TO TOP DRIVE LINKS, CONNECTED 4-1/16" 10M RISER (10FT LONG) & R/U INJECTOR ABOVE CT BOP. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1019 | 13523 |  | OTH | C | 4125 | NA | MIXED & PUMPED 10 BBLS PICKLING PILL FOLLOWED BY 50 BBLS SODA ASH PILL, DISPLACED WITH 20 BBLS WTR & CONFIRMED PICKLING PILL OUT OF CT NOZZLE.DROPPED 1-1/4" BALL TO DRIFT 2-3/8" CT & DISPL. W/ 74 BBLS OF WTR @ PR 3.3 BPM & 4100 PSI ( CT CAPACITY 74 BBL), OBSERVED PRESS INCREASED T/5700 PSI, DISCONNECTED RISER, BALL CAPTURE & RECOVERED BALL OK. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1020 | 13523 |  | OTH | C | 4125 | NA | M/U CT BHA ( 2-3/8" EXTERNAL CONNECTOR, MHA, 2-3/8" STRAIGHT BAR & NOZZLE). STAB THE COIL TBG INJECTOR ON TOP OF C/T BOP. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1021 | 13523 |  | OTH | C | 4125 | NA | HELD PJSM & COMPLETE P/T OF COIL TUBING PCE AS FOLLOW :-- P/T ALL RISER CONNECTIONS, UPPER STRIPPER AGAINST GATE VALVE TO 300 / 2500 PSI FOR 15 MINS, HOLD- OK.- P/T DOUBLE FLAPPER CHECK VALVE, RISER STACK AGAINST GATE VALVE TO 2500 PSI FOR 15 MINS, HOLD- OK.- P/T PIPE/SLIP RAM, LOWER STRIPPER AGAINST GATE VALVE TO 300 / 2500 PSI FOR 15 MINS, HOLD- OK. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1022 | 13523 |  | OTH | C | 4125 | NA | DISPLACED COIL TUBE W/77 PCF CACL2 BRINE WITH FRICTION REDUCER MEANWHILE MIX MUTUAL SOLVENT PRE-FLUSH ( 745 BBLS). | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1023 | 13523 |  | OTH | C | 4125 | NA | RIH WITH 2 3/8" CT TO 9640 FT (TOW) WHILE CONTINUOUSLY PUMPING 77 PCF LUBRICATED BRINE AT 0.5 BPM, CIRC. PRESS 450 PSI (121 BBLS).- KEPT THE CHOKE OPEN & PERFORMED PULL TESTS EVERY 1000 FT INSIDE CSG. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1024 | 13523 |  | OTH | C | 4125 | NA | RIH WITH 2 3/8" COIL TBG F/9640 FT ( 7" TOW) T/12,358 FT ( 70% OF THE OPEN HOLE) WHILE CONTINUOUSLY PUMPING 77 PCF LUBRICATED BRINE AT 1 BPM, CIRC.PRESS:750 PSI ( 229 BBLS ).- KEPT THE CHOKE OPEN & PERFORMED PULL TESTS EVERY 500 FT INSIDE OPEN HOLE. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1025 | 13523 |  | STIM | C | 4125 | CTU | RIH WITH 2 3/8" COIL TBG F/12,358 FT T/ 13,100 WHILE PUMPING PRE-FLUSH.- KEPT THE CHOKE OPEN UNTIL PUMP 142 BBL @ 3 BPM, CIRC. PRESS : 3300 PSI- CLOSED THE CHOKE & ATTEMPTED TO INJECT THE PRE FLUSH, OBSERVED LOW INJECTIVITY ( 0.5-0.7 BPM & WHP : 900 PSI (TOTAL PRE-FLUSH PUMPED VOLUME 220 BBLS OUT OF 745 BBLS).- DECISION MADE TO SPOT 50 BBLS OF 15% HCL ACID ACROSS THE OPEN HOLE TO IMPROVE THE INJECTIVITY. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1026 | 13523 |  | STIM | C | 4125 | CTU | HELD PJSM, RIH 2 3/8" CT F/13100 FT TO BTM @ 13523 FT MEANWHILE PUMPED 50 BBLS OF 15% HCL ACID & DISPLACED SAME W/ 24 BBLS OF 77 PCF PRE-FLUSH (CT CAPACITY 74 BBLS).- KEPT CHOKE 25% OPEN (PUMPING RATE: 2.0 BPM, WHP: 200 PSI, CIRC. PRESS: 2500 PSI). | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1027 | 13523 |  | STIM | C | 4125 | CTU | POOH 2 3/8" CT F/ 13523 FT T/12500 FT MEANWHILE DISPLACED 15% HCL ACID PILL TO THE OH & CONTINUUE PUMPING THE PLANNED VOLUME OF PRE FLUSH @ PR 2 BPM & CIRC. PRESS : 1500 PSI (TOTAL PRE-FLUSH PUMPED VOLUME 400 BBLS OUT OF 745 BBLS). - OBSERVED WHP PRESSURE DROPPED F/200 PSI TO ZERO PSI ONCE ACID OUT OF CT NOZZLE.- CLOSED THE CHOKE & MONITORING THE THE WELL (WHP:0).- MEANWHILE MIXING HCL ACID FOR THE STIMULATION JOB. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1028 | 13523 |  | STIM | C | 4125 | CTU | RIH W/ 2 3/8" CT F/12500 FT T/12900 FT MEANWHILE PUMPING PRE FLUSH @ PR 2 BPM & CIRC. PRESS : 1100 PSI (TOTAL PRE-FLUSH PUMPED VOLUME 525 BBLS OUT OF 745 BBLS).---- INCT @RPT. -PERFORMED PULL TESTS EVERY 500 FT INSIDE OPEN HOLE. | 13523 |  | SCT | 08/10/2022 | ADC-58L | STIM | ABHD-169
1029 | 44 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | STIMULATION JOB FOR L-1. | 24 | 4125 | 09 Aug 0030 | 08/10/2022 | ADC-58L | Type | ABHD-169
1030
1031
1032 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ADC-60 | Hrs | ABSF-216
1033 | FOT | BAL | 72 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/10/2022 | ADC-60 | 24 | ABSF-216
1034 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | BB-84A | Hrs | MRJN-587
1035 | GRF | RIG | 10.75 | 09 Aug 0115 - 1200 | 6753 | 900684 | RIG LOST DRILLER CONTROL POWER | UPRA | PSYS |  | 08/10/2022 | BB-84A | 7 | MRJN-587
1036 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | DPS-44 | Hrs | UTMN-2342
1037 | FOT | HDV | 37.5 | 09 Aug 0700 - 0500 | 6325 | 900681 | AFTER DROPPING HAL FREE FALL DV OPENING PLUG, ATTEMPTED TO PRESSURE UP TO OPEN DV WITHOUT SUCCESS. | TF | DV |  | 08/10/2022 | DPS-44 | 22 | UTMN-2342
1038 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | DPS-5 | Hrs | HRDH-2319
1039 | FOT | BLH | 64.75 | 08 Aug 1100 - 0500 | 14118 | 900565 | UNABLE TO GO DOWN W/ MSF LOWER COMPLETION ON 4.5" BKR LNR/HGR, POOH TO SURFACE & FOUND BKR LINER HGR SLIPS PREMATURE MECHANICAL SET. | TF | HGRL |  | 08/10/2022 | DPS-5 | 24 | HRDH-2319
1040 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ED-85A | Hrs | ZULF-2063
1041 | FOT | RIG | 17.25 | 10 Aug 0930 - 0245 | 15237 | 900736 | OBSERVED LEAK IN WASH PIPE, CHC AND POH TO SHOE TO CHANGE IT. | RR | SWVL |  | 08/10/2022 | ED-85A | 17.25 | ZULF-2063
1042 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ENS-108 | Hrs | ZULF-2014
1043 | FOT | ENV | 477.25 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/10/2022 | ENS-108 | 24 | ZULF-2014
1044 | FOT | RIG | 1 | 10 Aug 1445 - 1545 | 7700 | 900713 | TDS SWIVEL PACKING FAILED | RR | SWVL |  | 08/10/2022 | ENSCO-76 | 1 | MRJN-853
1045 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | ENSCO-76 | Hrs | MRJN-853
1046 | IHFL | RIG | .5 | 10 Aug 1415 - 1445 | 7700 | 900712 | REPAIR TDS HYDRAULIC SYSTEM (ELEVATORS WOULD NOT ROTATE) | RR | HSYS |  | 08/10/2022 | ENSCO-76 | .5 | MRJN-853
1047 | FOT | RIG | 1 | 10 Aug 1445 - 1545 | 7700 | 900713 | TDS SWIVEL PACKING FAILED | RR | SWVL |  | 08/10/2022 | ENSCO-76 | 1 | MRJN-853
1048 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | MP-1 | Hrs | MRJN-78
1049 | FOT | NRT | 221.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/10/2022 | MP-1 | 24 | MRJN-78
1050 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | NBR-115S | Hrs | SDGM-1221
1051 | FOT | RIG | 15 | 09 Aug 0100 - 1600 | 1958 | 900682 | PIPE GRAPPLE MALFUNCTIONING. | RR | TDS |  | 08/10/2022 | NBR-115S | 11 | SDGM-1221
1052 | FOT | RIG | 1.5 | 10 Aug 0000 - 0130 | 0 | 900752 | DELAY DURING MU BOP TEST ASSY DUE TO TDS ROTATION FAILUE BECAUSE OF ELEC. FAULT ON DRIVE HOUSE.TROUBLESHOOING TDS DRIVE HOUSE, FIXED SAME | RR | TDS |  | 08/10/2022 | NBR-263S | 1.5 | QTIF-736
1053 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | NBR-263S | Hrs | QTIF-736
1054 | STBH | ARM | 187.25 | 29 Jul 0230 - 2200 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE. | STUK | BHA |  | 08/10/2022 | NBR-263S | 17 | QTIF-736
1055 | FOT | RIG | 1.5 | 10 Aug 0000 - 0130 | 0 | 900752 | DELAY DURING MU BOP TEST ASSY DUE TO TDS ROTATION FAILUE BECAUSE OF ELEC. FAULT ON DRIVE HOUSE.TROUBLESHOOING TDS DRIVE HOUSE, FIXED SAME | RR | TDS |  | 08/10/2022 | NBR-263S | 1.5 | QTIF-736
1056 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | NBR-591S | Hrs | HRDH-2259
1057 | FOT | SDM | 23 | 09 Aug 1830 - 1730 | 10776 | 900675 | WHILE DRLG. @ 10,776' COMPLETELY LOST SIGNAL/COMMUNICATION WITH SLB MWD @ SURFACE | BHA | MWD |  | 08/10/2022 | NBR-591S | 12.5 | HRDH-2259
1058 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | NBR-654S | Hrs | HRDH-1150
1059 | FOT | PKP | 172 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/10/2022 | NBR-654S | 24 | HRDH-1150
1060 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | NBR-783S | Hrs | NJYN-93
1061 | FOT | CRT | 5.25 | 10 Aug 2345 - 0500 | 15392 | 900739 | LTTT PACKER FAILED MEAWHILE NEGATIVE TEST | TF | PCPD |  | 08/10/2022 | NBR-783S | 5.25 | NJYN-93
1062 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | NBR-987S | Hrs | JLMN-35
1063 | OTH | RIG | 45 | 09 Aug 0800 - 0500 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/10/2022 | NBR-987S | 24 | JLMN-35
1064 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | PN-7 | Hrs | MRJN-776
1065 | FOT | BHI | 10.5 | 10 Aug 1730 - 0400 | 2598 | 900738 | WHILE FILLING UP STRING, OBSERVED ABNORMAL PRESSURE. | BHA | MWD |  | 08/10/2022 | PN-7 | 10.5 | MRJN-776
1066 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | PN-9 | Hrs | MRJN-672
1067 | FOT | RIG | 3.25 | 10 Aug 1600 - 1915 | 8339 | 900732 | UNABLE TO MIX CASING GO PILL. MIXING HOPPERS NOT FUNCTIONING CORRECTLY DUE TO CIRCULATING LINE BLOCKED & HOPPER CHARGING PUMPS WITH NO SUCTION. | RR | CSYS |  | 08/10/2022 | PN-9 | 3.25 | MRJN-672
1068 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SINO-15L | Hrs | ANDR-566
1069 | FOT | SPS | 25 | 09 Aug 2230 - 2330 | 7881 | 900691 | LWD FAILURE, TROUBLESHOOT TOOLS, NO SUCCESS. | BHA | LWD |  | 08/10/2022 | SINO-15L | 18.5 | ANDR-566
1070 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SINO-28L | Hrs | SHYB-255
1071 | FOT | RIG | 18.25 | 10 Aug 1045 - 0500 | 1030 | 900742 | TDS CONTROL ROOM OVER HEATING ISSUES DUE TO A/C. 1 X A/C BROKEN COMPRESSOR FAILURE 1 X A/C OVERLOADED DUE TO COMPENSATING FOR BROKEN A/C | RR | TDS |  | 08/10/2022 | SINO-28L | 18.25 | SHYB-255
1072 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SINO-29N | Hrs | SFNY-2005
1073 | PCPF | ARM | 135.75 | 05 Aug 0500 - 2045 | 6825 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/10/2022 | SINO-29N | 15.75 | SFNY-2005
1074 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SINO-32L | Hrs | SHYB-198
1075 | HERR | TK2 | 6 | 10 Aug 1130 - 1730 | 11798 | 900737 | WIS L-3 WPS LOCKING PIN HEAD BROKE DUE TO OVER TORQUE. DECISION MADE TO RUN BAKER WPS. | JF | NA |  | 08/10/2022 | SINO-32L | 6 | SHYB-198
1076 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SND-2008 | Hrs | HRDH-1812
1077 | STDP | RIG | 689 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/10/2022 | SND-2008 | 24 | HRDH-1812
1078 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SND-2010 | Hrs | MNIF-869
1079 | WTHR | ARM | 2.5 | 10 Aug 0900 - 1130 | 3141 | 900661 | WHILE RIH UPPER COMPLETION HAD BAD AND DUSTY WEATHER WITH HIGH WIND SPEED 40-45 KM/HR | WON | NA |  | 08/10/2022 | SND-2010 | 2.5 | MNIF-869
1080 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SP-120 | Hrs | MNIF-187
1081 | PCPF | ARM | 88.75 | 07 Aug 1200 - 0500 | 5758 | 900604 | UNABLE TO PASS TIGHT HOLE W/ 9-5/8" CSG AT 5758', POOH & L/D CSG, RIH REAMING BHA. | TH | NA |  | 08/10/2022 | SP-120 | 24 | MNIF-187
1082 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SP-123 | Hrs | KRSN-124
1083 | FOT | RIG | 3.5 | 10 Aug 2145 - 0115 | 0 | 900743 | EXCESSIVE TIME WHILE OPENING RAM BONNET BOLTS. | BOP | RAMS |  | 08/10/2022 | SP-123 | 3.5 | KRSN-124
1084 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SP-124 | Hrs | FDHL-106
1085 | FOT | TIL | 97.25 | 06 Aug 0345 - 0500 | 10321 | 900615 | PERFORMD CEMENT JOB FOR 7" LINER , HAD NO BUMP PLUG , HAD RETRUN AND CEMENT U-TUBE AFTRE FINISHED THE JOB DUE TO FLOAT EQUIPMENT FAILEUR . | TF | HGRL |  | 08/10/2022 | SP-124 | 24 | FDHL-106
1086 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SP-167 | Hrs | HRDH-218
1087 | ORDS | ARN | 14.5 | 10 Aug 0800 - 2230 | 7167 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/10/2022 | SP-167 | 14.5 | HRDH-218
1088 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SP-260 | Hrs | HMYM-531812
1089 | STBH | ARM | 227 | 01 Aug 1800 - 0500 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/10/2022 | SP-260 | 24 | HMYM-531812
1090 | TOST | RIG | 48 | 06 Aug 1900 - 1645 | 9617 | 900628 | 7" WHIPSTOCK DROPPED IN HOLE WHILE RIH DUE SHEARED BOLT BY EXCESSIVE SLACKOFF WEIGHT | JF | STRG |  | 08/10/2022 | SSA-102 | 11.75 | QTIF-693
1091 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SSA-102 | Hrs | QTIF-693
1092 | FOT | WI3 | 48 | 06 Aug 1500 - 0500 | 9617 | 900488 | 7" WHIPSTOCK DROPPED IN HOLE WHILE RIH DUE SHEARED BOLT BY EXCESSIVE SLACKOFF WEIGHT, WIS SERVICE HAND WASN'T IN RIG FLOOR TO WITNESS THE JOB | TF | WPSTK |  | 08/10/2022 | SSA-102 | 11.75 | QTIF-693
1093 | TOST | RIG | 48 | 06 Aug 1900 - 1645 | 9617 | 900628 | 7" WHIPSTOCK DROPPED IN HOLE WHILE RIH DUE SHEARED BOLT BY EXCESSIVE SLACKOFF WEIGHT | JF | STRG |  | 08/10/2022 | SSA-102 | 11.75 | QTIF-693
1094 | EXPL | HWP | 23 | 09 Aug 1500 - 1500 | 3220 | 900680 | WORK ON STRING WITH OVERPULL AND SLACK OFF WHILE WAITING ON BAKER WIRELINE SINCE HALLIBURTON WIRELINE ( ASSIGNED COMPANY) NOT HAVING ENOUGH 9-1/2" DC DCST ( ONLY ONE ). | WO | NA |  | 08/10/2022 | SSA-5969 | 9.5 | UTMN-3148
1095 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/10/2022 | SSA-5969 | Hrs | UTMN-3148
1096 | STBH | ARM | 83.25 | 06 Aug 1315 - 0500 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | BHA |  | 08/10/2022 | SSA-5969 | 14 | UTMN-3148
1097 | EXPL | HWP | 23 | 09 Aug 1500 - 1500 | 3220 | 900680 | WORK ON STRING WITH OVERPULL AND SLACK OFF WHILE WAITING ON BAKER WIRELINE SINCE HALLIBURTON WIRELINE ( ASSIGNED COMPANY) NOT HAVING ENOUGH 9-1/2" DC DCST ( ONLY ONE ). | WO | NA |  | 08/10/2022 | SSA-5969 | 9.5 | UTMN-3148
1098 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ADC-17 | Hrs | ZULF-1218
1099 | WTHR | ARM | 5.5 | 11 Aug 0530 - 1100 | 0 | 900748 | WAIT ON WEATHER, HIGH WIND SPEED | WON | NA | 900662 | 08/11/2022 | ADC-17 | 5.5 | ZULF-1218
1100 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ADC-21 | Hrs | MZLJ-155201
1101 | XTRI | RIG | 7.25 | 11 Aug 1915 - 0230 | 19221 | 900780 | EXCESSIVE TIME TO NIPPLE DOWN BOP & DSA. DUE TROUBLE REMOVING NUTS & STUDS. | JF | BOP |  | 08/11/2022 | ADC-21 | 7.25 | MZLJ-155201
1102 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ADC-32 | Hrs | ANDR-1010
1103 | OTH | RIG | 67.25 | 09 Aug 0600 - 0115 | 8932 | 900677 | WHILE DRILLING 16" SECTION OBSERVED TDS MOTOR GROUNDED, DECISION MADE TO POOH TO 18-5/8" CSG SHOE TO L/D TDS AND REPLACE TDS MOTOR. | UPRA | NA |  | 08/11/2022 | ADC-32 | 20.25 | ANDR-1010
1104 | 12705 |  | OTH | C | 4145 | LINR | CONT. RIH WITH 4 1/2" TOT OB- LINER ASSY ON 4-1/2" TBG (11.6#, J-55, NEW VAM ) TO 4,249 FT (103/103 JTS).- FILL STRING WITH 79 PCF MUD EVERY JTS. | 12705 |  | ARM | 08/11/2022 | ADC-53L | CSG | HRDH-530
1105 | 12705 |  | RCSG | C | 4145 | HGRL | HPJSM , P/U & M/U 7" X 4-1/2" TOT LINER HANGER & TOP PACKER. RIH TO 4,352 FT.- VISUALLY INSPECTED PACKER & LINER HANGER DIES.- RECORD FREE PARAMETERS P/U 99 KLB & S/O 99 KLB. | 12705 |  | TOT | 08/11/2022 | ADC-53L | CSG | HRDH-530
1106 | 12705 |  | CIRC | C | 4145 | MPMP | CIRCULATE 1.2 LINER CAPACITY : 80 BBLS. FR: 4 BPM, SPP: 450 PSI.- R/D TESCO TBG HANDLING EQUIPMENT.- HPJSM FOR DRIFT 4" HWDP & 4" DP. | 12705 |  | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1107 | 12705 | 5315 | RCSG | C | 4145 | STRG | CONT. RIH WITH 4-1/2" OBL ON DRIFTED 4" HWDP F/ 4,352 FT TO TOW @ 5,315 FT.- RIH CONTROLLED SPEED 1.5 - 2 MIN SLIP TO SLIP. | 12705 | 4352 | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1108 | 12705 |  | CIRC | C | 4145 | MPMP | BREAK CIRCULATION WITH 100 GPM & PRESS: 400 PSI & RECORD P/U: 119 KLBS & S/O WT: 118 KLBS. | 12705 |  | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1109 | 12705 | 9300 | RCSG | C | 4145 | CTRQ | CONT. RIH WITH 4-1/2" OBL ON DRIFTED 4" HWDP & 4" DP F/ 5,315 FT TO TBR @ 9,300 FT.- RIH CONTROLLED SPEED 1.5 - 2 MIN SLIP TO SLIP. | 12705 | 5315 | TSC | 08/11/2022 | ADC-53L | CSG | HRDH-530
1110 | 12705 |  | OTH | C | 4145 | LINR | HPJSM M/U TOT CMT MANIFOLD. TOT DROP 1.5" BALL & CHASE DOWN. SET LINER HNGR @ 1500 PSI, CONFIRM HANGER SET WITH 30 KLB'S S/O, OK. SET BOTH I-PACK PKRS @ 1800 PSI, RELEASE RUNNING TOOL @ 2500 PSI & OPEN PORT COLLAR @ 3100 PSI, ESTABLISH CIRCULATION.- P/U: 180 KLB & S/D: 150 KLB WEIGHT. | 12705 |  | TK3 | 08/11/2022 | ADC-53L | CSG | HRDH-530
1111 | 12705 |  | CIRC | C | 4145 | MPMP | CIRCULATE HOLE TO 79 PCF WBM. | 12705 |  | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1112 | 12705 |  | PTST | C | 4145 | MPMP | HPJSM , P/T CMT LINES TO 500 PSI / 4000 PSI, OK. | 12705 |  | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1113 | 12705 |  | CIRC | C | 4145 | MPMP | CIRCULATE MEANWHILE BATCH MIXED TAIL SLURRY 125 PCF.- FR : 3 BPM , PRESS: 490 PSI. | 12705 |  | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1114 | 12705 |  | CMC | C | 4145 | LINR | PERFORMED CMT JOB FOR 4 1/2" OFF BTTM LINER AS BELOW:- PUMPED 110 BBL 90 PCF SPACER AHEAD.- PUMPED 106 BBL 125 PCF CEMENT SLURRY.- DROPPED DP DART.- DISPLACED WITH 108 BBLS , 79 PCF WBM- BUMP PLUG WITH 3500 PSI , 2200 PSI OVER FDP (1300 PSI) 5 MIN, PRESSURE HOLD. BLEED-OFF PRESSURE TO 0 PSI, NO BACK FLOW.- HAD 70 BBL'S LOSSES DURING CMT JOB. - CIP @ 23:00 HRS | 12705 |  | SCM | 08/11/2022 | ADC-53L | CSG | HRDH-530
1115 | 12705 |  | OTH | C | 4145 | LINR | R/D CMT HEAD AND LINES | 12705 |  | ARM | 08/11/2022 | ADC-53L | CSG | HRDH-530
1116 | 12705 | 4548 | RCSG | C | 4145 | STRG | POOH 5 STDS | 12705 | 5012 | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1117 | 12705 |  | CIRC | C | 4145 | MPMP | NORMAL CIRCULATION , FR: 300 GPM , P: 1060 PSIGOT ON SURFACE 20 BBLS CONTAMINATED SPACER AND 50 BBLS NEAT SPACER | 12705 |  | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1118 | 12705 |  | RR | C |  | DWKS | PERFORM SLIP & CUT DRILLING LINE.- CUT 130 FT DRILLING LINE | 12705 |  | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1119 | 12705 | 2334 | RCSG | C | 4145 | STRG | POOH WITH 4 1/2" LINER SETTING TOOL ON 4" DP STDS TO 2,334 FT...ON GOING ART.- MONITOR WELL ON TRIP TANK, LEVEL STATIC. | 12705 | 4548 | RIG | 08/11/2022 | ADC-53L | CSG | HRDH-530
1120 | 24 | OOS | Category | DOOS ID | RLIN | Out of Scope Summary | RIH 4-1/2" OFF BTTM LINER. | 22 | 4145 | 10 Aug 0300 | 08/11/2022 | ADC-53L | Type | HRDH-530
1121
1122
1123 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ADC-55L | Hrs | UTMN-3171
1124 | STBH | TK3 | 286 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/11/2022 | ADC-55L | 24 | UTMN-3171
1125 | 7019 | 6340 | LOG | E | 3965 | WLT | SLB WL TAKING SAMPLING WHILE POOH AS PER RMD REQUEST.SAMPLE #12 IN PROGRESS............. AT RPT.- SCAN AROUND 6,343 FT FOR SAMPLE #12.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. - MAX STATIONARY TIME: 4 HRS.- SAMPLE #9 @ 6,395 FT , TOTAL 1 SESSION.- SAMPLE #10 @ 6,380 FT , TOTAL 1 SESSION.- SAMPLE #11 @ 6,360 FT , TOTAL 2 SESSION.- TOTAL 12 SAMPLES OUT OF 13 TOTAL & 6 PUMP OUT ONE OUT OF 6 .- TOTAL PUMP OUT 688 L AT RPT, OVERBALANCE AFTER PUMP OUT 513 PSI.- MONITOR WELL ON TRIP TANK. | 7019 | 6395 | SWL | 08/11/2022 | ADC-57L | LOG | KRSN-175
1126 | 237.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/11/2022 | ADC-57L | Type | KRSN-175
1127
1128
1129 | 13523 |  | STIM | C | 4125 | CTU | RIH W/ 2 3/8" CT F/12900 FT TO BTM @13523 FT MEANWHILE PUMPING PRE FLUSH @ PR 2 BPM & CIRC. PRESS : 1100 PSI ( COMPLETED STAGE 1 & 2, TOTAL PRE-FLUSH PUMPED VOLUME 745 BBLS).- PERFORMED PULL TESTS EVERY 500 FT INSIDE OPEN HOLE. | 13523 |  | SCT | 08/11/2022 | ADC-58L | STIM | ABHD-169
1130 | 13523 |  | STIM | C | 4125 | CTU | POOH WITH SLB 2 3/8" CT F/15523 FT (BTM) T/9640 FT (TOW) WHILE PUMPING 15 BBLS OF 15% EMULSIFIED ACID FOLLOWING BY 48 BBLS OF 15% HCL ACID PER EACH STAGE (TOTAL 18 STAGES) WITH CHOKE CLOSED.- SLB CT FOLLOWED THE MATRIX ACID STIMULATION TREATMENT PUMPING SCHEDULE AS PROGRAM.- STOPPED 30 FT BELOW TOP OF WINDOW TILL ALL ACID PUMPED OUT OF COIL TBG NOZZLES.- TOTAL PUMPED VOLUME 272 BBLS OF 15% EMULSIFIED HCL & 907 BBLS OF 15% HCL.- CT-SPEED 6 FPM, PUMPING RATE: 2 BPM, CIRC. PRESS : 1250-1700 PSI, WHP: 0 PSI. | 13523 |  | SCT | 08/11/2022 | ADC-58L | STIM | ABHD-169
1131 | 13523 |  | STIM | C | 4125 | CTU | POOH WITH SLB 2-3/8" CT T/9540 FT ( 100 FT ABOVE TOW) AND PUMPED 745 BBLS OF POST -FLUSH & DISPLACED W/77 PCF BRINE AT FR 3 BPM, CIRC. PRESS 1200 PSI & WHP : ZERO. | 13523 |  | SCT | 08/11/2022 | ADC-58L | STIM | ABHD-169
1132 | 13523 |  | OTH | C | 4125 | NA | POOH WITH SLB 2-3/8" CT F/9540 FT TO SURCAE MEANWHILE RIG PUMPED 900 BBL 1.2 HOLE VOLUME OF 77 PCF BRINE ( CACL2) THRU CT KILL LINE @ 4 BPM. (SPP:20 PSI, WHP: 0 PSI). | 13523 |  | SCT | 08/11/2022 | ADC-58L | STIM | ABHD-169
1133 | 13523 |  | OTH | C | 4125 | NA | PUMPED 600 BBLS OF 77 PCF BRINE THRU CT KILL LINE @ 5 BPM ( SPP:30 PSI, WHP: 0 PSI ). | 13523 |  | RIG | 08/11/2022 | ADC-58L | STIM | ABHD-169
1134 | 13523 |  | OTH | C | 4125 | NA | CLOSED GATE VALVE & FLUSHED REEL WITH 80 BBLS OF WATER.- CONTINUOUSLY PUMPING 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH BOP KILL LINE, WELL IN TOTAL LOSSES. | 13523 |  | SCT | 08/11/2022 | ADC-58L | STIM | ABHD-169
1135 | 13523 |  | OTH | C | 4125 | NA | HELD PJSM DISCONNECTED 4 1/16" 10K FLANGE BETWEEN C/T BOP & 4 1/16" 10K RISER, LIFTED C/T INJECTOR BY TDS, L/D CT BHA, L/D 4 1/16" RISER.---- INCT@RPT.- CONTINUOUSLY PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH KILL LINE, WELL ON TOTAL LOSSES. | 13523 |  | SCT | 08/11/2022 | ADC-58L | STIM | ABHD-169
1136 | 68 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | PERFORM ACID STIMULATION JOB FOR L-1. | 24 | 4125 | 09 Aug 0030 | 08/11/2022 | ADC-58L | Type | ABHD-169
1137
1138
1139 | FOT | RIG | 1.5 | 11 Aug 0130 - 0300 | 11253 | 900787 | INTERLOCK SYSTEM NOT FUNCTIONING PROPERLY. UNABLE TO APPLY TORQUE - PIPE GRABBER SLIPPING. | RR | TDS |  | 08/11/2022 | ADC-60 | 1.5 | ABSF-216
1140 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ADC-60 | Hrs | ABSF-216
1141 | FOT | BAL | 94.5 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/11/2022 | ADC-60 | 22.5 | ABSF-216
1142 | FOT | RIG | 1.5 | 11 Aug 0130 - 0300 | 11253 | 900787 | INTERLOCK SYSTEM NOT FUNCTIONING PROPERLY. UNABLE TO APPLY TORQUE - PIPE GRABBER SLIPPING. | RR | TDS |  | 08/11/2022 | ADC-60 | 1.5 | ABSF-216
1143 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ADES-173 | Hrs | UTMN-1952
1144 | FOT | BAW | 13 | 11 Aug 1600 - 0500 | 11811 | 900746 | BAKER WIRELINE TOOLS LOST COMMUNICATION. | TF | WLT |  | 08/11/2022 | ADES-173 | 13 | UTMN-1952
1145 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ARO-2003 | Hrs | MNIF-733
1146 | WTHR | ARN | 24.5 | 10 Aug 1315 - 1345 | 0 | 900744 | WAIT ON WEATHER | WON | NA |  | 08/11/2022 | ARO-2003 | 8.75 | MNIF-733
1147 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ARO-3002 | Hrs | MRJN-813
1148 | HERR | BCT | 12 | 11 Aug 1100 - 2300 | 40 | 900715 | ATTEMPT TO RUN CT, OBSERVED A DAMAGE ON THE GOOSE NECK, CT REEL WAS LEFT SECURED FOR MAINTENANCE THE NIGHT BEFORE. | JF | CTAC |  | 08/11/2022 | ARO-3002 | 12 | MRJN-813
1149 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | DPS-44 | Hrs | UTMN-2342
1150 | FOT | HDV | 51 | 09 Aug 0700 - 1830 | 6325 | 900681 | AFTER DROPPING HAL FREE FALL DV OPENING PLUG, ATTEMPTED TO PRESSURE UP TO OPEN DV WITHOUT SUCCESS. | TF | DV |  | 08/11/2022 | DPS-44 | 13.5 | UTMN-2342
1151 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | DPS-5 | Hrs | HRDH-2319
1152 | FOT | BLH | 77.25 | 08 Aug 1100 - 1730 | 14118 | 900565 | UNABLE TO GO DOWN W/ MSF LOWER COMPLETION ON 4.5" BKR LNR/HGR, POOH TO SURFACE & FOUND BKR LINER HGR SLIPS PREMATURE MECHANICAL SET. | TF | HGRL |  | 08/11/2022 | DPS-5 | 12.5 | HRDH-2319
1153 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | DQ-47 | Hrs | KHRS-280
1154 | FWTS | RIG | 21.25 | 11 Aug 0745 - 0500 | 4461 | 900749 | WHILE REAMING DOWN AT DEPTH 4461' HAD 850 PSI SUDDEN PRESSURE DROP AND LOST 15 KLBS WEIGHT. | FISH | STRG |  | 08/11/2022 | DQ-47 | 21.25 | KHRS-280
1155 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | DQ-57L | Hrs | KHRS-68
1156 | FOT | SPS | 15 | 11 Aug 1400 - 0500 | 6257 | 900784 | SPS RSS (ICRUISE ) HAD NO SIGNAL & NOT RESPOND TROUBLESHOOT TOOLS, NO SUCCESS. | BHA | RSS |  | 08/11/2022 | DQ-57L | 15 | KHRS-68
1157 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | ENS-108 | Hrs | ZULF-2014
1158 | FOT | ENV | 476.75 | 21 Jul 0330 - 0500 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/11/2022 | ENS-108 | 24 | ZULF-2014
1159 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | NBR-16S | Hrs | HMYM-433112
1160 | FOT | RIG | 1.25 | 11 Aug 0815 - 0930 | 485 | 900786 | OBSERVED 400 PSI STAND PIPE PRESSURE DROP | RR | MPMP |  | 08/11/2022 | NBR-16S | 1.25 | HMYM-433112
1161 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | NBR-20S | Hrs | HMYM-433502
1162 | FOT | RIG | 1.5 | 11 Aug 1700 - 1830 | 7919 | 900777 | UNABLE TO DISCONNECT TDS. | RR | TDS |  | 08/11/2022 | NBR-20S | 1.5 | HMYM-433502
1163 | FOT | RIG | 1 | 11 Aug 1130 - 1230 | 0 | 900776 | HAD A PROBLEM ON BOP TEST PUMP PRESSURE GUAGE, TROUBLESHOOTING & REPLACED SAME. | RR | EDR |  | 08/11/2022 | NBR-263S | 1 | QTIF-736
1164 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | NBR-263S | Hrs | QTIF-736
1165 | STBH | ARM | 200.25 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/11/2022 | NBR-263S | 13 | QTIF-736
1166 | FOT | RIG | 2.5 | 10 Aug 0000 - 1530 | 0 | 900752 | DELAY DURING MU BOP TEST ASSY DUE TO TDS ROTATION FAILUE BECAUSE OF ELEC. FAULT ON DRIVE HOUSE.TROUBLESHOOING TDS DRIVE HOUSE, FIXED SAME | RR | TDS |  | 08/11/2022 | NBR-263S | 1 | QTIF-736
1167 | FOT | RIG | 1 | 11 Aug 1130 - 1230 | 0 | 900776 | HAD A PROBLEM ON BOP TEST PUMP PRESSURE GUAGE, TROUBLESHOOTING & REPLACED SAME. | RR | EDR |  | 08/11/2022 | NBR-263S | 1 | QTIF-736
1168 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | NBR-654S | Hrs | HRDH-1150
1169 | FOT | PKP | 196 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/11/2022 | NBR-654S | 24 | HRDH-1150
1170 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | NBR-783S | Hrs | NJYN-93
1171 | FOT | CRT | 29.25 | 10 Aug 2345 - 0500 | 15392 | 900739 | LTTT PACKER FAILED MEAWHILE NEGATIVE TEST | BHA | WBCL |  | 08/11/2022 | NBR-783S | 24 | NJYN-93
1172 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | NBR-987S | Hrs | JLMN-35
1173 | OTH | RIG | 69 | 09 Aug 0800 - 0500 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/11/2022 | NBR-987S | 24 | JLMN-35
1174 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | PA-70S | Hrs | HRDH-1939
1175 | EDIS | RIG | 1 | 11 Aug 2000 - 2100 | 2941 | 900775 | HAD RIG POWER SYSTEM SHUT DOWN DUE TO ENGINES OVERLOAD. | RR | PSYS |  | 08/11/2022 | PA-70S | 1 | HRDH-1939
1176 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SINO-15L | Hrs | ANDR-566
1177 | IDPR | RIG | 5 | 11 Aug 0500 - 1000 | 8186 | 900778 | OBSERVED PRESSURE DROP, POOH, STRING WASHOUT, REPLACED, RIH TO BTM. | DSF | DP |  | 08/11/2022 | SINO-15L | 5 | ANDR-566
1178 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SINO-28L | Hrs | SHYB-255
1179 | FOT | RIG | 34.75 | 10 Aug 1045 - 0030 | 1030 | 900742 | TDS CONTROL ROOM OVER HEATING ISSUES DUE TO A/C. 1 X A/C BROKEN COMPRESSOR FAILURE 1 X A/C OVERLOADED DUE TO COMPENSATING FOR BROKEN A/C | RR | TDS |  | 08/11/2022 | SINO-28L | 16.5 | SHYB-255
1180 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SINO-29N | Hrs | SFNY-2005
1181 | PCPF | ARM | 168 | 05 Aug 0500 - 0500 | 6825 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/11/2022 | SINO-29N | 24 | SFNY-2005
1182 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SND-2008 | Hrs | HRDH-1812
1183 | STDP | RIG | 713 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/11/2022 | SND-2008 | 24 | HRDH-1812
1184 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SP-120 | Hrs | MNIF-187
1185 | PCPF | ARM | 93.75 | 07 Aug 1200 - 1000 | 5758 | 900604 | UNABLE TO PASS TIGHT HOLE W/ 9-5/8" CSG AT 5758', POOH & L/D CSG, RIH REAMING BHA. | TH | NA |  | 08/11/2022 | SP-120 | 5 | MNIF-187
1186 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SP-167 | Hrs | HRDH-218
1187 | ORDS | ARN | 38.5 | 10 Aug 0800 - 0500 | 7167 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/11/2022 | SP-167 | 24 | HRDH-218
1188 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SP-260 | Hrs | HMYM-531812
1189 | STBH | ARM | 245 | 01 Aug 1800 - 2300 | 5095 | 900366 | ENCOUNTERED TIGHT HOLE AND DRILL STRING BECAME STUCK WITH CIRCULATION | STUK | BHA |  | 08/11/2022 | SP-260 | 18 | HMYM-531812
1190 | FOT | RIG | .5 | 11 Aug 0315 - 0345 | 10519 | 900779 | VALVE & SEAT FAILURE | RR | MPMP |  | 08/11/2022 | SSA-5892 | .5 | AWTD-141400
1191 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SSA-5892 | Hrs | AWTD-141400
1192 | FOT | RIG | 1 | 11 Aug 1645 - 1745 | 10220 | 900751 | POP OFF VALVE | RR | MPMP |  | 08/11/2022 | SSA-5892 | 1 | AWTD-141400
1193 | FOT | RIG | .5 | 11 Aug 2130 - 2200 | 10376 | 900772 | VALVE FAILURE | RR | MPMP |  | 08/11/2022 | SSA-5892 | .5 | AWTD-141400
1194 | FOT | RIG | .5 | 11 Aug 2245 - 2315 | 10376 | 900773 | VALVE FAILURE | RR | MPMP |  | 08/11/2022 | SSA-5892 | .5 | AWTD-141400
1195 | FOT | RIG | .5 | 11 Aug 0315 - 0345 | 10519 | 900779 | VALVE & SEAT FAILURE | RR | MPMP |  | 08/11/2022 | SSA-5892 | .5 | AWTD-141400
1196 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SSA-5969 | Hrs | UTMN-3148
1197 | STBH | ARM | 106.75 | 06 Aug 1315 - 0500 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | BHA |  | 08/11/2022 | SSA-5969 | 23.5 | UTMN-3148
1198 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | SSA-5972 | Hrs | SHDN-19
1199 | FOT | SAM | 19 | 11 Aug 0930 - 0500 | 9500 | 900747 | SAMAA 9.5/8" FSC PKR PREMATURE SET AND INTEGRITY TEST FAILED TO HOLD PRESS. | BHA | WBCL |  | 08/11/2022 | SSA-5972 | 19 | SHDN-19
1200 | ISEQ | WI3 | 11.5 | 11 Aug 0500 - 1630 | 6147 | 900781 | GYRO TOOL UNABLE TO LATCH UBHO. | TF | WPSTK |  | 08/11/2022 | T914 | 11.5 | UTMN-415
1201 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/11/2022 | T914 | Hrs | UTMN-415
1202 | HERR | OGS | 11.5 | 10 Aug 2330 - 0000 | 6147 | 900750 | GYRO TOOL UNABLE TO LATCH UBHO. | SURV | GYRO |  | 08/11/2022 | T914 | 6 | UTMN-415
1203 | ISEQ | WI3 | 11.5 | 11 Aug 0500 - 1630 | 6147 | 900781 | GYRO TOOL UNABLE TO LATCH UBHO. | TF | WPSTK |  | 08/11/2022 | T914 | 11.5 | UTMN-415
1204 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | ADC-17 | Hrs | ZULF-1218
1205 | WTHR | ARM | 15 | 10 Aug 0630 - 0900 | 0 | 900662 | WAIT ON WEATHER, HIGH WIND SPEED | WON | NA |  | 08/12/2022 | ADC-17 | 3.5 | ZULF-1218
1206 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | ADC-43L | Hrs | UTMN-3118
1207 | FRFM | TK3 | 19.5 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/12/2022 | ADC-43L | 17.5 | UTMN-3118
1208 | 12705 |  | WOC | C | 4145 | LINR | WOC- POOH W/CONTROLLED SPEED WITH 4 1/2" LINER SETTING TOOL F/2,334 FT TO SURFACE.- FLOW CHECK @ TOP OF BHA - WELL STATIC. | 12705 |  | RIG | 08/12/2022 | ADC-53L | CSG | HRDH-530
1209 | 12705 |  | WOC | C | 4145 | LINR | WOC. L/D TOT 4 1/2" LINER SETTING TOOL.- MONITOR WELL ON TRIP TANK - WELL STATIC. | 12705 |  | RIG | 08/12/2022 | ADC-53L | CSG | HRDH-530
1210 | 12705 |  | WOC | C |  | LINR | WOC. HPJSM, P/T 13-5/8" 5 K CLASS A BOP AS PER ARAMCO STANDARDP/U & M/U BOP TEST PLUG ASSY.- FLUSH BOP, KILL & CHOKE MANIFOLD, EMERGENCY KILL LINE, POOR BOY DEGASSER, LINES TO SHAKERS & FLARE PIT W/ WATER.- FUNCTION TEST BOP STACK- P/T ANNULAR @ 300 PSI/ 3000 PSI (10 MIN EACH) P/T UPPER VBR ( 3- 1/2" - 5-7/8" ), BLIND - SHEAR RAM, KILL LINES & VALVES, CHECK VALVES, HCR'S LOW/HIGH FOR @ 300 PSI/2,550 PSI.- P/T IBOP, MECH, STD PIPE, ROTARY HOSE AND SAFETY VALVES.- P/T VBR WITH 4" DP.L/D TEST PLUG ASSY & RIH 9-5/8 BOP CUP TESTER ASSY.P/T WELL HEAD SOV'S, 4'' LOWER RAMS TO 300/2,550 PSI FOR 10 MIN EACH OK.PERFORMED ACCUMULATOR DRAW DOWN TEST AS PER ARAMCO STANDARD.- L/D CUP TESTER ASSY. | 12705 |  | RIG | 08/12/2022 | ADC-53L | CSG | HRDH-530
1211 | 12705 |  | WOC | C | 4145 | LINR | WOC. P/U & M/U 6-1/8" SLICK BHA AND RIH 10 STDS HWDP.- MONITOR WELL ON TRIP TANK - WELL STATIC. | 12705 |  | RIG | 08/12/2022 | ADC-53L | CSG | HRDH-530
1212 | 12705 |  | OTH | C | 4145 | LINR | PERFORMED INJECTIVITY TEST USING SLB CMT UNIT.- P/TEST LINES TO 500/2500 PSI OK-TOTAL PUMPED VOLUME 0.5 BBL, PRESSURE 500 PSI @ 0.3 BPM. PRESSURE HOLD.- BLEED OFF, TOTAL RECOVERED VOLUME 0.5 BBL NO INJECTIVITY. | 12705 |  | ARM | 08/12/2022 | ADC-53L | CSG | HRDH-530
1213 | 12705 |  | OTH | C | 4145 | LINR | CONT RIH 6-1/8" SLICK BHA TO 4,500 FT.- WASH DOWN & TAG TOL @5,033 FT, WITH 5 KLB. | 12705 |  | ARM | 08/12/2022 | ADC-53L | CSG | HRDH-530
1214 | 12705 |  | OTH | C | 4145 | LINR | SET 4 1/2" LINER TOP PACKER AS PER TOT ENGINEER.- APPLY 60 KLBS S.O.W ON TOP OF LINER AND HAD GOOD INDICATION AT WEIGHT INDICATOR. CONFIRM LINER PKR SET. | 12705 |  | ARM | 08/12/2022 | ADC-53L | CSG | HRDH-530
1215 | 12705 |  | CIRC | C | 4145 | MPMP | CIRCULATE BTM-UP AND P/T TOL TO 2,000 PSI EQUIVALENT WATER ,OK. | 12705 |  | RIG | 08/12/2022 | ADC-53L | CSG | HRDH-530
1216 | 12705 |  | OTH | C | 4145 | LINR | POOH W/6-1/8" SLICK BHA TO SURFACE & L/D SAME.- FLOW CHECK AT TOP BHA.- MONITOR WELL ON TRIP TANK. | 12705 |  | ARM | 08/12/2022 | ADC-53L | CSG | HRDH-530
1217 | 12705 |  | HT | C | 4145 | BHA | R/U 2-3/8" HANDLING EQUIPMENT...ON GOING ART. | 12705 |  | RIG | 08/12/2022 | ADC-53L | CT | HRDH-530
1218 | 43.5 | OOS | Category | DOOS ID | RLIN | Out of Scope Summary | RIH 4-1/2" OFF BTTM LINER. | 19.5 | 4145 | 10 Aug 0300 | 08/12/2022 | ADC-53L | Type | HRDH-530
1219
1220
1221 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | ADC-55L | Hrs | UTMN-3171
1222 | STBH | TK3 | 310 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/12/2022 | ADC-55L | 24 | UTMN-3171
1223 | 7019 | 6343 | LOG | E | 3965 | WLT | SLB WL TAKING SAMPLING WHILE POOH AS PER RMD REQUEST.- SCAN AROUND 6,343 FT FOR SAMPLE #12.- PERFORM STICK TEST 3, 8, 15, 30 MIN PRIOR 1ST POINT IN THE FORMATION & THEN 5, 15 MIN FOR SUBSEQUENT SAMPLE POINT. - MAX STATIONARY TIME: 4 HRS.- SAMPLE #12 @ 6,343 FT , TOTAL 1 SESSION.- TOTAL 12 SAMPLES OUT OF 13 TOTAL & 6 PUMP OUT ONE OUT OF 6 .- TOTAL PUMP OUT 933 L AT RPT, OVERBALANCE AFTER PUMP OUT 507 PSI.- MONITOR WELL ON TRIP TANK. | 7019 | 6343 | SWL | 08/12/2022 | ADC-57L | LOG | KRSN-175
1224 | 7019 | 6500 | TI | E | 3965 | STDP | RIH LOGGING RUN #3 TOOLS (MDT-GR) FROM 6,343 FT TO 6,500 FT WITH CONTROLLED SPEED AS PER WL.- MONITOR WELL ON TRIP TANK. | 7019 | 6343 | RIG | 08/12/2022 | ADC-57L | LOG | KRSN-175
1225 | 7019 |  | CIRC | E | 3965 | MPMP | CIRC BTM UP, CIRCULATED PRECAUTIONARY LAST 50 BBL THRUGH CHOKE, CONT. CIRCULATE UNTILL HOLE CLEAN AND CONDITION MUD IN/OUT 79 PCF.- FLOW CHECK WELL STATIC. | 7019 |  | RIG | 08/12/2022 | ADC-57L | LOG | KRSN-175
1226 | 7019 | 4792 | TO | E | 3965 | STDP | POOH LOGGING TLC MDT RUN #3 STRING IN OH FROM 6,500 FT TO 4,792 FT INDSIDE 9-5/9" CSG .- MONITOR WELL ON TRIP TANK.- FLOW CHECK WELL STATIC. | 7019 | 6500 | RIG | 08/12/2022 | ADC-57L | LOG | KRSN-175
1227 | 7019 |  | OTH | E | 3965 | NA | HPJSM, UNLATCH AND RETRIEVE WIRELINE CABLE. L/D SAME.- PUMP SLUG.- MONITOR WELL ON TRIP TANK. | 7019 |  | SWL | 08/12/2022 | ADC-57L | LOG | KRSN-175
1228 | 7019 | 278 | TO | E | 3965 | STDP | POOH LOGGING TLC MDT RUN #3 STRING FROM 4,792 FT TO 278 FT.- MONITOR WELL ON TRIP TANK.- FLOW CHECK WELL STATIC AT TOP WR BHA. | 7019 | 4792 | RIG | 08/12/2022 | ADC-57L | LOG | KRSN-175
1229 | 7019 |  | OTH | E | 3965 | NA | POOH LOGGING TLC MDT RUN #3 TO SURFACE AND L/D TOOLS.- MONITOR WELL ON TRIP TANK. | 7019 |  | SWL | 08/12/2022 | ADC-57L | LOG | KRSN-175
1230 | 7019 |  | OTH | N | 3965 | WBSH | HPJSM, RETRIVE V.G. 11" WEAR BUSHING.- MONITOR WELL ON TRIP TANK. | 7019 |  | RIG | 08/12/2022 | ADC-57L | BOP | KRSN-175
1231 | 7019 |  | OTH | N | 3965 | BOP | FUNCTION TEST BOP FROM THREE STATIONS, OK.- FUNCTION TEST ALARMS OF BLIND SHARE RAMS FOR ALL UNITS.- FUNCTION TEST FLARE IGNITION SYSTEM.- FUNCTION TEST THE BOP LOCK DEVICE. | 7019 |  | RIG | 08/12/2022 | ADC-57L | BOP | KRSN-175
1232 | 7019 |  | OTH | N | 3965 | BOP | P/U & M/U 11" TEST ASSEMBLY.- 2 STDS 5" HWDP'S+ 11" BAKER TEST PLUG + 5" PJ + X/O + 4" DP + 4 "SES + 4" FOSV + X/O + 5" FOSV + 10" PJ TO TDS.- OPENED THS SOV'S.- RIH & LANDED TEST PLUG ONTO THS. | 7019 |  | RIG | 08/12/2022 | ADC-57L | BOP | KRSN-175
1233 | 7019 |  | OTH | N | 3965 | BOP | FLUSH BOP STACK, CHOKE MANIFOLD, MGS & FLARE LINES WITH WATER. | 7019 |  | RIG | 08/12/2022 | ADC-57L | BOP | KRSN-175
1234 | 7019 |  | BOPT | N | 3965 | BOP | P/T 13-5/8" 3 K BOP AS PER ARAMCO STANDARD.- TEST #1: P/T ANNULAR, PRIMARY & EMERGENCY KILL LINE MANUAL VALVES, CHOKE MANIFOLD MASTER VALVE, 4" FOSV TO 300/3000 PSI FOR 10 MIN EA.- TEST #2: UPPER PIPE RAM, 5" FOSV, KILL LINE MANUAL VALVE & CHOKE LINE HCR, EMERGENCY KILL LINE MANUAL VALVE #1 TO 300 / 3000 PSI FOR 10 MIN EA.- TEST #3: UPPER PIPE RAMS, KILL & CHOKE LINE MANUAL VALVE, EMERGENCY KILL LINE HCR, LOWER IBOP TO 300 /2550 PSI FOR 10 MIN EA.- TEST #4: LOWER 5" PIPE RAMS, EMERGENCY KILL LINE MANUAL VALVE #2, UPPER IBOP TO 300/ 2550 PSI FOR 10 MIN EA.- UNSCREW FROM TEST PLUG- TEST #5 BSR, NRV OF MUD PUMP KILL LINE, NRV OF CMT UNIT KILL LINE, AUTOCLAVE PLUG, CHOKE MANIFOLD VALVES 13,14 & 15 TO 300/2550 PSI FOR 10 MIN EA. | 7019 |  | RIG | 08/12/2022 | ADC-57L | BOP | KRSN-175
1235 | 261.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/12/2022 | ADC-57L | Type | KRSN-175
1236
1237
1238 | 13523 |  | STIM | C | 4125 | CTU | DISCONNECTED 4 1/16" 10K FLANGE BETWEEN C/T BOP & 4 1/16" 10K RISER, LIFTED C/T INJECTOR BY TDS, L/D CT BHA & 4 1/16"-10 M RISER 10 FT LONG. | 13523 |  | SCT | 08/12/2022 | ADC-58L | STIM | ABHD-169
1239 | 13523 |  | STIM | C | 4125 | CTU | HELD PJSM, PREPARED LIFTED PLAN, TRANSFERED CT INJECTOR HEAD FROM TDS LINKS TO CRANE & R/D SAME. | 13523 |  | SCT | 08/12/2022 | ADC-58L | STIM | ABHD-169
1240 | 13523 |  | OTH | C | 4125 | NA | N/D SLB 2-3/8" CTU PCE AS FOLLOW : 4-1/16"-10M COMBI BOP, 4-1/16" 10M RISER LONG 8 FT, 4-1/16" 10M RISER LONG 10FT, 4 1/16-10M SLB GATE VALVE, 5-1/8" X 4-1/16" 10M DSA & 13 5/8" 5M X 5-1/8" 10M DSA. | 13523 |  | SCT | 08/12/2022 | ADC-58L | STIM | ABHD-169
1241 | 13523 |  | OTH | C | 4125 | NA | R/U BELL NIPPLE, CONNECTED FLOW LINE, TRIP TANKS LINE & FUNCTIONED OK. | 13523 |  | RIG | 08/12/2022 | ADC-58L | STIM | ABHD-169
1242 | 13523 |  | PJSM | C |  | STRG | HPJSM PRIOR TO RETRIEVE 7" WHIPSTOCK OPERATIONS, DISCUSSED JOB PROCEDURES, RELATED HAZARDS, ASSIGNED TASKS & RESPONSIBILITIES. | 13523 |  | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1243 | 13523 |  | HT | C |  | STRG | P/U, M/U WIS (WELLBORE INTEGRITY SOLUTIONS) 7" RETRIEVING BHA AS FOLLOW:- 7" RETRIEVING HOOK, XO, 1 JT X 4" HWDP, XO, FLOAT SUB W/FV, SLIMPULSE MWD/GR, FILTER SUB, XO, 1 STD X 4" HWDP, 3 X 7" MI MAGNOSTAR MAGNETS, 4 JT'S X 4" HWDP, 4-3/4" HYD JAR, 4 JT'S X 4" HWDP & RIH TO DEPTH 996 FT.- SDM DD SCRIBED LINE & ORIENTED WPS RETRIEVING TOOL FACE ALONG W/ MWD, CONFIRMED AND VERIFIED OK. | 13523 |  | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1244 | 13523 | 1470 | TI | C |  | BHA | RIH WIS 7" W.S RETRIEVING BHA ON 4" DP'S FROM 996 FT TO 1470 FT. | 13523 | 996 | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1245 | 13523 |  | CIRC | C |  | MPMP | PERFORMED SHALLOW TEST FOR MWD TOOL (FR: 270 GPM, SPP: 620 PSI), CHECKED SIGNAL, OK. | 13523 |  | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1246 | 13523 | 6676 | TI | C |  | STDP | RIH WIS 7" W.S RETRIEVING TOOLS ON 4" DP'S FROM 1470 FT TO 6674 FT ( SLOW DOWN WHILE PASSING 7" TOP OF LINER @ 6561 FT). | 13523 | 1470 | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1247 | 13523 |  | HT | C |  | STRG | M/U CROSSOVER & CHANGED DP'S HANDLING TOOLS FROM 4" TO 5" SIZE. | 13523 |  | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1248 | 13523 | 9630 | TI | C |  | STDP | RIH WIS 7" W.S RETRIEVING TOOL TOOLS ON 5" DP FROM 6675 FT TO 9630 FT. (10 FT ABOVE TOW). | 13523 | 6675 | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1249 | 13523 |  | CIRC | C |  | MPMP | RECORDED PARAMETERS & ORIENTED TOOL FACE TO 125 DEG, CLEANED HOOK SLOT AREA @ FR :300 GPM & CIRC. PRESS: 1470 PSI.- P/U WT 225 KLB, S/O WT 212 KLB, TQ 2 KFT.LB AT 10 RPM W/FR 300 GPM.- P/U WT 222 KLB, S/O WT 207 KLB, TQ 2 KFT.LB AT 10 RPM W/O PUMP. | 13523 |  | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1250 | 13523 |  | HT | C |  | BHA | ORIENTED TOOL FACE TO -55 DEG TO ENGAGE WS, LOWERED STRING SLOWLY GOT 10 KLB SOW, PICKED UP STRING & APPLY 10 KLB OVERPULL, PERFORMED TORQUE TEST- CONFIRMED HOOK ENGAGED WITH WS -OK.- INCREASED OVERPULL GRADUALLY IN STAGES TO 77 KLBS (10 KLBS PER STAGE & WAIT 2 MINS IN EACH STAGE), OBSERVED 7" WS UNSET, PICK UP STRING 5 FT & WAIT TILL RUBBER ELEMENT RETRACTED.- FLOW CHECK FOR 15 MIN'S-WELL UNDER TOTAL LOSSES. | 13523 |  | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1251 | 13523 |  | PJSM | C |  | STRG | HELD PJSM PRIOR TO POOH 7" WS. | 13523 |  | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1252 | 13523 |  | HT | C |  | STRG | POOH WIS ETRIEVING BHA ENGAGED W/7" WS ON 5" DP'S @ CONTROLED SPEED FROM 9,640 FT TO 6,676 FT.------------- INCT@RPT.- CONTINUOUSLY PUMPING 77 PCF BRINE INTO ANNULUS AT 2 BPM DURING ALL PAST OPERATION. | 13523 |  | RIG | 08/12/2022 | ADC-58L | CT | ABHD-169
1253 | 73 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | PERFORM ACID STIMULATION JOB FOR L-1. | 5 | 4125 | 09 Aug 0030 | 08/12/2022 | ADC-58L | Type | ABHD-169
1254
1255
1256 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | ADES-798 | Hrs | HRDH-2302
1257 | FOT | SWL | 16 | 12 Aug 0700 - 0030 | 1037 | 900721 | SLB WIRE LINE ATTEMPTED TO LATCH PWCH NO SUCCESS. | TF | WLT |  | 08/12/2022 | ADES-798 | 16 | HRDH-2302
1258 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | ADES-889 | Hrs | HRDH-2122
1259 | HERR | RAC | 16.5 | 12 Aug 1230 - 0500 | 10875 | 900795 | VERY FAST WORN OUT FOR THE PILOT MILL LEAD TO UNDER GAUGED MILL WENT INSIDE THE 7" LINER WITHOUT MILLING. | BHA | MILL |  | 08/12/2022 | ADES-889 | 16.5 | HRDH-2122
1260 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | AOD-11 | Hrs | SFNY-1670
1261 | FOT | HWP | 25.5 | 10 Aug 2315 - 1430 | 5390 | 900788 | HALLIBURTON WIRELINE STRADDLE PACKER FAILED TO OBTAIN GOOD SEAL AGAINST FORMATION. | TF | WLT |  | 08/12/2022 | AOD-11 | 9.5 | SFNY-1670
1262 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | ARO-2003 | Hrs | MNIF-733
1263 | SRVC | ARN | 14 | 12 Aug 1500 - 0500 | 0 | 900789 | WAIT ON SEABED SURVEY. | WO | NA |  | 08/12/2022 | ARO-2003 | 14 | MNIF-733
1264 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | ARO-3004 | Hrs | MRJN-2060
1265 | SRVC | BCT | 6.25 | 12 Aug 2215 - 0430 | 0 | 900796 | BAKER HUGHES COIL TUBING REPORTED EMPTY NITORGEN TANK IN THE MIDDLE OF PRESSURE TESTING HALLIBURTON WELL TEST SURFACE EQUIPMENT. SERVICE REP ON BOARD CLAIMED NITROGEN TANK GAUGE SHOWED VOLUME READING DIFFERENT FROM ACTUAL CONTENT OF TANK. WAITED FOR STANDBY BOAT ON OPERATION ON ANOTHER LOCATION TO RETURN WITH FULL NITROGEN TANKS FOR SWAP OUT. | WO | NA |  | 08/12/2022 | ARO-3004 | 6.25 | MRJN-2060
1266 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | DPS-74 | Hrs | NJYN-33
1267 | FOT | HWP | 12.25 | 12 Aug 1415 - 0500 | 17900 | 900723 | DATA FROM HALLIBURTON NMR (MRIL) TOOL CAN NOT BE INTERPRETED DUE TO NOISE. | TF | WLT |  | 08/12/2022 | DPS-74 | 12.25 | NJYN-33
1268 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | DQ-47 | Hrs | KHRS-280
1269 | FWTS | RIG | 30.25 | 11 Aug 0745 - 1400 | 4461 | 900749 | WHILE REAMING DOWN AT DEPTH 4461' HAD 850 PSI SUDDEN PRESSURE DROP AND LOST 15 KLBS WEIGHT. | FISH | STRG |  | 08/12/2022 | DQ-47 | 9 | KHRS-280
1270 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | ENS-108 | Hrs | ZULF-2014
1271 | FOT | ENV | 482 | 21 Jul 0330 - 1015 | 6135 | 900310 | WHILE RIH WITH 9-5/8" CASING, ENCOUNTERED OBSTRUCTION W/ 10 KLBS S/O @6,135' (INSIDE LINER). | TF | EXPND |  | 08/12/2022 | ENS-108 | 5.25 | ZULF-2014
1272 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | MP-1 | Hrs | MRJN-78
1273 | FOT | NRT | 269.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/12/2022 | MP-1 | 24 | MRJN-78
1274 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | NBR-263S | Hrs | QTIF-736
1275 | STBH | ARM | 224.25 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/12/2022 | NBR-263S | 24 | QTIF-736
1276 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | NBR-591S | Hrs | HRDH-2259
1277 | FOT | RIG | 3.5 | 12 Aug 0830 - 1200 | 11485 | 900720 | WHILE DRLG. @ 11,485' LOST COMMUNICATION SUDDENLY WITH TDS. | RR | TDS |  | 08/12/2022 | NBR-591S | 3.5 | HRDH-2259
1278 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | NBR-654S | Hrs | HRDH-1150
1279 | FOT | PKP | 220 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/12/2022 | NBR-654S | 24 | HRDH-1150
1280 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | NBR-783S | Hrs | NJYN-93
1281 | FOT | CRW | 35.25 | 10 Aug 2345 - 1330 | 15392 | 900739 | LTTT PACKER FAILED WHILE PERFORMING NEGATIVE TEST | BHA | WBCL |  | 08/12/2022 | NBR-783S | 8.5 | NJYN-93
1282 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | NBR-987S | Hrs | JLMN-35
1283 | OTH | RIG | 93 | 09 Aug 0800 - 0500 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/12/2022 | NBR-987S | 24 | JLMN-35
1284 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | RM-74A | Hrs | HSBH-68
1285 | FOT | RIG | 1.75 | 12 Aug 1800 - 1945 | 4300 | 900792 | PORT AFTER CRANE MAULFUNCTION WHILE LAYING DOWN DRILL COLLAR'S | RR | CRN |  | 08/12/2022 | RM-74A | 1.75 | HSBH-68
1286 | 7221 | 200 | SET | N |  | RTTS | SET 7" RTTS @ 200', PT BELOW RTTS TO 1000 PSI, HOLD. POH W/RTTS STORM VALVE & L/D. CLOSE BSR, PT RTTS PKR TO 1000 PSI, HOLD. | 7221 | 200 | HCO | 08/12/2022 | SINO-36L | PA | ANDR-32
1287 | 7221 |  | ND | N |  | BOP | HPJSM , DISCONNECT EMERGENCY KILL LINES , HANG UP & SECURE BOP STACK. | 7221 |  | RIG | 08/12/2022 | SINO-36L | BOP | ANDR-32
1288 | 7221 |  | OTH | N |  | NA | HPJSM, ISSUE PTW & REVIEW JSA, GAS TEST CELLAR, DIG OUT CELLAR 6 FT BELOW LANDING BASE. - P/T 9 5/8" X 13 3/8" CCA TO 400 PSI, HOLDING- P/T 9 5/8" X 7" CCA TO 400 PSI, HOLDING.- P/T 9 5/8" CSG SLIP TO 1000 PSI - HOLDING.- P/T 7" SLIPS TO 1000 PSI, HOLDING.- 18-5/8" CSG IS SEAL WELDED TO DONUT PLATE. - PERFORM UT INSPECTION FOR 18 5/8" CSG & LANDING BASE, THICKNESS ACCEPTED. | 7221 |  | RIG | 08/12/2022 | SINO-36L | WH | ANDR-32
1289 | 7221 |  | OTH | N | 4165 | NA | (OOS) HOTHEAD PERFORM HOT-TAPPING TO 18-5/8" CSG. NO PRESSURE & NO GASSES. | 7221 |  | HTD | 08/12/2022 | SINO-36L | WH | ANDR-32
1290 | 7221 |  | OTH | N |  | NA | HOT HED CUT 18 5/8" CASING WINDOW, FOUND GOOD CMT. - ALMANSORI PERFORM UT INSPECTION FOR 13 3/8" CASING, ACCEPTED. - FILL ANNULUS BACK WITH CEMENT.- HOT HED SEAL WELD 18 5/8" CASING WINDOW.- ALMANSORI PERFORM MPI INSPECTION FOR WELDED AREAS. | 7221 |  | HTD | 08/12/2022 | SINO-36L | WH | ANDR-32
1291 | 7221 |  | OTH | N |  | NA | N/U SECOND 2 1/16" CIW GATE VALVE TO THS. | 7221 |  | RIG | 08/12/2022 | SINO-36L | WH | ANDR-32
1292 | 7221 |  | NU | N |  | BOP | HPJSM, N/U BOP & RELATED EQUIPMENT. | 7221 |  | RIG | 08/12/2022 | SINO-36L | BOP | ANDR-32
1293 | 7221 |  | BOPT | N |  | BOP | HPJSM, M/U 7" CUP TESTER ASSY, P/T THS GATE VALVES , BOP CONNECTIONS , E-KILL LINE TO 300/ 2550 PSI-OK , L/D TEST ASSY . | 7221 |  | RIG | 08/12/2022 | SINO-36L | BOP | ANDR-32
1294 | 7221 |  | OTH | N |  | NA | RIH & RETRIEVE 7" RTTS. | 7221 |  | HCO | 08/12/2022 | SINO-36L | PA | ANDR-32
1295 | 7221 | 0 | TO | N |  | STHDP | POH W/ 18 STD HWDP'S & RACK BACK IN DERRICK. | 7221 | 1700 | RIG | 08/12/2022 | SINO-36L | PA | ANDR-32
1296 | 7221 |  | HT | N |  | BHA | HPJSM. P/U & M/U 7"WFD WHIPSTOCK BHA.>> 7" WHIPSTOCK BHA: 5.5" RHN WHIPSTOCK,6" LEAD MILL,6-1/8" FLEX MILL,1 JT 3-1/2" HWDP, FLOAT SUB, UBHO SUB ,X/O.>> GAUGE LEAD & FLEX MILLS-OK>> ALIGN UBHO W/WHIPSTOCK | 7221 |  | RIG | 08/12/2022 | SINO-36L | TINL | ANDR-32
1297 | 7221 | 6066 | TI | N |  | STHDP | RIH W/ 7" WFD WHIPSTOCK & MILLING BHA ON 4" DP T/6066'.>> DRIFT 4" DP/HWDP WHILE RIH .>> CONTROL RIH SPEED .>> FILL STRG EVERY 10 STDS | 7221 | 0 | RIG | 08/12/2022 | SINO-36L | TINL | ANDR-32
1298 | 7221 |  | SURV | N |  | SS | HPJSM, R/U GYRO EQUIPMENT, RIH W/ GYRO, RECORD SINGLE SHOT, ORIENT WHIPSTOCK T/145 DEGREE, CONFIRM DIRECTION WITH 3 GYRO READING RECORDS....INC@RPT. | 7221 |  | SPS | 08/12/2022 | SINO-36L | TINL | ANDR-32
1299 | 2 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | HOTHEAD CONDUCT HOT TAPING FOR 18 5/8" CSG | 2 | 4165 | 12 Aug 0930 | 08/12/2022 | SINO-36L | Type | ANDR-32
1300
1301
1302 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SND-2008 | Hrs | HRDH-1812
1303 | STDP | RIG | 737 | 07 Jul 0500 - 0500 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/12/2022 | SND-2008 | 24 | HRDH-1812
1304 | XTRI | NWT | 4 | 12 Aug 1700 - 2100 | 5313 | 900791 | DELAY IN OPERATION WHILE R/U 2" NESR CTU. | JF | TESTT |  | 08/12/2022 | SND-2010 | 4 | MNIF-869
1305 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SND-2010 | Hrs | MNIF-869
1306 | XTRI | HTS | 2 | 12 Aug 2100 - 2300 | 5313 | 900722 | EXCESSIVE TIME WHILE R/U AND P/T HALL WELL TESTING EQUIPMETNS | JF | TESTT |  | 08/12/2022 | SND-2010 | 2 | MNIF-869
1307 | XTRI | NWT | 4 | 12 Aug 1700 - 2100 | 5313 | 900791 | DELAY IN OPERATION WHILE R/U 2" NESR CTU. | JF | TESTT |  | 08/12/2022 | SND-2010 | 4 | MNIF-869
1308 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SP-167 | Hrs | HRDH-218
1309 | ORDS | ARN | 62.5 | 10 Aug 0800 - 0500 | 7167 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/12/2022 | SP-167 | 24 | HRDH-218
1310 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SP-229 | Hrs | JLDI-862
1311 | FOT | RIG | 8 | 12 Aug 2100 - 0500 | 0 | 900724 | AFTER BOP TEST THE ANNULAR DIDN'T FULLY RETRACT. | BOP | RAMS |  | 08/12/2022 | SP-229 | 8 | JLDI-862
1312 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SP-53L | Hrs | HRDH-528
1313 | XBTR | BHT | 19.75 | 11 Aug 0300 - 0100 | 5989 | 900717 | LOW ROP 10 FPH | LROP | BIT |  | 08/12/2022 | SP-53L | 17.75 | HRDH-528
1314 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SSA-102 | Hrs | QTIF-693
1315 | TOST | RIG | 81.25 | 06 Aug 1900 - 0030 | 9617 | 900628 | 7" WHIPSTOCK DROPPED IN HOLE WHILE RIH DUE SHEARED BOLT BY EXCESSIVE SLACKOFF WEIGHT | JF | STRG |  | 08/12/2022 | SSA-102 | 19.5 | QTIF-693
1316 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SSA-5865 | Hrs | FRHH-3
1317 | FOT | RIG | 11 | 12 Aug 1800 - 0500 | 617 | 900793 | TOP DRIVE HYDRAULIC PUMP LEAKAGE. HYDRAULIC ORDERS NOT FUNCTION. | RR | TDS |  | 08/12/2022 | SSA-5865 | 11 | FRHH-3
1318 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SSA-5868 | Hrs | HRDH-2413
1319 | XTTE | WCR | 2 | 12 Aug 1830 - 2030 | 3391 | 900797 | EXCISSIVE TIME TO RIH 4.5" UPPER COMPLETION DUE TO MULTIPLE FAILURES IN TBG RUNNING EQUIPMENT | TF | CTRQ |  | 08/12/2022 | SSA-5868 | 2 | HRDH-2413
1320 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SSA-5914 | Hrs | WDYH-80
1321 | FOT | RIG | 1.5 | 12 Aug 0215 - 0345 | 13760 | 900725 | RIG GENIE LIFT BREAKDOWN | RR | CRN |  | 08/12/2022 | SSA-5914 | 1.5 | WDYH-80
1322 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SSA-5969 | Hrs | UTMN-3148
1323 | STBH | ARM | 130.75 | 06 Aug 1315 - 0500 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | BHA |  | 08/12/2022 | SSA-5969 | 24 | UTMN-3148
1324 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/12/2022 | SSA-5972 | Hrs | SHDN-19
1325 | FOT | SAM | 20.25 | 11 Aug 0930 - 0615 | 9500 | 900747 | SAMAA 9.5/8" FSC PKR PREMATURE SET AND INTEGRITY TEST FAILED TO HOLD PRESS. | BHA | WBCL |  | 08/12/2022 | SSA-5972 | 1.25 | SHDN-19
1326 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | 910TE | Hrs | DMMM-102
1327 | FOT | RIG | 3 | 13 Aug 0200 - 0500 | 8076 | 900728 | WHILE RAISING THE TRAVELING BLOCK TO PICK UP NEXT STAND, THE FAST LINE CLAMP IN THE DRAW WORK CAME OUT FROM ITS HOUSING WHICH RESULTED DAMAGED CLAMP. | RR | DWKS |  | 08/13/2022 | 910TE | 3 | DMMM-102
1328 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADC-17 | Hrs | ZULF-1218
1329 | WTHR | ARM | 21.5 | 10 Aug 0630 - 1500 | 0 | 900662 | WAIT ON WEATHER, HIGH WIND SPEED | WON | NA |  | 08/13/2022 | ADC-17 | 6.5 | ZULF-1218
1330 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADC-43L | Hrs | UTMN-3118
1331 | FRFM | TK3 | 43 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/13/2022 | ADC-43L | 23.5 | UTMN-3118
1332 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADC-52 | Hrs | SDGM-1185
1333 | HINW | BAW | 364.5 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/13/2022 | ADC-52 | 20.5 | SDGM-1185
1334 | 12705 |  | HT | N | 4185 | BHA | HPJSM. P/U AND M/U 3-7/8" CLEAN OUT ASSY.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 12705 |  | RIG | 08/13/2022 | ADC-53L | CT | HRDH-530
1335 | 12705 | 4531 | LDP | N | 4185 | STRG | RIH W/3-7/8" CLEAN OUT ASSY WHILE PICK UP 2-3/8" DP FROM RACK (TOTAL 144 JTS 2-3/8" DP).TO 4,531 FT.- C/O BHA: 3 7/8" PDC BIT (SF53, S/N: 1375458)+BIT SUB W/F.VALVE +144 JT 2-3/8" DP+XO+ 6X 4" DP+6X 4" HWDP+4-3/4" JAR+2X 4" HWDP.- FILL AND BREAK CIRC EVERY 20 JTS. - FLUSHED & DRIFTED WHILE P/U 2-3/8" DP'S.- MONITOR WELL THRU TRIP TANK, WELL STATIC. | 12705 | 0 | RIG | 08/13/2022 | ADC-53L | CT | HRDH-530
1336 | 12705 | 8771 | RW | N | 4185 | BIT | CONT RIH 3 7/8" C/O BHA ON 4" DP & 4" HWDP F/4,531 TO 8,722 FT, WASH DOWN & TAG TOC@ 8,771 FT.- FILL UP EVERY 20 STDS.- MONITOR WELL ON TRIP TANK.- P/U 4-3/4" JAR FROM RACK. | 12705 | 4531 | RIG | 08/13/2022 | ADC-53L | CT | HRDH-530
1337 | 12705 | 9058 | RW | N | 4185 | BIT | DRILL OUT CMT TO TOP OF HYDRO SEAL CMT VALVE F/8,771 FT TO 9,058 FT- FR 200 GPM, SPP 2,000 PSI, WOB 3-10 KLBS, RPM 70, TQ 1-2 KLB.FT. | 12705 | 8771 | RIG | 08/13/2022 | ADC-53L | CT | HRDH-530
1338 | 12705 |  | CIRC | N | 4185 | MPMP | PUMP SWEEP & CIRCULATE BTM-UP. P/T 4-1/2" LNR ABOVE CMT VALVE TO 2,000 PSI EQUIVALENT WATER ,OK. | 12705 |  | RIG | 08/13/2022 | ADC-53L | CT | HRDH-530
1339 | 12705 | 9063 | RW | N | 4185 | BIT | DRILL OUT WIPER PLUG, HYDRO SEAL CMT VALVE F/9.058 FT TO 9,063 FT.- CAREFULLY DRESS DART SEAT SEVERAL TIMES.- FR: 150 GPM, SPP: 2500 PSI, WOB: 5-10 , RPM: 70-80 , TQ: 2-3 KLB.FT. | 12705 | 9058 | RIG | 08/13/2022 | ADC-53L | CT | HRDH-530
1340 | 24.5 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | C/O TRIP FOR 4-1/2" OBL & LWR COMPL. | 24 | 4185 | 12 Aug 0430 | 08/13/2022 | ADC-53L | Type | HRDH-530
1341
1342
1343 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADC-54L | Hrs | HRDH-584
1344 | FOT | RIG | 2.5 | 13 Aug 1815 - 2045 | 4337 | 900760 | DRILLING LINE SLIPPED OUT OF DRAWWORKS GROOVE, CAUSED DRILLING LINE TO BE SLIGHTLY DAMAGED. | RR | DWKS |  | 08/13/2022 | ADC-54L | 2.5 | HRDH-584
1345 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADC-55L | Hrs | UTMN-3171
1346 | STBH | TK3 | 334 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/13/2022 | ADC-55L | 24 | UTMN-3171
1347 | 7019 |  | BOPT | N | 3965 | BOP | SCREW IN TEST PLUG AND CONTINUE PRESSURE TEST BOP.- TEST #6: P/T ANNULAR, PRIMARY & EMERGENCY KILL LINE MANUAL VALVES, CHOKE MANIFOLD MASTER VALVE,TO 300/3000 PSI FOR 10 MIN EA.- TEST #7: UPPER PIPE RAM, KILL LINE MANUAL VALVE & CHOKE LINE HCR, EMERGENCY KILL LINE MANUAL VALVE #1 TO 300 / 3000 PSI FOR 10 MIN EA. | 7019 |  | RIG | 08/13/2022 | ADC-57L | BOP | KRSN-175
1348 | 7019 |  | OTH | N | 3965 | BOP | L/D 4-1/2" TEST ASSY AND PU MU 5" TEST ASSEMBLY. | 7019 |  | RIG | 08/13/2022 | ADC-57L | BOP | KRSN-175
1349 | 7019 |  | BOPT | N | 3965 | BOP | CONT PRESSURE TEST BOP.- TEST #8: P/T ANNULAR, PRIMARY & EMERGENCY KILL LINE MANUAL VALVES, CHOKE MANIFOLD MASTER VALVE,TO 300/3000 PSI FOR 10 MIN EA.- TEST #9: UPPER PIPE RAM, KILL LINE MANUAL VALVE & CHOKE LINE HCR, EMERGENCY KILL LINE MANUAL VALVE #1 TO 300 / 2550 PSI FOR 10 MIN EA. | 7019 |  | RIG | 08/13/2022 | ADC-57L | BOP | KRSN-175
1350 | 7019 |  | OTH | N | 3965 | BOP | L/D 5" TEST ASSEMBLY AND PU MU TEST CUP ASSEMBLY. | 7019 |  | RIG | 08/13/2022 | ADC-57L | BOP | KRSN-175
1351 | 7019 |  | BOPT | N | 3965 | BOP | TEST #10 : TOP RAM, SOV 1 & 2 TO 300/2,550 PSI 10 MIN. | 7019 |  | RIG | 08/13/2022 | ADC-57L | BOP | KRSN-175
1352 | 7019 |  | OTH | N | 3965 | BOP | PERFORM ACCUMULATOR DRAW DOWN TEST & POOH & L/D CUP TESTER ASSEMBLY & TAIL PIPE. | 7019 |  | RIG | 08/13/2022 | ADC-57L | BOP | KRSN-175
1353 | 7019 |  | SET | N | 3965 | WBSH | INSTALL 11" V.G. WEAR BUSHING AND L/D RUNNING TOOL. | 7019 |  | RIG | 08/13/2022 | ADC-57L | WH | KRSN-175
1354 | 7019 |  | RR | N | 3965 | TDS | SERVICES TOP DRIVE SYSTEM. | 7019 |  | RIG | 08/13/2022 | ADC-57L | CT | KRSN-175
1355 | 7019 | 959 | TI | N | 3965 | BHA | HPJSM, P/U, M/U 8-1/2" CO BHA # 3 & RIH TO 959 FT. | 7019 | 0 | RIG | 08/13/2022 | ADC-57L | CT | KRSN-175
1356 | 7019 | 6954 | TI | N | 3965 | STDP | RIH 8-1/2" CO RUN #3 FROM 959 FT TO 6954 FT.- FILL THE STRING EVERY 20 STANDS- MONITOR THE WELL WITH TRIP TANK | 7019 | 959 | RIG | 08/13/2022 | ADC-57L | CT | KRSN-175
1357 | 7019 | 7019 | RW | N | 3965 | BIT | REAM DN PRECAUTIONALY FROM 6,954 FT TO BTM AT 7,019 FT. | 7019 | 6954 | RIG | 08/13/2022 | ADC-57L | CT | KRSN-175
1358 | 7019 |  | CIRC | N | 3965 | MPMP | SWEEP THE HOLE WITH 30 BBLS HI-VIS AND CIRCULATE TO CONDITION MUD IN/OUT 79 PCF.- RUN LAB TEST MUD N GOOD CONDITION.- FLOW CHECK WELL STATIC. | 7019 |  | RIG | 08/13/2022 | ADC-57L | CT | KRSN-175
1359 | 7019 | 4819 | TO | N | 3965 | BHA | POOH 8-1/2" CO BHA #3 ON ELEVATOR FROM 7,019 FT TO 9-5/8" SHOE AT 4,819 FT.- HOLE IN GOOD CONDITION.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 7019 | RIG | 08/13/2022 | ADC-57L | CT | KRSN-175
1360 | 7019 |  | RR | N | 3965 | DWKS | SLIP AND CUT 100 FT DRILLING LINE.- RESET AND TEST ANTI-COLLISION SYSTEM.- PERFORM FLOW CHECK DURING SLIP AND CUT- WELL STATIC. | 7019 |  | RIG | 08/13/2022 | ADC-57L | CT | KRSN-175
1361 | 7019 | 2900 | TO | N | 3965 | STDP | POOH 8-1/2" CO BHA # 3 FROM 4,819 FT TO 2,900 FT. | 7019 | 4819 | RIG | 08/13/2022 | ADC-57L | CT | KRSN-175
1362 | 285.25 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/13/2022 | ADC-57L | Type | KRSN-175
1363
1364
1365 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADC-58L | Hrs | ABHD-169
1366 | WTHR | OTH | 5 | 13 Aug 1200 - 1700 | 13523 | 900799 | WAIT ON WEATHER, SUSPENDED CRANE ACTIVITY DUE TO STRONG WIND STORM, WIND SPEED 50-68 KM/HR | WON | NA |  | 08/13/2022 | ADC-58L | 5 | ABHD-169
1367 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADC-60 | Hrs | ABSF-216
1368 | FOT | BAL | 142.5 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/13/2022 | ADC-60 | 24 | ABSF-216
1369 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADES-889 | Hrs | HRDH-2122
1370 | HERR | RAC | 27.5 | 12 Aug 1230 - 1600 | 10875 | 900795 | VERY FAST WORN OUT FOR THE PILOT MILL LEAD TO UNDER GAUGED MILL WENT INSIDE THE 7" LINER WITHOUT MILLING. | BHA | MILL |  | 08/13/2022 | ADES-889 | 11 | HRDH-2122
1371 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ADM-510 | Hrs | ABSF-225
1372 | IDPR | SDM | 3 | 13 Aug 2345 - 0245 | 9000 | 900814 | EXCESSIVE TIME DRILLING 8 1/2'' HOLE W/SDM RSS/MWD/LWD BHA WITH CONTROLLED ROP 50 FPH PRIOR ENTERING ARBD AS PER SDM. | LROP | BHA |  | 08/13/2022 | ADM-510 | 3 | ABSF-225
1373 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ARO-2003 | Hrs | MNIF-733
1374 | SRVC | ARN | 38 | 12 Aug 1500 - 0500 | 0 | 900789 | WAIT ON SEABED SURVEY. | WO | NA |  | 08/13/2022 | ARO-2003 | 24 | MNIF-733
1375 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ARO-4001 | Hrs | MRJN-532
1376 | FOT | RIG | 1.25 | 13 Aug 0730 - 0845 | 5826 | 900812 | HAD PIPE CAT WALK NOT WORKING WHILE RIH WITH 9 5/8" CSG, TROUBLESHOOTING SAME, FIX OK. | RR | CATW |  | 08/13/2022 | ARO-4001 | 1.25 | MRJN-532
1377 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | DPS-44 | Hrs | UTMN-2342
1378 | FOT | HDV | 74.5 | 09 Aug 0700 - 0430 | 6325 | 900681 | AFTER DROPPING HAL FREE FALL DV OPENING PLUG, ATTEMPTED TO PRESSURE UP TO OPEN DV WITHOUT SUCCESS. | TF | DV |  | 08/13/2022 | DPS-44 | 23.5 | UTMN-2342
1379 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | DPS-74 | Hrs | NJYN-33
1380 | FOT | HWP | 35.75 | 12 Aug 1415 - 0500 | 17900 | 900723 | DATA FROM HALLIBURTON NMR (MRIL) TOOL CAN NOT BE INTERPRETED DUE TO NOISE. | TF | WLT |  | 08/13/2022 | DPS-74 | 23.5 | NJYN-33
1381 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | ENS-108 | Hrs | ZULF-2015
1382 | LHFL | RIG | 6.25 | 13 Aug 0615 - 1230 | 0 | 900726 | OBSERVED HYDRAULIC FLUID LEAK FROM ANNULAR STRIPPING BOTTLE. | BOP | RWCS |  | 08/13/2022 | ENS-108 | 6.25 | ZULF-2015
1383 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | HI-9 | Hrs | BRRI-155
1384 | STDP | ARM | 42.5 | 12 Aug 1030 - 0500 | 11088 | 900798 | PERFORM 30 MINUTES STICKY TEST, OBSERVED OVER PULL ON 4" DRILL PIPE. STRING GOT DIFFERENTIALLY STUCK. | STUK | DP |  | 08/13/2022 | HI-9 | 24 | BRRI-155
1385 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | JACK-203 | Hrs | HZEM-849
1386 | FOT | RIG | 2 | 13 Aug 0600 - 0800 | 935 | 900759 | WHILE PUMPING MUD CAP. OBVERVE LEAKING FROM THE TRIP TANK CENTRIFUGAL PUMP. | RR | CFGE |  | 08/13/2022 | JACK-203 | 2 | HZEM-849
1387 | CPNF | HCM | 16.25 | 13 Aug 1245 - 0500 | 6450 | 900731 | RIH WITH C/O ASSY, NO BALANCED CEMENT KICK OFF PLUG FOUND AT EXPECTED DEPTH. SOFT CEMENT OBSERVED TILL TAG TOC AT 6931'. POH TO RE-RUN KOP. | CMT | NA | 900303 | 08/13/2022 | MP-1 | 16.25 | MRJN-78
1388 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | MP-1 | Hrs | MRJN-78
1389 | FOT | NRT | 293.5 | 31 Jul 0245 - 1245 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/13/2022 | MP-1 | 7.75 | MRJN-78
1390 | CPNF | HCM | 16.25 | 13 Aug 1245 - 0500 | 6450 | 900731 | RIH WITH C/O ASSY, NO BALANCED CEMENT KICK OFF PLUG FOUND AT EXPECTED DEPTH. SOFT CEMENT OBSERVED TILL TAG TOC AT 6931'. POH TO RE-RUN KOP. | CMT | NA | 900303 | 08/13/2022 | MP-1 | 16.25 | MRJN-78
1391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | NBR-16S | Hrs | HMYM-433112
1392 | XTTE | ITS | 1 | 13 Aug 0015 - 0115 | 425 | 900816 | EXCESSIVE TIME TO OPERATE BACK UP TONG WITH POWER TONG & TO CONNECT SPIDER SLIPS HOSES. | TF | CTRQ |  | 08/13/2022 | NBR-16S | 1 | HMYM-433112
1393 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | NBR-263S | Hrs | QTIF-736
1394 | STBH | ARM | 247.75 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/13/2022 | NBR-263S | 23.5 | QTIF-736
1395 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | NBR-633S | Hrs | HRDH-1911
1396 | FOT | RIG | 2 | 13 Aug 1400 - 1600 | 1890 | 900818 | EXCESS TIME WHILE N/U & P/T BOPE. | RR | RWCS |  | 08/13/2022 | NBR-633S | 2 | HRDH-1911
1397 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | NBR-654S | Hrs | HRDH-1150
1398 | FOT | PKP | 232.25 | 02 Aug 1915 - 1715 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/13/2022 | NBR-654S | 12.25 | HRDH-1150
1399 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | NBR-987S | Hrs | JLMN-35
1400 | OTH | RIG | 117 | 09 Aug 0800 - 0500 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/13/2022 | NBR-987S | 24 | JLMN-35
1401 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SINO-29N | Hrs | SFNY-2005
1402 | PCPF | ARM | 216 | 05 Aug 0500 - 0500 | 6825 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/13/2022 | SINO-29N | 24 | SFNY-2005
1403 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SND-2008 | Hrs | HRDH-1812
1404 | STDP | RIG | 755.5 | 07 Jul 0500 - 2330 | 12837 | 899514 | WHILE WORK ON STRG DUE TO STUCK, GOT FREE W/ 120 KLBS WITH STRING TWISTED OFF AT 2ND DC ABOVE MILL. | STUK | DP |  | 08/13/2022 | SND-2008 | 18.5 | HRDH-1812
1405 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SP-124 | Hrs | FDHL-106
1406 | FOT | TIL | 166.75 | 06 Aug 0345 - 0230 | 10321 | 900615 | PERFORMD CEMENT JOB FOR 7" LINER , HAD NO BUMP PLUG , HAD RETRUN AND CEMENT U-TUBE AFTRE FINISHED THE JOB DUE TO FLOAT EQUIPMENT FAILEUR . | TF | HGRL |  | 08/13/2022 | SP-124 | 21.5 | FDHL-106
1407 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SP-167 | Hrs | HRDH-218
1408 | ORDS | ARN | 86.5 | 10 Aug 0800 - 0500 | 7167 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/13/2022 | SP-167 | 24 | HRDH-218
1409 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SP-229 | Hrs | JLDI-862
1410 | FOT | RIG | 9.5 | 12 Aug 2100 - 0630 | 0 | 900724 | AFTER BOP TEST THE ANNULAR DIDN'T FULLY RETRACT. | BOP | RAMS |  | 08/13/2022 | SP-229 | 1.5 | JLDI-862
1411 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SP-262 | Hrs | JNAB-152802
1412 | FOT | WDS | 11.75 | 13 Aug 1715 - 0500 | 3648 | 900803 | WHILE CLEAN OUT TOP WIPER PLUG, NOTICED INCREASE IN PRESSURE OFF BOTTOM, POH FOUND MOTOR POWER SECTION HOUSING BACKED OFF. | BHA | MMOT |  | 08/13/2022 | SP-262 | 11.75 | JNAB-152802
1413 | 6188 |  | DMR | N |  | MMOT | PERFORMANCE MTR DRILLING 8-1/2" VERTICAL HOLE TO 6188' (50' INSIDE ARAB C RESERVOIR ) W/ 80 PCF SALT POLYMER MUD W/ 100 % RETURNS.-SWEEP HOLE W/ 50 BBLS HI-VIS PILL EVERY 45 FT DRILLED.-WASH UP & REAM DOWN EACH STD DRILLED.-NORMAL TRQ & DRAG W/ REASONABLE CUTTING SIZE & QUANTITY ON SHALE SHAKERS.-INCREASED MUD WT GRADUALY TO 80 PCF BEFORE ENTRING ARAB C RESERVIOR . | 6015 |  | BHI | 08/13/2022 | SP-53L | DRLG | HRDH-528
1414 | 6188 |  | SDR1 | N |  | NA | FLOW CHECK 50' INSIDE ARAB-C RESERVOIR WELL STATIC OK. | 6188 |  | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1415 | 6315 |  | DMR | N |  | MMOT | RESUMED PERFORMANCE MTR DRILLING 8-1/2" VERTICAL HOLE TO 6315' (50' INSIDE ARAB D ANHYDRITE ) W/ 80 PCF SALT POLYMER MUD W/ 100 % RETURNS.-SWEEP HOLE W/ 50 BBLS HI-VIS PILL EVERY 45 FT DRILLED.-WASH UP & REAM DOWN EACH STD DRILLED.-NORMAL TRQ & DRAG W/ REASONABLE CUTTING SIZE & QUANTITY ON SHALE SHAKERS.-INCREASED MUD WT GRADUALY FROM 68 PCF TO 80 PCF BEFORE ENTRING ARAB C RESERVIOR . | 6188 |  | BHI | 08/13/2022 | SP-53L | DRLG | HRDH-528
1416 | 6315 |  | SDR1 | N |  | NA | FLOW CHECK 50' INSIDE ARAB-D ANHYDRITE WELL STATIC OK. | 6315 |  | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1417 | 6345 |  | DMR | N |  | MMOT | RESUMED PERFORMANCE MTR DRILLING 8-1/2" VERTICAL HOLE TO CORE POINT @ 6345' W/ 80 PCF SALT POLYMER MUD W/ 100 % RETURNS.-SWEEP HOLE W/ 50 BBLS HI-VIS PILL EVERY 45 FT DRILLED.-WASH UP & REAM DOWN EACH STD DRILLED.-NORMAL TRQ & DRAG W/ REASONABLE CUTTING SIZE & QUANTITY ON SHALE SHAKERS.-CONFIRM CORE POINT WITH GOC. | 6315 |  | BHI | 08/13/2022 | SP-53L | DRLG | HRDH-528
1418 | 6345 |  | CIRC | N |  | MPMP | SWEEP THE HOLE W/ 50 BBLS HI VIS PILL & CIRCULAT HOLE CLEAN. | 6345 |  | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1419 | 6345 |  | SDR1 | N |  | NA | FLOW CHECK WELL STATIC OK. | 6345 |  | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1420 | 6345 | 5840 | ST | N |  | STDP | POOH ON ELEVATOR W/ 8-1/2" MTR/MWD/GR ASSY DRLG ASSY FROM 6345 FT TO 5840 FT FOR CORING . | 6345 | 6345 | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1421 | 6345 |  | SDR1 | N |  | NA | FLOW CHECK AFTER PULL 5 STDS WELL STATIC OK. | 6345 | 5840 | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1422 | 6345 | 3536 | ST | N |  | STDP | CONTD POOH ON ELEVATOR W/ 8-1/2" MTR/MWD/GR ASSY DRLG ASSY FROM 5840 FT TO 9-5/8" CSG SHOE @ 3536 FT FOR CORING . | 6345 | 5840 | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1423 | 6345 |  | SDR1 | N |  | NA | FLOW CHECK AT 9-5/8" CSG SHOE - WELL STATIC OK. | 6345 |  | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1424 | 6345 |  | RR | N |  | TDS | RIG SERVICE TDS.-DROP HOLLOW DRIFT. | 6345 |  | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1425 | 6345 | 1570 | TO | N | 4186 | STDP | CONTD POOH W/ 8-1/2" MTR/MWD/GR ASSY DRLG ASSY FROM 9-5/8" CSG SHOE @ 3536 FT TO TOP OF BHA @ 1570 FT FOR CORING. | 6345 | 3536 | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1426 | 6345 |  | SDR1 | N | 4186 | NA | FLOW CHECK @ TOP BHA WELL STATIC. | 6345 |  | RIG | 08/13/2022 | SP-53L | DRLG | HRDH-528
1427 | 6345 |  | HT | N | 4186 | BHA | CONTD POOH W/ 8-1/2" MTR/MWD/GR ASSY DRLG ASSY FROM TOP OF BHA @ 1567 FT TO SURFACE. FOR CORING .- BIT DULL GRADING : 1-1-WT-A-I-X-BT-CP. | 6345 |  | BHI | 08/13/2022 | SP-53L | DRLG | HRDH-528
1428 | 6345 |  | HT | E | 4186 | DCORE | HPJSM, P/U & M/U 6-1/8" NOV CORE ASSY. -6-1/8" CORE HEAD + 4-3/4" CORE OUTER BARRELS & 3-3/8" INNER BARRELS + FLOAT SUB W/ FLAPPER TYPE FLOAT VALVE (BALL SIZE IS 1")+3 X 6 1/2" DC'S+ 8-1/4"STAB +3 X 6 1/2" DC'S+ DRILLING JAR+2 X 6 1/2" DC'S +30 X 5" HWDP'S+ DP'S. | 6345 |  | NOC | 08/13/2022 | SP-53L | CORE | HRDH-528
1429 | 6345 | 4020 | TI | E | 4186 | STDP | RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 1,452' TO 4020'. | 6345 | 1365 | RIG | 08/13/2022 | SP-53L | CORE | HRDH-528
1430 | 11 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 11 | 4186 | 13 Aug 0230 | 08/13/2022 | SP-53L | Type | HRDH-528
1431
1432
1433 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SSA-102 | Hrs | QTIF-693
1434 | FOT | WWD | 22.75 | 13 Aug 0545 - 0500 | 9715 | 900815 | WFD WHIPSTOCK DID NOT SET, BOLT WAS SHEARED, LOST WHIPSTOCK IN HOLE. | TF | WPSTK |  | 08/13/2022 | SSA-102 | 22.75 | QTIF-693
1435 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SSA-5865 | Hrs | FRHH-3
1436 | FOT | RIG | 27.5 | 12 Aug 1800 - 2130 | 617 | 900793 | TOP DRIVE HYDRAULIC OIL LEAK AND HYDRAULIC SYSTEM NOT FUNCTION. SAIPEM HYDRAULIC ENGINEER ARRIVED TO RIG SITE, RIG DOWN TDS, DISCONNECT HYDRAULIC PUMP, FIX/REPAIR LEAK IN HYDRAULIC PUMP (WHICH WAS INSTALLED AS A NEW PRIOR TO SPUD DUE TO OLD ONE MALFUNCTION) COMPENSATOR BETWEEN HYDRAULIC PUMP AND TANK. INSTALLED PUMP AND R/U TDS. | RR | TDS |  | 08/13/2022 | SSA-5865 | 16.5 | FRHH-3
1437 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SSA-5868 | Hrs | HRDH-2413
1438 | XTTE | WCR | 5 | 12 Aug 1830 - 1330 | 3391 | 900797 | EXCISSIVE TIME TO RIH 4.5" UPPER COMPLETION DUE TO MULTIPLE FAILURES IN TBG RUNNING EQUIPMENT | TF | CTRQ |  | 08/13/2022 | SSA-5868 | 3 | HRDH-2413
1439 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SSA-5969 | Hrs | UTMN-3148
1440 | STBH | ARM | 154.25 | 06 Aug 1315 - 0500 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | BHA |  | 08/13/2022 | SSA-5969 | 23.5 | UTMN-3148
1441 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | SSA-5972 | Hrs | SHDN-19
1442 | FOT | BHI | 5 | 13 Aug 0000 - 0500 | 13888 | 900817 | MWD LOST SIGNAL | BHA | MWD |  | 08/13/2022 | SSA-5972 | 5 | SHDN-19
1443 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | T914 | Hrs | UTMN-415
1444 | IPDF | GDF | 8.5 | 13 Aug 2030 - 0500 | 6120 | 900729 | GYRO UNABLE LATCH UBHO,POH FOUND TOOL COVERED W/ MUD MARBLE SETTLING. | MUD | NA |  | 08/13/2022 | T914 | 8.5 | UTMN-415
1445 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/13/2022 | V140A | Hrs | ZULF-653
1446 | FOT | RIG | 1 | 13 Aug 2130 - 2230 | 450 | 900730 | OBSERVED DRAWWORKS MALFUNCTION,. NO MOVEMENT UP/DOWN. | RR | DWKS |  | 08/13/2022 | V140A | 1 | ZULF-653
1447 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | 910TE | Hrs | DMMM-102
1448 | FOT | RIG | 5.5 | 13 Aug 0200 - 0730 | 8076 | 900728 | WHILE RAISING THE TRAVELING BLOCK TO PICK UP NEXT STAND, THE FAST LINE CLAMP IN THE DRAW WORK CAME OUT FROM ITS HOUSING | RR | DWKS |  | 08/14/2022 | 910TE | 2.5 | DMMM-102
1449 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ADC-43L | Hrs | UTMN-3118
1450 | FRFM | TK3 | 66.5 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/14/2022 | ADC-43L | 23.5 | UTMN-3118
1451 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ADC-52 | Hrs | SDGM-1185
1452 | HINW | BAW | 388.5 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/14/2022 | ADC-52 | 24 | SDGM-1185
1453 | 12705 |  | CIRC | N | 4185 | MPMP | WASH DOWN TO 9,249 FT, TOP OF I-CIR & DISPLACE HOLE TO 80 PCF BRINE.- FLOW 200 GPM, 3400 PSI.- FLOW CHECK - WELL STATIC | 12705 |  | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1454 | 12705 |  | CIRC | N | 4185 | MPMP | P/T 4-1/2" LINER WITH 80 PCF TO 1250 PSI BRINE FOR 15 MINS OK ( 2,000 PSI EQUIVALENT WATER) | 12705 |  | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1455 | 12705 |  | CIRC | N | 4185 | MPMP | DISPLACE HOLE TO 79 PCF WBM.- FLOW 200 GPM, 3400 PSI.- FLOW CHECK - WELL STATIC | 12705 |  | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1456 | 12705 | 9250 | RW | N | 4185 | BIT | DRILL OUT I-CIRC @ 9,249 FT, FR: 200 GPM, SPP: 3,300 PSI, WOB: 1 - 2 , RPM: 80 , TORQ: 1-2.7 KLB.FT- DRESS I-CIRC & CHECK ON ELEVATOR OK. | 12705 | 9249 | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1457 | 12705 | 9329 | RW | N | 4185 | BIT | DRILL OUT FLOAT COLLAR @ 9,296 FT, FR: 200 GPM, SPP: 3,300 PSI, WOB: 3 - 5 , RPM: 60 , TORQ: 1.5-2.5 KLB.FT.- WASH DOWN TILL TAG TOP OF 1ST MPASS PACKER 9,329 FT | 12705 | 9296 | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1458 | 12705 |  | CIRC | N | 4185 | MPMP | PUMP 2 X 30 BBLS HVP & CIRCULATE HOLE CLEAN. - FR : 200 GPM & PRESS : 3400 PSI.FLOW CHECK - WELL STATIC- PUMP SLUG | 12705 |  | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1459 | 12705 | 4532 | TO | N | 4185 | STDP | POOH WITH 3-7/8" CLEAN OUT BHA ON 4" DP FROM 9,329 FT TO TOP OF 2-3/8" DP @ 4,532 FT.- FLOW CHECK @ TOP OF BHA - WELL STATIC. | 12705 | 9329 | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1460 | 12705 |  | HT | N | 4185 | PEL | R/U 2 3/8" HANDLING EQUIPMENT ON RIG FLOOR.- MONITOR WELL ON TRIP TANK | 12705 |  | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1461 | 12705 | 0 | TO | N | 4185 | BHA | POOH WITH 3-7/8" CLEAN OUT AND L/D 144 JTS 2-3/8" DP FROM 4,532 FT TO SURFACE.- MONITOR WELL ON TRIP TANK.- L/D 3 7/8" PDC BIT DULL GRADING:1-1-WT-A-X-I-NO-BHA. | 12705 | 4532 | RIG | 08/14/2022 | ADC-53L | CT | HRDH-530
1462 | 48.5 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | C/O TRIP FOR 4-1/2" OBL & LWR COMPL. | 24 | 4185 | 12 Aug 0430 | 08/14/2022 | ADC-53L | Type | HRDH-530
1463
1464
1465 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ADC-54L | Hrs | HRDH-584
1466 | CFFM | TK2 | 11 | 14 Aug 1800 - 0500 | 2325 | 900835 | WHILE RIH 9-5/8" CSG, HAD OBSTRUCTION @ 2325', WORKED ON OBSTRUCTION WITHOUT SUCCESS, DECIDED TO POOH & RUN REAMING TRIP. | BHS | NA |  | 08/14/2022 | ADC-54L | 11 | HRDH-584
1467 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ADC-55L | Hrs | UTMN-3171
1468 | STBH | TK3 | 358 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/14/2022 | ADC-55L | 24 | UTMN-3171
1469 | 7019 | 960 | TO | N | 3965 | STDP | POOH 8-1/2" CO BHA # 3 FROM 2,900 FT TO TOP BHA AT 960 FT.- MONITOR THE WELL WITH TRIP TANK | 7019 | 2900 | RIG | 08/14/2022 | ADC-57L | CT | KRSN-175
1470 | 7019 |  | SDR1 | N | 3965 | NA | CONDUCT H2S DRILL. | 7019 |  | RIG | 08/14/2022 | ADC-57L | CT | KRSN-175
1471 | 7019 | 0 | LDP | N | 3965 | STRG | POOH 8-1/2" CO RUN # 3 FROM 960 FT TO SURFACE.- BIT DULL GRADING: 1-2-WT-A-X-I-NO-BHA- L/D JAR- MONITOR THE WELL WITH TRIP TANK. | 7019 | 960 | RIG | 08/14/2022 | ADC-57L | CT | KRSN-175
1472 | 7019 |  | OTH | E | 3965 | NA | HPJSM PU MU LOGGING RUN #4 TLC VIT+MDT LOGGING TOOLS & RIH TO 155 FT.- CHECK TOOLS ON SURFACE. OK.- MONITOR WELL ON TRIP TANK. | 7019 |  | SWL | 08/14/2022 | ADC-57L | LOG | KRSN-175
1473 | 7019 |  | OTH | E | 3965 | NA | RIH TLC LOGGING TOOLS (MDT-VIT) ON 5" HWDP X 5" DP FROM 155 FT TO 4,660 FT WITH CONTROLLED SPEED.- FILL UP STRING EVERY 10 STANDS.- DRIFTED ALL STANDS RIH WITH 2.625" DRIFT.- MONITOR THE WELL ON TRIP TANK. | 7019 |  | SWL | 08/14/2022 | ADC-57L | LOG | KRSN-175
1474 | 7019 |  | CIRC | E | 3965 | MPMP | CIRCULATE 1.5 STRING VOLUME W/ 79 PCF OBM. | 7019 |  | RIG | 08/14/2022 | ADC-57L | LOG | KRSN-175
1475 | 7019 |  | OTH | E | 3965 | NA | LATCH WIRELINE CABLE PUMP-DOWN WET CONNECTOR HEAD INTO DOWN HOLE WET CONNECTOR HEAD @ 4,482 FT AS PER WIRELINE ENGINEER INSTRUCTION.- M/U WL CSES WITH FED THRU WIRE LINE CABLE.- RIH SLB WL CABLE- PUMP DOWN @ 100 GPM, 150 PSI TO ASSIST TO LATCH.- FUNCTION TEST SLB TOOLS- PERFORM PULL TEST TO 3,300 LBS.- MONITOR WELL THROUGH TRIP TANK. | 7019 |  | SWL | 08/14/2022 | ADC-57L | LOG | KRSN-175
1476 | 7019 |  | OTH | E | 3965 | NA | RIH TLC VIT MDT RUN #4 FROM 4,660 FT TO 6,712 FT.- FILL UP STRING EVERY 10 STANDS.- MONITOR WELL THROUGH TRIP TANK | 7019 |  | SWL | 08/14/2022 | ADC-57L | LOG | KRSN-175
1477 | 7019 | 6712 | LOG | E | 3965 | WLT | SLB WL PERFORM VIT AS PER ARAMCO RMD. SCAN AROUND 6,702 T0 6,715 FT ...... AT RPT.- PERFORMED STICK TEST 3, 8, 15, 30 MIN PRIOR TO EACH VIT POINT.- MAX STATIONARY TIME: 4 HRS.- VIT POINTS TAKEN "ZERO" OUT OF 3 VIT POINTS.- TOTAL "ZERO" SAMPLES OUT OF 1 TOTAL.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 6712 | SWL | 08/14/2022 | ADC-57L | LOG | KRSN-175
1478 | 293.75 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/14/2022 | ADC-57L | Type | KRSN-175
1479
1480
1481 |  |  | RIG | OTH |  | 13523 | CONT L/D 5" TEST ASSY AND P/U 4" TEST ASSY.- X.O 4-1/2" IF P X XT-39 B + 1 JNT 4" DP + 5 FT PJ + 4" SES + 4" FOSV + 10 FT PJ. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1482 |  | 900834 | RIG | OTH |  | 13523 | RIG REPAIR TRIP TANK PUMP MALFUNCTION. - POOH TEST ASSY AND PUMPED BRINE 77 PCF VIA KILL LINE @ 2BPM. |  | RR | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1483 |  |  | RIG | BOPT |  | 13523 | P/T 13-5/8" 5 K BOP AS PER ARAMCO WCM USING 4" DPS:- TEST # 5: TOP RAM, CHOCK AND KILE LINE MANUAL VALVES, LOWER KILL LINE MANUAL VALVE#2, 4"FOSV FOR 300/2550 PSI FOR 10 MIN- TEST # 6": ANNULAR, CHOCK AND KILE INE MANUAL VALVES, LOWER KILL LINE MANUAL VALVE#2, S. PIPE MANULA VALVE FOR 300/2550 PSI FOR 10 MIN. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1484 |  |  | RIG | OTH |  | 13523 | POOH AND L/D 4" TEST ASSY. P/U AND M/U 4-1/2" TEST ASSY & RIH WITH 11" TEST PLUG.- 5 STD'S 4" HWDP'S + CIW TEST PLUG + X.O (4-1/2" IF P X 4-1/2" NVAM B) + 40 FT 4-1/2" NVAM JT + X.O ( 4-1/2" NVAM P X XT-39 B) + 4" FOSV + 5 FT 4" PJ.- INSTALLED 2 PLUGS INTO 11" TEST PLUG. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1485 |  |  | RIG | BOPT |  | 13523 | P/T 13-5/8" 5 K BOP AS PER ARAMCO WCM. USING 4-1/2"" TBG.- TEST #7: P/T ANNULAR, 2 HCR TO 300/2500 PSI FOR 10 MIN EA.- TEST #8: UPPER PIPE RAM, 2 HCR TO 300/2550 PSI FOR 10 MIN EA. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1486 |  |  | RIG | OTH |  | 13523 | UNSCRWED AND POOH AND L/D 4-1/2" TEST ASSY. P/U AND M/U 3-1/2" TEST ASSY.- 5 STD'S 4" HWDP'S + CIW TEST PLUG + X.O (4-1/2" IF P X 4-1/2" NVAM B) + X.O ( 4-1/2" NVAM P X 3-1/2" EUE B) + 30 FT 3-1/2" EUE JT + X.O (3-1/2" EUE P X XT-39 B) + 10 FT 4"PJ. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1487 |  |  | RIG | BOPT |  | 13523 | P/T 13-5/8" 5 K BOP AS PER ARAMCO WCM. USING 3-1/2"" TBG.- TEST #9: P/T ANNULAR, 2 HCR TO 300/2500 PSI FOR 10 MIN EA.- TEST #10: UPPER PIPE RAM,2 HCR TO 300/2550 PSI FOR 10 MIN EA. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1488 |  |  | RIG | OTH |  | 13523 | L/D 4 1/2" TEST ASSY. AND P/U CUP TESTER TEST ASSY.- P/U SIDE ENTRY SUB AND CONNECTED SAME TO TRIP TANK TO FILL WITH 77 PCF BRINE @ 2 BPM. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1489 |  |  | RIG | BOPT |  | 13523 | TEST#11: P/T 13 5/8" 5K BOP ANNULAR & WELLHEAD SOVS' TO 300/2550 PSI FOR 10 MIN EA. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1490 |  |  | RIG | OTH |  | 13523 | PERFORMED ACCUMULATOR DRILL.- FUNCTION TESTED ADJUSTABLE CHOCKS HYDRAULIC PUMPS MANUALLY.- FUNCTION TESTED RAMS MANUAL LOCKING DEVICES.- PERFORMED 2 OFFLINE TESTS ON THE EMERGENCY KILL LINE TO 300/2550 PSI FOR 10 MIN EA. |  |  | 13523 | 08/14/2022 | ADC-58L | RBOP | ABHD-169
1491 |  |  | RIG | OTH |  | 13523 | POOH AND L/D CUP TESTER ASSY. |  |  | 13523 | 08/14/2022 | ADC-58L | BOP | ABHD-169
1492 |  |  | RIG | SDR1 |  | 13523 | CONDUCT H2S DRILL |  |  | 13523 | 08/14/2022 | ADC-58L | NA | ABHD-169
1493 |  |  | RIG | PJSM | 4125 | 13523 | HELD PJSM PRIOR TO START R/U SLB CTU EQUIPMENT. |  |  | 13523 | 08/14/2022 | ADC-58L | NA | ABHD-169
1494 |  |  | RIG | OTH | 4125 | 13523 | N/D BELL NIPPLE & DISCONNECTED FLOW LINE. |  |  | 13523 | 08/14/2022 | ADC-58L | NA | ABHD-169
1495 |  |  | SCT | OTH | 4125 | 13523 | R/U CT EQUIPMENT ON 13-5/8" -5M BOP ANNULAR PREVENTER:- DSA 13 5/8" 5M X 5-1/8" 10M, 5-1/8" X 4-1/16" 10M, 4 1/16-10M SLB GATE VALVE, 4-1/16" 10M RISER 10FT, 4-1/16" 10M RISER 8 FT & 4-1/16" QUAD BOP.- CONNECTED BOP HYD HOSES, FUNCTION TEST SAME & CONNECTED KILL LINE TO CT PUMPING UNIT.- P/T ALL ASSY. BETWEEN RIG BOP BLIND RAMS AND CT BOP BLIND RAMS TO 500 PSI FOR 15-MINS HOLD OK- P/T GATE VALVE, BOP BODY & BLIND RAMS TO 300/2,500-PSI FOR 15-MINS HOLD OK.- P/T CT KILL LINE AGAINST GATE VALVES (OFFLINE), TO 300/2,500-PSI FOR 15-MINS HOLD OK. |  |  | 13523 | 08/14/2022 | ADC-58L | NA | ABHD-169
1496 |  |  | SCT | OTH | 4125 | 13523 | HELD PJSM. LIFTED CT INJECTOR HEAD TO RIG FLOOR BY CRANE, TRANSFERED TO TOP DRIVE LINKS, CONNECTED 4-1/16" 10M RISER (10FT LONG) |  |  | 13523 | 08/14/2022 | ADC-58L | NA | ABHD-169
1497 |  |  | SCT | OTH | 4125 | 13523 | M/U CT BHA (2-3/8" EXTERNAL CONNECTOR, MHA, 2-3/8" STRAIGHT BAR & NOZZLE). STAB THE COIL TBG INJECTOR ON TOP OF C/T BOP.- CONTINUOUSLY PUMPING 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH THS SOV DURING ALL PAST OPERATION. |  |  | 13523 | 08/14/2022 | ADC-58L | NA | ABHD-169
1498 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ADC-58L | Hrs | ABHD-169
1499 | FOT | RIG | 1.5 | 14 Aug 0600 - 0730 | 13523 | 900834 | RIG REPAIR TRIP TANK PUMP MALFUNCTION. | RR | CSYS |  | 08/14/2022 | ADC-58L | 1.5 | ABHD-169
1500 | 83 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | PERFORM ACID STIMULATION JOB FOR L-1. | 10 | 4125 | 09 Aug 0030 | 08/14/2022 | ADC-58L | Type | ABHD-169
1501
1502
1503 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ADC-60 | Hrs | ABSF-216
1504 | FOT | BAL | 166.5 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/14/2022 | ADC-60 | 24 | ABSF-216
1505 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ADES-157 | Hrs | HRDH-642
1506 | FOT | ITS | 12.5 | 28 Jul 2230 - 0500 | 9100 | 900239 | DIES CARRIER (DIES FRAME) ON ITS POWER TONG BROKEN. WAIT FOR ANOTHER SET FROM ITS YARD. - CONT POOH USING RIG TONG | TF | CTRQ |  | 08/14/2022 | ADES-157 | 7 | HRDH-642
1507 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ADES-798 | Hrs | HRDH-2302
1508 | FOT | SWL | 30 | 12 Aug 0700 - 2200 | 1037 | 900721 | SLB WIRE LINE ATTEMPTED TO LATCH PWCH NO SUCCESS. | TF | WLT |  | 08/14/2022 | ADES-798 | 14 | HRDH-2302
1509 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ARO-3002 | Hrs | MRJN-813
1510 | FOT | HML | 7.25 | 14 Aug 2145 - 0500 | 8500 | 900769 | HALLIBURTON UNABLE TO RETRIVE TPI SLEEVE. | TF | WPSML |  | 08/14/2022 | ARO-3002 | 7.25 | MRJN-813
1511 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ARO-3003 | Hrs | SFNY-4220
1512 | HERR | RIG | 2 | 14 Aug 2345 - 0145 | 1465 | 900820 | CREW DROP DOPE BRUSH HEAD INTO STRING | FISH | STRG |  | 08/14/2022 | ARO-3003 | 2 | SFNY-4220
1513 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ARO-3004 | Hrs | MRJN-2060
1514 | FOT | INW | 8.5 | 14 Aug 2000 - 0500 | 225 | 900770 | SETTING ROD WAS OBSERVED LEFT IN HOLE AFTER RETRIEVING TUBING ME PLUG SETTING TOOL ON SLICKLINE | TF | SLICK |  | 08/14/2022 | ARO-3004 | 8.5 | MRJN-2060
1515 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | DPS-45 | Hrs | UTMN-2331
1516 | FOT | SDM | 30.5 | 13 Aug 0900 - 1530 | 15408 | 900822 | LOST COMMUNICATION W/ SLB RSS TOOLS. | BHA | RSS |  | 08/14/2022 | DPS-45 | 10.5 | UTMN-2331
1517 | FOT | HWP | 15 | 14 Aug 1200 - 0300 | 17096 | 900832 | PUMPING HEAD WOULD NOT LATCH TO WET CONNECT. POOH WIRELINE & DISCOVER PUMPING HEAD ALIGNMENT PIN MISSING. | TF | WLT | 900723 | 08/14/2022 | DPS-74 | 15 | NJYN-33
1518 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | DPS-74 | Hrs | NJYN-33
1519 | FOT | HWP | 57.75 | 12 Aug 1415 - 1200 | 17900 | 900723 | DATA FROM HALLIBURTON NMR (MRIL) TOOL CAN NOT BE INTERPRETED DUE TO NOISE. | TF | WLT |  | 08/14/2022 | DPS-74 | 7 | NJYN-33
1520 | FOT | HWP | 15 | 14 Aug 1200 - 0300 | 17096 | 900832 | PUMPING HEAD WOULD NOT LATCH TO WET CONNECT. POOH WIRELINE & DISCOVER PUMPING HEAD ALIGNMENT PIN MISSING. | TF | WLT | 900723 | 08/14/2022 | DPS-74 | 15 | NJYN-33
1521 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ENS-108 | Hrs | ZULF-2015
1522 | FPMP | RIG | 8 | 14 Aug 1530 - 2330 | 5087 | 900805 | MUD PUMPS #1 & #2 PRESSURE IS FLUCTUATING & NOT STEADY. | RR | MPMP |  | 08/14/2022 | ENS-108 | 8 | ZULF-2015
1523 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | ENSCO-54 | Hrs | ABSF-17
1524 | FOT | KSC | 1 | 14 Aug 2300 - 0000 | 273 | 900852 | ALKHORAYEF CABLE SPOOLING MACHINE DOWN, TROUBLESHOOT & FIXED SAME. | TF | ESPL |  | 08/14/2022 | ENSCO-54 | 1 | ABSF-17
1525 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | HI-2 | Hrs | BRRI-434
1526 | UVLC | ARM | .5 | 14 Aug 0215 - 0245 | 2070 | 900811 | DRILL 16" HOLE WITH SW , GEL SWEEP & MUD CAP DUE TO TOTAL LOSSES. | LCIR | NA |  | 08/14/2022 | HI-2 | .5 | BRRI-434
1527 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | HI-9 | Hrs | BRRI-155
1528 | STDP | ARM | 53 | 12 Aug 1030 - 1530 | 11088 | 900798 | PERFORM 30 MINUTES STICKY TEST, OBSERVED OVER PULL ON 4" DRILL PIPE. STRING GOT DIFFERENTIALLY STUCK. | STUK | DP |  | 08/14/2022 | HI-9 | 10.5 | BRRI-155
1529 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | MP-1 | Hrs | MRJN-78
1530 | CPNF | HCM | 40.25 | 13 Aug 1245 - 0500 | 6450 | 900731 | RIH WITH C/O ASSY, NO BALANCED CEMENT KICK OFF PLUG FOUND AT EXPECTED DEPTH. SOFT CEMENT OBSERVED TILL TAG TOC AT 6931'. POH TO RE-RUN KOP. | CMT | NA | 900303 | 08/14/2022 | MP-1 | 24 | MRJN-78
1531 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | NBR-16S | Hrs | HMYM-433112
1532 | DRIG | RIG | 1.5 | 14 Aug 1145 - 1315 | 4853 | 900767 | UNABLE TO LAND HANGER DUE TO RIG MISALIGNMENT | RR | RSYS |  | 08/14/2022 | NBR-16S | 1.5 | HMYM-433112
1533 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | NBR-263S | Hrs | QTIF-736
1534 | CPNF | NCS | 72 | 11 Aug 0330 - 0500 | 5145 | 900810 | LOST TIME ON NPS CEMENTING DUE TO SOFT CMT WHILE DRILL OUT CMT PLUG & FAILURE ON ZONAL ISOLATION AFTER CHECK CMT INTEGRITY, PLAN TO D/O CMT PLUG & SPOT ANOTHER CMT PLUG. | CMT | NA |  | 08/14/2022 | NBR-263S | 23 | QTIF-736
1535 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | NBR-654S | Hrs | HRDH-1150
1536 | FOT | PKP | 252.25 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/14/2022 | NBR-654S | 20 | HRDH-1150
1537 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | NBR-987S | Hrs | JLMN-35
1538 | OTH | RIG | 141 | 09 Aug 0800 - 0500 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/14/2022 | NBR-987S | 24 | JLMN-35
1539 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | PA-70S | Hrs | HRDH-1939
1540 | FOT | RIG | 1 | 14 Aug 0400 - 0500 | 3110 | 900836 | DOWN TIME ON SANAD DUE TO WATER TANK DISCHARGE PUMP WENT DOWN & NOT ABLE TO PROVIDE WATER TO CIRC. SYSTEM FOR DRILLING. | RR | CSYS |  | 08/14/2022 | PA-70S | 1 | HRDH-1939
1541 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | PA-861S | Hrs | HRDH-1973
1542 | FOT | FMC | 8.5 | 13 Aug 0100 - 0930 | 0 | 900765 | ATTEMPTED TO MAKE UP FIRST JOINTS AND OBSERVED POWER TONG MALFUNCTION . NOT ABLE TO PROVIDE SUFFICIENT MAKE UP TORQUE ON JAM UNIT. AND POWER UNIT FAILED | TF | CTRQ |  | 08/14/2022 | PA-861S | 4.5 | HRDH-1973
1543 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | PN-9 | Hrs | MRJN-673
1544 | CFST | HCM | 8.25 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/14/2022 | PN-9 | 8.25 | MRJN-673
1545 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SINO-10 | Hrs | JLDI-38
1546 | UNKN | MSL | 2 | 14 Aug 0700 - 0900 | 11030 | 900808 | WHILE R/UP AL-MANSORI SLICK LINE. A WRONG SIGNAL WAS GIVEN TO DRILLER WHILE PICKING UP S/L LUBRICATOR USING CRANE AND DRAW WORKS, LEADS STAFFING BOX TO HIT LUBRICATOR X/O . NO INJURY. | HSEI | NA |  | 08/14/2022 | SINO-10 | 2 | JLDI-38
1547 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SINO-29N | Hrs | SFNY-2005
1548 | PCPF | ARM | 240 | 05 Aug 0500 - 0500 | 6825 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/14/2022 | SINO-29N | 24 | SFNY-2005
1549 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SINO-37L | Hrs | HWYH-639
1550 | CEDE | HCM | 6.5 | 14 Aug 2230 - 0500 | 7055 | 900821 | TROUBLE SHOUTING ON CEMENT SYLO AND BACH MIXER, SUCTION LINE BETWEEN CEMNT SYLO AND BACH MIXER PLUGGED. CEMENT WEIGHT COULD NOT BE RAISED MORE THAN 112 PCF DURING 2H 45 MIN. | JF | NA |  | 08/14/2022 | SINO-37L | 6.5 | HWYH-639
1551 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SND-2004 | Hrs | BRRI-1148
1552 | FOT | SWL | 6 | 14 Aug 1200 - 1800 | 2000 | 900766 | SLB WL GR TOOL FAILURE. TROUBLE SHOOT, NO SUCCESS. CHANGE TOOL. | TF | WLT |  | 08/14/2022 | SND-2004 | 6 | BRRI-1148
1553 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SP-167 | Hrs | HRDH-218
1554 | ORDS | ARN | 110.5 | 10 Aug 0800 - 0500 | 7167 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/14/2022 | SP-167 | 24 | HRDH-218
1555 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SP-229 | Hrs | JLDI-862
1556 | FOT | WBP | 10 | 14 Aug 1900 - 0500 | 5660 | 900771 | ATTEPMT TO SET WFD 9-5/8" TRIAL TEST BRIDGE PLUG (WSBP) WITHOUT SUCCESS. | TF | BP |  | 08/14/2022 | SP-229 | 10 | JLDI-862
1557 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SP-261 | Hrs | MHWZ-903
1558 | HERR | ITS | 4.5 | 14 Aug 0030 - 0500 | 1589 | 900823 | ITS CREW MEMBER FUNCTIONED SPIDER SLIPS WITH CASING SET IN SLIPS FOR UNKNOWN REASON, - LEAVING THE SWITCH IN THE OPEN POSITION. WHEN CASING JERKED SLIGHTLY WHILE BACKING OUT A JOINT OF CASING, THE SLIPS OPENED DROPPING 3 JINTS OF 18 5/8" CASING DOWN THE HOLE | TF | TTRQ |  | 08/14/2022 | SP-261 | 4.5 | MHWZ-903
1559 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SP-262 | Hrs | JNAB-152802
1560 | FOT | WDS | 14.25 | 13 Aug 1715 - 0730 | 3648 | 900803 | WHILE CLEAN OUT TOP WIPER PLUG, NOTICED INCREASE IN PRESSURE OFF BOTTOM, POH FOUND MOTOR POWER SECTION HOUSING BACKED OFF. | BHA | MMOT |  | 08/14/2022 | SP-262 | 2.5 | JNAB-152802
1561 | 6345 | 6345 | TI | E | 4186 | STDP | CONTD RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 4020' TO CORE POINT @ 6345'.-WASH AND REAM DOWN LAST TWO STDS. | 6345 | 4050 | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1562 | 6345 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTMS UP WITH 200 GPM & PRESSURE 270 PSI. | 6345 |  | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1563 | 6345 |  | CIRC | E | 4186 | MPMP | DROP 1" NOV DIVERTING BALL, PUMP DOWN WITH 90 GPM & WAIT TILL SEATED IN ORDER TO DIVERT FLUID AWAY FROM THE INNER BARREL TO START CORING ACROSS PADS FORMATION.-CONFIRM SPACE OUT FOR CUTTING THE CORE.@6345.5' -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS. | 6345 |  | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1564 | 6378 |  | CORE | E | 4186 | CORC | CUT 6-1/8" X 2 5/8" CORE RUN #1 FROM 6345' TO 6378' W/80 PCF SALT POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, (RPM: 65 - TQ 2-3 KLFTLB) & (GPM: 170 - PRESS 650 PSI)-STOP ROTATION AND BREAK OUT CORE WITH 15K OVERPULL. | 6345 |  | NOC | 08/14/2022 | SP-53L | CORE | HRDH-528
1565 | 6378 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTM UP WITH 120 GPM @ 440 PSI WITH FULL RETURNS. | 6378 |  | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1566 | 6378 |  | SDR1 | E | 4186 | NA | FLOW CHECK-WELL STATIC OK. | 6378 |  | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1567 | 6378 | 5880 | TO | E | 4186 | STDP | HPJSM, POOH 6 1/8" NOV CORING ASSY. TO/5880' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS. | 6378 | 6375 | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1568 | 6378 |  | SDR1 | E | 4186 | NA | FLOW CHECK AFTER PULL 5 STDS WELL STATIC OK. | 6378 |  | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1569 | 6378 | 3536 | TO | E | 4186 | STDP | POOH 6 1/8" NOV CORING ASSY. TO 9-5/8" CSG SHOE 3536' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS. | 6378 | 5880 | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1570 | 6378 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT 9-5/8" CSG SHOE - WELL STATIC OK. | 6378 |  | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1571 | 6378 |  | HT | E | 4186 | CORC | CON'T POOH 6-1/8" NOV CORING ASSY. RUN #1 TO 1460 ' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS. | 6378 |  | NOC | 08/14/2022 | SP-53L | CORE | HRDH-528
1572 | 6378 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT TOP BHA - WELL STATIC OK.-CHECKING FOR H2S-ZERO H2S READING. | 6378 |  | RIG | 08/14/2022 | SP-53L | CORE | HRDH-528
1573 | 6378 |  | HT | E | 4186 | CORC | CON'T POOH 6-1/8" NOV CORING ASSY. RUN #1 TO 250' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-CHECKING FOR H2S EVERY CONNECTION & ZERO H2S READING. | 6378 |  | NOC | 08/14/2022 | SP-53L | CORE | HRDH-528
1574 | 35 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 24 | 4186 | 13 Aug 0230 | 08/14/2022 | SP-53L | Type | HRDH-528
1575
1576
1577 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SP-58 | Hrs | HRDH-795
1578 | FOT | SPS | 1 | 14 Aug 1845 - 1945 | 16672 | 900768 | MWD HAD BAD SIGNAL DETECTION , TROUBLESHOOTING SAME. OK. | TF | COMP |  | 08/14/2022 | SP-58 | 1 | HRDH-795
1579 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SSA-102 | Hrs | QTIF-693
1580 | FOT | WWD | 45.75 | 13 Aug 0545 - 0500 | 9715 | 900815 | WFD WHIPSTOCK DID NOT SET, BOLT WAS SHEARED, LOST WHIPSTOCK IN HOLE. | TF | WPSTK |  | 08/14/2022 | SSA-102 | 23 | QTIF-693
1581 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SSA-202 | Hrs | QTIF-191
1582 | CEDE | NCS | 2.75 | 14 Aug 0215 - 0500 | 17794 | 900872 | PERFORM CEMENT PLUG PRSSURE TEST @500 PSI -NEGATIF , DUE SOFT CEMENT . | JF | NA |  | 08/14/2022 | SSA-202 | 2.75 | QTIF-191
1583 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SSA-5969 | Hrs | UTMN-3148
1584 | STBH | ARM | 178.25 | 06 Aug 1315 - 0500 | 3220 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | BHA |  | 08/14/2022 | SSA-5969 | 24 | UTMN-3148
1585 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | SSA-5972 | Hrs | SHDN-19
1586 | FOT | BHI | 22.5 | 13 Aug 0000 - 0130 | 13888 | 900817 | MWD LOST SIGNAL | BHA | MWD |  | 08/14/2022 | SSA-5972 | 17.5 | SHDN-19
1587 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/14/2022 | T914 | Hrs | UTMN-415
1588 | IPDF | GDF | 32.5 | 13 Aug 2030 - 0500 | 6120 | 900729 | GYRO UNABLE LATCH UBHO,POH FOUND TOOL COVERED W/ MUD MARBLE SETTLING. | MUD | NA |  | 08/14/2022 | T914 | 24 | UTMN-415
1589 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | 910TE | Hrs | DMMM-102
1590 | FOT | WWL | 13 | 15 Aug 1530 - 0500 | 18795 | 900842 | AFTER L/D WFD LOGGING TOOLS FOUND CALIPER LOG DATA NOT RECORDED DUE TO COMMUNICATION FAULT IN WFD CBG TOOL. | TF | WLT |  | 08/15/2022 | 910TE | 13 | DMMM-102
1591 | FPMP | RIG | 1 | 15 Aug 2145 - 2245 | 11165 | 900879 | PRESSURE DROP DUE TO WASHOUT ON VALVE OF MP#2 | RR | MPMP |  | 08/15/2022 | ADC-14 | 1 | HRDH-1312
1592 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADC-14 | Hrs | HRDH-1312
1593 | FOT | SDM | .5 | 15 Aug 0945 - 1015 | 10965 | 900855 | SLB DRAWWORK SENSOR GIVE FALSE READING | TF | COMP |  | 08/15/2022 | ADC-14 | .5 | HRDH-1312
1594 | FPMP | RIG | 1 | 15 Aug 2145 - 2245 | 11165 | 900879 | PRESSURE DROP DUE TO WASHOUT ON VALVE OF MP#2 | RR | MPMP |  | 08/15/2022 | ADC-14 | 1 | HRDH-1312
1595 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADC-43L | Hrs | UTMN-3118
1596 | FRFM | TK3 | 90 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/15/2022 | ADC-43L | 23.5 | UTMN-3118
1597 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADC-52 | Hrs | SDGM-1185
1598 | HINW | BAW | 412.5 | 29 Jul 1300 - 0500 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/15/2022 | ADC-52 | 24 | SDGM-1185
1599 | 12705 |  | HT | N | 4185 | BHA | HPJSM, P/U & M/U 3-1/4" CLEAN OUT BHA.- M/U 3-1/4" CONE MILL + 3-3/8" BIT SUB WITH FLOAT.- MONITOR WELL ON TRIP TANK. | 12705 |  | RIG | 08/15/2022 | ADC-53L | CT | HRDH-530
1600 | 12705 | 7828 | LDP | N | 4185 | STRG | RIH W/ 3-1/4" CLEAN OUT ASSY ON 2-3/8" DP TO 6,790 FT...ON GOING ART.- P/U 216/249 JOINTS OF 2-3/8" DP FROM RACK WHILE RIH.- BREAK CIRC EVERY 20 JTS . | 12705 | 0 | RIG | 08/15/2022 | ADC-53L | CT | HRDH-530
1601 | 72.5 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | C/O TRIP FOR 4-1/2" OBL & LWR COMPL. | 24 | 4185 | 12 Aug 0430 | 08/15/2022 | ADC-53L | Type | HRDH-530
1602
1603
1604 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADC-54L | Hrs | HRDH-584
1605 | CFFM | TK2 | 35 | 14 Aug 1800 - 0500 | 2325 | 900835 | WHILE RIH 9-5/8" CSG, HAD OBSTRUCTION @ 2325', WORKED ON OBSTRUCTION WITHOUT SUCCESS, DECIDED TO POOH & RUN REAMING TRIP. | BHS | NA |  | 08/15/2022 | ADC-54L | 24 | HRDH-584
1606 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADC-55L | Hrs | UTMN-3171
1607 | STBH | TK3 | 382 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/15/2022 | ADC-55L | 24 | UTMN-3171
1608 | 7019 | 6356 | LOG | E | 3965 | WLT | SLB WL PERFORM VIT W/TLC MDT RUN#4 AS PER ARAMCO RMD. PERFORMING STICK TEST FOR VIT POINT # 3 .........AT RPT.- SCAN AROUND AT 6342 FT - 6356 FT FOR 3RD VIT.- PERFORMED STICK TEST 3, 8, 15, 30 MIN PRIOR TO EACH VIT POINT.- MAX STATIONARY TIME: 4 HRS.- VIT POINT # 1 AT 6702 FT - 6715 FT - NO SEAL - VIT POINT ABORTED AS PER RMD.- VIT POINT # 2 AT 6514 FT - 6528 FT - (TWO SESSIONS) - OK.- SAMPLE POINT # 1 AT 6393 FT - ( 1 SESSIONS).- VIT POINTS TAKEN 2 (ONE ABORTED) OUT OF 3 VIT POINTS.- SAMPLE POINT TAKEN 1 OUT OF 1 SAMPLE POINT.- TOTAL PUMP OUT 174 L AT RPT, OVERBALANCE AFTER PUMP OUT 667 PSI.- MONITOR THE WELL WITH TRIP TANK | 7019 | 6712 | SWL | 08/15/2022 | ADC-57L | LOG | KRSN-175
1609 | 317.75 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/15/2022 | ADC-57L | Type | KRSN-175
1610
1611
1612 | 14929 |  | OTH | C | 4125 | NA | - P/T ALL RISER CONNECTIONS, UPPER STRIPPER AGAINST GATE VALVE TO 300 / 2,500 PSI FOR 15 MINS, HOLD- OK.- P/T DOUBLE FLAPPER CHECK VALVE, RISER STACK AGAINST GATE VALVE TO 2,500 PSI FOR 15 MINS, HOLD- OK.- P/T CT PIPE RAM, LOWER STRIPPER AGAINST GATE VALVE TO 300 / 2,500 PSI FOR 15 MINS, HOLD- OK.- CONTINUOUSLY PUMP 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH THS SOV'S. | 14929 |  | SCT | 08/15/2022 | ADC-58L | STIM | ABHD-169
1613 | 14929 |  | OTH | C | 4125 | NA | DISPLACED COIL TUBE W/77 PCF LUBRICATED CACL2 BRINE.- CONTINUOUSLY PUMP 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH THS SOV'S. | 14929 |  | RIG | 08/15/2022 | ADC-58L | STIM | ABHD-169
1614 | 14929 |  | OTH | C | 4125 | NA | RIH WITH 2 3/8" COIL TBG FROM SURFACE TO 7" LINER SHOE 11,329 FT WHILE CONTINUOUSLY PUMPING LUBRICATED BRINE @ 0.5 BPM THROUGH C/T.- PERFORMED PULL TESTS EVERY 1,000 FT INSIDE CSG.- MEANWHILE MIX MUTUAL SOLVENT PREFLUSH.- CONTINUOUSLY PUMP 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH THS SOV'S. | 14929 |  | RIG | 08/15/2022 | ADC-58L | STIM | ABHD-169
1615 | 14929 |  | OTH | C | 4125 | NA | RIH WITH 2 3/8" COIL TBG FROM 7" TOW AT 11,329 FT TO 13,850 FT (70% OF OPEN HOLE) WHILE CONTINUOUSLY PUMPING LUBRICATED BRINE @ 1 BPM THROUGH C/T.- PERFORMED PULL TESTS EVERY 500 FT INSIDE OPEN HOLE.- CONTINUOUSLY PUMP 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH THS SOV'S. | 14929 |  | SCT | 08/15/2022 | ADC-58L | STIM | ABHD-169
1616 | 14929 |  | STIM | C | 4125 | CTU | RIH WITH 2 3/8" COIL TBG FROM 13,850 FT TO TD @ 14,929 FT WHILE PUMPING 77 PCF PRE-FLUSH- KEPT THE CHOKE OPEN & CONTINUOUSLY PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH THS SOV'S.- MEANWHILE MIXING AND 15% EMULSIFIED ACID & 15% ACID. | 14929 |  | SCT | 08/15/2022 | ADC-58L | STIM | ABHD-169
1617 | 14929 |  | STIM | C | 4125 | CTU | POOH WITH SLB 2-3/8" COIL TBG F/14,929 FT TO 11,428 FT (100 FT BELOW 7" LINER SHOE) WHILE PUMPING 14 BBLS OF 15% EMULSIFIED ACID FOLLOWING BY 48 BBLS OF15% HCL ACID PER EACH STAGE (TOTAL 18 STAGES) WITH CHOKE CLOSED.- SLB CT FOLLOWED THE MATRIX ACID STIMULATION TREATMENT PUMPING SCHEDULE AS PROGRAM.- TOTAL PUMPED VOLUME 245 BBLS OF 15% EMULSIFIED HCL & 840 BBLS OF 15% HCL.- PUMPING RATE: 2-3 BPM, CIRC. PRESS: 2800- 3100 PSI, WHP: 0 PSI. | 14929 |  | SCT | 08/15/2022 | ADC-58L | STIM | ABHD-169
1618 | 14929 |  | STIM | C | 4125 | CTU | POOH WITH SLB 2-3/8" COIL TBG F/13,428 FT TO 11,308 FT (20 FT ABOVE 7" LINER SHOE) AND PUMPED 686 BBLS OF POST-FLUSH...........IN PROGRESS- FR 3 BPM, CIRC. PRESS 3100 PSI & WHP : ZERO | 14929 |  | SCT | 08/15/2022 | ADC-58L | STIM | ABHD-169
1619 | 107 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | PERFORM ACID STIMULATION JOB FOR L-1. | 24 | 4125 | 09 Aug 0030 | 08/15/2022 | ADC-58L | Type | ABHD-169
1620
1621
1622 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADC-60 | Hrs | ABSF-216
1623 | HERR | BAL | 48 | 14 Aug 0500 - 0500 | 11253 | 900849 | WHILE L/D ESP ASSY, SAFETY CLAMP SLIPPED FROM 2-7/8" BY-PASS TBG CAUSING DOWNHOLE STRING TO DROP IN HOLE. | JF | ESP |  | 08/15/2022 | ADC-60 | 24 | ABSF-216
1624 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADES-157 | Hrs | HRDH-642
1625 | FOT | ITS | 13.5 | 28 Jul 2230 - 0600 | 9100 | 900239 | DIES CARRIER (DIES FRAME) ON ITS POWER TONG BROKEN. WAIT FOR ANOTHER SET FROM ITS YARD. - CONT POOH USING RIG TONG | TF | CTRQ |  | 08/15/2022 | ADES-157 | 1 | HRDH-642
1626 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADES-158 | Hrs | ABQQ-590
1627 | XTRI | RIG | 3 | 15 Aug 1400 - 1700 | 2540 | 900843 | EXCESSIVE TIME WHILE PRESSURE TESTING 21-1/4" BOPE DUE TO LEAKS BETWEEN FLANGES. | JF | BOP |  | 08/15/2022 | ADES-158 | 3 | ABQQ-590
1628 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADES-173 | Hrs | UTMN-1952
1629 | PCPF | ARM | 23.5 | 15 Aug 0500 - 0500 | 10223 | 900856 | SLICKLINE TAGGED OBSTRUCTION @ 11,223' | TH | NA |  | 08/15/2022 | ADES-173 | 23.5 | UTMN-1952
1630 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADES-174 | Hrs | GHZL-72
1631 | XTTE | RAC | 52.5 | 13 Aug 0030 - 0500 | 11022 | 900874 | FAILURE OF RAC ITCO SPEAR AND CUTTER BHA TO RETRIEVE PBR. | TF | FISHT |  | 08/15/2022 | ADES-174 | 24 | GHZL-72
1632 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADES-798 | Hrs | HRDH-2302
1633 | FOT | SWL | 16 | 15 Aug 0830 - 0100 | 10733 | 900837 | SLB MDT TOOL PUMP FAILURE. | TF | WLT |  | 08/15/2022 | ADES-798 | 16 | HRDH-2302
1634 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADM-262 | Hrs | MRJN-122
1635 | FOT | EX1 | 15 | 15 Aug 1400 - 0500 | 0 | 900838 | SLICK LINE UNIT UNABLE TO START DUE TO MECHANICAL ISSUE | TF | SLICK |  | 08/15/2022 | ADM-262 | 15 | MRJN-122
1636 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ADM-510 | Hrs | ABSF-225
1637 | FOT | RIG | 11 | 15 Aug 1000 - 2215 | 8080 | 900857 | HAD FAILURE IN TDS HYDRAULIC CIRCUIT, TROUBLE SHOOT & FOUND FAILURE IN TDS ELECTRIC/HYDRAULIC COMMUNICATION PANEL | RR | TDS |  | 08/15/2022 | ADM-510 | 11 | ABSF-225
1638 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ARO-3002 | Hrs | MRJN-813
1639 | FOT | HML | 27.25 | 14 Aug 2145 - 0100 | 8500 | 900769 | HALLIBURTON UNABLE TO RETRIVE TPI SLEEVE. | TF | WPSML |  | 08/15/2022 | ARO-3002 | 20 | MRJN-813
1640 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | ARO-3004 | Hrs | MRJN-2060
1641 | FOT | INW | 32.5 | 14 Aug 2000 - 0500 | 225 | 900770 | SETTING ROD WAS OBSERVED LEFT IN HOLE AFTER RETRIEVING TUBING ME PLUG SETTING TOOL ON SLICKLINE | TF | SLICK |  | 08/15/2022 | ARO-3004 | 24 | MRJN-2060
1642 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | CG-1 | Hrs | MRJN-740
1643 | FOT | BCM | 1 | 15 Aug 0800 - 0900 | 274 | 900840 | BAKER CEMENT HEAD FAILURE. IT WAS DELIVERED WITHOUT SEALS. | TF | PUMP |  | 08/15/2022 | CG-1 | 1 | MRJN-740
1644 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | DPS-44 | Hrs | UTMN-2342
1645 | XTTE | ITS | 45 | 14 Aug 0800 - 0500 | 3220 | 900848 | RAN RTTS AND FOUND LEAK IN CASING DUE TO IMPROPER MAKE UP TORQUE | TF | CTRQ |  | 08/15/2022 | DPS-44 | 24 | UTMN-2342
1646 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | DPS-74 | Hrs | NJYN-33
1647 | FOT | HWP | 31.5 | 14 Aug 1200 - 0500 | 17096 | 900832 | PUMPING HEAD WOULD NOT LATCH TO WET CONNECT. POOH WIRELINE & DISCOVER PUMPING HEAD ALIGNMENT PIN MISSING. | TF | WLU | 900723 | 08/15/2022 | DPS-74 | 16.5 | NJYN-33
1648 | CPNF | HCM | 42.25 | 13 Aug 1245 - 0700 | 6450 | 900731 | RIH WITH C/O ASSY, NO BALANCED CEMENT KICK OFF PLUG FOUND AT EXPECTED DEPTH. SOFT CEMENT OBSERVED TILL TAG TOC AT 6931'. POH TO RE-RUN KOP. | CMT | NA | 900303 | 08/15/2022 | MP-1 | 2 | MRJN-78
1649 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | MP-1 | Hrs | MRJN-78
1650 | FOT | NRT | 341.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/15/2022 | MP-1 | 22 | MRJN-78
1651 | CPNF | HCM | 42.25 | 13 Aug 1245 - 0700 | 6450 | 900731 | RIH WITH C/O ASSY, NO BALANCED CEMENT KICK OFF PLUG FOUND AT EXPECTED DEPTH. SOFT CEMENT OBSERVED TILL TAG TOC AT 6931'. POH TO RE-RUN KOP. | CMT | NA | 900303 | 08/15/2022 | MP-1 | 2 | MRJN-78
1652 | HERR | SPS | 1 | 15 Aug 1700 - 1800 | 6345 | 900851 | SPERRY MUD PUMP SENSOR NOT WORKING | DD | RSS |  | 08/15/2022 | MP-4 | 1 | LWHH-20
1653 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | MP-4 | Hrs | LWHH-20
1654 | FOT | RIG | 1 | 15 Aug 1600 - 1700 | 6435 | 900850 | MUD PUMP #3 PISTON & LINER GASKET CHANGE & MUD PUMP 1 BLOWER ISSUE. | RR | MPMP |  | 08/15/2022 | MP-4 | 1 | LWHH-20
1655 | HERR | SPS | 1 | 15 Aug 1700 - 1800 | 6345 | 900851 | SPERRY MUD PUMP SENSOR NOT WORKING | DD | RSS |  | 08/15/2022 | MP-4 | 1 | LWHH-20
1656 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | NBR-263S | Hrs | QTIF-736
1657 | CPNF | NCS | 95.5 | 11 Aug 0330 - 0500 | 5145 | 900810 | LOST TIME ON NPS CEMENTING DUE TO SOFT CMT WHILE DRILL OUT CMT PLUG & FAILURE ON ZONAL ISOLATION AFTER CHECK CMT INTEGRITY, PLAN TO D/O CMT PLUG & SPOT ANOTHER CMT PLUG. | CMT | NA |  | 08/15/2022 | NBR-263S | 23.5 | QTIF-736
1658 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | NBR-654S | Hrs | HRDH-1150
1659 | FOT | PKP | 276.25 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/15/2022 | NBR-654S | 24 | HRDH-1150
1660 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | NBR-783S | Hrs | NJYN-93
1661 | FOT | RIG | 1.75 | 15 Aug 0115 - 0300 | 9656 | 900880 | LEAK ON WATER COOLING SYSTEM OF DRAWWORKS | RR | DWKS |  | 08/15/2022 | NBR-783S | 1.75 | NJYN-93
1662 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | NBR-987S | Hrs | JLMN-35
1663 | OTH | RIG | 165 | 09 Aug 0800 - 0500 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/15/2022 | NBR-987S | 24 | JLMN-35
1664 | FPMP | RIG | 2 | 15 Aug 1400 - 1600 | 13610 | 900841 | DUE TO STAND PIPE PRESSURE FLUCTUATIONS, TROUBLESHOOT MUD PUMPS, REPAIR LEAKS AT MUD PUMPS SUCTION LINE & PRE-CHARGE PUMP #2. | RR | MPMP |  | 08/15/2022 | PA-622S | 2 | UTMN-3600
1665 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | PA-622S | Hrs | UTMN-3600
1666 | LHFL | RIG | 1.5 | 15 Aug 0900 - 1030 | 13570 | 900839 | WASHED OUT TDS SAVER SUB | RR | HSYS |  | 08/15/2022 | PA-622S | 1.5 | UTMN-3600
1667 | FPMP | RIG | 2 | 15 Aug 1400 - 1600 | 13610 | 900841 | DUE TO STAND PIPE PRESSURE FLUCTUATIONS, TROUBLESHOOT MUD PUMPS, REPAIR LEAKS AT MUD PUMPS SUCTION LINE & PRE-CHARGE PUMP #2. | RR | MPMP |  | 08/15/2022 | PA-622S | 2 | UTMN-3600
1668 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | PN-9 | Hrs | MRJN-673
1669 | CFST | HCM | 32.25 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/15/2022 | PN-9 | 24 | MRJN-673
1670 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SINO-10 | Hrs | JLDI-38
1671 | FOT | OZT | 2 | 15 Aug 0100 - 0300 | 11030 | 900845 | LOSS DATA DUE TO ELECTORNIC MALFUNCTION IN LOAD CELL ( ON INJECTOR) . | TF | CTAC |  | 08/15/2022 | SINO-10 | 2 | JLDI-38
1672 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SINO-16 | Hrs | JLDI-850
1673 | EXPL | NWL | 9.5 | 15 Aug 1930 - 0500 | 0 | 900858 | WAIT ON NESR EXPLOSIVE. | WO | NA |  | 08/15/2022 | SINO-16 | 9.5 | JLDI-850
1674 | FOT | RIG | 8 | 15 Aug 1030 - 1830 | 4660 | 900894 | RIG HAVE NO CORRECT MEANS TO HANG BLOCKS/TDS DURING SLIP AND CUT OPERATION. CRANE IS TOO SMALL ONLY 55TON CANNOT SUPPORT BLOCKS AND TDS FOR SLIP AND CUT, NO MEANS TO HANG BLOCKS IN THE MAST, INEXPERIENCED CREW DONT | RR | DWKS |  | 08/15/2022 | SINO-29N | 8 | SFNY-2005
1675 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SINO-29N | Hrs | SFNY-2005
1676 | PCPF | ARM | 256 | 05 Aug 0500 - 0500 | 4660 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/15/2022 | SINO-29N | 16 | SFNY-2005
1677 | FOT | RIG | 8 | 15 Aug 1030 - 1830 | 4660 | 900894 | RIG HAVE NO CORRECT MEANS TO HANG BLOCKS/TDS DURING SLIP AND CUT OPERATION. CRANE IS TOO SMALL ONLY 55TON CANNOT SUPPORT BLOCKS AND TDS FOR SLIP AND CUT, NO MEANS TO HANG BLOCKS IN THE MAST, INEXPERIENCED CREW DONT | RR | DWKS |  | 08/15/2022 | SINO-29N | 8 | SFNY-2005
1678 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SINO-37L | Hrs | HWYH-639
1679 | CEDE | HCM | 16.5 | 14 Aug 2230 - 1500 | 7055 | 900821 | TROUBLE SHOUTING ON CEMENT SYLO AND BACH MIXER, SUCTION LINE BETWEEN CEMNT SYLO AND BACH MIXER PLUGGED. CEMENT WEIGHT COULD NOT BE RAISED MORE THAN 112 PCF DURING 2H 45 MIN. | JF | NA |  | 08/15/2022 | SINO-37L | 10 | HWYH-639
1680 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SINO-47 | Hrs | HWYH-1341
1681 | HERR | SCM | 5 | 15 Aug 1000 - 1500 | 3170 | 900844 | SLB CEMENT UNIT FAILED WHILE PUMPING CEMENT SLURRY. | CMT | NA |  | 08/15/2022 | SINO-47 | 5 | HWYH-1341
1682 | FOT | SDM | 2 | 15 Aug 0300 - 0500 | 5006 | 900895 | MWD LOST SIGNAL | BHA | MWD |  | 08/15/2022 | SP-167 | 2 | HRDH-218
1683 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SP-167 | Hrs | HRDH-218
1684 | ORDS | ARN | 132.5 | 10 Aug 0800 - 0300 | 7167 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/15/2022 | SP-167 | 22 | HRDH-218
1685 | FOT | SDM | 2 | 15 Aug 0300 - 0500 | 5006 | 900895 | MWD LOST SIGNAL | BHA | MWD |  | 08/15/2022 | SP-167 | 2 | HRDH-218
1686 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SP-229 | Hrs | JLDI-862
1687 | FOT | WBP | 13 | 14 Aug 1900 - 0800 | 5660 | 900771 | ATTEPMT TO SET WFD 9-5/8" TRIAL TEST BRIDGE PLUG (WSBP) WITHOUT SUCCESS. | TF | BP |  | 08/15/2022 | SP-229 | 3 | JLDI-862
1688 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SP-261 | Hrs | MHWZ-903
1689 | HERR | ITS | 28.25 | 14 Aug 0030 - 0445 | 1589 | 900823 | ITS CREW MEMBER FUNCTIONED SPIDER SLIPS WITH CASING SET IN SLIPS FOR UNKNOWN REASON, - LEAVING THE SWITCH IN THE OPEN POSITION. WHEN CASING JERKED SLIGHTLY WHILE BACKING OUT A JOINT OF CASING, THE SLIPS OPENED DROPPING 3 JINTS OF 18 5/8" CASING DOWN THE HOLE | TF | TTRQ |  | 08/15/2022 | SP-261 | 23.75 | MHWZ-903
1690 | 6378 |  | HT | E | 4186 | CORC | CON'T POOH 6-1/8" NOV CORING ASSY. RUN #1 TO SURFACE CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-L/D INNER BARREL,RECOVERED 100% OF CORED 33 FT.-L/D 6-1/8" CORING HEAD AND OUTER BARREL-CORE HEAD DULL : 1-1-WT-A-X-NO-TD-RUN RIG FLOOR BUG BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.-ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL. | 6378 |  | NOC | 08/15/2022 | SP-53L | CORE | HRDH-528
1691 | 6378 |  | RR | N |  | TDS | RIG SERVICE TDS | 6378 |  | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1692 | 6378 |  | HT | N | 4186 | BHA | HPJSM, M/U & RIH 8-1/2" MTR/MWD/GR DRLG ASSY TO 1567' | 6378 |  | BHI | 08/15/2022 | SP-53L | DRLG | HRDH-528
1693 | 6378 | 3536 | TI | N | 4186 | STDP | RIH 8-1/2" MTR/MWD/GR DRLG ASSY. TO 9-5/8" CSG SHOE @ 3536' | 6378 | 1567 | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1694 | 6378 | 6245 | ST | N |  | STDP | RIH 8-1/2" MTR/MWD/GR DRLG ASSY. FROM 9-5/8" CSG SHOE @ 3536' TO 6245' | 6378 | 3536 | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1695 | 6378 |  | CIRC | N |  | MPMP | RE-LOG AS PER GOC FROM 6245 FT TO 6345 FT WITH 100 FPH. | 6378 |  | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1696 | 6378 |  | CIRC | N |  | MPMP | SWEEP HOLE W/ 50 BBLS HI-VIS PILL & CIRCULATE BTMS UP. | 6378 |  | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1697 | 6378 | 6378 | RW | N |  | BIT | ENLARGE HOLE FROM 6-1/8" TO 8-1/2" W/ MTR /MWD GR DRILLING ASSY. F/6345' TO 7" LP @ 6378' W/ 80 PCF SALT POLYMER MUD W/ 100 % RETURNS.-START ENLARGING W/ CONTROL PARAMETER.-SWEEP HOLE W/ 50 BBLS HI-VIS PILL E-WASH UP & REAM DOWN EACH STD DRILLED.-NORMAL TRQ & DRAG W/ REASONABLE CUTTING SIZE & QUANTITY ON SHALE SHAKERS.-CONFIRMED 7" CP WITH GOC. | 6378 | 6345 | BHT | 08/15/2022 | SP-53L | DRLG | HRDH-528
1698 | 6378 |  | CIRC | N |  | MPMP | SWEEP THE HOLE W/ 50 BBLS HI VIS PILL & CIRCULAT HOLE CLEAN. | 6378 |  | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1699 | 6378 |  | SDR1 | N |  | NA | FLOW CHECK WELL STATIC OK. | 6378 |  | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1700 | 6378 | 5732 | ST | N |  | STDP | POOH ON ELEVATOR W/ 8-1/2" MTR/MWD/GR ASSY DRLG ASSY FROM 6345 FT TO 5732 FT FOR RUN 7" LINER . | 6378 | 6378 | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1701 | 6378 |  | SDR1 | N |  | NA | FLOW CHECK AFTER PULL 5 STDS WELL STATIC OK. | 6378 |  | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1702 | 6378 | 3536 | ST | N |  | STDP | CONTD POOH ON ELEVATOR W/ 8-1/2" MTR/MWD/GR ASSY DRLG ASSY FROM 5732 FT TO 9-5/8" CSG SHOE @ 3536 FT FOR 7" LINER .-MONITOR WELL ON TRIP TANK AND TRIP SHEET. | 6378 | 5732 | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1703 | 6378 |  | SDR1 | N |  | NA | FLOW CHECK AT 9-5/8" CSG SHOE - WELL STATIC OK. | 6378 |  | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1704 | 6378 | 1570 | ST | N |  | STDP | CONTD POOH W/ 8-1/2" MTR/MWD/GR ASSY DRLG ASSY FROM 9-5/8" CSG SHOE @ 3536 FT TO TOP OF BHA @ 1570 FT FOR RUN 7" LINER.-MONITOR WELL ON TRIP TANK AND TRIP SHEET. | 6378 | 3536 | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1705 | 6378 |  | SDR1 | N |  | NA | FLOW CHECK @ TOP BHA WELL STATIC. | 6378 |  | RIG | 08/15/2022 | SP-53L | DRLG | HRDH-528
1706 | 6378 |  | HT | N |  | BHA | CONTD POOH W/ 8-1/2" MTR/MWD/GR ASSY DRLG ASSY FROM TOP OF BHA @ 1567 FT TO SURFACE. FOR RUN 7" LINER.-BIT DULL GRADING : 1-1-WT-A-I-X-BT-TD.-MONITOR WELL ON TRIP TANK AND TRIP SHEET. | 6378 |  | BHI | 08/15/2022 | SP-53L | DRLG | HRDH-528
1707 | 6378 |  | RTRV | N |  | WBSH | M/U FMC RUNNING TOOL TO RETRIEVE 11" FMC WEAR BUSHING... IN PROGRESS @RT | 6378 |  | RIG | 08/15/2022 | SP-53L | WH | HRDH-528
1708 | 42.5 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 7.5 | 4186 | 13 Aug 0230 | 08/15/2022 | SP-53L | Type | HRDH-528
1709
1710
1711 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SSA-102 | Hrs | QTIF-693
1712 | FOT | WWD | 69.25 | 13 Aug 0545 - 0500 | 9715 | 900815 | WFD WHIPSTOCK DID NOT SET, BOLT WAS SHEARED, LOST WHIPSTOCK IN HOLE. | TF | WPSTK |  | 08/15/2022 | SSA-102 | 23.5 | QTIF-693
1713 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SSA-201 | Hrs | WDYH-13
1714 | HERR | FME | 2.5 | 15 Aug 0500 - 0730 | 0 | 900875 | FMC HAND INSTALLED VR PLUG INCORRECTLY, TROUBLESHOOT AND FOUND NPT PLUG NOT INSTALLED. INSTALL NPT PLUG AND RE-TEST, OK. | WH | WH |  | 08/15/2022 | SSA-201 | 2.5 | WDYH-13
1715 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SSA-202 | Hrs | QTIF-191
1716 | CEDE | NCS | 26.75 | 14 Aug 0215 - 0500 | 17794 | 900872 | LOST TIME ON NPS CEMENTING DUE TO VERY SOFT CMT WHILE DRILL OUT CMT PLUG . | JF | NA |  | 08/15/2022 | SSA-202 | 24 | QTIF-191
1717 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SSA-302 | Hrs | HRDH-2512
1718 | FOT | CRW | 22.5 | 15 Aug 0500 - 0500 | 11440 | 900878 | AFTER DISP. TEH STRG W/ WTR AND SET 9-5/8" LTTT PKR HAD CLEAR COMMUNICATION BETWEEN TBG SIDE & BACK SIDE. | BHA | WBCL |  | 08/15/2022 | SSA-302 | 22.5 | HRDH-2512
1719 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | SSA-5969 | Hrs | UTMN-3148
1720 | STBH | ARM | 192.75 | 06 Aug 1315 - 0500 | 2262 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) AND WORKING ON STUCK | STUK | BHA |  | 08/15/2022 | SSA-5969 | 14.5 | UTMN-3148
1721 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | T907 | Hrs | SRYN-2
1722 | FOT | GCD | 3 | 15 Aug 1145 - 1445 | 9400 | 900877 | UNABLE TO LATCH INTO UBHO SUB. | TF | MS |  | 08/15/2022 | T907 | 3 | SRYN-2
1723 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/15/2022 | T914 | Hrs | UTMN-415
1724 | ISEQ | RIG | 38.5 | 14 Aug 1430 - 0500 | 6120 | 900876 | GYRO UNABLE LATCH UBHO,POH WITH STRING, FOUND CAVED LAYERS OF CMT ABOVE UBHO. | DSF | DP |  | 08/15/2022 | T914 | 24 | UTMN-415
1725 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | 910TE | Hrs | DMMM-102
1726 | FOT | WWL | 36.5 | 15 Aug 1530 - 0500 | 18795 | 900842 | AFTER L/D WFD LOGGING TOOLS FOUND CALIPER LOG DATA NOT RECORDED DUE TO COMMUNICATION FAULT IN WFD CBG TOOL. | TF | WLT |  | 08/16/2022 | 910TE | 23.5 | DMMM-102
1727 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADC-14 | Hrs | HRDH-1312
1728 | FPMP | RIG | 1 | 16 Aug 2100 - 2200 | 11365 | 900938 | PUMP #1 FAILURE DUE TO LEAK OF JUMPER HOSE . | RR | MPMP |  | 08/16/2022 | ADC-14 | 1 | HRDH-1312
1729 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADC-35 | Hrs | MAQL-5
1730 | MATL | HTS | 43 | 15 Aug 0600 - 0100 | 0 | 900896 | WAITING ON HALL FRAC (GULF CRYON) TO DELIVER CO2 TO COMPLETE THE VOLUME REQUIRED TO EXECUTE THE JOB AS PER PROGRAM. | WO | NA |  | 08/16/2022 | ADC-35 | 20 | MAQL-5
1731 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADC-43L | Hrs | UTMN-3118
1732 | FRFM | TK3 | 113 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/16/2022 | ADC-43L | 23 | UTMN-3118
1733 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADC-48 | Hrs | HRDH-2316
1734 | FOT | NDD | 10.5 | 16 Aug 0800 - 1830 | 12892 | 900861 | OBSERVED FLOAT-NOV ( 95' ABOVE BIT) NOT WORKING, TROUBLE SHOOT: DIRECT CIRC, CHECK WHILE RIH, FLOAT NOT WORKING, POOH, CHECK FLOAT AT SURFACE, OBSERVED FLOAT MALFUNCTIONING, NOV REPLACE WITH NEW FLOAT SUB, BAKER REPLACE MWD RIH | TF | FV |  | 08/16/2022 | ADC-48 | 10.5 | HRDH-2316
1735 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADC-52 | Hrs | SDGM-1185
1736 | HINW | BAW | 431.25 | 29 Jul 1300 - 2345 | 12600 | 900261 | LOGGING TOOLS GOT STUCK MECHANICALLY DUE TO WASHOUTS WHILE PERFORMING THE REPEAT PASS | STUK | WLT |  | 08/16/2022 | ADC-52 | 18.75 | SDGM-1185
1737 | 12705 | 7828 | TI | N | 4185 | BHA | RIH W/ 3-1/4" CLEAN OUT ASSY ON 2-3/8" DP F/6,790 FT TO 7,828 FT.- BREAK CIRC EVERY 20 JTS .- P/U TOTAL 249 JTS OF 2-3/8" DP FROM RACK WHILE RIH. | 12705 | 6790 | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1738 | 12705 |  | HT | N | 4185 | PEL | R/D 2-3/8" HANDLING EQUIPMENT & R/U 4" HANDLING EQUIPMENT.- MONITOR WELL ON TRIP TANK. | 12705 |  | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1739 | 12705 | 12580 | TI | N | 4185 | BHA | RIH WITH 3-1/4" C/O BHA W/CONTROLLED SPEED ON 4" DP & 4" HWDP F/ 7,828 FT TO 12,580 FT (10 FT ABOVE (WIV / ISOL VALVE).- FILL UP EVERY 20 STANDS.- MONITOR WELL ON TRIP TANK | 12705 | 7828 | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1740 | 12705 |  | CIRC | N | 4185 | MPMP | PUMP 30 BBLS HVP & CIRCULATE HOLE CLEAN , | 12705 |  | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1741 | 12705 |  | CIRC | C | 4185 | MPMP | DISPLACE HOLE TO 80 PCF SOILD FREE BRINE.- CIRCULATE TILL BRINE IN/OUT 80 PCF.- FR 126 BPM, SPP 2,700 - 2,985 PSI. | 12705 |  | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1742 | 12705 |  | CIRC | N | 4185 | MPMP | EXTEND FLOW CHECK : WELL STATIC- PUMP SLUG. | 12705 |  | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1743 | 12705 | 7828 | TO | N | 4185 | BHA | POOH W/3-1/4" C/O BHA ON 4" DP F/12,580 FT TO TOP OF 2-3/8" DP @7,828 FT.- FLOW CHECK @ TOP OF BHA - WELL STATIC. | 12705 | 12580 | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1744 | 12705 |  | HT | N | 4185 | PEL | R/U 2-3/8" HANDLING EQUIPMENT ON RIG FLOOR.- MONITOR WELL ON TRIP TANK. | 12705 |  | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1745 | 12705 | 5944 | TO | N | 4185 | BHA | CONT POOH W/3-1/4" C/O BHA F/7,828 FT TO 5,944 FT...ON GOING ART.- L/D 60 / 249 JTS OF 2-3/8" DP.- MONITOR WELL ON TRIP TANK. | 12705 | 7828 | RIG | 08/16/2022 | ADC-53L | CT | HRDH-530
1746 | 96.5 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | C/O TRIP FOR 4-1/2" OBL & LWR COMPL. | 24 | 4185 | 12 Aug 0430 | 08/16/2022 | ADC-53L | Type | HRDH-530
1747
1748
1749 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADC-54L | Hrs | HRDH-584
1750 | CFFM | TK2 | 54.75 | 14 Aug 1800 - 0045 | 2325 | 900835 | WHILE RIH 9-5/8" CSG, HAD OBSTRUCTION @ 2325', WORKED ON OBSTRUCTION WITHOUT SUCCESS, DECIDED TO POOH & RUN REAMING TRIP. | BHS | NA |  | 08/16/2022 | ADC-54L | 19.75 | HRDH-584
1751 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADC-55L | Hrs | UTMN-3171
1752 | STBH | TK3 | 406 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/16/2022 | ADC-55L | 24 | UTMN-3171
1753 | 7019 | 6356 | LOG | E | 3965 | WLT | SLB WL PERFORM VIT & SAMPLING AS PER ARAMCO RMD. PERFORMED STICK TEST 3, 8, 15, 30 MIN PRIOR TO EACH VIT POINT.- MAX STATIONARY TIME: 4 HRS.- VIT POINT # 1 AT 6702 FT - 6715 FT - NO SEAL- VIT POINT # 2 AT 6514 FT - 6528 FT - (TWO SESSIONS) - OK.- SAMPLE POINT # 1 AT 6393 FT - ( 1 SESSION).- VIT POINT # 3 AT 6342 FT - 6356 FT (TWO SESSIONS OK)- MONITOR THE WELL WITH TRIP TANK | 7019 | 6698 | SWL | 08/16/2022 | ADC-57L | LOG | KRSN-175
1754 | 7019 | 6715 | TI | E | 3965 | STDP | RIH LOGGING RUN #4 TOOLS (MDT-VIT) FROM 6,385 FT TO 6,715 FT WITH CONTROLLED SPEED.- MONITOR WELL ON TRIP TANK. | 7019 | 6385 | RIG | 08/16/2022 | ADC-57L | LOG | KRSN-175
1755 | 7019 | 6700 | LOG | E | 3965 | WLT | SLB WL PERFORM VIT & SAMPLING AS PER ARAMCO RMD. PERFORMED STICK TEST 3, 8, 15, 30 MIN PRIOR TO EACH VIT POINT.- MAX STATIONARY TIME: 4 HRS.- REPEATED VIT # 1 6697 FT TO 6710 FT- VIT POINTS TAKEN 3 OUT OF 3 VIT POINTS.- SAMPLE POINT TAKEN 1 OUT OF 1 SAMPLE POINT.- MONITOR THE WELL WITH TRIP TANK. | 7019 | 6715 | SWL | 08/16/2022 | ADC-57L | LOG | KRSN-175
1756 | 7019 | 6815 | TI | E | 3965 | STDP | RIH LOGGING RUN #4 TOOLS (MDT-VIT) FROM 6715 FT TO 6,815 FT WITH CONTROLLED SPEED.- MONITOR WELL ON TRIP TANK.- MONITOR WELL ON TRIP TANK. | 7019 | 6715 | RIG | 08/16/2022 | ADC-57L | LOG | KRSN-175
1757 | 7019 |  | CIRC | E | 3965 | MPMP | CIRC HOLE CLEAN & HOMOGENIZE MUD. PRECAUTIONARY CLOSED ANNULAR BOP & CIRC THROUGH CHOKE FOR LAST 50 BBLS PRIOR TO BOTTOMS UP.- FR: 150 GPM; SPP: 420 PSI, - NO DYNAMIC LOSSES. | 7019 |  | RIG | 08/16/2022 | ADC-57L | LOG | KRSN-175
1758 | 7019 | 4792 | TO | E | 3965 | STDP | POOH LOGGING RUN # 4 ( MDT/VIT ) TLC IN OH FROM 6,815 FT TO 4,676 FT. FLOW CHECK-OK.- POOH SPEED =2 MIN/STD SLIP TO SLIP- MONITOR WELL ON TRIP TANK | 7019 | 6997 | RIG | 08/16/2022 | ADC-57L | LOG | KRSN-175
1759 | 7019 |  | OTH | E | 3965 | NA | HPJSM, UNLATCH AND RETRIEVE WIRELINE CABLE IN PROGRESS. - MONITOR WELL ON TRIP TANK. | 7019 |  | SWL | 08/16/2022 | ADC-57L | LOG | KRSN-175
1760 | 341.75 | OOS | Category | DOOS ID | FPFS | Out of Scope Summary | MDT LOGGING , FLUID SAMPLING AND RELATED OPERATIONS, C/O AND DISPACE MUD WITH OBM | 24 | 3965 | 02 Aug 0115 | 08/16/2022 | ADC-57L | Type | KRSN-175
1761
1762
1763 | 14929 |  | STIM | C | 4125 | CTU | PUMPED 686 BBLS OF POST-FLUSH AT FR 3 BPM, CIRC. PRESS 3100 PSI & WHP : ZERO | 14929 |  | SCT | 08/16/2022 | ADC-58L | STIM | ABHD-169
1764 | 14929 |  | OTH | C | 4125 | NA | POOH WITH SLB 2-3/8" COIL TBG FROM 11,308 FT TO SURCAE MEANWHILE RIG PUMPED 1000 BBL OF 77 PCF BRINE THROUGH CT KILL LINE. | 14929 |  | SCT | 08/16/2022 | ADC-58L | STIM | ABHD-169
1765 | 14929 |  | CIRC | C | 4125 | MPMP | RIG PUMPED 700 BBL OF 77 PCF BRINE WHEN CT AT SURFACE THROUGH CT KILL LINE. CLOSED GATE VALVE. | 14929 |  | RIG | 08/16/2022 | ADC-58L | STIM | ABHD-169
1766 | 14929 |  | OTH | C | 4125 | NA | CT PUMPED 20 BBLS OF SODA ASH PILL, DISPLACED WITH 80 BBLS OF FRESH WATER, BURGED CT WITH 700 GAL OF N2 AND WAIT FOR PRESSURE TO BLEED OFF.- PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH WH SOV'S USING TT. | 14929 |  | SCT | 08/16/2022 | ADC-58L | STIM | ABHD-169
1767 | 14929 |  | OTH | C | 4125 | NA | HELD PRE JOB SAFETY MEETING PRIOR TO R/D C/T INJECTOR AND EQUIPMENT.- PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH WH SOV'S USING TT. | 14929 |  | SCT | 08/16/2022 | ADC-58L | STIM | ABHD-169
1768 | 14929 |  | OTH | C | 4125 | NA | DISCONNECTED 4 1/16" 10K FLANGE BETWEEN C/T BOP & 4 1/16" 10K RISER, LIFTED C/T INJECTOR BY TDS, L/D CT BHA, L/D 4 1/16" RISER.- R/D INJECTOR HEAD, DISCONNECTED STRIPPER FROM BOTTOM OF INJECTOR HEAD, REMOVED 2 3/8" COIL TBG FROM INJECTOR HEAD & SPOOLEDON REEL, N/D CT BOP & RISER.- PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH WH SOV'S USING TT. | 14929 |  | SCT | 08/16/2022 | ADC-58L | STIM | ABHD-169
1769 | 14929 |  | OTH | C | 4125 | NA | N/U BELL NIPPLE & CONNECTED FLOW LINE. INSTALLED MOUSEHOLE.- PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH WH SOV'S USING TT. | 14929 |  | RIG | 08/16/2022 | ADC-58L | STIM | ABHD-169
1770 | 14929 |  | OTH | C |  | BOP | M/U MI JETTING TOOL. JET BOP AND WELLHEAD USING 77 PCF BRINE. L/D JETTING TOOL. | 14929 |  | RIG | 08/16/2022 | ADC-58L | BOP | ABHD-169
1771 | 14929 |  | SET | C |  | WBSH | INSTALLED 11" WEAR BUSHING.- PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH TT LINE. | 14929 |  | RIG | 08/16/2022 | ADC-58L | WH | ABHD-169
1772 | 14929 |  | PJSM | C |  | STRG | HPJSM PRIOR TO RIH 7" & 9 5/8" COMBINED C/O TOOLS.- PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM THROUGH TT. | 14929 |  | RIG | 08/16/2022 | ADC-58L | CT | ABHD-169
1773 | 129 | OOS | Category | DOOS ID | STIM | Out of Scope Summary | PERFORM ACID STIMULATION JOB FOR L-1 & L-0 | 22 | 4125 | 09 Aug 0030 | 08/16/2022 | ADC-58L | Type | ABHD-169
1774
1775
1776 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADC-60 | Hrs | ABSF-216
1777 | HERR | BAL | 72 | 14 Aug 0500 - 0500 | 11253 | 900849 | WHILE L/D ESP ASSY, SAFETY CLAMP SLIPPED FROM 2-7/8" BY-PASS TBG CAUSING DOWNHOLE STRING TO DROP IN HOLE. | JF | ESP |  | 08/16/2022 | ADC-60 | 24 | ABSF-216
1778 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADES-174 | Hrs | GHZL-72
1779 | XTTE | RAC | 38.5 | 14 Aug 0230 - 1700 | 11022 | 900874 | FAILURE OF RAC ITCO SPEAR AND CUTTER BHA TO RETRIEVE PBR. | TF | FISHT |  | 08/16/2022 | ADES-174 | 12 | GHZL-72
1780 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADES-798 | Hrs | HRDH-2302
1781 | FOT | SWL | 26 | 15 Aug 0830 - 1100 | 10733 | 900837 | SLB MDT TOOL PUMP FAILURE. | TF | WLT |  | 08/16/2022 | ADES-798 | 6 | HRDH-2302
1782 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADES-889 | Hrs | HRDH-2122
1783 | HERR | RAC | 74.5 | 12 Aug 1230 - 0500 | 10875 | 900795 | VERY FAST WORN OUT FOR THE PILOT MILL LEAD TO UNDER GAUGED MILL WENT INSIDE THE 7" LINER WITHOUT MILLING. | BHA | MILL |  | 08/16/2022 | ADES-889 | 24 | HRDH-2122
1784 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ADM-262 | Hrs | MRJN-122
1785 | FOT | EX1 | 16.5 | 15 Aug 1400 - 0630 | 0 | 900838 | SLICK LINE UNIT UNABLE TO START DUE TO MECHANICAL ISSUE | TF | SLICK |  | 08/16/2022 | ADM-262 | 1.5 | MRJN-122
1786 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | AOD-1 | Hrs | ZULF-694
1787 | STCT | ARM | 19.5 | 16 Aug 0930 - 0500 | 7478 | 900936 | WHILE RIH W/ 4-1/2" BAKER ICD SCREENS, HOLE BECAME PACKED OFF & STRING STUCK. | STUK | SCRN |  | 08/16/2022 | AOD-1 | 19.5 | ZULF-694
1788 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ARO-2003 | Hrs | MNIF-733
1789 | SRVC | ARN | 110 | 12 Aug 1500 - 0500 | 0 | 900789 | WAIT ON SEABED SURVEY. | WO | NA |  | 08/16/2022 | ARO-2003 | 24 | MNIF-733
1790 | HERR | BCT | 11.5 | 16 Aug 1200 - 2330 | 0 | 900913 | BAKER CT OPERATOR APPLY EXCESS TENSION AND RUN CT TOO FAST DURING PULL TEST. CT HIT RIG FLOOR AND BEND. OBSERVE BREAK IN LENGTH OF CT AFTER INCIDENT | JF | CTAC |  | 08/16/2022 | ARO-3004 | 11.5 | MRJN-2060
1791 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | ARO-3004 | Hrs | MRJN-2060
1792 | FOT | INW | 45 | 14 Aug 2000 - 0500 | 225 | 900770 | SETTING ROD WAS OBSERVED LEFT IN HOLE AFTER RETRIEVING TUBING ME PLUG SETTING TOOL ON SLICKLINE | TF | SLICK |  | 08/16/2022 | ARO-3004 | 12.5 | MRJN-2060
1793 | HERR | BCT | 11.5 | 16 Aug 1200 - 2330 | 0 | 900913 | BAKER CT OPERATOR APPLY EXCESS TENSION AND RUN CT TOO FAST DURING PULL TEST. CT HIT RIG FLOOR AND BEND. OBSERVE BREAK IN LENGTH OF CT AFTER INCIDENT | JF | CTAC |  | 08/16/2022 | ARO-3004 | 11.5 | MRJN-2060
1794 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | DPS-43 | Hrs | SDGM-1218
1795 | FRFM | ARM | 16.25 | 16 Aug 1200 - 0500 | 8806 | 900935 | OBSERVED TOTAL LOSS IN BLFR | LCIR | NA |  | 08/16/2022 | DPS-43 | 16.25 | SDGM-1218
1796 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | DPS-44 | Hrs | UTMN-2342
1797 | XTTE | ITS | 68.5 | 14 Aug 0800 - 0500 | 3220 | 900848 | RAN RTTS AND FOUND LEAK IN CASING DUE TO IMPROPER MAKE UP TORQUE | TF | CTRQ |  | 08/16/2022 | DPS-44 | 23.5 | UTMN-2342
1798 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | DPS-74 | Hrs | NJYN-33
1799 | FOT | HWP | 55.5 | 14 Aug 1200 - 0500 | 17096 | 900832 | PUMPING HEAD WOULD NOT LATCH TO WET CONNECT. POOH WIRELINE & DISCOVER PUMPING HEAD ALIGNMENT PIN MISSING. | TF | WLU | 900723 | 08/16/2022 | DPS-74 | 24 | NJYN-33
1800 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | MP-1 | Hrs | MRJN-78
1801 | FOT | NRT | 365.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/16/2022 | MP-1 | 24 | MRJN-78
1802 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | NA-393S | Hrs | SDGM-1134
1803 | FOT | OCS | 2 | 16 Aug 2130 - 2330 | 11735 | 900937 | WHILE POOH 4-1/2" EXISTING COMPLETION THE ODFJELL POWER TONG MALFUNCTIONED. IT'S SENSOR WAS NOT WORKING AND TONG WAS UNABLE TO BE OPERATED. ODFJELL REP ATTEMPTED TO RECTIFY THE ISSUE BUT NO SUCCESS. | TF | CRT |  | 08/16/2022 | NA-393S | 2 | SDGM-1134
1804 | FOT | RIG | 7.5 | 16 Aug 2030 - 0400 | 5757 | 900939 | BATCH MIX CMT OF KICK OFF PLUG, WHILE START PUMP SPACER OBSERVE CMT TANK SUCTION VALVE BROKEN AND COULD NOT TRANSFER SPACER TO CMT UNIT. DUMP CMT DUE TO LIMIT OF THICKENING TIME MEANWHILE WORKING TO FIX THE VALVE. | RR | CSYS |  | 08/16/2022 | NBR-263S | 7.5 | QTIF-736
1805 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | NBR-263S | Hrs | QTIF-736
1806 | CPNF | NCS | 112 | 11 Aug 0330 - 0500 | 5145 | 900810 | LOST TIME ON NPS CEMENTING DUE TO SOFT CMT WHILE DRILL OUT CMT PLUG & FAILURE ON ZONAL ISOLATION AFTER CHECK CMT INTEGRITY, PLAN TO D/O CMT PLUG & SPOT ANOTHER CMT PLUG. | CMT | NA |  | 08/16/2022 | NBR-263S | 16.5 | QTIF-736
1807 | FOT | RIG | 7.5 | 16 Aug 2030 - 0400 | 5757 | 900939 | BATCH MIX CMT OF KICK OFF PLUG, WHILE START PUMP SPACER OBSERVE CMT TANK SUCTION VALVE BROKEN AND COULD NOT TRANSFER SPACER TO CMT UNIT. DUMP CMT DUE TO LIMIT OF THICKENING TIME MEANWHILE WORKING TO FIX THE VALVE. | RR | CSYS |  | 08/16/2022 | NBR-263S | 7.5 | QTIF-736
1808 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | NBR-654S | Hrs | HRDH-1150
1809 | FOT | PKP | 300.25 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/16/2022 | NBR-654S | 24 | HRDH-1150
1810 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | NBR-987S | Hrs | JLMN-35
1811 | OTH | RIG | 189 | 09 Aug 0800 - 0500 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/16/2022 | NBR-987S | 24 | JLMN-35
1812 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | PN-9 | Hrs | MRJN-673
1813 | CFST | HCM | 56.25 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/16/2022 | PN-9 | 24 | MRJN-673
1814 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SINO-12L | Hrs | HWYH-220
1815 | FOT | RIG | 4 | 15 Aug 0400 - 0800 | 9947 | 900860 | DEFORMATION IN THE FIRST RAW OF DRILLING LINE IN DRAWWORKS | RR | DWKS |  | 08/16/2022 | SINO-12L | 3 | HWYH-220
1816 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SINO-16 | Hrs | JLDI-850
1817 | EXPL | NWL | 20 | 15 Aug 1930 - 1530 | 0 | 900858 | WAIT ON NESR EXPLOSIVE. | WO | NA |  | 08/16/2022 | SINO-16 | 10.5 | JLDI-850
1818 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SND-2004 | Hrs | BRRI-1148
1819 | FOT | SWT | 22 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP AT 6,351' INSIDE 7" LINER WHILE RIH W/ SLB DST#2 STRING. SET PKR & ATTEMPT TO TEST PKR AND OPEN TFTV WITHOUT SUCCESS. | TF | DSTT |  | 08/16/2022 | SND-2004 | 22 | BRRI-1148
1820 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SND-3001 | Hrs | SMNH-10
1821 | SRVC | SWL | 8 | 16 Aug 1900 - 0300 | 0 | 900940 | EXCESS TIME TO RIG UP SLB WIRELINE LUBRICATOR AND TOOLS. | WO | NA |  | 08/16/2022 | SND-3001 | 8 | SMNH-10
1822 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SP-121 | Hrs | BRRI-522
1823 | FOT | RIG | 2 | 16 Aug 1515 - 1715 | 11518 | 900932 | REPAIR MP#1 (SUCTION MODULE) & MP#3 (PISTON AND VALVE COVER), MEANWHILE CIRCULATE WITH MP#2 & RECIPROCATE THE PIPE. | RR | MPMP |  | 08/16/2022 | SP-121 | 2 | BRRI-522
1824 | FOT | SDM | 14 | 15 Aug 0300 - 2130 | 5006 | 900895 | MWD LOST SIGNAL | BHA | MWD |  | 08/16/2022 | SP-167 | 12 | HRDH-218
1825 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SP-167 | Hrs | HRDH-218
1826 | ORDS | ARN | 144.5 | 10 Aug 0800 - 0500 | 5008 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/16/2022 | SP-167 | 12 | HRDH-218
1827 | FOT | SDM | 14 | 15 Aug 0300 - 2130 | 5006 | 900895 | MWD LOST SIGNAL | BHA | MWD |  | 08/16/2022 | SP-167 | 12 | HRDH-218
1828 | HERR | RIG | 2 | 16 Aug 1315 - 1630 | 1589 | 900912 | ACCUMULATED TIME SPENT REPLACING DAMAGED CASING DUE TO CROSS THREADING. DRILLER NOT FOLLOWING INSTRUCTIONS | JF | CTRQ |  | 08/16/2022 | SP-261 | 2 | MHWZ-903
1829 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SP-261 | Hrs | MHWZ-903
1830 | HERR | ITS | 33.75 | 14 Aug 0030 - 1100 | 1589 | 900823 | ITS CREW MEMBER FUNCTIONED SPIDER SLIPS WITH CASING SET IN SLIPS FOR UNKNOWN REASON, - LEAVING THE SWITCH IN THE OPEN POSITION. WHEN CASING JERKED SLIGHTLY WHILE BACKING OUT A JOINT OF CASING, THE SLIPS OPENED DROPPING 3 JINTS OF 18 5/8" CASING DOWN THE HOLE | TF | TTRQ |  | 08/16/2022 | SP-261 | 5.25 | MHWZ-903
1831 | HERR | RIG | 2 | 16 Aug 1315 - 1630 | 1589 | 900912 | ACCUMULATED TIME SPENT REPLACING DAMAGED CASING DUE TO CROSS THREADING. DRILLER NOT FOLLOWING INSTRUCTIONS | JF | CTRQ |  | 08/16/2022 | SP-261 | 2 | MHWZ-903
1832 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SSA-102 | Hrs | QTIF-693
1833 | FOT | WWD | 92.75 | 13 Aug 0545 - 0500 | 9715 | 900815 | WFD WHIPSTOCK DID NOT SET, BOLT WAS SHEARED, LOST WHIPSTOCK IN HOLE. | TF | WPSTK |  | 08/16/2022 | SSA-102 | 23.5 | QTIF-693
1834 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SSA-202 | Hrs | QTIF-191
1835 | CEDE | NCS | 50.75 | 14 Aug 0215 - 0500 | 17794 | 900872 | LOST TIME ON NPS CEMENTING DUE TO VERY SOFT CMT WHILE DRILL OUT CMT PLUG . | JF | NA |  | 08/16/2022 | SSA-202 | 24 | QTIF-191
1836 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SSA-302 | Hrs | HRDH-2512
1837 | FOT | CRW | 24.75 | 14 Aug 0400 - 0615 | 11440 | 900878 | AFTER DISP. TEH STRG W/ WTR AND SET 9-5/8" LTTT PKR HAD CLEAR COMMUNICATION BETWEEN TBG SIDE & BACK SIDE. | BHA | WBCL |  | 08/16/2022 | SSA-302 | 1.25 | HRDH-2512
1838 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SSA-5969 | Hrs | UTMN-3148
1839 | STBH | ARM | 216.25 | 06 Aug 1315 - 0430 | 2262 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) | STUK | BHA |  | 08/16/2022 | SSA-5969 | 23.5 | UTMN-3148
1840 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | SSA-5970 | Hrs | UTMN-2340
1841 | FOT | RIG | 10.5 | 16 Aug 1700 - 0330 | 12352 | 900941 | SHEAR RAM LEAKED DURING BOP TEST, | BOP | RAMS |  | 08/16/2022 | SSA-5970 | 10.5 | UTMN-2340
1842 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | T914 | Hrs | UTMN-415
1843 | ISEQ | RIG | 60 | 14 Aug 1430 - 0230 | 6120 | 900876 | GYRO UNABLE LATCH UBHO,POH WITH STRING, FOUND CAVED LAYERS OF CMT ABOVE UBHO. | DSF | DP |  | 08/16/2022 | T914 | 21.5 | UTMN-415
1844 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | V140A | Hrs | ZULF-655
1845 | FOT | RIG | 8 | 16 Aug 1200 - 2000 | 0 | 900933 | RIG REPAIR. WAIT ON INSPECTION FOR MPI INSPECTOR TO INSPECT THE TDS OF PIPE HANDLER. | RR | TDS |  | 08/16/2022 | V140A | 8 | ZULF-655
1846 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/16/2022 | WCL-83 | Hrs | MRJN-835
1847 | WTHR | ARM | 1.75 | 16 Aug 1330 - 1515 | 0 | 900942 | STOPPED FLARING DUE TO LOW WIND SPEED AT 1 KNOT. | WON | NA |  | 08/16/2022 | WCL-83 | 1.75 | MRJN-835
1848 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | 910TE | Hrs | DMMM-102
1849 | FOT | WWL | 60.5 | 15 Aug 1530 - 0500 | 18795 | 900842 | AFTER L/D WFD LOGGING TOOLS FOUND CALIPER LOG DATA NOT RECORDED DUE TO COMMUNICATION FAULT IN WFD CBG TOOL. | TF | WLT |  | 08/17/2022 | 910TE | 24 | DMMM-102
1850 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ADC-29 | Hrs | NYYM-100
1851 | HERR | RIG | 4 | 17 Aug 0500 - 0900 | 3560 | 900955 | SUSPECTED DRIFT LOST INSIDE STRING. DRIFT OD: 2.375" | TF | FV |  | 08/17/2022 | ADC-29 | 4 | NYYM-100
1852 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ADC-43L | Hrs | UTMN-3118
1853 | FRFM | TK3 | 137 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/17/2022 | ADC-43L | 24 | UTMN-3118
1854 | 12705 | 0 | TO | N | 4185 | BHA | CONT POOH W/3-1/4" C/O BHA F 5,944 FT TO SURFACE.- L/D 249 JTS OF 2-3/8" DP.- MONITOR WELL ON TRIP TANK. | 12705 | 5944 | RIG | 08/17/2022 | ADC-53L | CT | HRDH-530
1855 | 12705 |  | HT | N | 4185 | PEL | R/D 2 3/8" HANDLING EQUIPMENT ON RIG FLOOR.- MONITOR WELL ON TRIP TANK. | 12705 |  | RIG | 08/17/2022 | ADC-53L | CT | HRDH-530
1856 | 12705 |  | RTRV | N |  | WBSH | RETRIEVED 11" WEAR BUSHING. | 12705 |  | RIG | 08/17/2022 | ADC-53L | WH | HRDH-530
1857 | 12705 |  | HT | N |  | BHA | HPJSM, P/U, M/U 7" CLEAN OUT ASSY & RIH TO 300 FT.- M/U: 6-1/8" RR TCI BIT (RK0350), BIT SUB, 7" SCRAPER, 1 X 4" HWDP, 7" POSIDRIFT, 5 X 4" HWDP, 4-3/4" JAR, 2 X 4" HWDP.- MONITOR WELL ON TRIP TANK | 12705 |  | RIG | 08/17/2022 | ADC-53L | CT | HRDH-530
1858 | 12705 |  | CIRC | N |  | MPMP | M/U AND RIH WITH BOP JETTING ASSY.- FLUSHED THE BOP AND WELLHEAD. L/D JETTING ASSY. | 12705 |  | RIG | 08/17/2022 | ADC-53L | CT | HRDH-530
1859 | 12705 | 4745 | TI | N |  | BHA | RIH W/ 7" CLEAN OUT ASSY F/300 FT TO 4,745 FT.- FILL STRING AND BREAK CIRC EVERY 20 STD.- CAREFULLY PASS THROUGH 7" TOL AT 1,614 FT.- MONITOR WELL ON TRIP TANK. | 12705 | 300 | RIG | 08/17/2022 | ADC-53L | CT | HRDH-530
1860 | 12705 |  | CIRC | N |  | MPMP | PERFORMED CLEAN OUT OPERATION.- SCRAPED UPPER COMPL PKR SETTING DEPTH F/ 4,741 FT T/4,928 FT (4,745 FT TO 4,932 FT BIT DEPTH). | 12705 |  | RIG | 08/17/2022 | ADC-53L | CT | HRDH-530
1861 | 12705 |  | CIRC | N |  | MPMP | SWEEP & CIRCULATE HOLE CLEAN W/30 BBLS HI-VIS PILL.- FLOW CHECK, WELL STATIC. | 12705 |  | RIG | 08/17/2022 | ADC-53L | CT | HRDH-530
1862 | 12705 | 2594 | TO | N |  | BHA | POOH W/ 7" CLEAN OUT ASSY F/4,932 FT TO 2,594 FT...ON GOING ART.- MONITOR WELL ON TRIP TANK. | 12705 | 4932 | RIG | 08/17/2022 | ADC-53L | CT | HRDH-530
1863 | 112.5 | OOS | Category | DOOS ID | OTHR | Out of Scope Summary | C/O TRIP FOR 4-1/2" OBL & LWR COMPL. | 16 | 4185 | 12 Aug 0430 | 08/17/2022 | ADC-53L | Type | HRDH-530
1864
1865
1866 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ADC-55L | Hrs | UTMN-3171
1867 | STBH | TK3 | 430 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/17/2022 | ADC-55L | 24 | UTMN-3171
1868 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ADC-56L | Hrs | UTMN-3069
1869 | FOT | TSC | 1.5 | 17 Aug 1830 - 2000 | 1965 | 900988 | TROUBLESHOOT TESCO HYDRAULIC POWER UNIT. | TF | CTRQ |  | 08/17/2022 | ADC-56L | 1.5 | UTMN-3069
1870 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ADC-60 | Hrs | ABSF-216
1871 | FOT | BAL | 166.5 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/17/2022 | ADC-60 | 24 | ABSF-216
1872 | HERR | BCR | 2 | 17 Aug 1300 - 1500 | 932 | 900916 | INCOMPETENT CSG CREW, REPLACE DAMAGE JOINTS & M/U AND BREAK OUT JOINT TO OBTAIN ACCEPTABLE TORQUE GRAPH. | TF | TTRQ |  | 08/17/2022 | ADES-798 | 2 | HRDH-2302
1873 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ADES-798 | Hrs | HRDH-2302
1874 | FOT | BCR | 3 | 17 Aug 1000 - 1730 | 124 | 900863 | BAKER CSG TONG STUCK AROUND PIPE & REPLACE FAILED JAM UNIT. | TF | CTRQ |  | 08/17/2022 | ADES-798 | 3 | HRDH-2302
1875 | HERR | BCR | 2 | 17 Aug 1300 - 1500 | 932 | 900916 | INCOMPETENT CSG CREW, REPLACE DAMAGE JOINTS & M/U AND BREAK OUT JOINT TO OBTAIN ACCEPTABLE TORQUE GRAPH. | TF | TTRQ |  | 08/17/2022 | ADES-798 | 2 | HRDH-2302
1876 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ADES-889 | Hrs | HRDH-2122
1877 | HERR | RAC | 134 | 12 Aug 0500 - 0500 | 10875 | 900795 | VERY FAST WORN OUT FOR THE PILOT MILL LEAD TO UNDER GAUGED MILL WENT INSIDE THE 7" LINER WITHOUT MILLING. | BHA | MILL |  | 08/17/2022 | ADES-889 | 24 | HRDH-2122
1878 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | AOD-1 | Hrs | ZULF-694
1879 | STCT | ARM | 43.5 | 16 Aug 0930 - 0500 | 7478 | 900936 | WHILE RIH W/ 4-1/2" BAKER ICD SCREENS, HOLE BECAME PACKED OFF & STRING STUCK. | STUK | SCRN |  | 08/17/2022 | AOD-1 | 24 | ZULF-694
1880 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ARO-2003 | Hrs | MNIF-733
1881 | SRVC | ARN | 134 | 12 Aug 1500 - 0500 | 0 | 900789 | WAIT ON SEABED SURVEY. | WO | NA |  | 08/17/2022 | ARO-2003 | 24 | MNIF-733
1882 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ARO-3004 | Hrs | MRJN-2060
1883 | FOT | INW | 69 | 14 Aug 2000 - 0500 | 225 | 900770 | SETTING ROD WAS OBSERVED LEFT IN HOLE AFTER RETRIEVING TUBING ME PLUG SETTING TOOL ON SLICKLINE | TF | SLICK |  | 08/17/2022 | ARO-3004 | 24 | MRJN-2060
1884 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ARO-4001 | Hrs | MRJN-532
1885 | FOT | RIG | 3 | 17 Aug 2300 - 0200 | 6871 | 900987 | WHILE PREPARING HALL MIX FLUID AND SPACER, OBSERVED ONE ISOLATION VALVE BETWEEN MUD PITS LEAKING, CHANGE IT SAME. | RR | CSYS |  | 08/17/2022 | ARO-4001 | 3 | MRJN-532
1886 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | DPS-44 | Hrs | UTMN-2342
1887 | XTTE | ITS | 92.5 | 14 Aug 0800 - 0500 | 3220 | 900848 | RAN RTTS AND FOUND LEAK IN CASING DUE TO IMPROPER MAKE UP TORQUE | TF | CTRQ |  | 08/17/2022 | DPS-44 | 24 | UTMN-2342
1888 | FOT | HWP | 7 | 17 Aug 2200 - 0500 | 17410 | 900989 | HALLIBURTON NMR (MRIL) LOGGING TOOL FAILURE. | TF | WLT | 900832 | 08/17/2022 | DPS-74 | 7 | NJYN-33
1889 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | DPS-74 | Hrs | NJYN-33
1890 | FOT | HWP | 77.75 | 14 Aug 1200 - 2045 | 17096 | 900832 | PUMPING HEAD WOULD NOT LATCH TO WET CONNECT. POOH WIRELINE & DISCOVER PUMPING HEAD ALIGNMENT PIN MISSING. | TF | WLU | 900723 | 08/17/2022 | DPS-74 | 15.25 | NJYN-33
1891 | FOT | HWP | 7 | 17 Aug 2200 - 0500 | 17410 | 900989 | HALLIBURTON NMR (MRIL) LOGGING TOOL FAILURE. | TF | WLT | 900832 | 08/17/2022 | DPS-74 | 7 | NJYN-33
1892 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | ED-85A | Hrs | ZULF-2063
1893 | XTRI | RIG | .75 | 17 Aug 1445 - 1530 | 15682 | 900954 | EXCESSIVE TIME TO CHANGE OUT HANDLING EQUIPMENT | JF | NA |  | 08/17/2022 | ED-85A | .75 | ZULF-2063
1894 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | JACK-203 | Hrs | HZEM-849
1895 | CEDE | NCS | 2.5 | 17 Aug 1830 - 2100 | 2831 | 900985 | FAIL TO MIX AND MAINTAIN 118 PCF DUE TO SAILO COMPRESSORS NOT WORKING. | CMT | NA |  | 08/17/2022 | JACK-203 | 2.5 | HZEM-849
1896 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | MP-1 | Hrs | MRJN-78
1897 | FOT | NRT | 389.5 | 31 Jul 0245 - 0500 | 9345 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/17/2022 | MP-1 | 24 | MRJN-78
1898 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | NBR-16S | Hrs | HMYM-433112
1899 | DRIG | RIG | 1 | 17 Aug 0715 - 1745 | 7140 | 900917 | EXCESSIVE TIME TO TRIP OUT DUE TO RIG MISALINGMNET | RR | RSYS |  | 08/17/2022 | NBR-16S | 1 | HMYM-433112
1900 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | NBR-263S | Hrs | QTIF-736
1901 | CPNF | NCS | 136 | 11 Aug 0330 - 0500 | 5145 | 900810 | LOST TIME ON NPS CEMENTING DUE TO SOFT CMT WHILE DRILL OUT CMT PLUG & FAILURE ON ZONAL ISOLATION AFTER CHECK CMT INTEGRITY, PLAN TO D/O CMT PLUG & SPOT ANOTHER CMT PLUG. | CMT | NA |  | 08/17/2022 | NBR-263S | 24 | QTIF-736
1902 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | NBR-654S | Hrs | HRDH-1150
1903 | FOT | PKP | 324.25 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/17/2022 | NBR-654S | 24 | HRDH-1150
1904 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | NBR-987S | Hrs | JLMN-35
1905 | OTH | RIG | 213 | 09 Aug 0800 - 0500 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/17/2022 | NBR-987S | 24 | JLMN-35
1906 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | PA-70S | Hrs | HRDH-1939
1907 | FOT | RIG | 16 | 17 Aug 1300 - 0500 | 5418 | 900915 | TDS OVERHEATED & OBSERVE SMOKE FROM SERVICE LOOP. ACTIVATE TDS ESD & COOL DOWN SAME. TROUBLE SHOOTING TDS, FOUND SERVICE LOOP DAMAGED. POOH TO CSG SHOE & CHANGE OUT SERVICE LOOP. | RR | TDS |  | 08/17/2022 | PA-70S | 16 | HRDH-1939
1908 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | PN-9 | Hrs | MRJN-673
1909 | CFST | HCM | 80.25 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/17/2022 | PN-9 | 24 | MRJN-673
1910 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SIN30L | Hrs | KHRS-1716
1911 | FOT | RIG | 5.25 | 17 Aug 2345 - 0500 | 2100 | 900990 | POOH W/ 17" ROTARY DRLG BHA OBSEREVED LOST IN THE HOLE FROM NEAR BIT REAMER: 1 ROLLER CONE AND RODE AND ONE RODE SECURING BLOCK | BHA | RM |  | 08/17/2022 | SIN30L | 5.25 | KHRS-1716
1912 | 10922 |  | HT | N |  | BHA | FIN'D POOH W/ HLS MST & L/D CMT STINGER. | 10922 |  | RIG | 08/17/2022 | SINO-1L | PA | ABJF-260
1913 | 10922 |  | NU | N |  | SNIP | N/D FLOW LINE , BELL NIPPLE & N/U 9 5-8" SHOOTING NIPPLE. | 10922 |  | RIG | 08/17/2022 | SINO-1L | LOG | ABJF-260
1914 | 10922 |  | OTH | E |  | NA | HPJSM. R/U HES WL PCE, WL TOOLS AND SHEAVES. P/T W/L BOP TO 1000 PSI - OK. | 10922 |  | HWP | 08/17/2022 | SINO-1L | LOG | ABJF-260
1915 | 10922 | 0 | LOG | E |  | WLT | HES W/L RIH WITH MULTI-CASING CORROSION TO 4480'(20 FT ABOVE EZSV-CR).- LOG UP AND RECORD MAIN PASS F/ 4480' TO SURFACE .- RECORDED REPEAT PASS FROM 4400' TO 4200' AND POOH TO SURFACE. | 10922 | 4480 | HWP | 08/17/2022 | SINO-1L | LOG | ABJF-260
1916 | 10922 |  | OTH | E |  | NA | L/D W/L TOOL STRING, R/D W/L SHEAVES & BOP. | 10922 |  | HWP | 08/17/2022 | SINO-1L | LOG | ABJF-260
1917 | 10922 |  | ND | N |  | SNIP | N/D 9-5/8" SHOOTING NIPPLE , N/U BELL NIPPLE & FLOW LINE. | 10922 |  | RIG | 08/17/2022 | SINO-1L | LOG | ABJF-260
1918 | 10922 |  | OTH | N |  | NA | P/T 13-3/8" X 9-5/8" CCA TO 500 PSI / 10 MINS, PRESSURE DROPPED TO 200 PSI ,THEN HOLD. P/T 9-5/8" SEALS & SLIPS TO 1,500 PSI FOR 10 MINS, HOLD. | 10922 |  | IWS | 08/17/2022 | SINO-1L | WH | ABJF-260
1919 | 10922 |  | OTH | N |  | NA | HPJSM, DIG OUT CELLAR 6 FT BELLOW LANDING BASE. | 10922 |  | IWS | 08/17/2022 | SINO-1L | WH | ABJF-260
1920 | 10922 |  | OTH | N |  | NA | PERFORMED WELLHEAD WORK AS FOLLOWS: - AL MANSOURI UT INSPECTED EXPOSED 18-5/8" CSG & 13-5/8" 3M LANDING BASE, ALL OK.- FOUND 18-5/8" CSG SEAL WELDED WITH LANDING BASE DONUT PLATE. | 10922 |  | IWS | 08/17/2022 | SINO-1L | WH | ABJF-260
1921 | 10922 |  | OTH | N | 4225 | NA | CONT. PERFORM WELL HEAD WORK AS FOLLOWS: (OOS)- HOT-HED WELD 1" NIPPLE IN 18-5/8" CSG & AL-MANSOORI PERFORM MPI INSPECTION ON WELDING, THEN INSTALL 1" NIDDLE VLV, P/T SAME T/ 1000 PSI,HOLD.- BOOTS & COOTS PERFORM HOT HOT TAPPING ON-18-5/8" CSG BY OPEN1/2" HOLE IN 18-5/8" CSG THRU THE VLV.-MONITOR 13-3/8" X 9 5/8" CCA , NO PRESS., NO GAS READING. | 10922 |  | IWS | 08/17/2022 | SINO-1L | WH | ABJF-260
1922 | 10922 |  | OTH | N |  | NA | CONT. PERFORM WELL HEAD WORK AS FOLLOWS: OPENED TWO WINDOWS IN 18-5/8" CSG AND AL MANSOURI UT INSPECT 13-3/8" CSG , OK.- FILLED 18-5/8" X 13-5/8" ANNULUS W/ CMT & RE-WELD WINDOWS AGAIN.-WAIT FOR WELDING FOR 30 MIN. TO COOL DOWN.- AL-MANSOORI PERFORM MPI INSPECTION FOR 18-5/8" CSG WINDOW WELDING,OK.- AL-MANSOORI PERFORM UT INSPECTION FOR 18-5/8" CONDUCTOR AND LANDING BASE, FOUND SAME IN GOOD CONDITION.-FILL CELLAR W/ SWEET SAND. | 10922 |  | IWS | 08/17/2022 | SINO-1L | WH | ABJF-260
1923 | 1 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | WELL HEAD WORK. | 1 | 4225 | 17 Aug 0245 | 08/17/2022 | SINO-1L | Type | ABJF-260
1924
1925
1926 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SINO-29N | Hrs | SFNY-2005
1927 | PCPF | ARM | 304 | 05 Aug 0500 - 0500 | 4660 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/17/2022 | SINO-29N | 24 | SFNY-2005
1928 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SND-2001 | Hrs | HWYH-1229
1929 | WOTO | GOC | 1 | 17 Aug 1345 - 1445 | 45 | 900865 | FIX ALGAITH POWER UNIT. | WO | NA |  | 08/17/2022 | SND-2001 | 1 | HWYH-1229
1930 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SND-2002 | Hrs | WAQR-23
1931 | HERR | NCS | 24.5 | 16 Aug 0430 - 0500 | 15883 | 900943 | LOST RETURNS WHILE REVERSING OUT AFTER SPOTTED 1ST CEMENT PLUG. NPS REQUESTED VERY HIGH DENSITY AND VISCOSITY FOR THE HVP WHICH CREATED HIGH BACK PRESSURE WHILE REVERSE CIRCULATE. | CMT | NA |  | 08/17/2022 | SND-2002 | 24 | WAQR-23
1932 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SND-2004 | Hrs | BRRI-1148
1933 | FOT | SWT | 45.5 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP AT 6,351' INSIDE 7" LINER WHILE RIH W/ SLB DST#2 STRING. SET PKR & ATTEMPT TO TEST PKR AND OPEN TFTV WITHOUT SUCCESS. | TF | DSTT |  | 08/17/2022 | SND-2004 | 23.5 | BRRI-1148
1934 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SND-3001 | Hrs | SMNH-10
1935 | FOT | SWL | 17.75 | 17 Aug 0500 - 2245 | 0 | 900862 | WHILE ATTEMPTING TO RIH WITH WIRE LINE, UNABLE TO MOVE WIRELINE UP OR DOWN. | TF | WLT |  | 08/17/2022 | SND-3001 | 17.75 | SMNH-10
1936 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SP-121 | Hrs | BRRI-522
1937 | FPMP | RIG | 2 | 17 Aug 0045 - 0245 | 13819 | 900983 | REPAIR: MP #2 (ROTOR BROSH HOLDER ON DC MOTOR), MP#1 (PISTON LEACK) & MP#3 (PISTON LEACK), MEANWHILE CIRC. AND RECIPROCATE STRING | RR | MPMP |  | 08/17/2022 | SP-121 | 2 | BRRI-522
1938 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SP-125 | Hrs | ANDR-20
1939 | FOT | BHI | 3 | 17 Aug 0200 - 0500 | 8613 | 900991 | LOST BAKER MWD SIGNAL | BHA | LWD |  | 08/17/2022 | SP-125 | 3 | ANDR-20
1940 | FOT | SDM | 19.5 | 15 Aug 0300 - 2230 | 5006 | 900895 | MWD LOST SIGNAL | BHA | MWD |  | 08/17/2022 | SP-167 | 5.5 | HRDH-218
1941 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SP-167 | Hrs | HRDH-218
1942 | ORDS | ARN | 163 | 10 Aug 0800 - 0500 | 5008 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/17/2022 | SP-167 | 18.5 | HRDH-218
1943 | FOT | SDM | 19.5 | 15 Aug 0300 - 2230 | 5006 | 900895 | MWD LOST SIGNAL | BHA | MWD |  | 08/17/2022 | SP-167 | 5.5 | HRDH-218
1944 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SSA-102 | Hrs | QTIF-693
1945 | FOT | WWD | 105.75 | 13 Aug 0545 - 1830 | 9715 | 900815 | WFD WHIPSTOCK DID NOT SET, BOLT WAS SHEARED, LOST WHIPSTOCK IN HOLE. | TF | WPSTK |  | 08/17/2022 | SSA-102 | 13 | QTIF-693
1946 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SSA-201 | Hrs | WDYH-13
1947 | HERR | BC | 5.5 | 16 Aug 0145 - 0815 | 10000 | 900972 | MANSOORI S/L RIH W/ 3.795'' DRIFT, STOPPED @ 803', POH & L/D SUSPECTED JT, FOUND CREW DROPPED SLIPS WITHOUT MAKE SURE IT WAS CENTRED BEFORE PUTTING FULL STRG WT WHICH CAUSED COLLAPSE OF TBG JT. | JF | TBG |  | 08/17/2022 | SSA-201 | 2.25 | WDYH-13
1948 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SSA-202 | Hrs | QTIF-191
1949 | CEDE | NCS | 72.25 | 14 Aug 0215 - 0230 | 17794 | 900872 | LOST TIME ON NPS CEMENTING DUE TO VERY SOFT CMT WHILE DRILL OUT CMT PLUG . | JF | NA |  | 08/17/2022 | SSA-202 | 21.5 | QTIF-191
1950 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | SSA-5969 | Hrs | UTMN-3148
1951 | STBH | ARM | 239.75 | 06 Aug 1315 - 0500 | 2262 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) | STUK | BHA |  | 08/17/2022 | SSA-5969 | 23.5 | UTMN-3148
1952 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | T914 | Hrs | UTMN-415
1953 | ISEQ | RIG | 80.5 | 14 Aug 1430 - 0500 | 6120 | 900876 | GYRO UNABLE LATCH UBHO,POH WITH STRING, FOUND CAVED LAYERS OF CMT ABOVE UBHO. | DSF | DP |  | 08/17/2022 | T914 | 20.5 | UTMN-415
1954 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/17/2022 | V140A | Hrs | ZULF-655
1955 | LHFL | RIG | 2.75 | 17 Aug 0115 - 0400 | 1035 | 900984 | OBSERVED LEAKAGE IN TOP DRIVE HYDRAULIC LINES. | RR | HSYS |  | 08/17/2022 | V140A | 2.75 | ZULF-655
1956 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | 910TE | Hrs | DMMM-102
1957 | FOT | WWL | 79.5 | 15 Aug 1530 - 0000 | 18795 | 900842 | AFTER L/D WFD LOGGING TOOLS FOUND CALIPER LOG DATA NOT RECORDED DUE TO COMMUNICATION FAULT IN WFD CBG TOOL. | TF | WLT |  | 08/18/2022 | 910TE | 19 | DMMM-102
1958 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ADC-43L | Hrs | UTMN-3118
1959 | FRFM | TK3 | 160.5 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/18/2022 | ADC-43L | 23.5 | UTMN-3118
1960 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ADC-51 | Hrs | SDGM-1225
1961 | FOT | SPS | 4 | 18 Aug 1330 - 1730 | 100 | 901035 | WHILE SHALLOW TEST SPERRY DIR. TOOLS NO COMMUNICATION ESTABLISH BETWEEN DIR. TOOLS. | BHA | MWD |  | 08/18/2022 | ADC-51 | 4 | SDGM-1225
1962 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ADC-55L | Hrs | UTMN-3171
1963 | STBH | TK3 | 454 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/18/2022 | ADC-55L | 24 | UTMN-3171
1964 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ADC-60 | Hrs | ABSF-216
1965 | FOT | BAL | 187.75 | 08 Aug 0500 - 0215 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/18/2022 | ADC-60 | 21.25 | ABSF-216
1966 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ADES-889 | Hrs | HRDH-2122
1967 | HERR | RAC | 158 | 12 Aug 0500 - 0500 | 10875 | 900795 | VERY FAST WORN OUT FOR THE PILOT MILL LEAD TO UNDER GAUGED MILL WENT INSIDE THE 7" LINER WITHOUT MILLING. | BHA | MILL |  | 08/18/2022 | ADES-889 | 24 | HRDH-2122
1968 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ADM-510 | Hrs | ABSF-225
1969 | FOT | GOC | 2 | 17 Aug 0415 - 0615 | 1500 | 900992 | EXCESIVE TIME TO RUN 7" LINER DUE TO POWER TONG MALFUNCTION, CHANGE POWER TONG WITH BACKUP ONE | TF | TTRQ |  | 08/18/2022 | ADM-510 | 1.25 | ABSF-225
1970 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | AOD-1 | Hrs | ZULF-694
1971 | STCT | ARM | 64.25 | 16 Aug 0930 - 0145 | 7478 | 900936 | WHILE RIH W/ 4-1/2" BAKER ICD SCREENS, HOLE BECAME PACKED OFF & STRING STUCK. | STUK | SCRN |  | 08/18/2022 | AOD-1 | 20.75 | ZULF-694
1972 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | AOD-111 | Hrs | MRJN-725
1973 | FOT | FME | 1 | 18 Aug 0045 - 0145 | 13720 | 901041 | TRIED TO RETRIEVE 11" TBG SPOOL WEAR BUSHING SEVERAL TIMES WITHOUT SUCCESS. | WH | WBSH |  | 08/18/2022 | AOD-111 | 1 | MRJN-725
1974 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ARO-2003 | Hrs | MNIF-733
1975 | WOPF | AP2 | 72 | 16 Aug 0500 - 0500 | 0 | 900956 | WAIT ON FIELD SERVICE TO INSTALL ISOLATION PLUGS. | WO | NA |  | 08/18/2022 | ARO-2003 | 24 | MNIF-733
1976 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ARO-3002 | Hrs | MRJN-813
1977 | WTHR | ARM | 13 | 18 Aug 0500 - 1800 | 8852 | 900963 | BHI UNABLE TO CONTINUE MILLING OPERATION DUE TO LOW WIND SPEED. | WON | NA |  | 08/18/2022 | ARO-3002 | 13 | MRJN-813
1978 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | DPS-44 | Hrs | UTMN-2342
1979 | XTTE | ITS | 116.5 | 14 Aug 0800 - 0500 | 3220 | 900848 | AFTER COMPLETING THE FIRST STAGE CEMENT JOB FOR 18-5/8" CASING, ATTEMPTED TO INFLATE AND OPEN DV WITHOUT CLEAR INDICATION, ATTEMPTED TO PERFORM TOP JOB AND PUMPED ONLY 7 BBLS BEFORE GETTING CMT TO SURFACE. CLEAN OUT DV AND GET COMPLETE LOSSES, SUSPECT CASING LEAK. RAN 18-5/8" RTTS AND CONFIRM CASING LEAK AT DEPTH 3220' BETWEEN JOINTS NO. 78 & 79. | TF | CTRQ |  | 08/18/2022 | DPS-44 | 24 | UTMN-2342
1980 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | DPS-45 | Hrs | UTMN-2331
1981 | FOT | SDM | 22.75 | 17 Aug 1930 - 0500 | 16912 | 901034 | SLB MWD LOST SIGNAL. | BHA | MWD |  | 08/18/2022 | DPS-45 | 13.25 | UTMN-2331
1982 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | DPS-74 | Hrs | NJYN-33
1983 | FOT | HWP | 14.5 | 17 Aug 2200 - 1230 | 17410 | 900989 | HALLIBURTON NMR (MRIL) LOGGING TOOL FAILURE. | TF | WLT | 900832 | 08/18/2022 | DPS-74 | 7.5 | NJYN-33
1984 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ENS-108 | Hrs | ZULF-2015
1985 | FOT | RIG | 18.25 | 18 Aug 1045 - 0500 | 7186 | 901033 | OBSERVED FLOW LINE BETWEEN SHAKER AND PIT ROOM PLUGGED. | RR | FL |  | 08/18/2022 | ENS-108 | 18.25 | ZULF-2015
1986 | HERR | RIG | 3 | 18 Aug 0730 - 1030 | 0 | 901036 | RIG CREW DAMAGED 5 STUDS WHILE LOWERING DIVERTER, REPLACED / REDRESSED DAMAGED STUDS. | JF | DVRT |  | 08/18/2022 | ENS-141 | 3 | MRJN-3022
1987 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | ENS-141 | Hrs | MRJN-3022
1988 | FOT | RIG | 4 | 18 Aug 0030 - 0430 | 0 | 900964 | ATTEMPTED MANY TRIALS TO INSTALL OVERSHOT AND 500 KFDJ BIG BORE DIVERTER IN PLACE NO SUCCESS. | BOP | DVRT |  | 08/18/2022 | ENS-141 | 4 | MRJN-3022
1989 | HERR | RIG | 3 | 18 Aug 1930 - 2230 | 0 | 900966 | EXCESSIVE TIME N/U 30" DIVERTER AND CONNCETING HYDRAULIC HOSSES. | JF | DVRT |  | 08/18/2022 | ENS-141 | 3 | MRJN-3022
1990 | HERR | RIG | 3 | 18 Aug 0730 - 1030 | 0 | 901036 | RIG CREW DAMAGED 5 STUDS WHILE LOWERING DIVERTER, REPLACED / REDRESSED DAMAGED STUDS. | JF | DVRT |  | 08/18/2022 | ENS-141 | 3 | MRJN-3022
1991 | FOT | RIG | 7.75 | 18 Aug 1645 - 0030 | 3000 | 901042 | RIG REPAIR; DRAWWORK HI CLUTCH BLADDER LEAKING AIR, CHANGE IT OUT WITH NEW BLADDER. | RR | DWKS | 900303 | 08/18/2022 | MP-1 | 7.75 | MRJN-78
1992 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | MP-1 | Hrs | MRJN-78
1993 | FOT | NRT | 413.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/18/2022 | MP-1 | 16.25 | MRJN-78
1994 | FOT | RIG | 7.75 | 18 Aug 1645 - 0030 | 3000 | 901042 | RIG REPAIR; DRAWWORK HI CLUTCH BLADDER LEAKING AIR, CHANGE IT OUT WITH NEW BLADDER. | RR | DWKS | 900303 | 08/18/2022 | MP-1 | 7.75 | MRJN-78
1995 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | NBR-16S | Hrs | HMYM-433112
1996 | FOT | RIG | 7 | 18 Aug 2000 - 0300 | 7140 | 900960 | EXCESSIVE TIME TO REMOVE STUCK WASH PIPE. | RR | TDS |  | 08/18/2022 | NBR-16S | 7 | HMYM-433112
1997 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | NBR-263S | Hrs | QTIF-736
1998 | CPNF | NCS | 144 | 11 Aug 0330 - 1300 | 5145 | 900810 | LOST TIME ON NPS CEMENTING DUE TO SOFT CMT WHILE DRILL OUT CMT PLUG & FAILURE ON ZONAL ISOLATION AFTER CHECK CMT INTEGRITY, PLAN TO D/O CMT PLUG & SPOT ANOTHER CMT PLUG. | CMT | NA |  | 08/18/2022 | NBR-263S | 8 | QTIF-736
1999 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | NBR-654S | Hrs | HRDH-1150
2000 | FOT | PKP | 348.25 | 02 Aug 1915 - 0500 | 12809 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/18/2022 | NBR-654S | 24 | HRDH-1150
2001 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | NBR-987S | Hrs | JLMN-35
2002 | OTH | RIG | 229 | 09 Aug 0800 - 2100 | 264 | 900629 | DAMAGED TDS DUE TO PACKOFF WHILE DRILLING CEMENT | UPRA | NA |  | 08/18/2022 | NBR-987S | 16 | JLMN-35
2003 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | PA-529S | Hrs | SHYB-523
2004 | DSFT | BC | 26.25 | 17 Aug 2300 - 0115 | 10767 | 900961 | SET BAKER ISOLATION KIT AS PER BAKER ENGINEERING'S PROCEDURE UNSUCCESS. | JF | PAK |  | 08/18/2022 | PA-529S | 20.25 | SHYB-523
2005 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | PA-70S | Hrs | HRDH-1939
2006 | FOT | RIG | 27.25 | 17 Aug 1300 - 1615 | 5418 | 900915 | TDS OVERHEATED .ACTIVATE TDS ESD & COOL DOWN SAME. TROUBLE SHOOTING TDS, FOUND SERVICE LOOP DAMAGED. POOH TO CSG SHOE & CHANGE OUT SERVICE LOOP. | RR | TDS |  | 08/18/2022 | PA-70S | 11.25 | HRDH-1939
2007 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | PA-861S | Hrs | HRDH-1973
2008 | LHFL | RIG | 6 | 18 Aug 0800 - 1400 | 13048 | 900958 | WASH OUT IN TOPDRIVE ACTUATOR AND KELLY HOSE | RR | HSYS |  | 08/18/2022 | PA-861S | 6 | HRDH-1973
2009 | FOT | RIG | .5 | 18 Aug 1730 - 1800 | 8750 | 901043 | WHILE PRESSURE TESTING CASING W/MUD PUMP. OBSERVE MISLEADING PRESSURE DROP ON TEST DATA. | RR | MPMP |  | 08/18/2022 | PN-9 | .5 | MRJN-673
2010 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | PN-9 | Hrs | MRJN-673
2011 | CFST | HCM | 103.75 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/18/2022 | PN-9 | 23.5 | MRJN-673
2012 | FOT | RIG | .5 | 18 Aug 1730 - 1800 | 8750 | 901043 | WHILE PRESSURE TESTING CASING W/MUD PUMP. OBSERVE MISLEADING PRESSURE DROP ON TEST DATA. | RR | MPMP |  | 08/18/2022 | PN-9 | .5 | MRJN-673
2013 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SIN30L | Hrs | KHRS-1716
2014 | FOT | RIG | 9.25 | 17 Aug 2345 - 0900 | 2100 | 900990 | POOH W/ 17" ROTARY DRLG BHA OBSEREVED LOST IN THE HOLE FROM NEAR BIT REAMER: 1 ROLLER CONE AND RODE AND ONE RODE SECURING BLOCK | BHA | RM |  | 08/18/2022 | SIN30L | 4 | KHRS-1716
2015 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SINO-11 | Hrs | MZLJ-304
2016 | FOT | ESP | 11 | 18 Aug 1100 - 2200 | 4639 | 901037 | DURING ESP FUNCTION TEST, TRIED TO RUN ESP WITHOUT SUCCESS. | TF | ESPL |  | 08/18/2022 | SINO-11 | 11 | MZLJ-304
2017 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SINO-29N | Hrs | SFNY-2005
2018 | PCPF | ARM | 328 | 05 Aug 0500 - 0500 | 4660 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/18/2022 | SINO-29N | 24 | SFNY-2005
2019 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SINO-36L | Hrs | ANDR-32
2020 | MATL | SPS | 7 | 18 Aug 0630 - 1330 | 7225 | 900967 | SPS GEOSPANE (SURFACE UNIT) HAD MALFUNCTION AND INTERNAL VALVE NOT WORKING | WO | NA |  | 08/18/2022 | SINO-36L | 7 | ANDR-32
2021 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SINO-37L | Hrs | HWYH-639
2022 | FOT | ITS | 2 | 18 Aug 0300 - 0500 | 0 | 901040 | ITS POWER TONG OVER TORQUED FIRST JOINT THE TORQUE GAUGE NOT SHOWING THE PROPER TORQUE VALUE. | TF | CTRQ |  | 08/18/2022 | SINO-37L | 2 | HWYH-639
2023 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SINO-45L | Hrs | UTMN-1092
2024 | FOT | HSL | 2 | 18 Aug 0500 - 0700 | 0 | 901039 | DPU PUNCHER DIDN'T ACTIVATE ON TIME | TF | TPCH |  | 08/18/2022 | SINO-45L | 2 | UTMN-1092
2025 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SND-2004 | Hrs | BRRI-1148
2026 | FOT | SWT | 69 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/18/2022 | SND-2004 | 23.5 | BRRI-1148
2027 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SP-124 | Hrs | FDHL-106
2028 | FOT | BHI | .5 | 18 Aug 0430 - 0500 | 14722 | 900968 | LOST MWD SIGNAL | BHA | MWD |  | 08/18/2022 | SP-124 | .5 | FDHL-106
2029 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SP-125 | Hrs | ANDR-20
2030 | FOT | BHI | 26.5 | 17 Aug 0200 - 0500 | 8613 | 900991 | LOST BHI MWD SIGNAL | BHA | LWD |  | 08/18/2022 | SP-125 | 23.5 | ANDR-20
2031 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SP-167 | Hrs | HRDH-218
2032 | ORDS | ARN | 151.5 | 10 Aug 0800 - 0500 | 5008 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/18/2022 | SP-167 | 18.5 | HRDH-218
2033 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SP-58 | Hrs | HRDH-795
2034 | STBH | ARM | 11 | 18 Aug 1800 - 0500 | 15770 | 900965 | AFTER WORK TIDE SPOT @ 15813' HOLE PACKED OFF AT 15770' DEPTH, LOST ROTATION AND CIRCULATION. WORK ON STUCK PIPE. | STUK | BHA |  | 08/18/2022 | SP-58 | 11 | HRDH-795
2035 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SSA-102 | Hrs | QTIF-693
2036 | FOT | WWD | 113.75 | 13 Aug 0545 - 0500 | 9715 | 900815 | WFD WHIPSTOCK DID NOT SET, BOLT WAS SHEARED, LOST WHIPSTOCK IN HOLE. | TF | WPSTK |  | 08/18/2022 | SSA-102 | 8 | QTIF-693
2037 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SSA-46 | Hrs | JAHM-7
2038 | FRFM | ARM | 20.5 | 18 Aug 0830 - 0500 | 11350 | 901038 | CIRCULATE & CONDITION MUD, INCREASE GRADUALLY BY 0,5 BPM FLOW RATE TO 5BPM. AFTER 10 MIN CIRCULATE 5BMP/3,900 PSI PRESSURE SUDDENLY DROP TO 2,300 PSI. REDUCE FLOW RATE TO 2 BPM/1,000PSI & OBSERVED 77 BPH LOSSES. | LCIR | NA |  | 08/18/2022 | SSA-46 | 20.5 | JAHM-7
2039 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | SSA-5969 | Hrs | UTMN-3148
2040 | STBH | ARM | 263.25 | 06 Aug 1315 - 0500 | 2262 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) | STUK | BHA |  | 08/18/2022 | SSA-5969 | 23.5 | UTMN-3148
2041 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/18/2022 | T914 | Hrs | UTMN-415
2042 | ISEQ | RIG | 104.5 | 14 Aug 1430 - 0500 | 6120 | 900876 | GYRO UNABLE LATCH UBHO,POH WITH STRING, FOUND CAVED LAYERS OF CMT ABOVE UBHO. | DSF | DP |  | 08/18/2022 | T914 | 24 | UTMN-415
2043 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ADC-23 | Hrs | KIDN-23
2044 | FOT | EX1 | 21 | 19 Aug 0500 - 0200 | 0 | 901074 | MISSING EXPRO SLICKLINE DATA | TF | SLICK |  | 08/19/2022 | ADC-23 | 21 | KIDN-23
2045 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ADC-43L | Hrs | UTMN-3118
2046 | FRFM | TK3 | 182.5 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/19/2022 | ADC-43L | 22 | UTMN-3118
2047 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ADC-55L | Hrs | UTMN-3171
2048 | STBH | TK3 | 478 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/19/2022 | ADC-55L | 24 | UTMN-3171
2049 | 13523 | 11110 | TI | N |  | STDP | RIH 7" & 9 5/8" COMBINED C/O TOOLS RUN#3 ON 5" DP FROM 6500 FT TO 11110 FT. | 13523 | 6500 | RIG | 08/19/2022 | ADC-58L | CT | ABHD-169
2050 | 13523 |  | CIRC | C |  | MPMP | CIRC. HOLE CLEAN. (FR: 400 GPM, SPP: 300 PSI)- FLOW CHECK, WELL ON TOTAL LOSSES | 13523 |  | RIG | 08/19/2022 | ADC-58L | CT | ABHD-169
2051 | 13523 | 4710 | TO | C |  | STDP | POOH 7" & 9 5/8" COMBINED C/O TOOLS RUN#3 ON 5" DP FROM 11,110 FT TO 4710 FT.- FLOW CHECK AT TOL, WELL ON TOTAL LOSSES. | 13523 | 11110 | RIG | 08/19/2022 | ADC-58L | CT | ABHD-169
2052 | 13523 |  | HT | C |  | BHA | L/D 9-5/8" C/O TOOLS AND POOH FROM 4710 FT TO 4677 FT:- RECOVERED 0.3 KGS OF FINE RUST AND SCALES FROM 9- 5/8" MAGNETS.- CHANGED HANDLING TOOLS FROM 5" TO 4" | 13523 |  | RIG | 08/19/2022 | ADC-58L | CT | ABHD-169
2053 | 13523 | 101 | TO | C |  | STDP | POOH 7" C/O TOOLS RUN#3 ON 4" DP FROM 4677 FT TO 101 FT. | 13523 | 4677 | RIG | 08/19/2022 | ADC-58L | CT | ABHD-169
2054 | 13523 |  | HT | C |  | BHA | L/D 7" C/O TOOLS RUN#2 AND POOH FROM 154 FT TO SURFACE:- RECOVERED 2 KG RUST & SCALES FROM 7" MAGNETS & NO BIG PIECES OF METAL. | 13523 |  | RIG | 08/19/2022 | ADC-58L | CT | ABHD-169
2055 | 13523 |  | RTRV | C |  | WBSH | RETRIEVED 11" WEAR BUSHING. | 13523 |  | RIG | 08/19/2022 | ADC-58L | WH | ABHD-169
2056 | 13523 |  | OTH | C |  | SFLN | R/D D/P HANDLING EQUIPMENT AND PERFORMED HOUSEKEEPING ON RIG FLOOR. | 13523 |  | RIG | 08/19/2022 | ADC-58L | COMP | ABHD-169
2057 | 13523 |  | RR | C |  | TDS | SERVICED TDS | 13523 |  | RIG | 08/19/2022 | ADC-58L | COMP | ABHD-169
2058 | 13523 |  | HT | C | 4245 | PEL | R/U NABORS TUBING HANDLING EQUIPMENT W*JAM UNIT & SLB COMPLETION RUNNING EQUIPMENT.- PJSM & HANGED CONTROL LINE SHEAVE ON DERRICK. | 13523 |  | TSC | 08/19/2022 | ADC-58L | COMP | ABHD-169
2059 | 13523 |  | PJSM | C | 4245 | EQLZR | HELD PJSM PRIOR TO RIH MIDDLE SMART COMPLETION. | 13523 |  | SCP | 08/19/2022 | ADC-58L | COMP | ABHD-169
2060 | 13523 |  | HT | C | 4245 | EQLZR | PU/MU LOWER SMART COMPLETION ASSEMBLY TO 116 FT:- ASSY#1: 4-1/2" NVAM HALF MULE SHOE PUP JOINT- 4-1/2" NVAM L-80 12.6# TUBING JOINT- ASSY#2 (7" MFIV ASSEMBLY): 4-1/2" VAGT PUP JOINT + 7" MFIV + 4-1/2" NVAM PUP JOINT + XO + 3-1/2" NVAM PUP JOINT + 3-1/2" NVAM L-80 9.2# TBG JT | 13523 |  | SCP | 08/19/2022 | ADC-58L | COMP | ABHD-169
2061 | 13523 |  | DTU | C | 4245 | DRFT | R/U SLICK LINE, DRIFTED COMPLETION ASSEMBLY TO 45 FT W/ 2.867" DRIFT, R/D SLICK LINE. | 13523 |  | BTT | 08/19/2022 | ADC-58L | COMP | ABHD-169
2062 | 13523 |  | PTST | C | 4245 | BHA | R/U P/T ASSY & SURFACE LINE TO TEST UNIT. P/T SURFACE LINE TO 4500 PSI, P/T MFIV TO 4200 PSI FOR 10 MIN OK. R/D TEST ASSY. | 13523 |  | RIG | 08/19/2022 | ADC-58L | COMP | ABHD-169
2063 | 13523 |  | HT | C | 4245 | EQLZR | PU/MU MIDDLE SMART COMPLETION ASSEMBLY FROM 116 FT TO 208 FT:- ASSY#3 (TRFC#1 ASSEMBLY): 3-1/2" NVAM PUP JOINT + XO + 3-1/2" 9.3# EUE TRFC #1 + XO + 3-1/2" NVAM PUP JOINT- ASSY#4 (7" MULTIPORT PACKER ASSEMBLY): 3-1/2" NVAM PUP JOINT + 7" MULTIPORT PACKER + 3-1/2" NVAM PUP JOINT + 3-1/2" NVAM L-80 9.2# TBG JT | 13523 |  | SCP | 08/19/2022 | ADC-58L | COMP | ABHD-169
2064 | 13523 |  | DTU | C | 4245 | DRFT | R/U SLICK LINE, DRIFTED COMPLETION ASSEMBLY TO 100 FT W/ 2.867" DRIFT, R/D SLICK LINE. | 13523 |  | EX1 | 08/19/2022 | ADC-58L | COMP | ABHD-169
2065 | 13523 |  | HT | C | 4245 | EQLZR | CONNECTED CONTROL LINE TO TRFC#1 (ICV#1) IN PROGRESS- FLUSH CONTROL LINE, M/U CONTROL LINE CONNECTION- PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM DURING ALL PAST OPERATION, WELL ON TOTAL LOSSES. | 13523 |  | SCP | 08/19/2022 | ADC-58L | COMP | ABHD-169
2066 | 8.25 | OOS | Category | DOOS ID | COM | Out of Scope Summary | RUN SLB MIDDLE SMART COMPLETION | 8.25 | 4245 | 19 Aug 0100 | 08/19/2022 | ADC-58L | Type | ABHD-169
2067
2068
2069 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ADC-60 | Hrs | ABSF-216
2070 | FOT | BAL | 214.5 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/19/2022 | ADC-60 | 24 | ABSF-216
2071 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ADES-798 | Hrs | HRDH-2302
2072 | FOT | RIG | 2 | 19 Aug 1930 - 2130 | 11247 | 901077 | WAIT ON ADES TO REPLACE LOAD CELL DUE TO NO HOOKLOAD READING RESPONSE ON WEIGHT INDICATOR. | RR | DRRK |  | 08/19/2022 | ADES-798 | 2 | HRDH-2302
2073 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ADES-889 | Hrs | HRDH-2122
2074 | HERR | RAC | 159.5 | 12 Aug 0500 - 0630 | 10875 | 900795 | VERY FAST WORN OUT FOR THE PILOT MILL LEAD TO UNDER GAUGED MILL WENT INSIDE THE 7" LINER WITHOUT MILLING. | BHA | MILL |  | 08/19/2022 | ADES-889 | 1.5 | HRDH-2122
2075 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ADM-655 | Hrs | SFNY-306
2076 | WOPF | AP2 | 7.5 | 19 Aug 2130 - 0500 | 0 | 901075 | WAIT ON SFNY GOSP TO ACCEPT FLOW BACK OPS. | WO | NA |  | 08/19/2022 | ADM-655 | 7.5 | SFNY-306
2077 | FOT | RIG | 1.25 | 19 Aug 0345 - 0500 | 2563 | 901083 | FAILURE OF DRAWWORKS VFD BRAKE RESISTANCE COOLING FAN. | RR | DWKS |  | 08/19/2022 | AOD-1 | 1.25 | ZULF-694
2078 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | AOD-1 | Hrs | ZULF-694
2079 | STCT | ARM | 82 | 16 Aug 0930 - 0345 | 7478 | 900936 | WHILE RIH W/ 4-1/2" BAKER ICD SCREENS, HOLE BECAME PACKED OFF & STRING STUCK. | STUK | SCRN |  | 08/19/2022 | AOD-1 | 22.75 | ZULF-694
2080 | FOT | RIG | 1.25 | 19 Aug 0345 - 0500 | 2563 | 901083 | FAILURE OF DRAWWORKS VFD BRAKE RESISTANCE COOLING FAN. | RR | DWKS |  | 08/19/2022 | AOD-1 | 1.25 | ZULF-694
2081 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ARO-2003 | Hrs | MNIF-733
2082 | WOPF | AP2 | 96 | 16 Aug 0500 - 0500 | 0 | 900956 | WAIT ON FIELD SERVICE TO INSTALL ISOLATION PLUGS. | WO | NA |  | 08/19/2022 | ARO-2003 | 24 | MNIF-733
2083 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | BB-84A | Hrs | MRJN-581
2084 | FPMP | RIG | .75 | 19 Aug 1430 - 1515 | 7950 | 901085 | CUMULATIVE TIME FOR SWITCHING BETWEEN MUD PUMPS DUE TO LOSING PUMP PRESSURE & RE-START PUMPS. | RR | MPMP |  | 08/19/2022 | BB-84A | .75 | MRJN-581
2085 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | DPS-44 | Hrs | UTMN-2342
2086 | XTTE | ITS | 140.5 | 14 Aug 0800 - 0500 | 3220 | 900848 | AFTER COMPLETING THE FIRST STAGE CEMENT JOB FOR 18-5/8" CASING, ATTEMPTED TO INFLATE AND OPEN DV WITHOUT CLEAR INDICATION, ATTEMPTED TO PERFORM TOP JOB AND PUMPED ONLY 7 BBLS BEFORE GETTING CMT TO SURFACE. CLEAN OUT DV AND GET COMPLETE LOSSES, SUSPECT CASING LEAK. RAN 18-5/8" RTTS AND CONFIRM CASING LEAK AT DEPTH 3220' BETWEEN JOINTS NO. 78 & 79. | TF | CTRQ |  | 08/19/2022 | DPS-44 | 24 | UTMN-2342
2087 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | DPS-45 | Hrs | UTMN-2331
2088 | FOT | SDM | 44 | 17 Aug 1930 - 0315 | 16912 | 901034 | SLB MWD LOST SIGNAL. | BHA | MWD |  | 08/19/2022 | DPS-45 | 21.25 | UTMN-2331
2089 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | DQ-57L | Hrs | KHRS-68
2090 | FOT | RIG | 11 | 19 Aug 1000 - 2100 | 0 | 901086 | P/T ANNULAR HAD PTRESSURE TEST LEAK NOT HOLDING | BOP | BOP |  | 08/19/2022 | DQ-57L | 11 | KHRS-68
2091 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ENS-108 | Hrs | ZULF-2015
2092 | FOT | RIG | 42.25 | 18 Aug 1045 - 0500 | 7186 | 901033 | OBSERVED FLOW LINE BETWEEN SHAKER AND PIT ROOM PLUGGED. | RR | FL |  | 08/19/2022 | ENS-108 | 24 | ZULF-2015
2093 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | ENS-141 | Hrs | MRJN-3022
2094 | FOT | RIG | 3 | 19 Aug 0500 - 0800 | 0 | 901079 | OBSERVED LEAKAGE WHILE PERFORMING DIVERTER HYDRO TEST FROM 16" ACTUATOR VALVE ON PORT SIDE OF BIG BORE DIVERTER AND 7 1/16" HCR VALVE ON 30" DIVERTER STARBOARD SIDE. | BOP | DVRT |  | 08/19/2022 | ENS-141 | 3 | MRJN-3022
2095 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | HI-2 | Hrs | BRRI-433
2096 | FPMP | RIG | 1.5 | 19 Aug 0800 - 0930 | 3745 | 901081 | CLEANED SUCTION STRAINS OF MUD PUMPS AND FIXED LEAKAGE AT MP #1 MUD LINE CONNECTION. | RR | MPMP |  | 08/19/2022 | HI-2 | 1.5 | BRRI-433
2097 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | MP-1 | Hrs | MRJN-78
2098 | FOT | NRT | 437.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/19/2022 | MP-1 | 24 | MRJN-78
2099 | FOT | RIG | .75 | 19 Aug 0230 - 0315 | 3220 | 901078 | RIG REPAIR, PRAGMA STOP WORKING, FIX SAME & REFILL HYD OIL,OK. | RR | HSYS |  | 08/19/2022 | NBR-263S | .75 | QTIF-736
2100 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | NBR-263S | Hrs | QTIF-736
2101 | STBH | ARM | 238 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/19/2022 | NBR-263S | 23.25 | QTIF-736
2102 | FOT | RIG | .75 | 19 Aug 0230 - 0315 | 3220 | 901078 | RIG REPAIR, PRAGMA STOP WORKING, FIX SAME & REFILL HYD OIL,OK. | RR | HSYS |  | 08/19/2022 | NBR-263S | .75 | QTIF-736
2103 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | NBR-633S | Hrs | HRDH-1911
2104 | IBSL | CDB | 17.5 | 19 Aug 0600 - 0500 | 1588 | 901053 | EXCESS TIME TO DRILL OUT (DV & SHOE TRACK) DUE TO WRONG BIT SELECTION. | TF | BIT |  | 08/19/2022 | NBR-633S | 17.5 | HRDH-1911
2105 | FOT | HWP | 2.5 | 19 Aug 2030 - 2300 | 12807 | 901076 | LOST COMMUNICATION WITH RESISTIVITY TOOL. POOH. REPLACE RESISTIVITY TOOL. RIH TO 5000 FT. | TF | WLT |  | 08/19/2022 | NBR-654S | 2.5 | HRDH-1150
2106 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | NBR-654S | Hrs | HRDH-1150
2107 | FOT | PKP | 369.75 | 02 Aug 1915 - 0500 | 12807 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/19/2022 | NBR-654S | 21.5 | HRDH-1150
2108 | FOT | HWP | 2.5 | 19 Aug 2030 - 2300 | 12807 | 901076 | LOST COMMUNICATION WITH RESISTIVITY TOOL. POOH. REPLACE RESISTIVITY TOOL. RIH TO 5000 FT. | TF | WLT |  | 08/19/2022 | NBR-654S | 2.5 | HRDH-1150
2109 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | NBR-797S | Hrs | UTMN-3119
2110 | STBH | ARM | 4.5 | 18 Aug 0430 - 0900 | 7452 | 901052 | AFTER DRILLING STAND KELLY DOWN DRILL OFF WOB, PICK UP STRING OVERPULL. TRY TO MOVE DOWN WITHOUT SUCCESS STRING STUCK. | STUK | BHA |  | 08/19/2022 | NBR-797S | 4 | UTMN-3119
2111 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | PN-9 | Hrs | MRJN-673
2112 | CFST | HCM | 127.75 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/19/2022 | PN-9 | 24 | MRJN-673
2113 | FOT | HTS | 2.5 | 19 Aug 1630 - 1900 | 12595 | 900971 | HALLIBURTON WELL TEST IGNITION SYSTEM FLARE-BOOM FAILURE. REPAIR SAME. | TF | TESTT |  | 08/19/2022 | RBP-50A | 2.5 | HSBH-52
2114 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | RBP-50A | Hrs | HSBH-52
2115 | WTHR | ARM | 8 | 09 Aug 0500 - 1630 | 0 | 900658 | WAIT ON WEATHER, UNABLE TO FLOWBACK DUE TO UNFAVORABLE WIND CONDITION. | WON | NA |  | 08/19/2022 | RBP-50A | 1.75 | HSBH-52
2116 | FOT | HTS | 2.5 | 19 Aug 1630 - 1900 | 12595 | 900971 | HALLIBURTON WELL TEST IGNITION SYSTEM FLARE-BOOM FAILURE. REPAIR SAME. | TF | TESTT |  | 08/19/2022 | RBP-50A | 2.5 | HSBH-52
2117 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SINO-16 | Hrs | JLDI-850
2118 | FOT | KSC | 18 | 19 Aug 0800 - 0200 | 824 | 901072 | CHECK CABLE READING AND FOUND PH-G GROUNDED. POH WITH ESP COMPLETION. | TF | ESP |  | 08/19/2022 | SINO-16 | 18 | JLDI-850
2119 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SINO-29N | Hrs | SFNY-2005
2120 | PCPF | ARM | 352 | 05 Aug 0500 - 0500 | 4660 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/19/2022 | SINO-29N | 24 | SFNY-2005
2121 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SINO-37L | Hrs | HWYH-639
2122 | FOT | ITS | 7 | 18 Aug 0300 - 1000 | 0 | 901040 | ITS POWER TONG OVER TORQUED FIRST JOINT THE TORQUE GAUGE NOT SHOWING THE PROPER TORQUE VALUE. | TF | CTRQ |  | 08/19/2022 | SINO-37L | 5 | HWYH-639
2123 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SND-2003 | Hrs | GZLN-1
2124 | FOT | GOC | 4.75 | 19 Aug 2345 - 0430 | 2792 | 901087 | SPIDER SLIPS MALFUNCTIONED AND NOT RELEASING FROM CASING COLLAR, REPLACED SAME WITH BACKUP. | TF | CTRQ |  | 08/19/2022 | SND-2003 | 4.75 | GZLN-1
2125 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SND-2004 | Hrs | BRRI-1148
2126 | FOT | SWT | 90 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/19/2022 | SND-2004 | 21 | BRRI-1148
2127 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SND-2007 | Hrs | AWTD-104001
2128 | FOT | BHI | 4.5 | 19 Aug 0030 - 0500 | 18320 | 901082 | BAKER LOST COMMUNICATION WITH THE AUTOTRAK RSS TO THE MWD TOOL. | BHA | RSS |  | 08/19/2022 | SND-2007 | 4.5 | AWTD-104001
2129 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SP-124 | Hrs | FDHL-106
2130 | FOT | BHI | 24.5 | 18 Aug 0430 - 0500 | 14722 | 900968 | LOST MWD SIGNAL | BHA | MWD |  | 08/19/2022 | SP-124 | 24 | FDHL-106
2131 | IDPR | RIG | 14 | 19 Aug 1500 - 0500 | 6223 | 901088 | GOT DRILLING STRING PLUUGED | BHA | JBGR |  | 08/19/2022 | SP-125 | 14 | ANDR-20
2132 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SP-125 | Hrs | ANDR-20
2133 | FOT | BHI | 34.5 | 17 Aug 0200 - 1500 | 8613 | 900991 | LOST BHI MWD SIGNAL | BHA | LWD |  | 08/19/2022 | SP-125 | 8 | ANDR-20
2134 | IDPR | RIG | 14 | 19 Aug 1500 - 0500 | 6223 | 901088 | GOT DRILLING STRING PLUUGED | BHA | JBGR |  | 08/19/2022 | SP-125 | 14 | ANDR-20
2135 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SP-167 | Hrs | HRDH-218
2136 | ORDS | ARN | 175 | 10 Aug 0800 - 0430 | 5008 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/19/2022 | SP-167 | 23.5 | HRDH-218
2137 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SP-306 | Hrs | MNIF-192
2138 | FOT | RIG | 1 | 19 Aug 1300 - 1400 | 2795 | 900970 | TROUBLESHOOT PROBLEM ON SCR POWER LIMIT SENSOR. | RR | PSYS |  | 08/19/2022 | SP-306 | 1 | MNIF-192
2139 | 6380 | 5300 | ST | N | 4186 | STDP | POOH 6-1/8" C/O BHA FROM 7" CSG SHOE TO 5300 FT FOR CORING .-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET | 6380 | 6300 | RIG | 08/19/2022 | SP-53L | DRLG | HRDH-528
2140 | 6380 |  | SDR1 | N | 4186 | NA | FLOW CHECK AFTER PULL 10 STDS WELL STATIC OK. | 6380 |  | RIG | 08/19/2022 | SP-53L | DRLG | HRDH-528
2141 | 6380 | 1597 | ST | N | 4186 | STDP | CONTD POOH 6-1/8" C/O BHA FROM 5300 FT TO 7" TOL @ 1597FT FOR CORING .-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET | 6380 | 5300 | RIG | 08/19/2022 | SP-53L | DRLG | HRDH-528
2142 | 6380 |  | SDR1 | N | 4186 | NA | FLOW CHECK @7" TOL WELL STATIC OK. | 6380 |  | RIG | 08/19/2022 | SP-53L | DRLG | HRDH-528
2143 | 6380 | 600 | ST | N | 4186 | STDP | CONTD POOH W/ 6-1/8" CLEAN OUT ASSY FROM 7" TOL@1597 FT TO TOP OF BHA @ 600 FT. FOR CORING . | 6380 | 1597 | RIG | 08/19/2022 | SP-53L | DRLG | HRDH-528
2144 | 6380 |  | SDR1 | N | 4186 | NA | FLOW CHECK @ TOP BHA WELL STATIC. | 6380 |  | RIG | 08/19/2022 | SP-53L | DRLG | HRDH-528
2145 | 6380 |  | HT | N | 4186 | BHA | CONTD POOH W/ 6-1/8" CLEAN OUT ASSY TO SURFACE FOR CORING .- BIT DULL GRADING : 1-2-WT-A-I-E-NO-CP. | 6380 |  | RIG | 08/19/2022 | SP-53L | DRLG | HRDH-528
2146 | 6380 |  | HT | E | 4186 | CORC | HPJSM, P/U & M/U 6-1/8" NOV CORE ASSY. -6-1/8" CORE HEAD + 4-3/4" CORE OUTER BARRELS & 3-3/8" INNER BARRELS + FLOAT SUB W/ FLAPPER TYPE FLOAT VALVE (BALL SIZE IS 1")+15 X 4-3/4" DC'S+ + 4-3/4" DRILLING JAR+2 X 4 3/4" DC'S +XO+ DP'S. | 6380 |  | NOC | 08/19/2022 | SP-53L | CORE | HRDH-528
2147 | 6380 | 6374 | TI | E | 4186 | STDP | RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 612' TO 7" CSG SHOE @6374'.-GENTLY PASSED 7" TOL & SHOE TRACK. | 6380 | 612 | RIG | 08/19/2022 | SP-53L | CORE | HRDH-528
2148 | 6380 | 6380 | TI | E | 4186 | STDP | CONTD RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 6374' TO CORE POINT @ 6380'.-WASH AND REAM DOWN TILL TAG BTM @6380' | 6380 | 6374 | RIG | 08/19/2022 | SP-53L | CORE | HRDH-528
2149 | 6380 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTMS UP & CHC WITH 200 GPM & PRESSURE 430 PSI. | 6380 |  | RIG | 08/19/2022 | SP-53L | CORE | HRDH-528
2150 | 6380 |  | CIRC | E | 4186 | MPMP | DROP 1" NOV DIVERTING BALL, PUMP DOWN WITH 80 GPM & WAIT TILL SEATED IN ORDER TO DIVERT FLUID AWAY FROM THE INNER BARREL TO START CORING ACROSS PADS FORMATION.-CONFIRM SPACE OUT FOR CUTTING THE CORE.@6380' -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS. | 6380 |  | RIG | 08/19/2022 | SP-53L | CORE | HRDH-528
2151 | 6415 |  | CORE | E | 4186 | CORC | CUT 6-1/8" X 2 5/8" CORE RUN #1 FROM 6380' TO 6415' W/70 PCF POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, (RPM: 65 - TQ 2-3 KLFTLB) & (GPM: 170 - PRESS 550 PSI)-STOP ROTATION AND BREAK OUT CORE WITH 15K OVERPULL. | 6380 |  | NOC | 08/19/2022 | SP-53L | CORE | HRDH-528
2152 | 67 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 24 | 4186 | 13 Aug 0230 | 08/19/2022 | SP-53L | Type | HRDH-528
2153
2154
2155 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SSA-102 | Hrs | QTIF-693
2156 | FOT | WWD | 128.5 | 13 Aug 0545 - 1945 | 9715 | 900815 | WFD WHIPSTOCK DID NOT SET, BOLT WAS SHEARED, LOST WHIPSTOCK IN HOLE. | TF | WPSTK |  | 08/19/2022 | SSA-102 | 14.75 | QTIF-693
2157 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SSA-46 | Hrs | JAHM-7
2158 | FRFM | ARM | 26 | 18 Aug 0830 - 1030 | 11350 | 901038 | CIRCULATE & CONDITION MUD, INCREASE GRADUALLY BY 0,5 BPM FLOW RATE TO 5BPM. AFTER 10 MIN CIRCULATE 5BMP/3,900 PSI PRESSURE SUDDENLY DROP TO 2,300 PSI. REDUCE FLOW RATE TO 2 BPM/1,000PSI & OBSERVED 77 BPH LOSSES. | LCIR | NA |  | 08/19/2022 | SSA-46 | 5.5 | JAHM-7
2159 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SSA-5964 | Hrs | UTMN-1973
2160 | FOT | SLL | 2 | 19 Aug 0230 - 0430 | 13428 | 901080 | PLUG BODY LEFT IN TUBING | TF | PLUGN |  | 08/19/2022 | SSA-5964 | 2 | UTMN-1973
2161 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | SSA-5969 | Hrs | UTMN-3148
2162 | STBH | ARM | 286.75 | 06 Aug 1315 - 0500 | 2262 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) | STUK | BHA |  | 08/19/2022 | SSA-5969 | 23.5 | UTMN-3148
2163 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | T907 | Hrs | SRYN-2
2164 | FOT | SPS | 15 | 19 Aug 1115 - 0245 | 11318 | 900969 | MUD MOTOR FAILURE. | BHA | MMOT |  | 08/19/2022 | T907 | 15 | SRYN-2
2165 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | T914 | Hrs | UTMN-415
2166 | ISEQ | RIG | 124 | 14 Aug 1430 - 0100 | 6120 | 900876 | GYRO UNABLE LATCH UBHO,POH WITH STRING, FOUND CAVED LAYERS OF CMT ABOVE UBHO. | DSF | DP |  | 08/19/2022 | T914 | 19.5 | UTMN-415
2167 | FOT | SCP | 4 | 19 Aug 0930 - 1330 | 13815 | 901084 | ICV-1 NOT HOLDING PRESSURE DURING NEGATIVE TEST. | TF | HVLV |  | 08/19/2022 | WCL-83 | 4 | MRJN-835
2168 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/19/2022 | WCL-83 | Hrs | MRJN-835
2169 | FOT | HTS | 4 | 19 Aug 0530 - 0930 | 13815 | 901073 | GENERATOR FAILURE. | TF | WTSE |  | 08/19/2022 | WCL-83 | 4 | MRJN-835
2170 | FOT | SCP | 4 | 19 Aug 0930 - 1330 | 13815 | 901084 | ICV-1 NOT HOLDING PRESSURE DURING NEGATIVE TEST. | TF | HVLV |  | 08/19/2022 | WCL-83 | 4 | MRJN-835
2171 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ADC-41L | Hrs | SDGM-1244
2172 | FOT | TK3 | 11.5 | 26 Jul 0700 - 0500 | 6400 | 900240 | DRILL PIPE PLUGGING | DSF | DP |  | 08/20/2022 | ADC-41L | 7 | SDGM-1244
2173 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ADC-43L | Hrs | UTMN-3118
2174 | FRFM | TK3 | 206.5 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/20/2022 | ADC-43L | 24 | UTMN-3118
2175 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ADC-48 | Hrs | HRDH-2316
2176 | FOT | RIG | 2.25 | 20 Aug 0000 - 0215 | 14940 | 901094 | REPAIR HOOK LOAD SENSOR | RR | ACDC |  | 08/20/2022 | ADC-48 | 2.25 | HRDH-2316
2177 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ADC-55L | Hrs | UTMN-3171
2178 | STBH | TK3 | 502 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/20/2022 | ADC-55L | 24 | UTMN-3171
2179 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ADC-60 | Hrs | ABSF-216
2180 | FOT | BAL | 238.5 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/20/2022 | ADC-60 | 24 | ABSF-216
2181 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ADM-337 | Hrs | MRJN-900
2182 | FOT | BCT | 10.5 | 20 Aug 1330 - 0130 | 0 | 901089 | RE-TEST BAKER CTU VALVES AND LINES REQUIRING CHANGE OUT DUE TO PRIOR LEAKS, TROUBLE SHOOT LEAKING HCR ON BOT QAUD BOPS | TF | CTBG |  | 08/20/2022 | ADM-337 | 10.5 | MRJN-900
2183 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ADM-655 | Hrs | SFNY-306
2184 | WOPF | AP2 | 31.5 | 19 Aug 2130 - 0500 | 0 | 901075 | WAIT ON SFNY GOSP TO ACCEPT FLOW BACK OPS. | WO | NA |  | 08/20/2022 | ADM-655 | 24 | SFNY-306
2185 | FOT | RIG | 2.5 | 19 Aug 0345 - 0615 | 2563 | 901083 | FAILURE OF DRAWWORKS VFD BRAKE RESISTANCE COOLING FAN. | RR | DWKS |  | 08/20/2022 | AOD-1 | 1.25 | ZULF-694
2186 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | AOD-1 | Hrs | ZULF-694
2187 | STCT | ARM | 104.75 | 16 Aug 0930 - 0500 | 7478 | 900936 | WHILE RIH W/ 4-1/2" BAKER ICD SCREENS, HOLE BECAME PACKED OFF & STRING STUCK. | STUK | SCRN |  | 08/20/2022 | AOD-1 | 22.75 | ZULF-694
2188 | FOT | RIG | 2.5 | 19 Aug 0345 - 0615 | 2563 | 901083 | FAILURE OF DRAWWORKS VFD BRAKE RESISTANCE COOLING FAN. | RR | DWKS |  | 08/20/2022 | AOD-1 | 1.25 | ZULF-694
2189 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ARO-2003 | Hrs | MNIF-733
2190 | WOPF | AP2 | 120 | 16 Aug 0500 - 0500 | 0 | 900956 | WAIT ON FIELD SERVICE TO INSTALL ISOLATION PLUGS. | WO | NA |  | 08/20/2022 | ARO-2003 | 24 | MNIF-733
2191 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ARO-4001 | Hrs | MRJN-532
2192 | FOT | RIG | 1.5 | 20 Aug 0615 - 0745 | 6871 | 901017 | OBSERVED LOWER FLOW LINE SEAL LEAKING BELOW ROTARY HOUSING, PULL OUT 30" BIG BORE DIVERTER, CLEAN & GREASE FLOW LINE SEAL, OK, INSTALL 30" BIG BORE DIVERTER, CHECK FOR LEAKING, NO LEAK. | RR | BUSH |  | 08/20/2022 | ARO-4001 | 1.5 | MRJN-532
2193 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | BB-84A | Hrs | MRJN-581
2194 | FPMP | RIG | 2.25 | 19 Aug 1430 - 2245 | 7950 | 901085 | CUMULATIVE TIME FOR SWITCHING BETWEEN MUD PUMPS DUE TO LOSING PUMP PRESSURE & RE-START PUMPS. OBSERVED SUCTION LINE VALAVE WAS LEAKING, CLEAN MUD PUMP SUCTION VALVE. | RR | MPMP |  | 08/20/2022 | BB-84A | 1.5 | MRJN-581
2195 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | BCTD-3 | Hrs | HWYH-997
2196 | FOT | ARM | 17 | 20 Aug 1200 - 0500 | 0 | 901056 | LEAK ON THE TREE HYD VALVE ACTUATOR . | WH | WH |  | 08/20/2022 | BCTD-3 | 17 | HWYH-997
2197 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | DPS-4 | Hrs | MDRK-63
2198 | FOT | RIG | 7.5 | 20 Aug 1800 - 0130 | 16609 | 901016 | MALFUNCTION ON DRAWWORKS LOW SPEED CLUTCH. | RR | DWKS |  | 08/20/2022 | DPS-4 | 7.5 | MDRK-63
2199 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | DPS-44 | Hrs | UTMN-2342
2200 | XTTE | ITS | 164 | 14 Aug 0800 - 0500 | 3220 | 900848 | AFTER COMPLETING THE FIRST STAGE CEMENT JOB FOR 18-5/8" CASING, ATTEMPTED TO INFLATE AND OPEN DV WITHOUT CLEAR INDICATION, ATTEMPTED TO PERFORM TOP JOB AND PUMPED ONLY 7 BBLS BEFORE GETTING CMT TO SURFACE. CLEAN OUT DV AND GET COMPLETE LOSSES, SUSPECT CASING LEAK. RAN 18-5/8" RTTS AND CONFIRM CASING LEAK AT DEPTH 3220' BETWEEN JOINTS NO. 78 & 79. | TF | CTRQ |  | 08/20/2022 | DPS-44 | 23.5 | UTMN-2342
2201 | FOT | BCR | 2 | 20 Aug 1200 - 1400 | 0 | 901054 | EXCESSIVE TIME TO RIG UP TO RUN LOWER COMPLETIONS TBG DUE TO MAIN POWER TONGS/JAM UNIT NOT FUNCTIONING CORRECTLY. | TF | CTRQ |  | 08/20/2022 | DPS-74 | 2 | NJYN-33
2202 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | DPS-74 | Hrs | NJYN-33
2203 | XTTE | BCR | 4 | 20 Aug 0000 - 0400 | 4629 | 901020 | EXCESSIVE TIME TO RUN 101 JTS OF 4-1/2" CHROME TBG DUE TO POOR PERFORMANCE OF POWER TONG. | TF | CTRQ |  | 08/20/2022 | DPS-74 | 4 | NJYN-33
2204 | FOT | BCR | 2 | 20 Aug 1200 - 1400 | 0 | 901054 | EXCESSIVE TIME TO RIG UP TO RUN LOWER COMPLETIONS TBG DUE TO MAIN POWER TONGS/JAM UNIT NOT FUNCTIONING CORRECTLY. | TF | CTRQ |  | 08/20/2022 | DPS-74 | 2 | NJYN-33
2205 | GRF | RIG | 18.25 | 20 Aug 1045 - 0500 | 7186 | 901048 | OBSERVED FLOW LINE BETWEEN SHAKER AND PIT ROOM PLUGGED. | UPRA | FL |  | 08/20/2022 | ENS-108 | 18.25 | ZULF-2015
2206 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ENS-108 | Hrs | ZULF-2015
2207 | FOT | RIG | 48 | 18 Aug 1045 - 1045 | 7186 | 901033 | OBSERVED FLOW LINE BETWEEN SHAKER AND PIT ROOM PLUGGED. | RR | FL |  | 08/20/2022 | ENS-108 | 5.75 | ZULF-2015
2208 | GRF | RIG | 18.25 | 20 Aug 1045 - 0500 | 7186 | 901048 | OBSERVED FLOW LINE BETWEEN SHAKER AND PIT ROOM PLUGGED. | UPRA | FL |  | 08/20/2022 | ENS-108 | 18.25 | ZULF-2015
2209 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | ENS-141 | Hrs | MRJN-3022
2210 | FOT | RIG | 1.75 | 20 Aug 0800 - 0945 | 0 | 901051 | TROUBLESHOOT RIG MUD PUMPES, ADJUSTED PUP OFF VALVE SET LIMIT ON PUMP #1. CHANGED OUT SWAP IN PUMP#2. | RR | MPMP |  | 08/20/2022 | ENS-141 | 1.75 | MRJN-3022
2211 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | NBR-16S | Hrs | HMYM-433112
2212 | FOT | RIG | 1.5 | 20 Aug 2030 - 2200 | 8285 | 901019 | FIXED PUMP #1 & #3. | RR | MPMP |  | 08/20/2022 | NBR-16S | 1.5 | HMYM-433112
2213 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | NBR-263S | Hrs | QTIF-736
2214 | OTH | RIG | 24 | 20 Aug 0500 - 0500 | 4500 | 901090 | UNPLANED MAITENANCE DUE TO CAT III INSPECTION EXPIRED FOR CROWN BLOCK, TRAVELLING BLOCKS AND HOOK, ELEVATOR LINKS, ELEVATORS, MANUAL TONGS & MUD PUMPS. | UPRA | NA |  | 08/20/2022 | NBR-263S | 24 | QTIF-736
2215 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | NBR-654S | Hrs | HRDH-1150
2216 | FOT | PKP | 393.75 | 02 Aug 1915 - 0500 | 12807 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/20/2022 | NBR-654S | 24 | HRDH-1150
2217 | HERR | MSD | 2.75 | 20 Aug 0000 - 0245 | 16099 | 901113 | EXCESS TIME TO RUN 4 1/2" TUBING. | TF | TTRQ |  | 08/20/2022 | NBR-783S | 2.75 | NJYN-93
2218 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | NBR-783S | Hrs | NJYN-93
2219 | FOT | MSD | 7.5 | 20 Aug 1200 - 1930 | 614 | 901018 | EXCESS TIME SPENT ON REPLACING 2 DAMAGED JTS OF WFD 4-1/2" SCREEN WHILE RIH LOWER COMPLETION DUE TO MALFUNCTIONING OF AL-MASAOOD JAM UNIT + W.O ALMASAOOD TO REPLACE FAULTY JAM UNIT. | TF | TTRQ |  | 08/20/2022 | NBR-783S | 7.5 | NJYN-93
2220 | HERR | MSD | 2.75 | 20 Aug 0000 - 0245 | 16099 | 901113 | EXCESS TIME TO RUN 4 1/2" TUBING. | TF | TTRQ |  | 08/20/2022 | NBR-783S | 2.75 | NJYN-93
2221 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | PA-70S | Hrs | HRDH-1939
2222 | FOT | ITS | 8.25 | 20 Aug 1345 - 0030 | 5640 | 901055 | 13-3/8" CSG STRING SLIPPED FROM CRT & HANGED UP IN FLUSH MOUNTED SLIPS. R/D CRT & FLUSH MOUNTED SLIPS. R/U SIDE DOOR ELEVATOR & CONTINUE RIH CSG. | TF | CTRQ |  | 08/20/2022 | PA-70S | 8.25 | HRDH-1939
2223 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | PN-9 | Hrs | MRJN-673
2224 | CFST | HCM | 151.75 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/20/2022 | PN-9 | 24 | MRJN-673
2225 | FOT | HTS | 3.75 | 19 Aug 1630 - 0615 | 12595 | 900971 | HALLIBURTON WELL TEST IGNITION SYSTEM FLARE-BOOM FAILURE. REPAIR SAME. | TF | TESTT |  | 08/20/2022 | RBP-50A | 1.25 | HSBH-52
2226 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | RBP-50A | Hrs | HSBH-52
2227 | WTHR | ARM | 13 | 09 Aug 0500 - 1700 | 12595 | 900658 | WAIT ON WEATHER, UNABLE TO FLOWBACK DUE TO UNFAVORABLE WIND CONDITION. | WON | NA |  | 08/20/2022 | RBP-50A | 5 | HSBH-52
2228 | FOT | HTS | 3.75 | 19 Aug 1630 - 0615 | 12595 | 900971 | HALLIBURTON WELL TEST IGNITION SYSTEM FLARE-BOOM FAILURE. REPAIR SAME. | TF | TESTT |  | 08/20/2022 | RBP-50A | 1.25 | HSBH-52
2229 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SCTD-2 | Hrs | HRDH-2101
2230 | IDPR | SDM | 18 | 19 Aug 0400 - 2200 | 13300 | 901092 | TURBINE FAILURE. FOUND TURBINE SHAFT WIGGLE. | BHA | MWD |  | 08/20/2022 | SCTD-2 | 17 | HRDH-2101
2231 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SINO-10 | Hrs | JLDI-38
2232 | XTRI | SWL | 4.5 | 20 Aug 0030 - 0500 | 10858 | 901058 | WHILE RIGGING UP SCHLUMBERGER WIRELINE TOOLS PRIOR RUNNING 4-1/2" BRIDGE PLUG , THE WL ENGINEER RECOGNIZED THAT HE BROUGHT THE WRONG TOOL FOR THE JOB. | JF | WLT |  | 08/20/2022 | SINO-10 | 4.5 | JLDI-38
2233 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SINO-29N | Hrs | SFNY-2005
2234 | PCPF | ARM | 376 | 05 Aug 0500 - 0500 | 4660 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/20/2022 | SINO-29N | 24 | SFNY-2005
2235 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SND-2004 | Hrs | BRRI-1148
2236 | FOT | SWT | 113.5 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/20/2022 | SND-2004 | 23.5 | BRRI-1148
2237 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SND-2005 | Hrs | MHKK-2
2238 | WTHR | ARM | 4.5 | 20 Aug 0930 - 1400 | 14138 | 901047 | WINDS IN EXCESS OF 40 KM/HR (PRIOR TO TRIPPING OPERATIONS) | WON | NA |  | 08/20/2022 | SND-2005 | 4.5 | MHKK-2
2239 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SP-124 | Hrs | FDHL-106
2240 | FOT | BHI | 39.25 | 18 Aug 0430 - 2315 | 14722 | 900968 | LOST MWD SIGNAL | BHA | MWD |  | 08/20/2022 | SP-124 | 14.75 | FDHL-106
2241 | IDPR | RIG | 19.25 | 19 Aug 1500 - 1015 | 6223 | 901088 | GOT DRILLING STRING PLUUGED | BHA | JBGR |  | 08/20/2022 | SP-125 | 5.25 | ANDR-20
2242 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SP-125 | Hrs | ANDR-20
2243 | FOT | BHI | 40 | 17 Aug 0200 - 1615 | 8613 | 900991 | LOST BHI MWD SIGNAL | BHA | LWD |  | 08/20/2022 | SP-125 | 5.5 | ANDR-20
2244 | IDPR | RIG | 19.25 | 19 Aug 1500 - 1015 | 6223 | 901088 | GOT DRILLING STRING PLUUGED | BHA | JBGR |  | 08/20/2022 | SP-125 | 5.25 | ANDR-20
2245 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SP-167 | Hrs | HRDH-218
2246 | ORDS | ARN | 199 | 10 Aug 0800 - 0500 | 5008 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/20/2022 | SP-167 | 24 | HRDH-218
2247 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SP-257 | Hrs | HZEM-162412
2248 | FOT | BHI | 12.25 | 20 Aug 1645 - 0500 | 9348 | 901091 | BAKER RSS FAILURE. | BHA | RSS |  | 08/20/2022 | SP-257 | 12.25 | HZEM-162412
2249 | IPDF | EMC | 1.25 | 20 Aug 0900 - 1015 | 2658 | 901050 | EMEC MUD ENGINEER ADDED EXCESSIVE NUT PLUG TO ACTIVE SYSTEM CASING MUD PUMP SCREENS TO PLUG OFF | MUD | NA |  | 08/20/2022 | SP-261 | 1.25 | MHWZ-903
2250 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SP-261 | Hrs | MHWZ-903
2251 | IPDF | EMC | 2 | 20 Aug 0530 - 0730 | 2530 | 901049 | CIRCULATE & CONDITION MUD DUE TO HAVING VARIOUS MUD WEIGHTS IN ACTIVE SYSTEM | MUD | NA |  | 08/20/2022 | SP-261 | 2 | MHWZ-903
2252 | IPDF | EMC | 1.25 | 20 Aug 0900 - 1015 | 2658 | 901050 | EMEC MUD ENGINEER ADDED EXCESSIVE NUT PLUG TO ACTIVE SYSTEM CASING MUD PUMP SCREENS TO PLUG OFF | MUD | NA |  | 08/20/2022 | SP-261 | 1.25 | MHWZ-903
2253 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SP-262 | Hrs | JNAB-152802
2254 | FOT | BHI | 14.5 | 20 Aug 1430 - 0500 | 9201 | 901093 | RSS FAILURE, LOST DATA TRANSMISSION, POH TO CHANGE RSS. | BHA | RSS |  | 08/20/2022 | SP-262 | 14.5 | JNAB-152802
2255 | 6440 |  | CORE | E | 4186 | CORC | CONTD CUT 6-1/8" X 2 5/8" CORE RUN #1 FROM 6415' TO 6440' (60 FT INSIDE ABD1 TO AD2B) W/70 PCF POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, (RPM: 65 - TQ 2-3 KLFTLB) & (GPM: 170 - PRESS 550 PSI)-STOP ROTATION AND BREAK OUT CORE NO OVERPULL INDICATION, P/UP 5' AND RUN BACK TO BTM & CONFIRM CORE CATCHED OK. | 6415 |  | NOC | 08/20/2022 | SP-53L | CORE | HRDH-528
2256 | 6440 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTM UP WITH 120 GPM @ 440 PSI WITH FULL RETURNS. | 6440 |  | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2257 | 6440 |  | SDR1 | E | 4186 | NA | FLOW CHECK-WELL STATIC OK. | 6440 |  | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2258 | 6440 | 6374 | TO | E | 4186 | STDP | HPJSM, POOH 6 1/8" NOV CORING ASSY. TO/7" CSG SHOE @ 6374' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6440 | 6440 | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2259 | 6440 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT 7" CSG SHOE - WELL STATIC OK | 6440 |  | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2260 | 6440 | 5900 | TI | E | 4186 | STDP | HPJSM, POOH 6 1/8" NOV CORING ASSY. FROM / 7" CSG SHOE @ 6374' TO 5900' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6440 | 6374 | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2261 | 6440 |  | SDR1 | E | 4186 | NA | FLOW CHECK AFTER PULL 5 STDS WELL STATIC OK. | 6440 |  | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2262 | 6440 | 1597 | TO | E | 4186 | STDP | POOH 6 1/8" NOV CORING ASSY. TO 7" TOL@ 1597' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6440 | 5900 | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2263 | 6440 |  | SDR1 | E | 4186 | NA | FLOW CHECK @7" TOL WELL STATIC OK. | 6440 |  | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2264 | 6440 | 615 | TO | E | 4186 | STDP | CONT'D POOH 6-1/8" NOV CORING ASSY. RUN #1 TO 615' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6440 | 1597 | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2265 | 6440 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT TOP BHA - WELL STATIC OK.-CHECKING FOR H2S-ZERO H2S READING. | 6440 |  | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2266 | 6440 |  | HT | E | 4186 | CORC | CONT'D POOH 6-1/8" NOV CORING ASSY. RUN #1 TO 250' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-CHECKING FOR H2S EVERY CONNECTION & ZERO H2S READING. | 6440 |  | NOC | 08/20/2022 | SP-53L | CORE | HRDH-528
2267 | 6440 |  | HT | E | 4186 | CORC | HPJSM, CON'T POOH 6-1/8" NOV CORING ASSY. RUN #1 TO SURFACE CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-RUN RIG FLOOR BUG BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.-ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.-L/D INNER BARREL,RECOVERED 100% OF CORED 60 FT.-L/D 6-1/8" CORING HEAD AND OUTER BARREL-CORE HEAD DULL : 1-1-WT-A-X-NO-TD | 6440 |  | NOC | 08/20/2022 | SP-53L | CORE | HRDH-528
2268 | 6440 |  | HT | E | 4186 | CORC | HPJSM, P/U & M/U 6-1/8" NOV CORE ASSY. -6-1/8" CORE HEAD + 4-3/4" CORE OUTER BARRELS & 3-3/8" INNER BARRELS + FLOAT SUB W/ FLAPPER TYPE FLOAT VALVE (BALL SIZE IS 1")+15 X 4-3/4" DC'S+ + 4-3/4" DRILLING JAR+2 X 4 3/4" DC'S +XO+ DP'S. | 6440 |  | NOC | 08/20/2022 | SP-53L | CORE | HRDH-528
2269 | 6440 | 6374 | TI | E | 4186 | STDP | RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 615' TO 7" CSG SHOE @6374'.-GENTLY PASSED 7" TOL & SHOE TRACK. | 6440 | 615 | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2270 | 6440 | 6440 | TI | E | 4186 | STDP | CONTD RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 6374' TO CORE POINT @ 6440'.-WASH AND REAM DOWN TILL TAG BTM @6440' | 6440 | 6374 | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2271 | 6440 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTMS UP & CHC WITH 200 GPM & PRESSURE 510 PSI. | 6440 |  | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2272 | 6440 |  | CIRC | E | 4186 | MPMP | DROP 1" NOV DIVERTING BALL, PUMP DOWN WITH 80 GPM & WAIT TILL SEATED IN ORDER TO DIVERT FLUID AWAY FROM THE INNER BARREL. -CONFIRM SPACE OUT FOR CUTTING THE CORE.@6440' -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS. | 6440 |  | RIG | 08/20/2022 | SP-53L | CORE | HRDH-528
2273 | 6443 |  | CORE | E | 4186 | CORC | CUT 6-1/8" X 2 5/8" CORE RUN #1 FROM 6440' TO 6443' W/70 PCF POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, (RPM: 65 - TQ 2-3 KLFTLB) & (GPM: 170 - PRESS 710 PSI)-CORING WILL BE ACROSS ARAB D ZONE (AD2B TO AD2B13) FORMATION. | 6440 |  | CPR | 08/20/2022 | SP-53L | CORE | HRDH-528
2274 | 91 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 24 | 4186 | 13 Aug 0230 | 08/20/2022 | SP-53L | Type | HRDH-528
2275
2276
2277 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SP-58 | Hrs | HRDH-795
2278 | STBH | ARM | 37.5 | 18 Aug 1800 - 0800 | 15770 | 900965 | AFTER WORK TIDE SPOT @ 15813' HOLE PACKED OFF AT 15770' DEPTH, LOST ROTATION AND CIRCULATION. WORK ON STUCK PIPE. | STUK | BHA |  | 08/20/2022 | SP-58 | 3 | HRDH-795
2279 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | SSA-5969 | Hrs | UTMN-3148
2280 | STBH | ARM | 310.25 | 06 Aug 1315 - 0430 | 2262 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) | STUK | BHA |  | 08/20/2022 | SSA-5969 | 23.5 | UTMN-3148
2281 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | STY-038 | Hrs | ZULF-2089
2282 | FOT | MSL | 3 | 20 Aug 1800 - 2100 | 0 | 901112 | ATTEMPT TO START SLICKLINE UNIT ENGINE, NO SUCESS. TROUBLESHOOT AND RESTART. | TF | SLICK |  | 08/20/2022 | STY-038 | 3 | ZULF-2089
2283 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/20/2022 | T914 | Hrs | UTMN-415
2284 | FOT | RIG | 10.5 | 20 Aug 1830 - 0500 | 6060 | 901057 | HAD ELECTRICAL FAULT MAL-FUNCTION IN DYNAMIC MOTOR FOR DRAW-WORK. | RR | DWKS |  | 08/20/2022 | T914 | 10.5 | UTMN-415
2285 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADC-35 | Hrs | MAQL-5
2286 | MATL | HTS | 50.5 | 15 Aug 0600 - 0500 | 0 | 900896 | WAITING ON HALL FRAC (GULF CRYON) TO DELIVER CO2 TO COMPLETE THE VOLUME REQUIRED TO EXECUTE THE JOB AS PER PROGRAM. | WO | NA |  | 08/21/2022 | ADC-35 | 7.5 | MAQL-5
2287 | HERR | TK3 | 18.25 | 21 Aug 1045 - 0500 | 12747 | 901022 | OBSERVED STRING PLUGGED WITH LCM MATERIAL 2.5 FT ABOVE FLOAT VALVE IN BIT SUB. | JF | NA |  | 08/21/2022 | ADC-43L | 18.25 | UTMN-3118
2288 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADC-43L | Hrs | UTMN-3118
2289 | FRFM | TK3 | 212.25 | 11 Aug 2130 - 1045 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/21/2022 | ADC-43L | 5.75 | UTMN-3118
2290 | HERR | TK3 | 18.25 | 21 Aug 1045 - 0500 | 12747 | 901022 | OBSERVED STRING PLUGGED WITH LCM MATERIAL 2.5 FT ABOVE FLOAT VALVE IN BIT SUB. | JF | NA |  | 08/21/2022 | ADC-43L | 18.25 | UTMN-3118
2291 | HERR | BAL | 7.5 | 21 Aug 1900 - 0230 | 2380 | 901064 | DURING TEST ESP CABLE FOUND READING PH-GROUND ZERO. POH TO LAST SPLICE POINT & CHECK THE CABLE INTEGRITY. | JF | ESPL |  | 08/21/2022 | ADC-45 | 7.5 | MZLJ-277
2292 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADC-45 | Hrs | MZLJ-277
2293 | HERR | BAL | 5 | 21 Aug 1030 - 1530 | 1858 | 901063 | ESP ROUND CABLE DAMAGED DURING RIH WITH NEW ESP COMPLETION. | JF | ESPL |  | 08/21/2022 | ADC-45 | 5 | MZLJ-277
2294 | HERR | BAL | 7.5 | 21 Aug 1900 - 0230 | 2380 | 901064 | DURING TEST ESP CABLE FOUND READING PH-GROUND ZERO. POH TO LAST SPLICE POINT & CHECK THE CABLE INTEGRITY. | JF | ESPL |  | 08/21/2022 | ADC-45 | 7.5 | MZLJ-277
2295 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADC-55L | Hrs | UTMN-3171
2296 | STBH | TK3 | 526 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/21/2022 | ADC-55L | 24 | UTMN-3171
2297 | 14929 |  | HT | C | 4245 | PKR | SPACED OUT STRING TO HAVE HLWM AT ROTARY TABLE, TERMINATED CONTROL LINES FROM ICV#1 AND ICV#2 BELOW HLWM, CONNECTED DUAL FLATPACKC ABOVE HLWM, P/T CONTROL LINES T/9000 PSI FOR 15 MIN-HOLD OK ( 2 TESTS). | 14929 |  | SCP | 08/21/2022 | ADC-58L | COMP | ABHD-169
2298 | 14929 |  | HT | C | 4245 | PKR | PERFORMED ONE FULL CYCLE FOR ICV#1 & ICV #2 AND KEPT POSITION WHILE RIH AS FOLLOW ICV #1 AT 10 & ICV#2 AT 9. | 14929 |  | SCP | 08/21/2022 | ADC-58L | COMP | ABHD-169
2299 | 14929 |  | HT | C | 4245 | PEL | CHANGED TBG HANDLING TOOLS FROM 3-1/2" TO 4-1/2" SIZE. | 14929 |  | TSC | 08/21/2022 | ADC-58L | COMP | ABHD-169
2300 | 14929 |  | PJSM | C | 4245 | PKR | HELD PJSM PRIOR TO RUN SMART COMP ON 4-1/2" TBG, REVIEWED COMBINED JSA, PTW, ASSIGNED ROLES, RESPONSIBILITIES & DISCUSSED TECHNICAL ALERTS OF CABLE DAMAGE. | 14929 |  | SCP | 08/21/2022 | ADC-58L | COMP | ABHD-169
2301 | 14929 | 5666 | RPCS | C | 4245 | SMCOM | RIH WITH HLWM SMART COMPLETION ON 4-1/2" TBG FR/3552 FT T/5666 FT FT ( TOTAL 50 OUT OF 155 JT'S).- INSTALLED CABLE CLAMP " CCCP'S " ON EACH TUBING JOINT CONNECTIONS.- SLB SET PUMP THROUGH PLUG AT 4-1/2" JOINT#2 AT PIPE RACK.- TBG OPTIMUM M/U TORQUE: 4770 FT.LB. ( USING JAM UNIT).- FILLED UP STRING WHILE RIH EVERY 10 JOINTS. | 14929 | 3552 | RIG | 08/21/2022 | ADC-58L | COMP | ABHD-169
2302 | 14929 |  | DTU | C | 4245 | DRFT | R/U EXPRO SLICK LINE PCE, P/T SLICK LINE BOP & LUBRICATOR TO 300 / 2000 PSI FOR 10 MINS FOR MIN EACH, HOLD-OK.- RUN #6, DRIFT 4-1/2" TBG T/ 20400 FT W/ 3.833" DRIFT, POOH & R/D SLICKLINE EQUIPMENT. | 14929 |  | EX1 | 08/21/2022 | ADC-58L | COMP | ABHD-169
2303 | 14929 | 7700 | RPCS | C | 4245 | SMCOM | RIH WITH HLWM SMART COMPLETION ON 4-1/2" TBG FR/5666 FT T/7700 FT FT ( TOTAL 100 OUT OF 155 JT'S).- SLOW DOWN RUNNING SPEED WHILE 7" ASSY. PASSING 9 5/8" ASSY. PASSING DV. & 7" TOL.- INSTALLED CABLE CLAMP " CCCP'S " ON EACH TUBING JOINT CONNECTIONS.- TBG OPTIMUM M/U TORQUE: 4770 FT.LB. ( USING JAM UNIT).- FILLED UP STRING WHILE RIH EVERY 10 JOINTS. | 14929 | 5666 | RIG | 08/21/2022 | ADC-58L | COMP | ABHD-169
2304 | 14929 |  | DTU | C | 4245 | DRFT | R/U EXPRO SLICK LINE PCE, P/T SLICK LINE BOP & LUBRICATOR TO 300 / 2000 PSI FOR 10 MINS FOR MIN EACH, HOLD-OK.- RUN #7, DRIFT 4-1/2" TBG T/ 2040 FT W/ 3.833" DRIFT, POOH & R/D SLICKLINE EQUIPMENT. | 14929 |  | EX1 | 08/21/2022 | ADC-58L | COMP | ABHD-169
2305 | 14929 | 8944 | RPCS | C | 4245 | SMCO2 | RIH WITH HLWM SMART COMPLETION ON 4-1/2" TBG FR/7700 FT T/8944 FT ( TOTAL 130 OUT OF 155 JT'S).----INCT@RPT.- INSTALLED CABLE CLAMP " CCCP'S " ON EACH TUBING JOINT CONNECTIONS.- TBG OPTIMUM M/U TORQUE: 4770 FT.LB. ( USING JAM UNIT).- FILLED UP STRING WHILE RIH EVERY 10 JOINTS.- CONTINUOUSLY PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM DURING ALL PAST OPERATION, WELL ON TOTAL LOSSES. | 14929 | 7700 | RIG | 08/21/2022 | ADC-58L | COMP | ABHD-169
2306 | 56.25 | OOS | Category | DOOS ID | COM | Out of Scope Summary | RUN SLB HLWM SMART COMPLETION | 24 | 4245 | 19 Aug 0100 | 08/21/2022 | ADC-58L | Type | ABHD-169
2307
2308
2309 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADC-60 | Hrs | ABSF-216
2310 | FOT | BAL | 262.5 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/21/2022 | ADC-60 | 24 | ABSF-216
2311 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADC-66L | Hrs | UTMN-3155
2312 | FOT | RIG | 3.5 | 21 Aug 1930 - 2300 | 13440 | 901062 | - OBSERVED WASH PIPE LEAKING DECISION TO POOH TO SHOE TO CHANGE WASH PIPE. | RR | TDS |  | 08/21/2022 | ADC-66L | 3.5 | UTMN-3155
2313 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADES-889 | Hrs | HRDH-2122
2314 | FOT | RIG | 11.5 | 21 Aug 0930 - 2100 | 7464 | 901114 | WHILE POOH LOWER GEAR CLATCH CHAIN OF DROWWORKS BROKEN. | RR | DWKS |  | 08/21/2022 | ADES-889 | 11.5 | HRDH-2122
2315 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADM-266 | Hrs | MRJN-309
2316 | STOP | ARM | 3 | 21 Aug 0730 - 1030 | 7580 | 901118 | TROUBLE SHOOTING V-SAT SYSTEM | WO | NA |  | 08/21/2022 | ADM-266 | 3 | MRJN-309
2317 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADM-337 | Hrs | MRJN-900
2318 | FOT | BCT | 14.25 | 20 Aug 1330 - 0915 | 0 | 901089 | RE-TEST BAKER CTU VALVES AND LINES REQUIRING CHANGE OUT DUE TO PRIOR LEAKS, TROUBLE SHOOT LEAKING HCR ON BOT QAUD BOPS | TF | CTBG |  | 08/21/2022 | ADM-337 | 3.75 | MRJN-900
2319 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADM-511 | Hrs | MRJN-799
2320 | FOT | MSD | 1 | 21 Aug 1130 - 1230 | 0 | 901120 | AL MASAOOD TROUBLE SHOOT NON FUNCTIONING JAM UNIT WITHOUT SUCCESS. UNIT NOT POWERING UP. | TF | CTRQ |  | 08/21/2022 | ADM-511 | 1 | MRJN-799
2321 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ADM-655 | Hrs | SFNY-306
2322 | WOPF | AP2 | 55.5 | 19 Aug 2130 - 0500 | 0 | 901075 | WAIT ON SFNY GOSP TO ACCEPT FLOW BACK OPS, MEAN WHILE REQUESTED AND MOBILIZED NEW SET UP FOR ZERO FLARING EQPT. | WO | NA |  | 08/21/2022 | ADM-655 | 24 | SFNY-306
2323 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | AOD-1 | Hrs | ZULF-694
2324 | STCT | ARM | 120.25 | 16 Aug 0930 - 2045 | 7478 | 900936 | WHILE RIH W/ 4-1/2" BAKER ICD SCREENS, HOLE BECAME PACKED OFF & STRING STUCK. | STUK | SCRN |  | 08/21/2022 | AOD-1 | 15.5 | ZULF-694
2325 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ARO-2003 | Hrs | MNIF-733
2326 | WOPF | AP2 | 144 | 16 Aug 0500 - 0500 | 0 | 900956 | WAIT ON FIELD SERVICE TO INSTALL ISOLATION PLUGS. | WO | NA |  | 08/21/2022 | ARO-2003 | 24 | MNIF-733
2327 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ARO-4001 | Hrs | MRJN-532
2328 | FOT | RIG | 2.25 | 21 Aug 0630 - 0845 | 6876 | 901115 | ATTEMPT TO CIRCULATE WITH TRIP TANK, FOUND LINES PLUGGED WITH CMT, CLEAR SAME, OK. | RR | FL |  | 08/21/2022 | ARO-4001 | 2.25 | MRJN-532
2329 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | DQ-49L | Hrs | HRDH-575
2330 | FOT | BAW | 11 | 21 Aug 1200 - 2300 | 8100 | 901021 | WHILE RIH W/ BKR LOGGING TOOL (IMAGE /6 ARM CALIPER) ON 4" DP T/ 8,100' HAD SHORT IN E/L CABLE (ELECTRICAL CABLE LEAKAGE),POOH INSIDE LINER CSG SHOE,UNLATCH CABLE AND REPLACE W/L UNIT WITH ANOTHER UNIT. | TF | WLT |  | 08/21/2022 | DQ-49L | 11 | HRDH-575
2331 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ENS-108 | Hrs | ZULF-2015
2332 | GRF | RIG | 42.25 | 20 Aug 1045 - 0500 | 7186 | 901048 | OBSERVED FLOW LINE BETWEEN SHAKER AND PIT ROOM PLUGGED. | UPRA | FL |  | 08/21/2022 | ENS-108 | 24 | ZULF-2015
2333 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | MP-1 | Hrs | MRJN-78
2334 | FOT | NRT | 485.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/21/2022 | MP-1 | 24 | MRJN-78
2335 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | NBR-263S | Hrs | QTIF-736
2336 | OTH | RIG | 48 | 20 Aug 0500 - 0500 | 4500 | 901090 | UNPLANED MAITENANCE DUE TO CAT III INSPECTION EXPIRED FOR CROWN BLOCK, TRAVELLING BLOCKS AND HOOK, ELEVATOR LINKS, ELEVATORS, MANUAL TONGS & MUD PUMPS. | UPRA | NA |  | 08/21/2022 | NBR-263S | 24 | QTIF-736
2337 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | NBR-654S | Hrs | HRDH-1150
2338 | FOT | PKP | 417.75 | 02 Aug 1915 - 0500 | 12807 | 900388 | FAIL TO SET THE LINER HANGER, CMT PLUG WAS NOT BUMPED AND GOT BACKFLOW, FAIL TO SET LINER TOP PACKER, POOH R&R TOOL DAMAGED. INVESTIGATION AT WORKSHOP ATTENDED BY DTD CONCLUDED IMPROPER MAKE UP OF LH BALL SEATS. BACK FLOW IS SUSPECTED FROM LEAK IN THE SETTING TOOL. | TF | HGRL |  | 08/21/2022 | NBR-654S | 24 | HRDH-1150
2339 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | PA-326S | Hrs | SHDN-22
2340 | FOT | RIG | 2 | 21 Aug 0300 - 0500 | 1812 | 901119 | BIG LEACKAGE ON BELL NIPPLE | BOP | BOP |  | 08/21/2022 | PA-326S | 2 | SHDN-22
2341 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | PN-9 | Hrs | MRJN-673
2342 | CFST | HCM | 176.25 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/21/2022 | PN-9 | 24 | MRJN-673
2343 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | RBP-50A | Hrs | HSBH-52
2344 | WTHR | ARM | 22 | 09 Aug 0500 - 1830 | 12595 | 900658 | WAIT ON WEATHER, UNABLE TO FLOWBACK DUE TO UNFAVORABLE WIND CONDITION. | WON | NA |  | 08/21/2022 | RBP-50A | 9 | HSBH-52
2345 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SINO-10 | Hrs | JLDI-38
2346 | XTRI | SWL | 5.5 | 20 Aug 0030 - 0600 | 10858 | 901058 | WHILE RIGGING UP SCHLUMBERGER WIRELINE TOOLS PRIOR RUNNING 4-1/2" BRIDGE PLUG , THE WL ENGINEER RECOGNIZED THAT HE BROUGHT THE WRONG TOOL FOR THE JOB. | JF | WLT |  | 08/21/2022 | SINO-10 | 1 | JLDI-38
2347 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SINO-29N | Hrs | SFNY-2005
2348 | PCPF | ARM | 382 | 05 Aug 0500 - 1100 | 4660 | 900602 | HOLE NOT STABLE (SHALE CAVINGS), DIFFICULTY IN RIH OR POH WITH REAMING BHA, INCREASED MW TO CONTROL SHALE, CLEARED BHA MANY TIMES WITH SWEEPS, ROTATION & PIPE MOVEMENT.... EVENTUALY BECAME STUCK AT WINDOW WHILE ATTEMTING TO POH. PACKED OFF ABOVE DLR AT WINDOW DURING PUMPING OUT OF HOLE AND BACK REAMING OPERATIONS. | TH | NA |  | 08/21/2022 | SINO-29N | 6 | SFNY-2005
2349 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SINO-36L | Hrs | ANDR-32
2350 | FOT | RIG | 7 | 21 Aug 1300 - 2000 | 10875 | 901065 | OBSERVED TDS WASHPIPE LEAKAGE. | RR | TDS |  | 08/21/2022 | SINO-36L | 7 | ANDR-32
2351 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SINO-5L | Hrs | UTMN-639
2352 | FOT | SPS | 12 | 21 Aug 1700 - 0500 | 9402 | 901066 | HAD SPPERY MWD ALD TOOL MULFUNCTION, TROUBLE SHOOTING- MWD ALD TOOL FAILURE. | BHA | MWD |  | 08/21/2022 | SINO-5L | 12 | UTMN-639
2353 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SND-2004 | Hrs | BRRI-1148
2354 | FOT | SWT | 137.5 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/21/2022 | SND-2004 | 24 | BRRI-1148
2355 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SND-2005 | Hrs | MHKK-2
2356 | FOT | HCB | 6.5 | 21 Aug 2200 - 0430 | 14000 | 901095 | ATTEMPT TO SET HALLIBURTON 7" EZSV AT 14,000' WITH NO SUCCESS. | TF | BP |  | 08/21/2022 | SND-2005 | 6.5 | MHKK-2
2357 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SND-2007 | Hrs | AWTD-104001
2358 | FOT | BHI | 52.5 | 19 Aug 0030 - 0500 | 18320 | 901082 | BAKER LOST COMMUNICATION WITH THE AUTOTRAK RSS TO THE MWD TOOL. | BHA | RSS |  | 08/21/2022 | SND-2007 | 24 | AWTD-104001
2359 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SP-167 | Hrs | HRDH-218
2360 | ORDS | ARN | 207.5 | 10 Aug 0800 - 1330 | 5008 | 900735 | LOST TIME ON GOC DUE TO WRONG PLACEMENT OF WELL | WO | NA |  | 08/21/2022 | SP-167 | 8.5 | HRDH-218
2361 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SP-257 | Hrs | HZEM-162412
2362 | FOT | BHI | 18.25 | 20 Aug 1645 - 1130 | 9348 | 901091 | BAKER RSS FAILURE. | BHA | RSS |  | 08/21/2022 | SP-257 | 6 | HZEM-162412
2363 | FOT | BHI | 17.25 | 21 Aug 1015 - 0330 | 9353 | 901116 | BAKER BACK UP RSS FAILED AGAIN, POH AND CHANGE OUT RSS. | BHA | RSS |  | 08/21/2022 | SP-262 | 17.25 | JNAB-152802
2364 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SP-262 | Hrs | JNAB-152802
2365 | FOT | BHI | 16.5 | 20 Aug 1430 - 0700 | 9201 | 901093 | RSS FAILURE, LOST DATA TRANSMISSION, POH TO CHANGE RSS. | BHA | RSS |  | 08/21/2022 | SP-262 | 2 | JNAB-152802
2366 | FOT | BHI | 17.25 | 21 Aug 1015 - 0330 | 9353 | 901116 | BAKER BACK UP RSS FAILED AGAIN, POH AND CHANGE OUT RSS. | BHA | RSS |  | 08/21/2022 | SP-262 | 17.25 | JNAB-152802
2367 | 6491 |  | CORE | E | 4186 | CORC | NOV CUT 6-1/8" X 2 5/8" CORE RUN #2 FROM 6443' TO 6491' (51 FT) W/70 PCF POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, (RPM: 65 - TQ 2-3 KLFTLB) & (GPM: 170 - PRESS 550 PSI)-LOST TOURQUE & ROP, TROUBLE SHOOT SEVERAL TIMES WITHOUT PROGRESS GOT JAMMING -CORE JAMMED AFTER CUTTING 51' @ 6491' AND THE PLAN WAS TO CUT 60 FT. | 6443 |  | NOC | 08/21/2022 | SP-53L | CORE | HRDH-528
2368 | 6491 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTM UP WITH 120 GPM @ 500 PSI WITH FULL RETURNS. | 6491 |  | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2369 | 6491 |  | SDR1 | E | 4186 | NA | FLOW CHECK-WELL STATIC OK. | 6491 |  | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2370 | 6491 | 6374 | TO | E | 4186 | STDP | HPJSM, POOH 6 1/8" NOV CORING ASSY. TO/7" CSG SHOE @ 6374' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6491 | 6491 | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2371 | 6491 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT 7" CSG SHOE - WELL STATIC OK | 6491 |  | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2372 | 6491 | 5900 | TO | E | 4186 | STDP | HPJSM, POOH 6 1/8" NOV CORING ASSY. FROM / 7" CSG SHOE @ 6374' TO 5900' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6491 | 6374 | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2373 | 6491 |  | SDR1 | E | 4186 | NA | FLOW CHECK AFTER PULL 5 STDS WELL STATIC OK. | 6491 |  | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2374 | 6491 | 1597 | TO | E | 4186 | STDP | POOH 6 1/8" NOV CORING ASSY. TO 7" TOL@ 1597' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6491 | 5900 | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2375 | 6491 |  | SDR1 | E | 4186 | NA | FLOW CHECK @7" TOL WELL STATIC OK. | 6491 |  | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2376 | 6491 | 615 | TO | E | 4186 | STDP | CONT'D POOH 6-1/8" NOV CORING ASSY. RUN #2 TO 615' CONTROLLED SPEED 6MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6491 | 1597 | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2377 | 6491 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT TOP BHA - WELL STATIC OK.-CHECKING FOR H2S-ZERO H2S READING. | 6491 |  | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2378 | 6491 |  | HT | E | 4186 | CORC | HPJSM, CON'T POOH 6-1/8" NOV CORING ASSY. RUN #2 TO SURFACE CONTROLLED SPEED 6 MIN/STD SLIPS TO SLIPS.-RUN RIG FLOOR BUG BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.-ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.-DISCUSSED HSE ALERT 15-19 TRAPPED PRESSURE IN THE CORE INNER ALUMINUM BARREL.-L/D INNER BARREL,51 ' RECOVERED (100 % RECOVERY) FROM CORE RUN #2-CORE HEAD DULL : 1-1-WT-A-X-NO-TD | 6491 |  | NOC | 08/21/2022 | SP-53L | CORE | HRDH-528
2379 | 6491 |  | HT | E | 4186 | CORC | HPJSM, P/U & M/U 6-1/8" NOV CORE ASSY. RUN#3 -6-1/8" CORE HEAD + 4-3/4" CORE OUTER BARRELS & 3-3/8" INNER BARRELS (60FT) + FLOAT SUB W/ FLAPPER TYPE FLOAT VALVE (BALL SIZE IS 1")+15 X 4-3/4" DC'S+ 4-3/4" DRILLING JAR+2 X 4 3/4" DC'S +XO+ DP'S. | 6491 |  | NOC | 08/21/2022 | SP-53L | CORE | HRDH-528
2380 | 6491 | 6374 | TI | E | 4186 | STDP | RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 615' TO 7" CSG SHOE @6374'.-GENTLY PASSED 7" TOL & SHOE TRACK. | 6491 | 615 | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2381 | 6491 |  | CIRC | E | 4186 | MPMP | CONTD RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 6374' TO CORE POINT @ 6491'.-WASH AND REAM DOWN TILL TAG BTM @6491' | 6491 |  | RIG | 08/21/2022 | SP-53L | CORE | HRDH-528
2382 | 116.25 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 24 | 4186 | 13 Aug 0230 | 08/21/2022 | SP-53L | Type | HRDH-528
2383
2384
2385 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SP-58 | Hrs | HRDH-795
2386 | FOT | RIG | 1.5 | 21 Aug 1745 - 1915 | 4070 | 901025 | MAINTENANCE FOR POWER TONG. | RR | HSYS |  | 08/21/2022 | SP-58 | 1.5 | HRDH-795
2387 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SSA-102 | Hrs | QTIF-693
2388 | HERR | RIG | 5.25 | 21 Aug 1530 - 0500 | 10319 | 901024 | RIG OVER PULL ON WEAR BUSHING WHILE RETRIEVAL PROCESS, RESULTING IN BREAKING THE TWO SIDE BOLTS, TWO BOLTS LOST IN HOLE. | WH | WBSH |  | 08/21/2022 | SSA-102 | 5.25 | QTIF-693
2389 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SSA-5964 | Hrs | UTMN-1973
2390 | UNKN | RIG | 1 | 21 Aug 2300 - 0000 | 2100 | 901061 | WHILE PICKING UP 5" DP FROM RACK, A JOINT OF DP SLID INTO THE SUB-STRUCTURE. | HSEI | NA |  | 08/21/2022 | SSA-5964 | 1 | UTMN-1973
2391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | SSA-5969 | Hrs | UTMN-3148
2392 | STBH | ARM | 328.75 | 06 Aug 1315 - 2330 | 2262 | 900580 | 16" ROTARY BHA STUCK @ 3,220' ( TOP OF SHU'AIBA FM ) | STUK | BHA |  | 08/21/2022 | SSA-5969 | 18.5 | UTMN-3148
2393 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | STY-038 | Hrs | ZULF-2089
2394 | HINW | HWP | 19 | 21 Aug 1000 - 0500 | 5537 | 901117 | HALLIBURTON MADE ANOTHER CORRELATION PASS BELOW PUNCHING DEPTH, CAUSING THE TOOL TO GET STUCK AT X-NIPPLE | STUK | WLT |  | 08/21/2022 | STY-038 | 19 | ZULF-2089
2395 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/21/2022 | ZPEC-2 | Hrs | AMAD-815
2396 | HYFM | ARM | 63.5 | 19 Aug 1330 - 0500 | 915 | 901023 | 0 PRODUCTION | HC | NA |  | 08/21/2022 | ZPEC-2 | 24 | AMAD-815
2397 | HERR | TK3 | 19.5 | 21 Aug 1045 - 0615 | 12747 | 901022 | OBSERVED STRING PLUGGED WITH LCM MATERIAL 2.5 FT ABOVE FLOAT VALVE IN BIT SUB. | JF | NA |  | 08/22/2022 | ADC-43L | 1.25 | UTMN-3118
2398 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ADC-43L | Hrs | UTMN-3118
2399 | FRFM | TK3 | 235 | 11 Aug 2130 - 0500 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/22/2022 | ADC-43L | 22.75 | UTMN-3118
2400 | HERR | TK3 | 19.5 | 21 Aug 1045 - 0615 | 12747 | 901022 | OBSERVED STRING PLUGGED WITH LCM MATERIAL 2.5 FT ABOVE FLOAT VALVE IN BIT SUB. | JF | NA |  | 08/22/2022 | ADC-43L | 1.25 | UTMN-3118
2401 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ADC-50 | Hrs | SFNY-1176
2402 | WC20 | ARM | 8.25 | 22 Aug 1015 - 1830 | 765 | 901173 | WHILE POH WITH 10-5/8" X12-1/4" BHA, OBSERVED 90% LEL READING .SHUT-IN WELL ON UPPER PIPE RAMS AND SECURED WELL. | WCNT | NA |  | 08/22/2022 | ADC-50 | 8.25 | SFNY-1176
2403 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ADC-55L | Hrs | UTMN-3171
2404 | STBH | TK3 | 550 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/22/2022 | ADC-55L | 24 | UTMN-3171
2405 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ADC-56L | Hrs | UTMN-3069
2406 | IDCS | TK3 | 34.75 | 21 Aug 1715 - 0430 | 12333 | 901070 | 9 5/8"LINER HANGER POLSH MILL CAME OOH WITH WEAR ON THE MILL FROM 10.1" TO 9.9" | WI | NA |  | 08/22/2022 | ADC-56L | 23 | UTMN-3069
2407 | 13523 | 9968 | RPCS | C | 4245 | SPCOM | RIH WITH HLWM SMART COMPLETION ON 4-1/2" TBG FR/8944 FT T/9968 FT ( TOTAL 155 JT'S).- INSTALLED CABLE CLAMP " CCCP'S " ON EACH TUBING JOINT CONNECTIONS.- TBG OPTIMUM M/U TORQUE: 4770 FT.LB. ( USING JAM UNIT).- FILL UP STRING WHILE RIH EVERY 10 JOINTS. | 13523 | 8944 | RIG | 08/22/2022 | ADC-58L | COMP | ABHD-169
2408 | 13523 |  | DTU | C | 4245 | DRFT | HELD PJSM R/U EXPRO SLICK LINE PCE, P/T SLICK LINE BOP & LUBRICATOR TO 300 / 2000 PSI FOR 10 MINS FOR MIN EACH, HOLD-OK.- RUN #8, DRIFT 4-1/2" TBG T/ 2300 FT W/ 3.833" DRIFT, POOH & L/D DRIFT TOOL. | 13523 |  | EX1 | 08/22/2022 | ADC-58L | COMP | ABHD-169
2409 | 13523 |  | RTRV | C | 4245 | PLUGT | EXPRO M/U PUMP THROUGH PLUG RETRIEVING TOOL, RIH ( RUN #9), RETRIEVED PLUG, POOH TO SURFACE & R/D SLICKLINE EQUIPMENT. | 13523 |  | EX1 | 08/22/2022 | ADC-58L | COMP | ABHD-169
2410 | 13523 |  | PJSM | C | 4245 | PKR | HELD PJSM PRIOR TO SET 7" & 9 5/8" HLWM SMART COMPLETION PKR'S ASSIGNED ROLES, RESPONSIBILITIES & DISCUSSED GAME PLAN. | 13523 |  | SCP | 08/22/2022 | ADC-58L | COMP | ABHD-169
2411 | 13523 |  | HT | C | 4245 | PEL | CHANGED HANDLING TOOLS FROM 4-1/2" TBG TO 5" DP'S . | 13523 |  | RIG | 08/22/2022 | ADC-58L | COMP | ABHD-169
2412 | 13523 |  | PTST | C | 4245 | MPMP | R/U SETTING ASSY. AS FOLLOW:- 4-1/2" NVAM X 4 1/2" IF " X/O, 4 1/2"IF TIW, 5" SES, 4 1/2" IF TIW & 5" PJ, CONNECTED SURFACE LINES TO CEMENT UNIT, FLUSHED SAME WITH 5BBLS WTR & P/T SAME TO 500/4500 PSI FOR 10 MIN EACH-HOLD OK. | 13523 |  | RIG | 08/22/2022 | ADC-58L | CSG | ABHD-169
2413 | 13523 |  | CIRC | C | 4245 | MPMP | PUMPED STRING CAPACITY (130 BBLS) 77 PCF FRESH BRINE INTO TBG STG AT FR 2 BPM & SPP 20 PSI.- PUMPED 77 PCF BRINE INTO ANNULUS AT 2 BPM DURING ALL PAST OPERATION, WELL ON TOTAL LOSSES. | 13523 |  | RIG | 08/22/2022 | ADC-58L | COMP | ABHD-169
2414 | 13523 | 6458 | SET | C | 4245 | PKR | SET 7" & 9 5/8" HLWM SMART COMPLETION PKR'S AS FOLLOW:- - PUMPED 77 PCF BRINE INSIDE TUBING AT 1 BPM (15 BBLS) MEANWHILE CYCLED & CLOSED TRFC#1 & TRFC#2.- PRESS. UP TBG TO 3600 PSI & HOLD 15 MINUTES. SET PACKERS AS PER COMPL. ENG, BLED OFF SLOWLY TO ZERO.- FILLED TCA & OBSERVED FULL RETURNS ON TRIP TANK AFTER 65 BBLS. - PERFORMED PUSH TEST ON PACKER'S BY SLACK OFF ALL WEIGHT BELOW 9 5/8" PKR (40 KLB)+10 KLB (HKLD = 112 KLB), PICKED UP 10 KLB TO HAVE HLWM AT NEUTRAL (HKLD = 122 KLB). | 13523 | 6458 | SCP | 08/22/2022 | ADC-58L | COMP | ABHD-169
2415 | 13523 |  | PTST | C | 4245 | PKR | LINED UP TEST UNIT TO TCA & P/T TCA UP TO 500 PSI FOR 10 MIN-HOLD OK. | 13523 |  | RIG | 08/22/2022 | ADC-58L | COMP | ABHD-169
2416 | 13523 |  | OTH | C | 4245 | PBR | PRESSURED UP TCA UP TO 2000 PSI, HELD FOR 5 MIN, OPENED ANNULAR BOP, SLACKED OFF 10 KLBS. RELEASED HLWM RUNNING TOOLS. CONFERMED RELESE BY P/U STG 30 FT. | 13523 |  | SCP | 08/22/2022 | ADC-58L | COMP | ABHD-169
2417 | 13523 |  | OTH | C | 4245 | SFLN | R/D SURFACE LINES & L/D SETTING ASSY. CHANGED HANDLING TOOLS FROM 4-1/2" TBG TO 5" DP'S.- MONITORED WELL ON TRIP TANK; WELL STATIC. | 13523 |  | RIG | 08/22/2022 | ADC-58L | COMP | ABHD-169
2418 | 13523 |  | PJSM | C | 4245 | TBG | HELD PRE-JOB SAFETY PRIOR TO POOH HLWM RUNNING TOOL ON 4 1/2" TBG.- MEANWHILE CONDUCT FLOW CHECK, WELL STATIC. | 13523 |  | RIG | 08/22/2022 | ADC-58L | COMP | ABHD-169
2419 | 13523 | 4070 | TO | C | 4245 | TBG | POOH HLWM RUNNING TOOL ON 4-1/2" 12.6# L80 NVAM TUBING FROM 6433 FT TO 4070 FT (57 OF 155 JTS).-----INCT@RPT.- MONITORED WELL ON TRIP TANK & TRIP SHEET, WELL-STATIC. | 13523 | 6433 | RIG | 08/22/2022 | ADC-58L | COMP | ABHD-169
2420 | 79.25 | OOS | Category | DOOS ID | COM | Out of Scope Summary | RUN SLB HLWM SMART COMPLETION | 23 | 4245 | 19 Aug 0100 | 08/22/2022 | ADC-58L | Type | ABHD-169
2421
2422
2423 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ADC-60 | Hrs | ABSF-216
2424 | FOT | BAL | 286.5 | 08 Aug 0500 - 0500 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/22/2022 | ADC-60 | 24 | ABSF-216
2425 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ADES-174 | Hrs | GHZL-72
2426 | SFHS | BFW | 23.5 | 22 Aug 0530 - 0500 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/22/2022 | ADES-174 | 23.5 | GHZL-72
2427 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ADM-510 | Hrs | ABSF-225
2428 | UDWL | SDM | 1 | 22 Aug 1000 - 1100 | 11500 | 901179 | RECYCLE PUMP & DOWNLINK TO CHANGE TOOLS SETTINGS. | DD | RSS |  | 08/22/2022 | ADM-510 | 1 | ABSF-225
2429 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ADM-657 | Hrs | SFNY-1228
2430 | FOT | RIG | 3 | 22 Aug 1500 - 1800 | 110 | 901194 | LEAKS ON FLOW LINE SEALS | RR | FL |  | 08/22/2022 | ADM-657 | 3 | SFNY-1228
2431 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ARO-2003 | Hrs | MNIF-733
2432 | WOPF | AP2 | 168 | 16 Aug 0500 - 0500 | 0 | 900956 | WAIT ON FIELD SERVICE TO INSTALL ISOLATION PLUGS. | WO | NA |  | 08/22/2022 | ARO-2003 | 24 | MNIF-733
2433 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ARO-3002 | Hrs | MRJN-813
2434 | WTHR | ARM | 10.25 | 22 Aug 0745 - 1800 | 8852 | 901136 | WIND SPEED TO LOW TO COMMENCE FLKOW BACK OPERATION. | WON | NA |  | 08/22/2022 | ARO-3002 | 10.25 | MRJN-813
2435 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | BCTD-4 | Hrs | GHZL-67
2436 | FOT | BHI | 14 | 22 Aug 0500 - 1900 | 0 | 901068 | AUGUS NOT WORKING/ NO COMMUNICATIONS WITH BHA: OPEN BULKHEAD, FOUND CONDUCTORS WIRE HAD BROKEN OUTER COATING. REASSEMBLE CONDUCTOR WIRES. | BHA | MWD |  | 08/22/2022 | BCTD-4 | 14 | GHZL-67
2437 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | DPS-46 | Hrs | UTMN-102001
2438 | SRVC | GOC | 2 | 22 Aug 2015 - 2215 | 950 | 901174 | WAIT ON AL-GAITH 7" LINER RUNNING SERVICE | WO | NA |  | 08/22/2022 | DPS-46 | 2 | UTMN-102001
2439 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | DPS-74 | Hrs | NJYN-33
2440 | XTTE | BCR | 4 | 22 Aug 1700 - 2100 | 4572 | 901069 | EXCESSIVE TIME TO RUN 2-3/8" TBG DUE TO BAKER TONGS EXPERIENCING MULTIPLE TONG FAILURES. (USED 3 POWER TONGS TO COMPLETE JOB) | TF | CTRQ |  | 08/22/2022 | DPS-74 | 4 | NJYN-33
2441 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | DQ-48 | Hrs | KHRS-495
2442 | FOT | BHI | 20.5 | 22 Aug 0830 - 0500 | 7163 | 901193 | WHILE DRILLING HAD A SUDDEN INCREASE IN SPP (+/- 1,000 PSI) IN SPP AND OBSERVED MOTOR RUBBERS ON SHALE SHAKERS, DECISION MADE TO POOH TO CHANGE MOTOR. | BHA | MMOT |  | 08/22/2022 | DQ-48 | 20.5 | KHRS-495
2443 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ENS-108 | Hrs | ZULF-2015
2444 | GRF | RIG | 66.25 | 20 Aug 1045 - 0500 | 7186 | 901048 | OBSERVED FLOW LINE BETWEEN SHAKER AND PIT ROOM PLUGGED. | UPRA | FL |  | 08/22/2022 | ENS-108 | 24 | ZULF-2015
2445 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | ENS-141 | Hrs | MRJN-3022
2446 | FOT | RIG | 7 | 22 Aug 0945 - 1645 | 1194 | 901158 | OBSERVED MUD LEKAGE FROM KFDJ VENT LINE ON STBD SIDE, TROUBLESHOOT ACTUATOR BALL VALVE NO SUCCESS, | BOP | DVRT |  | 08/22/2022 | ENS-141 | 7 | MRJN-3022
2447 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | HI-2 | Hrs | BRRI-433
2448 | FOT | BCR | 1.5 | 22 Aug 2245 - 0015 | 7436 | 901178 | UNABLE TO OPERATE THE CRT. RELEASING MECHANISM MALFUNCTIONING. R/D CRT. | TF | CRT |  | 08/22/2022 | HI-2 | 1.5 | BRRI-433
2449 | FOT | RIG | 3 | 22 Aug 0200 - 0500 | 2165 | 901155 | DRILLER CONSOLE GAUGES WRONG READINGS (ROTARY TORQUE GAUGE & PUMP PRESSURE GAUGE). RETURN FLOW GAUGE WRONG READINGS. | RR | HSYS |  | 08/22/2022 | JACK-202 | 3 | THRY-829
2450 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | JACK-202 | Hrs | THRY-829
2451 | FOT | RIG | 10 | 22 Aug 1130 - 2130 | 2165 | 901152 | LEAK IN 18 5/8" CUP TESTER & TEST PUMP | TF | TESTT |  | 08/22/2022 | JACK-202 | 10 | THRY-829
2452 | FOT | RIG | 3 | 22 Aug 0200 - 0500 | 2165 | 901155 | DRILLER CONSOLE GAUGES WRONG READINGS (ROTARY TORQUE GAUGE & PUMP PRESSURE GAUGE). RETURN FLOW GAUGE WRONG READINGS. | RR | HSYS |  | 08/22/2022 | JACK-202 | 3 | THRY-829
2453 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | MP-1 | Hrs | MRJN-78
2454 | FOT | NRT | 509.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/22/2022 | MP-1 | 24 | MRJN-78
2455 | OTH | RIG | 58.25 | 20 Aug 0500 - 1515 | 4500 | 901090 | UNPLANED MAITENANCE DUE TO CAT III INSPECTION EXPIRED FOR CROWN BLOCK, TRAVELLING BLOCKS AND HOOK, ELEVATOR LINKS, ELEVATORS, MANUAL TONGS & MUD PUMPS. | UPRA | NA |  | 08/22/2022 | NBR-263S | 10.25 | QTIF-736
2456 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | NBR-263S | Hrs | QTIF-736
2457 | STBH | ARM | 239.75 | 29 Jul 0230 - 1700 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/22/2022 | NBR-263S | 1.75 | QTIF-736
2458 | CPNF | NCS | 156 | 11 Aug 0330 - 0500 | 5145 | 900810 | LOST TIME ON NPS CEMENTING DUE TO SOFT CMT WHILE DRILL OUT CMT PLUG & FAILURE ON ZONAL ISOLATION AFTER CHECK CMT INTEGRITY, PLAN TO D/O CMT PLUG & SPOT ANOTHER CMT PLUG. | CMT | NA |  | 08/22/2022 | NBR-263S | 12 | QTIF-736
2459 | OTH | RIG | 58.25 | 20 Aug 0500 - 1515 | 4500 | 901090 | UNPLANED MAITENANCE DUE TO CAT III INSPECTION EXPIRED FOR CROWN BLOCK, TRAVELLING BLOCKS AND HOOK, ELEVATOR LINKS, ELEVATORS, MANUAL TONGS & MUD PUMPS. | UPRA | NA |  | 08/22/2022 | NBR-263S | 10.25 | QTIF-736
2460 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | NBR-783S | Hrs | NJYN-93
2461 | FOT | RIG | 2 | 22 Aug 1600 - 1800 | 16099 | 901160 | REPAIR ON TDS SERVICE LOOP PROBLEM. | RR | TDS |  | 08/22/2022 | NBR-783S | 2 | NJYN-93
2462 | LHFL | RIG | 3 | 22 Aug 0800 - 1100 | 1000 | 901154 | TROUBLE SHOOT AND REPAIR LEAKS ON REMOTE BOP PANEL, PANEL KOOMEY LINES AND DIVERTER LINES. | RR | HSYS |  | 08/22/2022 | NBR-987S | 3 | JLMN-35
2463 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | NBR-987S | Hrs | JLMN-35
2464 | XTRI | RIG | 3 | 22 Aug 0500 - 0800 | 1000 | 901030 | EXCESSIVE TIME TO R/U BELL NIPPLE | JF | BOP |  | 08/22/2022 | NBR-987S | 3 | JLMN-35
2465 | LHFL | RIG | 3 | 22 Aug 0800 - 1100 | 1000 | 901154 | TROUBLE SHOOT AND REPAIR LEAKS ON REMOTE BOP PANEL, PANEL KOOMEY LINES AND DIVERTER LINES. | RR | HSYS |  | 08/22/2022 | NBR-987S | 3 | JLMN-35
2466 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | PA-326S | Hrs | SHDN-22
2467 | FOT | RIG | 3.5 | 22 Aug 0800 - 1130 | 2050 | 901133 | TOP DRIVE STOP WORKING INCOODER PROBLEM | RR | TDS |  | 08/22/2022 | PA-326S | 3.5 | SHDN-22
2468 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | PN-9 | Hrs | MRJN-673
2469 | CFST | HCM | 200.25 | 14 Aug 2045 - 0500 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/22/2022 | PN-9 | 24 | MRJN-673
2470 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | RBP-50A | Hrs | HSBH-52
2471 | WTHR | ARM | 35.5 | 09 Aug 0500 - 1830 | 12595 | 900658 | WAIT ON WEATHER, UNABLE TO FLOWBACK DUE TO UNFAVORABLE WIND CONDITION. | WON | NA |  | 08/22/2022 | RBP-50A | 13.5 | HSBH-52
2472 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SINO-12L | Hrs | HWYH-220
2473 | FOT | RIG | 5 | 22 Aug 1330 - 1830 | 3993 | 901071 | H2S SYSTEM MALFUNTION | RR | RSSS |  | 08/22/2022 | SINO-12L | 5 | HWYH-220
2474 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SINO-33L | Hrs | HRDH-1542
2475 | FOT | RIG | 16 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/22/2022 | SINO-33L | 16 | HRDH-1542
2476 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SINO-43L | Hrs | UTMN-4809
2477 | IDPR | TK2 | 8 | 22 Aug 2100 - 0500 | 5731 | 901157 | WHILE MRSS DRLG, HAD MOTOR STALLS ON BTM & PRESSURE SPIKES OFF BTM. TROUBLESHOOT, FOUND RUBBER AT THE SHAKER. SUSPECT MOTOR FAILURE. | DSF | STRG |  | 08/22/2022 | SINO-43L | 8 | UTMN-4809
2478 | 7300 | 0 | LOG | E |  | WLT | HALL WL RECORD REPEAT PASS FROM 2800' TO 2400' & FROM 1180' TO 1080'. POH TO SURFACE & R/D WL TOOLS. | 7300 | 2800 | HWP | 08/22/2022 | SINO-45L | LOG | UTMN-1092
2479 | 7300 | 1500 | TI | N |  | STHDP | RIH 15 STND 4" HWDP BELOW RTTS. | 7300 | 0 | RIG | 08/22/2022 | SINO-45L | PA | UTMN-1092
2480 | 7300 | 200 | SET | N |  | RTTS | HPJSM, M/U, RIH & SET 9-5/8" RTTS PKR W/ STORM VALVE AT 200'. PT TO 1000 PSI. OK. RELEASE TOOL & POH TO SURFACE. PT RTTS PKR AND STORM VALVE TO 1000 PSI, OK. | 7300 | 0 | HCO | 08/22/2022 | SINO-45L | PA | UTMN-1092
2481 | 7300 |  | ND | N |  | BOP | HPJSM, DISCONNECTED EMERGENCY KILL LINE, BELL NIPPLE & FLOW LINE. HANGED BOP & MOVED BOP STACK AWAY FROM WH. | 7300 |  | RIG | 08/22/2022 | SINO-45L | BOP | UTMN-1092
2482 | 7300 |  | PJSM | N |  | NA | HPJSM, DIG 6 FT CELLAR & PERFORM WELLHEAD WORK.- PT 13" X 9" CCA TO 500 PSI W/ 1% B-1400 INHIBITED WATER, DROP TO 150 PSI THEN HOLD.- PT 9 5/8" CSG SLIPS TO 1000 PSI, HOLD.- UT INSPECTION FOR 18-5/8"CSG & LANDING BASE, FOUND BTM SECTION OF 18 5/8" CONDUCTOR IS CORRODED. | 7300 |  | TK1 | 08/22/2022 | SINO-45L | WH | UTMN-1092
2483 | 7300 |  | OTH | N | 4285 | NA | HPJSM, HOTHED PERFORM HOT TAPPING ON SEAL WIELDED 18-5/8" CSG. - WELD 1.5" BALL VALVE 4 FT BELOW LANDING BASE. - UT INSPECT WIELD, OK. PT WIELD TO 1200 PSI W/ N2, OK. - DRILL 18-5/8" SURFACE CSG & CHECK FOR PRESSURE, NO PRESSURE & NO GAS. | 7300 |  | HTD | 08/22/2022 | SINO-45L | PA | UTMN-1092
2484 | 7300 |  | PJSM | N |  | NA | HPJSM, CONTINUE WH WORK.- OPEN 2 WINDOWS (OPPOSITE SIDES) IN 18-5/8" CSG; NO CMT BETWEEN 13"&18".- UT INSPECT 13-3/8" CSG & FOUND IN GOOD CONDITION.- FILL 18-5/8" X 13-5/8" CCA WITH CMT.- REWELD WINDOWS & MPI INSPECT WELDS, OK.- N/D OLD GRAY TBG SPOOL, CUT & RESTUB 9-5/8" CSG STUB.- N/U NEW 13-5/8" X 11" 3M FMC TBG SPOOL & PT SEAL TO 1000 PSI, OK. | 7300 |  | TK1 | 08/22/2022 | SINO-45L | WH | UTMN-1092
2485 | 7300 |  | NU | N |  | BNIP | HPJSM, N/U BOP, BELL NIPPLE AND CONNECT EMERGENCY KILL LINES. | 7300 |  | RIG | 08/22/2022 | SINO-45L | BOP | UTMN-1092
2486 | 7300 |  | BOPT | N |  | BOP | HPJSM, M/U BOP TEST ASSY & PT BOP AND THS CONNECTIONS. L/D TEST ASSY. | 7300 |  | RIG | 08/22/2022 | SINO-45L | BOP | UTMN-1092
2487 | 7300 | 200 | SET | N |  | RTTS | RIH W/ RTTS RTRV TOOL, ENGAGE & UNSET 9-5/8'' RTTS PKR. POH & L/D RTTS PACKER. | 7300 | 0 | HCO | 08/22/2022 | SINO-45L | PA | UTMN-1092
2488 | 7300 | 0 | TO | N |  | STHDP | POH 4" HWDP TO SURFACE. | 7300 | 1500 | RIG | 08/22/2022 | SINO-45L | PA | UTMN-1092
2489 | 7300 |  | HT | N |  | BHA | HPJSM. P/U & M/U WFD 7'' WHIPSTOCK BHA. - 7" WHIPSTOCK BHA: 5.5" RHN WHIPSTOCK,6-1/8" LEAD MILL,6-1/8" FLEX MILL,1 JT 3-1/2" HWDP, MWD, DOWN HOLE SCREEN SUB, FLOAT SUB, X/O. - GAUGE LEAD & FLEX MILLS-OK - ALIGN MWD W/WHIPSTOCK & & SHALLOW TEST MWD TOOL, OK.. | 7300 |  | RIG | 08/22/2022 | SINO-45L | TINL | UTMN-1092
2490 | 7300 | 1900 | TI | N |  | STHDP | RIH W/ 7" WFD WHIPSTOCK & MILLING BHA. FILL STRG E/ 5 STDS....ONGOING @RPT | 7300 | 0 | RIG | 08/22/2022 | SINO-45L | TINL | UTMN-1092
2491 | 1 | OOS | Category | DOOS ID | WHWK | Out of Scope Summary | HOT TAPPING AT 18-5/8" CSG. | 1 | 4285 | 22 Aug 1500 | 08/22/2022 | SINO-45L | Type | UTMN-1092
2492
2493
2494 | FOT | SPS | 5.5 | 22 Aug 2330 - 0500 | 9876 | 901137 | LOST SIGNAL FOR ALL MWD/LWD TOOLS, TROUBLE SHOOTING-NO SIGNAL. | BHA | LWD |  | 08/22/2022 | SINO-5L | 5.5 | UTMN-639
2495 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SINO-5L | Hrs | UTMN-639
2496 | FOT | SPS | 23.5 | 21 Aug 1700 - 1630 | 9402 | 901066 | HAD SPPERY LWD ALD TOOL MULFUNCTION, TROUBLE SHOOTING- LWD ALD TOOL FAILURE. | BHA | LWD |  | 08/22/2022 | SINO-5L | 11.5 | UTMN-639
2497 | FOT | SPS | 5.5 | 22 Aug 2330 - 0500 | 9876 | 901137 | LOST SIGNAL FOR ALL MWD/LWD TOOLS, TROUBLE SHOOTING-NO SIGNAL. | BHA | LWD |  | 08/22/2022 | SINO-5L | 5.5 | UTMN-639
2498 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SL-7 | Hrs | ZULF-1335
2499 | WTHR | ARM | 22.75 | 20 Aug 0600 - 1745 | 0 | 901027 | WAIT ON WEATHER. | WON | NA |  | 08/22/2022 | SL-7 | 11 | ZULF-1335
2500 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SND-2004 | Hrs | BRRI-1148
2501 | FOT | SWT | 160.5 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/22/2022 | SND-2004 | 23 | BRRI-1148
2502 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SND-2005 | Hrs | MHKK-2
2503 | FOT | HCB | 17.25 | 21 Aug 2200 - 1745 | 14000 | 901095 | ATTEMPT TO SET HALLIBURTON 7" EZSV AT 14,000' WITH NO SUCCESS. | TF | BP |  | 08/22/2022 | SND-2005 | 10.75 | MHKK-2
2504 | FOT | BHI | 15 | 22 Aug 1400 - 0500 | 18640 | 901156 | BAKER LOST COMMUNICATION WITH THE AUTOTRAK RSS TO THE MWD TOOL. | BHA | MWD |  | 08/22/2022 | SND-2007 | 15 | AWTD-104001
2505 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SND-2007 | Hrs | AWTD-104001
2506 | FOT | BHI | 57 | 19 Aug 0030 - 0930 | 18320 | 901082 | BAKER LOST COMMUNICATION WITH THE AUTOTRAK RSS TO THE MWD TOOL. | BHA | RSS |  | 08/22/2022 | SND-2007 | 4.5 | AWTD-104001
2507 | FOT | BHI | 15 | 22 Aug 1400 - 0500 | 18640 | 901156 | BAKER LOST COMMUNICATION WITH THE AUTOTRAK RSS TO THE MWD TOOL. | BHA | MWD |  | 08/22/2022 | SND-2007 | 15 | AWTD-104001
2508 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SP-261 | Hrs | MHWZ-903
2509 | HERR | ITS | .5 | 22 Aug 1815 - 1845 | 2231 | 901196 | HYDRAULIC SYSTEM FAILURE ON CRT. | JF | CRT |  | 08/22/2022 | SP-261 | .5 | MHWZ-903
2510 | 6491 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTMS UP & CHC WITH 200 GPM & PRESSURE 700 PSI. | 6491 |  | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2511 | 6491 |  | CIRC | E | 4186 | MPMP | DROP 1" NOV DIVERTING BALL, PUMP DOWN WITH 80 GPM & WAIT TILL SEATED IN ORDER TO DIVERT FLUID AWAY FROM THE INNER BARREL. -CONFIRM SPACE OUT FOR CUTTING THE CORE.@6491' -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS. | 6491 |  | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2512 | 6551 |  | CORE | E | 4186 | CORC | CUT 6-1/8" X 2 5/8" CORE RUN #3 FROM 6491' TO 6551' W/70 PCF POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, (RPM: 65 - TQ 2-3 KLFTLB) & (GPM: 180 - PRESS 850 PSI)-CORING 60 FT INSIDE ARAB D ZONE (AD2B12 TO AD3A17) FORMATION.-STOP ROTATION AND BREAK OUT CORE 10 KLBS OVERPULL INDICATION , P/UP 5' AND RUN BACK TO BTM & CONFIRM CORE CATCHED OK | 6491 |  | NOC | 08/22/2022 | SP-53L | CORE | HRDH-528
2513 | 6551 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTM UP WITH 120 GPM @ 500 PSI WITH FULL RETURNS. | 6551 |  | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2514 | 6551 |  | SDR1 | E | 4186 | NA | FLOW CHECK-WELL STATIC OK. | 6551 |  | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2515 | 6551 | 6374 | TO | E | 4186 | STDP | HPJSM, POOH 6 1/8" NOV CORING ASSY. TO/7" CSG SHOE @ 6374' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6551 | 6551 | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2516 | 6551 |  | SDR1 | E | 4186 | NA | FLOW CHECK AFTER PULL 5 STDS - WELL STATIC OK | 6551 |  | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2517 | 6551 | 5900 | TO | E | 4186 | STDP | HPJSM, POOH 6 1/8" NOV CORING ASSY. FROM / 7" CSG SHOE @ 6374' TO 5900' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6551 | 6374 | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2518 | 6551 |  | SDR1 | E | 4186 | NA | FLOW CHECK @7" TOL -WELL STATIC OK. | 6551 |  | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2519 | 6551 | 1597 | TO | E | 4186 | STDP | POOH 6 1/8" NOV CORING ASSY. TO 7" TOL@ 1597' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6551 | 5900 | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2520 | 6551 |  | SDR1 | E | 4186 | NA | FLOW CHECK @7" TOL WELL STATIC OK. | 6551 |  | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2521 | 6551 | 615 | TO | E | 4186 | STDP | CONT'D POOH 6-1/8" NOV CORING ASSY. RUN #3 TO 615' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6551 | 1597 | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2522 | 6551 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT TOP BHA - WELL STATIC OK.-CHECKING FOR H2S-ZERO H2S READING. | 6551 |  | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2523 | 6551 |  | HT | E | 4186 | CORC | HPJSM, CON'T POOH 6-1/8" NOV CORING ASSY. RUN #3 TO SURFACE CONTROLLED SPEED 6 MIN/STD SLIPS TO SLIPS.-RUN RIG FLOOR BUG BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.-ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.-L/D INNER BARREL,60 ' RECOVERED (100 % RECOVERY) FROM CORE RUN #3-CORE HEAD DULL : 1-1-WT-A-X-NO-TD | 6551 |  | NOC | 08/22/2022 | SP-53L | CORE | HRDH-528
2524 | 6551 |  | HT | E | 4186 | CORC | HPJSM, P/U & M/U 6-1/8" NOV CORE ASSY. RUN#4 -6-1/8" CORE HEAD + 4-3/4" CORE OUTER BARRELS & 3-3/8" INNER BARRELS (90FT) + FLOAT SUB W/ FLAPPER TYPE FLOAT VALVE (BALL SIZE IS 1")+15 X 4-3/4" DC'S+ 4-3/4" DRILLING JAR+2 X 4 3/4" DC'S +XO+ DP'S. | 6551 |  | NOC | 08/22/2022 | SP-53L | CORE | HRDH-528
2525 | 6551 | 2470 | TI | E | 4186 | STDP | RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 615' TO 2470'.-GENTLY PASSED 7" TOL . | 6551 | 615 | RIG | 08/22/2022 | SP-53L | CORE | HRDH-528
2526 | 140.25 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 24 | 4186 | 13 Aug 0230 | 08/22/2022 | SP-53L | Type | HRDH-528
2527
2528
2529 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SSA-102 | Hrs | QTIF-693
2530 | HERR | RIG | 16.5 | 21 Aug 1530 - 1700 | 10319 | 901024 | RIG OVER PULL ON WEAR BUSHING WHILE RETRIEVAL PROCESS, RESULTING IN BREAKING THE TWO SIDE BOLTS, TWO BOLTS LOST IN HOLE. | WH | WBSH |  | 08/22/2022 | SSA-102 | 11.25 | QTIF-693
2531 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SSA-51 | Hrs | MNIF-257
2532 | HERR | RIG | 1.25 | 22 Aug 1500 - 1615 | 9880 | 901192 | WHEN RUNNING IN HOLE W/ CO ASSY, STRING TAGGED ON CEMENT OBSTRUCTION LEADING TO TWO 4"DP DAMAGE, LD DAMAGED DP & REAM DOWN OBSTRUCTION | DSF | DP |  | 08/22/2022 | SSA-51 | 1.25 | MNIF-257
2533 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SSA-5865 | Hrs | FRHH-3
2534 | FOT | RIG | 3.5 | 22 Aug 1530 - 0300 | 4420 | 901159 | 1-7/8" BOP HYDRAULIC TORQUE WRENCH MALFUNCTION. USE HAMMER WRENCH FOR MAKE-UP BOLTS. LEAD TO EXTRA TIME AND LEAK DURING TEST. | RR | RWCS |  | 08/22/2022 | SSA-5865 | 3.5 | FRHH-3
2535 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | SSA-5972 | Hrs | SHDN-19
2536 | FOT | HWP | 15 | 22 Aug 0600 - 2100 | 13650 | 901177 | ELECTRIC FAULT TO LOGGING TOOL CABLE. | TF | WLTT |  | 08/22/2022 | SSA-5972 | 15 | SHDN-19
2537 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/22/2022 | STY-038 | Hrs | ZULF-2089
2538 | HINW | HWP | 43 | 21 Aug 1000 - 0500 | 5537 | 901117 | HALLIBURTON MADE ANOTHER CORRELATION PASS BELOW PUNCHING DEPTH, CAUSING THE TOOL TO GET STUCK AT X-NIPPLE | STUK | WLT |  | 08/22/2022 | STY-038 | 24 | ZULF-2089
2539 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADC-43L | Hrs | UTMN-3118
2540 | FRFM | TK3 | 251.75 | 11 Aug 2130 - 2215 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/23/2022 | ADC-43L | 16.75 | UTMN-3118
2541 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADC-50 | Hrs | SFNY-1176
2542 | WC20 | ARM | 1.25 | 23 Aug 1530 - 1645 | 3301 | 901169 | OBSERVED MUD RETURN ON FLOW LINE | WCNT | NA |  | 08/23/2022 | ADC-50 | 1.25 | SFNY-1176
2543 | 7045 | 7014 | LOG | E |  | WLT | LOGGING DOWN (GR/WGI) F/ 4136' TO TD @ 7014' AND (HDIL/CN) F/ 6475' TO TD @ 7014'.- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 | 4350 | BAW | 08/23/2022 | ADC-54L | LOG | HRDH-584
2544 | 7045 | 6475 | LOG | E |  | WLT | LOGGING UP MAIN PASS (MLL/HDIL/ZDL/CN/GR) F/ 7014' T/ 6475' (SPEED: 25-30 FT/MIN).- GOING DOWN WITH LOG & PERFORM REPEAT PASS (MLL/HDIL/ZDL/CN/GR) F/ 6875' T/ 6675' - MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 | 7014 | BAW | 08/23/2022 | ADC-54L | LOG | HRDH-584
2545 | 7045 | 7010 | LOG | E | 4305 | WLT | RIH W/ WL LOGGING TOOLS TO 7010' FOR MREX (PPGAS MODE) LOG.- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 | 6475 | BAW | 08/23/2022 | ADC-54L | LOG | HRDH-584
2546 | 7045 | 6475 | LOG | E | 4305 | WLT | LOGGING UP MAIN PASS (MREX) PPGAS MODE F/ 7010' T/ 6475' (SPEED: 2-3 FT/MIN).- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 | 7010 | BAW | 08/23/2022 | ADC-54L | LOG | HRDH-584
2547 | 7045 | 7010 | LOG | E | 4305 | WLT | RIH W/ WL LOGGING TOOLS TO 7010' FOR MREX (PP LIGHT OIL MODE) LOG.- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 | 6475 | BAW | 08/23/2022 | ADC-54L | LOG | HRDH-584
2548 | 7045 | 6475 | LOG | E | 4305 | WLT | LOGGING UP (MREX) PP LIGHT OIL MODE F/ 7010' T/ 6475' (SPEED: 2-3 FT/MIN).- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 | 7010 | BAW | 08/23/2022 | ADC-54L | LOG | HRDH-584
2549 | 7045 | 0 | LOG | E |  | WLT | CONT. LOG UP WGI TO CSG & CONT'D LOG UP CN/GR FROM 6475' TO 100' FROM SURFACE (LOG SPEED: 25-30 FPM).- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 | 6475 | BAW | 08/23/2022 | ADC-54L | LOG | HRDH-584
2550 | 7045 |  | OTH | E |  | NA | POOH WL LOGGING TOOL TO SURFACE, HPJSM & RETRIEVED RADIO ACTIVE SOURCE, L/D COMBINED TRIPLE COMBO LOGGING TOOLS & R/D BAKER WL SHEAVES.- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 |  | BAW | 08/23/2022 | ADC-54L | LOG | HRDH-584
2551 | 7045 |  | HT | N | 4306 | BHA | HPJSM, P/U & M/U 8-1/2" REAMING BHA T/ 804' AS FOLLOW:- REAMING BHA: 8-1/2" RR PDC BIT (OPEN JETS)+BIT SUB WITH FLOAT VALVE+8-1/2" STRR+X/O+1 X 6-1/2" DC+X/O+8-1/2" STRR+X/O+15 X 6-1/2" DC+JAR+2 X 6-1/2" DC.+X/O+6 X 5" HWDP+X/O+ 4" DPS TO SURFACE.- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 |  | RIG | 08/23/2022 | ADC-54L | CT | HRDH-584
2552 | 11 | OOS | HCRM | 4306 | LOG | CONDITION TRIP BEFORE PCL RCX LOG. | LOGGING : MREX | 11 | 4305 | 23 Aug 0830 | 08/23/2022 | ADC-54L | OOS | HRDH-584
2553
2554
2555
2556 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADC-55L | Hrs | UTMN-3171
2557 | STBH | TK3 | 574 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/23/2022 | ADC-55L | 24 | UTMN-3171
2558 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADC-56L | Hrs | UTMN-3069
2559 | IDCS | TK3 | 38.5 | 21 Aug 1715 - 0845 | 12333 | 901070 | 9 5/8"LINER HANGER POLSH MILL CAME OOH WITH WEAR ON THE MILL FROM 10.1" TO 9.9" | WI | NA |  | 08/23/2022 | ADC-56L | 3.75 | UTMN-3069
2560 | 13523 | 0 | TO | C | 4245 | TBG | POOH HLWM RUNNING TOOL ON 4-1/2" 12.6# L80 NVAM TUBING FROM 4070 FT TO SURFACE (TOTAL 155 JTS).- MONITORED WELL ON TRIP TANK & TRIP SHEET, WELL-STATIC.- FOUND A PIECE OF RUBBER FROM THE ANNULAR PACKING ELEMENT JAMMED ON THE CABLE CLAMP WHILE POOH. | 13523 | 4070 | RIG | 08/23/2022 | ADC-58L | COMP | ABHD-169
2561 | 13523 |  | OTH | C | 4245 | SEAL | L/D LOWER HLWM RUNNING TOOL & R/D C/L SHEAVE FROM DERRICK.- MONITORED WELL ON TRIP TANK & TRIP SHEET | 13523 |  | SCP | 08/23/2022 | ADC-58L | COMP | ABHD-169
2562 | 13523 |  | HT | C |  | SFLN | M/U JETTING TOOL AND JET BOPS.- RECOVERED SOME PIECES OF RUBBER FROM THE ANNULAR PACKING ELEMENT ON SKALE SKAKER. | 13523 |  | RIG | 08/23/2022 | ADC-58L | COMP | ABHD-169
2563 | 13523 | 0 | LDP | C |  | STRG | L/D 49 STD'S OF EXCESS 5" D/P FROM DERRICK. | 13523 | 4650 | RIG | 08/23/2022 | ADC-58L | COMP | ABHD-169
2564 | 13523 |  | PJSM | C |  | BOP | HELD PRE-JOB SAFETY MEETING PRIOR TO CHANGE ANNULAR PREVENTER PACKING ELEMENT. | 13523 |  | RIG | 08/23/2022 | ADC-58L | BOP | ABHD-169
2565 | 13523 |  | ND | C |  | BNIP | N/D BELL NIPPLE & DISCONNECTED FLOW LINE.- LINED UP TRIP TANK TO THS SOVS AND MONITORED WELL, STATIC. | 13523 |  | RIG | 08/23/2022 | ADC-58L | BOP | ABHD-169
2566 | 13523 |  | BOP | C |  | BOP | REPLACED ANNULAR PACKING ELEMENT BY NEW ELEMENT.- FOUND ELEMENT IN BAD CONDITION. | 13523 |  | RIG | 08/23/2022 | ADC-58L | BOP | ABHD-169
2567 | 89.75 | OOS | Category | DOOS ID | COM | Out of Scope Summary | RUN SLB HLWM SMART COMPLETION | 9.5 | 4245 | 19 Aug 0100 | 08/23/2022 | ADC-58L | Type | ABHD-169
2568
2569
2570 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADC-59L | Hrs | HWYH-1324
2571 | IPDF | SMI | 17.75 | 22 Aug 2245 - 1630 | 16562 | 901212 | PERFORM STICKY TEST AND HAD STICKING TENDANCEY. | DRG | NA |  | 08/23/2022 | ADC-59L | 11.5 | HWYH-1324
2572 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADC-60 | Hrs | ABSF-216
2573 | FOT | BAL | 302.5 | 08 Aug 0500 - 2100 | 11253 | 900636 | BAKER ESP CABLE GROUNDED. DECISION MADE TO DE-COMPLETE ABSF-216 & CHANGE ESP ASSY. | TF | ESP |  | 08/23/2022 | ADC-60 | 16 | ABSF-216
2574 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADES-174 | Hrs | GHZL-72
2575 | SFHS | BFW | 47.5 | 22 Aug 0530 - 0500 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/23/2022 | ADES-174 | 24 | GHZL-72
2576 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADM-337 | Hrs | MRJN-900
2577 | WTHR | ARM | 17.75 | 23 Aug 1045 - 0430 | 13019 | 901162 | WAIT ON WEATHER, UNABLE TO FLOWBACK DUE TO UNFAVORABLE WIND CONDITION. | WON | NA |  | 08/23/2022 | ADM-337 | 17.75 | MRJN-900
2578 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADM-339 | Hrs | MRJN-3017
2579 | HERR | HTD | 8.25 | 23 Aug 1715 - 0130 | 2615 | 901139 | DURING WELLHEAD REPAIRS & INSPECTION HOTHEAD DROPPED SMALL METAL TORCH IN WELL. | WH | WH |  | 08/23/2022 | ADM-339 | 8.25 | MRJN-3017
2580 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ADM-657 | Hrs | SFNY-1228
2581 | FOT | RIG | 10.25 | 22 Aug 1500 - 2330 | 110 | 901194 | LEAKS ON FLOW LINE SEALS | RR | FL |  | 08/23/2022 | ADM-657 | 7.25 | SFNY-1228
2582 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ARO-2003 | Hrs | MNIF-733
2583 | WOPF | AP2 | 192 | 16 Aug 0500 - 0500 | 0 | 900956 | WAIT ON FIELD SERVICE TO INSTALL ISOLATION PLUGS. | WO | NA |  | 08/23/2022 | ARO-2003 | 24 | MNIF-733
2584 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ARO-3002 | Hrs | MRJN-813
2585 | WTHR | ARM | 16.25 | 22 Aug 0745 - 1800 | 8852 | 901136 | WIND SPEED TO LOW TO COMMENCE FLKOW BACK OPERATION. | WON | NA |  | 08/23/2022 | ARO-3002 | 6 | MRJN-813
2586 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | DPS-45 | Hrs | UTMN-2331
2587 | FOT | SDM | 1.75 | 23 Aug 0315 - 0500 | 18171 | 901171 | LOST COMMUNICATION W/ SLB TOOLS MWD/LWD . | BHA | MWD |  | 08/23/2022 | DPS-45 | 1.75 | UTMN-2331
2588 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | DQ-47 | Hrs | KHRS-280
2589 | FOT | BAW | 4 | 23 Aug 1530 - 1930 | 7940 | 901167 | BHI WIRE LINE RIH W/ SINKER BAR ATTEMPT TO LATCH DEPTH @ 7,865' WUTHOUT SUCCESS. | TF | FREE |  | 08/23/2022 | DQ-47 | 4 | KHRS-280
2590 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | DQ-48 | Hrs | KHRS-495
2591 | FOT | BHI | 20.75 | 22 Aug 0830 - 0630 | 7163 | 901193 | WHILE DRILLING HAD A SUDDEN INCREASE IN SPP (+/- 1,000 PSI) IN SPP AND OBSERVED MOTOR RUBBERS ON SHALE SHAKERS, DECISION MADE TO POOH TO CHANGE MOTOR. | BHA | MMOT |  | 08/23/2022 | DQ-48 | 1.5 | KHRS-495
2592 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | ENS-108 | Hrs | ZULF-2015
2593 | GRF | RIG | 24 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/23/2022 | ENS-108 | 24 | ZULF-2015
2594 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | HI-4 | Hrs | BRRI-1001
2595 | FOT | SDM | 16 | 23 Aug 1300 - 0500 | 9518 | 901217 | SLB ADN TOOL LOST COMMUNICATION, TROUBLESHOOT AND ATTEMT TO REESTABLISH COMMUNICATION, NO SUCCESS | BHA | MWD |  | 08/23/2022 | HI-4 | 16 | BRRI-1001
2596 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | JACK-202 | Hrs | THRY-829
2597 | FOT | RIG | 11.5 | 23 Aug 0500 - 1630 | 2165 | 901161 | DRILLER CONSOLE GAUGES WRONG READINGS (ROTARY TORQUE GAUGE & PUMP PRESSURE GAUGE). RETURN FLOW GAUGE WRONG READINGS. | RR | HSYS |  | 08/23/2022 | JACK-202 | 11.5 | THRY-829
2598 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | MP-1 | Hrs | MRJN-78
2599 | FOT | NRT | 533.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/23/2022 | MP-1 | 24 | MRJN-78
2600 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | NBR-263S | Hrs | QTIF-736
2601 | STBH | ARM | 275.75 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/23/2022 | NBR-263S | 24 | QTIF-736
2602 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | PN-9 | Hrs | MRJN-673
2603 | CFST | HCM | 219.25 | 14 Aug 2045 - 0000 | 8745 | 900824 | WHILE PUMPING DOWN WFD DV OPENING PLUG FOR 1ST STAGE CEMENT JOB, STRING PRESSURED UP 34 BBLS PRIOR TO THEORETICAL DISPLACMENT. ATTEMPT TO BUMP WFD DV OPENING PLUG AND OPEN WFD DV PORTS WITH MAX 3500 PSI, NO SUCCESS. INSPECT SURACE CEMENT SAMPLES - SAMPLES SET & HARD. | CMT | NA |  | 08/23/2022 | PN-9 | 19 | MRJN-673
2604 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | RBP-50A | Hrs | HSBH-52
2605 | WTHR | ARM | 43 | 09 Aug 0500 - 1230 | 12595 | 900658 | WAIT ON WEATHER, UNABLE TO FLOWBACK DUE TO UNFAVORABLE WIND CONDITION. | WON | NA |  | 08/23/2022 | RBP-50A | 7.5 | HSBH-52
2606 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SCTD-1 | Hrs | SDGM-1084
2607 | FOT | RIG | 7 | 23 Aug 2200 - 0500 | 13558 | 901214 | DOWN HOLE MOTOR FAILURE | BHA | MMOT |  | 08/23/2022 | SCTD-1 | 7 | SDGM-1084
2608 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SINO-25 | Hrs | MNIF-645
2609 | FOT | NWL | 9.5 | 23 Aug 1900 - 0430 | 7410 | 901220 | NPS TRACTOR HAD SHORT CIRCUIT AND THE TRACTOR ELECTRONIC PANEL NOT WORKING WHILE RIH. | TF | WLTT |  | 08/23/2022 | SINO-25 | 9.5 | MNIF-645
2610 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SINO-33L | Hrs | HRDH-1542
2611 | FOT | RIG | 40 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/23/2022 | SINO-33L | 24 | HRDH-1542
2612 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SINO-43L | Hrs | UTMN-4809
2613 | FOT | BHI | 25.25 | 22 Aug 2100 - 0045 | 5731 | 901157 | WHILE MRSS DRLG, HAD MOTOR STALLS ON BTM & PRESSURE SPIKES OFF BTM. TROUBLESHOOT, FOUND RUBBER AT THE SHAKER. SUSPECT MOTOR FAILURE. | BHA | MMOT |  | 08/23/2022 | SINO-43L | 17.25 | UTMN-4809
2614 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SINO-5L | Hrs | UTMN-639
2615 | FOT | SPS | 28 | 22 Aug 2330 - 0330 | 9876 | 901137 | LOST SIGNAL FOR ALL MWD/LWD TOOLS, TROUBLE SHOOTING-NO SIGNAL. | BHA | LWD |  | 08/23/2022 | SINO-5L | 22.5 | UTMN-639
2616 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SND-2001 | Hrs | HWYH-1229
2617 | UNKN | RIG | 10.5 | 23 Aug 1330 - 0000 | 2681 | 901216 | WHILE CIRCULATING THRU CASING USING CIRCULATING HEAD & CHICKSAN LOOP SECURED BY TUGGER LINE AT 740PSI. CIRCULATING HEAD FAILED, JUMPED CAUSING CHICKSAN LOOP TO SWING AND HIT THE IP AND CAUSING BRUISES IN HIS RIGHT SHOULDER AND ABDOMINAL AREA. IP WAS SENT TO THE HOSPITAL FOR FURTHER MEDICAL TREATMENT. INVESTIGATION ON GOING. | HSEI | NA |  | 08/23/2022 | SND-2001 | 10.5 | HWYH-1229
2618 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SND-2003 | Hrs | GZLN-1
2619 | FOT | RIG | 24 | 23 Aug 0500 - 0500 | 5452 | 901218 | BOP LEAKS WHILE PRESSURE TESTING | BOP | BOP |  | 08/23/2022 | SND-2003 | 24 | GZLN-1
2620 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SND-2004 | Hrs | BRRI-1148
2621 | FOT | SWT | 175.75 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/23/2022 | SND-2004 | 15.25 | BRRI-1148
2622 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SND-2005 | Hrs | MHKK-2
2623 | WOTO | ARM | 6.25 | 23 Aug 2245 - 0500 | 5828 | 901213 | WAIT ON WFD HANDLING EQUIPMENT TO RUN 2-7/8" CEMENT STINGER. LAST MINUTE CHANGE OF PLANS TO SET CEMENT PLUG. | WO | NA |  | 08/23/2022 | SND-2005 | 6.25 | MHKK-2
2624 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SND-2007 | Hrs | AWTD-104001
2625 | FOT | BHI | 36 | 22 Aug 1400 - 0200 | 18640 | 901156 | BAKER LOST COMMUNICATION WITH THE AUTOTRAK RSS TO THE MWD TOOL. | BHA | MWD |  | 08/23/2022 | SND-2007 | 21 | AWTD-104001
2626 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SND-3001 | Hrs | SMNH-10
2627 | FOT | SWL | 3 | 23 Aug 0000 - 0300 | 0 | 901215 | LOST COMMUNICATION WITH CBL TOOLS | TF | WLT |  | 08/23/2022 | SND-3001 | 3 | SMNH-10
2628 | 6551 | 6551 | TI | E | 4186 | STDP | CONTD RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 2470' TO CORE POINT @ 6551'.-WASH AND REAM DOWN TILL TAG BTM @6551' | 6551 | 2470 | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2629 | 6551 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTMS UP & CHC WITH 200 GPM & PRESSURE 700 PSI. | 6551 |  | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2630 | 6551 |  | CIRC | E | 4186 | MPMP | DROP 1" NOV DIVERTING BALL, PUMP DOWN WITH 80 GPM & WAIT TILL SEATED IN ORDER TO DIVERT FLUID AWAY FROM THE INNER BARREL. -CONFIRM SPACE OUT FOR CUTTING THE CORE@6551' -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS. | 6551 |  | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2631 | 6559 |  | CORE | E | 4186 | CORC | CUT 6-1/8" X 2 5/8" CORE RUN #4 FROM 6551' TO 6559' W/70 PCF POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, (RPM: 65 - TQ 2-3 KLFTLB) & (GPM: 180 - PRESS 850 PSI)-NO PROGRESS LOST TOURQUE & ROP, TROUBLE SHOOT SEVERAL TIMES WITHOUT PROGRESS GOT JAMMING -CORE JAMMED AFTER CUTTING 08' @ 6559' AND THE PLAN WAS TO CUT 90 FT. | 6551 |  | CPR | 08/23/2022 | SP-53L | CORE | HRDH-528
2632 |  |  | CIRC | E | 4186 | MPMP | CIRCULATE BTM UP WITH 120 GPM @ 600 PSI WITH FULL RETURNS. | 6559 |  | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2633 |  |  | SDR1 | E | 4186 | NA | FLOW CHECK-WELL STATIC OK. |  |  | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2634 |  | 6374 | TO | E | 4186 | SPHDP | HPJSM, POOH 6 1/8" NOV CORING ASSY. TO/7" CSG SHOE @ 6374' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. |  | 6560 | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2635 |  |  | SDR1 | E | 4186 | NA | FLOW CHECK @ 7" CSG SHOE -WELL STATIC OK. |  |  | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2636 |  | 5900 | TO | E | 4186 | STDP | POOH 6 1/8" NOV CORING ASSY. FROM / 7" CSG SHOE @ 6374' TO 5900' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEE |  | 6374 | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2637 |  |  | SDR1 | E | 4186 | NA | FLOW CHECK AFTER PULL 5 STDS - WELL STATIC OK |  |  | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2638 |  | 1597 | TO | E | 4186 | STDP | CONTD POOH 6 1/8" NOV CORING ASSY. TO 7" TOL@ 1597' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. |  | 6374 | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2639 |  |  | SDR1 | E | 4186 | NA | FLOW CHECK @7" TOL WELL STATIC OK. |  |  | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2640 |  | 615 | TO | E | 4186 | STDP | CONTD POOH 6-1/8" NOV CORING ASSY. RUN #4 TO 615' CONTROLLED SPEED 6MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. |  | 1597 | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2641 |  |  | SDR1 | E | 4186 | NA | FLOW CHECK AT TOP BHA - WELL STATIC OK.-CHECKING FOR H2S-ZERO H2S READING. |  |  | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2642 |  |  | HT | E | 4186 | CORC | HPJSM, CON'T POOH 6-1/8" NOV CORING ASSY. RUN #4 TO SURFACE CONTROLLED SPEED 6 MIN/STD SLIPS TO SLIPS.-RUN RIG FLOOR BUG BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.-ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.-DISCUSSED HSE ALERT 15-19 TRAPPED PRESSURE IN THE CORE INNER ALUMINUM BARREL.-L/D INNER BARREL, 05' RECOVERED (62.5 % RECOVERY) FROM CORE RUN #4-CORE HEAD DULL : 1-1-WT-A-X-NO-TD |  |  | NOC | 08/23/2022 | SP-53L | CORE | HRDH-528
2643 |  |  | HT | E | 4186 | CORC | HPJSM, P/U & M/U 6-1/8" NOV CORE ASSY. RUN#5 -6-1/8" NEW CORE HEAD ( TYPE : CDPH713S)+ 4-3/4" CORE OUTER BARRELS & 3-3/8" INNER BARRELS (60FT) + FLOAT SUB W/ FLAPPER TYPE FLOAT VALVE (BALL SIZE IS 1")+15 X 4-3/4" DC'S+ 4-3/4" DRILLING JAR+2 X 4 3/4" DC'S +XO+ DP'S. |  |  | NOC | 08/23/2022 | SP-53L | CORE | HRDH-528
2644 |  | 3562 | TI | E | 4186 | STDP | RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 615' TO 7" CSG SHOE @3562'.-GENTLY PASSED 7" TOL |  | 615 | RIG | 08/23/2022 | SP-53L | CORE | HRDH-528
2645 | 164.25 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 24 | 4186 | 13 Aug 0230 | 08/23/2022 | SP-53L | Type | HRDH-528
2646
2647
2648 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SP-58 | Hrs | HRDH-795
2649 | FOT | RIG | 1 | 23 Aug 1700 - 1800 | 13700 | 901164 | OBSERVED LEAK IN DRAW WORK AIR HOSES. | RR | DWKS |  | 08/23/2022 | SP-58 | 1 | HRDH-795
2650 | FOT | RIG | 1 | 23 Aug 0400 - 0500 | 4420 | 901221 | RIG REPAIR EZY TORQ TONG. | RR | HSYS |  | 08/23/2022 | SSA-5865 | 1 | FRHH-3
2651 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SSA-5865 | Hrs | FRHH-3
2652 | FOT | RIG | 2 | 23 Aug 1900 - 2100 | 4420 | 901166 | IRON ROUGHNECK MALFUNCTION AND IMPACT TRIPPING PERFORMANCE. MANAGE TO CONTINUE OPERATION WITH CHAIN WRENCH AND MANUAL TONG. | RR | RSYS |  | 08/23/2022 | SSA-5865 | 2 | FRHH-3
2653 | FOT | RIG | 1 | 23 Aug 0400 - 0500 | 4420 | 901221 | RIG REPAIR EZY TORQ TONG. | RR | HSYS |  | 08/23/2022 | SSA-5865 | 1 | FRHH-3
2654 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | SSA-5972 | Hrs | SHDN-19
2655 | FOT | HWP | 11 | 23 Aug 1800 - 0500 | 14415 | 901168 | HALLIBURTON TPL LOGGING TOOL FAILURE. | TF | WLT |  | 08/23/2022 | SSA-5972 | 11 | SHDN-19
2656 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/23/2022 | STY-038 | Hrs | ZULF-2089
2657 | HINW | HWP | 67 | 21 Aug 1000 - 0500 | 5537 | 901117 | HALLIBURTON MADE ANOTHER CORRELATION PASS BELOW PUNCHING DEPTH, CAUSING THE TOOL TO GET STUCK AT X-NIPPLE | STUK | WLT |  | 08/23/2022 | STY-038 | 24 | ZULF-2089
2658 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | 088TE | Hrs | QTIF-519
2659 | MATL | FMC | 3 | 24 Aug 0900 - 1200 | 0 | 901254 | FRANKS BROUGHT WRONG HANDLING EQUIPMENT FOR 24" CSG. | WO | NA |  | 08/24/2022 | 088TE | 3 | QTIF-519
2660 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ADC-32 | Hrs | ANDR-1010
2661 | FOT | RIG | 3 | 24 Aug 1600 - 1900 | 10870 | 901256 | REPLACED TDS ENCODER AS SIGNAL OF OLD ENCODER WAS HAVING DISTORTION. | RR | TDS |  | 08/24/2022 | ADC-32 | 3 | ANDR-1010
2662 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ADC-42L | Hrs | SDGM-1258
2663 | FOT | TK3 | 8 | 24 Aug 2100 - 0500 | 12520 | 901271 | STRING GOT PLUGGED WHILE FILLING UP. | DSF | STRG |  | 08/24/2022 | ADC-42L | 8 | SDGM-1258
2664 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ADC-43L | Hrs | UTMN-3118
2665 | FOT | RIG | 16.75 | 24 Aug 0500 - 0145 | 12747 | 901255 | P/T 13-5/8" 10M ANNULAR BOP NOT HOLD, DUE TO LEAK FROM PISTON SEALS OF ANNULAR BOP. | BOP | BOP |  | 08/24/2022 | ADC-43L | 16.75 | UTMN-3118
2666 | 7045 | 4336 | TI | N | 4306 | STDP | RIH W/ 8-1/2" REAMING ASSY F/ 804' TO 9-5/8" CSG SHOE @ 4336'.- FILL STRING EVERY 20 STADS.- MONITOR WELL ON TRIP TANK & TRIP SHEET, WELL STATIC. | 7045 | 804 | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2667 | 7045 |  | CIRC | N | 4306 | MPMP | BREAK CIRCULATION @ 9-5/8" CSG SHOE, 100% RETURN. | 7045 |  | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2668 | 7045 | 7045 | ST | N | 4306 | STDP | CONT'D RIH W/ 8-1/2" REAMING ASSY ON ELEVATOR F/ 4336' TO BTM @ 7045', HOLE IN GOOD CONDITION.- FILL STRING EVERY 20 STADS.- WASH DOWN LAST STAND TO BTM- MONITOR WELL ON TRIP TANK & TRIP SHEET, WELL STATIC. | 7045 | 4336 | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2669 | 7045 |  | CIRC | N | 4306 | MPMP | SWEEP HOLE WITH 3 X 50 BBL'S HVP & CIRC HOLE CLEAN, SPOT 200 BBL TREATED POLYMER MUD 79 PCF AT BTM, 100% RETURN. | 7045 |  | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2670 | 7045 |  | WCNT | N | 4306 | NA | FLOW CHECK, WELL STATIC. | 7045 |  | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2671 | 7045 | 4336 | ST | N | 4306 | STDP | POOH W/ 8-1/2" REAMING ASSY ON ELEVATOR F/ 7045' TO 9-5/8" CSG SHOE @ 4336', HOLE IN GOOD CONDITION.- FLOW CHECK AFTER POOH 5 STDS, WELL STATIC.- MONITOR WELL ON TRIP TANK & TRIP SHEET, WELL STATIC. | 7045 | 7045 | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2672 | 7045 |  | WCNT | N | 4306 | NA | FLOW CHECK, WELL STATIC.- SLUG PIPE | 7045 |  | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2673 | 7045 | 804 | TO | N | 4306 | STDP | CONT'D POOH W/ 8-1/2" REAMING ASSY F/ 4336' TO TOP BHA @ 804'.- MONITOR WELL ON TRIP TANK & TRIP SHEET, WELL STATIC. | 7045 | 4336 | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2674 | 7045 |  | WCNT | N | 4306 | NA | FLOW CHECK, WELL STATIC. | 7045 |  | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2675 | 7045 |  | HT | N | 4306 | BHA | POOH W/ 8-1/2" REAMING BHA TO SURFACE & L/D BHA.- MONITOR WELL ON TRIP TANK & TRIP SHEET, WELL STATIC. | 7045 |  | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2676 | 7045 | 0 | LDP | E | 4305 | STRG | P/U, M/U & RACK BACK 4 STDS 4" DP FOR THE PCL LOGGING.- MONITOR WELL ON TRIP TANK, WELL STATIC. | 7045 | 0 | RIG | 08/24/2022 | ADC-54L | CT | HRDH-584
2677 | 7045 |  | PJSM | E | 4305 | NA | HPJSM WITH RIG & BAKER WIRELINE CREW PRIOR TO RU RCX LOGGING TOOLS, DISCUSSED JSA & PROCEDURES, SAFETY ISSUES, KEEP GOOD COMMUNICATION BETWEEN DRILLER, WL ENGINEER AND WINCH MAN IN THE WL UNIT.- R/U & FUNCTION TESTED MECHANICAL AND HYDRAULIC WL CABLE CUTTERS, OK. | 7045 |  | RIG | 08/24/2022 | ADC-54L | LOG | HRDH-584
2678 | 7045 | 176 | LOG | E | 4305 | WLT | P/U & M/U BHI W/L LOGGING TOOLS RUN #2: RCX-IFX-GR (FORMATION TESTER & SAMPLING).- 2 X PROBE (STANDARD & XL)-SAMPLE VIEW, FLUID ANALYZER, 3 X PUMPS, 2 CARRIERS (10 TANK, 2 FILTER), STRADDLE PKR'S (02 EA)-GAMMA RAY AND CALIPER LOG.- PERFORM SURFACE FUNCTION CHECKS AND TOOL CALIBRATION ON SURFACE BEFORE RIH, OK.- TOTAL LOGGING TOOL LENGTH: 176.51', WT: 5,280 LB & MAX OD: 7.8".- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 0 | BAW | 08/24/2022 | ADC-54L | LOG | HRDH-584
2679 | 7045 | 1400 | ST | E | 4305 | STDP | HPJSM, RIH WL RUN#2 LOGGING TOOLS (RCX-IFX-GR) ON 4" DRIFTED DP STDS WITH CONTROL SPEED 2 MIN/STD SLIPS TO SLIPS TO 1400' .. ONGOING @ RPT. - FILL STRING EVERY 10 STDS & BREAK CIRC.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 176 | RIG | 08/24/2022 | ADC-54L | LOG | HRDH-584
2680 | 17.75 | OOS | HCRM | 4306 | LOG | CONDITION TRIP PRIOR PCL RCX LOG. | 8-1/2" PILOT HOLE LOGGING : RUN#1: MREX LOG ON TWO MODES: GAS MODE & LIGHT OIL MODE / RUN#2: PCL LOG RUN#2: RCX-IFX-GR (PRESSURE & SAMPLES). | 6.75 | 4305 | 23 Aug 0830 | 08/24/2022 | ADC-54L | OOS | HRDH-584
2681
2682
2683
2684 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ADC-55L | Hrs | UTMN-3171
2685 | STBH | TK3 | 598 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/24/2022 | ADC-55L | 24 | UTMN-3171
2686 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ADC-58L | Hrs | ABHD-169
2687 | MATL | TK3 | 17.25 | 23 Aug 1430 - 0500 | 13523 | 901233 | OBSERVED A PIECE OF RUBBER FROM THE ANNULAR PACKING ELEMENTS' FINGERS JAMMED ON THE CABLE CLAMP WHILE POOH. | WO | NA |  | 08/24/2022 | ADC-58L | 11.25 | ABHD-169
2688 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ADES-158 | Hrs | ABQQ-590
2689 | FOT | BHI | 17 | 24 Aug 1000 - 0300 | 4858 | 901252 | HAD DECODING ISSUE FOR LWD SIGNAL, BCPM TOOL FAILURE. | BHA | LWD |  | 08/24/2022 | ADES-158 | 17 | ABQQ-590
2690 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ADES-174 | Hrs | GHZL-72
2691 | SFHS | BFW | 65.5 | 22 Aug 0530 - 2300 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/24/2022 | ADES-174 | 18 | GHZL-72
2692 | FOT | HCO | 1.25 | 24 Aug 0345 - 0500 | 200 | 901276 | UNABLE TO RETRIEVE HALLIBURTON RTTS. | TF | RTTS |  | 08/24/2022 | AOD-11 | 1.25 | SFNY-1670
2693 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | AOD-11 | Hrs | SFNY-1670
2694 | XTRI | RIG | 1 | 24 Aug 0000 - 0100 | 0 | 901275 | EXCESSIVE TIME TESTING WELLHEAD CASING VALVES. | JF | WH |  | 08/24/2022 | AOD-11 | 1 | SFNY-1670
2695 | FOT | HCO | 1.25 | 24 Aug 0345 - 0500 | 200 | 901276 | UNABLE TO RETRIEVE HALLIBURTON RTTS. | TF | RTTS |  | 08/24/2022 | AOD-11 | 1.25 | SFNY-1670
2696 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ARO-2003 | Hrs | MNIF-733
2697 | WOPF | AP2 | 216 | 16 Aug 0500 - 0500 | 0 | 900956 | WAIT ON FIELD SERVICE TO INSTALL ISOLATION PLUGS. | WO | NA |  | 08/24/2022 | ARO-2003 | 24 | MNIF-733
2698 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ARO-3002 | Hrs | MRJN-813
2699 | HERR | BCT | 11 | 24 Aug 1800 - 0500 | 8852 | 901268 | BAKER COIL TUBING REEL PLUG UP. | JF | CTAC |  | 08/24/2022 | ARO-3002 | 11 | MRJN-813
2700 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | DPS-45 | Hrs | UTMN-2331
2701 | FOT | SDM | 25.75 | 23 Aug 0315 - 0500 | 18171 | 901171 | LOST COMMUNICATION W/ SLB TOOLS MWD/LWD . | BHA | MWD |  | 08/24/2022 | DPS-45 | 24 | UTMN-2331
2702 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | DQ-47 | Hrs | KHRS-280
2703 | FOT | BAW | 12.75 | 24 Aug 1615 - 0500 | 11860 | 901263 | RDD REQUEST TO REPEAT THE LOG OF OPEN HOLE TO CONFIRM QUALITY LOG DATA. | TF | WLT |  | 08/24/2022 | DQ-47 | 12.75 | KHRS-280
2704 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | ENS-108 | Hrs | ZULF-2015
2705 | GRF | RIG | 48 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/24/2022 | ENS-108 | 24 | ZULF-2015
2706 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | EXL-IVA | Hrs | ZULF-2040
2707 | WOTO | EX1 | 12 | 24 Aug 1700 - 0500 | 6687 | 901258 | LOST TIME EXPRO: PICK UP EXPRO CROSSOVER AND LOWER TO TOP OF 4 1/16" TREE, ATTEMPT TO MAKE UP CROSSOVER WITHOUT SUCCESS, SOURCE A REPLACEMENT CROSSOVER. | WO | NA |  | 08/24/2022 | EXL-IVA | 12 | ZULF-2040
2708 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | HI-4 | Hrs | BRRI-1001
2709 | FOT | SDM | 19.25 | 23 Aug 1300 - 0815 | 9518 | 901217 | SLB ADN TOOL LOST COMMUNICATION, TROUBLESHOOT AND ATTEMT TO REESTABLISH COMMUNICATION, NO SUCCESS | BHA | LWD |  | 08/24/2022 | HI-4 | 3.25 | BRRI-1001
2710 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | MP-1 | Hrs | MRJN-78
2711 | FOT | NRT | 557.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/24/2022 | MP-1 | 24 | MRJN-78
2712 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | NBR-575S | Hrs | HRDH-1990
2713 | FRFM | ARM | 65.5 | 21 Aug 1930 - 1300 | 7436 | 901183 | OBSERVED LOSSES OF 180 BBL BPH WHILE DRILLING @ 7436'. | LCIR | NA |  | 08/24/2022 | NBR-575S | 8 | HRDH-1990
2714 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | PA-326S | Hrs | SHDN-22
2715 | HERR | FMC | 1.5 | 24 Aug 0330 - 0500 | 4285 | 901272 | POWER UNIT NOT WORKING. | TF | TTRQ |  | 08/24/2022 | PA-326S | 1.5 | SHDN-22
2716 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | PA-785S | Hrs | QTIF-269
2717 | XTTE | WDS | 1 | 24 Aug 2230 - 2330 | 13520 | 901259 | WFD MWD LOST SIGNAL. TROUBLE SHOOTING TILL FIX IT. | TF | MWD |  | 08/24/2022 | PA-785S | 1 | QTIF-269
2718 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SCTD-1 | Hrs | SDGM-1084
2719 | FOT | RIG | 17.5 | 23 Aug 2200 - 1530 | 13558 | 901214 | DOWN HOLE MOTOR FAILURE | BHA | MMOT |  | 08/24/2022 | SCTD-1 | 10.5 | SDGM-1084
2720 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SINO-10 | Hrs | JLDI-38
2721 | FOT | OZT | 2.5 | 24 Aug 1930 - 2200 | 10771 | 901267 | TROUBLESHOOTING ON OIL SERV N2 PUMP. | TF | CTPMP |  | 08/24/2022 | SINO-10 | 2.5 | JLDI-38
2722 | FOT | RIG | 2 | 24 Aug 0230 - 0430 | 4180 | 901273 | 2-3/8" DP POWER TONG MULFUNCTION | RR | HSYS |  | 08/24/2022 | SINO-12L | 2 | HWYH-220
2723 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SINO-12L | Hrs | HWYH-220
2724 | HERR | RIG | 1 | 24 Aug 1630 - 1730 | 0 | 901266 | - EXESSESS TIME TO L/D 2-3/8" DP'S INSTED OF RCK BACK IN DERRICK. | JF | DRRK |  | 08/24/2022 | SINO-12L | 1 | HWYH-220
2725 | FOT | RIG | 2 | 24 Aug 0230 - 0430 | 4180 | 901273 | 2-3/8" DP POWER TONG MULFUNCTION | RR | HSYS |  | 08/24/2022 | SINO-12L | 2 | HWYH-220
2726 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SINO-33L | Hrs | HRDH-1542
2727 | FOT | RIG | 64 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/24/2022 | SINO-33L | 24 | HRDH-1542
2728 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SND-2001 | Hrs | HWYH-1229
2729 | LHFL | RIG | 3 | 24 Aug 0730 - 1030 | 0 | 901269 | REPLACE/REPAIR DAMAGED HYDRAULIC FIITINGS ON TDS. | RR | HSYS |  | 08/24/2022 | SND-2001 | 3 | HWYH-1229
2730 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SND-2003 | Hrs | GZLN-1
2731 | FOT | RIG | 39.5 | 23 Aug 0500 - 2030 | 5452 | 901218 | BOP LEAKS WHILE PRESSURE TESTING | BOP | BOP |  | 08/24/2022 | SND-2003 | 15.5 | GZLN-1
2732 | FOT | NSL | 6 | 24 Aug 2300 - 0500 | 5 | 901274 | POOH 2"7/8 PUMP THRU PLUG,NOTICED 100 LBS OVER PULL WHILE ENTERING LUBRICATOR,JAR UP BY HAND,AND LOST 300LBS BHA WEIGHT - SLICK LINE CABLE PARTED- | TF | SLICK |  | 08/24/2022 | SND-2004 | 6 | BRRI-1148
2733 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SND-2004 | Hrs | BRRI-1148
2734 | FOT | SWT | 193.75 | 16 Aug 0700 - 2300 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/24/2022 | SND-2004 | 18 | BRRI-1148
2735 | FOT | NSL | 6 | 24 Aug 2300 - 0500 | 5 | 901274 | POOH 2"7/8 PUMP THRU PLUG,NOTICED 100 LBS OVER PULL WHILE ENTERING LUBRICATOR,JAR UP BY HAND,AND LOST 300LBS BHA WEIGHT - SLICK LINE CABLE PARTED- | TF | SLICK |  | 08/24/2022 | SND-2004 | 6 | BRRI-1148
2736 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SND-2005 | Hrs | MHKK-2
2737 | WOTO | ARM | 7.75 | 23 Aug 2245 - 0630 | 5828 | 901213 | WAIT ON WFD HANDLING EQUIPMENT TO RUN 2-7/8" CEMENT STINGER. LAST MINUTE CHANGE OF PLANS TO SET CEMENT PLUG. | WO | NA |  | 08/24/2022 | SND-2005 | 1.5 | MHKK-2
2738 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SND-2007 | Hrs | AWTD-104001
2739 | FOT | BHI | 50 | 22 Aug 1400 - 0500 | 18640 | 901156 | BAKER LOST COMMUNICATION WITH THE AUTOTRAK RSS TO THE MWD TOOL. | BHA | MWD |  | 08/24/2022 | SND-2007 | 14 | AWTD-104001
2740 | SRVC | HCM | 13.5 | 24 Aug 1530 - 0500 | 7470 | 901257 | WAIT ON HALLIBUTON FINAL WELL LOCK PROGRAM | WO | NA |  | 08/24/2022 | SP-154 | 13.5 | SDGM-353
2741 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SP-154 | Hrs | SDGM-353
2742 | FOT | TOD | 32.5 | 23 Aug 0700 - 1530 | 7267 | 901232 | UNABLE TO CLOSE HYDRO SEAL DURING CEMENTING OFF BOTTOM LINER CAUSING FAILED PRESSURE TEST, | TF | DV |  | 08/24/2022 | SP-154 | 10.5 | SDGM-353
2743 | SRVC | HCM | 13.5 | 24 Aug 1530 - 0500 | 7470 | 901257 | WAIT ON HALLIBUTON FINAL WELL LOCK PROGRAM | WO | NA |  | 08/24/2022 | SP-154 | 13.5 | SDGM-353
2744 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SP-165 | Hrs | FDHL-146
2745 | DFLI | EMC | 24 | 24 Aug 0500 - 0500 | 10585 | 901260 | MUD FOAMING ISSUE PRIOR LOGGING | MUD | NA |  | 08/24/2022 | SP-165 | 24 | FDHL-146
2746 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SP-260 | Hrs | HMYM-531812
2747 | FOT | BHI | 14 | 24 Aug 1430 - 0500 | 15978 | 901253 | BAKER MWD FAILED. | TF | MS |  | 08/24/2022 | SP-260 | 14 | HMYM-531812
2748 | 6559 | 6559 | TI | E | 4186 | STDP | CONTD RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 3562' TO TAG BTM @6559'.-WASH AND REAM DOWN TILL TAG BTM @6559'. | 6559 | 3562 | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2749 | 6559 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTMS UP & CHC WITH 200 GPM & PRESSURE 700 PSI. | 6559 |  | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2750 | 6559 |  | CIRC | E | 4186 | MPMP | DROP 1" NOV DIVERTING BALL, PUMP DOWN WITH 80 GPM & WAIT TILL SEATED IN ORDER TO DIVERT FLUID AWAY FROM THE INNER BARREL. -CONFIRM SPACE OUT FOR CUTTING THE CORE@6559'.-RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS. | 6559 |  | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2751 | 6621 |  | CORE | E | 4186 | CORC | CUT 6-1/8" X 2 5/8" CORE RUN #5 FROM 6559' TO 6621' W/70 PCF POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, RPM: 65 - TQ 2-3 KLFTLB & GPM: 180 - PRESS 800 PSI.-CORING 62 FT INSIDE ARAB D ZONE (ADAD3B TO ADABD4) FORMATION.-STOP ROTATION AND BREAK OUT CORE 15 KLBS OVERPULL INDICATION | 6559 |  | NOC | 08/24/2022 | SP-53L | CORE | HRDH-528
2752 | 6621 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTM UP WITH 120 GPM @ 500 PSI WITH FULL RETURNS. | 6621 |  | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2753 | 6621 |  | SDR1 | E | 4186 | NA | FLOW CHECK-WELL STATIC OK. | 6621 |  | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2754 | 6621 | 6374 | TO | E | 4186 | STDP | POOH 6 1/8" NOV CORING ASSY. TO/7" CSG SHOE @ 6374' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6621 | 6621 | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2755 | 6621 |  | SDR1 | E | 4186 | NA | FLOW CHECK @ 7" CSG SHOE -WELL STATIC OK. | 6621 |  | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2756 | 6621 | 5900 | TO | E | 4186 | STDP | CONTD POOH 6 1/8" NOV CORING ASSY. FROM / 7" CSG SHOE @ 6374' TO 5900' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEE | 6621 | 6374 | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2757 | 6621 |  | SDR1 | E | 4186 | NA | FLOW CHECK AFTER PULL 5 STDS - WELL STATIC OK | 6621 |  | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2758 | 6621 | 1597 | TO | E | 4186 | STDP | CONTD POOH 6 1/8" NOV CORING ASSY. TO 7" TOL@ 1597' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6621 | 5900 | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2759 | 6621 |  | SDR1 | E | 4186 | NA | FLOW CHECK @7" TOL WELL STATIC OK. | 6621 |  | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2760 | 6621 | 615 | TO | E | 4186 | STDP | CONTD POOH 6-1/8" NOV CORING ASSY. TO 615' CONTROLLED SPEED 6MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6621 | 1597 | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2761 | 6621 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT TOP BHA - WELL STATIC OK.-CHECKING FOR H2S-ZERO H2S READING. | 6621 |  | RIG | 08/24/2022 | SP-53L | CORE | HRDH-528
2762 | 6621 |  | HT | E | 4186 | CORC | HPJSM, CON'T POOH 6-1/8" NOV CORING ASSY TO SURFACE CONTROLLED SPEED 6 MIN/STD SLIPS TO SLIPS.-RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.-ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.-L/D INNER BARREL, 62' RECOVERED (100 % RECOVERY) FROM CORE RUN #5 -CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 6621 |  | NOC | 08/24/2022 | SP-53L | CORE | HRDH-528
2763 | 6621 |  | HT | E | 4186 | CORC | HPJSM, P/U & M/U 6-1/8" NOV CORE ASSY RUN#6 -----ONGOING.-6-1/8" CORE HEAD + 4-3/4" CORE OUTER BARRELS & 3-3/8" INNER BARRELS (30FT) + FLOAT SUB W/ FLAPPER TYPE FLOAT VALVE (BALL SIZE IS 1")+15 X 4-3/4" DC'S+ 4-3/4" DRILLING JAR+2 X 4 3/4" DC'S +XO+ DP'S. | 6621 |  | NOC | 08/24/2022 | SP-53L | CORE | HRDH-528
2764 | 188.25 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 24 | 4186 | 13 Aug 0230 | 08/24/2022 | SP-53L | Type | HRDH-528
2765
2766
2767 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SSA-101 | Hrs | QTIF-785
2768 | FOT | SJT | 9 | 24 Aug 0900 - 0500 | 19300 | 901261 | TAQA CTU MLT TOOL FAILURE (MULTI LATERAL TOOLS NOT WORKING PROPERLY) | TF | CTBG |  | 08/24/2022 | SSA-101 | 9 | QTIF-785
2769 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SSA-202 | Hrs | QTIF-191
2770 | FOT | SAM | 4.25 | 24 Aug 0015 - 0500 | 18120 | 901265 | PRESSURE SUDDENLY DROPPED WHILE DRLG AT 18120' MD AND LOST MWD SIGNAL. | BHA | MACS |  | 08/24/2022 | SSA-202 | 4.25 | QTIF-191
2771 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | SSA-5972 | Hrs | SHDN-19
2772 | FOT | HWP | 24 | 23 Aug 1800 - 0500 | 14415 | 901168 | HALLIBURTON TPL LOGGING TOOL FAILURE. | TF | WLT |  | 08/24/2022 | SSA-5972 | 13 | SHDN-19
2773 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/24/2022 | STY-038 | Hrs | ZULF-2089
2774 | HINW | HWP | 87.5 | 21 Aug 1000 - 0130 | 5537 | 901117 | HALLIBURTON MADE ANOTHER CORRELATION PASS BELOW PUNCHING DEPTH, CAUSING THE TOOL TO GET STUCK AT X-NIPPLE | STUK | WLT |  | 08/24/2022 | STY-038 | 20.5 | ZULF-2089
2775 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | 095TE | Hrs | MNIF-126
2776 | FPMP | RIG | 1.5 | 25 Aug 1730 - 1900 | 4497 | 901316 | CIRCULATE W/PUMP #02 MEANWHILE REPAIR ON MUD PUMP #01 & #03. | RR | MPMP |  | 08/25/2022 | 095TE | 1.5 | MNIF-126
2777 | FOT | GEP | 6.5 | 25 Aug 2230 - 0500 | 250 | 901326 | BEFORE MAKING UP TIE BACK TOOL TO CSG FOUND THAT MLS TOOL THREAD WAS INCOMPATIBLE WITH CASING, AND WOULD REQUIRE A CROSSOVER. | TF | MLS |  | 08/25/2022 | ADC-17 | 6.5 | ZULF-1380
2778 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ADC-17 | Hrs | ZULF-1380
2779 | FOT | GEP | 1 | 25 Aug 0500 - 0600 | 250 | 901325 | VETCO GRAY REP ATTEMPT TO CLOSE WASH PORTS OF 18-5/8" TIE BACK, ATTEMPT TO PRESSURE TEST WITHOUT SUCCESS, PRESSURE DROP. MADE MUUTLIPE ATTEMPTS WITH NO SUCCESS | TF | MLS |  | 08/25/2022 | ADC-17 | 1 | ZULF-1380
2780 | FOT | GEP | 6.5 | 25 Aug 2230 - 0500 | 250 | 901326 | BEFORE MAKING UP TIE BACK TOOL TO CSG FOUND THAT MLS TOOL THREAD WAS INCOMPATIBLE WITH CASING, AND WOULD REQUIRE A CROSSOVER. | TF | MLS |  | 08/25/2022 | ADC-17 | 6.5 | ZULF-1380
2781 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ADC-42L | Hrs | SDGM-1258
2782 | FOT | TK3 | 29 | 24 Aug 2100 - 0200 | 12520 | 901271 | STRING GOT PLUGGED WHILE FILLING UP. | DSF | STRG |  | 08/25/2022 | ADC-42L | 21 | SDGM-1258
2783 | 7045 | 4200 | LOG | E | 4305 | WLT | RIH WL RUN#2 LOGGING TOOLS (RCX-IFX-GR) ON 4" DRIFTED DP STDS WITH CONTROL SPEED 2 MIN/STD SLIPS TO SLIPS TO SES DEPTH @ 4200'. (LATCHING DEPTH).- FILL STRING EVERY 10 STDS & BREAK CIRC.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 1400 | BAW | 08/25/2022 | ADC-54L | LOG | HRDH-584
2784 | 7045 |  | CIRC | E | 4305 | MPMP | CIRCULATE TWICE STRING CAPACITY, 100% RETURN. USED BAKER WL SCREEN.- MW IN / OUT 79 PCF | 7045 |  | RIG | 08/25/2022 | ADC-54L | CT | HRDH-584
2785 | 7045 |  | OTH | E | 4305 | NA | HPJSM. R/U BH W/L SHEAVES AND INSTALL SES.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 |  | BAW | 08/25/2022 | ADC-54L | LOG | HRDH-584
2786 | 7045 | 4200 | LOG | E | 4305 | WLT | RIH WITH LATCH HEAD AND LATCH DOWN HOLE TOOL. TEST COMMUNICATION - OK. MAKE PULL TEST ON SES CABLE CLAMP W/ 5000 LB LINE PULL - OK.- PUMP 50 BBL LATCHING PILL PRIOR TO LATCH.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC | 7045 | 4200 | BAW | 08/25/2022 | ADC-54L | LOG | HRDH-584
2787 | 7045 | 6658 | LOG | E | 4305 | WLT | CONT. RIH WL RUN#2 LOGGING TOOLS (RCX-IFX-GR) ON 4" DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED 1-2 MIN/STD SLIPS TO SLIPS TO 6658' 1ST (PRESSURE POINT).- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7045 | 4200 | BAW | 08/25/2022 | ADC-54L | LOG | HRDH-584
2788 | 7045 | 6869 | LOG | E | 4305 | WLT | CONT. RIH WL RUN#2 LOGGING TOOLS (RCX-IFX-GR) ON 4" DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED WHILE LOG DOWN F/ 6658' T/ 6869'.- PERFORMED STICK TENDENCY TESTS @ 6658' FOR 15 MIN & 30 MINS, NO STICKING TENDENCY.- RECORDED 18/18 PRESSURE POINTS F/ 6,658' T/ 6,869'.- PRESS POINTS @: 6,658', 6,668', 6,675', 6,680', 6,686', 6,698', 6,706', 6,716', 6,721', 6,734', 6,742', 6,749', 6,757', 6,767' (REPEATED 3 TIMES), 6,779', 6,816' (TIGHT- REPEATED 3 TIMES), 6,838' (TIGHT- REPEATED 3 TIMES), 6,869'. - MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7045 | 6658 | BAW | 08/25/2022 | ADC-54L | LOG | HRDH-584
2789 | 41.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" PILOT HOLE LOGGING : RUN#1: MREX LOG ON TWO MODES: GAS MODE & LIGHT OIL MODE / RUN#2: PCL LOG RUN#2: RCX-IFX-GR (PRESSURE & SAMPLES). | 24 | 4305 | 23 Aug 0830 | 08/25/2022 | ADC-54L | Type | HRDH-584
2790
2791
2792 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ADC-55L | Hrs | UTMN-3171
2793 | STBH | TK3 | 622 | 30 Jul 0830 - 0500 | 12245 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/25/2022 | ADC-55L | 24 | UTMN-3171
2794 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ADC-58L | Hrs | ABHD-169
2795 | MATL | TK3 | 32.75 | 23 Aug 1430 - 2015 | 13523 | 901233 | OBSERVED A PIECE OF RUBBER FROM THE ANNULAR PACKING ELEMENTS' FINGERS JAMMED ON THE CABLE CLAMP WHILE POOH. | WO | NA |  | 08/25/2022 | ADC-58L | 15.25 | ABHD-169
2796 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ADES-174 | Hrs | GHZL-72
2797 | SFHS | BFW | 87.75 | 22 Aug 0530 - 0500 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/25/2022 | ADES-174 | 22.25 | GHZL-72
2798 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ADM-655 | Hrs | SFNY-183
2799 | WTHR | ARM | 10 | 25 Aug 1900 - 0500 | 0 | 901184 | WAIT ON HI-TIDE TO ENTER SFNY LAGOON FOR SAFE APPROACH TO NEXT PLATFORM SFNY 178/183. | WON | NA |  | 08/25/2022 | ADM-655 | 10 | SFNY-183
2800 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | AOD-1 | Hrs | ZULF-694
2801 | DSFT | HCO | 12.25 | 25 Aug 1645 - 0500 | 5623 | 901313 | ATTEMPTED TO RETRIEVE RBP PER HLB PROCEDURE, RBP WAS NOT IN RETRIEVAL TOOL. | JF | RTTS |  | 08/25/2022 | AOD-1 | 12.25 | ZULF-694
2802 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ARO-2001 | Hrs | BRRI-93
2803 | FOT | RIG | 1 | 25 Aug 1630 - 1730 | 300 | 901315 | DRAWORKS CLUTCH AIRLINE LEAKING | RR | DWKS |  | 08/25/2022 | ARO-2001 | 1 | BRRI-93
2804 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ARO-2003 | Hrs | MNIF-733
2805 | WOPF | AP2 | 240 | 16 Aug 0500 - 0500 | 0 | 900956 | WAIT ON FIELD SERVICE TO INSTALL ISOLATION PLUGS. | WO | NA |  | 08/25/2022 | ARO-2003 | 24 | MNIF-733
2806 | HERR | HWP | 6.5 | 25 Aug 2230 - 0500 | 8852 | 901324 | HALLIBURTON DEPTH COUNTER/ENCODER NOT READING CORRECTLY. | JF | TEMP |  | 08/25/2022 | ARO-3002 | 6.5 | MRJN-813
2807 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ARO-3002 | Hrs | MRJN-813
2808 | HERR | BCT | 18 | 24 Aug 1800 - 1200 | 8852 | 901268 | BAKER COIL TUBING REEL PLUG UP. | JF | CTAC |  | 08/25/2022 | ARO-3002 | 7 | MRJN-813
2809 | HERR | HWP | 6.5 | 25 Aug 2230 - 0500 | 8852 | 901324 | HALLIBURTON DEPTH COUNTER/ENCODER NOT READING CORRECTLY. | JF | TEMP |  | 08/25/2022 | ARO-3002 | 6.5 | MRJN-813
2810 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ARO-4001 | Hrs | MRJN-532
2811 | FOT | RIG | 4.5 | 25 Aug 2200 - 0500 | 8705 | 901321 | ATTEMPT TO PUMP DP SLUG, TDS IBOP NOT OPEN, TROUBLESHOOTING SAME, OBSERVED CRANK ARM ROLLERS ON BOTH SIDES OF ACTUATORS WERE BROKEN, NEED TO REPLACE SAME. | RR | TDS |  | 08/25/2022 | ARO-4001 | 4.5 | MRJN-532
2812 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | DPS-45 | Hrs | UTMN-2331
2813 | FOT | SDM | 48 | 23 Aug 0315 - 0415 | 18171 | 901171 | LOST COMMUNICATION W/ SLB TOOLS MWD/LWD . | BHA | MWD |  | 08/25/2022 | DPS-45 | 22.25 | UTMN-2331
2814 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | DPS-74 | Hrs | NJYN-33
2815 | FOT | RIG | 4.5 | 25 Aug 0030 - 0500 | 0 | 901320 | DRAW WORK ENCODER MOTOR-A FAILURE. | RR | DWKS |  | 08/25/2022 | DPS-74 | 4.5 | NJYN-33
2816 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | DQ-47 | Hrs | KHRS-280
2817 | FOT | BAW | 17.25 | 24 Aug 1615 - 0930 | 11860 | 901263 | RDD REQUEST TO REPEAT THE LOG OF OPEN HOLE TO CONFIRM QUALITY LOG DATA. | TF | WLT |  | 08/25/2022 | DQ-47 | 4.5 | KHRS-280
2818 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | ENS-108 | Hrs | ZULF-2015
2819 | GRF | RIG | 72 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/25/2022 | ENS-108 | 24 | ZULF-2015
2820 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | EXL-IVA | Hrs | ZULF-2040
2821 | WOTO | EX1 | 19.25 | 24 Aug 1700 - 1215 | 6687 | 901258 | LOST TIME EXPRO: PICK UP EXPRO CROSSOVER AND LOWER TO TOP OF 4 1/16" TREE, ATTEMPT TO MAKE UP CROSSOVER WITHOUT SUCCESS, SOURCE A REPLACEMENT CROSSOVER. | WO | NA |  | 08/25/2022 | EXL-IVA | 7.25 | ZULF-2040
2822 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | MP-1 | Hrs | MRJN-78
2823 | FOT | NRT | 581.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/25/2022 | MP-1 | 24 | MRJN-78
2824 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | MP-4 | Hrs | LWHH-20
2825 | FOT | ARM | 14 | 25 Aug 1500 - 0500 | 10598 | 901333 | OBSERVED PRESSURE DROP OF 700 PSI WHILE DRILLING 6-1/8" HOLE SECTION. | DSF | STRG |  | 08/25/2022 | MP-4 | 14 | LWHH-20
2826 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | NBR-263S | Hrs | QTIF-736
2827 | STBH | ARM | 306.5 | 29 Jul 0230 - 0300 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/25/2022 | NBR-263S | 22 | QTIF-736
2828 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | NBR-575S | Hrs | HRDH-1990
2829 | FRFM | ARM | 16 | 25 Aug 0500 - 2100 | 8080 | 901332 | OBSERVED LOSSES WHILE DRILLING @ 8080' | LCIR | NA |  | 08/25/2022 | NBR-575S | 16 | HRDH-1990
2830 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | PA-326S | Hrs | SHDN-22
2831 | HERR | FMC | 3.5 | 24 Aug 0330 - 0700 | 4285 | 901272 | EXCESSIF TIME WHILE RUNNING 13-3/8" CSG, DUE JAM UNIT . | TF | TTRQ |  | 08/25/2022 | PA-326S | 2 | SHDN-22
2832 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | PA-604S | Hrs | HRDH-2414
2833 | FOT | RIG | 7.5 | 25 Aug 2130 - 0500 | 160 | 901334 | DURING DRILLING BOTH CELLAR JETS STOP TO WORKING ONE BY ONE. | RR | CSYS |  | 08/25/2022 | PA-604S | 7.5 | HRDH-2414
2834 | FOT | BHI | 1.75 | 25 Aug 1900 - 2045 | 8660 | 901323 | BAKER HUGES CHANGE OUT ACTUATOR. | BHA | RSS |  | 08/25/2022 | PN-9 | 1.75 | MRJN-673
2835 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | PN-9 | Hrs | MRJN-673
2836 | FOT | RIG | 1 | 25 Aug 1630 - 1730 | 5225 | 901322 | CHANGE OUT BX ELEVATORS. | RR | TDS |  | 08/25/2022 | PN-9 | 1 | MRJN-673
2837 | FOT | BHI | 1.75 | 25 Aug 1900 - 2045 | 8660 | 901323 | BAKER HUGES CHANGE OUT ACTUATOR. | BHA | RSS |  | 08/25/2022 | PN-9 | 1.75 | MRJN-673
2838 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | RM-74A | Hrs | HSBH-68
2839 | FOT | RIG | 1 | 25 Aug 0100 - 0200 | 6333 | 901327 | DRAWWORK E-BRAKE HYDRAULIC LINE REPTURED, REPAIR THE SAME | RR | DWKS |  | 08/25/2022 | RM-74A | 1 | HSBH-68
2840 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SINO-12L | Hrs | HWYH-220
2841 | HERR | RIG | 2 | 24 Aug 1630 - 0645 | 0 | 901266 | - EXESSESS TIME TO L/D 2-3/8" DP'S INSTED OF RCK BACK IN DERRICK. | JF | DRRK |  | 08/25/2022 | SINO-12L | 1 | HWYH-220
2842 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SINO-33L | Hrs | HRDH-1542
2843 | FOT | RIG | 88 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/25/2022 | SINO-33L | 24 | HRDH-1542
2844 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SINO-5L | Hrs | UTMN-639
2845 | DFOR | SPS | 24.5 | 24 Aug 0800 - 0830 | 9979 | 901293 | UNABLE TO BUILD UP TO 90.5 DEG AS PER GOC | DD | RSS |  | 08/25/2022 | SINO-5L | 3.5 | UTMN-639
2846 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SND-1501 | Hrs | HWYH-89
2847 | FOT | WWD | 24 | 25 Aug 0500 - 0500 | 0 | 901328 | FAILED 7" WFD HYD WHIPSTOCK | TF | WPSTK |  | 08/25/2022 | SND-1501 | 24 | HWYH-89
2848 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SND-1502 | Hrs | HRDH-425
2849 | HINW | SPL | 4 | 25 Aug 0800 - 1200 | 5058 | 901317 | PARTED SLICK LINE. | STUK | SLICK |  | 08/25/2022 | SND-1502 | 4 | HRDH-425
2850 | FOT | NSL | 13 | 24 Aug 2300 - 1200 | 5 | 901274 | POOH 2"7/8 PUMP THRU PLUG,NOTICED 100 LBS OVER PULL WHILE ENTERING LUBRICATOR,JAR UP BY HAND,AND LOST 300LBS BHA WEIGHT - SLICK LINE CABLE PARTED- | TF | SLICK |  | 08/25/2022 | SND-2004 | 7 | BRRI-1148
2851 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SND-2004 | Hrs | BRRI-1148
2852 | FOT | SWT | 210.75 | 16 Aug 0700 - 0500 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/25/2022 | SND-2004 | 17 | BRRI-1148
2853 | FOT | NSL | 13 | 24 Aug 2300 - 1200 | 5 | 901274 | POOH 2"7/8 PUMP THRU PLUG,NOTICED 100 LBS OVER PULL WHILE ENTERING LUBRICATOR,JAR UP BY HAND,AND LOST 300LBS BHA WEIGHT - SLICK LINE CABLE PARTED- | TF | SLICK |  | 08/25/2022 | SND-2004 | 7 | BRRI-1148
2854 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SND-2005 | Hrs | MHKK-2
2855 | HERR | RIG | .5 | 25 Aug 0430 - 0500 | 5671 | 901331 | ROUSTABOUT CREW PUMPED OUT CELLAR TO SHAKER HEADER BOX CONTAMINATING ACTIVE MUD SYSTEM WITH WATER. | JF | CSYS |  | 08/25/2022 | SND-2005 | .5 | MHKK-2
2856 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SND-2007 | Hrs | AWTD-104001
2857 | FOT | BHI | 70.5 | 22 Aug 1400 - 0130 | 18640 | 901156 | BAKER LOST COMMUNICATION WITH THE AUTOTRAK RSS TO THE MWD TOOL. | BHA | MWD |  | 08/25/2022 | SND-2007 | 20.5 | AWTD-104001
2858 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SP-125 | Hrs | ANDR-20
2859 | FOT | HWP | 20 | 25 Aug 0900 - 0500 | 9513 | 901318 | HES WL CABLE CLAMP'S BAR AND EDGE CAP HEAD LEFT IN HOLE. | TF | WLT |  | 08/25/2022 | SP-125 | 20 | ANDR-20
2860 | SRVC | HCM | 17.5 | 24 Aug 1530 - 0900 | 7470 | 901257 | WAIT ON HALLIBUTON FINAL WELL LOCK PROGRAM | WO | NA |  | 08/25/2022 | SP-154 | 4 | SDGM-353
2861 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SP-154 | Hrs | SDGM-353
2862 | FOT | TOD | 52.5 | 23 Aug 0700 - 0500 | 7267 | 901232 | UNABLE TO CLOSE HYDRO SEAL DURING CEMENTING OFF BOTTOM LINER CAUSING FAILED PRESSURE TEST, | TF | DV |  | 08/25/2022 | SP-154 | 20 | SDGM-353
2863 | SRVC | HCM | 17.5 | 24 Aug 1530 - 0900 | 7470 | 901257 | WAIT ON HALLIBUTON FINAL WELL LOCK PROGRAM | WO | NA |  | 08/25/2022 | SP-154 | 4 | SDGM-353
2864 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SP-167 | Hrs | HRDH-218
2865 | FOT | RIG | 3.5 | 25 Aug 1330 - 1700 | 9725 | 901330 | HYDRAULIC UNIT MALFUNCTION. | RR | HSYS |  | 08/25/2022 | SP-167 | 3.5 | HRDH-218
2866 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SP-257 | Hrs | HZEM-162412
2867 | IDPR | BHI | 4.25 | 25 Aug 0815 - 0300 | 16803 | 901312 | BHI HIGH TOOL TEMP. | DD | RSS |  | 08/25/2022 | SP-257 | 4.25 | HZEM-162412
2868 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SP-260 | Hrs | HMYM-531812
2869 | FOT | BHI | 27.5 | 24 Aug 1430 - 0500 | 15978 | 901253 | BAKER MWD FAILED. | TF | MS |  | 08/25/2022 | SP-260 | 13.5 | HMYM-531812
2870 | 6621 |  | HT | E | 4186 | CORC | HPJSM, P/U & M/U 6-1/8" NOV CORE ASSY RUN#6 TO 585'.-6-1/8" CORE HEAD + 4-3/4" CORE OUTER BARRELS & 3-3/8" INNER BARRELS (30FT) +FLOAT SUB W/ FLAPPER TYPE FLOAT VALVE (BALL SIZE IS 1")+15 X 4-3/4" DC'S+ 4-3/4" DRILLING JAR+2 X 4 3/4" DC'S +XO+ DP'S. | 6621 |  | NOC | 08/25/2022 | SP-53L | CORE | HRDH-528
2871 | 6621 | 6621 | TI | E | 4186 | STDP | RIH 6-1/8" NOV CORE ASSY CONTROLLED SPEED FROM 585' TO TAG BTM@ 6621'.-GENTLY PASSED 7" TOL .-WASH AND REAM DOWN TILL TAG BTM @6621'. | 6621 | 585 | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2872 | 6621 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTMS UP & CHC WITH 200 GPM & PRESSURE 700 PSI. | 6621 |  | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2873 | 6621 |  | CIRC | E | 4186 | MPMP | DROP 1" NOV DIVERTING BALL, PUMP DOWN WITH 80 GPM & WAIT TILL SEATED IN ORDER TO DIVERT FLUID AWAY FROM THE INNER BARREL. -CONFIRM SPACE OUT FOR CUTTING THE CORE@6621'.-RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS. | 6621 |  | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2874 | 6647 |  | CORE | E | 4186 | CORC | CUT 6-1/8" X 2 5/8" CORE RUN #6 FROM 6621' TO 6647' W/70 PCF POLYMER MUD W/ 100 % RETURNS.-CORING PARAMETERS: WOB: 3-8 KLBS, RPM: 70 - TQ 2-3 KLFTLB & GPM: 180 - PRESS 800 PSI.-CORING 26 FT INSIDE ARAB D ZONE (ABD4 TO BADR) FORMATION.-STOP ROTATION AND BREAK OUT CORE 18 KLBS OVERPULL INDICATION | 6621 |  | NOC | 08/25/2022 | SP-53L | CORE | HRDH-528
2875 | 6647 |  | CIRC | E | 4186 | MPMP | CIRCULATE BTM UP WITH 120 GPM @ 500 PSI WITH FULL RETURNS. | 6647 |  | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2876 | 6647 |  | SDR1 | E | 4186 | NA | FLOW CHECK-WELL STATIC OK. | 6647 |  | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2877 | 6647 | 6374 | TO | E | 4186 | STDP | POOH 6 1/8" NOV CORING ASSY. TO/7" CSG SHOE @ 6374' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6647 | 6647 | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2878 | 6647 |  | SDR1 | E | 4186 | NA | FLOW CHECK @ 7" CSG SHOE -WELL STATIC OK. | 6647 |  | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2879 | 6647 | 5900 | TO | E | 4186 | STDP | CONTD POOH 6 1/8" NOV CORING ASSY. FROM / 7" CSG SHOE @ 6374' TO 5900' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEE | 6647 | 6374 | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2880 | 6647 |  | SDR1 | E | 4186 | NA | FLOW CHECK AFTER PULL 5 STDS - WELL STATIC OK | 6647 |  | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2881 | 6647 | 1597 | TO | E | 4186 | STDP | CONTD POOH 6 1/8" NOV CORING ASSY. TO 7" TOL@ 1597' CONTROLLED SPEED 3MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6647 | 5900 | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2882 | 6647 |  | SDR1 | E | 4186 | NA | FLOW CHECK @7" TOL WELL STATIC OK. | 6647 |  | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2883 | 6647 | 677 | TO | E | 4186 | STDP | CONTD POOH 6-1/8" NOV CORING ASSY. TO 677' CONTROLLED SPEED 6MIN/STD SLIPS TO SLIPS.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6647 | 1597 | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2884 | 6647 |  | SDR1 | E | 4186 | NA | FLOW CHECK AT TOP BHA - WELL STATIC OK.-CHECKING FOR H2S-ZERO H2S READING. | 6647 |  | RIG | 08/25/2022 | SP-53L | CORE | HRDH-528
2885 | 6647 |  | HT | E | 4186 | CORC | HPJSM, CONTD POOH 6-1/8" NOV CORING ASSY TO SURFACE CONTROLLED SPEED 6 MIN/STD SLIPS TO SLIPS.-RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.-ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.-L/D INNER BARREL, 26' RECOVERED (100 % RECOVERY) FROM CORE RUN #6-CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 6647 |  | CPR | 08/25/2022 | SP-53L | CORE | HRDH-528
2886 | 6647 |  | HT | N |  | BHA | HPJSM, M/U & RIH W/ 6-1/8" MTR/MWD/GR ASSY -------ON GOING -6-1/2" PDC BIT (DD406X, S/NO: 7915105, JETS: 3 X 14) +MTR, 6 1/8" STRR, MWD/GR, FILTER SUB, 6 1/8" STRR, 12 X 4 3/4" DC, D/JAR, 2X 4 3/4" DC, X/O, DP .-CONNECT TO TOOLS AND PERFORM TOOLS VERIFICATION TEST.-MTR SPECIFICATION: 5 7/8"DURAMAX & 0.75 REV/GAL.-SENSORS OFFSET FROM BIT: GR: 51.92 FT & DIRECTIONAL: 55.59 FT.-MONITOR WELL THRU TRIP TANK, WELL STATIC. | 6647 |  | RIG | 08/25/2022 | SP-53L | DRLG | HRDH-528
2887 | 211.25 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 23 | 4186 | 13 Aug 0230 | 08/25/2022 | SP-53L | Type | HRDH-528
2888
2889
2890 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SSA-101 | Hrs | QTIF-785
2891 | FOT | SJT | 25.75 | 24 Aug 0900 - 2215 | 19300 | 901261 | TAQA CTU MLT TOOL FAILURE (MULTI LATERAL TOOLS NOT WORKING PROPERLY) | TF | CTBG |  | 08/25/2022 | SSA-101 | 16.75 | QTIF-785
2892 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SSA-202 | Hrs | QTIF-191
2893 | FOT | SAM | 23 | 24 Aug 0015 - 2345 | 18120 | 901265 | PRESSURE SUDDENLY DROPPED WHILE DRLG AT 18120' MD AND LOST MWD SIGNAL. | BHA | MACS |  | 08/25/2022 | SSA-202 | 18.75 | QTIF-191
2894 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SSA-5914 | Hrs | WDYH-80
2895 | FOT | BHI | 43.25 | 24 Aug 0845 - 0500 | 13337 | 901292 | LOST SIGNAL WITH BAKER RSS | BHA | RSS |  | 08/25/2022 | SSA-5914 | 23 | WDYH-80
2896 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SSA-5962 | Hrs | HRDH-2513
2897 | FOT | CRW | 18.5 | 25 Aug 0645 - 0500 | 11714 | 901314 | CORETRAX 9-5/8" LTTT PACKER FAILURE. | TF | SCRP |  | 08/25/2022 | SSA-5962 | 18.5 | HRDH-2513
2898 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | SSA-5972 | Hrs | SHDN-19
2899 | FOT | HWP | 48 | 23 Aug 1800 - 0500 | 14415 | 901168 | HALLIBURTON TPL LOGGING TOOL FAILURE. | TF | WLT |  | 08/25/2022 | SSA-5972 | 24 | SHDN-19
2900 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/25/2022 | T914 | Hrs | UTMN-415
2901 | FOT | RIG | 2 | 25 Aug 0630 - 0830 | 5400 | 901319 | HAD ELECTRICAL FAULT PROBLEM ON DYNAMIC MOTOR FOR DRAWWORKS. | RR | DWKS |  | 08/25/2022 | T914 | 2 | UTMN-415
2902 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | ADC-17 | Hrs | ZULF-1380
2903 | FOT | GEP | 10.25 | 25 Aug 2230 - 0845 | 250 | 901326 | BEFORE MAKING UP TIE BACK TOOL TO CSG FOUND THAT MLS TOOL THREAD WAS INCOMPATIBLE WITH CASING, AND WOULD REQUIRE A CROSSOVER. | TF | MLS |  | 08/26/2022 | ADC-17 | 3.75 | ZULF-1380
2904 | 7045 | 6869 | LOG | E | 4305 | WLT | POSITION STRING @ 1ST SAMPLE POINT @ 6869',(STATION#1 SAMPLING POINT), PERFORM STICKY TENDENCY TEST FOR 15 MIN, 30 MIN & 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6869 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2905 | 7045 | 6869 | LOG | E | 4305 | WLT | STATION#1 (SAMPLING)@ 6869' (3B21), CYCLE#1 : - TRIED 2 TIMES WITH STANDARDS PROBE, NO MOBILITY.- CHANGE TO XL PROBE & PUMP OUT STATION #1 @ 6,869'.- PUMP OUT 140 LITRES OF FORMATION WATER, 8 LITERS OIL, NO SAMPLE TAKEN.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 0.94 BBLS (WATER: 0.88 BBLS - OIL: 0.04 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 400 PSI (3B21).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 7045 | 6869 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2906 | 7045 | 6869 | LOG | E | 4305 | WLT | STATION#1 (SAMPLING) @ 6869' (3B21), CYCLE#2 : - ACTIVATE XL PROBE & PUMP OUT STATION #1 @ 6,869'.- CONT. PUMP STATION#1, PUMP OUT 254 LITRES OF FORMATION WATER, 13 LITERS OIL, TAKE 1 BOTTLE OF 500CC FLUID SAMPLE - TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE FROM BOTH CYCLES - 1.68 BBLS (WATER: 1.60 BBLS - OIL: 0.08 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 400 PSI (3B21).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 7045 | 6869 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2907 | 7045 | 6767 | OTH | E | 4305 | NA | POOH W/ LOG TOOLS & POSITION STRING @ 6767' (STATION#2 PUMP OUT POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6869 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2908 | 7045 | 6767 | LOG | E | 4305 | WLT | STATION#2 (PUMP OUT/SAMPLE)@ 6767' (2B11), CYCLE#1 : - TRIED 5 TIMES WITH STANDARDS PROBE, NO MOBILITY (1HR).- CHANGE TO XL PROBE & PUMP OUT STATION #2 @ 6767'.- PUMP OUT 139 LITRES OF FORMATION WATER, 0 LITRES OIL, 100% WATER, TAKE 1 BOTTLE OF 500CC WATER FLUID SAMPLE AS PER RDD. - TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 2.54 BBLS (WATER: 2.46 BBLS - OIL: 0.08 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 391 PSI (2B11).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 7045 | 6767 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2909 | 7045 | 6742 | LOG | E | 4305 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 6742' (STATION#3 PUMP OUT POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6767 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2910 | 7045 | 6742 | LOG | E | 4305 | WLT | STATION#3 (PUMP OUT/SAMPLE)@ 6742' (2B08), CYCLE#1 :- ACTIVATED XL PROBE & PUMP OUT STATION #3 @ 6742'.- PUMP OUT 95 LITRES OF FORMATION WATER, 0 LITERS OIL, 100% WATER, TAKE 1 BOTTLE OF 500CC WATER FLUID SAMPLE AS PER RDD. - TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 3.14 BBLS (WATER: 3.06 BBLS - OIL: 0.08 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 386 PSI (2B08).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 7045 | 6742 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2911 | 7045 | 6734 | LOG | E | 4305 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 6734' (STATION#4 PUMP OUT POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6742 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2912 | 7045 | 6734 | LOG | E | 4305 | WLT | STATION#4 (PUMP OUT) @ 6734' (AD2B), SCANNING AROUND THE STATION FOR GOOD MOBILITY AND SEAL WITH STANDARDS PROBE, NO MOBILITY. | 7045 | 6734 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2913 | 7045 | 6734 | LOG | E | 4305 | WLT | STATION#4 (PUMP OUT) @ 6734' (AD2B), CYCLE#1 : .. ONGOING @ RT.- ACTIVATED XL PROBE & PUMP OUT STATION #4 @ 6734'.- PUMP OUT .. ONGOING- 44 HRS SINCE LAST CIRCULATION @ LATCH DEPTH.- 64 HRS SINCE LAST CIRCULATION W/ REAMING BHA AT BTM. | 7045 | 6734 | BAW | 08/26/2022 | ADC-54L | LOG | HRDH-584
2914 | 65.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" PILOT HOLE LOGGING : RUN#1: MREX LOG ON TWO MODES: GAS MODE & LIGHT OIL MODE / RUN#2: PCL LOG RUN#2: RCX-IFX-GR (PRESSURE & SAMPLES). | 24 | 4305 | 23 Aug 0830 | 08/26/2022 | ADC-54L | Type | HRDH-584
2915
2916
2917 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | ADC-55L | Hrs | UTMN-3171
2918 | STBH | TK3 | 646 | 30 Jul 0830 - 0500 | 10968 | 900335 | PU STRING AFTER DROP PBL BALLS FOUND STRING STUCK. | STUK | BHA |  | 08/26/2022 | ADC-55L | 24 | UTMN-3171
2919 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | ADES-174 | Hrs | GHZL-72
2920 | SFHS | BFW | 111.75 | 22 Aug 0530 - 0500 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/26/2022 | ADES-174 | 24 | GHZL-72
2921 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | AOD-1 | Hrs | ZULF-694
2922 | DSFT | HCO | 32 | 25 Aug 1645 - 0145 | 5623 | 901313 | ATTEMPTED TO RETRIEVE RBP PER HLB PROCEDURE, UNABLE TO RETRIEVE RBP WITH RETRIEVAL TOOL BHA CONFIGURATION. | JF | RTTS |  | 08/26/2022 | AOD-1 | 19.75 | ZULF-694
2923 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | ARO-4001 | Hrs | MRJN-532
2924 | FOT | RIG | 8 | 25 Aug 2200 - 0830 | 8705 | 901321 | ATTEMPT TO PUMP DP SLUG, TDS IBOP NOT OPEN, TROUBLESHOOTING SAME, OBSERVED CRANK ARM ROLLERS ON BOTH SIDES OF ACTUATORS WERE BROKEN, NEED TO REPLACE SAME. | RR | TDS |  | 08/26/2022 | ARO-4001 | 3.5 | MRJN-532
2925 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | DPS-74 | Hrs | NJYN-33
2926 | FOT | RIG | 8 | 25 Aug 0030 - 0830 | 0 | 901320 | DRAW WORK ENCODER MOTOR-A FAILURE. | RR | DWKS |  | 08/26/2022 | DPS-74 | 3.5 | NJYN-33
2927 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | DQ-47 | Hrs | KHRS-280
2928 | FOT | BAW | 40.25 | 24 Aug 1615 - 0500 | 11860 | 901263 | NOT ACCEPTABLE LOG DATA QUALITY. | TF | WLT |  | 08/26/2022 | DQ-47 | 23 | KHRS-280
2929 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | ED-85A | Hrs | ZULF-2066
2930 | HERR | RIG | 14 | 26 Aug 1500 - 0500 | 0 | 901374 | AFTER PICKING UP STAND 4" DRILL PIPE FROM DERRICK DRILLER ENGAGED "DRILL MODE" ON THE TDS LINK TILT INSTEAD OF USING "FLOAT MODE". THE ELEVATOR WERE TOO CLOSE TO TOP OF MONKEY BOARD SO WHEN THE ELEVATORS/LINKS TRIED TO MOVE BACK TO WELL CENTER THEY PUSHED DOWN ON THE DIVING BOARD CAUSING IT TO BE BEND DOWN +/- 6". | JF | DRRK |  | 08/26/2022 | ED-85A | 14 | ZULF-2066
2931 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | ENS-108 | Hrs | ZULF-2015
2932 | GRF | RIG | 96 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/26/2022 | ENS-108 | 24 | ZULF-2015
2933 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | MP-1 | Hrs | MRJN-78
2934 | FOT | NRT | 605.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/26/2022 | MP-1 | 24 | MRJN-78
2935 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | MP-4 | Hrs | LWHH-20
2936 | FOT | ARM | 31 | 24 Aug 1930 - 0830 | 10598 | 901333 | OBSERVED PRESSURE DROP OF 700 PSI WHILE DRILLING 6-1/8" HOLE SECTION. | DSF | STRG |  | 08/26/2022 | MP-4 | 3.5 | LWHH-20
2937 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | NA-393S | Hrs | SDGM-1134
2938 | FOT | SDM | 10 | 26 Aug 1730 - 0500 | 12900 | 901338 | WHILE DRILLING AT 12,900' OBSRVD MWD TOOL FAILURE - ATTEMPTED FOR TROUBLESHOOTING - NO SUCCESS. > PERFORMED DOWNLINKING TWICE. > PERFORMED ANTI JAMMING TECHNIQUE AS PER SLB RECOMMENDED PROCEDURE. | BHA | MWD |  | 08/26/2022 | NA-393S | 10 | SDGM-1134
2939 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | NBR-263S | Hrs | QTIF-736
2940 | STBH | ARM | 332.5 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/26/2022 | NBR-263S | 24 | QTIF-736
2941 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | PA-785S | Hrs | QTIF-269
2942 | FOT | RIG | 2 | 26 Aug 2330 - 0130 | 0 | 901339 | HYDRAULIC LEAK ON TDS ACTUATOR VALVE. | RR | TDS |  | 08/26/2022 | PA-785S | 2 | QTIF-269
2943 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | PA-866S | Hrs | SHHB-2
2944 | FOT | BLH | 18.75 | 26 Aug 1015 - 0500 | 8500 | 901294 | NOT ABLE TO PRESSURE SET LINER HANGER AFTER DROPPING 1.5" BRASS BALL. BRASS BALL DID NOT SEAT. | TF | HGRL |  | 08/26/2022 | PA-866S | 18.75 | SHHB-2
2945 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SINO-1L | Hrs | ABJF-260
2946 | HMWT | ARM | 10.5 | 26 Aug 0800 - 1830 | 8623 | 901372 | - NO SUFFICIENT DRILLING WATER AT RIG SITE DUE TO ABJF-817 WATER WELL PUMP FAILURE. | WO | NA |  | 08/26/2022 | SINO-1L | 10.5 | ABJF-260
2947 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SINO-33L | Hrs | HRDH-1542
2948 | FOT | RIG | 107.5 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/26/2022 | SINO-33L | 24 | HRDH-1542
2949 | 4720 | 621 | TO | E | 4385 | STDP | HPJSM, POOH CONTROLLED SPEED W/ CORE ASSY #1 ON 5" DP STD'S TO TOP OF BHA.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4720 | 1500 | RIG | 08/26/2022 | SINO-46L | CORE | SHYB-270
2950 | 4720 |  | HT | E | 4385 | CORC | HPJSM, CONTD POOH 8-1/2" CORPRO CORING ASSY TO SURFACE CONTROLLED SPEED.** RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.** ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.** L/D INNER BARRELS, 60' RECOVERED (100 % RECOVERY) FROM CORE RUN #1** CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 4720 |  | CPR | 08/26/2022 | SINO-46L | CORE | SHYB-270
2951 | 4720 |  | HT | E | 4385 | CORC | HPJSM, P/U & M/U 8-1/2" CORPRO CORING ASSY RUN # 2. ** 8-1/2" CORE HEAD + 7-1/8" CORE OUTER BARRELS & 4-1/2" INNER BARRELS + FLOAT SUB W/ FLOAT VALVE+15 X 6-1/2" DC'S+ 6-1/2" DRILLING JAR+2 X 6 1/2" DC'S +XO+ PBL + DP'S. | 4720 |  | CPR | 08/26/2022 | SINO-46L | CORE | SHYB-270
2952 | 4720 | 4641 | TI | E | 4385 | STDP | RIH 8-1/2" CORPRO CORING ASSY CONTROLLED SPEED FROM 612' TO 9-5/8" CSG SHOE @ 4641'.** GENTLY PASSED SHOE TRACK.** FLOW CHECK WELL STATIC. | 4720 | 621 | RIG | 08/26/2022 | SINO-46L | CORE | SHYB-270
2953 | 4720 |  | CIRC | E | 4385 | MPMP | WASH DOWN FROM 4641' TO CORE POINT @ 4720', CIRCULATE BTMS UP. | 4720 |  | RIG | 08/26/2022 | SINO-46L | CORE | SHYB-270
2954 | 4720 |  | CIRC | E | 4385 | MPMP | ACTIVATED DIVERTING BALL, PUMP DOWN WITH 400 GPM & WAIT TILL DIVERT FLUID AWAY FROM THE INNER BARREL TO START CORING ACROSS SHYB FORMATION.-CONFIRM SPACE OUT FOR CUTTING THE CORE. -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS | 4720 |  | RIG | 08/26/2022 | SINO-46L | CORE | SHYB-270
2955 | 4780 |  | CORE | E | 4385 | CORC | CUT 8-1/2" X 4" CORE RUN #2 FROM 4720' TO 4780' W/77 PCF AOM & FULL 100% RETURNS.** CORING PARAMETERS: ** WOB: 5-10 KLBS. GPM: 175 - 185 , SPP: 280-320 PSI. RPM: 60-65, TRQ: 2-4 KLB | 4720 |  | CPR | 08/26/2022 | SINO-46L | CORE | SHYB-270
2956 | 4780 |  | CIRC | E | 4385 | MPMP | BREAK OFF CORE #2 AS PER CORE ENG WITH 5 KLB OVERPULL , PUMP OUT TO CORE POINT @ 4720 ', CHC.** FLOW CHECK WELL STATIC. | 4780 |  | RIG | 08/26/2022 | SINO-46L | CORE | SHYB-270
2957 | 4780 | 4641 | TO | E | 4385 | STDP | POOH CONTROLLED SPEED W/ CORE ASSY #2 ON 5" DP STD'S TO CSG SHOE.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4780 | 4720 | RIG | 08/26/2022 | SINO-46L | CORE | SHYB-270
2958 | 4780 | 621 | TO | E | 4385 | STDP | HPJSM, POOH CONTROLLED SPEED W/ CORE ASSY #1 ON 5" DP STD'S TO TOP OF BHA.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4780 | 4641 | RIG | 08/26/2022 | SINO-46L | CORE | SHYB-270
2959 | 43 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | 8-1/2" CORING OPERATION | 24 | 4385 | 25 Aug 0045 | 08/26/2022 | SINO-46L | Type | SHYB-270
2960
2961
2962 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SND-1501 | Hrs | HWYH-89
2963 | FOT | WWD | 48 | 25 Aug 0500 - 0500 | 0 | 901328 | FAILED 7" WFD HYD WHIPSTOCK | TF | WPSTK |  | 08/26/2022 | SND-1501 | 24 | HWYH-89
2964 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SND-2004 | Hrs | BRRI-1148
2965 | FOT | SWT | 216.25 | 16 Aug 0700 - 1030 | 6351 | 900934 | HELD UP INSIDE 7" LINER @ AT 6,351' WHILE RIH W/ SLB DST#2 STRING. ATTEMPT TO SET PKR & OPEN TFTV WITHOUT SUCCESS- TRIP OUT TO CHECK DST ASSY. | TF | DSTT |  | 08/26/2022 | SND-2004 | 5.5 | BRRI-1148
2966 | HERR | RIG | 1.5 | 25 Aug 0430 - 0600 | 5671 | 901331 | ROUSTABOUT CREW PUMPED OUT CELLAR TO SHAKER HEADER BOX CONTAMINATING ACTIVE MUD SYSTEM WITH WATER. | JF | CSYS |  | 08/26/2022 | SND-2005 | 1 | MHKK-2
2967 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SND-2005 | Hrs | MHKK-2
2968 | WTHR | ARM | 1.5 | 26 Aug 1815 - 2015 | 769 | 901297 | WINDS IN EXCESS OF 35-47 KM/HR MAKING TRIPPING OPERATION UNSAFE. | WON | NA |  | 08/26/2022 | SND-2005 | 1.5 | MHKK-2
2969 | HERR | RIG | 1.5 | 25 Aug 0430 - 0600 | 5671 | 901331 | ROUSTABOUT CREW PUMPED OUT CELLAR TO SHAKER HEADER BOX CONTAMINATING ACTIVE MUD SYSTEM WITH WATER. | JF | CSYS |  | 08/26/2022 | SND-2005 | 1 | MHKK-2
2970 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SP-154 | Hrs | SDGM-353
2971 | FOT | TOD | 75 | 23 Aug 0700 - 0330 | 7267 | 901232 | UNABLE TO CLOSE HYDRO SEAL DURING CEMENTING OFF BOTTOM LINER CAUSING FAILED PRESSURE TEST, | TF | DV |  | 08/26/2022 | SP-154 | 22.5 | SDGM-353
2972 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SP-165 | Hrs | FDHL-146
2973 | DFLI | EMC | 71.5 | 24 Aug 0500 - 0500 | 10585 | 901187 | MUD FOAMING ISSUE PRIOR LOGGING | MUD | NA |  | 08/26/2022 | SP-165 | 23.5 | FDHL-146
2974 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SP-167 | Hrs | HRDH-218
2975 | HERR | RIG | 2 | 26 Aug 0300 - 0500 | 170 | 901354 | WHILE P/U 2 JOINT HWDP FROM MOUSE HOLE THE TDS ACCIDENTLY SLACK DOWN CAUSE ONE JOINT BENT. | BHA | HWDP |  | 08/26/2022 | SP-167 | 2 | HRDH-218
2976 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SP-257 | Hrs | HZEM-162412
2977 | KSFM | ARM | 2 | 26 Aug 2000 - 2200 | 19145 | 901296 | STRING STUCK WHILE BACK REAMING PRIOR TO CONNECTION. | STUK | STRG |  | 08/26/2022 | SP-257 | 2 | HZEM-162412
2978 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SP-260 | Hrs | HMYM-531812
2979 | FOT | BHI | 51.25 | 24 Aug 1430 - 0445 | 15978 | 901253 | BAKER MWD FAILED. | TF | MS |  | 08/26/2022 | SP-260 | 23.75 | HMYM-531812
2980 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SP-261 | Hrs | MHWZ-903
2981 | HERR | ARM | 19.5 | 26 Aug 0930 - 0500 | 5724 | 901340 | LOST CONNECTIVITY TO IOC / WELLLINK DUE TO VSAT COMMUNICATIONS FAILURE. | JF | NA |  | 08/26/2022 | SP-261 | 19.5 | MHWZ-903
2982 | 6647 |  | HT | N | 4186 | BHA | CONTD RIH W/ 6-1/8" MTR/MWD/GR ASSY TO 540-6-1/2" PDC BIT (DD406X, S/NO: 7915105, JETS: 3 X 14) +MTR, 6 1/8" STRR, MWD/GR, FILTER SUB, 6 1/8" STRR, 12 X 4 3/4" DC, D/JAR, 2X 4 3/4" DC, X/O, DP .-CONNECT TO TOOLS AND PERFORM TOOLS VERIFICATION TEST.-MTR SPECIFICATION: 5 7/8"DURAMAX & 0.75 REV/GAL.-SENSORS OFFSET FROM BIT: GR: 51.92 FT & DIRECTIONAL: 55.59 FT.-PERFORMED SHALLOW TEST W/ 290 GPM, 1250 PSI.-MONITOR WELL THRU TRIP TANK, WELL STATIC. | 6647 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2983 | 6647 | 6200 | TI | N | 4186 | STDP | RIH W/ 6-1/8" MTR BHA F/540' TO 6,200' | 6647 | 540 | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2984 | 6647 | 6380 | LOG | N | 4186 | LWD | RE-LOG AS PER GOC FROM 6200' TO 6380' FT WITH 100 FPH. | 6647 | 6200 | BHI | 08/26/2022 | SP-53L | DRLG | HRDH-528
2985 | 6647 | 6647 | RW | N |  | BIT | CONTD RIH W/ 6-1/8" MTR BHA F/6380' TO 6647'-PRECAUITONARY REAM DOWN CORED INTERVAL TO BTM | 6647 | 6380 | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2986 | 6769 |  | D | N |  | TDS | MOTOR DRILLED 6-1/8" VERTICAL HOLE F / 6,647' TO TD@ 6769' WITH 70 PCF POLYMER MUD & 100 % RETURN.- WOB: 5-15 KLB, FR: 250-300 GPM, SPP: 2500 PSI, SURFACE RPM: 60-80 RPM, TRQ ON/OFF: 1 / 4 K.FT.LBF.- SWEEP HOLE W/ 15 BBLS HI-VIS PILL EVERY STD DRILLED.- BACK REAM & REAM DOWN EACH STD DRILLED.- SENSORS OFFSET FROM BIT: GR: 51.92 FT & DIRECTIONAL: 55.59 FT. | 6647 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2987 | 6769 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH 02X20 BBLS HI VIS PILL AND CIRCULATE HOLE CLEAN,100 % RETURN. | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2988 | 6769 |  | SDR1 | N |  | NA | FLOW CHECK - WELL STATIC | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2989 | 6769 | 6374 | TO | N |  | STDP | POOH W/ 6-1/8'' MTR BHA TO SHOE @ 6,375'.- HOLE IN GOOD CONDITION.- MONITOR WELL VIA TRIP TANK. | 6769 | 6769 | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2990 | 6769 |  | SDR1 | N |  | NA | FLOW CHECK @ 07" CSG SHOE - WELL STATIC | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2991 | 6769 | 6769 | TI | N |  | STDP | RIH W/ 6-1/8'' MTR BHA TO BTM @ 6,769'.- HOLE IN GOOD CONDITION. | 6769 | 6374 | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2992 | 6769 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH 20 BBLS HI VIS PILL AND CIRCULATE HOLE CLEAN,100 % RETURN.- SPOT 50 BBL LUBRICATED HVP ON BTM. | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2993 | 6769 |  | SDR1 | N |  | NA | FLOW CHECK - WELL STATIC | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2994 | 6769 | 6374 | TO | N |  | STDP | POOH W/ 6-1/8'' MTR BHA TO SHOE @ 6,375'.- HOLE IN GOOD CONDITION.- MONITOR WELL VIA TRIP TANK. | 6769 | 6769 | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2995 | 6769 |  | SDR1 | N |  | NA | FLOW CHECK @ 07" CSG SHOE - WELL STATIC | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2996 | 6769 | 5962 | TO | N |  | STDP | POOH W/ 6-1/8" MOTOR BHA F/ 6,375' TO TOP OF 4" DP @ 5,962'. | 6769 | 6374 | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2997 | 6769 |  | HT | N |  | PEL | CHANGE 5" HANDLING TOOLS TO 4". | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2998 | 6769 | 1597 | TO | N |  | STDP | CONTD POOH W/ 6-1/8'' MTR BHA FROM 7" CSG SHOE TO TOL @1597'.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET | 6769 | 5962 | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
2999 | 6769 |  | SDR1 | N |  | NA | FLOW CHECK @7" TOL WELL STATIC OK. | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
3000 | 6769 | 540 | TO | N |  | STDP | CONTD POOH W/ 6-1/8'' MTR BHA FROM 1597" TO TOP BHA .-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET | 6769 | 1597 | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
3001 | 6769 |  | SDR1 | N |  | NA | FLOW CHECK AT TOP BHA - WELL STATIC OK. | 6769 |  | RIG | 08/26/2022 | SP-53L | DRLG | HRDH-528
3002 | 6769 | 0 | HT | N |  | BHA | CONTD POOH W/ 6-1/8'' MTR BHA FROM 1597" TO TOP BHA - BIT DULL GRADING: 1-1-WT-A-I-X-NO-TD. | 6769 | 540 | BHI | 08/26/2022 | SP-53L | DRLG | HRDH-528
3003 | 6769 |  | PJSM | E |  | NA | HPJSM PRIOR TO RU WL LOGGING, DISCUSSED JSA & PROCEDURES, SAFETY ISSUES, KEEP GOOD COMMUNICATION BETWEEN DRILLER, WL ENGINEER AND WINCH MAN IN THE WL UNIT, HANDLING RADIO ACTIVE SOURCE PROCEDURES & TO AVOID LONG STATIONARY TIME IN OPEN HOLE. - R/U & FUNCTION TESTED MECHANICAL AND HYDRAULIC WL CABLE CUTTERS, OKMONITORING WELL THROUGH TRIP TANK, WELL STATIC. | 6769 |  | RIG | 08/26/2022 | SP-53L | LOG | HRDH-528
3004 | 6769 |  | OTH | E |  | NA | HPJSM. R/U W/L TOOLS...........ON GOINGP/U & M/U BHI W/L LOGGING TOOLS RUN #1 (GR-CN-ZDL-ADEX - WGI - HDIL - MLL & MREX). | 6769 |  | BAW | 08/26/2022 | SP-53L | LOG | HRDH-528
3005 | 219.25 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | ALL CORING OPERATION AND THE REAMING TRIP IS OOS. | 7 | 4186 | 13 Aug 0230 | 08/26/2022 | SP-53L | Type | HRDH-528
3006
3007
3008 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SP-58 | Hrs | HRDH-795
3009 | FOT | SCD | 7 | 26 Aug 0730 - 1430 | 12600 | 901336 | RIH W/GYRO TOOLS ON WIRELINE, LATCH ON GYRO TOOL. ATTEMPT TO COMMUNICATE WITH GYRO TOOL, HAD MISS COMMUNICATION. | TF | GYRO |  | 08/26/2022 | SP-58 | 7 | HRDH-795
3010 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SSA-5914 | Hrs | WDYH-80
3011 | FOT | BHI | 62.25 | 24 Aug 0845 - 0045 | 13337 | 901292 | LOST SIGNAL WITH BAKER RSS | BHA | RSS |  | 08/26/2022 | SSA-5914 | 19 | WDYH-80
3012 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SSA-5962 | Hrs | HRDH-2513
3013 | FOT | CRW | 22.75 | 25 Aug 0645 - 0915 | 11714 | 901314 | CORETRAX 9-5/8" LTTT PACKER FAILURE. | TF | SCRP |  | 08/26/2022 | SSA-5962 | 4.25 | HRDH-2513
3014 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/26/2022 | SSA-5972 | Hrs | SHDN-19
3015 | FOT | HWP | 69.5 | 23 Aug 1800 - 0230 | 14415 | 901168 | HALLIBURTON TPL LOGGING TOOL FAILURE. | TF | WLT |  | 08/26/2022 | SSA-5972 | 21.5 | SHDN-19
3016 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ADC-42L | Hrs | SDGM-1258
3017 | WC11 | TK3 | 45.75 | 26 Aug 0715 - 0500 | 15570 | 901342 | OBSERVED WELL FLOWING WHILE CONNECTION AT 14790 FT. | WCNT | NA |  | 08/27/2022 | ADC-42L | 24 | SDGM-1258
3018 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ADC-43L | Hrs | UTMN-3118
3019 | FRFM | TK3 | 320 | 11 Aug 2130 - 0330 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/27/2022 | ADC-43L | 22.5 | UTMN-3118
3020 | 6734 |  | BAW | LOG | 4305 | 7045 | STATION#4 (PUMP OUT/SAMPLE) @ 6734' (AD2B), CYCLE#1 :- ACTIVATED XL PROBE & PUMP OUT STATION #4 @ 6734'.- PUMP OUT 136 LITRES OF FORMATION WATER, 7 LITERS OIL, 95% WATER / 5% OIL, TAKE 1 BOTTLE OF 500CC FLUID SAMPLE AS PER RDD.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 4.03 BBLS (WATER: 3.91 BBLS - OIL: 0.12 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 387 PSI (AD2B).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6734 |  | 7045 | 08/27/2022 | ADC-54L | WLT | HRDH-584
3021 | 6721 |  | BAW | LOG | 4305 | 7045 | POOH W/ LOG TOOLS & POSITION STRING @ 6721' (STATION#5 PUMP OUT POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6734 |  | 7045 | 08/27/2022 | ADC-54L | WLT | HRDH-584
3022 | 6721 |  | BAW | LOG | 4305 | 7045 | STATION#5 (PUMP OUT/SAMPLE) @ 6721' (2A06), SCANNING AROUND THE STATION FOR GOOD MOBILITY AND SEAL WITH STANDARDS PROBE, LOW MOBILITY. | 6721 |  | 7045 | 08/27/2022 | ADC-54L | WLT | HRDH-584
3023 | 6721 |  | BAW | LOG | 4305 | 7045 | STATION#5 (PUMP OUT/SAMPLE) @ 6721' (2A06), CYCLE#1 :- ACTIVATED XL PROBE & PUMP OUT STATION #4 @ 6721'.- PUMP OUT 102 LITRES OF FORMATION WATER, 25 LITERS OIL, 80% WATER / 20% OIL, TAKE 1 BOTTLE OF 500CC FLUID SAMPLE AS PER RDD.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 4.83 BBLS (WATER: 4.55 BBLS - OIL: 0.28 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 388 PSI (2A06).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 51 HRS SINCE LAST CIRCULATION @ LATCH DEPTH.- 71 HRS SINCE LAST CIRCULATION W/ REAMING BHA AT BTM. | 6721 |  | 7045 | 08/27/2022 | ADC-54L | WLT | HRDH-584
3024 | 7020 |  | BAW | LOG | 4305 | 7045 | RIH WITH LOGGING TOOL STRING TO BOTTOM AT 7020'.- MONITOR WELL THRU TRIP TANK, STATIC. | 6721 |  | 7045 | 08/27/2022 | ADC-54L | WLT | HRDH-584
3025 |  |  | RIG | CIRC | 4305 | 7045 | CIRCULATE 160 BBL UNTIL GET FORMATION FLUID (WATER: 4.55 BBLS - OIL: 0.28 BBLS) INSIDE 9-5/8" CSG SHOE. |  |  | 7045 | 08/27/2022 | ADC-54L | MPMP | HRDH-584
3026 |  |  | RIG | WCNT | 4305 | 7045 | FLOW CHECK, WELL STATIC. |  |  | 7045 | 08/27/2022 | ADC-54L | NA | HRDH-584
3027 | 4200 |  | RIG | ST | 4305 | 7045 | POOH W/ BHI PCL LOGGING RUN#2: RCX-IFX-GR TO SES DEPTH @ 4200'. - WHILE PULLING OUT, WL PINCHED INTO GROOVE IN THE MONKEY BOARD WALK WAY, OUTER ARMOR SLIGHTLY DAMAGED, CHECKED & BAKER WL DECIDED TO CONT. POOH AND FIX CABLE AT CSG SHOE. | 7020 |  | 7045 | 08/27/2022 | ADC-54L | STDP | HRDH-584
3028 |  | 901377 | BAW | OTH | 4305 | 7045 | HPJSM, BAKER WIRELINE UNLATCHED & POOH W/ WIRELINE CONNECTOR HEAD TO SURFACE.- L/D SES & WIRELINE SHEAVES. |  | TF | 7045 | 08/27/2022 | ADC-54L | NA | HRDH-584
3029 |  |  | RIG | CIRC | 4305 | 7045 | CLOSED ANNULAR BOP & CIRCULATE THRU. CHOKE & MGS TO CONDITION MUD 1X CYCLE (INTERNAL+ANNULUS), +/-3.5 BPM, 150 PSI, MW IN/OUT=79 PCF (NORMAL MUD), OK. SICP & SIDPP = 0 PSI. - MONITOR WELL THROUGH CHOKE WELL STATIC.- MEANWHILE BAKER WL LOGGING WORK TO CUT 6,870 FT OF WL CABLE, REMOVED PINCHED PIECE AND RE-CONNECTED SAME WITH CONNECTOR HEAD AGAIN, OK. |  |  | 7045 | 08/27/2022 | ADC-54L | MPMP | HRDH-584
3030 |  |  | RIG | WCNT | 4305 | 7045 | EXTENDED FLOW CHECK FOR 0.5 HR - WELL STATIC, |  |  | 7045 | 08/27/2022 | ADC-54L | NA | HRDH-584
3031 |  | 901377 | BAW | OTH | 4305 | 7045 | HPJSM, RU BAKER WL SHEAVES AND SES, RIH WITH LATCH HEAD, CIRCULATE AND LATCHED DOWN HOLE TOOL. TEST COMMUNICATION - OK. MAKE PULL TEST ON SES CABLE CLAMP W/ 5000 LB LINE PULL - OK.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC |  | TF | 7045 | 08/27/2022 | ADC-54L | NA | HRDH-584
3032 | 5600 |  | BAW | LOG | 4305 | 7045 | RIH WL PCL RUN#2 LOGGING TOOLS (RCX-IFX-GR) ON 4" DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED 2 MIN/STD SLIPS TO SLIPS TO 5600' .. ONGOING @ RPT.- MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 4200 |  | 7045 | 08/27/2022 | ADC-54L | WLT | HRDH-584
3033 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ADC-54L | Hrs | HRDH-584
3034 | FOT | BAW | 4 | 27 Aug 2000 - 0300 | 6620 | 901377 | WHILE PULLING OUT PCL LOGGING TOOLS, WIRELINE PINCHED INTO GROOVE IN THE MONKEY BOARD WALK WAY, OUTER ARMOR SLIGHTLY DAMAGED. | TF | WLT |  | 08/27/2022 | ADC-54L | 4 | HRDH-584
3035 | 89.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" PILOT HOLE LOGGING : RUN#1: MREX LOG ON TWO MODES: GAS MODE & LIGHT OIL MODE / RUN#2: PCL LOG RUN#2: RCX-IFX-GR (PRESSURE & SAMPLES). | 24 | 4305 | 23 Aug 0830 | 08/27/2022 | ADC-54L | Type | HRDH-584
3036
3037
3038 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ADC-55L | Hrs | UTMN-3171
3039 | FOT | RIG | 99 | 23 Aug 0200 - 0500 | 10968 | 901375 | WHILE PT BOP OBSERVED LEAK BETWEEN DSA & LOWER DBL GATE | BOP | RAMS |  | 08/27/2022 | ADC-55L | 24 | UTMN-3171
3040 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ADC-58L | Hrs | ABHD-169
3041 | LHFL | RIG | .5 | 27 Aug 2300 - 2330 | 13523 | 901359 | OBSERVED ACCUMULATOR UNIT AIR PUMPS STARTED TO WORK AND ACCUMULATOR PRESSURE WAS DROPPING. | BOP | RWCS |  | 08/27/2022 | ADC-58L | .5 | ABHD-169
3042 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ADC-62L | Hrs | ANDR-589
3043 | UNKN | RIG | 3.5 | 27 Aug 0600 - 0930 | 5240 | 901379 | SUSPEND OPERATIONS DUE TO FIRE INCIDENT IN MINI-CAMP ADC ROOM. | HSEI | NA |  | 08/27/2022 | ADC-62L | 3.5 | ANDR-589
3044 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ADM-511 | Hrs | MRJN-799
3045 | FOT | RIG | 4 | 27 Aug 0100 - 0500 | 11310 | 901378 | STOP DRILLING, BHI HAD BAD DECODING SIGNAL DUE TO FAILURE PUMP# SEAT VALVE, | RR | MPMP |  | 08/27/2022 | ADM-511 | 4 | MRJN-799
3046 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ADM-655 | Hrs | SFNY-183
3047 | FOT | RIG | 27 | 26 Aug 0200 - 0500 | 0 | 901300 | ONE OF STBD LEG BRACES HAVE BEEN PARTED WHIE PRELOADING. | RR | PSYS |  | 08/27/2022 | ADM-655 | 24 | SFNY-183
3048 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ARO-3002 | Hrs | MRJN-813
3049 | WTHR | ARM | 20 | 22 Aug 0745 - 1630 | 8852 | 901136 | WIND SPEED TO LOW TO COMMENCE FLKOW BACK OPERATION. | WON | NA |  | 08/27/2022 | ARO-3002 | 3.75 | MRJN-813
3050 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ARO-4001 | Hrs | MRJN-532
3051 | FOT | HCM | 4.5 | 26 Aug 0345 - 0815 | 8705 | 901376 | WHILE BATCH MIXING CMT SLURRY ONE PUMP WENT DOWN, DUMP CMT IN BATCH MIXER AND TROUBLESHOOTING PUMP, FIX SAME. | TF | PUMP |  | 08/27/2022 | ARO-4001 | 3.25 | MRJN-532
3052 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | DQ-47 | Hrs | KHRS-280
3053 | FOT | BAW | 50.75 | 24 Aug 1615 - 1530 | 11860 | 901263 | NOT ACCEPTABLE LOG DATA QUALITY. | TF | WLT |  | 08/27/2022 | DQ-47 | 10.5 | KHRS-280
3054 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ED-85A | Hrs | ZULF-2066
3055 | OTH | RIG | 38 | 26 Aug 1500 - 0500 | 0 | 901374 | AFTER PICKING UP STAND 4" DRILL PIPE FROM DERRICK DRILLER ENGAGED "DRILL MODE" ON THE TDS LINK TILT INSTEAD OF USING "FLOAT MODE". THE ELEVATOR WERE TOO CLOSE TO TOP OF MONKEY BOARD SO WHEN THE ELEVATORS/LINKS TRIED TO MOVE BACK TO WELL CENTER THEY PUSHED DOWN ON THE DIVING BOARD CAUSING IT TO BE BEND DOWN +/- 6". | UPRA | NA |  | 08/27/2022 | ED-85A | 24 | ZULF-2066
3056 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | ENS-108 | Hrs | ZULF-2015
3057 | GRF | RIG | 120 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/27/2022 | ENS-108 | 24 | ZULF-2015
3058 | FOT | ARN | 5 | 27 Aug 0500 - 1000 | 6500 | 901373 | GOC INSTRUCTED TO STOP DRILLING DUE TO UNABLE TO RECIEVE DATA DUE TO INTERRUPTION OF VSAT. | TF | VSAT |  | 08/27/2022 | HI-5 | 5 | MHRH-57
3059 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | HI-5 | Hrs | MHRH-57
3060 | FOT | SDM | 19 | 27 Aug 1000 - 0500 | 6500 | 901299 | SCHLUMBERGER LWD OBSERVED THAT ECOSCOPE TOOL DOESN'T READ DENSITY IMAGING PROPERLY, DECIDED TO POH TO REPLACE TOOL. | BHA | LWD |  | 08/27/2022 | HI-5 | 19 | MHRH-57
3061 | FOT | ARN | 5 | 27 Aug 0500 - 1000 | 6500 | 901373 | GOC INSTRUCTED TO STOP DRILLING DUE TO UNABLE TO RECIEVE DATA DUE TO INTERRUPTION OF VSAT. | TF | VSAT |  | 08/27/2022 | HI-5 | 5 | MHRH-57
3062 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | JACK-202 | Hrs | THRY-829
3063 | FOT | RIG | 11 | 27 Aug 1800 - 0500 | 2984 | 901301 | DURING POOH WIPER TRIP W/17" BHA, FOUND 2 JT'S * 5" D/P WITH DAMAGED THREAD DUE TO WRONG M/U. | TF | SLIPS |  | 08/27/2022 | JACK-202 | 11 | THRY-829
3064 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | MP-1 | Hrs | MRJN-78
3065 | FOT | NRT | 629.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/27/2022 | MP-1 | 24 | MRJN-78
3066 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | NA-393S | Hrs | SDGM-1134
3067 | FOT | SDM | 25.5 | 26 Aug 1730 - 2100 | 12900 | 901338 | WHILE DRILLING AT 12,900' OBSRVD MWD TOOL FAILURE - ATTEMPTED FOR TROUBLESHOOTING - NO SUCCESS. > PERFORMED DOWNLINKING TWICE. > PERFORMED ANTI JAMMING TECHNIQUE AS PER SLB RECOMMENDED PROCEDURE. | BHA | MWD |  | 08/27/2022 | NA-393S | 15.5 | SDGM-1134
3068 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | NBR-263S | Hrs | QTIF-736
3069 | STBH | ARM | 356.5 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/27/2022 | NBR-263S | 24 | QTIF-736
3070 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | PA-622S | Hrs | UTMN-3600
3071 | FOT | HWP | 4 | 27 Aug 0100 - 0500 | 14208 | 901357 | AT CORE#16 DEPTH 14207.75' CORE HEAD STUCK INSIDE FORMATION, TRY TO RETRACT BIT BY APPLYING SLACK OFF 900 LB AND OVERPULL 500, 1200 LBS TENSION ON TOOLS WITHOUT SUCCESS. APPLY 2100 LB TO BREAK COREHEAD SHAFT (COREHEAD FREE) AND APPLY 3500 LBS TO GET TOOLS FREE. TRY TO CUT CORE AND CONFIRM THERE IS NO INDICATION OF BIT TOUCHING THE FORMATION. | TF | WLT |  | 08/27/2022 | PA-622S | 4 | UTMN-3600
3072 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | PA-866S | Hrs | SHHB-2
3073 | FOT | BLH | 42.75 | 26 Aug 1015 - 0500 | 8500 | 901294 | NOT ABLE TO PRESSURE SET LINER HANGER AFTER DROPPING 1.5" BRASS BALL. BRASS BALL DID NOT SEAT. | TF | HGRL |  | 08/27/2022 | PA-866S | 24 | SHHB-2
3074 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | RBP-50A | Hrs | HSBH-52
3075 | HERR | SCT | 9 | 27 Aug 0645 - 1545 | 12595 | 901341 | HUMAN ERROR OF SLB CT SUPERVISOR NOT PROPERLY KEEPING UP WITH NITROGEN ONBOARD AND RUNNING OUT OF NITROGEN DURING OPERATIONS. | JF | CTAC |  | 08/27/2022 | RBP-50A | 9 | HSBH-52
3076 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SINO-26 | Hrs | UTMN-1312
3077 | FOT | RIG | 2.5 | 27 Aug 2130 - 0000 | 5515 | 901358 | WFD LOST MWD SIGNAL DUE TO PUMP ISSUE. | RR | MPMP |  | 08/27/2022 | SINO-26 | 2.5 | UTMN-1312
3078 | 4780 |  | HT | E | 4385 | CORC | HPJSM, CONTD POOH WITH 8-1/2" CORPRO CORING ASSY #2 TO SURFACE CONTROLLED SPEED.** RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.** ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.** L/D INNER BARRELS, 60' RECOVERED (100 % RECOVERY) FROM CORE #2.** CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 4780 |  | CPR | 08/27/2022 | SINO-46L | CORE | SHYB-270
3079 | 4780 |  | HT | E | 4385 | CORC | HPJSM, P/U & M/U 8-1/2" CORPRO CORING ASSY RUN # 3. ** 8-1/2" CORE HEAD + 7-1/8" CORE OUTER BARRELS & 4-1/2" INNER BARRELS + FLOAT SUB W/ FLOAT VALVE+15 X 6-1/2" DC'S+ 6-1/2" DRILLING JAR+2 X 6 1/2" DC'S +XO+ PBL + DP'S. | 4780 |  | CPR | 08/27/2022 | SINO-46L | CORE | SHYB-270
3080 | 4780 | 4780 | TI | E | 4385 | STDP | RIH WITH 8-1/2" CORPRO CORING ASSY #3 CONTROLLED SPEED FROM 612' TO 4780'.** PASSED 9-5/8" DV FREELY.** GENTLY PASSED SHOE TRACK.** WASH DOWN LAST STAND TILL TAGGED BTM GENTLY. | 4780 | 621 | RIG | 08/27/2022 | SINO-46L | CORE | SHYB-270
3081 | 4780 |  | CIRC | E | 4385 | MPMP | CIRCULATE BTMS UP, ACTIVATED DIVERTING BALL, PUMP DOWN WITH 400 GPM & WAIT TILL DIVERT FLUID AWAY FROM THE INNER BARREL TO START CORING ACROSS SHYB FORMATION.-CONFIRM SPACE OUT FOR CUTTING THE CORE. -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS | 4780 |  | RIG | 08/27/2022 | SINO-46L | CORE | SHYB-270
3082 | 4840 |  | CORE | E | 4385 | CORC | CUT 8-1/2" X 4" CORE #3 FROM 4780' TO 4840' W/77 PCF AOM & FULL 100% RETURNS.** CORING PARAMETERS: ** WOB: 5-10 KLBS. GPM: 175 - 185 , SPP: 280-320 PSI. RPM: 60-65, TRQ: 2-4 KLB | 4780 |  | CPR | 08/27/2022 | SINO-46L | CORE | SHYB-270
3083 | 4840 |  | CIRC | E | 4385 | MPMP | BREAK OFF CORE #3 AS PER CORE ENG WITH 5 KLB OVERPULL , PUMP OUT TO CORE POINT @ 4780 ', CHC.** FLOW CHECK WELL STATIC. | 4840 |  | RIG | 08/27/2022 | SINO-46L | CORE | SHYB-270
3084 | 4840 | 4641 | TO | E | 4385 | STDP | POOH CONTROLLED SPEED WITH CORE ASSY #3 ON 5" DP STD'S TO CSG SHOE.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4840 | 4780 | RIG | 08/27/2022 | SINO-46L | CORE | SHYB-270
3085 | 4840 | 621 | TO | E | 4385 | STDP | HPJSM, POOH CONTROLLED SPEED WITH CORE ASSY #3 ON 5" DP STD'S TO TOP OF BHA.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4840 | 4641 | RIG | 08/27/2022 | SINO-46L | CORE | SHYB-270
3086 | 4840 |  | HT | E | 4385 | CORC | HPJSM, CONTD POOH WITH 8-1/2" CORPRO CORING ASSY # 3 TO SURFACE CONTROLLED SPEED.** RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.** ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.** L/D INNER BARRELS, 60' RECOVERED (100 % RECOVERY) FROM CORE #3** CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 4840 |  | CPR | 08/27/2022 | SINO-46L | CORE | SHYB-270
3087 | 4840 |  | HT | E | 4385 | CORC | HPJSM, P/U & M/U 8-1/2" CORPRO CORING ASSY RUN #4. ** 8-1/2" CORE HEAD + 7-1/8" CORE OUTER BARRELS & 4-1/2" INNER BARRELS + FLOAT SUB W/ FLOAT VALVE+15 X 6-1/2" DC'S+ 6-1/2" DRILLING JAR+2 X 6 1/2" DC'S +XO+ PBL + DP'S. | 4840 |  | CPR | 08/27/2022 | SINO-46L | CORE | SHYB-270
3088 | 4840 | 1000 | TI | E | 4385 | STDP | RIH WITH 8-1/2" CORPRO CORING ASSY # 4 CONTROLLED SPEED FROM 612' TO 1000'. | 4840 | 621 | RIG | 08/27/2022 | SINO-46L | CORE | SHYB-270
3089 | 67 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | 8-1/2" CORING OPERATION | 24 | 4385 | 25 Aug 0045 | 08/27/2022 | SINO-46L | Type | SHYB-270
3090
3091
3092 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SND-1501 | Hrs | HWYH-89
3093 | FOT | WWD | 68.5 | 25 Aug 0500 - 0130 | 0 | 901328 | FAILED 7" WFD HYD WHIPSTOCK | TF | WPSTK |  | 08/27/2022 | SND-1501 | 20.5 | HWYH-89
3094 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SND-2003 | Hrs | GZLN-1
3095 | FOT | RIG | 8 | 26 Aug 0300 - 1100 | 5913 | 901302 | SCR ROOM AC MALFUNCTION | RR | DWKS |  | 08/27/2022 | SND-2003 | 6 | GZLN-1
3096 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SP-154 | Hrs | SDGM-353
3097 | FOT | TOD | 100.5 | 23 Aug 0700 - 0500 | 7267 | 901232 | UNABLE TO CLOSE HYDRO SEAL DURING CEMENTING OFF BOTTOM LINER CAUSING FAILED PRESSURE TEST, | TF | DV |  | 08/27/2022 | SP-154 | 24 | SDGM-353
3098 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SP-257 | Hrs | HZEM-162412
3099 | KSFM | ARM | 1 | 27 Aug 1145 - 1245 | 19807 | 901355 | STRING STUCK WHILE BACK REAMING PRIOR TO CONNECTION. | STUK | STRG |  | 08/27/2022 | SP-257 | 1 | HZEM-162412
3100 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SP-261 | Hrs | MHWZ-903
3101 | HERR | ARM | 34.75 | 26 Aug 0930 - 2015 | 5724 | 901340 | LOST CONNECTIVITY TO IOC / WELLLINK DUE TO VSAT COMMUNICATIONS FAILURE. | JF | NA |  | 08/27/2022 | SP-261 | 15.25 | MHWZ-903
3102 | 6769 |  | OTH | E |  | NA | P/U & M/U BAKER COMBINED RUN TRIPLE COMBO OH WL LOGGING TOOLS (1ST RUN:GR-CN-ZDL-ADEX-MREX-WGI-HDIL-MLL).- TOOL LENGTH: 167.97', MAX. OD:5", WT: 3,869 LBS.- FUNCTION TEST LOGGING TOOLS AT SURFACE, TOOLS VERIFICATION & CALIBRATION, OK.- HPJSM AND LOADED RADIO ACTIVE SOURCE.- MONITORING WELL ON TRIP TANK - WELL STATIC. | 6769 |  | BAW | 08/27/2022 | SP-53L | LOG | HRDH-528
3103 | 6769 | 6769 | LOG | E |  | CORRL | RIH W/ BAKER WL COMBINED LOGGING TOOLS (1ST RUN:GR-CN-ZDL-ADEX-MREX-WGI-HDIL-MLL)TO TD@ 6769'( 6778' WL DEPTH)- MONITOR WELL ON TRIP TANK, WELL STATIC. | 6769 | 0 | BAW | 08/27/2022 | SP-53L | LOG | HRDH-528
3104 | 6769 | 6150 | LOG | E |  | WLT | LOGGING UP MAIN PASS (MLL/HDIL/ZDL/CN/GR) F/ 6150' T/ 6750' (SPEED: 25-30 FT/MIN).- GOING DOWN WITH LOG & PERFORM REPEAT PASS (MLL/HDIL/ZDL/CN/GR) F/ 6150' T/ 6350' - MONITOR WELL ON TRIP TANK, WELL STATIC. | 6769 | 6769 | BAW | 08/27/2022 | SP-53L | LOG | HRDH-528
3105 | 6769 | 6769 | LOG | E | 4405 | WLT | RIH W/ WL LOGGING TOOLS FOR (ADEX-MREX-MLL) LOG TO TD@6769' .- MONITOR WELL ON TRIP TANK, WELL STATIC. | 6769 | 6150 | BAW | 08/27/2022 | SP-53L | LOG | HRDH-528
3106 | 6769 | 6150 | LOG | E | 4405 | WLT | LOGGING UP (ADEX-MREX-MLL) LOG AS PER PLAN FROM 6778' TO 6374' LOGGING SPEED 2 FPM- PERFORM REPEATED PASS FROM 6778' TO 6374'- MONITOR WELL ON TRIP TANK, WELL STATIC. | 6769 | 6769 | BAW | 08/27/2022 | SP-53L | LOG | HRDH-528
3107 | 6769 |  | OTH | E |  | NA | POOH WL LOGGING TOOL FROM 6374' TO 173',- MONITOR WELL ON TRIP TANK, WELL STATIC. | 6769 |  | BAW | 08/27/2022 | SP-53L | LOG | HRDH-528
3108 | 6769 |  | OTH | E |  | NA | HPJSM & RETRIEVED RADIO ACTIVE SOURCE AND L/D COMBINED TRIPLE COMBO LOGGING TOOLS .- MONITOR WELL ON TRIP TANK, WELL STATIC. | 6769 |  | BAW | 08/27/2022 | SP-53L | LOG | HRDH-528
3109 | 6769 |  | RR | E |  | TDS | HPJSM, TDS SERVICE. | 6769 |  | RIG | 08/27/2022 | SP-53L | LOG | HRDH-528
3110 | 6769 |  | HT | N | 4425 | BHA | HPJSM, P/U & M/U 6-1/8" ROTARY BHA T/ 437' .- BHA: 6 1/8" RB RC217 BIT, NBRR (FV), 1X 4 3/4" DC, 6 1/8" STRR, 1X4 3/4" DC, 6 1/8" STRR, 10 X 4 3/4" DC, D/JAR, 2X 4 3/4" DC, X/O, DP T/SURFACE.- MONITOR WELL ON TRIP TANK, WELL STATIC. | 6769 |  | RIG | 08/27/2022 | SP-53L | CT | HRDH-528
3111 | 6769 | 5500 | TI | N | 4425 | STDP | RIH 6-1/8" ROTARY BHA F/437' TO 5500',- FILL STRING EVERY 20 STDS.- PASS SMOOTHLY THROUGH 7'' TOL @ 1,597' | 6769 | 437 | RIG | 08/27/2022 | SP-53L | CT | HRDH-528
3112 | 10.5 | OOS | OTHR | 4425 | LOG | CONDITION TRIP PRIOR TO RUN PCL (GR-RCX-WGI) LOG | RECORDING (ADEX-MREX-MLL) LOG AS PER PLAN | 10.5 | 4405 | 27 Aug 1015 | 08/27/2022 | SP-53L | OOS | HRDH-528
3113
3114
3115
3116 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SSA-29 | Hrs | QTIF-423
3117 | FOT | HWP | 7 | 27 Aug 1730 - 0030 | 12740 | 901303 | UNABLE TO SWITCH FROM TRACTOR MODE TO LOGGING MODE. | TF | WLT |  | 08/27/2022 | SSA-29 | 7 | QTIF-423
3118 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SSA-5859 | Hrs | HWYH-1217
3119 | FOT | RIG | 4.5 | 27 Aug 0030 - 0500 | 302 | 901360 | LOST COMMUNICATION BETWEEN TDS & VFD. | RR | TDS |  | 08/27/2022 | SSA-5859 | 4.5 | HWYH-1217
3120 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SSA-5892 | Hrs | AWTD-141400
3121 | STBH | ARM | 63.5 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | STUK | BHA |  | 08/27/2022 | SSA-5892 | 24 | AWTD-141400
3122 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | SSA-5962 | Hrs | HRDH-2513
3123 | FOT | BHI | 1.75 | 27 Aug 0230 - 0415 | 11948 | 901343 | BAKER LOST MWD SIGNAL, TROUBLESHOOTING TO RECOVER MWD SIGNAL WITH DIFFERENT OPTIONS W/O SUCCESS. | TF | MS |  | 08/27/2022 | SSA-5962 | 1.75 | HRDH-2513
3124 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | T902 | Hrs | MHWZ-906
3125 | SRVC | NFT | 9.5 | 27 Aug 1030 - 2000 | 12835 | 901344 | NPS CAN'T GET FILTERED BRINE READINGS WITHIN ARAMCO REQUIREMENT. NO SPARE FILTERS ON LOCATION. | WO | NA |  | 08/27/2022 | T902 | 9.5 | MHWZ-906
3126 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/27/2022 | WCL-83 | Hrs | MRJN-835
3127 | WTHR | ARM | 4 | 27 Aug 1300 - 1700 | 0 | 901356 | STOPPED FLARING DUE TO LOW WIND SPEED AT 1 KNT. | WON | NA |  | 08/27/2022 | WCL-83 | 4 | MRJN-835
3128 | FRFM | ARM | 18 | 28 Aug 1030 - 0500 | 6100 | 901348 | CURE LOSSES AT SFNY FORMATION WITH LCM PILL AND CMT PLUG. | LCIR | NA |  | 08/28/2022 | 095TE | 18 | MNIF-126
3129 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | 095TE | Hrs | MNIF-126
3130 | FRFM | ARM | 8.75 | 27 Aug 2145 - 0630 | 5971 | 901346 | CURE LOSSES AT WARA FORMATION WITH LCM PILL. | LCIR | NA |  | 08/28/2022 | 095TE | 1.5 | MNIF-126
3131 | FRFM | ARM | 18 | 28 Aug 1030 - 0500 | 6100 | 901348 | CURE LOSSES AT SFNY FORMATION WITH LCM PILL AND CMT PLUG. | LCIR | NA |  | 08/28/2022 | 095TE | 18 | MNIF-126
3132 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ADC-17 | Hrs | ZULF-1385
3133 | FOT | RIG | 3.5 | 28 Aug 0130 - 0500 | 0 | 901365 | LEAK WHILE PRESSURE TEST DIVERTER. | BOP | DVRT |  | 08/28/2022 | ADC-17 | 3.5 | ZULF-1385
3134 | 7045 | 6716 | LOG | E | 4305 | WLT | CONT'D RIH PCL RUN#2 LOGGING TOOLS (RCX-IFX-GR) ON 4" DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED 2 MIN/STD SLIPS TO SLIPS TO 6716'.- MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7045 | 5600 | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3135 | 7045 | 6716 | LOG | E | 4305 | WLT | POSITION STRING @ 6TH SAMPLING POINT @ 6716',(STATION#6 SAMPLING POINT), PERFORM STICKY TENDENCY TEST FOR 15 MIN, 30 MIN & 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6716 | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3136 | 7045 | 6716 | LOG | E | 4305 | WLT | SCANNING AROUND THE STATION#6 (SAMPLE) @ 6716' (2A06) FOR GOOD MOBILITY: - CHECK MOBILITY WITH STANDARD PROBE AT 6716', 6715.5', AND 6716.5'- ATTEMPT PUMP OUT WITH XL PROBE AT 6716' AND 6715.5', ABORTED DUE TO LOW FLOW RATE.- RDD INSTRUCTED TO PUMP OUT AT 6715'. | 7045 | 6716 | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3137 | 7045 | 6715 | LOG | E | 4305 | WLT | STATION#6 (SAMPLE) @ 6715' (2A06), CYCLE#1 :- POSITION STRING @ 6715', ACTIVATED XL PROBE & PUMP OUT/SAMPLE STATION #6.- PUMP OUT 123 LITERS: 80 LITRES OF FORMATION WATER, 43 LITERS OIL (65% WATER / 35% OIL), TAKE 1 BOTTLE OF 500CC FLUID SAMPLE AS PER RDD.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 0.77 BBLS (WATER: 0.5 BBLS - OIL: 0.27 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 385 PSI (2A06).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 24.25 HRS SINCE LAST CIRCULATION AT BTM. | 7045 | 6715 | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3138 | 7045 | 6698 | LOG | E | 4305 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 6698' (STATION#7: PUMPING OUT POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6715 | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3139 | 7045 | 6698 | LOG | E | 4305 | WLT | STATION#7 (PUMPING OUT) @ 6698.5' (2A05), CYCLE#1 :- ACTIVATED STANDARD PROBE @ 6698.5' & PUMP OUT STATION #7.- PUMP OUT 153 LITERS: 145 LITRES OF FORMATION WATER, 8 LITERS OIL (95% WATER / 5% OIL), TAKE 1 BOTTLE OF 500CC FLUID SAMPLE AS PER RDD.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 1.73 BBLS (WATER: 1.4 BBLS - OIL: 0.33 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 385 PSI (2A05).- DEACTIVATE STANDARD PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 28.5 HRS SINCE LAST CIRCULATION AT BTM. | 7045 | 6698 | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3140 | 7045 |  | OTH | E | 4305 | NA | POSITION STRING @ 8TH SAMPLE POINT @ 6680',(STATION#8 SAMPLING POINT), PERFORM STICKY TENDENCY TEST FOR 15 MIN, 30 MIN & 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 |  | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3141 | 7045 | 6680 | LOG | E | 4305 | WLT | STATION#8 (SAMPLING POINT) @ 6680' (ABD1), CYCLE#1 :- POSITION STRING @ 6679.5', ACTIVATED STANDARD PROBE & SAMPLING STATION#8.- PUMP OUT 152 LITERS: 152 LITRES OF FORMATION WATER, 0 LITERS OIL (100% WATER / 0% OIL), TAKE 1 BOTTLE OF 500CC FLUID SAMPLE AS PER RDD.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 2.68 BBLS (WATER: 2.35 BBLS - OIL: 0.33 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 379 PSI (ABD1).- DEACTIVATE STANDARD PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 34.25 HRS SINCE LAST CIRCULATION AT BTM. | 7045 | 6680 | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3142 | 7045 |  | OTH | E | 4305 | NA | POSITION STRING @ 9TH POINT @ 6675',(STATION#9 PUMPING OUT POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 |  | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3143 | 7045 |  | OTH | E | 4305 | NA | SCANNING AROUND THE STATION#9 (PUMPING POINT) @ 6675' (ABD1) WITH STANDARD & XL PROBES FOR GOOD SEAL & MOBILITY. | 7045 |  | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3144 | 7045 | 6674 | LOG | E | 4305 | WLT | STATION#9 (PUMPING) @ 6674' (ABD1), CYCLE#1: .. ONGOING @ RPT.- POSITION STRING @ 6674', ACTIVATED XL PROBE & PUMPING OUT STATION #9 - 39 HRS SINCE LAST CIRCULATION AT BTM. | 7045 | 6674 | BAW | 08/28/2022 | ADC-54L | LOG | HRDH-584
3145 | 113.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" PILOT HOLE LOGGING : RUN#1: MREX LOG ON TWO MODES: GAS MODE & LIGHT OIL MODE / RUN#2: PCL LOG RUN#2: RCX-IFX-GR (PRESSURE & SAMPLES). | 24 | 4305 | 23 Aug 0830 | 08/28/2022 | ADC-54L | Type | HRDH-584
3146
3147
3148 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ADC-55L | Hrs | UTMN-3171
3149 | FOT | RIG | 123 | 23 Aug 0200 - 0500 | 10968 | 901375 | WHILE PT BOP OBSERVED LEAK BETWEEN DSA & LOWER DBL GATE | BOP | RAMS |  | 08/28/2022 | ADC-55L | 24 | UTMN-3171
3150 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ADC-62L | Hrs | ANDR-589
3151 | FPMP | RIG | 3 | 28 Aug 1800 - 2200 | 6197 | 901308 | REPAIR MUD PUMPS : CHANGED OUT MP# 1 & 2 WEAR PLATE | RR | MPMP |  | 08/28/2022 | ADC-62L | 3 | ANDR-589
3152 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ADC-68L | Hrs | FDHL-174
3153 | WTHR | TK3 | 1 | 28 Aug 1500 - 1600 | 6362 | 901349 | STRONG WINDSTORM, WIND SPEED 68 KM/HR WITH LOW VISIBILITY. | WON | NA |  | 08/28/2022 | ADC-68L | 1 | FDHL-174
3154 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ADES-174 | Hrs | GHZL-72
3155 | SFHS | BFW | 159.75 | 22 Aug 0530 - 0500 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/28/2022 | ADES-174 | 24 | GHZL-72
3156 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ADES-889 | Hrs | HRDH-2122
3157 | FOT | BHI | 2.25 | 28 Aug 0245 - 0500 | 11160 | 901383 | HAD NO COMMUNICATION WITH BAKER RSS TOOL | BHA | RSS |  | 08/28/2022 | ADES-889 | 2.25 | HRDH-2122
3158 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ADM-511 | Hrs | MRJN-799
3159 | FOT | RIG | 4.5 | 27 Aug 0100 - 0530 | 11310 | 901378 | STOP DRILLING, BHI HAD BAD DECODING SIGNAL DUE TO FAILURE PUMP#1 SEAT VALVE, | RR | MPMP |  | 08/28/2022 | ADM-511 | .5 | MRJN-799
3160 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ADM-655 | Hrs | SFNY-183
3161 | FOT | RIG | 51 | 26 Aug 0200 - 0500 | 0 | 901300 | ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | RR | PSYS |  | 08/28/2022 | ADM-655 | 24 | SFNY-183
3162 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ARO-3002 | Hrs | MRJN-813
3163 | WTHR | ARM | 25.25 | 22 Aug 0745 - 1200 | 8852 | 901136 | WIND SPEED TO LOW TO COMMENCE FLKOW BACK OPERATION. | WON | NA |  | 08/28/2022 | ARO-3002 | 5.25 | MRJN-813
3164 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ED-85A | Hrs | ZULF-2066
3165 | OTH | RIG | 54 | 26 Aug 1500 - 2100 | 0 | 901374 | AFTER PICKING UP STAND 4" DRILL PIPE FROM DERRICK DRILLER ENGAGED "DRILL MODE" ON THE TDS LINK TILT INSTEAD OF USING "FLOAT MODE". THE ELEVATOR WERE TOO CLOSE TO TOP OF MONKEY BOARD SO WHEN THE ELEVATORS/LINKS TRIED TO MOVE BACK TO WELL CENTER THEY PUSHED DOWN ON THE DIVING BOARD CAUSING IT TO BE BEND DOWN +/- 6". | UPRA | NA |  | 08/28/2022 | ED-85A | 16 | ZULF-2066
3166 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | ENS-108 | Hrs | ZULF-2015
3167 | GRF | RIG | 144 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/28/2022 | ENS-108 | 24 | ZULF-2015
3168 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | HI-2 | Hrs | BRRI-434
3169 | PCPF | ARM | 4.5 | 28 Aug 1315 - 1745 | 5350 | 901384 | UNABLE TO TOH FREELY DUE TO EXCESSIVE OVERPULL. | TH | NA |  | 08/28/2022 | HI-2 | 4.5 | BRRI-434
3170 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | HI-5 | Hrs | MHRH-57
3171 | FOT | SDM | 20 | 27 Aug 1000 - 0600 | 6500 | 901299 | SCHLUMBERGER LWD OBSERVED THAT ECOSCOPE TOOL DOESN'T READ DENSITY IMAGING PROPERLY, DECIDED TO POH TO REPLACE TOOL. | BHA | LWD |  | 08/28/2022 | HI-5 | 1 | MHRH-57
3172 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | JACK-202 | Hrs | THRY-829
3173 | FOT | RIG | 14.5 | 27 Aug 1800 - 0830 | 2984 | 901301 | DURING POOH WIPER TRIP W/17" BHA, FOUND 2 JT'S * 5" D/P WITH DAMAGED THREAD DUE TO WRONG M/U. | TF | SLIPS |  | 08/28/2022 | JACK-202 | 3.5 | THRY-829
3174 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | MP-1 | Hrs | MRJN-78
3175 | FOT | NRT | 653.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/28/2022 | MP-1 | 24 | MRJN-78
3176 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | NA-18S | Hrs | SDGM-444
3177 | FOT | WI3 | 12 | 28 Aug 1430 - 0300 | 11135 | 901381 | PASSED TOW AT 11,122FT BUT HAD TAG AT 11.135FT - ONE FT ABOVE BOW. HAD MANY TRIALS - NO SUCCESS | TF | WPSTK |  | 08/28/2022 | NA-18S | 12 | SDGM-444
3178 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | NBR-263S | Hrs | QTIF-736
3179 | STBH | ARM | 380.5 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/28/2022 | NBR-263S | 24 | QTIF-736
3180 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | NBR-783S | Hrs | NJYN-93
3181 | FOT | RIG | 1.5 | 28 Aug 2300 - 0030 | 16099 | 901350 | EXCESS TIME TO TEST SURFACE LINE DUE TO LEAKING ON LINES. | TF | SFLN |  | 08/28/2022 | NBR-783S | 1.5 | NJYN-93
3182 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | PA-622S | Hrs | UTMN-3600
3183 | FOT | HWP | 6 | 27 Aug 0100 - 0700 | 14208 | 901357 | AT CORE#16 DEPTH 14207.75' CORE HEAD STUCK INSIDE FORMATION, TRY TO RETRACT BIT BY APPLYING SLACK OFF 900 LB AND OVERPULL 500, 1200 LBS TENSION ON TOOLS WITHOUT SUCCESS. APPLY 2100 LB TO BREAK COREHEAD SHAFT (COREHEAD FREE) AND APPLY 3500 LBS TO GET TOOLS FREE. TRY TO CUT CORE AND CONFIRM THERE IS NO INDICATION OF BIT TOUCHING THE FORMATION. | TF | WLT |  | 08/28/2022 | PA-622S | 2 | UTMN-3600
3184 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | PA-866S | Hrs | SHHB-2
3185 | FOT | BLH | 50 | 26 Aug 1015 - 1215 | 8500 | 901294 | NOT ABLE TO PRESSURE SET LINER HANGER AFTER DROPPING 1.5" BRASS BALL. BRASS BALL DID NOT SEAT. | TF | HGRL |  | 08/28/2022 | PA-866S | 7.25 | SHHB-2
3186 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | SA5898 | Hrs | MDRK-66
3187 | FOT | RIG | 2.5 | 28 Aug 2300 - 0130 | 11300 | 901307 | HAD PROBLEM WITH TDS SAVER SUB, CHANGE SAME,OK | RR | TDS |  | 08/28/2022 | SA5898 | 2.5 | MDRK-66
3188 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | SINO-33L | Hrs | HRDH-1542
3189 | FOT | RIG | 155.5 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/28/2022 | SINO-33L | 24 | HRDH-1542
3190 | 0 |  | RTRV | N | 4406 | PLUGT | CONTINUE S/L AS FOLLOW:> RIH 7 RUNS (TOTAL 40 RUNS) WITH 3.5" OPEN FLAT SAND BAILER.> TAG DEPTH 2047'-2048'.> ARAMCO FIELD SERVICE ARRIVED LOCATION TO MAINTENANCE X. MASS TREE VALVES.** TOTAL SAND/SCALE RECOVERED: +/- 75 KG. | 0 |  | HSL | 08/28/2022 | SINO-37L | DCOM | HWYH-114
3191 | 0 |  | CIRC | N | 4406 | MPMP | PERFORMED INJECTIVITY TEST: PUMPED 05 STK (0.4 BBL) PRESSURE INCREASED TO 1550 PSI, CONTINUE PUMPING BY HESITATION FOR 30 MIN TOTAL PUMPED 12 STK (1 BBL) FOR 500 PSI PRESSURE 1 LIMIT. STOP PUMP, PRESSURE DECREASE TO 1200 PSI IN 20 MIN'S.> NO INJECTIVITY, PUMPING 2 BBLS/HRS. | 0 |  | RIG | 08/28/2022 | SINO-37L | DCOM | HWYH-114
3192 | 0 |  | CIRC | N | 4406 | MPMP | CONTINUE S/L AS FOLLOW:> RIH 6 RUNS (TOTAL 46 RUNS) WITH 3.5" OPEN FLAT SAND BAILER.> TAG DEPTH TAGGED SHALLOWER AFTER BULLHEADING 2042'.** TOTAL SAND/SCALE RECOVERED: +/- 80 KG. | 0 |  | RIG | 08/28/2022 | SINO-37L | DCOM | HWYH-114
3193 | 0 |  | OTH | N | 4406 | NA | R/U GDMC CT & RAWABI SURFACE FLOW EQUIPMENT. | 0 |  | GDM | 08/28/2022 | SINO-37L | DCOM | HWYH-114
3194 | 66 | OOS | Category | DOOS ID | DCOM | Out of Scope Summary | RETREIVE PX PLUG STACK IN X-NIPPLE, INSTALLED BY PRODUCTION TO SECURE THE WELL DURING CELLAR INSTALATION. | 24 | 4406 | 26 Aug 1100 | 08/28/2022 | SINO-37L | Type | HWYH-114
3195
3196
3197 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | SINO-42L | Hrs | HWYH-480
3198 | XTTE | HSL | 5 | 28 Aug 1200 - 1700 | 6331 | 901382 | HSL UNABLE TO SET "PXN" PLUG . | JF | SLICK |  | 08/28/2022 | SINO-42L | 5 | HWYH-480
3199 | 4840 | 4840 | TI | E | 4385 | STDP | RIH 8-1/2" CORPRO CORING ASSY #4 CONTROLLED SPEED FROM 1000' TO 4840'.** PASS 9-5/8" DV FREELY.** GENTLY PASSED SHOE TRACK.** FLOW CHECK WELL STATIC.** WASH DOWN LAST STAND TILL TAGGED BTM GENTLY. | 4840 | 1000 | RIG | 08/28/2022 | SINO-46L | CORE | SHYB-270
3200 | 4840 |  | CIRC | E | 4385 | MPMP | CIRCULATE BTMS UP, ACTIVATED DIVERTING BALL, PUMP DOWN WITH 400 GPM & WAIT TILL DIVERT FLUID AWAY FROM THE INNER BARREL TO START CORING ACROSS SHYB FORMATION.-CONFIRM SPACE OUT FOR CUTTING THE CORE. -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS | 4840 |  | RIG | 08/28/2022 | SINO-46L | CORE | SHYB-270
3201 | 4900 |  | CORE | E | 4385 | CORC | CUT 8-1/2" X 4" CORE #4 FROM 4840' TO 4900' W/77 PCF AOM & FULL 100% RETURNS.** CORING PARAMETERS: ** WOB: 5-10 KLBS. GPM: 175 - 185 , SPP: 280-320 PSI. RPM: 60-65, TRQ: 2-4 KLB | 4840 |  | CPR | 08/28/2022 | SINO-46L | CORE | SHYB-270
3202 | 4900 |  | CIRC | E | 4385 | MPMP | BREAK OFF CORE #4 AS PER CORE ENG WITH 5 KLB OVERPULL , PUMP OUT TO CORE POINT @ 4840 ', CHC.** FLOW CHECK WELL STATIC | 4900 |  | RIG | 08/28/2022 | SINO-46L | CORE | SHYB-270
3203 | 4900 | 4641 | TO | E | 4385 | STDP | POOH CONTROLLED SPEED WITH CORE ASSY #4 ON 5" DP STD'S TO CSG SHOE.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4900 | 4900 | RIG | 08/28/2022 | SINO-46L | CORE | SHYB-270
3204 | 4900 | 621 | TO | E | 4385 | STDP | HPJSM, POOH CONTROLLED SPEED WITH CORE ASSY #4 ON 5" DP STD'S TO TOP OF BHA.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4900 | 4641 | RIG | 08/28/2022 | SINO-46L | CORE | SHYB-270
3205 | 4900 |  | HT | E | 4385 | CORC | HPJSM, CONTD POOH WITH 8-1/2" CORPRO CORING ASSY #4 TO SURFACE CONTROLLED SPEED.** RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.** ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.** L/D INNER BARRELS, 60' RECOVERED (100 % RECOVERY) FROM CORE #4** CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 4900 |  | CPR | 08/28/2022 | SINO-46L | CORE | SHYB-270
3206 | 4900 |  | HT | E | 4385 | CORC | HPJSM, P/U & M/U 8-1/2" CORPRO CORING ASSY RUN #5 (80' CORE BARREL). ** 8-1/2" CORE HEAD + 7-1/8" CORE OUTER BARRELS & 4-1/2" INNER BARRELS + FLOAT SUB W/ FLOAT VALVE+15 X 6-1/2" DC'S+ 6-1/2" DRILLING JAR+2 X 6 1/2" DC'S +XO+ PBL + DP'S. | 4900 |  | CPR | 08/28/2022 | SINO-46L | CORE | SHYB-270
3207 | 4900 | 4900 | TI | E | 4385 | STDP | RIH WITH 8-1/2" CORPRO CORING ASSY #5 CONTROLLED SPEED FROM 621' TO 4900'.** PASSED 9-5/8" DV FREELY.** GENTLY PASSED SHOE TRACK.** WASH DOWN LAST STAND TILL TAGGED BTM GENTLY. | 4900 | 621 | RIG | 08/28/2022 | SINO-46L | CORE | SHYB-270
3208 | 4900 |  | CIRC | E | 4385 | MPMP | CIRCULATE BTMS UP, ACTIVATED DIVERTING BALL, PUMP DOWN WITH 400 GPM & WAIT TILL DIVERT FLUID AWAY FROM THE INNER BARREL TO START CORING ACROSS SHYB FORMATION.-CONFIRM SPACE OUT FOR CUTTING THE CORE. -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS | 4900 |  | RIG | 08/28/2022 | SINO-46L | CORE | SHYB-270
3209 | 4910 |  | CORE | E | 4385 | CORC | CUT 8-1/2" X 4" CORE #5 FROM 4900' TO 4910' W/77 PCF AOM & FULL 100% RETURNS.** CORING PARAMETERS: ** WOB: 5-10 KLBS. GPM: 175 - 185 , SPP: 280-320 PSI. RPM: 60-65, TRQ: 2-4 KLB | 4900 |  | CPR | 08/28/2022 | SINO-46L | CORE | SHYB-270
3210 | 91 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | 8-1/2" CORING OPERATION | 24 | 4385 | 25 Aug 0045 | 08/28/2022 | SINO-46L | Type | SHYB-270
3211
3212
3213 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | SND-2001 | Hrs | HWYH-1229
3214 | UVLC | ARM | 38 | 27 Aug 1500 - 0500 | 2674 | 901380 | WHILE DRILLING 22" HOLE SECTION HAD TOTAL LOSSES AT 2674' | LCIR | NA |  | 08/28/2022 | SND-2001 | 24 | HWYH-1229
3215 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | SP-154 | Hrs | SDGM-353
3216 | FOT | TOD | 124.5 | 23 Aug 0700 - 0500 | 7267 | 901232 | UNABLE TO CLOSE HYDRO SEAL DURING CEMENTING OFF BOTTOM LINER CAUSING FAILED PRESSURE TEST, | TF | DV |  | 08/28/2022 | SP-154 | 24 | SDGM-353
3217 | 6769 | 6375 | TI | E | 4425 | STDP | RIH 6-1/8" REAMING BHA F/5500' TO 7"CSG SHOE@ 6374'.- FILL STRING EVERY 20 STDS.- MONITOR WELL THRU TRIP TANK - WELL STATIC. | 6769 | 5500 | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3218 | 6769 | 6769 | TI | E | 4425 | STDP | CONTINUE RIH 6-1/8" REAMING BHA IN OH F/6374 ' TO BTM@ 6769'.- WASH DOWN LAST STAND TO BTM.- MONITOR WELL ON TRIP TANK & TRIP SHEET, WELL STATIC. | 6769 | 6375 | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3219 | 6769 |  | CIRC | E | 4425 | MPMP | SWEEP HOLE WITH 20 BBL'S HVP & CIRC HOLE CLEAN, MWT IN/OUT 70 PCF.-SPOTED 60 BBL LUBRICATED HVP AT BTM, 100% RETURN. | 6769 |  | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3220 | 6769 |  | WCNT | N | 4425 | NA | FLOW CHECK, WELL STATIC. | 6769 |  | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3221 | 6769 | 6374 | TO | N | 4425 | STDP | POOH W/ 6-1/8'' REAMING BHA TO 7'' CSG SHOE @ 6,374'. - HOLE IN GOOD CONDITION. | 6769 | 6769 | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3222 | 6769 |  | WCNT | N | 4425 | NA | FLOW CHECK @ 07" CSG SHOE , WELL STATIC. | 6769 |  | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3223 | 6769 | 1597 | TO | N | 4425 | STDP | CONTD POOH 6-1/8" REAMING BHA F/6374' TO TOL @ 1597'.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6769 | 6374 | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3224 | 6769 |  | WCNT | N | 4425 | NA | FLOW CHECK @7" TOL, WELL STATIC OK. | 6769 |  | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3225 | 6769 | 540 | TO | N | 4425 | STDP | CONTD POOH 6-1/8" REAMING BHA F/1597' TO TOP OF BHA @ 540'.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6769 | 1597 | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3226 | 6769 |  | WCNT | N | 4425 | NA | FLOW CHECK AT TOP BHA, WELL STATIC OK. | 6769 |  | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3227 | 6769 | 0 | TO | N | 4425 | STDP | CONTD POOH 6-1/8" REAMING BHA TO SURFACE.-MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 6769 | 540 | RIG | 08/28/2022 | SP-53L | CT | HRDH-528
3228 | 6769 |  | PJSM | E | 4405 | NA | HOLD PRE JOB SAFETY MEETING WITH ALL CONCERNED PERSONNEL PRIOR TO R/U W/L EQUIPMENT, DISCUSSED ALL RISKS AND MITIGATIONS MEANWHILE MONITORING WELL THROUGH TRIP TANK, WELL STATIC. | 6769 |  | RIG | 08/28/2022 | SP-53L | LOG | HRDH-528
3229 | 6769 | 181 | LOG | E | 4405 | WLT | P/U & M/U BHI W/L LOGGING TOOLS RUN #2: GR-RCX-IFX-WGI (FORMATION TESTER & SAMPLING).- 2 X PROBE (STANDARD &DXL)-SAMPLE VIEW, FLUID ANALYZER, 3 X PUMPS, 2 CARRIERS (10 TANK, 2 FILTER), STRADDLE PKR'S -GAMMA RAY AND CALIPER LOG.- PERFORM SURFACE FUNCTION CHECKS AND TOOL CALIBRATION ON SURFACE BEFORE RIH, OK.- TOTAL LOGGING TOOL LENGTH: 180.9', WT: 5303 LB & MAX OD: 5.6".- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 0 | BAW | 08/28/2022 | SP-53L | LOG | HRDH-528
3230 | 6769 | 6114 | LOG | E | 4405 | WLT | HPJSM, RIH WL RUN#2 LOGGING TOOLS (GR-RCX-IFX-WGI ) ON 4" &5'' DRIFTED DP STDS WITH CONTROL SPEED 2 MIN/STD SLIPS TO SLIPS TO 6114'(LATCHING DEPTH).- FILL STRING EVERY 15 STDS.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 181 | BAW | 08/28/2022 | SP-53L | LOG | HRDH-528
3231 | 6769 |  | CIRC | E | 4405 | MPMP | CIRCULATE TWICE STRING CAPACITY, 100% RETURN. USED BAKER WL SCREEN.- MW IN / OUT 70 PCF. | 6769 |  | RIG | 08/28/2022 | SP-53L | LOG | HRDH-528
3232 | 6769 |  | OTH | E | 4405 | NA | HPJSM. R/U BH W/L SHEAVES AND INSTALL SES.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 |  | BAW | 08/28/2022 | SP-53L | LOG | HRDH-528
3233 | 6769 | 6114 | LOG | E | 4405 | WLT | RIH WITH LATCH HEAD AND LATCH DOWN HOLE TOOL. TEST COMMUNICATION ,OK. MAKE PULL TEST ON SES CABLE CLAMP W/5000LB LINE PULL - OK.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6114 | BAW | 08/28/2022 | SP-53L | LOG | HRDH-528
3234 | 6769 | 6398 | LOG | E | 4405 | WLT | CONT. RIH WL RUN#2 LOGGING TOOLS (GR-RCX-IFX-WGI ) ON 4"&5'' DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED 3 MIN/STD SLIPS TO SLIPS TO 6398 1ST (PRESSURE POINT).- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 6769 | 6114 | BAW | 08/28/2022 | SP-53L | LOG | HRDH-528
3235 | 6769 | 6421 | LOG | E | 4405 | WLT | CONT. RIH WL RUN#2 LOGGING TOOLS (GR-RCX--IFX-WGI ) ON 4"&05'' DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED WHILE LOG DOWN F/ 6398' T/ 6421'.- PERFORMED STICK TENDENCY TESTS @ 6398' FOR 15 MIN & 30 MINS, NO STICKING TENDENCY.- RECORDED 03/18 PRESSURE POINTS F/ 6398' T/ 6416'.- PRESS POINTS @: 6398', 6408', 6416',- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION.- 6 HRS SINCE LAST CIRCULATION @ LATCH DEPTH.- 22.5 HRS SINCE LAST CIRCULATION W/ REAMING BHA AT BTM. | 6769 | 6398 | BAW | 08/28/2022 | SP-53L | LOG | HRDH-528
3236 | 26.5 | OOS | OTHR | 4425 | LOG | CONDITION TRIP PRIOR TO RUN PCL (GR-RCX-WGI) LOG | RECORDING (ADEX-MREX-MLL) LOG & RUN #2:(GR-RCX-IFX-WGI) LOG AS PER PLAN | 16 | 4405 | 27 Aug 1015 | 08/28/2022 | SP-53L | OOS | HRDH-528
3237
3238
3239
3240 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | SSA-5859 | Hrs | HWYH-1217
3241 | FOT | RIG | 16 | 28 Aug 0500 - 2100 | 302 | 901306 | REPAIR ON TDS: CHANGE BLOWER MOTOR. >> TRIED TO RESUME DRILLING: NOTICED THAT BLOWER MOTOR WAS BROKEN. | RR | TDS |  | 08/28/2022 | SSA-5859 | 16 | HWYH-1217
3242 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/28/2022 | SSA-5892 | Hrs | AWTD-141400
3243 | STBH | ARM | 78.5 | 25 Aug 1330 - 2000 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | STUK | BHA |  | 08/28/2022 | SSA-5892 | 15 | AWTD-141400
3244 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | 095TE | Hrs | MNIF-126
3245 | FRFM | ARM | 41.5 | 28 Aug 1030 - 0500 | 6100 | 901348 | CURE LOSSES AT SFNY FORMATION WITH LCM PILL AND CMT PLUG. | LCIR | NA |  | 08/29/2022 | 095TE | 23.5 | MNIF-126
3246 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ADC-17 | Hrs | ZULF-1385
3247 | GRF | RIG | 9.5 | 28 Aug 0130 - 1100 | 0 | 901365 | LEAK WHILE PRESSURE TEST DIVERTER BETWEEN DIVERTER & MUD CROSS, REPAIR AND OBSERVE ADDITIONAL LEAK BETWEEN WELD NECK FLANGE AND MUD CROSS, N/D WELD NECK FLANGE TO REPLACE GASKET | UPRA | RWCS |  | 08/29/2022 | ADC-17 | 6 | ZULF-1385
3248 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ADC-43L | Hrs | UTMN-3118
3249 | FRFM | TK3 | 339.25 | 11 Aug 2130 - 0600 | 12650 | 900794 | WHILE DRILLING PARTIAL LOSSES IN KHUFF B CARBONATE. PUMPING LCM & CEMENT PLUGS TO CURE THE LOSSES. | LCIR | NA |  | 08/29/2022 | ADC-43L | 1 | UTMN-3118
3250 | 7045 | 6674 | LOG | E | 4305 | WLT | STATION#9 (PUMPING) @ 6674' (ABD1), CYCLE#1: - POSITION STRING @ 6674', ACTIVATED XL PROBE & PUMPING OUT STATION #9 - PUMP OUT 127 LITERS: 6 LITRES OF FORMATION WATER, 121 LITERS OIL (5% WATER /95 % OIL), NO SAMPLE TAKEN.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 3.47 BBLS (WATER: 2.38 BBLS - OIL: 1.09 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 378 PSI (ABD1).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 39.5 HRS SINCE LAST CIRCULATION AT BTM. | 7045 | 6674 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3251 | 7045 | 6668 | LOG | E | 4305 | WLT | MOVE & POSITION STRING @ 10TH POINT @ 6668',(STATION#10 PUMPING OUT POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6674 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3252 | 7045 | 6668 | LOG | E | 4305 | WLT | STATION#10 (PUMPING) @ 6668' (BPDS), CYCLE#1: - ACTIVATED STANDARD PROBE & PUMPING OUT STATION #10 - PUMP OUT 121 LITERS: 6 LITRES OF FORMATION WATER, 115 LITERS OIL (5% WATER /95 % OIL), NO SAMPLE TAKEN.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 4.23 BBLS (WATER: 2.42 BBLS - OIL: 1.81 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 378 PSI (BPDS).- DEACTIVATE STANDARD PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 43 HRS SINCE LAST CIRCULATION AT BTM. | 7045 | 6668 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3253 | 7045 | 6658 | LOG | E | 4305 | WLT | MOVE & POSITION STRING @ 11TH POINT @ 6658',(STATION#11 PUMPING OUT POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6668 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3254 | 7045 | 6658 | LOG | E | 4305 | WLT | STATION#11 (PUMPING) @ 6658' (PADS), CYCLE#1: - ACTIVATED XL PROBE & PUMPING OUT STATION #11 @6658'- PUMP OUT 94 LITERS: 4.7 LITRES OF FORMATION WATER, 89.3 LITERS OIL (5% WATER /95 % OIL), NO SAMPLE TAKEN.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 4.82 BBLS (WATER: 2.45 BBLS - OIL: 2.37 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 376 PSI (PADS).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 46 HRS SINCE LAST CIRCULATION AT BTM.- RDD INSTRUCTED TO ADD 02 MORE POINTS (6686' AND 6706') | 7045 | 6658 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3255 | 7045 | 6686 | LOG | E | 4305 | WLT | MOVE & POSITION STRING @ 12TH POINT @ 6686',(STATION#12: SAMPLE POINT). PERFORM STICKY TENDENCY TEST FOR 15 MIN, 30 MIN & 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 | 6658 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3256 | 7045 | 6686 | LOG | E | 4305 | WLT | SCANNING AROUND THE STATION#12 WITH STANDARD PROBE @ 6687' (AD2A) FOR GOOD SEAL & MOBILITY. | 7045 | 6686 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3257 | 7045 | 6686 | LOG | E | 4305 | WLT | STATION#12 (PUMPING) POSITIONED @ 6687' (AD2A), CYCLE#1: - ACTIVATED STANDARD PROBE & PUMPING OUT STATION #12 @6687'- PUMP OUT 149 LITERS: 149 LITRES OF FORMATION WATER, 0 LITERS OIL (100% WATER /0 % OIL), TAKE 1 BOTTLE OF 500CC FLUID SAMPLE AS PER RDD- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 5.75 BBLS (WATER: 3.38 BBLS - OIL: 2.37 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 380 PSI (AD2A).- DEACTIVATE STANDARD PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 53 HRS SINCE LAST CIRCULATION AT BTM. | 7045 | 6686 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3258 | 7045 |  | OTH | E | 4305 | NA | MOVE & POSITION STRING @ 13TH POINT @ 6706',(STATION#13 SAMPLING POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 7045 |  | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3259 | 7045 |  | OTH | E | 4305 | NA | SCANNING AROUND THE STATION#13 WITH STANDARD PROBE @ 6706' (2A05) FOR GOOD MOBILITY. | 7045 |  | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3260 | 7045 | 6706 | LOG | E | 4305 | WLT | STATION#13 (SAMPLING) POSITIONED @ 6706' (2A05), CYCLE#1: - ACTIVATED XL PROBE & PUMPING OUT STATION #12 @6706'- PUMP OUT 143 LITERS: 136 LITRES OF FORMATION WATER, 7 LITERS OIL (95% WATER /5 % OIL), TAKE 1 BOTTLE OF 500CC FLUID SAMPLE AS PER RDD- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 6.65 BBLS (WATER: 4.23 BBLS - OIL: 2.42 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 381 PSI (2A05).- DEACTIVATE XL PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 58 HRS SINCE LAST CIRCULATION AT BTM. | 7045 | 6706 | BAW | 08/29/2022 | ADC-54L | LOG | HRDH-584
3261 | 7045 | 6900 | ST | E | 4305 | STDP | RIH WITH LOGGING TOOL STRING TO BOTTOM OF FORMATION FLUID AT 6900' (200' BELOW STATION#6).- MONITOR WELL THRU TRIP TANK, STATIC. | 7045 | 6706 | RIG | 08/29/2022 | ADC-54L | LOG | HRDH-584
3262 | 7045 |  | CIRC | E | 4305 | MPMP | CIRCULATE FROM BTM TO GET FORMATION FLUID INSIDE 9-5/8" CSG SHOE, OBSERVED CONTAMINATED MUD WITH TRACES OF OIL ON SHALE SHAKER, STOPPED, FLOW CHECK - WELL STATIC, CLOSE ANNULAR, SICP & SIDP=0 PSI, CONTINUED CIRCULATION TO CONDITION MUD THRU. CHOKE & MGS @ 150 GPM, 480 PSI, MWT IN/OUT=79 PCF, OK. - NO CUT ON MUD WT & NO GAS AT SURFACE WHILE CIRCULATION.- FLOW CHECK THRU CHOKE, WELL STATIC. | 7045 |  | RIG | 08/29/2022 | ADC-54L | LOG | HRDH-584
3263 | 7045 |  | WCNT | E | 4305 | NA | OPEN ANNULAR & EXTEND FLOW CHECK, WELL STATIC.- CHECK WL CONDITION & TOOLS COMMUNICATION, OK. | 7045 |  | RIG | 08/29/2022 | ADC-54L | LOG | HRDH-584
3264 | 137.75 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" PILOT HOLE LOGGING : RUN#1: MREX LOG ON TWO MODES: GAS MODE & LIGHT OIL MODE / RUN#2: PCL LOG RUN#2: RCX-IFX-GR (PRESSURE & SAMPLES). | 24 | 4305 | 23 Aug 0830 | 08/29/2022 | ADC-54L | Type | HRDH-584
3265
3266
3267 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ADC-55L | Hrs | UTMN-3171
3268 | FOT | RIG | 147 | 23 Aug 0200 - 0500 | 10968 | 901375 | WHILE PT BOP OBSERVED LEAK BETWEEN DSA & LOWER DBL GATE | BOP | RAMS |  | 08/29/2022 | ADC-55L | 24 | UTMN-3171
3269 | LHFL | RIG | 4.75 | 29 Aug 2200 - 0245 | 6952 | 901455 | OBSERVED LEAK ON STAND PIPE S BEND. | RR | HSYS |  | 08/29/2022 | ADC-62L | 4.75 | ANDR-589
3270 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ADC-62L | Hrs | ANDR-589
3271 | FPMP | RIG | 4.5 | 28 Aug 1800 - 1830 | 6197 | 901308 | REPAIR MUD PUMPS : CHANGED OUT MP# 1 & 2 WEAR PLATE | RR | MPMP |  | 08/29/2022 | ADC-62L | 1.5 | ANDR-589
3272 | LHFL | RIG | 4.75 | 29 Aug 2200 - 0245 | 6952 | 901455 | OBSERVED LEAK ON STAND PIPE S BEND. | RR | HSYS |  | 08/29/2022 | ADC-62L | 4.75 | ANDR-589
3273 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ADES-174 | Hrs | GHZL-72
3274 | SFHS | BFW | 183.75 | 22 Aug 0530 - 0500 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/29/2022 | ADES-174 | 24 | GHZL-72
3275 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ADES-889 | Hrs | HRDH-2122
3276 | FOT | BHI | 24.75 | 28 Aug 0245 - 0500 | 11160 | 901383 | HAD NO COMMUNICATION WITH BAKER RSS TOOL | BHA | RSS |  | 08/29/2022 | ADES-889 | 22.5 | HRDH-2122
3277 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ADM-511 | Hrs | MRJN-799
3278 | FOT | ARN | 1 | 29 Aug 1530 - 1645 | 13533 | 901418 | HAD V-SAT ISSUE UNABLE TO TRANSMIT REAL TIME DATA TO GOC. | TF | VSAT |  | 08/29/2022 | ADM-511 | 1 | MRJN-799
3279 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ADM-655 | Hrs | SFNY-183
3280 | OTH | RIG | 24 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 08/29/2022 | ADM-655 | 24 | SFNY-183
3281 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ARO-3004 | Hrs | MRJN-2060
3282 | HERR | RIG | 4 | 29 Aug 2030 - 0030 | 42 | 901398 | RIG FAILED TO FLUSH LINES CLEAR OF LCM, RESULTING IN LCM ON TOP OF 2-WAY CHECK VALVE & UNABLE TO RECOVER. | WH | BPV |  | 08/29/2022 | ARO-3004 | 4 | MRJN-2060
3283 | FOT | RIG | 4 | 29 Aug 1830 - 2230 | 0 | 901415 | CANNOT REMOVE WORN OUT JAWS OF POWER TONG | TF | SLIPS |  | 08/29/2022 | ED-85A | 4 | ZULF-2066
3284 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ED-85A | Hrs | ZULF-2066
3285 | OTH | RIG | 17.5 | 29 Aug 0730 - 0500 | 0 | 901414 | DUE TO SKID ENGINE CAPABILITY, RIG CANNOT PERFORM TRANSVERSE SKID WITH MORE THAN 100 KLB DRILL STRG WEIGHT ON DERRICK. AS PER RIG CONTRACT ,RIG CAPABLE TO TRANSVERSE SKID WITH 250 KLB. | UPRA | NA |  | 08/29/2022 | ED-85A | 17.5 | ZULF-2066
3286 | FOT | RIG | 4 | 29 Aug 1830 - 2230 | 0 | 901415 | CANNOT REMOVE WORN OUT JAWS OF POWER TONG | TF | SLIPS |  | 08/29/2022 | ED-85A | 4 | ZULF-2066
3287 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | ENS-108 | Hrs | ZULF-2015
3288 | GRF | RIG | 168 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/29/2022 | ENS-108 | 24 | ZULF-2015
3289 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | HWU-1 | Hrs | HMYM-431414
3290 | FOT | RIG | 12.75 | 29 Aug 1615 - 0500 | 0 | 901393 | UNABLE TO SCOPE UP GIN POLE | RR | CBLK |  | 08/29/2022 | HWU-1 | 12.75 | HMYM-431414
3291 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | MP-1 | Hrs | MRJN-78
3292 | FOT | NRT | 677.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/29/2022 | MP-1 | 24 | MRJN-78
3293 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | NA-18S | Hrs | SDGM-444
3294 | FOT | WI3 | 36 | 28 Aug 1430 - 0500 | 11135 | 901381 | PASSED TOW AT 11,122FT BUT HAD TAG AT 11.135FT - ONE FT ABOVE BOW. HAD MANY TRIALS - NO SUCCESS | TF | WPSTK |  | 08/29/2022 | NA-18S | 24 | SDGM-444
3295 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | NBR-263S | Hrs | QTIF-736
3296 | STBH | ARM | 404.5 | 29 Jul 0230 - 0500 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/29/2022 | NBR-263S | 24 | QTIF-736
3297 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | NBR-654S | Hrs | HRDH-1150
3298 | HERR | WCR | 3 | 29 Aug 1300 - 1600 | 8347 | 901396 | 3.795" DRIFT COULDNT PASS 270FT BELOW RT THROUGH 4.5" TUBING DUE TO DAMMAGED TUBING CONNECTION. CONNECTION DAMMAGE CAUSED BY OVERTORQUING WITH WFD POWER TONG | JF | CTRQ |  | 08/29/2022 | NBR-654S | 3 | HRDH-1150
3299 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | PA-622S | Hrs | UTMN-3600
3300 | FOT | HWP | 5.75 | 29 Aug 0500 - 1045 | 13651 | 901311 | HALLIBURTON TROUBLESHOOT WIRELINE LOGGING TOOLS (SIDEWALL CORRING) - NOT ABLE TO APPLY ROTATION & TORQUE TO COREHEAD. | TF | WLT |  | 08/29/2022 | PA-622S | 5.75 | UTMN-3600
3301 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | PA-70S | Hrs | HRDH-1939
3302 | ETRQ | CDB | 29.75 | 28 Aug 1000 - 0000 | 10320 | 901412 | BIT FAILED TO DRILL TO SECTION TD. ROP DROPPED & HAD ERRATIC TORQUE. | LROP | BIT |  | 08/29/2022 | PA-70S | 17.75 | HRDH-1939
3303 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | RBP-50A | Hrs | HSBH-52
3304 | FOT | SCT | 4 | 29 Aug 1845 - 2245 | 12595 | 901401 | ATTEMPT TO TEST HSL RISER, PCE & LUBRICATOR WITH WATER. NO SUCCESS, LEAKING LO-TORQUE. | TF | CTPMP |  | 08/29/2022 | RBP-50A | 4 | HSBH-52
3305 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SINO-11 | Hrs | MZLJ-23
3306 | FOT | INW | 35 | 28 Aug 1800 - 0500 | 4465 | 901417 | ATTEMPT TO RETRIEVE INTERWELL PLUG, NO SUCCESS. | TF | PLUGT |  | 08/29/2022 | SINO-11 | 24 | MZLJ-23
3307 | 0 |  | OTH | N | 4406 | NA | CONITNUE R/U 2" GDMC CTU EQUIPMENT (CONNECTED ALL HYDRAULIC HOSES TO CT INJECTOR,STRIPPER AND BOP.> CONNECT SURFACE LINES FROM HES PUMPING UNIT TO CT REEL AND BOP AT WH.> CONNECTED ALL HYDRAULIC HOSES TO CT INJECTOR,STRIPPER AND BOP.> FUNCTION TEST BOP RAMS. CONNECT SURFACE LINES TO COILED TBG UNIT. MAKE UP CONNECTOR HEAD & APPLIED PULL TEST TO 30 KLB-OK.> FILL COILED TBG WITH WATER, DROPPED BALL, DISPLACED SAME THROUGH THE COILED TBG.> RAISE INJECTOR HEAD TO RIG FLOOR.> CONNECT INJECTOR HEAD TO RISER AND PT RAMS TO 300/2500 PSI-OK.> OPEN INJECTOR HEAD CONNECTION, CONNECT WDF BHA#1 3.5" ROTATING JETTING NOZZLE & FUNCTION TEST.> P/T BHA FLAPPER VALVE TO 2500 PSI-OK.CONTINUE SPOT AND R/U RAWABI FLOWBACK & SURFACE EQUIPMENT.> SPOT & R/U TWO STORAGE TANKS, SURGE TANK AND RELATED SURFACE EQUIPMENT.> CONNCT SURFACE LINES TO WELL HEAD & P/T SAME TO 2500 PSI-OK. | 0 |  | GDM | 08/29/2022 | SINO-37L | DCOM | HWYH-114
3308 | 0 |  | OTH | N | 4406 | NA | PU & MU 3.5" WFD FULL BORE NOZZLES WITH HIGH SEED ROTATING TOOL WITH 3.5" CENTRALIZER AND CONNECT IT TO 2" CONNECTOR.- BHA LENGTH: 12.5 FT, MAX OD = 3.5".- FUNCTION TEST BHA ASSY WITH 1 BPM & 2 BPM @ 1120 PSI / 4200 PSI RESPECTIVELY.- CONNECT INJECTOR HEAD TO RISER AND PT TO 2500 PSI.- FUNCTION TEST WFD BHA FLAPPER VALVE . | 0 |  | GDM | 08/29/2022 | SINO-37L | DCOM | HWYH-114
3309 | 0 |  | OTH | N | 4406 | NA | HPSJM, WASH DOWN WITH 3.5" WFD FULL BORE NOZZLES ASSY. FROM 50 FT TO 600' WITH 82 PCF BRINE WITH 2 BPM @ 4,600 PSI.> HAD CT REEL SCREEN PARTIALLY PLUGGED AFTER PUMP 5 BBL HVP (60 CP) AT 150', POOH TO SURFACE, REPLACE THE CT REEL SCREEN, PT SURFACE LINE, CONTINUE WASH DOWN .> CLEANING SPEED: 10 FT/MIN.> PULL TEST EVERY 150 FT.> TAKE RETURNS THRU RAWABI CHOCK (CHOCK IS FULLY OPEN), P: 40-60 PSI. | 0 |  | GDM | 08/29/2022 | SINO-37L | DCOM | HWYH-114
3310 | 90 | OOS | Category | DOOS ID | DCOM | Out of Scope Summary | RETREIVE PX PLUG STACK IN X-NIPPLE, INSTALLED BY PRODUCTION TO SECURE THE WELL DURING CELLAR INSTALATION. | 24 | 4406 | 26 Aug 1100 | 08/29/2022 | SINO-37L | Type | HWYH-114
3311
3312
3313 | 4980 |  | CORE | E | 4385 | CORC | CONTINUE CUT 8-1/2" X 4" CORE #5 FROM 4900' TO 4980' W/77 PCF AOM & FULL 100% RETURNS.** CORING PARAMETERS: ** WOB: 5-10 KLBS. GPM: 175 - 185 , SPP: 280-320 PSI. RPM: 60-65, TRQ: 2-4 KLB | 4910 |  | CPR | 08/29/2022 | SINO-46L | CORE | SHYB-270
3314 | 4980 |  | CIRC | E | 4385 | MPMP | BREAK OFF CORE #5 AS PER CORE ENG WITH 5 KLB OVERPULL , PUMP OUT TO CORE POINT @ 4900 ', CIRC BTM/UP.** FLOW CHECK WELL STATIC | 4980 |  | RIG | 08/29/2022 | SINO-46L | CORE | SHYB-270
3315 | 4980 | 4641 | TO | E | 4385 | STDP | POOH CONTROLLED SPEED WITH CORE ASSY #5 ON 5" DP STD'S TO CSG SHOE.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4980 | 4900 | RIG | 08/29/2022 | SINO-46L | CORE | SHYB-270
3316 | 4980 | 621 | TO | E | 4385 | STDP | HPJSM, POOH CONTROLLED SPEED WITH CORE ASSY #5 ON 5" DP STD'S TO TOP OF BHA.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 4980 | 4641 | RIG | 08/29/2022 | SINO-46L | CORE | SHYB-270
3317 | 4980 |  | HT | E | 4385 | CORC | HPJSM, CONTD POOH WITH 8-1/2" CORPRO CORING ASSY #5 TO SURFACE CONTROLLED SPEED.** RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.** ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.** L/D INNER BARRELS, 60' RECOVERED (100 % RECOVERY) FROM CORE #4** CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 4980 |  | CPR | 08/29/2022 | SINO-46L | CORE | SHYB-270
3318 | 4980 |  | HT | E | 4385 | CORC | HPJSM, P/U & M/U 8-1/2" CORPRO CORING ASSY RUN #6 (80' CORE BARREL). ** 8-1/2" CORE HEAD + 7-1/8" CORE OUTER BARRELS & 4-1/2" INNER BARRELS + FLOAT SUB W/ FLOAT VALVE+15 X 6-1/2" DC'S+ 6-1/2" DRILLING JAR+2 X 6 1/2" DC'S +XO+ PBL + DP'S | 4980 |  | CPR | 08/29/2022 | SINO-46L | CORE | SHYB-270
3319 | 4980 | 4980 | TI | E | 4385 | STDP | RIH WITH 8-1/2" CORPRO CORING ASSY #6 CONTROLLED SPEED FROM 621' TO 4900'.** PASSED 9-5/8" DV FREELY.** GENTLY PASSED SHOE TRACK.** WASH DOWN LAST STAND TILL TAGGED BTM GENTLY. | 4980 | 621 | RIG | 08/29/2022 | SINO-46L | CORE | SHYB-270
3320 | 4980 |  | CIRC | E | 4385 | MPMP | CIRCULATE BTMS UP, ACTIVATED DIVERTING BALL, PUMP DOWN WITH 400 GPM & WAIT TILL DIVERT FLUID AWAY FROM THE INNER BARREL TO START CORING ACROSS SHYB FORMATION.-CONFIRM SPACE OUT FOR CUTTING THE CORE. -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS | 4980 |  | RIG | 08/29/2022 | SINO-46L | CORE | SHYB-270
3321 | 5060 |  | CORE | E | 4385 | CORC | CUT 8-1/2" X 4" CORE #6 FROM 4980' TO 5060' W/77 PCF AOM & FULL 100% RETURNS.** CORING PARAMETERS: ** WOB: 5-10 KLBS. GPM: 175 - 185 , SPP: 280-320 PSI. RPM: 60-65, TRQ: 2-4 KLB | 4980 |  | CPR | 08/29/2022 | SINO-46L | CORE | SHYB-270
3322 | 5060 |  | CIRC | E | 4385 | MPMP | BREAK OFF CORE #6 AS PER CORE ENG WITH 5 KLB OVERPULL , PUMP OUT TO CORE POINT @ 4980 ', CIRC BTM/UP.** FLOW CHECK WELL STATIC | 5060 |  | RIG | 08/29/2022 | SINO-46L | CORE | SHYB-270
3323 | 115 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | 8-1/2" CORING OPERATION | 24 | 4385 | 25 Aug 0045 | 08/29/2022 | SINO-46L | Type | SHYB-270
3324
3325
3326 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SND-2001 | Hrs | HWYH-1229
3327 | UVLC | ARM | 42.75 | 27 Aug 1500 - 0945 | 2674 | 901380 | HAD TOTAL LOSSES 3FT BELOW 24" CSG SHOE AT 2674' | LCIR | NA |  | 08/29/2022 | SND-2001 | 4.75 | HWYH-1229
3328 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SND-2003 | Hrs | GZLN-1
3329 | FOT | RIG | 5 | 29 Aug 0930 - 1430 | 7840 | 901420 | SCR MALFUNCTION, TROUBLESHOOT & FOUND SCR CIRCUIT CONTACTOR DAMAGED, REPAIR SAME. | RR | PSYS |  | 08/29/2022 | SND-2003 | 5 | GZLN-1
3330 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SP-154 | Hrs | SDGM-353
3331 | FOT | TOD | 148.5 | 23 Aug 0700 - 0500 | 7267 | 901232 | UNABLE TO CLOSE HYDRO SEAL DURING CEMENTING OFF BOTTOM LINER CAUSING FAILED PRESSURE TEST, | TF | DV |  | 08/29/2022 | SP-154 | 24 | SDGM-353
3332 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SP-258 | Hrs | JNAB-872212
3333 | OTH | RIG | 3.5 | 29 Aug 2000 - 2330 | 12910 | 901416 | DRILLING LINE JUMPED AND FLIPPED OVER OUT OF SPOOLER ON THE DRUM DUE TO PICK UP VERY FAST THEN SUDDENLY STOP | UPRA | NA |  | 08/29/2022 | SP-258 | 3.5 | JNAB-872212
3334 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SP-262 | Hrs | JNAB-152802
3335 | HERR | SCM | 4 | 29 Aug 0900 - 1300 | 18630 | 901395 | SLB CREW ACCIDENTALLY MIXED 4 BBLS OF CORROSION INHIBATOR IN THE SPACER TANK INSTEAD OF THE BRINE TANK. | CMT | NA |  | 08/29/2022 | SP-262 | 4 | JNAB-152802
3336 | 6769 | 6606 | LOG | E | 4405 | WLT | CONT. RIH WL RUN#2 LOGGING TOOLS (GR-RCX-IFX-WGI ) ON 4"&05'' DRIFTED DP STDS & WL CABLE WITH CONTROL SPEED WHILE LOG DOWN FROM 6421' TO 6606'.- PERFORMED STICK TENDENCY TESTS @ 6430', 6453', 6497' &6606' FOR 15 MIN & 30 MINS, NO STICKING TENDENCY.- COMPLETED RECORDING 18/18 PRESSURE POINTS F/ 6421' T/ 6606'.- PRESS POINTS @:6421(2A06) ; 6430'(2A06), 6435'(2A06), 6440'(AD2B),6444'(AD2B), 6453'(2B08),6460'(2B09), 6471'(2B10),6480'(2B11), 6490'(2B13),6497'(AD3A), 6558(AD3B)',6564(BADR)', 66575'(BADR),6606'(BADR),- MONITOR HOLE ON TRIP TANK, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 6769 | 6398 | BAW | 08/29/2022 | SP-53L | LOG | HRDH-528
3337 | 6769 | 6606 | LOG | E | 4405 | WLT | POSITION STRING @ 1ST SAMPLE POINT @ 6606',(STATION#1 SAMPLING POINT), PERFORM STICKY TENDENCY TEST FOR 1HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6606 | BAW | 08/29/2022 | SP-53L | LOG | HRDH-528
3338 | 6769 | 6606 | LOG | E | 4405 | WLT | STATION#1 (SAMPLING)@ 6606' (BADR),: -TRIED WITH DXL PROBE , LOW MOBILITY-CHANGE TO STRADDLE PKR'S AND TRY TO PUMP OUT-DRAY ,ABORTED DUE TO LOW MOBILITY-DEACTIVATE STRADDLE PKR'S , MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6606 | BAW | 08/29/2022 | SP-53L | LOG | HRDH-528
3339 | 6769 | 6564 | LOG | E | 4405 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 6564' (STATION#2 SAMPLING POINT),PERFORM STICKY TENDENCY TEST FOR 15 MIN, 30 MIN & 1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6606 | BAW | 08/29/2022 | SP-53L | LOG | HRDH-528
3340 | 6769 | 6575 | LOG | E | 4405 | WLT | STATION#2 @ 2ND SAMPLE POINT@ 6564' (AD3B)---ONGOING.- ACTIVATED STRADDLE PKR'S & PUMP OUT STATION#2 @ 6564'- PUMP OUT 7 LITRES OF FORMATION WATER, 132 LITERS OIL, TAKE 1 BOTTLE OF 500CC FLUID SAMPLE OIL. - TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 0.87 BBLS (WATER: 0.04 BBLS - OIL: 0.83 BBLS)- MINIMUM OVERBALANCE FROM PRESSURE POINTS- 369 PSI (AD3B).- 30 HRS SINCE LAST CIRCUATION @ LATCH DEPTH.- 46.5 HRS SINCE LAST CIRCULATION W/ REAMING BHA AT BTM. | 6769 | 6575 | BAW | 08/29/2022 | SP-53L | LOG | HRDH-528
3341 | 50.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RECORDING (ADEX-MREX-MLL) LOG & RUN #2:(GR-RCX-IFX-WGI) LOG AS PER PLAN | 24 | 4405 | 27 Aug 1015 | 08/29/2022 | SP-53L | Type | HRDH-528
3342
3343
3344 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SP-58 | Hrs | HRDH-795
3345 | FOT | RIG | 22 | 29 Aug 0700 - 0500 | 0 | 901397 | WHILE PERFORM ANNULAR BOPE TEST, OBSERVED PRESSURE DROP AND LEANK FROM ANNULAR TOP SIDE, RETRIEVED DAMAGED ANNULAR PKR ELEMENT AND OBSERVED SCRATCH ON INNER ANNULAR BODY. | BOP | BOP |  | 08/29/2022 | SP-58 | 22 | HRDH-795
3346 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SSA-29 | Hrs | QTIF-423
3347 | GRF | RIG | 5 | 29 Aug 1500 - 2000 | 12700 | 901394 | FAILURE OF THE ANTI COLLISION SENSOR | UPRA | DWKS |  | 08/29/2022 | SSA-29 | 5 | QTIF-423
3348 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/29/2022 | SSA-5892 | Hrs | AWTD-141400
3349 | FOT | RIG | 97 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 08/29/2022 | SSA-5892 | 21 | AWTD-141400
3350 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | 095TE | Hrs | MNIF-126
3351 | FRFM | ARM | 65 | 28 Aug 1030 - 0500 | 6100 | 901348 | CURE LOSSES AT SFNY FORMATION WITH LCM PILL AND CMT PLUG. | LCIR | NA |  | 08/30/2022 | 095TE | 23.5 | MNIF-126
3352 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-17 | Hrs | ZULF-1385
3353 | FPMP | RIG | .5 | 30 Aug 0245 - 0315 | 1470 | 901503 | PRESSURE DROP DUE TO FAILURE OF PISTON FOR MUD PUMP #1. | RR | MPMP |  | 08/30/2022 | ADC-17 | .5 | ZULF-1385
3354 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-35 | Hrs | MAQL-5
3355 | FOT | HCB | 28.5 | 29 Aug 0030 - 0500 | 5915 | 901459 | AFTER PLT LOGGING ANALYSIS, FOUND COMMUNCATION BETWEEN TOP AND BTTM OF BRIDGE PLUG. | TF | BP |  | 08/30/2022 | ADC-35 | 24 | MAQL-5
3356 | 7045 | 4200 | LOG | E | 4305 | WLT | POOH W/ BHI PCL LOGGING RUN#2: RCX-IFX-GR ON 4" DP STDS & WL CABLE TO SLIPS TO SES DEPTH @ 4200'. - MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 7045 | 6900 | BAW | 08/30/2022 | ADC-54L | LOG | HRDH-584
3357 | 7045 |  | WCNT | E | 4305 | NA | EXTENDED FLOW CHECK, WELL STATIC. | 7045 |  | RIG | 08/30/2022 | ADC-54L | LOG | HRDH-584
3358 | 7045 |  | OTH | E | 4305 | NA | HPJSM, BAKER WIRELINE UNLATCHED CABLE HEAD & POOH W/ WIRELINE CONNECTOR HEAD TO SURFACE, L/D SES & R/D WL SHEAVES.- MONITOR HOLE ON TRIP TANK, HOLE STATIC. | 7045 |  | BAW | 08/30/2022 | ADC-54L | LOG | HRDH-584
3359 | 7045 | 176 | LOG | E | 4305 | WLT | POOH W/ BHI PCL LOGGING RUN#2: RCX-IFX-GR ON 4" DP STDS TO LAST STD ABOVE LOG TOOLS @ 276'. - MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC. | 7045 | 4200 | BAW | 08/30/2022 | ADC-54L | LOG | HRDH-584
3360 | 7045 |  | WCNT | E | 4305 | NA | FLOW CHECK, WELL STATIC. | 7045 |  | RIG | 08/30/2022 | ADC-54L | LOG | HRDH-584
3361 | 7045 |  | OTH | E | 4305 | NA | CONT'D POOH WITH LOGGING TOOL TO SURFACE & L/D SAME. | 7045 |  | BAW | 08/30/2022 | ADC-54L | LOG | HRDH-584
3362 | 7045 |  | HT | N |  | BHA | HPJSM, PU & MU 4" PERFORATED DIVERTER DP JOINT 20 FT AS CEMENT STINGER, FUNCTION TEST SAME, OK. | 7045 |  | RIG | 08/30/2022 | ADC-54L | PA | HRDH-584
3363 | 7045 | 4336 | TI | N |  | STDP | RIH WITH 4" OEDP AS CEMENT STRING WITH 4" CMT STINGER DIVERTER JT TO 9-5/8" CSG SHOE @ 4336'.- BREAKE CIRCULATION EVERY 1000' IN CSD HOLE.- MONITOR WELL ON TRIP TANK & TRIP SHEET - WELL STATIC | 7045 | 0 | RIG | 08/30/2022 | ADC-54L | PA | HRDH-584
3364 | 7045 |  | CIRC | N |  | MPMP | TIME FOR BREAK CIRCULATION WHILE RIH EVERY 1000' AND @ 9-5/8" CSG SHOE, 2 BPM, 245 PSI, 100% CIRC. | 7045 |  | RIG | 08/30/2022 | ADC-54L | PA | HRDH-584
3365 | 7045 | 7040 | ST | N |  | STDP | CONT'D RIH WITH 4" OEDP AS CEMENT STRING WITH 20 FT 4" DIVERTER JT WASH DOWN LAST STAND & TAG BTM @ 7045', POOH TO 7040' BTM OF 1ST BALANCED CEMET PLUG.- BREAKE CIRCULATION EVERY 500' IN OPEN HOLE.- MONITOR WELL ON TRIP TANK & TRIP SHEET - WELL STATIC | 7045 | 4336 | RIG | 08/30/2022 | ADC-54L | PA | HRDH-584
3366 | 7045 |  | CIRC | N |  | MPMP | CIRCULATE AND CONDITION MUD 7 BPM, 735 PSI, MWT IN/OUT 79 PCF. | 7045 |  | RIG | 08/30/2022 | ADC-54L | PA | HRDH-584
3367 | 7045 |  | PTST | N |  | MPMP | R/U CEMENT UNIT AND SURFACE LINES, FLUSHED AND PRESSURE TEST TO 3000 PSI/10 MINS OK. | 7045 |  | RIG | 08/30/2022 | ADC-54L | PA | HRDH-584
3368 | 7045 |  | CIRC | N |  | MPMP | CIRCULATE WHILE BC BATCH MIXING 51 BBLS, 30% EXCESS, 118 PCF CEMET SLURRY. | 7045 |  | RIG | 08/30/2022 | ADC-54L | PA | HRDH-584
3369 | 7045 | 6540 | CMP | N |  | OEDP | PERFORMED 1ST P&A BALANCED CEMENT PLUG (7040' - 6540') AS FOLLOW:- CMT UNIT PUMED 55 BBLS, 101 PCF BH SPACER AHEAD, 5BPM.- CMT UNIT PUMPED 51 BBLS, 118 PCF BATCH MIXED CEMENT SLURRY CEMENT SLURRY (249 SXS G CLASS CMT, 0.01 GPS FP-12L & 0.06 GPS R-21L). AT 5 BPM, - FOLLOWED BY 9.4 BBLS, 101 PCF BH SPACER BEHIND.- DISPLACED ALL WITH TOTAL 51.7 BBLS 79 PCF WBM MUD (4 BBLS UNDER DISPACEMET, SLOW DOWN LAST 10 BBLS TO 2 BPM).- NO LOSSES DURING CEMENT JOB. | 7045 | 7040 | BCM | 08/30/2022 | ADC-54L | PA | HRDH-584
3370 | 7045 | 6340 | ST | N |  | STDP | HPJSM, R/D BAKER CEMENT LINES. | 7045 | 7040 | RIG | 08/30/2022 | ADC-54L | PA | HRDH-584
3371 | 151.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | 8-1/2" PILOT HOLE LOGGING : RUN#1: MREX LOG ON TWO MODES: GAS MODE & LIGHT OIL MODE / RUN#2: PCL LOG RUN#2: RCX-IFX-GR (PRESSURE & SAMPLES). | 13.75 | 4305 | 23 Aug 0830 | 08/30/2022 | ADC-54L | Type | HRDH-584
3372
3373
3374 | ORDS | TK3 | 15 | 30 Aug 1400 - 0500 | 10968 | 901520 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK | WO | NA |  | 08/30/2022 | ADC-55L | 15 | UTMN-3171
3375 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-55L | Hrs | UTMN-3171
3376 | FOT | RIG | 156 | 23 Aug 0200 - 1400 | 10968 | 901375 | WHILE PT BOP OBSERVED LEAK BETWEEN DSA & LOWER DBL GATE | BOP | RAMS |  | 08/30/2022 | ADC-55L | 9 | UTMN-3171
3377 | ORDS | TK3 | 15 | 30 Aug 1400 - 0500 | 10968 | 901520 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK | WO | NA |  | 08/30/2022 | ADC-55L | 15 | UTMN-3171
3378 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-56L | Hrs | UTMN-3069
3379 | FOT | RIG | 1.5 | 30 Aug 0530 - 0700 | 12333 | 901493 | WHILE WASHING DOWN OBSERVED LEAK IN SAVER SUB CONNECTION TO DP XT -54 CONNECTION | RR | CSYS |  | 08/30/2022 | ADC-56L | 1.5 | UTMN-3069
3380 | 13523 |  | NU | C |  | TREE | N/U 4-1/16" 3 K CIW X-MAS TREE, WING VALVE DIRECTION TO THE EAST WITH VALVE HANDELS FACING NORTH. | 13523 |  | RIG | 08/30/2022 | ADC-58L | WH | ABHD-169
3381 | 13523 |  | SET | C |  | BPV | RETRIEVED BPV & INSTALLED TWCV INTO TBG HGR. | 13523 |  | RIG | 08/30/2022 | ADC-58L | WH | ABHD-169
3382 | 13523 |  | PTST | C |  | TREE | R/U SURFACE LINES FROM TEST UNIT TO X-MAS TREE & CHOKE MANIFOLD, P/T X-MAS TREE TO 300/2500 PSI. EACH 10 MIN HOLD OK. | 13523 |  | RIG | 08/30/2022 | ADC-58L | WH | ABHD-169
3383 | 13523 |  | SET | C |  | BPV | RETRIEVED INSTALLED TWCV FM TBG HGR, SECURED WELL W/MLV | 13523 |  | RIG | 08/30/2022 | ADC-58L | WH | ABHD-169
3384 | 13523 |  | PJSM | C |  | PLUGN | HPJSM, DISCUSSED SPECIFIC GAME PLANE & RISK MITIGATIONS.- R/U SLB S/L EQPT. ON TOP OF X-TREE, P/T SAME TO 300/2500 PSI FOR 10 MIN, HOLD OK. | 13523 |  | SLL | 08/30/2022 | ADC-58L | COMP | ABHD-169
3385 | 13523 |  | RTRV | C |  | PLUGN | RIH SP-PULLING TOOL TO 6245' (RX-NIPPLE DEPTH), RETRIEVED PRONG, POOH TO SUR. & L/D SAME.- KEPT 500 PSI INSIDE STRG, RIH GS-PULLING TOOL, UNSET PX PLUG, POOH TO SUR., L/D PX PLUG, OBSERVED SAME IN GOOD COND.- BHGE. KEPT 5,000 PSI INSIDE TRSSSV CONTROL LINE PRIOR TO RIH WITH S/L & CLOSED SAME AFTER POOH WITH S/L TOOLS.- OBSERVED WELL FOR 15 MINS - NO PRESSURE WAS BUILT UP.- R/D SLB EQPT. SAFELY, CLOSED TRSSSV, BLED OFF PRESSURE ABOVE TRSSSV. | 13523 |  | SLL | 08/30/2022 | ADC-58L | COMP | ABHD-169
3386 | 13523 |  | SDR1 | C |  | NA | PERFORMED H2S DRILL, EXPLAINED RISKS WHILE FLOW BACK, FUNCION TEST SINOPIC H2S SENSORS, ASSIGNED ROLES AND RESPONSIBILITIES FOR ALL POB. | 13523 |  | RIG | 08/30/2022 | ADC-58L | LIFT | ABHD-169
3387 | 13523 |  | OTH | C | 4485 | NA | PREPARED & R/U HALL EQPT FOR FLOW BACK OPERATION............. IN PROGRESS- R/U MANUAL VALVE BEFORE T-BLOCK TO RIG KILL LINE.- R/U SSV AND CONNECTED LINES TO SAND FILTER.- R/U SAND FILTER UNIT AND CONNECTED TO HALL CHOKE MANIFOLD.- CONNECTED HALL DIVERTER TO RIG C.M TO FACILITATE LINES TO FLARE & WASTE PIT.- CONNCTED LINES FROM DIVERTER TO ARAMCO PRODUCTION LINES.- R/U PUMP FLUSH LINE TO SAND FILTER UNIT & DUMP LINES FROM SAND FILTER UNIT TO WASTE PIT.- INSTALLED SENSERS AND PRESSURE GAUGES.- BHGE CONNECTED ESP CABLES TO VSD & CONTROL SYSTEM- SLB CONNECTED TRSSSV & TRFC'S CONTROL LINES TO SURFACE CONTROL SYSTEM. | 13523 |  | HTS | 08/30/2022 | ADC-58L | LIFT | ABHD-169
3388 | 14 | OOSS | Category | DOOS ID | WTST | Out of Scope Summary | WELL FLOWBACK OPERATION | 14 | 4485 | 30 Aug 1500 | 08/30/2022 | ADC-58L | Type | ABHD-169
3389
3390
3391 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADC-62L | Hrs | ANDR-589
3392 | FPMP | RIG | 3.25 | 30 Aug 2200 - 0500 | 7520 | 901517 | REPAIR MUD PUMPS - CHANGED PISTON & GASKET OF MP#1& 3. | RR | MPMP |  | 08/30/2022 | ADC-62L | 3.25 | ANDR-589
3393 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADES-173 | Hrs | UTMN-1952
3394 | FOT | RIG | 3 | 30 Aug 1800 - 2100 | 10404 | 901494 | TOP DRIVE SAVER SUB LEAKING. | RR | TDS |  | 08/30/2022 | ADES-173 | 3 | UTMN-1952
3395 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADES-174 | Hrs | GHZL-72
3396 | SFHS | BFW | 200.25 | 22 Aug 0530 - 2130 | 11165 | 901031 | AFTER MILLING 4-1/2" HALL VERSA FLEX LINER HGR, ATTEMPT TO POH, STRING STALLED WITH 30 KLBS OVERPULL, UNABLE TO MOVE UP/DOWN & ROTATION RESTRICTED. | STUK | FISHT |  | 08/30/2022 | ADES-174 | 16.5 | GHZL-72
3397 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADES-889 | Hrs | HRDH-2122
3398 | FOT | BHI | 48.75 | 28 Aug 0245 - 0500 | 11160 | 901383 | HAD NO COMMUNICATION WITH BAKER RSS TOOL | BHA | RSS |  | 08/30/2022 | ADES-889 | 24 | HRDH-2122
3399 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADM-262 | Hrs | MRJN-446
3400 | XTRI | RIG | 2 | 30 Aug 1200 - 1400 | 450 | 901492 | ADES UNABLE TO RUN POWER TONG EFFICIENTLY, UNABLE TO CONFIGURE TOOL TO BREAK OUT X-OVERS AND COMPLETION COMPONENTS. | JF | CTRQ |  | 08/30/2022 | ADM-262 | 2 | MRJN-446
3401 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ADM-655 | Hrs | SFNY-183
3402 | OTH | RIG | 48 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 08/30/2022 | ADM-655 | 24 | SFNY-183
3403 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ENS-108 | Hrs | ZULF-2015
3404 | GRF | RIG | 192 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/30/2022 | ENS-108 | 24 | ZULF-2015
3405 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | ENS-141 | Hrs | MRJN-3027
3406 | FOT | RIG | 1.5 | 30 Aug 0745 - 0915 | 2055 | 901495 | TDS HPU OVER HEATED, UNABLE TO BREAK OUT STAND, CIRCULATE HOLE AND RECIPROCATE PIPE WHILE TROUBLESHOOTING AND COOLING DOWN SAME . | RR | TDS |  | 08/30/2022 | ENS-141 | 1.5 | MRJN-3027
3407 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | HI-5 | Hrs | MHRH-57
3408 | FOT | RIG | 3 | 30 Aug 1500 - 1800 | 8627 | 901499 | CHANGE IBOP AND FUNCTION TEST. | RR | TDS |  | 08/30/2022 | HI-5 | 3 | MHRH-57
3409 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | HWU-1 | Hrs | HMYM-431414
3410 | FOT | RIG | 34 | 29 Aug 1615 - 0215 | 0 | 901393 | UNABLE TO SCOPE UP GIN POLE | RR | CBLK |  | 08/30/2022 | HWU-1 | 21.25 | HMYM-431414
3411 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | NA-18S | Hrs | SDGM-444
3412 | FPMP | RIG | 1 | 30 Aug 1715 - 1815 | 11165 | 901506 | WORK ON MUD PUMP. | RR | MPMP |  | 08/30/2022 | NA-18S | 1 | SDGM-444
3413 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | NBR-115S | Hrs | SDGM-1221
3414 | FOT | SDM | 38 | 29 Aug 1045 - 0145 | 6554 | 901456 | NOTICED DRILL STRING PRESSURE DROP AND MWD TURBINE SPEED SLOWING. | BHA | MWD |  | 08/30/2022 | NBR-115S | 19.75 | SDGM-1221
3415 | FOT | NRC | 3.25 | 30 Aug 0145 - 0500 | 740 | 901518 | OBSERVE NAPESCO CRT HYD HOSES LEAKING, FIX SAME. | TF | CRT |  | 08/30/2022 | NBR-263S | 3.25 | QTIF-736
3416 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | NBR-263S | Hrs | QTIF-736
3417 | STBH | ARM | 412.5 | 29 Jul 0230 - 1300 | 13970 | 900313 | GOT STG STUCK AFTER OPEN BOP FOR WELL OBSERVATION, WELL STATIC, TRIED TO MOVE STG W/O SUCCESS & WORK ON STUCK, CUT PIPE & PLAN TO ST. | STUK | BHA |  | 08/30/2022 | NBR-263S | 8 | QTIF-736
3418 | FOT | NRC | 3.25 | 30 Aug 0145 - 0500 | 740 | 901518 | OBSERVE NAPESCO CRT HYD HOSES LEAKING, FIX SAME. | TF | CRT |  | 08/30/2022 | NBR-263S | 3.25 | QTIF-736
3419 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | NBR-633S | Hrs | HRDH-1911
3420 | FOT | SPS | 1.5 | 30 Aug 0200 - 0330 | 140 | 901500 | WHILE TESTING MWD TOOL (DGWD), HAD NO COMMUNICATION WITH TOOL. | BHA | MWD |  | 08/30/2022 | NBR-633S | 1.5 | HRDH-1911
3421 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | PA-218S | Hrs | HRDH-1976
3422 | FOT | RIG | .5 | 30 Aug 2030 - 2100 | 510 | 901523 | TRIP TANK PUMP FAILURE, REPAIR SAME & FIXED LEAKS IN FILL UP LINE. | RR | HSYS |  | 08/30/2022 | PA-218S | .5 | HRDH-1976
3423 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SDA | Hrs | MRJN-653
3424 | FOT | SCD | 7.25 | 30 Aug 2145 - 0500 | 314 | 901524 | UNABLE TO SURVEY AT SHOE DUE TO BAD DECODING. CYCLE PUMPS AND TROUBLESHOOTING SCIENTIFIC GYRO TOOL, CHANGE PRESSURE SENSOR, CHANGE MWD SURFACE BOX. APPLY DIFFERENT GPM AND FREQUENCY BANDS. ATTEMP TO CHANGE TOOL FREQUENCY - NO SUCCESS. POOH TO CHECK AND CHANGE GWD TOOLS. | SURV | GYRO |  | 08/30/2022 | SDA | 7.25 | MRJN-653
3425 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SINO-33L | Hrs | HRDH-1542
3426 | FOT | RIG | 203.5 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/30/2022 | SINO-33L | 24 | HRDH-1542
3427 |  | 901521 | RTW | OTH | 4406 | 0 | RAWABI SURGE TANK OVERLOADED DURING CT C/O JOB, STOP PUMP & POH CT TO SURFACE, TROUBLESHOOTING, FOUND TRANSFER PUMP NOT WORKING PROPERLY, FIX AND RESUME OPERATION. |  | TF | 0 | 08/30/2022 | SINO-37L | NA | HWYH-114
3428 |  |  | RTW | OTH | 4406 | 0 | RESUME RIH CT WASH DOWN WITH 3.5" WFD CLEAN OUT ASSY TO 300 FT, HAD SURGE TANK OVERLOADED AGAIN, POOH CT TO SURFACE. TROUBLESHOOTING, FOUND SAND/ SCALE INSIDE RAWABI CHOCK MANIFOLD, SECURE WELL. DISCISSION HAS BEEN TAKEN TO USE DE-SANDER. |  |  | 0 | 08/30/2022 | SINO-37L | NA | HWYH-114
3429 |  |  | RTW | OTH | 4406 | 0 | HELD MEETING WITH RAWABI TEAM ON LOCATION AND DISSCUSED REQUIRED EQUIPMENT AND LAYOUT, DISCONNECT RAWABI SURFACE LINE AND PREPARE LOCATION FOR NEW RAWABI LAY OUT MEANWHILE MOBILIZING DE-SANDER.* DE SANDER & FLUSHING PUMP ON LOCATION AT 20:00 HRS. FOUND MESSING SURFACE HRAD LINES TO CONNECT RECEIVED EQUIPMENT.* SPOT DE-SANDER ON PLANNED POISTION @ 21:00 HRS. |  |  | 0 | 08/30/2022 | SINO-37L | NA | HWYH-114
3430 |  | 901522 | RTW | OTH | 4406 | 0 | SURFACE HARD LINES AND CONNECTIONS ON LOCATION @ 02:00. FOUND MISSISNG SOME BOLTS AND NUTS FOR CONNECTION (CHECK AVILABILITY OF SAME, NOT AVAILABLE ON RIG LOCATION)* R/U DE SANDER, CONNECT FLUSH PUMP AND SURFACE LINES MEANWHILE WAIT TO RECEIVE MISSING BOLTS AND NUTS. |  | WO | 0 | 08/30/2022 | SINO-37L | NA | HWYH-114
3431 | MATL | RWC | 8 | 30 Aug 2100 - 0500 | 0 | 901522 | WHEN SEND DE-SANDER FOUND MISSING OF SURFACE LINES AND RELATED BOLTS AND NUTS. | WO | NA |  | 08/30/2022 | SINO-37L | 8 | HWYH-114
3432 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SINO-37L | Hrs | HWYH-114
3433 | FOT | RWC | 2.5 | 30 Aug 0500 - 0730 | 0 | 901521 | SURGE TANK OVERLOADED DURING CT C/O JOB, TROUBLESHOOTING FOUND TRANSFER PUMP NOT WORKING PROPERLY. | TF | CHK |  | 08/30/2022 | SINO-37L | 2.5 | HWYH-114
3434 | MATL | RWC | 8 | 30 Aug 2100 - 0500 | 0 | 901522 | WHEN SEND DE-SANDER FOUND MISSING OF SURFACE LINES AND RELATED BOLTS AND NUTS. | WO | NA |  | 08/30/2022 | SINO-37L | 8 | HWYH-114
3435 | 114 | OOS | Category | DOOS ID | DCOM | Out of Scope Summary | RETREIVE PX PLUG STACK IN X-NIPPLE, INSTALLED BY PRODUCTION TO SECURE THE WELL DURING CELLAR INSTALATION. | 24 | 4406 | 26 Aug 1100 | 08/30/2022 | SINO-37L | Type | HWYH-114
3436
3437
3438 | 5060 | 4641 | TO | E | 4385 | STDP | POOH CONTROLLED SPEED WITH CORE ASSY #6 ON 5" DP STD'S TO CSG SHOE.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 5060 | 5060 | RIG | 08/30/2022 | SINO-46L | CORE | SHYB-270
3439 | 5060 | 621 | TO | E | 4385 | STDP | HPJSM, POOH CONTROLLED SPEED WITH CORE ASSY #6 ON 5" DP STD'S TO TOP OF BHA.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC. | 5060 | 4641 | RIG | 08/30/2022 | SINO-46L | CORE | SHYB-270
3440 | 5060 |  | HT | E | 4385 | CORC | HPJSM, CONTD POOH WITH 8-1/2" CORPRO CORING ASSY #6 TO SURFACE CONTROLLED SPEED.** RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.** ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.** L/D INNER BARRELS, 80' RECOVERED (100 % RECOVERY) FROM CORE #6** CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 5060 |  | CPR | 08/30/2022 | SINO-46L | CORE | SHYB-270
3441 | 5060 |  | HT | E | 4385 | CORC | HPJSM, P/U & M/U 8-1/2" CORPRO CORING ASSY RUN #7 (80' CORE BARREL). ** 8-1/2" CORE HEAD + 7-1/8" CORE OUTER BARRELS & 4-1/2" INNER BARRELS + FLOAT SUB W/ FLOAT VALVE+15 X 6-1/2" DC'S+ 6-1/2" DRILLING JAR+2 X 6 1/2" DC'S +XO+ PBL + DP'S | 5060 |  | CPR | 08/30/2022 | SINO-46L | CORE | SHYB-270
3442 | 5060 | 5060 | TI | E | 4385 | STDP | RIH WITH 8-1/2" CORPRO CORING ASSY #6 CONTROLLED SPEED FROM 621' TO 5060'.** PASSED 9-5/8" DV FREELY.** GENTLY PASSED SHOE TRACK.** WASH DOWN LAST STAND TILL TAGGED BTM GENTLY. | 5060 | 621 | RIG | 08/30/2022 | SINO-46L | CORE | SHYB-270
3443 | 5060 |  | CIRC | E | 4385 | MPMP | CIRCULATE BTMS UP, ACTIVATED DIVERTING BALL, PUMP DOWN WITH 400 GPM & WAIT TILL DIVERT FLUID AWAY FROM THE INNER BARREL TO START CORING ACROSS SHYB FORMATION.-CONFIRM SPACE OUT FOR CUTTING THE CORE. -RECORD SPR'S, P/U AND S/O WT'S, TORQUE READINGS | 5060 |  | RIG | 08/30/2022 | SINO-46L | CORE | SHYB-270
3444 | 5140 |  | CORE | E | 4385 | CORC | CUT 8-1/2" X 4" CORE #7 FROM 5060' TO 5140' W/77 PCF AOM & FULL 100% RETURNS.** CORING PARAMETERS: ** WOB: 5-10 KLBS. GPM: 175 - 185 , SPP: 280-320 PSI. RPM: 60-65, TRQ: 2-4 KLB | 5060 |  | CPR | 08/30/2022 | SINO-46L | CORE | SHYB-270
3445 | 5140 |  | CIRC | E | 4385 | MPMP | BREAK OFF CORE #7 AS PER CORE ENG WITH 5 KLB OVERPULL , PUMP OUT TO CORE POINT @ 5060 ', CIRC BTM/UP.** FLOW CHECK WELL STATIC | 5140 |  | RIG | 08/30/2022 | SINO-46L | CORE | SHYB-270
3446 | 5140 | 4641 | TO | E | 4385 | STDP | POOH CONTROLLED SPEED WITH CORE ASSY #7 ON 5" DP STD'S TO CSG SHOE.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC | 5140 | 5140 | RIG | 08/30/2022 | SINO-46L | CORE | SHYB-270
3447 | 5140 | 3700 | TO | E | 4385 | STDP | HPJSM, POOH CONTROLLED SPEED WITH CORE ASSY #7 ON 5" DP STD'S TO 4000'.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC | 5140 | 4641 | RIG | 08/30/2022 | SINO-46L | CORE | SHYB-270
3448 | 139 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | 8-1/2" CORING OPERATION | 24 | 4385 | 25 Aug 0045 | 08/30/2022 | SINO-46L | Type | SHYB-270
3449
3450
3451 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SP-154 | Hrs | SDGM-353
3452 | FOT | TOD | 154.5 | 23 Aug 0700 - 1100 | 7267 | 901232 | UNABLE TO CLOSE HYDRO SEAL DURING CEMENTING OFF BOTTOM LINER CAUSING FAILED PRESSURE TEST, | TF | DV |  | 08/30/2022 | SP-154 | 6 | SDGM-353
3453 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SP-261 | Hrs | MHWZ-903
3454 | FOT | ITS | 1 | 30 Aug 0230 - 0330 | 202 | 901516 | WHILE CHAGING POWER TONG DIES ITS CREW ENCOUNTERED ISSUES WITH DAMAGED RETAINER PIN. | TF | CTRQ |  | 08/30/2022 | SP-261 | 1 | MHWZ-903
3455 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SP-306 | Hrs | MNIF-192
3456 | FOT | MSD | 1 | 30 Aug 2300 - 0000 | 8230 | 901514 | REPLACE AL-MASOOD CSG POWER TONG | TF | CTRQ |  | 08/30/2022 | SP-306 | 1 | MNIF-192
3457 | 6769 | 6564 | LOG | E | 4405 | WLT | COMPLETED STATION#2,SAMPLE POINT@ 6564' (AD3B).- ACTIVATED STRADDLE PKR'S & PUMP OUT STATION#2 @ 6564'.- PUMP OUT 7 LITRES OF FORMATION WATER, 132 LITERS OIL, TAKE 1 BOTTLE OF 500CC FLUID SAMPLE OIL. - TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE- 0.87 BBLS (WATER: 0.04 BBLS - OIL: 0.83 BBLS)- DEACTIVATE STRADDLE PKR'S , MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6564 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3458 | 6769 | 6496 | LOG | E | 4405 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 6496' (STATION#3 PUMP OUT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6564 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3459 | 6769 | 6496 | LOG | E | 4405 | WLT | STATION#3 ,PUMP OUT POINT @ 6496' (AD3A) : - ACTIVATE DXL PROBE & PUMP OUT STATION #3 @ 6496'.- PUMP OUT 21 LITRES OF FIILTRATED FLUID .- OBSERVED LOW MOBILITY AND TOOLS NOT SUCK WITH HIGH RATE. - TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE FROM BOTH CYCLES - 1.00 BBLS (WATER: 0.17 BBLS - OIL: 0.83 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6496 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3460 | 6769 | 6499 | LOG | E | 4405 | WLT | POSITION STRING AT STATION#4 ,PUMP OUT POINT@ 6499'(AD3A),SELECTED BY RDD.- ACTIVATED DXL & PUMP OUT STATION#4 @ 6499'.- PUMP OUT 27.3 LITRES FIILTRATED FLUID, 63.7 LITERS OIL. - TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE FROM BOTH CYCLES - 1.57 BBLS (WATER: 0.34 BBLS - OIL: 1.23 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6499 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3461 | 6769 | 6490 | LOG | E | 4405 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 6490' (STATION#5 SAMPLE POINT).PERFORM STICKY TENDENCY TEST FOR 15 MIN &1 HR - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6499 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3462 | 6769 | 6490 | LOG | E | 4405 | WLT | STATION#5, SAMPLE POINT @ 6490' (2B13): - ACTIVATE DXL PROBE & PUMP OUT STATION #5 @ 6490'.- PUMP OUT 18 LITRES FIILTRATED FLUID, 162 LITRES FORMATION WATER . - TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE-2.7 BBLS (WATER: 1.47 BBLS - OIL: 1.23 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6490 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3463 | 6769 | 6480 | LOG | E | 4405 | WLT | POOH W/ LOG TOOLS & POSITION STRING @ 6480' (STATION#5 SAMPLE POINT).- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6490 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3464 | 6769 | 6480 | LOG | E | 4405 | WLT | STATION#6 ,SAMPLE POINT @ 6480' (2B11): - ACTIVATE DXL PROBE & PUMP OUT STATION #6 @ 6480'.- PUMP OUT 6.5 LITRES OF FIILTRATED FLUID, 32.5 LITRES OF FORMATION WATER, 91 LITERS OIL.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 3.51 BBLS (WATER: 1.71 BBLS - OIL: 1.80 BBLS).- RDD DECIDED TO GO FOR CYCLE #2 TO COLLECT SIMPLE- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6480 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3465 | 6769 | 6480 | LOG | E | 4405 | WLT | STATION#6 ,SAMPLE POINT @ 6480' (2B11) CYCLE#2: - ACTIVATE DXL PROBE & PUMP OUT STATION #6 @ 6480'.- PUMP OUT 5 LITRES OF FIILTRATED FLUID, 23 LITRES OF FORMATION WATER, 84 LITERS OIL,TAKE 1 BOTTLE OF 500CC FLUID SAMPLE AS PER RDD- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 4.20 BBLS (WATER: 1.88 BBLS - OIL: 2.32 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED.- 52.5 HRS SINCE LAST CIRCUATION @ LATCH DEPTH.- 69 HRS SINCE LAST CIRCULATION W/ REAMING BHA AT BTM. | 6769 | 6480 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3466 | 6769 | 6727 | LOG | E | 4405 | WLT | RIH WITH LOGGING TOOL STRING TO BOTTOM @ 6727'.- MONITOR WELL THRU TRIP TANK, STATIC. | 6769 | 6480 | BAW | 08/30/2022 | SP-53L | LOG | HRDH-528
3467 | 6769 |  | CIRC | E | 4405 | MPMP | CIRCULATE 30 BBL UNTIL GET FORMATION FLUID (WATER: 1.88 BBLS - OIL: 2.32 BBLS) INSIDE 9-5/8" CSG SHOE. | 6769 |  | RIG | 08/30/2022 | SP-53L | LOG | HRDH-528
3468 | 6769 | 6267 | ST | E | 4405 | STDP | POOH W/ BHI PCL LOGGING RUN#2: (GR-RCX--IFX-WGI ) TO SES DEPTH @6267.........ON GOING | 6769 | 6727 | RIG | 08/30/2022 | SP-53L | LOG | HRDH-528
3469 | 74.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RECORDING (ADEX-MREX-MLL) LOG & RUN #2:(GR-RCX-IFX-WGI) LOG AS PER PLAN | 24 | 4405 | 27 Aug 1015 | 08/30/2022 | SP-53L | Type | HRDH-528
3470
3471
3472 | FOT | RIG | 3 | 30 Aug 1100 - 1400 | 0 | 901496 | OBSERVED LEAK IN KELLY HOSE WHILE STANDPIPE PRESSURE TEST, REPLACED WITH NEW ONE, PRESSURE SAME, OK. | RR | KELLY |  | 08/30/2022 | SP-58 | 3 | HRDH-795
3473 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SP-58 | Hrs | HRDH-795
3474 | FOT | RIG | 28 | 29 Aug 0700 - 1100 | 0 | 901397 | WHILE PERFORM ANNULAR BOPE TEST, OBSERVED PRESSURE DROP AND LEAK FROM ANNULAR TOP SIDE, RETRIEVED DAMAGED ANNULAR PKR ELEMENT AND OBSERVED SCRATCH ON INNER ANNULAR BODY. | BOP | BOP |  | 08/30/2022 | SP-58 | 6 | HRDH-795
3475 | FOT | RIG | 3 | 30 Aug 1100 - 1400 | 0 | 901496 | OBSERVED LEAK IN KELLY HOSE WHILE STANDPIPE PRESSURE TEST, REPLACED WITH NEW ONE, PRESSURE SAME, OK. | RR | KELLY |  | 08/30/2022 | SP-58 | 3 | HRDH-795
3476 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SSA-101 | Hrs | QTIF-785
3477 | FOT | SJT | 16.5 | 30 Aug 0500 - 2130 | 3850 | 901497 | LOST COMMUNICATION W/ PLT TOOLS DUE TO TAQA CABLE HEAD JUMPER BURNED AND FOUND WATER INSIDE, POOH AND CHANGED THE CABLE HEAD. | TF | CTBG |  | 08/30/2022 | SSA-101 | 16.5 | QTIF-785
3478 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SSA-102 | Hrs | QTIF-693
3479 | FOT | RIG | 18.5 | 30 Aug 0800 - 0230 | 3010 | 901472 | FOUND MOUNTING PLATE EYE FOR HANDLER LOCKING CYLINDER WAS BROKEN | RR | TDS |  | 08/30/2022 | SSA-102 | 18.5 | QTIF-693
3480 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SSA-29 | Hrs | QTIF-423
3481 | GRF | RIG | 15.5 | 29 Aug 1500 - 0500 | 12700 | 901394 | FAILURE OF THE ANTI COLLISION SENSOR | UPRA | DWKS |  | 08/30/2022 | SSA-29 | 10.5 | QTIF-423
3482 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SSA-5820 | Hrs | MSBA-1
3483 | FOT | RIG | 4.5 | 30 Aug 0030 - 0500 | 1414 | 901519 | RIG CRANE BROKE DOWN. UNABLE TO LAYDOWN BHA COMPONENTS. | RR | CRN |  | 08/30/2022 | SSA-5820 | 4.5 | MSBA-1
3484 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SSA-5859 | Hrs | HWYH-1217
3485 | MATL | RIG | 2 | 30 Aug 2230 - 0030 | 880 | 901512 | EXCESS TIME WHILE SPACE OUT FOR ISC DUE TO NON-AVAILABILITY OF 5' (X2) & 10' (X1) DP PUP JOINTS. | WO | NA |  | 08/30/2022 | SSA-5859 | 2 | HWYH-1217
3486 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SSA-5892 | Hrs | AWTD-141400
3487 | FOT | RIG | 121 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 08/30/2022 | SSA-5892 | 24 | AWTD-141400
3488 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | SSA-5962 | Hrs | HRDH-2513
3489 | FOT | GOC | 2 | 30 Aug 1600 - 1800 | 206 | 901498 | REPAIR ON AL-GHAITH POWER UNITS & TONGS. | TF | TTRQ |  | 08/30/2022 | SSA-5962 | 2 | HRDH-2513
3490 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/30/2022 | T914 | Hrs | UTMN-415
3491 | FOT | SPS | 2.5 | 30 Aug 0230 - 0500 | 12520 | 901513 | MWD LOST SIGNAL. | BHA | MWD |  | 08/30/2022 | T914 | 2.5 | UTMN-415
3492 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | 095TE | Hrs | MNIF-126
3493 | FRFM | ARM | 75 | 28 Aug 1030 - 1500 | 6100 | 901348 | CURE LOSSES AT SFNY FORMATION WITH LCM PILL AND CMT PLUG. | LCIR | NA |  | 08/31/2022 | 095TE | 10 | MNIF-126
3494 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ADC-17 | Hrs | ZULF-1385
3495 | FOT | RIG | 1 | 31 Aug 0300 - 0400 | 0 | 901554 | OBSERVED DAMAGE IN KELLY HOSE | RR | CSYS |  | 08/31/2022 | ADC-17 | 1 | ZULF-1385
3496 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ADC-34 | Hrs | UTMN-2309
3497 | FOT | RIG | 2 | 31 Aug 1330 - 1530 | 9994 | 901537 | REPAIR LEAKING KELLY HOSE. | RR | CSYS |  | 08/31/2022 | ADC-34 | 2 | UTMN-2309
3498 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ADC-35 | Hrs | MAQL-5
3499 | FOT | HCB | 52.5 | 29 Aug 0030 - 0500 | 5915 | 901459 | AFTER PLT LOGGING ANALYSIS, FOUND COMMUNCATION BETWEEN TOP AND BTTM OF BRIDGE PLUG. | TF | BP |  | 08/31/2022 | ADC-35 | 24 | MAQL-5
3500 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ADC-55L | Hrs | UTMN-3171
3501 | ORDS | TK3 | 39 | 30 Aug 1400 - 0500 | 10968 | 901520 | WAITING ON FINAL INVESTIGATION REPORT FOR AUG 23, 2022 BOP LEAK | WO | NA |  | 08/31/2022 | ADC-55L | 24 | UTMN-3171
3502 |  |  | HTS | OTH | 4485 | 13523 | CONT. R/U HALL EQPT FOR FLOW BACK OPERATION.- R/U MANUAL VALVE BEFORE T-BLOCK TO RIG KILL LINE.- R/U SSV AND CONNECTED LINES TO SAND FILTER.- R/U SAND FILTER UNIT AND CONNECTED TO HALL CHOKE MANIFOLD.- CONNECTED HALL DIVERTER TO RIG C.M TO FACILITATE LINES TO FLARE & WASTE PIT.- CONNCTED LINES FROM DIVERTER TO ARAMCO PRODUCTION LINES.- R/U PUMP FLUSH LINE TO SAND FILTER UNIT & DUMP LINES FROM SAND FILTER UNIT TO WASTE PIT.- INSTALLED SENSERS AND PRESSURE GAUGES. |  |  | 13523 | 08/31/2022 | ADC-58L | NA | ABHD-169
3503 |  |  | HTS | OTH |  | 13523 | 2 HRS REPORTED FOR IN SCOPE OPERATION WHERE THE RIG UP & TEST LINE WHILE FUNCTION TEST ESP AS PER PROGRAM IS IN SCOPE. |  |  | 13523 | 08/31/2022 | ADC-58L | NA | ABHD-169
3504 |  |  | RIG | PJSM | 4485 | 13523 | HPJSM FOR PRESSURE TEST. DISCUSS THE RED ZONE & BARRICADED AREA POLICY. JSA & RISK ASSOCIATED |  |  | 13523 | 08/31/2022 | ADC-58L | NA | ABHD-169
3505 |  | 901536 | HTS | OTH | 4485 | 13523 | INITIATED TO FLUSH THE LINES FOR HALL. WELL TESTING EQPT OBSERVED LEAK FROM DIFFERENT PLACES, FIX SAME AND FLUSHED THE LINE.- STARTED TO P/T DOWNSTREAM OBSERVED MANY CONNECTIONS WERE LEAKING FOR LOW AND HIGH PRESSURE.- TROUBLESHOOTING SSV FROM CONTROL PANNEL, DISCOVERED ACTUATOR IS INTERNALY LEAKING AND NEEDS TO BE CHANGED. CHANGED ACTUATOR, F/T SSV & ESD, OK.- VERY POOR ACTION FROM HALL TEAM TO PERFORM THE TEST AND FIX THE LEAKING CONNECTIONS. |  | TF | 13523 | 08/31/2022 | ADC-58L | NA | ABHD-169
3506 |  |  | HTS | OTH | 4505 | 13523 | P/T HALL WELL TESTING EQPT, FLUSHED TESTING LINES W/ WATER F/ KILL LINE TO HALL SAND FILTER & FLARE PIT.- P/T UP STREAM LINES, DOWN/UP STREAM VALVES UP TO 300/ 2500 PSI FOR 10 MIN EACH, HOLD OK.- P/T DOWN STREAM LINES AGAINST PRODUCTION ISOLATING VLV UP TO 300/1200 FOR 10 MIN EACH, HOLD OK.- P/T UPSTREAM LINE AGAINST SSV (IN CLOSED POSITION) UP TO 300/2500 PSI, 10 MIN EACH HOLD OK. |  |  | 13523 | 08/31/2022 | ADC-58L | NA | ABHD-169
3507 |  |  | TK3 | PJSM |  | 13523 | HPJSM, FOR ALL POB, EXPLAINED UPCOMING PLAN FOR FUNCTION TEST, HIGHLIGHTED RISKS AND ITS MITIGATIONS. |  |  | 13523 | 08/31/2022 | ADC-58L | NA | ABHD-169
3508 |  |  | SGR | OTH |  | 13523 | OPENED LMV, SLB OPENED TRSSSV AND CYCLED BOTH ICV'S 1 & 2 IN OPEN POSITION. |  |  | 13523 | 08/31/2022 | ADC-58L | NA | ABHD-169
3509 |  |  | BAL | OTH |  | 13523 | F/T BHGE ESP AS FOLLOW:- LINED UP FLOW THRU HALL CHOKE. SLOWLY OPEN UP CHOKE (24/64-32/64) & INCREASED ESP FREQUENCY. (45-50 HRTZ)WHP (658-1000 PSI), DOWN STREAM PRESS (100-575 PSI)- MONITORED TCA & BLEED OFF PRESSURE SLOWLY TO MAINTAIN 300-600 PSI AS PER BHGE. MONITORED WELL HEAD PRESSURE, CHECKED PRODUCED SAMPLE EVERY 30 MINS. OBSERVED OIL% INCREASED, OIL% @ RPT 95%.- TOTAL FLUID VOLUME PUMPED TO ARAMCO PRODUCTION LINE IS 680 BBLS. |  |  | 13523 | 08/31/2022 | ADC-58L | NA | ABHD-169
3510 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ADC-58L | Hrs | ABHD-169
3511 | XTTE | HTS | 7.5 | 31 Aug 0930 - 1700 | 13523 | 901536 | PRIOR FUNCTION TEST ESP AND FLOW BACK TYHE WELL, OBSERVED LEAK FROM DIFFERENT PLACES OF HALL WELL TESTING EQPT, FIX SAME AND FLUSHED THE LINE. - STARTED TO P/T DOWNSTREAM, OBSERVED MANY CONNECTIONS WERE LEAKING FOR LOW AND HIGH PRESSURE. - VERY POOR ACTION FROM HALL TEAM TO PERFORM THE TEST AND FIX THE LEAKING CONNECTIONS. | TF | TESTT |  | 08/31/2022 | ADC-58L | 7.5 | ABHD-169
3512 | 4 | OOS | WTST | 4485 | PTST | R/U HALLIBURTON WELL TESTING EQUIPMENT AND LINES. | PRESSURE TESTING WELL TESTING EQUIPMENT AND LINES WITH RIG MUD PUMPS | 4 | 4505 | 31 Aug 1700 | 08/31/2022 | ADC-58L | OOSS | ABHD-169
3513
3514
3515
3516 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ADES-13 | Hrs | HWYH-163
3517 | FRFM | ARM | 74.5 | 28 Aug 1300 - 0445 | 7809 | 901462 | SEVERE LOSSES WHILE CEMENT 4-1/2" OBL DUE TO FORMATION CATACHRESTIC. | CMT | NA |  | 08/31/2022 | ADES-13 | 23.75 | HWYH-163
3518 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ADES-889 | Hrs | HRDH-2122
3519 | FOT | BHI | 51.5 | 28 Aug 0245 - 0745 | 11160 | 901383 | HAD NO COMMUNICATION WITH BAKER RSS TOOL | BHA | RSS |  | 08/31/2022 | ADES-889 | 2.75 | HRDH-2122
3520 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ADM-655 | Hrs | SFNY-183
3521 | OTH | RIG | 72 | 29 Aug 0500 - 0500 | 0 | 901309 | UN PLANNED MAINTENANCE TO FIX ONE OF STBD LEG BRACES HAVE BEEN PARTED WHILE PRELOADING. | UPRA | NA |  | 08/31/2022 | ADM-655 | 24 | SFNY-183
3522 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ARO-3003 | Hrs | SFNY-1159
3523 | FOT | RIG | 1 | 31 Aug 0400 - 0500 | 1733 | 901572 | UNABLE TO BREAKING OUT TIGHT CONNECTION WITH TDS, UPPER IBOP BROKE OUT FROM QUILL SHAFT. | RR | TDS |  | 08/31/2022 | ARO-3003 | 1 | SFNY-1159
3524 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | BB-84A | Hrs | MRJN-581
3525 | FOT | RIG | .75 | 31 Aug 1730 - 1815 | 13501 | 901548 | LEAKING HYDRAULIC LINE | RR | HSYS |  | 08/31/2022 | BB-84A | .75 | MRJN-581
3526 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | DQ-47 | Hrs | KHRS-280
3527 | MATL | TK2 | 64 | 28 Aug 2100 - 1300 | 12026 | 901473 | ADITION REAMING TRIP WHILE WAITING ON LOWER COMPLETION EQUIPMENT. | WO | NA |  | 08/31/2022 | DQ-47 | 8 | KHRS-280
3528 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ED-85A | Hrs | ZULF-2066
3529 | OTH | RIG | 27.5 | 29 Aug 0730 - 2200 | 0 | 901414 | DUE TO SKID ENGINE CAPABILITY, RIG CANNOT PERFORM TRANSVERSE SKID WITH MORE THAN 100 KLB DRILL STRG WEIGHT ON DERRICK. AS PER RIG CONTRACT, RIG CAPABLE TO TRANSVERSE SKID WITH 250 KLB. | UPRA | NA |  | 08/31/2022 | ED-85A | 14 | ZULF-2066
3530 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ENS-108 | Hrs | ZULF-2015
3531 | GRF | RIG | 216 | 23 Aug 0500 - 0500 | 7186 | 901163 | UNABLE TO ENGAGE BREAKER FOR VFD #2 DUE TO THE UV TRIP NOT GETTING SIGNAL FROM PLC. THE PLC IS GETTING INPUT SIGNAL BUT NO OUTPUT TO THE UV TRIP ON BREAKER. | UPRA | PSYS |  | 08/31/2022 | ENS-108 | 24 | ZULF-2015
3532 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | ENSCO-76 | Hrs | MRJN-2004
3533 | FOT | RIG | 8 | 31 Aug 1530 - 2330 | 0 | 901560 | WHILE P/T BOP, OBSERVE LEAKAGE AT KILL LINE MANIFOLD SIDE, RE-TIGHTEN CONNECTION, NO SUCCESS, REPLACED RING GASKET WITH NEW ONE & TORQUED CONNECTION. | BOP | BOP |  | 08/31/2022 | ENSCO-76 | 8 | MRJN-2004
3534 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | JACK-202 | Hrs | THRY-829
3535 | FOT | RIG | 1.5 | 31 Aug 0600 - 0730 | 3700 | 901437 | HAD PROBLEM IN CASING M/U MANUAL TONG. | RR | SLIPS |  | 08/31/2022 | JACK-202 | 1.5 | THRY-829
3536 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | JACK-203 | Hrs | HZEM-849
3537 | OTH | RIG | 3 | 31 Aug 1730 - 2030 | 5092 | 901550 | RIG SHUT DOWN DUE HAJJAN MANAGEMENT DISHONESTY. THEY CLAIMS ALL THEIR EMPLOYEE HAVE VALID IQAMA. AFTER, CLOSE CHECKUP IT HAS BEEN FOUND THAT THEY ARE LYING REGARDING IQAMA VALIDATION. RIG WAS SHUT DOWN FOR THREE HOURS UNTIL THEY PROVIDE THE CORRECT DOCUMENTS. | UPRA | NA |  | 08/31/2022 | JACK-203 | 3 | HZEM-849
3538 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | MP-1 | Hrs | MRJN-78
3539 | FOT | NRT | 725.5 | 31 Jul 0245 - 0500 | 3000 | 900303 | NOV BULLNOSE & 4 INTERNAL HOUSING PARTS LOST IN HOLE DURING REAMING TRIP. | BHA | UNDR |  | 08/31/2022 | MP-1 | 24 | MRJN-78
3540 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SDA | Hrs | MRJN-653
3541 | FOT | SCD | 13.75 | 30 Aug 2145 - 1130 | 304 | 901524 | UNABLE TO SURVEY AT SHOE DUE TO BAD DECODING. CYCLE PUMPS AND TROUBLESHOOTING SCIENTIFIC GYRO TOOL, CHANGE PRESSURE SENSOR, CHANGE MWD SURFACE BOX. APPLY DIFFERENT GPM AND FREQUENCY BANDS. ATTEMP TO CHANGE TOOL FREQUENCY - NO SUCCESS. POOH TO CHECK AND CHANGE GWD TOOLS. | SURV | GYRO |  | 08/31/2022 | SDA | 6.5 | MRJN-653
3542 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SINO-33L | Hrs | HRDH-1542
3543 | FOT | RIG | 227.5 | 22 Aug 1300 - 0500 | 1396 | 901172 | WHILE DRILLING, THE ADJUSTABLE PLATE PARTED AND TDS MONORAIL SLIP DOWN ON RIG FLOOR IN VERTICAL POSITION | RR | TDS |  | 08/31/2022 | SINO-33L | 24 | HRDH-1542
3544 |  | 901522 | GDM | OTH | 4406 | 0 | CONTINUE WAIT TO RECEIVE MISSING BOLTS AND NUTS TO COMPLETE R/U DE-SANDER, AND EMERGENCY SHUT DOWN VALVE.> BOLTS AND NUTS RECEIVED @ 09:00 AM, COMPLETE R/U AND CONNECT ALL SURFACE LINES. |  | WO | 0 | 08/31/2022 | SINO-37L | NA | HWYH-114
3545 |  | 901549 | GDM | OTH | 4406 | 0 | CONNECT THE HYDRAULIC HOSE FROM ESD CONTROL PANEL TO SSV, THE HYDRAULIC HOSE WASH WHILE INCREASING OIL PRESSURE TO OPEN SSV.* WAIT ON RAWABI TO MOBILIZE NEW HYDRAULIC HOSE TO CONNECT THE SSV WITH ESD CONTROL PANEL MEANWHILE RAWABI P/T SURFACE LINE UPSTREAM 2500 PSI FOR 10 MIN AND DOWNSTREAM 100 PSI FOR 10 MIN.* HYDRAULIC HOSE ON LOCATION @ 18:00 HRS.* MAKE UP RECEIVED HYDRAULIC HOSE, FUNCTION TEST SSV FROM ESD CONTROL PANEL - OK. |  | TF | 0 | 08/31/2022 | SINO-37L | NA | HWYH-114
3546 |  |  | GDM | OTH | 4406 | 0 | HPJSM, RESUME RIH CT WASH DOWN WITH 3.5" WFD C/O ASSY. FROM SURFACE TILL TAG AT 2,055' ODF (CT DEPTH) WITH 82 PCF BRINE WITH 1.7- 2 BPM @ 4,900 PSI.> CLEANING SPEED: 10 FT/MIN.> PULL TEST CT EVERY 200 FT.> TCA: 0 PSI.> TAKE RETURNS THRU RAWABI DESANDER & CHOCK: CHOKE SIZE: 94/64", UPSTREAM PRESSURE: 100 PSI , DOWNSTREAM PRESSURE: 30-50 PSI. |  |  | 0 | 08/31/2022 | SINO-37L | NA | HWYH-114
3547 |  |  | GDM | OTH | 4406 | 0 | SWEEP TUBING WITH 10 BBL HVP AND CIRCULATE WITH 82 PCF BRINE WITH 1.9 BPM @ 4750 PSI.> PERFORM PULL TEST 10 MIN WHILE CIRCULATION.> TCA: 0 PSI.> TOTAL SAND/ SCALE HAS BEEN RECOVERED FROM DE-SANDER: 15 KG. |  |  | 0 | 08/31/2022 | SINO-37L | NA | HWYH-114
3548 |  |  | GDM | OTH | 4406 | 0 | CT POOH TO 1,850 FT, CT RIH AGAIN, TAG AT 2,045' ODF (CT DEPTH) ( 30 FT ABOVE 1ST TAG DEPTH). TRY TO PASS WITHOUT PUMP-NO SUCCESS, WASH DOWN WITH 1-1.5 BPM TILL TAG AT 2,055' ODF (CT DEPTH). |  |  | 0 | 08/31/2022 | SINO-37L | NA | HWYH-114
3549 |  |  | GDM | OTH | 4406 | 0 | CT POOH WITH 3.5" WFD CLEAN OUT ASSY. TO SURFACE ......... ONGOING @ RPT. |  |  | 0 | 08/31/2022 | SINO-37L | NA | HWYH-114
3550 | FOT | RWC | 7.5 | 31 Aug 1130 - 1900 | 0 | 901549 | WASH OUT OF HYDRAULIC HOSE BETWEEN ESD CONTROL PANEL AND SSV WHILE INCREASE PRESSURE TO OPEN THE VALVE. | TF | WTSE |  | 08/31/2022 | SINO-37L | 7.5 | HWYH-114
3551 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SINO-37L | Hrs | HWYH-114
3552 | MATL | RWC | 14.5 | 30 Aug 2100 - 1130 | 0 | 901522 | WHEN RECEIVED DE-SANDER FOUND MISSING SURFACE LINES AND RELATED BOLTS AND NUTS. | WO | NA |  | 08/31/2022 | SINO-37L | 6.5 | HWYH-114
3553 | FOT | RWC | 7.5 | 31 Aug 1130 - 1900 | 0 | 901549 | WASH OUT OF HYDRAULIC HOSE BETWEEN ESD CONTROL PANEL AND SSV WHILE INCREASE PRESSURE TO OPEN THE VALVE. | TF | WTSE |  | 08/31/2022 | SINO-37L | 7.5 | HWYH-114
3554 | 138 | OOS | Category | DOOS ID | DCOM | Out of Scope Summary | RETRIEVE PX PLUG STUCK IN X-NIPPLE, INSTALLED BY PRODUCTION TO SECURE THE WELL DURING CELLAR INSTALLATION. | 24 | 4406 | 26 Aug 1100 | 08/31/2022 | SINO-37L | Type | HWYH-114
3555
3556
3557 | 5140 | 621 | TO | E | 4385 | STDP | CONTINUE POOH CONTROLLED SPEED WITH CORE #7 ON 5" DP STD'S FROM 4000' TO TOP BHA.** MONITORED WELL ON TRIP TANK.** FLOW CHECK WELL STATIC | 5140 | 4000 | RIG | 08/31/2022 | SINO-46L | CORE | SHYB-270
3558 | 5140 |  | HT | E | 4385 | CORC | HPJSM, CONTD POOH WITH 8-1/2" CORPRO CORING ASSY #7 TO SURFACE CONTROLLED SPEED.** RUN RIG FLOOR BLOWER & CHECKING FOR H2S AT SURFACE ZERO H2S READING.** ALL CREW ON RIG FLOOR MASKED UP DURING DISCONNECTING CORE INNER BARREL.** L/D INNER BARRELS, 80' RECOVERED (100 % RECOVERY) FROM CORE #7** CORE HEAD DULL : 1-1-WT-A-X-NO-TD. | 5140 |  | CPR | 08/31/2022 | SINO-46L | CORE | SHYB-270
3559 | 5140 |  | HT | E |  | BHA | HPJSM, P/U & M/U 8-1/2" ROTARY BHA. | 5140 |  | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3560 | 5140 | 4641 | TI | N |  | STDP | RIH 8 1/2" ROTARY BHA TO 9-5/8' CS @ 4641'.** PASSED DV FREELY.** GENTLY PASSED 9-5/8" CS.** MONITOR WELL ON TRIP TANK. | 5140 | 621 | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3561 | 5140 | 5140 | RW | N |  | BIT | PRECAUTION WASH AND REAM CORING INTERVAL FROM 4660' TO BTM @ 5140'. | 5140 | 4660 | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3562 | 5163 |  | D | N |  | TDS | ROTARY DRILL 8-1/2' VH FROM 5140' TO TD @ 5163' (13' INSIDE BYDH) WITH 77 PCF AOM & FULL RETURN.** HLB MUD LOGGING COLLECTED SAMPLE EVERY 3' DRLD SHOWED TOP OF BYDH @ 5150'.** CONFIRMED TD WITH DE & RDD. | 5140 |  | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3563 | 5163 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH 50 BBLS HI VIS PILL AND CIRCULATE HOLE CLEAN.** FLOW CHECK WELL STATIC | 5163 |  | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3564 | 5163 | 4641 | TO | N |  | SPDP | POOH W/ 8-1/2" ROTARY ASSY TO 9-5/8" CS.** MONITOR WELL THROUGH TRIP TANK & TRIP SHEET.** FLOW CHECK WELL STATIC. | 5163 | 5163 | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3565 | 5163 | 5160 | TI | N |  | STDP | RIH W/ 8-1/2" ROTARY ASSY TO TD @ 5160'.** MONITOR WELL THROUGH TRIP TANK & TRIP SHEET.** WASH DOWN LAT STAND. | 5163 | 4641 | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3566 | 5163 |  | CIRC | N |  | MPMP | SWEEP HOLE WITH 50 BBLS HI VIS PILL AND CIRCULATE HOLE CLEAN.** FLOW CHECK WELL STATIC | 5163 |  | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3567 | 5163 | 4641 | TO | N |  | STDP | POOH W/ 8-1/2" ROTARY ASSY TO TOP 9-5/8" CS.** MONITOR WELL THROUGH TRIP TANK & TRIP SHEET.** FLOW CHECK WELL STATIC. | 5163 | 5160 | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3568 | 5163 | 621 | TO | N |  | STDP | POOH W/ 8-1/2" ROTARY ASSY FROM 4641' TOP BHA.** MONITOR WELL THROUGH TRIP TANK & TRIP SHEET. | 5163 | 4641 | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3569 | 5163 |  | HT | N |  | BHA | HPJSM, POOH & LD 8-1/2" ROTARY ASSY.** FLOW CHECK WELL STATIC.** BIT DULL GRADING : 2-2-WT-A-I-E-NO-TD. | 5163 |  | RIG | 08/31/2022 | SINO-46L | DRLG | SHYB-270
3570 | 5163 |  | ND | N |  | BNIP | HPJSM, L/D BELLE NIPPLE......ON-GOING @ RPT. | 5163 |  | RIG | 08/31/2022 | SINO-46L | BOP | SHYB-270
3571 | 147.5 | OOS | Category | DOOS ID | CORE | Out of Scope Summary | 8-1/2" CORING OPERATION | 8.5 | 4385 | 25 Aug 0045 | 08/31/2022 | SINO-46L | Type | SHYB-270
3572
3573
3574 | FOT | RIG | 5.5 | 31 Aug 2330 - 0500 | 6813 | 901552 | STAND PIPE ISOLATION VALVE LEAK | RR | CSYS |  | 08/31/2022 | SND-1501 | 5.5 | HWYH-89
3575 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SND-1501 | Hrs | HWYH-89
3576 | FOT | HUD | 4.75 | 31 Aug 1300 - 1745 | 6559 | 901545 | REPAIR MPD FLOW METER | TF | MPD |  | 08/31/2022 | SND-1501 | 4.75 | HWYH-89
3577 | FOT | RIG | 5.5 | 31 Aug 2330 - 0500 | 6813 | 901552 | STAND PIPE ISOLATION VALVE LEAK | RR | CSYS |  | 08/31/2022 | SND-1501 | 5.5 | HWYH-89
3578 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SND-2001 | Hrs | HWYH-1229
3579 | FOT | RIG | 3.25 | 31 Aug 0700 - 1015 | 3852 | 901539 | COMMUNICATION LOST WITHIN TOP DRIVE SYSTEM. UNABLE TO ROTATE OR USE HYDRAULIC SYSTEM OF TOP DRIVE | RR | TDS |  | 08/31/2022 | SND-2001 | 3.25 | HWYH-1229
3580 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SND-2007 | Hrs | AWTD-104001
3581 | FOT | RIG | 2.5 | 31 Aug 0630 - 0900 | 17800 | 901474 | WASHPIPE LEAKING ON THE TDS. | RR | TDS |  | 08/31/2022 | SND-2007 | 2.5 | AWTD-104001
3582 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SND-2009 | Hrs | SAHB-101
3583 | FOT | RIG | 1.5 | 31 Aug 2330 - 0100 | 2520 | 901553 | TDS HAS HYDRAULIC OIL LEAK HUGE AMOUNT. HYDRAULIC HOSSES WAS LEAKING. | RR | TDS |  | 08/31/2022 | SND-2009 | 1.5 | SAHB-101
3584 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SP-125 | Hrs | ANDR-20
3585 | SMDF | EMC | 9 | 31 Aug 1430 - 2330 | 4598 | 901441 | ATTEMPT TO PUMP, STRING PLUGGED | MUD | SCS |  | 08/31/2022 | SP-125 | 9 | ANDR-20
3586 | 6769 |  | OTH | E | 4405 | NA | POOH W/ BHI PCL LOGGING RUN#2: (GR-RCX-IFX-WGI ) TO SES DEPTH @6114'.- MONITOR WELL THROUGH TRIP TANK& TRIP SHEET. | 6769 |  | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3587 | 6769 |  | OTH | E | 4405 | NA | SPACE OUT AND CLOSED BOPE, LINE UP TO CHOKE MANIFOLD. | 6769 |  | RIG | 08/31/2022 | SP-53L | LOG | HRDH-528
3588 | 6769 |  | CIRC | E | 4405 | MPMP | CIRCULATED OUT FORMATION FLUID AND CONTINUED CIRCULATION & CONDITION MUD THROUGH CHOKE MWT IN/OUT 70 PCF. | 6769 |  | RIG | 08/31/2022 | SP-53L | LOG | HRDH-528
3589 | 6769 |  | OTH | E | 4405 | NA | EXTENDED FLOW CHECKED, WELL STATIC. | 6769 |  | RIG | 08/31/2022 | SP-53L | LOG | HRDH-528
3590 | 6769 |  | OTH | E | 4405 | NA | RIH BHI PCL LOGGING RUN#2: (GR-RCX-IFX-WGI ) TO 6471'.- MONITOR HOLE ON TRIP TANK & TRIP SHEET, HOLE STATIC.- OPEN HOLE IN GOOD CONDITION. | 6769 |  | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3591 | 6769 | 6471 | LOG | E | 4405 | WLT | POSITION STRING AT STATION#7,SAMPLING POINT @ 6471', PERFORM STICKY TENDENCY TEST FOR 15MIN & 60 MIN - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6471 | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3592 | 6769 | 6471 | LOG | E | 4405 | WLT | STATION#7,SAMPLE POINT @ 6471' (2B10).- ACTIVATE DXL PROBE & PUMP OUT STATION #7 @ 6471'.- PUMP OUT 8 LITRES OF FIILTRATED FLUID, 22 LITRES OF FORMATION WATER, 122 LITERS OIL,TAKE 1 BOTTLE OF 500CC FLUID SAMPLE.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE-0.95 BBLS (WATER: 0.19 BBLS - OIL: 0.76 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6471 | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3593 | 6769 | 6460 | LOG | E | 4405 | WLT | POSITION STRING AT STATION#8, SIMPLE POINT @ 6460' & PERFORM STICKY TENDENCY TEST FOR 60 MIN - OK, NO STICKING TENDENCY NOR OVERPULL OBSERVED.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6460 | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3594 | 6769 | 6459 | LOG | E | 4405 | WLT | SCANNING AROUND THE STATION#8 (SAMPLE) @ 6459, 6460,6461 (2B09) FOR GOOD MOBILITY.- ACTIVATE DXL PROBE AT 6460'.- PUMP OUT 1.5 LITRES OF FIILTRATED FLUID, 15 LITRES OF FORMATION WATER, 16.5 LITERS OIL,AFTER 01 HOUR LOST SEAL ,CHANGE POSITION TO 6459'.- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 1.15 BBLS (WATER: 0.29 BBLS - OIL: 0.86 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6460 | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3595 | 6769 | 6459 | LOG | E | 4405 | WLT | CONTD STATION#8 ,SAMPLE POINT @ 6459' (2B09). - ACTIVATE DXL PROBE & PUMP OUT STATION #8 @ 6459'.- PUMP OUT 5.6 LITRES OF FIILTRATED FLUID, 39.2 LITRES OF FORMATION WATER, 67.2 LITERS OIL,TAKE 1 BOTTLE OF 500CC FLUID SAMPLE- TOTAL CUMMULATIVE VOLUME PUMPED TO WELL BORE - 1.85 BBLS (WATER: 0.57 BBLS - OIL: 1.28 BBLS).- DEACTIVATE DXL PROBE, MOVED FREELY, NO OVERPULL OBSERVED. | 6769 | 6459 | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3596 | 6769 | 6453 | LOG | E | 4405 | WLT | POSITION STRING AT STATION#9, PUMP OUT POINT @ 6452'.- MONITOR THE WELL THROUGH TRIP TANK, WELL STATIC. | 6769 | 6459 | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3597 | 6769 | 6453 | LOG | E | 4405 | WLT | STATION#9 , PUMP OUT POINT @ 6452' (2B08) ...........ON GOING- ACTIVATE DXL PROBE & PUMP OUT STATION #9 @ 6452'.- 18.25 HRS SINCE LAST CIRCULATION AT BTM. | 6769 | 6453 | BAW | 08/31/2022 | SP-53L | LOG | HRDH-528
3598 | 98.5 | OOS | Category | DOOS ID | LOG | Out of Scope Summary | RECORDING (ADEX-MREX-MLL) LOG & RUN #2:(GR-RCX-IFX-WGI) LOG AS PER PLAN | 24 | 4405 | 27 Aug 1015 | 08/31/2022 | SP-53L | Type | HRDH-528
3599
3600
3601 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SSA-303 | Hrs | HRDH-2411
3602 | FOT | BLH | 26.5 | 30 Aug 1630 - 0430 | 14125 | 901436 | MECHANICAL FAILURE OF SLIPS 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY, POOH & CHANGE OUT 4-1/2" X 7" BAKER CSF LNR HGR & ZXTREME PKR ASSY | TF | HGRL |  | 08/31/2022 | SSA-303 | 14 | HRDH-2411
3603 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SSA-5820 | Hrs | MSBA-1
3604 | FOT | RIG | 9 | 30 Aug 0030 - 0930 | 1414 | 901519 | RIG CRANE BROKE DOWN. UNABLE TO LAYDOWN BHA COMPONENTS. | RR | CRN |  | 08/31/2022 | SSA-5820 | 4.5 | MSBA-1
3605 | Cause | Resp Co | Cum. Hrs | From - To | Depth | LT ID | LT Summary | Type | Object | Parent LT ID | 08/31/2022 | SSA-5892 | Hrs | AWTD-141400
3606 | FOT | RIG | 144.5 | 25 Aug 1330 - 0500 | 14481 | 901352 | AFTER MAKING CONNECTION PIPE BECAME STUCK | DSF | STRG |  | 08/31/2022 | SSA-5892 | 23.5 | AWTD-141400